ANNEX II

- Projects for which additional status reports were requested

| Agency | Code | Project Title | Reasons |
| --- | --- | --- | --- |
| Canada | CUB/PHA/45/INV/32 | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Additional status report to ascertain the completion of the remaining training workshops and public awareness activities. |
| France | IRA/HAL/28/TAS/49 | Halon management programme | Additional status report addressing the possibility of transferring the project to another agency to expedite implementation. |
| IBRD | ANT/PHA/44/INV/10 | CFC phase-out management plan | Additional status report on the resolution of the advancement of funds by the Government and the reimbursement of such funds by the Bank. |
| IBRD | ARG/HAL/26/TAS/80 | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Additional status report to ascertain options for the halon bank and report on the expected 2010 completion. |
| IBRD | IND/PRO/59/INV/435 | Accelerated CFC production phase-out (first tranche) | Additional report on status of project signature by the Government to enable disbursement of approved funds by the Bank. |
| IBRD | TUN/PHA/49/INV/47 | National ODS phase-out plan (first tranche) | Additional report on the status of disbursement |
| Italy | SEN/PHA/57/INV/28 | Terminal phase-out management plan for CFCs (second tranche) | Additional report on the status of bidding. |
| UNDP | DOM/HAL/51/TAS/39 | National halon bank management plan update | Additional status report to indicate if all remaining equipment has been procured. |
| UNDP | GUA/PHA/56/INV/35 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional report on the status of bidding. |
| UNDP | LAC/REF/47/DEM/36 | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Additional report on the status of the chiller replacement. |
| UNDP | MDV/PHA/53/INV/15 | Terminal phase-out management plan (first tranche) | Additional report on the status of disbursement |
| UNDP | PER/PHA/55/INV/41 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional status report to monitor the transfer of NOU activities from the Ministry of Environment to the Ministry of Production in order to expedite Fund activities in the country. |
| UNDP | SUR/PHA/56/INV/16 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional report on the status of bidding. |
| UNEP | BDI/PHA/55/TAS/22 | Terminal phase-out management plan (first tranche) | Additional report on the status of disbursement |
| UNEP | BOT/SEV/53/INS/10 | Extension of institutional strengthening project (phase III) | Additional report on the submission of reports to enable release of funds for INS |
| UNEP | GUA/PHA/56/TAS/34 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional report on the status of bidding. |
| UNEP | KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional status report on the status of the verification report. |
| UNEP | MAR/SEV/53/INS/19 | Extension of the institutional strengthening project (phase III) | Additional report on the signature of the funding agreement for the project. |
| UNEP | MAU/PHA/53/TAS/18 | Terminal phase-out management plan for CFCs (first tranche) | Additional report on the resolution of administrative issues |
| UNEP | MAU/SEV/57/INS/23 | Renewal of the institutional strengthening project (phase V) | Additional report on the resolution of administrative issues |
| UNEP | MOZ/PHA/58/PRP/17 | Preparation of a HCFC phase-out management plan (additional funding) | Additional report on the status of completion of survey. |
| UNEP | PAK/ARS/56/TAS/72 | National strategy for transition to non-CFC MDIs | Additional status report due to delays from security concerns and recent flooding |
| UNEP | PER/PHA/55/TAS/42 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Additional report on the issues related to changes in the government |
| UNEP | SAU/SEV/53/INS/02 | Institutional strengthening (establishment of Ozone Unit) | Additional report on the submission of reports to enable release of funds for INS |
| UNEP | ZAM/SEV/57/INS/24 | Extension of the institutional strengthening project (phase IV) | Additional report on the submission of reports to enable release of funds for INS |
| UNIDO | AFR/REF/48/DEM/37 | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Additional report on the status of disbursement |
| UNIDO | ARG/PHA/47/INV/147 | National CFC phase-out plan: 2006 work programme | Additional status report to address the issue of equipment being held up by Customs. |
| UNIDO | ARG/PHA/50/INV/150 | National CFC phase-out plan: 2007 work programme | Additional status report to address the issue of equipment being held up by Customs. |
| UNIDO | ARG/PHA/53/INV/152 | National CFC phase-out plan: 2008 work programme | Additional status report to address the issue of equipment being held up by Customs. |
| UNIDO | BHE/PHA/44/INV/21 | National ODS phase-out plan: second tranche | Additional status report to address the issue of equipment being held up by Customs. |
| UNIDO | BHE/PHA/52/INV/22 | National ODS phase-out plan (third tranche) | Additional status report to address the issue of equipment being held up by Customs. |
| UNIDO | IND/PHA/45/INV/385 | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Additional report on the status of bidding. |
| UNIDO | IND/PHA/49/INV/402 | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Additional report on the status of bidding. |
| UNIDO | SYR/REF/47/DEM/93 | Demonstration project on the replacement of CFC centrifugal chillers | Additional report on the status of the chiller replacement. |

-------