## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | IRD | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Obligated (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Obligated (US$) | Remarks | Remarks (Latest information) | Year of Contribution | Latest Planned Date of Completion | Business Plan Allocation (Investment/Non-Investment)
COM | IBRD | Core unit budget (2012) |  | GLO | GLO | SEV | 65 | TAS | 312 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1724644 | 0 | 1720663 | 3981 | 0 | Activities included travel to MP-related meetings; support of core unit staff; holding a 7th new OORG meeting; hosting a regional ODS workshop for countries and WB staff as well as ozone day celebrations for the 25th MP anniversary, incl. a roundtable discussion and technology fair; and, coordination of WB-MP activities, completion of reports and responses and providing information needed for preparing ExCom reports. |  |  |  | Non-INV
COM | UNDP | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 278 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1751000 | 0 | 1751000 | 0 | 0 | Completed in 2007. |  | 2006 |  | Non-Investment
COM | UNDP | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 285 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1803530 | 0 | 1803530 | 0 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
COM | UNDP | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 295 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-01 |  | 2009-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1857636 | 0 | 1857636 | 0 | 0 | Completed in 2009. |  | 2008 |  | Non-Investment
COM | UNDP | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 301 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1913365 | 0 | 1913365 | 0 | 0 | Completed in 2010. |  | 2009 |  | Non-Investment
COM | UNDP | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 304 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-01 |  | 2011-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1970766 | 0 | 1970766 | 0 | 0 | Completed in 2011. |  | 2010 |  | Non-Investment
COM | UNDP | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-01 |  | 2012-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1984561 | 0 | 1984561 | 0 | 0 | Completed in 2012. | Completed in 2012. | 2011 |  | Non-investment
COM | UNEP | Compliance Assistance Programme: 2012 budget | Individual | GLO | GLO | SEV | 65 | TAS | 313 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 |  | 8987000 | 0 | 8987000 | 7972226 | 88.71% | 1014774 | 614386 | 614386 | 718960 | 0 | 637778.08 | 81181.92 | 49150.88 | Project completed. Balances to be returned |  |  |  | Non Investment
COM | UNEP | Compliance Assistance Programme: 2011 budget | Individual | GLO | GLO | SEV | 62 | TAS | 302 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2011-12-01 |  | 2011-12-01 |  | 9007000 | -267214 | 8739786 | 8405157 | 96.17% | 334629 | 15844 | 0 | 720560 | -21377.12 | 672412.56 | 26770.32 | 1267.52 | Project completed. Balances to be returned |  |  |  | Non Investment
COM | UNEP | Compliance Assistance Programme: 2010 budget | Individual | GLO | GLO | SEV | 59 | TAS | 299 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-01-01 | 2010-12-01 |  | 2010-12-01 |  | 8745000 | -67253 | 8677747 | 8575247 | 98.82% | 102500 | 0 | 0 | 699600 | -5380.24 | 686019.76 | 8200 | 0 | Project completed. Balances to be returned |  |  |  | Non Investment
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 09 | TAS | 29 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | 1996-12-01 | Non-INV
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 43 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 |  |  |  |  | Non-INV
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Core unit (2003) |  | GLO | GLO | SEV | 38 | TAS | 245 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. |  |  |  | Non-INV
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. |  |  |  | Non-INV
FIN | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2006) |  | GLO | GLO | SEV | 47 | TAS | 273 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2007) |  | GLO | GLO | SEV | 50 | TAS | 279 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-11-01 | 2007-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1580000 | -17251 | 1562749 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of one MP event and completion of reports and responses. Two pamphlets completed for the 20th MP Anniversary. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2008) |  | GLO | GLO | SEV | 53 | TAS | 286 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2008-11-01 | 2008-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1614900 | -360069 | 1254831 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the MP annual workshop for FIs and staff; reconvening the OORG (with 2 meetings held in 2008); an analytical piece on HCFC and related side-event; commissioning of a "foam decision tree," for HCFC alternatives; completion of reports and responses and providing required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2009) |  | GLO | GLO | SEV | 56 | TAS | 294 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1663347 | -204863 | 1458484 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the 13th annual workshop for FIs and staff as well as the new OORG meeting; strategic business development; completion of draft foam decision-tree report; and providing required monitoring, data collection and information for ExCom reporting. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2010) |  | GLO | GLO | SEV | 59 | TAS | 298 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1701466 | -390706 | 1310760 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 14th annual workshop for FIs and staff, the 5th new OORG meeting and two technology roundtable meetings; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV
FIN | IBRD | Core unit budget (2011) |  | GLO | GLO | SEV | 62 | TAS | 305 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-06-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1713000 | -390685 | 1322315 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 15th annual workshop for FIs and staff and the 6th new OORG meeting; and coordination of WB-MP activities, completion of reports and responses and providing info |  |  |  | Non-INV
FIN | UNDP | Core Unit Support (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 243 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Core Unit Support (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 249 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNDP | Core unit (2005) | Individual | GLO | GLO | SEV | 44 | TAS | 259 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNDP | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 271 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1700000 | 0 | 1700000 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNDP | Initial start-up costs | Individual | GLO | GLO | SEV | 04 | TAS | 256 | A | I | CFC | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1991-12-01 |  | 1992-12-01 | 2004-07-01 | 596500 | 0 | 596500 | 596500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1992. Financially completed in 2004. |  | 2004 |  | Investment
FIN | UNEP | Support to national activities for 1999 | Individual | GLO | GLO | SEV | 26 | TAS | 173 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory group meeting (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-02-01 |  | 1993-03-01 | 1993-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Informal Advisory Group meeting (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 58 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Informal advisory group meeting (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 83 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Ad hoc Group meetings | Individual | GLO | GLO | SEV | 19 | TAS | 103 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 27,500 plus $ 3,575 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Advisory and expert group meetings (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 144 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -10000 | 65000 | 65000 | 100% | 0 | 0 | 0 | 9750 | -1300 | 8450 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory group meeting (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-03-01 | 1992-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Meeting of the consultants (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 60 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1995-07-01 | 1995-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Ad hoc group meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 88 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1997-06-01 | 1999-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory and expert group meetings (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 169 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 75000 | -3500 | 71500 | 71500 | 100% | 0 | 0 | 0 | 9750 | -455 | 9295 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 146 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -2950 | 72050 | 72050 | 100% | 0 | 0 | 0 | 9750 | -383 | 9366.5 | 0.5 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 107 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory and expert group meetings | Individual | GLO | GLO | SEV | 21 | TAS | 122 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. ($15400 plus $2002 PSC returned ExCom 32) |  |  |  | Non Investment
FIN | UNEP | Travel (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 124 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 171 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 194 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory and expert group meetings (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 199 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 215 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Ad hoc Group meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Travel (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 89 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-09-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Advisory group meeting (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2002 budget | Individual | GLO | GLO | SEV | 35 | TAS | 237 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2002-12-01 |  | 2002-12-01 | 2005-01-01 | 5351450 | -1500591.3 | 3850858.7 | 3850859 | 100% | -0.3 | 0 | -0.3 | 428116 | -120046.9 | 308068.72 | 0.38 | 0 | Project financially completed. ($ 173,035 plus $ 13,843 PSC returned ExCom 43$ 293,348 plus $ 23,468 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2003 budget | Individual | GLO | GLO | SEV | 38 | TAS | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-07-01 | 5830885 | -466383 | 5364502 | 5364502 | 100% | 0 | 0 | 0 | 466471 | -37310.84 | 429160.344 | -0.184 | 0 | Project financially completed. ($ 141,359 plus $11,309 returned to ExCom 48$ 48,858 plus $ 3,909 returned to ExCom 49) |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2004 budget | Individual | GLO | GLO | SEV | 41 | TAS | 252 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 6757900 | -190217 | 6567683 | 6567683 | 100% | 0 | 0 | 0 | 540632 | -15218 | 525414.64 | -0.64 | 0 | Project financially completed. ($ 13,267 plus $ 1,725 PSC returned to ExCom 54) |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2005 budget | Individual | GLO | GLO | SEV | 44 | TAS | 260 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-12-01 | 7157544 | -304536 | 6853008 | 6853008 | 100% | 0 | 0 | 0 | 572604 | -24362.84 | 548241.0996 | 0.060423 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2006 budget | Individual | GLO | GLO | SEV | 47 | TAS | 270 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-04-01 | 7770000 | -364599 | 7405401 | 7405401 | 100% | 0 | 0 | 0 | 621600 | -29167.44 | 592432.08 | 0.48 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2007 budget | Individual | GLO | GLO | SEV | 50 | TAS | 276 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2007-12-01 |  | 2007-12-01 | 2009-12-01 | 8003000 | -409308 | 7593692 | 7593692 | 100% | 0 | 0 | 0 | 640240 | -32744.64 | 607495.36 | 0 | 0 | Project financially completed. ($ 13,787 plus $ 1,792 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2008 budget | Individual | GLO | GLO | SEV | 53 | TAS | 284 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 8243090 | 0 | 8243090 | 8243090 | 100% | 0 | 0 | 0 | 659447 | 0 | 659447 | 0 | 0 | Project financially completed. ($ 337 plus $ 44 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2009 budget | Individual | GLO | GLO | SEV | 56 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 8490000 | -3520.35 | 8486479.65 | 8486480 | 100% | -0.35 | 0 | -0.35 | 679200 | -281.6 | 678918.4 | 0 | 0 | Project completed in December 2010. |  |  |  | Non Investment
FIN | UNIDO | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 244 | A | I |  | 0 | 0 |  |  | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 250 | A | I |  | 0 | 0 |  |  | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget for 2005 | Individual | GLO | GLO | SEV | 44 | TAS | 258 | A | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 272 | A | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1700000 | 0 | 1700000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 277 | A | I |  | 0 | 0 |  |  | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1751000 | 0 | 1751000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 287 | A | I |  | 0 | 0 |  |  | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2008-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1803530 | 0 | 1803530 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 293 | A | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1857636 | 0 | 1857636 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 300 | A | I |  | 0 | 0 |  |  | 2009-11-01 |  | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1913365 | 0 | 1913365 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 303 | A | I |  | 0 | 0 |  |  | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2011-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1970766 | 0 | 1970766 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 311 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1984561 | 0 | 1984561 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | IBRD | Core unit budget (2013) |  | GLO | GLO | SEV | 68 | TAS | 318 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-31 | 2013-12-31 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1725000 | 0 | 0 | 1725000 | 1725000 | Activities to include travel to MP-related meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; hosting an OORG meeting; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. | WB team of 3 participated at the Jan. 30-Feb. 1 2013 interagency coordination meeting in Montreal. MP program management and implementation ongoing. |  |  | Non-INV
ONG | UNDP | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 316 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1998453 | 0 | 0 | 1998453 | 0 | Newly approved. |  | 2012 |  | Non-investment
ONG | UNEP | Compliance Assistance Programme: 2013 budget | Individual | GLO | GLO | SEV | 68 | TAS | 315 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 9158000 | 0 | 9158000 | 0 | 0% | 9158000 | 0 | 9158000 | 732640 | 0 | 0 | 732640 | 0 | Project approved in November 2012. |  |  |  | Non Investment
ONG | UNIDO | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 317 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2013-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1998453 | 0 | 0 | 1998453 | 0 | - |  |  |  | NON-INV
ONG | Italy | Phase-out of HCFC-22 in the room and unitary air-conditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 163 | A | I |  | 0 | 0 | 0 |  | 2010-07-01 | 2011-06-01 | 2013-07-01 | 2013-12-01 |  |  | 300000 | 0 | 300000 | 8340 | 2.78% | 291660 | 0 | 50000 | 39000 | 0 | 1084.2 | 37915.8 | 0 | Despite the supplier's delay (Agramkow) in the release of equipment, it was delivered to Buenos Aires. The equipment customs clearance was completed and it was transferred from the customs to the warehouses of the local forwarders for further in-land transportation to the end-users. Activities in 2013 are inspection of equipment upon its delivery to the project beneficiaries. Local procurement of small equipment items. Installation, testing, training and commissioning of equipment. Release of IOCs. |  | 2010 |  | Investment
ONG | UNIDO | Phase-out of HCFC-22 in the room and unitary airconditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 164 | A | I | HCFC | 53.5 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2013-07-31 | 2013-07-01 |  |  | 8435542 | 0 | 8435542 | 154665.09 | 1.833% | 8280876.91 | 2670353.66 | 3000000 | 632666 | 0 | 11600 | 621066 | 200277 | Despite the supplier's delay (Agramkow) in the release of equipment, it was delivered to Buenos Aires. The equipment customs clearance was completed and it was transferred from the customs to the warehouses of the local forwarders for further in-land transportation to the end-users. Although disburement levels were low at the end of 2012, 34% of the funds have been committed by the end of 2012 and the obligated funds will be released during 2013. Furthermore, the majority of the approved funds are related to the IOC, which will only be paid after successful completion of the conversion activities. | Inspection of equipment upon its delivery to the project beneficiaries. Local procurement of small equipment items. Installation, testing, training and commissioning of equipment. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out. |  |  | INV
ONG | UNIDO | Demonstration sub-project for conversion from HCFC-22 to propane at Midea Room Air-conditioning Manufacturing Company | Individual | ASP | CPR | REF | 61 | DEM | 503 | A | I | HCFC | 13.2 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 | 2013-12-01 |  |  | 4026507 | 0 | 4026507 | 2789661.36 | 69.28% | 1236845.64 | 1187568.55 | 25000 | 301988 | 0 | 209225 | 92763 | 89068 | During 2012 procurement of equipment was finished and main components of the R-290 line were installed by November 2012. | Installations for power supply, compressed air, oxygen gas supply are in the process. TUV certification is scheduled for June 2013. Detailed report on the ICC was submitted to the 69th Meeting of the Executive Committee. The slight delay is due to the fact that national acceptance cannot be organized before the second quarter of 2013 and that the national standard allowing the use of flammable alternatives comes in to effect only 1 May 2013. |  |  | INV
CLO | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | AFR | AFR | HAL | 37 | TAS | 31 | A | I | Halon | 61 | 44.2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  |  | 2008-11-01 | 300000 | -81518.81 | 218481.19 | 218481.19 | 100% | 0 | 0 | 0 | 39000 | -10597.4453 | 28402.5547 | 0 | 0 | Canceled in 2008. Funds will be returned to Excom in 2011. |  | 2002 |  | Non-Investment
CLO | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | AFR | LIB | HAL | 47 | TAS | 26 | A | I | HAL | 653.9 | 0 |  |  | 2005-11-01 | 2006-09-01 | 2008-12-01 |  |  | 2010-09-01 | 343500 | -335125 | 8375 | 8375.18 | 100% | -0.18 | 0 |  | 25763 | -25135 | 628 | 0 | 0 | CLO |  |  |  | INV
COM | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Halon banking | AFR | AFR | HAL | 35 | TAS | 29 | A | I | HAL | 27 | 27 | 0 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2010-12-01 |  | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 | 0 | 45500 | 0 | 45500 | 0 | 0 | Many of the countries phased out halons through controls and awareness. Most recently Botswana successfully phased out approx 8MT of halons.
COM | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | AFR | ALG | HAL | 35 | TAS | 51 | A | I | HAL | 392.3 | 392.3 | 0 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2010-07-01 |  | 259500 | 0 | 259500 | 259500 | 100% | 0 | 0 | 0 | 33735 | 0 | 33735 | 0 | 0 | Project is completed, PCR has been sent to Algeria 10 months ago, so far no response.
COM | UNEP | Sectoral phase-out programme: Establishing a halon management plan | Individual | LAC | HAI | HAL | 50 | TAS | 10 | A | I | Halon | 1.5 | 1.5 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2009-11-01 |  | 2008-11-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | PCR submitted |  |  |  | Non Investment
FIN | Australia | National halon management and banking programme | Individual | ASP | IND | HAL | 32 | TAS | 281 | A | I | HAL | 197.2 | 197.2 | 0 | 0 | 2000-12-01 | 2002-02-01 | 2004-01-01 |  | 2007-05-01 | 2008-05-01 | 245700 | -24100 | 221600 | 221600 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed. |  | 2000
FIN | Canada | National halon management and banking programme | Halon Banking | ASP | IND | HAL | 32 | TAS | 278 | A | I | HAL | 197.2 | 197.2 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2007-03-01 | 2007-03-01 | 245700 | 0 | 245700 | 245700 | 100% | 0 |  | 0 | 24570 | 0 | 24570 | 0 |  | Halon reclamation facility established in 2003. Canadian component annd Australian component of project completed |  | 2000 |  | Investment
FIN | Canada | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenada, Guyana, Jamaica, and Trinidad and Tobago) | Halon Banking | LAC | LAC | HAL | 26 | TAS | 28 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-10-01 | 2000-06-01 |  | 2005-12-01 | 2006-03-01 | 177410 | 0 | 177410 | 177410 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Establishment of halon clearing house in Trinidad and promotional brochure completed in 2005. All 6 countries finished their halon surveys. All project activities completed. Last payment to UNEP to reimburse University of West Indies for halon clearing |  | 1998 |  | Non-Inv.
FIN | France | Survey for halon banking management plan in West Asia (Bahrain, Lebanon, Qatar and Yemen) |  | ASP | ASP | HAL | 28 | TAS | 29 | N | D |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2000-02-01 |  | 2000-02-01 | 2002-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with Germany) |  | ASP | ASP | HAL | 30 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2004-04-01 | 2001-10-01 |  | 2004-12-01 | 2005-01-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 |  | 0 | 5875 | 0 | 5875 | 0 |  | Project completed. Final payment to GTZ in 2004.
FIN | France | Development of a halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 50 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2004-04-01 | 2000-05-01 |  | 2001-05-01 | 2004-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 |  |  | 536 | 0 | 536 | 0 |  | Project completed.
FIN | France | Establishing a halon bank and umbrella project for 63 manufacturers |  | ASP | SYR | HAL | 34 | TAS | 78 | A | I | HAL | 284.5 |  | 0 |  | 2001-07-01 | 2004-04-01 | 2004-08-01 |  | 2004-04-01 | 2005-01-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 |  | 0 | 8050 | 0 | 8050 | 0 |  | Project completed.
FIN | Germany | Survey for halon banking management plan in West Asia: Bahrain, Lebanon, Qatar and Yemen | Halon banking | ASP | ASP | HAL | 28 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-02-01 |  | 2000-03-01 | 2000-09-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project approved at 30th ExCom.
FIN | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | Halon banking | ASP | ASP | HAL | 30 | TAS | 36 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-02-01 | 2001-10-01 |  | 2005-04-01 | 2007-12-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 | 0 | 0 | 15275 | 0 | 15275 | 0 | 0 | Evaluation meeting Beirut 31.5.-4.6.2004; Comment on Terms, Comment on evaluation report; Calculation of operational costs of halon R&R equipment; contact addresses and quotations received for storage cylinders; discussion of alternative strategies. Proje
FIN | Germany | Sectoral phase-out programme: establishment of a halon bank | Individual | EUR | CRO | HAL | 43 | TAS | 24 | A | I | HAL | 30.1 | 30.1 | 0 |  | 2004-07-01 | 2005-01-01 | 2007-07-01 |  | 2008-10-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Having identified an enterprise, tender for Halonbank equipment has been finalized in december 2007, equipment will be delivered in May 2008. Project completed. PCR was submitted in December 2008.
FIN | Germany | Sectoral phase-out programme: establishing a halon bank | Individual | AFR | NIR | HAL | 37 | TAS | 103 | A | I | HAL | 285.3 | 285.3 | 0 |  | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2007-08-01 | 2008-10-01 | 499000 | 0 | 499000 | 499000 | 100% | 0 | 0 | 0 | 64870 | 0 | 64870 | 0 | 0 | Project is completed. PCR has been submitted to the MLF in October 2008.
FIN | Germany | Development of halon banking management plan | Halon banking | ASP | SYR | HAL | 29 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2000-05-01 |  | 2000-05-01 | 2002-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 | 0 | 0 | 1396 | 0 | 1396 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Individual | ASP | SYR | HAL | 34 | TAS | 77 | A | I | HAL | 284.5 | 284.5 | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2005-12-01 | 2007-12-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project is completed. PCR was submitted in 2007.
FIN | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | I | HAL | 200 | 200 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 |  | 2010-12-31 | 2012-07-01 | 290620 | -112794.54 | 177825.46 | 177825.46 | 100% | 0 | 0 | 0 | 37780.6 | -14663.3 | 23117.3 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | I | HAL | 972 | 972 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 |  | 2007-01-01 | 2007-06-01 | 486200 | -11076.12 | 475123.88 | 475123.88 | 100% | 0 | 0 |  | 63206 | -1439.9 | 61766.1 | 0 | 0 | Project is physically and financially completed |  |  |  | INV
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 |  | 2007-12-01 | 2008-01-01 | 382250 | 0 | 382250 | 382250 | 100% | 0 | 0 |  | 49693 | 0 | 49693 | 0 | 0 | The halon recycling center has been completed and is operational. Consistent with ExCom policies, no newly produced halons will be allowed to be imported. The ban will be enforced thru the existing import lincensing system. |  |  |  | Non-INV
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2006-12-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 220750 | -168490 | 52260 | 52260 | 100% | 0 | 0 |  | 28697.5 | -21904 | 6793.5 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | Non-INV
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | I | HAL | 118 | 118 | 0 | 0 | 2002-11-01 | 2008-04-01 | 2005-11-01 |  | 2007-12-01 | 2008-04-01 | 439250 | -6992 | 432258 | 432258 | 100% | 0 | 0 |  | 57102.5 | -908.96 | 56193.54 | 0 | 0 | Project completed. |  |  |  | INV
FIN | Sweden | Halon management programme, halon recovery, recycling and banking | Halon banking | ASP | THA | HAL | 29 | TAS | 120 | A | I |  | 135.9 |  | 0 |  | 1999-11-01 | 2004-11-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Implementation of the halon management project completed in Sep 2010. Sweden disbursed the full project amount to the WB already in year 2000. Overall halon project financially completed Nov. 11 upon return of the savings by the WB to the 65th ExCom. |  | 1999
FIN | UNDP | National halon bank management plan development | Individual | LAC | DOM | HAL | 38 | TAS | 32 | N | I | Halon | 3 | 3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2007-12-01 | 2011-11-01 | 40000 | -6494.68 | 33505.32 | 33505.32 | 100% | 0 | 0 | 0 | 5200 | -844.3084 | 4355.6916 | 0 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Halon management bank programme | Individual | AFR | EGY | HAL | 32 | TAS | 81 | N | I | Halon | 754 | 754 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 405000 | -3894 | 401106 | 401106.32 | 100% | -0.32 | 0 | 0 | 52650 | -506.22 | 52143.8216 | -0.0416 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Investment
FIN | UNDP | National halon management and banking programme | Individual | LAC | MEX | HAL | 35 | TAS | 104 | A | I | Halon | 230 | 230 | 0 | 0 | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2007-12-01 | 2011-07-01 | 500000 | -55841.6 | 444158.4 | 444158.4 | 100% | 0 | 0 | 0 | 65000 | -7259.408 | 57740.592 | 0 | 0 | Completed in 2007. |  | 2001 |  | Investment
FIN | UNEP | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | Individual | ASP | ASP | HAL | 30 | TRA | 38 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2002-10-01 | 2001-10-01 |  | 2004-12-01 | 2006-12-01 | 50000 | -2360 | 47640 | 47640 | 100% | 0 | 0 | 0 | 6500 | -307 | 6193.2 | -0.2 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNIDO | Phase-out of halon consumption | Individual | EUR | BHE | HAL | 42 | TAS | 18 | A | I | HAL | 4.1 | 4.1 |  |  | 2004-04-01 | 2004-06-01 | 2006-04-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -403 | 64197 | 64196.77 | 100% | 0.23 | 0 |  | 5814 | -36 | 5778 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Halon banking management programme | Individual | EUR | GEO | HAL | 47 | TAS | 21 | A | I | HAL | 42.5 | 42.5 |  |  | 2005-11-01 | 2006-08-01 | 2008-12-01 |  | 2008-01-01 | 2008-09-01 | 64930 | -603 | 64327 | 64327.46 | 100% | -0.46 | 0 |  | 5844 | -55 | 5789 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon phase-out programme | Individual | EUR | KYR | HAL | 48 | TAS | 12 | A | I | HAL | 2.4 | 2.4 |  |  | 2006-04-01 | 2006-12-01 | 2009-04-01 |  | 2008-12-01 | 2012-05-01 | 50000 | -3838 | 46162 | 46161.89 | 100% | 0.11 | 0 |  | 4500 | -345 | 4155 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | ASP | PAK | HAL | 41 | TAS | 55 | A | I | HAL | 24.2 | 24.2 |  |  | 2003-12-01 | 2004-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 209400 | -786 | 208614 | 208614.4 | 100% | -0.4 | 0 |  | 18846 | -71 | 18775 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon management programme | Individual | EUR | ROM | HAL | 50 | TAS | 37 | A | I | HAL | 3.5 | 3.5 |  |  | 2006-11-01 | 2007-11-01 | 2008-11-01 |  | 2008-06-01 | 2009-06-01 | 32500 | -447 | 32053 | 32053.47 | 100% | -0.47 | 0 |  | 2925 | -40 | 2885 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | I | HAL | 370 | 370 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | -4216 | 245484 | 245483.51 | 100% | 0.49 | 0 |  | 32461 | -599 | 31862 | 0 | 0 | FIN |  |  |  | INV
ONG | UNDP | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Individual | LAC | CHI | HAL | 51 | TAS | 164 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2010-01-01 | 2009-09-01 | 2014-01-01 |  |  | 60000 | 0 | 60000 | 7085.35 | 11.81% | 52914.65 | 0 | 21165.86 | 4500 | 0 | 531.4013 | 3968.5988 | 0 | TORs for hiring of international expert was published several times. Potential candidates provided technical offers and were interviewed. Difficult to find a person with the required skills. In the end of 2012, a potential expert was identified and a contract is being negotiated with her. | Local Expert being hired. The Local expert will guide the creation of banks and identify other potential activities to close the project | 2007 |  | Non-Investment
ONG | UNDP | National halon bank management plan update | Individual | LAC | DOM | HAL | 51 | TAS | 39 | N | I | Halons | 1.2 | 1.2 | 0 | 0 | 2007-03-01 |  | 2011-01-01 | 2013-07-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 6000 | 1800 | 0 | 0 | 1800 | 0 | Expert was officially hired by the end of 2012. | Expert is in the process of conducting the pending work in the DR. The project is expected to be completed in 2013. | 2007 |  | Non-Investment
ONG | UNEP | Study on challenges associated with halon banking in developing countries | Individual | GLO | GLO | HAL | 52 | TAS | 281 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 | 2013-07-01 |  |  | 40000 | 0 | 40000 | 36000 | 90% | 4000 | 0 | 4000 | 5200 | 0 | 4680 | 520 | 0 | Draft document produced by consultant, however during the pre-publishing review phase, some of the key data were found to be out of date. In consultation with HTOC Co-Chairs, UNEP is currently in discussions with consultant about the means and timeline to update the data to enable production of a useful document. Additional time will be required to finalize the document. | In consultation with HTOC Co-Chairs, UNEP is currently in discussions with consultant about the means and timeline to update the data to enable production of a useful document. Additional time will be required to finalize the document. |  |  | Non Investment
ONG | UNIDO | Halon phase-out project (Transfer from France) | Individual | ASP | IRA | HAL | 63 | TAS | 198 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-11-01 | 2012-04-01 | 2013-12-01 |  |  | 397500 | 0 | 397500 | 5321.27 | 1.339% | 392178.73 | 282828.88 | 200000 | 29813 | 0 | 399 | 29414 | 21212 | Procurement of equipment completed and clearance to the security council requested, as soon as the import permission will be cleared the equipment will be sent to Iran. Although disbursement level was low at the end of 2012, 73% of the funds have already been committed in the same period. | Plans for 2013: Installation and commissioning of equipment, initiate the procedure of recovering and recycling of Halon. Final clearance from the Security Council, Export Authorities, Bank were received. UNIDO has transferred the advance payment to the supplier in April 2013. Delivery is planned for August 2013. The project is expected to be completed in 2013. Reason for the delay: The clearance of the equipment by the security council as well as other administrative issues such as export clearance from the national authorities of the supplier (Italy), bank clearance for funds transfer (all projects in Iran face bank restrictions) took longer than expected. |  |  | NON-INV
TRF | France | Halon management programme | Halon Banking | ASP | IRA | HAL | 28 | TAS | 49 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2003-08-01 |  |  | 2011-08-01 | 511175 | -397500 | 113675 | 113675 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The project transfer to UNIDO was acted by the 63rd ExCom meeting.
TRF | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 |  |  | 2007-03-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project transferred to UNDP in 2007 at the 51st ExCom. |  |  |  | Non-INV
COM | IBRD | Sector plan for CFC production phase-out: 2008 annual programme | Multiyear | ASP | CPR | PRO | 54 | INV | 459 | N | I | CFC | 0 | 0 | 6850 | 6850 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-03-01 |  | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 | 0 | 562500 | 0 | 562500 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2009 annual programme | Multiyear | ASP | CPR | PRO | 57 | INV | 487 | N | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-03-01 |  | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 | 0 | 562500 | 0 | 562500 | 0 | 0 | CFC Production Sector Plan fully disbursed, however FECO continues to implement TA activities especially related to the CFC and halon export/import control system. In addition, new TA activities have been added to the program to ensure long term sustainab |  |  |  | INV
COM | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 1170000 | 0 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | I | CFC | 0 | 0 | 4320 | 4320 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 |  | 6500000 | 6500000 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 585000 | 585000 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | I | CFC | 0 | 0 | 3568 | 3568 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 910000 | 0 | 910000 | 0 | 0 | Annual program completed. CFC production verified and confirmed to be within target. |  |  |  | INV
COM | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 | 2005-11-01 | 2004-12-01 |  | 2005-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2005 annual programme | Multiyear | ASP | CPR | PRO | 45 | INV | 428 | N | I | CFC | 0 | 0 | 6550 | 6550 | 2005-04-01 | 2005-12-01 | 2005-12-01 |  | 2006-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Fully completed and disbursed. 2005 CFC production was verified and within the control target. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2006 annual programme | Multiyear | ASP | CPR | PRO | 48 | INV | 443 | N | I | CFC | 0 | 0 | 5250 | 5250 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 |  | 10000000 | 10000000 | 20000000 | 20000000 | 100% | 0 | 0 | 0 | 900000 | 900000 | 1800000 | 0 | 0 | 1999 annual plan successfully completed. |  |  |  | INV
COM | IBRD | Sector plan for CFC production phase-out: 2007 annual programme | Multiyear | ASP | CPR | PRO | 51 | INV | 449 | N | I | CFC | 0 | 0 | 6100 | 6100 | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-03-01 |  | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 | 0 | 1800000 | 0 | 1800000 | 0 | 0 | Completed. CFC phaseout targets in 2007 met. |  |  |  | INV
COM | IBRD | Accelerated CFC production phase-out (first tranche) | Multiyear | ASP | IND | PRO | 59 | INV | 435 | N | I | CFC | 0 | 0 | 690 | 690 | 2009-11-01 | 2012-01-01 | 2010-11-30 |  | 2011-12-01 |  | 2113000 | 0 | 2113000 | 2113000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Funding disbursed to the country in Jan 2012. Next and final tranche for funding was deferred at the 66th ExCom Meeting. | This first tranche is fully disbursed. |  |  | INV
COM | USA | CFCs, CTC and halon accelerated phase-out plan (first tranche) | Multi-Year | ASP | CPR | PRO | 44 | INV | 425 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2006-10-01 | 2005-12-01 |  | 2006-10-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Completed. Funds disbursed in Oct. 2006.
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2007 annual programme | Multiyear | LAC | ARG | PRO | 53 | INV | 154 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2008-03-01 | 2010-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2005 annual programme | Multiyear | LAC | ARG | PRO | 45 | INV | 143 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2005-04-01 | 2007-09-01 | 2006-04-01 |  | 2006-04-01 | 2010-11-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV
FIN | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 20000 | 0 | 20000 | 0 | 0 | An accounting and technical monitoring was carried out to verify that no CFCs were produced during 2009, and it was verified that the plant didn't operate during that period. The entire production sector project is 100% completed within expected deadlines, including destruction of equipment. Funds were fully disbursed according to the disbursement schedule and prior annual audits ?technical and financial- according to UNEP?s regulations. Production cessation initially expected to be done by 2010 was done by 2007, when the company ceased definitely producing CFCs. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2008 annual programme | Multiyear | LAC | ARG | PRO | 54 | INV | 156 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-04-01 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2009 annual programme | Multiyear | LAC | ARG | PRO | 57 | INV | 160 | N | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-31 | 2010-03-31 |  | 2009-12-31 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 47000 | 0 | 47000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2006 annual programme | Multiyear | LAC | ARG | PRO | 50 | INV | 151 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-10-01 |  | 2007-10-01 | 2010-11-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 100000 | 0 | 100000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV
FIN | IBRD | Accelerated phase-out plan for CFC production | Multiyear | LAC | ARG | PRO | 53 | INV | 155 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2008-03-01 | 2010-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2004-12-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2010-11-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 200000 | 0 | 200000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 45 | INV | 390 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-04-01 | 2011-11-01 | 5850000 | 0 | 5850000 | 5850000 | 100% | 0 | 0 |  | 438750 | 0 | 438750 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 480000 | 0 | 480000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2007 annual implementation plan | Multiyear | ASP | IND | PRO | 51 | INV | 407 | N | I | CFC | 0 | 0 | 3953 | 3953 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2008-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2008 annual implementation plan | Multiyear | ASP | IND | PRO | 54 | INV | 417 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2009 annual implementation plan | Multiyear | ASP | IND | PRO | 59 | INV | 434 | N | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2011-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 | 2011-11-01 | 12000000 | 0 | 12000000 | 12000000 | 100% | 0 | 0 |  | 960000 | 0 | 960000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | National CFC production closure plan (fifth tranche) | Multiyear | LAC | VEN | PRO | 54 | INV | 111 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2008-12-01 | 2009-11-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78700 | 0 | 78700 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV
FIN | IBRD | National CFC production closure plan (third tranche) | Multiyear | LAC | VEN | PRO | 48 | INV | 107 | N | I | CFC | 0 | 0 | 2931 | 2931 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 |  | 131200 | 0 | 131200 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV
FIN | IBRD | National CFC production closure plan (fourth tranche) | Multiyear | LAC | VEN | PRO | 52 | INV | 110 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2009-01-01 | 2009-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV
FIN | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | I | CFC | 0 | 0 | 1469 | 1469 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2009-11-01 | 3300000 | 0 | 3300000 | 3300000 | 100% | 0 | 0 |  | 247500 | 0 | 247500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV
FIN | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-04-01 | 2009-11-01 | 8100000 | 0 | 8100000 | 8100000 | 100% | 0 | 0 |  | 607500 | 0 | 607500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: third tranche | Multi-Year | LAC | MEX | PRO | 45 | INV | 126 | A | I | CFC | 0 | 0 | 5616 | 5616 | 2005-04-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-05-01 | 4000000 | -563 | 3999437 | 3999437.41 | 100% | -0.41 | 0 |  | 300000 | -42 | 299958 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | Multi-Year | LAC | MEX | PRO | 40 | INV | 115 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-11-01 | 2004-03-01 |  | 2005-06-01 | 2006-12-01 | 5300000 | 0 | 5300000 | 5300000 | 100% | 0 | 0 |  | 397500 | 0 | 397500 | 0 | 0 | FIN
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (second tranche) | Multi-Year | LAC | MEX | PRO | 42 | INV | 119 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-05-01 | 2005-04-01 |  | 2005-06-01 | 2006-12-01 | 10700000 | 0 | 10700000 | 10700000.01 | 100% | -0.01 | 0 |  | 802500 | 0 | 802500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: fourth tranche | Multi-Year | LAC | MEX | PRO | 47 | INV | 128 | A | I | CFC | 0 | 0 | 6739 | 6739 | 2005-11-01 | 2006-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-12-01 | 11850000 | -139 | 11849861 | 11849861.21 | 100% | -0.21 | 0 |  | 888750 | -10 | 888740 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
ONG | IBRD | Accelerated CFC production phase-out (second tranche) | Multiyear | ASP | IND | PRO | 67 | INV | 446 | N | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-31 | 2013-07-31 |  |  | 739900 | 0 | 739900 | 0 | 0% | 739900 | 739900 | 739900 | 213968 | 0 | 0 | 213968 | 213968 | This is the first part of the second and final tranche approved in Jul 2012. Disbursement to the beneficiaries is pending approval of the second part of the second tranche. | US $317,000 of the second tranche released by the ExCom at its 69th Meeting in Apr. 2013 . WB supervision mission scheduled for late April through early May 2013. |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: balance from the 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 398 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-05-01 | 2007-04-01 |  | 2008-07-01 | 2011-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 11250 | 0 | 11250 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | I | CFC | 0 | 0 | 1832 | 1832 | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2005-01-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
FIN | IBRD | CFC production sector gradual phase-out: 2006 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 397 | N | I | CFC | 0 | 0 | 3389 | 3389 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV
CLO | Canada | Project preparation for a terminal phase-out management plan |  | AFR | BEN | PHA | 49 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2006-07-01 |  | 2007-07-01 |  |  | 2009-07-01 | 12000 | -12000 | 0 | 0 |  | 0 |  | 0 | 1560 | -1560 | 0 | 0 |  | TPMP has been prepared by UNEP and approved at 55th meeting, without the need for the funds approved for Canada. Therefore, Canada will ask for cancellation of this project at the 58th meeting and return related funds. |  | 2006 |  | Non-Inv.
CLO | UNDP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2009-12-01 | 12000 | -12000 | 0 | 0 |  | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2009. |  | 2007 |  | Investment
CLO | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | BAR | PHA | 54 | PRP | 14 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-01 |  |  | 2010-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1125 | -1125 | 0 | 0 | 0 | TPMP will not be prepared for Barbados and funds should be returned to the MLF. Project therefore canceled. Funds to be returned in 2011. |  | 2008 |  | Investment
CLO | UNEP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2008-11-01 | 18000 | -18000 | 0 | 0 |  | 0 | 0 | 0 | 2340 | -2340 | 0 | 0 | 0 | Project Closed |  |  |  | Non Investment
COM | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (second tranche) | Multi-Year | LAC | STL | PHA | 56 | INV | 15 | A | I | CFC | 1.2 | 1.2 | 0 |  | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2012-03-01 |  | 49000 | 0 | 49000 | 47960.84 | 97.88% | 1039.16 |  | 0 | 6370 | 0 | 6235 | 135 |  | Project completed in March 2012. 109 technicians and 85 customs officers trained, equipment purchased and distributed to workshops, and clearing house established for unwanted ODS. A balance of $1,039.16 in project costs and $135 in support cost is remaining and will be returned to the Fund at 70th meeting. |  | 2008 |  | Investment
COM | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | INV | 19 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2010-07-01 | 2011-05-01 | 2011-07-01 |  | 2011-12-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Project completed.
COM | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | INV | 17 | A | I | CFC | 0.7 | 0.7 | 0 |  | 2008-07-01 | 2010-06-01 | 2009-12-01 |  | 2011-09-01 |  | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Project completed.
COM | France | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 171 | A | I | CFC | 424.5 | 94.3 | 0 |  | 2005-04-01 | 2007-04-01 | 2007-04-01 |  | 2010-06-01 | 2012-04-01 | 500000 | 0 | 500000 | 203479.82 | 40.7% | 296520.18 |  | 0 | 55000 | 0 | 22382.7802 | 32617.2198 |  | The French contribution is implemented by GIZ-Proklima. Monitoring report was compiled in 2010. Project completed.
COM | France | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ETH | PHA | 51 | PRP | 17 | A | I | CFC | 0 |  | 0 |  | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-07-01 |  | 30000 | 0 | 30000 | 17600 | 58.67% | 12400 |  | 0 | 3900 | 0 | 2288 | 1612 |  | The French contribution is implemented by GTZ-Proklima. The survey for the preparation of the TPMP has been completed but the continued lack of regulations prevents Ethiopia from submitting the TPMP. Funds will be returned to MLF.
COM | Germany | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 265 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 |  | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 63000 | 0 | 63000 | 0 | 0 | By end of 2008, more than 300 technicians had been trained under this tranche. One train the trainer course with 35 participants was conducted. A total of 12 mobile training units have been built and are used in the field. Continue to further distribute educational materials and public relation materials and to monitor and to follow up the success of training activities of technicians.
COM | Germany | National CFC phase-out plan: 2009 annual implementation programme | Multi-Year | ASP | IRA | PHA | 57 | INV | 191 | A | I | CFC | 132.7 | 132.7 | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2011-04-01 |  | 512208 | 0 | 512208 | 512208 | 100% | 0 | 0 |  | 56343 | 0 | 56343 | 0 |  | project finally completed, financial completion under way
COM | Germany | Terminal CFC phase-out management plan (third tranche) | Multi-Year | AFR | LES | PHA | 50 | INV | 10 | A | I | CFC | 1.4 | 1.4 | 0 |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2009-11-01 |  | 17300 | 0 | 17300 | 17300 | 100% | 0 | 0 | 0 | 2249 | 0 | 2249 | 0 | 0 | Project has been completed, Lesotho has achieved complete phase out as per the Agreement with the Excom on the TPMP.
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, fourth tranche) | Multi-Year | AFR | ZIM | PHA | 60 | INV | 42 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-04-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5108 | 0 | 5108 | 0 | 0 | Zimbabwe conducted 2 technican trainings targetting 27 participants as well as 1 customs training for 21 officers on the use of idenitifers capable of monitoring blends.
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, second tranche) | Multi-Year | AFR | ZIM | PHA | 54 | INV | 39 | A | I | CFC | 20 | 20 | 0 |  | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2009-03-01 |  | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 20 additional conversions under the incentive scheme were completed and 3 customs trainings were conducted.
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, third tranche) | Multi-Year | AFR | ZIM | PHA | 57 | INV | 40 | A | I | CFC | 20 |  | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-06-01 |  | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 4 customs officers were trained. 61 technicans were trained in state of the art refrigeration servicing. 160 commercial refrigeration units were converted under the incentive scheme. 785 kgs of CFC refrigerant were recovered.
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 |  | 540000 | 0 | 540000 | 540000 | 100% | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | Implementation of project activities under this tranche completed since 2004. |  |  |  | INV
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 |  | 5194380 | 0 | 5194380 | 5194380 | 100% | 0 | 0 | 0 | 459494 | 0 | 459494 | 0 | 0 | Implementation of activities under this tranche completed. |  |  |  | INV
COM | IBRD | Total phase-out of CFCs plan: Implementation status of 2007AP and verification report for CFC consumption for 2007 | Multiyear | EUR | TUR | PHA | 53 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2012-06-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 30000 | 0 | 19500 | 10500 | 0 | PCR and implementation report completed. Turkey has complied with total CFC phaseout since 2006. Balance of funds for 2007 verification audit to be returned. | PCR submitted to the MLF SMEO in Word in Feb. 2013. Data will be entered in the electronic MYA PCR database upon clearance from the NOU. |  |  | INV
COM | Italy | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | INV | 28 | A | I | CFC | 23.4 | 23.4 | 0 |  | 2009-04-01 | 2008-06-01 | 2010-03-01 |  | 2012-12-01 |  | 135000 | 0 | 135000 | 84225 | 62.39% | 50775 | 1551 | 45000 | 17550 | 0 | 10949.25 | 6600.75 | 201.63 | A Purchase Order in the amount of US$ 44,512 was made in 2012 to buy Portable Refrigerant Identifiers, which is not reflected in records and will be corrected. Project completed in Dec 2012. |  | 2009 |  | Investment
COM | Italy | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | INV | 24 | A | I |  | 0 | 0 | 0 |  | 2007-07-01 | 2008-06-01 | 2008-07-01 |  | 2012-12-01 |  | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 | Project completed in Dec 2012. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | INV | 22 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2012-12-01 |  | 40000 | 0 | 40000 | 33153.87 | 82.88% | 6846.13 | 0 | 5476.904 | 3000 | 0 | 2486.5403 | 513.4597 | 0 | Completed in 2012. Some final payments pending. Final draft report on CFC re-use feasibility study was presented in August 2012. During presentation, NOU requested revisons and additional details to be included in the study document, specifically covering (1) situation regarding supply and availability of refillable cylinders; (2) a flowchart, highlighting the certification, licensing and enforcement; (3) minimum requirements to approve a reclaim facility. Revisions introduced. Two technical visits fielded with international expert during 2012. | Completed in 2012. Some final payments pending. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | BAH | PHA | 50 | INV | 16 | N | I | CFC | 38.4 | 38.4 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-12-01 |  | 2008-12-01 |  | 272500 | 0 | 272500 | 272500 | 100% | 0 | 0 | 0 | 20437 | 0 | 20437 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
COM | UNDP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | BRA | PHA | 50 | INV | 278 | N | I | CFC | 1050 | 1050 | 0 | 0 | 2006-11-01 | 2011-04-01 | 2009-12-01 |  | 2012-09-01 |  | 1190000 | 0 | 1190000 | 1190000 | 100% | 0 | 0 | 0 | 92300 | 0 | 92300 | 0 | 0 | Completed in 2012. Recycling equipments were installed and recipient recyclers trained.Tech. assistance for supermarkets energy savings and reduction of CFC emissions were concluded.Chillers equipment are under installation and will be ready for energy readings during the first quarter of 2013. An independent audit was held in December 2012 that confirmed that no CFCs were imported in 2011. | Completed in 2012. Chillers have been installed. PCR under preparation and will be submitted in July 2013. | 2006 |  | Investment
COM | UNDP | National CFC phase-out plan: fourth tranche | Multi-Year | LAC | BRA | PHA | 47 | INV | 274 | N | I | CFC | 1020 | 1020 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2006-12-01 |  | 2011-10-01 |  | 2856400 | 0 | 2856400 | 2856400 | 100% | 0 | 0 | 0 | 242276 | 0 | 242276 | 0 | 0 | Completed in 2011. Ongoing activities continued: 1,550 from 3,000 CFC recovery sets for refrigerations distributed; All 5 reclaim centers and planned storage centres for contaminated or impure CFCs established; 62 from 120 recycling centers established; Inventory of CFC-based chillers in the city of Brasilia (DF) finished; technical standards for the use of refrigerants completed and one technical standard on CFC emissions under discussion. | Completed in 2011. Ongoing activities continued: 120 recovery sets for refrigerationsdistributed; 58 recycling centers beneficiaries selected established; Procurement process of 3 CFC-based chillers initiated; one meeting held for the discussion of the CFC emissions standard. | 2005 |  | Investment
COM | UNDP | National CFC phase-out plan: third tranche | Multi-Year | LAC | BRA | PHA | 45 | INV | 270 | N | I | CFC | 743 | 743 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2006-04-01 |  | 2009-12-01 |  | 3970000 | 0 | 3970000 | 3970000 | 100% | 0 | 0 | 0 | 342500 | 0 | 342500 | 0 | 0 | Completed in 2009. |  | 2005 |  | Investment
COM | UNDP | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 264 | N | I | CFC | 737 | 737 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2008-12-01 |  | 5720000 | 0 | 5720000 | 5720000 | 100% | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | Completed in 2008. |  | 2003 |  | Investment
COM | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | INV | 262 | N | I | CFC | 1251 | 1251 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2003-12-01 |  | 2005-12-01 |  | 7860000 | 0 | 7860000 | 7860000 | 100% | 0 | 0 | 0 | 687700 | 0 | 687700 | 0 | 0 | Completed in 2005. |  | 2002 |  | Investment
COM | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-08-01 |  | 72000 | 0 | 72000 | 71980.37 | 99.97% | 19.63 | 0 | 15.704 | 6480 | 0 | 6478.2333 | 1.7667 | 0 | Completed. Tools and equipment delivered to technicians that participated in training courses. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | BZE | PHA | 53 | INV | 20 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-09-01 | 2009-11-01 |  | 2009-11-01 |  | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 | 0 | 10980 | 0 | 10980 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | INV | 20 | N | I | CFC | 5.2 | 5.2 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2010-12-01 |  | 82000 | 0 | 82000 | 71018.11 | 86.61% | 10981.89 | 0 | 8785.512 | 7380 | 0 | 6391.6299 | 988.3701 | 0 | Completed. All activities took place. Some final payments pending in 2011. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CHD | PHA | 53 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 |  | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 | 0 | 8280 | 0 | 8280 | 0 | 0 | Completed. See CHD-20 below. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | INV | 17 | N | I | CFC | 0.4 | 0.4 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 |  | 32000 | -719.78 | 31280.22 | 31280.22 | 100% | 0 | 0 | 0 | 2880 | -64.78 | 2815.22 | 0 | 0 | Completed. All activities took place. Some final payments pending in 2011. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | COI | PHA | 52 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-07-01 |  | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 3870 | 0 | 3870 | 0 | 0 | Completed. See COI-17. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (third tranche) | Multi-Year | LAC | COS | PHA | 58 | INV | 42 | N | I | CFC | 37.5 | 37.5 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-12-01 |  | 165000 | 0 | 165000 | 145500.17 | 88.18% | 19499.83 | 0 | 15599.864 | 12375 | 0 | 10912.5127 | 1462.4872 | 0 | Completed in 2011. Training of refrigeration technicians continued. Pilot project for reconversion in Milk sector was completed with success. TA assistance to Holcim was provded in order to be able to destroy ODS waste in CR. Final invoices pending. | Technical Assistance provided to Holcim, Ministry of Health, and Ministry of Environment for potential destruction of ODS waste. Final invoices pending. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | COS | PHA | 52 | INV | 37 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2008-12-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Completed in 2008. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-year | LAC | COS | PHA | 55 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-08-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Completed. Pilot project for reconversion in Milk sector was completed with success. Training of refrigeration technicians continued. |  | 2008 |  | Investment
COM | UNDP | National ODS phase-out plan for CFCs: 2005 annual implementation plan - UNDP Portion | Multi-Year | LAC | CUB | PHA | 45 | INV | 33 | N | I | CFC | 30 | 30 | 0 | 0 | 2005-04-01 | 2007-07-01 | 2006-04-01 |  | 2007-12-01 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 18750 | 0 | 18750 | 0 | 0 | Completed in 2007. |  | 2005 |  | Investment
COM | UNDP | National ODS phase-out plan for CFCs: balance of the 2004 and 2005 annual programmes (France and Germany) | Multi-Year | LAC | CUB | PHA | 48 | INV | 37 | N | I | CFC | 79.7 | 79.7 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-07-01 |  | 512228 | 0 | 512228 | 512228 | 100% | 0 | 0 | 0 | 38417 | 0 | 38417 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | National ODS phase-out plan for CFCs: 2006 and 2007 annual implementation plans | Multi-Year | LAC | CUB | PHA | 53 | INV | 39 | N | I | CFC | 166.2 | 166.2 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 |  | 641000 | 0 | 641000 | 641000 | 100% | 0 | 0 | 0 | 48075 | 0 | 48075 | 0 | 0 | Procurement process to get materials for the Commercial retrofit programme is under way and payments to be finalized in 2011. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | DJI | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 |  | 147000 | 0 | 147000 | 144849.12 | 98.54% | 2150.88 | 0 | 1720.704 | 13230 | 0 | 13036.4208 | 193.5792 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2009-12-01 |  | 2009-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fifth tranche) | Multi-Year | LAC | DOM | PHA | 58 | INV | 45 | N | I | CFC | 70.9 | 70.9 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2012-05-01 |  | 200000 | 0 | 200000 | 141708.03 | 70.85% | 58291.97 | 50134 | 46633.576 | 15000 | 0 | 10628.1022 | 4371.8978 | 3760.05 | Completed in 2012. Some final payments pending. Provision of tools and equipment to technicians that participated in training courses to promote use of HCs. Additional kits for retrofits were delivered in 2012. The project completed succesfully its activities. | Completed in 2012. Some final payments pending. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fourth tranche) | Multi-Year | LAC | DOM | PHA | 54 | INV | 41 | N | I | CFC | 28 | 28 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 |  | 211600 | 0 | 211600 | 211600 | 100% | 0 | 0 | 0 | 15870 | 0 | 15870 | 0 | 0 | Completed in 2009. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (second tranche) | Multi-Year | LAC | DOM | PHA | 48 | INV | 38 | N | I | CFC | 171 | 171 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-07-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (third tranche) | Multi-Year | LAC | DOM | PHA | 51 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-01-01 | 2009-03-01 |  | 2008-12-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Completed in 2008. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: 2005 annual implementation programme | Multi-Year | LAC | DOM | PHA | 45 | INV | 36 | N | I | CFC | 41.3 | 41.3 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-12-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Completed in 2007. |  | 2005 |  | Investment
COM | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | INV | 30 | N | I | CFC | 5 | 5 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-07-01 |  | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 | 0 | 5391 | 0 | 5391 | 0 | 0 | Completed. Purchase of tools, equipment and gas was completed and arrived in country. MDI component completed. International Consultant mission took place. New series of End User applications processed. Last quaterly advance to NOU was paid but will be implemented during first half of 2011. Large balance due to late payment of equipment vendor, which had to be postponed till 2011. |  | 2009 |  | Investment
COM | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | AFR | DRC | PHA | 49 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 |  | 193750 | 0 | 193750 | 193750 | 100% | 0 | 0 | 0 | 14531 | 0 | 14531 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | ELS | PHA | 53 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-11-01 |  | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | INV | 26 | N | I | CFC | 46 | 46 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-06-01 |  | 285000 | 0 | 285000 | 284995.44 | 100% | 4.56 | 0 | 3.648 | 21375 | 0 | 21374.658 | 0.342 | 0 | Completed in 2011. Final activities under the TPMP completed. Follow up actions with hospitals and training institutions,. Training programme in the process of being updated to fully reflect requirements from HCFC phase out. Final invoices pending. | Completed in 2011. Final activities under the TPMP completed. Follow up actions with hospitals and training institutions,. Training programme in the process of being updated to fully reflect requirements from HCFC phase out. Final invoices pending. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | INV | 22 | N | I | CFC | 3.6 | 3.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 |  | 30500 | -3000.54 | 27499.46 | 27499.46 | 100% | 0 | 0 | 0 | 2745 | -270.05 | 2474.95 | 0 | 0 | Completed. The delivery in the 2nd tranche reached 84%, and the project is considered as operationally completed as of end of December 2010. Final pending payments will be realized during 2011 as a part of closing the project financially. End-user component of TPMP progressed in implemented as planned. The companies which wished to retrofit their CFC equipment were identified. Three companies which approached NOU and submitted applications to receive grants: Marine sea food, Cattini Enterprise ltd and Tropical Ice plant. NOU held two sensitization workshops for End Users on the 7th of October and 23rd of December 2010 respectively. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | GAM | PHA | 53 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2008-12-01 |  | 99500 | 0 | 99500 | 99500 | 100% | 0 | 0 | 0 | 8955 | 0 | 8955 | 0 | 0 | Completed in 2008. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | INV | 16 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-11-01 |  | 2011-11-01 |  | 30000 | 0 | 30000 | 29336.87 | 97.79% | 663.13 | 0 | 530.504 | 2700 | 0 | 2640.3183 | 59.6817 | 0 | Completed in 2011. Equipment to support CFC phase-out procured and delivered to beneficiaries. | Completed in 2011. Equipment to support CFC phase-out procured and delivered to beneficiaries. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | GRN | PHA | 49 | INV | 10 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-07-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | LAC | GRN | PHA | 55 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2009-12-01 |  | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2009. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | GUY | PHA | 53 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-11-01 |  | 124000 | 0 | 124000 | 124000 | 100% | 0 | 0 | 0 | 11160 | 0 | 11160 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | INV | 20 | N | I | CFC | 10 | 10 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 |  | 85000 | -1774.06 | 83225.94 | 83225.94 | 100% | 0 | 0 | 0 | 6375 | -133.05 | 6241.95 | 0 | 0 | Completed. All activities relating to TPMP were completed and remaining components for closure of the project undertaken. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-Year | ASP | KAM | PHA | 53 | INV | 16 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-12-01 |  | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | INV | 22 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-12-01 |  | 55000 | -4966.47 | 50033.53 | 50033.53 | 100% | 0 | 0 | 0 | 4950 | -446.98 | 4503.02 | 0 | 0 | Completed. Consultant mission took place Equipment arrived early 2010 and sub-contracted centers operational. Some last invoices expected in 2011. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MAU | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | INV | 28 | N | I | CFC | 16.2 | 16.2 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2010-12-01 |  | 150000 | 0 | 150000 | 147197.98 | 98.13% | 2802.02 | 0 | 2241.616 | 11250 | 0 | 11039.8485 | 210.1515 | 0 | Completed. Consultant missions took place. Additional equipment arrived. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-12-01 |  | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 12900 | 0 | 12900 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLW | PHA | 53 | INV | 25 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 |  | 125500 | 0 | 125500 | 125500 | 100% | 0 | 0 | 0 | 11295 | 0 | 11295 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | MOL | PHA | 52 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-07-01 |  | 2008-11-01 |  | 152500 | 0 | 152500 | 152500 | 100% | 0 | 0 | 0 | 11438 | 0 | 11438 | 0 | 0 | Completed in 2008. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-11-01 |  | 320000 | -42.35 | 319957.65 | 319957.65 | 100% | 0 | 0 | 0 | 24000 | -3.18 | 23996.82 | 0 | 0 | Completed. The procurement of kits of good practices, and other equipment were completed in 2010 and delivered to beneficiaries. The incentive programme for key sectors has been very succesfull in lowering the demand for CFCs in Nicaragua. |  | 2008 |  | Investment
COM | UNDP | National CFC phase-out plan (seventh and eighth tranche) | Multi-Year | AFR | NIR | PHA | 59 | INV | 125 | N | I | CFC | 264.6 | 264.6 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2012-12-01 |  | 454200 | 0 | 454200 | 435941.01 | 95.98% | 18258.99 | 0 | 14607.192 | 36518 | 0 | 35049.9643 | 1468.0357 | 0 | Completed in 2012. Some pending payments remaining. Final progress report and CFC verification reports submitted and approved at the 68th ExCom in December. Last activities related to incentives for end users were completed, and a summary publication highlighting successes was finalised (to be released). | Completed in 2012. | 2009 |  | Investment
COM | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | AFR | NIR | PHA | 57 | INV | 122 | N | I | CFC | 200 | 200 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2011-11-01 |  | 385000 | 0 | 385000 | 385000 | 100% | 0 | 0 | 0 | 32770 | 0 | 32770 | 0 | 0 | Completed in 2011. See NIR-125. | Completed in 2011. | 2009 |  | Investment
COM | UNDP | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | NIR | PHA | 54 | INV | 117 | N | I | CFC | 1179.8 | 1179.8 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-09-01 |  | 1286303 | 0 | 1286303 | 1286303 | 100% | 0 | 0 | 0 | 111407 | 0 | 111407 | 0 | 0 | Completed in 2011. See NIR-125. | Completed in 2011. | 2008 |  | Investment
COM | UNDP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | NIR | PHA | 44 | INV | 112 | N | I | CFC | 850.7 | 850.7 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-09-01 |  | 2077141 | 0 | 2077141 | 2077141 | 100% | 0 | 0 | 0 | 183863 | 0 | 183863 | 0 | 0 | Completed in 2008. |  | 2004 |  | Investment
COM | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | NIR | PHA | 41 | INV | 108 | N | I | CFC | 830 | 830 | 0 | 0 | 2003-12-01 | 2007-03-01 | 2004-12-01 |  | 2007-12-01 |  | 2976827 | 0 | 2976827 | 2976827 | 100% | 0 | 0 | 0 | 264834 | 0 | 264834 | 0 | 0 | Completed in 2007. |  | 2003 |  | Investment
COM | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | Multi-Year | AFR | NIR | PHA | 38 | INV | 106 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2006-12-01 |  | 5013929 | 0 | 5013929 | 5013929 | 100% | 0 | 0 | 0 | 449318 | 0 | 449318 | 0 | 0 | Completed in 2006. |  | 2002 | 2005-12-01 | Investment
COM | UNDP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-Year | LAC | PAN | PHA | 50 | INV | 26 | N | I | CFC | 66 | 66 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2010-08-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Completed. The focus in 2010 has been on the training in good refrigeration practices where a large number of technicians have received training. The reconversion of the fishning fleet was completed in 2010. |  | 2006 |  | Investment
COM | UNDP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-Year | LAC | PAN | PHA | 47 | INV | 24 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 |  | 238000 | 0 | 238000 | 238000 | 100% | 0 | 0 | 0 | 17850 | 0 | 17850 | 0 | 0 | Completed in 2009. |  | 2005 |  | Investment
COM | UNDP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | INV | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-04-01 | 2005-12-01 |  | 2008-12-01 |  | 250152 | 0 | 250152 | 250152 | 100% | 0 | 0 | 0 | 18762 | 0 | 18762 | 0 | 0 | Completed in 2008. |  | 2004 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-year | LAC | PAR | PHA | 60 | INV | 26 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 2010-04-01 | 2011-12-01 | 2011-04-01 |  | 2012-12-01 |  | 21000 | 0 | 21000 | 15690.34 | 74.72% | 5309.66 | 0 | 4247.728 | 1575 | 0 | 1176.7755 | 398.2245 | 0 | Completed in 2012. Technical training of technicians took place in 2012. No more activities pending under the TPMP but some final payments pending | Completed in 2012. No activities in 2013. | 2010 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | INV | 17 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2010-12-01 |  | 2009-12-01 |  | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | INV | 23 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2011-07-01 |  | 2011-07-01 |  | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 14250 | 0 | 14250 | 0 | 0 | Completed in 2011. All remaining activities under the 2nd and 3rd tranches successfully completed. This includes additional training to technicians and provision of tools and equipment to technicians. | Completed in 2011. All remaining activities under the 2nd and 3rd tranches successfully completed. This includes additional training to technicians and provision of tools and equipment to technicians. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | INV | 17 | N | I | CFC | 4.6 | 4.6 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2012-12-01 |  | 43500 | 0 | 43500 | 32085.83 | 73.76% | 11414.17 | 0 | 9131.336 | 3915 | 0 | 2887.7247 | 1027.2753 | 0 | Completed in 2012. One (1) end-user company that submitted application for equipment retrofit did not fulfil technical requirements and the application was rejected. No more activities were planned in 2012 except monitoring. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | RWA | PHA | 53 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-11-01 | 2009-11-01 |  | 2010-12-01 |  | 124500 | 0 | 124500 | 124500 | 100% | 0 | 0 | 0 | 11205 | 0 | 11205 | 0 | 0 | Completed. R&R tools were previously delivered to Rwanda. Tools were distributed to three (3) regional R&R centers. Four (4) end-user companies received grants for equipment retrofit. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 |  | 45000 | 0 | 45000 | 43950 | 97.67% | 1050 | 0 | 840 | 4050 | 0 | 3955.5 | 94.5 | 0 | Completed. R&R equipment procurement and training program completed by Q2 / Q3 of the year 2010. |  | 2007 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | AFR | SIL | PHA | 61 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2011-12-01 |  | 20000 | 0 | 20000 | 14715.19 | 73.58% | 5284.81 | 0 | 4227.848 | 1800 | 0 | 1324.3671 | 475.6329 | 0 | Completed in 2011. A five day (26-30 September 2011) refresher trainings of trainers were conducted for staff of the centres of excellence to teach old and new students as the academic year begun in October 2011. There are regular awareness raising discussions on community radios on the activities of the ozone unit and how local communities can be a part to sustain the ban on CFCs. | Completed in 2011. Additional equipment has been distributed to the centres of excellence; the Kenema Polytechnic and the Magburuka Polytechnic (FEB 2012). Refresher trainings were also conducted for the Refrigerator Engineer Association on good refrigeration practices and retrofitting. Regular monitoring of the centres of excellence by the national ozone unit are ongoing, with the refrigerator engineers association taking the lead in partnership for technician training purposes. | 2010 |  | Investment
COM | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2009-11-01 | 2009-12-01 |  | 2009-12-01 |  | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | INV | 15 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2008-11-01 | 2010-11-01 | 2009-11-01 |  | 2012-05-01 |  | 27000 | 0 | 27000 | 26826.54 | 99.36% | 173.46 | 0 | 138.768 | 2430 | 0 | 2414.3886 | 15.6114 | 0 | Completed in 2012. Pending invoices being paid. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
COM | UNDP | Terminal phase out management plan for CFCs (first phase) | Multi-Year | LAC | STV | PHA | 47 | INV | 11 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2005-11-01 | 2007-08-01 | 2006-12-01 |  | 2008-12-01 |  | 101000 | 0 | 101000 | 101000 | 100% | 0 | 0 | 0 | 9090 | 0 | 9090 | 0 | 0 | Completed in 2008. |  | 2005 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | INV | 16 | N | I | CFC | 6.2 | 6.2 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-06-01 |  | 2011-12-01 |  | 125000 | 0 | 125000 | 124997.63 | 100% | 2.37 | 0 | 1.896 | 11250 | 0 | 11249.7867 | 0.2133 | 0 | Completed in 2011. Tools and equipment delivered to final beneficiaries in Suriname. One mission by international expert took place in 2011 to provide additional training to technicians. | Remaining invoices have been paid. | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | INV | 16 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2011-11-01 |  | 40000 | 0 | 40000 | 32298.84 | 80.75% | 7701.16 | 0 | 6160.928 | 3600 | 0 | 2906.8956 | 693.1044 | 0 | Completed in 2011. Three existing training schools reinforced. Support to end-users and MAC sectors provided and equipment has arrived. Final training meeting for retrofitting sites held at the end of 2011. | Completed in 2011. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-12-01 |  | 81500 | 0 | 81500 | 81500 | 100% | 0 | 0 | 0 | 7335 | 0 | 7335 | 0 | 0 | Completed. Consultant's mission took place. Equipment arrived. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | INV | 20 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2010-12-01 |  | 62000 | 0 | 62000 | 61133.96 | 98.6% | 866.04 | 0 | 692.832 | 5580 | 0 | 5502.0564 | 77.9436 | 0 | Completed. Consultant mission carried out. Equipment arrived. Final invoices expected in 2011. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-03-01 |  | 2010-12-01 |  | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 8550 | 0 | 8550 | 0 | 0 | Completed. See TOG-20 for continuation. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | TRI | PHA | 40 | INV | 16 | N | I | CFC | 42.9 | 42.9 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2006-03-01 |  | 2006-12-01 |  | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 16500 | 0 | 16500 | 0 | 0 | Completed in 2006. |  | 2003 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | LAC | TRI | PHA | 49 | INV | 20 | N | I | CFC | 34.1 | 34.1 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2008-12-01 |  | 2008-12-01 |  | 240000 | 0 | 240000 | 231586.74 | 96.49% | 8413.26 | 0 | 6730.608 | 18000 | 0 | 17369.0055 | 630.9945 | 0 | Completed in 2008. |  | 2006 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | INV | 50 | N | I | CFC | 69.7 | 69.7 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 |  | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Completed. Most of the tools incentives included in the TPMP were already distributed to the technicians in previous years. Technicians manifested the need of training in specific areas such as the handling of HCFC alternatives (HCs and ammoniac), the NOU is organizing a training on this area with the participation of international experts . The NOU completed 12 visits to monitor importers, 12 visits to technicians to monitor TPMP activities and 12 visits to areas out of Montevideo to identify additional technicians. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2011-12-01 |  | 109000 | 0 | 109000 | 78510.24 | 72.03% | 30489.76 | 0 | 24391.808 | 9810 | 0 | 7065.9216 | 2744.0784 | 0 | Completed in 2011. The project was operationally completed in Aug 2011. The project's achievements and operation of R/R center and R/R tools application was the only activity in 2011. | Completed in 2011. | 2007 |  | Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-12-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project completed in December 2012 |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-03-01 |  | 77000 | 0 | 77000 | 75355 | 97.86% | 1645 | 0 | 1645 | 10010 | 0 | 9796.15 | 213.85 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-year | AFR | DJI | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-03-01 |  | 2012-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | The final payment was made in July 2012 |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 |  | 2012-06-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | National customs training manual drafted. Project technically completed. Technical and financial reports submitted by the government. | PCR to be drafted in the second quarter of the year. |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 |  | 50000 | 0 | 50000 | 35000 | 70% | 15000 | 0 | 15000 | 6500 | 0 | 4550 | 1950 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GBS | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 |  | 62500 | 0 | 62500 | 61500 | 98.4% | 1000 | 1000 | 1000 | 8125 | 0 | 7995 | 130 | 130 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2008-11-01 |  | 2012-12-01 |  | 33000 | 0 | 33000 | 23016 | 69.75% | 9984 | 0 | 9984 | 4290 | 0 | 2992.08 | 1297.92 | 0 | Project completed in December 2012. |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2011-12-01 |  | 58000 | 0 | 58000 | 57000 | 98.28% | 1000 | 0 | 1000 | 7540 | 0 | 7410 | 130 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-11-01 |  | 2011-12-01 |  | 72000 | 0 | 72000 | 53434 | 74.21% | 18566 | 0 | 18566 | 9360 | 0 | 6946.42 | 2413.58 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-02-01 |  | 109000 | 0 | 109000 | 104225 | 95.62% | 4775 | 0 | 4775 | 14170 | 0 | 13549.25 | 620.75 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 |  | 81500 | 0 | 81500 | 76500 | 93.87% | 5000 | 0 | 5000 | 10595 | 0 | 9945 | 650 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | NIC | PHA | 60 | TAS | 25 | A | I | CFC-12 | 2 | 2 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2012-04-01 |  | 70000 | 0 | 70000 | 61466 | 87.81% | 8534 | 1765 | 8534 | 9100 | 0 | 7990.58 | 1109.42 | 229.45 | Project completed. Activities continued as planned. Awareness and information activities on ODS alternative technologies and illegal trade prevention addressed maintaining zero level of CFC consumption as well as preventing the continuous increase in the use of HCFC-22 in the country. Nicaragua hosted, in collaboration with CAP team, the Central America and Dominican Republic Training Workshop to coordinate ODS control measures and exchange of experiences among National Ozone Units and Customs Authorities held in December 2012. 26 national participants from Customs and Enforcement officers attended the workshop. |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2010-11-01 |  | 2012-06-01 |  | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Project completed. Activities continued as planned. Awareness and information activities on ODS alternative technologies and illegal trade prevention were addressed, maintaining zero level of CFC consumption, as well as, preventing the continuous increase in the use of HCFC-22 in the country. Training of technicians focused on low-GWP alternative technology and energy efficiency. |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-10-01 | 2011-04-01 |  | 2012-01-01 |  | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ZAM | PHA | 57 | TAS | 23 | A | I | CFC-12 | 4.1 | 4.1 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2012-03-01 |  | 42000 | 0 | 42000 | 37000 | 88.1% | 5000 | 0 | 5000 | 5460 | 0 | 4810 | 650 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | Individual | AFR | ANG | PHA | 51 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2012-03-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed | Project completed |  |  | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | URT | PHA | 50 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-11-01 |  | 17000 | 0 | 17000 | 3000 | 17.65% | 14000 | 14000 | 14000 | 2210 | 0 | 390 | 1820 | 1820 | Project completed |  |  |  | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | ZAM | PHA | 50 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 22000 | 73.33% | 8000 | 0 | 8000 | 3900 | 0 | 2860 | 1040 | 0 | Project completed |  |  |  | Non Investment
COM | UNIDO | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 51 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 |  | 134576 | 0 | 134576 | 114031.86 | 84.73% | 20544.14 | 20190.05 | 20000 | 10093 | 0 | 8552 | 1541 | 1514 | Project completed in Mar 2012. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 49 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 |  | 134575 | 0 | 134575 | 134480.04 | 99.93% | 94.96 | 0 | 50 | 10093 | 0 | 10086 | 7 | 0 | Project completed in Mar 2012. |  |  |  | INV
COM | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | INV | 20 | A | I | CFC | 1.4 | 1.4 |  |  | 2008-07-01 | 2009-06-01 | 2009-12-31 |  | 2012-02-01 |  | 140000 | 0 | 140000 | 139937.85 | 99.96% | 62.15 | 0 | 50 | 12600 | 0 | 12594 | 6 | 0 | Project completed in Feb 2012. |  |  |  | INV
COM | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | ASP | KUW | PHA | 52 | INV | 11 | A | I | CFC | 15 | 15 |  |  | 2007-07-01 | 2007-12-01 | 2008-11-01 |  | 2010-11-01 |  | 220000 | 0 | 220000 | 217492.94 | 98.86% | 2507.06 | 0 | 2500 | 19800 | 0 | 19574 | 226 | 0 | Project completed. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | MEX | PHA | 45 | INV | 123 | A | I | CFC | 100 | 100 |  |  | 2005-04-01 | 2006-05-01 | 2007-04-01 |  | 2011-12-01 |  | 4478000 | -200000 | 4278000 | 4196528.3 | 98.1% | 81471.7 | 3462.77 | 80000 | 335850 | -15000 | 314740 | 6110 | 260 | Project completed. |  |  |  | INV
COM | UNIDO | Terminal phase-out plan for CFCs (first tranche) | Multi-Year | EUR | MOG | PHA | 53 | INV | 03 | A | I | CFC | 3 | 3 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 |  | 175000 | 0 | 175000 | 170282.41 | 97.3% | 4717.59 | 4300 | 4000 | 13125 | 0 | 12771 | 354 | 323 | Project completed. |  |  |  | INV
COM | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | OMA | PHA | 57 | INV | 19 | A | I | CFC | 25 | 25 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2011-12-01 |  | 164200 | 0 | 164200 | 126903.03 | 77.29% | 37296.97 | 0 | 37000 | 12315 | 0 | 9518 | 2797 | 0 | Project completed. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan for Syria (first tranche) | Multi-Year | ASP | SYR | PHA | 49 | INV | 96 | A | I | CFC | 100 | 100 |  |  | 2006-07-01 | 2006-10-01 | 2008-07-01 |  | 2010-12-01 |  | 430000 | 0 | 430000 | 426680.87 | 99.23% | 3319.13 | 2829.84 | 3000 | 32250 | 0 | 32001 | 249 | 212 | Project completed. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan: 2009 work programme | Multi-Year | LAC | VEN | PHA | 57 | INV | 114 | A | I | CFC | 985 | 985 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2012-06-01 |  | 513465 | 0 | 513465 | 466381.23 | 90.83% | 47083.77 | 47121.1 | 47000 | 38510 | 0 | 34979 | 3531 | 3534.0825 | Project completed in Dec 2012. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | I | CFC | 2 | 2 |  |  | 2004-07-01 | 2004-08-01 | 2005-03-01 |  | 2009-12-01 |  | 474700 | 0 | 474700 | 439725.51 | 92.63% | 34974.49 | 0 | 30000 | 35603 | 0 | 32979 | 2624 | 0 | Project completed. |  |  | 2006-07-01 | INV
FIN | Canada | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | INV | 24 | A | I | CFC | 5.4 | 5.4 | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-12-01 | 2011-07-01 | 86500 | -3000 | 83500 | 83500 | 100% | 0 |  | 0 | 11245 | -495 | 10750 | 0 |  | Procurement of retrofit equipment and tools (2nd phase) completed in July 2009 ($57,481). $13,000 provided to Burkina Faso for awareness-raising activities and local purchase of tools. Additional technician training courses organized in 2009-beginning of 2010 by UNEP. Mission by EC in January 2010 revealed that tools had not yet been distributed to technicians, but this was subsequently reported by NOU to have been done. Project completed. $3,000 returned to the MLF with $495 in support costs, and noted at 64th ExCom meeting. |  | 2008 |  | Investment
FIN | Canada | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | BKF | PHA | 50 | INV | 22 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-01-01 | 2008-03-01 |  | 2008-09-01 | 2008-10-01 | 98500 | 0 | 98500 | 98500 | 100% | 0 |  | 0 | 12805 | 0 | 12805 | 0 |  |  |  | 2006 |  | Investment
FIN | Canada | Servicing sector terminal CFC phase-out plan (first tranche) | Multi-Year | LAC | CHI | PHA | 55 | INV | 166 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-02-01 | 2011-07-01 |  | 2012-03-01 | 2012-03-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 |  | 0 | 22880 | 0 | 22880 | 0 |  | Project was completed in March 2012. 107 conversions were undertaken and verified, 480 technicians received training in good practice, and a good practice standard was developed and officially published in June 2011 by the National Norm Institute. |  | 2008 |  | Investment
FIN | Canada | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 32 | A | I | CFC | 30 | 30 | 0 |  | 2005-04-01 | 2008-01-01 | 2007-04-01 |  | 2011-06-01 | 2012-05-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  | 0 | 8060 | 0 | 8060 | 0 |  | Project completed in June 2011 but Canada was awaiting final financial report from Cuba. Funds spent principally on R&R training and provision of tools and materiasl for technicians. Final financial report received in May 2012. |  | 2005 |  | Investment
FIN | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (first tranche) | Multi-Year | LAC | STL | PHA | 52 | INV | 12 | A | I | CFC | 0 |  | 0 |  | 2007-07-01 | 2007-09-01 | 2009-07-01 |  | 2010-03-01 | 2011-07-01 | 156000 | -504 | 155496 | 155496 | 100% | 0 |  | 0 | 20280 | -10617 | 9663 | 0 |  | R&R equipment and tools delivered in March 2008 and distributed. Technicians and customs officers training were undertaken through 2008. Legal framework for R&AC Association and revised MP regulations was completed. A code of good practices in Refrigeration has been finalised. In 2009, additional training for technicians and customs officers took place. Project was completed in March 2010 with $504 unspent was returned to the Fund, along with $10,617 in unspent support costs, as noted at ExCom 64 in July 2011. |  | 2007 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-Year | LAC | URU | PHA | 60 | TAS | 53 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Activities were rapidly completed as they consisted mainly of 4 training workshops on good practices and strengthening of the certification system. Project completed by end of 2011 and remaining balance paid by Canada in April 2012 after final progress and expenditure reports were submitted. |  | 2010 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | TAS | 51 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-03-01 | 2011-03-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  | 0 | 5460 | 0 | 5460 | 0 |  | Activities initiated in september 2009. 340 technicians trained. organization of 3 meetings with enforcement officials. Efforts to implement the technician certification scheme continued throughout the year. The online licensing system was implemented and one training workshop was held with stakeholders. Final training held in first quarter of 2011 and project completed by end of March 2011. $2,100 in support costs were erroneously reported as unspent in previous report and were in fact spent. |  | 2008 |  | Investment
FIN | Canada | Project preparation for the terminal phase-out management plan |  | AFR | BKF | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2006-10-01 | 2006-10-01 | 10000 | -650 | 9350 | 9350 | 100% | 0 |  | 0 | 1300 | -100 | 1200 | 0 |  | TPMP prepared and submitted with UNEP at ExCom 50. Project completed. Remaining balance of $650 and associated support costs ($100) were returned to Fund. |  | 2005 |  | Non-Inv.
FIN | Canada | Project preparation for the terminal phase-out management plan |  | LAC | BOL | PHA | 47 | PRP | 27 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-02-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | TPMP prepared, submitted to ExCom 51 and approved. Project and last payment completed in February 2007. |  | 2005 |  | Non-Inv.
FIN | Canada | Project preparation for a national phase-out plan |  | LAC | CHI | PHA | 50 | PRP | 162 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2008-04-01 | 2008-04-01 | 30000 | -1 | 29999 | 29999 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Chile servicing sector terminal phase-out plan preparation began in Oct 2007. Final proposal was completed by April 2008 and TPMP approved in July 2008. |  | 2006 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan for CFCs: training and recovery and recycling | One-off Phase-out | LAC | JAM | PHA | 37 | TAS | 16 | A | I | CFC | 57.5 | 57.5 | 0 |  | 2002-07-01 | 2002-09-01 | 2006-01-01 |  | 2006-03-01 | 2006-03-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 |  | 0 | 31200 | 0 | 31200 | 0 |  | All activities completed by end of 2005. Final monitoring reports received in March 2006. Jamaica provided comprehensive report on R&R activities. |  | 2002 |  | Non-Inv.
FIN | France | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 163 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2011-05-01 | 1006620 | 0 | 1006620 | 1006620 | 100% | 0 |  | 0 | 110728 | 0 | 110728 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal CFCs phase-out management plan (third tranche) | Multi-Year | AFR | KEN | PHA | 57 | INV | 46 | A | I | CFC | 65.8 | 65.2 | 0 |  | 2009-04-01 | 2009-06-01 | 2010-03-01 | 2012-03-01 | 2012-03-01 | 2012-12-01 | 179086 | -138033 | 41053 | 41053 | 100% | 0 |  | 0 | 23281 | -17944.1513 | 5336.8487 | 0 |  | The French contribution is implemented by GTZ-Proklima. The project is completed.
FIN | France | Terminal CFCs phase-out management plan (first tranche) | Multi-Year | AFR | KEN | PHA | 44 | INV | 37 | A | I | CFC | 53 | 53 | 0 |  | 2004-12-01 | 2007-08-01 | 2005-12-01 |  | 2008-05-01 | 2008-07-01 | 215914 | 0 | 215914 | 215914 | 100% | 0 |  | 0 | 28069 | 0 | 28069 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed. |  |  | 2007-06-01
FIN | France | Terminal CFCs phase-out management plan (second tranche) | Multi-Year | AFR | KEN | PHA | 54 | INV | 44 | A | I | CFC | 20 |  | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-03-01 | 2012-09-28 | 297000 | 0 | 297000 | 297000 | 100% | 0 |  | 0 | 38610 | 0 | 38610 | 0 |  | The French contribution is implemented by GTZ-Proklima. 2 trainers from local colleges were trained in a regional hydrocarbon training course in Namibia. Commercial refrigeration installations are being converted under the verification scheme. The project is completed.
FIN | France | Project preparation for a terminal phase-out management plan for CFCs |  | ASP | LAO | PHA | 49 | PRP | 16 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2007-05-01 | 2007-07-01 |  | 2008-02-01 | 2009-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Project completed. TPMP approved by 54th ExCom.
FIN | France | Project preparation for a terminal phase-out management plan |  | AFR | SEY | PHA | 49 | PRP | 11 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2006-09-01 | 2007-07-01 |  | 2007-03-01 | 2007-03-01 | 20000 | -5483 | 14517 | 14517 | 100% | 0 |  | 0 | 2600 | -712.79 | 1887.21 | 0 |  | The French contribution is implemented by GTZ. Project completed
FIN | Germany | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BOT | PHA | 60 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-11-01 | 2012-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | 10 additional refrigerant identifiers were purchased following the request from the customs dept. This was followed by 3 customs training at remote border posts of Botswana.
FIN | Germany | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BOT | PHA | 57 | INV | 12 | A | I | CFC | 1 |  | 0 |  | 2009-04-01 | 2009-06-01 | 2011-03-01 |  | 2010-12-01 | 2012-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | 7 customs training were realised, purchase of training equipment, major public awareness on phase out of CFCs was conducted
FIN | Germany | National CFC phase out plan: training of customs officers | Multi-Year | LAC | BRA | PHA | 37 | TRA | 260 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2007-12-01 | 2008-12-01 | 141200 | 0 | 141200 | 141200 | 100% | 0 | 0 | 0 | 18356 | 0 | 18356 | 0 | 0 | Training activities for 55 customs officers/instructors as well 9 staff members from the national environmental protection agency are completed. Refrigerant identifiers were purchased in 2007 and distributed to Customs officers. The project is completed.
FIN | Germany | National CFC phase-out plan: training of refrigeration mechanics in domestic and commercial refrigeration service sub-sectors (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | TRA | 261 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2006-12-01 | 2007-12-01 | 435937 | 1062863 | 1498800 | 1498800 | 100% | 0 | 0 | 0 | 56672 | 95658 | 152330 | 0 | 0 | By end of 2006 7000 technicians had been trained under this tranche. A total of 27 mobile training units have been built and are used in the field. Production of 8,000 free books with photo-training on good practices for mechanics in the commercial and do
FIN | Germany | National CFC phase-out plan: third and fourth tranches | Multi-Year | LAC | BRA | PHA | 48 | INV | 277 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2011-04-01 | 2011-12-01 | 1543600 | 0 | 1543600 | 1543600 | 100% | 0 | 0 | 0 | 138924 | 0 | 138924 | 0 | 0 | Project completed
FIN | Germany | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 169 | A | I | CFC | 0 | 0 | 0 |  | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2007-12-01 | 2007-12-01 | 479044 | 0 | 479044 | 479044 | 100% | 0 | 0 | 0 | 52695 | 0 | 52695 | 0 | 0 | Funds have been disbursed for the conversion of additional manufacturers in the foam sector. Certificates of destruction were handed in by Dec-2008.
FIN | Germany | National CFC phase-out plan: 2008 annual implementation programme | Multi-Year | ASP | IRA | PHA | 54 | INV | 186 | A | I | CFC | 195.7 | 195.7 | 0 |  | 2008-04-01 | 2008-04-01 | 2009-03-01 |  | 2011-04-01 | 2011-09-01 | 729846 | 0 | 729846 | 729846 | 100% | 0 | 0 | 0 | 80283 | 0 | 80283 | 0 | 0 | project completed
FIN | Germany | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | INV | 181 | A | I | CFC | 250 | 250.3 | 0 |  | 2007-03-01 | 2007-04-01 | 2008-03-01 |  | 2009-04-01 | 2011-09-01 | 920868 | 0 | 920868 | 920868 | 100% | 0 | 0 | 0 | 101295 | 0 | 101295 | 0 | 0 | 4 tenders were contracted and production started for 2 machines by end of 2008. The other 2 installations were completed by end of 2009/ beginning 2010.
FIN | Germany | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 176 | A | I | CFC | 30 | 30 | 0 |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2008-08-01 | 2011-09-01 | 1007124 | 0 | 1007124 | 1007124 | 100% | 0 | 0 | 0 | 110784 | 0 | 110784 | 0 | 0 | Funds have been disbursed for the conversion of manufacturers in the foam sector. Certificates of destruction will be collected and handed in during 2009.
FIN | Germany | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 160 | A | I | CFC | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 | 694124 | 946405 | 1640529 | 1640529 | 100% | 0 | 0 | 0 | 76354 | 104105 | 180459 | 0 | 0 | Activity progressed according to plan. So far, a total of 1500 ODP tons have been replaced with CFC-free technology. All of the funds have been disbursed and the targeted ODP phase out has been achieved. The tranche is completed, all outstanding certificates of destruction were handed in by december 2007.
FIN | Germany | Terminal CFC phase-out management plan (second tranche) | Multi-Year | AFR | LES | PHA | 45 | INV | 09 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2005-04-01 | 2005-04-01 | 2006-04-01 |  | 2007-12-01 | 2008-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | 3rd tranche was requested and approved.
FIN | Germany | Terminal CFC phase-out management plan (first tranche) | Multi-Year | AFR | LES | PHA | 41 | INV | 08 | A | I | CFC | 0.6 | 0.8 | 0 |  | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2005-03-01 | 2005-06-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Second tranche was requested for the TPMP.
FIN | Germany | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | NAM | PHA | 50 | INV | 12 | A | I | CFC | 3 | 3 | 0 |  | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-06-01 | 2012-12-01 | 92500 | 0 | 92500 | 92500 | 100% | 0 | 0 | 0 | 12025 | 0 | 12025 | 0 | 0 | All conversions under the incentive scheme have been completed. The project is completed and the final report is being drafted.
FIN | Germany | Terminal phase-out management plan for CFCs | Multi-Year | AFR | NAM | PHA | 41 | INV | 10 | A | I | CFC | 9 | 10.5 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2008-05-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Namibia continues to maintain zero imports in keeping with the TPMP targets. In 2007, 3 additional customs training were organised to maintain vigilance and update the ASCUYDA ++ system. Incentive scheme is being implemented successfully with 42 cold rooms being retrofitted mainly at hospitals and schools (hostels). A total of 312 kgs of ODS has been phased out |  |  | 2006-12-01
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, first tranche) | Multi-Year | AFR | ZIM | PHA | 51 | INV | 38 | A | I |  | 25 | 25 | 0 |  | 2007-03-01 | 2007-04-01 | 2009-12-01 |  | 2008-07-01 | 2008-10-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | Phase completed and 3rd tranche approved
FIN | Germany | Project preparation for a terminal phase-out management plan | Individual | AFR | BOT | PHA | 55 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2008-07-01 | 2008-10-01 | 2009-01-01 |  | 2009-03-01 | 2009-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | TPMP project was approved at the 57th Excom.
FIN | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2007-06-01 | 2007-10-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Project was completed and the 2nd tranche approved in March 2007
FIN | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | D | CFC | 2 | 3 | 0 | 0 | 2004-12-01 | 2012-05-01 | 2006-12-01 |  | 2011-12-01 | 2012-05-01 | 69400 | 0 | 69400 | 62987 | 90.76% | 6413 | 0 | 0 | 6246 | 0 | 5668.83 | 577.17 | 0 | Project operationally completed (Dec. 11) and financially closed (May 12). | Balance of funds returned in April 2013. |  |  | INV
FIN | IBRD | CFC phase-out management plan (second tranche) | Multiyear | LAC | ANT | PHA | 61 | INV | 13 | N | D |  | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-05-01 | 27900 | 0 | 27900 | 0 | 0% | 27900 | 0 | 0 | 2511 | 0 | 0 | 2511 | 0 | Project operationally completed (link to ANT/PHA/61/INV/13) Dec. 11 and financially closed May 12. | Balance of funds returned in April 2013. |  |  | INV
FIN | IBRD | Terminal phase-out management plan: 2006-2007 biennial programme | Multiyear | LAC | BHA | PHA | 51 | INV | 14 | N | I | CFC | 25 | 25 | 0 | 0 | 2007-03-01 | 2009-06-01 | 2009-03-01 |  | 2009-01-01 | 2009-06-01 | 120000 | -29054 | 90946 | 90946 | 100% | 0 | 0 |  | 15600 | -3777.02 | 11822.98 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2005-12-01 | 2009-06-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 08 | N | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 | 2009-06-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 |  | 31200 | 0 | 31200 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | LAC | ECU | PHA | 49 | INV | 37 | N | I | CFC | 70 | 70 | 0 | 0 | 2006-07-01 |  | 2007-12-01 |  | 2009-06-01 | 2010-12-01 | 227410 | -227410 | 0 | 0 |  | 0 | 0 |  | 17055 | -17055 | 0 | 0 | 0 | NCPP completed. Balance of $227,410 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | LAC | ECU | PHA | 52 | INV | 39 | N | I | CFC | 38 | 38 | 0 | 0 | 2007-07-01 |  | 2008-07-31 |  | 2009-06-01 | 2010-12-01 | 227411 | -227411 | 0 | 0 |  | 0 | 0 |  | 17056 | -17056 | 0 | 0 | 0 | NCPP completed. Balance of $227,411 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | LAC | ECU | PHA | 56 | INV | 41 | N | I | CFC | 42 | 42 | 0 | 0 | 2008-11-01 |  | 2009-11-30 |  | 2009-09-01 | 2010-12-01 | 18334 | -18334 | 0 | 0 |  | 0 | 0 |  | 1375 | -1375 | 0 | 0 | 0 | Project completed. Balance of $18,334 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | LAC | ECU | PHA | 45 | INV | 36 | N | I | CFC | 85 | 85 | 0 | 0 | 2005-04-01 | 2008-10-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 439319 | -22174 | 417145 | 417145 | 100% | 0 | 0 |  | 32349 | -1632.77 | 30716.23 | 0 | 0 | NCPP completed. Balance of $22,174 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2005-04-01 | 2010-12-01 | 777326 | 0 | 777326 | 777326 | 100% | 0 | 0 |  | 58299.45 | 0 | 58299.44 | 0.01 | 0.01 | NCPP completed. Balances of subsequent tranches returned to the MLF at the 62nd ExCom. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2009 annual programme | Multiyear | ASP | MAL | PHA | 59 | INV | 166 | N | I | CFC | 350.7 | 350.7 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 275000 | -75992 | 199008 | 199008 | 100% | 0 | 0 | 0 | 24750 | -6839.28 | 17910.72 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | MAL | PHA | 52 | INV | 158 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 2007-07-01 | 2009-12-01 | 2008-07-31 |  | 2010-09-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | MAL | PHA | 55 | INV | 160 | N | I | CFC | 89 | 89 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | MAL | PHA | 49 | INV | 157 | N | I | CFC | 120 | 120 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-12-01 | 2012-04-01 | 1013300 | 0 | 1013300 | 1013300 | 100% | 0 | 0 | 0 | 83197 | 0 | 83197 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | MAL | PHA | 47 | INV | 156 | N | I | CFC | 470.8 | 470.8 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2008-12-01 | 2012-04-01 | 1208300 | 0 | 1208300 | 1208300 | 100% | 0 | 0 | 0 | 100747 | 0 | 100747 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | I | CFC | 430 | 430 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 1688300 | 0 | 1688300 | 1688300 | 100% | 0 | 0 | 0 | 143947 | 0 | 143947 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2012-04-01 | 1799940 | 0 | 1799940 | 1799940 | 100% | 0 | 0 | 0 | 140395 | 0 | 140395 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-12-01 | 2012-04-01 | 2013100 | 0 | 2013100 | 2013100 | 100% | 0 | 0 | 0 | 169179 | 0 | 169179 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 | 2012-04-01 | 2969065 | 0 | 2969065 | 2969065 | 100% | 0 | 0 | 0 | 259216 | 0 | 259216 | 0 | 0 | NCPP completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2005 work programme | Multiyear | LAC | MEX | PHA | 45 | INV | 124 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2007-04-01 |  | 2006-02-01 | 2006-02-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | Funds were disbursed to FIDE. These funds were added to the rotating fund created with the first tranche. By the end of 2006, 19 chillers had been replaced (the target was 10), and as of Dec 06, collection rates on loans were 100%. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | PHI | PHA | 54 | INV | 82 | N | I | CFC | 421.3 | 421.3 | 0 | 0 | 2008-04-01 |  | 2009-03-31 |  | 2011-06-01 | 2012-04-01 | 110000 | -110000 | 0 | 0 |  | 0 | 0 | 0 | 5500 | -5500 | 0 | 0 | 0 | Transfer of the $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | PHI | PHA | 51 | INV | 81 | N | I | CFC | 907 | 907 | 0 | 0 | 2007-03-01 | 2007-12-01 | 2008-03-01 |  | 2011-06-01 | 2012-04-01 | 337717 | -18096 | 319621 | 319621.28 | 100% | -0.28 | -0.28 | 0 | 20795 | -1114 | 19680.75 | 0.25 | 0.25 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | PHI | PHA | 47 | INV | 79 | N | I | CFC | 149 | 149 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2011-06-01 | 2012-04-01 | 2873197 | -1683614 | 1189583 | 1189583 | 100% | 0 | 0 | 0 | 248588 | -145666 | 102922.3 | -0.3 | -0.3 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2012-04-01 | 1877418 | -23495 | 1853923 | 1853923 | 100% | 0 | 0 | 0 | 160968 | -2014 | 158953.56 | 0.44 | 0.44 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 2160071 | 0 | 2160071 | 2160071 | 100% | 0 | 0 | 0 | 186006 | 0 | 186006 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | I |  | 89.3 | 89.3 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2012-04-01 | 2858473 | 0 | 2858473 | 2858473 | 100% | 0 | 0 | 0 | 248663 | 0 | 248663 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV
FIN | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | I | CFC | 150 | 166 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-04-01 | 750000 | -434097 | 315903 | 315903 | 100% | 0 | 0 |  | 45000 | -26046 | 18954 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Total phase-out of CFCs plan: 2007 annual programme | Multiyear | EUR | TUR | PHA | 50 | INV | 89 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2007-12-01 | 2008-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Total phase-out of CFCs plan: 2006 annual programme | Multiyear | EUR | TUR | PHA | 47 | INV | 87 | N | I | CFC | 150 | 150 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2008-04-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2008-04-01 | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 |  | 175000 | 0 | 175000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2008-04-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 295000 | 0 | 295000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | Sweden | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-09-01 | 2004-12-01 |  | 2005-06-01 | 2005-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 3450 | 0 | 3450 | 0 | 0 | Annual report submitted and approved at the 42nd ExCom meeting. |  | 2003
FIN | Sweden | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | CRO | PHA | 42 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-12-01 | 2005-12-01 | 24700 | 0 | 24700 | 24700 | 100% | 0 |  |  | 1853 | 0 | 1853 | 0 | 0 | Annual report submitted and approved at the 46th ExCom meeting. |  | 2004
FIN | Sweden | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 27 | A | I | CFC | 13 | 13 | 0 |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-06-01 | 2006-06-01 | 21500 | 0 | 21500 | 21500 | 100% | 0 | 0 | 0 | 1613 | 0 | 1613 | 0 | 0 | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. The project was completed in June 2006. |  | 2005
FIN | Sweden | National CFC phase out plan: servicing sector (first tranche) | Multi-Year | ASP | PHI | PHA | 38 | TAS | 68 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2012-04-01 | 152400 | 0 | 152400 | 152400 | 100% | 0 |  |  | 11316 | 0 | 11316 | 0 | 0 | The original plan to establish a functioning Reclamation Facility in partnership with PARII was deemed not financially-viable and economically-feasible by PARII due to low amounts of reclaimable refrigerants from the servicing sector. Hence, an alternative model to establish an ODS management plan, including the collection, transport, and storage of recovered refrigerants and unwanted ODS was proposed by the PMU and included in the 2010-2011 Biennual Plan of the NCPP approved at the 60th ExCom Meeting. Procurement and selection process for equipment which complements that already procured under the reclamation scheme, as well as for contractors for ODS collection, transport and storage was not completed until 2010. Delsa Chemicals and Multi-Products Inc (DCMI), a member of PARII, the refrigerant importer association, was the contractor selected for the collection, transport and storage of recovered refrigerants for the NCPP and has completed its work in 2011. Overall NCPP closed by the WB in Jun 2011. Reconciliation of the account indicate a total savings of US$114,046.05 for the Swedish component because disbursement for some activities under Sweden was posted under the overall NCPP under the WB instead. | Financial completion of the NCPP under the WB occurred on Apr. 12 upon return of the balance of the funds to the 66th ExCom. | 2002
FIN | Sweden | National CFC phase-out plan servicing sector: 2004 annual programme | Multi-Year | ASP | PHI | PHA | 41 | TAS | 72 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2011-11-01 | 2012-04-01 | 166134 | -114046 | 52088 | 52088 | 100% | 0 | 0 | 0 | 12952 | 0 | 12952 | 0 | 0 | See remarks above. | See remarks above. | 2003 | 2006-12-01
FIN | Sweden | National CFC phase-out plan servicing sector: 2005 annual programme | Multi-Year | ASP | PHI | PHA | 44 | TAS | 77 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2010-07-01 | 2012-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | See remarks above. | See remarks above. | 2004
FIN | UNDP | National CFC phase-out plan (third tranche) | Multi-year | AFR | DRC | PHA | 61 | INV | 33 | N | I | CFC | 46.5 | 46.5 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2011-07-01 |  | 2011-12-01 | 2012-07-01 | 71875 | 0 | 71875 | 63558.97 | 88.43% | 8316.03 | 0 | 0 | 5391 | 0 | 4767.2544 | 623.7456 | 0 | Financially completed in 2012. | Completed in 2011. | 2010 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | INV | 25 | N | I | CFC | 1.5 | 1.5 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-11-01 | 40000 | -6716.7 | 33283.3 | 33283.3 | 100% | 0 | 0 | 0 | 3600 | -604.5 | 2995.5 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2009-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | GEO | PHA | 53 | INV | 25 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2011-10-01 | 108820 | -81.94 | 108738.06 | 108738.06 | 100% | 0 | 0 | 0 | 8162 | -6.15 | 8155.85 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | EUR | GEO | PHA | 50 | INV | 22 | N | I | CFC | 4.8 | 4.8 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2009-11-01 |  | 2008-12-01 | 2011-10-01 | 216180 | 0 | 216180 | 216180 | 100% | 0 | 0 | 0 | 16214 | 0 | 16214 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GHA | PHA | 53 | INV | 26 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-11-01 | 2011-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 | 0 | 10538 | 0 | 10538 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GHA | PHA | 50 | INV | 24 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2009-11-01 |  | 2008-11-01 | 2011-06-01 | 204394 | 0 | 204394 | 204394 | 100% | 0 | 0 | 0 | 15330 | 0 | 15330 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | INV | 19 | N | I | CFC | 8 | 8 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2012-07-01 | 91000 | 0 | 91000 | 90523.68 | 99.48% | 476.32 | 0 | 0 | 8190 | 0 | 8147.1312 | 42.8688 | 0 | Financially completed in 2012. | Completed in 2011. Equipment procured and delivered to final beneficiaries. | 2009 |  | Investment
FIN | UNDP | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 42 | INV | 165 | N | I | CFC | 56 | 56 | 0 | 0 | 2004-04-01 | 2005-05-01 | 2007-04-01 |  | 2007-12-01 | 2011-12-01 | 770000 | -13453.09 | 756546.91 | 756546.91 | 100% | 0 | 0 | 0 | 57750 | -1008.98 | 56741.02 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (third tranche) | Multi-year | ASP | KYR | PHA | 60 | INV | 23 | N | I | CFC | 5 | 5 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2011-01-01 | 60000 | 0 | 60000 | 59999.82 | 100% | 0.18 | 0 | 0 | 4500 | 0 | 4499.9865 | 0.0135 | 0 | Completed in 2010. Financially completed in 2011. |  | 2010 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-year | ASP | KYR | PHA | 55 | INV | 18 | N | I | CFC | 1 | 1 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-01-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 | 0 | 4725 | 0 | 4725 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | ASP | KYR | PHA | 50 | INV | 14 | N | I | CFC | 1 | 1 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2009-11-01 |  | 2008-12-01 | 2011-01-01 | 194000 | 0 | 194000 | 194000 | 100% | 0 | 0 | 0 | 14550 | 0 | 14550 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fifth tranche) | Multi-year | ASP | LEB | PHA | 55 | INV | 66 | N | I | CFC | 35 | 35 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2012-01-01 | 65000 | -400.46 | 64599.54 | 64599.54 | 100% | 0 | 0 | 0 | 4875 | -30.03 | 4844.97 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fourth tranche) | Multi-Year | ASP | LEB | PHA | 53 | INV | 65 | N | I | CFC | 40 | 40 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2012-01-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (second and third tranches) | Multi-Year | ASP | LEB | PHA | 48 | INV | 63 | N | I | CFC | 287 | 287 | 0 | 0 | 2006-04-01 | 2008-01-01 | 2007-04-01 |  | 2008-12-01 | 2012-01-01 | 865000 | 0 | 865000 | 865000 | 100% | 0 | 0 | 0 | 64875 | 0 | 64875 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (first tranche) | Multi-Year | ASP | LEB | PHA | 44 | INV | 57 | N | I | CFC | 55 | 55 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2012-01-01 | 1061420 | 0 | 1061420 | 1061420 | 100% | 0 | 0 | 0 | 79607 | 0 | 79607 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | INV | 16 | N | I | CFC | 8.4 | 8.4 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-12-01 | 28000 | -1436.95 | 26563.05 | 26563.05 | 100% | 0 | 0 | 0 | 2520 | -129.33 | 2390.67 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | LIR | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2011-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | INV | 29 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-12-01 | 2012-10-01 | 47500 | 0 | 47500 | 46255.49 | 97.38% | 1244.51 | 0 | 0 | 4275 | 0 | 4162.9941 | 112.0059 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | INV | 23 | N | I | CFC | 10 | 10 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 152500 | -159.02 | 152340.98 | 152340.98 | 100% | 0 | 0 | 0 | 11438 | -11.93 | 11426.07 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-02-01 | 17000 | 0 | 17000 | 15870.9 | 93.36% | 1129.1 | 0 | 0 | 1530 | 0 | 1428.381 | 101.619 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | INV | 15 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2008-11-01 | 2010-10-01 | 2010-11-01 |  | 2011-12-01 | 2012-02-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 | 0 | 9045 | 0 | 9045 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | NEP | PHA | 52 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-06-01 | 75000 | -86.06 | 74913.94 | 74913.94 | 100% | 0 | 0 | 0 | 6750 | -7.75 | 6742.25 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (fourth and fifth tranches) | Multi-Year | LAC | PAN | PHA | 56 | INV | 29 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-11-01 | 2010-02-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 255000 | -439.01 | 254560.99 | 254560.99 | 100% | 0 | 0 | 0 | 19125 | -32.93 | 19092.07 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ANG | PHA | 51 | PRP | 07 | A | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2010-12-01 | 2012-12-01 | 12000 | 0 | 12000 | 3805 | 31.71% | 8195 | 0 | 0 | 900 | 0 | 285.375 | 614.625 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | BHU | PHA | 50 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-12-01 |  | 2007-03-01 | 2009-12-01 | 15000 | -10265 | 4735 | 4735 | 100% | 0 | 0 | 0 | 1125 | -770.005 | 354.995 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan | One-off-Phaseout | ASP | BHU | PHA | 52 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2010-07-01 |  | 2009-12-01 | 2011-12-01 | 35000 | 0 | 35000 | 34999.85 | 100% | 0.15 | 0 | 0 | 3150 | 0 | 3149.9865 | 0.0135 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | BZE | PHA | 50 | PRP | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2010-12-01 | 15000 | -0.5 | 14999.5 | 14999.5 | 100% | 0 | 0 | 0 | 1125 | -0.0375 | 1124.9625 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Implementation of the TPMP (investment component) | One-off-Phaseout | ASP | FIJ | PHA | 47 | TAS | 15 | N | I | CFC | 0.5 | 0.5 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2012-07-01 | 40000 | 0 | 40000 | 39999.97 | 100% | 0.03 | 0 | 0 | 3600 | 0 | 3599.9973 | 0.0027 | 0 | Financially completed in 2012. |  | 2005 | 2009-12-01 | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | GAM | PHA | 49 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -240 | 11760 | 11759.75 | 100% | 0.25 | 0 | 0 | 900 | -18 | 881.9813 | 0.01875 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | TPMP verification | Individual | EUR | GEO | PHA | 57 | TAS | 29 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 20000 | -136.13 | 19863.87 | 19863.87 | 100% | 0 | 0 | 0 | 1800 | -12.25 | 1787.75 | 0 | 0 | Completed. Fully formulated TPMP verification report was submitted to the MLF Secretariat in February 2010. Further, it was reviewed and approved at the 60th meeting of the Executive Committee (60/8). |  | 2009 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | GUA | PHA | 50 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-03-01 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | HAI | PHA | 54 | PRP | 11 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-01 |  | 2009-07-01 | 2011-11-01 | 15000 | -1826 | 13174 | 13174 | 100% | 0 | 0 | 0 | 1125 | -136.95 | 988.05 | 0 | 0 | Completed in 2009. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs: retrofitting/replacement programme | Individual | LAC | JAM | PHA | 37 | TAS | 17 | N | I | CFC | 2 | 2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2006-01-01 |  | 2007-12-01 | 2011-09-01 | 140000 | -7662.97 | 132337.03 | 132337.03 | 100% | 0 | 0 | 0 | 18200 | -996.19 | 17203.81 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | ASP | KAM | PHA | 50 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -9560 | 5440 | 5440 | 100% | 0 | 0 | 0 | 1125 | -717 | 408 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | LIR | PHA | 49 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -617 | 11383 | 11382.75 | 100% | 0.25 | 0 | 0 | 900 | -46.005 | 853.9762 | 0.018756 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | MDV | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -8440 | 6560 | 6560 | 100% | 0 | 0 | 0 | 1125 | -633 | 492 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | NEP | PHA | 50 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-07-01 | 2011-11-01 | 15000 | -10146 | 4854 | 4854 | 100% | 0 | 0 | 0 | 1125 | -760.95 | 364.05 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | NIC | PHA | 49 | PRP | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-07-01 |  | 2008-09-01 | 2010-01-01 | 15000 | -1041.83 | 13958.17 | 13958.17 | 100% | 0 | 0 | 0 | 1125 | -78.1372 | 1046.8628 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | PER | PHA | 50 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-12-01 | 2010-01-01 | 15000 | -2400 | 12600 | 12600 | 100% | 0 | 0 | 0 | 1125 | -180 | 945 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | SUR | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2007-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1125 | -187.5 | 937.5 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -5090.73 | 9909.27 | 9909.27 | 100% | 0 | 0 | 0 | 1125 | -381.8 | 743.2 | 0 | 0 | Completed in 2008. |  | 2007 |  | Investment
FIN | UNDP | Audit for an ongoing terminal phase-out management plan | Individual | LAC | TRI | PHA | 51 | TAS | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-11-01 | 20000 | -7261.08 | 12738.92 | 12738.92 | 100% | 0 | 0 | 0 | 1500 | -544.58 | 955.42 | 0 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | URT | PHA | 50 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -3240.25 | 8759.75 | 8759.75 | 100% | 0 | 0 | 0 | 900 | -243.0188 | 656.9812 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 | 0 | 9620 | 0 | 9620 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | TAS | 22 | A | I |  | 0 | 0 | 0 |  | 2009-11-01 | 2009-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 8450 | 0 | 8450 | 0 | 0 | Project completed in November 2010. Country submitted progress and expenditure reports in July 2010. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2009-07-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | BKF | PHA | 50 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 100900 | -631 | 100269 | 100269 | 100% | 0 | 0 | 0 | 13117 | -82.03 | 13034.97 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 102100 | 0 | 102100 | 102100 | 100% | 0 | 0 | 0 | 13273 | 0 | 13273 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 6240 | 0 | 6240 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | BZE | PHA | 53 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2010-12-01 | 2011-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 | 0 | 6890 | 0 | 6890 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-12-01 |  | 2011-01-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | CBI | PHA | 59 | TAS | 15 | A | I | CFC-12 | 0.3 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2010-11-01 |  | 2011-11-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | CBI | PHA | 54 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2009-12-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | CHD | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 | 2011-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 | 0 | 12220 | 0 | 12220 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 | 0 | 6890 | 0 | 6890 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | COI | PHA | 52 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2011-12-01 | 77000 | -5978 | 71022 | 71022 | 100% | 0 | 0 | 0 | 10010 | -777.14 | 9232.86 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-12-01 |  | 2010-11-01 | 2011-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project completed in November 2010. IS renewal was submitted to the 61st ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project completed in April 2011. TPMP monitoring activities conducted. CFC zero level of consumption maintained. |  |  |  | Non Investment
FIN | UNEP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 | 0 | 9344 | 0 | 9344 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | DRC | PHA | 61 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-09-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 | 0 | 9344 | 0 | 9344 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National CFC phase-out plan (first tranche) | Multi-year | AFR | DRC | PHA | 49 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-12-01 |  | 2009-07-01 | 2010-12-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 | 0 | 18688 | 0 | 18688 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (fourth tranche) | Multi-Year | ASP | DRK | PHA | 54 | TAS | 50 | A | I | CFC | 19 | 19 | 0 | 0 | 2008-04-01 | 2011-01-01 | 2009-03-01 |  | 2011-04-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (third tranche) | Multi-Year | ASP | DRK | PHA | 51 | TAS | 47 | A | I | CFC | 18 | 18 | 0 |  | 2007-03-01 | 2009-04-01 | 2008-03-01 |  | 2011-03-01 | 2012-03-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (second tranche) | Multi-year | ASP | DRK | PHA | 49 | TAS | 44 | A | I | CFC | 54 | 54 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-12-01 |  | 2008-03-01 | 2011-11-01 | 163400 | -16532 | 146868 | 146868 | 100% | 0 | 0 | 0 | 21242 | -2149.16 | 19092.84 | 0 | 0 | Project completed in August 2010. The NOU conducted various sub-projects such as refresher trainings for customs and other security officers in three regions of the country and organized two trainings at the Central River Region and the Upper River region for Refrigeration technicians on good refrigeration practices. In a bid to reducing the use of CFCs an incentive programme was initiated to help end users with fish processing factories to retrofit or replace their equipment running on chlorofluorocarbons. Four companies were identified and all of the four companies’ were assisted financially to either replace or retrofit their equipment. The NOU celebrated the 2009 International Ozone Day and organized several awareness activities including an open day where many dignitaries, students and the general public were invited to the main office of the National Environment Agency to be informed of the general activities of the Agency with particular emphasis on issues affecting the Ozone layer. 500 T-shirts were printed with Ozone protection messages and distributed as awareness materials for the public. An essay writing competition for school children and a quiz competition for ten lower Basic Schools were organized. The NOU collected and submitted 2008 Article 7 data. |  |  |  | Non Investment
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (first tranche) | Multi-year | ASP | DRK | PHA | 47 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2008-07-01 | 2009-07-01 | 234600 | 0 | 234600 | 234600 | 100% | 0 | 0 | 0 | 30498 | 0 | 30498 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | ELS | PHA | 53 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2008-11-01 |  | 2009-06-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. ($14,300 plus $ 1,859 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2010-07-01 | 2012-07-01 | 65000 | -2493 | 62507 | 62507 | 100% | 0 | 0 | 0 | 8450 | -324.09 | 8125.91 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | GAM | PHA | 53 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 93000 | 0 | 93000 | 93000 | 100% | 0 | 0 | 0 | 12090 | 0 | 12090 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GBS | PHA | 60 | TAS | 13 | A | I | CFC-12 | 3.9 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | LAC | GRN | PHA | 49 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 37000 | 0 | 37000 | 37000 | 100% | 0 | 0 | 0 | 4810 | 0 | 4810 | 0 | 0 | Project completed in June 2010 NOU completed the implementation of TPMP and submitted report to UNEP. A total of 179 Enforcement officers and 622 refrigeration technicians were trained and toolkits distributed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | GRN | PHA | 55 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 6240 | 0 | 6240 | 0 | 0 | Project completed in November 2010. All funds are at country level. Pending country terminal financial report. New agreement being negotiated for implementation in 2011. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 | 0 | 9620 | 0 | 9620 | 0 | 0 | Project completed in March 2010. and PCR submitted to the MLFS in 2010. A total of 401 refrigeration technicians were trained (260 in the first tranche and 141 in the second tranche) A total of 357 customs officers and Camcontrol officers were trained (237 in the first tranche and 120 in the second tranche) |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | GUY | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2009-03-01 |  | 2010-05-01 | 2011-05-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 | 0 | 7540 | 0 | 7540 | 0 | 0 | Project completed in December 2010. NOU conducted awareness activities using Radio, TVs, and newspapers regarding the 2010 phase out target. Customs Officers were trained in the control of ODS importation. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-12-01 |  | 2011-12-01 | 2011-12-01 | 146000 | 0 | 146000 | 146000 | 100% | 0 | 0 | 0 | 18980 | 0 | 18980 | 0 | 0 | Coordination between the National Ozone Unit and Customs Department for training and strengthening controls on ODSs and ODSs based technology imports/exports. Actions have been conducted to verify the correct tariff classification of ODSs, establishing sub-items for those that did not had a specific position according to the Harmonized Customs Code. Monitoring and reporting of all TPMP components. |  |  |  | Non Investment
FIN | UNEP | National CFC phase-out plan: 2004 annual implementation programme | Multi-year | ASP | IRA | PHA | 41 | TAS | 161 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 140253 | 0 | 140253 | 140253 | 100% | 0 | 0 | 0 | 18233 | 0 | 18233 | 0 | 0 | Project completed in March 2010 PCR submitted to the MLFS in Feb 2011. Capacity building of technicians and customs and enforcement officers played a very important role in the CFC phase out. TPMP activities provided training for technician and customs and law enforcement officers. Technician training was provided to 300 technicians in cooperation with Nepal Refrigeration and Electro Mechanical Association wherein curriculum was formulated following the course contents of the Council for Technical Education and Vocational Training (CTEVT) of Nepal. And 112 technicians in the servicing workshops that contributed in improvement of refrigeration services and adopting good practices in the domestic refrigeration and AC servicing sector. Training of more than 55 customs and enforcement officers from strengthened enforcement at the border with Bhutan, Bangladesh, China and India. Capacity building of medical doctors through a MDI workshop in cooperation with Ministry of Industry and Department of Drug Administration, Ministry of Health. Awareness activities were strengthened through an active participation with the regional awareness activities being applied at a National level during the International Ozone Day. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 173000 | 0 | 173000 | 173000 | 100% | 0 | 0 | 0 | 22490 | 0 | 22490 | 0 | 0 | Project completed in November 2010. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-year | ASP | KAM | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2009-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. ($ 199 plus $ 26 returned to ExCom 51) |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | KYR | PHA | 60 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-04-01 | 2011-07-01 | 25300 | 0 | 25300 | 25300 | 100% | 0 | 0 | 0 | 3289 | 0 | 3289 | 0 | 0 | Project is completed. 2 regional workshops for customs officers were organised.5 workshops for training of customs officers and environmental inspectors on regulations regarding import/export of ODS and ODS containing products were organized. |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | KYR | PHA | 55 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-02-01 | 2011-12-01 | 65100 | 0 | 65100 | 65100 | 100% | 0 | 0 | 0 | 8463 | 0 | 8463 | 0 | 0 | Project is Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | KYR | PHA | 50 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-07-01 | 2009-07-01 | 142600 | 0 | 142600 | 142600 | 100% | 0 | 0 | 0 | 18538 | 0 | 18538 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | LIR | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 131500 | 0 | 131500 | 131500 | 100% | 0 | 0 | 0 | 17095 | 0 | 17095 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MAU | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-03-01 | 2011-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MDV | PHA | 58 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed in July 2010. Renewal of ISP phase VII approved. All funds are at the country level. ODS data reports and country progress report submitted to OS and MFS. NOU coordinates the development of the TPMP and HPMP preparation projects. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. ($2,000 plus $260 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2009-03-01 |  | 2010-12-01 | 2011-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2011-03-01 | 120000 | -5587.86 | 114412.14 | 114412 | 100% | 0.14 | 0 | 0 | 15600 | -726.42 | 14873.56 | 0.02 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2011-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 | 0 | 10010 | 0 | 10010 | 0 | 0 | The NOU conducted additional training for both customs officer and refrigeration technicians. 30 customs officers, 20 refrigeration technicians, and 10 police officers were trained in the control of illegal importation of ODS. Both Customs Officers and Refrigeration Technicians training schools have incorporated Montreal Protocol Issues in their training curricula and implementation of the new curricula has started. The NOU engaged into sensitization campaign of the revised ODS Regulations to the general public. Implementation of project activities completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MLW | PHA | 53 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-year | EUR | MOL | PHA | 52 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2009-12-01 | 2010-12-01 | 74500 | 0 | 74500 | 74500 | 100% | 0 | 0 | 0 | 9685 | 0 | 9685 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-06-01 | 2000-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 | 0 | 18265 | 0 | 18265 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2009-11-01 | 2011-03-01 | 75000 | -7550 | 67450 | 67450 | 100% | 0 | 0 | 0 | 9750 | -981.5 | 8768.5 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | NEP | PHA | 52 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-04-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. ($ 29,000 plus $ 3,770 PSC returned Excom 46) |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2010-12-01 | 2012-07-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2010-03-01 |  | 2010-04-01 | 2011-03-01 | 81000 | -1000 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10530 | -130 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-year | LAC | PAN | PHA | 50 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-09-01 | 2007-11-01 |  | 2011-06-01 | 2011-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-year | LAC | PAN | PHA | 47 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-Year | LAC | PAR | PHA | 60 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-10-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-07-01 | 2011-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2011-03-01 | 2012-03-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | RWA | PHA | 53 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 | 2010-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed. ($ 4,850 plus $ 631 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 | 0 | 13065 | 0 | 13065 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 109500 | -1000 | 108500 | 108500 | 100% | 0 | 0 | 0 | 14235 | -130 | 14105 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2009-12-01 |  | 2010-06-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 | 0 | 0 | 2730 | 0 | 2730 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 54000 | 0 | 54000 | 54000 | 100% | 0 | 0 | 0 | 7020 | 0 | 7020 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase out management plan for CFCs (fourth tranche) | Multi-Year | LAC | STV | PHA | 61 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 | 0 | 0 | 1820 | 0 | 1820 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-Year | LAC | STV | PHA | 47 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2010-12-01 | 2011-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 | 0 | 8710 | 0 | 8710 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 89000 | -292 | 88708 | 88712 | 100% | -4 | 0 | -4 | 11570 | -37.96 | 11532.56 | -0.52 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-03-01 | 2011-06-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 | 0 | 12220 | 0 | 12220 | 0 | 0 | Project financially completed. ($ 2,765 plus $ 359 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | BAR | PHA | 54 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2010-10-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | BEN | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2007-07-01 |  | 2007-10-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | BHU | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan | Individual | ASP | BHU | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project completed in December 2010. PCR has been submitted to the MLFS in Feb 2011. Capacity building of technicians and customs officers played a very important role in the CFC phase out. NPP activities provided training for technician and customs officers. Technician training workshops were provided to 23 technicians in the servicing workshops that contributed in improvement of refrigeration services and adopting good practices in the domestic refrigeration and AC servicing sector. Training of more than 53 customs officers contributed to implementation of ODS regulations during importation. • Five (5) Sets of ODS identifiers were provided through the projects. The overall result of these activities are control of ODS imports, enforcement of local regulation and subsequent timely phase-out of ODS.• Comprehensive awareness activities were developed, distributed and organized which contributed significantly to reducing the import of CFC based equipment by traders. Consumer awareness led people to choose non CFC equipment and subsequent market demand reduction of CFC based equipment. |  |  |  | Non Investment
FIN | UNEP | TPMP verification | Individual | AFR | BKF | PHA | 57 | TAS | 28 | A | I |  | 0 |  | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | BZE | PHA | 50 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2007-09-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. ($ 1,250 plus $ 163 returned to ExCom 49) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CAF | PHA | 49 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CBI | PHA | 50 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2011-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the TPMP (non-investment component) | Individual | ASP | FIJ | PHA | 47 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2009-12-01 |  | 2010-01-01 | 2011-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAM | PHA | 49 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-08-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GBS | PHA | 50 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. Balance returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUA | PHA | 50 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GUI | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | HAI | PHA | 54 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2010-12-01 | 2012-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 | 2010-12-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1950 | -325 | 1625 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | TPMP verification | Individual | AFR | IVC | PHA | 57 | TAS | 31 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. ($ 300 plus $ 39 PSC returned ExCom 31) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | KAM | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-09-01 | 2008-01-01 | 15000 | -11 | 14989 | 14989 | 100% | 0 | 0 | 0 | 1950 | 0 | 1948.57 | 1.43 | 0 | Project financially completed. ($ 54 plus $ 7 PSC returned to ExCom 54) |  |  |  | Non Investment
FIN | UNEP | TPMP verification report | Individual | EUR | KYR | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project completed in December 2010 a. In addition, capacity building of technicians and customs and enforcement officers played a very important role in the CFC phase out. TPMP activities provided training for technician and customs and law enforcement officers. Technician training was provided to 152 technicians in the servicing workshops that contributed in improvement of refrigeration services and adopting good practices in the domestic refrigeration and AC servicing sector. Training of more than 100 Customs, Quarantine and conservation officers contributed to implementation of ODS regulations during importation Awareness activities have been carried out for the relevant national stakeholders including workshops to further inform them of the relevant information that they need to be aware of. Furthermore, a number of Important Ozone Issues pertaining the Phasing out of CFCs have been published in the Samoa Observer Newspaper and the main Television channel for effective awareness of the public towards Ozone issues and results of workshops. Also displays of Ozone boards were carried out at the National University of Samoa’s Open Day and Career Day for two years The Samoa Refrigeration Engineering Association (SREA) is functioning well and collaborating with the NOU in conducting trainings and monitoring of the licensing system. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | LIR | PHA | 49 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. ($17,000 plus $2,210 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAG | PHA | 49 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-07-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | MDV | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-11-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLW | PHA | 50 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-02-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MOZ | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-11-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a terminal phase-out management plan | RMP | ASP | MYA | PHA | 55 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2008-12-01 |  | 2011-06-01 | 2011-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | NEP | PHA | 50 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2008-01-01 | 2008-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | NIC | PHA | 49 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-06-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | PER | PHA | 50 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | SAM | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-06-01 | 2008-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 5,864 plus $ 762 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | TPMP verification | Individual | AFR | STP | PHA | 57 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | STP | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-06-01 | 2009-12-01 | 30000 | -8 | 29992 | 29992 | 100% | 0 | 0 | 0 | 3900 | -1.04 | 3898.96 | 0 | 0 | Project financially completed. ($ 3,538 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | SUR | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. ($ 25,000 plus $ 3,250 PSC returned ExCom 44$ 10,000 plus $ 1,300 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a national phase-out management plan | RMP | ASP | YEM | PHA | 50 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-04-01 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | ASP | TLS | PHA | 59 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | ARG | PHA | 42 | INV | 138 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2008-12-01 | 2012-12-01 | 2740000 | 0 | 2740000 | 2740000.01 | 100% | -0.01 | 0 |  | 205500 | 0 | 205500 | 0 | 0 | Financial completion in Dec 2012. |  |  | 2006-12-01 | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | INV | 24 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-11-01 | 2009-12-31 |  | 2010-11-01 | 2012-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 6840 | 0 | 6840 | 0 | 0 | Financial completion in May 2012. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | INV | 23 | A | I | CFC | 4 | 4 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 | 2012-12-01 | 69000 | 0 | 69000 | 68999.81 | 100% | 0.19 | 0 |  | 6210 | 0 | 6210 | 0 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | INV | 19 | A | I | CFC | 3.9 | 3.9 |  |  | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2009-12-01 | 2011-12-01 | 106000 | -400 | 105600 | 105599.57 | 100% | 0.43 | 0 |  | 9540 | -36 | 9504 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal CFC phase-out management plan (4th tranche) | Multi-Year | EUR | CRO | PHA | 49 | TAS | 29 | A | I | CFC | 65 | 65 |  |  | 2006-07-01 | 2008-02-01 | 2008-12-01 |  | 2008-12-01 | 2011-12-01 | 20200 | -2100 | 18100 | 18100 | 100% | 0 | 0 |  | 1515 | -157 | 1358 | 0 | -1 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 26 | A | I | CFC | 20 | 20 |  |  | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2011-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan: 2004 annual implementation programme | Multi-Year | EUR | CRO | PHA | 42 | TAS | 22 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2011-05-01 | 48300 | 0 | 48300 | 48300 | 100% | 0 | 0 |  | 3623 | 0 | 3623 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | INV | 20 | A | I | CFC | 0 | 33 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2005-04-01 | 2010-04-01 | 184000 | -446 | 183554 | 183554.19 | 100% | -0.19 | 0 |  | 13800 | -33 | 13767 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the NPP: recovery and recycling | Multi-Year | ASP | DRK | PHA | 47 | TAS | 40 | A | I | CFC | 121.7 | 163.7 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 536000 | -7549 | 528451 | 528451.01 | 100% | -0.01 | 0 |  | 40200 | -566 | 39634 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 47 | A | I | CFC | 42 | 42 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 10849 | 0 | 10849 | 10848.65 | 100% | 0.35 | 0 |  | 814 | 0 | 814 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | AFR | EGY | PHA | 46 | INV | 91 | A | I | CFC | 190 | 190 |  |  | 2005-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -1043 | 998957 | 998956.56 | 100% | 0.44 | 0 |  | 75000 | -78 | 74922 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | AFR | EGY | PHA | 50 | INV | 93 | A | I | CFC | 182 | 182 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 1200000 | 0 | 1200000 | 1200000.08 | 100% | -0.08 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | INV | 05 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2010-05-01 | 2010-03-31 |  | 2012-03-01 | 2012-04-01 | 100000 | -1 | 99999 | 99999.35 | 100% | -0.35 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | The TPMP was the first MP project in the country and it was approved with condition on the licensing system. The implementation started only in March 2011 after the restriction was removed. The first tranche of the project was used basically to establish centers to teach refrigeration in the country and provide tools for the centers and trained technicians. 30 sets of tools for the laboratories of three training centers and for trained technicians were purchased and delivered to the country on August 2011. The project was completed in March 2012. Financial completion in Apr 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | INV | 33 | A | I | CFC | 39.7 | 39.7 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 37500 | -271 | 37229 | 37228.69 | 100% | 0.31 | 0 |  | 2813 | -21 | 2792 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | INV | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-12-31 |  | 2010-12-01 | 2011-12-01 | 301000 | -224 | 300776 | 300775.72 | 100% | 0.28 | 0 |  | 22575 | -17 | 22558 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | TRA | 182 | A | I |  | 0 | 66.6 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-04-01 | 2009-03-01 | 36179 | -1894 | 34285 | 34284.79 | 100% | 0.21 | 0 |  | 2713 | -142 | 2571 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 177 | A | I | CFC | 230 | 230 |  |  | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2008-12-01 | 66224 | -549 | 65675 | 65675.33 | 100% | -0.33 | 0 |  | 4967 | -41 | 4926 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 170 | A | I | CFC | 115.5 | 115.5 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 742449 | -52 | 742397 | 742396.93 | 100% | 0.07 | 0 |  | 55684 | -4 | 55680 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche of implementation plan 2004) | Multi-Year | ASP | IRA | PHA | 41 | INV | 162 | A | I | CFC | 274.1 | 274.1 |  |  | 2003-12-01 | 2004-03-01 | 2005-04-01 |  | 2005-12-01 | 2007-12-01 | 361840 | 2104066 | 2465906 | 2465905.96 | 100% | 0.04 | 0 |  | 27138 | 157805 | 184943 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | INV | 29 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-11-01 | 2010-03-31 |  | 2009-12-01 | 2010-12-01 | 162000 | 0 | 162000 | 162000.02 | 100% | -0.02 | 0 |  | 12150 | 0 | 12150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | LIB | PHA | 41 | INV | 22 | A | I | CFC | 150 | 150.4 |  |  | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-08-01 | 2008-12-01 | 1500000 | -21 | 1499979 | 1499978.61 | 100% | 0.39 | 0 |  | 112500 | -2 | 112498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (third tranche) | Multi-Year | EUR | MDN | PHA | 53 | INV | 24 | A | I | CFC | 5 | 5 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2008-11-01 | 2010-05-01 | 15000 | -15 | 14985 | 14985.03 | 100% | -0.03 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (fourth tranche) | Multi-Year | EUR | MDN | PHA | 56 | INV | 26 | A | I | CFC | 5 | 5 |  |  | 2008-11-01 | 2009-08-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 14999.99 | 100% | 0.01 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | EUR | MDN | PHA | 50 | INV | 23 | A | I | CFC | 5 | 5 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-11-01 | 2008-07-01 | 79871 | -123 | 79748 | 79748.05 | 100% | -0.05 | 0 |  | 5990 | -9 | 5981 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | MDN | PHA | 45 | INV | 21 | A | I | CFC | 10 | 10 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-11-01 | 2007-12-01 | 154210 | -134 | 154076 | 154075.51 | 100% | 0.49 | 0 |  | 11566 | -10 | 11556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | MEX | PHA | 50 | INV | 130 | A | I | CFC | 1435 | 1435 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-07-01 | 2010-12-01 | 299500 | -7411 | 292089 | 292088.84 | 100% | 0.16 | 0 |  | 22463 | -556 | 21907 | 0 | 0 | Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | MEX | PHA | 42 | INV | 120 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2009-12-01 | 3517000 | 0 | 3517000 | 3517000.03 | 100% | -0.03 | 0 |  | 263775 | 0 | 263775 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | INV | 23 | A | I | CFC | 4.8 | 4.8 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-02-01 | 2012-12-01 | 53000 | 0 | 53000 | 52983.49 | 99.97% | 16.51 | 0 | 1 | 4770 | 0 | 4769 | 1 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | INV | 21 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-12-01 | 2012-12-01 | 131000 | 0 | 131000 | 130814.51 | 99.86% | 185.49 | 0 | 1 | 11790 | 0 | 11773 | 17 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (aerosol sector) | Multi-Year | AFR | NIR | PHA | 41 | INV | 109 | A | I | CFC | 57.9 | 57.9 |  |  | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2008-03-01 | 2008-06-01 | 255000 | -2 | 254998 | 254998.02 | 100% | -0.02 | 0 |  | 33150 | 0 | 33150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: refrigeration manufacturing | Multi-Year | AFR | NIR | PHA | 38 | INV | 105 | A | I | CFC | 42.9 | 42.9 |  |  | 2002-11-01 | 2003-03-01 | 2005-06-01 |  | 2006-03-01 | 2008-09-01 | 682386 | 0 | 682386 | 682385.99 | 100% | 0.01 | 0 |  | 82521 | 0 | 82521 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | OMA | PHA | 52 | INV | 15 | A | I | CFC | 10 | 10 |  |  | 2007-07-01 | 2007-12-01 | 2009-12-31 |  | 2009-07-01 | 2012-12-01 | 305800 | 0 | 305800 | 305800 | 100% | 0 | 0 |  | 22935 | 0 | 22935 | 0 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | INV | 17 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-07-01 | 2010-03-31 |  | 2010-12-01 | 2011-05-01 | 50000 | -73 | 49927 | 49927.32 | 100% | -0.32 | 0 |  | 4500 | -7 | 4493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | ROM | PHA | 51 | INV | 38 | A | I | CFC | 48.9 | 48.9 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | ROM | PHA | 60 | TAS | 41 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2012-02-01 | 83219 | -898 | 82321 | 82320.82 | 100% | 0.18 | 0 |  | 6241 | -67 | 6174 | 0 | 0 | Financial completion in Feb 2012. Refund was reported to 67th ExCom, Jul 2012. FIN.
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | INV | 30 | A | I | CFC | 14.6 | 40 |  |  | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-03-01 | 2010-12-01 | 159050 | 0 | 159050 | 159050.03 | 100% | -0.03 | 0 |  | 11929 | 0 | 11929 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | ROM | PHA | 48 | INV | 34 | A | I | CFC | 35.8 | 35.8 |  |  | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2010-12-01 | 2011-05-01 | 236750 | 0 | 236750 | 236750.01 | 100% | -0.01 | 0 |  | 17756 | 0 | 17756 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | INV | 17 | A | I | CFC | 0.7 | 0.7 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2011-12-01 | 2011-12-01 | 49000 | -479 | 48521 | 48520.81 | 100% | 0.19 | 0 |  | 4410 | -43 | 4367 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | INV | 14 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-08-01 | 2010-03-31 |  | 2009-12-01 | 2011-05-01 | 66000 | -242 | 65758 | 65758.35 | 100% | -0.35 | 0 |  | 5940 | -22 | 5918 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | ASP | SYR | PHA | 56 | INV | 98 | A | I | CFC | 328.7 | 328.7 |  |  | 2008-11-01 | 2009-12-01 | 2009-11-30 |  | 2010-12-01 | 2012-10-01 | 170000 | 0 | 170000 | 169999.98 | 100% | 0.02 | 0 |  | 12750 | 0 | 12750 | 0 | 0 | Financial completion in Oct 2012. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | I | CFC | 50 | 50 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2007-07-01 | 2010-05-01 | 1631831 | 0 | 1631831 | 1631831 | 100% | 0 | 0 |  | 122387 | 0 | 122387 | 0 | 0 | FIN |  |  | 2007-12-01 | INV
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | VEN | PHA | 51 | INV | 109 | A | I | CFC | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2011-12-01 | 2012-12-01 | 2071831 | 0 | 2071831 | 2071545.2 | 99.99% | 285.8 | 0 | 1 | 155387 | 0 | 155366 | 21 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-09-01 | 2008-05-01 | 1895062 | 0 | 1895062 | 1895062 | 100% | 0 | 0 |  | 142130 | 0 | 142130 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | CMR | PHA | 49 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-08-01 | 2007-07-01 |  | 2006-11-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Monitoring and verification audit report | Individual | EUR | CRO | PHA | 52 | TAS | 30 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-01-31 |  | 2008-09-01 | 2009-09-01 | 20000 | -3296 | 16704 | 16703.54 | 100% | 0.46 | 0 |  | 1800 | -297 | 1503 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | GUI | PHA | 49 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-06-01 | 2009-03-01 | 15000 | -2888 | 12112 | 12111.6 | 100% | 0.4 | 0 |  | 1125 | -217 | 908 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-09-01 | 2008-09-01 | 15000 | -95 | 14905 | 14904.8 | 100% | 0.2 | 0 |  | 1125 | -7 | 1118 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Audit for the terminal phase-out management plan | Individual | ASP | OMA | PHA | 57 | TAS | 20 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2010-09-01 | 2010-03-31 |  | 2010-12-01 | 2011-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1800 | 0 | 1800 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | Canada | Servicing sector terminal CFC phase-out plan (second tranche) | Multi-Year | LAC | CHI | PHA | 60 | INV | 173 | A | I | CFC | 32.9 | 32.9 | 0 |  | 2010-04-01 | 2011-01-01 | 2011-04-01 | 2013-03-01 |  |  | 261500 | 0 | 261500 | 246841.61 | 94.39% | 14658.39 |  | 14658.39 | 33995 | 0 | 31805 | 2190 |  | By end of 2012, most activities had been completed (see column AH for key results). Still ongoing were the legal and administrative process related to the certification scheme for technicians and the procurement of equipment for training centres. | Project completed in March 2013. Key results included: training of 569 technicians (in addition to those trained under Phase I); development of official certification system for technicians; 98 end-user conversions; procurement of equipment for training centres ($81,000) including tools, recovery machines and refrigerant identifiers. | 2010 |  | Investment
ONG | France | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | LAO | PHA | 61 | INV | 21 | A | I | CFC | 6.5 |  | 0 |  | 2010-07-01 |  | 2011-07-01 | 2013-03-31 |  |  | 138500 | 0 | 138500 | 127175 | 91.82% | 11325 |  | 11300 | 18005 | 0 | 16533 | 1472 |  | The signature of the financing agreement related to the 2nd tranche occurred in May 2011. Implementation of tranches 1 and 2 are binded 1 in order to accelerate the pace of implementation. See comments of Tranche 1.
ONG | France | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | LAO | PHA | 54 | INV | 18 | A | I | CFC | 0 |  | 0 |  | 2008-04-01 | 2010-05-01 | 2010-03-01 | 2013-03-31 |  |  | 181500 | 0 | 181500 | 144270 | 79.49% | 37230 |  | 37000 | 23595 | 0 | 18755 | 4840 |  | Draft Ministerial Decision on the Control of ODS import- Export license has been finalised and signed by MoNRE on 3 November 2012, progress made re the refrigeration association and re ASICUDA network; tender carried out re the provision of servicing kits at a different rate than originaly planned. Kits were delivered in the country in Febuary 2012.
ONG | IBRD | National CFC phase-out plan: 2006 work programme | Multiyear | LAC | ARG | PHA | 47 | INV | 148 | N | I | CFC | 1.5 | 0 | 0 | 0 | 2005-11-01 | 2009-12-01 | 2006-12-01 | 2013-07-01 |  |  | 500000 | 0 | 500000 | 104650 | 20.93% | 395350 | 395300 | 80000 | 37500 | 0 | 7848.75 | 29651.25 | 29651.25 | WB has provided its no objection to disbursement to chiller beneficiaries in early 2012. Some additional delays in disbursement as well as entering into additional chiller subproject agreements have occurred due to significant changes in the organization at Ministry of Industry and a new project director. UEPRO is currently in discussions with 4 other companies interested in changing equipment | It is expected that 1 of the 4 enterprises will sign a subgrant agreement (SGA) in about a month. Another will submit its proposal for replacement to the project coordination unit and then an SGA would be signed. The third is considering its investment options and will take a decision later in the year. Finally, the two chillers at the fourth enterprise originally considered were proven ineligible. Therefore, the enterprise will not participate in the project. |  |  | INV
ONG | IBRD | National CFC phase-out plan: 2007 annual implementation plan | Multiyear | ASP | THA | PHA | 53 | INV | 149 | N | I | CFC | 209 | 209 | 0 | 0 | 2007-11-01 |  | 2009-11-30 | 2013-12-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 550000 | 55000 | 49500 | 0 | 0 | 49500 | 49500 | A Steering Committee was established in Sep. 2012 whereby all responsibilities for remaining activities under the NCPP will be transferred to it. Key priorities include hiring of personnel to perform specific duties (financial management, technical oversight of training program on R&R at vocational schools, etc.). | Steering Committee was disbanded. Responsibility for all activities under the NCPP have been transferred to within the National Ozone Unit (NOU). The project proposal for strengthening training capacity and bidding documentation were submitted to the Bank. |  |  | INV
ONG | IBRD | National CFC phase-out plan: 2008 annual implementation plan | Multiyear | ASP | THA | PHA | 55 | INV | 150 | N | I | CFC | 208 | 208 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2013-12-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 550000 | 55000 | 49500 | 0 | 0 | 49500 | 49500 | A Steering Committee was established in Sep. 2012 whereby all responsibilities for remaining activities under the NCPP will be transferred to it. Key priorities include hiring of personnel to perform specific duties (financial management, technical oversight of training program on R&R at vocational schools, etc.). | Steering Committee was disbanded. Responsibility for all activities under the NCPP have been transferred to within the National Ozone Unit (NOU). The project proposal for strengthening training capacity and bidding documentation were submitted to the Bank. |  |  | INV
ONG | IBRD | National CFC phase-out plan: 2010-2012 annual implementation plan | Multiyear | ASP | THA | PHA | 60 | INV | 154 | N | I | CFC | 501.6 | 501.6 | 0 | 0 | 2010-04-01 |  | 2011-04-30 | 2013-12-01 |  |  | 385000 | 0 | 385000 | 0 | 0% | 385000 | 385000 | 40000 | 34650 | 0 | 0 | 34650 | 34650 | A Steering Committee was established in Sep. 2012 whereby all responsibilities for remaining activities under the NCPP will be transferred to it. Key priorities include hiring of personnel to perform specific duties (financial management, technical oversight of training program on R&R at vocational schools, etc.). |  |  |  | INV
ONG | IBRD | National CFC phase-out plan: 2006 annual implementation plan | Multiyear | ASP | THA | PHA | 48 | INV | 146 | N | I | CFC | 243 | 243 | 0 | 0 | 2006-04-01 | 2009-12-01 | 2007-04-01 | 2013-12-01 |  |  | 851600 | 0 | 851600 | 40334 | 4.736% | 811266 | 811266 | 80000 | 68644 | 0 | 3251.15 | 65392.85 | 65392.85 | A Steering Committee was established in Sep. 2012 whereby all responsibilities for remaining activities under the NCPP will be transferred to it. Key priorities include hiring of personnel to perform specific duties (financial management, technical oversight of training program on R&R at vocational schools, etc.). | Steering Committee was disbanded. Responsibility for all activities under the NCPP have been transferred to within the National Ozone Unit (NOU). The project proposal for strengthening training capacity and bidding documentation were submitted to the Bank. |  |  | INV
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | THA | PHA | 45 | INV | 144 | N | I | CFC | 962.9 | 962.9 | 0 | 0 | 2005-04-01 | 2009-12-01 | 2006-04-01 | 2013-12-01 |  |  | 1330400 | 0 | 1330400 | 950400 | 71.44% | 380000 | 380000 | 180000 | 111736 | 0 | 79821.02 | 31914.98 | 31914.98 | NOU has scheduled consultations with the Bank procurement specialist in Apr 12 to discuss procurement process for all remaining activities to speed up NCPP implementation. Next WB mission to evaluate implementation progress is scheduled for Jun 12. |  |  |  | INV
ONG | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | LAC | BRA | PHA | 53 | INV | 280 | N | I | CFC | 576 | 576 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 | 2013-09-01 |  |  | 870000 | 0 | 870000 | 250043.28 | 28.74% | 619956.72 | 0 | 185987.016 | 63500 | 0 | 18250.2854 | 45249.7146 | 0 | Recycling equipments were installed and recipient recyclers trained.Tech. assistance for supermarkets energy savings and reduction of CFC emissions were concluded.Chillers equipment are under installation and will be ready for energy readings during the first quarter of 2013. An independent audit was held in December 2012 that confirmed that no CFCs were imported in 2011. | Chillers have been installed. PCR under preparation. Will be submitted in July 2013. | 2007 |  | Investment
ONG | UNDP | National CFC phase-out plan (seventh tranche) | Multi-Year | LAC | BRA | PHA | 56 | INV | 284 | N | I | CFC | 350 | 350 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2013-09-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 75000 | 12500 | 0 | 0 | 12500 | 0 | Recycling equipments were installed and recipient recyclers trained.Tech. assistance for supermarkets energy savings and reduction of CFC emissions were concluded.Chillers equipment are under installation and will be ready for energy readings during the first quarter of 2013. An independent audit was held in December 2012 that confirmed that no CFCs were imported in 2011. | Chillers have been installed. PCR under preparation. Will be submitted in 2013. | 2008 |  | Investment
ONG | UNDP | National CFC phase-out plan (eighth tranche) | Multi-Year | LAC | BRA | PHA | 59 | INV | 293 | N | I | CFC | 74 | 74 | 0 | 0 | 2009-11-01 |  | 2011-11-01 | 2013-09-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 30000 | 5000 | 0 | 0 | 5000 | 0 | Recycling equipments were installed and recipient recyclers trained.Tech. assistance for supermarkets energy savings and reduction of CFC emissions were concluded.Chillers equipment are under installation and will be ready for energy readings during the first quarter of 2013. An independent audit was held in December 2012 that confirmed that no CFCs were imported in 2011. | Chillers have been installed. PCR under preparation and will be submitted in July 2013. | 2009 |  | Investment
ONG | UNDP | National ODS phase-out plan for CFCs: 2009 and 2010 annual implementation plans | Multi-Year | LAC | CUB | PHA | 59 | INV | 44 | N | I | CFC | 53.8 | 53.8 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  |  | 156000 | 0 | 156000 | 70338.78 | 45.09% | 85661.22 | 0 | 25698.366 | 11700 | 0 | 5275.4085 | 6424.5915 | 0 | The procurement of final batch of tools and materials was made in the end of 2012. Payment will be reflected in early 2013. | Tools and materials delivered to Cuba. | 2009 |  | Investment
ONG | UNDP | Terminal CFC phase-out management plan (fourth tranche) | Multi-year | LAC | DMI | PHA | 61 | INV | 17 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2010-07-01 |  | 2011-07-01 | 2013-07-01 |  |  | 6000 | 0 | 6000 | 0 | 0% | 6000 | 0 | 1800 | 540 | 0 | 0 | 540 | 0 | Procurement process for equipment on going. Delays in receiving bids from potential suppliers. | No bids received yet. Contact has been made directly with an equipment supplier that has in the past delivered equipment in the Eastern Caribbean. | 2010 |  | Investment
ONG | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 | 2013-07-01 |  |  | 57000 | 0 | 57000 | 18079.47 | 31.72% | 38920.53 | 0 | 11676.159 | 5130 | 0 | 1627.1523 | 3502.8477 | 0 | Procurement process for equipment ongoing. Delays in receiving bids from potential suppliers. | No bids received yet. Contact has been made directly with an equipment supplier that has in the past delivered equipment in the Eastern Caribbean. | 2008 |  | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | INV | 35 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2010-11-01 | 2013-08-01 |  |  | 249000 | 0 | 249000 | 155183.99 | 62.32% | 93816.01 | 0 | 28144.803 | 22410 | 0 | 13966.5591 | 8443.4409 | 0 | Equipment was procured and delivered to Guatemala. | The equipment is in the process of being delivered to the beneficiaries. Technical training of technicians took place. | 2008 |  | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | INV | 14 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2009-07-01 |  | 2011-07-01 | 2014-03-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 60000 | 13500 | 0 | 0 | 13500 | 0 | Delays with the implementation of the TPMP activities in Haiti. A new work plan was prepared. | TORs for international consultant prepared and published. | 2009 |  | Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 53 | INV | 15 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2007-11-01 | 2011-04-01 | 2009-11-01 | 2013-06-01 |  |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Remaining funds under TPMP proposed to be used to sustain zero ODS consumption and support HCFC phaseout in line with decision 60/11, mainly the activity in Recovery and Reclamation. Procurement of equipment is currently in progress. During the year, advertisements were issued for procurement of equipment but no response was received from potential service providers. Government is proposing to have direct contract with single supplier for procuring equipment. | Equipment procurement process through a service provider is proposed to be completed by Q2 of 2013. | 2007 |  | Investment
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | INV | 26 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-09-01 | 2011-03-01 | 2013-06-01 |  |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | During the year 2012, UNDP continued to follow up with NOU for completing pending activities under the project. Due to changes in NOU staffing, activities were delayed. | Second and final disbursement under LoA expected to be made in Q2 of 2013 after respective milestone is achieved. | 2009 |  | Investment
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2011-03-01 | 2013-09-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 9000 | 2700 | 0 | 0 | 2700 | 0 | During the year 2012, due to staff changes in NOU, activities relating to retrofit of MACs was delayed. NOU has also reported limited number of CFC based MACs available for retrofits. They also propose to use remaining funds under TPMP for HPMP activities in line with decision 60/11. | Project implementation progress is being closely monitored. All activities under this project are expected to be completed by end of Q3 2013. | 2009 |  | Investment
ONG | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2014-01-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 22000 | 4950 | 0 | 0 | 4950 | 0 | Action Plan is in place and definition of equipment need is being concluded to start the procurement. | Action Plan is in place and definition of equipment need is being concluded to start the procurement. | 2008 |  | Investment
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | INV | 28 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 2009-07-01 |  | 2011-07-01 | 2013-12-01 |  |  | 72000 | 0 | 72000 | 0 | 0% | 72000 | 0 | 21600 | 5400 | 0 | 0 | 5400 | 0 | Monitoring over the operation of the zonal centres continued. In March 2012, two (2) training sessions for technicians completed (30 people each). Last tender for procurement of multi-gas identifiers had been announced twice during 2012 (after failed local tender in 2011). Initial tender during summer 2012 did not still generate enough interest from existing suppliers. Second tender was expanded in its scope in November 2012 to include standard R&R tools (recovery, containtment, leak detection) to encourage more companies to apply. | Last round of trainings can be expected, if funds allow, after equipment is delivered to Tanzania. However, it is expected that the last ITB will consume the majority of remaining budget. Project will be categorized as operationally completed shortly after. | 2009 |  | Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | INV | 23 | N | I | CFC | 15.9 | 15.9 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-01 | 2013-12-01 |  |  | 204000 | 0 | 204000 | 153092.16 | 75.05% | 50907.84 | 0 | 15272.352 | 15300 | 0 | 11481.912 | 3818.088 | 0 | Monitoring over the operation of the zonal centres continued. In March 2012, two (2) training sessions for technicians completed (30 people each). Last tender for procurement of multi-gas identifiers had been announced twice during 2012 (after failed local tender in 2011). Initial tender during summer 2012 did not still generate enough interest from existing suppliers. Second tender was expanded in its scope in November 2012 to include standard R&R tools (recovery, containtment, leak detection) to encourage more companies to apply. | Two companies only applied (STAG and Unicorn), and review on bids was provided. Clarifications were sought from the companies before selection process could be finalized. Unicorn is the selected bidder. Equipment will consist of multi-gas analyzers and R&R tools. Equipment is expected within next 7 months. | 2008 |  | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-year | LAC | URU | PHA | 60 | INV | 54 | N | I | CFC | 29.9 | 29.9 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 | 2013-05-01 |  |  | 45000 | 0 | 45000 | 1574.9 | 3.5% | 43425.1 | 0 | 13027.53 | 3375 | 0 | 118.1175 | 3256.8825 | 0 | Activities to sustain complete phaseout of CFCs implemented in 2012. This includes training by international expert to local technicians, and provision of incentives/tools to local technicians. Expenditures to be reflected in 2013. | Final training will take place in April 2013. | 2010 |  | Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2011-11-01 | 2013-11-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 0 | 95000 | 12350 | 0 | 0 | 12350 | 0 | All resources allocated in the 2nd tranche were transferred to the 1st tranche of the HPMP of Bahrain approved by the 68th ExCom | UNEP coordinated 2 preparatory meetings with NOU and UNIDO to prepare the detailed work-plan of the HPMP of Bahrain, including TPMP 2nd tranche resources, during the 1st quarter of 2013. Country contract planned to be signed by May 2013. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | BAH | PHA | 50 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-06-01 | 2008-07-01 | 2013-04-01 |  |  | 210000 | 0 | 210000 | 80000 | 38.1% | 130000 | 0 | 130000 | 27300 | 0 | 10400 | 16900 | 0 | All training activities and distribution of R&R equipment were completed. However final financial statement from country on 1st tranche of TPMP is pending. Detailed Study on the Feasibility of the Reclamation business in Bahrain was conducted during 2012, in coordination with UNDP to facilitate the operation of the R&R program under TPMP. | UNEP is following up closing the pending financial reports by the country of the 1st tranche contract |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2011-12-01 | 2013-12-01 |  |  | 41000 | 0 | 41000 | 30000 | 73.17% | 11000 | 0 | 11000 | 5330 | 0 | 3900 | 1430 | 0 | The SSFA has since expired but was revised and sent to country for signature. The country has signed awaiting disbursement. |  |  |  | Non Investment
ONG | UNEP | Terminal phase out management plan for CFCs (second tranche) | Multi-Year | AFR | DJI | PHA | 59 | TAS | 17 | A | I | CFC-12 | 3.2 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-01 | 2013-12-01 |  |  | 58000 | 0 | 58000 | 40000 | 68.97% | 18000 | 18000 | 18000 | 7540 | 0 | 5200 | 2340 | 2340 | The SSFA has since expired but was revised and sent to country for signature. The country has signed awaiting disbursement. | SSFA was sent to FMO for payment |  |  | Non Investment
ONG | UNEP | Terminal CFC phase-out management plan (fourth tranche) | Multi-Year | LAC | DMI | PHA | 61 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 | 2013-12-01 |  |  | 13000 | 0 | 13000 | 3792 | 29.17% | 9208 | 9208 | 9208 | 1690 | 0 | 492.96 | 1197.04 | 1197.04 | Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention were addressed, maintaining zero level of CFC consumption, as well as, preventing the continuous increase in the use of HCFC-22 in the country. Activities funded with resources available at country level disbursed in 2011. | (a) Consultation with main stakeholders to restrict ODS-based technology; (b) Provide technical support to RAC sector in alternatives to HCFCs; c) To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 | 2013-03-01 |  |  | 92835 | 0 | 92835 | 0 | 0% | 92835 | 0 | 92835 | 12069 | 0 | 0 | 12069 | 0 | 2012 annual operating plan and the procurement plan have been prepared by the NOU and customs focal point with the guidance of the CAP Team. NOU followed up with the Ministry of Finance to obtain the authorization for opening the Special Account needed for project funds management. By December 2012, the process still needed additional steps, preventing implementation of the project as planned. However, training activities on alternative technologies and reinforcement of Customs capacity were developed with resources of Ecuador HPMP to contribute towards country’s compliance. Awareness and information activities on ODSs alternative technologies and illegal trade prevention addressed maintaining zero level of CFCs consumption as well as preventing the continuous increase in the use of HCFC-22 in the country. | 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training and Brokers Workshop including 5th Amendment of Customs codes scheduled to April 22, 2013. The current implementation plan includes HPMP activities along with the activities under all remaining NPP tranches, which are planned for completion before end of 2013. The low disbursements were due to difficulty to open a special banking account to enable funds transfer to the NOU. The banking account is expected to be operational by July 2013. |  |  | Non Investment
ONG | UNEP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-09-01 | 2011-07-01 | 2013-03-01 |  |  | 7485 | 0 | 7485 | 2906.2 | 38.83% | 4578.8 | 4307 | 4578.8 | 973 | 0 | 377.7866 | 595.2134 | 559.8812 | Review of 2011 ODS consumption by an independent auditor completed. | Monitoring of TPMP activities conducted as planned. |  |  | Non Investment
ONG | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 | 2013-03-01 |  |  | 92835 | 0 | 92835 | 4282 | 4.612% | 88553 | 5528 | 88553 | 12069 | 0 | 556.6808 | 11512.3192 | 718.6668 | 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. NOU followed up with the Ministry of Finance to obtain the authorization for opening the special account needed for project funds management. By December 2012, the process still needed additional steps, preventing implementation of the project as planned. Expenditures expected to start in 2013 when the special account is opened. However, IAs, NOU and the Refrigeration Technician College (SECAP) drafted a training curriculum for Good Practices in Refrigeration Alternative Technologies to be launched in 2013. | The special account permission has been obtained in March 2013. NOU is preparing the institutional contract wih SECAP to launch national train the trainers programme on low GWP alternatives. The current implementation plan includes HPMP activities along with the activities under all remaining NPP tranches, which are planned for completion before end of 2013. The low disbursements were due to difficulty to open a special banking account to enable funds transfer to the NOU. The banking account is expected to be operational by July 2013. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | EQG | PHA | 57 | TAS | 04 | A | I | CFC-12 | 4.6 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-09-01 | 2013-06-01 |  |  | 105000 | 0 | 105000 | 80000 | 76.19% | 25000 | 0 | 25000 | 13650 | 0 | 10400 | 3250 | 0 | The country conducted training of 30 refrigeration technicians and 20 custom officers.. The activities are ongoing satisfactorily. |  |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 | 2013-03-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 9100 | 0 | 0 | 9100 | 0 | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the absence of Ozone Officer. The Government is in the process of appointing new Ozone Officer to proceeding with implementation of activities | Implementation of activities has delayed due to change of Ozone Officer. The government is in the process of appointing new Ozone Officer. The Government has not yet appointed a new Ozone Officer. CAP planning a Joint mission with UNIDO to discuss with the Government on how to proceed with the implementation of activities. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2011-02-01 | 2010-03-01 | 2013-07-01 |  |  | 100000 | 0 | 100000 | 80000 | 80% | 20000 | 0 | 20000 | 13000 | 0 | 10400 | 2600 | 0 | NOU trained 30 refrigeration experts and 15 customs officer. The country procured and distributed tools and equipment. Conducted public awareness activities on Montreal Protocol through radio and tv. | Implementation of activities has delayed due to change of Ozone Officer. The government is in the process of appointing new Ozone Officer |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 | 2013-12-01 |  |  | 32500 | 0 | 32500 | 23972 | 73.76% | 8528 | 0 | 8528 | 4225 | 0 | 3116.36 | 1108.64 | 0 | Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention addressed maintaining zero level of CFC consumption as well as preventing the continuous increase in the use of HCFC-22 in the country. Refrigeration Technicians trained on low-GWP technologies on a regular basis through the technician Association (GRAVA). NOO and President of the GRAVA attended international seminar in longer term alternatives that are non-ODS, energy efficient and low climate impact. | Audited Financial reports are being prepared and reconciliated by NOU in order for UNEP to release outstanding disbursements. (a) Consultation with main stakeholders to restrict ODS-based technology; (b) Provide technical support to RAC sector in alternatives to HCFCs; c) To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-06-01 | 2013-06-01 |  |  | 125000 | 0 | 125000 | 64943 | 51.95% | 60057 | 0 | 60057 | 16250 | 0 | 8442.59 | 7807.41 | 0 | New Minister briefed on the requirements of the TPMP. Agreement was reached on the planned approach. | (a) Consultation with main stakeholders to restrict ODS-based technology; (b) Provide technical support to RAC sector in alternatives to HCFCs; c) To closely monitor implementation progress. Activities (a) and (b) delayed due to frequent changes in the ministry and the NOU. UNEP is doing follow-up to adjust the plan of activities. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2010-11-01 | 2013-12-01 |  |  | 52000 | 0 | 52000 | 25000 | 48.08% | 27000 | 0 | 27000 | 6760 | 0 | 3250 | 3510 | 0 | Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention addressed maintaining zero level of CFC consumption as well as preventing the continuous increase in the use of HCFC-22 in the country. | According to UNEP rules, project balance is being obligated to proceed with outstanding disbursements, once audited financial reports are received by UNEP. (a) Consultation with main stakeholders to restrict ODS-based technology; (b) Provide technical support to RAC sector in alternatives to HCFCs; ( c) Activities coordinated with Customs to prevent ODSs illegal trade (d)To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | ASP | KUW | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2008-11-01 | 2013-12-01 |  |  | 240000 | 0 | 240000 | 1757 | 0.7321% | 238243 | 0 | 238243 | 31200 | 0 | 228.41 | 30971.59 | 0 | All remaining activities under TPMP were incorporated in the HPMP of Kuwait which approved by 66th ExCom. UNEP and NOU prepared comprehensive work-plan to start implementation of the HPMP and remaining TPMP activities | Country contract is due for signature by 1st half of 2013 for both HPMP and TPMP activities |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 | 2013-12-01 |  |  | 59000 | 0 | 59000 | 0 | 0% | 59000 | 0 | 59000 | 7670 | 0 | 0 | 7670 | 0 | Administrative stalement still not resolved | The issue of Administrative stalement in Mauritanian is being followed up very closely by the Regional Director and with the assistance of the office of the Deputy Executive Director and it is expected that the stalement will be resolved soon. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 | 2013-12-01 |  |  | 59000 | 0 | 59000 | 40000 | 67.8% | 19000 | 0 | 19000 | 7670 | 0 | 5200 | 2470 | 0 | Trained 70 refrigeration experts and 40 customs officers. The country procured and distributed equipment and tool kits and conducted awareness activities | project was completed |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 55 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 | 2013-12-01 |  |  | 77500 | 0 | 77500 | 36266 | 46.79% | 41234 | 0 | 41234 | 10075 | 0 | 4714.58 | 5360.42 | 0 | The ODS import/export licensing system has been updated in order to include the quotas for HCFCs as well as other adjustments needed for better functioning. This work has included the revision of all the legal framework governing ODS import, trade and use in the country, including a new set of regulations for refrigeration servicing technicians. The electronic interface between the licensing and customs system is being designed at the moment and is expected to be operative by the end of 2012. Two training and awareness seminars for customs control chain officers were held for 45 officers. Printed information and awareness material have been produced as needed for the customs training activities including the “Training Manual for Customs Officers”, the “Quick Guide for Customs Inspection of ODSs” and “Illicit Trade of ODSs” | (a) Consultation with main stakeholders to restrict ODS-based technology; (b) Provide technical support to RAC sector in alternatives to HCFCs; ( c) Activities coordinated with Customs to prevent ODSs illegal trade: ( d) To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | National CFC phase-out plan: Final implementation plan | Multi-Year | ASP | PHI | PHA | 66 | INV | 94 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-05-01 | 2014-03-01 | 2014-03-01 |  |  | 1835205 | 0 | 1835205 | 103924 | 5.663% | 1731281 | 0 | 1731281 | 154294 | 57579 | 8737.3616 | 203135.6384 | 0 | The list of planned activities for 2012: - Project Management - Prevention of additional supply of CFCs - Elimination of CFC demand in the country - Management of unwanted ODS - Information, Education and Communication (IEC) Campaign. Progress: The NCPP PMU conducted/organized four (4) Regional Consultations nationwide to gather significant comments from the concerned stakeholders in 2012. The NCPP PMU conducted turn-over of training equipment to Training Institutes (TIs) through awarding of Deed of Donations. As to date, 136 out of 139 TIs have been completed. Submitted CFC verification audit to UNEP last 22 February 2012. | The NCPP PMU conducted regional workshop last 20 February 2013 with selected Regional ODS Officers in Luzon Area to discuss the initial findings on the assessment of voucher grantees. Out of the 602 target service shops to be survey, all were completed. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-11-01 | 2013-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | All resources allocated in the 2nd tranche were transferred to the 1st tranche of the HPMP of Bahrain approved by the 65th ExCom Planning and finalizing contract for HPMP and remaining TPMP activities was delayed due to change of ODS Officer, without proper internal handover, and the need to rediscuss all working plans and contracting arrangements again. UNEP assisted NOU in reviewing its licensing and Quota procedures in order to reinforce in 2013 | All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-07-01 | 2009-03-01 | 2013-12-01 |  |  | 65000 | 0 | 65000 | 15000 | 23.08% | 50000 | 0 | 50000 | 8450 | 0 | 1950 | 6500 | 0 | ODS Officer of Qatar changed 3 times over the last 3 years resulting to delaying implementation of all projects. Early 2012 new ODS Officer nominated officially but no proper hand-over internally was arranged. * UNEP and UNIDO made plan to re-establish the operation of the Ozone Unit in Qatar and build its capacity through several meetings and missions to quickly orient the new ODS Officer and other officials with MP and project implementation needs. 2 Orientation meetings and one national workshop arranged by UNEP during 2012. All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 | All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 | 2013-12-01 |  |  | 67000 | 0 | 67000 | 50013 | 74.65% | 16987 | 0 | 16987 | 8710 | 0 | 6501.69 | 2208.31 | 0 | NOU conducted inspection visits to major boarders to monitor the control of ODS in collaboration with customs officials and Beaural of Standards. TPMP equipment and tools were procured and distributed. The country trained 50 Refrigeration experts and 20 customs officers | project completed |  |  | Non Investment
ONG | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2011-07-01 | 2013-07-01 |  |  | 40500 | 0 | 40500 | 10350 | 25.56% | 30150 | 0 | 30150 | 5265 | 0 | 1345.5 | 3919.5 | 0 | Curricula update has been finalized. The development of national code for good practices has been initiated. However, and due to limited funding and miscommunications between respective governmental authorities, completion of the code was delayed and expected to be completed under the HPMP. a second round of train the trainers took place during April 2012 and training equipment have been distributed among participating centres. Several training courses have been organized for RAC technicians in main cities where R&R equipment and tools supplied under the project have been provided. | The remaining training activities as well as the update of regulations and certification scheme will be incorporated in the HPMP action plan |  |  | Non Investment
ONG | UNEP | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-01-01 | 2009-03-01 | 2013-12-01 |  |  | 364500 | 0 | 364500 | 232639 | 63.82% | 131861 | 0 | 131861 | 47385 | 0 | 30243.07 | 17141.93 | 0 | Curricula update has been finalized. The development of national code for good practices has been initiated. However, and due to limited funding and miscommunications between respective governmental authorities, completion of the code was delayed and expected to be completed under the HPMP. a second round of train the trainers took place during April 2012 and training equipment have been distributed among participating centres. several training courses have been organized for RAC technicians in main cities where R&R equipment and tools supplied under the project have been provided. | The remaining training activities as well as the update of regulations and certification scheme will be incorporated in the HPMP action plan |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SIL | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2011-07-01 | 2013-12-01 |  |  | 55000 | 0 | 55000 | 2545 | 4.627% | 52455 | 0 | 52455 | 7150 | 0 | 330.85 | 6819.15 | 0 | NOU finalised review process of training curricula manual for both customs and refrigeration technicians training schools. Both training schools have started using the new curricula which include ozone modules. Revised ODS regulations were approved and enforcement is into effect | Final payment made in May 2013. Project completed |  |  | Non Investment
ONG | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 | 2013-06-01 |  |  | 90000 | 0 | 90000 | 64842 | 72.05% | 25158 | 25158 | 25158 | 11700 | 0 | 8429.46 | 3270.54 | 3270.54 | CAP Team conducted country mission in February 2012 to review project activities and agree on finalization of activities on the remaining funds. Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention were addressed, maintaining zero level of CFC consumption, as well as, preventing the continuous increase in the use of HCFC-22 in the country. | (a) Provide support in updating ODS legislation to include HCFCs; (b) Provide technical support in alternatives to HCFCs; c) To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-06-01 | 2013-12-01 |  |  | 100000 | 0 | 100000 | 85441 | 85.44% | 14559 | 14032 | 14559 | 13000 | 0 | 11107.33 | 1892.67 | 1824.16 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Two SSFAs were signed by the Government and UNEP. Fund disbursements released according to plan. Center of Excellence on low-GWP technology reinforced. HCFC quotas were issued by end of Dec. 2012. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. | 2013 annual work plan has been drafted. Quota system established. Customs Training Workshop including 5th Amendment of Customs codes has been planned for the current year. (a) Provide support in updating ODS legislation to include HCFCs; (b) Provide technical support in alternatives to HCFCs; c) To closely monitor implementation progress. |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 | 2013-06-01 |  |  | 57000 | 0 | 57000 | 40001 | 70.18% | 16999 | 0 | 16999 | 7410 | 0 | 5200.13 | 2209.87 | 0 | NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tool kits to some refrigeration repair workshops and refrigeration technicians. The refrigeration Association was assisted to get their constitution and get registered. |  |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 | 2013-12-01 |  |  | 75000 | 0 | 75000 | 50016 | 66.69% | 24984 | 0 | 24984 | 9750 | 0 | 6502.08 | 3247.92 | 0 | Country revised ODS Regulations to include HCFCs, reviewed training curricula for both customs training school and vocational training centre for refrigeration expert training. | project completed |  |  | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 | 2013-12-01 |  |  | 78000 | 0 | 78000 | 50000 | 64.1% | 28000 | 0 | 28000 | 10140 | 0 | 6500 | 3640 | 0 | NOU conducted inspection visits to major boarders to monitor the control of ODS in collaboration with customs officials and Beaural of Standards. TPMP equipment and tools were procured and distributed | project was completed |  |  | Non Investment
ONG | UNEP | TPMP verification | Individual | ASP | KUW | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 | 2013-07-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 0 | TPMP funds are incorporated in the HPMP project for developing verification for the 1st tranche of HPMP | Independent institute/firm will be contracted before end of 2013 to prepare the verification report for submitting the HPMP 2nd tranche including verifying TPMP. UNEP and NOU agreed on the terms of reference |  | 2012-07-01 | Non Investment
ONG | UNEP | TPMP verification | Individual | AFR | ZAM | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2010-03-01 | 2013-12-01 |  |  | 20000 | 0 | 20000 | 14000 | 70% | 6000 | 0 | 6000 | 2600 | 0 | 1820 | 780 | 0 | Verification report finalised submitted to UNEP | Verification report submitted to ExCom 69 for consideration |  | 2011-12-01 | Non Investment
ONG | UNIDO | National CFC phase-out plan: 2008 work programme | Multi-Year | LAC | ARG | PHA | 53 | INV | 152 | A | I | CFC | 1509.5 | 0 |  |  | 2007-11-01 | 2008-12-01 | 2009-12-31 | 2013-12-01 |  |  | 1167350 | 0 | 1167350 | 116134.12 | 9.949% | 1051215.88 | 39717.34 | 250000 | 87551 | 0 | 8710 | 78841 | 2979 | Technical and commercial evaluation of bids finalized, purchase orders on the supply of new chillers to two public hospitals issued. | Preparation of TORs on the dismantling of old chillers and installation of new ones followed by local bidding for provision of the above civil work and engineering services. Inspection of other public hospitals and preparation of TOR on the replacement of their CFC based chillers. Development and printing of new training manual for service technicians and procurement of refrigeration service equipment under HPMP implementation. The project is expected to be completed in 2013. Reason for the delay: The coordination on the preparation of the technical specification for the hospitals took longer than expected. During 2013 US$ 550,000 is expected to be committed and disbursement should reach US$ 250,000. The disbursement target has been modified accordingly. After operational completion it takes usually several months until all commitments can be cleared. |  |  | INV
ONG | UNIDO | National CFC phase-out plan: 2007 work programme | Multi-Year | LAC | ARG | PHA | 50 | INV | 150 | A | I | CFC | 200 | 0 |  |  | 2006-11-01 | 2007-09-01 | 2007-11-01 | 2013-12-01 |  |  | 1103500 | 0 | 1103500 | 428345.47 | 38.82% | 675154.53 | 351936.48 | 150000 | 82763 | 0 | 32126 | 50637 | 26395 | Technical and commercial evaluation of bids finalized, purchase orders on the supply of new chillers to two public hospitals issued. Actual implementation was over 70% at the end of 2012. The disbursement indicated for 2013 is our estimate at this stage, since usually after project completion, clearance of obligated balances takes several months. | Preparation of TORs on the dismantling of old chillers and installation of new ones followed by local bidding for provision of the above civil work and engineering services. Inspection of other public hospitals and preparation of TOR on the replacement of their CFC based chillers. The project is expected to be completed in 2013. Reason for the delay: The coordination on the preparation of the technical specification for the hospitals took longer than expected. |  |  | INV
ONG | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | ARG | PHA | 47 | INV | 147 | A | I | CFC | 100 | 100 |  |  | 2005-11-01 | 2006-04-01 | 2006-12-01 | 2013-12-01 |  |  | 1850000 | 0 | 1850000 | 1694036.79 | 91.57% | 155963.21 | 145147.67 | 100000 | 138750 | 0 | 127053 | 11697 | 10886 | Technical and commercial evaluation of bids finalized, purchase orders on the supply of new chillers to two public hospitals issued. | Preparation of TORs on the dismantling of old chillers and installation of new ones followed by local bidding for provision of the above civil work and engineering services. Inspection of other public hospitals and preparation of TOR on the replacement of their CFC based chillers. Reason for the delay: The coordination on the preparation of the technical specification for the hospitals took longer than expected. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | INV | 27 | A | I | CFC | 3.1 | 3.1 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 | 2013-06-01 |  |  | 53000 | 0 | 53000 | 1801.69 | 3.399% | 51198.31 | 50997.92 | 50000 | 4770 | 0 | 162 | 4608 | 4590 | The joint UNIDO-UNEP mission enabled the assessment of needs. The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 almost 100% of the funds have been committed and by now disbursement level is around 80%. | The equipment is being shipped. The project will be closed after the equipment delivery in 2013. Reason for the delay: The procurement and shipment process took longer than expected. |  |  | INV
ONG | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | EGY | PHA | 60 | INV | 101 | A | I |  | 65 | 65 |  |  | 2010-04-01 | 2010-05-01 | 2011-04-30 | 2013-12-01 |  |  | 300000 | 0 | 300000 | 91971.49 | 30.66% | 208028.51 | 207350.01 | 207350 | 22500 | 0 | 6898 | 15602 | 15551 | 1) A data management system linking the ozone office with all other relevant Governmental institutions was set up. Equipment and software were installed and tested during first half of 2012. Training started in May 2012 and was finished in September 2012. The database started full operation with start of 2013. 2) The CFC consumption of the year 2010 was verified and found to be zero. | No further activities, funds are obligated for the conversion of AC system in railway carriages. The slight delay is due to security reasons.
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | AFR | EGY | PHA | 54 | INV | 95 | A | I | CFC | 100 | 100 |  |  | 2008-04-01 | 2008-11-01 | 2009-03-31 | 2013-12-01 |  |  | 600000 | 0 | 600000 | 376763.04 | 62.79% | 223236.96 | 219100.17 | 219100 | 45000 | 0 | 28257 | 16743 | 16433 | The incentive program to retrofit 100 carriages of the National Railways Company has started, a demo retrofit was carried out and certification under national law was received for the new technology. Difficulties were encountered with custom clearance for the imported parts of equipment and spare parts (shipment from Turkey to Egypt). | Custom problems solved. Retrofits in progress. Finalization is expected for the end of 2013. Reason for delay: 1) certification for retrofitting took longer than expected; 2) security reasons; 3) difficulties encountered with custom clearance. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | INV | 09 | A | I | CFC | 4.2 | 4.2 |  |  | 2011-04-01 | 2011-12-01 | 2012-03-31 | 2013-03-01 |  |  | 75000 | 0 | 75000 | 23131.06 | 30.84% | 51868.94 | 49020 | 51500 | 6750 | 0 | 2082 | 4668 | 4412 | Project completed in Mar 2013. | Project will be completed in Mar 2013. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | INV | 24 | A | I |  | 1.5 | 1.5 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 | 2013-07-01 |  |  | 60000 | 0 | 60000 | 5176.78 | 8.628% | 54823.22 | 48000 | 6000 | 5400 | 0 | 466 | 4934 | 4320 | The procurement of equipment was initiated as planned jointly with the HPMP equipment. | Procurement of equipment was completed in the first quarter of 2013. All funds obligated in 2012 are by May disbursed. The remaining disbursement is indicated for the remaining funds. However, as of today all activities completed. The project is expected to be completed in 2013.
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | INV | 34 | A | I | CFC | 44.1 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 | 2013-06-01 |  |  | 121000 | 0 | 121000 | 97332.08 | 80.44% | 23667.92 | 3493.9 | 23500 | 9075 | 0 | 7300 | 1775 | 262.0425 | In 2012 the equipment needs were assessed, the technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated, purchase order was issued and the equipment shipped. | Equipment has been delivered and a mission to Abidjan took place in February 2013. The project will be closed after the equipment distribution. Reason for the delay: The political and security situation in the country. |  |  | INV
ONG | UNIDO | National ODS phase-out plan: 3rd tranche | Multi-Year | AFR | LIB | PHA | 54 | INV | 28 | A | I | CFC | 176 | 114.6 |  |  | 2008-04-01 | 2010-03-01 | 2009-03-31 | 2013-12-01 |  |  | 277947 | 0 | 277947 | 164624.72 | 59.23% | 113322.28 | 22354.64 | 90000 | 20846 | 0 | 12347 | 8499 | 1677 | Equipment delivered to 2 beneficiaries (in Tripoli region) forwarding to Benghazi is pending. Trainings are pending. Purchase of refrigerant identifiers for regional offices of state environmental agency (EGA) and custom authorities has been initiated based on request of NOU and after agreement with NOU on the scope and technical parameters. Bidding is in progress. | Delivery of equipment for monitoring and inspection. Training on the operation and proper use of equipment. Mission preparation is in progress. Reason for the delay: the security and social situation in the country that have not improved and stabilized. |  |  | INV
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | AFR | LIB | PHA | 45 | INV | 25 | A | I | CFC | 124 | 124 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2013-12-01 |  |  | 720000 | 0 | 720000 | 601629.45 | 83.56% | 118370.55 | 1226.16 | 110000 | 54000 | 0 | 45122 | 8878 | 92 | Equipment delivered to two beneficiaries (in Tripoli region) forwarding to Benghazi is pending. Trainings are pending. Purchase of refrigerant identifiers for regional offices of state environmental agency (EGA) and custom authorities has been initiated based on request of NOU and after agreement with NOU on the scope and technical parameters. Bidding is in progress. | Delivery of equipment for monitoring and inspection. Training on the operation and proper use of equipment. Mission preparation is in progress. Reason for the delay: the security and social situation in the country that have not improved and stabilized. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan for CFCs (fifth tranche) | Multi-Year | EUR | MDN | PHA | 59 | INV | 28 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 | 2013-01-01 |  |  | 15000 | 0 | 15000 | 4585 | 30.57% | 10415 | 0 | 10415 | 1125 | 0 | 344 | 781 | 0 | Project completed in Jan 2013. | Project will be completed in Jan 2013. |  |  | INV
ONG | UNIDO | Terminal phase-out plan for CFCs (second tranche) | Multi-Year | EUR | MOG | PHA | 58 | INV | 06 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 | 2013-07-01 |  |  | 95295 | 0 | 95295 | 72621.52 | 76.21% | 22673.48 | 15563 | 5000 | 7147 | 0 | 5447 | 1700 | 1167.225 | Equipment delivered and distributed in the fourth quarter of 2012. | All funds obligated in 2012 are by now disbursed. The remaining disbursement is indicated for the remaining funds. However, as of May all activities are completed. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 65 | INV | 44 | A | I | CFC | 15 | 0 |  |  | 2011-11-01 | 2012-01-01 | 2012-12-01 | 2013-07-01 |  |  | 183500 | 0 | 183500 | 149315.75 | 81.37% | 34184.25 | 25211.34 | 34000 | 13763 | 0 | 11199 | 2564 | 1891 | The tools for the training centres were purchased and delivered to the country in August 2012. A letter to the Government from the Executive Committee, that would provide information on the difficulties faced in the customs clearance could help. The issue is that since the Project was not registered in the International Cooperation Office, no release of taxes for import of equipment was approved. Help was requested from local UNDP and recently also from the Ministry of Production. At present the Ministry of Production is prepararing a Resolution however it has not been possible to obtain it. | It is expected to release the tools from the custom ands close the project in 2013. Reason for the delay: Since the training tool were delivered to the country, UNIDO has been trying to release them from the customs but it has not been possible yet. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | INV | 21 | A | I |  | 1.8 | 1.8 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 | 2013-12-01 |  |  | 45000 | 0 | 45000 | 7955.39 | 17.68% | 37044.61 | 37023.52 | 37045 | 4050 | 0 | 716 | 3334 | 3332 | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). Reason for the delay: UNIDO is of the view that the impact of the project is maximized linking it to the HPMP.
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | INV | 13 | A | I | CFC | 12 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 | 2013-12-01 |  |  | 70000 | 0 | 70000 | 42117.43 | 60.17% | 27882.57 | 26987 | 5000 | 5250 | 0 | 3159 | 2091 | 2024 | Any remaining balance of the TPMP is transferred to the HPMP. Almost all funds are obligated by the end of 2012. The remaining estimated disbursement is indicated for the remaining funds. After operational completion of the project, usually it takes several months to clear all commitments/obligations. However, UNIDO will do its utmost to disburse the remaining balance during 2013. | Project and remaining funding will be completed by Dec 2013. Reason for the delay: No NOU officer(s) were appointed for a long period of time. |  |  | INV
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | INV | 09 | A | I | CFC | 3 | 0 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 | 2013-12-01 |  |  | 242500 | 0 | 242500 | 185275.6 | 76.4% | 57224.4 | 54449.35 | 1000 | 18188 | 0 | 13896 | 4292 | 4084 | Any remaining balance of the TPMP is transferred to the HPMP. Almost all funds are obligated by the end of 2012. The remaining estimated disbursement is indicated for the remaining funds. After operational completion of the project, usually it takes several months to clear all commitments/obligations. | Project and remaining funding will be completed by Dec 2013. Reason for the delay: No NOU officer(s) were appointed for a long period of time. |  |  | INV
ONG | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | INV | 10 | A | I | CFC | 532 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 | 2013-12-01 |  |  | 143000 | 0 | 143000 | 72103.7 | 50.42% | 70896.3 | 4533.68 | 4000 | 10725 | 0 | 5408 | 5317 | 340 | All equipment was distributed during spring 2012. It was agreed to re-allocate some funds from NPP to exploration of E-licensing system as well as certification scheme for refrigeration technicians. HPMP approved at the 68th Meeting of the Executive Committee, the project transferred to the HPMP. The remaining balances of the NPP will be utilized for HPMP activities as specified in the HPMP. After operational completion of the project, usually it takes several months to clear all commitments/obligations. | 1. E-licensing system as well as certification scheme for refrigeration technicians. |  |  | INV
ONG | UNIDO | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | INV | 03 | A | I | CFC | 269.7 | 250 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 | 2014-12-01 |  |  | 1287000 | 0 | 1287000 | 1001115.85 | 77.79% | 285884.15 | 14158.93 | 10000 | 96525 | 0 | 75084 | 21441 | 1062 | All equipment was distributed during spring 2012. It was agreed to re-allocate some funds from NPP to exploration of E-licensing system as well as certification scheme for refrigeration technicians. The remaining balances of the NPP will be utilized for HPMP activities as specified in the HPMP. As both projects are interconnected the project has to remain open. | 1. Project and remaining funding moved to approved HPMP. |  |  | INV
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | ASP | SYR | PHA | 58 | INV | 99 | A | I | CFC | 70 | 70 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 | 2013-12-01 |  |  | 154050 | 0 | 154050 | 23650.62 | 15.35% | 130399.38 | 0 | 40000 | 11554 | 0 | 1774 | 9780 | 0 | No progress has been made due to the political and security situation. The date of project completion is unknown, due to the security situation, however, we had to indicate a planned completion date. We will revise the planned completion date in the next progress report depending on the developments in the country. | No progress has been made due to the political and security situation. |  |  | INV
ONG | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-01 | 2013-12-01 |  |  | 40678 | 0 | 40678 | 52.58 | 0.1293% | 40625.42 | 0 | 8000 | 3051 | 0 | 4 | 3047 | 0 | Decision of the NOU to utilize the funds for investment component (in combination with other tranches of NPP) delayed. Technical specification for consented scope of training equipment has been prepared as requested by the NOU. No procurement action has been agreed due to the pending decision of the NOU. | Purchase of equipment. Survey on the network of technical apprenticeship schools to carry out trainings. Select the schools; organize the trainings. Reason for the delay: coordinational activities took longer than expected. Indeed the planned level of 2013 expenditure is low. However, the draft TOR has been consented and quantitative requirement was received from the NOU (last week), to purchase service and training equipment for different categories of service shops. Procurement is being initiated. Mission to discuss further implementation of all components of the NPP is planned.
ONG | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | EUR | YUG | PHA | 60 | INV | 36 | A | I |  | 268 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 | 2013-12-01 |  |  | 193500 | 0 | 193500 | 40789.33 | 21.08% | 152710.67 | 6688.77 | 80000 | 14513 | 0 | 3059 | 11454 | 502 | Training of trainers was successfully implemented. 22 trainers were trained and certified. Scope of equipment for service technicians was coordinated. Potential local entities for training of service technicians surveyed by UNIDO national consultants, the respective proposals on the selection of training centers submitted to the NOU. However, the NOU's final selection of entities was still pending delaying procurement of equipment. | Selection and contracting training centers. Review and adjustment of the scope of equipment supply followed by international bidding, placement of purchase orders and delivery of training equipment. The project is expected to be completed in 2013. Reason for the delay: The procurement process was delayed because the NOU's final selection of entities was pending longer than expected.
ONG | UNIDO | National CFC phase-out plan (third tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 51 | INV | 31 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2009-12-01 | 2008-03-01 | 2013-12-01 |  |  | 222000 | 0 | 222000 | 15275.6 | 6.881% | 206724.4 | 0 | 40000 | 16650 | 0 | 1146 | 15504 | 0 | Decision of the NOU to utilize the funds for investment component (in combination with other tranches of NPP) delayed. Technical specification for consented scope of training equipment has been prepared as requested by the NOU. No procurement action has been agreed due to the pending decision of the NOU. | Purchase of equipment. Survey on the network of technical apprenticeship schools to carry out trainings. Select the schools; organize the trainings. Reason for the delay: coordinational activities took longer than expected. Indeed the planned level of 2013 expenditure is low. However, the draft TOR has been consented and quantitative requirement was received from the NOU (last week), to purchase service and training equipment for different categories of service shops. Procurement is being initiated. Mission to discuss further implementation of all components of the NPP is planned. |  |  | INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | I | cFC | 18 | 18 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 | 2013-12-01 |  |  | 759000 | 0 | 759000 | 135250.61 | 17.82% | 623749.39 | 5263.16 | 120000 | 56925 | 0 | 10144 | 46781 | 395 | Training of trainers was successfully implemented. 22 trainers were trained and certified. Scope of equipment for service technicians was coordinated. Potential local entities for training of service technicians surveyed by UNIDO national consultants, the respective proposals on the selection of training centers submitted to the NOU. However, the NOU's final selection of entities was still pending delaying procurement of equipment. | Selection and contracting training centers. Review and adjustment of the scope of equipment supply followed by international bidding, placement of purchase orders and delivery of training equipment. The project is expected to be completed in 2013. Reason for the delay: The procurement process was delayed because the NOU's final selection of entities was pending longer than expected. The planned level of disbursement and expenditure is indeed rather conservative, which takes into consideration the slow progress of the past years. Certainly UNIDO will do its utmost to accelerate project implementation. |  |  | INV
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | YUG | PHA | 50 | INV | 30 | A | I | CFC | 124 | 124 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 | 2013-12-01 |  |  | 1033344 | 0 | 1033344 | 866718.28 | 83.88% | 166625.72 | 0 | 40000 | 77501 | 0 | 65004 | 12497 | 0 | Decision of the NOU to utilize the funds for investment component (in combination with other tranches of NPP) delayed. Technical specification for consented scope of training equipment has been prepared as requested by the NOU. No procurement action has been agreed due to the pending decision of the NOU. | Purchase of equipment. Survey on the network of technical apprenticeship schools to carry out trainings. Select the schools; organize the trainings. Reason for the delay: coordinational activities took longer than expected. Indeed the planned level of 2013 expenditure is low. However, the draft TOR has been consented and quantitative requirement was received from the NOU (last week), to purchase service and training equipment for different categories of service shops. Procurement is being initiated. Mission to discuss further implementation of all components of the NPP is planned. |  |  | INV
TRF | France | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 31 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-06-01 | 200000 | -200000 | 0 | 0 |  | 0 |  | 0 | 26000 | -26000 | 0 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project was transferred to UNDP in Apr 06.
TRF | Germany | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 30 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-04-01 | 116000 | -116000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 15080 | -15080 | 0 | 0 | 0 | see remarks under MLF No. CUB/PHA/43/TAS/25. Transfer to UNDP completed.
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  |  | 2010-06-01 | 119500 | -83219 | 36281 | 36281 | 100% | 0 | 0 | 0 | 15535 | -10818 | 4717 | 0 | 0 | With ExCom decision 60/3 in April 2010, the remaining components of this project was formally handed over from Sweden to UNIDO and the contract with the international consultant was terminated. This progress report therefore only includes activities up to April 2010: The project has been suffering from a long delay even though a lot of progress was made during the last two years. The training of trainers for the vocation schools have been held and they have received the equipment needed for their training. Training of the existing workforce has also been conducted although in April 2010 a number of training sessions still remained to be undertaken. Up to April 2010, the Association of Refrigeration had given interim certificates to 19 Companies and 148 technicians (from which 89 are still under evaluation). A Governmental Decision had been sent for approval at all the signatory ministries and it was said that it would be published in the Official Journal no later than September 2010. The Governmental Decision was expected to be followed by a Ministerial Order which would establish the Association of Refrigeration as the interim certification body until 2011. With regards to the reuse scheme this activity is still not finalised. A number of seminars have been held to discuss the reuse scheme which raised a lot of interest. A survey was made of all the destruction facilities in the country to see which ones are incinerating based on the criteria of the Annex VI of the Regulation 1005/2009 regarding the ozone depleting substances. GreenWEEE was found to be the biggest integrated treatment plant for electric and electronic equipment waste (WEEE) in Romania and one of the most modern in Europe. They have 3 collection centers in the country (Lasi, Timisoara, Bucuresti). GreenWEEE can collect all the WEEE categories mentioned in the legislation (including large household appliances- refrigerators, freezers). The NOU has drafted a report for recycling systems in accordance with the EU existing legislation and based on the key aspects underlined by the consultation with the companies with interests in this field. Due to the existing economical situation the market is rather small. Also, meetings have been held with the customs and an draft instructions handbook was prepared based on the EU regulations. The additional delay is due to the initial long delay and the difficulties to speed up the process as much as needed to stick to the revised time plan. Also, the Governmental Decision was delayed and until September 2010 which further delayed the implementation of some of the measures proposed therein. Sweden also estimate that it will take time to get the reclamation system fully operational, something which will cause additional delay. Even if Romania had come quite far in April 2010 by holding stakeholder workshops and discussions and survey among the destruction facilities, this is much delayed already and it will take additional time to get it fully operational. The Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2005 | 2008-12-01
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 |  |  | 2010-06-01 | 148000 | -128678 | 19322 | 19322 | 100% | 0 | 0 | 0% | 19240 | -16728 | 2512 | 0 | 0 | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2004 | 2006-12-01
TRF | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 |  |  | 2006-11-01 | 134000 | -134000 | 0 | 0 |  | 0 | 0 | 0% | 17420 | -17420 | 0 | 0 | 0 | This activity was transferred to UNIDO in 2006. |  | 2005
TRF | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | PER | PHA | 55 | INV | 41 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-01 |  |  | 2011-07-01 | 183500 | -183500 | 0 | 0 |  | 0 | 0 | 0 | 13763 | -13763 | 0 | 0 | 0 | TPMP transferred to UNIDO. | TPMP transferred to UNIDO. | 2008 |  | Investment
CLO | France | Phasing out the use of CFC-113 in the electronics industry through the technical promotion of no clean processes |  | ASP | MAL | SOL | 18 | INV | 78 | A | D |  | 0 |  | 0 |  | 1995-11-01 |  | 1996-11-01 |  |  | 1997-11-01 | 226600 | -226600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet annulé
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 |  | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1997-06-01 | INV
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 15 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise is no longer eligible for grant funding. Project cancelled. |  |  |  | INV
CLO | UNDP | Elimination of the use of CFC-113 in the electron gun final cleaning processes at the Tianjin Picture Tube Factory | Individual | ASP | CPR | SOL | 19 | INV | 170 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1998-04-01 |  |  | 1999-03-01 | 132600 | -132600 | 0 | 0 |  | 0 | 0 | 0 | 17238 | -17238 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1996 |  | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the integral circuit lead frame cleaning processes at San Matech Sdn. Bhd. | Individual | ASP | MAL | SOL | 12 | INV | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-07-01 |  |  | 1995-07-01 | 141000 | -141000 | 0 | 0 |  | 0 | 0 | 0 | 18330 | -18330 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
CLO | UNIDO | Conversion of cleaning processes from CFC-113 to Aqueous Cleaning at Optica | Individual | AFR | EGY | SOL | 18 | INV | 51 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-06-01 |  |  | 1996-06-01 | 12043 | -12043 | 0 | 0 |  | 0 | 0 |  | 1566 | -1566 | 0 | 0 | 0 | CLO
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100% | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 05 | INV | 11 | N | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-06-01 | INV
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 14 | N | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | 1996-07-01 | INV
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 13 | N | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | 1997-02-01 | INV
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100% | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-02-01 | INV
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100% | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. |  |  |  | INV
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100% | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | Project implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV
FIN | UNDP | Elimination of CFC-113 from the precision cleaning and drying process at Brasimet | Individual | LAC | BRA | SOL | 18 | INV | 37 | N | I | CFC | 1.6 | 1.6 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1996-11-01 |  | 1999-12-01 | 2000-09-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Phase out of CFC-113 at DMG used in medical equipment parts cleaning | Individual | LAC | BRA | SOL | 18 | INV | 36 | N | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1997-11-01 | 2000-12-01 | 38000 | -6 | 37994 | 37994 | 100% | 0 | 0 | 0 | 4940 | -1 | 4939 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Hunan Computer Factory | Individual | ASP | CPR | SOL | 18 | INV | 152 | A | R | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 1997-12-01 | 2000-12-01 | 104700 | -18343 | 86357 | 86357 | 100% | 0 | 0 | 0 | 13611 | -2385 | 11226 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Computer Factory | Individual | ASP | CPR | SOL | 22 | INV | 216 | N | I | CFC | 6.3 | 6.3 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-11-01 | 2003-08-01 | 116767 | -1 | 116766 | 116766 | 100% | 0 | 0 | 0 | 15179.71 | 0.29 | 15180 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Sixth Radio Factory | Individual | ASP | CPR | SOL | 19 | INV | 169 | N | I | CFC | 4.5 | 4.5 | 0 | 0 | 1996-05-01 | 1999-09-01 | 1998-04-01 |  | 2001-08-01 | 2003-09-01 | 138400 | -14098 | 124302 | 124302 | 100% | 0 | 0 | 0 | 17992 | -1833 | 16159 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Railway Communication Equipment Factory | Individual | ASP | CPR | SOL | 22 | INV | 195 | N | I | CFC | 14.4 | 14.4 | 0 | 0 | 1997-05-01 | 1999-09-01 | 1999-06-01 |  | 2001-03-01 | 2003-03-01 | 276287 | -1 | 276286 | 276286 | 100% | 0 | 0 | 0 | 35917.31 | -0.31 | 35917 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai No 8 Radio Factory | Individual | ASP | CPR | SOL | 20 | INV | 186 | N | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 2000-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-09-01 | 378000 | -81073 | 296927 | 296927 | 100% | 0 | 0 | 0 | 49140 | -10539 | 38601 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai Automation Instrumentation Factory | Individual | ASP | CPR | SOL | 20 | INV | 178 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1999-08-01 | 1998-09-01 |  | 2001-03-01 | 2003-03-01 | 325000 | -5336 | 319664 | 319664 | 100% | 0 | 0 | 0 | 42250 | -694 | 41556 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at the Chengdu Qianfeng Radio Instrument Factory | Individual | ASP | CPR | SOL | 10 | INV | 37 | N | I | CFC | 7.2 | 7.2 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1995-12-01 |  | 1997-12-01 | 1999-12-01 | 394700 | -13224 | 381476 | 381476 | 100% | 0 | 0 | 0 | 51311 | -1719 | 49592 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at Nanjing Wire Works | Individual | ASP | CPR | SOL | 10 | INV | 36 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1993-06-01 | 1996-08-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 409000 | -511 | 408489 | 408489 | 100% | 0 | 0 | 0 | 53170 | -66 | 53104 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Dalian precision parts cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 19 | N | I | CFC | 69 | 69 | 0 | 0 | 1992-06-01 | 1996-04-01 | 1994-06-01 |  | 1996-09-01 | 1998-12-01 | 495000 | -34190.74 | 460809.26 | 460809 | 100% | 0.26 | 0 | 0 | 64350 | -4444.9962 | 59904.97 | 0.0338 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Dandong electronic tuner aqueous cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 20 | N | I | CFC | 20 | 20 | 0 | 0 | 1992-06-01 | 1995-07-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 495000 | -663 | 494337 | 494337 | 100% | 0 | 0 | 0 | 64350 | -86 | 64264 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Fujian Putian Vikay Electronics Co. Ltd. | Individual | ASP | CPR | SOL | 23 | INV | 224 | N | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2002-11-01 | 2008-10-01 | 619780 | -2356 | 617424 | 617424 | 100% | 0 | 0 | 0 | 80571.4 | -306.3985 | 80265.0015 | 0 | 0 | Completed in 2002. Financially completed in 2008. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-113 from the textile cleaning processes at Procesadora y Revitalizadora | Individual | LAC | MEX | SOL | 15 | INV | 37 | A | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-09-01 |  | 1996-08-01 | 2000-12-01 | 71337 | -1889 | 69448 | 69448 | 100% | 0 | 0 | 0 | 9273.81 | -245.81 | 9028 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise nationale des Detergents (ENAD-Lames) | Individual | AFR | ALG | SOL | 17 | INV | 10 | A | I | CFC | 5.6 | 5.6 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-06-01 | 2001-03-01 | 109900 | -606 | 109294 | 109294 | 100% | 0 | 0 |  | 14287 | -101 | 14186 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from CFC-113 to trichloroethylene at Hangli Refrigeration Ltd. | Individual | ASP | CPR | SOL | 22 | INV | 212 | A | I | CFC | 28.8 | 28.8 |  |  | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1999-12-01 | 2001-03-01 | 217762 | 0 | 217762 | 217762 | 100% | 0 | 0 |  | 28309 | -8 | 28301 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | SOL | 22 | INV | 213 | A | I | CFC | 37.6 | 37.6 |  |  | 1997-05-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 1999-07-01 | 236242 | 0 | 236242 | 236242 | 100% | 0 | 0 |  | 30711 | 0 | 30711 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Jiaxipera compressor factory | Individual | ASP | CPR | SOL | 22 | INV | 203 | A | I | CFC | 76 | 76 |  |  | 1997-05-01 | 1998-10-01 | 1998-12-01 |  | 1999-05-01 | 2000-04-14 | 308604 | 0 | 308604 | 308604 | 100% | 0 | 0 |  | 40119 | 0 | 40119 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 to IPA and xylene at Microraj Electronics PVT Ltd. & RCC (Sales) PVT ltd., Hyderabad (MRJ) | Individual | ASP | IND | SOL | 28 | INV | 230 | A | I | CFC | 4.3 | 4.3 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2001-11-01 | 2002-12-01 | 85431 | -431 | 85000 | 85000.01 | 100% | -0.01 | 0 |  | 11106 | -74 | 11032 | 0 | 0 | FIN
FIN | UNIDO | Conversion of CFC-113 as cleaning solvent to TCE at Bharat Electronics Limited (BEL), Bangalore | Individual | ASP | IND | SOL | 40 | INV | 362 | A | I | CFC | 16 | 16 |  |  | 2003-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-12-01 | 2006-12-01 | 151291 | -684 | 150607 | 150606.61 | 100% | 0.39 | 0 |  | 13616 | -61 | 13555 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 and CTC to processes based on IPA at Vidyut Metallics Ltd. (VML) | Individual | ASP | IND | SOL | 28 | INV | 223 | A | I | CFC CTC | 19.7 | 19.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2003-09-01 | 2004-06-01 | 225452 | -387 | 225065 | 225064.66 | 100% | 0.34 | 0 |  | 29309 | -97 | 29212 | 0 | 0 | FIN |  |  | 2002-03-01
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS to heat cleaning technologies and ODS free solvent coating at Lal Malhotra & Sons Ltd. | Individual | ASP | IND | SOL | 26 | INV | 191 | A | I | CFC | 16 | 16 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 308899 | 0 | 308899 | 308899.16 | 100% | -0.16 | 0 |  | 40157 | -8 | 40149 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Hyderabad | Individual | ASP | PAK | SOL | 22 | INV | 13 | A | I | CFC | 18.9 | 18.9 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 1999-12-01 | 2002-09-01 | 321172 | -3201 | 317971 | 317970.94 | 100% | 0.06 | 0 |  | 41752 | -481 | 41271 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning and coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Lahore | Individual | ASP | PAK | SOL | 22 | INV | 14 | A | I | CFC | 40.7 | 40.7 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2002-06-01 | 2003-06-01 | 510162 | 0 | 510162 | 510162.15 | 100% | -0.15 | 0 |  | 66321 | -37 | 66284 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-113 as solvent for dyaliser cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 08 | A | R | CFC | 54.6 | 54.6 |  |  | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960 | 0 | 76960 | 0 | 0 | FIN
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | INV
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | INV
COM | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2008-12-01 |  | 2010-12-01 |  | 787482 | 196871 | 984353 | 916847.64 | 93.14% | 67505.36 | 0 | 54004.288 | 59061 | 17718 | 71513.6185 | 5265.3815 | 0 | Completed. 5 chillers were commissioned in 2010 and are now up and running. The process to make the chillers fully operation is ongoing, and technicians from the chiller supplyer has visited Cuba to identify potential problems and solutions. Some invoices pending. |  | 2005 |  | Non-Investment
COM | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | LAC | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 |  | 2010-12-01 |  | 1000000 | -1000000 | 0 | 0 |  | 0 | 0 | 0 | 75000 | -52500 | 0 | 22500 | 0 | Completed. After replacing 7 chillers in previous years without needing funds, no additional CFC based chillers have been identified in the four countries, and the project thus has succesfully completed its objectives. Balances will be returned in 2011. |  | 2005 |  | Investment
FIN | France | CFC emission reduction in central air conditioning |  | ASP | SYR | REF | 29 | INV | 56 | A | I | CFC | 0.9 |  | 0 |  | 1999-11-01 | 2006-09-01 | 2002-06-01 |  | 2006-12-01 | 2009-08-25 | 143000 | -36617 | 106383 | 106383 | 100% | 0 |  | 0 | 7150 | -1831 | 5319 | 0 |  | Project completed.
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | I | CFC | 3.6 | 3.6 | 0 |  | 1999-07-01 | 2001-06-01 | 2001-08-01 |  | 2002-12-01 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed |  |  | 2002-12-01
FIN | Germany | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 34 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2009-09-01 |  | 2010-12-01 | 2011-12-01 | 192500 | 0 | 192500 | 192500 | 100% | 0 | 0 | 0 | 25025 | 0 | 25025 | 0 | 0 | Chiller has been delivered to Namibia and installed. Project and financial completion under way.
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 08 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-06-01 | INV
FIN | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 |  | 2002-12-01 |  | 2003-09-01 | 2005-04-01 | 2475000 | -2475000 | 0 | 0 |  | 0 | 0 |  | 282250 | -145520.83 | 136729.17 | 0 | 0 | Project completed. Funding of $1,198,947 was disbursed for replacing 17 chillers with the understanding that it would be paid back once energy savings were achieved. $1,198,947 was paid back in full by Thailand in 2007 directly to the Bank and was received as "other income." That amount was subsequently deducted by the Treasurer in new approvals at the 54th ExCom. |  |  |  | INV
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | INV
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 09 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | INV
FIN | UK | Chiller concessional lending pilot project | Individual | LAC | MEX | REF | 28 | INV | 95 | N | I | CFC | 5 | 7.8 | 0 |  | 1999-07-01 | 2001-02-22 | 2004-02-01 |  | 2004-03-01 |  | 565000 | 0 | 565000 | 565000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Phase I is completed and accomplished its objectives improving expected results: Twelve chillers were financed instead of the ten expected, with an additional two chillers financed from accumulated funds. 7.8 ODP tons were eliminated instead of 5 tons as expected. Disbursements have been made on schedule with 100% disbursement achieved in August 2002. 100% of building owners that participated in the program have made their monthly repayment on time. Energy savings were 36% higher than proposed. The project will be completed in March 2004.
ONG | France | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 36 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2008-10-01 | 2009-09-01 | 2013-06-01 |  |  | 360000 | 0 | 360000 | 172457 | 47.9% | 187543 |  | 187543 | 46800 | 0 | 22419.41 | 24380.59 |  | The French bi-lateral contribution is implemented through UNIDO and external funding is provided by the French Global Environment Facility. Progress was slow but has taken up. See UNIDO PR for details.
ONG | IBRD | Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines) | Individual | GLO | GLO | REF | 47 | DEM | 268 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-12-01 | 2013-12-01 | 2015-12-01 |  |  | 6884612 | 0 | 6884612 | 1478647.49 | 21.48% | 5405964.51 | 5405964.51 | 750000 | 516346 | 0 | 110898.58 | 405447.42 | 405447.42 | India: Replacement of CFC-based chillers is proceeding while discussions regarding restructuring are ongoing. Philippines: First chiller installed Jul. 12 and performance with regard to climate and ozone protection benefits is better than planned. Approx. 55 chillers in pipeline; 4 building owners will sign SGAs by Q1 2013. Jordan: Remaining CFC chillers in the old airport were dismantled by Dec. 2012. Project recovered total of 4 MT of CFC. Project completed. Indonesia: All preparation is completed however GEF component still awaits CEO endorsement before Grant Agreement signing. Argentina: Chiller replacement project will be incorporated into new GA between GoA and WB that is under preparation. Funding will flow once the GA is approved and signed (expected Q3 13). |  |  |  | Non-INV
ONG | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 35 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2007-06-01 | 2009-09-01 | 2014-02-01 |  |  | 700000 | 0 | 700000 | 74819 | 10.69% | 625181 | 508500 | 100000 | 91000 | 0 | 9726.47 | 81273.53 | 66105 | Update on the status of CFC chillers in Senegal received. Beneficiaries and financial scheme for Cameroon and Nigeria agreed. Mission planned to Egypt to discuss adjustments in the contract with the National bank of Egypt. Missions planned to discuss beneficiaries and financial scheme in Senegal and Sudan. Expert missions and other activities supporting identification of beneficiaries and relevant financial schemes for replacement of CFC chillers in Egypt, Senegal, and Sudan. | Completion is pending upon receipt of remaining tranches of approved funds from French Development Agency and FFEM. Funds have been requested. | 2006
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers. | Individual | LAC | BRA | REF | 47 | DEM | 275 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2014-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 400000 | 75000 | 0 | 0 | 75000 | 0 | The prodoc concerning the MLF part of this project has been signed and all the activities funded by the MLF are starting up. | Chillers equipment is in process of installation under the NPP and a company was hired to perform energy saving readings once the Chillers are started up. Further activities are related to the performance of this current assigment and it is expected to be concluded in the upcoming months. Project completion now expected in 2014. | 2005 |  | Non-Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | COL | REF | 47 | DEM | 65 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2008-12-01 | 2014-01-01 |  |  | 1000000 | 0 | 1000000 | 111945.01 | 11.19% | 888054.99 | 93984.24 | 355221.996 | 75000 | 0 | 8395.8757 | 66604.1242 | 7048.818 | Contract with EE auditing entity signed, survey among replaced chillers progressing according to plan. Financial and technical assistance contract signed and underway. Meetings with stakeholders have been held to discuss alternatives, cost and schedule. | Meetings with owners of remaining CFC based chillers took place. All will be replaced in 2013. | 2005 |  | Non-Investment
ONG | UNEP | Global technical assistance programme in the chiller sector | Individual | GLO | GLO | REF | 48 | TAS | 275 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2010-09-01 | 2009-04-01 | 2013-07-01 |  |  | 200000 | 0 | 200000 | 99194 | 49.6% | 100806 | 0 | 100806 | 26000 | 0 | 12895.22 | 13104.78 | 0 | Under this project, UNEP organized the conference “Road to Climate Friendly Chillers” from 30 September to 1 October 2010 in Cairo, Egypt in conjunction with ASHRAE's Annual Chapters Regional Conference. That conference achieved its main goal of disseminating information about CFC-free technologies then available in the chiller sector. With the complete phase out of CFCs achieved by Article 5 countries in 2010, the issue of CFC consumption in chillers sector has evolved and the remaining components of the project are less relevant. Since Articles 5 countries have already phased out CFCs, UNEP considers that the development of the remaining guidance kits, quick reference tools and other awareness materials in the CFC chiller sector is no longer relevant. Following Decision 68/4, UNEP therefore proposed to close the project and return the balance of the funds, as UNEP previously reported in its input to the Implementation Delays report for the 69th Executive Committee meeting. | UNEP proposed to close the project and return the balance of the funds, as part of its input to the Implementation Delays report for the 69th Executive Committee meeting. |  |  | Non Investment
ONG | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 37 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2009-09-01 | 2014-02-01 |  |  | 747500 | 0 | 747500 | 312044.13 | 41.75% | 435455.87 | 396015.53 | 39440 | 56063 | 0 | 23403 | 32660 | 29701 | Update on the status of CFC chillers in Senegal received. Beneficiaries and financial scheme for Cameroon and Nigeria agreed. Mission planned to Egypt to discuss adjustments in the contract with the National bank of Egypt. Missions planned to discuss beneficiaries and financial scheme in Senegal and Sudan. Completion is pending upon receipt of remaining tranches of approved funds from French Development Agency and FFEM. Funds have been requested. | Expert missions and other activities supporting identification of beneficiaries and relevant financial schemes for replacement of CFC chillers in Egypt, Senegal, and Sudan. |  |  | INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro) | Individual | EUR | EUR | REF | 47 | DEM | 06 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 | 2014-06-01 |  |  | 1069074 | 0 | 1069074 | 874048.56 | 81.76% | 195025.44 | 30380 | 80000 | 80181 | 0 | 65554 | 14627 | 2279 | Together with the NOU, UNIDO scheduled the visual inspection of the chiller for the 2nd half of May 2012. Reason for the delay: Chiller originally stolen from the bankrupt company Viskoza Cord was found in November 2012 and returned to the National Agency for Privatization. | Assessment of possibilities of repair of the chiller at Viskoza Cord and eventual relocation to new beneficiary (Clinical Center) January-March. Assessment of a potential beneficiary for replacement of one more chiller April - June. The chiller has to be inspected by a local representative of the supplier in order to assess the level of damage and possibility to repair it as well as the eventual period necessary for the repair. This is the reason why more time is required for project completion. Preparation of a regional workshop to be scheduled early in 2014. |  |  | INV
ONG | UNIDO | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 57 | INV | 32 | A | I | CFC | 18 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2011-04-01 | 2015-01-01 |  |  | 1000000 | 0 | 1000000 | 24692.77 | 2.469% | 975307.23 | 30 | 25000 | 75000 | 0 | 1852 | 73148 | 2.25 | In 2012 a consultant was hired and a mission took place during which a survey was conducted. The consultant's report, including the results of the survey, was received. The reason for the low disbursement is that first co-financing means need to be found before purchase of equipment. | A mission to Abidjan took place in February 2013. An action plan is being prepared in light of the analysis of the survey's results. Reason for the extended project duration: Long discussions and negotiations are foreseen to find co-financing means for the project implementation. |  |  | INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers | Individual | ASP | SYR | REF | 47 | DEM | 93 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 | 2015-03-01 |  |  | 585961 | 0 | 585961 | 375428.74 | 64.07% | 210532.26 | 0 | 20000 | 43947 | 0 | 28157 | 15790 | 0 | Obligation for retrofitting 3 chillers cancelled in November. No further progress possible due to the politicial situation in the country. | Implementation currently not possible due to the political situation in the country |  |  | INV
TRF | Canada | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 35 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2008-12-01 |  |  | 2007-03-01 | 196871 | -196871 | 0 | 0 |  | 0 |  | 0 | 25593 | -25593 | 0 | 0 |  | Project was transferred to UNDP at ExCom 51 (March 2007). Therefore there is no planned date of completion. Progress report for 2007 will show adjustment of funding approved. |  | 2005 |  | Non-Inv.
TRF | France | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 37 | INV | 17 | A | I | CFC | 0 |  | 0 |  | 2002-07-01 |  | 2006-08-01 |  |  | 2009-04-01 | 1000000 | -1000000 | 0 | 0 |  | 0 |  | 0 | 100000 | -100000 | 0 | 0 |  | Project transferred to UNIDO per decision 57/xx(f).
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 |  | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1998-06-01 | INV
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise decided not to proceed with project. Project cancelled. |  |  | 1993-09-01 | INV
CLO | UNDP | Elimination of the use of 111 TCA and CFC-113 in the manufacture of metal and plastic motorcycle parts at PT KGD Indonesia, Inc. | Individual | ASP | IDS | SOL | 15 | INV | 25 | A | R | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1996-02-01 |  |  | 1997-05-01 | 88000 | -88000 | 0 | 0 |  | 0 | 0 | 0 | 11440 | -11440 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 05 | INV | 12 | N | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-11-01 | INV
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 11 | N | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | 1995-09-01 | INV
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100% | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | Project completed. |  |  | 1996-12-01 | INV
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | UNDP | Elimination of the use of CFC-113 and methyl chloroform in the color picture tube cleaning processes at the Shanghai Novel CPT. Corp. Factory | Individual | ASP | CPR | SOL | 19 | INV | 171 | N | I | CFC | 75 | 75 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1998-04-01 |  | 2002-11-01 | 2008-10-01 | 849950 | -150442 | 699508 | 699508 | 100% | 0 | 0 | 0 | 110493.5 | -19557.5 | 90936 | 0 | 0 | Completed in 2002. Financially completed in 2008. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of ODS used in the production lines at Irico (Caihong) Color Picture Tube Factory | Individual | ASP | CPR | SOL | 28 | INV | 287 | N | I | TCA/CFC | 202 | 202 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2003-08-01 |  | 2002-10-01 | 2004-06-01 | 2853200 | -38805 | 2814395 | 2814395 | 100% | 0 | 0 | 0 | 323852 | -4404.9975 | 319447.0025 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Conversion of cleaning processes from CFC-113 and 1,1,1 TCA to semi-aqueous cleaning at Arab International Optronics | Individual | AFR | EGY | SOL | 18 | INV | 53 | A | I | CFC TCA | 2.1 | 2.1 |  |  | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1999-12-01 | 2000-03-01 | 48533 | 0 | 48533 | 48533 | 100% | 0 | 0 |  | 6309 | 0 | 6309 | 0 | 0 | FIN |  |  | 1999-07-01
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to non-ODS cleaning at 3 electronic companies | Individual | AFR | EGY | SOL | 18 | INV | 52 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-10-01 | 1998-11-01 | 227203 | 0 | 227203 | 227203 | 100% | 0 | 0 |  | 29536 | 0 | 29536 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes for ODS solvents to non-clean and hydrocarbon cleaning technologies at ERL-Bangalore | Individual | ASP | IND | SOL | 18 | INV | 65 | A | I | CFC TCA | 16.4 | 16.4 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2000-12-01 | 192421 | -1899 | 190522 | 190522 | 100% | 0 | 0 |  | 25015 | -286 | 24729 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to no-clean and aqueous photo resist developing and stripping technologies at ITI Palakkad | Individual | ASP | IND | SOL | 18 | INV | 66 | A | I | CFC TCA | 15 | 15 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1998-08-01 | 235744 | 5652 | 241396 | 241396 | 100% | 0 | 0 |  | 30647 | 734 | 31381 | 0 | 0 | FIN
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 |  | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | INV
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 07 | INV | 24 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 |  | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | Project has been cancelled. |  |  |  | INV
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100% | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | 1998-02-01 | INV
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 |  | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 |  | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | Project cancelled. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV
CLO | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores at Market Costan S.A. | Individual | LAC | ARG | REF | 18 | INV | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1997-05-01 |  |  | 1998-07-01 | 423000 | -421642 | 1358 | 1358 | 100% | 0 | 0 | 0 | 54990 | -54813 | 177 | 0 | 0 | Canceled in 1998. Financially completed in 1998. |  | 1995 |  | Investment
CLO | UNDP | Phaseout of CFC-11and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Quena S.A. | Individual | LAC | COS | REF | 27 | INV | 20 | A | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  |  | 2002-11-01 | 219430 | -111322 | 108108 | 108108 | 100% | 0 | 0 | 0 | 28525.9 | -14471.9 | 14054 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1999 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Amiral | Individual | AFR | EGY | REF | 20 | INV | 59 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-06-01 | 1998-09-01 |  |  | 2003-11-01 | 160000 | -70081 | 89919 | 89919 | 100% | 0 | 0 | 0 | 20800 | -9111 | 11689 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Baharanfarr Co. | Individual | ASP | IRA | REF | 31 | INV | 70 | A | I | CFC | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-01-01 | 2003-08-01 |  |  | 2002-11-01 | 208070 | -207415 | 655 | 655 | 100% | 0 | 0 | 0 | 27049.1 | -26964.1 | 85 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 2000 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers and refrigerators at Formetal | Individual | LAC | PER | REF | 19 | INV | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  |  | 2001-12-01 | 118000 | -64335 | 53665 | 53665 | 100% | 0 | 0 | 0 | 15340 | -8364 | 6976 | 0 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1996 |  | Investment
CLO | UNIDO | Phasing out of CFC-12 by HFC-134a and CFC-11 by cyclopentane in the production of commercial refrigeration equipment at Refrigeracao Rubra | Individual | LAC | BRA | REF | 23 | INV | 83 | A | I | CFC | 21.8 | 0 |  |  | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-10-01 | 320540 | -199780 | 120760 | 120760 | 100% | 0 | 0 |  | 41670 | -25996 | 15674 | 0 | 0 | CLO
CLO | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with cyclopentane in the production of commercial refrigeration equipment at Panamante Refrigeracao | Individual | LAC | BRA | REF | 25 | INV | 106 | A | I | CFC | 34.3 | 0 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  |  | 2002-09-01 | 377202 | -140248 | 236954 | 236954 | 100% | 0 | 0 |  | 49036 | -18281 | 30755 | 0 | 0 | CLO
CLO | UNIDO | Conversion of commercial refrigeration equipment to phase out CFC-12, HCFC-502 and CFC-11 at Technofrig S.A. | Individual | EUR | ROM | REF | 19 | INV | 08 | A | I | CFC | 6.92 | 6.92 |  |  | 1996-05-01 | 1997-03-01 | 1999-06-01 |  |  | 2000-07-01 | 297768 | -255677 | 42091 | 42091 | 100% | 0 | 0 |  | 38710 | -33247 | 5463 | 0 | 0 | CLO |  |  | 1999-07-01
COM | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures ( refrigeration sector terminal project) | Individual | AFR | ALG | REF | 44 | INV | 62 | A | I | CFC | 72.8 | 72.8 |  |  | 2004-12-01 | 2006-03-01 | 2007-04-01 |  | 2012-12-01 |  | 589000 | 0 | 589000 | 574920.48 | 97.61% | 14079.52 | 7501.11 | 14000 | 44175 | 0 | 43119 | 1056 | 563 | The training was postponed last minute due to the sickness of the trainer. The training took place 10-13 September 2012. Project completed in Dec 2012. |  |  |  | INV
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators |  | ASP | SYR | REF | 29 | INV | 54 | A | I | CFC | 3.2 | 3.2 | 0 |  | 1999-11-01 | 2005-02-01 | 2002-12-01 |  | 2005-02-01 | 2005-10-01 | 49113 | -1615 | 47498 | 47498 | 100% | 0 |  | 0 | 2456 | -81 | 2375 | 0 |  | Project completed. Balance returned at 57th ExCom.
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators |  | ASP | SYR | REF | 29 | INV | 48 | A | I | CFC | 3.8 |  | 0 |  | 1999-11-01 | 2007-03-01 | 2002-12-01 |  | 2007-12-01 | 2011-05-24 | 57783 | 0 | 57783 | 57783 | 100% | 0 |  | 0 | 2889 | 0 | 2889 | 0 |  | Project completed.
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Azkcon Refrigeration Industries, Inc. | Individual | ASP | PHI | REF | 23 | INV | 53 | A | I | CFC | 18.9 | 18.9 | 0 |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2005-04-01 | 370258 | -75353 | 294905 | 294905 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is completed, PCR drafted by UNDP for completion and submission by GTZ. Remaining balance and interest (USD 75.353) has been returned in Dec-04 to GTZ to be reported and returned to MLF at the 45th ExCom.
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100% | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | Refrigeration equipment acquired and installed. 134a production began May 98. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100% | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | Refrigeration equipment installed and operating. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100% | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100% | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 |  |  |  | 1999-06-01 | INV
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | 1999-05-01 | INV
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 07 | INV | 21 | N | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-23 | INV
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100% | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | Project has been fully executed. PCR being prepared. |  |  |  | INV
FIN | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | I | CFC | 25.8 | 7.85 | 0 | 0 | 2002-11-01 | 2005-12-01 | 2004-12-01 |  | 2005-10-01 | 2005-12-01 | 211636 | -130071 | 81565 | 81565 | 100% | 0 | 0 |  | 27512.68 | -16909.24 | 10603.44 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100% | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. |  |  | 2002-12-01 | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100% | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100% | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 125370 | -75182.45 | 50187.55 | 50187.55 | 100% | 0 | 0 |  | 16298.1 | -9773.72 | 6524.38 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 132320 | -81327 | 50993 | 50993 | 100% | 0 | 0 |  | 17201.6 | -10572.51 | 6629.09 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 147300 | -95904.45 | 51395.55 | 51395.55 | 100% | 0 | 0 |  | 19149 | -12467.58 | 6681.42 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100% | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | Project completed. PCR will be submitted January 2001. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100% | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100% | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  | 2000-09-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100% | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | Project completed. |  |  | 1997-08-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 100% | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100% | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  | 1999-12-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100% | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 |  |  |  | 1997-08-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100% | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-08-01 | INV
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100% | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100% | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100% | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 2000-06-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100% | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-11-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100% | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | Project completed. |  |  | 1999-06-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 100% | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-05-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100% | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | Complete. |  |  | 1998-02-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100% | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100% | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 100% | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100% | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 |  |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-08-01 | 2006-02-01 | 176681 | 0 | 176681 | 176681 | 100% | 0 | 0 |  | 22968.53 | 0 | 22968.53 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100% | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100% | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100% | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | Project completed. PCR submitted to the WB in Dec/1999. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100% | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 100% | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | Project completed. PCR submitted to the World Bank 4 September 2000. |  |  |  | INV
FIN | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | I | CFC | 173 | 186.1 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 | 2006-07-01 | 750000 | 1717315 | 2467315 | 2467315 | 100% | 0 | 0 |  | 97500 | 208904 | 306404 | 0 | 0 | Project physically and financially completed. PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100% | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100% | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | The project is completed 100% non-CFC production started. Waiting for PCR. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100% | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  |  | INV
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100% | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1998-09-01 | INV
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1999-04-01 | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 06 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 07 | N | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV
FIN | UNDP | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi | Individual | LAC | ARG | REF | 23 | INV | 60 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-11-01 | 2001-08-01 | 53850 | -4409 | 49441 | 49441 | 100% | 0 | 0 | 0 | 7000.5 | -572.5 | 6428 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of display cabinet and walk-in freezers at Disthel | Individual | LAC | ARG | REF | 19 | INV | 45 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 196000 | -5726 | 190274 | 190274 | 100% | 0 | 0 | 0 | 25480 | -744 | 24736 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio | Individual | LAC | ARG | REF | 23 | INV | 66 | A | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2002-11-01 | 2004-01-01 | 377350 | 0 | 377350 | 377350 | 100% | 0 | 0 | 0 | 49056 | 0 | 49056 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 | 2001-05-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores AT Perito Moreno Ref. | Individual | LAC | ARG | REF | 28 | INV | 92 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 1999-07-01 | 1999-09-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 379605 | 0 | 379605 | 379605 | 100% | 0 | 0 | 0 | 49349 | 0 | 49349 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | Individual | ASP | BAH | REF | 29 | INV | 10 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-06-01 | 224478 | -51106 | 173372 | 173372 | 100% | 0 | 0 | 0 | 29182.14 | -6644.14 | 22538 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | Individual | ASP | BAH | REF | 29 | INV | 09 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2011-12-01 | 173835 | 0 | 173835 | 173835 | 100% | 0 | 0 | 0 | 22599 | 0 | 22599 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11, CFC-12 and R-502 by conversion to HCFC-141b technology (foam) and HFC-134a and R-404a technology (refrigerant) in the manufacture of milk coolers and display cabinets at Incomar | Individual | LAC | BRA | REF | 28 | INV | 133 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 74529 | 0 | 74529 | 74529 | 100% | 0 | 0 | 0 | 9689 | 0 | 9689 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Niju Ind. Com Implem Rodov Ltda. | Individual | LAC | BRA | REF | 23 | INV | 86 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 111600 | 0 | 111600 | 111600 | 100% | 0 | 0 | 0 | 14508 | 0 | 14508 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and CFC-12 by conversion to HFC-134a in the manufacture of small commercial freezers and coolers at Bebber | Individual | LAC | BRA | REF | 26 | INV | 115 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2002-04-01 | 144500 | -3024 | 141476 | 141476 | 100% | 0 | 0 | 0 | 18785 | -393 | 18392 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mais Frio | Individual | LAC | BRA | REF | 23 | INV | 88 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 154400 | -25 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20072 | -3 | 20069 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b technology (foam) and HFC-134a -134a technology (refrigerant) in the manufacture of refrigerated truck trailers at Artica | Individual | LAC | BRA | REF | 27 | INV | 118 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-11-01 | 2003-10-01 | 183623 | -7277 | 176346 | 176346 | 100% | 0 | 0 | 0 | 23870.99 | -945.99 | 22925 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Friar | Individual | LAC | BRA | REF | 23 | INV | 91 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2003-04-01 | 185726 | -1023 | 184703 | 184703 | 100% | 0 | 0 | 0 | 24144.38 | -133.38 | 24011 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Artico | Individual | LAC | BRA | REF | 23 | INV | 81 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 225100 | -926.8 | 224173.2 | 224173 | 100% | 0.2 | 0 | 0 | 29263 | -120.0013 | 29142.9727 | 0.026 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-404a in the manufacture of freezer rooms and panels, and rigid foam at Schmit | Individual | LAC | BRA | REF | 31 | INV | 166 | A | I | CFC | 43.3 | 43.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2002-10-01 | 2003-11-01 | 288764 | -29918 | 258846 | 258846 | 100% | 0 | 0 | 0 | 37539.32 | -3889.32 | 33650 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b (foam) and HFC-134a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at Termisa | Individual | LAC | BRA | REF | 25 | INV | 111 | A | I | CFC | 27 | 27 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2001-12-01 | 322205 | 0 | 322205 | 322205 | 100% | 0 | 0 | 0 | 41887 | 0 | 41887 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-402a in the manufacture of commercial refrigeration products at General Icy | Individual | LAC | BRA | REF | 28 | INV | 134 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 411139 | 0 | 411139 | 411139 | 100% | 0 | 0 | 0 | 53448 | 0 | 53448 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Increal Ltda. | Individual | LAC | BRA | REF | 23 | INV | 90 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 418000 | -4 | 417996 | 417996 | 100% | 0 | 0 | 0 | 54340 | -1 | 54339 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Friomix, S.A. | Individual | LAC | COL | REF | 17 | INV | 15 | A | D | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1999-01-01 | 1996-07-01 |  | 1999-02-01 | 2000-12-01 | 11146 | 0 | 11146 | 11146 | 100% | 0 | 0 | 0 | 1449 | 0 | 1449 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refrigeracion Supernordico Ltda. | Individual | LAC | COL | REF | 19 | INV | 22 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2004-01-01 | 162500 | -1243 | 161257 | 161257 | 100% | 0 | 0 | 0 | 21125 | -162 | 20963 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Westell Ltd. | Individual | LAC | COL | REF | 17 | INV | 16 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 227602 | -2 | 227600 | 227600 | 100% | 0 | 0 | 0 | 29588 | 0 | 29588 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Wonder S.A. | Individual | LAC | COL | REF | 15 | INV | 12 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-12-01 | 1999-12-01 | 251315 | 0 | 251315 | 251315 | 100% | 0 | 0 | 0 | 32671 | 0 | 32671 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrial Colombia S.A. (Inducol) | Individual | LAC | COL | REF | 15 | INV | 14 | A | I | CFC | 16 | 16 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2001-12-01 | 381548 | -36480.18 | 345067.82 | 345068 | 100% | -0.18 | 0 | 0 | 49601.24 | -4743.2334 | 44858.03 | -0.0234 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industrias de Refrigeracion Comercial S.A. (Indufrial) | Individual | LAC | COL | REF | 15 | INV | 11 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-10-01 | 2000-12-01 | 442644 | -8866 | 433778 | 433778 | 100% | 0 | 0 | 0 | 57543.72 | -1152.72 | 56391 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Omega, S.A. | Individual | LAC | COS | REF | 27 | INV | 17 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 159883 | 0 | 159883 | 159883 | 100% | 0 | 0 | 0 | 20785 | 0 | 20785 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Hermanos González, S.A. | Individual | LAC | COS | REF | 27 | INV | 19 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-04-01 | 185168 | 0 | 185168 | 185168 | 100% | 0 | 0 | 0 | 24072 | 0 | 24072 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Wimmer Hnos., S.A. | Individual | LAC | COS | REF | 27 | INV | 18 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 186217 | 0 | 186217 | 186217 | 100% | 0 | 0 | 0 | 24208 | 0 | 24208 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Umbrella project for elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Empco-Mincin and Segere-Sime "Dionisio Rodrigues" | Individual | LAC | CUB | REF | 23 | INV | 06 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-06-01 | 2002-03-01 | 119505 | -9086 | 110419 | 110419 | 100% | 0 | 0 | 0 | 15535.65 | -1180.65 | 14355 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Industria Continental, C.A. by replacement with HCFC-141b and HFC 134a respectively | Individual | LAC | DOM | REF | 25 | INV | 16 | A | I | CFC | 19.9 | 19.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-03-01 | 303200 | -2802 | 300398 | 300398 | 100% | 0 | 0 | 0 | 39416 | -364 | 39052 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Metalgas S.A. by replacement with HCFC-141b and HFC-134a respectively | Individual | LAC | DOM | REF | 24 | INV | 11 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 1999-12-01 | 2001-12-01 | 316368 | -3741 | 312627 | 312627 | 100% | 0 | 0 | 0 | 41127.84 | -485.84 | 40642 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Fabrica de Refrigeradores Comerciales, C.A. (Farco) | Individual | LAC | DOM | REF | 22 | INV | 09 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-11-01 | 2000-07-01 | 423209 | -2883 | 420326 | 420326 | 100% | 0 | 0 | 0 | 55017.17 | -375.17 | 54642 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at El-Mohandes | Individual | AFR | EGY | REF | 20 | INV | 58 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 2000-06-01 | Investment
FIN | UNDP | Conversion to CFC free-technology Reftruck Company | Individual | AFR | EGY | REF | 12 | INV | 30 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1998-09-01 | 2002-11-01 | 385000 | -2692 | 382308 | 382308 | 100% | 0 | 0 | 0 | 50050 | -350 | 49700 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refcat Compnay Inc. | Individual | AFR | EGY | REF | 18 | INV | 50 | A | I | CFC | 26.8 | 26.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 2000-12-01 | 409000 | -18.76 | 408981.24 | 408981 | 100% | 0.24 | 0 | 0 | 53170 | -2.9988 | 53166.97 | 0.0312 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at United Investment Corporation Inc. | Individual | AFR | EGY | REF | 18 | INV | 49 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1999-11-01 | 2003-11-01 | 493350 | -32495 | 460855 | 460855 | 100% | 0 | 0 | 0 | 64135.5 | -4223.5 | 59912 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Port Said Metal Work, Co. (MOG) | Individual | AFR | EGY | REF | 15 | INV | 45 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1999-10-01 | 2003-02-01 | 484000 | 0 | 484000 | 484000 | 100% | 0 | 0 | 0 | 62920 | 0 | 62920 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Royal Engineering, Co. | Individual | AFR | EGY | REF | 15 | INV | 44 | A | I | CFC | 20.3 | 20.3 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 539000 | -1790 | 537210 | 537210 | 100% | 0 | 0 | 0 | 70070 | -232.9992 | 69837.0008 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Misr Panel (Egyptian Company for Cold Storage Industries) | Individual | AFR | EGY | REF | 12 | INV | 31 | A | I | CFC | 74.4 | 74.4 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2001-03-01 | 2002-03-01 | 636000 | 0 | 636000 | 636000 | 100% | 0 | 0 | 0 | 82680 | 0 | 82680 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industria Metalurgica Centroamericana S.A. (Imca) | Individual | LAC | GUA | REF | 15 | INV | 07 | A | I | CFC | 4 | 4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-07-01 | 2000-07-01 | 155017 | -5823 | 149194 | 149194 | 100% | 0 | 0 | 0 | 20152.21 | -757.21 | 19395 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at four enterprises (Exea S.A., Productos American Vitas S.A., Termomecanica S.A., Unirefri S.A.) | Individual | LAC | GUA | REF | 23 | INV | 16 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2002-03-01 | 212000 | -24132 | 187868 | 187868 | 100% | 0 | 0 | 0 | 27560 | -3137 | 24423 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Refrigeradores de Guatemala S.A. (Refrigua) | Individual | LAC | GUA | REF | 15 | INV | 08 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1996-10-01 | 1999-12-01 | 194866 | 0 | 194866 | 194866 | 100% | 0 | 0 | 0 | 25333 | 0 | 25333 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Leoindo Kreasi | Individual | ASP | IDS | REF | 35 | INV | 134 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 119394 | -4838 | 114556 | 114556 | 100% | 0 | 0 | 0 | 15521.22 | -629.22 | 14892 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at C.V. Kulkasindo | Individual | ASP | IDS | REF | 23 | INV | 66 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 136000 | -18593.63 | 117406.37 | 117406 | 100% | 0.37 | 0 | 0 | 17680 | -2417.0019 | 15262.95 | 0.048101 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Alfa Metalindo Agra | Individual | ASP | IDS | REF | 35 | INV | 135 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 146960 | -3500 | 143460 | 143460 | 100% | 0 | 0 | 0 | 19104.8 | -454.8 | 18650 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Supply conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Gaya Teknik | Individual | ASP | IDS | REF | 25 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-12-01 | 147880 | -2358 | 145522 | 145522 | 100% | 0 | 0 | 0 | 19224.4 | -306.4 | 18918 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Hatindo Metal Utama | Individual | ASP | IDS | REF | 35 | INV | 133 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2006-10-01 | 145894 | 0 | 145894 | 145894 | 100% | 0 | 0 | 0 | 18966 | 0 | 18966 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Tesaguna Sejati | Individual | ASP | IDS | REF | 26 | INV | 99 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 147900 | 0 | 147900 | 147900 | 100% | 0 | 0 | 0 | 19227 | 0 | 19227 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Sapporo Mestika | Individual | ASP | IDS | REF | 35 | INV | 132 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 153768 | -4603 | 149165 | 149165 | 100% | 0 | 0 | 0 | 19989.84 | -597.84 | 19392 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Aneka Froze Citratama | Individual | ASP | IDS | REF | 25 | INV | 90 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 174255 | -17790 | 156465 | 156465 | 100% | 0 | 0 | 0 | 22653.15 | -2313.15 | 20340 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, CFC-12 to HFC-134a and R-502 to R-404A technology in the manufacture of commercial refrigeration equipment at PT Algron | Individual | ASP | IDS | REF | 26 | INV | 105 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-11-01 | 158210 | 0 | 158210 | 158210 | 100% | 0 | 0 | 0 | 20567 | 0 | 20567 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of CFC-11 and CFC-12/R-502 to HCFC-141b (foam) and HFC-134a/R404a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at P.T. Intermas Pacific | Individual | ASP | IDS | REF | 25 | INV | 92 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 209300 | -20993 | 188307 | 188307 | 100% | 0 | 0 | 0 | 27209 | -2729 | 24480 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Gastro Gizi Sarana | Individual | ASP | IDS | REF | 35 | INV | 136 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 221049 | -6055 | 214994 | 214994 | 100% | 0 | 0 | 0 | 28736.37 | -787.37 | 27949 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Nikoteknik | Individual | ASP | IDS | REF | 35 | INV | 131 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 238903 | -19314 | 219589 | 219589 | 100% | 0 | 0 | 0 | 31057.39 | -2511.39 | 28546 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 3 enterprises: Bali Cool, Centrum Cool and Ever Cool | Individual | ASP | IDS | REF | 26 | INV | 104 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 231800 | -1729 | 230071 | 230071 | 100% | 0 | 0 | 0 | 30134 | -225 | 29909 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Herry Alter's | Individual | ASP | IDS | REF | 26 | INV | 102 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 438060 | -15658 | 422402 | 422402 | 100% | 0 | 0 | 0 | 56947.8 | -2035.8 | 54912 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ice-Make Refrigeration | Individual | ASP | IND | REF | 35 | INV | 340 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-12-01 | 157305 | -1232 | 156073 | 156073 | 100% | 0 | 0 | 0 | 20449.65 | -159.65 | 20290 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Konark Refrigeration Appliances P., Ltd. | Individual | ASP | IND | REF | 35 | INV | 341 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-09-01 | 182684 | -1327 | 181357 | 181357 | 100% | 0 | 0 | 0 | 23748.92 | -172.92 | 23576 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sandlas Air-Con Systems P. Ltd. | Individual | ASP | IND | REF | 32 | INV | 282 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 228517 | -9527 | 218990 | 218990 | 100% | 0 | 0 | 0 | 29707.21 | -1239.21 | 28468 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Fedders Lloyd Corporation Ltd. | Individual | ASP | IND | REF | 31 | INV | 257 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 257428 | -2616 | 254812 | 254812 | 100% | 0 | 0 | 0 | 33465.64 | -339.64 | 33126 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of commercial refrigeration equipment at 5 enterprises (Ahmedabad Low Temp, Kalkura Cooling Machines, Mechelec Steel Products, Polfrost Aircon and Shri Ambica Engineering) | Individual | ASP | IND | REF | 34 | INV | 323 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-11-01 | 2005-11-01 | 323627 | -7398 | 316229 | 316229 | 100% | 0 | 0 | 0 | 42071.51 | -961.51 | 41110 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 35 | INV | 342 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2007-03-01 | 726448 | -9086 | 717362 | 717362 | 100% | 0 | 0 | 0 | 89909.28 | -999.28 | 88910 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at fourteen enterprises | Individual | ASP | IND | REF | 35 | INV | 339 | A | I | CFC | 68 | 68 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2003-11-01 | 2005-10-01 | 960097 | -5024.0037 | 955072.9963 | 955073 | 100% | -0.0037 | 0 | 0 | 115610.7 | -552.6704 | 115058.03 | -0.00044574 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ojan Cooling Industries | Individual | ASP | IRA | REF | 34 | INV | 99 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2004-01-01 | 110863 | 0 | 110863 | 110863 | 100% | 0 | 0 | 0 | 14412 | 0 | 14412 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Part | Individual | ASP | IRA | REF | 34 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2005-10-01 | 114770 | 0 | 114770 | 114770 | 100% | 0 | 0 | 0 | 14920 | 0 | 14920 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | Individual | ASP | IRA | REF | 35 | INV | 131 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 116646 | -327 | 116319 | 116319 | 100% | 0 | 0 | 0 | 15163.98 | -42.98 | 15121 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 140 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 125244 | 0 | 125244 | 125244 | 100% | 0 | 0 | 0 | 16282 | 0 | 16282 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Khozestan Technique Co. | Individual | ASP | IRA | REF | 29 | INV | 58 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-04-01 | 132041 | -1 | 132040 | 132040 | 100% | 0 | 0 | 0 | 17165 | 0 | 17165 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at MH Seyed Salaki Co. | Individual | ASP | IRA | REF | 31 | INV | 68 | A | I | CFC | 9.8 | 9.8 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 141590 | 0 | 141590 | 141590 | 100% | 0 | 0 | 0 | 18407 | 0 | 18407 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Mehran Sard, Co. | Individual | ASP | IRA | REF | 35 | INV | 135 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 144715 | -1096.9978 | 143618.0022 | 143618 | 100% | 0.0022 | 0 | 0 | 18812.95 | -142.9501 | 18669.9996 | 0.00028599 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardkaran Industrial Manufacturing Co. | Individual | ASP | IRA | REF | 29 | INV | 56 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2002-03-01 | 2003-11-01 | 155405 | -6082 | 149323 | 149323 | 100% | 0 | 0 | 0 | 20202.65 | -790.65 | 19412 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fereidooni Refrigerant Industries | Individual | ASP | IRA | REF | 31 | INV | 71 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-11-01 | 157454 | 0 | 157454 | 157454 | 100% | 0 | 0 | 0 | 20469 | 0 | 20469 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Electro Sard Azna Co,. | Individual | ASP | IRA | REF | 29 | INV | 60 | A | I | CFC | 18.7 | 18.7 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 191061 | -33421 | 157640 | 157640 | 100% | 0 | 0 | 0 | 24837.93 | -4344.93 | 20493 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Boroudati Maleki | Individual | ASP | IRA | REF | 35 | INV | 138 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2006-06-01 | 215052 | -178 | 214874 | 214874 | 100% | 0 | 0 | 0 | 27956.76 | -22.76 | 27934 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Havasaz Manufacturing and Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 134 | A | I | CFC | 24.5 | 24.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 252294 | -19021.0026 | 233272.9974 | 233273 | 100% | -0.0026 | 0 | 0 | 32798.22 | -2473.2138 | 30325.0066 | -0.00033799 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Fan, Co. | Individual | ASP | IRA | REF | 35 | INV | 139 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-10-01 | 267075 | -26729.0015 | 240345.9985 | 240346 | 100% | -0.0015 | 0 | 0 | 34719.75 | -3474.7452 | 31245.005 | -0.000195 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fadak Refrigeration Industries | Individual | ASP | IRA | REF | 31 | INV | 66 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-11-01 | 2003-11-01 | 258937 | 0 | 258937 | 258937 | 100% | 0 | 0 | 0 | 33662 | 0 | 33662 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Tahvieh Garm va Sard Co. | Individual | ASP | IRA | REF | 28 | INV | 44 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-02-01 | 278659 | -13367 | 265292 | 265292 | 100% | 0 | 0 | 0 | 36225.67 | -1737.67 | 34488 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 tgo HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Electro Shargh Mazandaran Co. | Individual | ASP | IRA | REF | 29 | INV | 55 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 301715 | -31900 | 269815 | 269815 | 100% | 0 | 0 | 0 | 39222.95 | -4146.95 | 35076 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial and domestic refrigeration equipment at Jaleh & Segin Co. | Individual | ASP | IRA | REF | 31 | INV | 67 | A | I | CFC | 23.6 | 23.6 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 322309 | 0 | 322309 | 322309 | 100% | 0 | 0 | 0 | 41900 | 0 | 41900 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Foroughmanesh Co. | Individual | ASP | IRA | REF | 28 | INV | 43 | A | I | CFC | 35.8 | 35.8 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 399803 | -13456 | 386347 | 386347 | 100% | 0 | 0 | 0 | 51974.39 | -1749.39 | 50225 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HCFC-134a technology in the manufacture of commercial refrigeration equipment at Behsarma Co. | Individual | ASP | IRA | REF | 28 | INV | 65 | A | I | CFC | 34.5 | 34.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 455593 | -13588 | 442005 | 442005 | 100% | 0 | 0 | 0 | 59227.09 | -1766.09 | 57461 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Movaledsarma Co. (Zagross 1) | Individual | ASP | IRA | REF | 28 | INV | 46 | A | I | CFC | 77.6 | 77.6 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2004-01-01 | 816698 | -12094.36 | 804603.64 | 804604 | 100% | -0.36 | 0 | 0 | 99836.78 | -1330.7796 | 98506.0445 | -0.044074 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Farjallah Co. | Individual | ASP | LEB | REF | 29 | INV | 34 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-07-01 | 200046 | 0 | 200046 | 200046 | 100% | 0 | 0 | 0 | 26006 | 0 | 26006 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and R502 consumption at Thermo Cooling Engineering, Sdn. Bhd. | Individual | ASP | MAL | REF | 28 | INV | 126 | A | I | CFC | 5.9 | 5.9 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 46502 | -1900 | 44602 | 44602 | 100% | 0 | 0 | 0 | 6045.26 | -247.26 | 5798 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at Lian Pang Refrigerator and Electrical Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 45 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-07-01 |  | 1998-10-01 | 2003-09-01 | 201100 | -1 | 201099 | 201099 | 100% | 0 | 0 | 0 | 26143 | 1.0186e-12 | 26143 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufature of polyurethane foam at Kwang Tai Refrigeration | Individual | ASP | MAL | REF | 23 | INV | 103 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-04-01 | 316000 | -9988 | 306012 | 306012 | 100% | 0 | 0 | 0 | 41080 | -1298 | 39782 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 and R-502 in the manufacture of commercial refrigerators by conversion HCFC-141b, HCFC-22 and HFC-404a at Gai Hin Refrigeration Sdn. Bhd. | Individual | ASP | MAL | REF | 29 | INV | 128 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 354147 | -16712 | 337435 | 337435 | 100% | 0 | 0 | 0 | 46039.11 | -2173.11 | 43866 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at United Refrigerator Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 37 | A | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-12-01 | 2003-07-01 | 351200 | -11852 | 339348 | 339348 | 100% | 0 | 0 | 0 | 45656 | -1541 | 44115 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at three enterprises (SKE Fookmei, Master Shanghai Turnparts and Maltar Industries) | Individual | ASP | MAL | REF | 32 | INV | 141 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-11-01 | 2005-09-01 | 505184 | -12891 | 492293 | 492293 | 100% | 0 | 0 | 0 | 65570.24 | -1418.24 | 64152 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Umbrella project for elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration at 4 small enterprises: Lim Yew, Exquisite, FMC, Noblelane | Individual | ASP | MAL | REF | 18 | INV | 73 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2001-12-01 | 2003-04-01 | 680000 | -49438 | 630562 | 630562 | 100% | 0 | 0 | 0 | 88400 | -6427 | 81973 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1997-10-01 | Investment
FIN | UNDP | Terminal umbrella project to phase out CFC-11 and CFC-12 consumption in the manufacture of commercial refrigeration equipment by replacement with HCFC-141b and HFC-134a at 11 SMEs | Individual | LAC | PAR | REF | 34 | INV | 12 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2005-02-01 |  | 2005-12-01 | 2007-03-01 | 410379 | -27448 | 382931 | 382931 | 100% | 0 | 0 | 0 | 53349.27 | -3568.2719 | 49780.9981 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Master Service, S.A. | Individual | LAC | PER | REF | 19 | INV | 13 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-02-01 | 2002-04-01 | 140000 | -10839 | 129161 | 129161 | 100% | 0 | 0 | 0 | 18200 | -1409 | 16791 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Col-Frio S.A. | Individual | LAC | PER | REF | 19 | INV | 16 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 175000 | -468 | 174532 | 174532 | 100% | 0 | 0 | 0 | 22750 | -60.9988 | 22689.0012 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest feezers at Compañia Peruana de Máquinas para Coser S.A. (Copemaco) | Individual | LAC | PER | REF | 19 | INV | 14 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 193834 | 0 | 193834 | 193834 | 100% | 0 | 0 | 0 | 25198 | 0 | 25198 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Umbrella project for conversion from CFC-11 foam blowing agent into HCFC-141b, and CFC-12 and R-502 refrigerants into HFC-134a and HFC-404a at Gomeco, Chee Puck and Well Built | Individual | ASP | PHI | REF | 19 | INV | 44 | N | I | CFC | 28 | 28 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1998-04-01 |  | 2000-09-01 | 2003-04-01 | 156475 | -38769 | 117706 | 117706 | 100% | 0 | 0 | 0 | 20341.75 | -5039.75 | 15302 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of commercial refrigerators and ice boxes at Unimagna Philippines, Inc. | Individual | ASP | PHI | REF | 13 | INV | 33 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 1015700 | -54324 | 961376 | 961376 | 100% | 0 | 0 | 0 | 132041 | -7062 | 124979 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Individual | ASP | SYR | REF | 35 | INV | 81 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2001-12-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2006-06-01 | 166323 | -8826 | 157497 | 157497 | 100% | 0 | 0 | 0 | 21621.99 | -1147 | 20474.99 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Raed Refrigeration | Individual | ASP | SYR | REF | 32 | INV | 69 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-09-01 | 2005-11-01 | 211800 | 0 | 211800 | 211800 | 100% | 0 | 0 | 0 | 27534 | 0 | 27534 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Refrigeration House Co. | Individual | ASP | SYR | REF | 34 | INV | 79 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 2001-07-01 | 2002-11-01 | 2004-08-01 |  | 2003-09-01 | 2007-01-01 | 253653 | 0 | 253653 | 253653 | 100% | 0 | 0 | 0 | 32974.89 | 0 | 32974.89 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Ihsan Co. | Individual | ASP | SYR | REF | 28 | INV | 46 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-01-01 | 2003-05-01 | 497250 | -16958 | 480292 | 480292 | 100% | 0 | 0 | 0 | 64642.5 | -2204.5 | 62438 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigerarion equipment at seven enterprises | Individual | ASP | SYR | REF | 29 | INV | 52 | A | I | CFC | 51.9 | 51.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2003-08-01 | 2005-09-01 | 743419 | -20056 | 723363 | 723363 | 100% | 0 | 0 | 0 | 91776.09 | -2206.09 | 89570 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Elimination in the use of CFC in the manufacture of commercial refrigerators at Sanden Refrigerator Co. Ltd. | Individual | ASP | THA | REF | 13 | INV | 33 | A | I | CFC | 21 | 21 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1998-06-01 | 1999-12-01 | 533800 | 0 | 533800 | 533800 | 100% | 0 | 0 | 0 | 69394 | 0 | 69394 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -454.74 | 14118.26 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16070.99 | 0 | 16070.99 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1995 | 2000-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -378.83 | 161996.17 | 161996 | 100% | 0.17 | 0 | 0 | 21108.75 | -49.2479 | 21059.48 | 0.0221 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -337.87 | 24362.13 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387.16 | 47887.84 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | AFR | ALG | REF | 37 | INV | 56 | A | I | CFC | 18.6 | 18.6 |  |  | 2002-07-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2006-12-01 | 224320 | -22701 | 201619 | 201618.86 | 100% | 0.14 | 0 |  | 29162 | -2952 | 26210 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | Individual | AFR | ALG | REF | 32 | INV | 47 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-07-01 | 2003-05-01 |  | 2003-12-01 | 2004-12-01 | 351768 | -5863 | 345905 | 345904.94 | 100% | 0.06 | 0 |  | 45730 | -834 | 44896 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerants CFC-12 and R-502 with HFC-134a and R-404A, and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment and cold refrigeration chambers at Soko | Individual | EUR | BHE | REF | 35 | INV | 10 | A | I | CFC | 17.4 | 17.4 |  |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-05-01 | 159707 | -818 | 158889 | 158888.79 | 100% | 0.21 | 0 |  | 20762 | -139 | 20623 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a, CFC-11 with HCFC-141b, and TCA with non-cleaning process in the manufacture of commercial refrigeration equipment, panels, and heat exchangers at three enterprises (Soko Paneli, Soko IPV and Kuca Leda) | Individual | EUR | BHE | REF | 39 | INV | 14 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 2003-04-01 | 2003-11-01 | 2004-07-01 |  | 2005-12-01 | 2007-09-01 | 175283 | -5869 | 169414 | 169413.92 | 100% | 0.08 | 0 |  | 15775 | -528 | 15247 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Domnick Hunter Ltda. | Individual | LAC | BRA | REF | 31 | INV | 177 | A | I | CFC | 1.2 | 1.2 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 17971 | 0 | 17971 | 17971 | 100% | 0 | 0 |  | 2336 | 0 | 2336 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Ingecold Ltda. | Individual | LAC | BRA | REF | 31 | INV | 170 | A | I | CFC | 1.7 | 1.7 |  |  | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 25320 | -20 | 25300 | 25300.02 | 100% | -0.02 | 0 |  | 3292 | -8 | 3284 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Metalplan Ltda. | Individual | LAC | BRA | REF | 31 | INV | 176 | A | I | CFC | 1.9 | 1.9 |  |  | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 28885 | 0 | 28885 | 28885.21 | 100% | -0.21 | 0 |  | 3755 | -3 | 3752 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Klima Ltda. | Individual | LAC | BRA | REF | 31 | INV | 171 | A | I | CFC | 5.7 | 5.7 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 86464 | -13509 | 72955 | 72955.26 | 100% | -0.26 | 0 |  | 11240 | -1771 | 9469 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project for two enterprises converting from CFC-11 and HCFC-141b and from CFC-12 to HFC-134a at Argi and Hornburg | Individual | LAC | BRA | REF | 35 | INV | 241 | A | I | CFC | 11.2 | 11.2 |  |  | 2001-12-01 | 2002-11-01 | 2004-05-01 |  | 2004-10-01 | 2005-05-01 | 108050 | -12441 | 95609 | 95608.63 | 100% | 0.37 | 0 |  | 14047 | -1638 | 12409 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-12 and R-502 with HFC-134a and HFC-404A as well as of CFC-11 with HCFC-141 at Kalten Ltd. | Individual | LAC | BRA | REF | 31 | INV | 174 | A | I | CFC | 8.1 | 8.1 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2004-04-01 | 2004-09-01 | 122151 | -6158 | 115993 | 115993.1 | 100% | -0.1 | 0 |  | 15880 | -825 | 15055 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134A and CFC-11 with HFC-141b at five commercial refrigeration companies (Arparna, Begel, Belliere, Genaredx and Katz Refrigeracao) (umbrella project) | Individual | LAC | BRA | REF | 28 | INV | 139 | A | I | CFC | 26 | 26 |  |  | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 485916 | -115476 | 370440 | 370440.15 | 100% | -0.15 | 0 |  | 63169 | -15088 | 48081 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project for four enterprises converting from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a at EZ Industria, Menoncin, Unifrio and from CFC-12 to HFC-134a at Croydon | Individual | LAC | BRA | REF | 34 | INV | 219 | A | I | CFC | 30.18 | 30.18 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-04-01 | 2004-12-01 | 469452 | -94888 | 374564 | 374564.24 | 100% | -0.24 | 0 |  | 61029 | -12413 | 48616 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-12 by HFC-134a as refrigerant and CFC-11 by cyclopentane as foam blowing agent in commercial refrigeration equipment for supermarkets at Eletrofrio S/A | Individual | LAC | BRA | REF | 20 | INV | 54 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-07-01 | 1998-10-01 |  | 1999-12-01 | 2001-12-01 | 610650 | 0 | 610650 | 610650.1 | 100% | -0.1 | 0 |  | 79385 | -63 | 79322 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at P.T. Jalur Sejuk | Individual | ASP | IDS | REF | 22 | INV | 59 | A | I | CFC | 30.85 | 30.85 |  |  | 1997-05-01 | 1997-09-01 | 1998-11-01 |  | 1999-06-01 | 2001-07-01 | 171470 | 0 | 171470 | 171470 | 100% | 0 | 0 |  | 22291 | -17 | 22274 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out of ODS at P.T. Air Tech. Co. Ltd. | Individual | ASP | IDS | REF | 18 | INV | 35 | A | I | CFC | 30.1 | 30.1 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-05-01 | 409850 | 0 | 409850 | 409850 | 100% | 0 | 0 |  | 53281 | 0 | 53281 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | Individual | ASP | IND | REF | 32 | INV | 290 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-01-01 | 2003-02-01 |  | 2004-08-01 | 2005-09-01 | 328894 | -49284 | 279610 | 279609.93 | 100% | 0.07 | 0 |  | 42756 | -6464 | 36292 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Sherkate Taavoni 435 (Khorsandi Co.) | Individual | ASP | IRA | REF | 35 | INV | 122 | A | I | CFC | 5.4 | 5.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 82107 | -1871 | 80236 | 80236.24 | 100% | -0.24 | 0 |  | 10674 | -260 | 10414 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Gostar Co. | Individual | ASP | IRA | REF | 35 | INV | 130 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 100384 | -3803 | 96581 | 96580.99 | 100% | 0.01 | 0 |  | 13050 | -514 | 12536 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the Takran Mobbarad Co. | Individual | ASP | IRA | REF | 34 | INV | 98 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 119864 | -2915 | 116949 | 116948.51 | 100% | 0.49 | 0 |  | 15582 | -403 | 15179 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sard Va Garm | Individual | ASP | IRA | REF | 35 | INV | 128 | A | I | CFC | 8.4 | 8.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 125350 | -4570 | 120780 | 120779.6 | 100% | 0.4 | 0 |  | 16296 | -619 | 15677 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Novin Enjemad | Individual | ASP | IRA | REF | 34 | INV | 105 | A | I | CFC | 10.1 | 10.1 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 138702 | -1665 | 137037 | 137037.35 | 100% | -0.35 | 0 |  | 18031 | -244 | 17787 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Darvish Mohamad Nazari Company (Jahan Nama) | Individual | ASP | IRA | REF | 35 | INV | 126 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-05-01 | 139970 | -140 | 139830 | 139830.4 | 100% | -0.4 | 0 |  | 18196 | -47 | 18149 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Abbaspour Co. | Individual | ASP | IRA | REF | 35 | INV | 119 | A | I | CFC | 9.7 | 9.7 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 144206 | -741 | 143465 | 143464.74 | 100% | 0.26 | 0 |  | 18747 | -126 | 18621 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardintous Co. | Individual | ASP | IRA | REF | 35 | INV | 129 | A | I | CFC | 10.3 | 10.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 145879 | -281 | 145598 | 145597.6 | 100% | 0.4 | 0 |  | 18964 | -66 | 18898 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Gasso Co. | Individual | ASP | IRA | REF | 34 | INV | 113 | A | I | CFC | 11.7 | 11.7 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 158232 | -4811 | 153421 | 153421.46 | 100% | -0.46 | 0 |  | 20570 | -657 | 19913 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Avaj Sarma Co. | Individual | ASP | IRA | REF | 34 | INV | 108 | A | I | CFC | 15.2 | 15.2 |  |  | 2001-07-01 | 2001-11-01 | 2004-08-01 |  | 2004-06-01 | 2005-08-01 | 176477 | -534 | 175943 | 175943.3 | 100% | -0.3 | 0 |  | 22942 | -106 | 22836 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Donyaye Mojdeh | Individual | ASP | IRA | REF | 34 | INV | 103 | A | I | CFC | 15.4 | 15.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2004-09-01 | 191020 | -2225 | 188795 | 188794.71 | 100% | 0.29 | 0 |  | 24833 | -329 | 24504 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Roshan Ind. Group | Individual | ASP | IRA | REF | 34 | INV | 107 | A | I | CFC | 18.6 | 18.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 203960 | -5201 | 198759 | 198759.1 | 100% | -0.1 | 0 |  | 26515 | -717 | 25798 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Zarifan Mashad | Individual | ASP | IRA | REF | 34 | INV | 104 | A | I | CFC | 22 | 22 |  |  | 2001-07-01 | 2002-03-01 | 2003-12-01 |  | 2004-06-01 | 2005-12-01 | 200550 | -1183 | 199367 | 199367.16 | 100% | -0.16 | 0 |  | 26072 | -195 | 25877 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Tehran Shirak | Individual | ASP | IRA | REF | 34 | INV | 101 | A | I | CFC | 20.5 | 20.5 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2005-09-01 | 202836 | -1649 | 201187 | 201186.61 | 100% | 0.39 | 0 |  | 26369 | -256 | 26113 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 111 | A | I | CFC | 27.4 | 27.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2005-06-01 | 2006-09-01 | 209425 | -304 | 209121 | 209121.07 | 100% | -0.07 | 0 |  | 27225 | -39 | 27186 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at Sobouhi Refrigeration | Individual | ASP | IRA | REF | 26 | INV | 35 | A | I | CFC | 30.4 | 30.4 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 237847 | -23768 | 214079 | 214078.79 | 100% | 0.21 | 0 |  | 30920 | -3134 | 27786 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b AND cfc-12 TO hfc-134A in commercial refrigeration at the second group of Iranian Commercial Refrigeration Manufacturers | Individual | ASP | IRA | REF | 28 | INV | 45 | A | I | CFC | 42.5 | 42.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-09-01 | 309966 | -1621 | 308345 | 308345.18 | 100% | -0.18 | 0 |  | 40296 | -275 | 40021 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Broudati Ghandil Iran (Ghandil Co.) | Individual | ASP | IRA | REF | 28 | INV | 47 | A | I | CFC | 27.5 | 27.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 335423 | -3923 | 331500 | 331499.51 | 100% | 0.49 | 0 |  | 43605 | -578 | 43027 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and domestic refrigeration at the Sherkate Sanayee Emerson (Emerson Co). | Individual | ASP | IRA | REF | 28 | INV | 42 | A | I | CFC | 45.8 | 45.8 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-05-01 | 343873 | -10039 | 333834 | 333833.93 | 100% | 0.07 | 0 |  | 44703 | -1373 | 43330 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at Sanayee Broudati Partou Sard Tawan (Barez-Himalia) and Sanayee Broudati Himalia (Himalia) | Individual | ASP | IRA | REF | 31 | INV | 69 | A | I | CFC | 36.09 | 36.09 |  |  | 2000-07-01 | 2000-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-06-01 | 377544 | -3754 | 373790 | 373789.7 | 100% | 0.3 | 0 |  | 49081 | -565 | 48516 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Zagross II Co. | Individual | ASP | IRA | REF | 23 | INV | 28 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 444858 | -3734 | 441124 | 441123.94 | 100% | 0.06 | 0 |  | 57832 | -577 | 57255 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Saran Co. | Individual | ASP | IRA | REF | 23 | INV | 26 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 2002-06-01 | 2003-10-01 | 458663 | -2976 | 455687 | 455687.08 | 100% | -0.08 | 0 |  | 59626 | -481 | 59145 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Chavan Manufacturing Company | Individual | ASP | IRA | REF | 23 | INV | 25 | A | I | CFC | 41.8 | 41.8 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-03-01 | 527802 | 0 | 527802 | 527801.81 | 100% | 0.19 | 0 |  | 68614 | 0 | 68614 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b in manufacture of commercial refrigeration equipment at Yazd Arg Metal, Yazd Sardin and Shervin Electric | Individual | ASP | IRA | REF | 26 | INV | 37 | A | I | CFC | 62.2 | 62.2 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2003-02-01 | 743990 | -95365 | 648625 | 648625.39 | 100% | -0.39 | 0 |  | 91839 | -10603 | 81236 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Electro Steel Co. | Individual | ASP | IRA | REF | 23 | INV | 24 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 898159 | -20754 | 877405 | 877404.93 | 100% | 0.07 | 0 |  | 116761 | -2879 | 113882 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Abdin Industrial Est.Co. | Individual | ASP | JOR | REF | 20 | INV | 29 | A | I | CFC | 10.4 | 21.5 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1997-12-01 | 2000-07-01 | 116928 | -636 | 116292 | 116292 | 100% | 0 | 0 |  | 15201 | -107 | 15094 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Third Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 52 | A | I | CFC | 16.8 | 17.74 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 243764 | -79664 | 164100 | 164100.37 | 100% | -0.37 | 0 |  | 31689 | -10390 | 21299 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacturing commercial refrigeration equipment at 5th group of SMEs (Abdoulah Factory, Emad Addin Al- Sareegy, Ma-nna, Al-Mansour, Al-Ostath, Raed) | Individual | ASP | JOR | REF | 34 | INV | 74 | A | I | CFC | 26 | 26 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 244954 | -5781 | 239173 | 239173.25 | 100% | -0.25 | 0 |  | 31844 | -801 | 31043 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigertion equipment at Al-Arghawin & Marka commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 29 | INV | 55 | A | I | CFC | 27.4 | 27.4 |  |  | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 255203 | -9070 | 246133 | 246133.04 | 100% | -0.04 | 0 |  | 33176 | -1229 | 31947 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at Fourth Group of small size Jordanian Commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 31 | INV | 66 | A | I | CFC | 23.1 | 23.07 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 270034 | -18831 | 251203 | 251203.16 | 100% | -0.16 | 0 |  | 35104 | -2499 | 32605 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Second Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 62 | A | I | CFC | 25.8 | 25.8 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2000-08-01 | 2002-09-01 | 278950 | -2424 | 276526 | 276526.2 | 100% | -0.2 | 0 |  | 36264 | -373 | 35891 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at 6th group of SMEs (Abu-Khalaf, Al-Taghwa, Farough Refrigeration, Dawudiah Workshop, Makka Refrigeration and Teck-Tack workshop) | Individual | ASP | JOR | REF | 34 | INV | 72 | A | I | CFC | 24.4 | 24.4 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 286523 | -5667 | 280856 | 280856.08 | 100% | -0.08 | 0 |  | 37248 | -795 | 36453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at six Jordanian companies | Individual | ASP | JOR | REF | 26 | INV | 42 | A | I | CFC | 25.1 | 25.1 |  |  | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 1999-12-01 | 2002-09-01 | 305764 | -4822 | 300942 | 300941.61 | 100% | 0.39 | 0 |  | 39749 | -689 | 39060 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in manufacture of commercial refrigeration equipment at Maurice al-Deek Co. | Individual | ASP | JOR | REF | 26 | INV | 43 | A | I | CFC | 25.7 | 25.7 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 336233 | -7042 | 329191 | 329191.08 | 100% | -0.08 | 0 |  | 43710 | -983 | 42727 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in the production of commercial refrigeration equipment at the second medium-size commercial refrigerator manufacturers group (Abu Azmi, Hasouni Refrigeration and Majdi) | Individual | ASP | JOR | REF | 34 | INV | 71 | A | I | CFC | 26.4 | 26.4 |  |  | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-07-01 | 2005-09-01 | 342652 | -5429 | 337223 | 337222.65 | 100% | 0.35 | 0 |  | 44545 | -776 | 43769 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in production commercial refrigeration equipment at the medium size commercial refrigerator manufacturers (Jordan Catering Supplies, El-Shami, and Nedal Raja Al-Dwaik companies) in Jordan | Individual | ASP | JOR | REF | 31 | INV | 65 | A | I | CFC | 34.72 | 34.72 |  |  | 2000-07-01 | 2000-10-01 | 2003-08-01 |  | 2002-12-01 | 2004-09-01 | 469525 | -33258 | 436267 | 436266.87 | 100% | 0.13 | 0 |  | 61038 | -4413 | 56625 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at the Ihsan & Tahseen Baalbaki Co. | Individual | ASP | JOR | REF | 23 | INV | 35 | A | I | CFC | 66.5 | 66.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-06-01 | 2001-12-01 | 545103 | -5327 | 539776 | 539776.26 | 100% | -0.26 | 0 |  | 70863 | -803 | 70060 | 0 | 0 | FIN
FIN | UNIDO | CFC-phase out project at Kenya Cold Storages Ltd. and subsidiary companies: Hall Equatorial, Premier Refrigeration and Engineering, Refrigeration Services | Individual | AFR | KEN | REF | 11 | INV | 06 | A | I | CFC | 40.8 | 40.8 |  |  | 1993-11-01 | 1996-12-01 | 1997-03-01 |  | 1998-12-01 | 2001-07-01 | 380875 | 123140 | 504015 | 504015 | 100% | 0 | 0 |  | 49514 | 15904 | 65418 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the third group of Lebanese commercial refrigerator manufacturers | Individual | ASP | LEB | REF | 31 | INV | 39 | A | I | CFC | 15.8 | 15.8 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 208498 | -8133 | 200365 | 200364.97 | 100% | 0.03 | 0 |  | 27105 | -1099 | 26006 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the second group of Lebanese commercial refrigeration manufacturers | Individual | ASP | LEB | REF | 31 | INV | 36 | A | I | CFC | 15.66 | 15.66 |  |  | 2000-07-01 | 2000-09-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 203191 | -1043 | 202148 | 202147.72 | 100% | 0.28 | 0 |  | 26415 | -177 | 26238 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141B and CFC-12 to HFC-134a in the manufacture of commercial refrigeration at the first group of Lebanese Commercial Refrigerator Manufacturers | Individual | ASP | LEB | REF | 29 | INV | 33 | A | I | CFC | 18.5 | 18.5 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2000-07-01 | 2002-09-01 | 258006 | -8773 | 249233 | 249233.23 | 100% | -0.23 | 0 |  | 33541 | -1192 | 32349 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 4th group of enterprises | Individual | ASP | LEB | REF | 34 | INV | 45 | A | I | CFC | 18.8 | 18.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2004-06-01 | 2005-12-01 | 279672 | -9510 | 270162 | 270161.81 | 100% | 0.19 | 0 |  | 36357 | -1292 | 35065 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigerating equipment at Tung Kiong Factories Sdn. Bhd. | Individual | ASP | MAL | REF | 32 | INV | 143 | A | I | CFC | 18.9 | 18.9 |  |  | 2000-12-01 | 2001-10-01 | 2003-07-01 |  | 2003-03-01 | 2004-05-01 | 202075 | -503 | 201572 | 201571.65 | 100% | 0.35 | 0 |  | 26270 | -107 | 26163 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators at Refrigeracion Duran S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 91 | A | I | CFC | 15.1 | 15.1 |  |  | 2000-03-01 | 2000-09-01 | 2001-10-01 |  | 2002-07-01 | 2003-10-01 | 112985 | 0 | 112985 | 112984.94 | 100% | 0.06 | 0 |  | 14688 | -3 | 14685 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Torrey S.A. | Individual | LAC | MEX | REF | 23 | INV | 68 | A | I | CFC | 15.1 | 15.1 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 228165 | -4430 | 223735 | 223734.8 | 100% | 0.2 | 0 |  | 29661 | -622 | 29039 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Criotec S.A. | Individual | LAC | MEX | REF | 23 | INV | 67 | A | R | CFC | 16 | 16 |  |  | 1997-11-01 | 1998-09-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 240794 | 0 | 240794 | 240794 | 100% | 0 | 0 |  | 31303 | 0 | 31303 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Vendo S.A. | Individual | LAC | MEX | REF | 23 | INV | 74 | A | R | CFC | 16.5 | 16.5 |  |  | 1997-11-01 | 1999-03-01 | 1998-10-01 |  | 1998-12-01 | 1999-07-01 | 248524 | 0 | 248524 | 248524 | 100% | 0 | 0 |  | 32308 | 0 | 32308 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with cyclopentane and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators of Metaplus S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 90 | A | I | CFC | 20.1 | 20.1 |  |  | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-12-01 | 2004-04-01 | 303094 | -1405 | 301689 | 301689.18 | 100% | -0.18 | 0 |  | 39402 | -245 | 39157 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Nieto S.A. | Individual | LAC | MEX | REF | 23 | INV | 70 | A | R | CFC | 24.6 | 24.6 |  |  | 1997-11-01 | 1998-06-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 353976 | 0 | 353976 | 353976 | 100% | 0 | 0 |  | 46017 | 0 | 46017 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Plasticos Tecnicos Mexicanos (PTM) in the manufacture of commercial refrigeration equipment | Individual | LAC | MEX | REF | 25 | INV | 85 | A | I | CFC | 50.6 | 50.6 |  |  | 1998-07-01 | 1998-11-01 | 2000-01-01 |  | 1999-12-01 | 2002-09-01 | 398439 | 0 | 398439 | 398438.59 | 100% | 0.41 | 0 |  | 51797 | -1 | 51796 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Etablissement Lahdar | Individual | AFR | MOR | REF | 35 | INV | 47 | A | I | CFC | 7.4 | 7.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 101451 | -1363 | 100088 | 100087.56 | 100% | 0.44 | 0 |  | 13189 | -198 | 12991 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at First Clim Co. | Individual | AFR | MOR | REF | 35 | INV | 46 | A | I | CFC | 9 | 9 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 135258 | -980 | 134278 | 134277.6 | 100% | 0.4 | 0 |  | 17584 | -156 | 17428 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Climatisation et Froid Loudaya (CFL) | Individual | AFR | MOR | REF | 35 | INV | 45 | A | I | CFC | 15 | 15 |  |  | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 177312 | -847 | 176465 | 176464.91 | 100% | 0.09 | 0 |  | 23051 | -147 | 22904 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Sonyafroid | Individual | AFR | MOR | REF | 29 | INV | 36 | A | I | CFC | 13.1 | 13.1 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 275895 | -2567 | 273328 | 273327.76 | 100% | 0.24 | 0 |  | 35866 | -390 | 35476 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the terminal umbrella group of commercial refrigeration manufactures. | Individual | AFR | MOR | REF | 43 | INV | 50 | A | I | CFC | 18.4 | 18.4 |  |  | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 359864 | 0 | 359864 | 359863.76 | 100% | 0.24 | 0 |  | 26990 | 0 | 26990 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Fogel S.A. in the manufacture of commercial refrigeration equipment | Individual | LAC | NIC | REF | 25 | INV | 05 | A | R | CFC | 9.6 | 9.6 |  |  | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 1999-12-01 | 2001-03-01 | 130027 | 0 | 130027 | 130027 | 100% | 0 | 0 |  | 16904 | -22 | 16882 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration at Austin-Laz & Co. Ltd | Individual | AFR | NIR | REF | 29 | INV | 54 | A | I | CFC | 11.6 | 11.6 |  |  | 1999-11-01 | 2000-10-01 | 2001-06-01 |  | 2002-08-01 | 2003-07-01 | 147181 | 0 | 147181 | 147181 | 100% | 0 | 0 |  | 19134 | 0 | 19134 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Akocen Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 77 | A | I | CFC | 12.1 | 12.1 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2003-10-01 | 157894 | 0 | 157894 | 157894.01 | 100% | -0.01 | 0 |  | 20526 | 0 | 20526 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Coldcare Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 76 | A | I | CFC | 11.4 | 11.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-12-01 | 2003-12-01 | 173200 | 0 | 173200 | 173200 | 100% | 0 | 0 |  | 22516 | 0 | 22516 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs from Manufacturing of domestic and commercial refrigerators at Krayem Brothers Co. | Individual | ASP | SYR | REF | 18 | INV | 11 | A | I | CFC | 89 | 89 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1998-12-01 | 2002-09-01 | 1071575 | -13558 | 1058017 | 1058016.79 | 100% | 0.21 | 0 |  | 139305 | -1981 | 137324 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project to phase out ODS at 7 manufacturers of commercial and domestic refrigerators (Chahed Refrigeration, Sogima, Sotiem, Rei, Frigo BAF, Societe Moderne Refrigeration, Frigo Technique) | Individual | AFR | TUN | REF | 23 | INV | 27 | A | I | CFC | 29 | 29 |  |  | 1997-11-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2001-03-01 | 374111 | -1034 | 373077 | 373077 | 100% | 0 | 0 |  | 48634 | -211 | 48423 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | I | CFC | 32.3 | 32.3 |  |  | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | -84678 | 318912 | 318912.44 | 100% | -0.44 | 0 |  | 52467 | -11074 | 41393 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at five commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 76 | A | I | CFC | 30.9 | 30.9 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64008 | 405132 | 405131.58 | 100% | 0.42 | 0 |  | 60988 | -8404 | 52584 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 and CFC-12 withHCFC-141b and HFC-134a at INVITREL in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | I | CFC | 46.4 | 46.4 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -1714 | 417380 | 417379.62 | 100% | 0.38 | 0 |  | 54482 | -309 | 54173 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 04 | A | I | CFC | 40 | 40 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -2690 | 494380 | 494380 | 100% | 0 | 0 |  | 64619 | -452 | 64167 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | I | CFC | 6.1 | 6.1 |  |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1456 | 88775 | 88774.93 | 100% | 0.07 | 0 |  | 11730 | -208 | 11522 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | I | CFC | 7.3 | 7.3 |  |  | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1328 | 104313 | 104313.09 | 100% | -0.09 | 0 |  | 13733 | -194 | 13539 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | I | CFC | 10.9 | 10.9 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | -1869 | 148240 | 148239.7 | 100% | 0.3 | 0 |  | 19514 | -273 | 19241 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at seven enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | I | CFC | 59.6 | 59.6 |  |  | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -19150 | 736012 | 736012.22 | 100% | -0.22 | 0 |  | 93068 | -2235 | 90833 | 0 | 0 | FIN |  |  |  | INV
ONG | UNDP | Demonstration project for conversion from HCFC-22 technology to HFC-32 technology in the manufacture of commercial air-source chillers/heat pumps at Tsinghua Tong Fang Artifical Environment Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 498 | N | I | HCFC | 3.4 | 2.8 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 | 2013-06-01 |  |  | 1229336 | 0 | 1229336 | 724614.81 | 58.94% | 504721.19 | 0 | 151416.357 | 92200 | 0 | 54345.9929 | 37854.0071 | 0 | Prodoc finalized in December 2010. Project achieved technical completion in June 2012. Enterprise awaiting standards revisions to put products in the market. | Final verification in progress. Project targeted for completion in 2013. | 2010 |  | Investment
ONG | UNDP | Demonstration project for conversion from HCFC-22 technology to Ammonia/CO2 technology in the manufacture of two-stage refrigeration systems for cold storage and freezing applications at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 499 | N | I | HCFC | 13.8 | 13.4 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 | 2013-06-01 |  |  | 3964458 | 0 | 3964458 | 3913798.97 | 98.72% | 50659.03 | 0 | 15197.709 | 297334 | 0 | 293534.5772 | 3799.4228 | 0 | Prodoc finalized in December 2010. Project achieved technical completion in June 2012. | Final verification in progress. Project targeted for completion in 2013. | 2010 |  | Investment
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment at Petra Engineering Industries Co. | Multi-Year | ASP | JOR | REF | 60 | INV | 86 | A | I | HCFC | 8.1 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-10-31 | 2013-06-01 |  |  | 2167033 | 126500 | 2293533 | 853946.75 | 37.23% | 1439586.25 | 650683.26 | 800000 | 162527 | 9488 | 64046 | 107969 | 48801 | An additional amount of USD 126,500 was approved for heat exchangers at the 66th Meeting of the Executive Committee in April 2012. All the equipment was purchased in 2012 (with the exception of heat exchangers). The company started the production of devices with alternative refrigerants. The ICC was almost disbursed, the IOC was obligated and the initial payments is being done. The bidding for the heat exchanger was organized. The equipment for the foaming line was delivered and installed. | The disbursement level is at USD 762,000 compared to the disbursement level of USD 287,484. Increase in disbursement is due to the progress made in the project implementation in line with contracts made with suppliers. Installation of the heat exchange equipment and commissioning of the foaming line are foreseen for 2013. The project is supposed to be finalized this year. Reason for the delay: For the amount of money available, there was no offer received on the bidding for heat exchangers.
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Individual | ASP | SYR | REF | 62 | INV | 103 | A | I | HCFC | 12.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2015-01-01 |  |  | 1465361 | 0 | 1465361 | 18568.15 | 1.267% | 1446792.85 | 128526.02 | 128526 | 109902 | 0 | 1393 | 108509 | 9639 | The company and UNIDO held a meeting in Beirut, Lebanon, on 25 June 2012, and agreed on a work plan to be applied for the second half of 2012. Shortly after the meeting, the situation worsened in Aleppo, where the company has its main facility, making compliance with the approved work plan difficult. A contract has been signed in August to start the activities concerning the redesign and prototyping of the company's main products. The company and UNIDO agreed on the technical specifications of a new cleaning system for heat exchangers will be procured in December 2012, phasing-out the HCFC-141b used by the company for final cleaning of heat exchangers, representing 22 MT of annual HCFC-141b consumption. The current situation in the country has even forced to discontinue the activities initiated in 2012 (re-design and prototyping). | .- Completion of the works on re-design and prototyping; .- Subject to national conditions, a new cleaning system for heat exchangers will be procured; .- Subject to national conditions, progress in all other project activities. Reason for the extension of the project completion date: The security and political situation in the country. |  |  | INV
CLO | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. |  | ASP | SYR | REF | 29 | INV | 53 | A | I | CFC | 2.5 |  | 0 |  | 1999-11-01 |  | 2002-12-01 |  |  | 2008-07-01 | 33359 | -33359 | 0 | 0 |  | 0 |  | 0 | 1668 | -1668 | 0 | 0 |  | Project cancelled (Decision 55/4)
FIN | France | Conversion of refrigeration industrial facilities |  | ASP | LEB | REF | 23 | INV | 22 | A | I | CFC | 10.4 | 10.4 | 0 |  | 1997-11-01 | 1999-01-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 166605 | -13443 | 153162 | 153162 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100% | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 |  |  |  | 1999-06-01 | INV
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 07 | INV | 26 | N | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 07 | INV | 27 | N | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 07 | INV | 25 | N | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 07 | INV | 18 | N | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | I | CFC | 764.9 | 764.9 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 |  | 2007-12-01 | 2008-05-01 | 5250852 | 0 | 5250852 | 5250852 | 100% | 0 | 0 |  | 587593.72 | 0 | 587593.72 | 0 | 0 | Project completed. PCR prepared. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100% | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. |  |  |  | INV
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 05 | INV | 09 | N | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 05 | INV | 64 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-03-01 | INV
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 05 | INV | 65 | N | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 05 | INV | 63 | N | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 05 | INV | 61 | N | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 05 | INV | 62 | N | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV
FIN | UNDP | Terminal umbrella project for the commercial refrigeration manufacturing sector | Individual | LAC | BOL | REF | 42 | INV | 25 | N | I | CFC | 5.8 | 5.8 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 88840 | -130.13 | 88709.87 | 88709.87 | 100% | 0 | 0 | 0 | 7995 | -11.7108 | 7983.2892 | 0 | 0 | Completed in 2007. |  | 2004 |  | Investment
FIN | UNDP | Phase-out of CFC in refrigeration at Koldair Company | Individual | AFR | EGY | REF | 08 | INV | 09 | A | I | CFC | 18 | 18 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-01-01 | 2003-04-01 | 272000 | -21979 | 250021 | 250021 | 100% | 0 | 0 | 0 | 35360 | -2857 | 32503 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNIDO | Replacement of CFC-12 with HFC 134a for commercial refrigeration at Enapat | Individual | AFR | ALG | REF | 25 | INV | 26 | A | I | CFC | 9.2 | 9.2 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 1998-12-01 | 2000-12-01 | 139932 | -16937 | 122995 | 122995 | 100% | 0 | 0 |  | 18191 | -2227 | 15964 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox | Individual | AFR | MOR | REF | 25 | INV | 25 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-05-01 | 2002-09-01 | 32920 | -341 | 32579 | 32578.65 | 100% | 0.35 | 0 |  | 4280 | -51 | 4228 | 1 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Smifam | Individual | AFR | MOR | REF | 26 | INV | 27 | A | I | CFC | 4.9 | 4.9 |  |  | 1998-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-04-01 | 2002-09-01 | 62447 | -2267 | 60180 | 60179.88 | 100% | 0.12 | 0 |  | 8118 | -307 | 7811 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Alom du Nord | Individual | AFR | MOR | REF | 25 | INV | 24 | A | I | CFC | 7.7 | 7.7 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-04-01 | 2002-09-01 | 99402 | -12788 | 86614 | 86614.26 | 100% | -0.26 | 0 |  | 12922 | -1680 | 11242 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Mafidec | Individual | AFR | MOR | REF | 29 | INV | 35 | A | I | CFC | 5.6 | 5.6 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 117360 | -7879 | 109481 | 109480.65 | 100% | 0.35 | 0 |  | 15257 | -1047 | 14210 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Siafmo | Individual | AFR | MOR | REF | 29 | INV | 34 | A | I | CFC | 8.7 | 8.7 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 126240 | -3250 | 122990 | 122990.02 | 100% | -0.02 | 0 |  | 16411 | -448 | 15963 | 0 | 0 | FIN
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | INV
CLO | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at Fabricacion de Compresores S.A. (Facosa, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-06-01 |  |  | 1996-05-01 | 584000 | -581001 | 2999 | 2999 | 100% | 0 | 0 | 0 | 75920 | -75530 | 390 | 0 | 0 | Canceled in 1996. Financially completed in 1996. |  | 1994 |  | Investment
CLO | UNIDO | Conversion from CFC-12 to isobutane technologies and products at the compressor factory of the Hangli Refrigeration Ltd., in Hangzhou, China | Individual | ASP | CPR | REF | 26 | INV | 256 | A | I | CFC | 0 | 0 |  |  | 1998-11-01 | 1999-11-01 | 2001-12-01 |  |  | 2003-12-01 | 861000 | -180793 | 680207 | 680207 | 100% | 0 | 0 |  | 104710 | -20006 | 84704 | 0 | 0 | CLO
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | 1994-07-01 | INV
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100% | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | Project completed. Draft PCR underway. Savings to be returned to the MLF. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100% | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCOM. |  |  | 1998-06-01 | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100% | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100% | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100% | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100% | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100% | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100% | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100% | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | -291.22 | 1951465.78 | 1951465.78 | 100% | 0 | 0 |  | 224693.27 | -33.53 | 224659.74 | 0 | 0 | Financially completed. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100% | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100% | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | INV
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100% | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100% | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  | 2000-12-01 | INV
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the ExCom March 2000. |  |  | 1999-06-01 | INV
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-06-01 | INV
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100% | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | Project is financially completed. |  |  | 2002-06-01 | INV
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 08 | INV | 08 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | 1997-12-01 | INV
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100% | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-07-01 | INV
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-03-01 | INV
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 100% | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100% | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100% | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | Project completed. |  |  |  | INV
FIN | Japan | Phasing out ODS in the production of compressors at Changshu Refrigerating Equipment Works | Individual | ASP | CPR | REF | 28 | INV | 302 | A | I | CFC | 75 | 75 | 0 |  | 1999-07-01 | 2001-11-01 | 2002-12-01 |  | 2004-10-01 | 2005-12-01 | 2250000 | -3142 | 2246858 | 2246858 | 100% | 0 | 0 | 0 | 257500 | -9474 | 248026 | 0 | 9128 | The project was succesfully completed in October 2004. |  | 1999
FIN | UNDP | Conversion of CFC-12 to HFC-134a compresors at Compresores Andinos, S.A. | Individual | LAC | COL | REF | 13 | INV | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 313650 | -23379 | 290271 | 290271 | 100% | 0 | 0 | 0 | 40774.37 | -3039.37 | 37735 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at (Comasa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 32 | A | D | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-12-01 |  | 1995-11-01 | 1998-12-01 | 1188724 | -152860 | 1035864 | 1035864 | 100% | 0 | 0 | 0 | 154534.1 | -19872.13 | 134661.97 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | I | No_ODP | 0.7 | 0.7 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186.46 | 21873.54 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNIDO | Conversion of the assembly of refrigeration compressors to phase out CFC-12 and CFC/HCFC-502 by using HFC-134a and R-404a at Elgin Maquinas SA | Individual | LAC | BRA | REF | 17 | INV | 20 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-10-01 | 1999-07-01 |  | 1998-12-01 | 2001-07-01 | 460339 | 0 | 460339 | 460339 | 100% | 0 | 0 |  | 59844 | 0 | 59844 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the compressor factory of the Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | REF | 19 | INV | 165 | A | I | CFC | 60 | 60 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1998-12-01 | 2002-05-01 | 899030 | 0 | 899030 | 899030.28 | 100% | -0.28 | 0 |  | 116874 | -33 | 116841 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Zel Tianjin Compressor Co., Ltd. | Individual | ASP | CPR | REF | 22 | INV | 211 | A | I | CFC | 30 | 30 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 1999-07-01 | 962175 | 0 | 962175 | 962175 | 100% | 0 | 0 |  | 125083 | 0 | 125083 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Yuhuan Compressor Factory in Kanmen Town in Yuhuan County, South East China | Individual | ASP | CPR | REF | 23 | INV | 219 | A | I | CFC | 116 | 116 |  |  | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1465155 | -9186 | 1455969 | 1455969.4 | 100% | -0.4 | 0 |  | 190470 | -1494 | 188976 | 0 | 0 | FIN
FIN | UNIDO | Conversion of compressor production for domestic refrigerators from CFC-12 to hydrocarbon refrigerant at Jiaxipera compressor factory | Individual | ASP | CPR | REF | 18 | INV | 145 | A | I | CFC | 96 | 96 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 1490000 | 0 | 1490000 | 1490000.07 | 100% | -0.07 | 0 |  | 193700 | 0 | 193700 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the X'ian Yuan Dong Compressor Co., Xi'an | Individual | ASP | CPR | REF | 19 | INV | 164 | A | I |  | 0 | 0 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1999-06-01 | 2000-12-01 | 1599000 | -5860 | 1593140 | 1593140 | 100% | 0 | 0 |  | 207870 | -1090 | 206780 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Phasing out ODS at the Household Refrigerator Compressor Factory of the Guangzhou Wanbao Compressor Group | Individual | ASP | CPR | REF | 20 | INV | 185 | A | I | CFC | 3 | 3 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 1999-10-01 | 2002-09-01 | 2250000 | 0 | 2250000 | 2250000.13 | 100% | -0.13 | 0 |  | 292500 | -35 | 292465 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | Individual | ASP | IRA | REF | 28 | INV | 51 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2008-08-01 | 2009-09-01 | 1076148 | 58673 | 1134821 | 1134821.36 | 100% | -0.36 | 0 |  | 128376 | 6454 | 134830 | 0 | 0 | FIN
FIN | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | I | CFC | 2 | 2 |  |  | 2002-11-01 | 2003-06-01 | 2005-06-01 |  | 2006-06-01 | 2007-09-01 | 223412 | -44 | 223368 | 223367.9 | 100% | 0.1 | 0 |  | 29044 | -6 | 29038 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Demonstration sub-project for conversion of room airconditioning compressor manufacturing from HCFC-22 to propane at Guangdong Meizhi Co. | Individual | ASP | CPR | REF | 61 | DEM | 502 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 | 2013-06-01 |  |  | 1875000 | 0 | 1875000 | 1302268.85 | 69.45% | 572731.15 | 555448.52 | 500000 | 140625 | 0 | 97670 | 42955 | 41659 | Conversion at Meizhi was completed. The total actual investments (about USD 3.5 million) were about 10% higher than the total agreed project costs. However, in these costs, investments related to R&D of the past years have not been included, which is also of significant value. In light of the above, high level of co-financing was required from the enterprise in addition to covering the costs related to the 40% A2 ownership as well as the 10% additional investments. Two types of R290 compressors (fixed and variable frequency) with 1 HP and COP of 4.12-4.33 are available for mass production. Main challenge was the reduction of the charge size and the development of a suitable lubricant. The project will be completed upon national acceptance, that is foreseen for the second quarter of 2013. | Detailed report on the ICC was submitted to the 69th Meeting of the Executive Committee. Conversion activities were finished and the project will be completed upon national acceptance, that is foreseen for the second quarter 2013. The slight delay is due to the fact that national acceptance cannot be organized before the second quarter of 2013 and that the national standard allowing the use of flammable alternatives comes in to effect as of 1 May 2013. Funds obligated are expected to be disbursed during 2013. Expert mission is expected including project commissioning and equipment destruction. |  |  | INV
CLO | UNDP | Meenakshi aerosol and cosmetics conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1998-06-01 |  |  | 1998-07-01 | 98940 | -98940 | 0 | 0 |  | 0 | 0 | 0 | 12862.2 | -12862.2 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
COM | UNDP | Terminal umbrella project in the aerosol sector | Individual | ASP | IND | ARS | 38 | INV | 358 | A | I | CTC/CFC | 132.5 | 132.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-11-01 |  | 2007-03-01 |  | 583000 | 0 | 583000 | 583000 | 100% | 0 | 0 | 0 | 74130 | 0 | 74130 | 0 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 |  | 2005-02-01 | 2006-07-01 | 160160 | 0 | 160160 | 160160 | 100% | 0 | 0 |  | 20820.8 | 0 | 20820.8 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 29th ExCom. |  |  | 1998-06-01 | INV
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 14 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 23 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV
FIN | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 |  | 2005-05-01 | 2004-10-01 | 1175340 | 0 | 1175340 | 1175340 | 100% | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | Project financially and physically completed. |  |  | 2002-06-01 | INV
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100% | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | PCR finalized and submitted to ExCom. |  |  | 1999-06-01 | INV
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100% | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100% | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 1999-06-01 | INV
FIN | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 | 2005-01-01 | 134250 | -12102 | 122148 | 122148 | 100% | 0 | 0 |  | 17452.5 | -1573.26 | 15879.24 | 0 | 0 | Project financially completed and balance funds returned to ExCom. PCR submitted. |  |  | 1999-12-01 | INV
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 100% | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100% | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100% | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV
FIN | UNDP | Phaseout of CFC-12 and CTC by substituting with HAPs at Ruby Aerosols | Individual | ASP | IND | ARS | 28 | INV | 227 | A | I | CTC/CFC | 22.2 | 22.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2002-01-01 | 2005-11-01 | 45800 | -15.9956 | 45784.0044 | 45784 | 100% | 0.0044 | 0 | 0 | 5954 | -1.9994 | 5952 | 0.00057201 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC at Vimsons Aerosol by substituting with HAPs | Individual | ASP | IND | ARS | 28 | INV | 213 | A | I | CTC/CFC | 18.2 | 18.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-03-01 | 2002-11-01 | 66500 | -18505 | 47995 | 47995 | 100% | 0 | 0 | 0 | 8645 | -2406 | 6239 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Aerosol conversion at Spray Products | Individual | ASP | IND | ARS | 24 | INV | 173 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 65486 | -2975 | 62511 | 62511 | 100% | 0 | 0 | 0 | 8513.18 | -387.18 | 8126 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Texas Enterprises aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 117 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 70000 | -4903 | 65097 | 65097 | 100% | 0 | 0 | 0 | 9100 | -637 | 8463 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerosols D'Asia Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 135 | A | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -2379 | 67071 | 67071 | 100% | 0 | 0 | 0 | 9028.5 | -308.5 | 8720 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerol Formulations aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 118 | A | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -790.74 | 68659.26 | 68659 | 100% | 0.26 | 0 | 0 | 9028.5 | -102.4962 | 8925.97 | 0.033801 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aero Pack Products aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 138 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-04-01 | 69450 | 0 | 69450 | 69450 | 100% | 0 | 0 | 0 | 9029 | 0 | 9029 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Ultra Tech Specialty Chemicals Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 115 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Asian Aerosols Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 136 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 90890 | -7767 | 83123 | 83123 | 100% | 0 | 0 | 0 | 11815.7 | -1009.7 | 10806 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerosol conversion at Maja Cosmetics Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 172 | A | I | CFC | 31.3 | 31.3 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 125240 | -705 | 124535 | 124535 | 100% | 0 | 0 | 0 | 16281.2 | -92.2 | 16189 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | Individual | ASP | IND | ARS | 28 | INV | 221 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2005-09-01 | 2007-01-01 | 161518 | -15270 | 146248 | 146248 | 100% | 0 | 0 | 0 | 20997.34 | -1985.3379 | 19012.0021 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | Individual | ASP | LEB | ARS | 28 | INV | 35 | A | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 147333 | -2643.0037 | 144689.9963 | 144690 | 100% | -0.0037 | 0 | 0 | 19153.29 | -344.2853 | 18809.0052 | -0.00048098 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | Individual | ASP | LEB | ARS | 28 | INV | 30 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 158582 | -5069.0007 | 153512.9993 | 153513 | 100% | -0.0007 | 0 | 0 | 20615.66 | -658.661 | 19956.9991 | -9.1001e-05 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | Individual | ASP | LEB | ARS | 29 | INV | 32 | A | I | CFC | 50.7 | 50.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2004-09-01 | 2005-10-01 | 314092 | -1546.9981 | 312545.0019 | 312545 | 100% | 0.0019 | 0 | 0 | 40831.96 | -200.96 | 40630.9998 | 0.000247 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Mary Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 96 | A | I | CFC | 40 | 40 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 136400 | -4295 | 132105 | 132105 | 100% | 0 | 0 | 0 | 17732 | -558 | 17174 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Standard Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 94 | A | I | CFC | 41 | 41 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 138380 | -5000 | 133380 | 133380 | 100% | 0 | 0 | 0 | 17989.4 | -650 | 17339.4 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Packserv Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 45 | A | D | CFC | 155 | 155 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 474705 | -1221 | 473484 | 473484 | 100% | 0 | 0 | 0 | 61711.65 | -159 | 61552.65 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Sanit & Sons Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 46 | A | I | CFC | 194 | 194 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 2000-04-01 | 2002-03-01 | 582100 | 0 | 582100 | 582100 | 100% | 0 | 0 | 0 | 75673 | 0 | 75673 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Individual | LAC | TRI | ARS | 25 | INV | 12 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2004-12-01 | 2005-10-01 | 119570 | 0 | 119570 | 119570 | 100% | 0 | 0 | 0 | 15544.1 | 0 | 15544.1 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 1998 |  | Investment
CLO | Germany | Development of a country programme update | Individual | AFR | ALG | SEV | 43 | CPG | 60 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-09-01 | 2005-07-01 |  |  | 2007-09-01 | 13500 | 0 | 13500 | 13500 | 100% | 0 | 0 | 0 | 1215 | 0 | 1215 | 0 | 0 | The CPU update was cancelled by the Government of Algeria. The results have been used by UNIDO for the National Phase Out Plan.
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 06 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | UNIDO | Preparation of country programme update | Individual | LAC | ARG | SEV | 39 | CPG | 134 | A | I |  | 0 | 0 |  |  | 2003-04-01 |  | 2004-10-01 |  |  | 2005-08-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | CLO
FIN | France | Technical assistance for country programme and refrigerant management plan preparation |  | ASP | LAO | SEV | 27 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-12-01 |  | 2001-02-01 | 2001-02-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Le Plan de gestion des réfriférants a été approuvé en même temps que le Programme de pays à la 34ème réunion du Comité Exécutif. Project completed.
FIN | France | Country programme preparation |  | AFR | MAG | SEV | 21 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-09-01 | 1999-12-01 | 40000 | -3019 | 36981 | 36981 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Country programme preparation |  | AFR | MAU | SEV | 13 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-07-01 | 1995-07-01 |  | 1995-07-01 | 1995-09-01 | 44000 | -4229 | 39771 | 39771 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Balance returned at 57th ExCom.
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 03 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | Germany | Country programme preparation | Individual | AFR | ANG | SEV | 34 | CPG | 02 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | National consultants contracted, survey on ODS consump finalized, Country Programme prepared and submitted together with prop. for I.S. Angola. Aproved at 38th ExCom. (1st instalment of 1st tranche of IS funding of 81000) Request for 2nd instalment of IS
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program was completed and presented at the 13th E.C. meeting. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 06 | CPG | 12 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | $100,000 transferred to PPA-V. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | CP update submitted to the 38th ExCom. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 09 | CPG | 17 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | CPU submitted and approved at the 41st ExCom Meeting. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 09 | CPG | 22 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 |  | 2006-07-01 | 2006-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 7200 | 0 | 7200 | 0 | 0 | CPU completed and National ODS Phaseout Plan approved at the 49th ExCom. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | UNDP | Tecnical assistance for country programme preparation | Individual | LAC | ARG | SEV | 04 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-07-01 | 1993-02-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | BGD | SEV | 36 | CPG | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-10-01 |  | 2006-12-01 | 2007-03-01 | 18750 | -202 | 18548 | 18548 | 100% | 0 | 0 | 0 | 2437.5 | -25.5 | 2412 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | BGD | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-06-01 |  | 1994-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Reconnaissance survey and training | Individual | ASP | BGD | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1993-06-01 | 1997-12-01 | 55000 | -1150 | 53850 | 53850 | 100% | 0 | 0 | 0 | 7150 | -150 | 7000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | LAC | COL | SEV | 36 | CPG | 56 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-10-01 |  | 2004-06-01 | 2005-11-01 | 30000 | -415 | 29585 | 29585 | 100% | 0 | 0 | 0 | 3900 | -54 | 3846 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COL | SEV | 12 | CPG | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-03-01 |  | 1994-03-01 | 1994-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1994. Financially Completed in 1994. |  | 1994 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COS | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1992-09-01 |  | 1992-09-01 | 1997-12-01 | 20000 | 2909 | 22909 | 22909 | 100% | 0 | 0 | 0 | 2600 | 378 | 2978 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | ODS reconnaissance study | Individual | LAC | COS | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 20000 | 3422 | 23422 | 23422 | 100% | 0 | 0 | 0 | 2600 | 445 | 3045 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Survey and assessment of small CFC plant conversion possibilities | Individual | ASP | CPR | SEV | 09 | TAS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-05-01 | 1994-03-01 |  | 1998-10-01 | 2001-12-01 | 90000 | -701 | 89299 | 89299 | 100% | 0 | 0 | 0 | 11700 | -91.0016 | 11608.9984 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | CPR | SEV | 06 | CPG | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Update of the country programme and policy workshop | Individual | ASP | CPR | SEV | 21 | CPG | 188 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-03-01 |  | 1998-12-01 | 2002-06-01 | 225000 | -17054 | 207946 | 207946 | 100% | 0 | 0 | 0 | 29250 | -2217 | 27033 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Non-Investment
FIN | UNDP | National product qualification and standards evaluation for non-ODS alternatives to CFC applications | Individual | ASP | CPR | SEV | 11 | TAS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-11-01 |  | 1998-03-01 | 2000-12-01 | 362500 | -29055 | 333445 | 333445 | 100% | 0 | 0 | 0 | 47125 | -3777 | 43348 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | CUB | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 20000 | -5000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 2600 | -650 | 1950 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Survey of ODS use in the small scale (including tiny) and informal sectors, data base generation and ODS transition management planning | Individual | ASP | IND | SEV | 11 | TAS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-11-01 | 1994-05-01 |  | 1996-12-01 | 2001-12-01 | 120000 | -11230 | 108770 | 108770 | 100% | 0 | 0 | 0 | 15600 | -1460 | 14140 | 0 | 0 | Completed in 1996. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | IND | SEV | 36 | CPG | 349 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-09-01 | 2003-10-01 |  | 2006-07-01 | 2007-03-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 | 2004-12-01 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IND | SEV | 09 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1993-11-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Study to determine production and consumption of ODS | Individual | ASP | IRA | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 30350 | 0 | 30350 | 30350 | 100% | 0 | 0 | 0 | 3946 | 0 | 3946 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1993-06-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | AFR | KEN | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-07-01 |  | 1994-06-01 | 1997-12-01 | 25000 | -2270 | 22730 | 22730 | 100% | 0 | 0 | 0 | 3250 | -295 | 2955 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | LEB | SEV | 36 | CPG | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2003-12-01 | 2004-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Preparation of the country programme update | Individual | LAC | MEX | SEV | 38 | CPG | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-10-01 | 48046 | -17954.9993 | 30091.0007 | 30091 | 100% | 0.0007 | 0 | 0 | 6245.98 | -2333.9774 | 3912.0025 | 9.1004e-05 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | AFR | NIR | SEV | 36 | CPG | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-10-01 |  | 2007-12-01 | 2011-11-01 | 241493 | -10289.19 | 231203.81 | 231203.81 | 100% | 0 | 0 | 0 | 31394.09 | -1337.6809 | 30056.4091 | 0 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | PHI | SEV | 08 | CPG | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 39820 | 39820 | 79640 | 79640 | 100% | 0 | 0 | 0 | 5176.6 | 5177.4 | 10354 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Survey of ODS usage, data base generation and technical assistance for ODS phase-out for small-scale enterprises | Individual | ASP | PHI | SEV | 11 | TAS | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1996-09-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | SRL | SEV | 06 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-09-01 |  | 1994-03-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | TRI | SEV | 06 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1995-07-01 | 1997-12-01 | 25000 | 1200 | 26200 | 26200 | 100% | 0 | 0 | 0 | 3250 | 156 | 3406 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1696.5 | 128.96 | 1825.46 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106.22 | 201.5 | 3307.72 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNEP | Preparation of the country programme/RMP project | Individual | ASP | AFG | SEV | 43 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 |  | 2005-10-01 | 2011-12-01 | 60000 | -18155 | 41845 | 41845 | 100% | 0 | 0 | 0 | 7800 | -2360 | 5439.85 | 0.15 | 0 | Project financially completed. ($ 55 plus $ 7 returned to ExCom 51. $11,868 plus $1,543 PSC returned at ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | EUR | ALB | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-06-01 | 2005-12-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 | 0 | 7800 | -3770 | 4030 | 0 | 0 | Project financially completed. ($29,000 plus 3,770 PSC returned ExCom 46) |  |  | 2002-09-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ALG | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 |  | 1993-11-01 | 1994-12-01 | 15000 | 3000 | 18000 | 18000 | 100% | 0 | 0 | 0 | 1950 | 390 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ANT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1998-09-01 | 1999-06-01 | 30000 | -969 | 29031 | 29031 | 100% | 0 | 0 | 0 | 3900 | -125.97 | 3774.03 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BAH | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-06-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-12-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($1,050 plus $137 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | AFR | BDI | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-05-01 |  | 1998-09-01 | 1999-03-01 | 40000 | -10000 | 30000 | 30000 | 100% | 0 | 0 | 0 | 5200 | -1300 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BEN | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1995-10-01 | 1995-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BHA | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme/RMP project | Individual | ASP | BHU | SEV | 43 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  | 2005-07-01 | 2006-08-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BKF | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-11-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Completion of country programme preparation | Individual | LAC | BOL | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1995-10-01 | 1999-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BOT | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1994-07-01 |  | 1994-06-01 | 1994-12-01 | 30000 | 10000 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3900 | 1300 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BRU | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-01 | 1996-03-01 |  | 1998-09-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BZE | SEV | 24 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-02-01 |  | 1999-11-01 | 2000-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CAF | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-06-01 |  | 1995-10-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CHD | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-05-01 | 1996-03-01 |  | 1998-05-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 0 plus $ 376 PSC returned to ExCom 49$ 0 plus $-376 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CMR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-06-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | COI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1997-11-01 | 1999-01-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 4290 | 0 | 4290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | CRO | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme | Individual | EUR | CYP | SEV | 22 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-05-01 |  | 1997-05-01 | 1997-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | AFR | DJI | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-07-01 | 2007-01-01 | 60000 | -34200 | 25800 | 25800 | 100% | 0 | 0 | 0 | 7800 | -4446 | 3354 | 0 | 0 | Project financially completed |  |  | 2002-07-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DMI | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-08-01 |  | 1998-09-01 | 1999-07-01 | 40000 | -16000 | 24000 | 24000 | 100% | 0 | 0 | 0 | 5200 | -2080 | 3120 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DOM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1996-03-01 |  | 1995-07-01 | 1995-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | DRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | DRK | SEV | 36 | CPG | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2003-04-01 |  | 2003-10-01 | 2005-05-01 | 30000 | -684 | 29316 | 29316 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | DRK | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 1996-10-01 | 1997-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ELS | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-06-01 |  | 1997-03-01 | 1999-01-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 5200 | -650 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a country programme/refrigerant management plan | Individual | AFR | EQG | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-03-01 | 2007-07-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ETH | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | FIJ | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -2165 | 22835 | 22835 | 100% | 0 | 0 | 0 | 3250 | -281.45 | 2968.55 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GAB | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-05-01 | 1997-06-01 | 10000 | 33000 | 43000 | 43000 | 100% | 0 | 0 | 0 | 1300 | 4290 | 5590 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GAM | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-06-01 |  | 1995-10-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | GEO | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1997-11-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GHA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of refrigerant management plans/country programmes for VLVC/LVC | Individual | GLO | GLO | SEV | 22 | CPG | 132 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1997-12-01 |  | 2002-03-01 | 2007-01-01 | 200000 | -73040 | 126960 | 126960 | 100% | 0 | 0 | 0 | 26000 | -9495.2 | 16504.8 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GRN | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-08-01 |  | 1999-10-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project completed in June 2010 & financially completed. All funds disbursed. IS project phase III approved. Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GUA | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GUI | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-10-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GUY | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 5200 | -650 | 4550 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | LAC | HAI | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-04-01 |  | 2003-07-01 | 2005-06-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 | 0 | 7800 | -3770 | 4030 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | HON | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1996-06-01 | 1999-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 1 returned to ExCom 51) |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | IRA | SEV | 36 | CPG | 145 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 26250 | -3250 | 23000 | 23000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9 plus $1 PSC returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | IVC | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-03-01 | 1994-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | JAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | KIR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project completed in March 2010 & financially completed. IS renewal was submitted to the 59th ExCom and funding was approved. |  |  | 1999-10-01 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | ASP | KUW | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-06-01 |  | 2002-07-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme | Individual | EUR | KYR | SEV | 37 | CPG | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2002-07-01 |  | 2002-07-01 | 2002-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | LAO | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-07-01 |  | 2001-07-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | LEB | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-07-01 |  | 1996-05-01 | 1995-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 0 plus $ 1,515 returned to ExCom 49$ 0 plus $ -1,515 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | LES | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | LIR | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2000-07-01 |  | 2003-09-01 | 2008-12-01 | 50000 | -17000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 6500 | -2210 | 4290 | 0 | 0 | Project financially completed. |  |  | 2003-12-01 | Non Investment
FIN | UNEP | Complement for country programme preparation | Individual | AFR | MAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-06-01 |  | 1993-06-01 | 1993-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. ($ 25,000 plus $ 3,250 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MAS | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 5200 | -3250 | 1950 | 0 | 0 | Project completed in March 2010 & financially completed. IS renewal was submitted to the 59th ExCom and funding was approved. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | MAT | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-06-01 |  | 1995-07-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($1,069 plus $139 PSC to be returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MDV | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -5500 | 19500 | 19500 | 100% | 0 | 0 | 0 | 3250 | -715 | 2535 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MLI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-05-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MLW | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-05-01 | 1993-05-01 |  | 1994-03-01 | 1994-12-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3900 | -650 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme | Individual | EUR | MOL | SEV | 25 | CPG | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 1998-07-01 |  | 1998-07-01 | 1998-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme formulation | Individual | ASP | MON | SEV | 20 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 2 returned to ExCom 55) |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MOR | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-05-01 |  | 1996-05-01 | 1996-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme | Individual | AFR | MOZ | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MYA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | NAM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-04-01 | 1996-03-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | NEP | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | NER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1994-12-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | NIC | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-10-01 |  | 1996-11-01 | 1999-03-01 | 40000 | -3825 | 36175 | 36175 | 100% | 0 | 0 | 0 | 5200 | -497.25 | 4702.75 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | PAK | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1996-06-01 | 1996-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAN | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | -3000 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3900 | -390 | 3510 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-10-01 |  | 1996-10-01 | 1999-05-01 | 43000 | -4000 | 39000 | 39000 | 100% | 0 | 0 | 0 | 5590 | -520 | 5070 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1995-07-01 | 1995-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 | 0 | 6890 | 0 | 6890 | 0 | 0 | Project financially completed. ($ 3,588 plus $ 466 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | PNG | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-02-01 | 1995-10-01 |  | 1996-05-01 | 1999-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 2,967 plus 386 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | PRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  | 1995-07-01 | 1996-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1995-06-01 |  | 1997-05-01 | 1999-02-01 | 35000 | -4850 | 30150 | 30150 | 100% | 0 | 0 | 0 | 4550 | -630.5 | 3919.5 | 0 | 0 | Project financially completed. ($ 9,000 plus $ 1,170 PSC returned ExCom 44) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SEN | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1993-11-01 | 1993-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SEY | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1994-07-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SOI | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project financially completed |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STK | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-12-01 | 1999-12-01 | 35000 | -12500 | 22500 | 22500 | 100% | 0 | 0 | 0 | 4550 | -1625 | 2925 | 0 | 0 | Project financially completed. ($ 1,000 plus $ 130 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STL | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-10-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 400 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme and refrigerant management plan | Individual | AFR | STP | SEV | 36 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2007-12-01 | 30000 | -3538 | 26462 | 26462 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-08-01 |  | 1998-05-01 | 1999-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SUD | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1994-03-01 | 1994-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme | Individual | LAC | SUR | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-06-01 |  | 2003-08-01 | 2005-05-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 | 0 | Project financially completed. |  |  | 2003-07-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SWA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1994-12-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 10,000 plus $ 1,300 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SYR | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-11-01 | 1993-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. ($ 20,927 plus $ 2,721 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | TOG | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-02-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | TUV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 5200 | -3250 | 1950 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | UGA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1994-06-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | URT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1996-07-01 | 1999-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-01 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNIDO | Country Programme Preparation | Individual | EUR | BHE | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | -2 | 10398 | 0 | 0 | FIN
FIN | UNIDO | Joint UNIDO/UNEP preparation of country programmes | Individual | GLO | GLO | SEV | 12 | TAS | 62 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1996-06-01 | 1998-08-01 | 75000 | -3155 | 71845 | 71845 | 100% | 0 | 0 |  | 9750 | -425 | 9325 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of country programme | Individual | AFR | LIB | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 80000 | -3440 | 76560 | 76560.15 | 100% | -0.15 | 0 |  | 10400 | -463 | 9937 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a Country Programme | Individual | EUR | MDN | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-08-01 | 1995-12-01 |  | 1996-12-01 | 1998-08-01 | 80000 | -7780 | 72220 | 72220 | 100% | 0 | 0 |  | 10400 | -1026 | 9374 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for a country programme and a terminal phase-out plan | Individual | EUR | MOG | SEV | 51 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-04-01 | 2009-09-01 | 40000 | -826 | 39174 | 39174.1 | 100% | -0.1 | 0 |  | 3600 | -74 | 3526 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country programme update | Individual | AFR | MOR | SEV | 38 | CPG | 48 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-12-01 | 2005-05-01 | 40000 | -1747 | 38253 | 38253.07 | 100% | -0.07 | 0 |  | 5200 | -235 | 4965 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country programme preparation | Individual | ASP | OMA | SEV | 29 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-12-01 | 2002-05-01 | 80000 | -1455 | 78545 | 78544.87 | 100% | 0.13 | 0 |  | 10400 | -205 | 10195 | 0 | 0 | FIN
FIN | UNIDO | Preparation of the Country Programme | Individual | ASP | QAT | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Preparation of Country Programme | Individual | EUR | ROM | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1995-07-01 | 1998-08-01 | 80000 | -23457 | 56543 | 56543 | 100% | 0 | 0 |  | 10400 | -3061 | 7339 | 0 | 0 | FIN
FIN | UNIDO | Country programme update | Individual | EUR | ROM | SEV | 36 | CPG | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-01-01 | 2004-04-01 | 60000 | -356 | 59644 | 59644 | 100% | 0 | 0 |  | 7800 | -59 | 7741 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a country programme/national phase-out plan | Individual | ASP | SAU | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-09-01 | 2008-01-01 |  | 2007-12-01 | 2008-12-01 | 65000 | -3270 | 61730 | 61729.79 | 100% | 0.21 | 0 |  | 4875 | -245 | 4630 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country Programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | USA | Support for country programme preparation |  | LAC | ECU | SEV | 07 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-09-01 |  | 1993-09-01 | 1993-09-01 | 50000 | 6000 | 56000 | 56000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $6,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Assistance in implementation of country programme |  | LAC | ECU | SEV | 11 | CPG | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Assistance to country programme and investment projects preparation |  | LAC | MEX | SEV | 08 | CPG | 18 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Assistance in country programme preparation |  | LAC | VEN | SEV | 08 | CPG | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
TRF | UNEP | Preparation of country programme | Individual | AFR | ANG | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2002-04-01 |  |  | 2001-12-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Project financially completed. ($5,000 plus $650 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Technical assistance in CTC management | Individual | ASP | NEP | SOL | 47 | TAS | 17 | A | I | CTC | 0.9 | 0.9 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-01-01 | 2008-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNIDO | Conversion of metal cleaning processes from CTC solvent to TCE vapour degreasing at Ceramic Tools Factory (CTF) | Individual | ASP | DRK | SOL | 28 | INV | 12 | A | I | CTC | 19.8 | 19.8 |  |  | 1999-07-01 | 2000-08-01 | 2000-08-01 |  | 2001-12-01 | 2002-12-01 | 206657 | 0 | 206657 | 206657 | 100% | 0 | 0 |  | 26865 | 0 | 26865 | 0 | 0 | FIN
FIN | UNIDO | Conversion of Cleaning Processes from CTC to perchloroethylene cleaning at the galvanising workshop of the Pyongyang Illuminating Fixtures Factory (PIF) | Individual | ASP | DRK | SOL | 38 | INV | 21 | A | I | CTC | 29.7 | 29.7 |  |  | 2002-11-01 | 2004-06-01 | 2004-06-01 |  | 2004-12-01 | 2006-09-01 | 230172 | -59 | 230113 | 230112.94 | 100% | 0.06 | 0 |  | 29922 | -7 | 29915 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 23 | INV | 05 | A | I | CTC | 110 | 110 |  |  | 1997-11-01 | 1999-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-07-01 | 311922 | 0 | 311922 | 311922.08 | 100% | -0.08 | 0 |  | 40550 | 0 | 40550 | 0 | 0 | FIN
FIN | UNIDO | Conversion of remaining metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 26 | INV | 11 | A | I | CTC | 168 | 168 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2001-12-01 | 2002-12-01 | 490157 | -2198 | 487959 | 487958.96 | 100% | 0.04 | 0 |  | 63720 | -386 | 63334 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from CTC (formerly methyl chloroform) to perchloroethylene cleaning at the Plating Workshop (PLT) of the refrigeration factory of the 5 October Automation Complex, Pyongchon District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 22 | A | I | CTC | 69.3 | 69.3 |  |  | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2006-05-01 | 508068 | -1981 | 506087 | 506086.6 | 100% | 0.4 | 0 |  | 65887 | -306 | 65581 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of methyl chloroform and CTC to non-ODS solvent cleaning in the plating workshop of the Taedong-gang Television Factory (PTV), Taedong-gang District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 20 | A | I | CTC | 59.8 | 59.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-06-01 | 2006-07-01 | 597886 | -4408 | 593478 | 593477.81 | 100% | 0.19 | 0 |  | 75767 | -484 | 75283 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvent to vapour at Pyongyang September 18 Bearings Factory | Individual | ASP | DRK | SOL | 26 | INV | 10 | A | I | CTC | 121 | 121 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 1081024 | -2425 | 1078599 | 1078598.62 | 100% | 0.38 | 0 |  | 128913 | -455 | 128458 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride to aqueous cleaning techniques at the Gumsong Tractor Factory (GST) | Individual | ASP | DRK | SOL | 36 | INV | 18 | A | I | CTC | 198 | 198 |  |  | 2002-03-01 | 2002-06-01 | 2004-09-01 |  | 2004-12-01 | 2006-05-01 | 1932207 | 0 | 1932207 | 1932207.01 | 100% | -0.01 | 0 |  | 222543 | -1 | 222542 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning processes from CTC to aqueous and solvent cleaning techniques at Huichon February 26 Factory (HUI) | Individual | ASP | DRK | SOL | 37 | INV | 19 | A | I | CTC | 209 | 209 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-12-01 | 2006-05-01 | 1945477 | -950 | 1944527 | 1944527.06 | 100% | -0.06 | 0 |  | 224002 | -443 | 223559 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Blue Star Ltd., Thane | Individual | ASP | IND | SOL | 31 | INV | 266 | A | I | CTC | 6.6 | 6.6 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-12-01 | 2003-10-01 | 76027 | 0 | 76027 | 76027 | 100% | 0 | 0 |  | 9884 | 0 | 9884 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Engineer Industries, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 308 | A | I | CTC | 20.2 | 20.2 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 238776 | 0 | 238776 | 238775.51 | 100% | 0.49 | 0 |  | 31041 | -9 | 31032 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Engineering, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 306 | A | I | CTC | 14.5 | 14.5 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 240435 | 0 | 240435 | 240434.89 | 100% | 0.11 | 0 |  | 31257 | -19 | 31238 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Coils Ltd., Palghar | Individual | ASP | IND | SOL | 34 | INV | 327 | A | I | CTC | 22.8 | 22.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 245024 | 0 | 245024 | 245023.89 | 100% | 0.11 | 0 |  | 31853 | -19 | 31834 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Navdeep Engineering, Palghar | Individual | ASP | IND | SOL | 38 | INV | 354 | A | I | CTC | 53.9 | 53.9 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-12-01 | 2007-01-01 | 661842 | -1087 | 660755 | 660754.55 | 100% | 0.45 | 0 |  | 82803 | -120 | 82683 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | Individual | ASP | PAK | SOL | 37 | INV | 47 | A | I | CTC | 10 | 10 |  |  | 2002-07-01 | 2004-10-01 | 2004-08-01 |  | 2005-12-01 | 2006-12-01 | 122078 | -665 | 121413 | 121412.8 | 100% | 0.2 | 0 |  | 15870 | -86 | 15784 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal umbrella project for the phase-out of ODS solvents | Individual | EUR | ROM | SOL | 41 | INV | 22 | A | I | CTC | 11.1 | 11.1 |  |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-12-01 | 2007-05-01 | 220615 | -6247 | 214368 | 214367.81 | 100% | 0.19 | 0 |  | 19855 | -562 | 19293 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Terminal phase-out management plan of CTC production/consumption for process agent uses | Individual | EUR | ROM | PAG | 50 | INV | 36 | A | I | CTC | 120.5 | 120.5 |  |  | 2006-11-01 | 2007-06-01 | 2007-11-01 |  |  | 2010-09-01 | 1389800 | -370032 | 1019768 | 1019768.14 | 100% | -0.14 | 0 |  | 104235 | -27752 | 76483 | 0 | 0 | CLO |  |  | 2009-12-01 | INV
COM | UNDP | Phase-out of CTC as process agent in two applications at Braskem | Individual | LAC | BRA | PAG | 54 | INV | 281 | N | I | CTC | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-12-01 |  | 1178554 | -6110 | 1172444 | 1172444 | 100% | 0 | 0 | 0 | 88392 | -458.25 | 87933.75 | 0 | 0 | Completed. Final pending disbursement to companies after verification was done in 2010. |  | 2008 |  | Investment
FIN | UNIDO | Umbrella project for terminal phase-out of CTC | Individual | LAC | MEX | PAG | 52 | INV | 133 | A | I | CTC | 87.3 | 87.3 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-31 |  | 2009-12-01 | 2012-08-01 | 1518094 | -9212 | 1508882 | 1508881.83 | 100% | 0.17 | 0 |  | 113857 | -691 | 113166 | 0 | 0 | Financial completion in Aug 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  | 2010-01-01 | INV
TRF | IBRD | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 47 | INV | 64 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 |  |  | 2006-04-01 | 114480 | -114480 | 0 | 0 |  | 0 | 0 |  | 10303 | -10303 | 0 | 0 | 0 | All project funds and support costs were transferred to UNDP at 48th Meeting. |  |  |  | INV
COM | IBRD | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multiyear | ASP | IND | PHA | 45 | INV | 386 | N | I | CTC | 6158 | 9848 | 9827 | 9896 | 2005-04-01 | 2007-04-01 | 2006-04-01 |  | 2006-07-01 |  | 399045 | 0 | 399045 | 399045 | 100% | 0 | 0 | 0 | 29928 | 0 | 29928 | 0 | 0 | 2005 verification of CTC production and consumption completed as scheduled. Levels of CTC production and consumption in 2005, excluding the quantity stockpiled for feedstock use in the following years, are well under the agreed targets. |  |  |  | INV
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2008 annual programme | Multiyear | ASP | IND | PHA | 55 | INV | 422 | N | I | CTC | 440 | 440 | 440 | 440 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 |  | 3211875 | 0 | 3211875 | 3211875 | 100% | 0 | 0 | 0 | 240891 | 0 | 240891 | 0 | 0 | All funds disbursed and tranche completed |  |  |  | INV
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multiyear | ASP | IND | PHA | 52 | INV | 408 | N | I | CTC | 420 | 420 | 420 | 420 | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-07-01 |  | 4020938 | 0 | 4020938 | 4020938 | 100% | 0 | 0 | 0 | 301570 | 0 | 301570 | 0 | 0 | Tranche completed. |  |  |  | INV
COM | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-07-01 |  | 5000000 | 3520843 | 8520843 | 8520843 | 100% | 0 | 0 | 0 | 375000 | 264063 | 639063 | 0 | 0 | Tranche is completed. |  |  |  | INV
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 9180112 | 0 | 9180112 | 9180112 | 100% | 0 | 0 | 0 | 688508 | 0 | 688508 | 0 | 0 | Targets met, tranche completed. |  |  |  | INV
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multiyear | ASP | IND | PHA | 49 | INV | 400 | N | I | CTC | 232 | 232 | 232 | 232 | 2006-07-01 | 2007-11-01 | 2007-07-01 |  | 2007-07-01 |  | 9556267 | 0 | 9556267 | 9556267 | 100% | 0 | 0 | 0 | 716720 | 0 | 716720 | 0 | 0 | Tranche fully disbursed. |  |  |  | INV
FIN | France | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 399 | A | I | CTC | 0 |  | 0 |  | 2006-07-01 | 2009-01-01 | 2007-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | France | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 409 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2009-01-01 | 2008-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | France | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 374 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2008-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GTZ-Proklima. All activities planned under this tranche have been completed. |  |  | 2007-04-01
FIN | France | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 387 | A | I | CTC | 0 |  | 0 |  | 2005-04-01 | 2008-01-01 | 2006-04-01 |  | 2009-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009. |  |  | 2008-04-01
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 401 | A | I | CTC | 0 | 0 | 0 |  | 2006-07-01 | 2008-01-01 | 2007-07-01 |  | 2008-12-01 | 2010-07-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 410 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2008-12-01 | 2008-07-01 |  | 2010-12-01 | 2012-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | The environment, health and safety material has been completed and capacity building with institutional stakeholders from the power sector has taken place. All project activities have been completed now.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 375 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2007-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned with the funds from this tranche have been accomplished.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 388 | A | I | CTC | 0 | 970 | 0 |  | 2005-04-01 | 2006-01-01 | 2006-07-01 |  | 2008-12-01 | 2010-07-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
FIN | IBRD | Assessment of CTC phase-out in the chlo-alkali sector | Individual | GLO | GLO | PHA | 52 | TAS | 280 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-07-01 | 2008-09-30 |  | 2008-06-01 | 2008-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | Study completed and presented to the 55th ExCom. |  |  |  | Non-INV
FIN | UNIDO | Plan for terminal phase-out of CTC (6th tranche) | Multi-Year | ASP | DRK | PHA | 55 | INV | 52 | A | I | CTC | 77.8 | 77.8 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 100000 | -2024 | 97976 | 97975.55 | 100% | 0.45 | 0 |  | 7500 | -152 | 7348 | 0 | 0 | Financial completion in Oct 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (fifth tranche) | Multi-Year | ASP | DRK | PHA | 52 | INV | 48 | A | I | CTC | 15 | 15 |  |  | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-12-01 | 2009-05-01 | 284840 | -142 | 284698 | 284698.36 | 100% | -0.36 | 0 |  | 21363 | -11 | 21352 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (third tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 35 | A | I | CTC | 1441.4 | 597.7 |  |  | 2005-07-01 | 2006-04-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 300000 | 0 | 300000 | 300000.01 | 100% | -0.01 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (fourth tranche) | Multi-Year | ASP | DRK | PHA | 49 | INV | 45 | A | I | CTC | 100 | 100 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (second tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 36 | A | I | CTC | 0 | 0 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 1000000 | -157 | 999843 | 999842.55 | 100% | 0.45 | 0 |  | 75000 | -12 | 74988 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (first tranche) | Multi-Year | ASP | DRK | PHA | 41 | INV | 30 | A | I | CTC | 0 | 613.8 |  |  | 2003-12-01 | 2004-02-01 | 2004-12-01 |  | 2009-12-01 | 2011-05-01 | 3500000 | -2013 | 3497987 | 3497986.94 | 100% | 0.06 | 0 |  | 262500 | -151 | 262349 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Sector phase-out plan of CTC (third tranche) | Multi-Year | ASP | PAK | PHA | 54 | INV | 67 | A | I | CTC | 62.5 | 62.5 |  |  | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2009-12-01 | 2012-05-01 | 245665 | -912 | 244753 | 244752.62 | 100% | 0.38 | 0 |  | 25924 | -96 | 25828 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | Sector phase-out plan of CTC | Multi-Year | ASP | PAK | PHA | 41 | INV | 57 | A | I | CTC | 100 | 109.7 |  |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-07-01 | 2010-12-01 | 1200000 | -542 | 1199458 | 1199458.28 | 100% | -0.28 | 0 |  | 90000 | -41 | 89959 | 0 | 0 | FIN |  |  | 2006-07-01 | INV
FIN | UNIDO | Sector phase-out plan of CTC (second tranche) | Multi-Year | ASP | PAK | PHA | 44 | INV | 62 | A | I | CTC | 326.5 | 326.5 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-07-01 | 2012-05-01 | 1300000 | -2137 | 1297863 | 1297862.63 | 100% | 0.37 | 0 |  | 97500 | -160 | 97340 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
ONG | IBRD | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | Multiyear | ASP | IND | PHA | 58 | INV | 434 | N | I | CTC | 268 | 268 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-31 | 2013-12-01 |  |  | 3211874 | 0 | 3211874 | 2515000 | 78.3% | 696874 | 696874 | 696874 | 240891 | 0 | 188625.35 | 52265.65 | 52265.65 | TA workplan for $1,120,000 is pending approval. There are limited disbursements for basic functioning of the PMU until then. |  |  |  | INV
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 389 | N | I | CTC | 0 |  | 0 |  | 2005-04-01 |  | 2008-04-01 | 2013-12-01 |  |  | 2500000 | 0 | 2500000 | 881148.87 | 35.25% | 1618851.13 | 0 | 0 | 280000 | 0 | 98000 | 182000 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Estimated date of completion is December 2013. | None.
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 376 | N | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2013-12-01 |  |  | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 280000 | 0 | 280000 | 0 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Estimated date of completion is December 2013. | None. |  | 2006-11-01
ONG | UNIDO | CTC phase-out for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 402 | A | I | CTC | 347 | 347 | 347 |  | 2006-07-01 | 2007-06-01 | 2007-07-01 | 2013-07-01 |  |  | 399046 | 0 | 399046 | 224445.89 | 56.25% | 174600.11 | 18787.36 | 35000 | 29928 | 0 | 16833 | 13095 | 1409 | Local supplier (Hind Erectors) dismantled old equipment and installed the new one. The installation of multiple effect evaporator awarded earlier to another local supplier (Food & Biotech) is still pending delaying the project completion. UNIDO country office is taking care of the issue as well as of the one pertaining to the low disbursement of obligated funds, related to the long overdue submission of the interim and final reports by local sub-contractors. | A joint UNIDO/NOU inspection mission to the project sites for evaluation of the project results is planned for 2013. The project is expected to be completed in 2013. Reason for the delay: Installation of equipment procured from local supplier took longer than expected. In 2013 it is planned that US$ 40,000 will be obligated and at least US$ 35,000 will be disbursed. Unutilized funds will be returned after financial completion of the project. |  |  | INV
ONG | UNIDO | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 385 | A | I | CTC | 733 | 733 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 | 2013-07-01 |  |  | 3500000 | 0 | 3500000 | 3244925.14 | 92.71% | 255074.86 | 210308.72 | 100000 | 262500 | 0 | 243369 | 19131 | 15773 | Local supplier (Hind Erectors) dismantled old equipment and installed the new one. Installation of multiple effect evaporator awarded earlier to another local supplier (Food & Biotech) is still pending delaying the project completion. UNIDO country office is taking care of the issue as well as of the one pertaining to the low disbursement of obligated funds, related to the long overdue submission of the interim and final reports by local sub-contractors. | Procurement of additional backup glass lined reactor for Nikava Pharmaceuticals is required for certification of the new installation by the local environmental authorities. The project is expected to be completed in 2013. Reason for the delay: Installation of equipment procured from local supplier took longer than expected. |  |  | INV
ONG | France | Demonstration project for disposal of unwanted ODS |  | LAC | MEX | DES | 63 | DEM | 155 | A | I | CFC | 0 |  | 0 |  | 2011-04-01 | 2012-08-16 | 2013-03-01 | 2013-06-01 |  |  | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 65000 | 0 |  | 65000 |  | The French bi-lateral contribution is implemented through UNIDO and at the same time as UNIDO's share of the project. The Trust Fund was signed in the margins of Rio+20 between the DGs of both AFD and UNIDO. All funds have been released to UNIDO for the implementation. See UNIDO's PR for implementation details.
ONG | Japan | Pilot demonstration project on ODS waste management and disposal |  | ASP | CPR | DES | 67 | DEM | 521 | A | I |  | 0 |  | 0 |  | 2012-07-01 |  | 2015-01-01 |  |  |  | 900000 | 0 | 900000 |  | 0% | 900000 |  |  | 109000 | 0 |  | 109000
ONG | UNDP | Demonstration project on end of life ODS management and destruction | Individual | LAC | COL | DES | 66 | DEM | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-09-01 | 2015-04-01 | 2015-04-01 |  |  | 1195000 | 0 | 1195000 | 30444.95 | 2.548% | 1164555.05 | 62597.7 | 465822.02 | 89625 | 0 | 2283.3713 | 87341.6288 | 4694.8275 | Project document signed. Contract with international expert signed. First expert mission took place in November 2012. | Continued work with 3 companies that will participate in the project. | 2012 |  | Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 62 | DEM | 46 | N | I | No_ODP | 45.3 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-12-01 | 2014-12-01 |  |  | 525200 | 0 | 525200 | 3079.22 | 0.5863% | 522120.78 | 0 | 208848.312 | 39390 | 0 | 230.9415 | 39159.0585 | 0 | Civl works at the cement plant have been completed (co-finance by Government of Cuba). Development of technical specs. Procurement process on-going. | Bids being analyzed. | 2010 |  | Non-Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 63 | DEM | 33 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-03-01 | 2014-03-01 |  |  | 198000 | 0 | 198000 | 77074.15 | 38.93% | 120925.85 | 4000 | 48370.34 | 17820 | 0 | 6936.6735 | 10883.3265 | 360 | Progress report on ODS-demos was submitted. UNDP staff member met with the Energy Commission and the NOU in April 2012 to discuss coordination. Project progressed in cooperation with the UNDP GEF project and its rebate scheme for returning used refrigerators (incentive to replace them with more energy-efficient ones) launched in September. As of November 2012, 470 refrigerators removed from households and replaced. A mobile ODS recovery unit arrived from Germany (this is part of the GEF project, as is the rebate scheme) and the operators are being trained at the moment to collect the ODSs which will be put in custody of the Project team. | Mission by UNDP staff planned in 2013. The mix of substances contained in the collected refrigerators through the rebate scheme is being analysed, to allow for extrapolations of quantities to be expected. These quantities of ODSs are being handled now by the MLF-project team; by adding the quantities collected prior by EPA and kept for later disposal, the critical mass of ODS collected to be shipped is anticipated to be reached by end of 2013. | 2011 |  | Non-Investment
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2015-01-31 | 2015-09-01 |  |  | 1227885 | 0 | 1227885 | 0 | 0% | 1227885 | 0 | 425577 | 85952 | 0 | 0 | 85952 | 0 | The project was approved in 2012. Detailed work plan for implementation prepared and agreed upon between FECO and UNIDO. Project duration is 30 months. Since the project is also co-financed by Japan and the funds for the Japanese component was received end December 2012, implementation of the project could only be initiated in 2013. | .- Technical validation of the four facilities where destruction activities will take place; .- Development of training contents and organization of initial training courses; .- First batched of ODS waste destroyed in two of the four facilities |  |  | INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | LAC | MEX | DES | 63 | DEM | 154 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2013-03-31 | 2015-04-01 |  |  | 927915 | 0 | 927915 | 156567.76 | 16.87% | 771347.24 | 279138.91 | 300000 | 69594 | 0 | 11743 | 57851 | 20935 | TOR for incineration services were negotiated with the Government of Mexico and recycling facilities as well as an incineration facility were visited in the first quarter of 2013. International bidding was conducted in May and a destruction facility selected. Change of Government delayed signature of the contract as the selected incineration facility required extension of an authorization by the Government. The collected CFCs (52 tons) will therefore be incinerated early 2013. | Incineration of 52 tons of CFC. One bidding for incineration services is being conducted and is expected to be completed by May (for a total of 80 tons of CFCs). Depending on the amount available for destruction second bidding may take place in 2013. |  |  | INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | AFR | NIR | DES | 67 | DEM | 133 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2014-07-31 | 2015-03-01 |  |  | 911724 | 0 | 911724 | 0 | 0% | 911724 | 0 | 20000 | 63821 | 0 | 0 | 63821 | 0 | The project was approved at the 67th Meeting of the Executive Committee. PAD was issued and Gov. was informed about the approval. | Start of project. Timeline of project will be discussed with project developer (EOS Climate) and NOU, should there be slight changes to project document, in particular the first steps concerning aggregation and testing. In parallel, a contract between UNIDO and the project developer will be made stipulating the terms for transport and destruction of ODS. Discussions with project developer are being held on how to go about the current low prices of carbon credits. They will be able to give more information by July 2013. The NOU are informed and a work plan is being agreed with them. In light of the above, project duration of 24 months does not seem to be feasible. |  |  | INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | EUR | TUR | DES | 66 | DEM | 99 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2012-06-01 | 2014-04-30 | 2014-04-01 |  |  | 1076250 | 0 | 1076250 | 124208.64 | 11.54% | 952041.36 | 22568.3 | 200000 | 80719 | 0 | 9316 | 71403 | 1692.6225 | The project was approved at the 66th Meeting of the Executive Committee. The TOR for incineration services were negotiated with PanGulf company and a contract was signed. Recycling facilities were visited in Istanbul, Ankara and Izmir (together with PanGulf). Information meetings were held with RAC servicing companies and representatives of the municipalities to raise awareness. TOR for training activities provided by PanGulf were negotiated. There was an error in the planned completion date, it should read correctly Apr.14 | Information and training workshop were held in Istanbul and Izmir in March 2013. In April PanGulf will collect the first 30 tons of CFCs and ship to destruction. A thrid workshop for technicians at the PanGulf destruction facility in Saudi Arabia will take place during the second half of 2013. A further 30 tons of CFCs will be destroyed. |  |  | INV
CLO | UNEP | Development of tracking system for ODS and ODS-based equipment | Individual | GLO | GLO | SEV | 34 | TAS | 232 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2002-12-01 |  |  | 2005-03-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Project Closed |  |  |  | Non Investment
CLO | UNEP | Training modules on management of ODS phase out in SMEs | Individual | GLO | GLO | SEV | 19 | TAS | 112 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  |  | 2006-12-01 | 40000 | -19000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 5200 | -2470 | 2730 | 0 | 0 | Project Closed |  |  | 1999-12-01 | Non Investment
FIN | Canada | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 180 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-02-01 | 2000-04-01 |  | 2001-07-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | English version of manual completed in April 2001. Printing and dissemination has been completed. |  | 1999 |  | Non-Inv.
FIN | Finland | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 184 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2001-11-01 | 2002-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1999 | 2001-06-01
FIN | Japan | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 254 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2004-11-01 | 2004-11-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | PCR is expected to be submitted by Sweden Government in early autumn 2007. |  | 2003
FIN | Sweden | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 253 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-10-01 |  | 2006-02-01 | 2006-12-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | At the 41st meeting of the Executive Committee, the Government of Sweden in collaboration with the Government of Japan received approval for developing a Handbook related to the servicing sector. A Draft outline of the Handbook with a broader perspective in accordance with the ExCom decision was developed in March 04. Two consultants were recruited and a first full Draft was developed in Feb. 2005. The Draft was revised substantially twice before the text was sent for a review by UNEP/DTIE, Japan and the NOUs of Croatia and the Philippines in June 2005. Responses were received in Aug-Sept 2005. After taking into account the comments received, the layout and printing was organised. The printed version was received in February 2006 and the distribution to all NOUs and relevant agencies was organised by UNEP. The Handbook is available at the UNEP and SEI web pages for down load. |  | 2003
FIN | UNEP | Prepare an inventory and assessment of environmentally sound and economically viable technologies and know-how conducive to phase out of ODS | Individual | GLO | GLO | SEV | 19 | TAS | 106 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 2000-12-01 | 1996-08-01 |  | 2004-04-01 | 2005-12-01 | 50000 | -27500 | 22500 | 22500 | 100% | 0 | 0 | 0 | 6500 | -3575 | 2925 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Update the OAIC diskette version (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Produce handbook on technology options especially for SMEs | Individual | GLO | GLO | SEV | 19 | TRA | 111 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-11-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  | 1999-07-01 | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 19 | TAS | 99 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-04-01 | 1999-01-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Translate prioritized OzonAction Programme documents into French and Spanish | Individual | GLO | GLO | SEV | 21 | TAS | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-12-01 |  | 1998-12-01 | 1999-08-01 | 40000 | -1191 | 38809 | 38809 | 100% | 0 | 0 | 0 | 5200 | -154.83 | 5045.17 | 0 | 0 | Project financially completed. ($ 73,040 plus $ 9,495 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Translation of the "Protecting the Ozone Layer" sectoral technical brochures | Individual | GLO | GLO | SEV | 12 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-09-01 | 1999-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Update existing technical brochure series to include 1994/95 TOC data | Individual | GLO | GLO | SEV | 21 | TAS | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 2001-01-01 | 2002-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 50,000 plus $ 6,500 returned ExCom 46) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Develop a handbook on the practical use of policy instruments | Individual | GLO | GLO | SEV | 21 | TAS | 130 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-11-01 | 1997-12-01 |  | 2003-06-01 | 2005-12-01 | 50000 | -10000 | 40000 | 40000 | 100% | 0 | 0 | 0 | 6500 | -1300 | 5200 | 0 | 0 | Project financially completed. |  |  | 1999-07-01 | Non Investment
FIN | UNEP | Prepare information papers and case studies | Individual | GLO | GLO | SEV | 19 | TRA | 109 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 2001-09-01 | 2001-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 | 0 | 0 | 5980 | 0 | 5980 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Update the OAIC diskette version including "Simple Search" versions of prioritized OzonAction publications | Individual | GLO | GLO | SEV | 21 | TAS | 125 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-10-01 | 2000-06-01 | 63000 | -15400 | 47600 | 47600 | 100% | 0 | 0 | 0 | 8190 | -2002 | 6188 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Quality review technology catalogs | Individual | GLO | GLO | SEV | 12 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-04-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Develop fact sheet describing win-win technology options relative to Kyoto and Montreal Protocols | Individual | GLO | GLO | SEV | 27 | TAS | 182 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2000-04-01 |  | 2002-12-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Information papers and fact sheets for evaluation of technical options to replace ODS | Individual | GLO | GLO | SEV | 12 | TAS | 53 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1999-12-01 | 2000-01-01 | 60000 | -3500 | 56500 | 56500 | 100% | 0 | 0 | 0 | 7800 | -455 | 7345 | 0 | 0 | Project financially completed. |  |  | 1998-12-01 | Non Investment
FIN | UNEP | Update regulations to control ozone depleting substances | Individual | GLO | GLO | SEV | 27 | TAS | 183 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2001-09-01 | 2001-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training modules on policy design and setting up of legislation | Individual | GLO | GLO | SEV | 19 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Update the OAIC diskette version (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 140 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 26 | TAS | 167 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. ($ 6,300 plus $ 819 PSC returned ExCom 31) |  |  |  | Non Investment
FIN | UNEP | Develop sector specific videos | Individual | GLO | GLO | SEV | 16 | TAS | 75 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-05-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Update Technology Sourcebooks and quality review updated material | Individual | GLO | GLO | SEV | 16 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  | 2002-04-01 | Non Investment
FIN | UNEP | Updating OAIC diskette and on-line system (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Information papers and fact sheets to assist evaluation of technical options to replace ODS (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a training strategy | Individual | GLO | GLO | SEV | 09 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | OzonAction newsletter and special supplements (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 68 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 | 0 | 31850 | 0 | 31850 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 19 | TAS | 108 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 | 0 | 31850 | 0 | 31850 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of technical documents and newsletter | Individual | GLO | GLO | SEV | 06 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 320000 | 0 | 320000 | 320000 | 100% | 0 | 0 | 0 | 41600 | 0 | 41600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 21 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-01-01 |  | 1997-12-01 | 1999-01-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 | 0 | 43550 | 0 | 43550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 |  | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 |  | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 |  | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | Project cancelled at the 40th ExCom. |  |  | 1997-11-01 | INV
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 |  | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | Cancelled - 37th ExCom |  |  |  | INV
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 |  | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. |  |  |  | INV
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | 1997-06-01 | INV
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 |  | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | Project cancelled due to financial difficulties. |  |  |  | INV
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 |  | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 1.4097e-11 | 0 | Project has been cancelled. |  |  |  | INV
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 |  | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | Subproject cancelled. |  |  | 1998-12-01 | INV
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 |  | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 |  | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | Project cancelled at the 35th ExCom Meeting. |  |  |  | INV
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 |  | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | 1996-05-01 | INV
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 2000-01-01 | INV
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic freezers at DeBao Refrigeration Equipment Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 233 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-06-01 | 1208176 | -683628 | 524548 | 524548 | 100% | 0 | 0 | 0 | 157062.9 | -88871.88 | 68191.02 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Jilin Jinouer Electric Appliances Group Co. | Individual | ASP | CPR | REF | 23 | INV | 225 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-12-01 |  |  | 2003-09-01 | 2548360 | -1223403 | 1324957 | 1324957 | 100% | 0 | 0 | 0 | 331286.8 | -159041.81 | 172244.99 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 | 2000-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Andina Industrial S.A. | Individual | LAC | PER | REF | 15 | INV | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  |  | 2002-06-01 | 229816 | -75350 | 154466 | 154466 | 100% | 0 | 0 | 0 | 29876.08 | -9795.08 | 20081 | 0 | 0 | Canceled in 2000. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Reunidas S.A. (Inresa) | Individual | LAC | PER | REF | 15 | INV | 07 | A | D | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  |  | 2003-01-01 | 267641 | -91077 | 176564 | 176564 | 100% | 0 | 0 | 0 | 34793.33 | -11840.33 | 22953 | 0 | 0 | Canceled in 1999. Financially completed in 2003. |  | 1994 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29935.62 | -6664.58 | 23271.04 | 0 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1995 |  | Investment
CLO | UNIDO | Phasing out of CFCs in the manufacturing plant of domestic refrigerators of Radio Victoria Catamarca, S.A. | Individual | LAC | ARG | REF | 22 | INV | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  |  | 2001-07-01 | 599896 | -454313 | 145583 | 145583 | 100% | 0 | 0 |  | 77986 | -59090 | 18896 | 0 | 0 | CLO
CLO | UNIDO | Phasing out of CFCs at INDATEC/Industria de aplicacoes technico-domesticas Ltd. | Individual | AFR | MOZ | REF | 18 | INV | 04 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1997-03-01 |  |  | 2002-04-01 | 581515 | -246871 | 334644 | 334644 | 100% | 0 | 0 |  | 75597 | -32162 | 43435 | 0 | 0 | CLO |  |  | 1999-11-01
CLO | UNIDO | Phasing out of CFCs at Tanzania Domestic Appliance Manufacturers Ltd. | Individual | AFR | URT | REF | 18 | INV | 06 | A | I | CFC | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1997-03-01 |  |  | 2002-12-01 | 592790 | -101002 | 491788 | 491788.45 | 100% | -0.45 | 0 |  | 77063 | -13232 | 63831 | 0 | 0 | CLO |  |  | 1999-12-01
COM | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Multibras, S.A. | Individual | LAC | BRA | REF | 20 | INV | 57 | N | I | CFC | 1068.8 | 1068.8 | 0 | 0 | 1996-10-01 | 1997-07-01 | 1999-09-01 |  | 2001-12-01 |  | 4899790 | 0 | 4899790 | 4899790 | 100% | 0 | 0 | 0 | 636973.01 | 0 | 636973.01 | 0 | 0 | Completed in 2001. |  | 1996 | 1999-12-01 | Investment
FIN | Germany | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) | Individual | ASP | CPR | REF | 16 | INV | 115 | N | I | CFC | 174 | 174 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 1336918 | 0 | 1336918 | 1336918 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Oct 99 |  |  | 2000-01-01
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory | Individual | ASP | CPR | REF | 27 | INV | 282 | A | I | CFC | 95.5 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-04-01 |  | 2004-12-01 | 2006-10-01 | 1451137 | 0 | 1451137 | 1451137 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR has been submitted.
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100% | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | Completed. PCR has been sent |  |  |  | INV
FIN | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 |  | 2012-08-01 | 2012-08-01 | 686370 | 0 | 686370 | 686370 | 100% | 0 | 0 | 0 | 89228.1 | 0 | 89228.1 | 0 | 0 | On Aug. 22, 2012 a UEPRO representative visited Neba/Ikala and verified destruction of CFC-based equipment. With this verification action the project is completed. |  |  | 2001-09-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100% | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | 1999-10-01 | INV
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100% | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | Project completed and funding disbursed. PCR submitted Dec. 01. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100% | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | Project completed. |  |  | 2001-09-01 | INV
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | 2000-03-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100% | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | Project financially and physically completed. |  |  | 2000-01-01 | INV
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 100% | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | 1999-06-01 | INV
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100% | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | Project financially completed. |  |  | 2000-08-01 | INV
FIN | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | I | CFC | 174.2 | 174.2 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 |  | 2005-12-01 | 2006-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 164000 | 0 | 164000 | 0 | 0 | Project is completed. |  |  |  | INV
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100% | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | Project was completed; PCR submitted to 30th ExCOM. |  |  |  | INV
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100% | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. |  |  |  | INV
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100% | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358 | -0.1 | -0.1 | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | 1999-04-01 | INV
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100% | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100% | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100% | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | PCR has been submitted. Project is physically and financially completed. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100% | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | Project is completed. PCR has been submitted. |  |  | 1997-03-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 | 2005-01-01 | 510000 | -261775.31 | 248224.69 | 248224.69 | 100% | 0 | 0 |  | 66300 | -34030.79 | 32269.21 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2001-12-01 | INV
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 675165 | -276756 | 398409 | 398409 | 100% | 0 | 0 |  | 84268.15 | -39407.54 | 44860.61 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 | 2005-01-01 | 722906 | 302123 | 1025029 | 1025029 | 100% | 0 | 0 |  | 93977.78 | 35611.19 | 129588.97 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 | 2005-01-01 | 2724378 | -1093985 | 1630393 | 1630393 | 100% | 0 | 0 |  | 354169.14 | -142218 | 211951 | 0.14 | 0.14 | Project financially completed and balance funds returned. |  |  | 1999-11-01 | INV
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100% | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  | 1999-11-01 | INV
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. $5,096.82 will be returned. |  |  | 1996-01-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 | 2005-02-01 | 205893 | 0 | 205893 | 205893 | 100% | 0 | 0 |  | 26766 | 0 | 26766 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | I | CFC | 117.6 | 117.6 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 |  | 2006-12-01 | 2006-12-01 | 841750 | 0 | 841750 | 841750 | 100% | 0 | 0 |  | 109428 | 0 | 109428 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 09 | INV | 09 | N | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100% | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | 1997-07-01 | INV
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 09 | INV | 08 | N | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | 1997-01-01 | INV
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 09 | INV | 07 | N | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | 1997-07-01 | INV
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 09 | INV | 19 | N | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | 1998-01-01 | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100% | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100% | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100% | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | 1996-12-01 | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100% | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100% | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | 1996-12-01 | INV
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100% | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | 1996-04-01 | INV
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 08 | INV | 07 | N | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100% | -0.31 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-12-01 | INV
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | I | CFC | 4.62 | 4.62 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | The project was completed in July 99 |  |  | 1999-07-01 | INV
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 08 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 09 | N | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | Project completed. Funds returned at the 35th ExCom. |  |  | 1999-12-01 | INV
FIN | Italy | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (first tranche) | Multi-Year | ASP | CPR | REF | 38 | INV | 393 | A | I | CFC | 181 | 181 | 0 |  | 2002-11-01 | 2003-09-01 | 2005-11-01 |  | 2005-10-01 | 2005-12-01 | 1788991 | 0 | 1788991 | 1788991 | 100% | 0 | 0 |  | 161009 | 0 | 161009.19 | -0.19 | 0 | FIN |  | 2003 |  | Investment
FIN | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | I | CFC | 94.9 | 94.9 | 0 |  | 2001-07-01 | 2002-09-01 | 2003-10-01 |  | 2007-04-01 | 2008-12-01 | 1683135 | -91120 | 1592015 | 1592015 | 100% | 0 | 0 |  | 180348 | -10023.45 | 170324.55 | 0 | 0 | FIN |  | 2001 |  | Investment
FIN | UNDP | Demonstration programme to improve domestic refrigerator servicing and CFC recycling in service shops | Individual | LAC | BRA | REF | 06 | DEM | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-02-01 | 1993-12-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic chest freezers at Multibras, S.A. Electrodomésticos | Individual | LAC | BRA | REF | 17 | INV | 24 | N | I | CFC | 165.9 | 165.9 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-12-01 |  | 1997-12-01 | 1999-12-01 | 598499 | 0 | 598499 | 598499 | 100% | 0 | 0 | 0 | 77805 | 0 | 77805 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers by conversion to cyclo-pentane and HCF-134a at Metalurgica Venan Ltda. | Individual | LAC | BRA | REF | 28 | INV | 132 | N | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-02-01 |  | 2004-03-01 | 2009-07-01 | 741800 | -6793 | 735007 | 735007.3 | 100% | -0.3 | 0 | 0 | 91598 | -838.8045 | 90759.2325 | -0.037044 | 0 | Completed in 2004.Financially completed in 2009. |  | 1999 |  | Investment
FIN | UNDP | Demonstration programme for service centre technicians on CFC-11 venting and leakage from refrigerators during operation and servicing | Individual | LAC | CHI | REF | 06 | DEM | 02 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Unilemh Ltd. (Challenger) | Individual | LAC | COL | REF | 18 | INV | 21 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-07-01 | 155350 | -1561 | 153789 | 153789 | 100% | 0 | 0 | 0 | 20195.5 | -202.5 | 19993 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Polarix Electrodomesticos, S.A. | Individual | LAC | COL | REF | 13 | INV | 04 | A | I | CFC | 63 | 63 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 844824 | -205206 | 639618 | 639618 | 100% | 0 | 0 | 0 | 109827 | -26676.99 | 83150.01 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Corporacion de Electrodomesticos, S.A. (Corelsa) | Individual | LAC | COL | REF | 13 | INV | 08 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1999-07-01 | 2000-12-01 | 853432 | -166101 | 687331 | 687331 | 100% | 0 | 0 | 0 | 110946.2 | -21593.16 | 89353.04 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Haceb, S.A. | Individual | LAC | COL | REF | 13 | INV | 05 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1386314 | -340578 | 1045736 | 1045736 | 100% | 0 | 0 | 0 | 180220.7 | -44274.69 | 135946.01 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Icasa, S.A. | Individual | LAC | COL | REF | 13 | INV | 06 | A | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1410680 | -358123 | 1052557 | 1052557 | 100% | 0 | 0 | 0 | 183388.4 | -46556.41 | 136831.99 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Atlas Eléctrica S.A. | Individual | LAC | COS | REF | 18 | INV | 08 | A | D | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-04-01 |  | 1998-05-01 | 1999-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | Individual | ASP | CPR | REF | 32 | INV | 367 | N | I | CFC | 180.8 | 180.8 | 0 | 0 | 2000-12-01 | 2003-06-01 | 2004-01-01 |  | 2004-11-01 | 2011-08-01 | 788359 | -9293 | 779066 | 779066 | 100% | 0 | 0 | 0 | 96720 | -1140.1138 | 95579.8862 | 0 | 0 | Completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Honxiang Group, Laizhou Freezer Plant | Individual | ASP | CPR | REF | 23 | INV | 232 | N | I | CFC | 301.5 | 301.5 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2003-09-01 | 2005-03-01 | 1339203 | -6776 | 1332427 | 1332427 | 100% | 0 | 0 | 0 | 174096.4 | -881.39 | 173215.01 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1997 |  | Investment
FIN | UNDP | Conversion to cylopentane and R-134a in the manufacture of domestic freezers at Wanbao Freezer Industrial Corporation | Individual | ASP | CPR | REF | 24 | INV | 242 | N | I | CFC | 138.2 | 138.2 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-08-01 | 2004-06-01 | 1402370 | -52248 | 1350122 | 1350122 | 100% | 0 | 0 | 0 | 182308.1 | -6792.09 | 175516.01 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | Individual | ASP | CPR | REF | 25 | INV | 249 | N | I | CFC | 247.8 | 247.8 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2004-11-01 | 2008-10-01 | 2238580 | -1062 | 2237518 | 2237518 | 100% | 0 | 0 | 0 | 291015.4 | -138.4098 | 290876.9902 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 1998 | 2001-12-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Henan Freezer Factory | Individual | ASP | CPR | REF | 19 | INV | 168 | N | I | CFC | 167.7 | 167.7 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2001-06-01 | 2003-09-01 | 2550605 | -54725 | 2495880 | 2495880 | 100% | 0 | 0 | 0 | 331578.7 | -7113.66 | 324465.04 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Guingdao Haier General Freezer Company | Individual | ASP | CPR | REF | 19 | INV | 167 | N | I | CFC | 278.8 | 278.8 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2000-04-01 | 2003-07-01 | 2548280 | -22910 | 2525370 | 2525370 | 100% | 0 | 0 | 0 | 331276.4 | -2978.41 | 328297.99 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Changsha Zhongyi Group Corp. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 124 | A | I | CFC | 360.2 | 360.2 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 2000-09-01 | 2004-01-01 | 2961000 | -2311 | 2958689 | 2958689 | 100% | 0 | 0 | 0 | 384930 | -300 | 384630 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Guangdong Kelon Electrical Holding Company Ltd. | Individual | ASP | CPR | REF | 17 | INV | 123 | N | I | CFC | 767.2 | 767.2 | 0 | 0 | 1995-07-01 | 1997-04-01 | 1997-01-01 |  | 1999-06-01 | 2003-07-01 | 4483050 | -6913 | 4476137 | 4476137 | 100% | 0 | 0 | 0 | 582796.5 | -898.5 | 581898 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Wanbao Electrical Appliance Industries Co. | Individual | ASP | CPR | REF | 23 | INV | 226 | N | I | CFC | 574.2 | 574.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2003-12-01 | 2009-07-01 | 4566985 | 0 | 4566985 | 4566985 | 100% | 0 | 0 | 0 | 593708.04 | 0 | 593708.04 | 0 | 0 | Completed in 2003.Financially completed in 2009. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Prado, S.A. de C.V. | Individual | LAC | ELS | REF | 22 | INV | 03 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-06-01 | 2001-12-01 | 306229 | 0 | 306229 | 306229 | 100% | 0 | 0 | 0 | 39810 | 0 | 39810 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | Individual | ASP | IRA | REF | 35 | INV | 132 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2006-10-01 | 153447 | -30506 | 122941 | 122941 | 100% | 0 | 0 | 0 | 19948.11 | -3966.11 | 15982 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Electro Ara Co. | Individual | ASP | IRA | REF | 34 | INV | 85 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-06-01 | 2007-02-01 | 178784 | -45309 | 133475 | 133475 | 100% | 0 | 0 | 0 | 23241.92 | -5889.9203 | 17351.9997 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Shagayegh Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 112 | A | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 137985 | -514 | 137471 | 137471 | 100% | 0 | 0 | 0 | 17938.05 | -67.05 | 17871 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Mersun Co. | Individual | ASP | IRA | REF | 34 | INV | 89 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 162891 | -25194 | 137697 | 137697 | 100% | 0 | 0 | 0 | 21175.83 | -3274.83 | 17901 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Yakhchalsazi Anzabi Co. | Individual | ASP | IRA | REF | 34 | INV | 95 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 138935 | -16.9974 | 138918.0026 | 138918 | 100% | 0.0026 | 0 | 0 | 18061.55 | -1.5497 | 18059.9999 | 0.00033801 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Zenoz Sanaat Co. | Individual | ASP | IRA | REF | 34 | INV | 92 | A | I | CFC | 10.2 | 10.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2003-12-01 | 140036 | 0 | 140036 | 140036 | 100% | 0 | 0 | 0 | 18205 | 0 | 18205 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Rezvan Co. | Individual | ASP | IRA | REF | 34 | INV | 84 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 182182 | -34099 | 148083 | 148083 | 100% | 0 | 0 | 0 | 23683.66 | -4432.6636 | 19250.9964 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Sarmaye Sepahan Co. | Individual | ASP | IRA | REF | 34 | INV | 87 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 148525 | 0 | 148525 | 148525 | 100% | 0 | 0 | 0 | 19308 | 0 | 19308 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parsa Sazan Co. | Individual | ASP | IRA | REF | 34 | INV | 91 | A | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 212845 | -60001 | 152844 | 152844 | 100% | 0 | 0 | 0 | 27669.85 | -7799.85 | 19870 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sana Commercial Co. | Individual | ASP | IRA | REF | 34 | INV | 109 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 156286 | -367.0007 | 155918.9993 | 155919 | 100% | -0.0007 | 0 | 0 | 20317.18 | -48.1797 | 20269.0004 | -9.0998e-05 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sepand Afroz Co. | Individual | ASP | IRA | REF | 34 | INV | 94 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 172881 | -13071 | 159810 | 159810 | 100% | 0 | 0 | 0 | 22474.53 | -1698.53 | 20776 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ghaynar Khazar Co. | Individual | ASP | IRA | REF | 34 | INV | 97 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-11-01 | 2003-11-01 | 191092 | -30740 | 160352 | 160352 | 100% | 0 | 0 | 0 | 24841.96 | -3995.96 | 20846 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Hanzad Co. | Individual | ASP | IRA | REF | 34 | INV | 100 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2007-03-01 | 199627 | -28424 | 171203 | 171203 | 100% | 0 | 0 | 0 | 25951.51 | -3694.5098 | 22257.0002 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ideal Sardsir Co. | Individual | ASP | IRA | REF | 34 | INV | 90 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 187907 | -13311 | 174596 | 174596 | 100% | 0 | 0 | 0 | 24427.91 | -1729.91 | 22698 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Boloorin Yazd Refrigerator Co. | Individual | ASP | IRA | REF | 34 | INV | 86 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2005-09-01 | 212320 | -37255 | 175065 | 175065 | 100% | 0 | 0 | 0 | 27601.6 | -4842.6 | 22759 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Yakhchalsazi Yazd Co. | Individual | ASP | IRA | REF | 34 | INV | 82 | A | I | CFC | 30 | 30 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 248646 | -43159 | 205487 | 205487 | 100% | 0 | 0 | 0 | 32323.98 | -5610.98 | 26713 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Golsarma Co. | Individual | ASP | IRA | REF | 34 | INV | 110 | A | I | CFC | 28.3 | 28.3 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 230066 | -13115 | 216951 | 216951 | 100% | 0 | 0 | 0 | 29908.58 | -1704.58 | 28204 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parto Shiva Sanaat | Individual | ASP | IRA | REF | 35 | INV | 136 | A | I | CFC | 23.9 | 23.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2007-01-01 | 283948 | -36625 | 247323 | 247323 | 100% | 0 | 0 | 0 | 36913.24 | -4761.239 | 32152.001 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at General Industries | Individual | ASP | IRA | REF | 34 | INV | 96 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 428197 | 0 | 428197 | 428197 | 100% | 0 | 0 | 0 | 55666 | 0 | 55666 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Sanyo Industries (Malaysia) Berhad | Individual | ASP | MAL | REF | 18 | INV | 74 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 183260 | -1 | 183259 | 183259 | 100% | 0 | 0 | 0 | 23823.8 | 0.2 | 23824 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of refrigeration products at Oyl Appliances | Individual | ASP | MAL | REF | 13 | INV | 42 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-12-01 |  | 1997-12-01 | 2002-03-01 | 625100 | -38549 | 586551 | 586551 | 100% | 0 | 0 | 0 | 81263 | -5011 | 76252 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of home refrigerators at Sharp Roxy Appliance Corp. | Individual | ASP | MAL | REF | 12 | INV | 29 | A | D | CFC | 65 | 65 | 0 | 0 | 1994-03-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 962000 | -103353 | 858647 | 858647 | 100% | 0 | 0 | 0 | 125060 | -13436 | 111624 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Blyfridge Ltd. | Individual | AFR | MAR | REF | 15 | INV | 05 | A | I | CFC | 2 | 2 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 197208 | -20441.78 | 176766.22 | 176766 | 100% | 0.22 | 0 | 0 | 25637.04 | -2658.0414 | 22978.97 | 0.028599 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at A.H. Bahemia | Individual | AFR | MAR | REF | 15 | INV | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 213500 | -25495 | 188005 | 188005 | 100% | 0 | 0 | 0 | 27755 | -3314 | 24441 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Ensambladora de Refrigeradores (Enresa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 30 | A | I | CFC | 47 | 47 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 867033 | -51480.82 | 815552.18 | 815552 | 100% | 0.18 | 0 | 0 | 112714.3 | -6693.2866 | 106020.99 | 0.0234 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Estufas y Refrigeradores Nacionales S.A. (Erna, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 35 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-09-01 | 2000-12-01 | 1038309 | -49630 | 988679 | 988679 | 100% | 0 | 0 | 0 | 134980.2 | -6452.17 | 128528.03 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Supermatic, S.A. (Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 34 | A | I | CFC | 366 | 366 | 0 | 0 | 1994-12-01 | 1996-03-01 | 1996-06-01 |  | 1997-04-01 | 2000-12-01 | 2017517 | -5120 | 2012397 | 2012397 | 100% | 0 | 0 | 0 | 262277.2 | -666.22 | 261610.98 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Astral (Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 31 | A | I | CFC | 344 | 344 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 2439932 | -80899.32 | 2359032.68 | 2359033 | 100% | -0.32 | 0 | 0 | 317191.2 | -10517.1516 | 306674.09 | -0.0416 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Lenche S.A. (Inlensa) | Individual | LAC | PER | REF | 15 | INV | 06 | A | I | CFC | 6 | 6 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 2002-09-01 | 2003-11-01 | 201443 | -29670 | 171773 | 171773 | 100% | 0 | 0 | 0 | 26187.59 | -3856.59 | 22331 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Alfa S.A. | Individual | LAC | PER | REF | 15 | INV | 03 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-09-01 | 2000-12-01 | 252727 | -567 | 252160 | 252160 | 100% | 0 | 0 | 0 | 32854.51 | -73.51 | 32781 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrial Selva S.A. (Indusel) | Individual | LAC | PER | REF | 15 | INV | 08 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2002-03-01 | 412098 | -331 | 411767 | 411767 | 100% | 0 | 0 | 0 | 53572.74 | -42.74 | 53530 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coldex S.A. | Individual | LAC | PER | REF | 15 | INV | 05 | A | I | CFC | 67.4 | 67.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1998-01-01 | 2000-12-01 | 748966 | -102197 | 646769 | 646769 | 100% | 0 | 0 | 0 | 97365.58 | -13285.58 | 84080 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Matsushita Electric Philippines Corporation (Mepco) | Individual | ASP | PHI | REF | 18 | INV | 39 | A | R | CFC | 47 | 47 | 0 | 0 | 1995-11-01 | 1996-06-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 112244 | -4513 | 107731 | 107731 | 100% | 0 | 0 | 0 | 14591.72 | -586.72 | 14005 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Glacio Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 05 | A | I | CFC | 6.8 | 6.8 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 239500 | -26842.62 | 212657.38 | 212657 | 100% | 0.38 | 0 | 0 | 31135 | -3490.0006 | 27644.95 | 0.049399 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Associated Electrical Corporation (AEC) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 04 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1998-08-01 | 2000-12-01 | 250114 | -912 | 249202 | 249202 | 100% | 0 | 0 | 0 | 32514.82 | -118.82 | 32396 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Regnis (Lanka) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 06 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 284324 | -18407 | 265917 | 265917 | 100% | 0 | 0 | 0 | 36962.12 | -2393.12 | 34569 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at El-Effendi Refrigerator Plant | Individual | ASP | SYR | REF | 26 | INV | 39 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2007-01-01 | 182802 | -25050 | 157752 | 157752 | 100% | 0 | 0 | 0 | 23764.26 | -3256.2644 | 20507.9956 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ammar Industrial Establishment | Individual | ASP | SYR | REF | 26 | INV | 33 | A | I | CFC | 56 | 56 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 331080 | -222 | 330858 | 330858 | 100% | 0 | 0 | 0 | 43040.4 | -29.4 | 43011 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320.4144 | 75569.5856 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | I | CFC | 65.5 | 65.5 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89092.9 | -856.05 | 88236.85 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1997-12-01 | Investment
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (second tranche) | Multi-Year | ASP | CPR | REF | 41 | INV | 406 | A | I | CFC | 318 | 318 |  |  | 2003-12-01 | 2006-12-01 | 2007-12-01 |  | 2009-12-01 | 2010-04-01 | 2171539 | -27541 | 2143998 | 2143997.51 | 100% | 0.49 | 0 |  | 192239 | -2460 | 189779 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-Year | ASP | CPR | REF | 38 | INV | 394 | A | I | CFC | 600 | 600 |  |  | 2002-11-01 | 2003-09-01 | 2007-05-01 |  | 2007-06-01 | 2007-12-01 | 3400000 | 0 | 3400000 | 3399999.51 | 100% | 0.49 | 0 |  | 299200 | 0 | 299200 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electromenager, ENIEM | Individual | AFR | ALG | REF | 15 | INV | 09 | A | I | CFC | 425 | 425 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2002-09-01 | 6589550 | -82919 | 6506631 | 6506630.78 | 100% | 0.22 | 0 |  | 856642 | -12121 | 844521 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Frare S.A., Buenos Aires | Individual | LAC | ARG | REF | 23 | INV | 64 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-05-01 | 2002-09-01 | 514384 | -2300 | 512084 | 512084.45 | 100% | -0.45 | 0 |  | 66870 | -405 | 66465 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Bambi S.A., Santa Fe | Individual | LAC | ARG | REF | 23 | INV | 67 | A | I | CFC | 30.6 | 30.6 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 515258 | 0 | 515258 | 515257.55 | 100% | 0.45 | 0 |  | 66984 | -24 | 66960 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | Individual | EUR | BHE | REF | 35 | INV | 09 | A | I | CFC | 29 | 29 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2005-12-01 | 2006-12-01 | 536956 | -795 | 536161 | 536160.65 | 100% | 0.35 | 0 |  | 69065 | -87 | 68978 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Tecnigel Ltda | Individual | LAC | BRA | REF | 31 | INV | 172 | A | I | CFC | 2.5 | 2.5 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 34000 | -640 | 33360 | 33359.5 | 100% | 0.5 | 0 |  | 4420 | -90 | 4330 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Union Camerounaise d'Entreprise | Individual | AFR | CMR | REF | 18 | INV | 07 | A | I | CFC | 115.1 | 115.1 |  |  | 1995-11-01 | 1996-12-01 | 1997-03-01 |  | 2001-12-01 | 2002-12-01 | 1321400 | -20877 | 1300523 | 1300522.5 | 100% | 0.5 | 0 |  | 171782 | -2982 | 168800 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC at FAEM.SA | Individual | AFR | CMR | REF | 13 | INV | 05 | A | I | CFC | 62 | 62 |  |  | 1994-07-01 | 1995-11-01 | 1996-01-01 |  | 1996-06-01 | 2000-04-01 | 1935860 | -42791 | 1893069 | 1893069 | 100% | 0 | 0 |  | 251662 | -5953 | 245709 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b foam blowing agent and CFC-12 with HFC-134a in the manufacture of domestic refrigerators/ freezers at the Beijing Freezing Equipment Factory. | Individual | ASP | CPR | REF | 26 | INV | 259 | A | I | CFC | 35.3 | 35.3 |  |  | 1998-11-01 | 1999-09-01 | 2000-12-01 |  | 2000-12-01 | 2002-09-01 | 280901 | -8254 | 272647 | 272647.45 | 100% | -0.45 | 0 |  | 36517 | -1129 | 35388 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Hualing refrigerator plant | Individual | ASP | CPR | REF | 22 | INV | 204 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-04-01 | 879788 | -207466 | 672322 | 672322 | 100% | 0 | 0 |  | 114372 | -27109 | 87263 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Hefei Hualing Electronic Co., Ltd. | Individual | ASP | CPR | REF | 25 | INV | 253 | A | I | CFC | 82.8 | 82.8 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 785984 | -8264 | 777720 | 777719.64 | 100% | 0.36 | 0 |  | 102178 | -1235 | 100943 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zhejiang Rongsheng Electric Co. Ltd., Zhejiang, Deqing Country | Individual | ASP | CPR | REF | 23 | INV | 220 | A | I | CFC | 177.8 | 177.8 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1053910 | -67809 | 986101 | 986101.04 | 100% | -0.04 | 0 |  | 137008 | -9018 | 127990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | Individual | ASP | CPR | REF | 23 | INV | 222 | A | I | CFC | 132 | 132 |  |  | 1997-11-01 | 1998-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 1469029 | -1564 | 1467465 | 1467464.62 | 100% | 0.38 | 0 |  | 190974 | -4672 | 186302 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Moganshan Electric Appliances Co. | Individual | ASP | CPR | REF | 29 | INV | 308 | A | I | CFC | 667.6 | 667.6 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 2769118 | -754390 | 2014728 | 2014727.99 | 100% | 0.01 | 0 |  | 314603 | -83334 | 231269 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejian Electrical Equipment Co. | Individual | ASP | CPR | REF | 29 | INV | 336 | A | I | CFC | 199 | 199 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-09-01 | 2189782 | -42893 | 2146889 | 2146888.98 | 100% | 0.02 | 0 |  | 250876 | -4718 | 246158 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group | Individual | ASP | CPR | REF | 22 | INV | 207 | A | I | CFC | 423 | 423 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 2394178 | -10688 | 2383490 | 2383489.52 | 100% | 0.48 | 0 |  | 311243 | -1880 | 309362 | 1 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Little Swan Electric (Jingzhou) Co. Ltd. | Individual | ASP | CPR | REF | 32 | INV | 365 | A | I | CFC | 211.9 | 211.9 |  |  | 2000-12-01 | 2001-06-01 | 2003-12-01 |  | 2004-05-01 | 2005-09-01 | 2392316 | 0 | 2392316 | 2392316.08 | 100% | -0.08 | 0 |  | 273155 | -253 | 272902 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 by hydrocarbon isobutane and cyclopentane at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 17 | INV | 119 | A | I | CFC | 360 | 360 |  |  | 1995-07-01 | 1996-03-01 | 1997-07-01 |  | 2003-12-01 | 2004-12-01 | 2790320 | 0 | 2790320 | 2790320.21 | 100% | -0.21 | 0 |  | 362742 | -1 | 362741 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and HFC-134a in the production of refrigerators at Banshen Electric Appliances Co. | Individual | ASP | CPR | REF | 31 | INV | 357 | A | I | CFC | 563 | 563 |  |  | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-06-01 | 2005-04-01 | 2988840 | -196425 | 2792415 | 2792415.49 | 100% | -0.49 | 0 |  | 338772 | -22093 | 316679 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Hangzhou Huari Refrigerator Co. | Individual | ASP | CPR | REF | 18 | INV | 147 | A | I | CFC | 338 | 338 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 2827911 | -13884 | 2814027 | 2814027.14 | 100% | -0.14 | 0 |  | 367628 | -2384 | 365244 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Aucma Electric Appliances Group Co. | Individual | ASP | CPR | REF | 20 | INV | 173 | A | I | CFC | 708 | 708 |  |  | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 1998-12-01 | 2002-07-01 | 2914904 | 0 | 2914904 | 2914904.08 | 100% | -0.08 | 0 |  | 378938 | -192 | 378746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the freezer plant of Xing Xing Electric Appliances Industrial Co. | Individual | ASP | CPR | REF | 23 | INV | 223 | A | I | CFC | 348 | 348 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2002-04-01 | 3346941 | -334438 | 3012503 | 3012503.12 | 100% | -0.12 | 0 |  | 435102 | -44097 | 391005 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Changshu Refrigerating Equipment Works (Baixue), Changsu | Individual | ASP | CPR | REF | 23 | INV | 221 | A | I | CFC | 425.7 | 425.7 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 3548775 | -521956 | 3026819 | 3026819.15 | 100% | -0.15 | 0 |  | 461341 | -68478 | 392863 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigeration plant of Hefei Meiling | Individual | ASP | CPR | REF | 22 | INV | 196 | A | I | CFC | 849 | 849 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1998-12-01 | 2002-09-01 | 3247877 | -44594 | 3203283 | 3203282.91 | 100% | 0.09 | 0 |  | 422224 | -6457 | 415767 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Helwan Company for Metallic Appliances domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 38 | A | I | CFC | 7.5 | 7.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 644239 | -29419 | 614820 | 614820 | 100% | 0 | 0 |  | 83751 | -3951 | 79800 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Super Bosh Factory domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 39 | A | I | CFC | 13 | 13 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 760066 | -34709 | 725357 | 725357 | 100% | 0 | 0 |  | 98809 | -4662 | 94147 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at International Co. for Refrigeration and Appliances (Iberna) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 42 | A | I | CFC | 19 | 19 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 852738 | -38941 | 813797 | 813797 | 100% | 0 | 0 |  | 110856 | -5230 | 105626 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at El Nasr Company for Electric and Electronic Apparatus (Philips) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 43 | A | I | CFC | 22.5 | 22.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 854690 | -39030 | 815660 | 815660 | 100% | 0 | 0 |  | 111110 | -5242 | 105868 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Islamic Company for Industrialization (Siltal) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 40 | A | I | CFC | 26 | 26 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 866633 | -39576 | 827057 | 827057 | 100% | 0 | 0 |  | 112662 | -5315 | 107347 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Electrostar for Refrigeration Co. | Individual | AFR | EGY | REF | 13 | INV | 33 | A | I | CFC | 46 | 51 |  |  | 1994-07-01 | 1995-02-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1450585 | -13996 | 1436589 | 1436589 | 100% | 0 | 0 |  | 188576 | -2115 | 186461 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Société Mondiale pour Refroidissement (Alaska) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 41 | A | I | CFC | 55 | 55 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 1518606 | -69349 | 1449257 | 1449257 | 100% | 0 | 0 |  | 197419 | -9314 | 188105 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Kiriazi Refrigerators Manufacturing Co. | Individual | AFR | EGY | REF | 13 | INV | 35 | A | I | CFC | 137 | 137 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1643040 | -52934 | 1590106 | 1590106 | 100% | 0 | 0 |  | 213595 | -7209 | 206386 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plants of Delta Industrial Co. | Individual | AFR | EGY | REF | 13 | INV | 32 | A | I | CFC | 97 | 117 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1997-05-01 | 2000-07-01 | 2611986 | -133089 | 2478897 | 2478897 | 100% | 0 | 0 |  | 339558 | -17812 | 321746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Guyana Refrigerator Ltd., Guyana (GRL) | Individual | LAC | GUY | REF | 23 | INV | 05 | A | I | CFC | 7.2 | 7.2 |  |  | 1997-11-01 | 1998-08-01 | 1999-06-01 |  | 2001-04-01 | 2002-09-01 | 461000 | 0 | 461000 | 461000.01 | 100% | -0.01 | 0 |  | 59930 | -6 | 59924 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at the Ariz Pooyaye Sanat (Ariz Co.) | Individual | ASP | IRA | REF | 35 | INV | 124 | A | I | CFC | 7.6 | 7.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 86365 | -3752 | 82613 | 82612.98 | 100% | 0.02 | 0 |  | 11227 | -504 | 10723 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Borna Sanat Arak | Individual | ASP | IRA | REF | 35 | INV | 127 | A | I | CFC | 8 | 8 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2007-05-01 | 108238 | -802 | 107436 | 107435.59 | 100% | 0.41 | 0 |  | 14071 | -104 | 13967 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Yaghoubali Bazdid Vahdat (Isun Co.) | Individual | ASP | IRA | REF | 35 | INV | 125 | A | I | CFC | 10.5 | 10.5 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 131605 | -2900 | 128705 | 128704.73 | 100% | 0.27 | 0 |  | 17109 | -404 | 16705 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Monark Co. | Individual | ASP | IRA | REF | 18 | INV | 17 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 369939 | -859 | 369080 | 369079.6662 | 100% | 0.3338 | 0 |  | 48092 | -188 | 47904 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Gadook Industries, Co. | Individual | ASP | IRA | REF | 18 | INV | 15 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 373838 | -944 | 372894 | 372894.3966 | 100% | -0.3966 | 0 |  | 48599 | -200 | 48399 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Movalled Home Appliances Co. | Individual | ASP | IRA | REF | 18 | INV | 12 | A | I | CFC | 70 | 70 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 607732 | -1500 | 606232 | 606231.7394 | 100% | 0.2606 | 0 |  | 79005 | -320 | 78685 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Machine Manufacturing Co. | Individual | ASP | IRA | REF | 18 | INV | 13 | A | I | CFC | 62 | 62 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 608605 | -1737 | 606868 | 606867.5278 | 100% | 0.4722 | 0 |  | 79119 | -351 | 78768 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Faritz, Iran | Individual | ASP | IRA | REF | 18 | INV | 16 | A | I | CFC | 109 | 109 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 612504 | -1822 | 610682 | 610682.2582 | 100% | -0.2582 | 0 |  | 79626 | -363 | 79263 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Lorestan Refrigerator Manufacturing Industries | Individual | ASP | IRA | REF | 18 | INV | 14 | A | I | CFC | 94 | 94 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 615018 | -1793 | 613225 | 613225.4118 | 100% | -0.4118 | 0 |  | 79952 | -359 | 79593 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase-out CFC-11 and CFC-12 | Individual | ASP | IRA | REF | 11 | INV | 08 | A | I | CFC | 757 | 757 |  |  | 1993-11-01 | 1994-12-01 | 1995-11-01 |  | 1997-12-01 | 2002-09-01 | 3228395 | 5674963 | 8903358 | 8903358 | 100% | 0 | 0 |  | 419691 | 735911 | 1155602 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Household Appliance Manufacturing Co. (HAMCO) | Individual | ASP | JOR | REF | 13 | INV | 19 | A | I | CFC | 21.2 | 21.2 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 775602 | 0 | 775602 | 775602.11 | 100% | -0.11 | 0 |  | 100828 | -19 | 100809 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at National Refrigeration Co. (NRC) | Individual | ASP | JOR | REF | 13 | INV | 18 | A | I | CFC | 14.3 | 19.3 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-07-01 | 813887 | -29 | 813858 | 813857.62 | 100% | 0.38 | 0 |  | 105805 | -171 | 105634 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Middle East Electrical Industries Co. Ltd. | Individual | ASP | JOR | REF | 13 | INV | 20 | A | I | CFC | 16.6 | 23 |  |  | 1994-07-01 | 1994-12-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 883153 | -51 | 883102 | 883102.34 | 100% | -0.34 | 0 |  | 114810 | -189 | 114621 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Lebanese Modern Industrial and Trading Co. | Individual | ASP | LEB | REF | 22 | INV | 19 | A | I | CFC | 135 | 135 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1999-12-01 | 2002-10-01 | 1313121 | -65527 | 1247594 | 1247593.65 | 100% | 0.35 | 0 |  | 170706 | -8776 | 161930 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS in the production of refrigerators and freezers at Electrical Household Appliance Manufacturing | Individual | AFR | LIB | REF | 32 | INV | 03 | A | I | CFC | 53.4 | 53.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-06-01 |  | 2004-03-01 | 2009-12-01 | 558113 | -1527 | 556586 | 556585.87 | 100% | 0.13 | 0 |  | 71392 | -168 | 71224 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at the refrigerator plant of Frinko | Individual | EUR | MDN | REF | 20 | INV | 03 | A | I | CFC | 104 | 104 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1998-12-01 | 2001-12-01 | 1081724 | -556 | 1081168 | 1081168.35 | 100% | -0.35 | 0 |  | 140624 | -295 | 140329 | 0 | 0 | FIN
FIN | UNIDO | Conversion of HCFC-141b technology (rigid foam) and HFC-134a (refrigeration) in the manufacture of domestic refrigerators and freezers at Manar | Individual | AFR | MOR | REF | 29 | INV | 33 | A | R | CFC | 38.6 | 38.6 |  |  | 1999-11-01 | 2000-04-01 | 2000-07-01 |  | 1999-12-01 | 2000-11-01 | 434183 | 0 | 434183 | 434183 | 100% | 0 | 0 |  | 26051 | 0 | 26051 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration equipment at De Johnson Ltd. | Individual | AFR | NIR | REF | 29 | INV | 53 | A | I | CFC | 9 | 9 |  |  | 1999-11-01 | 2000-09-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 123816 | 0 | 123816 | 123816 | 100% | 0 | 0 |  | 16096 | 0 | 16096 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at United Technologies Ltd. | Individual | AFR | NIR | REF | 28 | INV | 52 | A | I | CFC | 9.6 | 9.6 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-12-01 | 130579 | 0 | 130579 | 130578.84 | 100% | 0.16 | 0 |  | 16975 | -6 | 16969 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Onward Electrical Industry Ltd. | Individual | AFR | NIR | REF | 28 | INV | 51 | A | I | CFC | 10.7 | 10.7 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2003-12-01 | 2004-04-01 | 146927 | 0 | 146927 | 146927 | 100% | 0 | 0 |  | 19101 | 0 | 19101 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at A.G. Leventis | Individual | AFR | NIR | REF | 26 | INV | 30 | A | I | CFC | 19.1 | 19.1 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2003-03-01 | 2004-04-01 | 190420 | 0 | 190420 | 190420.01 | 100% | -0.01 | 0 |  | 24755 | 0 | 24755 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Soesons Ltd. | Individual | AFR | NIR | REF | 28 | INV | 48 | A | I | CFC | 16.1 | 16.1 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-08-01 | 221353 | 0 | 221353 | 221353 | 100% | 0 | 0 |  | 28776 | 0 | 28776 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at New Ltd. | Individual | AFR | NIR | REF | 26 | INV | 40 | A | I | CFC | 20.9 | 20.9 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2003-05-01 | 361770 | 0 | 361770 | 361769.86 | 100% | 0.14 | 0 |  | 47030 | 0 | 47030 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at Kolinton Technical Industries | Individual | AFR | NIR | REF | 26 | INV | 44 | A | I | CFC | 39.5 | 39.5 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2003-12-01 | 2004-06-01 | 674348 | -902 | 673446 | 673445.54 | 100% | 0.46 | 0 |  | 84178 | -216 | 83962 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Debo Industries Ltd. Nigeria | Individual | AFR | NIR | REF | 18 | INV | 10 | A | I | CFC | 52 | 52 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1048053 | 0 | 1048053 | 1048052.6 | 100% | 0.4 | 0 |  | 136247 | -44 | 136203 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Thermocool Eng. Co. Ltd. | Individual | AFR | NIR | REF | 18 | INV | 11 | A | I | CFC | 82 | 82 |  |  | 1995-11-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1465750 | 0 | 1465750 | 1465750.06 | 100% | -0.06 | 0 |  | 190548 | -10 | 190538 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the production of domestic refrigeration equipment at Ideal Appliances, Ltd. | Individual | ASP | PAK | REF | 35 | INV | 43 | A | I | CFC | 12.9 | 12.9 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2004-07-01 | 2005-09-01 | 173101 | -1342 | 171759 | 171759.09 | 100% | -0.09 | 0 |  | 22503 | -210 | 22293 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out ODS at the freezer factory of Hirra Farooq's (Pvt) Ltd. | Individual | ASP | PAK | REF | 23 | INV | 17 | A | I | CFC | 31.2 | 31.2 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 2003-08-01 | 2003-12-01 | 521580 | -3110 | 518470 | 518469.84 | 100% | 0.16 | 0 |  | 67805 | -511 | 67294 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Chest Freezer Factory of Riaz Electric Co. Ltd. | Individual | ASP | PAK | REF | 19 | INV | 09 | A | I | CFC | 48.2 | 48.2 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-12-01 | 2005-12-01 | 822987 | -4083 | 818904 | 818903.75 | 100% | 0.25 | 0 |  | 106988 | -699 | 106289 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the refrigerator and chest freezer plants of Pak Elektron Ltd. (PEL) | Individual | ASP | PAK | REF | 19 | INV | 10 | A | I | CFC | 68 | 68 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-10-01 | 2006-05-01 | 1210295 | -67215 | 1143080 | 1143080.24 | 100% | -0.24 | 0 |  | 157338 | -8973 | 148365 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFC-11 and CFC-12 in the production of domestic refrigerators and replacing them by cyclopentane and HFC-134a at Ratmil, Uzine Mecanica Sadu | Individual | EUR | ROM | REF | 20 | INV | 10 | A | I | CFC | 73.3 | 73.3 |  |  | 1996-10-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2002-05-01 | 937859 | 0 | 937859 | 937859.21 | 100% | -0.21 | 0 |  | 121922 | 0 | 121922 | 0 | 0 | FIN
FIN | UNIDO | Phase out ODS at the domestic refrigeration factory Arctic S.A. | Individual | EUR | ROM | REF | 18 | INV | 06 | A | R | CFC | 206 | 206.7 |  |  | 1995-11-01 | 1996-10-01 | 1997-05-01 |  | 1997-05-01 | 2000-07-01 | 1095300 | -48009 | 1047291 | 1047291 | 100% | 0 | 0 |  | 142389 | -6457 | 135932 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of ODS at three small domestic refrigerator factories in Sudan (Coldair Refrigerator Factory, Modern Refrigerator + Metal furniture Co., Sheet Metal Industries Co. Refrigerator Factory) | Individual | AFR | SUD | REF | 19 | INV | 06 | A | I | CFC | 7.28 | 7.3 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 2002-03-01 | 2003-05-01 | 100000 | -13637 | 86363 | 86363.36 | 100% | -0.36 | 0 |  | 13000 | -1791 | 11209 | 0 | 0 | FIN |  |  | 1997-08-01
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Alaman Co. | Individual | ASP | SYR | REF | 28 | INV | 60 | A | I | CFC | 15.9 | 15.9 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 215910 | -36884 | 179026 | 179026.39 | 100% | -0.39 | 0 |  | 28068 | -4832 | 23237 | -1 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Golden Penguin Co. | Individual | ASP | SYR | REF | 28 | INV | 45 | A | I | CFC | 18.4 | 18.4 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 247481 | -52260 | 195221 | 195221.44 | 100% | -0.44 | 0 |  | 32173 | -6834 | 25339 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Barada General Co. for Metallic Industry | Individual | ASP | SYR | REF | 15 | INV | 09 | A | I | CFC | 109 | 97 |  |  | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-12-01 | 2001-07-01 | 989650 | -95593 | 894057 | 894057.23 | 100% | -0.23 | 0 |  | 128655 | -12612 | 116043 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFC at Penguin (Syrian Batric Co.) | Individual | ASP | SYR | REF | 15 | INV | 05 | A | I | CFC | 82.3 | 77.3 |  |  | 1994-12-01 | 1996-01-01 | 1996-06-01 |  | 1996-12-01 | 2000-12-01 | 1719900 | -1241 | 1718659 | 1718659 | 100% | 0 | 0 |  | 223587 | -515 | 223072 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Al Hafez Refrigeration Co. | Individual | ASP | SYR | REF | 13 | INV | 04 | A | I | CFC | 106.7 | 100.7 |  |  | 1994-07-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 2001-05-01 | 2883277 | 0 | 2883277 | 2883277 | 100% | 0 | 0 |  | 374826 | 0 | 374826 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project to phase out ODS at the six small refrigerator manufacturers | Individual | AFR | TUN | REF | 19 | INV | 17 | A | I | CFC | 78.5 | 78.5 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 1997-05-01 | 2001-10-01 | 764557 | -124194 | 640363 | 640362.85 | 100% | 0.15 | 0 |  | 99392 | -16277 | 83115 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at three domestic refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 79 | A | I | CFC | 27 | 27 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -75965 | 295740 | 295740.37 | 100% | -0.37 | 0 |  | 48322 | -9937 | 38385 | 0 | 0 | FIN
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) |  | ASP | CPR | REF | 16 | INV | 116 | N | I | CFC | 29 |  | 0 |  | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 2000-05-01 | 2000-05-01 | 1643865 | 0 | 1643865 | 1643865 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Conversion of line to produce cyclopentane-152a/22 refrigerators completed, certified Aug96; CFCs eliminated. Final funding to follow verification of old equipment destruction, review of receipts, final safety certification, and initial production. |  | 1995 | 1999-12-01
ONG | UNIDO | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | Individual | ASP | IRQ | REF | 57 | INV | 07 | A | I | CFC | 193.6 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 | 2013-12-01 |  |  | 2161581 | 0 | 2161581 | 1158599.72 | 53.6% | 1002981.28 | 712979.03 | 500000 | 162119 | 0 | 86895 | 75224 | 53473.4273 | 1. Finalization of details in terms of supply for both R-600a and cyclopentane. 2. Equipment shipped by suppliers. | Plans for 2013: 1. Custom clearance for all UNIDO equipment. 2. Installation, testing and commissioning. The project is expected to be completed in 2013. Reason for the delay: The customs clearance has taken longer than expected. The remaining balance of the project is connected to the tender of the reclaim and additional tool kits. Contract will be established within a month and funds will be commited. UNIDO has tried every approch, finally we seem to have a chance to get matters through with the Ministry of Finance. In late April, UNIDO managed to obtain custom clearance for one shipment. For the other three shipments, we are working heavily with the Iraqi Ministries to obtain further custom clearance. |  |  | INV
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. |  |  |  | INV
FIN | Germany | Conversion of the use of CFC-12 to HC in the manufacture of thermostats at Foshan Tongbao Co., Ltd. | Individual | ASP | CPR | REF | 35 | INV | 384 | A | I | CFC | 11.5 |  | 0 |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2006-10-01 | 213271 | 0 | 213271 | 213271 | 100% | 0 | 0 | 0 | 27725 | 0 | 27725 | 0 | 0 | Project completed. PCR has been submitted.
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 26th ExCom. |  |  | 1997-09-01 | INV
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-06-01 | INV
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1997-12-01 | INV
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100% | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. |  |  |  | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100% | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. |  |  |  | INV
FIN | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 2050000 | -250684.64 | 1799315.36 | 1799315.36 | 100% | 0 | 0 |  | 235500 | -28798.16 | 206701.84 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem | Individual | AFR | ALG | REF | 26 | INV | 30 | A | I | CFC | 12.8 | 12.8 |  |  | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 167332 | -2890 | 164442 | 164441.7 | 100% | 0.3 | 0 |  | 21753 | -409 | 21343 | 1 | 0 | FIN
COM | UNDP | Terminal umbrella project for phase-out of the use of CFC-11, CFC-12 and R-502 (CFC-115) in the manufacture of refrigeration equipment | Individual | LAC | CHI | REF | 48 | INV | 160 | N | I | CFC | 21.7 | 21.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2009-04-01 |  | 2012-07-01 |  | 282025 | 0 | 282025 | 279373.03 | 99.06% | 2651.97 | 0 | 2121.576 | 21152 | 0 | 20953.1011 | 198.8989 | 0 | Completed in 2012. Some final payments pending. Equipment delivered to beneficiary companies and Hand Over Protocol Signed. | Completed in 2012. Some final payments pending. No activities in 2013. | 2006 |  | Investment
COM | UNDP | Sector phase out plan for CFCs in the refrigeration manufacturing sector (except domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 86 | A | I | CFC | 246.2 | 246.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-12-01 |  | 2009-12-01 |  | 1665188 | -565630.98 | 1099557.02 | 1099557.02 | 100% | 0 | 0 | 0 | 191422 | -65022.22 | 126399.78 | 0 | 0 | Completed in 2009. |  | 2002 |  | Investment
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-11-01 | 2007-06-01 | 204736 | -21870.06 | 182865.94 | 182865.94 | 100% | 0 | 0 |  | 26615.68 | -2843.1 | 23772.9 | -0.32 | -0.32 | Project completed. |  |  |  | INV
FIN | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | I | CFC | 181.3 | 181.3 | 0 | 0 | 2004-04-01 | 2005-08-01 | 2007-04-01 |  | 2006-12-01 | 2007-06-01 | 1126855 | -49164 | 1077691 | 1077691 | 100% | 0 | 0 |  | 84514 | -3195 | 81319 | 0 | 0 | Project completed. |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 32 | INV | 286 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 789425 | -20719 | 768706 | 768706 | 100% | 0 | 0 | 0 | 96836.75 | -2278.75 | 94558 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | Individual | ASP | IRA | REF | 35 | INV | 137 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 152024 | -32223 | 119801 | 119801 | 100% | 0 | 0 | 0 | 19763.12 | -4189.12 | 15574 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | Individual | ASP | IRA | REF | 35 | INV | 133 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2001-12-01 | 2004-06-01 | 2004-07-01 |  | 2006-04-01 | 2011-07-01 | 170125 | -2574.31 | 167550.69 | 167550.69 | 100% | 0 | 0 | 0 | 22116.25 | -334.9065 | 21781.3435 | 0 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at eleven small and sedium-sized enterprises | Individual | ASP | MAL | REF | 32 | INV | 140 | A | I | CFC | 64.8 | 64.8 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 960658 | -29788 | 930870 | 930870 | 100% | 0 | 0 | 0 | 115672.4 | -3276.38 | 112396.02 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alfa Refrigerators Co. | Individual | ASP | SYR | REF | 31 | INV | 66 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-03-01 | 114461 | -2201 | 112260 | 112260 | 100% | 0 | 0 | 0 | 14879.93 | -286.1313 | 14593.7987 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Dolphin Refrigerators | Individual | ASP | SYR | REF | 31 | INV | 67 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 113045 | 0 | 113045 | 113045 | 100% | 0 | 0 | 0 | 14695.85 | 0 | 14695.85 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Assalam Refrigerator Co. | Individual | ASP | SYR | REF | 31 | INV | 65 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 144309 | 0 | 144309 | 144309 | 100% | 0 | 0 | 0 | 18760.17 | 0 | 18760.17 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Al-Wattar Home Appliances Co. | Individual | ASP | SYR | REF | 31 | INV | 64 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-05-01 | 2004-01-01 | 235860 | 0 | 235860 | 235860 | 100% | 0 | 0 | 0 | 30662 | 0 | 30662 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of domestic and commercial refrigeration equipment and foam sandwich panels at Ahmad Al-Hafez Al-Waha Refrigerator Co. | Individual | ASP | SYR | REF | 26 | INV | 38 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 330486 | 0 | 330486 | 330486 | 100% | 0 | 0 | 0 | 42963 | 0 | 42963 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (first tranche) | Multi-Year | ASP | DRK | REF | 40 | INV | 26 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-10-01 | 2004-07-01 |  | 2004-12-01 | 2008-07-01 | 384000 | 0 | 384000 | 384000 | 100% | 0 | 0 |  | 28800 | 0 | 28800 | 0 | 0 | FIN
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (second tranche) | Multi-Year | ASP | DRK | REF | 42 | INV | 32 | A | I | CFC | 56 | 56 |  |  | 2004-04-01 | 2004-08-01 | 2005-12-01 |  | 2009-12-01 | 2010-12-01 | 981011 | -33 | 980978 | 980978.41 | 100% | -0.41 | 0 |  | 73576 | -3 | 73573 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Moradi Company | Individual | ASP | IRA | REF | 35 | INV | 120 | A | I | CFC | 6.4 | 6.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-03-01 | 82400 | -2031 | 80369 | 80368.84 | 100% | 0.16 | 0 |  | 10712 | -281 | 10431 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Bouran Saz Karaj (Kohsar Co.) | Individual | ASP | IRA | REF | 35 | INV | 121 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 120526 | -2024 | 118502 | 118501.73 | 100% | 0.27 | 0 |  | 15668 | -287 | 15381 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Minavand Refrigeration Company | Individual | ASP | IRA | REF | 29 | INV | 54 | A | I | CFC | 13.4 | 13.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 176777 | -3308 | 173469 | 173468.82 | 100% | 0.18 | 0 |  | 22981 | -466 | 22515 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alborz Neishabour | Individual | ASP | IRA | REF | 35 | INV | 123 | A | I | CFC | 16 | 16 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2005-08-01 | 189669 | -4567 | 185102 | 185102.48 | 100% | -0.48 | 0 |  | 24657 | -632 | 24025 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Forouzan Yakhchal Company (Forouzan Ref. Co.) | Individual | ASP | IRA | REF | 29 | INV | 59 | A | I | CFC | 16.7 | 16.7 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 192704 | -5358 | 187346 | 187345.54 | 100% | 0.46 | 0 |  | 25052 | -736 | 24316 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Saiwan Sannat Co. | Individual | ASP | IRA | REF | 29 | INV | 52 | A | I | CFC | 14.9 | 14.9 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-03-01 | 200709 | 0 | 200709 | 200709 | 100% | 0 | 0 |  | 26092 | 0 | 26092 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co. | Individual | ASP | IRA | REF | 29 | INV | 53 | A | I | CFC | 16.4 | 16.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 205529 | 0 | 205529 | 205528.61 | 100% | 0.39 | 0 |  | 26719 | 0 | 26718 | 1 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic commercial refrigeration equiment at Comafro | Individual | AFR | MOR | REF | 29 | INV | 38 | A | I | CFC | 6.5 | 6.5 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 134750 | -1142 | 133608 | 133608.19 | 100% | -0.19 | 0 |  | 17518 | -177 | 17342 | -1 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Polade | Individual | AFR | NIR | REF | 35 | INV | 97 | A | I | CFC | 8.3 | 8.3 |  |  | 2001-12-01 | 2002-03-01 | 2004-05-01 |  | 2004-06-01 | 2005-03-01 | 70382 | 0 | 70382 | 70381.99 | 100% | 0.01 | 0 |  | 9150 | -4 | 9146 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Ristian | Individual | AFR | NIR | REF | 35 | INV | 98 | A | I | CFC | 11 | 11 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2004-06-01 | 2005-12-01 | 143729 | -706 | 143023 | 143023.47 | 100% | -0.47 | 0 |  | 18685 | -122 | 18564 | -1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC=12 withHFC-134a, and foam flowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration equipment at Bosmak Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 71 | A | I | CFC | 10.8 | 10.8 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2003-10-01 | 2004-06-01 | 154245 | -420 | 153825 | 153825.48 | 100% | -0.48 | 0 |  | 20052 | -86 | 19966 | 0 | 0 | FIN
FIN | UNIDO | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 87 | A | I | CFC | 51 | 51 |  |  | 2002-11-01 | 2003-06-01 | 2004-11-01 |  | 2006-12-01 | 2007-12-01 | 353100 | -527 | 352573 | 352573.39 | 100% | -0.39 | 0 |  | 40590 | -61 | 40529 | 0 | 0 | FIN |  |  |  | INV
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 |  | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | Project cancelled at the 39th ExCom. |  |  | 2000-12-01 | INV
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 07 | INV | 17 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | 1996-11-01 | INV
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at M/s Kooverji Devshi and Co. Pvt. Ltd., Mumbai | Individual | ASP | IND | HAL | 28 | INV | 256 | A | I | Halon | 25.5 | 25.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-05-01 | 2002-03-01 | 37740 | 0 | 37740 | 37740 | 100% | 0 | 0 | 0 | 4906 | 0 | 4906 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Zenith Fire Services, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 216 | A | I | Halon | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 53280 | -3309 | 49971 | 49971 | 100% | 0 | 0 | 0 | 6926.4 | -430.4 | 6496 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Ashoka Engineering Co., New Delhi | Individual | ASP | IND | HAL | 24 | INV | 177 | A | I | Halon | 34 | 34 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 50320 | 0 | 50320 | 50320 | 100% | 0 | 0 | 0 | 6542 | 0 | 6542 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of production halon-1211 fire extinguishers at Atkins, New Delhi | Individual | ASP | IND | HAL | 24 | INV | 170 | A | I | Halon | 37 | 37 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2001-05-01 | 2002-03-01 | 54760 | -739 | 54021 | 54021 | 100% | 0 | 0 | 0 | 7118.8 | -95.8 | 7023 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Bharat Engineering Works, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 209 | A | I | Halon | 49.5 | 49.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 73260 | -7751 | 65509 | 65509 | 100% | 0 | 0 | 0 | 9523.8 | -1007.8 | 8516 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher to ABC powder and CO2 units together with the use of recycled halon-1301 in lieu of virgin product at Standard Castings Pvt. Ltd. New Delhi, under the name of Pyrosafety | Individual | ASP | IND | HAL | 28 | INV | 222 | A | I | Halon | 64.1 | 64.1 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-11-01 | 92000 | -23084 | 68916 | 68916 | 100% | 0 | 0 | 0 | 11960 | -3001 | 8959 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Cascade Counsel Ltd. New Delhi | Individual | ASP | IND | HAL | 28 | INV | 208 | A | I | Halon | 54 | 54 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79920 | 0 | 79920 | 79920 | 100% | 0 | 0 | 0 | 10390 | 0 | 10390 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Steelage Industries Limited Minimax Division/ Chennai | Individual | ASP | IND | HAL | 24 | INV | 163 | A | I | Halon | 116 | 116 | 0 | 0 | 1998-03-01 | 2000-05-01 | 2000-04-01 |  | 2002-01-01 | 2003-04-01 | 131915 | -41454 | 90461 | 90461 | 100% | 0 | 0 | 0 | 17148.95 | -5388.95 | 11760 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Extinguisher production and elimination of its consumption of virgin halon-1301 at New Fire Engineers Pvt. Ltd. Mumbai | Individual | ASP | IND | HAL | 28 | INV | 220 | A | I | Halon | 120 | 120 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at New Age Industries, Bombay | Individual | ASP | IND | HAL | 24 | INV | 175 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 132248 | -292 | 131956 | 131956 | 100% | 0 | 0 | 0 | 17192.24 | -38.24 | 17154 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Nitin Fire Protection Industries Ltd., Bombay | Individual | ASP | IND | HAL | 24 | INV | 168 | A | I | Halon | 212 | 212 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 165818 | 0 | 165818 | 165818 | 100% | 0 | 0 | 0 | 21556 | 0 | 21556 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vimal Industrial Safety Equipment Corporation Baroda, Gujrat | Individual | ASP | IND | HAL | 24 | INV | 176 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 186152 | 0 | 186152 | 186152 | 100% | 0 | 0 | 0 | 24200 | 0 | 24200 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vijay Fire Protection Systems Ltd. | Individual | ASP | IND | HAL | 24 | INV | 165 | A | I | Halon | 292 | 292 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 219152 | 0 | 219152 | 219152 | 100% | 0 | 0 | 0 | 28490 | 0 | 28490 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converson of production of portable fire extinguishers at Eversafe | Individual | ASP | MAL | HAL | 18 | INV | 72 | A | D | Halon | 574 | 574 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 2002-03-01 | 179586 | -4214 | 175372 | 175372 | 100% | 0 | 0 | 0 | 23346.18 | -548.18 | 22798 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Umbrella project for the conversion of production of portable halon fire extinguishers of members companies of Fire Protectors Federation Inc. | Individual | ASP | PHI | HAL | 18 | INV | 38 | N | I | Halon | 77 | 77 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 2000-09-01 | 2003-04-01 | 114108 | -8935 | 105173 | 105173 | 100% | 0 | 0 | 0 | 14834.04 | -1161.04 | 13673 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | I | Halon | 2.7 | 2.7 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149.25 | 0 | 3149.25 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4959.5 | 0 | 4959.5 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 |  | 2008-01-01 | 2008-12-01 | 563000 | 0 | 563000 | 563000 | 100% | 0 | 0 |  | 71930 | 0 | 71930 | 0 | 0 | Project completed. PCR under preparation. |  |  | 2003-06-01 | INV
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 |  | 2010-09-01 | 2011-11-01 | 568000 | -264529 | 303471 | 303471 | 100% | 0 | 0 |  | 72480 | -33755.4 | 38724.6 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | INV
FIN | UNIDO | Conversion from halon 1211 to ABC dry powder and foam water spray at Nanjing Fire Fighting Equipment Factory | Individual | ASP | CPR | HAL | 15 | INV | 104 | A | I | HAL | 1110 | 1480 |  |  | 1994-12-01 | 1995-10-01 | 1996-12-01 |  | 1996-12-01 | 2000-12-01 | 496000 | 0 | 496000 | 496000 | 100% | 0 | 0 |  | 64480 | -53 | 64427 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | AFR | ALG | ARS | 20 | INV | 18 | A | I | CFC | 19.2 | 19.2 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  |  | 2002-05-01 | 56790 | -3005 | 53785 | 53785 | 100% | 0 | 0 |  | 7383 | -402 | 6981 | 0 | 0 | CLO
CLO | UNIDO | Phase-out of CFC-12 in the manufacture of cosmetics aerosols (deodorants) by conversion to hydrocarbon aerosol propellant (HAP) at COPACI, Abidjan (terminal aerosol sector project) | Individual | AFR | IVC | ARS | 46 | INV | 23 | A | I | CFC | 43.4 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-09-01 |  |  | 2009-06-01 | 110428 | -109351 | 1077 | 1077 | 100% | 0 | 0 |  | 9939 | -9842 | 97 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | Individual | EUR | MDN | ARS | 32 | INV | 17 | A | I | CFC | 25 | 25 |  |  | 2000-12-01 | 2001-12-01 | 2003-03-01 |  |  | 2008-12-01 | 110000 | -10533 | 99467 | 99467 | 100% | 0 | 0 |  | 14300 | -1369 | 12931 | 0 | 0 | CLO
CLO | UNIDO | Phasing out CFCs at Alki S.A. | Individual | AFR | TUN | ARS | 22 | INV | 20 | A | I |  | 0 | 0 |  |  | 1997-05-01 |  | 1998-09-01 |  |  | 1999-12-01 | 74565 | -74565 | 0 | 0 |  | 0 | 0 |  | 9693 | -9693 | 0 | 0 | 0 | CLO |  |  | 1999-03-01
FIN | Germany | Investment project for phasing out CFCs at Chem Tech-Stella Industries, Port Louis | Individual | AFR | MAR | ARS | 27 | INV | 11 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-03-01 | 1999-03-01 | 1999-11-01 |  | 2001-06-01 | 2002-01-01 | 90400 | 0 | 90400 | 90400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted |  |  | 2000-12-01
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 | 2006-07-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100% | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 09 | INV | 12 | N | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. |  |  |  | INV
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 2000-10-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | No change in previous status |  |  | 1999-06-01 | INV
FIN | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2005-02-01 | 2005-02-01 | 49539 | 0 | 49539 | 49539 | 100% | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | Project completed. |  |  | 2003-06-01 | INV
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100% | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100% | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. |  |  |  | INV
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100% | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | Project completed. |  |  | 2002-03-01 | INV
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 07 | INV | 13 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 07 | INV | 14 | N | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100% | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-04-01 | INV
FIN | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | I | CFC | 57.3 | 63.98 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2006-12-01 |  | 2006-03-01 | 2006-03-01 | 252340 | 0 | 252340 | 252340 | 100% | 0 | 0 |  | 18925.5 | 0 | 18925.5 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 07 | INV | 04 | N | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998 |  |  | 1997-06-01 | INV
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100% | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | Project fully implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV
FIN | UNDP | Phase-out of CFC-11 and CFC-12 mixture in the manufacture of insecticides by conversion to hydrocarbon propellant at Fadi, S.A. (Fabrication d'insecticide et de product chimique) | Individual | AFR | BDI | ARS | 35 | INV | 09 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2004-12-01 |  | 2003-12-01 | 2011-12-01 | 128900 | -180 | 128720 | 128720 | 100% | 0 | 0 | 0 | 16757 | -23 | 16734 | 0 | 0 | Completed in 2003. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | Individual | ASP | BGD | ARS | 17 | INV | 05 | N | I | CFC | 123.6 | 123.6 | 0 | 0 | 1995-07-01 | 1998-12-01 | 1996-07-01 |  | 2002-08-01 | 2003-10-01 | 322920 | -343 | 322577 | 322577 | 100% | 0 | 0 | 0 | 41979.6 | -44.6 | 41935 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 2001-05-01 | Investment
FIN | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | Individual | LAC | CUB | ARS | 34 | INV | 18 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-05-01 |  | 2006-12-01 | 2008-04-01 | 124220 | 0 | 124220 | 124219.85 | 100% | 0.15 | 0 | 0 | 16149 | 0 | 16148.9805 | 0.0195 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Aerosol conversion at Sunder Chemical | Individual | ASP | IND | ARS | 24 | INV | 167 | A | I | CFC | 15 | 15 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 59892 | -3617 | 56275 | 56275 | 100% | 0 | 0 | 0 | 7785.96 | -469.96 | 7316 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Sara-Chem Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 171 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 89164 | -29723 | 59441 | 59441 | 100% | 0 | 0 | 0 | 11591.32 | -3864.32 | 7727 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Chem-Verse Consultants | Individual | ASP | IND | ARS | 24 | INV | 174 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 67324 | -1872 | 65452 | 65452 | 100% | 0 | 0 | 0 | 8752.12 | -243.12 | 8509 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol Conversion at Midas Care Pharmaceuticals | Individual | ASP | IND | ARS | 24 | INV | 179 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 110880 | -2729 | 108151 | 108151 | 100% | 0 | 0 | 0 | 14414.4 | -355.4 | 14059 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 19 | DEM | 69 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-09-01 | 1997-06-01 |  | 2001-11-01 | 2002-03-01 | 0 | 168783 | 168783 | 168783 | 100% | 0 | 0 | 0 | 0 | 21942 | 21942 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1996 | 1998-04-01 | Non-Investment
FIN | UNDP | Conversion to hydrocarbon technology in the manufacture of aerosol products at Maya Chemical Industries Sdn., Bhd. | Individual | ASP | MAL | ARS | 17 | INV | 60 | A | R | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 37808 | 0 | 37808 | 37808 | 100% | 0 | 0 | 0 | 4915 | 0 | 4915 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Alloychem Malaysia Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 64 | A | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2001-12-01 | 2003-11-01 | 99500 | -13228 | 86272 | 86272 | 100% | 0 | 0 | 0 | 12935 | -1720 | 11215 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | Individual | ASP | MAL | ARS | 19 | INV | 85 | A | I | CFC | 250 | 250 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1998-04-01 |  | 2005-12-01 | 2011-05-01 | 1486660 | -149073.72 | 1337586.28 | 1337586.28 | 100% | 0 | 0 | 0 | 193265.8 | -19379.3836 | 173886.4164 | 0 | 0 | Completed in 2005. |  | 1996 | 2001-12-01 | Investment
FIN | UNDP | Aerosol conversion at Compagnie Manufacturiere de Produits Cosmetiques Ltee. | Individual | AFR | MAR | ARS | 12 | INV | 03 | A | D | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-06-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 62150 | 0 | 62150 | 62150 | 100% | 0 | 0 | 0 | 8080 | 0 | 8080 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at International Cosmetic Ltd. (ICL) | Individual | ASP | SRL | ARS | 18 | INV | 07 | A | I | CFC | 5 | 5 | 0 | 0 | 1995-11-01 | 1997-04-01 | 1996-11-01 |  | 2001-08-01 | 2003-11-01 | 38968 | -5599 | 33369 | 33369 | 100% | 0 | 0 | 0 | 5065.84 | -727.84 | 4338 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | P-Tech Manuchem Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 83 | A | I | CFC | 37.3 | 37.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2001-12-01 | 115830 | -8432 | 107398 | 107398 | 100% | 0 | 0 | 0 | 15057.9 | -1096 | 13961.9 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | J.M.T. Laboratories Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 84 | A | I | CFC | 36.6 | 36.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2003-11-01 | 127920 | -5082 | 122838 | 122838 | 100% | 0 | 0 | 0 | 16629.6 | -660.66 | 15968.94 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 | 2008-10-01 | 49720 | 0 | 49720 | 49720 | 100% | 0 | 0 | 0 | 6463.6 | 0 | 6463.6 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344.2 | -41.6 | 14302.6 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 | 2007-03-01 | 125400 | 0 | 125400 | 125400 | 100% | 0 | 0 | 0 | 16302 | 0 | 16302 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 07 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2438.84 | 235991.16 | 235991 | 100% | 0.16 | 0 | 0 | 30995.9 | -317.0492 | 30678.83 | 0.0208 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37065.6 | -343.33 | 36722.27 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 1999-09-01 | Investment
FIN | UNIDO | Phasing out CFCs at Ets. COPHYD | Individual | AFR | ALG | ARS | 20 | INV | 19 | A | I | CFC | 15 | 15 |  |  | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1997-07-01 | 1999-08-01 | 53024 | -1291 | 51733 | 51733 | 100% | 0 | 0 |  | 6893 | -178 | 6715 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | AFR | ALG | ARS | 28 | INV | 41 | A | I | CFC | 19 | 19 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2002-02-01 | 2003-05-01 | 73691 | -74 | 73617 | 73617 | 100% | 0 | 0 |  | 9580 | -25 | 9555 | 0 | 0 | FIN |  |  | 2002-03-01
FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | AFR | ALG | ARS | 28 | INV | 38 | A | I | CFC | 18.1 | 18.1 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-07-01 | 2002-09-01 | 77145 | -78 | 77067 | 77066.69 | 100% | 0.31 | 0 |  | 10029 | -26 | 10003 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | AFR | ALG | ARS | 20 | INV | 15 | A | I | CFC | 22.5 | 22.5 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 82018 | 0 | 82018 | 82018 | 100% | 0 | 0 |  | 10662 | -2 | 10660 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | AFR | ALG | ARS | 25 | INV | 28 | A | I | CFC | 38.4 | 38.4 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2000-12-01 | 2002-08-01 | 147807 | -316 | 147491 | 147490.52 | 100% | 0.48 | 0 |  | 19215 | -72 | 19143 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | AFR | ALG | ARS | 20 | INV | 16 | A | I | CFC | 51.4 | 51.4 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2001-12-01 | 164623 | 0 | 164623 | 164623.06 | 100% | -0.06 | 0 |  | 21401 | -13 | 21388 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ets. Wouroud | Individual | AFR | ALG | ARS | 20 | INV | 17 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 187772 | -420 | 187352 | 187352 | 100% | 0 | 0 |  | 24410 | -93 | 24317 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Entreprise Nationale des Detergents (ENAD) | Individual | AFR | ALG | ARS | 18 | INV | 12 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 2002-05-01 | 614850 | 0 | 614850 | 614850.15 | 100% | -0.15 | 0 |  | 79931 | -46 | 79885 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Pliva D.D. | Individual | EUR | CRO | ARS | 22 | INV | 05 | A | I | CFC | 10.6 | 10.6 |  |  | 1997-05-01 | 1997-10-01 | 1998-08-01 |  | 2000-10-01 | 2001-12-01 | 89779 | -2344 | 87435 | 87434.5 | 100% | 0.5 | 0 |  | 11671 | -323 | 11348 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Sicobel | Individual | AFR | IVC | ARS | 20 | INV | 08 | A | I | CFC | 20.8 | 20.8 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-09-01 | 59171 | -453 | 58718 | 58717.83 | 100% | 0.17 | 0 |  | 7692 | -71 | 7621 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Parfumerie Gandour D.A.F. | Individual | AFR | IVC | ARS | 20 | INV | 07 | A | I | CFC | 66 | 66 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-10-01 | 106061 | 0 | 106061 | 106060.67 | 100% | 0.33 | 0 |  | 13788 | 0 | 13788 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Jordan Tunisian Chemical Company | Individual | ASP | JOR | ARS | 32 | INV | 68 | A | I | CFC | 12 | 12 |  |  | 2000-12-01 | 2001-10-01 | 2003-03-01 |  | 2002-12-01 | 2003-10-01 | 52800 | -23 | 52777 | 52776.74 | 100% | 0.26 | 0 |  | 6864 | -14 | 6850 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mirage Industries Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 11 | A | I | CFC | 51 | 51 |  |  | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 47250 | -371 | 46879 | 46879.18 | 100% | -0.18 | 0 |  | 6143 | -58 | 6085 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFCs at Aesthetics Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 10 | A | I | CFC | 107 | 107 |  |  | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 55000 | 0 | 55000 | 54999.76 | 100% | 0.24 | 0 |  | 7150 | -1 | 7149 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of CFCs at Cosmaline Industries s.a.al. | Individual | ASP | LEB | ARS | 19 | INV | 05 | A | I | CFC | 87.7 | 87.7 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-07-01 | 212500 | 0 | 212500 | 212500 | 100% | 0 | 0 |  | 27625 | 0 | 27625 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Zeeni's Trading Agency | Individual | ASP | LEB | ARS | 19 | INV | 06 | A | I | CFC | 212 | 212 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 361900 | -9467 | 352433 | 352433 | 100% | 0 | 0 |  | 47047 | -1303 | 45744 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | Individual | EUR | ROM | ARS | 44 | INV | 26 | A | I | CFC | 46.5 | 46.5 |  |  | 2004-12-01 | 2005-07-01 | 2007-02-01 |  | 2006-06-01 | 2007-09-01 | 204776 | -640 | 204136 | 204136 | 100% | 0 | 0 |  | 18430 | -58 | 18372 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFCs at FARMEC SA | Individual | EUR | ROM | ARS | 18 | INV | 05 | A | I | CFC | 730 | 730 |  |  | 1995-11-01 | 1996-09-01 | 1997-11-01 |  | 1998-12-01 | 2001-07-01 | 895880 | -29399 | 866481 | 866481 | 100% | 0 | 0 |  | 116464 | -4000 | 112464 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Tag Cosmetics Ltd. | Individual | AFR | SUD | ARS | 28 | INV | 13 | A | I | CFC | 45.1 | 45.1 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2002-07-01 | 2002-12-01 | 131718 | 0 | 131718 | 131718 | 100% | 0 | 0 |  | 17123 | -8 | 17115 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Sudanese Cosmetics and Household Products | Individual | AFR | SUD | ARS | 18 | INV | 04 | A | I | CFC | 281.5 | 281.5 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 497613 | -297 | 497316 | 497316 | 100% | 0 | 0 |  | 64690 | -141 | 64549 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | Individual | ASP | SYR | ARS | 32 | INV | 72 | A | I | CFC | 10.5 | 10.5 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 46200 | 0 | 46200 | 46200.14 | 100% | -0.14 | 0 |  | 6006 | -3 | 6003 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | Individual | ASP | SYR | ARS | 32 | INV | 73 | A | I | CFC | 11 | 11 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 48400 | -31 | 48369 | 48369.2 | 100% | -0.2 | 0 |  | 6292 | -14 | 6278 | 0 | 0 | FIN
FIN | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | Individual | ASP | SYR | ARS | 32 | INV | 71 | A | I | CFC | 15.6 | 15.6 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 68640 | 0 | 68640 | 68639.82 | 100% | 0.18 | 0 |  | 8923 | -3 | 8920 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | Individual | ASP | SYR | ARS | 32 | INV | 74 | A | I | CFC | 36 | 36 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 87298 | -770 | 86528 | 86527.74 | 100% | 0.26 | 0 |  | 11349 | -118 | 11231 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al-Fajer Co. | Individual | ASP | SYR | ARS | 26 | INV | 36 | A | I | CFC | 44 | 44 |  |  | 1998-11-01 | 1999-10-01 | 2000-04-01 |  | 2000-06-01 | 2001-07-01 | 169985 | -1059 | 168926 | 168926 | 100% | 0 | 0 |  | 22098 | -172 | 21926 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ahmed Ali Harsho Sons Co. | Individual | ASP | SYR | ARS | 22 | INV | 21 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-12-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 175328 | -3796 | 171532 | 171532.15 | 100% | -0.15 | 0 |  | 22793 | -529 | 22264 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Laboratories Kosmeto | Individual | ASP | SYR | ARS | 23 | INV | 23 | A | I | CFC | 59.9 | 59.9 |  |  | 1997-11-01 | 1998-10-01 | 1999-02-01 |  | 1999-10-01 | 2001-11-01 | 175062 | -1772 | 173290 | 173289.67 | 100% | 0.33 | 0 |  | 22758 | -266 | 22492 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mariza Co. | Individual | ASP | SYR | ARS | 25 | INV | 31 | A | I | CFC | 90 | 90 |  |  | 1998-07-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 207652 | -3210 | 204442 | 204442.48 | 100% | -0.48 | 0 |  | 26995 | -460 | 26535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al Yaman | Individual | ASP | SYR | ARS | 22 | INV | 20 | A | I | CFC | 95 | 95 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2002-08-01 | 216128 | -2737 | 213391 | 213391.36 | 100% | -0.36 | 0 |  | 28097 | -400 | 27697 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Dina Cosmetics | Individual | ASP | SYR | ARS | 23 | INV | 24 | A | I | CFC | 70 | 70 |  |  | 1997-11-01 | 1998-10-01 | 1999-08-01 |  | 2000-07-01 | 2001-12-01 | 228477 | -456 | 228021 | 228021.2 | 100% | -0.2 | 0 |  | 29702 | -106 | 29596 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Taki Eddin & Co. | Individual | ASP | SYR | ARS | 22 | INV | 22 | A | I | CFC | 118.8 | 118.8 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 244203 | 0 | 244203 | 244203.21 | 100% | -0.21 | 0 |  | 31746 | -44 | 31702 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Careesse Cosmetics | Individual | ASP | SYR | ARS | 21 | INV | 16 | A | I | CFC | 185 | 185 |  |  | 1997-02-01 | 1997-06-01 | 1998-04-01 |  | 1998-12-01 | 2000-12-01 | 272621 | -1208 | 271413 | 271413 | 100% | 0 | 0 |  | 35441 | -213 | 35228 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Gaston Banna & Sons Co. | Individual | ASP | SYR | ARS | 19 | INV | 13 | A | I | CFC | 104 | 104 |  |  | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 1998-12-01 | 2000-04-01 | 299500 | 0 | 299500 | 299500 | 100% | 0 | 0 |  | 38935 | 0 | 38935 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parhycos, Sfax, Tunisia | Individual | AFR | TUN | ARS | 23 | INV | 25 | A | I | CFC | 10 | 10 |  |  | 1997-11-01 | 1999-04-01 | 1999-02-01 |  | 1999-12-01 | 2001-03-01 | 41195 | 0 | 41195 | 41195 | 100% | 0 | 0 |  | 5355 | -2 | 5353 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Sogepar | Individual | AFR | TUN | ARS | 22 | INV | 21 | A | I | CFC | 18.15 | 18.15 |  |  | 1997-05-01 | 1998-11-01 | 1998-09-01 |  | 2000-01-01 | 2001-07-01 | 68833 | 0 | 68833 | 68832.64 | 100% | 0.36 | 0 |  | 8948 | -4 | 8944 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Laboratoires Parcos | Individual | AFR | TUN | ARS | 28 | INV | 35 | A | I | CFC | 29.8 | 29.8 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2004-03-01 | 2004-09-01 | 76127 | -469 | 75658 | 75658.39 | 100% | -0.39 | 0 |  | 9897 | -77 | 9820 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Satem Parfums et Produits Cosmetiques | Individual | AFR | TUN | ARS | 19 | INV | 15 | A | I | CFC | 29 | 29 |  |  | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 119500 | 0 | 119500 | 119500 | 100% | 0 | 0 |  | 15535 | 0 | 15535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at CODIFA | Individual | AFR | TUN | ARS | 22 | INV | 19 | A | I | CFC | 60.25 | 60.25 |  |  | 1997-05-01 | 1997-09-01 | 1998-09-01 |  | 1999-12-01 | 2000-11-01 | 179986 | 0 | 179986 | 179986 | 100% | 0 | 0 |  | 23398 | 0 | 23398 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Jasminal Laboratories | Individual | AFR | TUN | ARS | 19 | INV | 14 | A | I | CFC | 86 | 86 |  |  | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1998-12-01 | 2001-03-01 | 210000 | -77 | 209923 | 209923 | 100% | 0 | 0 |  | 27300 | -53 | 27247 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Mansoor Daya Chemicals Ltd. | Individual | AFR | URT | ARS | 18 | INV | 05 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1997-12-01 | 1999-08-01 | 417163 | -2138 | 415025 | 415025 | 100% | 0 | 0 |  | 54231 | -363 | 53868 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | I | CFC | 82.7 | 82.7 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | 0 | 179508 | 179507.91 | 100% | 0.09 | 0 |  | 23336 | -33 | 23303 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 08 | A | R | CFC | 96.6 | 96.6 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | -5910 | 360894 | 360893.99 | 100% | 0.01 | 0 |  | 34676 | -613 | 34063 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b in aerosol manufacturing at Silimex | Multi-Year | LAC | MEX | ARS | 63 | INV | 156 | A | I | HCFC | 11.1 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2013-09-30 | 2014-03-01 |  |  | 520916 | 0 | 520916 | 12439.43 | 2.388% | 508476.57 | 143214.45 | 300000 | 39069 | 0 | 933 | 38136 | 10741 | No offer was received in the first bidding, therefore the exercise was repeated. The second bidding was successful and an equipment could be selected. The purchase order was issued in December 2012. Disbursement level at the end of 2012 does not reflect actual progress in the project. Contract for conversion was signed in 2012. | The delivery of equipment is expected by the end of April 2013, contract of the local works and logistic support will be finalized in the second half of 2013. Conversion later this year will result in total disbursement for equipment and IOC will be paid in 2014. |  |  | INV
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project implementation has been transferred to UNDP. |  |  | 1996-06-01 | Non-INV
FIN | France | Conversion to non-CFC technology in the manufacture of polyurethane flexible molded foam at Meuble Mode Sarl |  | ASP | LEB | FOA | 20 | INV | 10 | A | I | CFC | 9 | 9 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-03-01 | 55700 | -235 | 55465 | 55465 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | Germany | Conversion of Algeria Mousse Polyurethane (AMP) | Individual | AFR | ALG | FOA | 31 | INV | 44 | A | I | CFC | 152 | 152 | 0 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 |  | 2004-12-01 | 2007-12-01 | 565728 | 0 | 565728 | 565728 | 100% | 0 | 0 | 0 | 73545 | 0 | 73545 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100% | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-01-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-07-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100% | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100% | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | Project completed, PCR submitted June 2000. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 06 | N | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 |  | 2005-02-01 | 2006-07-01 | 1247330 | -1030 | 1246300 | 1246300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-09-01 | INV
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Massimo | Individual | LAC | BRA | FOA | 31 | INV | 173 | A | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-09-01 | 2003-09-01 | 52279 | -5260 | 47019 | 47019 | 100% | 0 | 0 | 0 | 6796.27 | -684.27 | 6112 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Beijing Yanxi | Individual | ASP | CPR | FOA | 15 | INV | 94 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 125000 | -31250 | 93750 | 93750 | 100% | 0 | 0 | 0 | 16250 | -4063 | 12187 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of moulded polyurethane foams at Technopol Egypt SAE | Individual | AFR | EGY | FOA | 08 | INV | 07 | A | I | CFC | 55 | 55 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-04-01 | 2003-04-01 | 645000 | 31211 | 676211 | 676211 | 100% | 0 | 0 | 0 | 83850 | 4057 | 87907 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Raipur Agencies | Individual | ASP | IND | FOA | 31 | INV | 269 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 144567 | -2814 | 141753 | 141753 | 100% | 0 | 0 | 0 | 18793.71 | -365.71 | 18428 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at SR Poly-steel P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 274 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 144299 | -1 | 144298 | 144298 | 100% | 0 | 0 | 0 | 18759 | 0 | 18759 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Nindra Foams | Individual | ASP | IND | FOA | 31 | INV | 273 | A | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 148804 | -2244 | 146560 | 146560 | 100% | 0 | 0 | 0 | 19344.52 | -291.52 | 19053 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at R.H. Industries | Individual | ASP | IND | FOA | 31 | INV | 271 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 153895 | -2700 | 151195 | 151195 | 100% | 0 | 0 | 0 | 20006.35 | -351.35 | 19655 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pyarelal Coir Products Ltd. | Individual | ASP | IND | FOA | 31 | INV | 270 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 167381 | -2886 | 164495 | 164495 | 100% | 0 | 0 | 0 | 21759.53 | -374.53 | 21385 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Alka International Ltd. | Individual | ASP | IND | FOA | 31 | INV | 276 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 173155 | -6690 | 166465 | 166465 | 100% | 0 | 0 | 0 | 22510.15 | -870.15 | 21640 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pinnacle Industries Ltd. | Individual | ASP | IND | FOA | 31 | INV | 272 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 186392 | 0 | 186392 | 186392 | 100% | 0 | 0 | 0 | 24231 | 0 | 24231 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD and water-based technology in the manufacture of flexible molded foam at Unique Field | Individual | ASP | MAL | FOA | 31 | INV | 137 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 109990 | 0 | 109990 | 109990 | 100% | 0 | 0 | 0 | 14299 | 0 | 14299 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible molded foam at Pointray | Individual | ASP | MAL | FOA | 31 | INV | 138 | A | I | CFC | 24.3 | 24.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 130896 | -27 | 130869 | 130869 | 100% | 0 | 0 | 0 | 17016.48 | -4.48 | 17012 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Eversoft Foam Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 39 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1996-12-01 | 1998-12-01 | 185000 | -1 | 184999 | 184999 | 100% | 0 | 0 | 0 | 24050 | 1.0186e-12 | 24050 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Nian Aik Foam Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 40 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 245000 | -53100 | 191900 | 191900 | 100% | 0 | 0 | 0 | 31850 | -6903 | 24947 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Masterfoam Products | Individual | ASP | MAL | FOA | 29 | INV | 130 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 208900 | 0 | 208900 | 208900 | 100% | 0 | 0 | 0 | 27157 | 0 | 27157 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible polyurethane foam at Kemas Mekar Sdn Bhd | Individual | ASP | MAL | FOA | 29 | INV | 131 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 385900 | -11270 | 374630 | 374630 | 100% | 0 | 0 | 0 | 50167 | -1465 | 48702 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to liquid carbon dioxide blown technology in the manufacture of molded flexible polyurethane foam at Automotive Component Industries Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 50 | A | I | CFC | 37 | 37 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 204761 | 0 | 204761 | 204761 | 100% | 0 | 0 | 0 | 26619 | 0 | 26619 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 |  | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 |  | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 1.0459e-11 | 0 | Project cancelled at the 35 th ExCom. |  |  |  | INV
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 |  | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | Project cancelled at the 40th ExCom. |  |  |  | INV
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 |  | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 |  | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | -3.1832e-12 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | 1998-12-01 | INV
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 |  | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 |  | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. |  |  |  | INV
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | 1997-12-01 | INV
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Company moved to the Sudan. |  |  | 1994-06-01 | INV
CLO | UNDP | Continuation of conversion to CFC-free technology in manufacturing of flexible polyurethane foam at Vita-Centrafrique | Individual | AFR | CAF | FOA | 19 | INV | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1997-05-01 |  |  | 2001-12-01 | 62000 | -30537 | 31463 | 31463 | 100% | 0 | 0 | 0 | 8060 | -3970 | 4090 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
CLO | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Yanfeng | Individual | ASP | CPR | FOA | 13 | INV | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1995-07-01 |  |  | 1995-07-01 | 670000 | -670000 | 0 | 0 |  | 0 | 0 | 0 | 87100 | -87100 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF at El-Tawil Manufacturing Company | Individual | AFR | EGY | FOA | 15 | INV | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-12-01 |  |  | 2000-12-01 | 121000 | -91977.38 | 29022.62 | 29023 | 100% | -0.38 | 0 | 0 | 15730 | -11956.9994 | 3773.05 | -0.049401 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | Individual | AFR | LIB | FOA | 32 | INV | 05 | A | I | CFC | 26 | 19 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  |  | 2008-04-01 | 128097 | -106916 | 21181 | 21181 | 100% | 0 | 0 | 0 | 16652.61 | -13898.6055 | 2754.0045 | 0 | 0 | Canceled in 2005. Financially completed in 2008. Balance returned in 2009. |  | 2000 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Mousse d'Or S.A. | Individual | AFR | MOR | FOA | 23 | INV | 19 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 280350 | 0 | 280350 | 280350 | 100% | 0 | 0 | 0 | 36446 | 0 | 36446 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture fo flexible foam (slabstock) at Salidor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 13 | A | I | CFC | 48 | 48 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Dolidol | Individual | AFR | MOR | FOA | 22 | INV | 10 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 1999-06-01 |  |  | 2003-12-01 | 475822 | -61553 | 414269 | 414269 | 100% | 0 | 0 | 0 | 61856.86 | -8001.86 | 53855 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richbond S.A. | Individual | AFR | MOR | FOA | 22 | INV | 08 | A | I | CFC | 150 | 150 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-06-01 |  |  | 2004-12-01 | 470625 | -40035.82 | 430589.18 | 430589.18 | 100% | 0 | 0 | 0 | 61181.25 | -5205.2453 | 55976.0047 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
CLO | UNDP | Conversion to LCD technology in the manufacture of flexible foam (slabstock) to replace CFC-11 at Bonbino Confort | Individual | AFR | MOR | FOA | 25 | INV | 22 | A | I | CFC | 90 | 90 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  |  | 2004-12-01 | 490200 | 0 | 490200 | 490200 | 100% | 0 | 0 | 0 | 63726 | 0 | 63726 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1998 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | Individual | AFR | MOR | FOA | 23 | INV | 12 | A | I | CFC | 85 | 85 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2005-09-01 | 517300 | -5023 | 512277 | 512277 | 100% | 0 | 0 | 0 | 67249 | -653 | 66596 | 0 | 0 | Canceled in 2004. Financially completed in 2005. |  | 1997 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at H.K. Foam Ltd. | Individual | AFR | URT | FOA | 26 | INV | 10 | A | I | CFC | 2 | 2 | 0 | 0 | 1998-11-01 | 2003-01-01 | 2000-12-01 |  |  | 2003-11-01 | 113700 | -105743 | 7957 | 7957 | 100% | 0 | 0 | 0 | 14781 | -13746.59 | 1034.41 | 0 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1998 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pan Africa Enterprises Ltd. | Individual | AFR | URT | FOA | 26 | INV | 11 | A | I | CFC | 35 | 0 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  |  | 2004-03-01 | 213800 | 0 | 213800 | 213800 | 100% | 0 | 0 | 0 | 27794 | 0 | 27794 | 0 | 0 | Canceled in 2002. Financially completed in 2004. |  | 1998 |  | Investment
CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 21 | A | I | CFC | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1998-06-01 |  |  | 2002-09-01 | 61880 | -55372 | 6508 | 6508.1 | 100% | -0.1 | 0 |  | 8044 | -7199 | 845 | 0 | 0 | CLO
CLO | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | Individual | ASP | IRA | FOA | 28 | INV | 50 | A | I | CFC | 83 | 83 |  |  | 1999-07-01 | 2000-11-01 | 2001-02-01 |  |  | 2009-05-01 | 485929 | -5381 | 480548 | 480548.04 | 100% | -0.04 | 0 |  | 63171 | -700 | 62471 | 0 | 0 | CLO |  |  | 2002-06-01
CLO | UNIDO | Phasing out CFC-11 at Go-Ya Sungar Ltd. Sti. | Individual | EUR | TUR | FOA | 23 | INV | 31 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-11-01 | 1998-12-01 |  |  | 2002-04-01 | 533400 | -313280 | 220120 | 220120.42 | 100% | -0.42 | 0 |  | 69342 | -40772 | 28570 | 0 | 0 | CLO
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Merza Foam Sarl |  | ASP | LEB | FOA | 20 | INV | 13 | A | I | CFC | 45 | 45 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-04-01 | 108172 | -950 | 107222 | 107222 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Furniture and Plastic Sarl (FAP) |  | ASP | LEB | FOA | 20 | INV | 11 | A | I | CFC | 28 | 28 | 0 |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 2000-09-01 | 2000-12-01 | 128700 | 0 | 128700 | 128700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Plastiflex Sarl |  | ASP | LEB | FOA | 20 | INV | 12 | A | I | CFC | 42 | 42 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-03-01 | 1999-08-01 | 154000 | -7224 | 146776 | 146776 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Fomaco Sarl |  | ASP | LEB | FOA | 20 | INV | 15 | A | I | CFC | 26 | 26 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-09-01 | 1999-12-01 | 154000 | -2258 | 151742 | 151742 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Fofy Industrie |  | AFR | MLI | FOA | 26 | INV | 05 | A | I | CFC | 19.5 | 19.5 | 0 |  | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 151000 | 0 | 151000 | 151000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 45 | A | I | CFC | 80 | 80 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 | 0 | 64792 | 0 | 64792 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of Matelas Souf to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 46 | A | I | CFC | 95 | 95 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 561379 | 0 | 561379 | 561379 | 100% | 0 | 0 | 0 | 72979 | 0 | 72979 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | Individual | ASP | IRA | FOA | 34 | INV | 114 | A | I | CFC | 62 | 62 | 0 |  | 2001-07-01 | 2001-08-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 386260 | 0 | 386260 | 386260 | 100% | 0 | 0 | 0 | 50214 | 0 | 50214 | 0 | 0 | Project completed except for the certificate of destruction which is still outstanding. PCR was prepared and forwarded to the country for comment..
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company | Individual | ASP | IRA | FOA | 37 | INV | 151 | A | I | CFC | 77 | 77 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 387174 | 0 | 387174 | 387174 | 100% | 0 | 0 | 0 | 50333 | 0 | 50333 | 0 | 0 | Equipment has been delivered and installed, certificate of destruction was signed. Project is completed. PCR has been submitted for comment to the country.
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | Individual | ASP | IRA | FOA | 35 | INV | 116 | A | I | CFC | 89 | 89 | 0 |  | 2001-12-01 | 2001-01-01 | 2003-05-01 |  | 2004-12-01 | 2007-12-01 | 499299 | 0 | 499299 | 499299 | 100% | 0 | 0 | 0 | 64909 | 0 | 64909 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted to ExCom. |  |  | 1999-08-01 | INV
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100% | -0.29 | -0.29 |  | 27209 | 0 | 27209.03 | -0.03 | -0.03 | Project completed; PCR submitted. |  |  | 1998-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1998-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100% | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | Project complete; PCR submitted to 29th ExCOM. |  |  | 1999-03-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to 30th ExCom. |  |  | 1999-01-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 |  | 2005-04-01 | 2005-01-01 | 301000 | 0 | 301000 | 301000 | 100% | 0 | 0 |  | 39130 | 0 | 39130 | 0 | 0 | Project completed. |  |  | 2000-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-03-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100% | 0 | 0 |  | 41675.79 | -11 | 41665 | -0.21 | -0.21 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100% | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100% | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | Project completed. PCR will be submitted in January 2001. |  |  | 1999-06-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100% | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 | 2005-04-01 | 440461 | 0 | 440461 | 440461 | 100% | 0 | 0 |  | 57259.93 | 0 | 57259.93 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100% | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-05-01 | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 | 2005-04-01 | 473480 | 0 | 473480 | 473480 | 100% | 0 | 0 |  | 61552.4 | 0 | 61552.4 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100% | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 |  |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 | 2005-04-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 |  | 64792 | 0 | 64792 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100% | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | Financially completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | I | CFC | 136.67 | 136.67 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2005-03-01 | 2005-07-01 | 515970 | 0 | 515970 | 515970 | 100% | 0 | 0 |  | 66756.7 | 0 | 66756.7 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 | 2005-03-01 | 525483 | 0 | 525483 | 525483 | 100% | 0 | 0 |  | 67803.13 | 0 | 67803.13 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 | 2005-04-01 | 536403 | 0 | 536403 | 536403 | 100% | 0 | 0 |  | 69004.33 | 0 | 69004.33 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100% | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | Financially completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100% | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 | 2005-12-01 | 600066 | 0 | 600066 | 600066 | 100% | 0 | 0 |  | 76007.26 | 0 | 76007.26 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100% | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | I | CFC | 134.9 | 134.9 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2005-05-01 | 2005-12-01 | 609616 | 0 | 609616 | 609616 | 100% | 0 | 0 |  | 77057.76 | 0 | 77057.76 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted December 2000. |  |  | 1999-05-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100% | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1999-12-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | 2000-12-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | 2000-12-01 | INV
FIN | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | I | CFC | 954 | 954 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2007-01-01 | 2007-03-01 | 4060640 | -467626.72 | 3593013.28 | 3593013.28 | 100% | 0 | 0 |  | 527883 | -60791.46 | 467091.54 | 0 | 0 | Project is physically and financially completed |  |  | 2002-12-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-09-01 | INV
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 07 | INV | 08 | N | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 | 2007-07-01 | 553400 | -131363.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 71942 | -17077.2 | 54864.79 | 0.01 | 0.01 | Project completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2007-07-01 | 529490 | -107453.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 68243.9 | -13849.21 | 54394.68 | 0.01 | 0.01 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100% | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | Project fully implemented. 100% non-CFC production started. Awaiting PCR. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100% | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  |  | INV
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Mac-Vico (Nig.) Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 74 | A | I | CFC | 28.4 | 28.4 | 0 |  | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-07-01 | 2003-10-01 | 105209 | 0 | 105209 | 105209 | 100% | 0 | 0 | 0 | 13677 | 0 | 13677 | 0 | 0 | Operationally completed July 2003, financially completed October 2003 |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Eastern Wrought Iron Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 73 | A | I | CFC | 27.1 | 27.1 | 0 |  | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2004-11-01 | 2006-05-01 | 109345 | -3207 | 106138 | 106138 | 100% | 0 | 0 | 0 | 14215 | -417 | 13798 | 0 | 0 | Operationally completed November 2004. COC issued. Final revision issued but unspent balance and corresponding support cost still to be returned in 2007. |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Martchem Industries Limited (at 2 plants) by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 75 | A | I | CFC | 38.4 | 38.4 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2003-03-01 | 2003-10-01 | 175121 | 0 | 175121 | 175121 | 100% | 0 | 0 | 0 | 22766 | 0 | 22766 | 0 | 0 | Operationally and financially completed 2003 |  | 2000 |  | investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. | Individual | LAC | ARG | FOA | 22 | INV | 56 | A | I | CFC | 19 | 19 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-05-01 | 2004-01-01 | 118000 | -34528 | 83472 | 83472 | 100% | 0 | 0 | 0 | 15340 | -4489 | 10851 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Mentvil S.A. | Individual | LAC | ARG | FOA | 18 | INV | 28 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1997-04-01 | 2001-12-01 | 115000 | -12796 | 102204 | 102204 | 100% | 0 | 0 | 0 | 14950 | -1663 | 13287 | 0 | 0 | Completed in 1997. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | Individual | LAC | ARG | FOA | 25 | INV | 76 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 1998-07-01 | 2000-08-01 | 2000-08-01 |  | 2002-11-01 | 2004-01-01 | 122100 | 0 | 122100 | 122100 | 100% | 0 | 0 | 0 | 15873 | 0 | 15873 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | Individual | LAC | ARG | FOA | 31 | INV | 111 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2003-12-01 | 2005-09-01 | 295300 | -97042 | 198258 | 198258 | 100% | 0 | 0 | 0 | 38389 | -12615 | 25774 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax | Individual | LAC | ARG | FOA | 30 | INV | 106 | A | I | CFC | 50 | 50 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2003-04-01 |  | 2002-11-01 | 2004-01-01 | 252000 | 0 | 252000 | 252000 | 100% | 0 | 0 | 0 | 32760 | 0 | 32760 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Nuvel Corp. S.A. | Individual | LAC | ARG | FOA | 18 | INV | 27 | A | I | CFC | 53 | 53 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 313500 | 0 | 313500 | 313500 | 100% | 0 | 0 | 0 | 40755 | 0 | 40755 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC | Individual | LAC | ARG | FOA | 18 | INV | 30 | A | I | CFC | 64 | 64 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 341000 | -1708 | 339292 | 339292 | 100% | 0 | 0 | 0 | 44330 | -222 | 44108 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Limansky | Individual | LAC | ARG | FOA | 18 | INV | 29 | A | I | CFC | 95 | 95 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 473000 | -364 | 472636 | 472636 | 100% | 0 | 0 | 0 | 61490 | -47 | 61443 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. | Individual | LAC | ARG | FOA | 20 | INV | 48 | A | I | CFC | 92.5 | 92.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2002-11-01 | 2004-01-01 | 561000 | 0 | 561000 | 561000 | 100% | 0 | 0 | 0 | 72930 | 0 | 72930 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 1998-01-01 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstock) at Sueño Estelar S.A. and Estelar San Luis S.A. | Individual | LAC | ARG | FOA | 18 | INV | 31 | A | I | CFC | 128.6 | 128.6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 690000 | -2837 | 687163 | 687163 | 100% | 0 | 0 | 0 | 89700 | -369 | 89331 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis | Individual | LAC | ARG | FOA | 18 | INV | 26 | A | I | CFC | 145 | 145 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2001-08-01 | 715000 | -10 | 714990 | 714990 | 100% | 0 | 0 | 0 | 92950 | -1 | 92949 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Exim, S.A. | Individual | AFR | BDI | FOA | 35 | INV | 10 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2005-01-01 |  | 2003-12-01 | 2006-06-01 | 78262 | -8335 | 69927 | 69927 | 100% | 0 | 0 | 0 | 10174.06 | -1084.06 | 9090 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | Individual | AFR | BEN | FOA | 32 | INV | 12 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2003-07-01 |  | 2003-08-01 | 2005-09-01 | 143027 | -6481 | 136546 | 136546 | 100% | 0 | 0 | 0 | 18593.51 | -842.51 | 17751 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Tecnosono | Individual | LAC | BRA | FOA | 36 | INV | 248 | A | I | CFC | 23 | 23 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2003-07-01 | 2004-01-01 | 134718 | -4512.44 | 130205.56 | 130206 | 100% | -0.44 | 0 | 0 | 17513.34 | -587.3358 | 16926.0614 | -0.057198 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Jiangsu Jintan Insulation Material Plant | Individual | ASP | CPR | FOA | 19 | INV | 161 | N | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 66000 | -5638 | 60362 | 60362 | 100% | 0 | 0 | 0 | 8580 | -733 | 7847 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Faw-Trim | Individual | ASP | CPR | FOA | 15 | INV | 95 | A | I | CFC | 28 | 28 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Tianjin Daqui Foam Plant | Individual | ASP | CPR | FOA | 18 | INV | 141 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 160000 | -60 | 159940 | 159940 | 100% | 0 | 0 | 0 | 20800 | -8 | 20792 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride and forced cooling system in the manufacture of flexible polyurethane foam (slabstock) at Cangzhou New-Type Foam Decoration Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 250 | N | I | CFC | 67 | 67 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2001-05-01 | 2003-09-01 | 417410 | -17009 | 400401 | 400401 | 100% | 0 | 0 | 0 | 54263.3 | -2211.3 | 52052 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of flexible slabstock polyurethane foam at Ningbo Yongling Rubber and Plastic Co. | Individual | ASP | CPR | FOA | 26 | INV | 266 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 448560 | -20224 | 428336 | 428336 | 100% | 0 | 0 | 0 | 58312.8 | -2628.8 | 55684 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology int he manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Co. Plastics Factory | Individual | ASP | CPR | FOA | 25 | INV | 247 | N | I | CFC | 81 | 81 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2000-08-01 |  | 2003-05-01 | 2005-02-01 | 504630 | -4472 | 500158 | 500158 | 100% | 0 | 0 | 0 | 65601.9 | -580.9 | 65021 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Tianjin conversion to CFC-free technology in the manufacture of flexible polyurethane foam | Individual | ASP | CPR | FOA | 10 | INV | 32 | N | I | CFC | 180 | 180 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1994-09-01 |  | 1995-04-01 | 1998-12-01 | 1080000 | -41407 | 1038593 | 1038593 | 100% | 0 | 0 | 0 | 140400 | -5383 | 135017 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Poquinsa (Poliuretano Químico Indutrial, S.A.) | Individual | LAC | DOM | FOA | 29 | INV | 24 | A | I | CFC | 4 | 4 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 24920 | 0 | 24920 | 24920 | 100% | 0 | 0 | 0 | 3240 | 0 | 3240 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Espumas del Cibao | Individual | LAC | DOM | FOA | 29 | INV | 22 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2002-11-01 | 89712 | -1048 | 88664 | 88664 | 100% | 0 | 0 | 0 | 11662.56 | -135.56 | 11527 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 12 | A | I | CFC | 21 | 21 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 69920 | 0 | 69920 | 69920 | 100% | 0 | 0 | 0 | 9090 | 0 | 9090 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 11 | A | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 75490 | 0 | 75490 | 75490 | 100% | 0 | 0 | 0 | 9814 | 0 | 9814 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by convesion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 10 | A | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-09-01 |  | 2005-12-01 | 2011-11-01 | 165670 | -25705.47 | 139964.53 | 139964.53 | 100% | 0 | 0 | 0 | 21537.1 | -3341.8111 | 18195.2889 | 0 | 0 | Completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slastock foam by conversion to methylene chloride at M.K. SPRL | Individual | AFR | DRC | FOA | 35 | INV | 07 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-04-01 | 149800 | 0 | 149800 | 149800 | 100% | 0 | 0 | 0 | 19474 | 0 | 19474 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Individual | AFR | DRC | FOA | 35 | INV | 06 | A | I | CFC | 38 | 38 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-11-01 | 2007-03-01 | 190820 | 0 | 190820 | 190820 | 100% | 0 | 0 | 0 | 24807 | 0 | 24807 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Terminal umbrella project for the foam sector | Individual | AFR | DRC | FOA | 41 | INV | 19 | N | I | CFC | 123 | 123 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2012-07-01 | 640820 | -22461.21 | 618358.79 | 618358.79 | 100% | 0 | 0 | 0 | 48062 | -1684.61 | 46377.39 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam (PUF) at Horse Foam Co. | Individual | AFR | EGY | FOA | 11 | INV | 20 | A | I | CFC | 120 | 120 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-08-01 |  | 1997-03-01 | 2000-07-01 | 385000 | -107636 | 277364 | 277364 | 100% | 0 | 0 | 0 | 50050 | -13993 | 36057 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded flexible polyurethane foam at Modern Building Carpentry Co. (Mobica) | Individual | AFR | EGY | FOA | 10 | INV | 15 | A | I | CFC | 20 | 20 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 434000 | 0 | 434000 | 434000 | 100% | 0 | 0 | 0 | 56420 | 0 | 56420 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of flexible polyurethane foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 08 | INV | 05 | A | I | CFC | 121 | 121 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1993-10-01 |  | 1994-01-01 | 2003-04-01 | 497000 | 3489 | 500489 | 500489 | 100% | 0 | 0 | 0 | 64610 | 454 | 65064 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of flexible polyurethane foam at Foam Industrial and Hyma | Individual | AFR | EGY | FOA | 12 | INV | 22 | A | I | CFC | 170 | 170 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-06-01 |  | 1997-03-01 | 2000-07-01 | 525000 | -11897.74 | 513102.26 | 513102 | 100% | 0.26 | 0 | 0 | 68250 | -1546.9962 | 66702.97 | 0.0338 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam at Alex Foam (formerly Dekheila Chemical Industries Co.) | Individual | AFR | EGY | FOA | 11 | INV | 19 | A | I | CFC | 130 | 130 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1995-11-01 | 1998-12-01 | 650000 | -82388 | 567612 | 567612 | 100% | 0 | 0 | 0 | 84500 | -10710 | 73790 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Karan Foam Manufacturing Ltd. | Individual | AFR | GAM | FOA | 22 | INV | 06 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 63500 | -2619 | 60881 | 60881 | 100% | 0 | 0 | 0 | 8255 | -340 | 7915 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Umbrella project for continuation of CFC free-technology in the manufacture of flexible polyurethane foam at Ashanti, Latex Foam, Nsawam and Prestige Foam | Individual | AFR | GHA | FOA | 12 | INV | 07 | A | I | CFC | 316 | 316 | 0 | 0 | 1994-03-01 | 1997-12-01 | 1994-12-01 |  | 2000-06-01 | 2001-12-01 | 345000 | -53650 | 291350 | 291350 | 100% | 0 | 0 | 0 | 44850 | -6974 | 37876 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1994 | 1999-08-01 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) in the manufacture of flexible polyurethane foam (box) at Prasert Foam Co., Ltd. | Individual | ASP | LAO | FOA | 38 | INV | 10 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-08-01 | 2005-11-01 | 139343 | 0 | 139343 | 139343 | 100% | 0 | 0 | 0 | 18115 | 0 | 18115 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | Individual | AFR | LIB | FOA | 32 | INV | 06 | A | I | CFC | 40.3 | 40.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-12-01 | 2011-12-01 | 109810 | 0 | 109810 | 109810 | 100% | 0 | 0 | 0 | 14275 | 0 | 14275 | 0 | 0 | Completed in 2005. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | Individual | AFR | LIB | FOA | 35 | INV | 14 | A | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-10-01 | 112440 | 0 | 112440 | 112440 | 100% | 0 | 0 | 0 | 14617 | 0 | 14617 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa | Individual | AFR | LIB | FOA | 34 | INV | 13 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2008-04-01 | 113727 | 0 | 113727 | 113727 | 100% | 0 | 0 | 0 | 14785 | 0 | 14785 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | Individual | AFR | LIB | FOA | 32 | INV | 08 | A | I | CFC | 31.4 | 31.4 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2007-04-01 | 2008-03-01 | 124860 | -97 | 124763 | 124763 | 100% | 0 | 0 | 0 | 16231.8 | -12.8002 | 16218.9998 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga | Individual | AFR | LIB | FOA | 35 | INV | 16 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2007-03-01 | 125640 | 0 | 125640 | 125640 | 100% | 0 | 0 | 0 | 16333 | 0 | 16333 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | Individual | AFR | LIB | FOA | 34 | INV | 12 | A | I | CFC | 32 | 32 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2007-03-01 | 129109 | 0 | 129109 | 129109 | 100% | 0 | 0 | 0 | 16784 | 0 | 16784 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to liquid carbon dioxide (LCD) in the manufacture of flexible polyurethane foam at El Houria Unit Plant | Individual | AFR | LIB | FOA | 35 | INV | 15 | A | I | CFC | 96 | 96 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-08-01 | 2011-11-01 | 520405 | -49886.77 | 470518.23 | 470518.23 | 100% | 0 | 0 | 0 | 67244.55 | -6445.7522 | 60798.7978 | 0 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology for the manufacture of flexible polyurethane foam at Nite Beauty Industries | Individual | ASP | MAL | FOA | 19 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-06-01 | 1999-12-01 | 36875 | 0 | 36875 | 36875 | 100% | 0 | 0 | 0 | 4794 | 0 | 4794 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at N.L.Y. Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 27 | A | I | CFC | 55 | 55 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 130000 | -14651 | 115349 | 115349 | 100% | 0 | 0 | 0 | 16900 | -1905 | 14995 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at Phoenix Base Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 44 | A | I | CFC | 61 | 61 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-06-01 |  | 1995-02-01 | 1998-12-01 | 165000 | 12784 | 177784 | 177784 | 100% | 0 | 0 | 0 | 21450 | 1662 | 23112 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam at Pexafoam Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 26 | A | I | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 2003-09-01 | 195000 | -5077.19 | 189922.81 | 189923 | 100% | -0.19 | 0 | 0 | 25350 | -660 | 24690.0247 | -0.0247 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of flexible polyurethane foam (slabstock) at small scale producers | Individual | ASP | MAL | FOA | 12 | INV | 33 | A | I | CFC | 80 | 80 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-03-01 |  | 1998-08-01 | 2000-12-01 | 1045000 | -55551.66 | 989448.34 | 989448 | 100% | 0.34 | 0 | 0 | 135850 | -7221.9958 | 128627.96 | 0.0442 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | Individual | AFR | MLW | FOA | 26 | INV | 12 | A | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 156500 | -17548.0048 | 138951.9952 | 138952 | 100% | -0.0048 | 0 | 0 | 20345 | -2281.0006 | 18064 | -0.00062401 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Molen Industrie S.A. | Individual | AFR | MOR | FOA | 23 | INV | 16 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-12-01 | 1999-12-01 |  | 2002-06-01 | 2003-11-01 | 56070 | 0 | 56070 | 56070 | 100% | 0 | 0 | 0 | 7289 | 0 | 7289 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richdor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 14 | A | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 62300 | 0 | 62300 | 62300 | 100% | 0 | 0 | 0 | 8099 | 0 | 8099 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Royal Foam Products | Individual | AFR | NIR | FOA | 20 | INV | 12 | A | D | CFC | 43 | 43 | 0 | 0 | 1996-10-01 | 1998-08-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 34000 | -600 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4420 | -78 | 4342 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafco Industries Limited | Individual | AFR | NIR | FOA | 29 | INV | 56 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-12-01 | 2006-06-01 | 58559 | 0 | 58559 | 58559 | 100% | 0 | 0 | 0 | 7613 | 0 | 7613 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Teju Industries Limited | Individual | AFR | NIR | FOA | 20 | INV | 13 | A | D | CFC | 47 | 47 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-10-01 | 2003-01-01 | 75000 | -6859 | 68141 | 68141 | 100% | 0 | 0 | 0 | 9750 | -892 | 8858 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 32 | A | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 2001-10-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 84600 | 0 | 84600 | 84600 | 100% | 0 | 0 | 0 | 10998 | 0 | 10998 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 | 2003-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Rubez (Nig.) Ltd. (Current Foam) | Individual | AFR | NIR | FOA | 29 | INV | 55 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2002-12-01 |  | 2003-08-01 | 2005-11-01 | 89803 | -65 | 89738 | 89738 | 100% | 0 | 0 | 0 | 11674.39 | -8.39 | 11666 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride blown technology in the manufacture of flexible polyurethane foam at Betaday Industries Ltd. | Individual | AFR | NIR | FOA | 29 | INV | 58 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 104495 | -1 | 104494 | 104494 | 100% | 0 | 0 | 0 | 13584.35 | -0.35 | 13584 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Sara Products Limited | Individual | AFR | NIR | FOA | 20 | INV | 15 | A | D | CFC | 27.7 | 27.7 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1999-07-01 | 2001-12-01 | 107000 | -2075 | 104925 | 104925 | 100% | 0 | 0 | 0 | 13910 | -270.0037 | 13639.9963 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bamako Industrial, Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 94 | A | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2005-11-01 | 114510 | -3460 | 111050 | 111050 | 100% | 0 | 0 | 0 | 14886.3 | -450.3 | 14436 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Diamond Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 49 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2001-11-01 | 2002-11-01 | 112150 | 0 | 112150 | 112150 | 100% | 0 | 0 | 0 | 14580 | 0 | 14580 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 89 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2005-11-01 | 126531 | -13568.0041 | 112962.9959 | 112963 | 100% | -0.0041 | 0 | 0 | 16449.03 | -1764.0273 | 14685.0032 | -0.00053299 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bibafoam Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 92 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-10-01 | 114685 | 0 | 114685 | 114685 | 100% | 0 | 0 | 0 | 14909 | 0 | 14909 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafa Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 70 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-12-01 | 2006-10-01 | 124667 | -9881 | 114786 | 114786 | 100% | 0 | 0 | 0 | 16206.71 | -1284.71 | 14922 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Winco Foam Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 21 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 117200 | -321 | 116879 | 116879 | 100% | 0 | 0 | 0 | 15236 | -42 | 15194 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manfuacture of flexible slabstock foam by conversion to methylene chloride at Abeokuta Commercial and Industrial Co. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 66 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 118468 | -382 | 118086 | 118086 | 100% | 0 | 0 | 0 | 15400.84 | -49.84 | 15351 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Rima Foam Products Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 88 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-06-01 | 119036 | -582 | 118454 | 118454 | 100% | 0 | 0 | 0 | 15474.68 | -75.68 | 15399 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Atuchukwu Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 83 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 118488 | -1 | 118487 | 118487 | 100% | 0 | 0 | 0 | 15403 | 0 | 15403 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Tinuola Bay Industries Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 47 | A | I | CFC | 21 | 21 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-09-01 | 2003-09-01 | 119410 | 0 | 119410 | 119410 | 100% | 0 | 0 | 0 | 15523 | 0 | 15523 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Elico Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 23 | A | I | CFC | 25.7 | 25.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 133900 | -13658 | 120242 | 120242 | 100% | 0 | 0 | 0 | 17407 | -1776 | 15631 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Bajabure Industrial Complex Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 22 | A | I | CFC | 32.3 | 32.3 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2002-11-01 | 135400 | -11117 | 124283 | 124283 | 100% | 0 | 0 | 0 | 17602 | -1445 | 16157 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pesaco Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 39 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1998-11-01 | 2000-08-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 126400 | 0 | 126400 | 126400 | 100% | 0 | 0 | 0 | 16432 | 0 | 16432 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Group Enterprises Nig. Ltd. (Polly Foam) | Individual | AFR | NIR | FOA | 26 | INV | 38 | A | I | CFC | 26 | 26 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 128900 | -2349 | 126551 | 126551 | 100% | 0 | 0 | 0 | 16757 | -305 | 16452 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Marta Industries (Nig.) Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 34 | A | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 130600 | -1299 | 129301 | 129301 | 100% | 0 | 0 | 0 | 16978 | -169 | 16809 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Wappah Foam Limited | Individual | AFR | NIR | FOA | 31 | INV | 69 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 130081 | -4 | 130077 | 130077 | 100% | 0 | 0 | 0 | 16910.53 | -0.53 | 16910 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at United Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 46 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-07-01 | 2001-10-01 | 2002-02-01 |  | 2003-08-01 | 2007-01-01 | 137310 | -6098 | 131212 | 131212 | 100% | 0 | 0 | 0 | 17850.3 | -793.2967 | 17057.0033 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Okin Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 33 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-11-01 | 2002-11-01 | 133200 | 0 | 133200 | 133200 | 100% | 0 | 0 | 0 | 17316 | 0 | 17316 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to mehtylene chloride in the manufacture of flexible polyurethane foam at Vito Company (Nig.) Ltd., Victory Foam | Individual | AFR | NIR | FOA | 29 | INV | 59 | A | I | CFC | 26 | 26 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 133560 | -188 | 133372 | 133372 | 100% | 0 | 0 | 0 | 17362.8 | -24.8 | 17338 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Orbit Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 31 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-07-01 | 2003-11-01 | 135200 | -1 | 135199 | 135199 | 100% | 0 | 0 | 0 | 17576 | 0 | 17576 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Universal Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 43 | A | I | CFC | 30.6 | 30.6 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-11-01 | 135300 | 0 | 135300 | 135300 | 100% | 0 | 0 | 0 | 17589 | 0 | 17589 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Bodefoam Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 37 | A | I | CFC | 35.3 | 35.3 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 136400 | 0 | 136400 | 136400 | 100% | 0 | 0 | 0 | 17732 | 0 | 17732 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Sokoto Foam Factory (Nig.) Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 65 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-12-01 | 2005-09-01 | 141421 | -4328 | 137093 | 137093 | 100% | 0 | 0 | 0 | 18384.73 | -562.73 | 17822 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Mouka Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 24 | A | I | CFC | 30.3 | 30.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2004-01-01 | 143600 | -3462 | 140138 | 140138 | 100% | 0 | 0 | 0 | 18668 | -450 | 18218 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 35 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 142300 | -1209.9956 | 141090.0044 | 141090 | 100% | 0.0044 | 0 | 0 | 18499 | -156.9994 | 18342 | 0.00057201 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Safa Foam Products (Nig) Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 25 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-12-01 |  | 2003-08-01 | 2006-10-01 | 146400 | 0 | 146400 | 146400 | 100% | 0 | 0 | 0 | 19032 | 0 | 19032 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 1997 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Apaco Foam and Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 84 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 147018 | 0 | 147018 | 147018 | 100% | 0 | 0 | 0 | 19112 | 0 | 19112 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Chemical and Wire Manufacturers Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 36 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-01-01 | 2003-11-01 | 164500 | 0 | 164500 | 164500 | 100% | 0 | 0 | 0 | 21385 | 0 | 21385 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 | 2003-07-01 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Climax Ind. Ltd. (Ely Foam) | Individual | AFR | NIR | FOA | 31 | INV | 68 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 173362 | -575 | 172787 | 172787 | 100% | 0 | 0 | 0 | 22537.06 | -75.06 | 22462 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Vono Products PLC | Individual | AFR | NIR | FOA | 29 | INV | 57 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 173782 | 0 | 173782 | 173782 | 100% | 0 | 0 | 0 | 22592 | 0 | 22592 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Yinka-Oba Foam Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 42 | A | I | CFC | 30 | 30 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2003-08-01 | 2005-10-01 | 185300 | -628.997 | 184671.003 | 184671 | 100% | 0.003 | 0 | 0 | 24089 | -81.9996 | 24007 | 0.00039 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Gasfa Industries Nig., Ltd. (Meka Foam) | Individual | AFR | NIR | FOA | 34 | INV | 85 | A | I | CFC | 40.5 | 40.5 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2003-08-01 | 2005-09-01 | 238843 | -9895 | 228948 | 228948 | 100% | 0 | 0 | 0 | 31049.59 | -1285.59 | 29764 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Ugochukwu Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 28 | A | I | CFC | 118.6 | 118.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-07-01 | 2002-11-01 | 407600 | 0 | 407600 | 407600 | 100% | 0 | 0 | 0 | 52988 | 0 | 52988 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Individual | AFR | NIR | FOA | 35 | INV | 96 | A | I | CFC | 199.2 | 199.2 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2007-02-01 | 1062808 | 0 | 1062808 | 1062808 | 100% | 0 | 0 | 0 | 126909.02 | 0 | 126909.02 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible polyurethane foam at Foamcraft Incorporated | Individual | ASP | PHI | FOA | 13 | INV | 31 | A | I | CFC | 90 | 90 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1998-05-01 | 2001-12-01 | 185000 | -19094.3 | 165905.7 | 165906 | 100% | -0.3 | 0 | 0 | 24050 | -2481.999 | 21568.04 | -0.039 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of flexible polyurethane (slabstock) at Mandaue Foam Industries Inc. | Individual | ASP | PHI | FOA | 17 | INV | 37 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-12-01 |  | 1997-06-01 | 2000-07-01 | 217000 | -9332 | 207668 | 207668 | 100% | 0 | 0 | 0 | 28210 | -1213 | 26997 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-use at small manufacturers of flexible foam | Individual | ASP | PHI | FOA | 12 | INV | 26 | N | I | CFC | 35 | 35 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1999-12-01 | 2003-04-01 | 745000 | -262154 | 482846 | 482846 | 100% | 0 | 0 | 0 | 96850 | -34080 | 62770 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Conversion from CFC-11 to low index additive (LIA) technology in the manufacture of flexible polyurethane foam at P.T. Foam Chiengmai L.P. | Individual | ASP | THA | FOA | 28 | INV | 118 | A | I | CFC | 12.7 | 12.7 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79120 | 0 | 79120 | 79120 | 100% | 0 | 0 | 0 | 10285.6 | 0 | 10285.6 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam at Chareon Porn | Individual | ASP | THA | FOA | 23 | INV | 68 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | -29 | 93471 | 93471 | 100% | 0 | 0 | 0 | 12155 | -3.77 | 12151.23 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam (boxfoam) at Thai International | Individual | ASP | THA | FOA | 23 | INV | 69 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 | 0 | 12155 | 0 | 12155 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane boxfoam at Nun Charoen | Individual | ASP | THA | FOA | 23 | INV | 71 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at P. Chongcharoen | Individual | ASP | THA | FOA | 26 | INV | 102 | A | I | CFC | 24 | 24 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 130500 | -256 | 130244 | 130244 | 100% | 0 | 0 | 0 | 16965 | -33.28 | 16931.72 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to low index/additive technology and methylene chloride in the manufacture of flexible polyurethane boxfoam at City Foam Co., Ltd. | Individual | ASP | THA | FOA | 25 | INV | 91 | A | I | CFC | 42 | 42 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2000-12-01 | 156100 | 0 | 156100 | 156100 | 100% | 0 | 0 | 0 | 20293 | 0 | 20293 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of flexible PUF slabstock at Karn Yang Yeen Yong Industry Ltd. | Individual | ASP | THA | FOA | 15 | INV | 44 | A | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-11-01 |  | 1999-04-01 | 2000-12-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 | 0 | 22100 | 0 | 22100 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible polyurethane foam at Lucky Group | Individual | ASP | THA | FOA | 13 | INV | 35 | A | I | CFC | 187 | 187 | 0 | 0 | 1994-07-01 | 1997-12-01 | 1995-07-01 |  | 1999-11-01 | 2003-07-01 | 605000 | -1836 | 603164 | 603164 | 100% | 0 | 0 | 0 | 78650 | -238.68 | 78411.32 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Plyfoam Limited | Individual | AFR | URT | FOA | 31 | INV | 13 | A | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-07-01 | 2002-07-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 175134 | 0 | 175134 | 175134 | 100% | 0 | 0 | 0 | 22767.42 | 0 | 22767.42 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 09 | N | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664.17 | 25335.83 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Matelas Djurdjura | Individual | AFR | ALG | FOA | 25 | INV | 27 | A | I | CFC | 28 | 28 |  |  | 1998-07-01 | 1998-12-01 | 1999-08-01 |  | 2001-07-01 | 2002-09-01 | 82608 | -753 | 81855 | 81855.45 | 100% | -0.45 | 0 |  | 10739 | -115 | 10624 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Snam flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 22 | A | I | CFC | 32 | 32 |  |  | 1997-05-01 | 1997-11-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 88360 | -408 | 87952 | 87952.11 | 100% | -0.11 | 0 |  | 11487 | -71 | 11416 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Maghreb Mousse | Individual | AFR | ALG | FOA | 26 | INV | 29 | A | I | CFC | 24 | 24 |  |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 2001-07-01 | 2002-09-01 | 96492 | -500 | 95992 | 95992.28 | 100% | -0.28 | 0 |  | 12544 | -85 | 12459 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 23 | A | I | CFC | 24 | 24 |  |  | 1997-05-01 | 1997-10-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 98770 | -1411 | 97359 | 97359.2 | 100% | -0.2 | 0 |  | 12840 | -203 | 12637 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | AFR | ALG | FOA | 28 | INV | 37 | A | I | CFC | 20 | 20 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 97986 | -66 | 97920 | 97919.63 | 100% | 0.37 | 0 |  | 12738 | -29 | 12709 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | AFR | ALG | FOA | 28 | INV | 39 | A | I | CFC | 18 | 18 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 99477 | -104 | 99373 | 99373.32 | 100% | -0.32 | 0 |  | 12932 | -34 | 12898 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | AFR | ALG | FOA | 27 | INV | 34 | A | I | CFC | 20 | 20 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2003-07-01 | 110179 | -38 | 110141 | 110140.55 | 100% | 0.45 | 0 |  | 14323 | -27 | 14296 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | AFR | ALG | FOA | 27 | INV | 33 | A | I | CFC | 22 | 22 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2004-03-01 | 120060 | 0 | 120060 | 120059.99 | 100% | 0.01 | 0 |  | 15608 | 0 | 15608 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 23 | INV | 25 | A | I | CFC | 95 | 95 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-10-01 | 2003-07-01 | 553480 | -1430 | 552050 | 552049.87 | 100% | 0.13 | 0 |  | 71952 | -299 | 71653 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | Individual | EUR | BHE | FOA | 35 | INV | 08 | A | I | CFC | 21 | 21 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 101950 | -1506 | 100444 | 100444.19 | 100% | -0.19 | 0 |  | 13254 | -196 | 13058 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at Sonopol | Individual | AFR | CMR | FOA | 23 | INV | 11 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-02-01 | 506310 | 0 | 506310 | 506309.62 | 100% | 0.38 | 0 |  | 65820 | -30 | 65790 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Scimpos | Individual | AFR | CMR | FOA | 23 | INV | 10 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-06-01 | 541350 | -491 | 540859 | 540859.12 | 100% | -0.12 | 0 |  | 70376 | -176 | 70200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Oriolik Co. flexible polyurethane foam plant | Individual | EUR | CRO | FOA | 22 | INV | 04 | A | I | CFC | 25 | 25 |  |  | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-11-01 | 2000-07-01 | 110780 | -24 | 110756 | 110756 | 100% | 0 | 0 |  | 14401 | -26 | 14375 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Elastino Satyajaya flexible polyurethane foam plant | Individual | ASP | IDS | FOA | 22 | INV | 58 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 75943 | 0 | 75943 | 75943 | 100% | 0 | 0 |  | 9873 | -5 | 9868 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Winnerfoam Abadi | Individual | ASP | IDS | FOA | 22 | INV | 56 | A | I | CFC | 40 | 40 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 79472 | -1287 | 78185 | 78185 | 100% | 0 | 0 |  | 10331 | -183 | 10148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Panca Duta foam industry | Individual | ASP | IDS | FOA | 22 | INV | 57 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2001-12-01 | 86955 | -621 | 86334 | 86334.05 | 100% | -0.05 | 0 |  | 11304 | -98 | 11206 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | Individual | ASP | IRA | FOA | 37 | INV | 149 | A | I | CFC | 91.1 | 91.1 |  |  | 2002-07-01 | 2002-11-01 | 2004-03-01 |  | 2008-12-01 | 2009-03-01 | 373515 | 0 | 373515 | 373514.99 | 100% | 0.01 | 0 |  | 48557 | 0 | 48557 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Urethane Systems Company (USC) | Individual | ASP | IRA | FOA | 22 | INV | 21 | A | I | CFC | 110 | 110 |  |  | 1997-05-01 | 2001-09-01 | 1998-06-01 |  | 2003-03-01 | 2004-02-01 | 487125 | -4690 | 482435 | 482435.39 | 100% | -0.39 | 0 |  | 63326 | -709 | 62617 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Safoam Co. | Individual | ASP | IRA | FOA | 22 | INV | 20 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 2002-12-01 | 2003-12-01 | 487125 | 0 | 487125 | 487125.1 | 100% | -0.1 | 0 |  | 63326 | -85 | 63241 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 from flexible slabstock foam manufacturing at Shizar Co. | Individual | ASP | IRA | FOA | 22 | INV | 22 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2003-12-01 | 2004-12-01 | 487125 | 0 | 487125 | 487124.7 | 100% | 0.3 | 0 |  | 63326 | 0 | 63326 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Mashhad Foam | Individual | ASP | IRA | FOA | 23 | INV | 29 | A | I | CFC | 90 | 90 |  |  | 1997-11-01 | 1999-01-01 | 1998-12-01 |  | 2003-12-01 | 2004-12-01 | 503330 | -1856 | 501474 | 501473.82 | 100% | 0.18 | 0 |  | 65433 | -345 | 65088 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out ODS in the manufacture of flexible slab stock foam through the use of LCD blowing technology at Abre Shomal Co. | Individual | ASP | IRA | FOA | 35 | INV | 115 | A | I | CFC | 90.4 | 90.4 |  |  | 2001-12-01 | 2002-06-01 | 2003-07-01 |  | 2004-03-01 | 2005-08-01 | 552148 | -50609 | 501539 | 501538.52 | 100% | 0.48 | 0 |  | 70736 | -5654 | 65082 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at F.I.M.A. flexible polyurethane foam plant | Individual | AFR | IVC | FOA | 19 | INV | 06 | A | I | CFC | 53.1 | 53.1 |  |  | 1996-05-01 | 1997-09-01 | 1997-07-01 |  | 1997-12-01 | 2001-03-01 | 85087 | -246 | 84841 | 84841 | 100% | 0 | 0 |  | 11061 | -49 | 11012 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Ets. Henri Abdallah P.F.M. | Individual | ASP | LEB | FOA | 21 | INV | 18 | A | I | CFC | 16.6 | 16.6 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 81291 | -583 | 80708 | 80708 | 100% | 0 | 0 |  | 10568 | -93 | 10475 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Nasri Karam and Sons | Individual | ASP | LEB | FOA | 20 | INV | 09 | A | I | CFC | 22 | 22 |  |  | 1996-10-01 | 1997-07-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 100109 | -106 | 100003 | 100003 | 100% | 0 | 0 |  | 13014 | -34 | 12980 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 05 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2002-09-01 | 520125 | -4895 | 515230 | 515230.18 | 100% | -0.18 | 0 |  | 67616 | -742 | 66874 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at S.C. Spumotim S.A. | Individual | EUR | ROM | FOA | 20 | INV | 09 | A | I | CFC | 30 | 30 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1997-12-01 | 2000-07-01 | 142293 | -83 | 142210 | 142210 | 100% | 0 | 0 |  | 18498 | -40 | 18458 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Patra Foam Co. flexible polyurethane foam plant | Individual | AFR | SUD | FOA | 19 | INV | 05 | A | I | CFC | 16 | 16 |  |  | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1997-12-01 | 2000-04-01 | 72227 | 0 | 72227 | 72227 | 100% | 0 | 0 |  | 9390 | -1 | 9389 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Walid and Nabil Rankousi Ltd. | Individual | ASP | SYR | FOA | 21 | INV | 18 | A | I | CFC | 38.7 | 38.7 |  |  | 1997-02-01 | 1998-11-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 86782 | -2175 | 84607 | 84607 | 100% | 0 | 0 |  | 11282 | -301 | 10981 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Abdul Karim Sbei | Individual | ASP | SYR | FOA | 21 | INV | 17 | A | I | CFC | 61.7 | 61.7 |  |  | 1997-02-01 | 1997-06-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 92256 | -1984 | 90272 | 90272 | 100% | 0 | 0 |  | 11993 | -276 | 11717 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Dakkak Co. flexible polyurethane foam plant | Individual | ASP | SYR | FOA | 19 | INV | 14 | A | I | CFC | 17 | 17 |  |  | 1996-05-01 | 1996-10-01 | 1997-05-01 |  | 1998-12-01 | 2001-11-01 | 96553 | 0 | 96553 | 96552.94 | 100% | 0.06 | 0 |  | 12552 | -17 | 12535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in the manufacture of flexible PU slabstock foam through the use of methylene chloride as blowing agent at Chaar Bros Co. | Individual | ASP | SYR | FOA | 26 | INV | 34 | A | I | CFC | 50 | 50 |  |  | 1998-11-01 | 1999-02-01 | 2000-04-01 |  | 2000-05-01 | 2001-07-01 | 98248 | -79 | 98169 | 98169 | 100% | 0 | 0 |  | 12772 | -30 | 12742 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al-Muzayek | Individual | ASP | SYR | FOA | 34 | INV | 76 | A | I | CFC | 33.7 | 33.7 |  |  | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-12-01 | 2004-12-01 | 106789 | 0 | 106789 | 106789.12 | 100% | -0.12 | 0 |  | 13883 | -9 | 13874 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Akal Factory | Individual | ASP | SYR | FOA | 23 | INV | 25 | A | I | CFC | 101 | 101 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 2002-10-01 | 2004-04-01 | 510130 | 0 | 510130 | 510130.14 | 100% | -0.14 | 0 |  | 66317 | -26 | 66291 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU slabstock foam through the use of CO2 blowing technology at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 26 | INV | 32 | A | I | CFC | 96 | 96 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2001-12-01 | 2003-12-01 | 543918 | 0 | 543918 | 543917.73 | 100% | 0.27 | 0 |  | 69831 | -3 | 69828 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Phasing out CFC-11 at Sotrapoc flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 24 | A | I | CFC | 20 | 20 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 90037 | -1704 | 88333 | 88332.94 | 100% | 0.06 | 0 |  | 11705 | -240 | 11465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Polymousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 26 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 104343 | -88 | 104255 | 104255.05 | 100% | -0.05 | 0 |  | 13565 | -33 | 13532 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sud Inter Mousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 23 | A | I | CFC | 102 | 102 |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 2001-12-01 | 2003-08-01 | 546920 | -271 | 546649 | 546649.3 | 100% | -0.3 | 0 |  | 71100 | -148 | 70952 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU molded foam through the use of CO2 blosing technology at Sungersan, Bursa | Individual | EUR | TUR | FOA | 27 | INV | 53 | A | I | CFC | 30 | 30 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2002-05-01 | 327374 | 0 | 327374 | 327374.39 | 100% | -0.39 | 0 |  | 42559 | -9 | 42550 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of CO2 blowing technology at Serra Sunger | Individual | EUR | TUR | FOA | 25 | INV | 47 | A | I | CFC | 86 | 86 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-08-01 | 454358 | 0 | 454358 | 454358.36 | 100% | -0.36 | 0 |  | 59067 | -16 | 59051 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in the manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Sungersan | Individual | EUR | TUR | FOA | 27 | INV | 52 | A | I | CFC | 78 | 78 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 467397 | 0 | 467397 | 467397 | 100% | 0 | 0 |  | 60762 | 0 | 60762 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Isbir Termoset Plastic San. A.S., Ankara, Turkey | Individual | EUR | TUR | FOA | 23 | INV | 30 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1999-03-01 | 1998-12-01 |  | 2001-04-01 | 2002-09-01 | 501350 | 0 | 501350 | 501350.19 | 100% | -0.19 | 0 |  | 65176 | -45 | 65131 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Espol Sunger Company | Individual | EUR | TUR | FOA | 31 | INV | 68 | A | I | CFC | 95 | 95 |  |  | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2004-02-01 | 2004-12-01 | 552297 | 0 | 552297 | 552297.4 | 100% | -0.4 | 0 |  | 70753 | -31 | 70722 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Urosan Kimiya Sanayii A.S. | Individual | EUR | TUR | FOA | 20 | INV | 22 | A | I | CFC | 135 | 135 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1999-12-01 | 2002-04-01 | 643500 | -10955 | 632545 | 632544.84 | 100% | 0.16 | 0 |  | 83655 | -1555 | 82100 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | I | CFC | 34.4 | 34.4 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -169 | 100071 | 100071.22 | 100% | -0.22 | 0 |  | 13031 | -42 | 12989 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al Hadi Co. | Individual | ASP | IRQ | FOA | 57 | INV | 06 | A | I | CFC | 20 | 0 |  |  | 2009-04-01 | 2010-12-01 | 2011-03-31 | 2013-12-01 |  |  | 126457 | 0 | 126457 | 125104.58 | 98.93% | 1352.42 | 0 | 1352 | 11381 | 0 | 11259 | 122 | 0 | Equipment has been shipped and stays in customs. Coordination meeting had taken place in Bahrain; Government (PMU) committed to assist with custom clearance. Forwarder is ready to bring equipment to the site for subsequent installation, commissioning and start-up trial by the supplier as soon as cleared from customs. | Equipment installation, commissioning, start-up trial; project completion. Reason for the delay: The customs clearance has taken longer than expected. |  | 2011-12-01 | INV
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom. |  |  | 1994-12-01 | INV
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 07 | INV | 18 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. |  |  |  | INV
COM | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | AFG | PHA | 60 | PRP | 11 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-03-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP approved at 63rd meeting
COM | Germany | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IRA | PHA | 57 | PRP | 192 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2011-04-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 |  | HPMP was approved based on preparatory study
COM | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | KEN | PHA | 58 | PRP | 49 | A | I | HCFC | 0 |  | 0 |  | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2012-04-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP document was finalised and was approved at the 66th Excom as bilateral contribution of France. | The HPMP is being successfully implemented.
COM | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 59 | PRP | 42 | A | I | HCFC | 0 |  | 0 |  | 2009-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | A comprehensive survey of the R&AC use was conducted and information put together into the HPMP which included both foam and R&AC components. The project was approved at the 65th Excom.
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | INV | 77 | N | I | HCFC | 7.7 | 7.7 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2012-12-01 |  | 400000 | 0 | 400000 | 337301.38 | 84.33% | 62698.62 | 62698.62 | 50158.896 | 30000 | 0 | 25297.6035 | 4702.3965 | 4702.3965 | Completed in 2012. The second tranche request was prepared and approved by the ExCom in 2012. Substantial advances with training of technicians and introduction of new alternatives for flushing. New legislation was introduced for the Domestic Refrigeration Sector. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
COM | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | AFR | GHA | PHA | 61 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2014-12-01 |  | 2012-12-01 |  | 200000 | 0 | 200000 | 199835.58 | 99.92% | 164.42 | 0 | 131.536 | 15000 | 0 | 14987.6685 | 12.3315 | 0 | Completed in 2012. The centre of excellence has been established, HCFC control measures (legal) analysis completed, first version of the paperless monitoring system was completed (awaiting testing). HCFC quota system is being enforced allowing for the tight control of imports. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2011-12-01 |  | 2012-10-01 |  | 855603 | 0 | 855603 | 855603 | 100% | 0 | 0 | 0 | 64170 | 0 | 64170 | 0 | 0 | Completed in 2012. First tranche completed, with finalisation of facility construction at the Pamaque's new facility for hydrocarbon supply and part of equipment delivered. Two (2) missions with international consultant and staff were conducted in 2012 and during the 2nd mission a workshop with HPMP stakeholders was held as well as a tour of the new HC facility. Second tranche was approved at the 66th ExCom. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | ANG | PHA | 55 | PRP | 08 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 |  | 85000 | 0 | 85000 | 84844.72 | 99.82% | 155.28 | 0 | 155.28 | 6375 | 0 | 6363.354 | 11.646 | 0 | Completed in 2011. HPMP Submitted at 65th meeting. Last mission in March 2011 and an extensive and proactive follow-up resulted in ratification of MP amendments and reconciliation / vetting of data. | Completed in 2011. Only some final payments may need to be settled in 2012, including for holding of a series of customs training workshops to strengthen control capacities at ports of entry. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | BGD | PHA | 56 | PRP | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 |  | 125000 | 0 | 125000 | 22298.4 | 17.84% | 102701.6 | 0 | 102701.6 | 9375 | 0 | 1672.38 | 7702.62 | 0 | Completed in 2012. Project preparation is complete but some remaining invoices to be settled in 2013. | Completed in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CHI | PHA | 55 | PRP | 165 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2010-12-01 |  | 150000 | 0 | 150000 | 146643.95 | 97.76% | 3356.05 | 0 | 3356.05 | 11250 | 0 | 10998.2962 | 251.7037 | 0 | Completed. HPMP formulation completed and project will be submitted to the 63rd Executive Committee Meeting. Final invoices still expected in 2011. |  | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COS | PHA | 55 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-10-01 |  | 150000 | 0 | 150000 | 148042.25 | 98.69% | 1957.75 | 0 | 1957.75 | 11250 | 0 | 11103.1688 | 146.8312 | 0 | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting Some final invoices pending. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting Some final invoices pending. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 471 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 |  | 84000 | 0 | 84000 | 72328.03 | 86.1% | 11671.97 | 0 | 11671.97 | 6300 | 0 | 5424.6022 | 875.3977 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. The survey of the XPS Foams Sector covering mainly SMEs was carried out in 2010. However SMEs were not included in the XPS Foam Sector Plan in China's HPMP Stage-I | Completed in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of an overarching HPMP strategy | Individual | ASP | CPR | PHA | 55 | PRP | 464 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-08-01 | 2009-07-01 |  | 2012-08-01 |  | 360000 | 0 | 360000 | 292017.02 | 81.12% | 67982.98 | 0 | 67982.98 | 27000 | 0 | 21901.2765 | 5098.7235 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. The overarching strategy was submitted to and approved at the 64th ExCom. | Completed in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan: solvent sector | Individual | ASP | CPR | PHA | 55 | PRP | 461 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 |  | 432000 | 0 | 432000 | 298981.47 | 69.21% | 133018.53 | 0 | 133018.53 | 32400 | 0 | 22423.6103 | 9976.3898 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. The Solvents Sector Plan was prepared in 2011 and submitted to the 65th Excom meeting in November 2011. | Completed in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan: industrial and commercial refrigeration sub-sectors | Individual | ASP | CPR | PHA | 55 | PRP | 460 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 |  | 604000 | 0 | 604000 | 529745.71 | 87.71% | 74254.29 | 0 | 74254.29 | 45300 | 0 | 39730.9282 | 5569.0718 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. The ICR Sector Plan was prepared in 2010 and submitted as part of China's HPMP Stage-I in July 2011. | Completed in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CUB | PHA | 56 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 |  | 150000 | 0 | 150000 | 130778.48 | 87.19% | 19221.52 | 0 | 19221.52 | 11250 | 0 | 9808.386 | 1441.614 | 0 | HPMP activities completed. Some final payments pending and will be processed in 2013. | Pending payments have been made. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | DOM | PHA | 55 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 |  | 2012-05-01 |  | 150000 | 0 | 150000 | 102703.67 | 68.47% | 47296.33 | 45631.37 | 47296.33 | 11250 | 0 | 7702.7752 | 3547.2247 | 3422.3528 | Completed in 2012. HPMP approved by the 65th Executive Committee Meeting. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ELS | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-06-01 |  | 150000 | 0 | 150000 | 130260.95 | 86.84% | 19739.05 | 7500 | 19739.05 | 11250 | 0 | 9769.5713 | 1480.4288 | 562.5 | Completed in 2012. Some final payments pending. HPMP successfully approved at 65th ExCom. | Completed in 2012. No activities in 2013. Pending payments were made. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 55 | PRP | 19 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 83756.13 | 98.54% | 1243.87 | 0 | 1243.87 | 6375 | 0 | 6281.7097 | 93.2903 | 0 | Completed in 2011. HPMP survey was completed in June 2011. HPMP document was finalised in consultation with national stakeholders in July 2011. HPMP document was submitted to and approved at the 65th Excom held in November 2011. The remaining balance would be used for pending payments for HPMP preparation. | Project Targeted for Completion in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GAM | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 |  | 85000 | -8939.46 | 76060.54 | 76060.54 | 100% | 0 | 0 | 1.4552e-11 | 6375 | -670.46 | 5704.54 | 0 | 0 | Completed. The project was fully staffed by national and international experts. The work on HCFC survey continued through 2010 under UNDP guidance. Last technical visit took place in October 2010. The submission of HPMP was planned for 63rd meeting of the Executive Committee. Final invoices still expected in 2011. |  | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | GEO | PHA | 55 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 |  | 85000 | 0 | 85000 | 83962.32 | 98.78% | 1037.68 | 0 | 1037.68 | 6375 | 0 | 6297.174 | 77.826 | 0 | Completed. HPMP fully formulated and submitted in December 2010 for the consideration of the 63rd meeting of the Executive Committee. Final invoices still expected in 2011. |  | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (refrigeration sector) | Individual | ASP | IND | PHA | 56 | PRP | 433 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 |  | 80000 | 0 | 80000 | 44054.3 | 55.07% | 35945.7 | 0 | 35945.7 | 6000 | 0 | 3304.0725 | 2695.9275 | 0 | See response to IND/PHA/56/PRP/428 on HPMP preparation. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (air conditioning sector) | Individual | ASP | IND | PHA | 56 | PRP | 432 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 |  | 125000 | 0 | 125000 | 55826.4 | 44.66% | 69173.6 | 0 | 69173.6 | 9375 | 0 | 4186.98 | 5188.02 | 0 | See response to IND/PHA/56/PRP/428 on HPMP preparation. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IND | PHA | 56 | PRP | 431 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 |  | 105000 | 0 | 105000 | 65645.52 | 62.52% | 39354.48 | 0 | 39354.48 | 7875 | 0 | 4923.414 | 2951.586 | 0 | See response to IND/PHA/56/PRP/428 on HPMP preparation. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 428 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 |  | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Survey findings were reviewed and updated for data gaps during the period Q1-Q3 of 2011. Draft HPMP document was prepared in Q4. National Stakeholder consultation workshop held in October 2011. | HPMP Stage-I submitted early January for the 66th Excom meeting. Project targeted for financial completion in 2012. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (fire fighting and solvent sectors) | Individual | ASP | IND | PHA | 56 | PRP | 430 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 |  | 2011-12-01 |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1500 | 0 | 0 | 1500 | 0 | See response to IND/PHA/56/PRP/428 on HPMP preparation. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | LEB | PHA | 55 | PRP | 67 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2011-12-01 |  | 137250 | 0 | 137250 | 137250 | 100% | 0 | 0 | 0 | 10294 | 0 | 10294 | 0 | 0 | Completed in 2011. HPMP document was submitted to and approved at the 64th Excom. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | MAL | PHA | 55 | PRP | 161 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 |  | 2011-12-01 |  | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031 | 0 | 13031 | 0 | 0 | Completed in 2011. The HPMP document finalized, submitted to and approved at the 65th ExCom. The remaining balance will be used for pending payments under HPMP preparation and stakeholder consultations. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PAN | PHA | 55 | PRP | 28 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 |  | 150000 | 0 | 150000 | 143544.88 | 95.7% | 6455.12 | 0 | 6455.12 | 11250 | 0 | 10765.866 | 484.134 | 0 | Completed in 2011. HPMP approved by the 65th Executive Committee Meeting. Some final invoices pending. | Completed in 2011. HPMP approved by the 65th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | PAR | PHA | 57 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2012-05-01 |  | 65000 | 0 | 65000 | 50017.15 | 76.95% | 14982.85 | 0 | 14982.85 | 4875 | 0 | 3751.2863 | 1123.7137 | 0 | Completed in 2012. Pending payments made in 2012. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PER | PHA | 55 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2012-12-01 |  | 150000 | 0 | 150000 | 78367.91 | 52.25% | 71632.09 | 20000 | 71632.09 | 11250 | 0 | 5877.5932 | 5372.4068 | 1500 | Completed in 2012. Some final payments and activities pending. Stakeholder consultations took place. HPMP was presented and approved at ExCom 68. | Completed in 2012. Expert mission to take place in April 2013 to discuss pending approval of quota system for HCFCs. UNDP prodoc has been prepared. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | SRL | PHA | 55 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 |  | 112250 | 0 | 112250 | 107221.46 | 95.52% | 5028.54 | 0 | 5028.54 | 8419 | 0 | 8041.8483 | 377.1517 | 0 | Completed in 2011. The HPMP document was finalized and approved at 62nd ExCom . The remaining balance would be used for pending payments. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | TRI | PHA | 59 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2012-06-01 |  | 65000 | 0 | 65000 | 58502.53 | 90% | 6497.47 | 0 | 6497.47 | 4875 | 0 | 4387.6897 | 487.3102 | 0 | Completed in 2012. Some pending payments to be made. Quota system approved and under full enforcement. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | TRI | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | URU | PHA | 55 | PRP | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-12-01 |  | 150000 | 0 | 150000 | 149834.62 | 99.89% | 165.38 | 0 | 165.38 | 11250 | 0 | 11237.5965 | 12.4035 | 0 | HPMP approved by the 65th Executive Committee Meeting. In the process of preparing the implementation of qouta system. | Final payments have been settled. | 2008 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-30 |  | 2012-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed in December 2012. Annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. HCFC baseline changed. HCFC license and quota system completed. Refreshing customs training workshop held in June 2012, 29 participants attended. |  |  |  | Non Investment
COM | UNEP | Development of HCFC phase-out management plan for PIC countries through regional approach | Individual | ASP | ASP | PHA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-09-01 |  | 2011-12-01 |  | 494600 | 0 | 494600 | 373120 | 75.44% | 121480 | 0 | 121480 | 64298 | 0 | 48505.6 | 15792.4 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BDI | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 70000 | 82.35% | 15000 | 0 | 15000 | 11050 | 0 | 9100 | 1950 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BHU | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2010-12-01 |  | 30000 | 0 | 30000 | 23470 | 78.23% | 6530 | 0 | 6530 | 3900 | 0 | 3051.1 | 848.9 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | ASP | BHU | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-12-01 |  | 55000 | 0 | 55000 | 43686 | 79.43% | 11314 | 0 | 11314 | 7150 | 0 | 5679.18 | 1470.82 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BZE | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 80774 | 95.03% | 4226 | 0 | 4226 | 11050 | 0 | 10500.62 | 549.38 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CBI | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 65448 | 77% | 19552 | 0 | 19552 | 11050 | 0 | 8508.24 | 2541.76 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CHD | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2012-12-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project completed in December 2012. The country conducted training of refrigeration technicians and 50 custom officers. |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | DMI | PHA | 57 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 47247 | 55.58% | 37753 | 14793 | 37753 | 11050 | 0 | 6142.11 | 4907.89 | 1923.09 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ECU | PHA | 59 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 |  | 75000 | 0 | 75000 | 69706 | 92.94% | 5294 | 2358 | 5294 | 9750 | 0 | 9061.78 | 688.22 | 306.54 | Project completed. Audited Financial reports received. UNEP released outstanding disbursements to the University that drafted the HPMP | Project completed |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | EQG | PHA | 56 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 74472 | 87.61% | 10528 | 0 | 10528 | 11050 | 0 | 9681.36 | 1368.64 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GAB | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-01-01 |  | 85000 | 0 | 85000 | 80053 | 94.18% | 4947 | 0 | 4947 | 11050 | 0 | 10406.89 | 643.11 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUY | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 67782 | 79.74% | 17218 | 0 | 17218 | 11050 | 0 | 8811.66 | 2238.34 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HON | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2011-12-01 |  | 35000 | 0 | 35000 | 17500 | 50% | 17500 | 0 | 17500 | 4550 | 0 | 2275 | 2275 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | IRQ | PHA | 60 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2011-12-01 |  | 100000 | 0 | 100000 | 74329 | 74.33% | 25671 | 0 | 25671 | 13000 | 0 | 9662.77 | 3337.23 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | IVC | PHA | 57 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2012-02-01 |  | 85000 | 0 | 85000 | 64985 | 76.45% | 20015 | 0 | 20015 | 11050 | 0 | 8448.05 | 2601.95 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KAM | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-07-01 |  | 125000 | 0 | 125000 | 104958 | 83.97% | 20042 | 0 | 20042 | 16250 | 0 | 13644.54 | 2605.46 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KUW | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-12-01 |  | 125000 | 0 | 125000 | 98731 | 78.98% | 26269 | 0 | 26269 | 16250 | 0 | 12835.03 | 3414.97 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | LAO | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-01-01 |  | 150000 | 0 | 150000 | 110454 | 73.64% | 39546 | 0 | 39546 | 19500 | 0 | 14359.02 | 5140.98 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MDV | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 |  | 85000 | 0 | 85000 | 65094 | 76.58% | 19906 | 0 | 19906 | 11050 | 0 | 8462.22 | 2587.78 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MON | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-03-01 |  | 85000 | 0 | 85000 | 67295 | 79.17% | 17705 | 0 | 17705 | 11050 | 0 | 8748.35 | 2301.65 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | MOZ | PHA | 58 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-12-01 |  | 55000 | 0 | 55000 | 39013 | 70.93% | 15987 | 0 | 15987 | 7150 | 0 | 5071.69 | 2078.31 | 0 | Project completed. HPMP project approved at ExCom 66 | project was completed |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MYA | PHA | 57 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-12-01 |  | 42500 | 0 | 42500 | 40539 | 95.39% | 1961 | 0 | 1961 | 5525 | 0 | 5270.07 | 254.93 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | NEP | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-01-01 |  | 85000 | 0 | 85000 | 66029 | 77.68% | 18971 | 0 | 18971 | 11050 | 0 | 8583.77 | 2466.23 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | OMA | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-06-01 | 2009-07-01 |  | 2011-12-01 |  | 50000 | 0 | 50000 | 39000 | 78% | 11000 | 0 | 11000 | 6500 | 0 | 5070 | 1430 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | PAK | PHA | 55 | PRP | 69 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 |  | 60000 | 0 | 60000 | 57550 | 95.92% | 2450 | 0 | 2450 | 7800 | 0 | 7481.5 | 318.5 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | PAR | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-04-01 |  | 85000 | 0 | 85000 | 78211 | 92.01% | 6789 | 0 | 6789 | 11050 | 0 | 10167.43 | 882.57 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | QAT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-01-01 | 2009-07-01 |  | 2011-08-01 |  | 30000 | 0 | 30000 | 29000 | 96.67% | 1000 | 0 | 1000 | 3900 | 0 | 3770 | 130 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | RWA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-07-01 |  | 85000 | 0 | 85000 | 65000 | 76.47% | 20000 | 0 | 20000 | 11050 | 0 | 8450 | 2600 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SRL | PHA | 55 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2010-12-01 |  | 25000 | 0 | 25000 | 19588 | 78.35% | 5412 | 0 | 5412 | 3250 | 0 | 2546.44 | 703.56 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STL | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-02-01 | 2009-07-01 |  | 2012-12-01 |  | 85000 | 0 | 85000 | 82468 | 97.02% | 2532 | 16 | 2532 | 11050 | 0 | 10720.84 | 329.16 | 2.08 | According to UNEP rules, project balance was re-obligated to proceed with outstanding disbursements, once audited financial reports received by UNEP. | Audited Financial reports are being prepared and reconciled by NOU in order for UNEP to release outstanding disbursements. |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | STP | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-03-01 |  | 85000 | 0 | 85000 | 70000 | 82.35% | 15000 | 15000 | 15000 | 11050 | 0 | 9100 | 1950 | 1950 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | SUR | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-07-01 |  | 85000 | 0 | 85000 | 58000 | 68.24% | 27000 | 27000 | 27000 | 11050 | 0 | 7540 | 3510 | 3510 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SWA | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-11-01 |  | 2011-07-01 |  | 85000 | 0 | 85000 | 65000 | 76.47% | 20000 | 0 | 20000 | 11050 | 0 | 8450 | 2600 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | ASP | TLS | PHA | 61 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-06-01 | 2010-11-01 |  | 2011-12-01 |  | 55000 | 0 | 55000 | 53255 | 96.83% | 1745 | 0 | 1745 | 7150 | 0 | 6923.15 | 226.85 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | TOG | PHA | 56 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 |  | 85000 | 0 | 85000 | 70692 | 83.17% | 14308 | 0 | 14308 | 11050 | 0 | 9189.96 | 1860.04 | 0 | Project completed |  |  |  | Non Investment
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 64 | PRP | 165 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-02-01 | 2012-07-01 |  | 2012-04-01 |  | 43657 | 0 | 43657 | 42898.47 | 98.26% | 758.53 | 27.56 | 500 | 3274 | 0 | 3217 | 57 | 2 | Project completed in Apr 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | BHE | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2012-04-01 |  | 150000 | 0 | 150000 | 140898 | 93.93% | 9102 | 8600 | 9000 | 11250 | 0 | 10567 | 683 | 645 | Project completed in Apr 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 55 | PRP | 51 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-12-01 |  | 50000 | 0 | 50000 | 47974.03 | 95.95% | 2025.97 | 1059.01 | 2000 | 3750 | 0 | 3598 | 152 | 79 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ECU | PHA | 59 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-03-01 | 2010-11-30 |  | 2012-03-01 |  | 75000 | 0 | 75000 | 74999.87 | 100% | 0.13 | 0 | 0.13 | 5625 | 0 | 5625 | 0 | 0 | Project completed in Mar 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | GUA | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-07-01 | 2010-03-31 |  | 2012-03-01 |  | 75000 | 0 | 75000 | 73630.11 | 98.17% | 1369.89 | 1150 | 1000 | 5625 | 0 | 5522 | 103 | 86.25 | Project completed in Mar 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | IRQ | PHA | 59 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 |  | 65000 | 0 | 65000 | 50052.88 | 77% | 14947.12 | 14829.51 | 14000 | 4875 | 0 | 3754 | 1121 | 1112 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | MOR | PHA | 55 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 |  | 150000 | 0 | 150000 | 143123.4 | 95.42% | 6876.6 | 6370.65 | 6000 | 11250 | 0 | 10734 | 516 | 478 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | MYA | PHA | 57 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2012-12-01 |  | 42500 | 0 | 42500 | 30659.15 | 72.14% | 11840.85 | 11733.42 | 1000 | 3188 | 0 | 2299 | 889 | 880.0065 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | NER | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-07-01 |  | 85000 | 0 | 85000 | 77311.52 | 90.95% | 7688.48 | 670.26 | 7000 | 6375 | 0 | 5798 | 577 | 50 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SAU | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-03-01 | 2009-07-31 |  | 2012-12-01 |  | 130000 | 0 | 130000 | 80275.6 | 61.75% | 49724.4 | 49700 | 10000 | 9750 | 0 | 6021 | 3729 | 3728 | HPMP approved at the 68th Excom, project transferred with the HPMP. Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOA | PHA | 55 | PRP | 01 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-06-01 | 2009-07-31 |  | 2012-12-01 |  | 195000 | 0 | 195000 | 141509.33 | 72.57% | 53490.67 | 53154.41 | 50000 | 14625 | 0 | 10613 | 4012 | 3987 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOM | PHA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2012-12-01 |  | 85000 | 0 | 85000 | 67911.46 | 79.9% | 17088.54 | 16039.04 | 17000 | 6375 | 0 | 5093 | 1282 | 1203 | Project completed in Dec 2012.
COM | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | SUD | PHA | 59 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 |  | 120000 | 0 | 120000 | 113177.76 | 94.31% | 6822.24 | 6688.1 | 6000 | 9000 | 0 | 8488 | 512 | 502 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TUR | PHA | 55 | PRP | 91 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2012-12-01 |  | 195000 | 0 | 195000 | 168810.93 | 86.57% | 26189.07 | 25902.97 | 26000 | 14625 | 0 | 12661 | 1964 | 1943 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | YEM | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2012-12-01 |  | 70000 | 0 | 70000 | 67229.34 | 96.04% | 2770.66 | 2599.7 | 2600 | 5250 | 0 | 5042 | 208 | 195 | HPMP approved at the 68th Excom, project transferred with the HPMP. Project completed in Dec 2012. |  |  |  | NON-INV
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BOL | PHA | 55 | PRP | 31 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | HPMP approved at 64th meeting
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BRA | PHA | 55 | PRP | 282 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-04-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP was approved based on a preperatory study
FIN | Germany | Preparation of a HCFC phase-out management plan (extruded polystyrene foam sector) | Individual | LAC | BRA | PHA | 57 | PRP | 286 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  | 0 | 5460 | 0 | 5460 | 0 | 0 | HPMP was approved based on a preperatory study
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 469 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 201369 | 0 | 201369 | 201369 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam (additional funding) | Individual | ASP | CPR | PHA | 57 | PRP | 482 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 201370 | 0 | 201370 | 201370 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 426 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP has been drafted and submitted to the NOU.
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 190 | A | I | HCFC | 0 |  | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | HPMP was approved based on preparatory study
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | LES | PHA | 57 | PRP | 12 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-06-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP was prepared and submitted and approved at the 64th Excom. The document was developed following the completion of a detailed survey and stakeholder workshop.
FIN | Germany | Preparation of a HCFC phase-out management plan |  | AFR | LIR | PHA | 57 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP was submitted as planned in Dec 2010.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | MAR | PHA | 55 | PRP | 20 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | HPMP submitted as planned in Dec 2010
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | NAM | PHA | 55 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP submitted as planned in Dec 2010
FIN | Germany | Preparation of a HCFC phase-out management plan (additional funding) |  | AFR | NAM | PHA | 57 | PRP | 15 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | HPMP submitted as planned in Dec 2010
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | PNG | PHA | 57 | PRP | 10 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP completed and approved
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | SEY | PHA | 58 | PRP | 15 | A | I | HCFC | 0 | 0 | 0 |  | 2009-07-01 | 2009-09-01 | 2010-07-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP dafted and approved.
FIN | IBRD | Preparation of a HCFC phase-out management plan: polyurethane foam sector |  | ASP | CPR | PHA | 55 | PRP | 468 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2011-07-01 | 2012-12-01 | 685900 | 0 | 685900 | 685900 | 100% | 0 | 0 | 0 | 51443 | 0 | 51443 | 0 | 0 | Last disbursement made in Dec. 2012. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out management plan (foam sector) |  | ASP | IDS | PHA | 57 | PRP | 186 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-12-31 |  | 2011-07-01 | 2011-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HPMP foam sector plan prepared and approved at the 64th ExCom Meeting. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | PHI | PHA | 55 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | HPMP resubmitted and approved at the 68th ExCom with UNEP as the lead IA. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | THA | PHA | 55 | PRP | 151 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | HPMP approved at the 68th ExCom Meeting. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | VIE | PHA | 55 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2011-03-01 | 2011-06-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Fully completed and disbursed. Project approved at the 63rd Meeting. |  |  |  | Non-INV
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | ARM | PHA | 55 | PRP | 03 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -1548.67 | 83451.33 | 83451.33 | 100% | 0 | 0 | 0 | 6375 | -116.15 | 6258.85 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | BRA | PHA | 55 | PRP | 283 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-06-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 | 0 | 10781 | 0 | 10781 | 0 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COL | PHA | 55 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 173750 | -6849.95 | 166900.05 | 166900.05 | 100% | 0 | 0 | 0 | 13031 | -513.74 | 12517.26 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GHA | PHA | 55 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-07-01 | 2011-02-01 | 85000 | -2468.29 | 82531.71 | 82531.71 | 100% | 0 | 0 | 0 | 6375 | -185.12 | 6189.88 | 0 | 0 | Completed. HPMP submitted and approved at 61st meeting. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | IDS | PHA | 55 | PRP | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031 | 0 | 13031 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-07-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | JAM | PHA | 55 | PRP | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-08-01 | 85000 | 0 | 85000 | 56965.03 | 67.02% | 28034.97 | 0 | 0 | 6375 | 0 | 4272.3772 | 2102.6227 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KAM | PHA | 55 | PRP | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2010-12-01 | 2012-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KYR | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -739.48 | 84260.52 | 84260.52 | 100% | 0 | 0 | 0 | 6375 | -55.46 | 6319.54 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 140 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2009-11-01 | 2012-06-01 | 69500 | -6719.29 | 62780.71 | 62780.71 | 100% | 0 | 0 | 0 | 5212.5 | -503.45 | 4709.05 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | MOL | PHA | 55 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-07-01 | 85000 | -3117.49 | 81882.51 | 81882.51 | 100% | 0 | 0 | 0 | 6375 | -233.81 | 6141.19 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 121 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | NIR | PHA | 55 | PRP | 119 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | AFG | PHA | 55 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BEN | PHA | 57 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BGD | PHA | 56 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BKF | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed in December 2010. HCFC Survey finalized in March 2010 and HPMP submitted to UNEP in June 2010 |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | AFR | BKF | PHA | 56 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project completed in December 2010. HCFC Survey finalized in March 2010 and HPMP submitted to UNEP in June 2010 |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BRU | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-06-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP document has been developed and submitted to the 66th ExCom meeting for consideration. |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CAF | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | COI | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-11-01 | 2012-11-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan: enabling components | RMP | ASP | CPR | PHA | 55 | PRP | 472 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan: refrigeration servicing sub-sector | RMP | ASP | CPR | PHA | 55 | PRP | 465 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DRC | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-03-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GUI | PHA | 56 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IND | PHA | 56 | PRP | 429 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IRA | PHA | 56 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-01-01 | 2012-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAG | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-01-01 | 2011-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLW | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-03-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project completed in July 2010. Country submit TPMP completion and expenditure reports in January 2010. |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MOZ | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | PRC | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SIL | PHA | 56 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of HCFC phase-out management plan | RMP | ASP | TLS | PHA | 59 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | MDN | PHA | 60 | INV | 29 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2015-12-31 |  | 2011-03-01 | 2012-05-01 | 15000 | 0 | 15000 | 14999.98 | 100% | 0.02 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Financial completion in May 2012.
FIN | UNIDO | HCFC phase-out management plan (advance funding for the institutional strengthening) | Multi-Year | EUR | MDN | PHA | 63 | INV | 30 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-06-01 | 2012-03-31 |  | 2011-12-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000.01 | 100% | -0.01 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Financial completion in May 2012. |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | ALB | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 30000 | -74 | 29926 | 29926.15 | 100% | -0.15 | 0 |  | 2250 | -6 | 2244 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | EUR | ALB | PHA | 57 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2011-06-01 | 2012-10-01 | 55000 | -897 | 54103 | 54102.72 | 100% | 0.28 | 0 |  | 4125 | -67 | 4058 | 0 | 0 | Financial completion in Oct 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | ALG | PHA | 58 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2012-12-01 | 2012-12-01 | 65000 | 0 | 65000 | 64978.26 | 99.97% | 21.74 | 0 | 1 | 4875 | 0 | 4873 | 2 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | ALG | PHA | 55 | PRP | 68 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 85000 | -255 | 84745 | 84744.79 | 100% | 0.21 | 0 |  | 6375 | -19 | 6356 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | BAH | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 45000 | 0 | 45000 | 44708.92 | 99.35% | 291.08 | 0 | 1 | 3375 | 0 | 3353 | 22 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | CMR | PHA | 58 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 65000 | -364 | 64636 | 64636.28 | 100% | -0.28 | 0 |  | 4875 | -27 | 4848 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | CMR | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 81920.91 | 96.38% | 3079.09 | 0 | 1 | 6375 | 0 | 6144 | 231 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (XPS foam sector) | Individual | ASP | CPR | PHA | 55 | PRP | 466 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-10-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 84000 | 0 | 84000 | 84000.02 | 100% | -0.02 | 0 |  | 6300 | 0 | 6300 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (Room air-conditioning sector) | Individual | ASP | CPR | PHA | 55 | PRP | 470 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 500000 | -2 | 499998 | 499997.65 | 100% | 0.35 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | CRO | PHA | 55 | PRP | 31 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 150000 | -456 | 149544 | 149543.63 | 100% | 0.37 | 0 |  | 11250 | -34 | 11216 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | EGY | PHA | 55 | PRP | 96 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-08-01 | 2012-12-01 | 195000 | 0 | 195000 | 194166.18 | 99.57% | 833.82 | 0 | 1 | 14625 | 0 | 14562 | 63 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | HON | PHA | 55 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 115000 | -82 | 114918 | 114917.64 | 100% | 0.36 | 0 |  | 8625 | -6 | 8619 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (transportation refrigeration and air-conditioning sectors) | Individual | ASP | IND | PHA | 56 | PRP | 427 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-05-01 | 2011-05-01 | 70000 | -170 | 69830 | 69829.97 | 100% | 0.03 | 0 |  | 5250 | -13 | 5237 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | IRQ | PHA | 55 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 27090.88 | 90.3% | 2909.12 | 0 | 1 | 2250 | 0 | 2032 | 218 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | JOR | PHA | 55 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 | 2012-05-01 | 150000 | -975 | 149025 | 149025.08 | 100% | -0.08 | 0 |  | 11250 | -73 | 11177 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | KUW | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 70000 | 0 | 70000 | 69242.53 | 98.92% | 757.47 | 0 | 1 | 5250 | 0 | 5193 | 57 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MDN | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-04-01 | 2010-12-01 | 85000 | -634 | 84366 | 84366.02 | 100% | -0.02 | 0 |  | 6375 | -48 | 6327 | 0 | 0 | Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-10-01 | 104250 | -291 | 103959 | 103959 | 100% | 0 | 0 |  | 7819 | -22 | 7797 | 0 | 0 | Financial completion in Oct 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MOG | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2009-12-01 | 2012-02-01 | 85000 | -767 | 84233 | 84233.23 | 100% | -0.23 | 0 |  | 6375 | -58 | 6317 | 0 | 0 | Financial completion in Feb 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | NIC | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 85000 | -130 | 84870 | 84869.65 | 100% | 0.35 | 0 |  | 6375 | -10 | 6365 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 120 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 20000 | -4 | 19996 | 19996.09 | 100% | -0.09 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | OMA | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 99708.42 | 99.71% | 291.58 | 0 | 1 | 7500 | 0 | 7478 | 22 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | PAK | PHA | 59 | PRP | 76 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2010-12-01 | 2012-06-01 | 45000 | -831 | 44169 | 44169.11 | 100% | -0.11 | 0 |  | 3375 | -62 | 3313 | 0 | 0 | Financial completion in Jun 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | PAK | PHA | 55 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 90000 | -5024 | 84976 | 84976.18 | 100% | -0.18 | 0 |  | 6750 | -377 | 6373 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | QAT | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 55000 | 0 | 55000 | 53955.29 | 98.1% | 1044.71 | 0 | 1 | 4125 | 0 | 4047 | 78 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SEN | PHA | 55 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-05-01 | 85000 | -1026 | 83974 | 83973.9 | 100% | 0.1 | 0 |  | 6375 | -77 | 6298 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SUD | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 30000 | -2950 | 27050 | 27050.21 | 100% | -0.21 | 0 |  | 2250 | -221 | 2029 | 0 | 0 | Financial completion in Oct 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TKM | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-02-01 | 85000 | -909 | 84091 | 84090.6 | 100% | 0.4 | 0 |  | 6375 | -68 | 6307 | 0 | 0 | Financial completion in Feb 2012. Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | VEN | PHA | 55 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 173750 | 0 | 173750 | 173031.53 | 99.59% | 718.47 | 0 | 1 | 13031 | 0 | 12977 | 54 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | YUG | PHA | 55 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-12-01 | 150000 | 0 | 150000 | 149044.87 | 99.36% | 955.13 | 0 | 1 | 11250 | 0 | 11178 | 72 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
ONG | Australia | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) |  | ASP | IDS | PHA | 64 | TAS | 196 | A | I |  | 3.7 |  | 0 |  | 2011-07-01 |  | 2014-12-01 | 2016-12-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 0 | 50000 | 39000 | 0 | 39000 | 0 | 0 | Ongoing | Agreement with UNDP the executing agency signed in December 2012 | 2011
ONG | France | HCFC phase-out management plan (stage I, first tranche) |  | AFR | KEN | PHA | 66 | INV | 53 | A | I | HCFC | 3.1 |  | 0 |  | 2012-04-01 |  | 2014-04-01 | 2012-04-01 |  |  | 257500 | 0 | 257500 | 0 | 0% | 257500 |  | 226450 | 31186 | 0 |  | 31186 |  | The French contribution is to be implemented by GIZ Proklima.
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | AFG | PHA | 63 | INV | 13 | A | I | HCFC | 0 | 0 | 0 |  | 2011-04-01 | 2011-10-01 | 2012-03-01 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 4500 | 5.294% | 80500 | 0 | 80500 | 11050 | 0 | 585 | 10465 | 0 | Project Delay - Accessability of project site - HCFC survey completed - Local institutions identified - All technical input completed - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Experts recruited
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BOL | PHA | 64 | INV | 36 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-10-01 | 2015-07-01 | 2013-12-01 |  |  | 94500 | 0 | 94500 | 12614 | 13.35% | 81886 | 0 | 81886 | 12285 | 0 | 1640 | 10645 | 0 | Project Delay - Change of NOU - HCFC survey completed - Stakeholders workshop held - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Local institutions identified
ONG | Germany | HCFC phase-out management plan (refrigeration servicing sector) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 296 | A | I | HCFC | 14.8 | 2 | 0 |  | 2011-07-01 | 2011-10-01 | 2012-07-01 | 2013-12-01 |  |  | 1209091 | 0 | 1209091 | 264651 | 21.89% | 944440 | 25995 | 944440 | 153000 | 0 | 34405 | 118595 | 3379 | Project Delay - Signing of agreement - HCFC survey completed - Stakeholders workshop held - Local institutions identified - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Experts recruited
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 68 | INV | 299 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 2472727 | 0 | 2472727 | 0 | 0% | 2472727 | 0 | 780000 | 262000 | 0 | 0 | 262000 | 0 |  | Agreement negotiated - Start of activities - Operational Plan finalised -
ONG | Germany | HCFC phase-out management plan (extruded polystyrene foam sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 518 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-07-01 | 2012-07-01 | 2013-11-01 |  |  | 459023 | 0 | 459023 | 385346 | 83.95% | 73677 | 73677 | 73677 | 51260 | 0 | 50095 | 1165 | 1165 | HCFC survey completed - Stakeholders workshop held - Local institutions identified - Experts recruited - Draft document completed - Documents signed - TOR completed - All funds disbursed - | All technical input completed
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 66 | INV | 442 | A | I | HCFC | 0 |  | 0 |  | 2012-04-01 | 2012-05-01 | 2013-04-01 | 2013-12-01 |  |  | 925452 | 0 | 925452 | 505435 | 54.61% | 420017 |  | 420017 | 106440 | 0 | 58132 | 48308 |  | Stakeholder Workshop in May 2012, Development of training material, Training of Trainer programs in Dec 2012, Procurement of equipment for training partners, Regional Management Organisation contracted | Contracts with 15 training partners in progress, equipment has been procured and will be delivered to all training partners in May 2013, training material will be finalised in May/June 2013. There has been a delay of 3-4 month due to internal contract award procedures, therefore the number of training programs will be increased in the next training season.
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 205 | A | I | HCFC | 1.2 | 0 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 | 2013-12-01 |  |  | 100600 | 0 | 100600 | 20347 | 20.23% | 80253 | 25273 | 80253 | 11415 | 0 | 2645 | 8770 | 3285 | Agreement negotiated - Start of activities - Operational Plan finalised | Experts recruited
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 201 | A | I | HCFC | 20.1 | 3 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 | 2013-12-01 |  |  | 1962400 | 0 | 1962400 | 146215 | 7.451% | 1816185 | 1447932 | 1816185 | 222664 | 0 | 19008 | 203656 | 188231 | Project Delay - Procurement was delayed by bidders - HCFC survey completed - Stakeholders workshop held - Local institutions identified - Experts recruited - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | All technical input completed
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 68 | INV | 207 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 534233 | 0 | 534233 | 0 | 0% | 534233 |  | 267117 | 60617 | 0 | 0 | 60617 |  |  | Agreement negotiated - Start of activities - Operational Plan finalised
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LES | PHA | 64 | INV | 14 | A | I | HCFC | 0 | 0.6 | 0 |  | 2011-07-01 | 2011-08-01 | 2014-07-01 | 2014-07-01 |  |  | 100000 | 0 | 100000 | 43248 | 43.25% | 56752 |  | 40000 | 13000 | 0 | 5622 | 7378 |  | Refrigerant identifiers suitable for blends have been supplied. A customs trainer from Namibia conducted a train the trainers course. This was followed by 3 additional courses covering 7 border posts of the country. | Additional training equipment has been ordered for the VTCs. Discussions ongoing on how to undertake certification of the technicians in order to monitor their practices in the industry.
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LIR | PHA | 63 | INV | 18 | A | I | HCFC | 0.6 | 0.09 | 0 |  | 2011-04-01 | 2011-06-01 | 2015-03-01 | 2015-03-01 |  |  | 157500 | 0 | 157500 | 63874 | 40.55% | 93626 |  | 30000 | 20475 | 0 | 8304 | 12171 |  | 3 technician training courses have been conducted. 2 customs trainings have been completed. Awareness strategy has been developed targetting various media forms. | 1 customs training completed. Awareness material being printed, training equipment requested is being purchased
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 63 | INV | 21 | A | I | HCFC | 0 |  | 0 |  | 2011-04-01 | 2011-10-01 | 2014-03-01 | 2014-03-01 |  |  | 157050 | 0 | 157050 | 76917 | 48.98% | 80133 |  | 70000 | 18846 | 0 | 9230 | 9616 |  | Mauritius requested training in non HFC alternatives. An extensive NH3 training was conducted. HC based AC split units and 20 appropriate tool kits have been supplied. Also identifiers specially designed for blends have been provided. | Plans for a regional training on HC based split units is being designed and specifications for a demonstration unit for CO2 for supermarkets have been developed.
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | NAM | PHA | 63 | INV | 17 | A | I | HCFC | 0.9 |  | 0 |  | 2011-04-01 | 2011-06-01 | 2014-03-01 | 2014-03-01 |  |  | 300000 | 0 | 300000 | 95037 | 31.68% | 204963 |  | 100000 | 36333 | 0 | 11510 | 24823 |  | The planned ban on HCFC equipment to start from 1st Jan 2012 could not be enforced until August 2012 following another high level stakeholder workshop in the country primarily to encourage acceptance of controls. A widespread awareness campaign was conducted through the local media to ensure all importers were aware of the ban and controls. Identifiers suitable for idenitifying blends were purchased. 4 Technician trainings in various towns on best practices were conducted. Necessary equipment for 1 of the local training centres was provided and 3 customs training conducted to train officers on the use of these idenitfiers. HC based split units have been purchased as well as related tool kits. | Ongoing customs training and a regional HC based AC training course is being planned for June/July
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | PNG | PHA | 63 | INV | 11 | A | I | HCFC | 0.2 |  | 0 |  | 2011-04-01 | 2011-07-01 | 2014-03-01 | 2014-03-01 |  |  | 350000 | 0 | 350000 | 61016 | 17.43% | 288984 |  | 120000 | 41300 | 0 | 7200 | 34100 |  | Implementation has been slow because there was no appointed NOU in 2012 . Also there were elections which were disputed and until a new government was in place, many months passed. PMU tried to keep the project activites moving forward within his abilities including representing PNG at the PIC network meeting. With the new govt. in place, the ratification of the Beijing amendment could be discussed and brought to the cabinet. Identifiers for use with blends were deliverd and 3 customs trainings conducted. Industry request for revisiting HC trainings has required the purchase of HC relevant training equipment/tools to be supplied to the insitutions. In order to enourge industry participation, stakeholder dialogues have been organised. | Finally a new assistant NOU has been hired who is being trained to become the NOU. Ratification still needs to be finalised, 1 additional customs training has been conducted, training using international expert for hydrocarbons is currently being planned
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 63 | INV | 17 | A | I | HCFC | 0.4 | 0.37 | 0 |  | 2011-04-01 | 2011-06-01 | 2013-03-01 | 2013-12-01 |  |  | 200000 | 0 | 200000 | 88043 | 44.02% | 111957 |  | 111957 | 25333 | 0 | 11152 | 14181 |  | Seychelles has conducted 2 trainings of technicians on conversions of AC units to HCs. Training equipment requested by the trainings centres to work with HCs has been provided along with the necessary tool kits for technicians to work with HCs R600a and R290. 6 AC split units running on HCs have also been provided for training purposes. Discussions have been long on the solar AC demonstration at a local building. Various technical proposals have been provided and discussed but restricted funding availability has led to so far no clear decision on the most suitable system that can be demonstrated. | Enforcement of controls through monitoring and follow up by NOU. Discussions still ongoing on suitable solar AC option as demonstration. Further trainings and conversions of R22 systems planned.
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing sector:Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 44 | A | I | HCFC | 6.1 |  | 0 |  | 2011-11-01 | 2011-12-01 | 2013-11-01 | 2013-11-01 |  |  | 3737 | 311173 | 314910 | 3454 | 1.097% | 311456 | 0 | 311456 | 486 | 37213 | 413 | 37286 | 0 | technical specifications for equipment purchase has been completed. Delay was caused by prolonged discussions regarding companies commitment towards the phase out in terms of part cost sharing. | Tender has been awarded and delivery expected in May 2013
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 45 | A | I | HCFC | 0 | 3.6 | 0 |  | 2011-11-01 | 2012-01-01 | 2013-11-01 | 2013-11-01 |  |  | 3737 | 108244 | 111981 | 46000 | 41.08% | 65981 | 0 | 65981 | 486 | 12945 | 5517 | 7914 | 0 | stakeholder workshop held following approval of the HPMP to create awareness about HCFC phase out. Customs training handbook was amended to reflect the new HCFC inclusions. Identifier for blends provided and re-fresher customs trainings conducted in 7 towns on provisions for HCFCs. 2 Technician trainings have been completed. | Monitoring of controls and site training at border posts have been completed. Equipment for 8 VTCs ordered.
ONG | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | BOT | PHA | 60 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 | 2013-08-01 |  |  | 150000 | 0 | 150000 | 148206 | 98.8% | 1794 | 0 | 1794 | 19500 | 0 | 19267 | 233 | 0 | The HPMP document was submitted for the 65th Excom. However Botswana could not confirm on an established licensing system for ODS imports which is a pre-condition for any HPMP approval. This has prevented the approval of the HPMP for Botswana until now and it is still unclear when Botswana will have a licensing system in place and enforced. Repeated efforts have been made to encourage the government to approve the establishing of a licensing system but it has still not been approved by the government. | Unfortunately communication with the NOU has been very poor. There is no designated officer currently assigned as the NOU. Various mails are sent to persons who have been involved with Ozone issues but no real progress can be reported despite writing to Minister, Permanent Secretary etc.
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the production of polyurethane rigid insulation foam for domestic refrigerators at Mabe) | Multiyear | LAC | ARG | PHA | 66 | INV | 171 | N | I | HCFC | 18.46 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-30 | 2014-11-01 |  |  | 838612 | 0 | 838612 | 0 | 0% | 838612 | 838612 | 80000 | 62896 | 0 | 0 | 62896 | 62896 | The Mabe reconversion project is the first component of a new ozone operation under preparation between the Government of Argentina and the WB which includes the broad framework of the future foam sector plan that will be prepared for inclusion in the country's Stage II HPMP. Given varying subproject components preparation and approval schedules, this process has suffered some delays. A project mission took place in Dec. 2012. | Overall project appraisal document to which the MABE sub-project is tied is nearing completion and project appraisal mission is scheduled for week of Apr. 22, 2013. MABE subproject is slated to be under implementation by Nov. 2013; or as soon as the grant agreement becomes effective. Following effectiveness, the project is expected to be completed within 12 months. In line with the compliance requirements laid out in the Argentina HPMP, the project is plannned to close by the end of 2014. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (monitoring and reporting of HCFC-22 production) | Multiyear | LAC | ARG | PHA | 66 | TAS | 170 | N | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-30 | 2015-12-01 |  |  | 76000 | 0 | 76000 | 0 | 0% | 76000 | 76000 | 8000 | 5700 | 0 | 0 | 5700 | 5700 | Technical assistance (TA) component is part of the new ozone operation that the Bank is currently preparing with the Government of Argentina and which includes the MABE sub-project and the broad framework of the future foam sector plan that will be prepared for inclusion in the country's Stage II HPMP. Given varying component preparation and approval schedules, this process has suffered some delays. A project mission took place in Dec. 2012. | Overall project appraisal document is nearing completion. Project appraisal mission is scheduled for the week of Apr. 22, 2013 and the monitoring and reporting of HCFC-22 production is slated to be under implementation by Nov. 2013. |  |  | Non-INV
ONG | IBRD | HCFC phase-out management plan (polyurethane rigid foam sector plan) (stage I, first tranche) | Multiyear | ASP | CPR | PHA | 64 | INV | 508 | N | I |  | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2012-07-31 | 2013-12-01 |  |  | 38859000 | 0 | 38859000 | 0 | 0% | 38859000 | 38859000 | 19000000 | 2914000 | 0 | 0 | 2914000 | 2914000 | Appraisal mission to assess readiness of WB project documents (PIM, disbursement and procurement arrangements, subproject implementation arrangements, etc.) done in Feb. 12. Grant Agreement signed Nov. 2012. Pipeline of 32 enterprises identified as project beneficiaries to undertake conversion to either HC or water blown technology. This will result in a combined reduction of 8,869 metric tons based on 2011 data -representing 60% of the overall reduction target. | Two contracts signed during Q1 2013. An additional 12 contracts will be signed in Apr. 2013. First disbursement of $19 million expected in early Apr. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 68 | INV | 526 | N | I | HCFC | 103.8 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-31 | 2013-12-31 |  |  | 5520000 | 0 | 5520000 | 0 | 0% | 5520000 | 5520000 | 2000000 | 386400 | 0 | 0 | 386400 | 386400 | Second funding tranche newly approved at end of Dec. 2012. No disbursement made in 2012. | Additional beneficiaries are being identified in 2013. At least additional 15 contracts will be signed during the calendar year. ODP tons to be captured by new contracts will be provided once verification process is completed. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multiyear | ASP | IDS | PHA | 64 | INV | 191 | A | I | HCFC | 18.9 | 0 | 0 | 0 | 2011-07-01 |  | 2013-03-31 | 2013-12-01 |  |  | 1500000 | 0 | 1500000 | 0 | 0% | 1500000 | 1500000 | 250000 | 112500 | 0 | 0 | 112500 | 112500 | Initial WB preparation mission held in Mar.12. WB internal concept review for a new grant agreement occurred in June 2012. | Appraisal was in Apr. 2013 and WB approval of the new grant agreement is slated for May 2013, at which time disbursement can start. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (air-conditioning sector plan) | Multiyear | ASP | JOR | PHA | 65 | INV | 91 | N | I | HCFC | 7.8 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-30 | 2013-11-30 |  |  | 1070100 | 0 | 1070100 | 0 | 0% | 1070100 | 1070100 | 265000 | 80258 | 0 | 0 | 80258 | 80258 | Two WB preparation missions for a new ODS Project/Grant Agreement held Mar & Oct 12. Project implementation manual for overall new ODS project completed which includes proforma appraisal/subproject templates,subgrant agreements, and TORs for the PMU and other technical support in the AC sector. | Legislation updates and HCFC quota issued by Jan. 13. Gov. of Jordan-WB negotiations on the new GA completed Mar 13. WB approval of the new GA expected by Apr. 2013 and effectiveness to follow immediately thereafter. Subproject implementation to begin in Q2 2013. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | THA | PHA | 68 | INV | 161 | N | I | HCFC | 33.4 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2014-06-01 |  |  | 2343653 | 0 | 2343653 | 0 | 0% | 2343653 | 2343653 | 200000 | 164055 | 0 | 0 | 164055 | 164055 | First tranche approved in Dec. 2012. A preparation mission (for a new Thailand-WB grant agreement) was launched immediately after the ExCom approval of the HPMP. | 2013 HCFC import quota was established in Jan. 2013. Thailand initiated preparation of environmental safeguard plans to ensure safe introduction of flammable materials in both foam and a/c sectors. First inter-departmental meeting was held to discuss the need to amend regulations and standards pertaining to use of mildly flammable materials as refrigerants. Consultations with Council of Engineers to promote the use of non-HCFC-22 a/c held. GoT is encouraging a/c enterprises not eligible for funding from the MLF to also adopt lower-GWP alternatives. Several multinational companies have started preparation to offer a similar product in Thailand and for export markets. WB project appraisal expected Jun 13, followed by negotiations in Oct. Grant Agreement expected to be approved by the WB in Dec. 2013. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning group project) | Multiyear | ASP | THA | PHA | 68 | INV | 162 | N | I | HCFC | 11.4 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2014-06-01 |  |  | 2089100 | 0 | 2089100 | 0 | 0% | 2089100 | 2089100 | 0 | 146237 | 0 | 0 | 146237 | 146237 | First tranche approved in Dec. 2012. A preparation mission (for a new Thailand-WB grant agreement) was launched immediately after the ExCom approval of the HPMP. | 2013 HCFC import quota was established in Jan. 2013. Thailand initiated preparation of environmental safeguard plans to ensure safe introduction of flammable materials in both foam and a/c sectors. First inter-departmental meeting was held to discuss the need to amend regulations and standards pertaining to use of mildly flammable materials as refrigerants. Consulatations with Council of Engineers to promote the use of non-HCFC-22 a/c held. GoT is encouraging a/c enterprises not eligible for funding from the MLF to also adopt lower-GWP alternatives. Several multinational companies have started preparation to offer a similar product in Thailand and for export markets. WB project appraisal expected Jun 13, followed b negotiations in Oct. Grant Agreement expected to be approved by the WB in Dec. 2013. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (technical assistance) | Multiyear | ASP | THA | PHA | 68 | TAS | 160 | N | I | HCFC | 1.3 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2014-06-01 |  |  | 108185 | 0 | 108185 | 0 | 0% | 108185 | 108185 | 0 | 7575 | 0 | 0 | 7575 | 7575 | First tranche approved in Dec. 2012. A preparation mission (for a new Thailand-WB grant agreement) was launched immediately after the ExCom approval of the HPMP. | 2013 HCFC import quota was established in Jan. 2013. Thailand initiated preparation of environmental safeguard plans to ensure safe introduction of flammable materials in both foam and a/c sectors. First inter-departmental meeting was held to discuss the need to amend regulations and standards pertaining to use of mildly flammable materials as refrigerants. Consulatations with Council of Engineers to promote the use of non-HCFC-22 a/c held. GoT is encouraging a/c enterprises not eligible for funding from the MLF to also adopt lower-GWP alternatives. Several multinational companies have started preparation to offer a similar product in Thailand and for export markets. WB project appraisal expected Jun 13, followed b negotiations in Oct. Grant Agreement expected to be approved by the WB in Dec. 2013. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multiyear | ASP | THA | PHA | 68 | TAS | 163 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2014-06-01 |  |  | 276228 | 0 | 276228 | 0 | 0% | 276228 | 276228 | 0 | 19335 | 0 | 0 | 19335 | 19335 | First tranche approved in Dec. 2012. A preparation mission (for a new Thailand-WB grant agreement) was launched immediately after the ExCom approval of the HPMP. | 2013 HCFC import quota was established in Jan. 2013. Thailand initiated preparation of environmental safeguard plans to ensure safe introduction of flammable materials in both foam and a/c sectors. First inter-departmental meeting was held to discuss the need to amend regulations and standards pertaining to use of mildly flammable materials as refrigerants. Consulatations with Council of Engineers to promote the use of non-HCFC-22 a/c held. GoT is encouraging a/c enterprises not eligible for funding from the MLF to also adopt lower-GWP alternatives. Several multinational companies have started preparation to offer a similar product in Thailand and for export markets. WB project appraisal expected Jun 13, followed b negotiations in Oct. Grant Agreement expected to be approved by the WB in Dec. 2013. |  |  | Non-INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 63 | INV | 56 | N | I | HCFC | 44.7 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-31 | 2013-12-01 |  |  | 2832518 | 0 | 2832518 | 0 | 0% | 2832518 | 2832518 | 1500000 | 212439 | 0 | 0 | 212439 | 212439 | PMU was established in Aug. 12. Grant Agreement was signed in Nov 12. PMU was staffed and equipped in Dec 2012. First sub-grant with one of the 12 foam enterprises was signed Dec 12. Some TA activities were initiated. | HCFC import quota was issued for 2013. Project launch workshop is scheduled in May 2013. Most subgrants are expected to be signed by the end of Jun 2013. First disbursement of US$500,000 made in Jan 2013. |  |  | INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (Technical assistance and project management) | Multiyear | ASP | VIE | PHA | 63 | TAS | 58 | N | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-12-31 | 2013-12-01 |  |  | 221905 | 0 | 221905 | 0 | 0% | 221905 | 221905 | 100000 | 16643 | 0 | 0 | 16643 | 16643 | PMU was established in Aug. 12. Grant Agreement was signed in Nov 12. PMU was staffed and equipped in Dec 2012. First sub-grant with one of the 12 foam enterprises was signed Dec 12. Some TA activities were initiated. | HCFC import quota was issued for 2013. Project launch workshop is scheduled in May 2013. Most subgrants are expected to be signed by the end of Jun 2013. First disbursement of US$500,000 made in Jan 2013. |  |  | Non-INV
ONG | IBRD | Preparation of a HCFC phase-out management plan: HCFC production sector |  | ASP | CPR | PHA | 55 | PRP | 467 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-12-31 | 2013-07-01 |  |  | 473300 | 0 | 473300 | 400252 | 84.57% | 73048 | 73048 | 73048 | 35498 | 0 | 30019.32 | 5478.68 | 5478.68 | From Feb to Apr 2012, China and the WB intensively put together a production sector plan thru a WB mission and by correspondence which was submitted on 9 Apr 2012 to the 67th ExCom and to be ready at the time that final technical audit was officially considered by the production sector subgroup. Proposal was deferred by the production subgroup until the 68th ExCom. A special meeting was set up after the MOP in Nov. 13 between China, donors and the IAs, leading up to the 68th Meeting. During 68th ExCom, small group discussions. Proposal not considered by production sector subgroup. | Consultation meeting held Mar 2013 in DC between FECO, the US and the WB. Proposal is to be considered by the production sector subgroup at the 69th ExCom. |  |  | Non-INV
ONG | Italy | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | AFR | GHA | PHA | 61 | TAS | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2014-12-01 | 2014-12-01 | 2012-12-01 |  | 70000 | 0 | 70000 | 69826 | 99.75% | 174 | 0 |  | 9100 | 0 | 4320 | 4780 | 5256 | All Italian components have progressed in a satisfactory way, completing the work of the first tranche. The international consultant on legislative aspects completed the study for Ghana's consideration. The international consultant on the introduction of a paperless licensing system also completed the work in collaboration with the national consultant. |  |  |  | INV
ONG | Italy | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GHA | PHA | 67 | INV | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 |  | 7800 | 0 | 0 | 7800 | 0 | Planning for the second tranche has been completed in 2012, with a focus on the safety aspects for alternatives to HCFC, continuation of support on legislation and provision of customs identifiers. | Implementation has been initiated and a mission will be conducted in 2013 on the occasion of the Joint Regional Network Meeting being held in September 2013 in Ghana. |  |  | INV
ONG | Japan | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 516 | A | I |  | 0 |  | 0 |  | 2011-07-01 |  | 2013-07-01 |  |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 10400 | 0 |  | 10400 |  | The launching meeting was held in Shanghai in December 2011, not only for the servicing sector but also for all the sectors.
ONG | Japan | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 68 | INV | 527 | A | I |  | 0 |  | 0 |  | 2012-12-01 |  | 2013-12-01 |  |  |  | 80000 | 0 | 80000 |  | 0% | 80000 |  | 80000 | 10400 | 0 |  | 10400 |  | Refer to multi-year sheet.
ONG | Japan | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | INV | 18 | A | I |  | 0.5 |  | 0 |  | 2011-04-01 |  | 2013-03-01 |  |  |  | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 0 | 16900 | 16900 | Refer to multi-year sheet.
ONG | Japan | HCFC phase-out management plan (stage I, first tranche) (technical assistance) |  | ASP | THA | PHA | 68 | TAS | 158 | A | I |  | 4.2 |  | 0 |  | 2012-12-01 |  | 2013-11-01 |  |  |  | 302965 | 0 | 302965 |  | 0% | 302965 |  |  | 39385 | 0 |  | 39385
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ANG | PHA | 65 | INV | 10 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 | 2015-11-01 |  |  | 86222 | 0 | 86222 | 3840 | 4.454% | 82382 | 0 | 32952.8 | 7760 | 0 | 345.6009 | 7414.3991 | 0 | The project was initiated in 2012, with the signature of the Project document and the first mission completed in June by the international consultant. Consultations were held throughout 2012 with the NOU for prioritisation of activities in the first tranche. Some changes in the structure of the NOU explained also that additional time was needed in order to launch activities. | Agreement on the work plan for 2013 to accelerate implementation of activities, with a focus on customs and service technicians' training. Mission to be held in the first half of 2013 by UNDP staff with support from international consultant. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ARM | PHA | 62 | INV | 06 | N | I | HCFC | 2.2 | 2.2 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 | 2013-12-01 |  |  | 265661 | 0 | 265661 | 98791.19 | 37.19% | 166869.81 | 0 | 50060.943 | 19925 | 0 | 7409.4973 | 12515.5027 | 0 | During 2012, two missions were fielded to Armenia (January and November 2012) to provide technical support and supervision. NOU/UNDP Armenia announced RFQ for procurement of RAC service tools for local companies. Among two local and one international bidders, TST STAG S.A. was selected a winner. Following this, in October 2012, 29 sets of service tools were delivered to Yerevan. 25 sets were distributed to service companies, and remaning 4 sets to Refrigeration Association of Armenia. | In March 2013, tender documentation was cleared by regional procurement panel (ACP), and Transfair (Germany) was selected for equipment delivery to SAGA. Equipment is expected to arrive within 6-7 months after the contract signature around September/October 2013. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | ARM | PHA | 66 | INV | 09 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2015-04-01 | 2015-04-01 |  |  | 297177 | 0 | 297177 | 0 | 0% | 297177 | 0 | 118870.8 | 22288 | 0 | 0 | 22288 | 0 | 2nd tranche request was approved at the 66th ExCom, and this allowed to complete ITB for SAGA. | In March 2013, tender documentation was cleared by regional procurement panel (ACP), and Transfair (Germany) was selected for equipment delivery to SAGA. Equipment is expected to arrive within 6-7 months after the contract signature around September/October 2013. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | BGD | PHA | 65 | INV | 40 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2011-11-01 |  | 2015-12-01 | 2015-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 22000 | 4125 | 0 | 0 | 4125 | 0 | During 2012, terms of agreement for implementation of HPMP project management components were discussed. Due to change in personnel in Government, finalisation of terms of the agreement got delayed though the draft documents were shared with Government in Q1 of 2012. Project activities for HCFC phaseout under a project for HCFC-141b consumption progressed satisfactorily through direct monitoring and supervision of NOU. | Memorandum of Agreement signed by Government in March 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | INV | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 21000 | 6300 | 0 | 0 | 6300 | 0 | Prodoc for HPMP was finalised after detailed consultations with NOU on implementation priorities during the year 2012. The main reason for the delay was finalisation of consultations on priorities and plan for implementing project activities and subsequent, administrative approval of the same. The prodoc Is expected to be signed in early 2013. | HPMP prodoc was signed in February 2013. First disbursements made by end-March 2013 | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 295 | N | I | HCFC | 48.7 | 48.7 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2012-07-01 | 2015-12-01 |  |  | 4456257 | 0 | 4456257 | 24628.89 | 0.5527% | 4431628.11 | 0 | 1772651.244 | 334219 | 0 | 1847.1652 | 332371.8348 | 0 | UNDP project document was signed in 2012. 5 technical missions took place to visit participating companies in Brazil. Main focus in 2012 was on Continous Panels sector where contracts were signed with the companies and important progress was made. Agreements have been reached with 2 system houses and 2 individual companies about selection of technology and terms for contracts. Remaining system houses are individual projects are making in-house trials with new alternatives. | Trials continues at system houses and individual companies. More contracts have been signed and payments been made. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | LAC | BRA | PHA | 68 | INV | 298 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 3400000 | 0 | 3400000 | 0 | 0% | 3400000 | 0 | 1360000 | 255000 | 0 | 0 | 255000 | 0 | Newly approved. | 2nd tranche incorporated in the Project Document allowing the expansion of activities. New contracts are being negotiated with beneficiary companies in order to make feasible the financial transference of funds under the 2nd tranche. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | BRU | PHA | 66 | INV | 13 | N | I | HCFC | 0.2 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2015-12-01 |  |  | 52800 | 0 | 52800 | 0 | 0% | 52800 | 0 | 21120 | 4752 | 0 | 0 | 4752 | 0 | A draft Letter of Agreement between Brunei Government and UNDP and prodoc were prepared in Q2/Q3 of 2012 and sent to the Government in July, 2012. The Government is reviewing this agreement. This agreement is expected to be finalised by end of Q2 or early Q3 of 2013 after administrative clearance from Government. | The Government is reviewing the agreement and is expected to be finalized in Q2/Q3 of this year. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 5400 | 0 | 0 | 5400 | 0 | Prodoc was signed in 2011. In 2012, workplans and specs for procurement of tools and equipment prepared. Procurement process had to be repeated several times because of limited interest from potential suppliers. | Bidding process is progressing. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | INV | 174 | N | I | HCFC | 5.7 | 0 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-01 | 2014-01-01 |  |  | 465566 | 0 | 465566 | 2892.8 | 0.6214% | 462673.2 | 0 | 185069.28 | 34917 | 0 | 216.9572 | 34700.0428 | 0 | Project Document was signed. TORs have been developed and published. Quota system has been implemented. | Contracts and Long Term Agreements have been signed with main experts (national and international). Activities in commercial refrigeration sector are advancing. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | COL | PHA | 66 | INV | 81 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2014-04-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 13159.48 | 220000 | 41250 | 0 | 0 | 41250 | 986.961 | The second tranche request was prepared and approved by the ExCom in 2012. Substantial advances with training of technicians (597 trained)and introduction of new alternatives for flushing. New legislation was introduced for the Domestic Refrigeration Sector. 7 courses in good refrigeration practices were conducted and one train the trainers seminar took place. | Activities continue to be implemented under the HPMP in Colombia. Seminars on alternatives to HCFC 141b in flushing conducted. Continued training of refrigeration technicians. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2014-01-01 |  |  | 168000 | 0 | 168000 | 5147.99 | 3.064% | 162852.01 | 0 | 65140.804 | 12600 | 0 | 386.0992 | 12213.9008 | 0 | Project document was signed by the Government of Costa Rica. The experts have been hired. Legislation has been updated in Costa Rica, and a quota system has been agreed with all the importers. | HPMP activities continue to be implemented. There is a focus on the flushing sector and training of technicians. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 45 | N | I | HCFC | 14 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 593523 | 0 | 593523 | 313603.28 | 52.84% | 279919.72 | 0 | 83975.916 | 44514 | 0 | 23520.1271 | 20993.8729 | 0 | Two expert missions took place in 2012. Equipment was delivered in October 2012, and is being installed at MABE. | Project has been installed and test with Cyclopentane was made. Project is expected to be completed in 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (national coordination) (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 64 | INV | 515 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 | 2013-12-01 |  |  | 360000 | 0 | 360000 | 120000 | 33.33% | 240000 | 0 | 72000 | 27000 | 0 | 9000 | 18000 | 0 | The overall HPMP launch workshop was held in December 2011. The prodoc was signed in December 2011. | Overall coordinaton in progress as planned. | 2011 |  | Investment
ONG | UNDP | Sector plan for phase-out of HCFCs in the solvent sector (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 65 | INV | 519 | N | I | HCFC | 33 | 0 | 0 | 0 | 2011-11-01 | 2012-07-01 | 2016-10-01 | 2016-10-01 |  |  | 2500000 | 0 | 2500000 | 1250000 | 50% | 1250000 | 0 | 500000 | 187500 | 0 | 93750 | 93750 | 0 | Project approved in November 2011. Prodoc signed in 2Q2012. Work Plan and enterprise-level agreements finalized in 4Q2012 | N/A | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (industrial and commercial refrigeration and air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 512 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 | 2013-12-01 |  |  | 25380000 | 0 | 25380000 | 25380000 | 100% | 0 | 0 | 0 | 1903500 | 0 | 1903500 | 0 | 0 | The prodoc was finalized and signed in December 2011. Verification of baseline of participating beneficiaries in Stage-I was carried out by September 2012. Enterprise-level phase-out agreements finalized. Second disbursement was made in December 2012. | Enterprise-level activities, including signing of remaining agreements and related monitoring proceeding as planned | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 68 | INV | 525 | N | I | HCFC | 44 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 6900000 | 0 | 6900000 | 0 | 0% | 6900000 | 0 | 2760000 | 483000 | 0 | 0 | 483000 | 0 | Newly approved. | Prodoc is being finalised. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-year | LAC | CUB | PHA | 65 | INV | 49 | N | I | HCFC | 13.4 | 6 | 0 | 0 | 2011-11-01 |  | 2016-10-01 | 2016-10-01 |  |  | 650000 | 0 | 650000 | 0 | 0% | 650000 | 0 | 260000 | 48750 | 0 | 0 | 48750 | 0 | Two technical missions took place in 2012 to develop the technical specs with the beneficiary companies in the foam sector. Training was given to personnel working in the plants. | Technical specs agreed among all foam companies in the foam sector and are in the process of being published. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | CUB | PHA | 65 | TAS | 48 | N | I | HCFC | 1.7 | 0 | 0 | 0 | 2011-11-01 |  | 2016-10-01 | 2016-10-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7500 | 0 | 0 | 7500 | 0 | Project document was prepared and is in the process of being revised and agreed by the Government of Cuba. | Prodoc agreed by Ministries. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-Year | LAC | CUB | PHA | 68 | INV | 50 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 537527 | 0 | 537527 | 0 | 0% | 537527 | 0 | 215010.8 | 40315 | 0 | 0 | 40315 | 0 | Newly approved. | Technical specifications for the complete investment project has been developed and discussed with beneficiary enterprises. The TORs will be published at the earliest convenience. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector) | Multi-year | LAC | DOM | PHA | 65 | INV | 48 | N | I | HCFC | 8.2 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 | 2016-10-01 |  |  | 343468 | 0 | 343468 | 1693.53 | 0.4931% | 341774.47 | 0 | 136709.788 | 25760 | 0 | 127.0143 | 25632.9857 | 0 | 2 expert missions took place in 2012 to visit all the foam companies in the DR. Technical Assistance was provided regarding new alternatives was provided. Companies have made further investigation and have selected technology for the reconversion. MOAs were prepared for 4 foam companies. | MOAs were signed by four companies. Methyl Formate for trials were procured to make on site test. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 65 | INV | 49 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 | 2016-10-01 |  |  | 336532 | 0 | 336532 | 10115.26 | 3.006% | 326416.74 | 0 | 130566.696 | 25240 | 0 | 758.6475 | 24481.3525 | 0 | Project Document was signed in 2012. HCFC quota system and related legislation in place. Agreement was made with INDOTEP about training of technicians. | Contract with INFOTEP was signed. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | DRC | PHA | 63 | INV | 36 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 | 2013-03-01 |  |  | 100000 | 0 | 100000 | 29086.15 | 29.09% | 70913.85 | 67756 | 21274.155 | 9000 | 0 | 2617.7535 | 6382.2465 | 6098.04 | The purchase of equipment was finalised and it arrived in Kinshasa in November 2012. The national HPMP consultant insured the follow-up of activities throughout the year and public awareness was raised about the results of the HPMP’s 1st phase. | A mission by international consultant took place in February 2013 and on this occasion the equipment was handed over during a ceremony with the NOU. Activities to be undertaken under next tranche were agreed upon with NOU and National Consultant and will be submitted to 70th ExCom. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-year | AFR | EGY | PHA | 65 | INV | 113 | N | I | HCFC | 42.1 | 42.1 | 0 | 0 | 2011-11-01 |  | 2015-11-01 | 2015-11-01 |  |  | 2000000 | 0 | 2000000 | 0 | 0% | 2000000 | 0 | 800000 | 150000 | 0 | 0 | 150000 | 0 | Initial mission by a group of international experts was fielded during February 2012 to initiate FSPOP and discuss MOU implementation modality with Al Fateh, Reftruck and 4 system houses. Redachem (Dubai) had facility fire and was put out of operation. It was replaced with Obegi system house which was found to be eligible. For Refrtruck, purchase order placed in December 2012 with equipment expected in July 2013. Site preparation is underway. | MOAs are being revised to reflect final comments from system houses. Mission is planned in April 2013 for follow-up support. For Al Fateh, purchase order for equipment delivery placed in January 2013 with equipment expected in August 2013. Site preparation is underway in coordination with Reftruck activities to save costs. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-Year | AFR | EGY | PHA | 68 | INV | 117 | N | I | HCFC | 42.1 | 0 | 0 | 0 | 2012-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 2000000 | 0 | 2000000 | 0 | 0% | 2000000 | 0 | 800000 | 150000 | 0 | 0 | 150000 | 0 | Newly approved. | DOA prepared; Mission is planned in April 2013 | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | INV | 30 | N | I | HCFC | 0.9 | 0 | 0 | 0 | 2011-11-01 |  | 2015-11-01 | 2015-11-01 |  |  | 91072 | 0 | 91072 | 0 | 0% | 91072 | 0 | 36428.8 | 6830 | 0 | 0 | 6830 | 0 | Project document was signed by the Government of El Salvador. Internal reorganization of Ministry of Environment delayed the start up of activities. | Mission by international expert took place in January 2013. Local expert has been hired for the project, and activities are being implemented according to the plan. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase out of HCFC-141b in imported pre-blended polyols used in the foam manufacturing sector) | Multi-year | LAC | ELS | PHA | 65 | INV | 29 | N | I | HCFC | 4.9 | 0 | 0 | 0 | 2011-11-01 |  | 2015-11-01 | 2015-11-01 |  |  | 439277 | 0 | 439277 | 0 | 0% | 439277 | 0 | 175710.8 | 32946 | 0 | 0 | 32946 | 0 | Project Document was signed. MOAs for participating enterprises have been prepared. 2 technical missions took place to discuss project implementation and selection of technology with foam companies. | MF material in the process of being procured for trials in El Salvador. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | FIJ | PHA | 65 | INV | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2014-11-01 | 2014-12-01 |  |  | 71800 | 0 | 71800 | 18524.99 | 25.8% | 53275.01 | 0 | 21310.004 | 6462 | 0 | 1667.2491 | 4794.7509 | 0 | HPMP prodoc was finalised and signed in July 2012. The Government has implemented a quota system for controlling HCFC consumption in the country and HCFC quotas for the year 2012 have been issued to licensed importers. Procurement plan for R&R equipment was finalised in Q4 of 2012. Project Management Unit has been set-up under NOU. | Project activities are progressing satisfactorily. Procurement process has been initiated by the Government and the equipment is expected to be available in the country by middle of the year 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | GEO | PHA | 63 | INV | 30 | N | I | HCFC | 0.7 | 0 | 0 | 0 | 2011-04-01 |  | 2014-03-01 | 2014-03-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 80000 | 15000 | 0 | 0 | 15000 | 0 | The project document was signed between UNDP and the Ministry of Environment Protection. National consultants have been recruited for updating the Code of Practice and the Syllabus of Vocational Schools and for collection/processing of data on installations using ODS solvents. The first draft of the updated Code of Practice and the syllabus for vocational schools both are developed. First draft of the strategy and a list of needed ODS free dry cleaning equipment and potential suppliers prepared with help of national and international experts. | Selection of the legal expert for Introduction of licensing and quota system for HCFCs is completed. Update of the software for Customs officers to monitor HCFC import-export is nearing completion. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | GHA | PHA | 67 | INV | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 80000 | 15000 | 0 | 0 | 15000 | 0 | Tranche 2 was approved at the July 2012 ExCom and activities have progressed well throughout the year. Following approval, project document has been amended and DOA issued to allow HPMP activities to continue. | Work plan approved for 2013 and implementation initiated. Technical workshops are being visited to check for safety processes and identifying lead workshops for the conversion scheme. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | INV | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-08-01 | 2012-03-01 | 2015-01-01 |  |  | 48000 | 0 | 48000 | 1781.78 | 3.712% | 46218.22 | 0 | 18487.288 | 4320 | 0 | 160.3602 | 4159.6398 | 0 | UNDP project document was signed. Technical specs prepared. | Technical specs have been published. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 195 | N | I | HCFC | 14.5 | 0 | 0 | 0 | 2011-07-01 |  | 2013-03-01 | 2013-12-01 |  |  | 1995519 | 52800 | 2048319 | 0 | 0% | 2048319 | 0 | 614495.7 | 149664 | 3960 | 0 | 153624 | 0 | Prodoc signed in March 2012. Stakeholder consultations continued. | Enterprise-level phase-put agreements signed. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (refrigeration sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 193 | N | I | HCFC | 24.4 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-03-01 | 2013-12-01 |  |  | 1802807 | 0 | 1802807 | 3156.29 | 0.1751% | 1799650.71 | 0 | 539895.213 | 135210 | 0 | 236.7208 | 134973.2792 | 0 | Prodoc signed in March 2012. Stakeholder consultations continued. | Enterprise-level phase-put agreements signed. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (project management and coordination) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | TAS | 192 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-03-01 | 2013-12-01 |  |  | 201674 | 0 | 201674 | 0 | 0% | 201674 | 0 | 60502.2 | 15126 | 0 | 0 | 15126 | 0 | Prodoc signed in March 2012. Stakeholder consultations continued. | TA activities proceeding as planned. | 2011 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | IND | PHA | 66 | INV | 441 | N | I | HCFC | 145.4 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-01 | 2014-12-01 |  |  | 9400000 | 0 | 9400000 | 0 | 0% | 9400000 | 0 | 3760000 | 705000 | 0 | 0 | 705000 | 0 | In 2012, the prodoc was signed. Stakeholder consultations continued to get consensus on technology and financing approach. | Enterprise-level phase-put agreements signed. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management component) | Multi-year | ASP | IND | PHA | 66 | TAS | 440 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-01 | 2014-12-01 |  |  | 600000 | 0 | 600000 | 0 | 0% | 600000 | 0 | 240000 | 45000 | 0 | 0 | 45000 | 0 | In 2012, the prodoc was signed. | Activities progressing as planned. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (foam sector plan: one foam systems house) | Multi-Year | ASP | IRA | PHA | 63 | INV | 204 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2015-03-01 | 2015-03-01 |  |  | 225500 | 0 | 225500 | 0 | 0% | 225500 | 0 | 90200 | 16913 | 0 | 0 | 16913 | 0 | In January 2012, project document between Government and UNDP was signed. Beneficiary is assessing alternatives for use among SMEs, price and availability of such alternatives in Iran. | The phase-out agreement between NOU and beneficiary is expected to be concluded in Q2-2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 199 | N | I | HCFC | 18.4 | 0 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2015-03-01 | 2015-03-01 |  |  | 1938500 | 0 | 1938500 | 662361.63 | 34.17% | 1276138.37 | 0 | 510455.348 | 145387 | 0 | 49676.9514 | 95710.0486 | 0 | The phase-out agreement between NOU and beneficiary was signed in Q4-2012. The enterprise has completed redesign of models of air-conditioners and plant layout for manufacturing air-conditioners with the new technology in 4Q-2012. The first payment was re | Implementation progessing as planned. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 203 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 | 2013-06-01 |  |  | 78000 | 0 | 78000 | 0 | 0% | 78000 | 0 | 23400 | 5850 | 0 | 0 | 5850 | 0 | In January 2012, project document between Government and UNDP was signed. Interagency meeting on project implemenation progress was held in January 2012. PMU was established under NOU in the beginning of the year 2012 and the unit is working with lead | Implementation of activities are progressing in a satisfactory manner. Currently, third tranche for HPMP of Iran is under preparation for submission to the 70th meeting of the Executive Committee. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 208 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 1370000 | 0 | 1370000 | 0 | 0% | 1370000 | 0 | 548000 | 102750 | 0 | 0 | 102750 | 0 | Newly approved. | AWP is being finalised. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 28 | N | I | HCFC | 3.6 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 | 2014-01-01 |  |  | 95450 | 0 | 95450 | 1160.32 | 1.216% | 94289.68 | 0 | 37715.872 | 7159 | 0 | 87.027 | 7071.973 | 0 | Seal Sprayed Inc. has concluded all trials with methyl formate and retrofit process of dispensers has been initiated. | Technical specifications are being concluded and procurement of parts will be undertaken in May 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 | 2015-01-01 |  |  | 142000 | 0 | 142000 | 3750.76 | 2.641% | 138249.24 | 0 | 55299.696 | 10650 | 0 | 281.307 | 10368.693 | 0 | Project document was signed. Local expert was identified and hired. | International expert on RAC hired. In April 2013, a first mission will be undertaken to initiate the technical assistance activities. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | ASP | KAM | PHA | 61 | INV | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-05-01 | 2019-12-01 | 2019-12-01 |  |  | 200000 | 0 | 200000 | 100000 | 50% | 100000 | 100000 | 40000 | 15000 | 0 | 7500 | 7500 | 7500 | The LOA was signed in January 2012. Activities under HPMP are progressing satisfactorily. R&R equipment procurment has commenced in August 2012. Retrofit activities are planned beginning HY1 of 2013. | Project implementation is progressing satisfactorily. Equipment distribution would be complete by Q2 of 2013. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | KYR | PHA | 63 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 | 2014-12-01 |  |  | 47520 | 0 | 47520 | 19981.4 | 42.05% | 27538.6 | 0 | 11015.44 | 4277 | 0 | 1798.4101 | 2478.5899 | 0 | National expert continued providing technical support on a part-time basis. Three (3) workshops on HCFC alternatives were held in April and October 2012 (75 participants). | Workplan for 2013 formulated and endorsed by NOU. Funds for 2013 plan allocated. Discussions on development of R/R tools' specifications are currently ongoing with intentions to procure tools through a local supplier. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 76 | N | I | HCFC | 9.1 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 810000 | 0 | 810000 | 334076.28 | 41.24% | 475923.72 | 0 | 142777.116 | 60750 | 0 | 25055.721 | 35694.279 | 0 | Prodoc signed in Jan 2012. Enterprise-level phase-out agreement signed. Activities progressing as planned. | N/A | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 74 | N | I | HCFC | 3 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 555000 | 0 | 555000 | 555000 | 100% | 0 | 0 | 0 | 41625 | 0 | 41625 | 0 | 0 | Prodoc signed in Jan 2012. Enterprise-level phase-out agreement signed. Activities progressing as planned. | N/A | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | TAS | 75 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2013-07-01 |  |  | 135000 | 0 | 135000 | 0 | 0% | 135000 | 0 | 40500 | 10125 | 0 | 0 | 10125 | 0 | HPMP Stage-I overall prodoc signed in Jan 2012. Launch workshop held in Jan 2012 | N/A | 2011 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | MAL | PHA | 65 | INV | 169 | N | I | HCFC | 49.3 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2016-10-01 | 2016-10-01 |  |  | 4327247 | 0 | 4327247 | 479524.7 | 11.08% | 3847722.3 | 0 | 1539088.92 | 324544 | 0 | 35964.4051 | 288579.5949 | 0 | Prodoc signed in March 2012. Enterprise-level agreements were progressively completed by July 2012. | Activities progressing as planned. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (management and coordination) | Multi-year | ASP | MAL | PHA | 65 | TAS | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2016-10-01 | 2016-10-01 |  |  | 312908 | 0 | 312908 | 0 | 0% | 312908 | 0 | 125163.2 | 23468 | 0 | 0 | 23468 | 0 | Overall HPMP prodoc signed in March 2012. Launch workshop held in March 2012. | Activities progressing as planned. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the servicing sector) | Multi-year | ASP | MAL | PHA | 65 | TAS | 168 | N | I | HCFC | 4.4 | 0 | 0 | 0 | 2011-11-01 |  | 2016-10-01 | 2016-10-01 |  |  | 359845 | 0 | 359845 | 0 | 0% | 359845 | 0 | 143938 | 26988 | 0 | 0 | 26988 | 0 | Prodoc signed in March 2012. Activities will be initiated in 2013. | N/A | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 60 | INV | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 |  | 2019-12-01 | 2019-12-01 |  |  | 400000 | 0 | 400000 | 0 | 0% | 400000 | 0 | 160000 | 30000 | 0 | 0 | 30000 | 0 | During the year 2012, consultations were held with Ministry of Fisheries and Agriculture (MoFA) on retrofit incentive scheme implementation for consumers in fisheries industry. The modalities of implementation were finalised in Q2 of 2012 and the final agreement was signed October 2012. Technical consultant is to be engaged by early 2013 for redesigning and undertaking retrofitting of HCFC based equipment. Consultations are underway for adopting not-in-kind options for converting residential air-conditioning industry (e.g., district cooling). | The recruitment of technical expert for retrofitting is in progress. The implementation plan is closely being monitored. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector plan for systems houses and local customers) (stage I, first tranche) | Multi-Year | LAC | MEX | PHA | 64 | INV | 159 | N | I | HCFC | 66.8 | 66.8 | 0 | 0 | 2011-07-01 | 2011-08-01 | 2013-07-01 | 2013-07-01 |  |  | 2502526 | 0 | 2502526 | 676592.64 | 27.04% | 1825933.36 | 0 | 547780.008 | 187689 | 0 | 50744.3263 | 136944.6737 | 0 | 6 international expert missions took place in 2012. All local system houses have selected technologies and made trials with new low GWP alternatives. Trials are currently being made at customers' level in most advanced system houses. | Safety Audit completed at 3 system house. One international expert mission took place in Feb/March to provide technical assistance to foam companies. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan for systems houses and local customers) | Multi-Year | LAC | MEX | PHA | 68 | INV | 165 | N | I | HCFC | 101.5 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 3800000 | 0 | 3800000 | 0 | 0% | 3800000 | 0 | 1520000 | 285000 | 0 | 0 | 285000 | 0 | Newly approved. | Second tranche budget has been included in project. Contracts has been signed with system houses. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLI | PHA | 63 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 | 2013-03-01 |  |  | 160000 | 0 | 160000 | 126746.1 | 79.22% | 33253.9 | 640 | 9976.17 | 12000 | 0 | 9505.9575 | 2494.0425 | 48 | Equipment specifications and RFQ were issued and equipemnt purchased. Delivery of equipment (lot #1) completed in 2012. Activities progressed smoothly with support from international and national consultants. The scheme of subsidees for end-users progressed as approved, in spite of the difficult political situation in the country throughout the year. | Delivery of equipment (lot #2) in expected Q2 2013. Work plan approved for 2013. Mission by international consultant is planned once all equipment is received and security situation allows for it. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOL | PHA | 63 | INV | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 | 2014-12-01 |  |  | 79200 | 0 | 79200 | 14616.02 | 18.45% | 64583.98 | 22600.44 | 25833.592 | 7128 | 0 | 1315.4418 | 5812.5582 | 2034.0396 | Two (2) awareness raising workshops organized by NOU and Refrigeration Association in 2012. Three (3) multi-gas identifiers procured for Customs. NOU updated lists of servicing companies (and total number of technicians) and developed EU harmonized framework for new certification system and ODS use reporting system (supported by workshop). Twenty (20) sets of tools procured. Website for Refrigeration association created. Information materials prepared, printed and distributed. | Workplan for 2013 reviewed and approved with the Government. Funds for 2013 allocated. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | NEP | PHA | 66 | INV | 30 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2012-04-01 |  | 2015-04-01 | 2015-04-01 |  |  | 42000 | 0 | 42000 | 0 | 0% | 42000 | 0 | 16800 | 3780 | 0 | 0 | 3780 | 0 | During the year 2012, consultations were held with NOU of Nepal on implementation plan for HPMP. Due to changes in NOU staff, finalisation of plan got delayed, however, it is expected to be back on track in 2013. | Implementation plan is expected to be completed by Q2 of 2013. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam, refrigeration air-conditioning servicing and coordination) | Multi-year | AFR | NIR | PHA | 66 | INV | 132 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2013-04-01 | 2013-12-01 |  |  | 836515 | 0 | 836515 | 109621.89 | 13.1% | 726893.11 | 15720 | 218067.933 | 62739 | 0 | 8221.6909 | 54517.3091 | 1179.007 | DOA for 2nd tranche prepared in October 2012 and funds allocated. PU foam conversion started in 1st tranche at VitaPUR is ongoing, with local preparatory work under way (reorganization of the facility to accomodate new equipment). | Equipment shipped from South Africa expected shortly at VitaPUR. Safety audit is expected at the Pamaque facility by April 2013, with mission of international consultant and MPU staff. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | LAC | PAN | PHA | 65 | INV | 32 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2016-10-01 | 2016-10-01 |  |  | 132773 | 0 | 132773 | 731.32 | 0.5508% | 132041.68 | 0 | 52816.672 | 9958 | 0 | 54.8491 | 9903.1509 | 0 | UNDP project document was signed in 2012 by the Government of Panama. TORs for experts were prepared. Quota system was established. | TORS published and experts hired. Project has started up implementation of activities. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | INV | 29 | N | I | HCFC | 0.9 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2015-05-01 |  |  | 168500 | 0 | 168500 | 36002.51 | 21.37% | 132497.49 | 0 | 52998.996 | 12638 | 0 | 2700.2951 | 9937.7049 | 0 | Team of local experts were hired for the project implementation. The quota system has been established and agreed with stakeholders. Training of technicians took place. Intternational expert made train the trainers on the use of HC. | Changes in government in the end of 2012 and upcoming elections in April has made it very difficult to implement activities in the beginning of 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 108000 | 0 | 108000 | 0 | 0% | 108000 | 0 | 43200 | 9720 | 0 | 0 | 9720 | 0 | Newly approved. | Options for the Licensing System evaluated by the Government and in April, a sector consultation will be carried between public and private sector to finalize the model and establish the Licensing and quota systems. UNDP project document has been develop | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | INV | 40 | N | I | HCFC | 0.4 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 | 2014-12-01 |  |  | 180000 | 0 | 180000 | 40169.34 | 22.32% | 139830.66 | 0 | 55932.264 | 13500 | 0 | 3012.7005 | 10487.2995 | 0 | HPMP activities are in progress. During the year 2012, the Government consulted importers and national stakeholders on development of quota system. Quotas for the year 2013 were allocated in Q4 of 2012. Training program was conducted for service technicians focusing on stopping use of HCFC-141b in RAC equipment servicing. Agreement with Regnis which uses HCFC-141b preblended polyol for manufacturing foam for conversion to HC is at advanced stages of discussion and is expected to be concluded by Q1 of 2013. Discussions are underway with enterprises assembling air-conditioners for conversion to HCFC free technologies. Baselin data from these enterprises have been verified. | On 16 February 2013, the training on 141b cleaning agent was held for enabling cessation of HCFC-141b use in cleaning. Other activities under HPMP are underway. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 16 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 16000 | 3600 | 0 | 0 | 3600 | 0 | Prodoc has been prepared and submitted to the Govt and is awaiting the legal advisory of the Minister prior to signature. | ProDoc has not been signed yet but is expected to be signed shortly. | 2011 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | INV | 19 | N | I | HCFC | 7.7 | 3.5 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-09-01 | 2013-09-01 |  |  | 667948 | 0 | 667948 | 581642.6 | 87.08% | 86305.4 | 0 | 25891.62 | 50096 | 0 | 43623.1079 | 6472.8921 | 0 | The project is on-track with its planned completion date. The equipment was received in 2012 and has started being installed at the Palfridge facility. However, full testing of equipment and training was not possible yet as of end of 2012 corresponded with high workload for factory, and will take place in 2013. | Local works progressed including exhaust, ventilation, enclosures, pipelines and safety equipment. International consultant will have a one-day visit in April on the occasion of another project mission in South Africa. The final safety audit visit and training by international expert is planned by July 2013. | 2011 |  | Investment
ONG | UNDP | CFC and HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | INV | 07 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-10-01 | 2012-03-01 | 2013-12-01 |  |  | 96120 | 0 | 96120 | 30000 | 31.21% | 66120 | 51120 | 19836 | 8651 | 0 | 2700.0624 | 5950.9376 | 4600.9064 | The Letter of Agreement was signed in April 2012. The implementation plan finalized and agreed. The first disbursement was made in Oct 2012. Technical specifications of equipment for R&R were finalised. | Procurement process is underway. The procurement committeee are being established and wil review the documents for Procurement of R&R equipment. Equipment procurement is expected tobe completed by end of Q3 of 2013. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 26 | N | I | HCFC | 2.5 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2014-07-01 |  |  | 173800 | 0 | 173800 | 0 | 0% | 173800 | 0 | 69520 | 13035 | 0 | 0 | 13035 | 0 | Prodoc signed and companies are to assess Methyl Formate samples to start trials. | Seal Spray foam in TT is testing Methyl Formate in trials. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-12-01 | 2013-07-01 | 2015-12-01 |  |  | 386100 | 0 | 386100 | 911.77 | 0.2361% | 385188.23 | 0 | 154075.292 | 28958 | 0 | 68.3839 | 28889.6161 | 0 | Prodoc signed. National Expert hired and International Expert in process of being contracted. | TORs for international expert published and contracting process has progressed. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | URU | PHA | 65 | INV | 57 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2015-11-01 | 2015-11-01 |  |  | 100000 | 0 | 100000 | 25774.16 | 25.77% | 74225.84 | 18287 | 29690.336 | 7500 | 0 | 1933.062 | 5566.938 | 1371.525 | UNDP project document was signed in 2012. International expert was hired to do training in Uruguay. There is a focus on activities for flushing as 141b pure will be banned during Stage I of the HPMP. | Second and third training by international expert has been scheduled for May and June. Equipment is in the process of being procured. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | URU | PHA | 68 | INV | 58 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7500 | 0 | 0 | 7500 | 0 | Newly approved. | Second tranche budget has been included in the project. | 2012 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | AFG | PHA | 63 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-01 | 2014-06-01 |  |  | 120000 | 0 | 120000 | 69254 | 57.71% | 50746 | 30000 | 50746 | 15600 | 0 | 9003.02 | 6596.98 | 3900 | The list of planned activities for 2012: HCFC Phase-out Policies and Enforcement - Stakeholder consultations for finalizing draft quota system and strengthening licensing system - Train the Trainer workshop - Procurement of equipment. Capability Certification System and Good Practice Program for the Servicing Technicians - Train the Trainers workshop. Enhanced communication and outreach - Organizing technical workshop-to raise awareness on HCFC phase-out and energy efficiency - Media Campaign for Customs/enforcement, servicing sector, and energy efficiency Progress: The HPMP project was launched in January 2012. One workshop was organized in March 2012 for customs officer wherein 49 officers from 13 customs provinces participated. Awareness activities were implemented with developed ODS identification tool for customs officers, ozone story book, customs training manual, ozone regulation booklet, HPMP brochures. HPMP qouta system was establised in April 2012. Additional workshop was organized in May 2012 for customs officer wherein 50 officers from 13 customs provinces participated. And, in June 2012, additional workshop was organized for customs officer wherein 54 officers from 13 customs provinces participated. ToT was organized in 29 May - 1 June 2012 for refrigeration technicians wherein 25 participated. One day survey of HCFC gas was carried out in Kabul city on 14 July 2012 wherein 25 workshops were surveyed.Lastly, new models of refrigerant identifiers were procured and delivered on December 2012. | The remaining training for enforcement and servicing sector is being planned under tranche one of HPMP Implementation and prepared in details for implementation for 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ALB | PHA | 64 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-01-01 | 2013-07-01 | 2013-07-01 |  |  | 25000 | 0 | 25000 | 20156 | 80.62% | 4844 | 4844 | 4844 | 3250 | 0 | 2620.28 | 629.72 | 629.72 | The implementation of the HCFC Phase out Management Plan has begun by the end of the year 2011.The SSFA was signed and the first payment was released. The country has initiated a development of training materials and the preparation of technical base for theoretical and practical training programme in the refrigeration sector. Two workshops were held in 2012 and 59 refrigeration technicians were trained (52 received certificates). The NOPIU also organized the Customs training with participation of 50 customs officers from various regions of the country (43 received certificates). The second and third (last) payments were also released | The quota system to control HCFCs is introduced. Extension of the licensing system to include HCFCs containing mixtures was done. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ANT | PHA | 66 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2015-04-01 | 2015-04-01 |  |  | 45850 | 0 | 45850 | 7240 | 15.79% | 38610 | 559 | 38610 | 5961 | 0 | 941.279 | 5019.721 | 72.6761 | HPMP launched in Sept. 2012. UNEP country mission carried out. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. Ministerial Order to legalize HCFC quota system drafted. | SSFA drafted. National Training workshop on RAC alternatives and associated good practices. 20 technicians trained. HCFC imports are controlled by the NOU with authority under the Trade Department of the Ministry of Finance and the Economy. The HCFC quota system will be formalized by a Ministerial Order under discussion with stakeholders, and expected to be issued in June 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ARM | PHA | 62 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2011-12-01 | 2013-12-01 |  |  | 31515 | 0 | 31515 | 26000 | 82.5% | 5515 | 5515 | 5515 | 4097 | 0 | 3380.0413 | 716.9587 | 716.9587 | The legislation system was updated and import quotas on HCFCs are introduced. NOU has completed the translation of UNEP’s Training Manual for refrigeration technicians (E book) into Armenian language. 25 Refrigeration technicians were trained on 23 October 2012. The first part of the training was combined with the investment component under HPMP and accompanied by the distribution of R&R sets (The second part of the training is planned for autumn 2013). A national certification system for refrigeration technicians and service providers is under development. A monitoring officer has been hired to closely monitor the timely implementation of HPMP’s non‐investment component and review its effectiveness. | Upon submission of the Draft Government Resolution on Monitoring and Control of Imported HCFC-based Equipment and Products it has been proposed by the Ministry to firstly draft the Resolution on Banning CFC-based old equipment. Drafting has been initiated. It has been agreed with the Customs Service to organize a combined (e-learning and auditorium classes) training. The training materials (Customs Manual in Armenian including) were prepared and submitted to the Customs Service. The training undergoes an internal approval at the Customs Service at the moment. A round table for importers and exporters was organized on 1 February 2013 to clarify the HCFC quota system. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche) | Multi-year | ASP | ASP | PHA | 63 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-03-01 |  |  | 134000 | 0 | 134000 | 125000 | 93.28% | 9000 | 0 | 9000 | 17420 | 0 | 16250 | 1170 | 0 | The list of planned activities for 2012: - Joint meeting of ozone and customs officers meeting - iPIC - Training manual and awareness material Progress: Customs Enforcement Training completed in 6 of the Pacific Islands Countries. The training assisted participating countries for instances on the monitoring, controlling and reporting of the Trade in ODS and ODS containing technologies and with particular attention to HCFC controls. Also included in this training was HS 2012 version, reducing risk of illegal trade and review of legislative framework to be consistent with WCO and use of the new model refrigerant identifiers. Completion of the procurement of Equipment for the RAC servicing sector and for all 12 countries. Agreement was met for countries for the approach to national training and in scheduling. | Customs enforcement training in Tuvalu. Agreement for the delivery of training on Micronesia (April 21-24) 2013. Receipt of equipment for the training in the RAC sector. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Multi-year | ASP | BAH | PHA | 68 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 15600 | 0 | 0 | 15600 | 0 | Project approved in November 2012. | UNEP coordinated 2 preparatory meetings with NOU and UNIDO to prepare the detailed work-plan of the HPMP of Bahrain during the 1st quarter of 2013. Country contract planned to be signed by May 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BDI | PHA | 65 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2013-11-01 |  |  | 45000 | 0 | 45000 | 25000 | 55.56% | 20000 | 15000 | 20000 | 5850 | 0 | 3250 | 2600 | 1950 | SSFA signed and 1st disbursement made in March 2012. SSFA valid upto Feb. 2014. |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BEN | PHA | 63 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 | 2013-03-01 |  |  | 85000 | 0 | 85000 | 56314 | 66.25% | 28686 | 25000 | 28686 | 11050 | 0 | 7320.82 | 3729.18 | 3250 | The NOU conducted training activities for Custom Officer and progressing well with implementation of HPMP activities | The country trained 40 customs officers and 20 refrigeration technician trainers. The NOU conducted a national meeting of Refrigeration Association to plan for implementation of certification programme. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | BGD | PHA | 65 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 230000 | 0 | 230000 | 0 | 0% | 230000 | 0 | 230000 | 29900 | 0 | 0 | 29900 | 0 | The list of planned activities for 2012: Training of refrigeration technicians on good practice - Organization of train-the-trainer workshop. Customs training and strengthening enforcement capacity - Procurement of equipment - Local training for customs. Awareness and information outreach targeted at HCFC consumers and strengthening HCFC servicing industry associations - Publication and promotional materials (printing and distribution) Progress: The agreement is not reported signed because the Government is taking some time to get internal clearance from the Ministry of Economic and Development. UNEP is in constant touch with the MoE and is expecting to have the agreement signed in May 2013. Mission to the country were conducted by UNEP staff member in March 2012 wherein HPMP plan was discussed and agreed. | UNEP is following up the signing of the agreement and it is expected to be signed by May 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2013-12-01 |  |  | 18200 | 0 | 18200 | 6155 | 33.82% | 12045 | 5000 | 12045 | 2366 | 0 | 800.15 | 1565.85 | 650 | Funds for first tranche programmed. 2012 annual operating and procurement plans have been prepared by the NOU with the guidance of the CAP Team. SSFA for training technicians during 2012 is signed. First disbursement issued. Two workshops on Good Practices about Alternatives Refrigerant delivered, 30 participants attended. Mission completed Aug 2012 to meet new authorities and agreed on further steps. HPMP launched including mass media coverage carried out in Sept 2012. HCFC Quotas were determined through consultation process between NOU and importers. | SSFA for funding Customs Training Workshops is drafted and being cleared by the Government. The NOU efforts were focused on establishing HCFC quotas with importers. These are very time demanding activities and constitute an important step to comply with HCFC phase-out goals. General elections took place in first quarter of 2012 and new authorities were briefed about the Montreal Protocol agenda during third quarter. Launching of HPMP under new administration took place in September 2012. Agreement is under signature awaiting official delegation of authority from the Permanent Secretary to the Director of the Department of Environmental Health Services of the Ministry of Housing and Environment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-12-01 | 2013-11-01 |  |  | 100000 | 0 | 100000 | 35934 | 35.93% | 64066 | 46000 | 64066 | 13000 | 0 | 4671.42 | 8328.58 | 5980 | The agreement was signed and initial disbursement of funds made in May 2012. The list of planned activities for 2012: HCFC Phase-out Policy and Enforcement - Procurement of equipment - Train-the-trainers workshops for enforcement officers, Information Exchange and Advocacy programmes - Design information exchange and advocacy programme - Research and Analyses. Servicing technician training and certification programme - Organization of train-the-trainer workshop of technicians - Production of training documents and materials. Progress: 3 Customs/Enforcement officers training programme was organized. ToT was organized for RAC sector. Stakeholders’ Workshop was organized. Public service announcement and poster have been completed since project approval. Developed training curriculum for vocational training schools and certification system for RAC technicians. New models of refrigerant identifiers were procured on December 2012. | UNEP purchased and distributed 3 units of RAC equipment in Feb 2013. UNEP is following up preparation for 2nd tranche request for 70th ExCom. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2013-12-01 | 2013-12-01 |  |  | 120000 | 0 | 120000 | 111430 | 92.86% | 8570 | 4000 | 8570 | 15600 | 0 | 14485.9 | 1114.1 | 520 | Refrigeration training equipment purchased and refrigeration training of trainers held in April 2012. Customs training was conducted for 30 Officers. Second payment was made in Nov 2012 |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | BRU | PHA | 66 | TAS | 12 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2014-04-01 |  |  | 123000 | 0 | 123000 | 31144 | 25.32% | 91856 | 56678 | 91856 | 15990 | 0 | 4048.72 | 11941.28 | 7368.14 | The agreement was signed and initial disbursement of funds made in August 2012. The list of planned activities for 2012: Training of enforcement officers - Procurement of equipment - Local training for enforcement officers Training of RAC technician on good practice - Organization of train-the-trainer workshop. Progress: The train-the-trainer workshop was organized for enforcement officers during 18-20 Sep 12, ten trainees from RCED and three from DOEPR attended his workshop. The train-the-trainer workshop was organized for refrigeration technicians during 8-11 Oct 12 at Jefri Bolkiah College of Engineering. New models of refrigerant identifiers were procured on December 2012 | The remaining training for enforcement and servicing sector are being planned and prepared in details for implementation. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2015-12-01 | 2015-12-01 |  |  | 80000 | 0 | 80000 | 30000 | 37.5% | 50000 | 50000 | 50000 | 10400 | 0 | 3900 | 6500 | 6500 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance by CAP Team. NOU began fund-raising in order to obtain additional funds for the HPMP implementation. Examinations for technicians certification were established in 2012 by National Refrigeration Association (ARACT). Customs Training Refreshing Workshop were held in Oct. 2012, 43 participants attended. To better address specific needs, training was done at 3 hierarchical levels of the Enforcement Officers, 60 participants attended. HCFC Quotas were determined through consultation process between NOU and importers. Two RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. | 4 training workshops for customs officials took place in Jan-Feb 2013. The Cabinet approved the policy directive and amendments to the Pollution Regulations of Belize which cover ozone layer depletion. Importers of ODS and RAC equipment have been sensitized. The HCFC quota system is in place as of 1 Jan 2013. The import/export of HCFC-based equipment has been added to the licensing system. Continuous training workshops for middle and front-line enforcement personnel during the first quarter 2013. (a) To draft 2012 operational and procurement plan; (b) To advise NOU on co-funding options; (c) To provide technical advice to National Refrigeration Association (ARACT) on certification; (d) Organize and deliver customs training workshop; (e) To provide policy guidance on HCFC quotas. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CAF | PHA | 64 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 75000 | 0 | 75000 | 45000 | 60% | 30000 | 25027 | 30000 | 9750 | 0 | 5850 | 3900 | 3253.51 | First payment sent in May 2012. The country conducted training of refrigeration technicians and custom officers. | The agreement was signed and first payment was made in May 2012. The agreement expires in April 2014. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CBI | PHA | 64 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 44000 | 0 | 44000 | 6308 | 14.34% | 37692 | 15000 | 37692 | 5720 | 0 | 820.04 | 4899.96 | 1950 | The country has conducted training of refrigeration technicians and 30 custom officers. | SSFA was signed and first payment made in March 2012. SSFA expires in January 2014. Country to submit reports for the first payment and to request for the second payment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 | 2013-06-01 |  |  | 100000 | 0 | 100000 | 95000 | 95% | 5000 | 0 | 5000 | 13000 | 0 | 12350 | 650 | 0 | The final payment was made in Oct 2012. The country conducted several trainings of refrigeration technicians | Country trained 50 refrigeration technicians and 25 customs officers. A few toolkits were procured and distributed to refrigeration technicians and to 3 repair workshops. Refrigeration Association was assisted to conduct their meeting where they planned on how to assist the NOU in conducting trainings and monitoring activities. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | TAS | 175 | A | I |  | 1.9 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 | 2013-03-01 |  |  | 153217 | 0 | 153217 | 0 | 0% | 153217 | 0 | 153217 | 19918 | 0 | 0 | 19918 | 0 | Consultations were concluded and final draft legislation was presented to main institutional stakeholders before submission to interministerial commission for approval. 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. Terms of reference were drafted by NOU for the implementation of the control system that will support enforcement of new legislation. In spite of some progress achieved, total disbursement rate was less than 20%. Consequently, 2nd tranche was not submitted in 2012. | HCFC quota system approved. SSFA has been cleared by Government and UNEP, pending signature. (a) The NOU efforts were focused on approving legislation to establish and enforce the HCFC quota system. These are very time demanding activities and constitute an important step to comply with HCFC phase-out goals. (b) SSFA signed by UNEP and the Government on May 2013. Disbursements will address training of 100 customs officers and other stakeholders during 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Cook Islands) | Multi-Year | ASP | CKI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-02-01 |  |  | 49250 | 0 | 49250 | 18875 | 38.32% | 30375 | 18375 | 30375 | 6403 | 0 | 2453.9416 | 3949.0584 | 2388.9365 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: The country organized customs training programme on 29 November – 1 December 2011 participated by 17 officers. Refrigerant identifiers provided. The procurement of equipment for the RAC servicing was done in December 2012 and training planned for August of 2013. Country has established ODS licensing and quota systems wherein it is functioning well. | The remaining training for enforcement and servicing sector is being planned and prepared in details for implementation. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | COI | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 | 2013-07-01 |  |  | 44000 | 0 | 44000 | 41950 | 95.34% | 2050 | 0 | 2050 | 5720 | 0 | 5453.5 | 266.5 | 0 | The fist payment was made in June 2012. The project is ongoing satisfactorily. | SSFA was signed and first payment made in April 2012. SSFA expires in April 2014. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 | 2013-10-01 |  |  | 50000 | 0 | 50000 | 44900 | 89.8% | 5100 | 5100 | 5100 | 6500 | 0 | 5837 | 663 | 663 | SSFA disbursements were carried out through UNDP Colombia. Progress Report and Annual Implementation Plan submitted to the 66 ExCom in order to request for the second tranche of funds. Five portable ODSs and blends identifiers purchased and delivered. Updated Custom Train of Trainers programme relaunched. Seven workshops were held to train Customs Officers and 167 participants attended. Seven workshops were held to train Refrigerant distributors and 72 participants attended. | HCFC quota system is in progress. Imports and production of HCFC-based domestic refrigerators have been banned. (a) Organize and deliver customs training workshop; (b) Procure equipment required for the customs; c) Organize and deliver training workshops for refrigerant distributors; (d) Prepare progress report; (e) In consultation with the lead agency prepare annual implementation plan for the second tranche; (f) Submit second tranche request; (g) Second tranche approval. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | COL | PHA | 66 | TAS | 80 | A | I |  | 1.5 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2014-04-01 |  |  | 50000 | 0 | 50000 | 4316 | 8.632% | 45684 | 41375 | 45684 | 6500 | 0 | 561.08 | 5938.92 | 5378.75 | SSFA signed in Dec. 2012. | First disbursement issued through UNDP Colombia. The NOU and Customs are collecting data on ODS trade across the country through monitoring the local ODS suppliers in order to prevent ODS illegal trade. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | TAS | 517 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-07-01 | 2013-07-01 |  |  | 1579000 | 0 | 1579000 | 309283 | 19.59% | 1269717 | 0 | 1269717 | 176703 | 0 | 34611.2945 | 142091.7055 | 0 | The agreement was signed on August 2012 and initial disbursement was made on September 2012. The list of planned activities for 2012: - Develop and Enforce the Relevant Policies and Regulations - Qualification Certificate System for Servicing Workshop - Qualification Certification System for Servicing Technicians - Formulate Standards/codes - Procure and Distribute Equipment - Training of Technicians - Policy Enforcement/Inspection, and Information System - Reward and Penalty - Pilot City - Outreach. Progress: For the implementation of the approved refrigeration servicing sector HPMP and the three enabling components, i.e. Capacity-building of national and local authorities, strengthening the HCFC import/export control, and the outreach and communication strategy, FECO and UNEP/Japan organized meetings in April 2012 and September 2012, with participation of the industry associations and national experts to discuss the scope of the work as well as budget allocation among various activities. During the year 2012, the development process for the relevant industry servicing standards and codes have been initiated in accordance with the activities plan under the HPMP. FECO/MEP organized consultation meetings with UNEP, CRAA and CHEAA to prioritize the most needed industrial codes or standards in the servicing sector, and developed relevant TORs for the organization of the development work in both RAC and ICR sector. The national stakeholders’ consultation workshop was organized jointly by FECO/MEP and UNEP/Japan during 19-20 September 2012 to review, discussing the implementation plan. The project proposal and action plan was further reviewed and discussed with national consultation workshop during 19-20 September 2012. The project contract between FECO and Shenzhen was by Nov 2012. During the launching meeting of HCFC Phase-out Management Plans in December 2012, a coordination meeting on the implementation of strategy on capacity-building of national and local authorities was held with participation of the Ozone officers from Local EPBs. Training Workshop 1: The first training workshop had been held in Ningbo City, Zhejiang Province during 24-26 April 2012. The workshop focused on strengthening the enforcement capacity of 70 local customs. Training Workshop 2: The second training workshop was held in Hangzhou City where most of HCFCs exporters were located during 1-3 August 2012. The workshop focused on training of the 95 importers and exporters on China’s HCFC import/export management system. FECO and its partner, Center for Environmental Education & Communications of Ministry of Environmental Protection (CEEC) who was contracted by FECO following evaluation of all options, organized the youth video competition among youth under 25 years old across the nation, and organized the ozone day celebration. | Under another system, the servicing technicians are required to have the compulsory certificate to be qualified to work in the servicing sector, one of the legally defined specialized sectors due to the nature of the safety concerns. FECO/MEP with assistance of UNEP, has already conducted desk study on these two systems, a feasibility study would be organized in 2013. The train the trainer approach will be adopted for the training on good practices including the recovery and recycling. Two national training centres and 10 regional training centres would be established under the HPMP. The participants for the train-the-trainer workshop will be selected from the manufacturing industry as well as the existing vocational or technical Institutes. FECO/MEP will select one city to establish a national training centre first in 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan(stage I, second tranche) (refrigeration servicing sector including enabling programme) | Multi-year | ASP | CPR | PHA | 68 | TAS | 528 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 598000 | 0 | 598000 | 0 | 0% | 598000 | 0 | 598000 | 66921 | 0 | 0 | 66921 | 0 | Newly approved project. The agreement has been drafted for country's review. | The amendment to the PCA is being finalized in consultation with the Government for agreement. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DJI | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 | 2016-04-01 |  |  | 81000 | 0 | 81000 | 50000 | 61.73% | 31000 | 26000 | 31000 | 10530 | 0 | 6500 | 4030 | 3380 | The first payment was made in August 2012. The project is ongoing satisfactorily | Country trained 20 refrigeration technicians trainers and 25 customs officers. Refrigeration Association conducted inspection and monitoring visits to major suppliers, and conducted annual meeting to plan on how to assist the NOU implement some of the training activities and agree on the major repair workshops to benefit from the toolkit programme. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | DMI | PHA | 62 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 82250 | 0 | 82250 | 0 | 0% | 82250 | 60000 | 82250 | 10693 | 0 | 0 | 10693 | 7800.3647 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. HCFC Quotas were determined through consultation process between NOU and importers. Twelve Enforcement and Customs Officer participated in the ODSs control Training/Refreshing Workshop. Official mission carried out to encourage Government to adopt HCFC quotas and streamline projects implementation. | Special training for custom brokers in proper classification of ODS products and refrigerants conducted in Feb. 2013, 15 participants attended. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN. The activities in the HPMP are combined with the remaining TPMP activities which are foreseen for completion before end of 2013. In 2012, country spent remaining TPMP funds, while the HPMP funds are scheduled for disbursement during 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | DOM | PHA | 65 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 0 | 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. HPMP implementation launching workshop carried out in April 2012. HCFC quota system drafted. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. NOO, consultant and Customs officer attended Central America and Dominican Republic Training Workshop for National Ozone Units and Customs Authorities held in Nicaragua on December 2012. | SSFA cleared by Government, pending signature. 2013 work plan prepared. 2nd tranche request submitted to 69th ExCom Meeting. (a) The Agreement has been signed in April 2013; (b) A payment was released in May 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DRC | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 | 2013-03-01 |  |  | 95000 | 0 | 95000 | 85478 | 89.98% | 9522 | 5000 | 9522 | 12350 | 0 | 11112.14 | 1237.86 | 650 | The NOU organized one training for 40 refrigeration technicians on good refrigeration practices. |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | TAS | 28 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 | 2015-11-01 |  |  | 166500 | 0 | 166500 | 11304 | 6.789% | 155196 | 0 | 155196 | 5850 | 0 | 397.1676 | 5452.8324 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. SSFA between the Government and UNEP was drafted. | SSFA has been revised and cleared by the Government. Executive agreement to enforce the HCFC quota system is being sanctioned by Cabinet. (a) The Agreement is under signature as of May 2013 (b) The quota system was approved in April 2013 |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | EQG | PHA | 65 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2013-11-01 |  |  | 40000 | 0 | 40000 | 21985 | 54.96% | 18015 | 18014.8 | 18015 | 5200 | 0 | 2858.05 | 2341.95 | 2341.924 | NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tools and equipment under the HPMP programme. |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ERI | PHA | 67 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the absence of Ozone Officer. The Government is in the process of appointing new Ozone Officer to proceeding with implementation of activities | The Government has not yet appointed a new Ozone Officer. CAP planning a Joint mission with UNIDO to discuss with the Government on how to proceed with the implementation of activities. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ETH | PHA | 68 | TAS | 21 | A | I |  | 0.3 | 0 | 0 | 0 | 2012-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the change of Ozone Office from Meteorological Department to Environment Protection Agency. New Ozone Officer has been appointed and CAP is training the new officer to start implementation of HPMP activities |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | FIJ | PHA | 65 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2014-11-01 | 2014-11-01 |  |  | 47900 | 0 | 47900 | 25000 | 52.19% | 22900 | 22900 | 22900 | 6227 | 0 | 3250 | 2977 | 2977 | The agreement was signed in September 2012. The list of planned activities for 2012: Training of enforcement officers - Procurement of equipment - Local organization of Train-the-Trainer workshop. Training of RAC technician on good practice - Organization of train-the-trainer workshop, Information, education, and communication - Design and production of awareness materials. Progress: collection of feedback from technicians and enforcement officers on the training needs, to get prepared for the update of the training materials. The country also organized outreach and awareness activities for the HCFC phaseout during the 25th Anniversary celebration on the International Ozone Day. The train-the-trainer workshop is planned to be organized in May 2013, and the enforcement training workshop will be organized in June 2013. |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Micronesia) | Multi-Year | ASP | FSM | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-09-01 | 2015-03-01 | 2015-02-01 |  |  | 53875 | 0 | 53875 | 26068 | 48.39% | 27807 | 17200 | 27807 | 7004 | 0 | 3388.961 | 3615.039 | 2236.0798 | The agreement was signed in April 2012 and initial disbursement was made in May 2012: The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training Progress: Due to changes in the NOO, required processing at national level took some time. This resulting in delays in the documentation preparation processes. The agreement was signed in April 2012 and initial disbursement was made on May 2012. Equipment was procured in December 2012. Training programme for Customs officers was organized in April 2013. | Shipment of the RAC training equipment processed. Customs training to be delivered April 21-24, 2013 |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 85000 | 90000 | 11700 | 0 | 0 | 11700 | 11050 | The first payment was made in Jan 2012. The country conducted training workshop for 30 refrigeration technicians and 20 custom officers. | First payment made in January 2012 and SSFA still valid up to November 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 | 2013-11-01 |  |  | 25000 | 0 | 25000 | 10000 | 40% | 15000 | 10000 | 15000 | 3250 | 0 | 1300 | 1950 | 1300 | HPMP was launched and the country trained 55 Refrigeration technicians and 30 customs officers. ODS Regulations were submitted to the government for approval. | Country approved revised ODS Regulations and started preparations for hosting Network Meeting |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 | 2013-11-01 |  |  | 35000 | 0 | 35000 | 19293 | 55.12% | 15707 | 15004 | 15707 | 4550 | 0 | 2508.09 | 2041.91 | 1950.52 | The country conducted training of 30 refrigeration technicians and 20 custom officers.. The activities are ongoing satisfactorily. | SSFA was signed and first payment was made in March 2012. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GRN | PHA | 62 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 | 2013-12-01 |  |  | 105000 | 0 | 105000 | 19221 | 18.31% | 85779 | 55000 | 85779 | 13650 | 0 | 2498.73 | 11151.27 | 7150 | Annual plan agreed to and in alignment with the SSFA. HCFC Quota system approved. Import/Export licensing system electronic through a ASYCUDA World. 15 RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. Official mission conducted in November 2012 to support the workshop delivery. | 2013 annual work plan has been drafted. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN. HCFC quota system being implemented. (a) Review and update ODS legislation to include HCFCs quota system; (b) Organize and deliver training workshop for technicians; c) Provide policy and technical support targeted public awareness on alternatives to HCFCs; (d) Monitor and evaluate the implementation of activities by NOU. 2012 annual progress report is pending. UNEP is doing follow up to obtain progress and financial reports. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | GUA | PHA | 64 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2013-07-01 |  |  | 28250 | 0 | 28250 | 0 | 0% | 28250 | 0 | 28250 | 3673 | 0 | 0 | 3673 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Second tranche submitted to the 68 ExCom. HCFC quota system drafted. | (a) The Agreement has not been signed. It is expected to be signed during second half of 2013. UNEP is planning a bilateral meeting with NOO on the margins of the Network Meeting to be held in June 2013 to determine the dates for an official mission; (b) The main activity in 2012 was the establishment of the HCFC quota system, which did not require any disbursement. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | GUI | PHA | 66 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2014-04-01 |  |  | 85000 | 0 | 85000 | 55019 | 64.73% | 29981 | 25000 | 29981 | 11050 | 0 | 7152.47 | 3897.53 | 3250 | Project approved in November 2012. | SSFA was signed and first payment was made in July 2012. The country trained 35 refrigeration technicians and 20 customs officers. The NOU procured and distributed toolkits to technicians and repair workshops. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 | 2013-03-01 |  |  | 11000 | 0 | 11000 | 0 | 0% | 11000 | 9000 | 11000 | 1430 | 0 | 0 | 1430 | 1170 | New NOO joined the Ministry of Agriculture in February 2012. Implementation plan revised and approved by the government. A consultant from Trinidad & Tobago was hired to review curriculum of vocational training schools. HCFC Quota system approved. | 2013 annual work plan has been drafted. Consultant conducted country mission in Feb. 2013 to meet vocational schools and main stakeholders. HCFC quota system being implemented. An international consultant was hired in October 2012 to advise on RAC sector certification scheme and technicians training. The first mission by the consultant took place in February 2013, first payment was made in March 2013. Second mission is planned for July 2013. The activities will be completed as planned. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HAI | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | HPMP approved in Dec 2012. | Country mission and official launch already scheduled for second quarter of 2013. Work plan drafted, including: policy workshop, scheduling deliverables and stakeholders responsibilities. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2014-03-01 | 2014-03-01 |  |  | 75000 | 0 | 75000 | 38355 | 51.14% | 36645 | 0 | 36645 | 9750 | 0 | 4986.15 | 4763.85 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. HCFC quota system approved. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. 2 NOU officials attended Central America and Dominican Republic Training Workshop for National Ozone Units and Customs Authorities held in Nicaragua in December 2012. | 2013 annual work plan has been drafted. HCFC quota system being implemented. (a) In consultation with NOU prepare annual work and procurement plan; (b) Provide policy advice in establishment of a HCFC quota system; c) Provide policy and technical support in revision of national customs training curriculum to include HCFCs; (d) To monitor implementation progress. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (enabling activities) | Multi-year | ASP | IND | PHA | 66 | TAS | 443 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2013-04-01 | 2013-04-01 |  |  | 250000 | 0 | 250000 | 7112 | 2.845% | 242888 | 0 | 242888 | 30402 | 0 | 864.8761 | 29537.1239 | 0 | The agreement has been signed in May 2013 and initial disbursement is being processed. The list of planned activities for 2012: Policy & Enforcement Capacity-building - Preparation of Training Materials - Training of Trainers - Enforcement studies and campaigns. Progress: Consultation meeting organized in Bangkok on December 2012 participated by NOU, NACEN and UNEP to discuss the implementation of the HPMP project (enabling). Implementation plan from 2013 to 2015 was negotiated in consultation with the NOU since 2012 and was finalized only in 2013. This was also due to finalization of the HPMP plans with other Implementing Agency's. Disbursement of funds is expected to increase significantly in 2013. Activities that have been completed in 2012 includes: • 1 Technology and Policy Workshop on HCFC Phase out in India in Delhi • Finalization of Timeline for all outputs in UNEP component • Identification of national organizations to implement enforcement training. | HPMP launched on January 2013. Implementation Plan with NOU, NACEN and Vigyan Prasar finalized. SSFAs were formulated and in consultation with the Government for agreement. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | IND | PHA | 66 | TAS | 445 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-01 | 2013-04-01 |  |  | 180800 | 0 | 180800 | 0 | 0% | 180800 | 0 | 180800 | 21986 | 0 | 0 | 21986 | 0 | The agreement for this component is expected to be signed by May 2013. The list of planned activities for 2012: Awareness - RAC & refrigerant dealer half day awareness workshops - HCFC Awareness Campaign - Development of awareness materials. Progress: Consultation meeting organized in Bangkok on December 2012 participated by NOU, NACEN and UNEP to discuss the implementation of the HPMP project. Implementation plan from 2013 to 2015 was negotiated in consultation with the NOU since 2012 and was finalized only in 2013. This was also due to finalization of the HPMP plans with other Implementing Agency's. Disbursement of funds is expected to increase significantly in 2013. Activities that have been completed in 2012 includes: • 1 Awareness workshop for RAC and Refrigerant Dealers in Mumbai • Initiation of development of website • Finalization of Timeline for all outputs in UNEP component • Identification of national organization to support awareness component implementation | Awareness Workshop for RACSS completed on 4 in Mumbai |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 200 | A | I |  | 3.2 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2015-03-01 | 2015-02-01 |  |  | 262000 | 0 | 262000 | 3293 | 1.257% | 258707 | 0 | 258707 | 34060 | 0 | 428.09 | 33631.91 | 0 | The agreement has been signed on April 2012 and initial disbursement has been transferred. The list of planned activities for 2012: Training programme for servicing technicians and Customs officers - Organizing training of trainers(TOT) workshops for servicing technicians - Organizing TOT workshops for Customs officers Information Exchange and Advocacy Programmes - Conducting research and analysis to improve info exchange. Progress: A three days training workshop on Good Practices in Refrigeration & Air-conditioning Servicing Sector for trainers was conducted by UNEP in close consultation and cooperation with the National Ozone Unit and GIZ from 18th to 20th February 2013 in Karadj Instructor Training Centre & Technical and Vocational Researches .Trainers of provincial vocational training centers (34 trainers from twenty provinces of the country) attended in this programme. NOU will use the capacity of trained master trainers of the provincial vocational training centers to organize similar training programs in near future for the other technicians which will help the country in reducing the consumption of HCFCs in the servicing sector. | The remaining training for enabling component are being planned and prepared in details for implementation. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 115000 | 0 | 115000 | 0 | 0% | 115000 | 0 | 115000 | 14144 | 0 | 0 | 14144 | 0 | As all activities under HPMP of Iraq are supplementing the NPP activities and depend on completion/implementation of NPP activities, mainly for the servicing sector, the contract for the HPMP is delayed till reaching adequate percentage of the NPP resource utilization and progress of activities. However, work-plan is prepared in details and ready for start by 2013 | Draft country contract is under review by UNEP and country and will be signed by 1st half of 2013 |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-04-01 | 2014-04-01 |  |  | 250000 | 0 | 250000 | 85014 | 34.01% | 164986 | 60015 | 164986 | 30260 | 0 | 10290.0946 | 19969.9054 | 7264.2156 | The Country organized training workshop for 30 refrigeration technicians and 20 custom officers. | SSFA was signed and first payment was sent to the country in September, 2012. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 | 2013-07-01 |  |  | 20000 | 0 | 20000 | 9000 | 45% | 11000 | 11000 | 11000 | 2600 | 0 | 1170 | 1430 | 1430 | 2012 annual operating plan and the procurement plan were implemented by the NOU. SSFA signed and first disbursement released. 2013 HCFC quotas allocated to importers. | 2013 annual work plan has been drafted. Second disbursement released. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN. HCFC quota system being implemented. ODSs control Training/Refreshing Workshop was in March 2013, 10 Enforcement and Custom Officers attended. (a) Draft agreement; (b) Obtain clearance by UNEP and Country; c) Obtain agreement signature; (d) Develop guidelines to support HCFCs licensing and quota system including guidance for transport, handling and labeling; (e) Organize and deliver training workshop for customs and enforcement officers; (f) Monitor implementation of activities. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | ASP | KAM | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2019-12-01 | 2013-06-01 |  |  | 150000 | 0 | 150000 | 126974 | 84.65% | 23026 | 15789 | 23026 | 19500 | 0 | 16506.62 | 2993.38 | 2052.57 | The list of planned activities for 2012: - Training of enforcement officers - Training of RAC technician on good practice - Information, education, and communication - Project Management & Monitoring. Progress: UNEP six units of identifiers purchased and distributed to Cambodia in Dec 2012. The train-the-trainer workshop was organized for enforcement officers in August 2012, and followed with one training workshop for enforcement officers during 24-25 December 2012 at Sihanoukville. The train-the-trainer workshop was organized for refrigeration technicians during 2-5 October 2012, followed with a technician training workshop during 26-27 December 2012 at Sihanoukville. | UNEP purchased and distributed 3 units of RAC equipment to Cambodia in Feb 2013. A training workshop to enforcement officers was organized during 21-22 February 2013 at Bavet, Svai Rieng Province, and one training workshop to technicians was organized during 29-30 January 2013 in Phnom Penh. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Kiribati) | Multi-Year | ASP | KIR | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-02-01 |  |  | 53250 | 0 | 53250 | 35250 | 66.2% | 18000 | 6000 | 18000 | 6923 | 0 | 4582.831 | 2340.169 | 780.0563 | The agreement was signed in September 2011 and initial disbursement was made on October 2011. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training HCFC import quota system and allocation of quota for 2013 established and functioning well. New model of refrigerant identifier were procured and delivered on December 2012. Organized customs training programme on 23-25Jan 2013 participated by 19 officers, partnered with OCO. The technicians training is being planned and will be organized by middle of the year. | Shipment of the RAC training equipment processed. Customs enforcement training delivered in January 23-25 2013 and participated by 19 officers. This training provided the skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | Multi-Year | ASP | KUW | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2014-04-01 |  |  | 277000 | 0 | 277000 | 0 | 0% | 277000 | 0 | 277000 | 33126 | 0 | 0 | 33126 | 0 | Country visited by UNEP and UNIDO to work-out detailed implementation plan coordination meetings with respective authorities concluded in forming 3 national teams for the codes/standards update, establishing certification scheme and control of ODS trade * National Ozone Committee concluded draft update legislation for initiating HCFC Quota by Jan 2013 and control trade of HCFC and all its blends |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | KYR | PHA | 63 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-12-01 | 2014-12-01 |  |  | 31680 | 0 | 31680 | 30000 | 94.7% | 1680 | 1680 | 1680 | 4118 | 0 | 3899.6212 | 218.3788 | 218.3788 | The licensing and quota system to control HCFCs is operational. There were held nine training workshops - one additional for customs officers (the northern and southern regions) and two for the specialists of the refrigeration sector. There were prepared new edition of the State Program on phase-out ozone-depleting substances in the Kyrgyz Republic for the period 2011-2025 years. The NOU continues developing the technical guide book for the certification of technicians in the refrigeration and air conditioning sectors. The dissemination of logbooks was initiated during the monitoring of servicing shops. | The regulatory act was developed to set a quota for HCFCs for the year of 2013. It should be approved by the Ministry of Economy and the State Agency on Environment Protection. The NOU participated in the working group on Customs Union. The NOU officially informed the Ministry of Economy and the Customs authorities about the specific issues in controlling ODSs. The new training materials for workshops in the refrigeration sector are under development based on new materials which are received during the network and thematic meetings. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | LAO | PHA | 63 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-03-01 |  |  | 113625 | 0 | 113625 | 41062 | 36.14% | 72563 | 46282 | 72563 | 14771 | 0 | 5337.9697 | 9433.0303 | 6016.5582 | The agreement was signed and initial disbursement was made on May 2012. The list of planned activities for 2012: Policy review and amendments of regulations - Initial meeting with Working Group, Brainstorming workshops, Legal requirement finalization workshop. Training of enforcement officers - Procurement of equipment Training of RAC technician on good practice - Procurement of equipment - Organization of train-the-trainer workshop. Progress: All meetings were organized for policy review and amendments in 2012. Procured refrigerant identifiers and distributed in Dec 2012. The train-the-trainer workshop was organized for refrigeration technicians on 26-30 November 2012 wherein 29 trainees from five institutes attended this workshop. The train-the-trainer workshop for enforcement was organized during 14-16 January 2013 wherein 58 enforcement officers from five institutes attended this workshop. | The train-the-trainer workshop was organized for enforcement officers during 14-16 January 2013. 58 trainees from five institutes attended this workshop. UNEP purchased and distributed 3 units of RAC equipment to Lao PDR in Feb 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 | 2013-12-01 |  |  | 70000 | 0 | 70000 | 51362 | 73.37% | 18638 | 5000 | 18638 | 9100 | 0 | 6677.06 | 2422.94 | 650 | The second payment was made in July 2012. The NOU conducted training of 20 Custom and 30 Refrigeration technicians. |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Marshall Islands) | Multi-year | ASP | MAS | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-02-01 |  |  | 54000 | 0 | 54000 | 32546 | 60.27% | 21454 | 13977 | 21454 | 7020 | 0 | 4230.98 | 2789.02 | 1817.01 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on November 2012 participated by 14 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012. New NOO appointed in September of 2012 was trained in the HPMP project implementation. | Shipment of the RAC training equipment processed. Agreement reached on the scheduling of the training of RAC servicing technicians. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 60 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2019-12-01 | 2013-03-01 |  |  | 355940 | 0 | 355940 | 183738 | 51.62% | 172202 | 0 | 172202 | 46272 | 0 | 23885.8368 | 22386.1632 | 0 | The list of planned activities for 2012: - HCFCs phase-out Policies and Enforcement - Plan for Gradual Reduction of HCFC - Enhanced awareness and outreach. Progress: New models of refrigerant identifiers were procured and delivered on December 2012.Second tranche request submitted for 69th ExCom, Enforcement Training conducted in March 2012 and Media Workshop organized in February 2012. | UNEP purchased and distributed 10 units of RAC equipment in Feb 2013. Second tranche request submitted for 69th ExCom, Enforcement Training conducted in March, Media Workshop in February |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MLI | PHA | 63 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 | 2013-03-01 |  |  | 65000 | 0 | 65000 | 37830 | 58.2% | 27170 | 25000 | 27170 | 8450 | 0 | 4917.9 | 3532.1 | 3250 | The country continued to enforce regulations for importation of ODS. The SSFA has since expired and was revised. | The SSFA was sent to FMO for payment |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 50000 | 83.33% | 10000 | 0 | 10000 | 7800 | 0 | 6500 | 1300 | 0 | NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tools and equipment under the HPMP programme. | NOU conducted training workshop for 30 refrigeration technicians |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 | 2013-03-01 |  |  | 65000 | 0 | 65000 | 50500 | 77.69% | 14500 | 9500 | 14500 | 8450 | 0 | 6565 | 1885 | 1235 | The agreement was signed in August 2011 and initial disbursement was made on October 2011. The list of planned activities for 2012: Strengthening of HCFC control policies/regulations - Introduction licensing/certification system for refrigeration/air conditioning technicians - National stakeholders consultation meeting Capability building for enforcement and customs officers - Training for Customs officers(Train-The-Trainers). Progress: Enforced quota for HCFC since 2011 according to the Air law of Mongolia wherein amended in 2012. According to the Article 25.2 of the Amendment of Air law of Mongolia, quantities/quotas of HCFC and request of its alternatives, that contained equipment for ODS importing and refrigeration servicing companies was approved by Decree of Minister of Nature, Environment & Tourism for 2011 and 2012 respectively. • The proposed HCFCs were included in the amendment of the Government Resolution#95, 2007: ‘’List of the toxic and hazardous chemicals restricted and banned for using in Mongolia’’ which was approved by Government Resoultion#145, dated on 01 December 2012.Customs training was organized during 25-27 June 2012 at the Ulaanbaatar with 25 trained. 2 training workshops for customs officers by trained trainers were conducted at the customs points during July 2012 to December 2012. A National Training curriculum involving vocational schools for the technician training was developed in English and Mongolian. The curriculum was delivered to ‘’Master Potentials‘’ National training center for technician training established with inauguration ceremony on 14 February 2012. The National training center conducted 5 training workshops during June-December 2012 with 102 trained technicians. One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Quota for HCFC-22 in 2013 was approved by Ministerial Decree and distributed to the registered importers in 02 January 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MOZ | PHA | 66 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2014-04-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | SSFA was signed and the NOU launched the HPMP implementation. List of equipment and tool kits agreed with IA's. Action Plan for implementation was established | The country preparing for the National train the trainers workshops for customs officer and refrigeration technicians |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | MYA | PHA | 68 | TAS | 14 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 159000 | 0 | 159000 | 0 | 0% | 159000 | 0 | 159000 | 20670 | 0 | 0 | 20670 | 0 | The agreement for transfer funding can’t be processed as per the ExCom decision 68/31. UNEP is following up with the country regularly on the approval of the Ozone Order. One unit of new model of refrigerant identifier were procured and delivered on December 2012. This project is newly approved in December 2012. | UNEP purchased and distributed 1 unit of RAC equipment in Feb 2013. The funds is being programming. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Nauru) | Multi-Year | ASP | NAU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-02-01 |  |  | 45625 | 0 | 45625 | 17625 | 38.63% | 28000 | 16000 | 28000 | 5931 | 0 | 2291.1534 | 3639.8466 | 2079.9123 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: One unit of new model of refrigerant identifier were procured and delivered on December 2012.The training programme is being planned and expected to be organized by middle of 2013. | The RAC training is being planned to be organized. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | NEP | PHA | 66 | TAS | 29 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2015-04-01 | 2015-04-01 |  |  | 63000 | 0 | 63000 | 15530 | 24.65% | 47470 | 37700 | 47470 | 8190 | 0 | 2018.9 | 6171.1 | 4901 | The SSFA has been signed and initial payment disbursed in December 2012. The list of planned activities for 2012: HCFC Phase-out Policies (HPP) - Procurement of equipment Enhanced awareness and outreach - Stakeholder Engagement/Workshops - Development of awareness materials such as posters, flyers Promote good practices in the refrigeration and air conditioning installation and servicing sector - Train-the-trainers workshop. Progress: The HPMP project was launched and Stakeholders’ workshop was organized in December 2012. One Customs poster has also been developed and distributed. One Train-the-Trainers (TTT) workshop with 33 master trainers. Technicians’ workshop was organized in December 2012. A survey on HCFC equipment in the hotel industry in Kathmandu has been completed in collaboration with the Hotel Association of Nepal. | Enforcement workshop planned for May or June |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | TAS | 27 | A | I |  | 1 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 | 2016-04-01 |  |  | 100000 | 0 | 100000 | 60000 | 60% | 40000 | 35000 | 40000 | 13000 | 0 | 7800 | 5200 | 4550 | First payment was sent in July 2012. The country conducted training workshop for 30 refrigeration technicians and 20 Custom officers |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | NIC | PHA | 66 | TAS | 26 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 |  | 2015-04-01 | 2015-04-01 |  |  | 38000 | 0 | 38000 | 0 | 0% | 38000 | 0 | 38000 | 4940 | 0 | 0 | 4940 | 0 | NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. HCFC Quota system approved in Dec 2012 by Ministerial Resolution. Capacity of National Refrigeration Technicians Association was built through one-day symposium on low-GWP alternative technologies. | 2013 annual work plan has been drafted. HCFC quota system being implemented. SSFA signed by UNEP in April 2013. (a) Draft agreement; (b) Obtain clearance by UNEP and Country; c) Obtain agreement signature; (d) Policy support to approve HCFCs quota system; (e) Organize and deliver training workshop for customs and refrigeration servicing technicians; (f) Monitor implementation of activities. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Niue) | Multi-year | ASP | NIU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-02-01 |  |  | 45625 | 0 | 45625 | 23625 | 51.78% | 22000 | 10000 | 22000 | 5931 | 0 | 3071.1205 | 2859.8795 | 1299.9452 | The agreement was signed and initial disbursement was made on October 2011. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training Progress: The import/export licensing system of ODS to include HCFC has been put in place and endorsed by Niue’s Cabinet Ministers on 27 August 2010. A meeting with Customs Organisation, technicians and other relevant national stakeholders were organized to develop the quota system for HCFCs. New model of refrigerant identifier were procured and delivered on December 2012. The customs training programme is planned to be organized by July 2013. Refrigerant identifier received in January 2013. Training of technicians planned in August of 2013. International trainers for both the customs and technician trainer contracted. | Shipment of the RAC training equipment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | TAS | 22 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 |  | 2015-11-01 | 2015-11-01 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 65000 | 8450 | 0 | 0 | 8450 | 0 | During the reporting period, the necessary assistance have been provided to establish the PMU and its agreed teamwork and national ozone committee (NOC) to supervise the implementation of the MP related activities as well as the implementation of the HPMP. the PMU with its technical teams is now operational. the preparation of the e-licensing system for the trade on ODSs is progressing according to the plan. necessary technical support was provided to the local IT team for integrating the system into the Ministry's under development system. it is expected to complete the online system by Q4 2013. the bylaws for the implementation of the unified GCC regulations on ODSs have been drafted with assistance of UNEP and subject for final adoption. Follow up with NOU regarding their signature of the SSFA agreement for the implementation of the first stage under HPMP that was finalized and signed by UNEP during early 2012 and submitted for government signature | The SSFA agreement for the implementation of the first stage under HPMP was finalized and signed in Feb. 2013. Assistance was provided to finalize the ToRs for the national ozone committee (NOC) to supervise the implementation of the MP related activities as well as the implementation of the HPMP. the 1st meeting of the NOC was held on 5 March 2013 with UNEP and UNIDO participation. the preparation of the e-licensing system for the trade on ODSs is progressing according to the plan and expected to be completed by Q4. the bylaws for the implementation of the unified GCC regulations on ODSs are at final stage for adoption. International experts will be recruited to work with PMU to finalize the update of curricula and expedite the enforcement of the certification scheme for RAC technicians during Q3. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 | 2013-12-01 |  |  | 200000 | 0 | 200000 | 102956 | 51.48% | 97044 | 68500 | 97044 | 26000 | 0 | 13384.28 | 12615.72 | 8905 | The agreement was signed on May 2011 and initial disbursement was made on June 2011. The list of planned activities for 2012: Policy & Enforcement Capacity-building - Training for Customs officers - Procurement of equipment National Project for Training Service Technicians - Training at the provincial levels - Production of material to promote standards/ Code of Good Practices (in Urdu only) Awareness - Stakeholder awareness workshops at the provincial level Progress: The training and a side meeting with senior management of the Pakistan Customs were held at Old Customs House in Karachi (where 70% of Customs Officers in the country are posted) on September 2012 wherein 60 officers participated at the opening and 35 officers were trained from Customs and other enforcement departments including: Directorate General of Training and Research(DGTR) Karachi, DGTR (Customs), DGTR Lahore, Customs Control Appraisement Karachi, HQ Frontier Corps KPK Peshawar, General of Intelligence & Investigation-FBR, Customs Control Hyderabad, Customs Control Gwadar, DGTR (Customs), Islamabad, MCC Appraisement Karachi, Karachi International Container Terminal, Model Customs Collectorate of Preventive of Karachi and the Ozone Cell of the Ministry of Climate Change. TTT & Technicians Training was organized on September 2012, the training has been conducted in Karachi with 29 trainers and 19 technicians. New models of refrigerant identifiers were procured and delivered on December 2012. Conducted Awareness Workshop for government of Punjab and industry in Lahore on February 2013; Ozone Cell participated in national annual HVACR Exhibition. | UNEP purchased and distributed 4 units of RAC equipment in Feb 2013. Conducted Awareness Workshop for government of Punjab and industry in Lahore on 13 February; Ozone Cell participated in national annual HVACR Exhibition |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | PAN | PHA | 65 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2014-01-01 |  |  | 35000 | 0 | 35000 | 1840 | 5.257% | 33160 | 5000 | 33160 | 4550 | 0 | 239.2 | 4310.8 | 650 | 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. Consultation meetings about ODS legislation were held with importers of gases and equipment . HCFC quota were allocated. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. | 2013 annual work plan has been drafted. HCFC quota system being implemented. ODS control and Montreal Protocol Refreshing Workshop was held in March 2013, 21 Enforcement Officers participated. The Government of Panama requested UNEP's direct administration of funds to expedite the process and improve monitoring of the implementation instead of signing an agreement which is ongoing as planned. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | TAS | 28 | A | I |  | 0.9 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2013-12-01 |  |  | 146500 | 0 | 146500 | 50027 | 34.15% | 96473 | 52000 | 96473 | 19045 | 0 | 6503.51 | 12541.49 | 6760 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Agreement documents coordinated between the Government, UNDP and UNEP. SSFA signed in March 2012. First disbursement in April 2012. HCFC Quota system approved. Electronic Import/Export licensing system through SOFIA online system. Five workshops on Good Practices were held in 2012, 101 refrigeration technicians attended. 214 RAC technicians took the certification exam and 147 were duly certified. | 2013 annual work plan has been drafted. HCFC quota system being implemented. ODS control and Montreal Protocol Refreshing Workshop was held in the first quarter of 2013, 37 Enforcement Officers participated. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation to include HCFCs; (g) Customs Officers training; (h) Continuation with certification of RAC technicians . |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 0 | HPMP approved in Dec 2012. | Country mission and official launch already scheduled for second quarter of 2013. Annual work plan drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PHI | PHA | 68 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 207000 | 0 | 207000 | 0 | 0% | 207000 | 0 | 207000 | 26910 | 0 | 0 | 26910 | 0 | The draft agreement is being reviewed and for clearance by the Government in order to proceed for signing. It is expected to be signed by May 2013. | The agreement is being drafted and in consultation with the Government for agreement. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 | 2013-03-01 |  |  | 45000 | 0 | 45000 | 23595 | 52.43% | 21405 | 16405 | 21405 | 5850 | 0 | 3067.35 | 2782.65 | 2132.65 | Survey for 2011 data was completed. The country organized training workshops for 35 refrigeration technicians and 30 custom officers |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | TAS | 17 | A | I |  | 1.3 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 105000 | 0 | 105000 | 0 | 0% | 105000 | 0 | 105000 | 13650 | 0 | 0 | 13650 | 0 | ODS Officer of Qatar changed 3 times over the last 3 years resulting to delaying implementation of all projects. Early 2012 new ODS Officer nominated officially but no proper hand-over internally was arranged. UNEP and UNIDO made plan to re-establish the operation of the Ozone Unit in Qatar and build its capacity through several meetings and missions to quickly orient the new ODS Officer and other officials with MP and project implementation needs. 2 Orientation meetings and one national workshop arranged by UNEP during 2012. All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 | * UNEP organized training program in Qatar in April 2013 on the control and monitor of ODS. * UNEP and NOU started national study to assess A/C technologies and facilitate promoting long-term technologies *All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2013-07-01 |  |  | 42000 | 0 | 42000 | 22000 | 52.38% | 20000 | 15000 | 20000 | 5460 | 0 | 2860 | 2600 | 1950 | SSFA was signed and the NOU launched the HPMP implementation. List of equipment and tool kits agreed with IAs. Country trained 20 refrigeration experts and 15 customs officers as trainers. The NOU conducted National Refrigeration Association meeting to plan for effective implementation of HPMP activities including strengthening of certification programme | Country procured some tool kits and distributed to repair workshops and refrigeration experts |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Samoa) | Multi-Year | ASP | SAM | PHA | 63 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-02-01 |  |  | 76250 | 0 | 76250 | 50632 | 66.4% | 25618 | 15371 | 25618 | 9913 | 0 | 6582.492 | 3330.508 | 1998.3308 | The agreement was signed and initial disbursement was made on August 2012. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on December 2012 participated by 18 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. New NOO appointed in August of 2012, trained on the implementation of the HPMP project. New model of refrigerant identifier were procured and delivered on December 2012. Completion of the procurement of the RAC servicing training equipment | Shipment of the RAC training equipment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 233674 | 0 | 233674 | 0 | 0% | 233674 | 0 | 233674 | 28946 | 0 | 0 | 28946 | 0 | Project approved in November 2012. | HPMP project( approved at the 68th ExCom) was launched on 19 March 2013 in Jeddah- KSA. UNEP and UNIDO organized several consultation meetings during and at the margin of the workshop. PMU is being established and detailed work-plan for implementing the approved activities including the remaining activities of NPP 2nd tranche, is being finalized. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 56726 | 0 | 56726 | 0 | 0% | 56726 | 0 | 56726 | 7027 | 0 | 0 | 7027 | 0 | Project approved in November 2012. | HPMP launched in March 2013. UNEP and UNIDO organized the first consultation meeting for the foam sector during the launching workshop. detailed work-plan for the sector is being developed based on the inputs received |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | TAS | 30 | A | I |  | 1.2 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2014-11-01 | 2014-11-01 |  |  | 100000 | 0 | 100000 | 62290 | 62.29% | 37710 | 35000 | 37710 | 12887 | 0 | 8027.3123 | 4859.6877 | 4510.45 | Country conducted training workshops for 40 refrigeration technicians and 30 custom officers | SSFA was signed and second payment sent in March 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-11-01 | 2013-11-01 |  |  | 25000 | 0 | 25000 | 10000 | 40% | 15000 | 10000 | 15000 | 3250 | 0 | 1300 | 1950 | 1300 | NOU launched the HPMP implementation. List of equipment and tool kits agreed with IAs and procurement process started. Country trained 20 refrigeration experts and 15 customs officers as trainers. The NOU conducted National Refrigeration Association meeting to plan for effective implementation of HPMP activities including strengthening of certification programme | SSFA was signed and first payment made in April 2012. NOU trained 15 customs officers who are based on the boarders and distributed refrigerant identifiers. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Solomon Islands) | Multi-Year | ASP | SOI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-02-01 |  |  | 110250 | 0 | 110250 | 68739 | 62.35% | 41511 | 27818 | 41511 | 14333 | 0 | 8936.3817 | 5396.6183 | 3616.4662 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on August 2012 participated by 26 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. Two unit of new model of refrigerant identifier were procured and delivered on December 2012. Completion of procurement of RAC Servicing training equipment. | Shipment of the RAC training equipment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 | 2014-12-01 |  |  | 125000 | 0 | 125000 | 56293 | 45.03% | 68707 | 47103 | 68707 | 16250 | 0 | 7318.09 | 8931.91 | 6123.39 | The agreement was signed and initial disbursement was made on December 2011. The list of planned activities for 2012: Policy, Regulations & Enforcement - Customs Train-the-Trainers - Training Service Technicians - Development of technicians training curricula for RAC technicians. Awareness - Production of awareness materials. Progress: Training for the Sri Lanka Customs officers and other law enforcement authorities on WCO HS Codes 2012 was conducted on 29 - 30 March 2012 in Colombo. On 22 August 2012, the Cabinet of Ministers of the Government of Sri Lanka considered the Cabinet Paper No.12/1126/527/010-I and granted approval to control the import and export and production of virgin Hydrochlorofluorocarbons (HCFCs) and HCFC blends with effect from 1st of January 2013 and thereafter eventually phase out per HPMP. Import of used equipment working with HCFC is banned from 1 January 2013. Controller of Import & Export has issued circular on 2 November 2012. The Ministry of Environment is planning to ban import of HCFC-141 b from 1 January 2016, and equipment working with HCFC from 1 January 2018. Newspaper advertisements were published on 26th January 2012, requesting to submit proposals to develop training curricula. Ministry of Vocational Training & Skill development and National Apprentice & Industrial Training Authority would be supporting development of training curricula. A Steering Committee would be formed in 2013 for development of the curricula. The NOU will prepare a draft model curriculum by adding new material that is relevant to HCFC phaseout to be incorporated into the curricula used by Sri Lanka Technical Colleges and vocational Training Institutes. Train the Trainers workshop was organized by UNEP in March 2012 at Bangkok and two Master Trainers from Sri Lanka joined this workshop. These master trainers would continue to support the training activities for service technicians during HPMP implementation. A three day workshop was conducted in January/February 2012 in Anuradhapura District for Technical college students and staff and RAC Technicians on good refrigeration practices. For undertaking training activities, 3 Refrigerant Recovery equipment and Accessories were distributed to Technical College, Anuradapura, Technical College Batticaloa and Eastern Technical Institute, Batticaloa. A 3day workshop on ‘Good practices in Refrigeration’ was conducted from 21-23 February 2013 at College of Technology Jaffna. 85 Technicians in Jaffna peninsula (almost all the technicians currently employed) participated for this workshop. They highly praised with the opportunity that has been received after 30 years of civil war. NOU initiative to train technicians in destitute areas was highly commended by the Government Agent in Jaffna. A 2 day training program was conducted on 29- 30 March 2012 with the participation of nearly 70 enforcement officers from Sri Lanka Customs, Department of Import & Export Controller, Board of Investment and Ministry of Environment. One unit of HCFC identification equipment was distributed on 29 March 2012 to the Department of Sri Lanka Customs (Colombo Port). Two refrigerant identifiers procured by UNEP received in February 2013 will be distributed to Sri Lanka Customs to be utilized in newly opened Port in Hambantota and in Colombo International Airport. Awareness and information outreach activities on HPMP are being carried out on an ongoing basis. Given that 25th anniversary of signature of Montreal Protocol was celebrated in the year 2012, the Ozone Day was used as an important platform for creating awareness on ODS phase-out and specifically on HPMP project activities. In addition to this, leaflets on HPMP was produced in 3 official languages and distributed at the National Exhibition in February 2012. Dockets were also designed and distributed during the year 2012. To promote technology adoption, Sri Lankan industry participated in the technology conference held in July 2012 in Bangkok. | The remaining trainings to be organized for enforcement and servicing sector is being planned and prepared in details for implementation. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 17 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 |  | 2015-07-01 | 2015-06-01 |  |  | 58400 | 0 | 58400 | 0 | 0% | 58400 | 16876 | 58400 | 7592 | 0 | 0 | 7592 | 2193.88 | SSFA signed. Official mission to encourage the Government to adopt HCFC quotas and streamline projects implementation in February 2012. HCFC quotas issued on Dec. 2012. ODS control Training/Refreshing Workshop of 15 Enforcement and Customs Officer in November 2012. | Legal consultant hired. International consultant hired to deliver a national training workshop on alternatives to ODS. 28 RAC technician attended the sub-regional training in alternative refrigerants held in SKN. Support organization of judiciary training for second quarter 2013. The NOU efforts were focused on approving legislation to establish and enforce the HCFC legislation. These are very time demanding activities and constitute an important step to comply with HCFC phase-out goals. As of to-date, over 30% of total budget has been disbursed. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2012-07-01 | 2013-07-01 |  |  | 13000 | 0 | 13000 | 6000 | 46.15% | 7000 | 7000 | 7000 | 1690 | 0 | 780 | 910 | 910 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. First disbursement release in August 2012. Support provided to request HCFC baseline change, including verification of 2010 data. Documents to support second tranche request prepared and submitted. Customs Training Refreshing Workshop was held in Nov. 2012, 32 participants attended. HCFC quotas system approved. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. | Final activities in work plan being completed. HCFC quota system being implemented. The Agreement is signed. The activities are ongoing as planned. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 13150 | 0 | 13150 | 0 | 0% | 13150 | 0 | 13150 | 1710 | 0 | 0 | 1710 | 0 | Project approved in Dec 2012. | 2013 annual work plan has been drafted. HCFC quota system being implemented. The customs brokers training has been planned for the current year. NOO has held discussions with customs IT unit on the disaggregation on ODS refrigerants and refrigerants products in ASYCUDA for the current year. Yes, the licensing system is in place. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | STP | PHA | 63 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2013-03-01 |  |  | 44000 | 0 | 44000 | 24009 | 54.57% | 19991 | 15000 | 19991 | 5720 | 0 | 3121.17 | 2598.83 | 1950 | Country conducted training workshops for 40 refrigeration technicians and 30 custom officers |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | TAS | 19 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 | 2012-10-01 | 2014-12-01 | 2014-12-01 |  |  | 55809 | 0 | 55809 | 34450 | 61.73% | 21359 | 12342 | 21359 | 7255 | 0 | 4478.3951 | 2776.6049 | 1604.4224 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Two SSFAs were signed by the Government and UNEP. Fund disbursements released according to plan. Center of Excellence on low-GWP technology reinforced. HCFC quotas were issued by end of Dec. 2012. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. | 2013 annual work plan has been drafted. Quota system established. Customs Training Workshop including 5th Amendment of Customs codes has been planned for the current year. (a) Draft agreement; (b) Obtain clearance by UNEP and Country; c) Obtain agreement signature; (d) Provide policy support in review and update of HCFCs legislation and issuance of quotas for HCFCs; (e) Provide technical support in establishing a center of excellence in RAC servicing sector; (f) Monitor implementation of activities. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 27000 | 0 | 27000 | 0 | 0% | 27000 | 27000 | 27000 | 3510 | 0 | 0 | 3510 | 3510 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. SSFA signed in April 2012. First disbursement released in May 2012. HPMP launched in Sep 2012. HCFC quota system in place. Three RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. National seminar with support of National Refrigeration Association was organized for technicians on low-GWP technologies and recovery and recycling of ODS, 15 participants attended. | 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training workshop including 5th Amendment of Customs codes has been planned for the current year. National refrigeration training workshop to be conducted through the association of technicians with support of NOU and UNEP. The activities in the HPMP are combined with the remaining TPMP activities which are planned for completion before end of 2013. In 2012, country spent remaining TPMP funds, while the HPMP funds are scheduled for disbursement during 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-03-01 | 2013-03-01 |  |  | 75000 | 0 | 75000 | 45010 | 60.01% | 29990 | 20000 | 29990 | 9750 | 0 | 5851.3 | 3898.7 | 2600 | NOU procured tool kits and distributed to the technicians and repair workshops. The country trained 40 customs officers and 70 refrigeration experts. NOU conducted inspection visits to some of the boarders to check on the compliance requirement of the National's ODS Regulation enforcement. | NOU conducted national train the trainer for 30 refrigeration technicians on the safety of hydrocarbons |  |  | Non Investment
ONG | UNEP | HCFC and CFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-06-01 | 2012-03-01 | 2013-03-01 |  |  | 93500 | 0 | 93500 | 24000 | 25.67% | 69500 | 49500 | 69500 | 12155 | 0 | 3120 | 9035 | 6435 | The list of planned activities for 2012: - Regulatory and Policy Measures and Technical Assistance for Improvement of HCFC Data Collection and Management Procedures - Strengthening the Capacity of Customs and Enforcement Officers at Both National and Regional Level - Technical assistance activities for the refrigeration and air conditioning sector - Project Management Unit and Annual Verification. Progress: The Decree Law on the Control of Export, Import and Use of Ozone Depleting Substances (Decree Law No. 36/2012) entered into effect on 14 August 2012, and controls trade and use of ODS including HCFCs through an import quota and licensing scheme. UNEP purchased and distributed 3 units of identifiers to Timor Leste in Dec 2012. Preparatory work has been carried out to establish the nation’s first training centre for Refrigeration and Air-conditioning (RAC) Servicing and retrofitting. The first training of trainers for 5 Customs brokers on the World Customs Organization Harmonized Commodity Description and Coding System (“HS code”) was conducted. This type of training is expected to increase use of correct HS codes and increase accuracy in monitoring of trade data as well. Another training on law enforcement to Customs officers will be held after the launching of the decree law, this issue has been discussed with General Directorate for the Customs. Timor Leste Ozone logo has been designed. Some 100 books of Decree Law has been produced and distributed to stockholders related. Some 500 copies of the brochure (A4 Size, Full Colour) on the history and information on the Montreal Protocol have been produced and disseminated to stakeholders including students. The first training of trainer for custom officers on ODS issue was conducted in 25- 27 of July 2012. | The NOU conducted door by door visiting of all of HCFC importers (8 Importers), and received all their application for import license by March 2013. The NOU participated a meeting in Suai District during 3-4 April to present the Decree Law to national stakeholders. The cooperation MOU with the Vocational Training Department has drafted and being consulted for the delivery of the good practices training. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 | 2013-12-01 |  |  | 70000 | 0 | 70000 | 61946 | 88.49% | 8054 | 0 | 8054 | 9100 | 0 | 8052.98 | 1047.02 | 0 | Country continue to enforce ODS regulations |  |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tonga) | Multi-Year | ASP | TON | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-02-01 |  |  | 64750 | 0 | 64750 | 35763 | 55.23% | 28987 | 17681 | 28987 | 8418 | 0 | 4649.4662 | 3768.5338 | 2298.6665 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on July 2012 participated by 40 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Shipment of the RAC training equipment. Completion of second national Montreal Protocol customs training, additional 22 officers were trained. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche Palau) | Multi-Year | ASP | TTR | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-02-01 |  |  | 62375 | 0 | 62375 | 36402 | 58.36% | 25973 | 16330 | 25973 | 8109 | 0 | 4732.4059 | 3376.5941 | 2122.9655 | The SSFA has been signed and initial payment disbursed. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Refrigerant identifier provided. The country completed customs train the trainer on 1-3 November 2012 participated by 14 officers representing customs and other enforcement officers. The procurement of technician training equipment was finalized in December 2012 and is scheduled to reach country in May 2013. Training of the RAC servicing technician planned for July. Country has established ODS licensing and quota systems and functioning well. | Shipment of the RAC training equipment |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 101 | A | I |  | 11 | 0 | 0 | 0 | 2012-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 103450 | 0 | 103450 | 0 | 0% | 103450 | 0 | 103450 | 13449 | 0 | 0 | 13449 | 0 | The project was approved by ExCom in December of 2012. | The discussion has been initiated on the action plan for implementation of the Customs training components under the approved HPMP. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tuvalu) | Multi-Year | ASP | TUV | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-02-01 |  |  | 47875 | 0 | 47875 | 38782 | 81.01% | 9093 | 9093 | 9093 | 6224 | 0 | 5041.8625 | 1182.1375 | 1182.1375 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Agreement on the agenda and date of training on Customs Enforcement. Completion of the procurement of the RAC service equipment One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Conducted capacity for customs and law enforcement officials on January 2013 participated by 23 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO and risk reduction for illegal trade. Shipment of the RAC Servicing training equipment. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 40500 | 0 | 40500 | 0 | 0% | 40500 | 0 | 40500 | 5265 | 0 | 0 | 5265 | 0 | Country finalised HPMP and was approved at 68 ExCom. | SSFA drafted and sent to the country for signing |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | TAS | 31 | A | I |  | 0.1 | 0 | 0 | 0 | 2012-07-01 |  | 2015-07-01 | 2015-07-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | SSFA was signed and country launched the implementation of HPMP activities. List of equipment agreed by IA and the country conducted training of 20 customs officers and 45 refrigeration experts. NOU conducted meeting of Refrigeration Association | Country procured and distributed tool kits to refrigeration experts and a few repair workshops. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Vanuatu) | Multi-Year | ASP | VAN | PHA | 63 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2015-03-01 | 2015-02-01 |  |  | 76250 | 0 | 76250 | 51263 | 67.23% | 24987 | 15056 | 24987 | 9913 | 0 | 6664.5262 | 3248.4738 | 1957.3787 | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on October 2012 participated by 8 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. Two unit of new model of refrigerant identifier were procured and delivered on December 2012. Training of the NOO on the HPMP project implementation. Completion of the procurement process for the RAC Servicing training equipment. | Shipment of the RAC Servicing training equipment |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | INV | 119 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-01 | 2013-03-01 |  |  | 50646 | 0 | 50646 | 7465 | 14.74% | 43181 | 1.4552e-13 | 43181 | 6584 | 0 | 970.4529 | 5613.5471 | 1.8918e-14 | 2012 annual operating plan and procurement plans were prepared by the NOU with the guidance of the CAP Team. Progress Report and Annual Implementation Plan submitted to the 67 ExCom Meeting, in order to request the second tranche. ODS revised legislation was drafted and will be approved in 2013. | 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training workshop including 5th Amendment of Customs codes has been planned for the current year. (a) In consultation with NOU prepare annual work and procurement plan; (b) Provide policy advice in establishment of a HCFC quota system; c) Provide policy and technical support in revision of national customs training curriculum to include HCFCs. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-01 | 2013-07-01 |  |  | 46661 | 0 | 46661 | 0 | 0% | 46661 | 0 | 46661 | 6066 | 0 | 0 | 6066 | 0 | HPMP approved in July 2012. Funds programming within UNEP accounts prepared. | ODS portable identifiers to be purchased. (a) The Agreement has not been signed. It is expected to be signed in the second half of 2013. UNEP is planning a bilateral meeting with NOO on the margins of the Network Meeting to be held in June 2013 to determine the dates for an official mission; The NOU efforts were focused on approving legislation to establish and enforce the HCFC quota system. These are time consuming activities and constitute an important step to start with customs training activities. This is the main reason for the low disbursement rate; (c) In consultation with the NOU, the planned completion dates have been revised reflecting the actual implementation pace of current planned activities, and planned expenditures. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | INV | 40 | A | I |  | 11.6 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 215000 | 0 | 215000 | 0 | 0% | 215000 | 0 | 215000 | 27950 | 0 | 0 | 27950 | 0 | Project approved by 68th ExCom (Dec-12) | UNEP and UNIDO are coordinating with NOU to finalize the work-plan of all HPMP activities and remaining TPMP activities. Country contract is planned to be established by June 2013 Due to recent political development and subsequent changes of Minister of Environment & Water, as well as the Chairman of Environment Protection Authority (EPA); UNEP is waiting for clear instructions of new management to draft and process new ISP agreement. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-02-01 | 2012-12-01 | 2013-12-01 |  |  | 26000 | 0 | 26000 | 7827 | 30.1% | 18173 | 154 | 18173 | 3380 | 0 | 1017.51 | 2362.49 | 20.02 | Organization of the exhibition booth and forum on energy efficiency, ozone and climate friendly modern refrigeration technologies to inform and raise awareness of HCFC alternatives and technology innovation in cooperation with the Serbian Ministry of Energy, Development and Environment protection and the Serbian Society on Heating, Refrigeration and Air- Conditioning held on 5-7 December of 2012. | The publication of the article and interview in the quarterly journal of Serbia's RAC association on the improvement of energy efficiency in the latest climate and ozone friendly refrigeration technologies (the first quarter of 2013).The concept note for National Training of Customs Officers and Environment Inspectors to control HCFCs consumption in Serbia has been developed. The training is planned to be organized in the third quarter of 2013. |  |  | Non Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 | 2013-07-01 |  |  | 40000 | 0 | 40000 | 22000 | 55% | 18000 | 13000 | 18000 | 5200 | 0 | 2860 | 2340 | 1690 | Country trained 40 refrigeration experts and 20 customs officer. NOU procured and distributed tools and equipment. Conducted public awareness activities | SSFA signed and first payment made in June 2012. Country conducted national train the trainer workshop for 20 Refrigeration experts from all provinces of Zambia |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ANT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 | 2013-03-01 |  |  | 85000 | 0 | 85000 | 67284 | 79.16% | 17716 | 5666 | 17716 | 11050 | 0 | 8746.92 | 2303.08 | 736.58 | Project completed in December 2012. HPMP submitted and approved by the 66 ExCom Meeting. | (a) HPMP proposal submission; (b) HPMP proposal approval; (c) Final progress and financial report. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BAH | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 | 2013-08-01 |  |  | 105000 | 0 | 105000 | 79083 | 75.32% | 25917 | 0 | 25917 | 13650 | 0 | 10280.79 | 3369.21 | 0 | UNEP, in coordination with UNIDO, completed the preparation of the HPMP and submitted the project as approved by the 68th ExCom. Several consultation meetings, high level meetings and national stakeholders workshop/functions conducted during 2012 to conclude the preparation of the HPMP of Bahrain. | Completed |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BAR | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-01-01 | 2009-07-01 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 51498 | 60.59% | 33502 | 14059 | 33502 | 11050 | 0 | 6694.74 | 4355.26 | 1827.67 | NOO attended the March 2012 network meeting and presented on country's challenges for the preparation of the HPMP. HCFC data were collected and cross-checked with industry stakeholders. HCFC phase out schedule discussed and agreed among Government and main stakeholders. Cabinet endorsed and submitted HPMP for the 69th ExCom Meeting. | HPMP approved in the 69th ExCom Meeting. Audited Financial reports are being prepared and reconciliated by NOU in order for UNEP to release outstanding disbursements. (a) HCFC survey validation; (b) HCFC phase-out schedule endorsement; (c) HPMP proposal submission; (d) HPMP proposal approval. Activity (b) took longer than planned and consequently delayed activities c) and (d). UNEP held a series of consultations with NOU on specific assistance required. Proposal endorsed by Dec 2012 and submitted to the first ExCom meeting in 2013. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BHA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 50119 | 58.96% | 34881 | 1118 | 34881 | 11050 | 0 | 6515.47 | 4534.53 | 145.34 | HPMP launched in Sep. 2012. | Audited Financial reports are being prepared and reconciliated by NOU in order for UNEP to release outstanding disbursements. (a) HPMP launch; (b) Final progress and financial report; (c) Project closing. Conciliation of accounts is in progress. UNEP and NOU are cross checking information to proceed with financial completion of the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DJI | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 | 2013-12-01 |  |  | 30000 | 0 | 30000 | 5602 | 18.67% | 24398 | 0 | 24398 | 3900 | 0 | 728.26 | 3171.74 | 0 | The SSFA has since expired but was revised and sent to country for signature. The country has signed awaiting disbursement. | SSFA was sent to FMO for payment |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | DJI | PHA | 58 | PRP | 16 | A | I |  | 0 | 0 | 0 |  | 2009-07-01 | 2009-12-01 | 2010-07-01 | 2013-07-01 |  |  | 55000 | 0 | 55000 | 45013 | 81.84% | 9987 | 0 | 9987 | 7150 | 0 | 5851.69 | 1298.31 | 0 | Project ongoing satisfactorily |  |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 64 | PRP | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 | 2013-07-01 |  |  | 35000 | 0 | 35000 | 6450 | 18.43% | 28550 | 15273 | 28550 | 4550 | 0 | 838.5 | 3711.5 | 1985.49 | The HPMP was developed with UNEP's input and submitted to the 68th Excom meeting for consideration. | The project is completed. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ERI | PHA | 55 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 | 2013-07-01 |  |  | 85000 | 0 | 85000 | 70000 | 82.35% | 15000 | 0 | 15000 | 11050 | 0 | 9100 | 1950 | 0 | HPMP for Eritrea approve at the 67 ExCom | project completed |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ETH | PHA | 56 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 | 2013-07-01 |  |  | 85000 | 0 | 85000 | 61419 | 72.26% | 23581 | 0 | 23581 | 11050 | 0 | 7984.47 | 3065.53 | 0 | Country finalized HPMP and was approved at 68 ExCom. | SSFA drafted and sent to the country for signing |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GBS | PHA | 57 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 | 2013-07-01 |  |  | 85000 | 0 | 85000 | 66979 | 78.8% | 18021 | 0 | 18021 | 11050 | 0 | 8707.27 | 2342.73 | 0 |  |  |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GRN | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 | 2013-06-01 |  |  | 85000 | 0 | 85000 | 77469 | 91.14% | 7531 | 0 | 7531 | 11050 | 0 | 10070.97 | 979.03 | 0 | According to UNEP rules, project balance was re-obligated to proceed with outstanding disbursements, while audited financial reports are received by UNEP. | Audited Financial reports are being prepared and reconciliated by NOU. (a) Final progress and financial report; (b) Project completion. UNEP is doing follow up with the NOU to obtain the final financial report in order to close the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUA | PHA | 57 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 | 2013-12-01 |  |  | 75000 | 0 | 75000 | 22357 | 29.81% | 52643 | 0 | 52643 | 9750 | 0 | 2906.41 | 6843.59 | 0 | No progress. The Government has instructed public institutions to put projects on hold, including any disbursements, while an internal assessment/audit is conducted. | (a) Final progress and financial report; (b) Project closing. Conciliation of accounts is in progress. UNEP and NOU are cross checking information to proceed with financial completion of the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HAI | PHA | 57 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 | 2013-06-01 |  |  | 85000 | 0 | 85000 | 56110 | 66.01% | 28890 | 7012 | 28890 | 11050 | 0 | 7294.3 | 3755.7 | 911.56 | NOO attended the March 2012 network meeting and presented on country's challenges for the preparation of the HPMP. HCFC data were collected and cross-checked with industry stakeholders. HPMP approved in the 68th ExCom Meeting. | Accounting reports are being reconciliated among NOU, UNDP country office and UNEP. (a) HCFC survey validation; (b) HCFC phase-out schedule endorsement; (c) HPMP proposal submission; (d) HPMP proposal approval. (e) Final progress and financial report; (f) Project closing. Conciliation of accounts is in progress. UNEP and NOU are cross checking information to proceed with financial completion of the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAU | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 25000 | 29.41% | 60000 | 0 | 60000 | 11050 | 0 | 3250 | 7800 | 0 | Administrative stalement still not resolved | The issue of Administrative stalement in Mauritanian is being followed up very closely by the Regional Director and with the assistance of the office of the Deputy Executive Director and it is expected that the stalement will be resolved soon. The HCFC survey has not yet been conducted as the HPMP preparatory funds can not be sent to the country before resolving the stalement. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLI | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 73894 | 86.93% | 11106 | 0 | 11106 | 11050 | 0 | 9606.22 | 1443.78 | 0 | Final payment made in Jan 2012 |  |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SAU | PHA | 55 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-02-01 | 2009-07-01 | 2013-12-01 |  |  | 65000 | 0 | 65000 | 35766 | 55.02% | 29234 | 0 | 29234 | 8450 | 0 | 4649.58 | 3800.42 | 0 | Due to the gaps in data about the industry using sectors mainly in the PU manufacturing, additional work was required to complete the project proposal by UNIDO. UNEP provided the necessary assistance to secure the missing data and actively participated in the negotiation of the document | HPMP finalized and approved at the 68th ExCom |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STK | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 | 2013-06-01 |  |  | 85000 | 0 | 85000 | 44909 | 52.83% | 40091 | 37565 | 40091 | 11050 | 0 | 5838.17 | 5211.83 | 4883.45 | HPMP launched in first quarter 2012. According to UNEP rules, project balance was re-obligated to proceed with outstanding disbursements, while audited financial reports are received by UNEP. | Audited Financial reports are being prepared and reconciled by NOU in order for UNEP to release outstanding disbursements. (a) HPMP launch; (b) Final progress and financial report; (c) Project completion. Conciliation of accounts is in progress. UNEP and NOU are cross checking information to proceed with financial completion of the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STV | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 | 2013-06-01 |  |  | 85000 | 0 | 85000 | 58131 | 68.39% | 26869 | 24035 | 26869 | 11050 | 0 | 7557.03 | 3492.97 | 3124.55 | According to UNEP rules, project balance was re-obligated to proceed with outstanding disbursements, once audited financial reports received by UNEP. | Audited Financial reports are being prepared and reconciled by NOU in order for UNEP to release outstanding disbursements. (a) HPMP launch; (b) Final progress and financial report; (c) Project completion. Conciliation of accounts is in progress. UNEP and NOU are cross checking information to proceed with financial completion of the project. |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | UGA | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 | 2013-07-01 |  |  | 30000 | 0 | 30000 | 21752 | 72.51% | 8248 | 0 | 8248 | 3900 | 0 | 2827.76 | 1072.24 | 0 | Country finalised HPMP and was approved at 68 ExCom. | SSFA drafted and sent to the country for signing |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | URT | PHA | 57 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 | 2013-07-01 |  |  | 85000 | 0 | 85000 | 75000 | 88.24% | 10000 | 0 | 10000 | 11050 | 0 | 9750 | 1300 | 0 | Project completed. HPMP approved at 67 ExCom |  |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | YEM | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 | 2013-08-01 |  |  | 125000 | 0 | 125000 | 35151 | 28.12% | 89849 | 0 | 89849 | 16250 | 0 | 4569.63 | 11680.37 | 0 | Despite the inability of UNEP and UNIDO to visit the country, due to security considerations, the preparation of the HPMP completed in 2012 through close communication and final coordination meeting with NOU outside Yemen. NOU completed data collection. UNEP and UNIDO requested additional information and clarification on some sectors and NOU responded. Project submitted and approved by 68th ExCom | Work completed but financial closing is pending till receiving final financial statements |  |  | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ZAM | PHA | 56 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 | 2013-07-01 |  |  | 85000 | 0 | 85000 | 65000 | 76.47% | 20000 | 0 | 20000 | 11050 | 0 | 8450 | 2600 | 0 | Project completed and HPMP approved at 64 ExCom |  |  |  | Non Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ALB | PHA | 64 | INV | 22 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-03-01 | 2013-07-31 | 2013-07-01 |  |  | 45000 | 0 | 45000 | 3754.92 | 8.344% | 41245.08 | 33809.9 | 7435 | 4050 | 0 | 338 | 3712 | 3043 | R&R and refrigeration tools/equipment were procured and delivered to the NOU for further dissemination among the end users. Although the level of disbursement at the end of 2012 is low, over 80% of the funds were implemented by end 2012 that will result in disbursement during 2013. | Delivery of procured R&R and refrigeration tools/equipment to four designated service centers followed by training the trainers and subsequent training of service technicians. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | Multi-Year | AFR | ALG | PHA | 66 | INV | 77 | A | I | HCFC | 2.8 | 0 |  |  | 2012-04-01 | 2012-10-01 | 2013-04-30 | 2014-12-01 |  |  | 214400 | 0 | 214400 | 413.86 | 0.193% | 213986.14 | 0 | 10000 | 16080 | 0 | 31 | 16049 | 0 | Activities implemented in 2012The project was approved in 2012. The government was informed. The work plan was established. Project implementation was slowed down due to postponed mission planned for August 2012. Delays due to lack of agreement with the national counterpart. | Mission took place and discussion took place on all pending issues and on the plan of action for 2013 with the representatives of the MATE. MATE has recently changed the focal point for ozone matters and UNIDO starts dialogue with the new appointed NOU as soon as possible. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | Multi-Year | AFR | ALG | PHA | 66 | INV | 76 | A | I | HCFC | 8.3 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2015-01-01 |  |  | 1379460 | 0 | 1379460 | 4207.01 | 0.305% | 1375252.99 | 331.01 | 50000 | 103460 | 0 | 316 | 103144 | 24.8257 | The project was approved in 2012 at the 66th Meeting of the Executive Committee. Due to lack of support from NOU, no real progress was made in 2012 in this project, despite regular follow-up by UNIDO HQ as well as UNIDO's office in Algiers. There were extensive preparations from UNIDO to organize the HPMP launching meeting in October 2012. However, the meeting had to be cancelled, since no confirmation was received from the government. However, on the technical level, in November 2012 a study tour to Japan was arranged for the technical manager of Condor to get acquainted with the R32 technology developments. Due to lack of support from NOU, no real progress was made in 2012 in this project, despite regular follow-up by UNIDO HQ as well as UNIDO's office in Algiers. | In the beginning of 2013 a new Environment and Sustainable Development Director has been appointed by the Government, to whom UNIDO managed to establish contact. As a result, a mission was organized to Algiers in February 2013. The representative of Condor company has also participated in the meeting and has also ensured Condor's commitment in implementing the project in an accelerated manner. At the same time, it was pointed out with concern that R32 kits are not readily available in Algeria yet. The final project details and implementation modalities were discussed with the company's representative. It was also agreed that an expert mission should be organized in June 2013 to prepare the TORs for equipment purchase. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | ARG | PHA | 66 | INV | 169 | A | I | HCFC | 7.1 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2013-12-01 |  |  | 685388 | 0 | 685388 | 0 | 0% | 685388 | 0 | 100000 | 51404 | 0 | 0 | 51404 | 0 | Activities implemented in 2012. The project was approved at the 66th Meeting of the Executive Committee in 2012. The Government was informed. The new manual for training of service technicians was prepared. Specifications and the scope of service equipment finalized and coordinated with the NOU. | Printing of the new manual for service technicians, procurement of equipment and arrangement of training workshops are planned for 2013. By May 2013, PO on training the trainers in the amount of US$ 48,910 has been already issued and US$ 400,000 has been obligated on the supply of equipment and tools for service technicians. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-22 from the manufacturing of central air conditioning and window air conditioning at Awal Gulf manufacturing company) | Multi-Year | ASP | BAH | PHA | 68 | INV | 27 | A | I | HCFC | 3.7 | 0 |  |  | 2012-12-01 |  | 2014-12-31 | 2014-12-01 |  |  | 387855 | 0 | 387855 | 0 | 0% | 387855 | 0 | 20000 | 27150 | 0 | 0 | 27150 | 0 | The project was approved at 68th Meeting of the Executive Committee in December 2012. | A mission was undertaken in February 2013 to agree on the implementation plan with the beneficiary (Awal Gulf). |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (reclamation facility) | Multi-Year | ASP | BAH | PHA | 68 | TAS | 26 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2020-12-31 | 2020-12-01 |  |  | 161600 | 0 | 161600 | 0 | 0% | 161600 | 0 | 20000 | 11312 | 0 | 0 | 11312 | 0 | The project was approved at 68th Meeting of the Executive Committee in December 2012. | A mission was undertaken in February 2013 to agree on implementation plan with the NOU and UNEP. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BDI | PHA | 65 | INV | 29 | A | I | HCFC | 0.4 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2016-11-30 | 2016-11-01 |  |  | 80000 | 0 | 80000 | 4730.7 | 5.913% | 75269.3 | 59000 | 59000 | 7200 | 0 | 426 | 6774 | 5310 | The joint UNIDO-UNEP mission enabled the assessment of needs. The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 78% of the funds have been committed. Equipment for RAC servicing, recovery and recycling shipped, pending custom clearance. Disbursement is by now above USD 50k. | The equipment is being shipped. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BEN | PHA | 63 | INV | 26 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-04-01 | 2013-03-31 | 2013-06-01 |  |  | 100000 | 0 | 100000 | 5627.55 | 5.628% | 94372.45 | 10000 | 75000 | 7500 | 0 | 422 | 7078 | 750 | A mission to Benin was organized in the first week of April 2012, whereby the implementation strategy, implementation modalities and list of equipment to be purchased have been agreed upon. After this successful mission, TORs for the purchase of equipment and tools for the service workshops were prepared and agreed upon with the NOU. Bidding was completed in October, technical and financial evaluation was finished and agreed upon in November 2012 and the contract was issued in December 2012. Disbursement at the end of 2012 were limited due to the IPSAS, although by the end of 2012 most of the funds were committed. | The supplier was supposed to deliver the equipment within 10 weeks after the issuance of the purchase order. However, due to delays in shipment, equipment arrived only end April 2013 in Cotonou. The second tranche will be submitted to the 70th ExCom Meeting. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | INV | 18 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2013-11-30 | 2013-11-01 |  |  | 105128 | 0 | 105128 | 0 | 0% | 105128 | 93103 | 12025 | 9462 | 0 | 0 | 9462 | 8379 | TOR for servicing equipment was finalized with NOU. Tender was raised. After evaluation of offers, contract was issued to the supplier in October 2012. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 89% of the funds have been committed. | The shipment arrived in Nassau end of January 2013 and ithas been cleared from customs. A three-day training on operation and maintenance of equipment by the supplier was carried out in March. Thus, disbursement level in 2013 will significantly increase. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 66 | INV | 26 | A | I | HCFC | 0.2 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2014-06-01 |  |  | 76070 | 0 | 76070 | 33.72 | 0.04433% | 76036.28 | 0 | 40000 | 5705 | 0 | 3 | 5702 | 0 | The project was approved in 2012. PAD was issued and the Gov. was informed about the approval. The project document was revised by the NOU and submitted to the Government. There were no other activities conducted in 2012 other than those indicated above, since the revised Project Document was under Government review until January 2013. The reason for low disbursement is explained above. | Training workshops and certification for service technicians and mechanics outline in March.Conduction of workshop June- December. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion to cyclopentane in the manufacture of panels at Alternativa, and conversion to methyl formate (foam) and non-HCFCs refrigerant in 6 manufacturers of commercial refrigeration equipment) | Multi-Year | EUR | BHE | PHA | 66 | INV | 27 | A | I | HCFC | 5.1 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2014-06-01 |  |  | 555212 | 0 | 555212 | 33.72 | 0.006073% | 555178.28 | 0 | 150000 | 41641 | 0 | 3 | 41638 | 0 | The project was approved in 2012. PAD was issued and the Gov. was informed about the approval. The project document was revised by the NOU and submitted to the Government. There were no other activities conducted in 2012 other than those indicated above, since the revised Project Document was under Government review until January 2013. The reason for low disbursement is explained above. | A mission to develop technical specifications for conversion to cyclopentane in the manufacture of panels at Alternativa was undertaken in February 2013. Equipment purchase March - June. Preparation of specifications for conversion of foam production in 6 manufacturers of commercial refrigeration equipment in Jun Equipment purchase October - December |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | INV | 30 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-12-01 |  |  | 150000 | 0 | 150000 | 104516.55 | 69.68% | 45483.45 | 33786.32 | 11697 | 13500 | 0 | 9406 | 4094 | 3041 | After TOR for servicing equipment was finalized with NOU, tender was raised. After evaluation of offers, contract was issued to supplier. Equipment was delivered to Ouagadougou in June 2012. An agreement was reached with NOU to purchase further equipment for retrofit training with remaining funds. These were purchased through local suppliers in December 2012. Two out three purchases were delivered. | One local supplier did not deliver so the rebidding process was initiated. The request for the second tranche report is planned to be submitted to the 70th Meeting of the Executive Committee. The project is expected to be completed in 2013. UNEP is the lead agency. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CAF | PHA | 64 | INV | 21 | A | I | HCFC | 0.5 | 0 |  |  | 2011-07-01 | 2012-09-01 | 2016-07-31 | 2016-07-01 |  |  | 125000 | 0 | 125000 | 19000.74 | 15.2% | 105999.26 | 105950 | 105999 | 9375 | 0 | 1425 | 7950 | 7946 | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-12-01 |  |  | 135000 | 0 | 135000 | 52.58 | 0.03895% | 134947.42 | 114754.91 | 134000 | 10125 | 0 | 4 | 10121 | 8607 | The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 85% of the funds have been committed. | By May 2013 equipment has been delivered as well as a training on the use of the equipment. Disbursement level is now over USD 100k. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 34 | A | I | HCFC | 15.7 | 0 |  |  | 2011-07-01 | 2012-04-01 | 2015-07-31 | 2014-07-01 |  |  | 310900 | 0 | 310900 | 22997.69 | 7.397% | 287902.31 | 176746.89 | 50000 | 23318 | 0 | 1725 | 21593 | 13256 | Workplan and time-schedule for investment activities for the years 2012 - 2013 was agreed in January 2012. Technical specification for delivery of portable foaming machines for field applications was completed in June 2012. International bidding was organized during third quarter of 2012 and the contract was signed with equipment supplier (TEC MAC) during the fourth quarter of 2012. Disbursement level does not reflect actual progress, since most of the funds are already committed. UNIDO is ensuring funds disbursement for the agreed contracts once the equipment is delivered and installed in field, thus disbursements for committed funding will be achieved in 2013. | Delivery of equipment is taking place May 2013, commissioning and training will be organized May - June 2013. Local Purchase of methyl formate for demonstration/tests was initiated, test and demonstrations with methyl formate will take place back-to-back with the training. An international expert has been contracted to assist field demonstrations. Briefing meeting with NOU and foam companies will take place during the second half of 2013 to assess results and review activities for the completion of the investment component. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 35 | A | I | HCFC | 6.4 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2015-07-31 | 2015-07-01 |  |  | 573553 | 0 | 573553 | 93952.86 | 16.38% | 479600.14 | 164138.89 | 150000 | 43016 | 0 | 7046 | 35970 | 12310 | Subcontract with counterpart to address policy component was signed last quarter of 2012 (the outcome will consist in legislation review, training and monitoring of the achieved HPMP progress. In September 2012 train the trainer component for customs officers and the first customs training workshop was completed. Additional customs training will further take place as an outcome of the mentioned subcontract). | Follow-up of the activities defined by the subcontract with counterpart will take place in 2013. Train the trainers component for technicians is scheduled for the first half of 2013. |  |  | INV
ONG | UNIDO | Sector plan for phase-out of HCFCs in the extruded polystyrene foam sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 514 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2014-12-01 |  |  | 21372000 | 0 | 21372000 | 9617316.79 | 45% | 11754683.21 | 5343000 | 4274400 | 1602900 | 0 | 721299 | 881601 | 400725 | A detailed work plan was submitted by FECO. After comprehensive evaluation it was approved in September 2012. In March 2012 XPS companies were invited to submit individual conversion plans. 12 proposals were received. In August and September an independent audit agency was selected and the consumption baseline was verified. 11 enterprises signed sub-contracts to start conversion (all companies selected CO2 technology). The procurement capacity of 4 equipment providers was assessed. The second round of conversion was started in December 2012 by requesting companies to submit proposals. The submission of the second tranche was prepared and submitted to the MLF. | Conversion of 11 companies that signed individual phase-out agreements is planned for 2013. Preparation and endorsement of the work plan for the second tranche as soon as approved. The consumption baseline of companies that are going to submit phase-out proposals will be verified and contracts signed. In the second half of 2013 the next call for individual sub-projects will follow together with the preparation of the third tranche of the project and consecutive submission to the MLF and request for approval. |  |  | INV
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 513 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2014-12-01 |  |  | 36430000 | 0 | 36430000 | 18214916.75 | 50% | 18215083.25 | 0 | 5000000 | 2732250 | 0 | 1366119 | 1366131 | 0 | 1. Institutional setup between UNIDO, FECO and project beneficiaries in place. 2. First round of beneficiaries identified and verified by FECO. 50% of the funds have been disbursed by end 2012. The project is progressing very well without delays. | 1. Beneficiaries procurement capacity assessed. 2. Contracts signed between FECO and beneficiaries. 3. Conversion at 7 manufacturer of R-410 A/C. 4. Conversion at 7 manufacturer of R-290 A/C. 5. Conversion at 3 R-290 compressor manufacturer. |  |  | INV
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 68 | INV | 524 | A | I | HCFC | 176 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2015-03-01 |  |  | 9200000 | 0 | 9200000 | 0 | 0% | 9200000 | 0 | 1840000 | 644000 | 0 | 0 | 644000 | 0 | The tranche was approved in December 2012. Subsequently, still in 2012, the PAD was issued. | A mission was organized to China after the Spring Festival, in early March 2013. Details of the project implementation including the results of the 68th Meeting of the Executive Committee were discussed in detail. Beneficiaries procurement capacity was assessed and cleared. Contracts were prepared for the companies to be covered under tranches I and II. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | CRO | PHA | 61 | INV | 36 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2014-12-31 | 2013-09-01 |  |  | 180000 | 0 | 180000 | 146670.49 | 81.48% | 33329.51 | 1538.96 | 30000 | 13500 | 0 | 11000 | 2500 | 115 | Bidding for demonstration units based on low-GWP alternatives was organized, however, no offers were received. Bidding for additional tools for training centers was also organized. However, after closing the bids, the NOU decided that funding foreseen for the tools should be reallocated to actual conversion due to the pressing phase-out deadline. Installation owners for potential conversion to low-GWP technology were approached in order to work out a workable financing scheme. A mission took place in December 2012 to meet with representatives of the National Environmental Protection and Energy Efficiency Fund on the financing of the conversion of HCFC-based installations. | After follow-up with potential suppliers for the low-GWP demonstration unit it turned out that the task was complex and longer bidding time was required. In light of the above, a new bidding was announced for over 4 weeks. Interested companies confirmed their interest in participating, but no offers were received again. This component may have to be reallocated to the conversion activities. Another mission took place in February to work out the contract details between the Environment Fund and UNIDO for the financing of the conversion/retrofit of selected HCFC installations. All elements were agreed upon afterwards and the contract is expected to be signed in May 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second and third tranches) | Multi-Year | EUR | CRO | PHA | 66 | INV | 38 | A | I | HCFC | 4.3 | 0 |  |  | 2012-04-01 |  | 2013-07-31 | 2014-05-01 |  |  | 360000 | 0 | 360000 | 33.72 | 0.009367% | 359966.28 | 0 | 50000 | 27000 | 0 | 3 | 26997 | 0 | The project was approved at the 66th Meeting of the Executive Committee. The PAD was issued and the government was informed on accelerated payment schedule of the tranches. Installation owners for potential conversion to low-GWP technology were approached in order to work out a workable financing scheme. A mission took place in December 2012 to meet with representatives of the National Environmental Protection and Energy Efficiency Fund on the financing of the conversion of HCFC-based installations. The main activity for 2012 was related to the financing of the conversion/retrofit of selected HCFC installations. Installation owners for potential conversion to low-GWP technology were approached in order to work out a workable financing scheme. A mission took place in December 2012 to meet with representatives of the National Environmental Protection and Energy Efficiency Fund on the financing of the conversion of HCFC-based installations. Since there was no agreement signed in 2012 for the conversion of HCFC-based installations, no disbursement could be made. | Another mission took place in February to work out the contract details between the Environment Fund and UNIDO for the financing of the conversion/retrofit of selected HCFC installations. All elements were agreed upon afterwards and the contract is expected to be signed in May 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | INV | 58 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-08-01 | 2013-11-30 | 2013-11-01 |  |  | 200500 | 0 | 200500 | 25892.38 | 12.91% | 174607.62 | 83088.82 | 174000 | 15038 | 0 | 1942 | 13096 | 6232 | Tools for the training centres were purchased and delivered to the country. A total of 9 vocational centres will be upgraded with tools for didactic purposes. It was agreed to train trainers from the mentioned centres in February 2013. On the other hand, the destruction machine and refrigerant reclaiming machine were installed and commissioned. The last one has been used for HCFC-22 reclaiming. | Training of 60 trainers was carried out by two UNIDO experts in February 2013. It is expected to train 30 trainers. At the same time, conferences on good refrigeration practices will be carried out. The reclaim of refrigerant will be promoted and some drop in with HC activities will be carried out. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing by Indurama) | Multi-Year | LAC | ECU | PHA | 65 | INV | 55 | A | I | HCFC | 15 | 0 |  |  | 2011-11-01 | 2012-03-01 | 2013-11-30 | 2014-11-01 |  |  | 1331440 | 0 | 1331440 | 29157.45 | 2.19% | 1302282.55 | 215810.05 | 400000 | 99858 | 0 | 2187 | 97671 | 16186 | Terms of reference was completed. The bidding process was carried out and the cyclopentane production line was selected and purchased. Although disbursement level at the end of 2012 was low, 18% of the funds have been committed by the end of 2012. The contract was signed in 2012 and about USD 1 million committed. By now over USD 250,000 has been disbursed and over USD 750,000 obligated. The project is going as planned. | The supplier OMS visited INDURAMA in March 2013. After the visit the production line will be delivered, installed and commissioned in September 2013. In parallel, other activities will be carried out in the project. The tank, accessories and other elements will be purchased during the time the production line is manufactured. The project duration was extended in order to carry out all the activities properly. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the manufacture of insulation foam for refrigeration equipment) | Multi-Year | AFR | EGY | PHA | 65 | INV | 112 | A | I | HCFC | 9 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 | 2014-12-01 |  |  | 905700 | 0 | 905700 | 13383.22 | 1.478% | 892316.78 | 287280.31 | 350000 | 67928 | 0 | 1004 | 66924 | 21546 | 1) Foam sector: Conversion of insulation foam for refrigeration equipment at Kiriazi. Contract for consultancy and technical services for implementation and local technical supervision of the project has been issued in January 2012. Detailed TOR for equipment was prepared and discussed with the company during a site visit. International bidding was concluded in August. Technical queries were cleared with the company. Due to the limited funds available for the foam part of the HPMP negotiation of the cost of equipment was carried out. Purchase order was issued in November 2012. 2) RAC sector: the enabling activities started with a brainstorming meeting in June 2012, all relevant stakeholders and Ministries participated. It was recommended to start with the survey study to analyze the needs of the sector in detail. TOR for consultancy were prepared. While disbursement rate is low at the end of 2012, there has been significant progress made in the implementation of the HPMP. The conversion schedule in the foam sector has been confirmed and will lead to a disbursement of over USD 500,000 by end April 2014 (disbursement in 4 steps in accordance with to performance based contract with the equipment provider). | 1) Foam sector: The delivery of equipment is expected for October 2013, contract of the local works and logistic support will be finalized in February 2014. The completion of this part of the HPMP is envisaged for April 2014. 2) Enabling activities in the RAC sector: Start with a consultancy study for RAC enabling activities to go into detail planning for the overall design and supervision. Selection of an educational institution to be upgraded as a training center for certification and select two servicing companies that have experience with retrofit, recovery and recycling programmes through the NPP to undertake the HCFC-22 based RRR activities focusing on the use of hydrocarbon and other natural refrigerants. Formulation of detailed TOR for those activities. Initial conference on low-GWP technologies took place 2nd week of May - companies for upgrade to hydrocarbon technology have been selected; the training and upgrade will be carried out 2nd half 2013 and 1st half 2014 - expected disbursement: USD 250,000 |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (coordination and management) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 111 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2012-11-30 | 2013-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 5000 | 1500 | 0 | 0 | 1500 | 0 | 1) Foam sector: Conversion of insulation foam for refrigeration equipment at Kiriazi. Contract for consultancy and technical services for implementation and local technical supervision of the project has been issued in January 2012. Detailed TOR for equipment was prepared and discussed with the company during a site visit. International bidding was concluded in August. Technical queries were cleared with the company. Due to the limited funds available for the foam part of the HPMP negotiation of the cost of equipment was carried out. Purchase order issued in November 2012. - 2) RAC sector: the enabling activities started with a brainstorming meeting in June 2012, all relevant stakeholders and Ministries participated. It was recommended to start with the survey study to analyze the needs of the sector in detail. TOR for consultancy were prepared. This component is a small part of the HPMP and constitues only 1 % of the funds released so far. The HPMP is progressing well and over USD 1 million has already been obligated under the HPMP. | 1) Foam sector: The delivery of equipment is expected for October 2013, contract of the local works and logistic support will be finalized in February 2014. The completion of this part of the HPMP is envisaged for April 2014. 2) Enabling activities in the RAC sector: Start with a consultancy study for RAC enabling activities to go into detail planning for the overall design and supervision. Selection of an educational institution to be upgraded as a training center for certification and select two servicing companies that have experience with retrofit, recovery and recycling programmes through the NPP to undertake the HCFC-22 based RRR activities focusing on the use of hydrocarbon and other natural refrigerants. Formulation of detailed TOR for those activities. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 114 | A | I | HCFC | 0.3 | 0 |  |  | 2011-11-01 |  | 2012-11-30 | 2013-12-01 |  |  | 24300 | 0 | 24300 | 0 | 0% | 24300 | 0 | 10000 | 1823 | 0 | 0 | 1823 | 0 | The enabling activities started with a brainstorming meeting in June 2012, all relevant stakeholders and Ministries participated. It was recommended to start with the survey study to analyze the needs of the sector in detail. TOR for consultancy were prepared. This component is a small part of the HPMP and constitues only 1 % of the funds released so far. The HPMP is progressing well and over USD 1 million has already been obligated under the HPMP. | 1) Foam sector: The delivery of equipment is expected for October 2013, contract of the local works and logistic support will be finalized in February 2014. The completion of this part of the HPMP is envisaged for April 2014. 2) Enabling activities in the RAC sector: Start with a consultancy study for RAC enabling activities to go into detail planning for the overall design and supervision. Selection of an educational institution to be upgraded as a training center for certification and select two servicing companies that have experience with retrofit, recovery and recycling programmes through the NPP to undertake the HCFC-22 based RRR activities focusing on the use of hydrocarbon and other natural refrigerants. Formulation of detailed TOR for those activities. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 68 | TAS | 116 | A | I | HCFC | 3.1 | 0 |  |  | 2012-12-01 |  | 2018-12-31 | 2018-12-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 20000 | 18750 | 0 | 0 | 18750 | 0 | This project is the second tranche of the HPMP Egypt. It was approved in at the 68th Meeting of the Executive Committee in December 2012. | The enabling activities planned for 2013 in the RAC sector: Start with a consultancy study for RAC enabling activities to go into detail planning for the overall design and supervision. Selection of an educational institution to be upgraded as a training center for certification and select two servicing companies that have experience with retrofit, recovery and recycling programmes through the NPP to undertake the HCFC-22 based RRR activities focusing on the use of hydrocarbon and other natural refrigerants. Formulation of detailed TOR for those activities is foreseen. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | EQG | PHA | 65 | INV | 06 | A | I | HCFC | 0.3 | 0 |  |  | 2011-11-01 | 2012-09-01 | 2016-11-30 | 2013-12-01 |  |  | 75000 | 0 | 75000 | 7139.34 | 9.519% | 67860.66 | 61900 | 67861 | 6750 | 0 | 643 | 6107 | 5571 | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ERI | PHA | 67 | INV | 10 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2016-07-31 | 2016-07-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 15000 | 3600 | 0 | 0 | 3600 | 0 | The project was approved in July 2012 at the time the TPMP were implemented and completed. As indicated in the previous project, the National Ozone Office left the country and jeopardize the implementation of the project. | The project will be implemented as second step of the TPMP. It is planned a joint mission with UNEP in April 2013. Demonstration projects with HC or alternative refrigerants is planned. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ETH | PHA | 68 | INV | 22 | A | I | HCFC | 0.2 | 0 |  |  | 2012-12-01 |  | 2016-12-31 | 2016-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 25000 | 6300 | 0 | 0 | 6300 | 0 | The project was approved at the 68th Meeting of the Executive Committee in December 2012. The government was informed. The work plan was established. | Agreement on TOR, purchase and delivery of equipment planned to take place by the end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | INV | 27 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2014-07-01 |  |  | 130000 | 0 | 130000 | 52.58 | 0.04045% | 129947.42 | 60430 | 60400 | 11700 | 0 | 5 | 11695 | 5439 | The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 50% of the funds have been committed. | A new NOU has been set up. Contacts have been made to discuss activities with the new focal point. Reason for the extended project duration: The NOU was not operational for a certain period of time. Equipment shipped, pending custom clearance. Disbursement by May above USD 50k. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0 |  |  | 2011-11-01 | 2012-07-01 | 2016-11-30 | 2013-12-01 |  |  | 50000 | 0 | 50000 | 5469.93 | 10.94% | 44530.07 | 36824.63 | 7705 | 4500 | 0 | 492 | 4008 | 3314 | TOR for servicing and training equipment, finalized with NOU. Contract was issued to suppliers in December 2012. | Equipment was delivered in April 2013. The NOU facilitates the customs clearance. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | INV | 15 | A | I | HCFC | 0.1 | 0 |  |  | 2011-11-01 |  | 2016-11-30 | 2013-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 40000 | 3600 | 0 | 0 | 3600 | 3600 | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. Disbursement at the end of 2012 was limited due to the IPSAS, although by the end of 2012 most of the funds were committed. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 44 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-06-01 | 2013-07-31 | 2013-07-01 |  |  | 8450 | 0 | 8450 | 8009.95 | 94.79% | 440.05 | 0 | 400 | 634 | 0 | 601 | 33 | 0 | National expert was hired for the HPMP activities. The NOU is finishing the implementation of the TPMP. | The implementation will be coordinated with the second tranche UNIDO project MPGUA12002. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 43 | A | I | HCFC | 1.7 | 0 |  |  | 2011-07-01 | 2012-10-01 | 2013-07-31 | 2013-07-01 |  |  | 109637 | 0 | 109637 | 719.01 | 0.6558% | 108917.99 | 40570 | 108000 | 8223 | 0 | 54 | 8169 | 3043 | The cyclopentane production line was selected and purchased. It is expected the production line to be installed in May 2013. Although disbursement level at the end of 2012 was low, about 40% of the funds were obligated at that time. | Plans: To follow up the installation of the cyclopentane production line and monitoring the phase out of premixed HCFC-141b. By May 2013, most of the funds have been committed for the conversion to Cyclopentane production line. With the delivery of the equipment planned in June 2013 a total of US$ 98,600 will be disbursed. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GUA | PHA | 68 | INV | 45 | A | I | HCFC | 0.6 | 0 |  |  | 2012-12-01 |  | 2015-07-31 | 2015-07-01 |  |  | 97925 | 0 | 97925 | 0 | 0% | 97925 | 0 | 40000 | 7344 | 0 | 0 | 7344 | 0 | The tranche was approved at the 68th Meeting of the Executive Committee in December 2012. The Government was informed. | The project site was visited in February 2013. The first activities will be the purchase of tools required to complement those supplied for the vocational centres. The TOR is ready and it is expected to purchase the tools in May 2013. An international expect is scheduled in May 2013 to visit the country and train trainers in good refrigeration practices and drop in with HC. Some pilot projects for drop-in with HC will be carried out. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GUI | PHA | 66 | INV | 26 | A | I | HCFC | 1.2 | 0 |  |  | 2012-04-01 |  | 2016-04-30 | 2013-12-01 |  |  | 160000 | 0 | 160000 | 0 | 0% | 160000 | 143348.2 | 160000 | 12000 | 0 | 0 | 12000 | 10751.115 | The project was approved in 2012. The Government was informed. The draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in November 2012. Purchase order was issued in December 2012. Disbursement at the end of 2012 was limited due to the IPSAS, although by the end of 2012 most of the funds were committed. | .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | INV | 34 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-09-01 | 2014-03-31 | 2014-03-01 |  |  | 100000 | 0 | 100000 | 43962.58 | 43.96% | 56037.42 | 34500 | 56000 | 7500 | 0 | 3297 | 4203 | 2588 | The training program of technicians continued. The country is implementing a project to replace HCFC-22 for HC-290 in the air-conditioners, already more than 50 units have been converted. Refrigeration equipment sized by the custom were also converted to HC and delivered to schools and vocational centres. Some technicians visited Colombia in study tour to learn from the HC achievement in the country. | Training in cleaning refrigeration systems is planned in May 2013. International expert will train trainers and technicians during one week. Tools for the use with HC will be purchased. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (Umbrella project to phase-out HCFC-141b from the manufacturing of rigid polyurethane foam at Isotech Jaya Makmur, Airtekindo, Sinar Lentera Kencana and Mayer Jaya) | Multi-Year | ASP | IDS | PHA | 64 | INV | 194 | A | I | HCFC | 10.4 | 0 |  |  | 2011-07-01 | 2012-02-01 | 2012-03-31 | 2013-12-01 |  |  | 777395 | 0 | 777395 | 10015.03 | 1.288% | 767379.97 | 0 | 25000 | 58305 | 0 | 751 | 57554 | 0 | Draft agreements on implementation procedures have been communicated with beneficiaries and agreed in principle. The draft TORs were prepared. However, implementation modalities according to new financial rules of the Government of Indonesia, has not yet been settled due to lengthy process of approval throughout different ministries and Government departments (Ministry of Finance, Ministry of Planning, Bappenas). Contracting was delayed due to above mentioned reason. Action taken to eliminate the delay: UNIDO field office intervened through Ministry of Environment (Official letter) to have the project registered for "direct implementation", in accordance to new financial rules of Indonesian government for the implementation of foreign technical assistance. Disbursement is low due to the delays and reasons mentionedabove, and thus, equipment procurement could not start. | Purchase of equipment Reason for the delay: the implementation modalities according to new financial rules of the Government of Indonesia, has not been settled for a long period of time due to lengthy process of approval throughout different ministries and Government departments. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | IRA | PHA | 63 | INV | 202 | A | I | HCFC | 18.6 | 0 |  |  | 2011-04-01 | 2011-08-01 | 2015-03-31 | 2015-12-01 |  |  | 1300000 | 0 | 1300000 | 20483.36 | 1.576% | 1279516.64 | 1241335.17 | 500000 | 97500 | 0 | 1536 | 95964 | 93100 | Procurement of equipment completed for 7 companies, PO signed with the supplier, all factories assessed and monitored. Disbursement level at the end of 2012 does not reflect actual progress in the project, since by end 2012, 97% has already been committed. Accordingly, significant disbursement is expected in 2013. | Delivery and installation of equipment. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 209 | A | I | HCFC | 11.9 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2015-12-01 |  |  | 830000 | 0 | 830000 | 0 | 0% | 830000 | 0 | 100000 | 62250 | 0 | 0 | 62250 | 0 | The project was approved at the 68th Meeting of the Executive Committee. The Government was informed. Workplan was developed. Integral skin manufacturer assessed (3 companies) and alternative technology agreed with counterpart, small users in the panel and domestic refrigeration sectors monitored. Conversion of the latest will be addressed in 2013 (4 companies). | Procurement and installation of equipment for integral skin sector (3 companies) and remaining panel and domestic refrigeration companies (4 companies). |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | INV | 16 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2013-11-30 | 2013-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 10000 | 6000 | 0 | 0 | 6000 | 0 | Tender has been awarded, and contract has been established. The reason for the zero disbursement is that the Iraqi government had requested to adjust part of the tender to accommodate for abroad training for 15 Iraqis. After review of the possibility to accommodate the requirements set by the Iraqi government, it was highlighted that the cost and the logistical organization would be too high. | Plans for 2013: 1. Delivery of Equipment. 2. Installation and testing. In May 2013 the Iraqi Government has re- approved the tender and requested UNIDO to issue the contract. Due to this matter the order has pended for a couple of months. However, the supplier confirms that the task will be completed within 2013. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | INV | 36 | A | I | HCFC | 3.3 | 0 |  |  | 2012-04-01 |  | 2016-04-30 | 2016-04-01 |  |  | 460000 | 0 | 460000 | 33.72 | 0.00733% | 459966.28 | 0 | 10000 | 34500 | 0 | 3 | 34497 | 0 | The project was approved in 2012. PAD was issued and the Government was informed. The reason for the delay and the low disbursement is the delay in setting up an agreement between the NOU and the centre of excellence. | A mission to Abidjan took place in February 2013. A consultant will be hired to assess the needs of the center of excellence. Technical specification will be prepared and call for bids will then be issued in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (policy support, awareness promotion, monitoring) | Multi-Year | ASP | JOR | PHA | 65 | TAS | 90 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2013-11-30 | 2015-12-01 |  |  | 70000 | 0 | 70000 | 7491.93 | 10.7% | 62508.07 | 592.1 | 10000 | 6300 | 0 | 674 | 5626 | 53 | Monitoring the implementation of the WB in the foam sector was carried out. Legislation was under preparation. | The legislation will be finalized. UNIDO will continue monitoring the implementation of the WB. Reason for the extended project duration: It is in line with the HCFC phase-out target of 2015. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | KUW | PHA | 66 | INV | 18 | A | I |  | 0 | 0 |  |  | 2012-04-01 |  | 2014-04-30 | 2015-12-01 |  |  | 210160 | 0 | 210160 | 0 | 0% | 210160 | 0 | 20000 | 15762 | 0 | 0 | 15762 | 0 | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Coordination meeting with government and industry took place. 3. Workplan developed and agreed. The reason for the low disbursement is that the focus of the government of Kuwait is the XPS foam sector and any UNIDO activities related to the service sector activities will fall only after XPS sector is in progress. | 1. Expert has visited the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by end of 2013. For the Government, the priority is in the implementation of the approved projects in the manufacturing sectors. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Multi-Year | ASP | KUW | PHA | 66 | INV | 20 | A | I | HCFC | 10.9 | 0 |  |  | 2012-04-01 |  | 2014-04-30 | 2014-12-01 |  |  | 284628 | 0 | 284628 | 33.72 | 0.01185% | 284594.28 | 0 | 20000 | 21347 | 0 | 3 | 21344 | 0 | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Coordination meeting with government and industry took place. 3. Workplan developed and agreed. The reason for the low disbursement is that the focus of the government of Kuwait is the XPS foam sector and any UNIDO activities related to the PU sector activities will fall only after XPS sector is in progress. | 1. Expert has visited the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Comapny) | Multi-Year | ASP | KUW | PHA | 66 | INV | 21 | A | I | HCFC | 49.8 | 0 |  |  | 2012-04-01 |  | 2014-04-30 | 2014-12-01 |  |  | 3042662 | 0 | 3042662 | 33.72 | 0.001108% | 3042628.28 | 0 | 200000 | 228200 | 0 | 3 | 228197 | 0 | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Coordination meeting with government and industry took place. 3. Workplan developed and agreed. Although disbursement is low at the end of 2012, since the project beneficiary has thoroughly considered technologies and impact on production. TORs are prepared and tender will be advertised shortly and significant expenditure is expected during 2013. | 1. Expert has visited the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by end of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-12-01 |  |  | 140000 | 0 | 140000 | 94074.64 | 67.2% | 45925.36 | 2838.4 | 43087 | 10500 | 0 | 7056 | 3444 | 213 | TOR for equipment was finalized with NOU, contract was issued to supplier and equipment was delivered in April 2012. Train the trainers session held 14 - 17 January : 16 participants from 8 regions of Madagascar (two from each region). Training conducted by local consultant. | Wider dissemination of training will be carried out to enable technicians to perform retrofits successfully in preparation for the retrofit incentive scheme (with l'Union des Frigoriste de Madagascar) in the following tranche and also on a workshop for technicians in the fishing industry. Equipment to be distributed to servicing centers in the 8 regions. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, remainder of second tranche) | Multi-Year | EUR | MDN | PHA | 64 | INV | 31 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 | 2013-07-01 |  |  | 81000 | 0 | 81000 | 77660.9 | 95.88% | 3339.1 | 2322.39 | 1017 | 6075 | 0 | 5825 | 250 | 174 | Implementation of the HPMP second tranche was completed according to the work plan. During reporting period limits on import of HCFC-22 based air-conditioners were introduced through the licensing and quota system and order prohibiting export/import of HCFC containing products was developed. Four awareness raising workshops for service technicians as well as two for trainers were carried out. | All the activities have been carried out. The uncommitted balance of US$ 1,017 will be used to implement planned activities of the third tranche. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, third tranche) (conversion from HCFC-141b to HFCs in the manufacture of polyurethane foam for the commercial refrigeration units, sandwich panels and insulated doors) | Multi-Year | EUR | MDN | PHA | 67 | INV | 32 | A | I | HCFC | 1.6 | 0 |  |  | 2012-07-01 | 2012-11-01 | 2014-07-31 | 2014-07-01 |  |  | 136955 | 0 | 136955 | 481.99 | 0.3519% | 136473.01 | 0 | 90000 | 10272 | 0 | 36 | 10236 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012. A joint UNIDO/NOU team visited Koper, Negotino, the largest consumer of HCFC-141b producing domestic and commercial refrigeration appliances: refrigerators and display cases (48,000 units per year). Director of the company on the recently approved umbrella investment project in the foam sector, the selected conversion technology (Methyl Formate), the budget allocated to Koper and UNIDO procedures for procurement of equipment and services. It was agreed that the company and UNIDO national experts would prepare technical specification of the new foaming machine and submit them to UNIDO for the preparation of the TOR and international bidding arrangement. | Finalization of TOR on the supply of a new foaming machine followed by international bidding is planned for 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, third tranche) | Multi-Year | EUR | MDN | PHA | 67 | INV | 33 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2012-11-01 | 2013-07-31 | 2013-07-01 |  |  | 158000 | 0 | 158000 | 16497.39 | 10.44% | 141502.61 | 0 | 60000 | 11850 | 0 | 1237 | 10613 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012. A joint UNIDO/NOU team visited the country. Local consultants were recruited. The technical specifications and the scope of supply of R&R equipment were prepared and coordinated with the NOU. The international bidding was initiated. | Evaluation of bids received and placement of the purchase order. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b as a cleaning agent in refrigeration servicing) | Multi-Year | LAC | MEX | PHA | 64 | INV | 160 | A | I | HCFC | 4.3 | 4.3 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 | 2013-03-01 |  |  | 100000 | 0 | 100000 | 56693.73 | 56.69% | 43306.27 | 8075.01 | 20000 | 7500 | 0 | 4252 | 3248 | 606 | After the HPMP launching meeting in December 2011, there have been various stakeholders and awareness raising meetings with the service sector and training centres. 2 national experts have been hired to develop a training manual in good practices in cleaning of refrigeration and air-conditioning systems and substitutes for HCFCs. Manual was prepared and its English translation was being developed by the end of 2012. Training needs were assessed and technical specifications for equipment procurement were under preparation by the experts. The tranche was successfully completed in March 2013. | The tranche will be successfully completed in March 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (legislation customs training and monitoring) | Multi-Year | LAC | MEX | PHA | 64 | TAS | 158 | A | I | HCFC | 1.1 | 1.1 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 | 2013-03-01 |  |  | 125500 | 0 | 125500 | 116921.53 | 93.16% | 8578.47 | 2750 | 5000 | 9413 | 0 | 8769 | 644 | 206 | There were two main activities that were developed in coordination with the custom offices from the beginning of the implementation of the HCFC phase out programme: Adoption of custom registration code for HCFCs as well as Custom training and equipping. During the NPP implementation one of the most important aspects was to avoid illegal trade into México and also to avoid the movement of substances through México to other developing and developed countries. This gave priority to the custom officers training. Substantial progress was achieved also in this component and more than 50 customs and other related officials were trained in the gas identification, intelligence procedures, local and international prosecution procedures and other related environmental issues. More than 100 industrial stakeholders were informed on the HPMP implementation procedures. 12 identifiers were purchased and delivered to various customs offices. The tranche was successfully completed in March 2013. | The tranche will be successfully completed in March 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (umbrella project for conversion from HCFC-141b to cyclopentane insulation foam blowing technology at three refrigeration appliances manufacturing enterprises: FERSA, Frigopanel and Metalfrio) | Multi-Year | LAC | MEX | PHA | 64 | INV | 157 | A | I | HCFC | 23 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2014-01-31 | 2014-10-01 |  |  | 2046110 | 0 | 2046110 | 11139.45 | 0.5444% | 2034970.55 | 140000 | 500000 | 153458 | 0 | 835 | 152623 | 10500 | Frigopanel and Metalfrio were visited in December 2011 after the HPMP launching meeting. Fersa company was also planned to be visited at the same time, but due to a management change of the enterprise, no visit was possible to their premises. Final approved project was presented to the visited companies and requirements for the conversion activities were discussed and agreed upon with Frigopanel and Metalfrio. Main elements for the Terms of Reference were agreed upon and the final TOR was agreed upon in the first quarter of 2012. Bidding was completed in May 2012. Frigopanel informed UNIDO before the finalization of the technical evaluation that they were considering the introduction of another low-GWP alternative, thus, UNIDO was requested to cancel the bidding. Although technical evaluation was finished and agreed upon with Metalfrío end July 2012, there were some delays in the finalization of the contract, since some last-minute modifications were proposed by the new technical manager of the beneficiary. Although it was expected that the contract can be issued by the end of November 2012, the Purchase Order was approved in December 2012 and the contract was signed only in January 2013. | Frigopanel and Fersa companies were visited end January by an expert to discuss the issues raised by them and to review again the final selected technology, related costs and technical requirements for implementation. Availability, advantages and disadvantages of the various technologies were presented to both Frigopanel and Fersa. Fersa had a new team assigned to the conversion project and they showed full commitment in implementing the project in an accelerated manner. Both companies have confirmed their decision to go for cyclopentane. TORs were drafted in March. TOR for Frigopanel-Ojeda was cleared and bidding started end April 2013. Clearance of TOR by Fersa is pending company's management decision. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 68 | INV | 164 | A | I | HCFC | 11.4 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2013-12-01 |  |  | 695011 | 0 | 695011 | 0 | 0% | 695011 | 0 | 140000 | 52126 | 0 | 0 | 52126 | 0 | The tranche was approved in December 2012. Subsequently, still in 2012, the PAD was issued. | A UNIDO mission was organized in March 2013 to finalize the agreement on the activities and the implementation plan. Final review of the new manual for technicians on good maintenance practices was finished in April 2013 and it will be shortly printed in at least 1,000 copies. This will be the basis for Stage I HPMP service sector training activities. Training of trainers (50-60) will be organized after May in 12 public training centers selected by SEMARNAT and the Ministry of Education. This will be followed by large-scale training activities. TOR for the equipment and tools required for the training have been agreed upon with SEMARNAT end March 2013. Bidding started in April 2013. In addition, 2 training courses will be organized for customs trainers, one in Matamoros and one in Manzanillo in May/June 2013; |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | INV | 32 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-05-01 |  |  | 60000 | 0 | 60000 | 58425.47 | 97.38% | 1574.53 | 1137.39 | 1000 | 5400 | 0 | 5258 | 142 | 102 | TOR was finalized with NOU. After international bidding process, contract was issued to supplier. Equipment was delivered in April 2012. Training by supplier took place in Lilongwe in July 2012. The second training session took place 3 - 6 December 2012 in Lilongwe. 22 participants attended. Two training sessions similar, included retrofits of actual A/Cs. | The request for the second tranche report is planned to be submitted to the 70th Meeting of the Executive Committee. The project is expected to be completed in 2013. UNEP is the lead agency. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOG | PHA | 63 | INV | 08 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-10-01 | 2013-03-31 | 2013-12-01 |  |  | 155000 | 0 | 155000 | 79474.83 | 51.27% | 75525.17 | 90.54 | 50000 | 11625 | 0 | 5961 | 5664 | 7 | Training conducted in the fourth quarter of 2012 and equipment delivered. | Preparation of 2nd tranche submission. Continuations of the training programe. Recruitment of national staff. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 65 | INV | 68 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-03-01 | 2012-11-30 | 2013-07-01 |  |  | 80000 | 0 | 80000 | 18627.2 | 23.28% | 61372.8 | 100 | 30000 | 6000 | 0 | 1397 | 4603 | 8 | Launching ceremony was conducted in June 2012. Measures to revise ODS policies as well as adoption of measures on licensing system under execution. | Training of custom authorities as well as purchase of equipment for the replacement of HCFC 141b in the flushing of refrigeration circuits sector expected to be implemented in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 68 | INV | 69 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2017-12-31 | 2017-12-01 |  |  | 220000 | 0 | 220000 | 0 | 0% | 220000 | 0 | 30000 | 16500 | 0 | 0 | 16500 | 0 | Launching ceremony was conducted in June 2012. Measures to revise ODS policies as well as adoption of measures on licensing system under execution. | Training of custom authorities as well as purchase of equipment for the replacement of HCFC 141b in the flushing of refrigeration circuits sector expected to be implemented in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MOZ | PHA | 66 | INV | 23 | A | I | HCFC | 0.3 | 0 |  |  | 2012-04-01 |  | 2016-04-30 | 2016-04-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 10000 | 6750 | 0 | 0 | 6750 | 0 | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Coordination meeting with government and industry took place. 3. Workplan developed and agreed. Due to difficulties scheduling start-up mission and agree on exact equipment needs, current disbursement is low. Substantial disbursement is planned by end 2013. | 1. Joint mission with UNEP planned for the second quarter of 2013. 2. Agreement of equipment scope and advertisement of tender. 3. Equipment supply end 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | INV | 28 | A | I | HCFC | 1.7 | 0 |  |  | 2012-04-01 | 2012-11-01 | 2016-04-30 | 2016-04-01 |  |  | 175000 | 0 | 175000 | 13237.15 | 7.564% | 161762.85 | 0 | 25000 | 13125 | 0 | 993 | 12132 | 0 | Activities implemented in 2012: The project was approved at the 66th Meeting of the Executive Committee. The Government was informed. Train the trainer component for the refrigeration technicians was organized in 2012, focusing on the results of the NPP and addressing additional needs with a view to HCFCs. The main reason for the low disbursement is that the contract for the equipment component (which is the main component of the project) will only be signed in 2013 after completion of UNEP's training component. | Workplan for the year 2013 and Terms of Reference for subcontract with counterpart for implementation of the policy component is under agreement with counterpart. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | NIC | PHA | 66 | INV | 27 | A | I | HCFC | 0.5 | 0 |  |  | 2012-04-01 | 2012-09-01 | 2015-04-30 | 2015-04-01 |  |  | 96500 | 0 | 96500 | 6065.65 | 6.286% | 90434.35 | 0 | 60000 | 8685 | 0 | 546 | 8139 | 0 | Activities implemented in 2012: The project was approved at the 66 the Meeting of the Executive Committee in 2012. The Government was informed. The first mission took place only in September since a joint mission with UNEP was required. Vocational centres were visited, some tools are required to upgrade the centres but it is planned to establish new centres in different locations. At present the centres are only in Managua. The reason for the low disbursement is that the joint mission with UNEP could only be organized in September 2012. Substantial progress is expected in 2013. | National expert was hired for the monitoring of the project. International expert visited the country in March to train trainers and technicians in different cities. At the same time, bases for the creation of code of practice will be established by the UNIDO consultant. Once the new training centres are defined, the TOR will be prepared and tools purchased. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 129 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 | 2013-12-01 |  |  | 550000 | 0 | 550000 | 48127.55 | 8.75% | 501872.45 | 72.72 | 100000 | 41250 | 0 | 3610 | 37640 | 5 | The TOR on the procurement of low pressure foaming machines prepared and coordinated with the NOU. It was agreed to accommodate first the end-users located in Ibadan (29 companies) and Abuja (24 companies). However, international bidding was delayed as it was found that none of the project beneficiaries had the power supply of 380 V, 3 phases, 50 Hz required to run the new foaming equipment. The NOU was requested to obtain a written commitment by project beneficiaries to ensure the adequate power supply by the time of equipment delivery. Low funds disbursement is the result of delay of the bidding for the supply of new low pressure PU foam injection equipment . The reason for that was that the power supply at the beneficiaries was not appropriate for the new equipment. | It is expected to obtain written commitment by project beneficiaries to ensure the adequate power supply. International bidding, evaluation of proposals received and placement of purchase order. The project is expected to be completed in 2013. Reason for the delay: Power supply at the beneficiaries was not appropriate for the new equipment. In the meantime commitment from the beneficiaries to arrange adequate power supply was obtained. USD 500,000 has already been obligated in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration air-conditioning manufacturing and coordination) | Multi-Year | AFR | NIR | PHA | 66 | INV | 131 | A | I |  | 0 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2013-12-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 0 | 100000 | 41250 | 0 | 0 | 41250 | 0 | The project was approved at the 66th Meeting of the Executive Committee in 2012. PAD was issued, Government was informed about the approval; The TOR on the procurement of low pressure foaming machines prepared and coordinated with the NOU. It was agreed to accommodate first the end users located in Ibadan (29 companies) and Abuja (24 companies). However, international bidding was delayed as it was found that none of the project beneficiaries had the power supply of 380 V, 3 phases, 50 Hz required to run the new foaming equipment. NOU was requested to obtain a written commitment by project beneficiaries to ensure the adequate power supply by the time of equipment delivery. Actions were taken to get commitment letters from the beneficiaries to ensure adequate power supply. Delays in the procurement activies due to the issue of power supply were the main reasons for low disbursement during 2012. | It is expected to obtain written commitment by project beneficiaries to ensure the adequate power supply. International bidding, evaluation of proposals received and placement of purchase order. The project is expected to be completed in 2013. Reason for the delay: Power supply at the beneficiaries was not appropriate for the new equipment. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the foam sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 24 | A | I | HCFC | 2.3 | 0 |  |  | 2011-11-01 | 2012-05-01 | 2012-12-31 | 2013-12-01 |  |  | 104120 | 0 | 104120 | 16068.44 | 15.43% | 88051.56 | 61.17 | 87990 | 7809 | 0 | 1205 | 6604 | 5 | UNIDO international foam expert visited the four foam manufacturing companies identified under the HPMP. He assessed the needs of the companies using HCFCs in pre-blended polyols and advised on their conversion to non-ozone depleting blowing agents, as part of the technical assistance component. He also visited National Heaters Industry (NHI) LLC to discuss the technical and financial implications their conversion to water-blown technology. A draft specification was agreed upon during the mission. A final draft was sent to NHI for comments in September 2012. The specifications are still being discussed. NHI would like to clarify some issues before going ahead. | UNIDO mission took place in February 2013. Once the TOR is finalized, tender will be raised in 2013 as soon as possible. Reason for the delay: TOR for water-blown foaming machine is still to be agreed with NHI. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 23 | A | I | HCFC | 2.3 | 0 |  |  | 2011-11-01 |  | 2015-11-30 | 2015-11-01 |  |  | 210000 | 0 | 210000 | 7455.36 | 3.55% | 202544.64 | 0 | 26000 | 15750 | 0 | 559 | 15191 | 0 | PAD was issued and the Government was informed about the approval. Reason for the low disbursement was the delay in agreement of TOR for NHI resulted in funds for foam component not being disbursed. Also, the mission of refrigeration expert to identify potential sites for the set up of recovery and reclaim centers had been postponed to 2013. | UNIDO international refrigeration expert visited Muscat 2-6 March 2013 with regards to the establishment of a centralized refrigerant recovery network. The expert also visited potential reclaim centers. (NOU was previously sent a questionnaire to identify potential sites). Based upon the findings of the expert and his discussions with the NOU, a TOR for equipment for a reclaim center and servicing tools will be drafted. TOR will be finalized with NOU. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | INV | 79 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-03-01 |  |  | 68000 | 0 | 68000 | 61450.35 | 90.37% | 6549.65 | 2929.76 | 3620 | 5100 | 0 | 4609 | 491 | 220 | UNIDO investment component completed. Monitoring, data collection and reporting is being finalized. Report and request for 2013 Tranche was submitted to 69th Executive Committee Meeting, however on the request of the Secretariat the submission is shifted to the 70th Meeting. | Project will be completed in Mar 2013. The request for the next tranche will be submitted to the 70th Meeting. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | INV | 23 | A | I |  | 0 | 0 |  |  | 2011-04-01 |  | 2013-03-31 | 2013-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 100000 | 100000 | 9000 | 0 | 0 | 9000 | 9000 | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. Disbursement at the end of 2012 was limited due to the IPSAS, although by the end of 2012 most of the funds were committed. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | INV | 18 | A | I | HCFC | 1.6 | 0 |  |  | 2011-11-01 |  | 2013-11-30 | 2014-12-01 |  |  | 131157 | 0 | 131157 | 0 | 0% | 131157 | 0 | 20000 | 9837 | 0 | 0 | 9837 | 0 | 1. Project and remaining funding moved to approved HPMP. The reason for the low disbursement is that no major progress could be made before Qatar has officially appointed the NOU, which took place only early 2013. | Reason for the extension of the project duration: Changes in the NOU. Qatar has officially appointed the NOU, which took place only early 2013. In the meantime, TOR's have been prepared. It is envisioned that the contract will be issued by September. This is taking in account the time required to advertize the tender, evaluate the offers and to obtain internal approval. It is estimated that 80% of the available UNIDO balance will be allocated to these contracts. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | Multi-Year | ASP | QAT | PHA | 65 | INV | 19 | A | I | HCFC | 19.1 | 0 |  |  | 2011-11-01 | 2012-09-01 | 2013-11-30 | 2014-12-01 |  |  | 914750 | 0 | 914750 | 8032.92 | 0.8782% | 906717.08 | 0 | 50000 | 68606 | 0 | 602 | 68004 | 0 | 1. HPMP approved at the 65th Meeting of the Executive Committee. 2. Coordination meeting with government and industry took place. 3. Workplan developed and agreed. The reason for the low disbursement is that no major progress could be made before Qatar has officially appointed the NOU, which took place only early 2013. | 1. Expert has visited the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by the end of 2013. Implementation with the new NOU already restarted. Reason for the extension of the project duration: No NOU officer(s) were appointed for a long period of time. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | INV | 18 | A | I | HCFC | 0.2 | 0 |  |  | 2011-07-01 | 2012-11-01 | 2016-07-31 | 2016-07-01 |  |  | 55000 | 0 | 55000 | 6710.78 | 12.2% | 48289.22 | 0 | 35000 | 4950 | 0 | 604 | 4346 | 0 | A mission to Rwanda took place in October 2012. Implementation modalities were discussed with the NOU and recycling centers visited. Strategies for upgrading those centers were discussed and detailed TOR for equipment prepared. | Bidding will be conducted during the first half of 2013. The delivery of equipment and upgrade of the recycling centers will be coordinated with UNEP (in charge of the training activities under the HPMP) to ensure that the new equipment supports the training most effectively. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2015-12-31 | 2015-12-01 |  |  | 341733 | 0 | 341733 | 0 | 0% | 341733 | 0 | 100000 | 23921 | 0 | 0 | 23921 | 0 | The project was approved in 2012. The Government was informed. | Consultation with NOU and UNEP held in January 2013. Expert mission for specification for 14 companies of the PU foam sector - March/April Project Management Unit established April Survey of the RAC sector Developing a national strategy for end users in the RAC sector to minimise ODS emissions Developing infrastructure for certification in the RAC sector Review and update curriculum for technical and vocational qualifications relating refrigeration and air-conditioning. Provision of training equipment to educational institutions related to refrigeration and air-conditioning Progress made to issues raised in relevant status reports; |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | INV | 19 | A | I | HCFC | 52.1 | 0 |  |  | 2012-12-01 |  | 2015-12-31 | 2015-12-01 |  |  | 1827867 | 0 | 1827867 | 0 | 0% | 1827867 | 0 | 300000 | 127951 | 0 | 0 | 127951 | 0 | The project was approved in 2012. The Government was informed. | Consultation with NOU and UNEP held in January 2013. Expert mission for specification for 14 companies of the PU foam sector - March/April Project Management Unit established April Call for offers on equipment for 2-3 companies in the PU foam sector April-June and further 3 companies August - September National expert to collect data on SME downstream users March - June Expert misssion to develop specifications for systems houses - April/May Call for offers for further 3 companies of the PU sector June - September Procurement of equipment for the first 3 companies of the PU foam sector for the SHs July - December |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | INV | 31 | A | I | HCFC | 2.4 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2014-11-30 | 2014-11-01 |  |  | 200000 | 0 | 200000 | 2419.6 | 1.21% | 197580.4 | 26.56 | 80000 | 15000 | 0 | 181 | 14819 | 2 | Activities implemented in 2012: 'National consultant contracted to review ToR and assess the required no. and type of equipment to be delivered to service shops. The subcontract with the counterpart as per the ToR was finalized in December 2012. The main reason for the low disbursement is that the contract for the equipment component (which is the main component of the project) will only be signed in 2013 after completion of UNEP's training component. | National consultant report and technical specification for equipment delivery to be finalized in May 2013. The subcontract with counterpart will be processed first half of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0 |  |  | 2011-11-01 |  | 2016-11-30 | 2013-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 47620 | 2380 | 4500 | 0 | 0 | 4500 | 4286 | TOR finalized with NOU.Contract was issued to supplier in December 2012. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 95% of the funds have been committed. | Equipment was shipped and supposed to arrive in May 2013. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 67 | TAS | 04 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2013-07-31 | 2014-07-01 |  |  | 110005 | 0 | 110005 | 0 | 0% | 110005 | 0 | 80000 | 7700 | 0 | 0 | 7700 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of workshops; assistance to the government on reporting and legislation. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SOM | PHA | 67 | INV | 08 | A | I | HCFC | 0.5 | 0 |  |  | 2012-07-01 |  | 2016-07-31 | 2016-07-01 |  |  | 133500 | 0 | 133500 | 0 | 0% | 133500 | 0 | 10000 | 9345 | 0 | 0 | 9345 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of of workshops. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (additional security) | Multi-Year | AFR | SOM | PHA | 67 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2016-07-31 | 2016-07-01 |  |  | 40374 | 0 | 40374 | 0 | 0% | 40374 | 0 | 20000 | 2826 | 0 | 0 | 2826 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012 on an exceptional basis, and without setting a precedent for any future projects, the security-related costs in addition to the funding of the first tranche of stage I of the HPMP to enable the implementation of the programme. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of of workshops. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | INV | 17 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-04-01 | 2012-07-31 | 2013-11-01 |  |  | 88850 | 0 | 88850 | 460.7 | 0.5185% | 88389.3 | 82672 | 88000 | 7997 | 0 | 41 | 7956 | 7440 | The project site was visited and HPMP implementation planned. Based on the needs some tools for vocational centres and trained technicians were purchased. Tools for the training centres were purchased and delivered to the country. Disbursement at the end of 2012 does not reflect actual progress of the project. Contract for equipment purchase was signed in 2012 and 94% of the funds have been committed by end 2012. | The tools arrived in February 2013. The activities are linked with the second tranche UNIDO project MPSTL12001 Reason for the delay: The coordination with the counterparts, the procurement process and the shipment took longer than expected. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | INV | 21 | A | I | HCFC | 0.1 | 0 |  |  | 2012-12-01 |  | 2015-12-31 | 2015-12-01 |  |  | 11000 | 0 | 11000 | 0 | 0% | 11000 | 0 | 5000 | 990 | 0 | 0 | 990 | 0 | The project was approved at the 68th Meeting of the Executive Commitee in Decemeber 2012. The Government was informed. | Training of trainers and workshop on drop-in with HC is planned to be carried out in the country. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | INV | 20 | A | I | HCFC | 0.1 | 0 |  |  | 2011-07-01 |  | 2014-12-31 | 2014-12-01 |  |  | 124115 | 0 | 124115 | 0 | 0% | 124115 | 62466.25 | 43000 | 11170 | 0 | 0 | 11170 | 5622 | TOR finalized with NOU.Contract was issued to supplier in December 2012. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 50% of the funds have been committed. | Equipment was shipped and supposed to arrive in summer 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SUD | PHA | 66 | INV | 29 | A | I |  | 0 | 0 |  |  | 2012-04-01 |  | 2013-04-30 | 2014-03-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 20000 | 18750 | 0 | 0 | 18750 | 0 | The project was approved at the 66th Meeting of the Executive Committee. In December 2012 a national consultant was recruited. Technical assistance including equipment was provided to manufacturing companies in refrigeration sector. Project is implemented as planned. Training programme including purchase of training and servicing equipment is being prepared. Only technical assistance to the foam companies was planned for 2012. Funds disbursed in 2012 are low due to delays in preparation of TORs. National project officer/coordinator to be contracted to follow up with training, public awareness and monitoring activities. | Refreshment trainings for different groups (custom officers; trainers at training centers (e.g. IRCC) and schools (e.g. SUST Khartoum) as a follow up to earlier established RMP. Review of training facilities; identify the needs for training programs and training equipment (for demonstration, servicing, monitoring/identification of refrigerants). Technical and public awareness workshops on alternative technologies to be considered for HPMP, Stage II. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | INV | 18 | A | I | HCFC | 0.1 | 0 |  |  | 2011-11-01 |  | 2016-11-30 | 2013-12-01 |  |  | 68000 | 0 | 68000 | 0 | 0% | 68000 | 57178.4 | 10822 | 6120 | 0 | 0 | 6120 | 5146 | TOR finalized with NOU. Contract was issued to supplier in October 2012. Equipment was shipped out early January 2012. Disbursement level at the end 2012 does not reflect actual progress. By the end of 2012 84% of the funds have been committed. | The equipment is arrived at Paramaribo in March 2013. The NOU handled customs clearance. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | TKM | PHA | 62 | INV | 08 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 309050 | 0 | 309050 | 13165.94 | 4.26% | 295884.06 | 0 | 150000 | 23179 | 0 | 987 | 22192 | 0 | Agreement with the Government signed. National staff for the NOU and international experts recruited. Stakeholder meeting conducted. "Low cost" activities (like monthly salaries) are the reason for low disbursement figures. The majority of the funds is reserved for equipment that is implemented in 2013. | Equipment delivery is planned for the first quarter of 2013. Contract for the IS component is under preparation. Workshop is planned the first half of the year. The equipment for the training curses will be purchased locally. The trainers are under recruitment. UNIDO mission is planned for May 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2013-12-01 |  |  | 200000 | 0 | 200000 | 120733.38 | 60.37% | 79266.62 | 64.84 | 79202 | 15000 | 0 | 9055 | 5945 | 5 | Contract was issued to supplier and equipment was delivered in May 2012. Training on the use of equipment, general refrigeration practices, recycling and reclamation by supplier took place in Lome in September 2012. | Remaining funds are being spent on wider dissemination of training to enable technicians to successfully carry out retrofits in preparation for the retrofit incentive scheme planned for the following tranches. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | EUR | TUR | PHA | 68 | INV | 100 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2014-12-01 |  |  | 658470 | 0 | 658470 | 0 | 0% | 658470 | 0 | 80000 | 46093 | 0 | 0 | 46093 | 0 | The project was approved at the 68th Meeting of the Executive Committee in November 2012. The Government was informed. | Mission and meeting with the NOU is scheduled for the second quarter of 2013 to initiate the implementation and agree on activities priority, due to limited budget of the first tranche. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 102 | A | I | HCFC | 16.3 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2014-12-01 |  |  | 149280 | 0 | 149280 | 0 | 0% | 149280 | 0 | 80000 | 10450 | 0 | 0 | 10450 | 0 | The project was approved at the 68th Meeting of the Executive Committee in November 2012. The Government was informed. | UNIDO mission and meeting with the NOU is scheduled for the second quarter of 2013. International consultant field visit to agree workplan with the SH companies to take place during the second quarter of 2013. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2016-12-31 | 2016-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 25000 | 3600 | 0 | 0 | 3600 | 0 | The project was approved at the 68th Meeting of the Executive Commitee in Decemeber 2012. The Government was informed. | A joint mission with UNEP is planned in May 2013. A that the implementing activities will start. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | INV | 30 | A | I | HCFC | 0.1 | 0 |  |  | 2012-07-01 |  | 2015-07-31 | 2015-07-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 30000 | 4500 | 0 | 0 | 4500 | 0 | Project approved in July 2012. UNIDO approach the NOU and it was agreed to wait for the joint mission. | A joint mission is planned with UNEP in June 2013. The main plan for 2013 is to equip the vocational centres with tools and work with alternatives. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | INV | 118 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 | 2013-12-01 |  |  | 654854 | 0 | 654854 | 277061.52 | 42.31% | 377792.48 | 139634.52 | 200000 | 49114 | 0 | 20780 | 28334 | 10473 | More than 80 trainers were trained in good refrigeration practices. A survey was carried out to verify the needs of the INCES (vocational centres) in terms of tools. Some INCES received from the NPP didactic tools and the objective was to review the condition of the tools and real requirements. Tools for the equivalent of 36 training centres were purchased and delivered to the country. National consultants were hired for the implementing activities of the project. | Training of 20 more trainers to complete the cycle. The program for training and certification technicians will continue. Other activities are linked with the second tranche UNIDO project MPVEN12001 Reason for the delay: Change of the National Ozone Officer. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | INV | 120 | A | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2013-07-31 | 2014-07-01 |  |  | 603339 | 0 | 603339 | 0 | 0% | 603339 | 0 | 100000 | 45250 | 0 | 0 | 45250 | 0 | The project was approved in July 2012. Activities were implemented in parallel with the First tranche. Contract for implementing services were prepared for the NOU. Mission was carried out to the country for project monitoring. | Training of technicians and certification program will continue. TOR for refrigeration simulators working with HC will be made. A pilot project to convert a small hotel to HC (propane) will be implemented as pilot project. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 39 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2014-12-31 | 2014-12-01 |  |  | 410000 | 0 | 410000 | 0 | 0% | 410000 | 0 | 150000 | 28700 | 0 | 0 | 28700 | 0 | The project was approved in 2012. The Government was informed. | Specification for supply of identifier units - April Equipment purchase - May - July Specification for upgrade of R&R units and recycle/recovery kits - August Equipment purchase - September - November |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | INV | 38 | A | I | HCFC | 2.3 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 360130 | 0 | 360130 | 119323.95 | 33.13% | 240806.05 | 15849.52 | 100000 | 27010 | 0 | 8949 | 18061 | 1189 | Non-investment activities in connection with legislation review were under implementation. Train the trainers component and trainers certification for refrigeration service technicians took place 29 October - 6 November 2012. Both mentioned activities were built up on the latest results of the NCPP technicians training of August 2012. Non-investment activities under UNEP lead have been intensively organized jointly with NOU. Under the investment component, conversion of ALFA KLIMA was finalized in September 2012 | Field mission will be organized 2nd quarter of 2013 to asses the possibility to convert one more enterprise before second tranche aproval (having in view that the HPMP investment funding is divided in 2 tranches, and 50% of the funds are subject to approval of the 71st Meeting of the Executive Committee). |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | INV | 26 | A | I | HCFC | 0.4 | 0 |  |  | 2011-07-01 |  | 2016-07-31 | 2016-07-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 65000 | 6300 | 0 | 0 | 6300 | 0 | TORs for the equipment for training purposes for vocational training institution and refrigerant centers have been finalized. Contract with provider was signed in March 2013 and delivery of equipment and installation are under execution. This explains the zero disbursement in 2012. | Bidding for training equipment was done in January and the contract will be avarded as soon as possible. Training is planned for the second quarter of 2013. A mission is planned in June 2013. |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | DRK | PHA | 64 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 | 2013-12-01 |  |  | 65000 | 0 | 65000 | 33015.76 | 50.79% | 31984.24 | 0 | 10000 | 4875 | 0 | 2476 | 2399 | 0 | The project will be included into the HPMP. However, the HPMP could not be submitted to the 67th Meeting of the Executive Committee in 2012. | Resubmission of the HPMP to the 69th Meeting of the Executive Committee in 2013. Reason for the delay: Significant delays in the collection and submission of requested data and information by local consultants. |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | LIB | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 64675.49 | 76.09% | 20324.51 | 3100 | 3000 | 6375 | 0 | 4851 | 1524 | 233 | Desk study on HPMP preparation has been completed. Field inspections; identification and verification of the manufacturing facilities have not been possible to carry out. The survey could not be completed and stakeholder workshop was postponed. | To recruit national consultant to help NOU with field visits; verify the consumption of HCFCs, prepare HPMP. Mission preparation is in progress. Reason for the delay: the security and social situation in the country that have not improved and stabilized. |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SYR | PHA | 55 | PRP | 97 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2013-12-01 |  |  | 136250 | 0 | 136250 | 108362.56 | 79.53% | 27887.44 | 27960 | 1000 | 10219 | 0 | 8127 | 2092 | 2097 | HPMP project document was submitted for discussion at 68th Meeting of the Executive Committee. Resubmission of the HPMP at a future meeting when national conditions have improved. |  |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | TUN | PHA | 55 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2013-12-01 |  |  | 150000 | 0 | 150000 | 115924.09 | 77.28% | 34075.91 | 4715.61 | 29000 | 11250 | 0 | 8694 | 2556 | 354 | The HPMP was finalized. UNIDO is in the process of obtaining agreement and endorsement from national authorities. | The HPMP will be submitted to the 71st Meeting of the Executive Committee in July 2013. Reason for the delay: 1. Government authorities requested changes in the project document. 2. The endorsement of the authorities is stilll awaited. |  |  | NON-INV
TRF | IBRD | Preparation of a HCFC phase-out management plan |  | LAC | ECU | PHA | 55 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 |  |  | 2009-11-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 11250 | -11250 | 0 | 0 | 0 | Preparation activity transferred to UNEP and UNIDO at the 59th ExCom Meeting. |  |  |  | Non-INV
TRF | IBRD | Preparation of a HCFC phase-out management plan (refrigeration and air-conditioning sectors) |  | ASP | SRL | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-12-31 |  |  | 2010-07-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project preparation of HCFC phaseout in the refrigeration and AC sectors was transferred to UNDP at the 61st ExCom Meeting. |  |  |  | Non-INV
TRF | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 157 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 |  |  | 2011-11-01 | 95750 | -43657 | 52093 | 52093.19 | 100% | -0.19 | 0 | 0 | 7181.25 | -3274.525 | 3906.7392 | -0.014249 | 0 | Project PRP transferred to UNIDO and remaining funds returned to MLF. | Project PRP transferred to UNIDO and remaining funds returned to MLF. | 2008 |  | Investment
FIN | UNEP | Deliver OAIC-DV and other OzonAction Programme information through World Wide Web home page site on a one year trial basis | Individual | GLO | GLO | SEV | 19 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 | 0 | 1885 | 0 | 1885 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Organizing a global video competition on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 206 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2000-09-01 |  | 2002-11-01 | 2006-01-01 | 60000 | -42676 | 17324 | 17324 | 100% | 0 | 0 | 0 | 7800 | -5547.92 | 2252.12 | -0.04 | 0 | Project financially completed. |  |  | 2001-10-01 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 110 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Deliver OzonAction newsletter and other information through the World Wide Web home page | Individual | GLO | GLO | SEV | 21 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. ($1191 plus $155 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through World Wide Web home page site | Individual | GLO | GLO | SEV | 23 | TAS | 143 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. ($ 1,750 plus $,228 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through world wide web home page site (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 162 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through worldwide web home page site (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 202 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 26250 | 0 | 26250 | 26250 | 100% | 0 | 0 | 0 | 3413 | 0 | 3413 | 0 | 0 | Project financially completed. ($ 2,353 plus $ 306 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Support to national activities (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 102 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-05-01 | 1999-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Continue to maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 19 | TAS | 105 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to national activities (1998) | Individual | GLO | GLO | SEV | 23 | TRA | 148 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-10-01 |  | 1998-10-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 79 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 21 | TAS | 131 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Translation and printing of OzonAction documents into French, Spanish and Arabic | Individual | GLO | GLO | SEV | 30 | TAS | 207 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-05-01 | 2001-03-01 |  | 2001-12-01 | 2002-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 9,321 plus $ 1,212 PSC returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Deliver OzonAction Newsletter and other information through world wide web home page site in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 220 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 8212 plus $ 1068 returned to ExCom 50. $ 18,000 plus $ 2,340 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 23 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-08-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 26 | TAS | 166 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. ($ 3,500 plus $ 455 PSC returned ExCom 33) |  |  |  | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 201 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Maintain contact database of experts and mailing list for OzonAction programme publications in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 225 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. ($ 13,971 plus $ 1,816 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 101 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 6240 | 0 | 6240 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Outreach at conferences and workshops (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 123 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Develop awareness materials for 1999 freeze to support national initiatives on awareness raising | Individual | GLO | GLO | SEV | 21 | TAS | 128 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 152 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | New awareness raising activities and materials for dissemination to the general public | Individual | GLO | GLO | SEV | 30 | TAS | 209 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-02-01 |  | 2001-12-01 | 2002-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 226 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 55000 | -5 | 54995 | 54995 | 100% | 0 | 0 | 0 | 7150 | -1 | 7149.35 | -0.35 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 192 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Query-response service (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 67 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | Individual | GLO | GLO | SEV | 39 | TAS | 248 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-03-01 |  | 2008-05-01 | 2009-05-01 | 75000 | -8215 | 66785 | 66785 | 100% | 0 | 0 | 0 | 9750 | -1067.95 | 8682.05 | 0 | 0 | Project financially completed. ($ 111,925 plus $ 8954 PSC returned to ExCom 50US$ 101,599 plus US$ 8,128 PSC returned to ExCom 54US$ 56,023 plus US$ 4,482 PSC returned to ExCom 55US$ 34,989 plus US$ 2,799 PSC returned to ExCom 56) |  |  | 2005-09-01 | Non Investment
FIN | UNEP | Update the OAIC CD-Rom | Individual | GLO | GLO | SEV | 29 | TAS | 186 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-01-01 | 2002-01-01 | 69300 | 0 | 69300 | 69300 | 100% | 0 | 0 | 0 | 9009 | 0 | 9009 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 214 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Project financially completed. ($13,916 plus $ 1,809 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 142 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. ($ 2,950 plus $ 383 PSC returned ExCom 33) |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 168 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 197 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 84000 | 0 | 84000 | 84000 | 100% | 0 | 0 | 0 | 10920 | 0 | 10920 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide direct query-response service in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 217 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Project financially completed. ($ 5,051 plus $ 657 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 164 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 | 0 | 11570 | 0 | 11570 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Develop materials to educate children on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 210 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2004-07-01 | 2006-02-01 | 100000 | -10448 | 89552 | 89552 | 100% | 0 | 0 | 0 | 13000 | -1359 | 11641.76 | -0.76 | 0 | Project financially completed. |  |  | 2003-07-01 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 196 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 93450 | 0 | 93450 | 93450 | 100% | 0 | 0 | 0 | 12149 | 0 | 12149 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 19 | TAS | 100 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-12-01 | 1999-01-01 | 104500 | 0 | 104500 | 104500 | 100% | 0 | 0 | 0 | 13585 | 0 | 13585 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 21 | TAS | 120 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-02-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 23 | TAS | 139 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 | 0 | 14560 | 0 | 14560 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 29 | TAS | 193 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 117600 | 0 | 117600 | 117600 | 100% | 0 | 0 | 0 | 15288 | 0 | 15288 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance for regional awareness raising (2005) | Individual | GLO | GLO | SEV | 45 | TAS | 262 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2008-12-01 | 2012-11-01 | 200000 | -60190 | 139810 | 139810 | 100% | 0 | 0 | 0 | 26000 | -7824.7 | 18175.3 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Regional awareness raising and South-South assistance | Individual | GLO | GLO | SEV | 32 | TAS | 224 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2001-12-01 |  | 2004-12-01 | 2006-01-01 | 191000 | -26212 | 164788 | 164788 | 100% | 0 | 0 | 0 | 24830 | -3408 | 21422.44 | -0.44 | 0 | Project financially completed. |  |  | 2003-07-01 | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 82 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-08-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 | 0 | 23400 | 0 | 23400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Disseminate information (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 77 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Sectoral data collection (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1997-03-01 | 1999-02-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 | 0 | 27950 | 0 | 27950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Disseminate information | Individual | GLO | GLO | SEV | 19 | TRA | 113 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-05-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 221 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 280000 | -5051 | 274949 | 274949 | 100% | 0 | 0 | 0 | 36400 | -656.63 | 35743.37 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Disseminate awareness material, technical, and policy information in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 219 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 346000 | -13916 | 332084 | 332084 | 100% | 0 | 0 | 0 | 44980 | -1809.08 | 43170.92 | 0 | 0 | Project financially completed. ($ 7,392 plus $ 961 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 21 | TAS | 118 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 23 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. ($ 10,000 plus $ 1,300 PSC returned ExCom 32) |  |  |  | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 165 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 23 | TAS | 147 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-07-01 | 347000 | -1750 | 345250 | 345250 | 100% | 0 | 0 | 0 | 45110 | -227.5 | 44882.5 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 26 | TAS | 174 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 347000 | 0 | 347000 | 347000 | 100% | 0 | 0 | 0 | 45110 | 0 | 45110 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 195 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 357000 | 0 | 357000 | 357000 | 100% | 0 | 0 | 0 | 46410 | 0 | 46410 | 0 | 0 | Project financially completed. ($ 22,000 plus US$ 2,860 PSC returned to ExCom 55) |  |  |  | Non Investment
FIN | UNEP | Translate and print three guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 23 | TAS | 153 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 2002-12-01 | 2003-08-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 | 0 | 0 | 46800 | 0 | 46800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 200 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2002-03-01 | 364000 | 0 | 364000 | 364000 | 100% | 0 | 0 | 0 | 47320 | 0 | 47320 | 0 | 0 | Project financially completed. ($26,684 plus $3,469 PSC returned ExCom 44. $ 15,992 plus $ 2,079 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Information dissemination (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 49 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 380000 | 0 | 380000 | 380000 | 100% | 0 | 0 | 0 | 49400 | 0 | 49400 | 0 | 0 | Project financially completed. ($ 3,500 plus $ 455 PSC returned ExCom 33) |  |  |  | Non Investment
FIN | UNEP | OzonAction Information Clearing-house (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 430000 | 0 | 430000 | 430000 | 100% | 0 | 0 | 0 | 55900 | 0 | 55900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Information exchange and technology transfer (1991-1992) | Individual | GLO | GLO | SEV | 04 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-12-01 |  | 1993-06-01 | 1993-12-01 | 526000 | 0 | 526000 | 526000 | 100% | 0 | 0 | 0 | 68380 | 0 | 68380 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Information Exchange Clearing-house System (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-06-01 | 1996-07-01 | 705000 | 0 | 705000 | 705000 | 100% | 0 | 0 | 0 | 91650 | 0 | 91650 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Information exchange programme | Individual | ASP | PHI | SEV | 11 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1995-12-01 |  | 2000-12-01 | 2003-07-01 | 200000 | -1488 | 198512 | 198512 | 100% | 0 | 0 | 0 | 26000 | -193.44 | 25806.56 | 0 | 0 | Project financially completed. ($9 plus $ 1 returned to ExCom 60) |  |  |  | Non Investment
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 09 | TAS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. |  |  |  | Non-INV
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 |  | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. |  |  |  | INV
CLO | UNDP | Conversion to non CFC technology in the manufacture of integral skin and flexible moulded foam at Strapur | Individual | LAC | ARG | FOA | 23 | INV | 62 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2001-08-01 | 212500 | -162380 | 50120 | 50120 | 100% | 0 | 0 | 0 | 27625 | -21109 | 6516 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFCs in the manufacture of cold cured molded PUF products at Autofit P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 103125 | -103125 | 0 | 0 |  | 0 | 0 | 0 | 13406.25 | -13406.25 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1996 |  | Investment
COM | UNDP | Retroactive funding for the conversion from CFC-11 to water-based technology in the manufacture of flexible molded and integral skin foam at Espumlatex-Promicolda | Individual | LAC | COL | FOA | 32 | INV | 49 | N | R | CFC | 11.5 | 11.5 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2001-05-01 |  | 82020 | 0 | 82020 | 82020 | 100% | 0 | 0 | 0 | 4921 | 0 | 4921 | 0 | 0 | Completed in 2001. |  | 2000 |  | Investment
FIN | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components | Individual | ASP | IND | FOA | 36 | INV | 350 | A | I | CFC | 22 | 22 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 200282 | -26 | 200256 | 200256 | 100% | 0 | 0 | 0 | 26037 | -3 | 26034 | 0 | 0 | Project has been completed. PCR submitted in 2006. Remaining funds will be returned. |  |  | 2004-12-01
FIN | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products | Individual | ASP | IND | FOA | 36 | INV | 351 | A | I | CFC | 27 | 27 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 224812 | -9 | 224803 | 224803 | 100% | 0 | 0 | 0 | 29226 | -1 | 29225 | 0 | 0 | Project has been completed. PCR submitted in 2006 |  |  | 2004-12-01
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | Individual | ASP | IRA | FOA | 37 | INV | 152 | A | I | CFC | 22 | 22 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2007-12-01 | 2009-12-01 | 185632 | -42000 | 143632 | 143632 | 100% | 0 | 0 | 0 | 24132 | -5459.96 | 18672 | 0.04 | 0 | NOU acknowledged destruction of old equipment in December 2007. PCR was approved by NOU in Oct-2009. Funds of USD 42.000 have been returned to MFS.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj | Individual | ASP | IRA | FOA | 37 | INV | 153 | A | I | CFC | 18.6 | 18.6 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 228310 | 0 | 228310 | 228310 | 100% | 0 | 0 | 0 | 29680 | 0 | 29680 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group | Individual | ASP | IRA | FOA | 37 | INV | 150 | A | I | CFC | 23 | 23 | 0 |  | 2002-07-01 | 2002-10-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 335249 | 0 | 335249 | 335249 | 100% | 0 | 0 | 0 | 43582 | 0 | 43582 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 |  | 2005-12-01 | 2005-12-01 | 165201 | -20510.44 | 144690.56 | 144690.56 | 100% | 0 | 0 |  | 21476.13 | -2666.36 | 18809.77 | 0 | 0 | Project financially and technically completed. |  |  |  | INV
FIN | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2005-04-01 | 2005-12-01 | 3538400 | -1983523.96 | 1554876.04 | 1554876.04 | 100% | 0 | 0 |  | 459992 | -257858.12 | 202133.88 | 0 | 0 | Project completed. |  |  | 2002-12-01 | INV
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100% | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-06-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 | 2005-01-01 | 187864 | -41523 | 146341 | 146341 | 100% | 0 | 0 |  | 24422.32 | -5397.99 | 19024.33 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2000-12-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-06-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-12-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 100% | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100% | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | Complete. |  |  | 1993-07-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23796.5 | 136828.5 | 136828.5 | 100% | 0 | 0 |  | 20881 | -3093.5 | 17787.5 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 |  | 2005-06-01 | 2005-09-01 | 279280 | -5612.86 | 273667.14 | 273667.14 | 100% | 0 | 0 |  | 36306.4 | -729.68 | 35576.72 | 0 | 0 | Project completed. |  |  | 2003-12-01 | INV
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 | 2005-02-01 | 51795 | -14902 | 36893 | 36893 | 100% | 0 | 0 |  | 6733.35 | -1936.91 | 4796.09 | 0.35 | 0.35 | Project completed and PCR under review. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100% | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 | 2005-07-01 | 398378 | -277445.52 | 120932.48 | 120932.48 | 100% | 0 | 0 |  | 51789.14 | -36067.98 | 15721.22 | -0.06 | -0.06 | Project completed and non-ODS production at all 5 participating companies underway. |  |  | 2004-01-01 | INV
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100% | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100% | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100% | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | Project completed. |  |  | 2004-01-01 | INV
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100% | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 100% non-CFC production started. Draft PCR prepared. |  |  |  | INV
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Oto Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 336 | A | I | CFC | 12.7 | 12.7 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 139716 | -381 | 139335 | 139335 | 100% | 0 | 0 |  | 18163 | -47 | 18116 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Flexo Foam P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 307 | A | I | CFC | 19.4 | 19.4 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 185241 | 0 | 185241 | 185241 | 100% | 0 | 0 |  | 24081 | 0 | 24081 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sutlej Coach Products P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 318 | A | I | CFC | 18 | 18 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 187400 | 0 | 187400 | 187400 | 100% | 0 | 0 |  | 24362 | 0 | 24362 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in June 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Malvika Polymers | Individual | ASP | IND | FOA | 34 | INV | 319 | A | I | CFC | 20 | 20 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 196610 | -295 | 196315 | 196315 | 100% | 0 | 0 |  | 25559 | -38 | 25521 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. | Individual | LAC | ARG | FOA | 23 | INV | 63 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-03-01 | 2001-12-01 | 132000 | -9838 | 122162 | 122162 | 100% | 0 | 0 | 0 | 17160 | -1279 | 15881 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast | Individual | LAC | ARG | FOA | 14 | INV | 13 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-09-01 | 1995-12-01 | 1995-09-01 |  | 1999-11-01 | 2001-12-01 | 345000 | -5021 | 339979 | 339979 | 100% | 0 | 0 | 0 | 44850 | -653 | 44197 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Injetec | Individual | LAC | BRA | FOA | 34 | INV | 240 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 43334 | -2371 | 40963 | 40963 | 100% | 0 | 0 | 0 | 5633.42 | -308.42 | 5325 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Ornati-Luce | Individual | LAC | BRA | FOA | 34 | INV | 212 | A | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2003-11-01 | 46292 | -1550 | 44742 | 44742 | 100% | 0 | 0 | 0 | 6017.96 | -201.96 | 5816 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Juntafacil | Individual | LAC | BRA | FOA | 34 | INV | 211 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2004-01-01 | 55204 | -3500 | 51704 | 51704 | 100% | 0 | 0 | 0 | 7176.52 | -454.52 | 6722 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid and flexible integral skin foams at Air Micro | Individual | LAC | BRA | FOA | 34 | INV | 229 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2004-01-01 | 56490 | -2984 | 53506 | 53506 | 100% | 0 | 0 | 0 | 7343.7 | -387.7 | 6956 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Menaf | Individual | LAC | BRA | FOA | 31 | INV | 168 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 80994 | -11239 | 69755 | 69755 | 100% | 0 | 0 | 0 | 10529.22 | -1461.22 | 9068 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Injebank | Individual | LAC | BRA | FOA | 25 | INV | 101 | A | I | CFC | 6 | 6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-04-01 | 86300 | -10846 | 75454 | 75454 | 100% | 0 | 0 | 0 | 11219 | -1410 | 9809 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mikawa & Cia | Individual | LAC | BRA | FOA | 23 | INV | 87 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 80600 | 0 | 80600 | 80600 | 100% | 0 | 0 | 0 | 10478 | 0 | 10478 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free techcnology in the manufacture of polyurethane foam at Blitz Ind. Com. de Plasticos | Individual | LAC | BRA | FOA | 19 | INV | 46 | A | I | TCA/CFC | 9.8 | 9.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-07-01 | 2000-07-01 | 120000 | -36822 | 83178 | 83178 | 100% | 0 | 0 | 0 | 15600 | -4787 | 10813 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based and HCFC-141b technology in the manufacture of rigid and flexible integral skin foam at VM | Individual | LAC | BRA | FOA | 34 | INV | 220 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-11-01 | 83902 | 0 | 83902 | 83902 | 100% | 0 | 0 | 0 | 10907 | 0 | 10907 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam at Paranoa | Individual | LAC | BRA | FOA | 34 | INV | 213 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-05-01 | 2004-01-01 | 84660 | -1 | 84659 | 84659 | 100% | 0 | 0 | 0 | 11006 | 0 | 11006 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of flexible molded foam and to HCFC-141b for flexible integral skin foam at Rosil | Individual | LAC | BRA | FOA | 34 | INV | 215 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 87672 | -2545 | 85127 | 85127 | 100% | 0 | 0 | 0 | 11397.36 | -331.36 | 11066 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at FJ Polymers | Individual | LAC | BRA | FOA | 23 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 89500 | -992 | 88508 | 88508 | 100% | 0 | 0 | 0 | 11635 | -129 | 11506 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CMZ Poliuretanos | Individual | LAC | BRA | FOA | 23 | INV | 79 | A | I | CFC | 5.5 | 5.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 92750 | -305.36 | 92444.64 | 92445 | 100% | -0.36 | 0 | 0 | 12057.5 | -39.502 | 12018.0448 | -0.046801 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam for steering wheels at Plascar | Individual | LAC | BRA | FOA | 17 | INV | 21 | A | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-12-01 |  | 1997-10-01 | 2000-07-01 | 119400 | -25268 | 94132 | 94132 | 100% | 0 | 0 | 0 | 15522 | -3285 | 12237 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kalf Calcados | Individual | LAC | BRA | FOA | 23 | INV | 89 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-11-01 | 2003-11-01 | 101100 | 0 | 101100 | 101100 | 100% | 0 | 0 | 0 | 13143 | 0 | 13143 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and flexible molded foam at Fabbrini | Individual | LAC | BRA | FOA | 31 | INV | 167 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 124887 | -17316 | 107571 | 107571 | 100% | 0 | 0 | 0 | 16235.31 | -2251.31 | 13984 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible integral skin and flexible molded foams at Royal Rubber | Individual | LAC | BRA | FOA | 34 | INV | 216 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 120795 | -3396 | 117399 | 117399 | 100% | 0 | 0 | 0 | 15703.35 | -442.35 | 15261 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Beneplast | Individual | LAC | BRA | FOA | 34 | INV | 230 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 135176 | -12534 | 122642 | 122642 | 100% | 0 | 0 | 0 | 17572.88 | -1628.88 | 15944 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at ELV TEC Industria e Commercio Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 155 | A | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 134265 | 0 | 134265 | 134265 | 100% | 0 | 0 | 0 | 17454 | 0 | 17454 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin and flexible molded foams at Purtec | Individual | LAC | BRA | FOA | 29 | INV | 156 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2005-10-01 | 140769 | -3173.9956 | 137595.0044 | 137595 | 100% | 0.0044 | 0 | 0 | 18299.97 | -412.9701 | 17886.9993 | 0.00057199 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Cougar | Individual | LAC | BRA | FOA | 25 | INV | 108 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 154375 | 0 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20069 | 0 | 20069 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams at Nicos do Brasil | Individual | LAC | BRA | FOA | 29 | INV | 152 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technlogy in the manufacture of polyurethane foam at Plasmold | Individual | LAC | BRA | FOA | 23 | INV | 77 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 161500 | -737.36 | 160762.64 | 160763 | 100% | -0.36 | 0 | 0 | 20995 | -95.9976 | 20899.0492 | -0.0468 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at Mach-Plast | Individual | LAC | BRA | FOA | 31 | INV | 180 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 188951 | -12871 | 176080 | 176080 | 100% | 0 | 0 | 0 | 24563.63 | -1672.63 | 22891 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Giroflex | Individual | LAC | BRA | FOA | 22 | INV | 64 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-08-01 | 2002-11-01 | 177500 | 0 | 177500 | 177500 | 100% | 0 | 0 | 0 | 23075 | 0 | 23075 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams (shoesoles) at Megaflex | Individual | LAC | BRA | FOA | 32 | INV | 191 | A | I | CFC | 41.5 | 41.5 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-04-01 | 2003-05-01 | 205568 | -4726 | 200842 | 200842 | 100% | 0 | 0 | 0 | 26723.84 | -613.84 | 26110 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of rigid integral skin foam at Spray | Individual | LAC | BRA | FOA | 29 | INV | 151 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 211080 | -4717 | 206363 | 206363 | 100% | 0 | 0 | 0 | 27440.4 | -613.4 | 26827 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Gnatus | Individual | LAC | BRA | FOA | 25 | INV | 107 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-04-01 | 207225 | -488 | 206737 | 206737 | 100% | 0 | 0 | 0 | 26939.25 | -63.25 | 26876 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Nacra | Individual | LAC | BRA | FOA | 18 | INV | 28 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 254500 | -47523.49 | 206976.51 | 206977 | 100% | -0.49 | 0 | 0 | 33085 | -6178.0037 | 26907.06 | -0.0637 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam, and water-blown technology for flexible moulded foam at Arquespuma | Individual | LAC | BRA | FOA | 36 | INV | 252 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-01-01 | 207741 | 0 | 207741 | 207741 | 100% | 0 | 0 | 0 | 27006 | 0 | 27006 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin (shoesoles) at Prosola | Individual | LAC | BRA | FOA | 31 | INV | 188 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 214118 | -165 | 213953 | 213953 | 100% | 0 | 0 | 0 | 27835.34 | -21.34 | 27814 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams (microcellular) at Bicicletos Caloi, S.A. | Individual | LAC | BRA | FOA | 27 | INV | 117 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 227600 | -4765 | 222835 | 222835 | 100% | 0 | 0 | 0 | 29588 | -619 | 28969 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Durothan | Individual | LAC | BRA | FOA | 29 | INV | 145 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 228625 | 0 | 228625 | 228625 | 100% | 0 | 0 | 0 | 29721 | 0 | 29721 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Macform | Individual | LAC | BRA | FOA | 18 | INV | 27 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 243500 | -8086 | 235414 | 235414 | 100% | 0 | 0 | 0 | 31655 | -1051 | 30604 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam, elastomers and integral skin foam for automotive applications and to HCFC-141b for furniture integral skin foam applications at Steel Plastik | Individual | LAC | BRA | FOA | 36 | INV | 259 | A | I | CFC | 46.7 | 46.7 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-12-01 | 2005-11-01 | 247882 | 0 | 247882 | 247882 | 100% | 0 | 0 | 0 | 32225 | 0 | 32225 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of integral skin foams at Spandy Peças em Poliuretano, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 125 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 261400 | -4032 | 257368 | 257368 | 100% | 0 | 0 | 0 | 33982 | -524 | 33458 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Panther | Individual | LAC | BRA | FOA | 25 | INV | 105 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2000-11-01 | 2003-05-01 | 275805 | 0 | 275805 | 275805 | 100% | 0 | 0 | 0 | 35855 | 0 | 35855 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bruzze | Individual | LAC | BRA | FOA | 23 | INV | 80 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-11-01 |  | 2000-11-01 | 2002-03-01 | 278190 | -456 | 277734 | 277734 | 100% | 0 | 0 | 0 | 36164.7 | -58.7 | 36106 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at MBR | Individual | LAC | BRA | FOA | 18 | INV | 29 | A | I | CFC | 40 | 40 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 338500 | -44421 | 294079 | 294079 | 100% | 0 | 0 | 0 | 44005 | -5775 | 38230 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Espumatec | Individual | LAC | BRA | FOA | 23 | INV | 94 | A | I | CFC | 64.6 | 64.6 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-04-01 | 2003-04-01 | 372000 | -271 | 371729 | 371729 | 100% | 0 | 0 | 0 | 48360 | -35 | 48325 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible integral skin at Moldepol | Individual | LAC | BRA | FOA | 28 | INV | 136 | A | I | CFC | 34.8 | 34.8 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 421444 | -2 | 421442 | 421442 | 100% | 0 | 0 | 0 | 54787.72 | 0.28 | 54788 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Indaru | Individual | LAC | BRA | FOA | 36 | INV | 258 | A | I | CFC | 93.8 | 93.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2004-06-01 | 2007-03-01 | 423121 | 0 | 423121 | 423121 | 100% | 0 | 0 | 0 | 55006 | 0 | 55006 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion to hexane and LCD technology in the manufacture of polyurethane foam at Herval | Individual | LAC | BRA | FOA | 25 | INV | 102 | A | I | CFC | 64.5 | 64.5 | 0 | 0 | 1998-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 637335 | 0 | 637335 | 637335 | 100% | 0 | 0 | 0 | 82854 | 0 | 82854 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Umbrella project covering 6 companies for the conversion to CFC-free technology in the manufacture of integral rigid skin and flexible molded polyurethane foam (Rorispuma, Indek, Flexfom, Walrod, Rigi | Individual | LAC | BRA | FOA | 19 | INV | 45 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-11-01 | 2000-07-01 | 746000 | 1.94 | 746001.94 | 746002 | 100% | -0.06 | 0 | 0 | 96980 | 0 | 96980.0078 | -0.0078 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Trambusti Naue | Individual | LAC | BRA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2000-11-01 | 2001-11-01 | 763600 | -2355 | 761245 | 761245 | 100% | 0 | 0 | 0 | 99268 | -306 | 98962 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Hebei Tianye Automobile Group Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 326 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 98800 | -21346 | 77454 | 77454 | 100% | 0 | 0 | 0 | 12844 | -2774.8698 | 10069.1302 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Dongfeng Automobile Body Company | Individual | ASP | CPR | FOA | 29 | INV | 319 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 111120 | -9255 | 101865 | 101865 | 100% | 0 | 0 | 0 | 14446 | -1203.0033 | 13242.9967 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of integral skin foam at Guangzhou Haohua Automobile Carpet Plant | Individual | ASP | CPR | FOA | 29 | INV | 328 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-09-01 | 2004-06-01 | 119540 | -8640 | 110900 | 110900 | 100% | 0 | 0 | 0 | 15540 | -1123 | 14417 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Ningxian Oriental Auto Parts Plant | Individual | ASP | CPR | FOA | 29 | INV | 329 | N | I | CFC | 7.3 | 7.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 122235 | -6311 | 115924 | 115924 | 100% | 0 | 0 | 0 | 15891 | -821.0026 | 15069.9974 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of integral skin polyurethane foam at Hubei Auto Engineering | Individual | ASP | CPR | FOA | 15 | INV | 96 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin and cold cured PUF moldings at Jiangxi Auto Engineering Plastic Plant | Individual | ASP | CPR | FOA | 18 | INV | 142 | N | I | CFC | 39 | 39 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 2001-03-01 | 2003-07-01 | 170000 | -6784 | 163216 | 163216 | 100% | 0 | 0 | 0 | 22100 | -882 | 21218 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Hangzhou Fanlong Steering Wheel, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 305 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 176520 | -4703 | 171817 | 171817 | 100% | 0 | 0 | 0 | 22948 | -612 | 22336 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water blown and HCFC-141b in the manufacture of ISF at 4 SMEs (Ningbo Yongling Rubber & Plastic, Sichuan Mianyang Jinpan Automobile Parts, Zhenjiang Xingda Auto Par | Individual | ASP | CPR | FOA | 29 | INV | 304 | N | I | CFC | 17.6 | 17.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2008-10-01 | 245710 | -19126.2 | 226583.8 | 226584 | 100% | -0.2 | 0 | 0 | 31942 | -2485.9966 | 29456.0294 | -0.026 | 0 | Completed in 2003. Financially completed in 2008. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam and flexible molded foam at Zhongqi Jinan Auto Parts Factory | Individual | ASP | CPR | FOA | 29 | INV | 331 | N | I | CFC | 21.6 | 21.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 236130 | -8780.42 | 227349.58 | 227350 | 100% | -0.42 | 0 | 0 | 30697 | -1141 | 29556.0546 | -0.054601 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Jizhou Beinei Automobile Cushion Plant | Individual | ASP | CPR | FOA | 29 | INV | 333 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-05-01 | 2005-03-01 | 484040 | -18030 | 466010 | 466010 | 100% | 0 | 0 | 0 | 62925 | -2344.0026 | 60580.9974 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at Plysindo Inter Mouldi (PIM) | Individual | ASP | IDS | FOA | 22 | INV | 60 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1997-09-01 | 2001-12-01 | 75870 | -1848 | 74022 | 74022 | 100% | 0 | 0 | 0 | 9863.1 | -240.1 | 9623 | 0 | 0 | Completed in 1997. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded PUF at Ciptaindah Jokindo | Individual | ASP | IDS | FOA | 23 | INV | 82 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 77125 | -58 | 77067 | 77067 | 100% | 0 | 0 | 0 | 10026.25 | -7.25 | 10019 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded and integral skin PUF at PT Archigramma | Individual | ASP | IDS | FOA | 23 | INV | 71 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 106625 | -14881 | 91744 | 91744 | 100% | 0 | 0 | 0 | 13861.25 | -1935.25 | 11926 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at PT Kemenangan | Individual | ASP | IDS | FOA | 35 | INV | 126 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 104817 | -2098 | 102719 | 102719 | 100% | 0 | 0 | 0 | 13626.21 | -273.21 | 13353 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at PT Dithon Urethane | Individual | ASP | IDS | FOA | 20 | INV | 46 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-02-01 | 2000-07-01 | 184000 | -295 | 183705 | 183705 | 100% | 0 | 0 | 0 | 23920 | -38 | 23882 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at Siddhi Polymer P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 148 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 75250 | -737 | 74513 | 74513 | 100% | 0 | 0 | 0 | 9782.5 | -95.499 | 9687.001 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of integral skin PUF products at Legend Interiors | Individual | ASP | IND | FOA | 23 | INV | 154 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 124000 | -14125 | 109875 | 109875 | 100% | 0 | 0 | 0 | 16120 | -1836 | 14284 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Primrose Multiplast P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 215 | A | D | CFC | 9.6 | 9.6 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 117105 | -1131 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15223.65 | -146.655 | 15076.995 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at K. J. Polymers P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 155 | A | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 127550 | -353 | 127197 | 127197 | 100% | 0 | 0 | 0 | 16581.5 | -45.5047 | 16535.9953 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at K.B. Poly Industries P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 99 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 149000 | -19595 | 129405 | 129405 | 100% | 0 | 0 | 0 | 19370 | -2547 | 16823 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Coolwels Automobile Engineers | Individual | ASP | IND | FOA | 29 | INV | 234 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 133221 | -669 | 132552 | 132552 | 100% | 0 | 0 | 0 | 17319 | -87 | 17232 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible moulded cold-cured and integral skin PU foam at Venus Auto P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 147 | A | I | CFC | 21 | 21 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 137250 | -1155 | 136095 | 136095 | 100% | 0 | 0 | 0 | 17842.5 | -149.4966 | 17693.0034 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Jaiswal Industries | Individual | ASP | IND | FOA | 29 | INV | 241 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 152070 | -14822 | 137248 | 137248 | 100% | 0 | 0 | 0 | 19769 | -1927 | 17842 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Premium Mouldings and Pressings P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 236 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 138432 | -87 | 138345 | 138345 | 100% | 0 | 0 | 0 | 17996 | -11 | 17985 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sun Steering Wheels, Ltd. | Individual | ASP | IND | FOA | 32 | INV | 285 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-02-01 | 2005-10-01 | 144379 | -2997 | 141382 | 141382 | 100% | 0 | 0 | 0 | 18769.27 | -390.27 | 18379 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Viking Engineers P. Ltd. | Individual | ASP | IND | FOA | 34 | INV | 305 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-10-01 | 144900 | -2745 | 142155 | 142155 | 100% | 0 | 0 | 0 | 18837 | -357 | 18480 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at Krishna Fabrications Ltd. | Individual | ASP | IND | FOA | 20 | INV | 103 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 164000 | -21543 | 142457 | 142457 | 100% | 0 | 0 | 0 | 21320 | -2801 | 18519 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of the CFCs in the manufacture of cold cured molded and integral skin PUF products at Preto Foams | Individual | ASP | IND | FOA | 19 | INV | 76 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-11-01 | 2000-12-01 | 167100 | -17268 | 149832 | 149832 | 100% | 0 | 0 | 0 | 21723 | -2245 | 19478 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Nu-Foam Rubber Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 330 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2003-02-01 | 2005-10-01 | 160150 | -1114.9952 | 159035.0048 | 159035 | 100% | 0.0048 | 0 | 0 | 20819.5 | -144.5029 | 20674.9965 | 0.00062401 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Netplast Ltd. | Individual | ASP | IND | FOA | 32 | INV | 280 | A | I | CFC | 18 | 18 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-09-01 | 2005-09-01 | 177224 | -2199 | 175025 | 175025 | 100% | 0 | 0 | 0 | 23039.12 | -286.12 | 22753 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Meenakshi Polymers Pvt. Ltd. | Individual | ASP | IND | FOA | 19 | INV | 82 | A | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1996-11-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 214000 | -38836 | 175164 | 175164 | 100% | 0 | 0 | 0 | 27820 | -5049 | 22771 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Delite Foam and Polymers | Individual | ASP | IND | FOA | 29 | INV | 245 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 188832 | -2784 | 186048 | 186048 | 100% | 0 | 0 | 0 | 24548.16 | -362.16 | 24186 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured moulded and integral skin at Shri Krishna Polyurethane Industries P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 149 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-08-01 | 2002-11-01 | 192875 | -486 | 192389 | 192389 | 100% | 0 | 0 | 0 | 25073.75 | -62.75 | 25011 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured and integral skin PUF moldings at Amit Polyseats Ltd. | Individual | ASP | IND | FOA | 19 | INV | 79 | A | I | CFC | 19.3 | 19.3 | 0 | 0 | 1996-05-01 | 1996-10-01 | 1997-11-01 |  | 1997-06-01 | 2000-07-01 | 243000 | -28744 | 214256 | 214256 | 100% | 0 | 0 | 0 | 31590 | -3737 | 27853 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Harjas Plastic and Metal Components P. Ltd. | Individual | ASP | IND | FOA | 29 | INV | 246 | A | I | CFC | 20.2 | 20.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-05-01 | 2003-07-01 | 246386 | -30539 | 215847 | 215847 | 100% | 0 | 0 | 0 | 32030.18 | -3970.18 | 28060 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of cold cured molded and integral skin PUF products at Kaygee Foams P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 74 | A | I | CFC | 33 | 33 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 217250 | -1198 | 216052 | 216052 | 100% | 0 | 0 | 0 | 28242.5 | -155.5 | 28087 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sawhney Seating Systems | Individual | ASP | IND | FOA | 32 | INV | 289 | A | I | CFC | 28 | 28 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-07-01 | 2005-09-01 | 241619 | -3124 | 238495 | 238495 | 100% | 0 | 0 | 0 | 31410.47 | -406.47 | 31004 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Punjab Scooters Ltd. | Individual | ASP | IND | FOA | 19 | INV | 83 | A | I | CFC | 39 | 39 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 312200 | -23972 | 288228 | 288228 | 100% | 0 | 0 | 0 | 40586 | -3116 | 37470 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | Individual | ASP | IRA | FOA | 35 | INV | 117 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2007-02-01 | 188820 | -7749 | 181071 | 181071 | 100% | 0 | 0 | 0 | 24546.6 | -1006.5964 | 23540.0036 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded and integral skin polyurethane foams at Abre Sanati Iran | Individual | ASP | IRA | FOA | 34 | INV | 88 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2005-11-01 | 344407 | -7956 | 336451 | 336451 | 100% | 0 | 0 | 0 | 44772.91 | -1033.91 | 43739 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to n-pentane technology in the manufacture of integral skin polyurethane foam products at Iran Polyurethane Manufacturing Co. | Individual | ASP | IRA | FOA | 32 | INV | 76 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-08-01 | 2003-11-01 | 796230 | 0 | 796230 | 796230 | 100% | 0 | 0 | 0 | 97585 | 0 | 97585 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Artwright Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 65 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2002-03-01 | 90320 | 0 | 90320 | 90320 | 100% | 0 | 0 | 0 | 11742 | 0 | 11742 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Sze Chuan Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 68 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin polyurethane foam at P.U. Mate Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 25 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 113000 | -9294 | 103706 | 103706 | 100% | 0 | 0 | 0 | 14690 | -1208 | 13482 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of molded/integral skin PUF at Bristol Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 67 | A | I | CFC | 8 | 8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-02-01 | 2000-07-01 | 123400 | -475 | 122925 | 122925 | 100% | 0 | 0 | 0 | 16042 | -61 | 15981 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Minply | Individual | ASP | MAL | FOA | 26 | INV | 115 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 158050 | -3297 | 154753 | 154753 | 100% | 0 | 0 | 0 | 20546.5 | -428.5 | 20118 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Grorich | Individual | ASP | MAL | FOA | 26 | INV | 116 | A | I | CFC | 32.9 | 32.9 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 174150 | 0 | 174150 | 174150 | 100% | 0 | 0 | 0 | 22640 | 0 | 22640 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured/integral skin PUF molded at Muda Murni Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 66 | A | I | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2000-12-01 | 236500 | -52362 | 184138 | 184138 | 100% | 0 | 0 | 0 | 30745 | -6807 | 23938 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured PUF molded products at Urethane Technologies Sdn., Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 61 | A | D | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-07-01 |  | 1997-12-01 | 2000-12-01 | 199000 | -7010 | 191990 | 191990 | 100% | 0 | 0 | 0 | 25870 | -911 | 24959 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin, spoiler and moulded flexible foam at P.U. Tech Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 24 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 198000 | -0.35 | 197999.65 | 198000 | 100% | -0.35 | 0 | 0 | 25740 | 0.0045 | 25740.05 | -0.0455 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Island Resources Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 17 | A | I | TCA/CFC | 16.5 | 16.5 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-04-01 | 1998-12-01 | 230000 | -14204 | 215796 | 215796 | 100% | 0 | 0 | 0 | 29900 | -1846 | 28054 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CT Foam | Individual | ASP | MAL | FOA | 23 | INV | 99 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 236000 | 0 | 236000 | 236000 | 100% | 0 | 0 | 0 | 30680 | 0 | 30680 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Heng Huat Furniture | Individual | ASP | MAL | FOA | 23 | INV | 105 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 269500 | 0 | 269500 | 269500 | 100% | 0 | 0 | 0 | 35035 | 0 | 35035 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of polyurethane foam at Tenaga | Individual | ASP | MAL | FOA | 25 | INV | 111 | A | I | CFC | 23 | 23 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 308800 | 0 | 308800 | 308800 | 100% | 0 | 0 | 0 | 40144 | 0 | 40144 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Key Asset Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 15 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-11-01 |  | 1995-02-01 | 1998-12-01 | 690000 | -15755 | 674245 | 674245 | 100% | 0 | 0 | 0 | 89700 | -2048 | 87652 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin foam at Air Design | Individual | LAC | MEX | FOA | 23 | INV | 71 | A | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 80500 | -1178 | 79322 | 79322 | 100% | 0 | 0 | 0 | 10465 | -153.0016 | 10311.9984 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to water-based technology in the manufacture of integral skin foam at Moldecor, S.A. de C.V. | Individual | LAC | MEX | FOA | 25 | INV | 84 | A | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2000-04-01 | 2001-12-01 | 86500 | -845 | 85655 | 85655 | 100% | 0 | 0 | 0 | 11245 | -110.0047 | 11134.9953 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Industrias Pol-Rym S.A. de C.V., (IPR) | Individual | LAC | MEX | FOA | 22 | INV | 55 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1998-11-01 |  | 1998-11-01 | 2001-12-01 | 421500 | -4909 | 416591 | 416591 | 100% | 0 | 0 | 0 | 54795 | -638 | 54157 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Umbrella project for conversion to CFC-free technology in the manufacture of polyurethane shoe soles (seven enterprises) | Individual | LAC | MEX | FOA | 20 | INV | 49 | A | I | CFC | 95 | 95 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 2001-08-01 | 2003-04-01 | 1201590 | -3434 | 1198156 | 1198156 | 100% | 0 | 0 | 0 | 156206.7 | -445.7 | 155761 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Group Project (Orca) | Individual | LAC | MEX | FOA | 23 | INV | 73 | A | I | CFC | 190 | 190 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-11-01 | 1471500 | -154071 | 1317429 | 1317429 | 100% | 0 | 0 | 0 | 191295 | -20029 | 171266 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of integral skin and cold cured molded PUF products at Maghreb Elastoplast | Individual | AFR | MOR | FOA | 20 | INV | 04 | A | D | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1997-09-01 | 2000-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 2.9104e-13 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Soutech | Individual | ASP | PHI | FOA | 23 | INV | 51 | N | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 1999-12-01 | 2003-04-01 | 326750 | -1799 | 324951 | 324951 | 100% | 0 | 0 | 0 | 42477.5 | -233.5 | 42244 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam (flexible molded, integral skin) at World Plaster/Europlan Furniture Co. | Individual | ASP | THA | FOA | 26 | INV | 105 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 135800 | -5000 | 130800 | 130800 | 100% | 0 | 0 | 0 | 17654 | -650 | 17004 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Novochem | Individual | ASP | THA | FOA | 23 | INV | 70 | A | I | CFC | 19.7 | 19.7 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2002-08-01 | 2004-01-01 | 196600 | 0 | 196600 | 196600 | 100% | 0 | 0 | 0 | 25558 | 0 | 25558 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to LCD technology (flexible) and water based technology (integral skin) in the manufacture of polyurethane foam at Duriflex | Individual | ASP | THA | FOA | 25 | INV | 90 | A | I | TCA/CFC | 21.2 | 21.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2001-12-01 | 278800 | -285 | 278515 | 278515 | 100% | 0 | 0 | 0 | 36244 | -37.0544 | 36206.9456 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam at J.S. Industry Co. Ltd. | Individual | ASP | THA | FOA | 26 | INV | 98 | A | I | CFC | 93.2 | 93.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 418800 | -15974 | 402826 | 402826 | 100% | 0 | 0 | 0 | 54444 | -2076.62 | 52367.38 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Pilot project for validation of methyl formate in microcellular polyurethane applications (phase I) | Individual | LAC | MEX | FOA | 56 | DEM | 141 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-06-01 |  | 2010-11-01 | 2012-12-01 | 291500 | 0 | 291500 | 290081.62 | 99.51% | 1418.38 | 0 | 0 | 21862 | 0 | 21755.6239 | 106.3761 | 0 | Financially completed in 2012. |  | 2008 | 2011-01-01 | Non-Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown and HCFC-141b technology at Sector Co. in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | LAC | BRA | FOA | 31 | INV | 186 | A | I | CFC | 17.7 | 17.7 |  |  | 2000-07-01 | 2001-11-01 | 2003-01-01 |  | 2002-12-01 | 2003-02-01 | 130490 | 0 | 130490 | 130489.64 | 100% | 0.36 | 0 |  | 16964 | -7 | 16957 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Frisokar Equipamentos Plasticos Ltd. | Individual | LAC | BRA | FOA | 17 | INV | 26 | A | I | CFC | 42 | 42 |  |  | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1997-10-01 | 2000-07-01 | 267948 | -13521 | 254427 | 254427 | 100% | 0 | 0 |  | 34833 | -1810 | 33023 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of integral skin automotive parts at PT Wulansari Raharja | Individual | ASP | IDS | FOA | 36 | INV | 141 | A | I | CFC | 10.8 | 10.8 |  |  | 2002-03-01 | 2004-02-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 101301 | -632 | 100669 | 100668.52 | 100% | 0.48 | 0 |  | 13169 | -103 | 13066 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown technology in the manufacturing of polyurethane integral skin shoe soles at P.T. Trias Rantai Mas | Individual | ASP | IDS | FOA | 31 | INV | 119 | A | I | CFC | 18.4 | 18.4 |  |  | 2000-07-01 | 2000-11-01 | 2003-01-01 |  | 2003-01-01 | 2003-12-01 | 141319 | 0 | 141319 | 141319.29 | 100% | -0.29 | 0 |  | 18371 | 0 | 18371 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Nirwana in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 110 | A | I | CFC | 32.6 | 32.6 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 206911 | 0 | 206911 | 206911.12 | 100% | -0.12 | 0 |  | 26898 | -27 | 26871 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Meta Presindo Utama in the manufacture of polyurethane integral skin and moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 113 | A | I | CFC | 21.8 | 21.8 |  |  | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 213603 | 0 | 213603 | 213603.43 | 100% | -0.43 | 0 |  | 27768 | -15 | 27753 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out ODS at PT Naviri Kencana Perdana | Individual | ASP | IDS | FOA | 19 | INV | 43 | A | I | CFC | 47.8 | 47.8 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 377382 | -402 | 376980 | 376980 | 100% | 0 | 0 |  | 49060 | -130 | 48930 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT Solindah Kita | Individual | ASP | IDS | FOA | 36 | INV | 144 | A | I | CFC | 48 | 48 |  |  | 2002-03-01 | 2002-08-01 | 2004-09-01 |  | 2005-12-01 | 2006-12-01 | 390760 | -5753 | 385007 | 385007.42 | 100% | -0.42 | 0 |  | 50799 | -748 | 50051 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT. Accurai | Individual | ASP | IDS | FOA | 37 | INV | 147 | A | I | CFC | 50 | 50 |  |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2005-06-01 | 2006-09-01 | 523943 | -656 | 523287 | 523287.38 | 100% | -0.38 | 0 |  | 67634 | -72 | 67562 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at Meublatex | Individual | AFR | TUN | FOA | 19 | INV | 16 | A | I | CFC | 28 | 28 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-10-01 | 2000-07-01 | 105000 | -681 | 104319 | 104319 | 100% | 0 | 0 |  | 13650 | -110 | 13540 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of moulded integral skin flexible PU foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | I | CFC | 11.4 | 11.4 |  |  | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882.27 | 100% | -0.27 | 0 |  | 20525 | 0 | 20525 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | I | CFC | 32 | 32 |  |  | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | 0 | 198882 | 198881.59 | 100% | 0.41 | 0 |  | 25855 | -15 | 25840 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 07 | INV | 04 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | 1997-04-30 | INV
FIN | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 | 2007-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  | 2000-05-01 | INV
FIN | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 | 2007-06-01 | 2800000 | -1512624 | 1287376 | 1287376 | 100% | 0 | 0 |  | 318000 | -166389 | 151611 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  |  | INV
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 05 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 07 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV
FIN | France | Conversion to non-CFC facilities of 4 companies producing cars and wagons equipped with MAC-umbrella project |  | ASP | IRA | REF | 24 | INV | 34 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 2000-02-01 | 1999-04-01 |  | 2002-06-01 | 2008-09-01 | 138600 | -35471 | 103129 | 103129 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-06-01
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fifth tranche) | Multiyear | ASP | IDS | REF | 51 | INV | 178 | N | I | CFC | 110 | 110 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-03-01 | 2010-05-01 | 125800 | 0 | 125800 | 125800 | 100% | 0 | 0 |  | 10002 | 0 | 10002 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fourth tranche) | Multiyear | ASP | IDS | REF | 48 | INV | 173 | N | I | CFC | 110 | 110 | 0 | 0 | 2006-04-01 | 2008-12-01 | 2007-04-01 |  | 2008-12-01 | 2010-05-01 | 126800 | 0 | 126800 | 126800 | 100% | 0 | 0 |  | 10092 | 0 | 10092 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1999-08-01 | INV
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100% | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | 2000-11-01 | INV
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. PCR was sent to ExCom. |  |  | 1999-08-01 | INV
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  | 1999-11-01 | INV
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100% | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100% | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-04-01 | INV
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100% | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | Project completed; PCR submitted to the 31th ExCom. |  |  | 1998-12-01 | INV
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100% | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | Project completed. Completion report submitted. |  |  |  | INV
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100% | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100% | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV
FIN | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 | 2005-01-01 | 1181693 | -83277 | 1098416 | 1098416 | 100% | 0 | 0 |  | 222895 | -15708 | 207187.01 | -0.01 | -0.01 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100% | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | Project fully completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100% | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | 1999-06-01 | INV
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100% | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | 2000-03-01 | INV
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100% | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | 1997-07-01 | INV
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100% | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). |  |  |  | INV
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100% | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | Project completed. Indirect phaseout of 110.5 MT. |  |  |  | INV
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | INV
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1998-06-01 | INV
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100% | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | Project completed; Draft PCR is under review. |  |  | 1999-12-01 | INV
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-03-01 | INV
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | 2001-12-01 | INV
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 06 | TAS | 05 | N | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-08-01 | INV
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 07 | TAS | 07 | N | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | -74881 | 825119 | 825119 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV
FIN | UNDP | Feasibility study on the application of HFC-134a technology in MACs and CFC recycling | RMP-Component | ASP | CPR | REF | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-09-01 |  | 1993-12-01 | 1997-12-01 | 40000 | -15164 | 24836 | 24836 | 100% | 0 | 0 | 0 | 5200 | -1971 | 3229 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204.1 | 206795.9 | 206796 | 100% | -0.1 | 0 | 0 | 28600 | -1716.533 | 26883.48 | -0.013 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | USA | MAC servicing demonstration |  | LAC | ARG | REF | 16 | DEM | 22 | A | I | CFC | 20.4 | 20 | 0 |  | 1995-03-01 | 1995-09-01 | 1995-12-01 |  | 1997-06-01 | 1998-06-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-06-01
FIN | USA | Demonstration mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | CHI | REF | 19 | DEM | 15 | A | I | CFC | 10 | 10 | 0 |  | 1996-05-01 | 1996-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-10-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-12-01
FIN | USA | MAC emissions reduction demonstration programme |  | LAC | COL | REF | 15 | DEM | 13 | A | I | CFC | 11.5 | 12 | 0 |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1999-06-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. Project will be classified as financially complete at that time. |  | 1994
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | COS | REF | 19 | DEM | 09 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 2000-05-01 | 2000-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery are planned for May 2000. |  | 1995 | 1997-12-01
FIN | USA | MAC servicing demonstration |  | ASP | CPR | REF | 16 | DEM | 117 | A | I | CFC | 7 | 11.4 | 0 |  | 1995-03-01 | 1995-04-01 | 1995-03-01 |  | 1996-03-01 | 1996-03-01 | 172500 | -6667 | 165833 | 165833 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995
FIN | USA | Refrigeration mobile air conditioning (MAC) servicing |  | ASP | CPR | REF | 19 | DEM | 163 | A | I | CFC | 11.4 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1999-05-01 |  | 1998-11-01 | 1998-12-01 | 385000 | 77600 | 462600 | 462600 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1995 | 1997-12-01
FIN | USA | Demonstration project in MACs |  | LAC | DOM | REF | 17 | DEM | 03 | A | I |  | 0 | 10 | 0 |  | 1995-07-01 | 1995-09-01 | 1996-12-01 |  | 1997-12-01 | 1999-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Refrigeration: mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | GUA | REF | 19 | DEM | 10 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 1998-08-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. |  | 1995 | 1997-12-01
FIN | USA | MAC demonstration project |  | LAC | JAM | REF | 23 | DEM | 07 | A | I | CFC | 9.6 |  | 0 |  | 1997-11-01 | 1998-02-01 | 1998-12-01 |  | 1999-06-01 | 2000-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Equipment delivered and training conducted in March 99, with follow-up mission in June 1999. Final report will be submitted June 2000. |  | 1997
FIN | USA | Demonstration project in MAC |  | LAC | MEX | REF | 13 | DEM | 27 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | MACs servicing demonstration project |  | ASP | PHI | REF | 18 | DEM | 41 | A | I | CFC | 11 |  | 0 |  | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1999-09-01 | 1999-09-01 | 285500 | 0 | 285500 | 285500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | UNDP is working with the Government of the Philippines to complete the project. |  | 1995 | 1997-05-01
FIN | USA | MAC demonstration project |  | LAC | TRI | REF | 23 | DEM | 08 | A | I | CFC | 10 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1999-05-01 | 2000-05-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1997
FIN | USA | MACs servicing demonstration project |  | EUR | TUR | REF | 23 | DEM | 32 | A | I | CFC | 12 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 2000-07-01 | 205000 | 0 | 205000 | 205000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery planned for May 99. |  | 1997
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector |  | LAC | VEN | REF | 15 | DEM | 30 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | MAC servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Terminated. |  | 1996 | 1998-12-01
COM | UNIDO | Sector plan for methyl bromide production sector (first tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 436 | A | I | MBR | 0 | 0 | 231 | 231 | 2005-11-01 | 2006-06-01 | 2008-12-01 |  | 2008-12-01 |  | 3000000 | 0 | 3000000 | 2817721.44 | 93.92% | 182278.56 | 145044.36 | 180000 | 225000 | 0 | 211329 | 13671 | 10878 | Project completed. |  |  |  | INV
ONG | UNIDO | Sector plan for methyl bromide production sector (third tranche) | Multi-Year | ASP | CPR | PRO | 64 | INV | 510 | A | I | MBR | 0 | 0 | 126 | 26 | 2011-07-01 |  | 2014-07-31 | 2014-12-01 |  |  | 2000000 | 0 | 2000000 | 0 | 0% | 2000000 | 2000000 | 1000000 | 150000 | 0 | 0 | 150000 | 150000 | 2012 methyl bromide production target met as planned, contracts for 2013 signed and funds disbursed accordingly. Carried out awareness activities in cooperation with the Ministry of Agriculture for controlled uses of methyl bromide. Disbursement level at the end of 2012 does not reflect actual progress by the end of 2012, since all the funds have been obligated through a contract signed with FECO. Disbursement level will increase in 2013. | Formulate and sign contracts for 2014 production targets, finalize final report for Phase III and formulate funds disbursement request for Phase IV. Carry out awareness activities in cooperation with AQSIQ for QPS uses of methyl bromide and with MOA for controlled uses of methyl bromide. |  |  | INV
ONG | UNIDO | Sector plan for methyl bromide production sector (second tranche) | Multi-Year | ASP | CPR | PRO | 56 | INV | 475 | A | I |  | 0 | 0 | 214 | 214 | 2008-11-01 | 2009-02-01 | 2011-11-30 | 2013-03-01 |  |  | 3000000 | 0 | 3000000 | 1516082 | 50.54% | 1483918 | 1483918 | 500000 | 225000 | 0 | 113706 | 111294 | 111294 | This is a part of a multiyear project that will end in 2015, the last payment for this tranche had been released in March 2013. | Project will be completed in Mar 2013. |  |  | INV
COM | UNDP | Phase-out of CFC in the manufacturing of MDIs | Individual | LAC | COL | ARS | 56 | INV | 71 | N | I | CFC | 7.4 | 7.4 | 0 | 0 | 2008-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-09-01 |  | 409359 | 0 | 409359 | 409353.04 | 100% | 5.96 | 0 | 4.768 | 30701 | 0 | 30700.553 | 0.44699 | 0 | Completed in 2012. Final workshop with international expert took place in September 2012. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
COM | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | CUB | ARS | 41 | INV | 23 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2006-09-01 |  | 2011-12-01 |  | 5960000 | 0 | 5960000 | 5851300.38 | 98.18% | 108699.62 | 0 | 86959.696 | 447000 | 0 | 438847.5285 | 8152.4715 | 0 | Completed in 2011. CFC-free salbutamol registered and being produced commercially (80% of the plant production), and fluticasone failed one-year stability tests. Adjustments made a new lot of products produced. Has complied with 6 month stability test. Final invoices pending. | One year stability test will be done in April 2012. Final registration will take place after that, if tests are successful. | 2003 | 2008-03-01 | Investment
COM | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | I | CFC | 10 | 10 | 0 | 0 | 2004-07-01 | 2006-04-01 | 2007-07-01 |  | 2009-12-01 |  | 427023 | 0 | 427023 | 426114.65 | 99.79% | 908.35 | 0 | 726.68 | 32027 | 0 | 31958.8732 | 68.1268 | 0 | Completed in 2009. |  | 2004 |  | Investment
COM | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | MEX | ARS | 53 | INV | 135 | A | I | CFC | 97 | 97 |  |  | 2007-11-01 | 2008-04-01 | 2010-01-31 |  | 2011-09-01 |  | 2630503 | 0 | 2630503 | 2616610.18 | 99.47% | 13892.82 | 9668.15 | 13000 | 197288 | 0 | 196246 | 1042 | 725 | Project completed. |  |  |  | INV
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | CPR | ARS | 62 | TAS | 505 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Verification of 2010 CFC production for EUN consumption was conducted in accordance with Dec. 60/47 at the only one remaining CFC producer starting in May 11. Report submitted to the 65th ExCom. |  |  |  | Non-INV
FIN | IBRD | Technical assistance to implement national transition strategy to CFC-free MDI | Individual | ASP | IDS | ARS | 56 | TAS | 184 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 13950 | 0 | 13950 | 0 | 0 | Project completed as scheduled on the basis of workplan including development of database for registration of products, review of relevant policy and regulations within Agency for Drug and Food Control, preparation of a guideline for using CFC-free MDIs; workshop held for stakeholders and relevant leaflets produced. |  |  |  | INV
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | IND | ARS | 62 | TAS | 438 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-08-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Independent audit submitted to the 65th ExCom in Nov 11. Report shows that CFC producers produced less CFCs than approved by the Parties for essential use, and that these pharma grade CFCs were sold to 2 MDI manufacturers authorized by GoI to produce MDIs according to EUN Process. |  |  |  | Non-INV
FIN | UNDP | Formulation of a phase-out project in the MDI sector | Individual | ASP | BGD | ARS | 50 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -7050 | 22950 | 22950 | 100% | 0 | 0 | 0 | 2250 | -529 | 1721 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | LAC | COL | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-12-01 | 2011-11-01 | 30000 | -3478 | 26522 | 26522 | 100% | 0 | 0 | 0 | 2250 | -260.85 | 1989.15 | 0 | 0 | Completed in 2008. |  | 2008 |  | Investment
FIN | UNDP | MDI transition strategy | Individual | AFR | GHA | ARS | 56 | TAS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-05-01 |  | 2009-12-01 | 2011-09-01 | 30000 | -40.56 | 29959.44 | 29959.44 | 100% | 0 | 0 | 0 | 2700 | -3.65 | 2696.35 | 0 | 0 | Completed in 2009. |  | 2008 |  | Non-Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | IND | ARS | 52 | PRP | 411 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2008-07-01 | 2010-01-01 | 100000 | -23585.72 | 76414.28 | 76414.28 | 100% | 0 | 0 | 0 | 7500 | -1768.929 | 5731.071 | 0 | 0 | Financially completed in 2010. |  | 2007 |  | Investment
FIN | UNDP | MDI transition strategy | Individual | EUR | MOL | ARS | 54 | TAS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-08-01 | 2009-09-01 |  | 2010-12-01 | 2012-07-01 | 30000 | -18.36 | 29981.64 | 29981.64 | 100% | 0 | 0 | 0 | 2700 | -1.65 | 2698.35 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | PAK | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-11-01 | 2011-11-01 | 60000 | -9095.82 | 50904.18 | 50904.18 | 100% | 0 | 0 | 0 | 4500 | -682.19 | 3817.81 | 0 | 0 | Completed in 2008. |  | 2008 |  | Investment
FIN | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 70000 | 0 | 70000 | 70000.24 | 100% | -0.24 | 0 | 0 | 9100 | 0 | 9100.0312 | -0.0312 | 0 | Completed in 2009. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNEP | Formulation of a transition strategy for MDI | Individual | ASP | BGD | ARS | 50 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Transition strategy for phasing out use of CFCs in the manufacturing of MDIs | Individual | ASP | BGD | ARS | 52 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2011-07-01 |  | 2011-12-01 | 2012-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | MDI regional workshops/CAP | Individual | GLO | GLO | ARS | 52 | TAS | 282 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2008-07-01 |  | 2009-12-01 | 2012-06-01 | 200000 | -49311 | 150689 | 150689 | 100% | 0 | 0 | 0 | 16000 | -3944.88 | 12055.12 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | PAK | ARS | 56 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2011-11-01 |  | 2011-11-01 | 2012-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | ASP | IRA | ARS | 52 | INV | 183 | A | I | CFC | 96.4 | 96.4 |  |  | 2007-07-01 | 2007-12-01 | 2010-09-30 |  | 2010-12-01 | 2012-12-01 | 3529508 | -232750 | 3296758 | 3296009.14 | 99.98% | 748.86 | 0 | 1 | 264713 | -17456 | 247201 | 56 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Project preparation for a MDI project, including the development of a national transitional strategy for the sector | Individual | LAC | MEX | ARS | 52 | PRP | 134 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-04-01 | 2008-07-01 | 50000 | -275 | 49725 | 49724.98 | 100% | 0.02 | 0 |  | 3750 | -21 | 3729 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | IBRD | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | ARG | ARS | 56 | INV | 159 | N | I | CFC | 118.4 | 7 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2012-01-31 | 2014-12-01 |  |  | 2806874 | 0 | 2806874 | 2451253 | 87.33% | 355621 | 355621 | 250000 | 210516 | 0 | 183844.36 | 26671.64 | 26671.64 | The remaining plant to convert, Cassara (LPC) is currently installing the filling line for production tests of pilot lots. |  |  | 2014-12-01 | INV
ONG | Italy | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 424 | N | I | CFC | 139.7 | 28 | 0 |  | 2008-11-01 | 2011-03-01 | 2013-11-01 | 2013-11-01 |  |  | 2000000 | 0 | 2000000 | 1244930 | 62.25% | 755070 | 0 |  | 230000 | 0 | 143166.95 | 86833.05 | 0 | Technical verification of conversion by external expert completed by November 2012. The project expected to be operationally completed by November 2013. |  |  | 2013-11-01
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol MDIs (Beximco, Square Pharmaceutical and Acme Pharmaceutical) | Individual | ASP | BGD | ARS | 52 | INV | 26 | N | I | CFC | 76.3 | 76.3 | 0 | 0 | 2007-07-01 | 2010-11-01 | 2011-07-01 | 2013-06-01 |  |  | 2776778 | 0 | 2776778 | 2287787.52 | 82.39% | 488990.48 | 4.72 | 146697.144 | 208258 | 0 | 171583.7756 | 36674.2244 | 0.354 | During 2012, Beximco and ACME have completed phase-out of CFC MDIs in all their formulations. Square has completed conversion to CFC free MDIs in all formulations except one and this is expected to be completed by Q2 / Q3 of 2013. Bangladesh also had an awareness and outreach workshop in March 2012 on their successful completion of CFC MDI phaseout projects for a majority of the formulation. No EUN was requested for 2013. | Project progress in Square is monitored through periodic consultations with the company. | 2007 | 2011-07-01 | Investment
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 423 | N | I | CFC | 564.6 | 564.6 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2013-11-01 | 2013-11-01 |  |  | 8082267 | 0 | 8082267 | 7835363.79 | 96.95% | 246903.21 | 0 | 74070.963 | 606170 | 0 | 587652.26 | 18517.74 | 0 | During 2012, completion of conversion projects of all enterprises was completed and verified. For milestones achieved, funds are being disbursed to the beneficiary enterprises. Completion targeted for Nov-2013. | Funds are being disbursed to the beneficiary enterprises. | 2008 |  | Investment
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | PAK | ARS | 56 | INV | 71 | N | I | CFC | 83.8 | 83.4 | 0 | 0 | 2008-11-01 | 2011-03-01 | 2011-11-01 | 2013-12-01 |  |  | 449996 | 0 | 449996 | 55300 | 12.29% | 394696 | 8500 | 118408.8 | 33750 | 0 | 4147.5369 | 29602.4631 | 637.5057 | During the year 2012, GSK initiated procurement of equipment for manufacturing HFA-based MDIs at their facility. The equipment procurement was completed in 2012. It appears that Zafa, the second beneficiary is no longer interested in pursuing the project. Government has been following up with Zafa on the return of US$ 55,000, the initial payment under the phase-out agreement. | No EUN was submitted for the year 2013. Project activities at GSK would be completed by Q3 of 2013. Project is expected to be closed by Q4 of 2013. | 2008 |  | Investment
ONG | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | IND | ARS | 56 | TAS | 425 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2013-11-01 | 2013-11-01 |  |  | 120000 | 0 | 120000 | 46599 | 38.83% | 73401 | 0 | 73401 | 15600 | 0 | 6057.87 | 9542.13 | 0 | UNEP is on the process of project completion. | UNEP completed the awareness activities and finalizing the reports for submission to UNEP. |  |  | Non Investment
ONG | UNIDO | Sector plan for phase-out of CFCs consumption in MDI sector | Individual | ASP | CPR | ARS | 56 | INV | 473 | A | I | CFC | 322.5 | 0 |  |  | 2008-11-01 | 2009-10-01 | 2013-12-31 | 2015-12-01 |  |  | 13500000 | 0 | 13500000 | 10753023.66 | 79.65% | 2746976.34 | 0 | 1340000 | 1012500 | 0 | 806477 | 206023 | 0 | Further contracts to phase out CFCs in the production of MDIs were signed, until the end of 2012 a total of 19 companies had started the final CFC phase-out. Their consumption of CFCs represents 99.2% of the baseline year 2007. The awareness activities started in January 2012, three programmes were finalized: a campaign to raise awareness for the general public, and two awareness activities aiming at professional staff, researchers and manufacturers. The regulation on “Exemption Management” for CFCs based MDI entered into force. This regulation combines the quota with a licensing system and mandates reduction of remaining CFC usage in MDI production. The new fast-track authorization procedure has become fully operational; several submissions for registration of non-CFC MDIs were received by SFDA. Additional supporting activities started in May 2012: a site supervision programme for CFC users and manufacturers, a programme to establish quality standards for HFC-134a, and the development of a monitoring and information system. | Phase-out contracts with the remaining 4 companies will be signed (0.8% of the 2007 consumption), cancellation of existing licenses will be discussed. Registration of up to 5 non-CFC MDIs is envisaged to be finalized and additional submissions for registration are expected for the first half of 2013. The programmes to conduct site supervision for CFC users and manufacturers, to establish quality standards for HFC-134a, and to develop a monitoring and information system will continue and could be finalized by end of 2013. Additional campaigns to raise awareness of the general public, and two awareness activities aiming at professional staff, researchers and manufacturers have started in March 2013. |  | 2015-12-01 | INV
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | AFR | EGY | ARS | 50 | INV | 92 | A | I | CFC | 159.5 | 159.5 |  |  | 2006-11-01 | 2007-01-01 | 2009-12-01 | 2013-12-01 |  |  | 5899000 | 0 | 5899000 | 5581931.44 | 94.63% | 317068.56 | 173546.75 | 250000 | 442425 | 0 | 418645 | 23780 | 13016 | 1) Problems were encountered in the production of Salmeterol which resulted from an inadequate reaction vessel from local production. Therefore a new vessel has to be procured. 2) The awareness workshops had to be postponed because of security reasons. The results of the project including samples of the new MDIs were presented at an international chest conference in Cairo. | 1) International bidding for a new reaction vessel is currently ongoing. Equipment is expected to be delivered and installed as soon as the bidding is completed. 2) One awareness workshop took place in February 2013, the last one is planned for May 2013. Closure of the project is envisaged for the end of 2013. Reason for delay: 1) No satisfactory offer was received so far - bidding in progress. Note: the company is looking for a less expensive offer than the one that was primarily received. 2)The slight delay of the awareness workshop was due to security reasons. |  |  | INV
CLO | Australia | Replacement of methyl bromide with non ozone depleting substances in grain storage | Individual | AFR | KEN | FUM | 21 | DEM | 12 | A | D |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-07-01 |  |  | 2000-06-01 | 232834 | -91869 | 140965 | 140965 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | 1996
CLO | Canada | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 49 | TAS | 19 | A | I | MBR | 0.1 |  | 0 |  | 2006-07-01 |  | 2008-01-01 |  |  | 2009-07-01 | 30000 | -30000 | 0 | 0 |  | 0 |  | 0 | 3900 | -3900 | 0 | 0 |  | Canada will ask for cancellation of project at 58th meeting and return all related funds. Country NOU has agreed to cancellation as it has not been possible for government to sign agreement for over 18 months. |  | 2006 |  | Investment
CLO | IBRD | Phase-out of all the remaining uses of methyl bromide in soil application pest control (first tranche) | Multiyear | LAC | CHI | FUM | 45 | INV | 158 | N | I | MBR | 1.3 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-07-01 | 691703 | -691703 | 0 | 0 |  | 0 | 0 |  | 51878 | -51878 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV
CLO | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | Multi-Year | AFR | KEN | FUM | 38 | INV | 31 | A | I | MeBr | 10 | 10 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  |  | 2010-10-01 | 510660 | -6535.52 | 504124.48 | 504124.48 | 100% | 0 | 0 | 0 | 66173 | -846.8941 | 65326.1059 | 0 | 0 | Financially completed in 2010 and cancelled in 2007. |  | 2002 | 2005-07-01 | Investment
CLO | UNIDO | Demonstration project - alternatives to the use of methyl bromide in structural and commodity fumigation | Individual | LAC | JAM | FUM | 26 | DEM | 10 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  |  | 2001-07-01 | 102850 | -102850 | 0 | 0 |  | 0 | 0 |  | 13371 | -13371 | 0 | 0 | 0 | CLO
COM | Canada | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | JAM | FUM | 47 | TAS | 22 | A | I | MBR | 1.2 | 1.2 | 0 |  | 2005-11-01 | 2006-09-01 | 2007-12-01 |  | 2011-11-01 |  | 55530 | -2733 | 52797 | 48368 | 91.61% | 4429 |  | 0 | 7219 | 0 | 7219 | 0 |  | Project completed in November 2011 as reported to ExCom 65. However, $2,733 in project costs were remaining upon closure and were returned to ExCom 67 in July 2012. However, in developing PCR, Canada identified another unspent of balance $4,429 for the project and proposes to return this amount to ExCom 70 |  | 2005 | 2009-04-01 | Investment
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 2) | Multi-Year | ASP | YEM | FUM | 57 | INV | 33 | A | I | MBR | 0 | 5.4 | 0 |  | 2009-04-01 | 2009-05-01 | 2014-12-01 |  | 2010-12-01 |  | 91710 | 0 | 91710 | 91710 | 100% | 0 | 0 | 0 | 11613 | 0 | 11613 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 1) | Multi-Year | ASP | YEM | FUM | 56 | INV | 32 | A | I | MBR | 5.9 | 4.8 | 0 |  | 2008-11-01 | 2008-11-01 | 2014-12-01 |  | 2010-12-01 |  | 109740 | 0 | 109740 | 109740 | 100% | 0 | 0 | 0 | 13896 | 0 | 13896 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | IBRD | National phase-out plan of out methyl bromide (first tranche) | Multiyear | ASP | VIE | FUM | 50 | INV | 48 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-12-01 | 2007-11-01 |  | 2011-11-01 |  | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | Tranche funding fully disbursed. |  |  |  | INV
COM | IBRD | National phase-out plan of out methyl bromide (second tranche) | Multiyear | ASP | VIE | FUM | 59 | INV | 53 | N | I | MBR | 5.2 | 5.2 | 0 | 0 | 2009-11-01 | 2011-12-01 | 2011-11-30 |  | 2012-12-01 |  | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Vietnam successfully met its 2012 MB consumption reduction targets. After 1st study on PH3 resistance, PMU carried out in 2012 a follow-up study to develop a national strategy on PH3 resistance management. All training centers fully equipped with fumigation and protection equipment as well as PH3 for practical training on site for fumigation service companies and owners of storage facilities. Train-the-trainers workshop for the 5 centers held in early 2012. 4 training workshops for fumigation service companies and 5 for owners of storage facilities held by 5 Regional Plant Quarantine Sub-Departments assigned as these training centers. Assessment of integrated approaches for MB replacement in pre-harvest applications completed in 2012. 3 alternatives show relatively good results, especially economic efficiency, on crops chosen for demonstrations. Alternatives evaluated to be effective will be printed on leaflets and introduced on local televisions so that more growers are aware. PMU organized 2 training workshops for farmers and local technicians. 9 fumigation service companies completed purchasing of fumigation equipment since May 2012. | MB import quota for 2013 has been issued. |  |  | INV
COM | Italy | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 137 | A | I | MBR | 70 | 70 | 0 |  | 2008-04-01 | 2009-07-01 | 2014-03-01 |  | 2012-11-01 | 2012-11-01 | 1000000 | 0 | 1000000 | 993996 | 99.4% | 6004 | 0 |  | 120000 | 0 | 119279.52 | 720.48 | 0 | Project completed in Nov 2012. Financial completion in Nov 2012. |  | 2008 |  | Investment
COM | Italy | Total phase-out of methyl bromide used in stored commodities fumigation | Individual | AFR | CMR | FUM | 52 | INV | 27 | A | I | MBR | 14.5 | 14.5 | 0 |  | 2007-07-01 | 2008-04-01 | 2010-12-01 |  | 2011-12-01 |  | 259713 | 0 | 259713 | 257036 | 98.97% | 2677 | 1354 | 1000 | 33763 | 0 | 33414.68 | 348.32 | 176.02 | Project completed. |  | 2007 |  | Investment
COM | Spain | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 151 | A | I | MBR | 50 | 50 | 0 |  | 2010-04-01 | 2012-09-01 | 2012-04-01 |  | 2012-11-01 | 2012-11-01 | 800000 | 0 | 800000 | 799997 | 100% | 3 |  |  | 93000 | 0 | 92999.6512 | 0.34875 |  | Project completed in Nov 2012. Financial completion in Nov 2012. |  |  |  | Investment
COM | Spain | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | PAR | FUM | 47 | TAS | 15 | A | I | MBR | 0.2 | 0.2 | 0 | 0 | 2005-11-01 | 2007-07-01 | 2007-12-01 |  | 2009-07-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 |  | 5200 |  | This Project was approved on ExCom 47th, December 2005. 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only signature of PCR is remaining and expectd by Jul 09. . 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only PCR remain for signature that is expected on July 2009. | Project is completed. All funds were exhausted. The balance of US$ 1500 is not real. Clarification of accounts between UNDP Country Office and UNEP is in progress
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche IV) | Multi-Year | LAC | COS | FUM | 49 | INV | 36 | N | I | MeBr | 63.6 | 63.6 | 0 | 0 | 2006-07-01 | 2008-01-01 | 2008-12-01 |  | 2009-12-01 |  | 969057 | 0 | 969057 | 969057 | 100% | 0 | 0 | 0 | 72679 | 0 | 72679 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | Multi-Year | LAC | COS | FUM | 35 | INV | 25 | N | I | MeBr | 84.4 | 84.4 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2002-12-01 |  | 2005-07-01 |  | 1211321 | 0 | 1211321 | 1211321 | 100% | 0 | 0 | 0 | 143244.99 | 0 | 143244.99 | 0 | 0 | Completed in 2005. |  | 2001 | 2004-07-01 | Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranches II and III) | Multi-Year | LAC | COS | FUM | 43 | INV | 33 | N | I | MeBr | 130.8 | 130.8 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 |  | 1938114 | 0 | 1938114 | 1938114 | 100% | 0 | 0 | 0 | 145359 | 0 | 145359 | 0 | 0 | Completed in 2007. |  | 2004 |  | Investment
COM | UNDP | Demonstration and phase-out project for methyl bromide soil fumigation for fruit tree production and replant | One-off-Phaseout | LAC | CHI | FUM | 32 | INV | 143 | N | I | MeBr | 76.2 | 76.2 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2006-06-01 |  | 2007-12-01 |  | 805000 | -453.72 | 804546.28 | 804546.28 | 100% | 0 | 0 | 0 | 98550 | -55.55 | 98494.45 | 0 | 0 | Completed in 2007. |  | 2000 |  | Investment
COM | UNDP | Alternatives to methyl bromide for structural fumigation in Mexico | Individual | LAC | MEX | FUM | 26 | DEM | 86 | A | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2010-10-01 |  | 498300 | -87984.02 | 410315.98 | 410315.98 | 100% | 0 | 0 | 0 | 64779 | -11437.92 | 53341.08 | 0 | 0 | Completed. Two consultancies took place in 2010 to succesfully complete the implementation of the project. Some outstanding invoices still pending. |  | 1998 |  | Investment
COM | UNIDO | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 150 | A | I | MBR | 250 | 250 |  |  | 2010-04-01 | 2010-05-01 | 2012-04-30 |  | 2012-12-01 |  | 2000000 | 0 | 2000000 | 1957674.97 | 97.88% | 42325.03 | 30425.69 | 40000 | 150000 | 0 | 146826 | 3174 | 2282 | Project completed in Dec 2012.
COM | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (sixth tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 60 | A | I | MBR | 182.4 | 182.4 |  |  | 2008-11-01 | 2009-03-01 | 2010-11-30 |  | 2011-12-01 |  | 398427 | 0 | 398427 | 387037.51 | 97.14% | 11389.49 | 0 | 11000 | 29882 | 0 | 29028 | 854 | 0 | Project completed. |  |  |  | INV
COM | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 61 | A | I | MBR | 35 | 35 |  |  | 2008-11-01 | 2008-12-01 | 2012-11-30 |  | 2012-10-01 |  | 690000 | 0 | 690000 | 649999.98 | 94.2% | 40000.02 | 40000 | 40000 | 51750 | 0 | 48750 | 3000 | 3000 | Project completed in Oct 2012. |  |  |  | INV
COM | UNIDO | Phase-out methyl bromide in grain fumigation (third tranche) | Multi-Year | ASP | SYR | FUM | 47 | INV | 94 | A | I | MBR | 70.2 | 70.2 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2011-12-01 |  | 432414 | 0 | 432414 | 425907.91 | 98.5% | 6506.09 | 900 | 1000 | 32431 | 0 | 31943 | 488 | 68 | Project completed. |  |  |  | INV
FIN | Canada | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 138 | A | I | MBR | 20 | 20 | 0 |  | 2008-04-01 | 2009-09-01 | 2014-03-01 |  | 2012-03-01 | 2012-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 58527 | 0 | 58527 | 0 |  | Project was completed in March 2012 and financially closed in April 2012. |  | 2008 |  | Investment
FIN | Canada | Bromosorb technology in commodity fumigation | Individual | LAC | CHI | FUM | 15 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1997-04-01 | 1997-04-01 | 300000 | 17000 | 317000 | 317000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 1996-12-01 | Non-Inv.
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | ASP | CPR | FUM | 22 | DEM | 199 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-06-01 | 1999-06-01 |  | 1998-10-01 | 1998-10-01 | 145000 | 0 | 145000 | 145000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed |  | 1997 |  | Non-Inv.
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | AFR | KEN | FUM | 26 | DEM | 20 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-05-01 | 1999-12-01 |  | 2007-06-01 | 2007-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998 |  | Non-Inv.
FIN | Canada | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 122 | A | I | MBR | 18.2 | 18.2 | 0 |  | 2004-04-01 | 2006-09-01 | 2006-10-01 |  | 2009-03-01 | 2009-04-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 24700 | 0 | 24700 | 0 |  | This project was implemented by UNDP on behalf of Canada. Project was nearly completed by end of 2008, with 10 companies successfully completing alternative fumigations techniques. Remaining activities for 2009 included preparing a report focused on lessons learned from the project and finalizing financial reporting. These were completed by April 2009. |  | 2004 | 2008-06-01 | Investment
FIN | France | Phase-out of methyl bromide use in the cut flower and banana production |  | AFR | MOR | FUM | 29 | INV | 37 | A | I | MBR | 61 | 61 | 0 |  | 1999-11-01 | 2002-06-01 | 2003-12-01 |  | 2008-07-01 | 2012-12-01 | 1006652 | -78440 | 928212 | 928212 | 100% | 0 |  |  | 120732 | -9408 | 111324 | 0 |  | This project was implemented through UNIDO on behalf of France. It is completed. |  |  | 2005-04-01
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 41 | A | I | MBR | 17 | 9.7 | 0 |  | 2006-11-01 | 2007-01-01 | 2009-12-01 |  | 2010-01-01 | 2011-05-01 | 114898 | 0 | 114898 | 114898 | 100% | 0 | 0 | 0 | 14937 | 0 | 14937 | 0 | 0 | The Project has been completed. PCR submitted in September 2010
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (second tranche) | Multi-Year | AFR | KEN | FUM | 42 | INV | 35 | A | I | MBR | 12 | 14.7 | 0 |  | 2004-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-12-01 | 2011-05-01 | 172347 | 0 | 172347 | 172347 | 100% | 0 | 0 | 0 | 22405 | 0 | 22405 | 0 | 0 | Second tranche approved at 42nd ExCom. During 2005 technology transfer activities continued through agreements with farms for the adoption of alternatives such as substrates, IPM and chemicals such as metham sodium.
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) | Multi-Year | AFR | KEN | FUM | 39 | INV | 33 | A | I | MBR | 5 | 8 | 0 |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-04-01 | 2006-04-01 | 287247 | 0 | 287247 | 287247 | 100% | 0 | 0 | 0 | 37342 | 0 | 37342 | 0 | 0 | During 2004 the project staff was completed, a demonstration facility was set up in cooperation with the University of Nairobi, a very successful demonstration of substrates as alternative to MB was held at this facility. In sectors and areas where viable
FIN | Germany | Four alternatives to the use of methyl bromide in horticulture (strawberries, tomatoes, cucurbits) | Individual | AFR | EGY | FUM | 26 | DEM | 69 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-12-01 | 2001-03-01 | 308000 | -81000 | 227000 | 227000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted. Balance was offset against German contribution at the 40th Meeting.
FIN | Germany | Application of methyl bromide alternatives in grain storage | Individual | AFR | EGY | FUM | 26 | DEM | 70 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted.
FIN | Germany | Comprehensive approach to disseminate soil solarization technology for methyl bromide substitution | Individual | ASP | JOR | FUM | 26 | DEM | 41 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-08-01 | 2002-01-01 | 232789 | 0 | 232789 | 232789 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completion report submitted
FIN | Germany | Three alternatives to the use of methyl bromide: enemy plants, organic amendments and grafting on resistant rootstocks in combination with an integrated pest management system in tomatoes and curcubits | Individual | AFR | MOR | FUM | 26 | DEM | 26 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 2001-10-01 | 2003-10-01 | 229523 | 0 | 229523 | 229523 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to 41st ExCom
FIN | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | I | MBR | 9.1 | 17.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2008-04-01 | 2009-10-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Farmers were trained in the usage of MB alternatives. More field visits to farmers promoting MB alternatives took place. All project activities were successfully completed. The PCR has been prepared.
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2006-12-01 | 2007-06-01 | 348130 | -73.55 | 348056.45 | 348056.45 | 100% | 0 | 0 |  | 45256.9 | -9.57 | 45247.33 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of the whole umbrella project in Jun 07. |  |  |  | Non-INV
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | I | MBR | 15 | 15 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 |  | 2009-06-01 | 2009-09-01 | 244244 | -20203.07 | 224040.93 | 224040.93 | 100% | 0 | 0 |  | 31751.72 | -2626.4 | 29125.32 | 0 | 0 | Second testing was completed in Jun 09. Results were positive, reconfirming that the alternative substance (Agrocelhone) is effective for pest control. National consumption of Methyl Bromide by the closing of the WB umbrella ODS project in Sep 09 was 51 ODP MT. |  |  |  | INV
FIN | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 |  | 2005-01-01 | 2005-02-01 | 597945 | 0 | 597945 | 597945 | 100% | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | I | MBR | 9 | 9 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-12-01 |  | 2010-12-01 | 2010-12-01 | 330000 | 0 | 330000 | 330000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | Project was extended to allow transfer of activities to regular personnel of the implementing agency to ensure sustainability of MB phaseout in non-QPS applications and prevent return of stockholders to use of MB in non-QPS after project completion; facilitate coordination of activities of the FPA and BPI in monitoring QPS use of MB, Administrative Order No. 17 series of 2010 on "Guidelines for the Bureau of Plant Industry and Fertilizer and Pesticides Authority (FPA) on the Implementation of a Logbook System for Methyl Bromide QPS Uses" signed 16 Aug 2010. Regular inspection and monitoring visits conducted in selected regions; follow-thru workshops for database establishment for FPA regions held; verification and on-the-spot inspection of QPS MB consumption also conducted; consumption verification audits for 2008-2009 completed. |  |  |  | INV
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100% | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. |  |  |  | INV
FIN | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | I | MBR | 30 | 30 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 |  | 2006-06-01 | 2006-12-01 | 479040 | -1980.74 | 477059.26 | 477059.26 | 100% | 0 | 0 |  | 62275.2 | -257.5 | 62017.7 | 0 | 0 | Project completed both physically and financially. Currently, beneficiary uses CO2 and phosphine in fumigation. No more MeBr is in use. |  |  |  | INV
FIN | Italy | National phase-out of methyl bromide (phase II) | Multi-Year | ASP | CPR | FUM | 46 | INV | 431 | A | I | MBR | 534 | 534 | 0 |  | 2005-07-01 | 2007-03-01 | 2015-07-01 |  | 2009-12-01 | 2009-12-01 | 4000000 | 0 | 4000000 | 4000000 | 100% | 0 | 0 |  | 470000 | 0 | 470000 | 0 | 0 | FIN |  | 2005 |  | Investment
FIN | Italy | Phase out of methyl bromide in horticulture | Individual | EUR | ROM | FUM | 34 | INV | 19 | A | I | MBR | 93.9 | 93.9 | 0 |  | 2001-07-01 | 2002-02-01 | 2005-08-01 |  | 2006-12-01 | 2007-08-01 | 630517 | -996 | 629521 | 629521 | 100% | 0 | 0 |  | 79357 | -109.69 | 79247.31 | 0 | 0 | FIN |  | 2001 |  | Investment
FIN | Spain | Total phase-out of MB used in tobacco, flowers, ornamental plants, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 272 | A | I | MBR | 65.4 | 65.4 | 0 |  | 2005-07-01 | 2006-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-06-01 | 580390 | -212 | 580178 | 580178 | 100% | 0 | 0 |  | 75451 | -28 | 75423 | 0 | 0 | Financial completion in Jun 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | Spain | Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras | Individual | LAC | LAC | FUM | 47 | TAS | 37 | A | I | MBR | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-07-01 | 2008-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 |  | 10400
FIN | Spain | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 118 | A | I | MBR | 107.2 | 107.2 | 0 |  | 2004-04-01 | 2005-10-01 | 2006-10-01 |  | 2008-12-01 | 2010-03-01 | 707965 | -24181 | 683784 | 683784 | 100% | 0 | 0 | 0 | 87876 | -2659.76 | 85216 | 0.24 | 0 | Financial completion in Mar 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (sixth tranche) | Multi-Year | LAC | ARG | FUM | 48 | INV | 149 | N | I | MeBr | 56.7 | 56.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2009-06-01 | 2012-07-01 | 467000 | -73.49 | 466926.51 | 466926.51 | 100% | 0 | 0 | 0 | 35025 | -5.51 | 35019.49 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | Multi-Year | LAC | ARG | FUM | 40 | INV | 136 | N | I | MeBr | 21 | 21 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-03-01 |  | 2005-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2003 | 2005-07-01 | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fourth tranche) | Multi-Year | LAC | ARG | FUM | 43 | INV | 139 | N | I | MeBr | 16 | 16 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-07-01 |  | 2006-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fifth tranche) | Multi-Year | LAC | ARG | FUM | 46 | INV | 146 | N | I | MeBr | 33.3 | 33.3 | 0 | 0 | 2005-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | Multi-Year | LAC | ARG | FUM | 36 | INV | 129 | N | I | MeBr | 29 | 29 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2002-12-01 |  | 2004-12-01 | 2012-07-01 | 1720000 | 0 | 1720000 | 1720000 | 100% | 0 | 0 | 0 | 199200 | 0 | 199200 | 0 | 0 | Financially completed in 2012. |  | 2001 | 2004-03-01 | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 61 | N | I | MeBr | 66.4 | 66.4 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-03-01 |  | 2009-12-01 | 2012-01-01 | 210000 | 56717 | 266717 | 266716.59 | 100% | 0.41 | 0 | 0 | 15750 | 4254 | 20003.9692 | 0.03075 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fourth tranche) | Multi-Year | ASP | LEB | FUM | 44 | INV | 58 | N | I | MeBr | 36 | 36 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2005-12-01 |  | 2008-12-01 | 2012-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetable, cut flower and tobacco production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 53 | N | I | MeBr | 54 | 54 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-06-01 | 2012-01-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (second tranche) | Multi-Year | ASP | LEB | FUM | 38 | INV | 51 | N | I | MeBr | 31.8 | 31.8 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2004-12-01 | 2012-01-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 76000 | 0 | 76000 | 0 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 46 | N | I | MeBr | 25.8 | 25.8 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-12-01 |  | 2004-12-01 | 2012-01-01 | 800000 | 0 | 800000 | 800000 | 100% | 0 | 0 | 0 | 98000 | 0 | 98000 | 0 | 0 | Financially completed in 2012. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of all non-essential and non-QPS methyl bromide (release of first tranche) | Multi-Year | AFR | MLW | FUM | 32 | DEM | 15 | N | I | MeBr | 19.3 | 19.3 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2001-12-01 |  | 2001-12-01 | 2011-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2001. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (release of third tranche) | Multi-Year | AFR | MLW | FUM | 40 | INV | 18 | N | I | MeBr | 41.1 | 41.1 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2011-12-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 56250 | 0 | 56250 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (fourth tranche) | Multi-Year | AFR | MLW | FUM | 43 | INV | 21 | N | I | MeBr | 47.7 | 47.7 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2011-12-01 | 849824 | -11520.51 | 838303.49 | 838303.49 | 100% | 0 | 0 | 0 | 63737 | -864.04 | 62872.96 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | Multi-Year | AFR | MLW | FUM | 34 | INV | 16 | N | I | MeBr | 20.9 | 20.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2002-08-01 |  | 2004-12-01 | 2011-12-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | Individual | LAC | ARG | FUM | 26 | DEM | 79 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-04-01 | 2003-11-01 | 273350 | -1493 | 271857 | 271857 | 100% | 0 | 0 | 0 | 35535.5 | -193.5 | 35342 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Terminal methyl bromide phase-out, excluding QPS applications | One-off-Phaseout | LAC | BOL | FUM | 35 | INV | 16 | N | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-12-01 |  | 2007-12-01 | 2011-10-01 | 221032 | -1 | 221031 | 221031.31 | 100% | -0.31 | 0 | 0 | 28734.16 | -0.16 | 28734.0403 | -0.0403 | 0 | Completed in 2007. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100% | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100% | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Demonstration project of alternative to methyl bromide for soil fumigation (greenhouse) | Individual | ASP | LEB | FUM | 26 | DEM | 24 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 328200 | -2958 | 325242 | 325242 | 100% | 0 | 0 | 0 | 42666 | -385 | 42281 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Technical assistance programme to install alternatives and phase-out all remaining non-QPS uses of methyl bromide | Individual | ASP | MAL | FUM | 43 | TAS | 151 | N | I | MeBr | 8.7 | 8.7 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2007-12-01 |  | 2011-07-01 | 2012-05-01 | 200000 | -10970.51 | 189029.49 | 189029.49 | 100% | 0 | 0 | 0 | 18000 | -987.35 | 17012.65 | 0 | 0 | Financially completed in 2012. | The project is expected to be financially closed by June 12. | 2004 |  | Non-Investment
FIN | UNDP | Alternatives to the use of methyl bromide on Malaysian timbers | Individual | ASP | MAL | FUM | 29 | DEM | 129 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2006-07-01 | 2010-10-01 | 230000 | -8078.19 | 221921.81 | 221921.81 | 100% | 0 | 0 | 0 | 29900 | -1050.1647 | 28849.8353 | 0 | 0 | Financially completed in 2010. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of methyl bromide in soil fumigation | One-off-Phaseout | LAC | PER | FUM | 31 | INV | 28 | N | I | MeBr | 4 | 4 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-11-01 | 209770 | 0 | 209770 | 209770 | 100% | 0 | 0 | 0 | 27270 | 0 | 27270 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Demonstration, training and policy development on alternatives to methyl bromide for banana soil fumigation | Individual | ASP | PHI | FUM | 26 | DEM | 57 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-07-01 | 2003-07-01 | 231000 | -214534 | 16466 | 16466 | 100% | 0 | 0 | 0 | 30030 | -27889 | 2141 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for eradication of tea nematodes in Sri Lanka | Individual | ASP | SRL | FUM | 27 | DEM | 13 | A | I | MeBr | 3.9 | 3.9 | 0 | 0 | 1999-03-01 | 2000-07-01 | 2001-04-01 |  | 2007-10-01 | 2012-06-01 | 310200 | -7844.05 | 302355.95 | 302355.95 | 100% | 0 | 0 | 0 | 40326 | -1019.73 | 39306.27 | 0 | 0 | Financially completed in 2012. |  | 1999 |  | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27670.5 | -1318.52 | 26351.98 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNEP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 8450 | 0 | 8450 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | STK | FUM | 50 | TAS | 11 | A | I | MB | 0.8 | 0.8 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  | 2008-12-01 | Non Investment
FIN | UNIDO | National phase-out of methyl bromide (phase II, fifth tranche) | Multi-Year | ASP | CPR | FUM | 61 | INV | 501 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2011-12-01 | 2012-12-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | ASP | CPR | FUM | 52 | INV | 451 | A | I | MBR | 65.2 | 65.2 |  |  | 2007-07-01 | 2008-02-01 | 2008-07-31 |  | 2008-09-01 | 2008-09-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, fourth tranche) | Multi-Year | ASP | CPR | FUM | 58 | INV | 489 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2010-12-01 | 1300000 | 0 | 1300000 | 1300000 | 100% | 0 | 0 |  | 97500 | 0 | 97500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, third tranche) | Multi-Year | ASP | CPR | FUM | 55 | INV | 462 | A | I | MBR | 124.6 | 124.6 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2010-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (first tranche) | Multi-Year | ASP | CPR | FUM | 41 | INV | 407 | A | I | MBR | 364 | 364 |  |  | 2003-12-01 | 2004-04-01 | 2007-03-01 |  | 2007-12-01 | 2008-09-01 | 4086600 | -1 | 4086599 | 4086599.43 | 100% | -0.43 | 0 |  | 306495 | 0 | 306495 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (fourth tranche) | Multi-Year | LAC | HON | FUM | 59 | INV | 31 | A | I | MBR | 20.4 | 20.4 |  |  | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2011-12-01 | 2012-05-01 | 106301 | -45 | 106256 | 106255.65 | 100% | 0.35 | 0 |  | 7973 | -4 | 7969 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (third tranche) | Multi-Year | LAC | HON | FUM | 56 | INV | 29 | A | I | MBR | 23.9 | 23.9 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-12-01 | 2012-05-01 | 300000 | -73 | 299927 | 299926.9 | 100% | 0.1 | 0 |  | 22500 | -5 | 22495 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (first tranche) | Multi-Year | LAC | HON | FUM | 50 | INV | 21 | A | I | MBR | 31.8 | 31.8 |  |  | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-09-01 | 2008-12-01 | 600000 | 0 | 600000 | 600000.02 | 100% | -0.02 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (second tranche) | Multi-Year | LAC | HON | FUM | 53 | INV | 24 | A | I | MBR | 47.5 | 47.5 |  |  | 2007-11-01 | 2007-12-01 | 2008-11-30 |  | 2009-10-01 | 2010-09-01 | 800000 | 0 | 800000 | 799999.95 | 100% | 0.05 | 0 |  | 60000 | 0 | 60000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technology transfer leading to methyl bromide phase-out in soil fumigation | Multi-Year | AFR | KEN | FUM | 53 | INV | 43 | A | I | MBR | 53 | 53 |  |  | 2007-11-01 | 2008-02-01 | 2010-11-01 |  | 2009-12-01 | 2012-07-01 | 510659 | -1888 | 508771 | 508770.66 | 100% | 0.34 | 0 |  | 38300 | -142 | 38158 | 0 | 0 | Financial completion in Jul 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 62 | A | I | MBR | 9 | 9 |  |  | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 | 2010-12-01 | 42504 | -692 | 41812 | 41811.71 | 100% | 0.29 | 0 |  | 3188 | -52 | 3136 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 44 | A | I | MBR | 26.1 | 26.1 |  |  | 2001-07-01 | 2002-04-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide (strawberries): release of second tranche | Multi-Year | ASP | LEB | FUM | 38 | INV | 52 | A | I | MBR | 10.1 | 10.1 |  |  | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2007-12-01 | 421946 | 0 | 421946 | 421945.97 | 100% | 0.03 | 0 |  | 54853 | 0 | 54853 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 54 | A | I | MBR | 14.2 | 25.3 |  |  | 2003-12-01 | 2005-07-01 | 2004-12-01 |  | 2008-12-01 | 2011-05-01 | 450000 | -18846 | 431154 | 431153.54 | 100% | 0.46 | 0 |  | 33750 | -1413 | 32337 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others | Multi-Year | AFR | LIB | FUM | 47 | INV | 27 | A | I | MBR | 56 | 56 |  |  | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2012-10-01 | 743000 | 0 | 743000 | 743000.05 | 100% | -0.05 | 0 |  | 55725 | 0 | 55725 | 0 | 0 | Financial completion in Oct 2012. |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 136 | A | I | MBR | 130 | 130 |  |  | 2008-04-01 | 2008-06-01 | 2014-03-31 |  | 2012-07-01 | 2012-12-01 | 2000000 | 0 | 2000000 | 1999961.17 | 100% | 38.83 | 0 | 1 | 150000 | 0 | 149997 | 3 | 0 | Project completed in Jul 2012. Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | Multi-Year | AFR | MOR | FUM | 34 | INV | 44 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-10-01 | 2002-12-01 |  | 2005-09-01 | 2008-09-01 | 400000 | 0 | 400000 | 399999.97 | 100% | 0.03 | 0 |  | 52000 | 0 | 52000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fourth tranche) | Multi-Year | AFR | MOR | FUM | 50 | INV | 55 | A | I | MBR | 56.4 | 56.4 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 411633 | 0 | 411633 | 411633.01 | 100% | -0.01 | 0 |  | 30872 | 0 | 30872 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fifth tranche) | Multi-Year | AFR | MOR | FUM | 53 | INV | 58 | A | I | MBR | 78 | 78 |  |  | 2007-11-01 | 2008-02-01 | 2008-11-30 |  | 2010-12-01 | 2010-12-01 | 424381 | 0 | 424381 | 424380.99 | 100% | 0.01 | 0 |  | 31829 | 0 | 31829 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (balance of the first tranche) | Multi-Year | AFR | MOR | FUM | 44 | INV | 52 | A | I | MBR | 34.1 | 34.1 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-12-01 | 607513 | -236 | 607277 | 607277.03 | 100% | -0.03 | 0 |  | 45563 | -17 | 45546 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (third tranche) | Multi-Year | AFR | MOR | FUM | 47 | INV | 54 | A | I | MBR | 39 | 39 |  |  | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 1670995 | 0 | 1670995 | 1670995 | 100% | 0 | 0 |  | 125325 | 0 | 125325 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage (first tranche) | Multi-Year | ASP | SYR | FUM | 34 | INV | 80 | A | I | MBR | 5 | 5 |  |  | 2001-07-01 | 2002-08-01 | 2002-12-01 |  | 2006-12-01 | 2008-12-01 | 300000 | 0 | 300000 | 299999.97 | 100% | 0.03 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | FIN |  |  | 2005-12-01 | INV
FIN | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | Multi-Year | ASP | SYR | FUM | 41 | INV | 89 | A | I | MBR | 29.8 | 29.8 |  |  | 2003-12-01 | 2005-02-01 | 2004-12-01 |  | 2010-12-01 | 2010-12-01 | 351725 | -1572 | 350153 | 350152.88 | 100% | 0.12 | 0 |  | 26379 | -118 | 26261 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (second tranche) | Multi-Year | EUR | TUR | FUM | 41 | INV | 82 | A | I | MBR | 58 | 58 |  |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 | 2011-04-01 | 1000000 | -2624 | 997376 | 997375.92 | 100% | 0.08 | 0 |  | 75000 | -197 | 74803 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of methyl bromide in protected tomato, cucumber and carnation crops (first tranche) | Multi-Year | EUR | TUR | FUM | 35 | INV | 74 | A | I | MBR | 29.2 | 29.2 |  |  | 2001-12-01 | 2002-08-01 | 2002-12-01 |  | 2003-12-01 | 2006-11-01 | 1000000 | 0 | 1000000 | 999999.99 | 100% | 0.01 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (third and fourth tranches) | Multi-Year | EUR | TUR | FUM | 47 | INV | 88 | A | I | MBR | 205 | 205 |  |  | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2009-11-01 | 2012-09-01 | 1408844 | -76709 | 1332135 | 1332135.31 | 100% | -0.31 | 0 |  | 105663 | -5753 | 99910 | 0 | 0 | Financial completion in Sep 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (second tranche) | Multi-Year | AFR | ZIM | FUM | 51 | INV | 37 | A | I | MBR | 120 | 120 |  |  | 2007-03-01 | 2007-11-01 | 2009-12-01 |  | 2008-12-01 | 2010-09-01 | 1862486 | -2 | 1862484 | 1862483.73 | 100% | 0.27 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | I | MBR | 50 | 50 |  |  | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-09-01 | 1862486 | 0 | 1862486 | 1862486.01 | 100% | -0.01 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance to phase out methyl bromide in pulses disinfestations | Individual | AFR | ALG | FUM | 50 | TAS | 65 | A | I | MBR | 1.6 | 1.6 |  |  | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2010-05-01 | 51000 | -1274 | 49726 | 49725.97 | 100% | 0.03 | 0 |  | 4590 | -115 | 4475 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration Project: Open and closed circuit non-soil cultivation as main alternatives to the use of methyl bromide in tomato, cut flowers and strawberry production | Individual | LAC | ARG | FUM | 23 | DEM | 71 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-06-01 | 2002-09-01 | 481800 | -19112 | 462688 | 462687.69 | 100% | 0.31 | 0 |  | 62634 | -2580 | 60054 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling vegetables and flower production sector | Individual | EUR | BHE | FUM | 41 | INV | 17 | A | I | MBR | 11.8 | 11.8 |  |  | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 229000 | -3337 | 225663 | 225662.9 | 100% | 0.1 | 0 |  | 20610 | -300 | 20310 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Three alternatives to the use of methyl bromide: non-soil cultivation techniques, bio-fumigation with solarization, and application of various mixtures of other chemicals in low doses in tomatoes and curcubits | Individual | AFR | BOT | FUM | 25 | DEM | 05 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-11-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 146300 | 0 | 146300 | 146300.01 | 100% | -0.01 | 0 |  | 19019 | 0 | 19019 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: three alternatives to the use of methyl bromide: non-soil cultivation, solarization and low-dose chemicals | Individual | LAC | BRA | FUM | 22 | DEM | 73 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2000-05-01 | 2002-09-01 | 393800 | -28111 | 365689 | 365689.05 | 100% | -0.05 | 0 |  | 51194 | -3730 | 47464 | 0 | 0 | FIN
FIN | UNIDO | Total phase-out of MB used in tobacco, flowers, ornamentals, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 273 | A | I | MBR | 153.2 | 153.2 |  |  | 2005-07-01 | 2005-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-12-01 | 1450251 | -454 | 1449797 | 1449797.43 | 100% | -0.43 | 0 |  | 108769 | -34 | 108735 | 0 | 0 | FIN |  |  | 2008-12-01 | INV
FIN | UNIDO | Phasing out methyl bromide in the entire Tobacco Sector | Individual | LAC | BRA | FUM | 28 | INV | 142 | A | I | MBR | 84.4 | 84.4 |  |  | 1999-07-01 | 2000-06-01 | 2002-08-01 |  | 2001-12-01 | 2002-10-01 | 2344440 | -19971 | 2324469 | 2324468.93 | 100% | 0.07 | 0 |  | 267888 | -2602 | 265286 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the elimination of methyl bromide in soil fumigation | Individual | LAC | CHI | FUM | 57 | PRP | 169 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-05-01 | 2010-03-31 |  | 2010-12-01 | 2011-03-01 | 50000 | -152 | 49848 | 49847.63 | 100% | 0.37 | 0 |  | 3750 | -11 | 3739 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for the total phase-out of methyl bromide in all remaining uses | Individual | AFR | CMR | FUM | 50 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -60 | 29940 | 29939.69 | 100% | 0.31 | 0 |  | 2250 | -4 | 2245 | 1 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Two alternatives to the use of methyl bromide: non-soil cultivation techniques and application of various mixtures of other chemicals in low doses in tobacco | Individual | AFR | CMR | FUM | 25 | DEM | 16 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 160600 | -1033 | 159567 | 159566.82 | 100% | 0.18 | 0 |  | 20878 | -167 | 20711 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in the methyl bromide sector | Individual | LAC | COL | FUM | 55 | TAS | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2010-07-01 |  | 2009-12-01 | 2011-05-01 | 40000 | -620 | 39380 | 39380.46 | 100% | -0.46 | 0 |  | 3600 | -56 | 3544 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in banana growing at Cenibanano | Individual | LAC | COL | FUM | 26 | DEM | 32 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2002-12-01 | 2003-06-01 | 123200 | -377 | 122823 | 122823.29 | 100% | -0.29 | 0 |  | 16016 | -74 | 15942 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project on alternatives to the use of methyl bromide in soil fumigation | Individual | ASP | CPR | FUM | 22 | DEM | 201 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-08-01 | 443300 | -13942 | 429358 | 429358.46 | 100% | -0.46 | 0 |  | 57629 | -1901 | 55728 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide in tobacco production; namely: solarization plus bio-fumigation, the use of low-dose chemicals, and non-soil cultivation, in combination with an integrated pest management programme | Individual | EUR | CRO | FUM | 25 | DEM | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-09-01 | 2000-08-01 |  | 2001-05-01 | 2003-03-01 | 288200 | -28165 | 260035 | 260034.82 | 100% | 0.18 | 0 |  | 37466 | -3715 | 33751 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide in tobacco seedlings | Individual | EUR | CRO | FUM | 35 | INV | 14 | A | I | MBR | 16.2 | 16.2 |  |  | 2001-12-01 | 2002-07-01 | 2007-01-01 |  | 2006-12-01 | 2007-12-01 | 476833 | -5789 | 471044 | 471044.2 | 100% | -0.2 | 0 |  | 61988 | -752 | 61236 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide in soil, substrate, storage and structure fumigation | Individual | LAC | CUB | FUM | 44 | INV | 29 | A | I | MBR | 24.1 | 24.1 |  |  | 2004-12-01 | 2005-07-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 537763 | 0 | 537763 | 534220.49 | 99.34% | 3542.51 | 0 | 1 | 40332 | 0 | 40067 | 265 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Phasing out methyl bromide in the tobacco sector | Individual | LAC | CUB | FUM | 26 | INV | 11 | A | I | MBR | 48 | 48 |  |  | 1998-11-01 | 1999-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-12-01 | 1673324 | -294 | 1673030 | 1673030.39 | 100% | -0.39 | 0 |  | 194066 | -324 | 193742 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: alternatives to the use of methyl bromide: soil pasteurization (steam), non soil cultivation, solarization with biofumigation and low dose chemicals all in combination with IPM system | Individual | LAC | DOM | FUM | 26 | DEM | 19 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2002-03-01 | 2003-05-01 | 324500 | -699 | 323801 | 323800.91 | 100% | 0.09 | 0 |  | 42185 | -158 | 42027 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in melon, flowers and tobacco | Individual | LAC | DOM | FUM | 38 | INV | 33 | A | I | MBR | 141 | 141 |  |  | 2002-11-01 | 2003-01-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 922900 | -886 | 922014 | 922014.19 | 100% | -0.19 | 0 |  | 111519 | -97 | 111422 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation | Individual | AFR | EGY | FUM | 38 | INV | 86 | A | I | MBR | 185.6 | 185.6 |  |  | 2002-11-01 | 2003-09-01 | 2009-11-01 |  | 2009-06-01 | 2011-03-01 | 2750592 | -95 | 2750497 | 2750497.35 | 100% | -0.35 | 0 |  | 312565 | -10 | 312555 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance for the elimination of methyl bromide in grain and storage facilities | Individual | EUR | GEO | FUM | 47 | INV | 20 | A | I | MBR | 7.2 | 7.2 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2012-05-01 | 225500 | -2 | 225498 | 225498.11 | 100% | -0.11 | 0 |  | 20295 | 0 | 20295 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | Project preparation for the phase out of 800 tonnes in the methyl bromide sector (melon) | Individual | LAC | GUA | FUM | 29 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2002-04-01 | 2000-12-01 |  | 2002-12-01 | 2003-12-01 | 45000 | -1164 | 43836 | 43836.4 | 100% | -0.4 | 0 |  | 5850 | -160 | 5690 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization, and low-dose chemicals in combination with an IPM system | Individual | LAC | GUA | FUM | 22 | DEM | 15 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-07-01 | 440000 | -57777 | 382223 | 382222.67 | 100% | 0.33 | 0 |  | 57200 | -7590 | 49610 | 0 | 0 | FIN
FIN | UNIDO | National phase out of methyl bromide | Individual | LAC | GUA | FUM | 38 | INV | 29 | A | I | MBR | 502.6 | 502.6 |  |  | 2002-11-01 | 2003-03-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 3257377 | 0 | 3257377 | 3257376.85 | 100% | 0.15 | 0 |  | 368311 | 0 | 368311 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in melon and banana production sector and tobacco seedling | Individual | LAC | HON | FUM | 37 | INV | 10 | A | I | MBR | 213 | 213 |  |  | 2002-07-01 | 2002-11-01 | 2008-12-01 |  | 2006-12-01 | 2007-09-01 | 1977454 | -6 | 1977448 | 1977448.01 | 100% | -0.01 | 0 |  | 227519 | 0 | 227519 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in store products (rice, coffee and corn) | Individual | ASP | IDS | FUM | 26 | DEM | 94 | A | I |  | 0 | 0 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-12-01 | 2003-10-01 | 332200 | -5985 | 326215 | 326214.65 | 100% | 0.35 | 0 |  | 43186 | -845 | 42341 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 44 | INV | 168 | A | I | MBR | 37.8 | 37.8 |  |  | 2004-12-01 | 2005-04-01 | 2007-12-01 |  | 2008-09-01 | 2009-09-01 | 350000 | -372 | 349628 | 349628.38 | 100% | -0.38 | 0 |  | 26250 | -28 | 26222 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide in soil fumigation in olive seedings, fruit trees, nurseries and others | Individual | ASP | IRA | FUM | 47 | INV | 175 | A | I | MBR | 14.4 | 14.4 |  |  | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2008-12-01 | 2009-12-01 | 227950 | -107 | 227843 | 227842.61 | 100% | 0.39 | 0 |  | 20516 | -10 | 20506 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | Individual | ASP | IRA | FUM | 29 | INV | 57 | A | I | MBR | 12.4 | 12.4 |  |  | 1999-11-01 | 2000-04-01 | 2001-12-01 |  | 2006-12-01 | 2009-03-01 | 260698 | -15748 | 244950 | 244950.15 | 100% | -0.15 | 0 |  | 33891 | -2047 | 31844 | 0 | 0 | FIN
FIN | UNIDO | Phase-out the use of methyl bromide commodities and storage fumigation | Individual | AFR | IVC | FUM | 42 | INV | 19 | A | I | MBR | 8.5 | 8.5 |  |  | 2004-04-01 | 2004-04-01 | 2006-10-01 |  | 2008-12-01 | 2010-12-01 | 222210 | -19676 | 202534 | 202534.15 | 100% | -0.15 | 0 |  | 19999 | -1771 | 18228 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Three alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation and optimal use of soil fumigants in combination with an integrated pest management | Individual | ASP | JOR | FUM | 25 | DEM | 40 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-10-01 | 2000-08-01 |  | 2001-12-01 | 2003-08-01 | 385000 | -64217 | 320783 | 320783.16 | 100% | -0.16 | 0 |  | 50050 | -8414 | 41636 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in cut-flowers at Kenya Agricultural Research Institute - KARI | Individual | AFR | KEN | FUM | 24 | DEM | 17 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-10-01 | 2000-04-01 |  | 2003-03-01 | 2004-03-01 | 328900 | -2958 | 325942 | 325942.31 | 100% | -0.31 | 0 |  | 42757 | -452 | 42305 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - three alternatives to the use of methyl bromide: non-soil cultivation, biofumigation and low dose chemicals in tobacco and horticultural production | Individual | EUR | MDN | FUM | 26 | DEM | 09 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-04-01 | 2003-05-01 | 259600 | -558 | 259042 | 259042.44 | 100% | -0.44 | 0 |  | 33748 | -126 | 33622 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling and horticulture production sector | Individual | EUR | MDN | FUM | 32 | INV | 16 | A | I | MBR | 27.2 | 27.2 |  |  | 2000-12-01 | 2001-10-01 | 2006-01-01 |  | 2004-12-01 | 2006-05-01 | 1075207 | -3327 | 1071880 | 1071880.3 | 100% | -0.3 | 0 |  | 128273 | -553 | 127720 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigant sector | Individual | LAC | MEX | FUM | 51 | PRP | 131 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-08-01 | 2009-05-01 | 60000 | -509 | 59491 | 59490.51 | 100% | 0.49 | 0 |  | 4500 | -38 | 4462 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 121 | A | I | MBR | 36.9 | 132.9 |  |  | 2004-04-01 | 2004-11-01 | 2006-10-01 |  | 2006-12-01 | 2008-06-01 | 207035 | -1912 | 205123 | 205122.67 | 100% | 0.33 | 0 |  | 18633 | -172 | 18461 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide in the cultivation of tomatoes, strawberries, tobacco, melons and cut flowers | Individual | LAC | MEX | FUM | 25 | DEM | 81 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-08-01 |  | 2004-12-01 | 2006-05-01 | 790350 | -13975 | 776375 | 776375.15 | 100% | -0.15 | 0 |  | 102746 | -1977 | 100769 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for a methyl bromide phase-out plan (green beans and cucumber) | Individual | AFR | MOR | FUM | 51 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-03-01 |  | 2008-06-01 | 2009-05-01 | 35000 | -133 | 34867 | 34866.96 | 100% | 0.04 | 0 |  | 2625 | -10 | 2615 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Demonstration project - four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization and low-dose chemicals in combination with an integrated pesticide management system | Individual | AFR | MOR | FUM | 22 | DEM | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 2000-12-01 | 2002-08-01 | 487300 | -7238 | 480062 | 480062.23 | 100% | -0.23 | 0 |  | 63349 | -1040 | 62309 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide for soil fumigation in strawberry production | Individual | AFR | MOR | FUM | 32 | INV | 41 | A | I | MBR | 155 | 155 |  |  | 2000-12-01 | 2001-01-01 | 2006-01-01 |  | 2007-12-01 | 2008-12-01 | 2189729 | 0 | 2189729 | 2189728.97 | 100% | 0.03 | 0 |  | 250870 | 0 | 250870 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide used in peanut seed fumigation in Novasen Ltd. | Individual | AFR | SEN | FUM | 26 | INV | 12 | A | I | MBR | 0.7 | 0.7 |  |  | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-02-01 | 62945 | -3226 | 59719 | 59718.78 | 100% | 0.22 | 0 |  | 8183 | -432 | 7751 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in horticulture and commodities fumigation | Individual | ASP | SYR | FUM | 24 | DEM | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 2001-05-01 | 2003-05-01 | 509850 | -33283 | 476567 | 476566.89 | 100% | 0.11 | 0 |  | 66281 | -4425 | 61856 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide ingrain storage (rice, maize, tapioca, feed grains and pulses) | Individual | ASP | THA | FUM | 25 | DEM | 97 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-04-01 | 2000-08-01 |  | 2003-07-01 | 2004-12-01 | 280500 | -21687 | 258813 | 258813.44 | 100% | -0.44 | 0 |  | 36465 | -2873 | 33592 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Preparation of a project for the elimination of methyl bromide in the post harvest sector | Individual | EUR | TKM | FUM | 53 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 |  | 2009-12-01 | 2011-12-01 | 20000 | -609 | 19391 | 19391.34 | 100% | -0.34 | 0 |  | 1500 | -46 | 1454 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Alternatives to the use of methyl bromide in horticulture at Société Méditeranéene Fruitière | Individual | AFR | TUN | FUM | 24 | DEM | 29 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 2001-02-01 | 2003-05-01 | 301730 | -11452 | 290278 | 290277.8 | 100% | 0.2 | 0 |  | 39225 | -1549 | 37676 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticulture (tomatoes and cucumbers) and ornamental (carnations) crops | Individual | EUR | TUR | FUM | 25 | DEM | 46 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-02-01 | 2000-08-01 |  | 2001-05-01 | 2002-12-01 | 314600 | -9324 | 305276 | 305276.17 | 100% | -0.17 | 0 |  | 40898 | -1275 | 39623 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | UGA | FUM | 34 | INV | 08 | A | I | MBR | 30 | 30 |  |  | 2001-07-01 | 2002-10-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 228800 | -797 | 228003 | 228003.23 | 100% | -0.23 | 0 |  | 29744 | -104 | 29640 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1381 | 297819 | 297819.43 | 100% | -0.43 | 0 |  | 38896 | -241 | 38655 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | I | MBR | 24 | 24 |  |  | 2001-07-01 | 2002-02-01 | 2012-12-01 |  | 2009-12-01 | 2010-12-01 | 469370 | -204 | 469166 | 469166.21 | 100% | -0.21 | 0 |  | 61018 | -26 | 60992 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -9744 | 401436 | 401435.78 | 100% | 0.22 | 0 |  | 53453 | -1349 | 52104 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants sector (soil fumigation) | Individual | AFR | ZAM | FUM | 54 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-09-01 | 2009-03-31 |  | 2008-12-01 | 2011-09-01 | 35000 | -9714 | 25286 | 25285.83 | 100% | 0.17 | 0 |  | 2625 | -729 | 1896 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide used in grain fumigation | Individual | AFR | ZIM | FUM | 50 | INV | 36 | A | I | MBR | 10.2 | 10.2 |  |  | 2006-11-01 | 2007-01-01 | 2010-11-01 |  | 2008-12-01 | 2011-05-01 | 192073 | -246 | 191827 | 191826.75 | 100% | 0.25 | 0 |  | 17287 | -23 | 17264 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project - Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17402 | 353298 | 353297.55 | 100% | 0.45 | 0 |  | 48191 | -2335 | 45856 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | I | MBR | 132 | 132 |  |  | 2000-07-01 | 2001-03-01 | 2004-08-01 |  | 2006-12-01 | 2010-03-01 | 904200 | -10989 | 893211 | 893211.37 | 100% | -0.37 | 0 |  | 109462 | -1209 | 108253 | 0 | 0 | FIN |  |  |  | INV
ONG | Germany | Terminal phase-out of methyl bromide (second tranche) | Multi-Year | ASP | YEM | FUM | 62 | INV | 37 | A | I | MBR | 10 | 6.5 | 0 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-06-01 |  |  | 200000 | 0 | 200000 | 144608 | 72.3% | 55392 |  | 55391.53 | 25325 | 0 | 18234 | 7091 |  | The fruitful cooperation with Custom Authority and related bodies leads to good controlling on imports of methyl bromide by means of quota and licensing systems. Consequently, reduction achieved in methyl bromide importation in 2012 is about 5 ODP tonnes, which fulfill the targets (10 ODP for 2012-2013). During 2011-2012, 181 farmers and 21 extentionists were trained while 100 farms received plastic sheets.
ONG | Germany | Terminal phase-out of methyl bromide (third tranche) | Multi-Year | ASP | YEM | FUM | 68 | INV | 41 | A | I | MBR | 20 |  | 0 |  | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 |  | 155500 | 25325 | 0 | 0 | 25325 |  | Approval at ExCom 68, December 2012 | Following up the results of local herbal technology for soil fumigation as well as the applications of solarization technology at 100 farms that received plastic sheets from the project recently. In addition to distribution of more 20 plastic sheets for farms in Sana'a, Dhamar, Mahweet and Hudiadah.
ONG | Germany | Complete phase-out of the use of methyl bromide in Jordan | Individual | ASP | JOR | FUM | 29 | INV | 54 | A | I | MBR | 180 | 164 | 0 |  | 1999-11-01 | 2000-03-01 | 2014-12-01 | 2015-12-01 |  |  | 3063000 | 0 | 3063000 | 2989451 | 97.6% | 73549 |  | 50000 | 398190 | 0 | 390226 | 7964 |  | 3 field days & 4 workshops held for 163 farmers & intersted engineers & students, 75 farm visits
ONG | IBRD | National methyl bromide phase-out plan (third tranche) | Multiyear | ASP | THA | FUM | 57 | INV | 152 | N | I | MBR | 73.3 | 0 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2012-12-31 | 2013-12-01 |  |  | 942395 | 0 | 942395 | 63149.78 | 6.701% | 879245.22 | 879245.22 | 879245.22 | 70680 | 0 | 4736.25 | 65943.75 | 65943.75 | MB consumption for non-QPS application of 17.04 ODP MT in 2012 did not exceed the agreed plan amount. 13 type 1 subprojects were approved by PMU-DoA for financial assistance under the project. One is financially completed, 5 are physically completed, 6 are under implementation and one remaining is being appraised by Government Savings Bank (GSB). PMU-DoA conducted training on MB alternatives for 5 enterprises (Type I) that already received equipment in Aug. 12. For type 2 beneficiaries, PMU-DoA approached the Rice Mill Association to seek cooperation to disseminate project information to its members. In 2012, PMU-DOA also developed another publication on fumigation techniques namely ?Conducting Fumigation Manual.? 500 copies produced and distributed to users and other stakeholders. In addition, PMU-DOA produced 500 copies of a training video on MB elimination. | PMU-DOA will organize additional training for other beneficiaries in early 2013. Subproject implementation (Type I) and signing of new SGAs continues. |  |  | INV
ONG | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | I | MBR | 58.7 | 58.7 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2006-12-01 | 2013-12-01 |  |  | 546991 | 0 | 546991 | 524830.92 | 95.95% | 22160.08 | 22160.08 | 22160.08 | 41024 | 0 | 39362 | 1662 | 1662 | MB consumption for non-QPS application of 17.04 ODP MT in 2012 did not exceed the agreed plan amount. 13 type 1 subprojects were approved by PMU-DoA for financial assistance under the project. One is financially completed, 5 are physically completed, 6 are under implementation and one remaining is being appraised by Government Savings Bank (GSB). PMU-DoA conducted training on MB alternatives for 5 enterprises (Type I) that already received equipment in Aug. 12. For type 2 beneficiaries, PMU-DoA approached the Rice Mill Association to seek cooperation to disseminate project information to its members. In 2012, PMU-DOA also developed another publication on fumigation techniques namely ?Conducting Fumigation Manual.? 500 copies produced and distributed to users and other stakeholders. In addition, PMU-DOA produced 500 copies of a training video on MB elimination. | PMU-DOA will organize additional training for other beneficiaries in early 2013. Subproject implementation (Type I) and signing of new SGAs continues. |  |  | INV
ONG | IBRD | National methyl bromide phase-out plan (second tranche) | Multiyear | ASP | THA | FUM | 50 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 | 2013-12-01 |  |  | 1412214 | 0 | 1412214 | 525110.01 | 37.18% | 887103.99 | 887103.99 | 887103.99 | 105916 | 0 | 39383.23 | 66532.77 | 66532.77 | MB consumption for non-QPS application of 17.04 ODP MT in 2012 did not exceed the agreed plan amount. 13 type 1 subprojects were approved by PMU-DoA for financial assistance under the project. One is financially completed, 5 are physically completed, 6 are under implementation and one remaining is being appraised by Government Savings Bank (GSB). PMU-DoA conducted training on MB alternatives for 5 enterprises (Type I) that already received equipment in Aug. 12. For type 2 beneficiaries, PMU-DoA approached the Rice Mill Association to seek cooperation to disseminate project information to its members. In 2012, PMU-DOA also developed another publication on fumigation techniques namely ?Conducting Fumigation Manual.? 500 copies produced and distributed to users and other stakeholders. In addition, PMU-DOA produced 500 copies of a training video on MB elimination. | PMU-DOA will organize additional training for other beneficiaries in early 2013. Subproject implementation (Type I) and signing of new SGAs continues. |  |  | INV
ONG | IBRD | National phase-out plan of methyl bromide (third tranche) | Multiyear | ASP | VIE | FUM | 65 | INV | 59 | N | I | MBR | 10 | 0 | 0 | 0 | 2011-11-01 | 2012-12-01 | 2013-11-30 | 2013-11-30 |  |  | 120000 | 0 | 120000 | 108163.33 | 90.14% | 11836.67 | 11836.67 | 11836.67 | 9000 | 0 | 8112.24 | 887.76 | 887.76 | After 1st study on PH3 resistance, PMU carried out in 2012 a follow-up study to develop a national strategy on PH3 resistance management. All training centers fully equipped with fumigation and protection equipment as well as PH3 for practical training on site for fumigation service companies and owners of storage facilities. Train-the-trainers workshop for the 5 centers held in early 2012. 4 training workshops for fumigation service companies and 5 for owners of storage facilities held by 5 Regional Plant Quarantine Sub-Departments assigned as these training centers. Assessment of integrated approaches for MB replacement in pre-harvest applications completed in 2012. 3 alternatives show relatively good results, especially economic efficiency, on crops chosen for demonstrations. Alternatives evaluated to be effective will be printed on leaflets and introduced on local televisions so that more growers are aware. PMU organized 2 training workshops for farmers and local technicians. 9 fumigation service companies completed purchasing of fumigation equipment since May 2012. | MB import quota for 2013 has been issued. |  |  | INV
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 | 2013-06-01 |  |  | 375000 | 0 | 375000 | 192328 | 51.29% | 182672 | 182672 | 120000 | 48750 | 0 | 25002.64 | 23747.36 | 23747.36 | Given long timeframe and high cost to obtain results, the PCU informed the Bank that after discussions with the Ministry of Industry, the project will be closed. INTA has been notified by UEPRO (the PCU) to return the unused funds. INTA sent a draft/preliminary report on the use of funds to UEPRO for review, which was returned to INTA for clarifications. According to UEPRO, updated information on the status of the project will be available after Mar. 2013 upon return of the project management staff at INTA. |  |  |  | Non-INV
ONG | Italy | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 62 | A | I | MBR | 15 | 15 | 0 |  | 2008-11-01 | 2009-07-01 | 2012-11-01 | 2013-12-01 |  |  | 310000 | 0 | 310000 | 250186 | 80.71% | 59814 | 3679 | 50000 | 40300 | 0 | 32524.18 | 7775.82 | 478.27 | Mission to the composting plants was conducted in June 2012 and it was established that the composting plants are operational and the production of high-quality compost as alternative to MB for green-beans in ongoing. Final workshop and project closure planned in 2013. The achieved phase-out is within the agreed phase-out schedule. |  | 2008 |  | Investment
ONG | Spain | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others (second tranche) | Multi-Year | AFR | LIB | FUM | 56 | INV | 30 | A | I | MBR | 40 |  | 0 |  | 2008-11-01 | 2010-05-01 | 2010-11-01 | 2013-12-01 |  |  | 500000 | 0 | 500000 | 220112 | 44.02% | 279888 | 164344 | 20000 | 65000 | 0 | 28614.56 | 36385.44 | 21364.72 | Project implementation in Libya reverted to operational conditions. Two greenhouses purchased in 2010 have been completed in the first week of 2013 and three national experts are assisting UNIDO in monitoring activities and implementing training and awareness activities. Monitoring and planning mission by UNIDO is planned to take place as soon as clearance is received by Libyan Authorities. |  |  |  | Investment
ONG | Spain | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 161 | A | I | MBR | 80 |  | 0 |  | 2012-04-01 |  | 2013-04-01 | 2014-06-01 |  |  | 800000 | 0 | 800000 |  | 0% | 800000 |  | 50000 | 93000 | 0 |  | 93000 |  | Purchase of additional greenhouses and installed. Continue support to the strawberry farmers. To continue the installation of greenhouse, support in grafting, support the strawberry sector. Request of the final tranche at the 69th ExCom. |  |  |  | Investment
ONG | Spain | Technical assistance to introduce chemical alternatives in countries which have rescheduled methyl bromide phase out plan (Argentina and Uruguay) | Individual | LAC | LAC | FUM | 54 | TAS | 40 | A | I | MBR | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 | 2013-12-01 |  |  | 147400 | 0 | 147400 | 62336 | 42.29% | 85064 | 72606 | 50000 | 19162 | 0 | 8103.68 | 11058.32 | 9438.78 | Waiting for the results of Argentina to carry out the final workshop. |  |  |  | Investment
ONG | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche V) | Multi-Year | LAC | COS | FUM | 59 | INV | 43 | N | I | MeBr | 174 | 23 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2013-11-01 | 2014-06-01 |  |  | 726791 | 0 | 726791 | 310357.93 | 42.7% | 416433.07 | 0 | 166573.228 | 54509 | 0 | 23276.706 | 31232.294 | 0 | Biological alternatives are being introduced at commercial scale in the MB sector in Costa Rica. The 2012-13 season was the last season where MB could be used. Technical assistance and investments are being made to be ready for the 2013-14 season, which will be the first free of MB. Progress report was presented to ExCom 68. | The project is closely following the 2012-13 harvest season to trouble shoot on the problems arising with the use of new alternatives. In May the final evaluation of the harvest season will be done. | 2009 |  | Investment
ONG | UNEP | National phase-out of methyl bromide, terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | TAS | 172 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2014-04-01 | 2014-04-01 |  |  | 73000 | 0 | 73000 | 68700 | 94.11% | 4300 | 4300 | 4300 | 9490 | 0 | 8931 | 559 | 559 | 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. National consultant hired to draft adjustments on current pesticides legislation to enforcement the online traceability system. | Adjustments to current pesticides legislations are being reviewed by the Cabinet. (a) Draft TOR for legal consultancy; (b) Review consultant's report on adjustments to MB legislation; c) Provide technical assistance in design and establishment of a web-based MB tracking system. The product (b) required approval by the Cabinet in order to better understand the institutional involvement by the governmental authorities. UNEP provided technical and policy advice relative to the report. In 2013, UNEP will draft an agreement with the Servicio Agricola y Ganadero (SAG) which will in charge of implementation of the web-based tracking system. |  |  | Non Investment
ONG | UNEP | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 9100 | 0 | 0 | 9100 | 0 | Investment activities were implemented by UNIDO. According to the project work plan, UNEP was responsible for the non-investment activities, scheduled for 2013. | Changes in the Government delayed implementation of all Montreal Protocol activities, including this project. The activities expected to resume as planned during 2013. |  |  | Non Investment
ONG | UNEP | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2014-11-01 | 2014-11-01 |  |  | 12500 | 0 | 12500 | 0 | 0% | 12500 | 0 | 12500 | 1625 | 0 | 0 | 1625 | 0 | Investment activities were implemented by UNIDO. According to the project work plan, UNEP was responsible for the non-investment activities, scheduled for 2013. | (a) The Agreement is being drafted. It is expected to be signed by July 2013; (b) The low disbursement was due to lengthy procedure to open a special banking account at the Government level to enable funds transfer to the NOU. The special banking account is expected to be operational by July 2013. |  |  | Non Investment
ONG | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 65 | TAS | 28 | A | I |  | 0.2 | 0 | 0 | 0 | 2011-11-01 |  | 2012-11-01 | 2013-11-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 0 | The project funds approved by the Executive Committee has been pulled together with national funds in order to provide comprehensive technical assistance for the MB phase-out at country level. Assessment of uses of MB, revision of legislation, training activities on the application of suitable alternatives combined with integrated pest management (IPM) and integrated commodity management practices are progressing. 30 Officers from Plant Quarantine, Trade and Ports Departments trained in Methyl Bromide and suitable alternatives. 25 persons from pest control operators, grain mills and flour mills trained. The latter activities were funded from Government funds. | The Government of Trinidad and Tobago requested UNEP's direct administration of funds to pay directly to suppliers instead of signing an agreement. Following the NOU's completion of the technical specifications for equipment required, UNEP will proceed with the procurement. Consequently, the disbursements are foreseen for second half of 2013. |  |  | Non Investment
ONG | UNIDO | National phase-out of methyl bromide - terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | INV | 171 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2014-04-30 | 2014-04-01 |  |  | 1100000 | 0 | 1100000 | 598828.7 | 54.44% | 501171.3 | 258203.45 | 250000 | 82500 | 0 | 44912 | 37588 | 19365 | Grafting technology and biofumigation were introduced and consolidated in two areas: Quillota and Arica. The recruitment of a national consultant company for the strawberry sector started. | The first tranche is almost completed and the request for the second (final) tranche was approved at the 69th Meeting of the Executive Committee in April 2013. The work in the grafting, mainly in the management of grafted plants, is planned to be continued in 2013. In addition, more pilot cases are anticipated in the strawberry and in the tomato sector (biofumigation). A study tour is planned to Mexico with focus on the grafted tomato plants nurseries.
ONG | UNIDO | National phase-out of methyl bromide (phase II, sixth tranche) | Multi-Year | ASP | CPR | FUM | 64 | INV | 509 | A | I | MBR | 26 | 33 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 | 2013-12-01 |  |  | 500000 | 0 | 500000 | 299997.77 | 60% | 200002.23 | 200000 | 100000 | 37500 | 0 | 22500 | 15000 | 15000 | Signed contract with international consultancy company to fine tune MB alternative technologies in ginger sector, project staff participated in study tour at Horty Fair in the Netherland and visited UNIDO's projects in Mexico to acquire new experiences to fine tune MB alternatives. The MB phase-out target was achieved in 2012. The ginger sector has been the sector using most of the MB still available. The tomato, cucumber and strawberry have been almost completely converted, monitoring going on in other sectors. | Develop and test new injection machines for chloropicrin, dazomet and metham sodium (all sectors), fine tune grafting technology for tomato and cucumber, monitor the situation in Taro and other rhizome crops where some MB had been used in 2012. Training and awareness programme continue as planned. There is no delay, the phase-out is on track as well as all the activities. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, seventh tranche) | Multi-Year | ASP | CPR | FUM | 67 | INV | 522 | A | I | MBR | 50 | 26 |  |  | 2012-07-01 |  | 2013-07-31 | 2014-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 500000 | 200000 | 37500 | 0 | 0 | 37500 | 37500 | The 2012 annual implementation programme associated with the 7th tranche was approved in 2012. Signed contract with international consultancy company to fine tune MB alternative technologies in ginger sector, project staff participated in study tour at Horty Fair in the Netherland and visited UNIDO's projects in Mexico to acquire new experiences to fine tune MB alternatives in China. The MB phase-out target was achieved in 2012. The ginger sector has been the sector using most of the MB still available. The tomato, cucumber and strawberry have been almost completely converted, monitoring going on in other sectors. | Develop and test new injection machines for chloropicrin, dazomet and metham sodium (all sectors), fine tune grafting technology for tomato and cucumber, monitor the situation in Taro and other rhizome crops where some MB had been used in 2012. Training and awareness programme continue as planned. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | INV | 38 | A | I | MBR | 48 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2013-11-30 | 2013-11-01 |  |  | 1300000 | 0 | 1300000 | 660821.44 | 50.83% | 639178.56 | 221340.81 | 300000 | 97500 | 0 | 49562 | 47938 | 16601 | Purchase and delivery of the laboratory equipment was carried out in 2012. Farmers got support in the use of alternative fumigants. | The establishment of the laboratory is planned and the first run of the biological agents will be tested and applied. The project is supposed to be finalized at the end of the year. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | LAC | GUA | FUM | 68 | INV | 46 | A | I | MBR | 217.7 | 0 |  |  | 2012-12-01 |  | 2014-12-31 | 2014-12-01 |  |  | 943047 | 0 | 943047 | 0 | 0% | 943047 | 0 | 100000 | 70729 | 0 | 0 | 70729 | 0 | UNIDO was requested to submit the project completion report to the Executive Committee soon after completion of the 2013 annual implementation programme. Purchase of the laboratory equipment was carried out. Farmers got support in the use of alternative fumigants. | The establishment of the laboratory is planned and the first run of the biological agents will be tested and applied. |  |  | INV
ONG | UNIDO | Methyl bromide phase-out plan (Transfer from Canada) | Multi-Year | LAC | MEX | FUM | 63 | INV | 153 | A | I | MBR | 50 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-04-30 | 2014-06-01 |  |  | 500000 | 0 | 500000 | 257256.52 | 51.45% | 242743.48 | 188808.31 | 70000 | 37500 | 0 | 19294 | 18206 | 14161 | The equipment was purchased and delivered in 2012. The fumigators company got continuous support on the adoption to the alternative. | Training will be organized on the use of the new equipment and application to different storage facilities. Reason for the delay: The delivery of the equipment took longer than expected. |  |  | INV
ONG | UNIDO | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 162 | A | I | MBR | 120 | 0 |  |  | 2012-04-01 | 2012-07-01 | 2013-04-30 | 2014-06-01 |  |  | 1200000 | 0 | 1200000 | 502398.78 | 41.87% | 697601.22 | 35637.27 | 150000 | 90000 | 0 | 37680 | 52320 | 2672.7953 | The following activities were implemented in 2012: Soil component: Third planning workshop held in Oaxaca in 2012; • Tomatoes in Baja California, (Los Pinos): One greenhouse was installed. • Tomatoes: One additional greenhouse in Hermosillo (Heras); • Tomatoes: Two recently new companies identified and interested in grafting technologies. Agreements have been made and the necessary equipment (two additional greenhouses) TOR prepared. • Cut flowers: As cut flower sectors have successfully eliminated the use of methyl bromide, some additional technical support was provided to sustain the alternative adopted. • Strawberries in Baja California: Promotion of alternative fumigants was continued; • Substrate (coconut fibre) was purchased as part of the agreement with an important strawberry producer supporting the use of substrates in this sector. • For the strawberry runners and eventually for the production, two spading machines recently purchased. Structures component • Technical assistance to companies on the selection and application of the alternatives to methyl bromide continued; • Demonstration and training workshops were carried out for dissemination of alternatives and distribution of monitoring kits purchased; • Equipment purchased for Heat Treatment; | It is planned to continue the installation of greenhouses and support the strawberry sector in the grafting. The request for the final tranche was submitted and approved at the 69th Meeting of the Executive Committee in April 2013. |  |  | INV
ONG | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and cucurbits (second tranche) | Multi-Year | AFR | MOR | FUM | 62 | INV | 66 | A | I | MBR | 94.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 437594 | 0 | 437594 | 378631.66 | 86.53% | 58962.34 | 4608.31 | 50000 | 32820 | 0 | 28397 | 4423 | 346 | Mission to the composting plants was conducted in June 2012. The composting plants are operational and the production of high-quality compost as alternative to MB for green-beans is ongoing. All main activities have been completed in the year 2012 and closure ceremony was scheduled for 19 December 2012. Due to logistic reasons, the project closure could not take place in 2012 and it has been postponed to 2013. | Final workshop and project closure planned for the second half of 2013. Morocco has confirmed the ban on the import of Methyl Bromide. |  |  | INV
ONG | UNIDO | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | Individual | AFR | AFR | FUM | 54 | DEM | 40 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-06-01 | 2010-03-31 | 2014-12-01 |  |  | 306812 | 0 | 306812 | 98698.49 | 32.17% | 208113.51 | 15643.78 | 5000 | 23011 | 0 | 7402 | 15609 | 1173 | Report and data collection through National Expert in Tunisia have shown good examples in MB alternatives in Tunisia. Report and data collection was conducted by a national consultant. | A follow-up meeting between the national consultant and the PM took place in February 2013 in Algeria. The report of the national expert in Tunisia is under consideration by the NOU for follow-up actions. A mission to Tunisia to discuss the outcomes of the report from the Tunisian expert is scheduled for May 2013. UNIDO expects to reach an agreement with Tunisian counterparts on tests and activities to be performed in the cropping season 2013-2014. Reason for the delay: Due to the lack of national experts, no tests were conducted in the season 2011-2012. |  |  | INV
ONG | UNIDO | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | Individual | LAC | ARG | FUM | 30 | INV | 105 | A | I | MBR | 331 | 224.4 |  |  | 2000-03-01 | 2000-07-01 | 2015-01-01 | 2015-01-01 |  |  | 3183390 | 0 | 3183390 | 3073551.38 | 96.55% | 109838.62 | 93263.86 | 5000 | 360173 | 0 | 348091 | 12082 | 10259 | Following the implementation of all the milestone activities in the previous years, the results of the trial runs were collected and addition trials were initiated in 2012. | To finalize the results of the trial runs and disseminate them.
ONG | UNIDO | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | INV | 57 | A | I | MBR | 40.8 | 0 |  |  | 2011-11-01 | 2012-03-01 | 2014-11-30 | 2014-11-01 |  |  | 317500 | 0 | 317500 | 56082.35 | 17.66% | 261417.65 | 1562.37 | 150000 | 23813 | 0 | 4206 | 19607 | 117 | A national coordinator was recruited in 2012. Agreement was reached with farmers on the alternatives to be demonstrated. Some farmers started their use already. Agreements with laboratory analysis were discussed. | It is planned to establish all the alternatives at the field level, and to collect and analyze the results. A study tour is planned to Spain for 2013 on the biofumigation of cut flowers. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation except in date use | Individual | AFR | EGY | FUM | 56 | INV | 98 | A | I | MBR | 184.2 | 37.8 |  |  | 2008-11-01 | 2009-04-01 | 2013-11-30 | 2014-01-01 |  |  | 1934994 | 0 | 1934994 | 1572509.5 | 81.27% | 362484.5 | 114901.39 | 150000 | 145125 | 0 | 117938 | 27187 | 8618 | Following the implementation of all the milestone activities in the previous years, all the trials were completed in 2012. | Some of the alternative chemicals are in the process of being registered. Continue support in grafting. A final workshop will be organized in 2013. The project is to be completed this year. |  |  | INV
ONG | UNIDO | Project preparation in the fumigant sector (flowers) | Individual | AFR | ETH | FUM | 54 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2013-12-01 |  |  | 35000 | 0 | 35000 | 2435.44 | 6.958% | 32564.56 | 0 | 5000 | 2625 | 0 | 183 | 2442 | 0 | The project was not submitted to the 68th Meeting of the Executive Committee. Reason for delay: there was no significant advancement in the selection of national expert from last report. UNIDO was not in a position to allocate or spend money without the clearance from the official counterpart in the country. | As discussed at the 2013 IAs coordination meeting, UNIDO is considering proposing to the GOV of Ethiopia to use the available budget for a Technical Assistant support, to be implemented in the course of 2013. Consultation with the Government took place in this regard after the 2013 IAs coordination meeting. UNIDO is discussing with the NOU on the scope of the project activities and the budget allocation. |  |  | NON-INV
ONG | UNIDO | Technical assistance for alternatives to methyl bromide | Individual | ASP | IRQ | FUM | 62 | INV | 13 | A | I | MBR | 3.5 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2014-07-01 |  |  | 211970 | 0 | 211970 | 14224.36 | 6.711% | 197745.64 | 52238.87 | 25000 | 19077 | 0 | 1280 | 17797 | 4701 | Contract between UNIDO and the State Board for Plant Protection (SBPP) of the Ministry of the Agriculture of Iraq signed in February 2012. Mission undertaken by the UNIDO Project Manager and the representatives of the SBPP took place in September 2012, in order to finalize the Terms of Reference for the equipment and Plan of Action. Plan of action was agreed upon; TORs were prepared and agreed upon; Funds disbursed until end 2012 does not reflect the work done in 2012. While disbursement is low at the end of 2012, funds have been obligated for main activities. | a. ToR for the purchase of Project equipment and supplies have been prepared according to the Decisions of the UN Sanction Committee and will be submitted for further approvals shortly. b. Study tour to Jordan for the representatives of the SBPP is planned in 2013. The purpose of the visit is to offer the Iraqi experts and technicians an overview on the available technical and logistic alternative solutions to the use of Methyl Bromide. |  |  | INV
ONG | UNIDO | Technical assistance for the final elimination of methyl bromide in post harvest sector | Individual | AFR | KEN | FUM | 65 | INV | 52 | A | I | MBR | 6.6 | 0 |  |  | 2011-11-01 | 2012-09-01 | 2012-11-30 | 2013-12-01 |  |  | 287700 | 0 | 287700 | 23456.83 | 8.153% | 264243.17 | 8056.27 | 80000 | 21578 | 0 | 1759 | 19819 | 604 | Mission organized in August 2012, based on which the TORs were finalized. It is confirmed that the planned completion date is December 2013. The reason for the low disbursement is that contracts for all equipment will be signed in 2013. | a. The bidding was opened in January 2013. b. Awarding the contract to the suppliers for the required equipment. C. Mission planned in June 2013 to monitor on equipment delivery and installation. The reason for the low disbursement is that contracts for all equipment will be signed in 2013 (expected by end of May) and installation will be executed in 2013 as soon as items are delivered at project sites. |  | 2014-01-01 | INV
ONG | UNIDO | Methyl bromide national phase-out plan (soil fumigation) | Individual | ASP | SYR | FUM | 49 | TAS | 95 | A | I | MBR | 48 | 75 |  |  | 2006-07-01 | 2007-12-01 | 2010-07-01 | 2013-12-01 |  |  | 240000 | 0 | 240000 | 141578.29 | 58.99% | 98421.71 | 33484.4 | 45000 | 21600 | 0 | 12742 | 8858 | 3014 | In agreement with the NOU in 2011, the sub-contract with the national team of experts was extended until September 2012. Project implemenation has been slowed down due to the to unstabile security situation in the country. However, UNIDO maintained constant contact and consultation with the the national agency GSCAR (General Commision for Scientific Agricultural Research) for the project execution. GCSAR managed to implement training activities under the contract with UNIDO. | UNIDO is discussing sub-contracting GCSAR for the remaining activities (e.g. final workshop, production of last awareness materials) in order to solve the implementation obstacles. Reason for the delay: The security and political situation in the country. |  |  | INV
ONG | UNIDO | Technical assistance for the elimination of methyl bromide in post harvest sector | Individual | EUR | TKM | FUM | 59 | INV | 06 | A | I | MBR | 2.8 | 0.6 |  |  | 2009-11-01 | 2010-07-01 | 2013-12-01 | 2013-12-01 |  |  | 179586 | 0 | 179586 | 142956.8 | 79.6% | 36629.2 | 16505.98 | 2000 | 16163 | 0 | 12866 | 3297 | 1486 | Study tour for the national project manager and the national expert on QPS and technical assistance was organized in May 2012 to the University of Mollise, Italy. Aim was to gain necessary knowledge and experience on alternatives in using MB in actual use in grain and food processing sector. Guide on MB alternatives was prepared in the cooperation with the University of Mollise, in addition to updated legislation. In addition to the activities indicated above, in 2012 the latest training activities took place, including publication of technical guide on management of grains and use of alternative technologies for insect control and eradication. | Final workshop and project closure is planned in May 2013. The achieved phase-out is within the agreed phase-out schedule. |  |  | INV
ONG | UNIDO | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses | Individual | AFR | ZAM | FUM | 56 | INV | 21 | A | I | MBR | 7.4 | 7.4 |  |  | 2008-11-01 | 2009-12-01 | 2011-11-30 | 2013-12-01 |  |  | 289548 | 0 | 289548 | 168373.27 | 58.15% | 121174.73 | 41160 | 60000 | 21716 | 0 | 12628 | 9088 | 3087 | TORs for purchasing materials and consumables for tobacco sub-sector have been prepared. | The bidding was initiated and the calls are ongoing with the deadline of April 2013. Contracts are expected to be signed by end of May and delivery to take place by July 2013. Reason for delay: longer time needed for the elaboration of the TORs. |  |  | INV
TRF | Canada | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 149 | A | I | MBR | 0 |  | 0 |  | 2010-04-01 |  | 2011-04-01 |  |  |  | 500000 | -500000 | 0 | 0 |  | 0 |  | 0 | 58527 | -58527 | 0 | 0 |  | Project was transferred to UNIDO at 63rd ExCom meeting. No expenditures will thus be made by Canada. |  | 2010 |  | Investment
TRF | Canada | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 41 | INV | 158 | A | I |  | 0 |  | 0 |  | 2003-12-01 |  | 2007-12-01 |  |  | 2004-12-01 | 350000 | -350000 | 0 | 0 |  | 0 |  | 0 | 45500 | -45500 | 0 | 0 |  | Project transferred to UNIDO. |  | 2003 |  | Non-Inv.
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation (second tranche) | Multi-Year | AFR | KEN | FUM | 44 | INV | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-11-01 | 306396 | -306396 | 0 | 0 |  | 0 | 0 | 0 | 22980 | -22980 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2004 |  | Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flowers (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 40 | A | I | MeBr | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2009-12-01 |  |  | 2007-11-01 | 204263 | -204263 | 0 | 0 |  | 0 | 0 | 0 | 15320 | -15320 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2010 annual programme | Multi-Year | ASP | CPR | SOL | 59 | INV | 495 | N | I | TCA | 85 | 85 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 |  | 1480000 | 0 | 1480000 | 1479999.6 | 100% | 0.4 | 0 | 0.32 | 111000 | 0 | 110999.97 | 0.03 | 0 | Completed in 2012. Most activities are completed. Monitoring of programme execution at the state-level EPBs was ongoing. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2008 annual programme | Multi-Year | ASP | CPR | SOL | 53 | INV | 457 | N | I | TCA | 85 | 85 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 |  | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2009 annual programme | Multi-Year | ASP | CPR | SOL | 56 | INV | 479 | N | I | TCA | 84 | 84 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 |  | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Completed in 2009. |  | 2008 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2006 annual programme | Multi-Year | ASP | CPR | SOL | 47 | INV | 435 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2005-11-01 | 2009-05-01 | 2006-12-01 |  | 2009-12-01 |  | 5055000 | 0 | 5055000 | 5055000 | 100% | 0 | 0 | 0 | 379125 | 0 | 379125 | 0 | 0 | Completed in 2009. |  | 2005 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2007 annual programme | Multi-Year | ASP | CPR | SOL | 50 | INV | 446 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-12-01 |  | 2009-12-01 |  | 5480000 | 0 | 5480000 | 5480000 | 100% | 0 | 0 | 0 | 411000 | 0 | 411000 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2004 annual programme | Multi-Year | ASP | CPR | SOL | 42 | INV | 410 | N | I | CFC | 733 | 733 | 0 | 0 | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2006-12-01 |  | 5555000 | 0 | 5555000 | 5555000 | 100% | 0 | 0 | 0 | 416625 | 0 | 416625 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2005 annual programme | Multi-Year | ASP | CPR | SOL | 45 | INV | 429 | N | I | TCA/CTC | 635 | 635 | 0 | 0 | 2005-04-01 | 2007-02-01 | 2006-04-01 |  | 2009-12-01 |  | 5680000 | 0 | 5680000 | 5680000 | 100% | 0 | 0 | 0 | 426000 | 0 | 426000 | 0 | 0 | Completed in 2009. |  | 2005 |  | Investment
COM | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (fourth tranche) | Multi-Year | AFR | NIR | SOL | 52 | INV | 116 | A | I | CTC | 45.9 | 45.9 |  |  | 2007-07-01 | 2007-12-01 | 2010-01-01 |  | 2012-11-01 |  | 303200 | 0 | 303200 | 288812.68 | 95.25% | 14387.32 | 13410 | 14000 | 22740 | 0 | 21661 | 1079 | 1006 | Project completed in Nov 2012. |  |  |  | INV
FIN | France | Conversion to ODS-free technology at Dorcharkh Company |  | ASP | IRA | SOL | 28 | INV | 48 | A | I | CTC | 11 | 11 | 0 |  | 1999-07-01 | 2001-08-01 | 2001-08-01 |  | 2002-12-01 | 2008-10-01 | 165140 | 0 | 165140 | 165140 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project completed. 5% support costs mentioned by the financing agreement were included in the allocated amount.
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1996-12-01 | INV
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV
FIN | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | I | TCA | 15.4 | 15.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 |  | 2005-02-01 | 2005-12-01 | 518693 | -45479.16 | 473213.84 | 473213.84 | 100% | 0 | 0 |  | 67056.23 | -5538.18 | 61517.82 | 0.23 | 0.23 | All 16 projects completed. |  |  |  | INV
FIN | Italy | Terminal CTC phase-out project | Individual | EUR | YUG | SOL | 56 | INV | 33 | A | I | CTC | 2.6 | 2.6 | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2010-06-01 | 2011-12-01 | 49324 | -338 | 48986 | 48986 | 100% | 0 | 0 |  | 6412 | -43.82 | 6368.18 | 0 | 0 | FIN |  | 2008 |  | Investment
FIN | UNDP | ODS-free cleaning equipment manufacturing center for phasing out ODS consuming solvents across China | Individual | ASP | CPR | SOL | 12 | INV | 65 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1997-06-01 | 1996-03-01 |  | 1999-11-01 | 2002-07-01 | 524734 | -50707 | 474027 | 474027 | 100% | 0 | 0 | 0 | 68215.42 | -6592.42 | 61623 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-113, l,l,l trichloroethane and CFC-12 at multiple corporations that manufacture special formulations for industrial markets (Ariad Industrial Co., Cloisonne, Redisol, Rodler) | Individual | ASP | PHI | SOL | 25 | INV | 56 | A | I | TCA/CFC | 18.4 | 18.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2003-04-01 | 334600 | -93314 | 241286 | 241286 | 100% | 0 | 0 | 0 | 43498 | -12131 | 31367 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Elimination of the use of CFC-113, 1,1,1 trichloroethane (TCA), CFC-11 and CFC-12 at multiple corporations that manufacture special formulations for various industrial markets | Individual | ASP | PHI | SOL | 19 | INV | 46 | N | I | TCA/CFC | 53.6 | 53.6 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1998-06-01 | 2003-09-01 | 642800 | -181667 | 461133 | 461133 | 100% | 0 | 0 | 0 | 83564 | -23617 | 59947 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (2nd tranche) | Multi-Year | AFR | NIR | SOL | 46 | INV | 113 | A | I | CTC TCA | 0 | 0 |  |  | 2005-07-01 | 2005-11-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 23775 | 0 | 23775 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase out umbrella project in the solvent sector (first tranche) | Multi-Year | AFR | NIR | SOL | 43 | INV | 110 | A | I | CTC | 152.1 | 152.1 |  |  | 2004-07-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-05-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 39750 | 0 | 39750 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | AFR | EGY | SOL | 44 | INV | 89 | A | I | CFC CTC TCA | 41 | 41 |  |  | 2004-12-01 | 2005-02-01 | 2006-06-01 |  | 2007-12-01 | 2009-05-01 | 778464 | -5845 | 772619 | 772619.45 | 100% | -0.45 | 0 |  | 58385 | -439 | 57946 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to semi-aqueous cleaning and no-clean soldering technologies at ITI, Bangalore | Individual | ASP | IND | SOL | 19 | INV | 95 | A | I | CFC TCA | 7 | 7 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1996-12-01 | 1999-08-01 | 107954 | -808 | 107146 | 107146 | 100% | 0 | 0 |  | 14034 | -127 | 13907 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from TCA and CTC to non-ODS solvent cleaning technologies (trichloroethylene and alkozypropanol) at Videocon Group (VDC) | Individual | ASP | IND | SOL | 28 | INV | 225 | A | I | CTC TCA | 7.2 | 7.2 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2002-01-01 | 2003-03-01 | 234978 | -4 | 234974 | 234973.65 | 100% | 0.35 | 0 |  | 30547 | -49 | 30498 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS solvents to heat cleaning technologies and ODS free solvent coating at Malhotra Shaving Products Ltd. | Individual | ASP | IND | SOL | 25 | INV | 181 | A | I | CFC | 13.6 | 13.6 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-01-01 | 255112 | 0 | 255112 | 255111.63 | 100% | 0.37 | 0 |  | 33165 | 0 | 33165 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents aqueous cleaning at ITI Mankapur | Individual | ASP | IND | SOL | 13 | INV | 25 | A | I | CFC | 34 | 48.8 |  |  | 1994-07-01 | 1996-06-01 | 1996-01-01 |  | 1996-10-01 | 2000-12-01 | 610160 | 0 | 610160 | 610160 | 100% | 0 | 0 |  | 79321 | -2 | 79319 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) and methyl chloroform (MCF) to tetrachloroethylene (PER) and water in combination with partial process modification at Hirra Farooq Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 51 | A | I | CTC MCF | 37.5 | 37.5 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 246493 | -536 | 245957 | 245956.64 | 100% | 0.36 | 0 |  | 22184 | -48 | 22136 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC), methyl chloroform (MCF) and CFC-113 to tetrachloroethylene (PER) and water in combination with process modification at Breeze Frost Industries Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 52 | A | I | CTC MCF CFC | 33.2 | 33.2 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 282056 | -204 | 281852 | 281852.22 | 100% | -0.22 | 0 |  | 21254 | -15 | 21239 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project for phase-out of remaining ozone depleting solvents | Individual | EUR | TUR | SOL | 41 | INV | 83 | A | I | CTC | 24 | 24 |  |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2005-12-01 | 2007-03-01 | 531644 | -52625 | 479019 | 479018.64 | 100% | 0.36 | 0 |  | 39873 | -3947 | 35926 | 0 | 0 | FIN |  |  |  | INV
ONG | Japan | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. |  | ASP | CPR | SOL | 64 | DEM | 506 | A | I |  | 1.1 |  | 0 |  | 2011-07-01 |  | 2012-09-01 | 2013-12-01 |  |  | 205616 | 0 | 205616 | 0 | 0% | 205616 | 0 |  | 26730 | 0 |  | 26730 |  | Planned completion date is December 2013 | None.
ONG | UNDP | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. | Individual | ASP | CPR | SOL | 64 | DEM | 511 | N | I | HCFC | 2 | 0 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 | 2013-12-01 |  |  | 352051 | 0 | 352051 | 172026 | 48.86% | 180025 | 0 | 54007.5 | 26404 | 0 | 12902.0355 | 13501.9645 | 0 | Project document signed. Enterprise-level phase-out agreement concluded. Project activities progressed as planned. | Project targeted for completion in 2013. | 2011 |  | Non-Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Dalian No. 1 | Individual | ASP | CPR | FOA | 15 | INV | 97 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1998-12-01 |  |  | 2000-07-01 | 490000 | -457910 | 32090 | 32090 | 100% | 0 | 0 | 0 | 63700 | -59528 | 4172 | 0 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
CLO | UNDP | Conversion from CFC-11 in the manufacture of boxfoam (FPF) and insulated containers (RPF) in Prasert Sofa Shop Co., Ltd. | Individual | ASP | LAO | FOA | 44 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-12-01 | 184660 | -184660 | 0 | 0 |  | 0 | 0 | 0 | 16619 | -16619 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2004 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 179 | N | I | CFC | 172 | 172 | 0 | 0 | 2007-03-01 | 2009-02-01 | 2009-03-01 |  | 2010-12-01 |  | 159555 | 0 | 159555 | 150506.86 | 94.33% | 9048.14 | 0 | 7238.512 | 13160 | 0 | 12413.7149 | 746.2851 | 0 | Technical assistance, monitoring and management continued throughout 2010. Procurement of additional identifiers for supporting decentralized monitoring by district environment units completed. Activities are completed but final payments still due to take place in 2011. |  | 2007 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (sixth tranche) | Multi-Year | ASP | IDS | REF | 54 | INV | 181 | N | I | CFC | 241 | 241 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2011-12-01 |  | 181000 | 0 | 181000 | 174359.93 | 96.33% | 6640.07 | 0 | 5312.056 | 16290 | 0 | 15692.3937 | 597.6063 | 0 | Completed in 2011. Technical assistance, monitoring and management continued throughout 2011. Some pending payments remaining. | Project targeted for financial closure in 2012 | 2008 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 177 | N | I | CFC | 300 | 300 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2009-03-01 |  | 2010-12-01 |  | 217000 | 0 | 217000 | 217000 | 100% | 0 | 0 | 0 | 19530 | 0 | 19530 | 0 | 0 | Completed. Technical assistance, monitoring and management continued in 2010. Activities are completed but final payments still due to take place in 2011. Follow-up activities in IDS-181. |  | 2007 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 175 | N | I | CFC | 200 | 200 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2007-04-01 |  | 2008-12-01 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21300 | 0 | 21300 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 174 | N | I | CFC | 300 | 300 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-12-01 |  | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 67500 | 0 | 67500 | 0 | 0 | Completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (third tranche) | Multi-Year | ASP | IND | FOA | 44 | INV | 384 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-12-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (second tranche) | Multi-Year | ASP | IND | FOA | 41 | INV | 365 | N | I | CFC | 210 | 210 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-07-01 |  | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 | 0 | 153500 | 0 | 153500 | 0 | 0 | Completed in 2006. |  | 2003 |  | Investment
COM | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | ARG | FOA | 38 | INV | 132 | A | I | CFC | 192.3 | 192.3 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2007-12-01 |  | 1324843 | -17620.02 | 1307222.98 | 1307222.98 | 100% | 0 | 0 | 0 | 155732.7 | -2070.93 | 153661.77 | 0 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | IBRD | Phase-out of residual CFCs in the foam sector (fourth tranche) | Multiyear | ASP | IDS | FOA | 54 | INV | 182 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-04-01 | 2010-06-01 | 2009-03-31 |  | 2010-06-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phase-out of residual CFCs in the foam sector (third tranche) | Multiyear | ASP | IDS | FOA | 51 | INV | 176 | N | I | CFC | 156 | 156 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-06-01 | 2010-12-01 | 147564 | 0 | 147564 | 147564 | 100% | 0 | 0 |  | 11067 | 0 | 11067 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phase-out of residual CFCs in the foam sector (second tranche) | Multiyear | ASP | IDS | FOA | 48 | INV | 172 | N | I | CFC | 130 | 130 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78750 | 0 | 78750 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100% | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | 2000-12-01 | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | I | CFC | 51.75 | 51.75 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 100% | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | Project technically and financially completed. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 09 | N | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 07 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2002-11-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100% | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | Project and draft PCR completed. |  |  | 1999-09-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 |  | 2005-02-01 | 2007-06-01 | 563339 | 0 | 563339 | 563339 | 100% | 0 | 0 |  | 73234 | 0 | 73234 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | Project completed. PCR submitted to the WB in Sep. 01 |  |  |  | INV
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 07 | INV | 05 | N | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100% | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100% | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | Installation completed. 100% non-CFC production started. PCR submitted. |  |  |  | INV
FIN | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (third tranche) | Multi-Year | ASP | IND | REF | 44 | INV | 383 | N | I | CFC | 141 | 141 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2012-11-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21621 | 0 | 21621 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin and flexible molded foam at PPU | Individual | LAC | BRA | FOA | 31 | INV | 178 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2003-09-01 | 64568 | -5159 | 59409 | 59409 | 100% | 0 | 0 | 0 | 8393.84 | -670.84 | 7723 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam and rigid integral skin foam at Piatex | Individual | LAC | BRA | FOA | 34 | INV | 214 | A | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-11-01 | 83075 | 0 | 83075 | 83075 | 100% | 0 | 0 | 0 | 10800 | 0 | 10800 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin and rigid foam at Montreal | Individual | LAC | BRA | FOA | 31 | INV | 181 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2003-08-01 |  | 2002-08-01 | 2003-09-01 | 83117 | 0 | 83117 | 83117 | 100% | 0 | 0 | 0 | 10805 | 0 | 10805 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Pretty Glass | Individual | LAC | BRA | FOA | 36 | INV | 243 | A | I | CFC | 17.2 | 17.2 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 91508 | -6465 | 85043 | 85043 | 100% | 0 | 0 | 0 | 11896.04 | -840.04 | 11056 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam and rigid foam at Trantor | Individual | LAC | BRA | FOA | 31 | INV | 184 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 102234 | -5218 | 97016 | 97016 | 100% | 0 | 0 | 0 | 13290.42 | -679.42 | 12611 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and rigid foam at Injepol | Individual | LAC | BRA | FOA | 31 | INV | 175 | A | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 107678 | -9727 | 97951 | 97951 | 100% | 0 | 0 | 0 | 13998.14 | -1265.14 | 12733 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam, from CFC-11 to water-blown foam in flexible molded foam, and from CFC-11 to HCFC-141b in flexible integral skin foam at Multispuma | Individual | LAC | BRA | FOA | 31 | INV | 187 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 123929 | 0 | 123929 | 123929 | 100% | 0 | 0 | 0 | 16111 | 0 | 16111 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam and to HCFC-141b for rigid polyurethane foam at Poliumetka | Individual | LAC | BRA | FOA | 32 | INV | 194 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-05-01 | 2003-09-01 | 136183 | -10263 | 125920 | 125920 | 100% | 0 | 0 | 0 | 17703.79 | -1333.79 | 16370 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by HCFC-141b in the manufacture of integral skin foam furniture and conversion from CFC-11 to methylene chloride in the manufacture of polyurethane boxfoam at Cantegril | Individual | LAC | BRA | FOA | 26 | INV | 116 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-05-01 | 154740 | -4476 | 150264 | 150264 | 100% | 0 | 0 | 0 | 20116.2 | -582.2 | 19534 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Tolling Quimica | Individual | LAC | BRA | FOA | 36 | INV | 249 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-08-01 | 2005-10-01 | 159662 | -1356.0019 | 158305.9981 | 158306 | 100% | -0.0019 | 0 | 0 | 20756.06 | -176.0597 | 20580.0005 | -0.000247 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible microcellular foams at Hidroplas | Individual | LAC | BRA | FOA | 34 | INV | 238 | A | I | CFC | 33 | 33 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2002-11-01 | 2004-01-01 | 166211 | -5537 | 160674 | 160674 | 100% | 0 | 0 | 0 | 21607.43 | -720.43 | 20887 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in flexible molded foam, to water and methylene chloride technology in semi-rigid packaging foam, and to HCFC-141b in flexible integral skin foams at Espuma Oeste | Individual | LAC | BRA | FOA | 28 | INV | 138 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 181616 | -5766 | 175850 | 175850 | 100% | 0 | 0 | 0 | 23610.08 | -750.08 | 22860 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin foam, flexible molded foam and rigid foam at Jetpol | Individual | LAC | BRA | FOA | 31 | INV | 183 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2003-08-01 |  | 2002-05-01 | 2003-09-01 | 214600 | -9772 | 204828 | 204828 | 100% | 0 | 0 | 0 | 27898 | -1270 | 26628 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam, rigid foam and flexible molded foam at Carolinas | Individual | LAC | BRA | FOA | 34 | INV | 232 | A | I | CFC | 49.7 | 49.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 237597 | -80 | 237517 | 237517 | 100% | 0 | 0 | 0 | 30887.61 | -9.61 | 30878 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water/methylene chloride/hydrocarbon-blown technology in the manufacture of rigid and flexible foam at Toro | Individual | LAC | BRA | FOA | 36 | INV | 255 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2004-12-01 | 2005-10-01 | 279477 | 0 | 279477 | 279477 | 100% | 0 | 0 | 0 | 36332 | 0 | 36332 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid foam and flexible integral skin foam and water-blown technology for flexible moulded foam and rigid integral skin foam at Ariston Polimeros | Individual | LAC | BRA | FOA | 36 | INV | 257 | A | I | CFC | 75.1 | 75.1 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-08-01 | 2005-09-01 | 369242 | -12749 | 356493 | 356493 | 100% | 0 | 0 | 0 | 48001.46 | -1657.46 | 46344 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam and rigid integral skin foam, and to HCFC-141b for rigid, flexible integral skin and phenolic foams at J. Dal Ponte | Individual | LAC | BRA | FOA | 34 | INV | 233 | A | I | CFC | 97.6 | 97.6 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 384134 | 0 | 384134 | 384134 | 100% | 0 | 0 | 0 | 49937 | 0 | 49937 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and integral skin foam at JNP Group | Individual | LAC | BRA | FOA | 28 | INV | 140 | A | I | CFC | 80.3 | 80.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2002-12-01 | 2006-10-01 | 823867 | -22056 | 801811 | 801811 | 100% | 0 | 0 | 0 | 100625.4 | -2426.37 | 98199.03 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and flexible molded/integral skin foam at 50 small enterprises centered around their systems house Plastquim | Individual | LAC | BRA | FOA | 31 | INV | 189 | A | I | CFC | 153.4 | 153.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-12-01 | 931599 | -41480 | 890119 | 890119 | 100% | 0 | 0 | 0 | 112475.9 | -4562.89 | 107913.01 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at Olaflex with a technical assistance programme covering 10 small customers | Individual | LAC | COL | FOA | 32 | INV | 47 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2001-12-01 | 2003-10-01 | 191833 | 0 | 191833 | 191833 | 100% | 0 | 0 | 0 | 24938 | 0 | 24938 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion rom CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at 25 small enterprises centered around their systems house Espumlatex | Individual | LAC | COL | FOA | 32 | INV | 48 | A | I | CFC | 38.4 | 38.4 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2004-12-01 | 2004-12-01 | 332768 | 0 | 332768 | 332768 | 100% | 0 | 0 | 0 | 43260 | 0 | 43260 | 0 | 0 | Completed in 2004. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | COL | FOA | 38 | INV | 58 | A | I | CFC | 123.2 | 123.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-04-01 | 840170 | 0 | 840170 | 840170 | 100% | 0 | 0 | 0 | 102419 | 0 | 102419 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane products at Daimei | Individual | ASP | CPR | FOA | 17 | INV | 134 | N | I | CFC | 77 | 77 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-12-01 |  | 1998-12-01 | 2001-12-01 | 362600 | -43425.16 | 319174.84 | 319175 | 100% | -0.16 | 0 | 0 | 47138 | -5645.0008 | 41493.02 | -0.0208 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible molded PUF and integral skin foam at El Shabrawi | Individual | AFR | EGY | FOA | 18 | INV | 48 | A | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 1999-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacturing of moulded, flexible, semi-rigid and rigid polyurethane foam at Taki-Vita factory | Individual | AFR | EGY | FOA | 08 | INV | 06 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1995-04-01 | 2003-04-01 | 293950 | 58550 | 352500 | 352500 | 100% | 0 | 0 | 0 | 38213.5 | 7612.5 | 45826 | 0 | 0 | Completed in 1995. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of rigid molded and miscellaneous PUF at 5 plants: Tiba Air, Egat Company, Solar Energy Company, Ismailia Aluminum Company, and Fu Tech Company | Individual | AFR | EGY | FOA | 12 | INV | 26 | A | I | CFC | 44.2 | 44.2 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-03-01 | 1997-11-01 | 870000 | -107668 | 762332 | 762332 | 100% | 0 | 0 | 0 | 113100 | -13997 | 99103 | 0 | 0 | Completed in 1997. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | Individual | AFR | EGY | FOA | 22 | INV | 64 | A | I | CFC | 319 | 319 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 2005-01-01 | 2007-01-01 | 1672000 | -18136 | 1653864 | 1653864 | 100% | 0 | 0 | 0 | 217360 | -2358 | 215002 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1997 | 2000-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based systems and HCFC-141b in the manufacture of polyurethane foam for automotive and furniture applications at P.T. Yoska Prima Inti | Individual | ASP | IDS | FOA | 29 | INV | 114 | A | I | CFC | 49.5 | 49.5 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 368868 | -221866 | 147002 | 147002 | 100% | 0 | 0 | 0 | 47952.84 | -28842.84 | 19110 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Enkay Foam P., Ltd. | Individual | ASP | IND | FOA | 31 | INV | 275 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 162339 | -4442 | 157897 | 157897 | 100% | 0 | 0 | 0 | 21104.07 | -577.07 | 20527 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and integral skin foam products to water blown systems in flexible molded polyurethane foam at Joti Foam Pr | Individual | ASP | IND | FOA | 26 | INV | 185 | A | I | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 174290 | -287 | 174003 | 174003 | 100% | 0 | 0 | 0 | 22657.7 | -36.7 | 22621 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of polyurethane foam at U-Foam Private Ltd. | Individual | ASP | IND | FOA | 13 | INV | 30 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1997-11-01 | 2000-12-01 | 328500 | -77822 | 250678 | 250678 | 100% | 0 | 0 | 0 | 42705 | -10117 | 32588 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Reactive Polymers Ltd. | Individual | ASP | IND | FOA | 29 | INV | 240 | A | I | CFC | 29.6 | 29.6 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 354175 | -56621 | 297554 | 297554 | 100% | 0 | 0 | 0 | 46042.75 | -7360.75 | 38682 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | LIB | FOA | 32 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2000-12-01 | 2001-12-01 |  | 2001-03-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of moulded and flexible PU foams at Dream Products Snd. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 48 | A | D | CFC | 15 | 15 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-11-01 |  | 1998-09-01 | 2000-07-01 | 66500 | -154 | 66346 | 66346 | 100% | 0 | 0 | 0 | 8645 | -20 | 8625 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC -free technology for the manufacture of flexible polyurethane foam at Far East Foam Industries | Individual | ASP | MAL | FOA | 19 | INV | 89 | A | I | CFC | 41.2 | 41.2 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-09-01 | 2001-12-01 | 209000 | -2275 | 206725 | 206725 | 100% | 0 | 0 | 0 | 27170 | -296 | 26874 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam and to LCD technology in the manufacture of flexible molded foam at Sy Heng Huat | Individual | ASP | MAL | FOA | 31 | INV | 136 | A | I | CFC | 46.2 | 46.2 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-01-01 | 2003-11-01 | 272235 | 0 | 272235 | 272235 | 100% | 0 | 0 | 0 | 35391 | 0 | 35391 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid foam (spray) and integral skin foam at Con Espuma | Individual | LAC | MEX | FOA | 23 | INV | 72 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 96100 | -2230 | 93870 | 93870 | 100% | 0 | 0 | 0 | 12493 | -290 | 12203 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b or water-blown technology in rigid polyurethane foam (spray) and to water based formulations in integral skin foam at Comsisa | Individual | LAC | MEX | FOA | 31 | INV | 98 | A | I | CFC | 68.7 | 68.7 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2003-08-01 |  | 2003-10-01 | 2004-01-01 | 424050 | 0 | 424050 | 424050 | 100% | 0 | 0 | 0 | 55127 | 0 | 55127 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Foam sector ODS phaseout plan (first trnache) | Individual | LAC | MEX | FOA | 35 | INV | 103 | N | I | CFC | 145 | 145 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2003-07-01 |  | 2004-11-01 | 2009-08-01 | 833150 | 0 | 833150 | 833150 | 100% | 0 | 0 | 0 | 101647 | 0 | 101647 | 0 | 0 | Completed in 2004.Financially completed in 2009. |  | 2000 |  | Investment
FIN | UNDP | Foam sector ODS phase-out plan (second tranche) | Individual | LAC | MEX | FOA | 42 | INV | 117 | N | D | CFC | 192 | 192 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2007-12-01 | 2009-08-01 | 1109120 | -78998 | 1030122 | 1030122.23 | 100% | -0.23 | 0 | 0 | 83184 | -5924.85 | 77259.1672 | -0.01725 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible and rigid polyurethane foam at Plastifoam, S.A., Profomsa, and Thermofoam, S.A. | Individual | LAC | PAN | FOA | 13 | INV | 05 | A | I | CFC | 26 | 26 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1999-08-01 | 2002-10-01 | 155000 | -13140 | 141860 | 141860 | 100% | 0 | 0 | 0 | 20150 | -1708 | 18442 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of polyurethane foam at Superspuma Del Paraguay SAIC, Suenolar, La Asuncena, and Industrias Cel | Individual | LAC | PAR | FOA | 23 | INV | 04 | A | I | CFC | 55.5 | 55.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-10-01 | 405600 | -118208 | 287392 | 287392 | 100% | 0 | 0 | 0 | 52728 | -15367 | 37361 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Foam sector ODS phaseout plan (covering 5 enterprises: Molflex; Zetaflex; EMSA; Metusa; Polishoes) | Individual | LAC | PER | FOA | 35 | INV | 30 | A | I | CFC | 33.8 | 33.8 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2006-12-01 | 2008-04-01 | 325277 | 0 | 325277 | 325277 | 100% | 0 | 0 | 0 | 42286 | 0 | 42286 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of PUF foam at RGC Foam Group (Polyfoam/Uratex) | Individual | ASP | PHI | FOA | 18 | INV | 62 | A | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1997-05-01 |  | 1997-06-01 | 2000-07-01 | 650000 | -3624 | 646376 | 646376 | 100% | 0 | 0 | 0 | 84500 | -471 | 84029 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF slabstock and cold cured mouldings st Somboon Paisarn 85 Company Ltd. | Individual | ASP | THA | FOA | 15 | INV | 42 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-11-01 |  | 1998-11-01 | 2000-12-01 | 225000 | -5000 | 220000 | 220000 | 100% | 0 | 0 | 0 | 29250 | -650 | 28600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA (flexible), to water-based technology (flexible molded, structural and integral skin) and HCFC-141b technology (rigid) at Great Foam Products, Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 122 | A | I | CFC | 22.1 | 22.1 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 231843 | -23 | 231820 | 231820 | 100% | 0 | 0 | 0 | 30139.59 | -2.99 | 30136.6 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF cold cured mouldings, integral skin mouldings and rigid PUF articles at Thai Union PU Co. Ltd. | Individual | ASP | THA | FOA | 15 | INV | 41 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1996-12-01 | 2000-12-01 | 525000 | -72931 | 452069 | 452069 | 100% | 0 | 0 | 0 | 68250 | -9481.03 | 58768.97 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid and integral skin polyurethane foam at Bangkok Foam Group | Individual | ASP | THA | FOA | 22 | INV | 63 | A | I | CFC | 90.6 | 90.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2001-12-01 | 480500 | 0 | 480500 | 480500 | 100% | 0 | 0 | 0 | 62465 | 0 | 62465 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian) | Individual | ASP | CPR | FOA | 34 | INV | 375 | A | I | CFC | 191.6 | 191.6 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-07-01 | 2005-12-01 | 1087764 | -80453 | 1007311 | 1007310.63 | 100% | 0.37 | 0 |  | 129654 | -9025 | 120628 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at Hamhung Foam Factory, Hamgyong South Province | Individual | ASP | DRK | FOA | 23 | INV | 06 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 102680 | -2145 | 100535 | 100535 | 100% | 0 | 0 |  | 13348 | -299 | 13049 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Pyongyang Foam Plant | Individual | ASP | DRK | FOA | 23 | INV | 07 | A | I | CFC | 83 | 83 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 103570 | -1984 | 101586 | 101585.63 | 100% | 0.37 | 0 |  | 13464 | -279 | 13185 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Chongjin Foam Factory, Hamgyong North Province | Individual | ASP | DRK | FOA | 23 | INV | 08 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 103670 | -72 | 103598 | 103598 | 100% | 0 | 0 |  | 13477 | -31 | 13446 | 0 | 0 | FIN
ONG | Italy | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid and integral skin foams at Poly-Mix | Multi-Year | EUR | CRO | FOA | 60 | INV | 35 | A | I | HCFC | 1.8 | 0 | 0 |  | 2010-04-01 | 2011-12-01 | 2012-04-01 | 2013-09-01 |  |  | 210000 | 0 | 210000 | 163507 | 77.86% | 46493 | 21500 | 30000 | 27300 | 0 | 21255.91 | 6044.09 | 2795 | Foaming equipment was installed end January 2012. Additional accessories required for the operation were purchased in the first half of 2012, but installation delayed until early 2013. Contract for the payment of incremental operating cost was signed in March 2013 and payment will be released upon presentation of invoices. Destruction of replaced equipment and finalization of the project is planned for the third quarter 2013. The company is already using water based formulation and there is no more use of HCFC-141b. |  | 2010 |  | Investment
ONG | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of PU insulated sandwich panels and phaseout HCFC-142b and HCFC-22 in the manufacture of extruded polystyrene boardstock | Multi-Year | EUR | TUR | FOA | 62 | INV | 97 | A | I | HCFC | 213.2 | 80 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2014-03-01 |  |  | 7713490 | 0 | 7713490 | 473139.08 | 6.134% | 7240350.92 | 1390299.4 | 2000000 | 578512 | 0 | 35485 | 543027 | 104272 | Equipment delivery and installations were undertaken for 4 companies (out of 9) during the first half of 2012. For the other 5 companies, technical specifications were finalized and bidding/ contracts awards for conversion were issued during 2012. Approved Technologies: N-pentane, HFC-152a/dimethyl ether (DME), CO2/ethanol. | Conversion is on-going with private co-financing component, thus, subject to reimbursements when safety certification and other operation permits procedures are finalized Completion of the conversions / project completion is expected in 2013. |  |  | INV
FIN | Czech Republic | Regional network for 10 article 5 countries in Eastern Europe and Central Asia (jointly implemented with Hungary, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 58487 | 0 | 58487 | 58487 | 100% | 0 | 0 | 0 | 7603 | 0 | 7603 | 0 | 0 | Financially completed. | Financially completed. | 2003 |  | 2003
FIN | Hungary | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 2 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 41145 | 0 | 41145 | 41145 | 100% | 0 |  |  | 5349 | 0 | 5349 | 0
FIN | Slovak Republic | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 3 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 14622 | 0 | 14622 | 14622 | 100% | 0 |  |  | 1901 | 0 | 1901 | 0
FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | AFR | AFR | SEV | 12 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-03-01 | 2000-03-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 | 0 | 23400 | 0 | 23400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | AFR | AFR | SEV | 16 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-01-01 | 232200 | 0 | 232200 | 232200 | 100% | 0 | 0 | 0 | 30186 | 0 | 30186 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | African Network (1996) | Individual | AFR | AFR | SEV | 19 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299400 | 0 | 299400 | 299400 | 100% | 0 | 0 | 0 | 38922 | 0 | 38922 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | African Region Network (1997) | Individual | AFR | AFR | SEV | 21 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 411000 | -33344 | 377656 | 377656 | 100% | 0 | 0 | 0 | 53430 | -4334.72 | 49095.28 | 0 | 0 | Project financially completed. ($33,344 plus $4,335 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | AFR | AFR | SEV | 23 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 |  | 1998-12-01 | 2000-03-01 | 431000 | -21369 | 409631 | 409631 | 100% | 0 | 0 | 0 | 56030 | -2777.97 | 53252.03 | 0 | 0 | Project financially completed. ($21,369 plus $2,778 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | AFR | AFR | SEV | 26 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 431000 | -14398 | 416602 | 416602 | 100% | 0 | 0 | 0 | 56030 | -1871.74 | 54158.26 | 0 | 0 | Project financially completed. ($14,398 plus $1,872 PSC returned ExCom 37) |  |  |  | Non Investment
FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | AFR | AFR | SEV | 29 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-01-01 | 452550 | -30254 | 422296 | 422296 | 100% | 0 | 0 | 0 | 58832 | -3933 | 54898.9466 | 0.053426 | 0 | Project financially completed. ($30,000 plus $3900 PSC returned ExCom46 $ 254 plus $ 33 returned from ExCom 49) |  |  |  | Non Investment
FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | AFR | AFR | SEV | 32 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 464000 | -36863 | 427137 | 427137 | 100% | 0 | 0 | 0 | 60320 | -4792.19 | 55527.81 | 0 | 0 | Project financially completed. ($36,863 plus 4,792 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Networking and Training (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($24,323 plus $3,162 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | ODS officers network for Asia and the Pacific (1995) | Individual | ASP | ASP | SEV | 16 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 2000-03-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | South Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 199000 | -109950 | 89050 | 89050 | 100% | 0 | 0 | 0 | 25870 | -14293.5 | 11576.5 | 0 | 0 | Project financially completed. ($48,604 plus $6,319 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | West Asian region network (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2005-12-01 | 120750 | -15000 | 105750 | 105750 | 100% | 0 | 0 | 0 | 15698 | -1950 | 13747.9379 | 0.062112 | 0 | Project financially completed. ($15,122 plus $1,966 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | West Asian regional network (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 124000 | -15001 | 108999 | 108999 | 100% | 0 | 0 | 0 | 16120 | -1950.13 | 14169.87 | 0 | 0 | Project financially completed. ($20,468 plus $2,661 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | West Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. ($109,950 plus 14294 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | West Asian regional network (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | West Asian Region Network (1999) | Individual | ASP | ASP | SEV | 26 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. ($18,941 plus $2,462 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | West Asian Network (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-12-01 | 169200 | -24323 | 144877 | 144877 | 100% | 0 | 0 | 0 | 21996 | -3161.99 | 18834.01 | 0 | 0 | Project financially completed. ($19,056 plus $2,477 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Asia Regional Networks for SEAP and East Asia (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 209000 | -48604 | 160396 | 160396 | 100% | 0 | 0 | 0 | 27170 | -6318.52 | 20851.48 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Asia and the Pacific Regional networks (South East Asia and Pacific and South Asia) (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 219450 | -18941 | 200509 | 200509 | 100% | 0 | 0 | 0 | 28529 | -2462.33 | 26066.6268 | 0.043156 | 0 | Project financially completed. ($15,000 plus $1,950 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | South East Asia and the Pacific and South Asia regional networks (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2002-06-01 | 2003-06-01 | 225000 | -20468 | 204532 | 204532 | 100% | 0 | 0 | 0 | 29250 | -2660.84 | 26589.16 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Asia Regional Networks (South-East and Pacific and South Asia) | Individual | ASP | ASP | SEV | 26 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 | 0 | 27170 | 0 | 27170 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | Individual | EUR | EUR | SEV | 39 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 53666 | 0 | 53666 | 53666 | 100% | 0 | 0 | 0 | 6977 | 0 | 6977 | 0 | 0 | Project financially completed. ($ 83 plus $11 returned to ExCom 51) |  |  |  | Non Investment
FIN | UNEP | Support to networking activities | Individual | GLO | GLO | SEV | 09 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1993-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to regional network for OzonAction/ODS focal points | Individual | LAC | LAC | SEV | 09 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-03-01 | 2000-12-01 | 130000 | -9000 | 121000 | 121000 | 100% | 0 | 0 | 0 | 16900 | -1170 | 15730 | 0 | 0 | Project financially completed. ($ 57,167 plus $ 7,432 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1994) | Individual | LAC | LAC | SEV | 12 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1995-03-01 | 2000-12-01 | 224000 | -14500 | 209500 | 209500 | 100% | 0 | 0 | 0 | 29120 | -1885 | 27235 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Networking and Training in Latin American Region Network (including English-speaking Caribbean) | Individual | LAC | LAC | SEV | 19 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299000 | -57167 | 241833 | 241833 | 100% | 0 | 0 | 0 | 38870 | -7431.71 | 31438.29 | 0 | 0 | Project financially completed. ($ 53,324 plus $ 6,932 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1995) | Individual | LAC | LAC | SEV | 16 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-05-01 | 1996-03-01 |  | 1995-08-01 | 2000-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Project financially completed. ($ 38,093 plus $ 4,952 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Latin American Region Network (1997) | Individual | LAC | LAC | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 380000 | -38093 | 341907 | 341907 | 100% | 0 | 0 | 0 | 49400 | -4952.09 | 44447.91 | 0 | 0 | Project financially completed. ($ 55,099 plus $ 7,163 PSC returned ExCom 37) |  |  |  | Non Investment
FIN | UNEP | Latin America Region Network (South America, Central America and the Caribbean) | Individual | LAC | LAC | SEV | 26 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-12-01 | 2000-12-01 | 399000 | -55099 | 343901 | 343901 | 100% | 0 | 0 | 0 | 51870 | -7162.87 | 44707.13 | 0 | 0 | Project financially completed. ($ 42 plus $ 5 PSC returned to ExCom 54$ 12,458 plus $ 1,620 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Latin America Region Networks for LAC South, LAC Central, and Caribbean (1998) | Individual | LAC | LAC | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 399000 | -53324 | 345676 | 345676 | 100% | 0 | 0 | 0 | 51870 | -6932.12 | 44937.88 | 0 | 0 | Project financially completed. ($ 30,000 plus 3,900 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Latin America and the Caribbean regional networks (South America, Central America, Caribbean) (2000) | Individual | LAC | LAC | SEV | 29 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 418950 | -30000 | 388950 | 388950 | 100% | 0 | 0 | 0 | 54464 | -3900 | 50563.9642 | 0.035804 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | South American, Central American and the Caribbean regional networks (2001) | Individual | LAC | LAC | SEV | 32 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 429000 | -17257 | 411743 | 411743 | 100% | 0 | 0 | 0 | 55770 | -2243.41 | 53526.59 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | AFR | AFR | FUM | 17 | TAS | 14 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-10-01 | 1995-11-01 | 38896 | 0 | 38896 | 38896 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNIDO | Non-investment project: promotion and information transfer of alternatives to the use of methyl bromide in the preparation of seedbeds for the cultivation of rice and maize | Individual | ASP | DRK | FUM | 25 | TAS | 09 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 1999-07-01 |  | 1999-11-01 | 2001-03-01 | 27500 | -153 | 27347 | 27347 | 100% | 0 | 0 |  | 3575 | -25 | 3550 | 0 | 0 | FIN |  |  |  | NON-INV
COM | USA | CFCs, CTC and halon accelerated phase-out-plan (second tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 439 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2009-01-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 |  |  | 375000 | 0 | 375000 | 0 |  | Ongoing.
FIN | UNIDO | Closure of ODS production plant (third tranche) | Multi-Year | ASP | DRK | PRO | 49 | INV | 43 | A | I |  | 0 | 0 | 2530 | 2530 | 2006-07-01 | 2006-11-01 | 2008-12-01 |  | 2006-12-01 | 2008-04-01 | 488750 | 0 | 488750 | 488750 | 100% | 0 | 0 |  | 24438 | 0 | 24438 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant: verification of complete closure of all CFC-11 and CFC-12 production facilities (second tranche) | Multi-Year | ASP | DRK | PRO | 42 | INV | 33 | A | I | CFC | 0 | 0 | 1250 | 1250 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2004-06-01 | 2004-12-01 | 733700 | 0 | 733700 | 733700 | 100% | 0 | 0 |  | 36685 | 0 | 36685 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant | Multi-Year | ASP | DRK | PRO | 36 | INV | 17 | A | R | CFC | 0 | 0 | 500 | 500 | 2002-03-01 | 2002-10-01 | 2003-03-01 |  | 2002-10-01 | 2003-05-01 | 1344350 | 0 | 1344350 | 1344350 | 100% | 0 | 0 |  | 67217 | 0 | 67217 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (second tranche) | Multi-Year | EUR | ROM | PRO | 50 | INV | 35 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2007-06-01 | 2012-10-01 | 900000 | 0 | 900000 | 858528.16 | 95.39% | 41471.84 | 0 | 1 | 67500 | 0 | 64390 | 3110 | 0 | Financial completion in Oct 2012. |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (third tranche) | Multi-Year | EUR | ROM | PRO | 52 | INV | 39 | A | I | CTC | 0 | 0 | 170 | 170 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2007-12-01 | 2008-07-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (fourth tranche) | Multi-Year | EUR | ROM | PRO | 53 | INV | 40 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2010-12-01 | 2012-11-01 | 1200000 | 0 | 1200000 | 1199999.88 | 100% | 0.12 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | Financial completion in Nov 2012. |  |  |  | INV
FIN | UNIDO | Sector plan for production sector | Multi-Year | EUR | ROM | PRO | 47 | INV | 32 | A | I | MBR | 0 | 0 | 5 | 5 | 2005-11-01 | 2006-04-01 | 2006-07-01 |  | 2006-12-01 | 2011-12-01 | 3200000 | -150 | 3199850 | 3199850.03 | 100% | -0.03 | 0 |  | 240000 | -11 | 239989 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
COM | Germany | National phase-out plan (1st tranche) | Multi-Year | ASP | AFG | PHA | 47 | INV | 06 | A | I | CFC | 28 | 28 | 0 |  | 2005-11-01 | 2006-05-07 | 2007-12-01 |  | 2008-08-01 |  | 118438 | 0 | 118438 | 118438 | 100% | 0 | 0 | 0 | 15397 | 0 | 15397 | 0 | 0 | The foam sector was evaluated. A strategy was worked out based on the training of technicians for one foam company. A training was conducted for Afghan technicians in Tehran, Iran in April 2008. In addition, an inspection was carried out to the foam company in Afghanistan, Kabul in 2008.
COM | Germany | National phase-out plan (2nd tranche) | Multi-Year | ASP | AFG | PHA | 48 | INV | 07 | A | I | CFC | 151.8 | 151.8 | 0 |  | 2006-04-01 | 2006-05-01 | 2009-12-01 |  | 2009-12-01 |  | 642368 | 0 | 642368 | 642368 | 100% | 0 | 0 | 0 | 83508 | 0 | 83508 | 0 | 0 | R&R equipment was delivered in Apr-2007, training and commissioning was accomplished in May 2007, 83 R&R units have been distributed until 12-2008, furhter 63 will be distributed in 2009. In addition, two train the trainer workshops were organized in 2007 and 2008.
COM | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | I | CFC | 486 | 486 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 1315400 | 0 | 1315400 | 1315400 | 100% | 0 | 0 | 0 | 118386 | 0 | 118386 | 0 | 0 | Implementation of activities under this tranche completed. |  |  |  | INV
COM | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-03-01 |  | 4011846 | 0 | 4011846 | 4011846 | 100% | 0 | 0 | 0 | 353066 | 0 | 353066 | 0 | 0 | Implementation of activities under this tranche completed. |  |  |  | INV
COM | Japan | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MON | PHA | 53 | INV | 12 | A | I | CFC | 1.5 | 1.5 | 0 |  | 2007-11-01 | 2009-11-01 | 2009-11-01 |  | 2010-12-01 |  | 55000 | 0 | 55000 | 40000 | 72.73% | 15000 | 0 | 15000 | 7150 | 0 |  | 7150
COM | Japan | Terminal phase-out management plan: first tranche | Multi-Year | ASP | MON | PHA | 47 | INV | 10 | N | I | CFC | 1.8 | 1.8 | 0 |  | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2010-09-01 |  | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0
COM | Japan | National compliance action plan: incentive programme for commercial and industrial refrigeration end-users | Individual | ASP | SRL | PHA | 43 | TAS | 26 | A | I | CFC | 5 |  | 0 |  | 2004-07-01 | 2008-12-01 | 2005-12-01 |  | 2011-12-01 |  | 144000 | 0 | 144000 | 144000 | 100% | 0 | 0 | 0 | 18720 | 0 | 18720 | 0 | 0 | PCR is being completed. |  | 2004 | 2007-12-01
COM | Japan | National compliance action plan: monitoring the activities proposed in the plan | Individual | ASP | SRL | PHA | 43 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2009-12-01 |  | 2011-12-01 |  | 108000 | 0 | 108000 | 108000 | 100% | 0 | 0 | 0 | 14040 | 0 | 14040 | 0 | 0 | PCR is being completed. |  | 2004
COM | Japan | National compliance action plan: MAC recovery/recycling and retrofit | Individual | ASP | SRL | PHA | 43 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2006-12-01 | 2005-12-01 |  | 2010-09-01 |  | 123000 | 0 | 123000 | 123000 | 100% | 0 | 0 | 0 | 15990 | 0 | 15990 | 0 |  | PCR is being completed. |  | 2004
COM | Japan | National compliance action plan: recovery and recycling programme | Individual | ASP | SRL | PHA | 43 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2008-10-01 | 2006-12-01 |  | 2010-12-01 |  | 290400 | 0 | 290400 | 290400 | 100% | 0 | 0 | 0 | 37752 | 0 | 37752 | 0 |  | PCR is being completed. |  | 2004
COM | UNDP | National ODS phase-out plan: technical assistance for the phase-out of ODS solvents (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 20 | N | I | CTC | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed. During the year 2010, 2 training programs were held in Dhaka and Chittagong. About 200 supervisors of ready- made garment industry were trained on the using non-ODS alternatives of CTC. |  | 2004 |  | Investment
COM | UNDP | National ODS phase-out plan: monitoring and management unit (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 |  | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 2550 | 0 | 2550 | 0 | 0 | Completed. The PMU in coordination with NOU undertakes management and monitoring of activities under the NoPP. |  | 2004 |  | Non-Investment
COM | UNDP | National ODS phase-out plan (fifth and sixth tranches) | Multi-year | ASP | BGD | PHA | 60 | INV | 36 | N | I | CFC | 21.9 | 21.9 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2012-12-01 |  | 55000 | 0 | 55000 | 50112.36 | 91.11% | 4887.64 | 0 | 3910.112 | 4125 | 0 | 3758.427 | 366.573 | 0 | Completed in 2012. All activities under this project completed in the year 2012. | Completed in 2012. The project is expected to be financially closed by end of Q2 2013. | 2010 |  | Investment
COM | UNDP | National ODS phase-out plan: technical assistance programme for the refrigeration servicing sub-sector (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 19 | N | I | CFC | 36 | 36 | 0 | 0 | 2004-04-01 | 2008-02-01 | 2005-04-01 |  | 2010-12-01 |  | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 7200 | 0 | 7200 | 0 | 0 | Completed. In the year 2010, procurement of Equipment completed and distribution of equipment to identified beneficiaries is underway. On activities relating to retrofit of CFC based refrigerators, 15 workshops were held in different parts of Bangladesh namely Chittagong, Khulna, Rajshahi, Rangpur, Dinajpur, Sylhet, Mymensing, Tangail, Satkhira, Jessore, Kustia, Narayanganj, Dhaka(2), Gajipur. About 1000 technicians were trained. Two seminars were held in Dhaka and Chittagong on Chiller sector ODS phase-out and alternatives to be adopted in chiller sector. 200 personnel handling policy issues and operating/servicing chillers attended the workshop. Awareness activities were organized in conjunction with retrofit project. Participants in these programs included local administration, elites, school/college teachers and NGOs. Monitoring and follow-up activities were also undertaken in Dhaka and Chittagong during the year 2010. |  | 2004 |  | Investment
COM | UNDP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TAS | 31 | N | I | CFC | 202.6 | 202.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2011-07-01 |  | 669750 | 0 | 669750 | 669750 | 100% | 0 | 0 | 0 | 50231 | 0 | 50231 | 0 | 0 | Completed in 2011. See BGD-36. | Completed in 2011. See BGD-36. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | INV | 33 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2012-10-01 |  | 222000 | 5000 | 227000 | 221848.2 | 97.73% | 5151.8 | 0 | 4121.44 | 16650 | 375 | 16638.615 | 386.385 | 0 | Completed in 2012. Final activities under the TPMP have been implemented and project is completed. | Completed in 2012. 5000 US$ from Environment Canada has been transferred to UNDP and will be implemented under this project.The remaining resources will be used for training of technicians in Bolivia. | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | INV | 29 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-03-01 |  | 2009-12-01 |  | 151000 | 0 | 151000 | 151000 | 100% | 0 | 0 | 0 | 11325 | 0 | 11325 | 0 | 0 | Completed in 2009. |  | 2007 |  | Investment
COM | UNDP | National phase-out plan for Annex A (Group I and II) substances: first implementation programme | Multi-Year | LAC | COL | PHA | 41 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2008-12-01 |  | 2146820 | 0 | 2146820 | 2146820 | 100% | 0 | 0 | 0 | 161011 | 0 | 161011 | 0 | 0 | Completed in 2008. |  | 2003 |  | Investment
COM | UNDP | National phase-out plan for Annex A (Group I and II) substances: second implementation programme | Multi-Year | LAC | COL | PHA | 47 | INV | 63 | N | I | CFC | 805.9 | 805.9 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2011-12-01 |  | 2353180 | 0 | 2353180 | 2340380.6 | 99.46% | 12799.4 | 0 | 10239.52 | 176488 | 0 | 175528.0477 | 959.9523 | 0 | Completed in 2011. CFCs phased out succesfully. Training of technicians continued. | Final financial obligations being disbursed. | 2005 |  | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | INV | 20 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2010-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Completed. Technical visit by international expert fielded in March 2010. TPMP/RMP implementation plans were discussed and updated. National team of technical experts pre-screened fifteen (15) compnaies to participate in the end-user programme. Twenty four (24) units of MAC (and some household) equipment were retrofitted with the use of HFC-134a. Improved performance of retrofitted MAC equipment was recorded. Capacity strenthening of two centers of excellence was performed in parallel to similar activities carried out under RMP -specialized trainings in retrofit techniques were held under umbrella of RMP. |  | 2009 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | INV | 46 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 |  | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
COM | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-10-01 | 2010-06-01 |  | 2012-07-01 |  | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNIDO | National ODS Phase out plan (seventh tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 20 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-09-01 |  | 22322 | 0 | 22322 | 21454.56 | 96.11% | 867.44 | 0 | 500 | 1674 | 0 | 1609 | 65 | 0 | Project completed in Sep 2012. |  |  |  | INV
COM | UNIDO | National CFC/CTC phase-out plan (fourth tranche) | Multi-Year | AFR | SUD | PHA | 58 | INV | 23 | A | I | CFC | 65.3 | 65.3 |  |  | 2009-07-01 | 2009-12-01 | 2011-07-31 |  | 2012-03-01 |  | 200000 | 0 | 200000 | 198511.86 | 99.26% | 1488.14 | 1486.6 | 1000 | 15000 | 0 | 14888 | 112 | 111.495 | Project completed in Mar 2012. |  |  |  | INV
FIN | Canada | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | TAS | 28 | A | I | CFC,CTC | 15.3 | 15.3 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-12-01 |  | 2009-03-01 | 2009-04-01 | 79000 | 0 | 79000 | 79000 | 100% | 0 |  | 0 | 10270 | 0 | 10270 | 0 |  | Completion of the revision of the legal framework, diffusion of awareness-raising material, training of 159 customs officers. Inspection visits to workshops and importers took place in several cities throughout 2009 to evaluate their compliance with national legislation and verify the consumption. Most project activities completed by March 2009. A CTC workshop with users was rescheduled under second tranche to September 2009 due to coordination issues. |  | 2007 |  | Investment
FIN | Canada | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2008-01-01 | 2008-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 |  | 0 | 52000 | 0 | 52000 | 0 |  | First phase of R&R equipment shipped in May 2005. Public awareness activities initiated in 2005 are continuing and include the production of technical pamphlets, videos, TV commercials, education workshops etc.. 2nd phase of R&R equipment and retrofit tools delivered in November 2007. 3rd phase completed in January 2008. Note that target and consumption indicated under columns BB and BC are for 2005. |  | 2004 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | TAS | 47 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2008-01-01 | 2007-11-01 |  | 2010-07-01 | 2011-07-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 |  | 0 | 20800 | -9120 | 11680 | 0 |  | All project activities, including training and establishment of collaboration with enforcement, had been completed. Final report from NOU received. $9,120 remaining in support costs were returned to Fund, as noted at ExCom 64 in July 2011. |  | 2006 |  | Investment
FIN | France | Terminal ODS phase-out management plan (third tranche) | Multi-Year | AFR | SEY | PHA | 59 | INV | 16 | A | I | CFC | 0.4 |  | 0 |  | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 13000 | -13000 | 0 | 0 |  | 0 |  | 0 | 1690 | -1690 | 0 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal ODS phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 55 | INV | 14 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-05-01 | 2009-03-01 |  | 2010-12-01 | 2012-12-01 | 60000 | -40121 | 19879 | 19879 | 100% | 0 |  | 0 | 7800 | -5215.73 | 2584.27 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal ODS phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 51 | INV | 12 | A | I | CFC | 0 | 0 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-06-01 | 2011-06-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 15600 | 0 | 15600 | 0 |  | The French contribution is implmented by GTZ-Proklima. Project completed.
FIN | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | UGA | PHA | 59 | INV | 15 | A | I | CFC | 1.9 | 1.9 | 0 |  | 2009-11-01 | 2010-01-01 | 2010-11-01 |  | 2011-04-01 | 2012-12-01 | 62500 | -5571 | 56929 | 56929 | 100% | 0 |  | 0 | 8125 | -724.23 | 7400.77 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | UGA | PHA | 55 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-12-01 | 2010-12-01 |  | 2010-09-01 | 2012-12-01 | 152500 | 0 | 152500 | 152500 | 100% | 0 |  | 0 | 19825 | 0 | 19825 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | UGA | PHA | 50 | PRP | 12 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2009-03-01 | 2012-12-01 | 30000 | -2264 | 27736 | 27736 | 100% | 0 |  | 0 | 3900 | -294.32 | 3605.68 | 0 |  | The French contribution is implmented by GTZ; Project completed.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (third tranche) | Multi-Year | AFR | MAR | PHA | 50 | INV | 18 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-03-01 | 2007-12-01 |  | 2010-08-01 | 2012-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | All activities under the TPMP have been completed.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 45 | INV | 16 | A | I | CFC | 2 | 2 | 0 |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2007-12-01 | 2008-04-01 | 62030 | 0 | 62030 | 62030 | 100% | 0 | 0 | 0 | 8064 | 0 | 8064 | 0 | 0 | 2nd tranche was approved.
FIN | Germany | Implementation of an ODS terminal phase out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 41 | INV | 15 | A | I | CFC | 0 | 2.6 | 0 |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-10-01 | 2006-04-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | 2 Hydrocarbon trainings have been conducted. NOU started the process of converting the New Court House through a subsidy scheme provided under the project. Next tranche has been approved.
FIN | Germany | Terminal phase-out management plan for ODS (2nd tranche) | Multi-Year | ASP | PNG | PHA | 48 | INV | 08 | A | I | CFC | 17 | 4.5 | 0 |  | 2006-04-01 | 2006-08-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | PNG has maintained compliance of zero CFC-imports. PNG has completed the incentive scheme. The final report is under preparation.
FIN | Germany | Terminal phase-out management plan for ODS (1st tranche) | Multi-Year | ASP | PNG | PHA | 39 | INV | 05 | A | I | CFC | 18 | 30.8 | 0 |  | 2003-04-01 | 2003-08-01 | 2005-12-01 |  | 2006-07-01 | 2006-12-01 | 480000 | 0 | 480000 | 480000 | 100% | 0 | 0 | 0 | 59700 | 0 | 59700 | 0 | 0 | PNG has successfully completed the 1st Action Plan of the TPMP and the country's consumption is well below the TPMP reduction targets.
FIN | IBRD | National ODS phase-out plan (second tranche) | Multiyear | AFR | TUN | PHA | 61 | INV | 51 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2012-06-01 | 2012-10-01 | 345395 | -345395 | 0 | 0 |  | 0 | 0 | 0 | 25905 | -25905 | 0 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV
FIN | IBRD | National ODS phase-out plan (first tranche) | Multiyear | AFR | TUN | PHA | 49 | INV | 47 | N | I | CFC | 169.5 | 169.5 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2008-07-31 |  | 2012-06-01 | 2012-10-01 | 790000 | -360123 | 429877 | 429877 | 100% | 0 | 0 | 0 | 59250 | -27009 | 32241 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV
FIN | IBRD | National CFC and halon phase-out plan (third tranche) | Multiyear | ASP | VIE | PHA | 55 | INV | 51 | N | I | CFC | 58.7 | 58.7 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2011-02-01 | 178463 | -551.92 | 177911.08 | 177911.08 | 100% | 0 | 0 |  | 13385 | -41.4 | 13343.6 | 0 | 0 | Project physically and financially completed. Unused amount of US$552 returned. |  |  |  | INV
FIN | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | I | CFC | 40 | 40 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2007-04-01 |  | 2008-07-01 | 2011-02-01 | 495537 | 0 | 495537 | 495537 | 100% | 0 | 0 |  | 37165 | 0 | 37165 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | National CFC and halon phase-out plan (second tranche) | Multiyear | ASP | VIE | PHA | 49 | INV | 47 | N | I | CFC | 165 | 165 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-06-01 | 2011-02-01 | 586000 | 0 | 586000 | 586000 | 100% | 0 | 0 |  | 43950 | 0 | 43950 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | I |  | 157.4 | 157.4 | 0 | 0 | 2002-11-01 | 2005-11-01 | 2009-11-01 |  | 2009-11-01 | 2009-12-01 | 590000 | 0 | 590000 | 590000 | 100% | 0 | 0 |  | 74900 | 0 | 74900 | 0 | 0 | All investment work has been undertaken. Last public awareness event held in 2009 on the achievements of the NOPP and future challenges. Training was also conducted for the solvents sector. PCR is under preparation. |  |  |  | INV
FIN | UNEP | National phase-out plan (1st tranche) | Multi-year | ASP | AFG | PHA | 47 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 305000 | 0 | 305000 | 305000 | 100% | 0 | 0 | 0 | 39650 | 0 | 39650 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Multi-year | EUR | ALB | PHA | 39 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2005-08-01 | 2007-04-01 | 35700 | -278 | 35422 | 35422 | 100% | 0 | 0 | 0 | 4641 | -36 | 4604.86 | 0.14 | 0 | Project financially completed. ($ 278 plus $ 36 PSC returned at ExCom 52) |  |  |  | Non Investment
FIN | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Multi-year | EUR | ALB | PHA | 39 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2006-07-01 | 2010-12-01 | 82425 | -10163 | 72262 | 72262 | 100% | 0 | 0 | 0 | 10715 | -1322 | 9393.8408 | -0.84082 | 0 | Project financially completed balance returned to ExCom 63 ($6,805 plus $885 PSC returned at ExCom 53) |  |  | 2005-07-01 | Non Investment
FIN | UNEP | National ODS phase-out plan: training programme for custom officers (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 | 0 | 0 | 2730 | 0 | 2730 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National ODS phase-out plan (fifth and sixth tranches) | Multi-Year | ASP | BGD | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-12-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 | 0 | 3445 | 0 | 3445 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 2007-12-01 | Non Investment
FIN | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-04-01 | 2009-04-01 | 39500 | 0 | 39500 | 39500 | 100% | 0 | 0 | 0 | 5135 | 0 | 5135 | 0 | 0 | Project financially completed. |  |  | 2007-12-01 | Non Investment
FIN | UNEP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TRA | 32 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 177175 | 0 | 177175 | 177175 | 100% | 0 | 0 | 0 | 23033 | 0 | 23033 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-03-01 | 2011-07-01 | 87000 | 0 | 87000 | 87000 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 133000 | 0 | 133000 | 133000 | 100% | 0 | 0 | 0 | 17290 | 0 | 17290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National compliance action plan: halon bank management | Individual | ASP | SRL | PHA | 43 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-06-01 | 2009-12-01 |  | 2009-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 22,003 plus $ 2,860 PSC returned to ExCom 50$ 16,501 plus $ 2,145 PSC returned to ExCom 54$ 33,504 plus $ 4,356 PSC returned to ExCom 59) |  |  | 2007-12-01 | Non Investment
FIN | UNEP | National compliance action plan: enhancement of national capacity to monitor trade and prevent illegal trade of ODS | Individual | ASP | SRL | PHA | 43 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2009-12-01 |  | 2008-12-01 | 2009-12-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 | 0 | 17550 | 0 | 17550 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National compliance action plan: extension training of the established refrigeration technicians | Individual | ASP | SRL | PHA | 43 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 174600 | 0 | 174600 | 174600 | 100% | 0 | 0 | 0 | 22698 | 0 | 22698 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNIDO | National ODS Phase out plan (sixth tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 19 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-05-01 | 2012-12-01 | 22322 | 0 | 22322 | 21883.81 | 98.04% | 438.19 | 0 | 1 | 1674 | 0 | 1641 | 33 | 0 | Project completed in May 2012. Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: programme management and auditing | Multi-Year | EUR | ALB | PHA | 39 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2005-04-01 | 2009-12-01 |  | 2007-12-01 | 2008-07-01 | 16068 | 0 | 16068 | 16068 | 100% | 0 | 0 |  | 1205 | 0 | 1205 | 0 | 0 | FIN |  |  | 2009-12-01 | NON-INV
FIN | UNIDO | National ozone depleting substances phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | EUR | ALB | PHA | 39 | TAS | 08 | A | I | MBR | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2005-09-01 | 20000 | -319 | 19681 | 19681.27 | 100% | -0.27 | 0 |  | 1500 | -26 | 1474 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ODS phase out plan (fourth and fifth tranches) | Multi-Year | EUR | ALB | PHA | 54 | INV | 15 | A | I | CFC | 13 | 13 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2011-01-01 | 2012-05-01 | 64644 | -17 | 64627 | 64627.39 | 100% | -0.39 | 0 |  | 4848 | -1 | 4847 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | EUR | ALB | PHA | 39 | INV | 10 | A | I | CTC | 2.3 | 2.3 |  |  | 2003-04-01 | 2005-09-01 | 2005-04-01 |  | 2005-12-01 | 2007-09-01 | 45000 | -192 | 44808 | 44807.85 | 100% | 0.15 | 0 |  | 3375 | -14 | 3361 | 0 | 0 | FIN
FIN | UNIDO | National ODS phase out plan (3rd tranche) | Multi-Year | EUR | ALB | PHA | 50 | INV | 14 | A | I | CFC | 21 | 21 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 72322 | 0 | 72322 | 72321.85 | 100% | 0.15 | 0 |  | 5424 | 0 | 5424 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | Multi-Year | EUR | ALB | PHA | 39 | TAS | 05 | A | I | CFC | 6.8 | 6.8 |  |  | 2003-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-12-01 | 2008-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | EUR | ALB | PHA | 46 | INV | 11 | A | I | CFC | 25 | 25 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-04-01 | 2010-12-01 | 172322 | 0 | 172322 | 172322.01 | 100% | -0.01 | 0 |  | 12924 | 0 | 12924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | ALG | PHA | 53 | INV | 67 | A | I | CFC TCA | 130.5 | 130.5 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2010-04-01 | 2012-07-01 | 723500 | 0 | 723500 | 723500.02 | 100% | -0.02 | 0 |  | 54263 | 0 | 54263 | 0 | 0 | Financial completion in Jul 2012. |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan (first trance) | Multi-Year | EUR | BHE | PHA | 41 | INV | 16 | A | I | CFC TCA | 0 | 27.3 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2006-12-01 | 2009-05-01 | 265300 | -1999 | 263301 | 263301.14 | 100% | -0.14 | 0 |  | 19898 | -150 | 19748 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (third tranche) | Multi-Year | AFR | CMR | PHA | 58 | INV | 31 | A | I | CFC TCA | 24 | 24 |  |  | 2009-07-01 | 2010-11-01 | 2010-07-31 |  | 2011-12-01 | 2012-12-01 | 95000 | 0 | 95000 | 93428.21 | 98.35% | 1571.79 | 0 | 1 | 7125 | 0 | 7007 | 118 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (second tranche) | Multi-Year | AFR | CMR | PHA | 54 | INV | 29 | A | I | CFC CTC | 13.9 | 13.9 |  |  | 2008-04-01 | 2009-02-01 | 2009-03-31 |  | 2009-12-01 | 2010-12-01 | 105000 | -1 | 104999 | 104999.08 | 100% | -0.08 | 0 |  | 7875 | 0 | 7875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (first tranche) | Multi-Year | AFR | CMR | PHA | 50 | INV | 26 | A | I | CFC TCA | 12.7 | 12.7 |  |  | 2006-11-01 | 2007-01-01 | 2008-07-01 |  | 2008-12-01 | 2011-12-01 | 600000 | -486 | 599514 | 599514.01 | 100% | -0.01 | 0 |  | 45000 | -36 | 44964 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | INV | 19 | A | I | CFC CTC | 2.4 | 2.4 |  |  | 2008-11-01 | 2009-02-01 | 2009-11-30 |  | 2009-11-01 | 2010-12-01 | 47000 | -2474 | 44526 | 44526.18 | 100% | -0.18 | 0 |  | 4230 | -223 | 4007 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | INV | 16 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-01 |  | 2008-11-01 | 2009-05-01 | 78000 | -13 | 77987 | 77986.83 | 100% | 0.17 | 0 |  | 7020 | -1 | 7019 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (3rd tranche) | Multi-Year | AFR | NIR | PHA | 49 | INV | 115 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 425000 | 0 | 425000 | 425000.01 | 100% | -0.01 | 0 |  | 31875 | 0 | 31875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (third tranche) | Multi-Year | AFR | SUD | PHA | 53 | INV | 20 | A | I | CFC | 65 | 65 |  |  | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-12-01 | 2012-12-01 | 220000 | 0 | 220000 | 219701.7 | 99.86% | 298.3 | 0 | 1 | 16500 | 0 | 16478 | 22 | 0 | Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (second tranche) | Multi-Year | AFR | SUD | PHA | 50 | INV | 19 | A | I | CFC | 70 | 70 |  |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2007-12-01 | 2009-05-01 | 220000 | -88 | 219912 | 219912.27 | 100% | -0.27 | 0 |  | 16500 | -7 | 16493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (first tranche) | Multi-Year | AFR | SUD | PHA | 44 | INV | 18 | A | I | CFC CTC | 17.4 | 17.4 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2010-12-01 | 499480 | -105 | 499375 | 499375.19 | 100% | -0.19 | 0 |  | 37461 | -8 | 37453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for an ODS phase-out management plan | Individual | AFR | ALG | PHA | 51 | PRP | 66 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2007-11-01 | 2007-12-01 | 15000 | -882 | 14118 | 14118.22 | 100% | -0.22 | 0 |  | 1125 | -66 | 1059 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ODS phase out plan: commercial manufacturing and servicing and transport refrigeration | One-off Phase Out | ASP | JOR | PHA | 38 | INV | 78 | A | I | CFC | 41 | 41 |  |  | 2002-11-01 | 2003-06-01 | 2009-12-01 |  | 2006-12-01 | 2007-12-01 | 410000 | -2466 | 407534 | 407534.13 | 100% | -0.13 | 0 |  | 53300 | -321 | 52979 | 0 | 0 | FIN |  |  |  | INV
ONG | Canada | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | TAS | 32 | A | I | CFC, CTC | 0 | 0 | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 | 2013-07-01 |  |  | 88000 | -5000 | 83000 | 83000 | 100% | 0 |  | 0 | 11440 | -650 | 10790 | 0 |  | Activities undertaken up to March 2012 consists of a CTC information workshop (including printing and distribution of report on alternatives to CTC for laboratories); 62 inspections of servicing workshops; modifications to ODS regulations and printing regulatory text; printing of 300 copies of customs training manual; various public awareness activities, and project management. Since then, Bolivia advised that it still held about US $7,000 in funds advanced from Canada and requested approval to use for project management and awareness-raising activities. Canada asked fo additional justification for activities, but has not heard back from Bolivia since November 2012. Canada is continuing to attempt to communicate with NOU. Meanwhile, ExCom 68 approved transfer of remaining funds not transferred from Canada (US $5,000) to UNDP for HCFC activities under UNDP's final tranche of the TPMP. | No additional information up to April 29 2013. | 2009 |  | Investment
ONG | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2012-03-01 | 2013-03-01 |  |  | 505000 | 0 | 505000 | 822 | 0.1628% | 504178 | 2472 | 504178 | 65650 | 0 | 106.86 | 65543.14 | 321.36 | 2nd tranche activities are designed as continuation of the 1st tranche activities, respective resources are incorporated in the revised NPP work-plan. Contract for the 2nd tranche was pending till disbursing at least 70% of the 1st tranche resources | Revised contract will be established by May 2013 incorporating 2nd tranche resources in the agreement |  |  | Non Investment
ONG | UNEP | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2012-07-01 | 2013-07-01 |  |  | 1136000 | 0 | 1136000 | 586137 | 51.6% | 549863 | 9407.5016 | 549863 | 147680 | 0 | 76197.81 | 71482.19 | 1222.9752 | Train the trainers workshop on good practices and R&R conducted in Erbil, Iraq during May 2012 where 45 master trainers received comprehensive training. Training equipment distributed to 10 training institutes * Coordination meeting, organized in Bahrain Oct-12, for PMU and orientation meeting for Finance Officials, from Ministry of Environment, on proper financial reporting according to UN requirements * Pending payments under the 1st tranche contract released after receiving proper financial and progress reports resulting in releasing 70% of the total fund under the 1st tranche contract | PMU concluded agreement with Ministry of Higher Education to train 300 technicians in Iraq over a period of 2 years i.e. 2013-2014 which is total targeted under NPP project (1st and 2nd tranches). PMU, NOU and UNEP revised the work-plan for the 2013-2014 in line with delays encountered due to administrative and logistical difficulties on ground to ensure completion of all activities by end of 2014 * Revised contract will be established by May 2013 incorporating 2nd tranche resources in the agreement |  |  | Non Investment
ONG | UNEP | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 |  | 2011-04-01 | 2013-04-01 |  |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 140000 | 18200 | 0 | 0 | 18200 | 0 | All remaining activities under NPP of Yemen are incorporated in the HPMP approved Dec-12 which will start in 2013 UNEP still follow-up with country to receive final financial statements to allow closing the project. | All remaining activities under NPP of Yemen are incorporated in the HPMP approved Dec-12 which will start in 2013 |  |  | Non Investment
ONG | UNEP | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2010-12-01 | 2013-12-01 |  |  | 315000 | 0 | 315000 | 227600 | 72.25% | 87400 | 0 | 87400 | 40950 | 0 | 29588 | 11362 | 0 | All remaining activities under NPP of Yemen are incorporated in the HPMP approved Dec-12 which will start in 2013 | Due to recent political development and subsequent changes of Minister of Environment & Water, as well as the Chairman of Environment Protection Authority (EPA); UNEP is waiting for clear instructions of new management to draft and process new ISP agreement. |  |  | Non Investment
ONG | UNIDO | National phase-out plan (second tranche) | Multi-Year | AFR | ALG | PHA | 58 | INV | 71 | A | I | CFC CTC TCA | 154 | 154 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 | 2013-11-01 |  |  | 198000 | 0 | 198000 | 99943.63 | 50.48% | 98056.37 | 1124.01 | 50000 | 14850 | 0 | 7496 | 7354 | 84.3007 | Due to lack of support from NOU, no real progress was made in 2012 in this project, despite regular follow-up by UNIDO HQ as well as UNIDO's office in Algiers. There were extensive preparations from UNIDO to organize the HPMP launching meeting in October 2012. However, the meeting had to be cancelled, since no confirmation was received from the government. | In beginning of 2013 a new Environment and Sustainable Development Director has been appointed by the Government, to whom UNIDO managed to establish contact. As a result, a mission was organized in February 2013 where the whole MP portfolio was discussed. UNIDO got confirmation on the government's support in reviving the activities in an accelerated manner. As a result, it was agreed that a customs training will be organized in the first half of 2013 jointly with UNEP, being in charge of the institutional strengthening project. It is expected to be held in June 2013. Furthermore, bidding documents were prepared for the purchase of 10 refrigerant identifiers. Bidding was closed in March and the contract was issued in April 2013. |  |  | INV
ONG | UNIDO | National ODS phase-out plan (third tranche) | Multi-Year | EUR | BHE | PHA | 52 | INV | 22 | A | I | CFC | 121.1 | 121 |  |  | 2007-07-01 | 2008-12-01 | 2008-07-31 | 2013-12-01 |  |  | 303000 | 0 | 303000 | 67438.28 | 22.26% | 235561.72 | 55338.35 | 140000 | 22725 | 0 | 5058 | 17667 | 4150 | TOR on the local bidding for selection of R&R centers prepared. Following the established procedures the NOU finalized the public call for submission of proposals. | Selection of R&R centers. International bidding for R&R equipment. Evaluation of proposals and placement of the purchase order. Delivery of R&R equipment and start of R&R operation. The project is expected to be completed in 2013. Reason for the delay: The selection of the beneficiary companies by the NOU took longer than expected. |  |  | INV
ONG | UNIDO | National ODS Phase-out Plan: second tranche | Multi-Year | EUR | BHE | PHA | 44 | INV | 21 | A | I | CFC TCA | 0 | 31.1 |  |  | 2004-12-01 | 2005-12-01 | 2005-12-01 | 2013-06-01 |  |  | 295860 | 0 | 295860 | 287735.57 | 97.25% | 8124.43 | 7193.46 | 7000 | 22190 | 0 | 21580 | 610 | 540 | Training equipment delivered, training workshop for service technicians implemented. TOR on the local bidding for selection of R&R centers prepared. Almost all the funds were obligated at the end of 2012, which is expected to be disbursed in 2013. Estimated disbursement has been amended accordingly. | Uncommitted project balance will be used for the procurement of R&R equipment. The project is expected to be completed in 2013. Reason for the delay: The selection of the beneficiary companies by the NOU took longer than expected. |  |  | INV
ONG | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | INV | 15 | A | I |  | 0 | 0 |  |  | 2011-04-01 |  | 2012-03-31 | 2013-12-01 |  |  | 303000 | 0 | 303000 | 0 | 0% | 303000 | 0 | 50000 | 22725 | 0 | 0 | 22725 | 0 | The planned training was conducted in Erbil during summer 2012. Additional equipment (3 x reclaim centers) has been tendered and evaluated. While the evaluation was finished in 2012, contract could only be issued in 2013. The main reason for the zero disbursement is that the entire balance of the project is allocated for the above mentioned contract. | Plans for 2013: '1. Delivery of Equipment. 2. Installation and testing. The project is expected to be completed in 2013. Reason for the delay: The customs clearance has taken longer than expected. Since most of the committments are in 2013, not all funds can be disbursed during 2013. After project completion, usually it takes several months until all obligations can be cleared. Expenditures will be made for the contracting of the equipment for the reclaim centers. |  |  | INV
ONG | UNIDO | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | INV | 09 | A | I | CFC CTC | 1257.9 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2012-07-31 | 2013-12-01 |  |  | 4353530 | 0 | 4353530 | 2573380.14 | 59.11% | 1780149.86 | 1419897.86 | 500000 | 326515 | 0 | 193004 | 133511 | 106492.3395 | The planned training was conducted in Erbil during summer 2012. Additional equipment (3 x reclaim centers) has been tendered and evaluated. | Plans for 2013: Custom clearance for all UNIDO equipment and installation, testing and commissioning. The project is expected to be completed in 2013. The remaining balance of the project is connected to the tender of the reclaim and additional tool kits. Contract will be established within a month and funds will be commited. Reason for the delay: The customs clearance has taken longer than expected. UNIDO has tried every approch, finally we seem to have a chance to get matters through with the Ministry of Finance. In late April, UNIDO managed to obtain custom clearance for one shipment. For the other three shipments, we are working heavily with the Iraqi Ministries to obtain further custom clearance. |  |  | INV
ONG | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | AFR | TUN | PHA | 68 | INV | 54 | A | I | CFC | 172.5 | 0 |  |  | 2012-12-01 |  | 2013-12-31 | 2013-12-01 |  |  | 705518 | 0 | 705518 | 0 | 0% | 705518 | 0 | 100000 | 52914 | 0 | 0 | 52914 | 0 | The project was transferred from the World Bank to UNIDO at the 68th Meeting of the Executive Committee in 2012. | Agreement on plan of activities, drafting of technical specifications for the purchase of equipment and international bidding process will be carried out in 2013. The scope of activities for 2013 was discussed by the country and UNIDO during a meeting in Tunis (26 February - 1 March). Due to the on-going preparation of the HPMP document for the country, there is a possibility of integrating some of the activities under the NPP in the HPMP implementation. |  |  | INV
ONG | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | INV | 36 | A | I |  | 268.7 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 | 2014-06-01 |  |  | 233000 | 0 | 233000 | 120790.22 | 51.84% | 112209.78 | 27107.38 | 1000 | 17475 | 0 | 9059 | 8416 | 2033 | No additional equipment purchases have been done within tranche 2 of the Yemen TPMP. It has been agreed that any remaining funds will be utilized in the HPMP; submitted for the 68th ExCom. | The HPMP was approved at the 68th Meeting of the Executive Committee. In connection with the approved HPMP, the remaining balances of the NPP will be utilized for HPMP activities as specified in the HPMP. As both projects are interconnected the project has to remain open.
ONG | UNIDO | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | INV | 28 | A | I | CFC | 339.4 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-12-31 | 2014-06-01 |  |  | 1137500 | 0 | 1137500 | 977952.61 | 85.97% | 159547.39 | 18871.04 | 1000 | 85313 | 0 | 73346 | 11967 | 1415 | Equipment for the PU manufacturer (10 companies) has been procured and it arrived in Yemen in 2010. Due to the political unrest and travel restrictions, equipment couldn't be installed and commissioned. UNIDO is currently exploring an option to have engineers from Yemen trained in Italy at the equipment supplier with the aim that these engineers can undertake installation within Yemen. | Installation and commissioning of equipment is planned for 2013. Reason for the delay: the security situation in the country. (Traveling in and out of the country is not allowed.) UNIDO will do its utmost to complete this project in 2013, but due to the security situation in the country, traveling in and out of the country is currently not allowed and for this reason we do not expect completion before June 2014. |  |  | INV
TRF | France | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 27 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-06-01 | 200000 | -119681 | 80319 | 80319 | 100% | 0 |  | 0 | 26000 | -15559 | 10441 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
TRF | Germany | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 25 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-04-01 | 120000 | -76547 | 43453 | 43453 | 100% | 0 | 0 | 0 | 15600 | -9951 | 5649 | 0 | 0 | Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emis
COM | Germany | Extension of the institutional strengthening project (phase II) | Individual | AFR | ANG | SEV | 50 | INS | 05 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2009-01-01 |  | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 | 0 | 17472 | 0 | 17472 | 0 | 0 | NOU moved into the building of the Ministry (Urbanism & Environment). NOU collected and reported data for 2006, preparations for reporting of ODS data for 2007 has started. - After General elections in Angola restructuring of Government took place. Angolan NOU is now part of newly created Ministry of Environment. According to NOU ODS data for 2007 and 2008 have been reported to Ozone Secretariat and MFsecretariat. - All approved funds have been spent, with final payment done in January 2009. All project acitvities were completed in December 2008.
COM | Germany | Extension of the institutional strengthening project (phase IV) | Individual | ASP | PNG | SEV | 54 | INS | 09 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | The ISP has been completed and the next phase is now part of the exisiting HPMP
COM | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | THA | SEV | 58 | INS | 153 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 |  | 260001 | 0 | 260001 | 219954.21 | 84.6% | 40046.79 | 40046.79 | 40046.79 | 19500 | 0 | 16496.5 | 3003.5 | 3003.5 | Thru effective enforcement of control measures and quota system, Thailand has met and sustained MP phaseout obligations of controlled substances under Annex A and Annex B, Groups I and II. Public awareness activities conducted including circulation of awareness materials and annual celebrations of ozone day. NOU worked closely with WB and key stakeholders to develop the Thailand HPMP. A major milestone is the agreement reached with chemical suppliers and HCFC consuming industries including foam and AC sectors on adoption of HCFC import quotas and allocations for chemical suppliers and major industries. NOU also participated in MP-related meetings and coordinated with UNEP to facilitate the 22nd MOP in 2010 and 32nd OEWG meeting. | Balance of funds will be disbursed against SOEs in the first part of 2013. |  |  | Non-INV
COM | UNDP | Extension for institutional strengthening project (phase VI) | Individual | LAC | ARG | SEV | 59 | INS | 162 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 |  | 155784 | 155784 | 311568 | 311020.15 | 99.82% | 547.85 | 0 | 438.28 | 11684 | 11684 | 23326.9105 | 41.0895 | 0 | Completed in 2012. Followed up on the implementation of existing MP projects in Argentina. There are many public awareness activities ongoing in Argentina, including the celebration of the Ozone day. | Completed in 2012. | 2009 |  | Non-Investment
COM | UNDP | Renewal of the institutional strengthening under the Montreal Protocol (Phase II) | Individual | LAC | ARG | SEV | 29 | INS | 98 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2003-05-01 |  | 239700 | 0 | 239700 | 239700 | 100% | 0 | 0 | 0 | 31161 | 0 | 31161 | 0 | 0 | Completed in 2003. |  | 1999 |  | Non-Investment
COM | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | BRA | SEV | 24 | INS | 100 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 2000-04-01 |  | 2000-11-01 |  | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2000. |  | 1998 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | LAC | CHI | SEV | 57 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-03-01 |  | 2011-09-01 |  | 186550 | 0 | 186550 | 183456.53 | 98.34% | 3093.47 | 0 | 2474.776 | 13991 | 0 | 13758.9939 | 232.0061 | 0 | Completed in 2011. The NOU coordinated the finalization of several activities related to achieve and maintain the total phase out of CFCs. These activities include training in GPR of more than 2,500 technicians, 99 equipment conversions, preparation of a norm in good practices in servicing, delivery of 13 equipment for spray foam manufacturing, completion of the solvents sector project, identification of the halons users for the halon bank, and the preparation of the HFC phase out plan. | NOU activily supporting the introduction of quota system for HCFCs. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COL | SEV | 58 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-10-01 |  | 2011-12-01 |  | 160767 | 114833 | 275600 | 275587.23 | 100% | 12.77 | 0 | 10.216 | 12058 | 8612 | 20669.0422 | 0.95775 | 0 | Completed in 2011. The NOU plays an active role in the implementation of MLF funded projects in Colombia. The NOU is in the process of establishing the qoutas for HCFCs for 2013 and include supporting legislation for HCFC phase out. Final invoices pending. | The NOU plays an active role in the implementation of MLF funded projects in Colombia. The NOU is in the process of establishing the qoutas for HCFCs for 2013 and include supporting legislation for HCFC phase out. Final invoices pending. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | LAC | COS | SEV | 59 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2011-12-01 |  | 70257 | 70257 | 140514 | 140502.22 | 99.99% | 11.78 | 0 | 9.424 | 5269 | 5269 | 10537.1165 | 0.88345 | 0 | Completed in 2011. NOU in Costa Rica is actively supporting the implementation of MLF funded projects in Costa Rica. Costa Rica in compliance with all reporting and consumption obligations. HCFC legislation including qoutas have been established for 2013. Prodoc is in process of being developed. Final invoices pending. | Final invoices pending. | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | CUB | SEV | 59 | INS | 43 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 |  | 74533 | 74533 | 149066 | 149065.58 | 100% | 0.42 | 0 | 0.336 | 5590 | 5590 | 11179.9685 | 0.0315 | 0 | Completed in 2012. The NOU in Cuba plays a fundamental role in the implementation of the projects funded by the MLF. Cuba has established the import quotas for HCFCS and related legislation has been passed. | Completed in 2012. No activities in 2013. | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | GEO | SEV | 57 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-06-01 |  | 2011-12-01 |  | 60667 | 0 | 60667 | 60619.85 | 99.92% | 47.15 | 0 | 37.72 | 4550 | 0 | 4546.4638 | 3.5362 | 0 | Completed in 2011. Data on consumption of ODS collected and verified for 2010, NOU submitted an annual report on Country Programme progress to the MLF and an annual report on Data Consumption for 2010 to the Ozone Secretariat. Series of workshops organized on ODS for the variety of audience, which included students, representatives of the solvent sector, libraries and mass media. A special round-table discussions for UNDP parallel projects that were intended to find cross-cutting links and potential areas of cooperation. Learning products - guidebooks for students-technicians have been elaborated and released | Completed in 2011. | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | GHA | SEV | 62 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 |  | 139100 | 0 | 139100 | 137433.99 | 98.8% | 1666.01 | 0 | 1332.808 | 10433 | 0 | 10308.0433 | 124.9567 | 0 | Completed in 2012. Some pending payments remaining. Ozone office under Ghana-EPA is operating smoothly, implementing awareness activities, responding to data-reporting obligations, coordinating and implementing ODS-waste and HPMP programmes. The 25th anniversary of the Montreal Protocol was celebrated with important awareness raising event on this occasion. The 10th Phase was approved in July 2012. | Completed in 2012. Some pending payments remaining. | 2010 |  | Non-Investment
COM | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | AFR | GHA | SEV | 32 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2003-02-01 |  | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 2003. |  | 2000 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IDS | SEV | 59 | INS | 189 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2011-12-01 |  | 2011-12-01 |  | 135623 | 135623 | 271246 | 270169.26 | 99.6% | 1076.74 | 0 | 861.392 | 10172 | 10172 | 20263.2423 | 80.7577 | 0 | Completed in 2011. Monitoring of ongoing ODS phaseout projects and HPMP preparation activities were undertaken. HPMP was submitted to and approved at 64th ExCom. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for the year 2010 was reported in timely manner. On an ongoing basis, Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. IS-VIII request was submitted to and approved at 65th ExCom. Some pending payments remaining. | The project is being financially closed by June 12, and activities will continue under IS-VIII. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | IND | SEV | 60 | INS | 436 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2012-03-01 |  | 2012-06-01 |  | 326576 | 0 | 326576 | 326576 | 100% | 0 | 0 | 0 | 24493 | 0 | 24493 | 0 | 0 | Completed in 2012. Activities remaining under this phase were completed satisfactorily. | Completed in 2012. | 2010 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IND | SEV | 47 | INS | 392 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2008-12-01 |  | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Completed in 2008. |  | 2005 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IND | SEV | 54 | INS | 416 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 |  | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Completed. During the year 2010, monitoring, awareness and enforcement activities were undertaken on an ongoing basis. In 2009, the focus was on implementation of CFC MDI phase-out, completing pending activities under CFC production sector, CTC production and consumption sectors and HPMP preparation. Licensing for ODS production and imports is being implemented effectively. Data for CY 2009 have been reported to MLFS and Ozone Secretariat during the year. Awareness activities and other regulatory initiatives including border dialogues were implemented during the year 2010. In MOP 22, Government of India declared that they would not be requiring CFCs for MDI manufacturing through EUN process from 2011. |  | 2008 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | LEB | SEV | 56 | INS | 68 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-03-01 |  | 2011-06-01 |  | 155090 | 0 | 155090 | 155089.73 | 100% | 0.27 | 0 | 0.216 | 11632 | 0 | 11631.9797 | 0.02025 | 0 | Completed in 2011. The project is being financially closed in 2012. | Completed in 2011. The project is being financially closed in 2012. | 2008 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | MAL | SEV | 58 | INS | 165 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-11-01 |  | 2011-12-01 |  | 139750 | 139750 | 279500 | 262924.26 | 94.07% | 16575.74 | 0 | 13260.592 | 10481 | 10481 | 19718.8492 | 1243.1508 | 0 | Completed in 2011. Monitoring of ongoing ODS phaseout projects and HPMP preparation activities were undertaken. HPMP was submitted to and approved at 65th ExCom. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for the year 2010 was reported in timely manner. On an ongoing basis, Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. IS-IX request was submitted to and approved at 64th ExCom. Some pending payments remaining. | The project is being financially closed in 2012. | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | AFR | NIR | SEV | 54 | INS | 118 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2010-12-01 |  | 260000 | 0 | 260000 | 256233.46 | 98.55% | 3766.54 | 0 | 3013.232 | 19500 | 0 | 19217.5095 | 282.4905 | 0 | Completed. Ozone Office fully operational and implementing activities according to action plan. New extension approved at 62nd ExCom meeting. |  | 2008 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | PAK | SEV | 57 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2011-03-01 |  | 2011-06-01 |  | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 16835 | 0 | 16835 | 0 | 0 | Completed in 2011. Financial closure expected in 2012. | Completed in 2011. Financial closure expected in 2012. | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | SRL | SEV | 61 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-12-01 |  | 2012-12-01 |  | 134056 | 0 | 134056 | 133599.99 | 99.66% | 456.01 | 0 | 364.808 | 10054 | 0 | 10019.7999 | 34.2001 | 0 | Completed in 2012. During the year 2012, the focus was on implementation of HPMP project components and completing pending activities under NCAP. During the year, technician training was undertaken for stopping use of HCFC-141b in foam and good RAC servicing practices. The Government also undertook elaborate public awareness activiities as a part of 20th Anniversary celebrations and such activities are ongoing. The Government has also implemented quota system for HCFC-22 starting 1 January 2013. | Completed in 2012. Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | TRI | SEV | 50 | INS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2012-06-01 |  | 60000 | 0 | 60000 | 56926.89 | 94.88% | 3073.11 | 0 | 2458.488 | 4500 | 0 | 4269.5167 | 230.4832 | 0 | Completed in 2012. Pending invoices are being evaluated in order to proceed to the financial closure. | Completed in 2012. No activities in 2013. | 2006 |  | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | URU | SEV | 56 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2010-10-01 |  | 2011-12-01 |  | 150800 | 0 | 150800 | 150473.08 | 99.78% | 326.92 | 0 | 261.536 | 11310 | 0 | 11285.481 | 24.519 | 0 | Completed in 2011. In 2011, the NOU worked on the HPMP preparation collecting information on HCFC consumption all the user sectors. Numerous meetings with stakeholders were organized by the NOU in order to better understand the HCFC consumption situation as part of the HPMP design. The HPMP was finally submitted to ExCom 65 and approved. The NOU plays an important role in the implementation of MLF funded projects in Uruguay. Final invoices pending. | NOU is preparing for the first control target for HCFCs in 2013. This includes introduction of qouta system and initiating implementation of HPMP. Final invoices pending. | 2008 |  | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (phase IX) | Individual | LAC | VEN | SEV | 56 | INS | 113 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2010-12-01 |  | 2010-12-01 |  | 285480 | -2637.08 | 282842.92 | 282842.92 | 100% | 0 | 0 | 0 | 21411 | -197.78 | 21213.22 | 0 | 0 | Completed. The NOU completed the training in GPR of 5,500 technicians (estimated for the end of 2010), an agreement with institutions to provide private training, the preparation of the code in good practices and development of a national norm for certification, the creation of CFC bank for future destruction, and the exploration of the introduction of HCs (imports and local production) as a final alternative to ODSs. The NOU also completed the preparation of the HCFC phase out plan and worked on the regular reporting and awareness activities including a campaign through different media. |  | 2008 |  | Non-Investment
COM | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | EUR | ALB | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-06-01 |  | 2012-12-01 |  | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Extension of the licensing system to include HCFCs containing mixtures was done. Inclusion into the iPIC the list of HCFC licensing importers and to continue cooperation under the information sharing (iPIC). The Draft Guidelines for Good Practices in the refrigeration sector was developed. | Project activities are completed |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | ANT | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. Annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). Final progress and financial report endorsed by Permanent Secretary. CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase IV. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. | Project completed. |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | BAH | SEV | 60 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-12-01 |  | 2012-12-01 |  | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Due to the unrest and instability over 2011, Bahrain could not provide their required reports for renewal ISP on time and therefore implementation was delayed up to Nov-2012. After receipt of final expenditure, audit and interim-terminal reports, the renewal was submitted to 68 ExCom. Final payment disbursed accordingly. | Project completed |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | AFR | BEN | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-12-01 |  | 2011-12-01 |  | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | BKF | SEV | 62 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 |  | 72410 | 0 | 72410 | 71110 | 98.2% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | Project was completed and country prepared and sent IS request for renewal. |  |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | BOL | SEV | 59 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-12-01 |  | 2012-06-01 |  | 39434 | 39434 | 78868 | 78868 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in June 2012. New Coordinator of the NOU was hired in April 2012, and received training from CAP Team. 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOU submitted Article 7 data report and Country Programme Report. NOU did follow up on Beijing Amendment ratification. NOU was in charge of the HPMP implementation. ISP Phase 7 renewal prepared and submitted to the 66 ExCom for approval. All funds released. Audited final financial report submitted to UNEP. | Project completed. |  |  | Non Investment
COM | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | BRU | SEV | 43 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2011-06-01 | 2006-07-01 |  | 2012-12-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. The NOU is back on track with its operation and implementation of both IS and HPMP projects. This IS project phase is being finalized to be completed. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | CKI | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOO resigned late of 2012 but in November 2012, new ODS officer was appointed. The NOU is operational and full in staff. Good awareness raising activities were organized including newspaper articles, airing of ozone documentary, television news interview of NOO about ozone day. | Draft 2012 CP and article 7 data prepared. Continuation of training of New NOO appointed in last quarter of 2012. |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | CMR | SEV | 59 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-12-01 |  | 2012-12-01 |  | 69766 | 69766 | 139532 | 139532 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | DOM | SEV | 62 | INS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-12-01 |  | 2012-12-01 |  | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Change of NOO in February of 2012. CAP team provided assistance in this transition. 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. Second and third disbursements released in April and October 2012. NOO attended Network Meetings held in Chile (June 2012) and Panama (October 2012). NOU organized the International Ozone Day celebration at national level. NOU was in charge of the HPMP implementation. With CAP Team support, the NOU submitted the ISP Phase 7 to the 68 ExCom for approval. |  |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (year 2 of phase V) | Individual | LAC | ELS | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 |  | 30000 | 0 | 30000 | 9661 | 32.2% | 20339 | 0 | 20339 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | FIJ | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-11-01 |  | 2012-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A7 and country report was submitted to MLF, UNEP and OS. The new ODS Laws and Refrigerant Management Laws has been formulated on July 2012 and endorsed on December 2012. Fiji participated In the OEWG/MOP/COP in 2012. | The project is completed. |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | FSM | SEV | 61 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-12-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | The permits issued for importation and export from 1 January 2013. |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAM | SEV | 61 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-10-01 | 2012-06-01 |  | 2012-10-01 |  | 60000 | 0 | 60000 | 54661 | 91.1% | 5339 | 5339 | 5339 | 0 | 0 | 0 | 0 | 0 | The NOU conducted training for twenty refrigeration technicians’ on good practices, forty Clearing agents, Customs and other security officers were trained on identification of refrigerants, illegal trade in ODS among other things. The Noun has introduced an incentive programme for end-users in the fish processing sector to convert their systems running on HCFCs (R22), into more Ozone friendly and energy efficient refrigerants. The NOU conducted ODS monitoring activities and confiscated 13 refrigerant cylinders with impure refrigerants. CP report and 2011 A7 data was collected, compiled and submitted. The NOU celebrated the Ozone day and conducted quiz competitions. The NOU attended all the Montreal Protocol meetings and network meetings. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | GUY | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2012-12-01 |  | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. New NOO hired in 2012 and trained by CAP through an official mission. 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. Second disbursement released. NOO attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase V. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU was in charge of HPMP implementation. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | HON | SEV | 57 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. Annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. All funds released. NOO and Assistant attended Network Meetings held in Chile (June 2012) and Panama (October 2012). CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase 7. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU was in charge of HPMP and MB Phase-out implementation. |  |  |  | Non Investment
COM | UNEP | Institutional strengthening (phase I) | Individual | ASP | IRQ | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2011-03-01 |  | 2012-12-01 |  | 240000 | 0 | 240000 | 238641 | 99.43% | 1359 | 0 | 1359 | 0 | 0 | 0 | 0 | 0 | Project completed. Being the first ISP for Iraq and given their internal complications regarding financial processing between the Ministry of Environment & Ministry of Finance (including receipt of payments & disbursements), there was a delay in submission of final required reporting and subsequent final payment by UNEP. Therefore ISP renewal is submitted for ExCom 69. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | IVC | SEV | 62 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 |  | 106340 | 0 | 106340 | 104602 | 98.37% | 1738 | 1738 | 1738 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KUW | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-12-01 |  | 57048 | 48272 | 105320 | 105320 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Overall delay was faced due to change in internal structure of Environment Public Authority of Kuwait (change of senior management, including ODS Officer). However after receipt of final ISP reports as required, the new cycle ISP renewal was submitted and approved at 68 ExCom | UNEP visited the country and concluded a revised work-plan with NOU based on additional input received locally from respective authorities. Draft Country contract prepared and is under review for signature |  |  | Non Investment
COM | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | LAO | SEV | 61 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | The project is completed. |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | LES | SEV | 62 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. NOU collected 2012 ODS data, celebrated Ozone Day and conducted several awareness activities. | NOU started collection of 2012 ODS data, trained 20 customs officers and 30 refrigeration experts |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LES | SEV | 53 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-05-01 | 2009-11-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 59081 | 98.47% | 919 | 0 | 919 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012 |  |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAG | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-07-01 |  | 32879 | 27821 | 60700 | 60700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final payment was made in Feb 2012. The country prepared and submitted IS renewal request. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | MDV | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-11-01 |  | 2012-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU is operating smoothly and the staff is full. The Government is focusing on the HPMP implementation and numerous activities were completed as indicated in the report submitted to the 69th ExCom. | The project is completed. |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | MLI | SEV | 63 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  | 2012-12-01 |  | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. The NOU conducted several awareness raising activities and celebrated the ozone day | Documents were sent for final payment |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | MLW | SEV | 59 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 |  | 36147 | 30586 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOU commenced 2011 data collection exercise and conducted inspection visits to some shops dealing with ODS and ODS equipment | project was completed |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MOL | SEV | 61 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 |  | 2012-12-01 |  | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. The licensing system has been updated and HCFCs are controlled by the national legislation. A set of legal documentation for the Certification System of the service refrigeration technicians, harmonized with F-gas EU Regulation was developed. There was elaborated and opened a web site of the Association of Refrigeration Technicians. There were disseminated flyers with information about the Association of Refrigeration Technicians. The books "Salvaţi Stratul de Ozon" (Save the Ozone layer) and “Guide for teacher – Protection of the Ozone Layer” were printed and distributed. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NAU | SEV | 60 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-11-01 | 2011-12-01 |  | 2012-01-01 |  | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. Completed revision of the ODS regulations and submission to Parliament. NOO attended to SA and SEAP network meeting in October of 2012. | Draft 2012 CP and article 7 data prepared. Continuation of training of New NOO appointed in last quarter of 2012. |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | NEP | SEV | 61 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. NOO attended to SA and SEAP network meeting in October of 2012. The focus is the HPMP implementation wherein numerous activities were implemented in 2012. | The project completed in Nov2012. |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | NIC | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-12-01 |  | 2012-03-01 |  | 30000 | 30000 | 60000 | 48000 | 80% | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | Documents for renewal of ISP were prepared and submitted to the 66 ExCom meeting. | Project completed in March 2013 |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | NIC | SEV | 49 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-06-01 |  | 2009-09-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2011-12-01 |  | 60000 | 0 | 60000 | 20733 | 34.55% | 39267 | 0 | 39267 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | STL | SEV | 62 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-11-01 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP team. NOO attended the Caribbean Network Meetings held in Dominica and Panama (March and October 2012). All funds released. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. Final progress and financial reports were drafted. CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase VIII. NOO was in charge of HPMP implementation. | NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. NOO Assistant attended the sub-regional network meeting held in SKN on March 2013. |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | SUR | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2011-11-01 |  | 2012-12-01 |  | 39722 | 33611 | 73333 | 73333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2012. Annual operating plan which includes newly approved HPMP and the procurement plan were prepared by the NOU with the guidance of the CAP team. NOO attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level through an expo on RAC technology with private companies from the Caribbean. NOU was in charge of the TPMP and HPMP implementation. Documents for renewal of ISP were prepared and submitted to the 67 ExCom meeting. All funds released. | Audited final progress and financial reports are expected by next quarter. |  |  | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SWA | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2011-12-01 |  | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | TKM | SEV | 61 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-09-01 |  | 2012-09-01 |  | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project activities are completed | Project activities are completed |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | TOG | SEV | 62 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 |  | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final payment was sent in Oct 2012. Country prepared and submitted IS renewal request. |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | YEM | SEV | 59 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2011-11-01 |  | 2012-12-01 |  | 92083 | 77916 | 169999 | 169999 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yemen NOU, despite their political and security instability, succeeded to implement the ISP and submitted required reporting (financial, audit, terminal reports), based on which UNEP submitted renewal for new ISP cycle to 68 ExCom |  |  |  | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ZAM | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-11-01 | 2011-03-01 |  | 2012-03-01 |  | 65520 | 0 | 65520 | 24974 | 38.12% | 40546 | 40546 | 40546 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
COM | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | ARM | SEV | 62 | INS | 08 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-03-31 |  | 2012-12-01 |  | 120000 | 0 | 120000 | 118998.15 | 99.17% | 1001.85 | 219.14 | 500 | 9000 | 0 | 8925 | 75 | 16 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening: phase II | Individual | EUR | BHE | SEV | 43 | INS | 19 | N | I |  | 0 | 0 |  |  | 2004-07-01 | 2008-12-01 | 2006-07-01 |  | 2011-12-01 |  | 95333 | 0 | 95333 | 85632.95 | 89.83% | 9700.05 | 7288.02 | 9000 | 7150 | 0 | 6422 | 728 | 547 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | EGY | SEV | 61 | INS | 103 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2011-02-01 | 2012-12-31 |  | 2011-12-01 |  | 228323 | 0 | 228323 | 220000 | 96.35% | 8323 | 8323.01 | 8000 | 17124 | 0 | 16500 | 624 | 624 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase X) | Individual | LAC | MEX | SEV | 62 | INS | 152 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2012-06-01 |  | 247000 | 0 | 247000 | 145017.34 | 58.71% | 101982.66 | 11354.28 | 80000 | 18525 | 0 | 10876 | 7649 | 852 | Project completed in Jun 2012. |  |  |  | NON-INV
COM | UNIDO | Institutional strengthening project (Phase I) | Individual | EUR | MOG | SEV | 55 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-06-30 |  | 2010-12-01 |  | 60000 | 0 | 60000 | 58676.08 | 97.79% | 1323.92 | 1116.88 | 1000 | 4500 | 0 | 4401 | 99 | 84 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening: phase III | Individual | ASP | SYR | SEV | 45 | INS | 91 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2007-04-01 |  | 2009-12-01 |  | 203823 | 0 | 203823 | 199696.98 | 97.98% | 4126.02 | 3134 | 4000 | 15287 | 0 | 14977 | 310 | 235 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase IV) | Individual | EUR | TUR | SEV | 58 | INS | 93 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 |  | 195000 | 0 | 195000 | 186069.59 | 95.42% | 8930.41 | 6114.4 | 8000 | 14625 | 0 | 13955 | 670 | 458.58 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase III) | Individual | EUR | YUG | SEV | 59 | INS | 34 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2011-11-01 |  | 71121 | 60179 | 131300 | 110828.92 | 84.41% | 20471.08 | 8800.5 | 20000 | 5334 | 4513 | 8312 | 1535 | 660 | Project completed. |  |  |  | NON-INV
FIN | Australia | Additional support for the regional strategy for 11 Article 5 countries in the Pacific (PIC strategy) | Individual | ASP | ASP | SEV | 50 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2011-03-01 | 2012-05-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | completed |  | 2007
FIN | France | Institutional strengthening project proposal |  | AFR | MAU | SEV | 14 | INS | 02 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 1999-12-01 | 1999-12-01 | 38874 | -12891 | 25983 | 25983 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | Germany | Establishment of the Ozone Unit | Individual | AFR | ANG | SEV | 38 | INS | 03 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-06-01 | 71682 | 141618 | 213300 | 213300 | 100% | 0 | 0 | 0 | 9319 | 18411 | 27730 | 0 | 0 | 1st phase of Institutional Strengthening project is completed. - the infrastructure of the NOU-office in Luanda has been completed, with internet and telepone / fax connection. - Regional support groups have been created in serveral of Angolas provinces in order to assist NOU in data collection, public awareness activities, etc.- ODS data up to reporting year 2006 have been submitted to both Ozone Secretariat and Multilateral Fund Secretariat. - Angola is in compliance with phase-out schedule and data reporting obligations.
FIN | Germany | Extension of institutional strengthening project | Individual | ASP | PNG | SEV | 41 | INS | 06 | N | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-06-01 | 2005-12-01 |  | 2006-03-01 | 2006-06-01 | 39693 | 0 | 39693 | 39693 | 100% | 0 | 0 | 0 | 5160 | 0 | 5160 | 0 | 0 | ISP completed successfully.
FIN | Germany | Extension of the institutional strengthening project (phase III) | Individual | ASP | PNG | SEV | 48 | INS | 07 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-05-01 | 2008-04-01 |  | 2008-04-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | ISP completed successfully.
FIN | IBRD | Extension of the institutional strengthening project (phase VI, second year) | Individual | LAC | CHI | SEV | 45 | INS | 157 | N | I | CFC | 7.7 | 7.7 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening (phase VI, year 2) | Individual | LAC | CHI | SEV | 47 | INS | 159 | N | D | CFC | 7.7 | 7.7 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2006-12-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100% | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | Completed |  |  | 1998-10-31 | Non-INV
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | I | CFC | 15.42 | 15.42 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0 | Phase V of the IS project completed. |  |  |  | Non-INV
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 07 | INS | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 100% | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase IV, first year) | Individual | LAC | ECU | SEV | 51 | INS | 38 | N | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2009-04-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Phase IV completed. ISP transferred to UNEP. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase IV, second year) | Individual | LAC | ECU | SEV | 56 | INS | 42 | N | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-09-30 |  | 2009-09-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Ecuador has complied with all MP targets for Annex A substance phaseout and has been actively engaged in maintaining its compliance status with methyl bromide. The ISP was transferred to UNEP (starting with phase V). |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100% | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. |  |  |  | Non-INV
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 09 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | 1997-06-01 | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-02-01 | 2007-03-01 | 176800 | 0 | 176800 | 176800 | 100% | 0 | 0 |  | 13260 | 0 | 13260 | 0 | 0 | IS completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase IX) | Individual | ASP | JOR | SEV | 62 | INS | 88 | N | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | IS Phase IX completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase VIII) | Individual | ASP | JOR | SEV | 58 | INS | 84 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2011-03-01 | 2011-03-01 | 110500 | 0 | 110500 | 110500 | 100% | 0 | 0 |  | 8288 | 0 | 8288 | 0 | 0 | IS Phase VIII completed. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | PIU fully operational. Funds were fully disbursed. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | IS tranche completed and full funding dibursed. |  |  | 2000-12-01 | Non-INV
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | -20000 | 113333 | 113333 | 100% | 0 | 0 |  | 17333.29 | -2600 | 14733.29 | 0 | 0 | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening project (phase VI) | Individual | ASP | JOR | SEV | 46 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-31 | 147320 | 0 | 147320 | 147320 | 100% | 0 | 0 |  | 11049 | 0 | 11049 | 0 | 0 | IS Phase VI is completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-06-01 | 2005-07-01 |  | 2005-06-01 | 2005-06-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Phase 6 of the IS project completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | JOR | SEV | 52 | INS | 81 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-07-01 |  | 2009-09-01 | 2010-01-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | IS Phase VII is completed. |  |  |  | Non-INV
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 07 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | 1997-06-01 | Non-INV
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2005-05-01 | 90566 | 0 | 90566 | 90566 | 100% | 0 | 0 |  | 6792 | 0 | 6792 | 0 | 0 | First half of Phase IV of the IS project completed. |  |  |  | Non-INV
FIN | IBRD | Extension of the institutional strengthening project (phase IV, second year) | Individual | ASP | PHI | SEV | 45 | INS | 78 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2006-05-01 | 90567 | 0 | 90567 | 90567 | 100% | 0 | 0 |  | 6793 | 0 | 6793 | 0 | 0 | Second half of Phase IV of the IS project completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 60 | INS | 89 | N | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-12-31 |  | 2011-06-01 | 2011-11-01 | 158491 | -64471 | 94020 | 94020 | 100% | 0 | 0 |  | 11887 | -4835 | 7052 | 0 | 0 | Balance of IS VII transferred to UNEP in Nov 11 subsequent to the closing of the overall ODS Grant Agreement between the Philippines and the WB. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100% | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | Phase II completed and IS renewal approved at the 36th ExCom. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 | 2005-01-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 23547.29 | 0 | 23547.29 | 0 | 0 | Phase III completed and IS renewal approved at the 42nd ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | PHI | SEV | 48 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2008-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase V completed and IS renewal approved at the 54th ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | PHI | SEV | 54 | INS | 83 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-31 |  | 2010-06-01 | 2010-11-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase VI completed. IS renewed at the 60th ExCom. |  |  |  | Non-INV
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 09 | INS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed physically and financially. |  |  | 1999-12-01 | Non-INV
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100% | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-08-01 | 2005-08-01 | 346667 | 0 | 346667 | 346667 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Remaining budget was used for public awareness activities e.g. ozone road show, publications, etc. These PR activities were conducted to promote and ensure sustainable ODS phaseout. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening project (phase IV) | Individual | ASP | THA | SEV | 46 | INS | 145 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-09-01 | 2007-10-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Phase IV of the IS project successfully completed. IS renewed at the 52nd ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | THA | SEV | 52 | INS | 148 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-06-30 |  | 2010-11-01 | 2010-11-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Capacity of NOU and government agencies have been continuously enhanced. Phase V of the IS project successfully completed. IS renewed at the 58th ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | AFR | TUN | SEV | 61 | INS | 52 | N | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2012-06-30 |  | 2012-06-01 | 2012-10-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 | 0 | 18545 | 0 | 18545 | 0 | 0 | Phase V completed. IS project transferred to UNIDO at the 66th ExCom meeting. |  |  |  | Non-INV
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100% | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. |  |  |  | Non-INV
FIN | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | I | CFC | 20.2 | 20.2 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 242667 | 0 | 242667 | 242667 | 100% | 0 | 0 |  | 18200.03 | 0 | 18200.02 | 0.01 | 0.01 | Phase III IS completed and IS IV approved at the 48th ExCom. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase IV) | Individual | AFR | TUN | SEV | 48 | INS | 46 | N | I | CFC | 20.05 | 20.05 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2008-06-01 |  | 2008-12-01 | 2009-07-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | AFR | TUN | SEV | 55 | INS | 49 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-06-30 |  | 2011-06-01 | 2011-09-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Phase V IS completed. IS VI approved at the 61st ExCom. |  |  |  | Non-INV
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 08 | INS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | Non-INV
FIN | IBRD | Renewal of institutional strengthening | Individual | EUR | TUR | SEV | 32 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2007-12-01 | 2008-04-01 | 200000 | -3641 | 196359 | 196359.49 | 100% | -0.49 | -0.49 |  | 26000 | -473 | 25526.73 | 0.27 | 0.27 | All activities completed and project is physically and financially closed. |  |  |  | Non-INV
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 260000 | -23601 | 236399 | 236399.08 | 100% | -0.08 | -0.08 |  | 19500 | -1770 | 17729.93 | 0.07 | 0.07 | Field work and information dissemination via workshops and other meetings carried out by MARA. Training programs and other project components all completed. |  |  |  | Non-INV
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 08 | INS | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IS project extended to accommodate additional work program of ozone unit. |  |  | 1999-12-01 | Non-INV
FIN | UNDP | Extension for institutional strengthening project (phase IV) | Individual | LAC | ARG | SEV | 46 | INS | 145 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2008-05-01 | 2009-07-01 | 311567 | -521 | 311046 | 311045.65 | 100% | 0.35 | 0 | 0 | 23368 | -39.0758 | 23328.8979 | 0.026251 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | ARG | SEV | 38 | INS | 130 | N | I | No_ODP | 25.7 | 25.7 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2008-10-01 | 311610 | -197 | 311413 | 311413 | 100% | 0 | 0 | 0 | 40509.3 | -26.3 | 40483 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase V) | Individual | LAC | ARG | SEV | 53 | INS | 153 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-05-01 | 2011-12-01 | 311567 | 0 | 311567 | 311567 | 100% | 0 | 0 | 0 | 23368 | 0 | 23368 | 0 | 0 | Completed. National Ozone Unit monitoring elimination of use of CFCs in ARG.. Very strong licensing system allows country to have very reliable consumption data. Active public awareness programmes in place. Ozone Unit preparing for future challenges related to HCFCs. |  | 2007 |  | Non-Investment
FIN | UNDP | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1997-07-01 |  | 1999-12-01 | 2000-12-01 | 359500 | 0 | 359500 | 359500 | 100% | 0 | 0 | 0 | 46735 | 0 | 46735 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | BGD | SEV | 35 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-01-01 |  | 2004-12-01 | 2008-08-01 | 100000 | -2099 | 97901 | 97900.9 | 100% | 0.1 | 0 | 0 | 13000 | -273 | 12726.987 | 0.013 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase II) | Individual | ASP | BGD | SEV | 29 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2001-12-01 | 2008-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2001. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | BGD | SEV | 44 | INS | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 130000 | -1588 | 128412 | 128411.73 | 100% | 0.27 | 0 | 0 | 9750 | -119.1 | 9630.8798 | 0.02025 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | BGD | SEV | 53 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2011-12-01 | 2012-07-01 | 130000 | 0 | 130000 | 129727.19 | 99.79% | 272.81 | 0 | 0 | 9750 | 0 | 9729.5392 | 20.4608 | 0 | Financially completed in 2012. | The project is being financially closed by June 12. | 2007 |  | Non-Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | BGD | SEV | 14 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-09-01 | 1997-09-01 |  | 1999-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | LAC | BRA | SEV | 32 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2006-07-01 | 2009-07-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BRA | SEV | 43 | INS | 267 | N | I | No_ODP | 29 | 29 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2009-07-01 | 351000 | -76482 | 274518 | 274517.65 | 100% | 0.35 | 0 | 0 | 26325 | -5736.15 | 20588.8237 | 0.02625 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | LAC | BRA | SEV | 52 | INS | 279 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-06-01 |  | 2010-12-01 | 2012-04-01 | 351000 | -49671.43 | 301328.57 | 301328.57 | 100% | 0 | 0 | 0 | 26325 | -3725.36 | 22599.64 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Institutional strengthening support for the implementation of the Montreal Protocol | Individual | LAC | BRA | SEV | 10 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-03-01 | 1999-12-01 | 403100 | 0 | 403100 | 403100 | 100% | 0 | 0 | 0 | 52403 | 0 | 52403 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening (phase VII) | Individual | LAC | CHI | SEV | 51 | INS | 163 | N | I | No_ODP | 15.4 | 15.4 | 0 | 0 | 2007-03-01 | 2007-04-01 | 2009-03-01 |  | 2009-07-01 | 2011-09-01 | 186550 | -372.06 | 186177.94 | 186177.94 | 100% | 0 | 0 | 0 | 13991 | -27.9 | 13963.1 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | COL | SEV | 24 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 2000-03-01 |  | 2000-03-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2000. Financially completed in 2007. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening: Phase 3 | Individual | LAC | COL | SEV | 30 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2002-04-01 |  | 2003-05-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COL | SEV | 52 | INS | 67 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-10-01 |  | 2010-08-01 | 2011-10-01 | 275600 | -317.26 | 275282.74 | 275282.74 | 100% | 0 | 0 | 0 | 20670 | -23.79 | 20646.21 | 0 | 0 | Completed. See report on IS Colombia in COL/SEV/52/INS/73. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | COL | SEV | 45 | INS | 61 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-12-01 | 2010-10-01 | 275600 | -13.86 | 275586.14 | 275586.14 | 100% | 0 | 0 | 0 | 20670 | -1.0395 | 20668.9605 | 0 | 0 | Financially completed in 2010. |  | 2005 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening (phase 4) | Individual | LAC | COL | SEV | 38 | INS | 59 | N | I | No_ODP | 22.8 | 22.8 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 275600 | -3.79 | 275596.21 | 275596.21 | 100% | 0 | 0 | 0 | 35828 | -0.4927 | 35827.5073 | 0 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Institutional strengthening for implementation of the Montreal Protocol in Colombia | Individual | LAC | COL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1997-03-01 |  | 1998-03-01 | 1999-12-01 | 317790 | 0 | 317790 | 317790 | 100% | 0 | 0 | 0 | 41313 | 0 | 41313 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | COS | SEV | 35 | INS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2004-12-01 | 2007-06-01 | 108087 | -3863 | 104224 | 104224 | 100% | 0 | 0 | 0 | 14051.31 | -502.3057 | 13549.0043 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol (Phase III) | Individual | LAC | COS | SEV | 27 | INS | 16 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-04-01 |  | 2001-12-01 | 2005-11-01 | 108087 | -2519 | 105568 | 105568 | 100% | 0 | 0 | 0 | 14051.31 | -327.3128 | 13723.9972 | 0 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase II) | Individual | LAC | COS | SEV | 21 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1999-02-01 |  | 1999-02-01 | 2000-12-01 | 108087 | 0 | 108087 | 108087 | 100% | 0 | 0 | 0 | 14051 | 0 | 14051 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COS | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-09-01 | 2011-08-01 | 140513 | -12595.67 | 127917.33 | 127917.33 | 100% | 0 | 0 | 0 | 10538 | -944.63 | 9593.37 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COS | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2008-12-01 |  | 2008-02-01 | 2009-07-01 | 140513 | -2445 | 138068 | 138068.17 | 100% | -0.17 | 0 | 0 | 10538 | -183.3667 | 10354.646 | -0.012749 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | COS | SEV | 41 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 140513 | -776 | 139737 | 139737 | 100% | 0 | 0 | 0 | 10538 | -57.9974 | 10480.0026 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | COS | SEV | 08 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-08-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 213160 | 0 | 213160 | 213160 | 100% | 0 | 0 | 0 | 27711 | 0 | 27711 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol - Phase II | Individual | ASP | CPR | SEV | 20 | INS | 181 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 300000 | -1 | 299999 | 299999 | 100% | 0 | 0 | 0 | 39000 | -2.6193e-12 | 39000 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol (Phase III) | Individual | ASP | CPR | SEV | 26 | INS | 262 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | ASP | CPR | SEV | 32 | INS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2003-01-01 |  | 2003-06-01 | 2008-10-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2003. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | CPR | SEV | 50 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2010-10-01 | 390000 | -413.47 | 389586.53 | 389586.53 | 100% | 0 | 0 | 0 | 29250 | -31.0102 | 29218.9898 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | CPR | SEV | 44 | INS | 421 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2010-10-01 | 390000 | -129.12 | 389870.88 | 389870.88 | 100% | 0 | 0 | 0 | 29250 | -9.684 | 29240.316 | 0 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening (phase 5) | Individual | ASP | CPR | SEV | 38 | INS | 398 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2005-09-01 | 2008-10-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 50700 | 0 | 50700 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | CPR | SEV | 56 | INS | 477 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-07-01 | 390000 | 0 | 390000 | 389999.51 | 100% | 0.49 | 0 | 0 | 29250 | 0 | 29249.9633 | 0.03675 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNDP | Institutional strengthening, including establishment of the Information Clearing-house at NEPA | Individual | ASP | CPR | SEV | 06 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-04-01 | 1995-02-01 |  | 1996-12-01 | 1998-12-01 | 150000 | 299997 | 449997 | 449997 | 100% | 0 | 0 | 0 | 19500 | 39000 | 58500 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | CUB | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening under Montreal Protocol (phase III) | Individual | LAC | CUB | SEV | 34 | INS | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2003-08-01 |  | 2003-09-01 | 2004-12-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase 4) | Individual | LAC | CUB | SEV | 40 | INS | 22 | N | I | No_ODP | 12.3 | 12.3 | 0 | 0 | 2003-07-01 | 2003-10-01 | 2005-07-01 |  | 2006-12-01 | 2008-08-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | CUB | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-11-01 | 2007-12-01 |  | 2008-03-01 | 2009-07-01 | 149066 | 0 | 149066 | 149066.11 | 100% | -0.11 | 0 | 0 | 11180 | 0 | 11180.0083 | -0.00825 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | CUB | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2010-03-01 | 2011-05-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of OTOZ | Individual | LAC | CUB | SEV | 10 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-10-01 | 2000-12-01 | 172000 | -5 | 171995 | 171995 | 100% | 0 | 0 | 0 | 22360 | -1 | 22359 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 52 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-03-01 |  | 2009-12-01 | 2011-08-01 | 60667 | -39.95 | 60627.05 | 60627.05 | 100% | 0 | 0 | 0 | 4550 | -3 | 4547 | 0 | 0 | Completed in 2009. |  | 2007 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | AFR | GHA | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2011-12-01 | 107000 | -7725 | 99275 | 99275 | 100% | 0 | 0 | 0 | 13910 | -1004 | 12906 | 0 | 0 | Completed in 2000. Financially completed in 2011. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | GHA | SEV | 20 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-12-01 | 1999-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (phase 5) | Individual | AFR | GHA | SEV | 38 | INS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2009-08-01 | 139100 | -860 | 138240 | 138240 | 100% | 0 | 0 | 0 | 18083 | -112 | 17971 | 0 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GHA | SEV | 43 | INS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2006-07-01 |  | 2006-12-01 | 2008-08-01 | 139100 | -272 | 138828 | 138828 | 100% | 0 | 0 | 0 | 10433 | -20.001 | 10412.999 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | GHA | SEV | 56 | INS | 29 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-12-01 |  | 2010-12-01 | 2012-01-01 | 139100 | -116.65 | 138983.35 | 138983.35 | 100% | 0 | 0 | 0 | 10433 | -8.75 | 10424.25 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GHA | SEV | 50 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2011-09-01 | 139100 | -70.57 | 139029.43 | 139029.43 | 100% | 0 | 0 | 0 | 10433 | -5.29 | 10427.71 | 0 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | GHA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 160000 | 23200 | 183200 | 183200 | 100% | 0 | 0 | 0 | 20800 | 3016 | 23816 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IDS | SEV | 23 | INS | 80 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 208650 | -265 | 208385 | 208385 | 100% | 0 | 0 | 0 | 27124.5 | -33.5 | 27091 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (Phase III) | Individual | ASP | IDS | SEV | 32 | INS | 121 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2003-01-01 |  | 2004-09-01 | 2006-08-01 | 208650 | -86 | 208564 | 208564 | 100% | 0 | 0 | 0 | 27124.5 | -10.5 | 27114 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IDS | SEV | 41 | INS | 159 | N | I | No_ODP | 22.4 | 22.4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2011-11-01 | 271245 | -702.61 | 270542.39 | 270542.39 | 100% | 0 | 0 | 0 | 20343 | -52.6948 | 20290.3052 | 0 | 0 | Completed in 2006. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IDS | SEV | 47 | INS | 171 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2011-11-01 | 271245 | -100.7 | 271144.3 | 271144.3 | 100% | 0 | 0 | 0 | 20343 | -7.5524 | 20335.4476 | 0 | 0 | Completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IDS | SEV | 53 | INS | 180 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-12-01 | 2012-07-01 | 271245 | 0 | 271245 | 271244.55 | 100% | 0.45 | 0 | 0 | 20343 | 0 | 20342.9663 | 0.033749 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection and Ozone Depleting Substances Phase-out Unit | Individual | ASP | IDS | SEV | 10 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 1997-06-01 | 2003-04-01 | 314780 | 0 | 314780 | 314780 | 100% | 0 | 0 | 0 | 40921 | 0 | 40921 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase IV) | Individual | ASP | IND | SEV | 34 | INS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2003-08-01 |  | 2004-03-01 | 2009-01-01 | 287100 | -1304.01 | 285795.99 | 285796.29 | 100% | -0.3 | 0 | 0 | 37323 | -170.0013 | 37153.0377 | -0.038999 | 0 | Completed in 2004.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Institutional strengthening project for the phaseout of ODSs under the Montreal Protocol: Phase II | Individual | ASP | IND | SEV | 20 | INS | 107 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1999-03-01 | 1999-12-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of Institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol : Phase 3 | Individual | ASP | IND | SEV | 27 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2001-04-01 |  | 2001-08-01 | 2002-01-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project: phase 5 | Individual | ASP | IND | SEV | 41 | INS | 367 | N | I | No_ODP | 30.8 | 30.8 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-07-01 | 2011-12-01 | 373230 | -2920 | 370310 | 370310.21 | 100% | -0.21 | 0 | 0 | 27992 | -218.998 | 27773.0177 | -0.01575 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IND | SEV | 08 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-06-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 430600 | -1671 | 428929 | 428929 | 100% | 0 | 0 | 0 | 55978 | -217 | 55761 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IRA | SEV | 44 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-03-01 | 2007-06-01 | 86755 | -1313 | 85442 | 85442 | 100% | 0 | 0 | 0 | 6507 | -97.9992 | 6409.0008 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI, second year) | Individual | ASP | IRA | SEV | 53 | INS | 185 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 86756 | -87.31 | 86668.69 | 86668.69 | 100% | 0 | 0 | 0 | 6507 | -6.55 | 6500.45 | 0 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V, year 2) | Individual | ASP | IRA | SEV | 47 | INS | 174 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-03-01 | 2008-09-01 | 86756 | -69 | 86687 | 86686.89 | 100% | 0.11 | 0 | 0 | 6507 | -4.9952 | 6501.9965 | 0.0082506 | 0 | Completed in 2007. Financially Completed in 2008. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | IRA | SEV | 50 | INS | 179 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-07-01 | 2009-06-01 | 86755 | -65 | 86690 | 86690.32 | 100% | -0.32 | 0 | 0 | 6507 | -4.8753 | 6502.1487 | -0.024001 | 0 | Completed in 2008.Financially completed in 2009. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | IRA | SEV | 32 | INS | 74 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-08-01 | 2004-01-01 | 133470 | -25 | 133445 | 133445 | 100% | 0 | 0 | 0 | 17351.1 | -3.1 | 17348 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IRA | SEV | 23 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-08-01 | 1999-12-01 |  | 2002-05-01 | 2003-11-01 | 133470 | 0 | 133470 | 133470 | 100% | 0 | 0 | 0 | 17351 | 0 | 17351 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IRA | SEV | 38 | INS | 157 | N | I | No_ODP | 14.3 | 14.3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2005-12-01 | 2007-06-01 | 173511 | -1407 | 172104 | 172104.15 | 100% | -0.15 | 0 | 0 | 22556.43 | -183.4278 | 22373.0217 | -0.0195 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | IRA | SEV | 56 | INS | 187 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 173511 | -403.06 | 173107.94 | 173107.94 | 100% | 0 | 0 | 0 | 13013 | -30.23 | 12982.77 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IRA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-12-01 | 2000-12-01 | 200200 | 0 | 200200 | 200200 | 100% | 0 | 0 | 0 | 26026 | 0 | 26026 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1992 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | AFR | KEN | SEV | 32 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2005-09-01 | 116667 | -234 | 116433 | 116433 | 100% | 0 | 0 | 0 | 15166.71 | -29.7106 | 15136.9994 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | KEN | SEV | 25 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-12-01 | 2003-10-01 | 116667 | 0 | 116667 | 116667 | 100% | 0 | 0 | 0 | 15167 | 0 | 15167 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | KEN | SEV | 38 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 151667 | -204 | 151463 | 151463.01 | 100% | -0.01 | 0 | 0 | 19716.71 | -26.71 | 19690.0013 | -0.0013 | 0 | Completed in 2004. Financially completed in 2006. |  | 2002 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | KEN | SEV | 09 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-06-01 | 2005-09-01 | 175000 | -34 | 174966 | 174966 | 100% | 0 | 0 | 0 | 22750 | -4 | 22746 | 0 | 0 | Completed in 1998. Financially completed in 2005. |  | 1993 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | ASP | LEB | SEV | 31 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2003-07-01 | 2004-12-01 | 119300 | 0 | 119300 | 119300 | 100% | 0 | 0 | 0 | 15509 | 0 | 15509 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | LEB | SEV | 44 | INS | 59 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-06-01 | 2010-10-01 | 155090 | -2834.99 | 152255.01 | 152255.01 | 100% | 0 | 0 | 0 | 11632 | -212.6288 | 11419.3712 | 0 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 3) | Individual | ASP | LEB | SEV | 37 | INS | 50 | N | I | No_ODP | 12.8 | 12.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-12-01 | 2009-07-01 | 155090 | -979 | 154111 | 154110.9 | 100% | 0.1 | 0 | 0 | 20161.7 | -126.9719 | 20034.7151 | 0.013 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | LEB | SEV | 50 | INS | 64 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 155090 | -372.8 | 154717.2 | 154717.2 | 100% | 0 | 0 | 0 | 11632 | -27.96 | 11604.04 | 0 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Creation of an Ozone Unit | Individual | ASP | LEB | SEV | 19 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 2000-05-01 |  | 2000-12-01 | 2002-03-01 | 179000 | -63 | 178937 | 178937 | 100% | 0 | 0 | 0 | 23270 | -8 | 23262 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | MAL | SEV | 26 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-05-01 | 215000 | -36884 | 178116 | 178116 | 100% | 0 | 0 | 0 | 27950 | -4795 | 23155 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase IV) | Individual | ASP | MAL | SEV | 32 | INS | 142 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2005-03-01 | 2009-07-01 | 215000 | -10994 | 204006 | 204006.18 | 100% | -0.18 | 0 | 0 | 27950 | -1429.22 | 26520.8034 | -0.0234 | 0 | Completed in 2005.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 20 | INS | 91 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-10-01 |  | 1998-10-01 | 2003-04-01 | 215000 | -5523 | 209477 | 209477 | 100% | 0 | 0 | 0 | 27950 | -718 | 27232 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 38 | INS | 148 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 279500 | -17132.83 | 262367.17 | 262367.17 | 100% | 0 | 0 | 0 | 36335 | -2227.2679 | 34107.7321 | 0 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | MAL | SEV | 53 | INS | 159 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 279500 | -2000.74 | 277499.26 | 277499.26 | 100% | 0 | 0 | 0 | 20963 | -150.06 | 20812.94 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | MAL | SEV | 44 | INS | 153 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2008-07-01 | 2011-12-01 | 279500 | 0 | 279500 | 279500.22 | 100% | -0.22 | 0 | 0 | 20963 | 0 | 20963.0165 | -0.0165 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Institutional strengthening in relation to projects on reduction of ozone depleting substances | Individual | ASP | MAL | SEV | 09 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-12-01 | 2003-04-01 | 322520 | -15703 | 306817 | 306816.99 | 100% | 0.01 | 0 | 0 | 41927.6 | -2040.6 | 39886.9987 | 0.0013 | 0 | Completed in 1996. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening | Individual | LAC | MEX | SEV | 17 | INS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-12-01 |  | 1996-10-01 | 2003-11-01 | 47500 | 47500 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6175 | 6175 | 12350 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1995 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 31 | INS | 97 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-08-01 | 2003-11-01 | 190000 | -45584 | 144416 | 144416 | 100% | 0 | 0 | 0 | 24700 | -5926 | 18774 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODSs under the Montreal Protocol | Individual | LAC | MEX | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-10-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project | Individual | LAC | MEX | SEV | 25 | INS | 83 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-07-01 |  | 2000-07-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase II) | Individual | AFR | NIR | SEV | 34 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-08-01 | 2009-07-01 | 200000 | -851 | 199149 | 199149.21 | 100% | -0.21 | 0 | 0 | 26000 | -110.63 | 25889.3973 | -0.0273 | 0 | Completed in 2003.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | NIR | SEV | 48 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2007-12-01 | 2012-04-01 | 260000 | -195.2 | 259804.8 | 259804.8 | 100% | 0 | 0 | 0 | 19500 | -14.64 | 19485.36 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | NIR | SEV | 40 | INS | 107 | N | I | No_ODP | 21.5 | 21.5 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2012-04-01 | 260000 | -100.24 | 259899.76 | 259899.76 | 100% | 0 | 0 | 0 | 19500 | -7.52 | 19492.48 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | NIR | SEV | 09 | INS | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-01-01 | 1996-03-01 |  | 2001-01-01 | 2003-09-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV, second year) | Individual | ASP | PAK | SEV | 53 | INS | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-10-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 112234 | -17570.62 | 94663.38 | 94663.38 | 100% | 0 | 0 | 0 | 8418 | -1317.87 | 7100.13 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | PAK | SEV | 51 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-03-01 | 2009-04-01 |  | 2008-09-01 | 2011-12-01 | 112233 | 0 | 112233 | 112233 | 100% | 0 | 0 | 0 | 8418 | 0 | 8418 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | PAK | SEV | 35 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2004-01-01 |  | 2004-01-01 | 2007-06-01 | 172666 | -102 | 172564 | 172564 | 100% | 0 | 0 | 0 | 22446.58 | -12.5763 | 22434.0037 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project: phase 3 | Individual | ASP | PAK | SEV | 41 | INS | 54 | N | I | No_ODP | 18.6 | 18.6 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-11-01 | 224467 | -2476 | 221991 | 221990.55 | 100% | 0.45 | 0 | 0 | 16835 | -185.9997 | 16648.9665 | 0.033749 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | PAK | SEV | 14 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 2001-12-01 | 2003-05-01 | 259000 | -4042 | 254958 | 254958 | 100% | 0 | 0 | 0 | 33670 | -525 | 33145 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | SRL | SEV | 23 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-11-01 | 1999-12-01 |  | 1999-12-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase III) | Individual | ASP | SRL | SEV | 29 | INS | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2002-02-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | SRL | SEV | 55 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-11-01 | 134056 | -14374.2 | 119681.8 | 119681.8 | 100% | 0 | 0 | 0 | 10054 | -1078.04 | 8975.96 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 4) | Individual | ASP | SRL | SEV | 37 | INS | 20 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-08-01 | 2010-06-01 | 134056 | -2677.85 | 131378.15 | 131378.15 | 100% | 0 | 0 | 0 | 17427.28 | -348.3949 | 17078.8851 | 0 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | SRL | SEV | 50 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2008-11-01 | 2011-01-01 | 134056 | -1295.2 | 132760.8 | 132760.8 | 100% | 0 | 0 | 0 | 10054 | -97.1381 | 9956.8619 | 0 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | SRL | SEV | 43 | INS | 22 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-12-01 | 2008-10-01 | 134056 | -14 | 134042 | 134042.03 | 100% | -0.03 | 0 | 0 | 10054 | -0.99998 | 10053.0023 | -0.00225 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | SRL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1997-03-01 |  | 1997-10-01 | 2003-09-01 | 154680 | 0 | 154680 | 154680 | 100% | 0 | 0 | 0 | 20108 | 0 | 20108 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol | Individual | ASP | THA | SEV | 25 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-07-01 | 2000-07-01 |  | 2003-04-01 | 2003-05-01 | 266667 | -225128 | 41539 | 41539 | 100% | 0 | 0 | 0 | 34666.71 | -29266.64 | 5400.07 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection Unit | Individual | ASP | THA | SEV | 09 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-12-01 | 1996-03-01 |  | 2002-01-01 | 2003-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1993 | 1997-12-01 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | LAC | TRI | SEV | 32 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2011-12-01 | 44000 | -3631.6 | 40368.4 | 40368.4 | 100% | 0 | 0 | 0 | 5720 | -472.108 | 5247.892 | 0 | 0 | Completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase 3) | Individual | LAC | TRI | SEV | 38 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2006-12-01 | 2011-12-01 | 57200 | -506.64 | 56693.36 | 56693.36 | 100% | 0 | 0 | 0 | 7436 | -65.8632 | 7370.1368 | 0 | 0 | Completed in 2006. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | LAC | TRI | SEV | 44 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-05-01 | 2011-12-01 | 60000 | -448.48 | 59551.52 | 59551.52 | 100% | 0 | 0 | 0 | 4500 | -34 | 4466 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | TRI | SEV | 20 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 2000-12-01 | 2003-06-01 | 66000 | -5223 | 60777 | 60777.04 | 100% | -0.04 | 0 | 0 | 8580 | -678.99 | 7901.0152 | -0.0052 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-12-01 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -2 | 15078 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2006-01-01 | 2009-08-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 19604 | 0 | 19604 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 150800 | 0 | 150800 | 150800.34 | 100% | -0.34 | 0 | 0 | 11310 | 0 | 11310.0255 | -0.0255 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | URU | SEV | 49 | INS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-10-01 |  | 2010-08-01 | 2012-07-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-07-01 | 285480 | -981 | 284499 | 284499 | 100% | 0 | 0 | 0 | 37112.4 | -127 | 36985.4 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | VEN | SEV | 49 | INS | 108 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2008-07-01 |  | 2008-12-01 | 2011-10-01 | 285480 | -0.99 | 285479.01 | 285479.01 | 100% | 0 | 0 | 0 | 21411 | -0.0743 | 21410.9257 | 0 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 285480 | 0 | 285480 | 285479.78 | 100% | 0.22 | 0 | 0 | 21411 | 0 | 21410.9835 | 0.0165 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42794.96 | 0 | 42794.96 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | UNEP | Start up of institutional strengthening project | Individual | ASP | AFG | SEV | 46 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 |  | 2005-10-01 | 2006-10-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 13 reinstated at ExCom 54) |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | AFG | SEV | 43 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2005-07-01 | 2007-04-01 | 40000 | -13 | 39987 | 39987 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | ASP | AFG | SEV | 47 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | AFG | SEV | 53 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2009-11-01 | 2009-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | AFG | SEV | 58 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 81250 | 68750 | 150000 | 150000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | ALB | SEV | 35 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (second year) | Individual | EUR | ALB | SEV | 38 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 |  | 2005-07-01 | 2007-06-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | EUR | ALB | SEV | 46 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2007-07-01 |  | 2006-07-01 | 2008-03-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | EUR | ALB | SEV | 54 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-06-01 |  | 2011-06-01 | 2012-06-01 | 109200 | 0 | 109200 | 109137 | 99.94% | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | EUR | ALB | SEV | 49 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-08-01 | 2008-06-01 |  | 2008-06-01 | 2010-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ALG | SEV | 27 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2003-06-01 | 90010 | 0 | 90010 | 90010 | 100% | 0 | 0 | 0 | 11701 | 0 | 11701 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ALG | SEV | 48 | INS | 64 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2012-08-01 | 257400 | 0 | 257400 | 257400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | AFR | ALG | SEV | 37 | INS | 54 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2006-07-01 | 2007-07-01 | 257000 | -1 | 256999 | 256999 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. (US$ 1 returned to ExCom 55) |  |  |  | Non Investment
FIN | UNEP | Institutional support for ODS phase-out | Individual | AFR | ALG | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 |  | 1999-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 38610 | 0 | 38610 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ANT | SEV | 38 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-06-01 | 2009-06-01 | 31200 | -13 | 31187 | 31187 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | ANT | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-09-01 | 2001-12-01 |  | 2002-12-01 | 2004-10-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 | 0 | 0 | 4680 | 0 | 4680 | 0 | 0 | Project financially completed. ($ 13 returned to ExCom 51) |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | BAH | SEV | 31 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | BAH | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | BAH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | BAH | SEV | 47 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($17,982 plus $2,338 returned ExCom 46 $ -10,000 plus $ -1,300 PSC returned from ExCom 48) |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | ASP | BAH | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III, year 2) | Individual | LAC | BAR | SEV | 46 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2008-01-01 | 2007-07-01 |  | 2011-03-01 | 2012-06-01 | 58500 | 0 | 58500 | 58500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of Institutional strengthening project (phase III) | Individual | LAC | BAR | SEV | 42 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2007-11-01 | 2009-07-01 | 58500 | -560 | 57940 | 57940 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BAR | SEV | 26 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2005-12-01 | 2005-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. ($ 560 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | BAR | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1997-12-01 |  | 1998-12-01 | 1999-10-01 | 136000 | -1050 | 134950 | 134950 | 100% | 0 | 0 | 0 | 17680 | -136.5 | 17543.5 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | AFR | BDI | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-12-01 | 2005-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BDI | SEV | 44 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | BDI | SEV | 50 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | AFR | BDI | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2002-07-01 | 2003-07-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | BEN | SEV | 28 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-09-01 | 2001-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333 | 0 | 4333 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | BEN | SEV | 33 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333 | 0 | 4333 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | BEN | SEV | 40 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | BEN | SEV | 18 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | AFR | BEN | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-06-01 | 2008-06-01 |  | 2008-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 (one year) | Individual | LAC | BHA | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-04-01 |  | 2006-07-01 | 2007-07-01 | 21666 | 0 | 21666 | 21666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II ) | Individual | LAC | BHA | SEV | 42 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2006-07-01 | 2009-07-01 | 21667 | 0 | 21667 | 21667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | BHA | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-03-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III ) | Individual | LAC | BHA | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-06-01 | 2008-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | BHU | SEV | 43 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-07-01 | 2006-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | BHU | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | BHU | SEV | 58 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (phase I) | Individual | ASP | BHU | SEV | 46 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2008-07-01 |  | 2007-07-01 | 2008-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | BKF | SEV | 22 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 1999-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | BKF | SEV | 27 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-07-01 | 2001-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase IV) | Individual | AFR | BKF | SEV | 33 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-01-01 | 2003-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | BKF | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase 5) | Individual | AFR | BKF | SEV | 38 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | BKF | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | BKF | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Board | Individual | AFR | BKF | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-12-01 | 1996-11-01 |  | 1997-06-01 | 1996-02-01 | 83500 | 0 | 83500 | 83500 | 100% | 0 | 0 | 0 | 10855 | 0 | 10855 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BOL | SEV | 26 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 | 0 | 7887 | 0 | 7887 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | BOL | SEV | 34 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 | 0 | 7887 | 0 | 7887 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | BOL | SEV | 47 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BOL | SEV | 53 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Governmental Commission (COGO) | Individual | LAC | BOL | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 1999-12-01 | 91000 | 0 | 91000 | 91000 | 100% | 0 | 0 | 0 | 11830 | 0 | 11830 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project | Individual | LAC | BOL | SEV | 40 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | BOT | SEV | 41 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-06-01 | 2005-12-01 |  | 2008-02-01 | 2012-12-01 | 78173 | 0 | 78173 | 78173 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Office) | Individual | AFR | BOT | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1997-07-01 |  | 2003-12-01 | 2003-12-01 | 90200 | 0 | 90200 | 90200 | 100% | 0 | 0 | 0 | 11726 | 0 | 11726 | 0 | 0 | Project financially completed. ($ 5,000 plus $ 650 PSC returned to ExCom 50$ 10,500 plus $ 1,365 PSC returned to ExCom 59) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Creation of a Brunei Ozone Office | Individual | ASP | BRU | SEV | 26 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2004-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | BZE | SEV | 40 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-07-01 | 2007-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | LAC | BZE | SEV | 46 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-07-01 | 2007-07-01 |  | 2008-09-01 | 2009-09-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BZE | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-07-01 | 2011-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Creation of the national ozone unit | Individual | LAC | BZE | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2003-01-01 | 2004-10-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 | 0 | 11505 | 0 | 11505 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | CAF | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2004-10-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | AFR | CAF | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2006-01-01 | 2007-04-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Technical Ozone Group (Ozone Unit) | Individual | AFR | CAF | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 2000-06-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 | 0 | 5928 | 0 | 5928 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CAF | SEV | 45 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-06-01 | 2007-04-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | CBI | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2005-06-01 | 2003-04-01 |  | 2007-11-01 | 2011-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | CBI | SEV | 44 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-09-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | CBI | SEV | 50 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2008-11-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | AFR | CHD | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2001-07-01 |  | 2004-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | CHD | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CHD | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2011-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($8,217 plus $1,068 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CHD | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-12-01 | 2006-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The project is completed and PCR submitted to the MLFS in Feb 2011. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | CKI | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-10-01 | 2005-12-01 |  | 2007-01-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase I) | Individual | ASP | CKI | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-01-01 | 2007-11-01 |  | 2008-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($10,136 plus $1,318 PSC returned ExCom 44) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | CKI | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-05-01 | 2008-11-01 |  | 2011-01-01 | 2011-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | CKI | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2010-12-01 |  | 2011-03-01 | 2011-06-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | CMR | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (second year of phase IV) | Individual | AFR | CMR | SEV | 44 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | CMR | SEV | 22 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-12-01 | 2000-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | AFR | CMR | SEV | 28 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. ($ 1,994 returned to ExCom 50) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase V | Individual | AFR | CMR | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | CMR | SEV | 53 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Ozone Monitoring Commission | Individual | AFR | CMR | SEV | 11 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-10-01 | 1996-11-01 |  | 1997-10-01 | 1997-06-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | COI | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 18533 | 0 | 18533 | 18533 | 100% | 0 | 0 | 0 | 2409 | 0 | 2409 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | COI | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24093 | 0 | 24093 | 24093 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Ozone Unit | Individual | AFR | COI | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 2000-12-01 |  | 2001-03-01 | 2001-12-01 | 27800 | 0 | 27800 | 27800 | 100% | 0 | 0 | 0 | 3614 | 0 | 3614 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | COI | SEV | 45 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | COI | SEV | 51 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-05-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($42,082 plus $5471 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | COI | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2011-03-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | CRO | SEV | 29 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2001-12-01 |  | 2002-03-01 | 2003-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 | 0 | 8710 | 0 | 8710 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | EUR | CRO | SEV | 56 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-04-01 | 2011-01-01 |  | 2011-07-01 | 2012-07-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | EUR | CRO | SEV | 41 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2006-12-01 | 2008-05-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | EUR | CRO | SEV | 47 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2008-04-01 |  | 2008-11-01 | 2009-11-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening projects (phase III) | Individual | EUR | CRO | SEV | 36 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2004-04-01 |  | 2004-12-01 | 2007-05-01 | 87900 | 0 | 87900 | 87900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | EUR | CRO | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 101200 | 0 | 101200 | 101200 | 100% | 0 | 0 | 0 | 13156 | 0 | 13156 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | DJI | SEV | 57 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2011-07-01 | 2012-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | DJI | SEV | 48 | INS | 09 | A | I |  | 0 | 0.9 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2008-04-01 |  | 2009-04-01 | 2010-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($3,000 plus $390 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | DJI | SEV | 37 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-08-01 |  | 2006-04-01 | 2007-04-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | DMI | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-12-01 | 2007-04-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | LAC | DMI | SEV | 45 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-10-01 | 2008-01-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($9,183 plus $1,194 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | DMI | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-07-01 | 2001-12-01 |  | 2004-02-01 | 2005-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | DMI | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($25,000 plus $3,250 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DMI | SEV | 56 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 36000 | 60% | 24000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | IS Phase completed as planned. New phase 5 approved in Nov 2010. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | DOM | SEV | 29 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 103000 | 0 | 103000 | 103000 | 100% | 0 | 0 | 0 | 13390 | 0 | 13390 | 0 | 0 | Project financially completed. ($ 1 returned to ExCom 54) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | DOM | SEV | 39 | INS | 34 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2006-11-01 | 2007-04-01 | 134333 | -1 | 134332 | 134332 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DOM | SEV | 48 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2009-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed ($ 4,805 plus $ 625 returned from ExCom 48$ 12,180 plus $ 1,583 returned to ExCom 62) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DOM | SEV | 56 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2010-11-01 |  | 2011-04-01 | 2011-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Financial and progress report received. Project renewed at the 62 ExCom. |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Commission for the Ozone (Cogo) | Individual | LAC | DOM | SEV | 17 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1998-10-01 |  | 2000-02-01 | 2001-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Project financially completed. |  |  | 1998-10-01 | Non Investment
FIN | UNEP | Creation of an Ozone Office | Individual | AFR | DRC | SEV | 27 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2003-06-01 | 2000-04-01 |  | 2000-12-01 | 2004-04-01 | 32270 | 0 | 32270 | 32270 | 100% | 0 | 0 | 0 | 4195 | 0 | 4195 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | DRC | SEV | 58 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2011-08-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 48405 | 0 | 48405 | 48405 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (renewal) | Individual | AFR | DRC | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-09-01 | 2005-12-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 | 0 | 8390 | 0 | 8390 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | DRC | SEV | 46 | INS | 22 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2005-07-01 | 2007-01-01 | 2007-07-01 |  | 2007-07-01 | 2009-07-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | DRC | SEV | 52 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-06-01 |  | 2009-06-01 | 2011-11-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in July 2010. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | ASP | DRK | SEV | 32 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-08-01 | 2003-01-01 |  | 2003-10-01 | 2003-12-01 | 95040 | 0 | 95040 | 95040 | 100% | 0 | 0 | 0 | 12355 | 0 | 12355 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | DRK | SEV | 41 | INS | 31 | A | I | CFC | 10.2 | 9.8 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2010-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | DRK | SEV | 47 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | DRK | SEV | 53 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Cell | Individual | ASP | DRK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 2000-02-01 |  | 2000-12-01 | 2003-06-01 | 142560 | 0 | 142560 | 142560 | 100% | 0 | 0 | 0 | 18533 | 0 | 18533 | 0 | 0 | Project financially completed. ($684 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (year 1 of phase V) | Individual | LAC | ELS | SEV | 52 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-09-01 |  | 2009-09-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | ELS | SEV | 32 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-03-01 | 2004-05-01 | 44600 | 0 | 44600 | 44600 | 100% | 0 | 0 | 0 | 5798 | 0 | 5798 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ELS | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2006-10-01 | 57980 | 0 | 57980 | 57980 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | ELS | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-06-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Area of policies for the protection of the ozone layer (institutional strengthening) | Individual | LAC | ELS | SEV | 22 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 2000-05-01 |  | 2001-06-01 | 2001-12-01 | 66900 | 0 | 66900 | 66900 | 100% | 0 | 0 | 0 | 8697 | 0 | 8697 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Start-up of institutional strengthening project | Individual | AFR | EQG | SEV | 49 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-12-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($2,000 plus $260 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | ERI | SEV | 47 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2008-02-01 | 2009-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 7,326 plus $ 952 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project for a one year period (phase 3) | Individual | AFR | ETH | SEV | 39 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2006-12-01 | 2009-05-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2005-12-01 |  | 2008-12-01 | 2009-12-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase 3 year 2) | Individual | AFR | ETH | SEV | 29 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 40300 | 0 | 40300 | 40300 | 100% | 0 | 0 | 0 | 5239 | 0 | 5239 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of national ozone cell for the implementation of Montreal Protocol in Ethiopia | Individual | AFR | ETH | SEV | 20 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-01-01 | 1999-11-01 | 60500 | 0 | 60500 | 60500 | 100% | 0 | 0 | 0 | 7865 | 0 | 7865 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | FIJ | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV- year 2) | Individual | ASP | FIJ | SEV | 47 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balance to be returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | FIJ | SEV | 29 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2001-12-01 |  | 2002-05-01 | 2007-03-01 | 43930 | 0 | 43930 | 43930 | 100% | 0 | 0 | 0 | 5711 | 0 | 5711 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | ASP | FIJ | SEV | 37 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2004-08-01 | 2008-12-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | FIJ | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-11-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | FIJ | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed in December 2010. All remaining project activities were completed in 2010. Funding contributed to supporting the Montreal Protocol components of: regional and national customs training workshops (co-financed by UNEP supplementary Environment Fund) production of Green Customs Video GCI e-learning module created in cooperation with World Customs Organization case study/ ODS illegal trade risk analysis report. MLF funding for this project was catalytic in attracting and securing significant other funding for GCI activities from a variety of sources. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | FIJ | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1997-03-01 |  | 2000-07-01 | 2001-12-01 | 65890 | 0 | 65890 | 65890 | 100% | 0 | 0 | 0 | 8566 | 0 | 8566 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | FSM | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-07-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (2nd year of phase II) | Individual | ASP | FSM | SEV | 58 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | FSM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | -2761.13 | 31238.87 | 31239 | 100% | -0.13 | 0 | -0.13 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | GAB | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | AFR | GAB | SEV | 37 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2005-02-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of a National Ozone Technical Group | Individual | AFR | GAB | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2001-12-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 | 0 | 5928 | 0 | 5928 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAB | SEV | 56 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | GAB | SEV | 44 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAB | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | GAM | SEV | 30 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Project financially completed. ($29 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | GAM | SEV | 41 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2006-03-01 | 2007-03-01 | 36573 | 0 | 36573 | 36573 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | GAM | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-09-01 | 2000-09-01 | 42200 | 0 | 42200 | 42200 | 100% | 0 | 0 | 0 | 5486 | 0 | 5486 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | GAM | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | -29 | 59971 | 59971 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAM | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. Public awareness raising and educational campaigns were conducted. Refrigeration technicians and customs officers were trained in good refrigeration practices. 40 technicians have been trained in alternative technologies. Refrigerant identifiers were purchased and made available for the customs training. |  |  |  | Non Investment
FIN | UNEP | Establishment of ozone unit | Individual | AFR | GBS | SEV | 39 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2010-01-01 | 2004-04-01 |  | 2004-07-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | GBS | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2011-11-01 | 2012-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening project) | Individual | AFR | GBS | SEV | 43 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9,800 plus $ 1,274 PSC returned to ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | GEO | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-08-01 | 2003-01-01 |  | 2003-02-01 | 2003-12-01 | 46700 | 0 | 46700 | 46700 | 100% | 0 | 0 | 0 | 6071 | 0 | 6071 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | EUR | GEO | SEV | 39 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2004-12-01 | 2008-12-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project: phase IV | Individual | EUR | GEO | SEV | 45 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 18,194 plus $ 2,365 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | GEO | SEV | 23 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 2000-12-01 |  | 2001-05-01 | 2001-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project | Individual | LAC | GRN | SEV | 44 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of a National Ozone Unit | Individual | LAC | GRN | SEV | 30 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2003-06-01 | 2003-04-01 |  | 2006-08-01 | 2007-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | GRN | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-11-01 |  | 2010-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | LAC | GUA | SEV | 43 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2010-06-01 | 2010-12-01 | 62400 | 0 | 62400 | 62400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 23,512 plus $ 3,057 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | GUA | SEV | 22 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2000-05-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project completed in June 2010. Project financially closed in February 2009. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | LAC | GUA | SEV | 28 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-12-01 | 2003-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | GUA | SEV | 35 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-09-01 | 2004-01-01 |  | 2004-03-01 | 2007-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | LAC | GUA | SEV | 53 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2011-12-01 | 124800 | 0 | 124800 | 124800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed in last quarter of 2011. Financial and progress report already submitted to UNEP. NOU is in charge of coordinate TPMP/HPMP implementation. Furthermore, the MeBr phase-out project is led by NOU as the Chair of the National Steering Committee on MeBr uses. The 2010 ODSs consumption data and Country Programme report have been respectively submitted to the OS and the MFS. ODSs data are depurated through cross-checking information from different sources (ODSs licensing system, database of the Superintendence of Customs and the Ministry of Agriculture). CFCs, Halons and carbon tetrachloride total phase-out kept in the 2011 through banning imports of substances as well as equipment and related technology. 90 requests to import refrigerants, plus 14 of MeBr and 3550 requests of refrigeration equipment and air conditioning have been approved by the Ministry of Environment with the support of NOU. NOO attended the network meetings carried out in Paraguay (June 2011) and Trinidad and Tobago (October 2011). |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | GUA | SEV | 10 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-12-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 22360 | 0 | 22360 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | GUI | SEV | 28 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333 | 0 | 4333 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | GUI | SEV | 34 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333 | 0 | 4333 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | GUI | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 4,000 plus $ 520 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | GUI | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project: (phase V) | Individual | AFR | GUI | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2009-02-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project: (phase VI) | Individual | AFR | GUI | SEV | 56 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. The NOU successfully implemented TPMP activities including training of customs officers and refrigeration technicians. The NOU established the ODS Licensing unit to be in-charge of all applications for ODS importations. The NOU conducted awareness sensitization to the general Public on ODS issues. The NOU carried out detailed survey of ODS consumption, and submitted data to Ozone Secretariat and Multilateral Fund Secretariat in time. Awareness materials like stickers, caps, calendars and leaflets were produced and distributed. .ODS programmes were featured in several radio stations, TV stations and several newspapers. The country celebrated Ozone Day and carried out several awareness activities during the day. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | GUY | SEV | 34 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2005-02-01 | 2003-08-01 |  | 2008-09-01 | 2009-09-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. ($ 9,000 plus $1,170 PSC returned ExCom 44$ 20,000 plus $ 2,600 PSC retuned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GUY | SEV | 48 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 56333 | 0 | 56333 | 56333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of the National Ozone Action Unit | Individual | LAC | GUY | SEV | 23 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 2000-11-01 |  | 2001-08-01 | 2007-03-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 8450 | 0 | 8450 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | HAI | SEV | 38 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-07-01 | 2003-12-01 |  | 2004-08-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($628 plus $82 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase I, years 2 and 3) | Individual | LAC | HAI | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-09-01 | 2008-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | HAI | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-09-01 | 2011-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in June 2010. Country submitted final reports in June 2010. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | HON | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-05-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | HON | SEV | 40 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-07-01 | 2005-07-01 |  | 2005-07-01 | 2007-02-01 | 57200 | -1 | 57199 | 57199 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | HON | SEV | 45 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-05-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | HON | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. The progress of the project implementation is being monitored regularly through communication by telephone and email. Awareness: Regular organization of awareness activities have been carried out for the relevant national stakeholders including workshops to further inform them of the relevant information that they need to be aware of. Furthermore, comprehensive awareness activities were organized in collaboration with TUNZA Mongolia (youth), Media, schools and public. Using media agents such as national TV channels, radio stations, newspapers, and journals. Publishing and delivering awareness-raising and educational packages. And, conducting workshops and seminars, involving specialists of relevant sectors especially during the International Ozone Day. The NOO participated in all the meetings organized by UNEP such as network meetings, and other meetings under the south-south cooperation. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit Cell for the institutional strengthening programme | Individual | LAC | HON | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1999-10-01 |  | 2001-06-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | IRQ | SEV | 54 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2010-03-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | IVC | SEV | 43 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-09-01 | 2005-07-01 |  | 2005-11-01 | 2007-08-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III, year 2) | Individual | AFR | IVC | SEV | 48 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | IVC | SEV | 26 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2004-04-01 | 2004-12-01 | 81800 | 0 | 81800 | 81800 | 100% | 0 | 0 | 0 | 10634 | 0 | 10634 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | IVC | SEV | 53 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-06-01 | 2011-06-01 | 106340 | 0 | 106340 | 106340 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. Country submitted final activity and expenditure reports. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Secretariat) | Individual | AFR | IVC | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-01-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 122810 | -300 | 122510 | 122510 | 100% | 0 | 0 | 0 | 15965 | -39 | 15926.0007 | -0.00073284 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | JAM | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-01-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | JAM | SEV | 35 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-08-01 | 2004-10-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. ($ 11 plus $ 1 returned to ExCom 56) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | JAM | SEV | 40 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-01-01 | 2007-01-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | JAM | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2008-02-01 |  | 2008-06-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | JAM | SEV | 55 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. The 2010 Annual Implementation Reports were prepared and presented to 63rd Executive Committee of the Multilateral Fund Meeting. The TPMP implementation was coordinated at an effective cost and in accordance with terms established in the Implementation Plan through following activities: Permanent and close surveillance of the project results and objectives, preparation of periodic reports of the objectives, progress and results to facilitate corrective actions, processing the disclosed information by surveys on the ODS consumption in order to detect and identify facilities that still require CFCs to function, Monitoring and supervision visits to Customs stations, and training institutions. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening through creation of a National Ozone Unit | Individual | LAC | JAM | SEV | 20 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-05-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | KAM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | KAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-01-01 | 2006-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9,392 plus $ 1,221 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | KAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KAM | SEV | 53 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-10-01 | 2010-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | KAM | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 61028 | 51639 | 112667 | 112667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 52 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase VI) | Individual | AFR | KEN | SEV | 55 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-06-01 |  | 2010-12-01 | 2011-12-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | KEN | SEV | 58 | INS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 107431 | 0 | 107431 | 107431 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | KIR | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-01-01 | 2007-03-01 |  | 2008-12-01 | 2009-12-01 | 7666 | 0 | 7666 | 7666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | KIR | SEV | 36 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | KIR | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-02-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | KIR | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | KUW | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | KUW | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening and capacity building | Individual | ASP | KUW | SEV | 37 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-03-01 | 2005-08-01 |  | 2006-01-01 | 2008-12-01 | 121520 | 0 | 121520 | 121520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | EUR | KYR | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | KYR | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 4,000 plus $ 520 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | KYR | SEV | 55 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-01-01 |  | 2010-07-01 | 2011-07-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in July 2010. The NOU in collaboration with the National Fire Force conducted awareness raising workshop on Alternatives to Halon for Fire Fighting for the Police, the Military, the Airport Authority, and the Sea Port Authority, Institute of Engineers, Institute of Architect, NGOs and Government Ministries etc. Forty five Refrigeration Technicians and Engineers were trained on retrofitting refrigeration and air conditioning appliance with non CFCs and hydrocarbons. Good refrigeration practice on the use of non-ODS refrigeration was taught in four newly created Centres of excellence including the Government Technical Institute in Freetown. However, refrigeration technicians continue to face serious problems of contamination of ozone friendly alternatives. This is damaging the transformers of refrigerators. A farmer’s field school on alternatives to methyl bromide has been set up and the agricultural sector is now adapting to alternatives. Cooperation between the NOU and stakeholders is improving. HCFC and HFCs are gradually been replaced by hydrocarbon in the country. The main success is the reduction of ODS use and increased awareness on ODS. The Ozone Protection Act is part of the Environment Protection Agency Act which is now in force. The NOU celebrated the 2010 International Ozone Day and raised awareness on ODS phase-out. 2009 Article 7 data were collected and submitted. A new National Ozone Officer Victor H. O. Sawyerr was recruited to replace Mr. John S. Kamara in November 2010. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | KYR | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2005-08-01 |  | 2004-12-01 | 2011-03-01 | 133650 | 0 | 133650 | 133650 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2010. IS renewal was submitted to the 58th ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | LAO | SEV | 43 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | LAO | SEV | 50 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | LAO | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-11-01 |  | 2010-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit for implementing the phase-out of ODS under the Montreal Protocol | Individual | ASP | LAO | SEV | 34 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-08-01 | 2006-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project completed in November 2010 & financially completed. IS renewal was submitted to the 62nd ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | LES | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-12-01 |  | 2005-04-01 | 2007-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LES | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($2,389 plus $311 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | LES | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1999-10-01 |  | 1999-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | LIR | SEV | 51 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LIR | SEV | 57 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 |  | 2010-11-01 | 2011-11-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in March 2010. IS renewal was submitted to the 59th ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Establishment of the ozone unit | Individual | AFR | LIR | SEV | 41 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2007-12-01 | 127820 | 0 | 127820 | 127820 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MAG | SEV | 43 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2008-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | MAG | SEV | 49 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-07-01 | 2008-06-01 |  | 2009-06-01 | 2010-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of a Ozone Unit | Individual | AFR | MAG | SEV | 29 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2004-07-01 | 2007-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ozone depleting substances | Individual | AFR | MAR | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-08-01 | 1996-06-01 |  | 2004-12-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 822 returned to ExCom 58) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | MAR | SEV | 45 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-04-01 |  | 2007-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | MAS | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-02-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | MAS | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($834 plus $108 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | MAS | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-08-01 | 2009-12-01 | 34000 | -822 | 33178 | 33178 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | MAS | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | MAU | SEV | 33 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2004-01-01 | 2003-04-01 |  | 2004-01-01 | 2007-01-01 | 25900 | 0 | 25900 | 25900 | 100% | 0 | 0 | 0 | 3367 | 0 | 3367 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MAU | SEV | 43 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 33670 | 0 | 33670 | 33670 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 1,849 plus $ 240 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | MDV | SEV | 37 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2004-08-01 |  | 2004-10-01 | 2005-12-01 | 35753 | 0 | 35753 | 35753 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | MDV | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1997-03-01 |  | 2002-05-01 | 2005-12-01 | 41250 | 0 | 41250 | 41250 | 100% | 0 | 0 | 0 | 5363 | 0 | 5363 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | MDV | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2005-11-01 | 2007-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | MDV | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | MDV | SEV | 56 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2010. Country sent a verification report in January 2010 and UNEP released final payment in February 2010. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | MLI | SEV | 35 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-03-01 | 2007-06-01 | 46667 | 0 | 46667 | 46667 | 100% | 0 | 0 | 0 | 6067 | 0 | 6067 | 0 | 0 | Project financially completed. ($ 9,242 plus $ 1,201 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | MLI | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MLI | SEV | 50 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | MLI | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in April 2010. Renewal of the IS Project approved. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project for Mali | Individual | AFR | MLI | SEV | 24 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | MLW | SEV | 31 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-01-01 | 2005-12-01 | 51300 | 0 | 51300 | 51300 | 100% | 0 | 0 | 0 | 6669 | 0 | 6669 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Request for renewal of institutional strengthening | Individual | AFR | MLW | SEV | 25 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-06-01 |  | 2000-12-01 | 2003-12-01 | 51350 | 0 | 51350 | 51350 | 100% | 0 | 0 | 0 | 6676 | 0 | 6676 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | MLW | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | MLW | SEV | 47 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2007-12-01 |  | 2007-12-01 | 2008-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 11,000 plus $ 1,430 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | MLW | SEV | 53 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in March 2010. IS renewal was submitted to the 59th ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | MLW | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1997-03-01 |  | 1998-10-01 | 1999-10-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 | 0 | 10010 | 0 | 10010 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening projects (Phase II) | Individual | EUR | MOL | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2004-04-01 |  | 2004-07-01 | 2007-06-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 1,886 plus $245 PSC returned ExCom 44$ 13,529 plus $1759 PSC retuned ExCom 46$ 8 plus returned to ExCom 49) |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MOL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-03-01 | 2007-03-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 5,003 plus $ 650 PSC returned ExCom 44$ 10,000 plus $ 1300 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | MOL | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | MOL | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-07-01 |  | 2011-12-01 | 2011-12-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project activities are financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | MOL | SEV | 25 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2002-07-01 | 2004-05-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | MON | SEV | 60 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | MON | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-07-01 | 2007-07-01 | 57200 | -2 | 57198 | 57198 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | ASP | MON | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 4,984 plus $ 648 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | MON | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-06-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | MON | SEV | 55 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | MON | SEV | 28 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-08-01 |  | 2002-08-01 | 2003-09-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MOR | SEV | 43 | INS | 49 | A | I | CFC | 12.8 | 0 | 0 | 0 | 2004-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of Ozone Unit | Individual | AFR | MOR | SEV | 19 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1999-05-01 |  | 2004-07-01 | 2007-02-01 | 179000 | 0 | 179000 | 179000 | 100% | 0 | 0 | 0 | 23270 | 0 | 23270 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | MOZ | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-03-01 | 2005-12-01 |  | 2007-01-01 | 2008-12-01 | 80080 | 0 | 80080 | 80080 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MOZ | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2008-11-01 |  | 2009-07-01 | 2010-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MOZ | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | MOZ | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1997-12-01 |  | 2003-12-01 | 2005-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 12012 | 0 | 12012 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | MYA | SEV | 58 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | MYA | SEV | 62 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the national Ozone Cell for implementing the phase out of ODSs under the Montreal Protocol | Individual | ASP | MYA | SEV | 29 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2007-07-01 | 2002-12-01 |  | 2009-12-01 | 2011-03-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | NAM | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 41177 | 0 | 41177 | 41177 | 100% | 0 | 0 | 0 | 5353 | 0 | 5353 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | NAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 53530 | 0 | 53530 | 53530 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | NAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NAM | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | AFR | NAM | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 2000-02-01 | 2001-12-01 | 61765 | 0 | 61765 | 61765 | 100% | 0 | 0 | 0 | 8029 | 0 | 8029 | 0 | 0 | Project financially completed. |  |  | 1998-11-01 | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NAU | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NAU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-01-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | NAU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | NEP | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-08-01 | 2007-06-01 | 53733 | 0 | 53733 | 53733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | NEP | SEV | 44 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | NEP | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2008-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 24,000 plus $ 3,120 PSC returned Excom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | NEP | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | ASP | NEP | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2001-12-01 |  | 2002-05-01 | 2003-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | NER | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-06-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | NER | SEV | 33 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NER | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 64827 | -545 | 64282 | 64282 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | NER | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 900 plus $ 117 returned to ExCom 50) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NER | SEV | 47 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | NER | SEV | 59 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 35115 | 29713 | 64828 | 64828 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of an Ozone Secretariat | Individual | AFR | NER | SEV | 15 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1997-12-01 |  | 1999-05-01 | 1999-10-01 | 74800 | 0 | 74800 | 74800 | 100% | 0 | 0 | 0 | 9724 | 0 | 9724 | 0 | 0 | Project financially completed. ($ 1,995 returned to ExCom 50) |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | NIC | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2002-08-01 |  | 2003-09-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. ($ 3,277 plus $ 426 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | NIC | SEV | 39 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-10-01 | 2005-04-01 |  | 2007-03-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | NIC | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2002-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. ($ 16,990 plus $ 2,209 PSC returned ExCom 44) |  |  | 2000-05-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NIU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 15000 | -4900 | 10100 | 10100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NIU | SEV | 44 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-06-01 | 2007-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($52 returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | NIU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NIU | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PAN | SEV | 31 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2002-08-01 |  | 2002-12-01 | 2004-10-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase 3) | Individual | LAC | PAN | SEV | 38 | INS | 17 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2007-01-01 | 2010-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 4,000 plus $ 520 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAN | SEV | 44 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2009-09-01 | 2006-12-01 |  | 2011-12-01 | 2011-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | PAN | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-04-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 | 0 | 0 | 22425 | 0 | 22425 | 0 | 0 | Project financially completed |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | PAR | SEV | 32 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-01-01 | 2004-09-01 | 44200 | 0 | 44200 | 44200 | 100% | 0 | 0 | 0 | 5746 | 0 | 5746 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | PAR | SEV | 39 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2005-04-01 |  | 2009-07-01 | 2010-12-01 | 57460 | 0 | 57460 | 57460 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | LAC | PAR | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 2000-02-01 |  | 2001-07-01 | 2001-12-01 | 66300 | 0 | 66300 | 66300 | 100% | 0 | 0 | 0 | 8619 | 0 | 8619 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PER | SEV | 29 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2002-06-01 | 2011-03-01 | 102700 | -30102 | 72598 | 72598 | 100% | 0 | 0 | 0 | 13351 | -3913 | 9437.74 | 0.26 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | PER | SEV | 17 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1998-10-01 |  | 2000-08-01 | 2001-08-01 | 154000 | 0 | 154000 | 154000 | 100% | 0 | 0 | 0 | 20020 | 0 | 20020 | 0 | 0 | Project financially completed. ($1,488 plus $ 193 PSC returned ExCom 41) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Creation of an Ozone Unit | Individual | ASP | PNG | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1999-05-01 |  | 2003-12-01 | 2009-10-01 | 45800 | -24715 | 21085 | 21085 | 100% | 0 | 0 | 0 | 5954 | -3212.95 | 2741.05 | 0 | 0 | Project financially completed. ($ 25,378 plus $ 3,299 returned ExCom 46) |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | PRC | SEV | 32 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 41950 | 0 | 41950 | 41950 | 100% | 0 | 0 | 0 | 5454 | 0 | 5454 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | PRC | SEV | 39 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2005-12-01 | 54531 | 0 | 54531 | 54531 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extensionl of the institutional strengthening project (phase IV) | Individual | AFR | PRC | SEV | 45 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-04-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 35,000 plus $ 4,550 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | PRC | SEV | 51 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | PRC | SEV | 57 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | PRC | SEV | 17 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 2000-12-01 | 2001-12-01 | 62920 | 0 | 62920 | 62920 | 100% | 0 | 0 | 0 | 8180 | 0 | 8180 | 0 | 0 | Project financially completed |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2003-04-01 |  | 2005-01-01 | 2007-03-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | RWA | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2010-12-01 | 60000 | -3852.45 | 56147.55 | 56148 | 100% | -0.45 | 0 | -0.45 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9,474 plus $ 1,232 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | RWA | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-03-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU completed implementation of TPMP activities including training of customs officers and refrigeration technicians. The NOU drafted HPMP for submission to Ex-com for approval. The country conducted several awareness activities and produced awareness materials such as stickers, caps, calendars and leaflets. The NOU conducted schools competition and the winners were announced during the Ozone Day Celebration. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 41 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2007-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 64600 | 0 | 64600 | 64600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 2) | Individual | ASP | SAM | SEV | 39 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2005-04-01 |  | 2006-01-01 | 2009-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Ozone Committee | Individual | ASP | SAM | SEV | 22 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-04-01 | 2000-06-01 |  | 2003-04-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SAM | SEV | 47 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | SAM | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | SAM | SEV | 58 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-10-01 |  | 2011-12-01 | 2011-12-01 | 35000 | 25000 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | SEN | SEV | 23 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-02-01 | 2000-02-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 | 0 | 15210 | 0 | 15210 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | SEN | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-12-01 |  | 2001-12-01 | 2003-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 | 0 | 15210 | 0 | 15210 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening projects (Phase IV) | Individual | AFR | SEN | SEV | 36 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 5 | Individual | AFR | SEN | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | SEN | SEV | 47 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | SEN | SEV | 53 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | SEN | SEV | 59 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 82388 | 69713 | 152101 | 152101 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Ozone Focal Point | Individual | AFR | SEN | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1996-11-01 |  | 1997-12-01 | 1999-09-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22750 | 0 | 22750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEY | SEV | 31 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2002-08-01 |  | 2004-12-01 | 2005-12-01 | 21267 | 0 | 21267 | 21267 | 100% | 0 | 0 | 0 | 2765 | 0 | 2765 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | SEY | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-03-01 | 1997-07-01 |  | 2000-07-01 | 2000-07-01 | 31900 | 0 | 31900 | 31900 | 100% | 0 | 0 | 0 | 4147 | 0 | 4147 | 0 | 0 | Project financially completed |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SEY | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SEY | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-07-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 7,000 plus $ 910 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II, one year) | Individual | AFR | SIL | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2007-01-01 | 2008-12-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II, 2nd year) | Individual | AFR | SIL | SEV | 51 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (phase I) | Individual | AFR | SIL | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SIL | SEV | 54 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | SOI | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-12-01 |  | 2008-12-01 | 2010-12-01 | 6833 | 0 | 6833 | 6833 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | SOI | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | SOI | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | SOI | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SOM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2008-12-01 | 2009-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Ozone Committee (institutional strengthening) | Individual | AFR | SOM | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2005-12-01 |  | 2010-07-01 | 2011-07-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening (first phase) | Individual | AFR | SOM | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-02-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 30000 | 60000 | 59995 | 99.99% | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STK | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-08-01 | 2005-04-01 |  | 2007-08-01 | 2008-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | LAC | STK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 2000-02-01 |  | 2006-09-01 | 2007-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | STK | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | STL | SEV | 30 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2002-04-01 |  | 2002-06-01 | 2003-07-01 | 24400 | 0 | 24400 | 24400 | 100% | 0 | 0 | 0 | 3172 | 0 | 3172 | 0 | 0 | Project financially completed. ($ 8 plus $ 1 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | LAC | STL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-10-01 | 2006-07-01 |  | 2007-04-01 | 2009-09-01 | 31200 | -400 | 30800 | 30800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | STL | SEV | 37 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-06-01 | 2005-12-01 | 31200 | 0 | 31200 | 31200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of an Ozone Cell | Individual | LAC | STL | SEV | 21 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 2000-02-01 |  | 2000-08-01 | 2001-08-01 | 36580 | 0 | 36580 | 36580 | 100% | 0 | 0 | 0 | 4755 | 0 | 4755 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | STL | SEV | 49 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | LAC | STL | SEV | 55 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | STP | SEV | 38 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | STP | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2006-06-01 | 2008-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | STP | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-12-01 |  | 2011-02-01 | 2012-06-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 42 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-03-01 | 2005-04-01 |  | 2005-03-01 | 2005-12-01 | 13130 | 0 | 13130 | 13130 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV, additional funding) | Individual | LAC | STV | SEV | 62 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2011-08-01 |  | 2011-12-01 | 2012-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2008-03-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Creation of the National Ozone Unit | Individual | LAC | STV | SEV | 25 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-06-01 |  | 2004-03-01 | 2005-12-01 | 30300 | 0 | 30300 | 30300 | 100% | 0 | 0 | 0 | 3939 | 0 | 3939 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | STV | SEV | 58 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | STV | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2008-11-01 |  | 2010-01-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening: phase V | Individual | AFR | SUD | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-04-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 109395 | 0 | 109395 | 109395 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | SUD | SEV | 28 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-12-01 | 2001-12-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 | 0 | 14586 | 0 | 14586 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | SUD | SEV | 34 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 | 0 | 14586 | 0 | 14586 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening: phase IV | Individual | AFR | SUD | SEV | 42 | INS | 16 | A | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-04-01 | 2009-06-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 145860 | 0 | 145860 | 145860 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | SUD | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1997-03-01 |  | 1999-07-01 | 1999-12-01 | 168300 | 0 | 168300 | 168300 | 100% | 0 | 0 | 0 | 21879 | 0 | 21879 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | SUR | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2010-04-01 | 2011-04-01 | 73333 | 0 | 73333 | 73333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening and capacity building: establishment of the Ozone Unit | Individual | LAC | SUR | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2009-06-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | SWA | SEV | 41 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2007-12-01 | 2009-10-01 | 58344 | 0 | 58344 | 58344 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9,096 plus $ 1,182 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | SWA | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1998-12-01 |  | 2003-12-01 | 2007-02-01 | 67320 | 0 | 67320 | 67320 | 100% | 0 | 0 | 0 | 8752 | 0 | 8752 | 0 | 0 | Project financially completed. |  |  | 1998-03-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-04-01 |  | 2010-07-01 | 2011-07-01 | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (phase I) | Individual | EUR | TKM | SEV | 46 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-10-01 | 2008-07-01 |  | 2008-02-01 | 2010-12-01 | 115693 | 0 | 115693 | 115693 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 1,003 plus $ 131 PSC returned to ExCom 57 & 58) |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | TLS | SEV | 56 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-11-01 |  | 2010-11-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening project (phase II, year 1) | Individual | ASP | TLS | SEV | 61 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2011-12-01 |  | 2011-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | TOG | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-06-01 | 2010-12-01 |  | 2011-12-01 | 2012-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | TOG | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-09-01 | 2008-11-01 |  | 2009-11-01 | 2010-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | AFR | TOG | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-08-01 | 2007-02-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | TOG | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2006-12-01 |  | 2007-09-01 | 2009-03-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of the National Ozone Office | Individual | AFR | TOG | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-07-01 | 2004-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TON | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-02-01 | 2007-03-01 |  | 2008-12-01 | 2009-01-01 | 6566 | 0 | 6566 | 6566 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TON | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2009-01-01 | 19700 | 0 | 19700 | 19700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TON | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-03-01 | 2008-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TON | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TTR | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-12-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TTR | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TTR | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TTR | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase II) | Individual | ASP | TUV | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 7583 | 0 | 7583 | 7583 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TUV | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase II) | Individual | ASP | TUV | SEV | 56 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | URT | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 7,000 plus $ 910 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | URT | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | URT | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | URT | SEV | 20 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1999-10-01 |  | 2004-12-01 | 2007-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. ($ 2,831 plus $ 368 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | VAN | SEV | 54 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-02-01 | 2009-03-01 |  | 2011-01-01 | 2011-06-01 | 6750 | 0 | 6750 | 6750 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2008-12-01 | 2009-11-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 40,959 plus $ 5,325 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | VAN | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11898 | 0 | 11898 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | ASP | VIE | SEV | 33 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11898 | 0 | 11898 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | A | I | CFC | 9.8 | 10.2 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2005-07-01 | 2007-12-01 | 118976 | -20 | 118956 | 118956 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | VIE | SEV | 52 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-06-01 |  | 2009-06-01 | 2009-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | VIE | SEV | 57 | INS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-06-01 |  | 2011-06-01 | 2011-11-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 | 0 | 0 | 17846 | 0 | 17846 | 0 | 0 | Project financially completed. ($ 20 plus returned to ExCom 50) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV-supplementary request) | Individual | ASP | YEM | SEV | 48 | INS | 25 | A | I | CFC | 5.4 | 0 | 0 | 0 | 2006-04-01 | 2006-06-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | YEM | SEV | 41 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 104000 | -391 | 103609 | 103609 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 9,259 plus $ 1,204 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 | 0 | 0 | 15340 | 0 | 15340 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | YEM | SEV | 53 | INS | 27 | A | I | CFC | 14 | 14 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 170000 | -392 | 169608 | 169608 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 | 2008-12-01 | 50400 | 0 | 50400 | 50400 | 100% | 0 | 0 | 0 | 6552 | 0 | 6552 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 |  | 2009-03-01 | 2011-03-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 09 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 | 0 | 0 | 9828 | 0 | 9828 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824 | 0 | 14824 | 0 | 0 | Project Financially completed |  |  | 2001-06-01 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824 | 0 | 14824 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-11-01 | 2009-06-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Financially completed |  |  |  | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | ZIM | SEV | 50 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-06-01 | 2008-11-01 |  | 2011-07-01 | 2011-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 | 0 | 0 | 22237 | 0 | 22237 | 0 | 0 | Project Financially completed |  |  | 1999-05-01 | Non Investment
FIN | UNIDO | Institutional strengthening (phase I) | Individual | EUR | ARM | SEV | 57 | INS | 05 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 |  | 2010-12-01 | 2012-12-01 | 120000 | 0 | 120000 | 118811.98 | 99.01% | 1188.02 | 0 | 1 | 9000 | 0 | 8911 | 89 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Establishment of an Ozone Unit | Individual | EUR | BHE | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2001-05-01 | 2002-04-01 |  | 2004-12-01 | 2005-12-01 | 110000 | -5291 | 104709 | 104708.57 | 100% | 0.43 | 0 |  | 14300 | -709 | 13591 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase IV) | Individual | AFR | EGY | SEV | 34 | INS | 83 | N | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-12-01 | 175000 | -8670 | 166330 | 166330.22 | 100% | -0.22 | 0 |  | 22750 | -1161 | 21589 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase III: Institutional Strengthening Project for the Montreal Protocol Related Activities | Individual | AFR | EGY | SEV | 27 | INS | 73 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 2001-04-01 |  | 2001-11-01 | 2002-05-01 | 175000 | 0 | 175000 | 175000.46 | 100% | -0.46 | 0 |  | 22750 | -1 | 22749 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening project for the Montreal Protocol related activities (Phase II) | Individual | AFR | EGY | SEV | 21 | INS | 61 | N | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1999-02-01 |  | 1998-12-01 | 1999-09-01 | 43900 | 132009 | 175909 | 175909 | 100% | 0 | 0 |  | 5707 | 17125 | 22832 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project | Individual | AFR | EGY | SEV | 40 | INS | 87 | N | I |  | 18.9 | 18.9 |  |  | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-08-01 | 228323 | -1 | 228322 | 228322 | 100% | 0 | 0 |  | 17125 | -1 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase VI) | Individual | AFR | EGY | SEV | 51 | INS | 94 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening projects (phase VII) | Individual | AFR | EGY | SEV | 56 | INS | 97 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2011-03-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening unit for the Montreal Protocol related activities | Individual | AFR | EGY | SEV | 10 | INS | 14 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1996-05-01 |  | 1996-12-01 | 2000-07-01 | 263450 | 0 | 263450 | 263450 | 100% | 0 | 0 |  | 34249 | 0 | 34249 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Creation of the National Ozone Unit | Individual | AFR | LIB | SEV | 32 | INS | 04 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2009-06-01 | 2011-12-01 | 157000 | -48043 | 108957 | 108956.98 | 100% | 0.02 | 0 |  | 20410 | -6246 | 14164 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening for Montreal Protocol related activities, Phase II | Individual | EUR | MDN | SEV | 30 | INS | 12 | N | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 101950 | 0 | 101950 | 101949.6 | 100% | 0.4 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MDN | SEV | 35 | INS | 18 | N | I |  | 0 | 0 |  |  | 2001-12-01 | 2002-08-01 | 2004-01-01 |  | 2004-07-01 | 2005-09-01 | 101950 | 0 | 101950 | 101949.96 | 100% | 0.04 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase V) | Individual | EUR | MDN | SEV | 48 | INS | 22 | N | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2008-04-01 |  | 2008-12-01 | 2011-05-01 | 132347 | -1127 | 131220 | 131220.16 | 100% | -0.16 | 0 |  | 9926 | -84 | 9842 | 0 | -1 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MDN | SEV | 57 | INS | 27 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2012-02-01 | 132347 | -43 | 132304 | 132304.06 | 100% | -0.06 | 0 |  | 9926 | -3 | 9923 | 0 | 0 | Financial completion in Feb 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project: phase IV | Individual | EUR | MDN | SEV | 42 | INS | 20 | N | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-05-01 | 132347 | 0 | 132347 | 132347 | 100% | 0 | 0 |  | 9926 | 0 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | MDN | SEV | 20 | INS | 04 | N | I |  | 0 | 0 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-08-01 | 2001-07-01 | 152900 | 0 | 152900 | 152900 | 100% | 0 | 0 |  | 19877 | -25 | 19852 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Renewal of the institutional strengthening project for the phase out of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 37 | INS | 109 | N | I |  | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2002-08-01 |  | 2003-12-01 | 2005-03-01 | 0 | 50040 | 50040 | 50039.54 | 100% | 0.46 | 0 |  | 0 | 6495 | 6495 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase IX) | Individual | LAC | MEX | SEV | 58 | INS | 147 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2012-12-01 | 185250 | 0 | 185250 | 184969.2 | 99.85% | 280.8 | 0 | 1 | 13894 | 0 | 13873 | 21 | 0 | Financial completion in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | MEX | SEV | 37 | INS | 110 | N | I | CFC | 20.4 | 20.4 |  |  | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2005-03-01 | 2006-05-01 | 247000 | -4309 | 242691 | 242690.6 | 100% | 0.4 | 0 |  | 32110 | -610 | 31500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase VIII) | Individual | LAC | MEX | SEV | 52 | INS | 132 | N | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2009-07-31 |  | 2009-06-01 | 2011-12-01 | 247000 | -1203 | 245797 | 245797.09 | 100% | -0.09 | 0 |  | 18525 | -90 | 18435 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase VII | Individual | LAC | MEX | SEV | 45 | INS | 125 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-08-01 | 2008-08-01 | 247000 | 0 | 247000 | 247000 | 100% | 0 | 0 |  | 18525 | 0 | 18525 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Establishment of the ozone unit | Individual | EUR | MOG | SEV | 51 | INS | 02 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-09-01 | 30000 | -8112 | 21888 | 21888.39 | 100% | -0.39 | 0 |  | 2250 | -608 | 1642 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase III) | Individual | ASP | OMA | SEV | 56 | INS | 18 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2011-02-01 | 2010-11-30 |  | 2011-11-01 | 2012-11-01 | 68467 | 0 | 68467 | 68467 | 100% | 0 | 0 |  | 5135 | 0 | 5135 | 0 | 0 | Financial completion in Nov 2012. |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase II) | Individual | ASP | OMA | SEV | 46 | INS | 14 | N | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-03-01 | 2007-07-01 |  | 2007-12-01 | 2009-09-01 | 68467 | -73 | 68394 | 68394.4 | 100% | -0.4 | 0 |  | 5135 | -5 | 5130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional Strengthening/Support to the National Ozone Unit in Oman | Individual | ASP | OMA | SEV | 32 | INS | 02 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2005-12-01 | 2006-02-01 | 79000 | 0 | 79000 | 78999.73 | 100% | 0.27 | 0 |  | 10270 | -1 | 10269 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase II, second year funding) | Individual | ASP | QAT | SEV | 49 | INS | 08 | N | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-01-01 | 2007-07-01 |  | 2009-06-01 | 2012-12-01 | 44500 | 0 | 44500 | 42780.98 | 96.14% | 1719.02 | 0 | 1 | 3338 | 0 | 3209 | 129 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase 2 | Individual | ASP | QAT | SEV | 41 | INS | 06 | N | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2006-09-01 | 2008-05-01 | 44500 | -1215 | 43285 | 43284.99 | 100% | 0.01 | 0 |  | 3338 | -92 | 3246 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional Strengthening Project: Creation of the National Ozone Unit | Individual | ASP | QAT | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-11-01 | 2002-04-01 |  | 2004-10-01 | 2005-12-01 | 68450 | -4279 | 64171 | 64170.89 | 100% | 0.11 | 0 |  | 8899 | -570 | 8329 | 0 | 0 | FIN |  |  | 2002-04-01 | NON-INV
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | ROM | SEV | 17 | INS | 04 | N | I |  | 0 | 0 |  |  | 1995-07-01 | 1997-12-01 | 1998-07-01 |  | 2003-12-01 | 2005-01-01 | 168443 | -80350 | 88093 | 88092.81 | 100% | 0.19 | 0 |  | 21898 | -10464 | 11434 | 0 | 0 | FIN |  |  | 2000-01-01 | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase II | Individual | EUR | ROM | SEV | 45 | INS | 29 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-05-01 | 145984 | -981 | 145003 | 145003.27 | 100% | -0.27 | 0 |  | 10949 | -74 | 10875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening (Phase II) | Individual | ASP | SYR | SEV | 33 | INS | 75 | N | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-12-01 | 2003-04-01 |  | 2006-12-01 | 2009-09-01 | 195000 | -3117 | 191883 | 191882.56 | 100% | 0.44 | 0 |  | 25350 | -405 | 24945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Support to strengthening the General Commission for Environmental Affairs to implement Montreal Protocol related activities | Individual | ASP | SYR | SEV | 10 | INS | 03 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 2002-11-01 | 2003-06-01 | 235180 | -15273 | 219907 | 219907.1 | 100% | -0.1 | 0 |  | 30573 | -2030 | 28543 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-11-01 | 2009-03-31 |  | 2010-12-01 | 2012-02-01 | 15000 | -62 | 14938 | 14938.25 | 100% | -0.25 | 0 |  | 1125 | -5 | 1120 | 0 | 0 | Financial completion in Feb 2012. Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-07-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 131300 | -7175 | 124125 | 124124.73 | 100% | 0.27 | 0 |  | 9848 | -539 | 9309 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Creation of Ozone Secretariat | Individual | EUR | YUG | SEV | 25 | INS | 07 | N | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | 0 | 151500 | 151500.04 | 100% | -0.04 | 0 |  | 19695 | -5 | 19690 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | Institutional strengthening |  | LAC | MEX | SEV | 07 | INS | 16 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 285000 | 65000 | 350000 | 350000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. US $65,000 against 1994 contributions (15th meeting)
ONG | IBRD | Extension of institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | JOR | SEV | 68 | INS | 92 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-31 | 2014-12-31 |  |  | 147333 | 0 | 147333 | 0 | 0% | 147333 | 147333 | 66300 | 10313 | 0 | 0 | 10313 | 10313 | Phase X of the Jordan Institutional Strengthening Project newly approved 7 Dec. 12. | Ozone program management and implementation and enforcement of the quota system ongoing. NOU actively participated in discussions on new umbrella grant agreement implementation arrangements, particularly in regards to the IS component. |  |  | Non-INV
ONG | IBRD | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | THA | SEV | 68 | INS | 159 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-31 | 2014-12-31 |  |  | 346668 | 0 | 346668 | 0 | 0% | 346668 | 346668 | 100000 | 24267 | 0 | 0 | 24267 | 24267 | Phase VII of the IS project newly approved in Dec. 12. |  |  |  | Non-INV
ONG | UNDP | Extension for institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | ARG | SEV | 65 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 | 2014-03-01 |  |  | 311567 | 0 | 311567 | 37967.66 | 12.19% | 273599.34 | 0 | 109439.736 | 23368 | 0 | 2847.6324 | 20520.3676 | 0 | Project Document signed. National Ozone Unit is monitoring complete phase-out of CFC and preparing for HCFC phase-out. Country in compliance with reporting and consumption obligations. | Review of imports of HCFCs in 2012 and preparation of reports to the OS. Follow up on existing MP funded projects in Argentina. Approval of import licenses of HCFCs. | 2011 |  | Non-investment
ONG | UNDP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | BGD | SEV | 61 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2012-06-01 | 2013-06-01 |  |  | 130000 | 0 | 130000 | 58196.53 | 44.77% | 71803.47 | 0 | 21541.041 | 9750 | 0 | 4364.7397 | 5385.2603 | 0 | During the year 2012, the Government continued implementation of national regulations including licensing of imports of ODSs and development of regulations for monitoring and controlling HCFCs. The Government also undertook awareness activities on the occasion of 25th Anniversary of Montreal Protocol. Most of the project activities under CFC MDI phaseout projects were completed by HY1 of the year 2012. HPMP project implementation was also monitored during the year. The NOU staff participated in the regional and global meetings relating to Montreal Protocol. Article 7 and CP progress report for the year 2011 were submitted in the year 2012. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BRA | SEV | 60 | INS | 294 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2011-12-01 | 2013-05-01 |  |  | 307125 | 0 | 307125 | 162361.22 | 52.86% | 144763.78 | 0 | 43429.134 | 23034 | 0 | 12176.8933 | 10857.1067 | 0 | IS activities ongoing. IS Phase-VII Final Report being prepared along with request for IS Phase-IX | IS Phase-VII final report and IS Phase-IX request submitted to the 66th Executive Committee Meeting. | 2010 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | BRA | SEV | 66 | INS | 297 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2013-12-01 | 2014-03-01 |  |  | 351000 | 0 | 351000 | 0 | 0% | 351000 | 0 | 140400 | 26325 | 0 | 0 | 26325 | 0 | The UNDP project document has been developed and finalized. | The UNDP project document is in the process of being signed by the National counterparts in Brazil. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | LAC | CHI | SEV | 63 | INS | 176 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 | 2013-03-01 |  |  | 186550 | 0 | 186550 | 114795.14 | 61.54% | 71754.86 | 0 | 21526.458 | 13991 | 0 | 8609.4817 | 5381.5183 | 0 | Follow up on the implementation of MP funded projects. Active public awareness campaign in Chile including the celebration of National Ozone Day. Establishment of quota system for HCFCs. | Approval of import licenses for HCFCs. Follow up on implementation of existing MLF funded projects. | 2011 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VIII: 11/2011-10/2013) | Individual | LAC | COL | SEV | 64 | INS | 79 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-10-01 | 2013-10-01 |  |  | 275600 | 0 | 275600 | 98190.78 | 35.63% | 177409.22 | 0 | 53222.766 | 20670 | 0 | 7364.3085 | 13305.6915 | 0 | The NOU plays an active role in the implementation of MLF funded projects in Colombia. The NOU established the qoutas for HCFCs for 2013 and legistlation supporting HCFC phase out was approved. | Celebration of successful completion of domestic Refrigeration programme. Active public awareness campaign. Control of imports of HCFCs and equipment. | 2011 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | COS | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-12-01 | 2014-01-01 |  |  | 140513 | 0 | 140513 | 36213.52 | 25.77% | 104299.48 | 0 | 41719.792 | 10538 | 0 | 2715.8916 | 7822.1084 | 0 | Project document signed. HCFC quota system in place. Active public awareness campaign and celebration of Ozone Day. | Implementation of standard IS activities. Agreed quotas for 2013 discussed with importers. Follow up on the implementation of existing projects. | 2011 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | ASP | CPR | SEV | 62 | INS | 504 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 | 2013-06-01 |  |  | 390000 | 0 | 390000 | 375140.19 | 96.19% | 14859.81 | 0 | 4457.943 | 29250 | 0 | 28135.5143 | 1114.4858 | 0 | Monitoring of ongoing ODS phaseout projects continued. Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for 2011 was reported in timely manner. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | CPR | SEV | 68 | INS | 523 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2015-03-01 | 2015-03-01 |  |  | 390000 | 0 | 390000 | 0 | 0% | 390000 | 0 | 156000 | 27300 | 0 | 0 | 27300 | 0 | Newly approved. | Prodoc is being finalised. | 2012 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | LAC | CUB | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 | 2014-01-01 |  |  | 149066 | 0 | 149066 | 32616.53 | 21.88% | 116449.47 | 0 | 46579.788 | 11180 | 0 | 2446.2507 | 8733.7493 | 0 | Project Document was signed in 2012. Standard IS activities are being implemented. | The NOU continues its strong support of the implementation of MLF funded projects in Cuba. There is an active Public Awareness campaign in Cuba. | 2011 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | EUR | GEO | SEV | 63 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-06-01 | 2013-06-01 |  |  | 60667 | 0 | 60667 | 20377.93 | 33.59% | 40289.07 | 0 | 12086.721 | 4550 | 0 | 1528.3364 | 3021.6636 | 0 | The project document was signed between UNDP and Government. National consultants recruited for collection/processing data on ODSs consumption. International Ozone Day celebrated by developing and sending out e-cards and electronic leaflets; and a banner dedicated to the 25th anniversary celebrations was placed at central street in Tbilisi (capital city). Logistical requirements to arrange an international conference on ozone layer issues for university students defined. 2011 progress report on country program implementation was opportunely submitted to the Secretariat of the MLF. The project is on track after a delayed start. | On a daily basis, the IS project has been managed by the Project Management Unit and all ozone-related activities that are currently underway in Georgia have been coordinated as well. Update of the website of the National Ozone Unite is nearing completion. | 2011 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | GHA | SEV | 67 | INS | 36 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 139100 | 0 | 139100 | 0 | 0% | 139100 | 0 | 55640 | 9737 | 0 | 0 | 9737 | 0 | Newly approved. DOA package to start the project sent in October 2012. Project documentation signed with the Government in December 2012. | Activities under Phase 9 were fully completed so that Phase 10 would be initiated by January 2013. Workplan for 2013 prepared. Funds allocated. Planned activities ongoing. | 2012 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | IDS | SEV | 65 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2013-12-01 | 2013-12-01 |  |  | 271246 | 0 | 271246 | 64812.33 | 23.89% | 206433.67 | 0 | 61930.101 | 20343 | 0 | 4860.8172 | 15482.1828 | 0 | Prodoc signed. Activities progressing as planned. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (remaining balance for phase VIII) | Individual | ASP | IND | SEV | 65 | INS | 439 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-03-01 | 2013-03-01 |  |  | 46654 | 0 | 46654 | 10299.82 | 22.08% | 36354.18 | 0 | 10906.254 | 3499 | 0 | 772.4755 | 2726.5245 | 0 | During 2012, remaining activities under the Phase VIII primarily relating to ongoing implementation of licensing system and project monitoring were undertaken satisfactorily. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 4/2012-3/2014) | Individual | ASP | IND | SEV | 66 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-03-01 | 2014-03-01 |  |  | 373230 | 0 | 373230 | 0 | 0% | 373230 | 0 | 149292 | 27992 | 0 | 0 | 27992 | 0 | During 2012, monitoring of ongoing ODS phaseout projects and HPMP initiation activities were undertaken. HPMP document was approved in the 66th Excom. Awareness activities including celebrations on the occasion of 25th Anniversary of Montreal Protocol w | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | IRA | SEV | 61 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 | 2013-03-01 |  |  | 173511 | 0 | 173511 | 163496.11 | 94.23% | 10014.89 | 0 | 3004.467 | 13013 | 0 | 12261.902 | 751.098 | 0 | In 2012, monitoring of ongoing ODS phaseout projects and HPMP preparation activities were undertaken. HPMP project activities were monitored closely with support from PMU. HPMP second tranche request was submitted and approved by the Excom in its 68th Me | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | IRA | SEV | 67 | INS | 206 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 173511 | 0 | 173511 | 0 | 0% | 173511 | 0 | 69404.4 | 12146 | 0 | 0 | 12146 | 0 | Newly approved in 2012. Activities are expected to be initiated in the second quarter of 2013. | Activities to be initiated in Q2 of 2013. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | LEB | SEV | 62 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-03-01 | 2013-03-01 |  |  | 155090 | 0 | 155090 | 87869.89 | 56.66% | 67220.11 | 0 | 20166.033 | 11632 | 0 | 6590.3834 | 5041.6166 | 0 | Monitoring of ongoing ODS phaseout projects. Awareness activities including National Ozone Day celebrations. CP progress and Article 7 data for 2011 was reported in timely manner. Controls on ODSs through licensing system were implemented. NOU participat | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 4/2013-3/2015) | Individual | ASP | LEB | SEV | 68 | INS | 77 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2015-03-01 | 2015-03-01 |  |  | 155090 | 0 | 155090 | 0 | 0% | 155090 | 0 | 62036 | 10856 | 0 | 0 | 10856 | 0 | Newly approved. | Prodoc is being finalised. | 2012 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | ASP | MAL | SEV | 64 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 | 2013-12-01 |  |  | 279500 | 0 | 279500 | 99218.03 | 35.5% | 180281.97 | 0 | 54084.591 | 20963 | 0 | 7441.5297 | 13521.4703 | 0 | Activities progressed as planned in continuation with the Phase-VIII implementation. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2011 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | NIR | SEV | 62 | INS | 130 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-11-01 | 2013-03-01 |  |  | 260000 | 0 | 260000 | 194031.54 | 74.63% | 65968.46 | 0 | 19790.538 | 19500 | 0 | 14552.3655 | 4947.6345 | 0 | Activities completed in 2012, only some pending payments remaining. The NOO is operational and following up on ongoing project as well as its requirements under the Montreal Protocol, including the implementation of the ongoing HPMP. Activities completed in 2012 and Phase 7 approved at 69th ExCom in December 2012. The country organised celebration of the 25th anniversary of the MP. | Activities completed in 2012, only some pending payments remaining. Final disbursements made for national experts, local monitoring missions, public awareness raising, publications. | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | AFR | NIR | SEV | 68 | INS | 134 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 260000 | 0 | 260000 | 0 | 0% | 260000 | 0 | 104000 | 18200 | 0 | 0 | 18200 | 0 | Newly approved. | Delegation of Authority issued, implementation will be initiated shortly, with the Project Document revision. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | PAK | SEV | 62 | INS | 81 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2013-03-01 | 2013-04-01 |  |  | 224467 | 0 | 224467 | 189840.43 | 84.57% | 34626.57 | 0 | 10387.971 | 16835 | 0 | 14238.0111 | 2596.9889 | 0 | During the year 2012, IS project primarily focused on monitoring ODS consumption in country and managing ongoing implementation of CFC MDI phaseout project and HPMP. Celebrations commemorating 20th Anniversary of Montreal Protocol were also undertaken during the year. The Government continued to closely monitor licensing system and import controls of ODSs particularly HCFCs and CFCs for MDI manufacturing. NOU also participated in regional network meetings and global meetings relating to Montreal Protocol. IS for phase VII was approved in 68th meeting of the Executive Committee. CP progress report and Article 7 data report for 2011 were submitted by NOU. | Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | ASP | PAK | SEV | 68 | INS | 82 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2015-03-01 | 2015-03-01 |  |  | 224467 | 0 | 224467 | 0 | 0% | 224467 | 0 | 89786.8 | 15713 | 0 | 0 | 15713 | 0 | Newly approved. | Prodoc is being finalised. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | SRL | SEV | 67 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 134056 | 0 | 134056 | 0 | 0% | 134056 | 0 | 53622.4 | 9384 | 0 | 0 | 9384 | 0 | Project work plan under finalization, which is expected to occur in 2013. | Project work plan has been finalised in Feb 2013 and activities as per work plan are in progress. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | TRI | SEV | 59 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-10-01 | 2011-12-01 | 2013-06-01 |  |  | 30000 | 30000 | 60000 | 10713.24 | 17.86% | 49286.76 | 0 | 14786.028 | 2250 | 2250 | 803.493 | 3696.507 | 0 | Project document was signed in 2012. Standard IS activities are being implemented. Several pending payments in the process of being processed in UNDPs financial system. | NOU is implementing the activities through active support in the HPMP implementation. | 2009 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | TRI | SEV | 68 | INS | 29 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 4200 | 0 | 0 | 4200 | 0 | Newly approved. | Project Document signed and activities being implemented by the NOU. | 2012 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | URU | SEV | 65 | INS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-02-01 | 2013-12-01 | 2014-02-01 |  |  | 150800 | 0 | 150800 | 32103.87 | 21.29% | 118696.13 | 0 | 47478.452 | 11310 | 0 | 2407.7903 | 8902.2097 | 0 | UNDP project document was signed in 2012. HCFC quota system was established. Standard IS activities were implemented in Uruguay. | ODS import licenses given to importers. Public awareness activities continue. | 2011 |  | Non-investment
ONG | UNDP | Renewal of institutional strengthening project (phase X) | Individual | LAC | VEN | SEV | 62 | INS | 117 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 | 2013-03-01 |  |  | 285480 | 0 | 285480 | 256901.13 | 89.99% | 28578.87 | 0 | 8573.661 | 21411 | 0 | 19267.5848 | 2143.4153 | 0 | Venezuela has an active NOU that supports the implementation of the MLF funded portfolio in Venezuela. Standard IS activities are being implemented. | All funds from current phase have been disbursed and project is expected to be completed in 2013. | 2010 |  | Non-Investment
ONG | UNDP | Renewal of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | VEN | SEV | 68 | INS | 122 | N | I | HCFC | 0 |  | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 285480 | 0 | 285480 | 0 | 0% | 285480 | 0 | 114192 | 19984 | 0 | 0 | 19984 | 0 | Newly approved. | UNDP Project Document has been signed. | 2012 |  | Non-investment
ONG | UNEP | Extension of institutional strengthening project (phase V: 12/2011-11/2013) | Individual | ASP | AFG | SEV | 64 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-11-01 | 2013-12-01 |  |  | 150000 | 0 | 150000 | 81317 | 54.21% | 68683 | 0 | 68683 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: Regular mission with a delegation from ozone office including Ozone Officer and Project Management Unit Coordinator went to Herat Province. A half day public awareness workshop carried out for the staff of the National Environmental Protection Agency (NEPA) on 25th of December 2011. The purpose of this workshop was to familiar the NEPA staff with new phase of ozone unit plans and activities. A total of 35 NEPA staff participated which were the target audience of the workshop. The NOU has participated in three days exhibition held from 7th May to 9th May 2012 in Afghan- Korea Vocational Training Center. Participation to the Joint Meeting of the Regional Ozone Network for South and Southeast Asia and Pacific 15 – 17 May 2012 and Regional Workshop for Enhancing Institutional Capacity for Climate and Energy Use (CEU) Benefit of HPMP 17- 18 May 2012. NOU also have carried out some public awareness activities. Based on request from Police academy through the public awareness division of NEPA, NOU has prepared a chapter about the ozone (in our local language) with the technical assistant from one of University lecturer to be thought at the police academy. During this period NOU has also updated some of its current public awareness materials. | The renewal is being prepared for submission to the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | EUR | ALB | SEV | 66 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-06-01 | 2014-06-01 |  |  | 109200 | 0 | 109200 | 0 | 0% | 109200 | 90208 | 109200 | 0 | 0 | 0 | 0 | 0 | The project was approved by ExCom in April of 2012. The SSFA was signed and the first payment released. The NOPIU initiated activities agreed in the work programme under the renewed IS project. | The country continues the development of supportive legislative measures to control HCFCs consumption. The data collection for HCFCs consumption in 2012 is ongoing. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ALG | SEV | 57 | INS | 69 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 | 2013-07-01 |  |  | 257400 | 0 | 257400 | 128700 | 50% | 128700 | 0 | 128700 | 0 | 0 | 0 | 0 | 0 | The government is in the process of recruiting new Ozone Unit and joint mission of CAP/UNIDO planned to take place soon to train the new ozone staff team | Implementation of activities delayed due to the absence of NOU. The Agreement is not yet signed. The signed agreement has to be submitted together with reports of the previous IS Phase and in the absence of the Ozone Officer, the country is not able to prepare the reports. The Government is in the process of finalizing the recruitment process following the normal Government process . |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | ANG | SEV | 63 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 | 2013-03-01 |  |  | 134400 | 0 | 134400 | 74400 | 55.36% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | In 2012, the NOU conducted several awareness program, trained about 100 customs and other law enforcement officers for successful phase out of HCFC. The NOU also conducted trainings for 70 farmers on MB alternative technologies. 2012 Customs Tariff was approved and listed on Article 110. The NOU celebrated the Ozone day, distributed awareness materials and organized several competitions. The NOU submitted 2011 A7 data and CP report and participated in all network meetings and OEWG/MOP meetings. There was no delay in submission of IS reports and disbursement of payments. | The NOU prepared and submitted IS renewal request to ExCom 69. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | ANT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project approved in December 2012. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | BAH | SEV | 68 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | ISP new cycle approved at ExCom 68 | New cycle agreement under process with Country and payment will be processed accordingly |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BAR | SEV | 61 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-06-01 | 2013-03-01 |  |  | 117000 | 0 | 117000 | 114240 | 97.64% | 2760 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | Second and third disbursements released. 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU took the lead of HPMP preparation. CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase V. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. Audited final financial report to be endorsed by Permanent Secretary. (a) To review and update ODS legislation; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | BAR | SEV | 68 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-02-01 | 2015-02-01 |  |  | 117000 | 0 | 117000 | 0 | 0% | 117000 | 0 | 117000 | 0 | 0 | 0 | 0 | 0 | Project recently approved (Dec. 2012). | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | BDI | SEV | 57 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-12-01 | 2011-03-01 | 2013-03-01 |  |  | 60000 | 0 | 60000 | 19000 | 31.67% | 41000 | 0 | 41000 | 0 | 0 | 0 | 0 | 0 | The SSFA has since expired but was revised and sent to country for signature. The country has signed awaiting disbursement. | The NOU continues to collect and compile A7 data for 2012. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | AFR | BEN | SEV | 62 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-04-01 | 2012-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | SSFA was sent for signing in January 2012. Delay caused by delay in completion of previous phase leading to confusion in reporting of disbursement. 1st disbursement was made in July 2012. | The NOU continues to collect and compile A7 data for 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BHA | SEV | 61 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2012-06-01 | 2013-07-01 |  |  | 60000 | 0 | 60000 | 27886 | 46.48% | 32114 | 64 | 32114 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO and Assistant attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU was in charge of launching and monitoring HPMP project. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) To review and update ODS legislation (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | BHU | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-11-01 | 2013-04-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is in normal operation with full staff. All planned activities under HPMP project are being implemented on time wherein the 2nd tranche request will be submitted to the 70th ExCom. | The focus of the NOU remain to be in HPMP implementation project wherein the 2nd tranche request will be submitted to the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | BKF | SEV | 68 | INS | 32 | A | I |  | 0 |  | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 72410 | 0 | 72410 | 0 | 0% | 72410 | 0 | 72410 | 0 | 0 | 0 | 0 | 0 | SSFA has been drafted and sent to country for signature |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 8/2012-7/2014) | Individual | LAC | BOL | SEV | 67 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-11-01 | 2014-07-01 | 2014-07-01 |  |  | 78867 | 0 | 78867 | 31500 | 39.94% | 47367 | 47367 | 47367 | 0 | 0 | 0 | 0 | 0 | SSFA signed and first disbursement released. NOO attended Network Meeting held in Panama (October 2012). NOU organized the International Ozone Day celebration at national level. NOU was in charge of the HPMP implementation. | NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) Draft agreement under consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BOT | SEV | 53 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2011-05-01 | 2009-11-01 | 2013-07-01 |  |  | 78173 | 0 | 78173 | 42087 | 53.84% | 36086 | 36086 | 36086 | 0 | 0 | 0 | 0 | 0 | Country ratified Montreal and Beijing Amendments and followed up on the approval of ODS Regulations. NOU collected 2011 ODS data, celebrated Ozone Day, conducted awareness activities through the radio, tv and produced awareness materials. | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | AFR | BOT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 78173 | 0 | 78173 | 0 | 0% | 78173 | 0 | 78173 | 0 | 0 | 0 | 0 | 0 | Project approved at 68th ExCom in Dec 2012, No progress in 2012 accordingly | SSFA drafted and awaiting the country to establish licensing and quota system before disbursement is made |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase III: 1/2013-12/2014) | Individual | ASP | BRU | SEV | 67 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The draft SSFA has been formulated for country's agreement. Each legal agreement will be reviewed by Ministry of Foreign Affair and Trade, which could be timing consuming, and out of control of the NOU. UNEP just received feedback on the proposed agreement on the proposed general provisions, which CAP needs to go to Nairobi for guidance should the country insist to make any change of the text in the Agreement. Hopefully the agreement for IS could be signed within the second half of 2013. | UNEP is currently in consultation |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | BZE | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-12-01 | 2013-03-01 |  |  | 38350 | 38350 | 76700 | 60800 | 79.27% | 15900 | 0 | 15900 | 0 | 0 | 0 | 0 | 0 | Annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO attended Network Meeting held in Dominica (March 2012). NOU submitted Article 7 data report and Country Programme Report. NOU was in charge of the HPMP implementation. ISP Phase 7 renewal prepared and submitted to the 66 ExCom for approval. All funds released. Audited final financial report submitted to UNEP. | Project completed. (a) To review and update ODS legislation to include HCFCs; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) IS terminal report preparation support; (f) IS renewal request support; (g) IS renewal approval. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | BZE | SEV | 66 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2014-03-01 |  |  | 76700 | 0 | 76700 | 30400 | 39.63% | 46300 | 46300 | 46300 | 0 | 0 | 0 | 0 | 0 | SSFA signed. First disbursement released in August 2012. NOO attended Network Meeting held in Panama (October 2012). NOU organized the International Ozone Day celebration at national level. NOU was in charge of the HPMP implementation. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. Second disbursement released in January 2013. NOO attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | CAF | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2012-03-01 | 2011-03-01 | 2013-03-01 |  |  | 60000 | 0 | 60000 | 22380 | 37.3% | 37620 | 37620 | 37620 | 0 | 0 | 0 | 0 | 0 | Country prepared and sent IS request for renewal, which was approved. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | CAF | SEV | 68 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | SSFA was prepared and sent to country for signature | CAP received information that the NOU had conducted activities and incurred expenses above half of the IS funds available and the NOU was preparing reports to account for the expenditures incurred. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CBI | SEV | 57 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2011-03-01 | 2013-03-01 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 0 | 40500 | 0 | 0 | 0 | 0 | 0 | Country conducted awareness raising activities | Country is hosting French-speaking network |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2012-12/2013) | Individual | AFR | CHD | SEV | 65 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 | 2013-04-01 |  |  | 60000 | 0 | 60000 | 10515 | 17.52% | 49485 | 49485 | 49485 | 0 | 0 | 0 | 0 | 0 | The NOU conducted training of refrigeration technicians and custom officers. The NOU celebrated the Ozone day and conducted quiz competitions. 2011 Article 7 data was collected, compiled and submitted. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | CKI | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: In Mid 2012, the NOO vacated office. In November of 2012, Government appointed public official to oversee the implementation of the Montreal Protocol. New NOO is still to be recruited. With the assigned of the officer, the agreement was approved nationally and now being processed for signature by both UNEP and country. This is expected to be signed on May 2013. | The SSFA was formulated and in consultation with the Government for agreement, expected to sign in April 2013. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | CMR | SEV | 65 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 | 2013-09-01 |  |  | 139532 | 0 | 139532 | 29759 | 21.33% | 109773 | 69890 | 109773 | 0 | 0 | 0 | 0 | 0 | The NOU conducted training on good fumigation with phosphine with more than 60 participants. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | COI | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 | 2013-06-01 |  |  | 60000 | 0 | 60000 | 32550 | 54.25% | 27450 | 0 | 27450 | 0 | 0 | 0 | 0 | 0 | The second payment was made in July 2012. The NOU conducted several awareness raising activities and training of Custom and Refrigeration technicians. |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VII) | Individual | EUR | CRO | SEV | 63 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2013-03-01 |  |  | 87707 | 0 | 87707 | 35150 | 40.08% | 52557 | 52557 | 52557 | 0 | 0 | 0 | 0 | 0 | HCFC quota is introduced according to schedule under ODS and F-gas Regulation. Submit ion of iPIC form on Croatia import/export. Establishment of Croatian Refrigeration and Air-Conditioning and Heat Pumps Association (CRACHA) on 23 April 2012. CRACHA has 50 members, 44 physical and 6 legal entities. Cooperation with Croatian chamber of economy is strengthened. Informing end users of CTC about new technologies. Dissemination of information regarding ban of use of CTC. Participation in European Mobility Week, cooperation with eco schools. | Dissemination of information to RAC stakeholders regarding ODS and F-gas legislation, new technologies, public awareness activities is ongoing. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | DJI | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 | 2013-06-01 |  |  | 60000 | 0 | 60000 | 46500 | 77.5% | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | The NOU hosted the 16th Joint ODSONET for English and French speaking Africa. The NOU compiled and submitted 2011 CP report and A7 data to the Secretariats. NOU attended all the MP meetings. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DMI | SEV | 62 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2012-11-01 | 2013-02-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO co-organized the Caribbean Network Meeting held in Dominica, March 2012. NOO attended Network Meeting held in Panama, October 2012. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU was in charge of the HPMP implementation. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. Due to internal changes within the Environment Coordination Unit (ECU), no expenditure report were received from the NOO. The reports were received in April 2013. Disbursements will resume as planned. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | DOM | SEV | 68 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 134333 | 0 | 134333 | 0 | 0% | 134333 | 0 | 134333 | 0 | 0 | 0 | 0 | 0 | Project recently approved (Dec. 2012). | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | DRC | SEV | 62 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-12-01 | 2013-06-01 |  |  | 64540 | 0 | 64540 | 20829 | 32.27% | 43711 | 0 | 43711 | 0 | 0 | 0 | 0 | 0 | 2012 CP report and A7 data were submitted. The NOU conducted training activities for 20 refrigeration technicians and 25 Custom officers |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phases VI and VII: 1/2010-12/2013) | Individual | ASP | DRK | SEV | 68 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 260000 | 0 | 260000 | 0 | 0% | 260000 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | The SSFA was formulated and in consultation with the Government for agreement. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | ECU | SEV | 59 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-03-01 | 2011-11-01 | 2013-11-01 |  |  | 95767 | 81034 | 176801 | 7320 | 4.14% | 169481 | 0 | 169481 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOU did follow up to the authorization of opening an special account to receive project funds, but the process could not be completed in 2012. This is the reason why UNEP processed direct payments to suppliers. NOO attended Network Meeting held in Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU was in charge of the NPP/HPMP coordination. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. Beijing amendment ratification completed in February 2013. Authorization to opening the special account was given in March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. The low disbursement was due to lengthy procedure to open a special banking account at the Government level to enable funds transfer to the NOU. As an emergency solution, UNEP made several direct payments to suppliers based on the Government's requests. The special banking account is expected to be operational by July 2013. |  |  | Non Investment
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | EQG | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 | 2013-07-01 |  |  | 80000 | 0 | 80000 | 44250 | 55.31% | 35750 | 0 | 35750 | 0 | 0 | 0 | 0 | 0 | The country conducted training of 30 refrigeration technicians and 20 custom officers. The activities are ongoing satisfactorily as planned. |  |  |  | Non Investment
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | ERI | SEV | 54 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2010-05-01 | 2010-03-01 | 2013-07-01 |  |  | 40000 | 0 | 40000 | 20000 | 50% | 20000 | 2000 | 20000 | 0 | 0 | 0 | 0 | 0 | Country celebrated Ozone Day, produced awareness materials and collected 2011 ODS data. Implementation of activities delayed due the absence of Ozone Officer. Government in the process of appointing new Ozone Officer |  |  |  | Non Investment
ONG | UNEP | Institutional strengthening (phase II: 1/2013-12/2014) | Individual | AFR | ERI | SEV | 68 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the absence of Ozone Officer. The Government is in the process of appointing new Ozone Officer to proceeding with implementation of activities | The Government has not yet appointed a new Ozone Officer. CAP planning a Joint mission with UNIDO to discuss with the Government on how to proceed with the implementation of activities. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ETH | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 | 2013-12-01 |  |  | 32500 | 27500 | 60000 | 19500 | 32.5% | 40500 | 0 | 40500 | 0 | 0 | 0 | 0 | 0 | The ODS licensing system and regulation was approved and gazetted. The NOU conducted several awareness program and celebrated the Ozone Day. HPMP implementation is ongoing. CP reports and A7 data for 2011 was collected, compiled and submitted to the Secretariats. There was change of Ozone officer and the institution hosting the NOU from National Meteorological Services Agency to Environmental Protection Agency. The CAP team has trained the new Ozone Officer on the implementation of the Montreal Protocol. | The NOU conducted customs training. CAP received information that the NOU had conducted activities and incurred expenses above half of the IS funds available and the NOU was preparing reports to account for the expenditures incurred. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 50 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-07-01 | 2008-11-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 38920 | 64.87% | 21080 | 0 | 21080 | 0 | 0 | 0 | 0 | 0 |  | Government Structural Changes has delayed implementation of activities. The NOU has moved from Meteorological Agency to Environmental Protection Agency (EPA) and a new ozone officer from EPA has just been appointed. CAP is planning a mission to facilitate smooth transfer of activities to the new NOU. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2012-11/2014) | Individual | ASP | FIJ | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The SSFA has been developed for country's agreement. | The SSFA signed in March 2013 and initial payment being processed. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | FSM | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The SSFA has been developed for country's agreement. | The SSFA has been signed and initial payment being processed for disbursement. Draft of 2012 Article 7 and CP data prepared. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GAB | SEV | 62 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 40500 | 67.5% | 19500 | 9074 | 19500 | 0 | 0 | 0 | 0 | 0 | A survey for 2011 data collection was completed .The NOU participated in MP meetings. The project is ongoing satisfactorily. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 8/2012-7/2014) | Individual | AFR | GAM | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-06-01 | 2014-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 38061 | 60000 | 0 | 0 | 0 | 0 | 0 | The first payment was made in Oct 2012. In order to enforce control measures to sustain CFC phase out, the NOU organized a one day seminar for stakeholders to discuss enforcement of the licensing system. | The country is preparing to host the 19th ODSONET meeting for English-speaking Africa scheduled in May 2013. SSFA was signed and first payment was sent in October 2012. SSFA valid up to August 2014. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III: 7/2102-6/2014) | Individual | AFR | GBS | SEV | 67 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2014-06-01 |  |  | 60000 | 0 | 60000 | 19496 | 32.49% | 40504 | 40504 | 40504 | 0 | 0 | 0 | 0 | 0 | The first payment was made in Sept 2012. CP report and A7 data for 2011 were submitted to the secretariats. The country celebrated the Ozone day and conducted several awareness activities | SSFA was signed and first payment was made in September, 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GRN | SEV | 60 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 | 2013-12-01 |  |  | 52500 | 0 | 52500 | 42000 | 80% | 10500 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO and Assistant attended the Caribbean Network Meeting held in Dominica (March 2012). NOO and Assistant attended Network Meeting held in Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. NOU was in charge of HPMP implementation. | Audited final progress and financial reports are expected by next quarter. NOO and Assistant attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) To review and update ODS legislation; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | LAC | GRN | SEV | 67 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | ISP (Phase IV) can be implemented after the Government exhaust the resources of ISP (Phase III). | Work plan and SSFA being drafted. The Agreement is being drafted and expected to be signed in July 2013. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase VII) | Individual | LAC | GUA | SEV | 61 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-11-01 | 2012-06-01 | 2013-10-01 |  |  | 124800 | 0 | 124800 | 22960 | 18.4% | 101840 | 101840 | 101840 | 0 | 0 | 0 | 0 | 0 | New Government Authorities took office in January 2012. 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. New National Focal Point of Montreal Protocol attended the Network Meeting held in Panama, Oct 2012. NOU submitted Article 7 data report and Country Programme Report. NOU was in charge of the NPP/HPMP coordination. Activities funded with resources available at country level disbursed in 2011. | (a) To review and update ODS legislation (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. New government since January 2012. The Government has instructed public institutions to put projects on hold, including any disbursements, while an internal assessment/audit is conducted. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GUI | SEV | 63 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 | 2013-03-01 |  |  | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | The survey for 2011 ODS data was completed. The country celebrated the ozone day and conducted several awareness raising activities. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | GUY | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project recently approved (Dec. 2012). | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Additional emergency assistance for institutional strengthening | Individual | LAC | HAI | SEV | 61 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2011-06-01 | 2013-12-01 |  |  | 20000 | 0 | 20000 | 9000 | 45% | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | CFC zero level of consumption maintained since 1st Dec of 2010. There were two changes at the level of the Minister of Environment and the NOO which lead to the re-examination of actions and the slow rate of implementation in 2012. Despite challenges, the programme implementation has progressed through a strategic adaption to the current country level institutional circumstances. In moving the training components forward, the relationship already built with MINUSTAH has been maintained, as the country’s rebuilding efforts continued to respond to national needs for housing and RAC equipment as well as requirements of the Montreal Protocol. UNEP, UNDP and the National Ozone Unit drafted a strategy and a work plan to address the RAC sector as a whole, as part of the HPMP preparation process. Activities and resources oriented not only to maintain zero consumption of CFCs, but also to introduce low GWP alternative technologies. | 2013 annual operating plan and the procurement plan is been prepared by the IAs and NOU. Additional assistance to equip the office is waiting for the re-construction of a new room for the NOU. UNEP is doing close follow up to the country political situation where many turn over at the Ministerial level and NOO has affected projects implementation. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | HAI | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 | 2013-12-01 |  |  | 54167 | 45834 | 100001 | 69377 | 69.38% | 30624 | 0 | 30624 | 0 | 0 | 0 | 0 | 0 | For 2012 there were two changes in Ministers of Environment and consequently, two NOOs. UNEP ROLAC conducted two official missions in January and September. CAP Team met with New Line Ministers and NOOs for revising planned activities and coordinate HPMP preparation. NOU reviewed and endorsed the final HPMP document, which was approved in Dec. 2012. NOO attended Network Meetings held in Dominica (March 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOO did follow up to the Beijing Amendment ratification. | New SSFA is being drafted and finalized with NOO. 2013 annual operating plan and procurement plan were prepared. NOO attended the sub-regional network meeting held in SKN on March 2013. Bilateral meetings between NOO and UNEP conducted on the margins of the Network Meeting in SKN. Arrangements were addressed to reinforce the national capacity in data collecting and reporting. (a) To review and update ODS legislation; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. Goals (a ), ( c) , (d ), (e ), (f ), and ( g) were affected by frequent changes of NOO, loosing continuity and institutional memory. UNEP provided training and technical support to new NOOs. UNEP is doing follow-up to adjust the plan of activities. Progress and financial reports from the Government are being awaited for 2013. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | HON | SEV | 68 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-02-01 | 2014-02-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project recently approved (Dec. 2012). | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | IVC | SEV | 68 | INS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 106340 | 0 | 106340 | 0 | 0% | 106340 | 0 | 106340 | 0 | 0 | 0 | 0 | 0 | The SSFa was prepared and sent to country for signature |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | JAM | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-11-01 | 2013-01-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO attended the Caribbean Network Meeting held in Dominica, March 2012. | NOO Assistant attended the sub-regional network meeting held in SKN on March 2013. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) To review and update ODS legislation (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | JAM | SEV | 68 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 12000 | 60000 | 0 | 0 | 0 | 0 | 0 | Project recently approved (Dec. 2012). | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI:12/2011-11/2013) | Individual | ASP | KAM | SEV | 64 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 | 2013-11-01 |  |  | 112667 | 0 | 112667 | 61028 | 54.17% | 51639 | 0 | 51639 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is on operation efficiently and full in staff. UNEP is informed of regular national consultation being arranged quarterly and annually. Awareness activities were organized during the International Ozone day in 2012. | The NOU's focus is the HPMP implementation and the country is preparing the submission of IS renewal for the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | KEN | SEV | 62 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 | 2013-06-01 |  |  | 151667 | 0 | 151667 | 113867 | 75.08% | 37800 | 37800 | 37800 | 0 | 0 | 0 | 0 | 0 | NOU collected 2012 ODS data, celebrated Ozone Day and conducted several awareness activities. | NOU started collection of 2012 ODS data, trained 40 customs officers |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | KIR | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on February 2012 and initial disbursement was made on May 2012.The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on February 2012 and initial disbursement was made on May 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | NOO successfully worked with national stake holders, regional and international experts in the selection and decisions making of non methyl bromide QPS approach for the treatment of a shipment of gravel. Draft of 2012 Article 7 and CP ODS data completed. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | ASP | KUW | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 105320 | 0 | 105320 | 0 | 0% | 105320 | 0 | 105320 | 0 | 0 | 0 | 0 | 0 | ExCom 68 approved new cycle | Agreement and related payment under finalization and processing with country |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | KYR | SEV | 61 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 | 2013-12-01 |  |  | 115830 | 0 | 115830 | 111200 | 96% | 4630 | 0 | 4630 | 0 | 0 | 0 | 0 | 0 | A set of legal documentation for the Certification System of the service refrigeration technicians was developed. There was elaborated and opened a web site of the Association of Refrigeration Technicians . RAC "Ecoholod" together with the Kyrgyz State Technical University are teaching mechanical engineers in the field of refrigeration and air-conditioning as well as a refrigeration technicians at 4 Vocational colleges | Project activities are completed |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | EUR | KYR | SEV | 68 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 115830 | 0 | 115830 | 0 | 0% | 115830 | 0 | 115830 | 0 | 0 | 0 | 0 | 0 | The project was approved by ExCom in December of 2012 | The SSFA has been already signed and the first payment released. The Ozone Centre has initiated activities agreed in the work programme under the renewed IS project. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase VI: 12/2012-11/2014) | Individual | ASP | LAO | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | The SSFA has been signed in December 2012. | Initial payment disbursed on March 2013. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | LES | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project approved in November 2012. | SSFA drafted and sent to the country for signing |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LIR | SEV | 63 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 | 2013-03-01 |  |  | 85213 | 0 | 85213 | 65713 | 77.12% | 19500 | 19500 | 19500 | 0 | 0 | 0 | 0 | 0 | The NOU trained 100 technicians, 30 customs and other law enforcement officers in readiness for HCFC phase out. Licensing system in place and functioning and information disseminated on HCFC phase out and alternative and acceptable refrigerants promoted. In addition, the NOU trained 90 customs and other law enforcers in the art of detecting ODS using detection equipment and other methods. The NOU celebrated the Ozone day and conducted quiz competitions. 2011 CP report and A7 data was collected, compiled and submitted. The NOU attended all the Montreal Protocol meetings and network meetings. | The NOU conducted Training and Awareness Workshop for MB Phase-out with participation of more than 60 stakeholders. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | AFR | MAG | SEV | 67 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2014-06-01 |  |  | 60700 | 0 | 60700 | 19675 | 32.41% | 41025 | 41025 | 41025 | 0 | 0 | 0 | 0 | 0 | First payment was made in Oct 2012. The Country conducted several awareness raising activities and celebrated the Ozone day. CP report and A7 data for 2011 were submitted | SSFA was signed and first payment was sent to the country in October, 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2012-03-01 | 2009-11-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 0 | 40500 | 0 | 0 | 0 | 0 | 0 | NOU collected 2012 ODS data, celebrated Ozone Day and conducted several awareness activities. | NOU started collection of 2012 ODS data and produced awareness materials |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2011-11/2013) | Individual | ASP | MAS | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on April 2012 and initial disbursement was made on November 2012. The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on April 2012 and initial disbursement was made on November 2012. New NOO appointed in September of 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | Continuation of training of NOO, Planning for the delivery of Customs training in April of 2013, preparation of draft 2012 CP and Article 7 data. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | MAU | SEV | 57 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2011-03-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Administrative stalement still not resolved | The issue of Administrative stalement in Mauritanian is being followed up very closely by the Regional Director and with the assistance of the office of the Deputy Executive Director and it is expected that the stalement will be resolved soon. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAU | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2008-06-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 46955 | 78.26% | 13045 | 0 | 13045 | 0 | 0 | 0 | 0 | 0 | Administrative stalement still not resolved | The issue of Administrative stalement in Mauritanian is being followed up very closely by the Regional Director and with the assistance of the office of the Deputy Executive Director and it is expected that the stalement will be resolved soon. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | MDV | SEV | 67 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The SSFA has been signed in in March and initial payment is being processed. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 4/2012-3/2014) | Individual | AFR | MLW | SEV | 66 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2014-03-01 |  |  | 66733 | 0 | 66733 | 21184 | 31.74% | 45549 | 45549 | 45549 | 0 | 0 | 0 | 0 | 0 | SSFA was signed and NOU collected 2011 ODS data. The country celebrated Ozone Day, produced and distributed awareness materials and organized schools competitions | NOU started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | EUR | MOL | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2014-06-01 |  |  | 69334 | 0 | 69334 | 3200 | 4.615% | 66134 | 62602 | 66134 | 0 | 0 | 0 | 0 | 0 | The project was approved by ExCom in July of 2012. The SSFA was signed and the first payment released. The NOU initiated activities which are agreed in the work programme under the renewed IS project. | National Phase-out plan for HCFCs for the period 2013-2040 (Governmental Decision) has been elaborated by the NOU and Ministry of Environment. The data on consumption of ODSs in 2012 has been collected, now the data is under processing. The annual import quotas on HCFCs for 2013 has been distributed. The radio advertisement in the format “Matinal National”, under the topic “HPMP implementation in Moldova” have been broadcasted. Round table discussion was organized by the NOU, the Association of Refrigeration technicians and Training Centre “Tehnofrig” with a topic: “2013 – year for freeze HCFC consumption”. NOU took part (with promotional materials) in celebration of the Planet Day (March 23, 2013), organized by the Ministry of Environment. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | ASP | MON | SEV | 64 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The International Ozone Day for the Preservation of the Ozone layer was celebrated with participation of multi-stakeholders in Mongolia in 2012. During the celebration of the 25th Anniversary of Montreal Protocol and International Ozone day for Preservation of the Ozone layer, several events were organized with collaboration of MRA and other main multipliers such as media. The United Nations Secretary General's Message on the occasion of this year's International Day for the Preservation of the Ozone Layer was translated into Mongolian and disseminated on the Press Conference for journalist. TV programme on the ozone issues was broadcasted 5 times through Eco TV and ZA TV channels. | The NOU's focus is the HPMP implementation and the country is preparing the submission of IS renewal for the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | MOR | SEV | 59 | INS | 63 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2011-11-01 | 2013-12-01 |  |  | 84500 | 71500 | 156000 | 0 | 0% | 156000 | 0 | 156000 | 0 | 0 | 0 | 0 | 0 | SSFA was reviewed again by FMO in Nov 2012 | NOU has not submitted required reports despites several reminders by CAP. The Moroccan Minister in Nairobi is assisting to resolve the matter with the NOU. The contact with the NOU has been established and UNEP is planning a mission to Morocco in July 2013 to relaunch ozone activities. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MOR | SEV | 53 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2013-12-01 |  |  | 156000 | 0 | 156000 | 117798 | 75.51% | 38202 | 0 | 38202 | 0 | 0 | 0 | 0 | 0 | SSFA has since expired and was revised and sent to FMO in Nov 2012. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 7/2011-6/2013) | Individual | AFR | MOZ | SEV | 64 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 | 2013-06-01 |  |  | 80800 | 0 | 80800 | 24700 | 30.57% | 56100 | 56100 | 56100 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted awareness programmes on radio and tv stations. | NOU started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III: 1/2012-12/2013) | Individual | ASP | MYA | SEV | 64 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on November 2012.The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on November 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | The NOU's focus is the HPMP implementation and the country is preparing the submission of IS renewal for the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NAM | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 | 2013-12-01 |  |  | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted schools competition and awareness programmes on tv and radio stations |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VII: 4/2012-3/2014) | Individual | AFR | NAM | SEV | 66 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-03-01 | 2014-03-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 46810 | 60000 | 0 | 0 | 0 | 0 | 0 | SSFA was signed with the country and NOU conducted inspection visits to some entry points to monitor control of ODS importation. NOU organized National Ozone Steering Committee meeting | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | ASP | NAU | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The SSFA has been signed in in March and initial payment is being processed. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | NEP | SEV | 67 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The SSFA has been signed and initial payment disbursed. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | NER | SEV | 65 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 | 2013-12-01 |  |  | 64828 | 0 | 64828 | 35616 | 54.94% | 29212 | 29212 | 29212 | 0 | 0 | 0 | 0 | 0 | SSFA was signed by country |  |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | NIC | SEV | 66 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-03-01 | 2014-03-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | SSFA signed. First disbursement released in September 2012. NOO attended Networks Meeting held in Chile (June 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. The Government of Nicaragua reviewed and endorsed the final HPMP document, which was approved in March 2012. NOU was in charge of the TPMP and HPMP implementation. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation to include HCFCs; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | NIU | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-09-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on February 2012 and initial disbursement was made on March 2012. The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on February 2012 and initial disbursement was made on March 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | New NOO appointed in March of 2013. Training to begin in second quarter of 2013. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V: 11/2011-10/2013) | Individual | LAC | PAN | SEV | 65 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2013-08-01 | 2014-05-01 |  |  | 149500 | 0 | 149500 | 81867 | 54.76% | 67633 | 11879 | 67633 | 0 | 0 | 0 | 0 | 0 | New NOO was assigned and new team was hired in mid-2012. NOU received training and mentoring from CAP Team. 2012 annual operating plan and procurement plans were prepared by the NOU with the guidance of the CAP Team. SSFA signed. Funds were managed through direct implementation by UNEP. NOO attended Networks Meeting held in Chile (June 2012) and Panama (October 2012). NOO, assistant and Customs focal point attended the Central America and Dominican Republic Training Workshop for National Ozone Units and Customs Authorities held in Nicaragua on December 2012. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. Awareness raising and capacity building activities about Montreal Protocol and HPMP started in four regions of the country. NOU was in charge of the HPMP implementation. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. Awareness raising and capacity building activities about Montreal Protocol and HPMP started in three regions of the country. CAP team provides on-going technical and administrative support for project implementation (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation to include HCFCs; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | PAR | SEV | 61 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 | 2013-03-01 |  |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Documents for renewal of ISP were prepared and submitted to the 66 ExCom meeting. All funds released through UNDP Paraguay. NOU submitted Article 7 data report and Country Programme Report. NOU was in charge of the HPMP implementation. Audited final financial report submitted to UNEP. | Project completed in March 2013. (a) To review and update ODS legislation; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI: 7/2012-6/2014) | Individual | LAC | PAR | SEV | 66 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 | 2014-06-01 |  |  | 60000 | 0 | 60000 | 25027 | 41.71% | 34973 | 34973 | 34973 | 0 | 0 | 0 | 0 | 0 | SSFA signed. First disbursement released in July 2012. NOO attended Network Meeting held in Panama (October 2012). NOU organized the International Ozone Day celebration at national level. NOU was in charge of the HPMP implementation. | 2013 annual operating plan and procurement plan were prepared by the NOU with the guidance of CAP team. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | PER | SEV | 37 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2011-06-01 | 2004-08-01 | 2013-06-01 |  |  | 133510 | 0 | 133510 | 112670 | 84.39% | 20840 | 20840 | 20840 | 0 | 0 | 0 | 0 | 0 | NOO attended Networks Meeting held in Chile (June 2012) and Panama (October 2012). NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. The Government reviewed and endorsed the final HPMP document, which was approved in December 2012. CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase 5, approved by the 68 ExCom. NOU was in charge of the TPMP implementation. | Audited final progress and financial reports are expected by next quarter. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) To review and update ODS legislation; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) ISP terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | PER | SEV | 68 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 133510 | 0 | 133510 | 0 | 0% | 133510 | 0 | 133510 | 0 | 0 | 0 | 0 | 0 | Project approved in December 2012. | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 65 | INS | 93 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2012-12-01 | 2013-12-01 |  |  | 64471 | 0 | 64471 | 60000 | 93.07% | 4471 | 4471 | 4471 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed and initial disbursement was made on October 2012. The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed and initial disbursement was made on October 2012. In August 2012, the POD-EMB in consultation with FASPO representative, prepared the endorsement of the plan to the Executive Committee of the MLF. The Philippines HPMP was endorsed by the ODS National Coordinator on 30 August 2012. The POD-EMB provided assistance in the preparation of the investment proposal prepared by UNDP. Prior to its finalization, the POD reviewed the proposal. The project proposal is also part of the overarching HPMP strategy which was endorsed by the ODS National Coordinator on 30 August 2012 and re-endorsed on 13 November 2012. The Philippines HPMP was approved during the 68th Meeting of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol held in Montreal, Canada from 3 to 7 December 2012. Publication/printing of a full page International Ozone Day Advertorial in a major newspaper on 16 September 2012. IEC activities were also conducted by the 16 EMB Regional Offices during the ozone month and other events such as: seminars/workshops, lectures, ozone network meetings (O-Net), story-telling on the protection of the ozone layer, hanging of streamers, distribution of ODS Videos and AVPs and distribution of information materials, etc. The POD was represented in the regional network meetings and related MP activities. |  |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | PHI | SEV | 64 | INS | 92 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-10-01 | 2013-12-01 | 2013-12-01 |  |  | 181133 | 0 | 181133 | 163020 | 90% | 18113 | 18113 | 18113 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on October 2011 and initial disbursement was made on November 2011.The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on October 2011 and initial disbursement was made on November 2011. In August 2012, the POD-EMB in consultation with FASPO representative, prepared the endorsement of the plan to the Executive Committee of the MLF. The Philippines HPMP was endorsed by the ODS National Coordinator on 30 August 2012. The POD-EMB provided assistance in the preparation of the investment proposal prepared by UNDP. Prior to its finalization, the POD reviewed the proposal. The project proposal is also part of the overarching HPMP strategy which was endorsed by the ODS National Coordinator on 30 August 2012 and re-endorsed on 13 November 2012. The Philippines HPMP was approved during the 68th Meeting of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol held in Montreal, Canada from 3 to 7 December 2012. Publication/printing of a full page International Ozone Day Advertorial in a major newspaper on 16 September 2012. IEC activities were also conducted by the 16 EMB Regional Offices during the ozone month and other events such as: seminars/workshops, lectures, ozone network meetings (O-Net), story-telling on the protection of the ozone layer, hanging of streamers, distribution of ODS Videos and AVPs and distribution of information materials, etc. The POD was represented in the regional network meetings and related MP activities. | The NOU's focus is the HPMP implementation and the completion of NCPP. The country is preparing the submission of IS renewal for the 70th ExCom. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | PRC | SEV | 64 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 | 2013-06-01 |  |  | 60000 | 0 | 60000 | 32964 | 54.94% | 27036 | 0 | 27036 | 0 | 0 | 0 | 0 | 0 | The country submitted 2011 CP report and A7 data to the Secretariats. The country celebrated the Ozone day and conducted several awareness raising activities. | SSFA was signed and first payment was made in April 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | RWA | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-06-01 | 2013-06-01 |  |  | 60000 | 0 | 60000 | 46500 | 77.5% | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | SSFA was signed and NOU collected 2011 ODS data. The country celebrated Ozone Day, produced and distributed awareness materials and conducted awareness programmes on TV and radio stations. | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI: 11/2011-10/2013) | Individual | ASP | SAM | SEV | 64 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-10-01 | 2013-10-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on August 2012 and initial disbursement was made on November 2012.The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on August 2012 and initial disbursement was made on November 2012. New NOO appointed in October of 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. NOO attended the 2012 SA and SEAP Ozone officers network meeting as part of her training as new officer. | NOO and national community held a Country wide event over three weeks for the management of refrigerants included those that are ODS contained in RAC systems in the aftermath of Cyclone Evan (January 2013). Draft 2012 ODS consumption data completed. |  |  | Non Investment
ONG | UNEP | Institutional strengthening (establishment of Ozone Unit) | Individual | ASP | SAU | SEV | 53 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2010-11-01 | 2013-02-01 |  |  | 300000 | 0 | 300000 | 250000 | 83.33% | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | Being the first ISP for Saudi Arabia, Country faced difficulty in aligning procedures including financial mechanism within the Presidency of Metrology & Environment (PME), thus causing long delay. However Country successfully submitted all required reporting by early 2012 and accordingly ISP renewal was submitted by 67 ExCom. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II: 7/2012-6/2014) | Individual | ASP | SAU | SEV | 67 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2014-07-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | ExCom 67 approved new cycle | UNEP is in process of finalizing agreement and related payment with Country |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | AFR | SEN | SEV | 65 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 | 2013-12-01 |  |  | 152101 | 0 | 152101 | 120767 | 79.4% | 31334 | 31334 | 31334 | 0 | 0 | 0 | 0 | 0 | CP report and A7 data were submitted to the Secretariats. Country celebrated the Ozone day and conducted quiz competitions. | SSFA was signed and third payment was made in February 2013. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | SEY | SEV | 63 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 33004 | 55.01% | 26996 | 0 | 26996 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted awareness programmes on radio and TV stations. | Country collected 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SIL | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2012-06-01 | 2013-06-01 |  |  | 85800 | 0 | 85800 | 45900 | 53.5% | 39900 | 0 | 39900 | 0 | 0 | 0 | 0 | 0 | The NOU successful launched HPMP activities and commenced the update of National Environmental Policy. Five centres of excellence were established and equipped for training of refrigeration technicians. The NOU trained 300 Customs Officers and other Law enforcement agents in readiness for HCFC phase-out. The NOU participated in the 2012 Annual Trade Fair organized by the Chamber of Commerce and raised awareness on Ozone issues. The NOU celebrated the Ozone day and conducted quiz competitions. CP report and 2011 A7 data was collected, compiled and submitted to the Secretariats. The NOU attended all the Montreal Protocol meetings and network meetings. | The NOU conducted awareness raising activities |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | SOI | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on February 2012 and initial disbursement was made on March 2012. The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on February 2012 and initial disbursement was made on March 2012. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | Draft 2012 CP and article 7 data prepared. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II: 1/2013-12/2014) | Individual | AFR | SOM | SEV | 68 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2014-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted awareness programmes on radio and TV stations. | Country collected 2012 ODS data |  |  | Non Investment
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | SSD | SEV | 68 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-07-01 | 2014-07-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted awareness programmes on radio and TV stations. | Country collected 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | STK | SEV | 59 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 | 2013-07-01 |  |  | 32500 | 27500 | 60000 | 41000 | 68.33% | 19000 | 12000 | 19000 | 0 | 0 | 0 | 0 | 0 | CAP Team conducted country mission for review of project activities and to agree on finalization of this project. NOO Assistant attended the Network meeting held in Dominica (March 2012). CAP team provided technical support to the NOU in order to prepare final report and renewal request for ISP phase V. NOU submitted Article 7 data report and Country Programme Report. NOU organized the International Ozone Day celebration at national level. Final progress and financial reports were drafted. NOO was in charge of HPMP implementation. | 2013 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. NOO co-organized the Caribbean Network Meeting held in SKN (March 2013). NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) To review and update ODS legislation to include HCFCs; (b) Article 7 data and CP progress report data submission; (c) Project implementation support; (d) Public awareness activities; (e) IS terminal report preparation support; (f) ISP renewal request support; (g) ISP renewal approval. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | STK | SEV | 68 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project approved in December 2012. | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | STL | SEV | 68 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-01-01 | 2015-01-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project approved in December 2012. | Work plan and SSFA being drafted. Approved in Dec 2012. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | STP | SEV | 63 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2013-03-01 |  |  | 60666 | 0 | 60666 | 19665 | 32.42% | 41001 | 0 | 41001 | 0 | 0 | 0 | 0 | 0 | CP report and A7 data were submitted to the Secretariats. Country celebrated the Ozone day and conducted quiz competitions. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | LAC | STV | SEV | 66 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2014-03-01 |  |  | 60000 | 0 | 60000 | 22950 | 38.25% | 37050 | 24950 | 37050 | 0 | 0 | 0 | 0 | 0 | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. SSFA signed. First Disbursement released. NOO and assistants attended Network Meetings held in Dominica (March 2012) and in Panama (October 2012). NOO submitted Article 7 data report and CP report. NOO organized the International Ozone Day celebrations at national level. NOU was in charge of TPMP and HPMP implementation. | NOU and assistant attended the subregional network meeting held in SKN on March 2013. NOU has been collecting ODS data and cross-checking information to prepare CP report. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening: phase VI | Individual | AFR | SUD | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 | 2013-12-01 |  |  | 145860 | 0 | 145860 | 51841 | 35.54% | 94019 | 35090 | 94019 | 0 | 0 | 0 | 0 | 0 | The NOU conducted training for 80 refrigeration technicians and distributed equipment for good refrigeration practices to 2 vocational centres and 20 refrigeration shop services. The NOU distributed 5 sets of control and measurements tools as awards to the best 5 performing technicians. The NOU trained 180 custom officers and other law enforcements agents on illegal ODS trade. Current licensing system and procedures is effectively functioning and supporting all HCFCs phase-out programme. The NOU conducted training in good phosphine fumigation at Port Sudan. The NOU celebrated the Ozone day and conducted quiz competitions. 2011 CP report and A7 data was collected, compiled and submitted to the Secretariats. The NOU attended all the Montreal Protocol meetings and network meetings. | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2012 data on ODS imports and consumption is ongoing. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 7/2012-6/2014) | Individual | LAC | SUR | SEV | 67 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2014-06-01 |  |  | 73333 | 0 | 73333 | 900 | 1.227% | 72433 | 72433 | 72433 | 0 | 0 | 0 | 0 | 0 | SSFA signed in December 2012. | 2013 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. NOO has been collecting ODS data and cross-checking information to prepare Country Programme Report. (a) Draft agreement in consultation with NOU; (b) Obtaining agreement clearance by UNEP and Country; (c) Obtaining agreement signature; (d) Draft indicative work plan; (e) To review and update ODS legislation; (f) Article 7 data and CP progress report data submission; (g) Project implementation support; (h) Public awareness activities. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SWA | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 | 2013-07-01 |  |  | 32500 | 27500 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | NOU collected 2011 ODS data and celebrated Ozone Day. Awareness materials such caps, t-shirts, calendars, car stickers and pamphlets were produced and distributed. The country conducted awareness programmes on radio and TV stations. | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Institutional strengthening project (phase II, year 2: 1/2012-12/2012) | Individual | ASP | TLS | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2012-12-01 | 2013-12-01 |  |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on April 2011. The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on April 2011. The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. |  |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | AFR | TOG | SEV | 68 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60666 | 0 | 60666 | 0 | 0% | 60666 | 0 | 60666 | 0 | 0 | 0 | 0 | 0 | SSFA drafted and sent to country for review |  |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TON | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | Draft 2012 CP and article 7 data prepared. |  |  | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TTR | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 | 2013-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | The agreement has been signed on February 2012 and initial disbursement was made on November 2012.The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The agreement has been signed on February 2012 and initial disbursement was made on November 2012. The NOU is operational and full in staff. NOO of Palau hosted and trained the new NOOS of Federal States of Micronesia and Republic of Marshall Islands. | Draft 2012 CP and Article 7 data prepared and being reviewed |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | TUV | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | NOO organised and deliver the Customs training. Draft 2012 Article 7 and CP data under review. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | TUV | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The SSFA has been signed and the initial payment being processed for signature. |  |  | Non Investment
ONG | UNEP | Institutional strengthening (establishment of the ODS unit) | Individual | AFR | UGA | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1997-07-01 | 2013-12-01 |  |  | 64515 | 0 | 64515 | 29774 | 46.15% | 34741 | 0 | 34741 | 8387 | 0 | 3870.6431 | 4516.3569 | 0 | Country is finalising preparation of all pending reports with the assistance of CAP to revitalise implementation of project activities. |  |  | 1999-12-01 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | AFR | URT | SEV | 66 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2014-03-01 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | SSFA was signed and NOU collected 2011 ODS data. The country celebrated Ozone Day, produced and distributed awareness materials and organised schools competitions | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | VAN | SEV | 62 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. NOO attended the SA and SEAP Pataya Ozone officers Network meeting as part of her training. | Draft 2012 Article 7 and CP ODS data prepared and under review. |  |  | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | VAN | SEV | 67 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-12-01 | 2014-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The SSFA has been signed and the initial payment being processed for signature. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | VIE | SEV | 63 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-06-01 | 2013-06-01 |  |  | 118976 | 0 | 118976 | 101130 | 85% | 17846 | 17846 | 17846 | 0 | 0 | 0 | 0 | 0 | The list of planned activities for 2012: - Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption - Efficient and timely data collection and reporting - Consultations and coordination with other national agencies/stakeholders - Supervision of timely implementation of phase-out activities and reduction in ODS consumption - Awareness raising and information exchange - Regional cooperation and participation to Montreal Protocol meetings. Progress: The NOU is operational and full in staff. Awareness activities were organized during the International Ozone day in 2012. | The IS renewal was approved in the 68th ExCom. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 7/2013-6/2015) | Individual | ASP | VIE | SEV | 68 | INS | 60 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2015-06-01 | 2015-06-01 |  |  | 118976 | 0 | 118976 | 0 | 0% | 118976 | 0 | 118976 | 0 | 0 | 0 | 0 | 0 | Newly approved project. The draft SSFA has been formulated for country's agreement. | The draft SSFA has been formulated for country's agreement which will start by June 2013.. |  |  | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | YEM | SEV | 68 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 |  |  | 169999 | 0 | 169999 | 0 | 0% | 169999 | 0 | 169999 | 0 | 0 | 0 | 0 | 0 | Extension approved for Phase VII | Due to recent political development and subsequent changes of Minister of Environment & Water, as well as the Chairman of Environment Protection Authority (EPA); UNEP is waiting for clear instructions of new management to draft and process new ISP agreement. |  |  | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | AFR | ZIM | SEV | 59 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 | 2013-07-01 |  |  | 80297 | 67944 | 148241 | 115494 | 77.91% | 32747 | 32747 | 32747 | 0 | 0 | 0 | 0 | 0 | Country collected 2011 ODS data, celebrated Ozone Day and conducted schools competition. The NOU produced and distributed awareness materials | Country started collection of 2012 ODS data |  |  | Non Investment
ONG | UNIDO | Extension of institutional strengthening project (phase III: 4/2013-3/2015) | Individual | EUR | ARM | SEV | 68 | INS | 10 | N | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2014-12-31 | 2015-03-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 50000 | 8400 | 0 | 0 | 8400 | 0 | The project was approved at the 68th Meeting of the Executive Committee. The NOU staffed confirmed, the implementation was initiated. | Workplan for the year 2013 is finalized. (It includes training for other institutions with responsibilities in phasing out HCFCs, additional customs training, legislation review, monitoring component, data collection and reporting, awareness activities in schools and high-schools.) |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase III: 3/2012-2/2014) | Individual | EUR | BHE | SEV | 65 | INS | 25 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2014-02-28 | 2014-02-01 |  |  | 95333 | 0 | 95333 | 31632.77 | 33.18% | 63700.23 | 0 | 35000 | 7150 | 0 | 2372 | 4778 | 0 | NOU fully staffed and incentives component was committed for the first half of 2012. Activities planned in 2012 were completed successfully. | Workplan for 2013 has been agreed with counterpart and 2013 activities implementation has been initiated. (Awareness through involvement of short-term national consultants , public awareness, office equipment purchase, monitoring with a view to HPMP implementation.) |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | AFR | EGY | SEV | 67 | INS | 115 | N | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2014-12-31 | 2014-12-01 |  |  | 228323 | 0 | 228323 | 0 | 0% | 228323 | 0 | 100000 | 15983 | 0 | 0 | 15983 | 0 | The subcontract with the Egyptian Environmental Affairs Agency was signed for the execution of the project. The NOU was fully staffed and activities were planned for the years 2013 - 2014, as per the project document. | Follow-up, monitoring and reporting on the activities defined by the subcontract with counterpart. Funds are fully committed through subcontract. |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase II) | Individual | AFR | LIB | SEV | 59 | INS | 31 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-11-01 | 2013-12-01 |  |  | 73702 | 62363 | 136065 | 45511.19 | 33.45% | 90553.81 | 5120 | 50000 | 5528 | 4677 | 3413 | 6792 | 384 | NOU staff was nominated in 2012. Consultants were contracted for carrying specific activities. Office equipment was locally purchased and delivered. | Workplan with a view to public awareness activities to be organized in 2013 is under development. The main activities in 2013 will focus on data collection, HPMP progress and coordination. Reason for the delay: The political and security situation in the country in the beginning of the project implementation. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | MEX | SEV | 68 | INS | 163 | N | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2014-12-31 | 2014-12-01 |  |  | 247000 | 0 | 247000 | 0 | 0% | 247000 | 0 | 130000 | 17290 | 0 | 0 | 17290 | 0 | The project was approved at the 68th Meeting of the Executive Committee in November 2012. The Government was informed. | Workplan for the year 2013 was finalized. (It includes SISSAO OD database up-date, legislation review, monitoring component with a specific view to the HPMP, data collection and data reporting, and awareness activities.) |  |  | NON-INV
ONG | UNIDO | Institutional strengthening project (phase II) | Individual | EUR | MOG | SEV | 61 | INS | 07 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-06-30 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 47969.24 | 79.95% | 12030.76 | 5071.38 | 10000 | 4500 | 0 | 3598 | 902 | 380 | NOU staff assigned, public awareness activities organized, reporting commitments were achieved. IS further extension request foreseen with the next HPMP tranche | The final activity in 2013 will be the printing of the awareness raising publications. Reason for the delay: The design of the awareness raising publications took longer than expected. |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening support (phase IV: 12/2011-11/2013) | Individual | ASP | OMA | SEV | 65 | INS | 21 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2013-11-30 | 2013-12-01 |  |  | 68467 | 0 | 68467 | 7.86 | 0.01148% | 68459.14 | 35000 | 10000 | 5135 | 0 | 1 | 5134 | 2625 | Subcontract with NOU was signed for the execution of the project. The NOU is fully staffed and activities planned for the years 2012 - 2013, as per the project document. Disbursements were delayed from 2012 to 2013 due to migration to new financial system. | Follow-up, monitoring and reporting on the activities defined by the subcontract with counterpart. Project funds are fully committed through subcontract. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out. By the first quarter 2013, 50% of the funds have been disbursed. |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase III) | Individual | ASP | QAT | SEV | 59 | INS | 15 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2011-11-01 | 2015-06-01 |  |  | 48208 | 40792 | 89000 | 52.58 | 0.05908% | 88947.42 | 0 | 10000 | 3616 | 3059 | 4 | 6671 | 0 | To date no NOU officer(s) were appointed, and thus, no progress was made in spite of many efforts done by UNIDO. UNIDO will continue liaising with Ministry of Environment to progress on the nomination of NOU staff. During 2012 no NOU officer(s) were appointed, and thus, no progress was made in spite of many efforts done by UNIDO. This explains the zero disbursement. | To date no NOU officer(s) were appointed, and thus, no progress was made in spite of many efforts done by UNIDO. UNIDO will continue liaising with Ministry of Environment to progress on the nomination of NOU staff. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening (phase IV) | Individual | ASP | SYR | SEV | 58 | INS | 101 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-12-01 | 2014-07-01 |  |  | 152867.25 | 0 | 152867.25 | 33846.69 | 22.14% | 119020.56 | 8757 | 50000 | 11465 | 0 | 2539 | 8926 | 656.775 | The NOU staff was nominated during the fourth quarter of 2012. Contracts are to be released starting with 2013. | Public awareness activities and training workshops planned in 2013 (field security issues). Reason for the delay: The security and political situation in the country. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | AFR | TUN | SEV | 66 | INS | 53 | N | I |  | 0 | 0 |  |  | 2012-04-01 |  | 2014-06-30 | 2015-01-01 |  |  | 247270 | 0 | 247270 | 0 | 0% | 247270 | 0 | 100000 | 18545 | 0 | 0 | 18545 | 0 | The project was approved at the 66th Meeting of the Executive Committee. The Government was informed. | UNIDO mission was conducted to the country in March 2013 to agree on the Tor for the sub-contracts with the counterparts. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase V) | Individual | EUR | TUR | SEV | 64 | INS | 98 | N | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2013-06-30 | 2013-06-01 |  |  | 260000 | 0 | 260000 | 59343.25 | 22.82% | 200656.75 | 25355.48 | 5000 | 19500 | 0 | 4451 | 15049 | 1902 | 4 national consultants' contracts issued during the first quarter of 2012. The Workplan was agreed with the NOU. Two workshops and several meetings took place in 2012 with the stakeholders. Public awareness activities have been carried out as per the project document. | The NOU is fully staffed with 5 national consultans. The training for the new NOU staff will be organized togather with UNEP in June 2013. The request for the extension of the project will be submitted in 2013. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | EUR | YUG | SEV | 65 | INS | 40 | N | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2013-11-30 | 2013-11-01 |  |  | 131300 | 0 | 131300 | 35.42 | 0.02698% | 131264.58 | 732.39 | 60000 | 9848 | 0 | 3 | 9845 | 55 | Implementation was slightly affected by administrative changes within the Ministry of Environment. The NOU staff was re-nominated/confirmed on the post due to administrative restructuring. Workplan was agreed, awareness activities took place as planned NOU was under administrative restructuring and lost 2 officers. NOU staff was re-nominated/confirmed on the post during 2012. Funds comitments were achieved second half of 2012 affecting the level of disbursement.Note also that disbursements were also made against the remaining funds of the previous tranche. | Contracting NOU staff is on-going. Workplan for the year 2013 to be reviewed. The project is expected to be completed in 2013, sonner than originally planned, since all the activities have been carried out. |  |  | NON-INV
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transfered to UNDP |  |  |  | Non-INV
TRF | UNDP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 50 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  |  | 2007-12-01 | 75833 | -75833 | 0 | 0 |  | 0 | 0 | 0 | 5688 | -5688 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Non-Investment
TRF | UNDP | Extension of institutional strengthening project (phase V) | Individual | AFR | KEN | SEV | 44 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  |  | 2010-10-01 | 151667 | -785.64 | 150881.36 | 150881.36 | 100% | 0 | 0 | 0 | 11375 | -58.9229 | 11316.0771 | 0 | 0 | Transferred in 2007. Financially completed in 2010. |  | 2004 |  | Non-Investment
TRF | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 51 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2009-03-01 |  |  | 2007-12-01 | 60667 | -60667 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of phenolic foam at Bakelite Hylam Ltd. | Individual | ASP | IND | FOA | 13 | INV | 27 | A | I | CFC | 58 | 58 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1998-11-01 | 1999-12-01 | 367000 | 0 | 367000 | 367000 | 100% | 0 | 0 | 0 | 47710 | 0 | 47710 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | 1995-09-01 | INV
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1995-09-01 | INV
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1996-01-01 | INV
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 100% | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100% | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | UNDP | Conversion from CFC-11 to CFC-free technology in the manufacture of rigid polyurethane foam chemical systems at Shivathene Linopack | Individual | ASP | IND | FOA | 28 | INV | 218 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 209000 | -16227 | 192773 | 192773 | 100% | 0 | 0 | 0 | 27170 | -2110 | 25060 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 |  | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | Project is cancelled. Funds returned to 28th meeting. |  |  | 1997-10-01 | INV
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 |  | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | Cancelled |  |  | 1997-09-01 | INV
CLO | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Industria Nacional de Desechables (Inaldes) | Individual | LAC | COL | FOA | 13 | INV | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  |  | 2001-12-01 | 380500 | -373255 | 7245 | 7245 | 100% | 0 | 0 | 0 | 49465 | -48523 | 942 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1994 | 2000-03-01 | Investment
CLO | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at Productos Moldeados America S.R. Ltda. (Plasticos Modernos) | Individual | LAC | PAN | FOA | 22 | INV | 09 | A | I | CFC | 16.2 | 16 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2003-11-01 | 339296 | -213326 | 125970 | 125970 | 100% | 0 | 0 | 0 | 44108.48 | -27732.48 | 16376 | 0 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFC-114 in the manufacture of extruded polystyrene foam sheet and profiles at Thermaflex Insulation Asia Co. Ltd. | Individual | ASP | THA | FOA | 11 | INV | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-07-01 |  |  | 2001-07-01 | 220000 | -220000 | 0 | 0 |  | 0 | 0 | 0 | 28600 | -28600.08 | 0 | -0.08 | 0 | Canceled in 1995. Financially Completed in 2001. |  | 1993 |  | Investment
CLO | UNIDO | Phase-out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polyethylene foams for thermal insulation and food packaging purposes at Epex Co. | Individual | LAC | BRA | FOA | 28 | INV | 141 | A | I |  | 0 | 0 |  |  | 1999-07-01 |  | 2001-08-01 |  |  | 2001-07-01 | 632391 | -632391 | 0 | 0 |  | 0 | 0 |  | 79563 | -79563 | 0 | 0 | 0 | CLO
COM | UNDP | Validation of the use of HFO-1234ze as blowing agent in the manufacture of extruded polystyrene foam boardstock (phase I) | Individual | EUR | TUR | FOA | 60 | DEM | 96 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-02-01 |  | 2011-12-01 |  | 165000 | 0 | 165000 | 164609.31 | 99.76% | 390.69 | 0 | 312.552 | 14850 | 0 | 14814.8379 | 35.1621 | 0 | Completed in 2011. During initial trials, the technology did not perform and foam board with pin holes were received as a result. For improved foam quality testing, a set of analytical equipment was procured and delivered to the trial site in October 2011. A final visit to try an optimized blend at the second (main) production line was fielded in December 2011. It is hoped that the tests will be completed sucessfully in early 2012. Some payments still pending. | Completed in 2011. All tests have been completed. An initial draft technology report was prepared in February 2012. The project is considered as completed. The final technology report will be submitted to 67th ExCom | 2010 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom in January 1999. |  |  | 1997-03-01 | INV
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-09-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the 30th ExCom. |  |  | 1997-03-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 27th ExCom. |  |  | 1997-02-01 | INV
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 07 | INV | 15 | N | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. ODP phaseout target reached. |  |  | 1995-09-01 | INV
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100% | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  | 2001-02-01 | INV
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 08 | N | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 07 | N | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100% | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2001-02-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100% | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | 1997-03-01 | INV
FIN | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | I | CFC | 106.9 | 106.9 | 0 | 0 | 2003-12-01 | 2005-11-01 | 2006-01-01 |  | 2006-12-01 | 2007-06-01 | 658973 | -12331 | 646642 | 646642 | 100% | 0 | 0 |  | 49423 | -801 | 48622 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100% | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. |  |  |  | INV
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 05 | N | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100% | -0.18 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | INV
FIN | UNDP | Conversion from CFC-12 to isobutane technology in the manufacture of extruded polyethylene foam at Thermo-flex | Individual | LAC | BRA | FOA | 32 | INV | 196 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-10-01 | 123300 | 0 | 123300 | 123300 | 100% | 0 | 0 | 0 | 16029 | 0 | 16029 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyethylene foam tubing at Polipex | Individual | LAC | BRA | FOA | 22 | INV | 65 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2002-01-01 | 2002-12-01 | 191000 | 0 | 191000 | 191000 | 100% | 0 | 0 | 0 | 24830 | 0 | 24830 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Manufacturas Ajover Ltda. | Individual | LAC | COL | FOA | 13 | INV | 09 | A | I | CFC | 190 | 190 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  | 1998-12-01 | 2001-12-01 | 691500 | -22425 | 669075 | 669075 | 100% | 0 | 0 | 0 | 89895 | -2915 | 86980 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Sino-Foreign Joint Stock Shenyang Shenrong Co. | Individual | ASP | CPR | FOA | 15 | INV | 89 | A | I | CFC | 48 | 48 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-05-01 | 2002-04-01 | 166700 | -1 | 166699 | 166699 | 100% | 0 | 0 | 0 | 21671 | 1.0186e-12 | 21671 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinfeng | Individual | ASP | CPR | FOA | 15 | INV | 98 | A | R | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 235340 | 0 | 235340 | 235340 | 100% | 0 | 0 | 0 | 30594 | 0 | 30594 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 used in the manufacture of EPE foam sheet at Danshui Huaya Plastics Industries Co. Ltd. | Individual | ASP | CPR | FOA | 13 | INV | 73 | A | R | CFC | 160 | 160 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1995-04-01 | 1997-12-01 | 241000 | 0 | 241000 | 241000 | 100% | 0 | 0 | 0 | 31330 | 0 | 31330 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE netting at Hebei Sixing Polypack Products Co. Ltd., Shijiazhuang | Individual | ASP | CPR | FOA | 15 | INV | 93 | A | I | CFC | 65 | 65 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 436000 | -183121 | 252879 | 252879 | 100% | 0 | 0 | 0 | 56680 | -23806 | 32874 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guizhou Jinchang Plastics Products Co. Ltd. | Individual | ASP | CPR | FOA | 15 | INV | 100 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 390000 | -117155 | 272845 | 272845 | 100% | 0 | 0 | 0 | 50700 | -15230 | 35470 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE/PS foam sheet at Shanghai Jianhua Electro-Mechanical and Mechanical Company | Individual | ASP | CPR | FOA | 15 | INV | 102 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-11-01 | 2002-04-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Hailun Plastic Packaging Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 101 | A | I | CFC | 95 | 95 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 321000 | -2 | 320998 | 320998 | 100% | 0 | 0 | 0 | 41730 | 2.0373e-12 | 41730 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE foam tubing at Suzhou Plastic Works No. 7 | Individual | ASP | CPR | FOA | 15 | INV | 88 | A | I | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 358000 | -36690 | 321310 | 321310 | 100% | 0 | 0 | 0 | 46540 | -4770 | 41770 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinan | Individual | ASP | CPR | FOA | 15 | INV | 99 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 337000 | 0 | 337000 | 337000 | 100% | 0 | 0 | 0 | 43810 | 0 | 43810 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shenzhen Shentie Plastics Tableware Products Company, Shenzhen | Individual | ASP | CPR | FOA | 15 | INV | 92 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 345000 | 0 | 345000 | 345000 | 100% | 0 | 0 | 0 | 44850 | 0 | 44850 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guangxing Plastics Products Co., Hubei | Individual | ASP | CPR | FOA | 15 | INV | 91 | A | I | CFC | 36 | 36 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE foam sheet and netting at Feicheng Plastic Products Factory | Individual | ASP | CPR | FOA | 15 | INV | 90 | A | I | CFC | 150 | 150 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-04-01 | 2002-04-01 | 388000 | 0 | 388000 | 388000 | 100% | 0 | 0 | 0 | 50440 | 0 | 50440 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhoushan Fuchuan Plastic Products Factory | Individual | ASP | CPR | FOA | 22 | INV | 206 | N | I | CFC | 61 | 61 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 403711 | -9044.73 | 394666.27 | 394666 | 100% | 0.27 | 0 | 0 | 52482.43 | -1175.43 | 51306.9649 | 0.0351 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Handan No. 7 | Individual | ASP | CPR | FOA | 17 | INV | 126 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 400950 | -446 | 400504 | 400504 | 100% | 0 | 0 | 0 | 52123.5 | -57.5 | 52066 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhejiang Wanpeng Clique Co., Ltd. | Individual | ASP | CPR | FOA | 22 | INV | 202 | N | I | CFC | 120 | 120 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 412666 | -10472.44 | 402193.56 | 402194 | 100% | -0.44 | 0 | 0 | 53646.58 | -1361.58 | 52285.0572 | -0.0572 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Tianjin Gangda | Individual | ASP | CPR | FOA | 18 | INV | 143 | N | I | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1997-05-01 |  | 2000-10-01 | 2003-07-01 | 404250 | -1033 | 403217 | 403217 | 100% | 0 | 0 | 0 | 52552.5 | -133.5 | 52419 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Cangzhou Foreign Trade Packaging Co. | Individual | ASP | CPR | FOA | 17 | INV | 125 | N | I | CFC | 75 | 75 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 450800 | -445 | 450355 | 450355 | 100% | 0 | 0 | 0 | 58604 | -58 | 58546 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Joint Industrial Plastic Corporation, Buotou | Individual | ASP | CPR | FOA | 17 | INV | 127 | N | I | CFC | 90 | 90 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2001-05-01 | 604450 | -446 | 604004 | 604004 | 100% | 0 | 0 | 0 | 78578.5 | -57.5 | 78521 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shijiazhuang Plastic Cement General Factory | Individual | ASP | CPR | FOA | 15 | INV | 87 | A | I | CFC | 160 | 160 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 621000 | 0 | 621000 | 621000 | 100% | 0 | 0 | 0 | 80730 | 0 | 80730 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Foshan No. 3 Plastic Factory | Individual | ASP | CPR | FOA | 15 | INV | 103 | A | I | CFC | 360 | 360 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 1065000 | -1 | 1064999 | 1064999 | 100% | 0 | 0 | 0 | 138450 | 4.6566e-12 | 138450 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of molded foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 09 | INV | 12 | A | I | CFC | 28 | 28 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1993-11-01 | 2003-04-01 | 275000 | 9431 | 284431 | 284431 | 100% | 0 | 0 | 0 | 35750 | 1226 | 36976 | 0 | 0 | Completed in 1993. Financially completed in 2003. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at Al-Sharif Plastic Factories | Individual | AFR | EGY | FOA | 09 | INV | 10 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-03-01 | 1998-12-01 | 1994-06-01 |  | 2001-12-01 | 2003-04-01 | 498000 | -22472 | 475528 | 475528 | 100% | 0 | 0 | 0 | 64740 | -2921 | 61819 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of EPE foam products at Vora Cork Industries | Individual | ASP | IND | FOA | 20 | INV | 101 | A | I | CFC | 39.6 | 39.6 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 2003-07-01 | 2005-09-01 | 264500 | -52153 | 212347 | 212347 | 100% | 0 | 0 | 0 | 34385 | -6780 | 27605 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of extruded polyethylene foam sheet at Camphor and Allied Products Ltd. | Individual | ASP | IND | FOA | 12 | INV | 16 | A | R | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1995-12-01 | 1994-09-01 |  | 1995-12-01 | 1997-12-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at West Indies Synthetics Company, Ltd (Wisynco) | Individual | LAC | JAM | FOA | 22 | INV | 06 | A | I | CFC | 81.6 | 81.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 1998-12-01 | 2000-12-01 | 596000 | -3008.19 | 592991.81 | 592992 | 100% | -0.19 | 0 | 0 | 77480 | -391.0047 | 77089.02 | -0.0247 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam sheet at Jumaya Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 10 | INV | 11 | A | R | CFC | 150 | 150 | 0 | 0 | 1993-06-01 | 1993-12-01 | 1994-12-01 |  | 1993-12-01 | 1997-12-01 | 235811 | 62 | 235873 | 235873 | 100% | 0 | 0 | 0 | 30655.43 | 7.57 | 30663 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polysterene and polyethylene foam sheet at Associated Air-Pack Industries, Sdb. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 21 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 234000 | 17126 | 251126 | 251126 | 100% | 0 | 0 | 0 | 30420 | 2226 | 32646 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-12 in the manufacture of EPS/EPE foam sheet at Pulai Lamipak Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 23 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1994-12-01 |  | 1996-08-01 | 2002-03-01 | 355000 | -17066 | 337934 | 337934 | 100% | 0 | 0 | 0 | 46150 | -2219 | 43931 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the production of polystyrene foam at Productos Moldeados America SR, Ltd. (Promola) | Individual | LAC | PER | FOA | 17 | INV | 09 | A | D | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1998-11-01 | 1999-12-01 | 294960 | 0 | 294960 | 294960 | 100% | 0 | 0 | 0 | 38345 | 0 | 38345 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the residual use of CFC in the manufacture of extruded polystyrene foam sheet at Styrotech Co. | Individual | ASP | PHI | FOA | 13 | INV | 34 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 60000 | -2296.7 | 57703.3 | 57703 | 100% | 0.3 | 0 | 0 | 7800 | -299.001 | 7500.96 | 0.038998 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the residual use of CFC in the manufacture of extruded polystyrene foam sheet in 3 companies: Concept Packaging Co., Amtes Co., and Q.C. Styropackaging Co. | Individual | ASP | PHI | FOA | 12 | INV | 27 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-12-01 | 1995-03-01 |  | 1997-12-01 | 1999-05-01 | 505000 | -230578 | 274422 | 274422 | 100% | 0 | 0 | 0 | 65650 | -29975 | 35675 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at Ponsri | Individual | ASP | THA | FOA | 13 | INV | 36 | A | I | CFC | 125 | 125 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1995-07-01 |  | 1996-06-01 | 2002-03-01 | 340000 | -6035 | 333965 | 333965 | 100% | 0 | 0 | 0 | 44200 | -784.26 | 43415.74 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC-12 and CFC-114 in the manufacture of extruded low density polyethylene foam sheet at Mic-Cell Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 27 | A | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-11-01 | 2001-12-01 | 339500 | -1725.9 | 337774.1 | 337774 | 100% | 0.1 | 0 | 0 | 44135 | -224.367 | 43910.62 | 0.013 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at 2 companies (Tahi Poly Seal Material Industries Co. Ltd, and Food Box Co. Ltd.): Phase I | Individual | ASP | THA | FOA | 12 | INV | 30 | A | R | CFC | 100 | 100 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1995-03-01 |  | 1995-02-01 | 2000-12-01 | 455000 | -2639 | 452361 | 452361 | 100% | 0 | 0 | 0 | 59150 | -343 | 58807 | 0 | 0 | Completed in 1995. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNIDO | Phasing out of CFC-12 at Multiespuma Saic | Individual | LAC | ARG | FOA | 20 | INV | 49 | A | I | CFC | 60 | 60 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2000-12-01 | 2001-11-01 | 282438 | -11981 | 270457 | 270457.47 | 100% | -0.47 | 0 |  | 36717 | -1613 | 35104 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNIDO | Phasing out CFC-12 at Mallol Saic | Individual | LAC | ARG | FOA | 20 | INV | 47 | A | I | CFC | 36.5 | 36.5 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2003-12-01 | 2004-03-01 | 299344 | 0 | 299344 | 299343.73 | 100% | 0.27 | 0 |  | 38915 | -53 | 38862 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNIDO | Phase out of ODS at CELPACK S.A. | Individual | LAC | ARG | FOA | 13 | INV | 10 | A | I | CFC | 135 | 135 |  |  | 1994-07-01 | 1994-12-01 | 1995-07-01 |  | 1995-12-01 | 1998-08-01 | 503094 | 377 | 503471 | 503471 | 100% | 0 | 0 |  | 65402 | 49 | 65451 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Bandex S.A. | Individual | LAC | ARG | FOA | 13 | INV | 09 | A | I | CFC | 214 | 214 |  |  | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1995-11-01 | 1998-08-01 | 517630 | -555 | 517075 | 517075 | 100% | 0 | 0 |  | 67292 | -179 | 67113 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | One-off Phase Out | ASP | CPR | FOA | 35 | INV | 379 | A | I | CFC | 359 | 359 |  |  | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 2450123 | -2605 | 2447518 | 2447518.19 | 100% | -0.19 | 0 |  | 279514 | -287 | 279227 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | Individual | ASP | CPR | FOA | 34 | INV | 376 | A | I | CFC | 750 | 750 |  |  | 2001-07-01 | 2002-02-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 2808338 | 0 | 2808338 | 2808337.9 | 100% | 0.1 | 0 |  | 318917 | 0 | 318917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal umbrella project for the elimination of CFC-12 in manufacturing of EPE foam packaging nets at 30 enterprises | One-off Phase Out | ASP | CPR | FOA | 36 | INV | 387 | A | I | CFC | 849.3 | 849.3 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-12-01 | 2010-04-01 | 1525648 | 2800061 | 4325709 | 4325709 | 100% | 0 | 0 |  | 171352 | 314476 | 485828 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 25 enterprises (umbrella project) | Individual | ASP | CPR | FOA | 25 | INV | 248 | A | I | CFC | 1146 | 1146 |  |  | 1998-07-01 | 1998-12-01 | 2000-01-01 |  | 2000-12-01 | 2002-09-01 | 4488516 | 0 | 4488516 | 4488515.76 | 100% | 0.24 | 0 |  | 583507 | -341 | 583166 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 27 enterprises (Umbrella Project) | Individual | ASP | CPR | FOA | 28 | INV | 301 | A | I | CFC | 825.7 | 825.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 5289441 | 0 | 5289441 | 5289440.76 | 100% | 0.24 | 0 |  | 591839 | -187 | 591652 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNIDO | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at (ADVECHEMS) | Individual | AFR | EGY | FOA | 10 | INV | 16 | A | I | CFC | 196 | 183.3 |  |  | 1993-06-01 | 1994-03-01 | 1994-06-01 |  | 1994-12-01 | 2000-12-01 | 904000 | 0 | 904000 | 904000 | 100% | 0 | 0 |  | 117520 | -44 | 117476 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC 11 and CFC-12 in the manufacture of extruded polyethylene and polystyrene foams through the use of butane as a blowing agent at Romcarbon, S.A. | Individual | EUR | ROM | FOA | 27 | INV | 15 | A | I | CFC | 132.4 | 132.4 |  |  | 1999-03-01 | 2000-04-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 516512 | 0 | 516512 | 516511.83 | 100% | 0.17 | 0 |  | 66816 | -11 | 66805 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polystyrene (EPS) foam for packing purposes at Shanko and Partners Co. | Individual | ASP | SYR | FOA | 38 | INV | 88 | A | I | CFC | 16 | 16 |  |  | 2002-11-01 | 2003-11-01 | 2005-06-01 |  | 2004-08-01 | 2004-12-01 | 132200 | 0 | 132200 | 132200.18 | 100% | -0.18 | 0 |  | 17186 | -23 | 17163 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | I | CFC | 45 | 45 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | 0 | 290481 | 290480.82 | 100% | 0.18 | 0 |  | 37763 | -15 | 37748 | 0 | 0 | FIN
ONG | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Individual | ASP | SAU | FOA | 62 | INV | 12 | A | I | HCFC-22,HCFC-142b | 5.2 |  | 0 |  | 2010-12-01 |  | 2012-12-01 | 2015-12-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 5000 | 14300 | 0 | 0 | 14300 | 0 | Several consultations have been held with ACC; in particular on technology options. Due to ACC joint venture with DOW Chemicals this has been a lengthy process. Furthermore, ACC considers their production technology proprietary. Hence, it has been agreed that the MLF grant will focus on auxiliary equipment enabling usage of flammable blowing agent - and that the modifications related to the extruder will be handled by ACC as part of their co-financing. UNIDO has prepared the TOR for the equipment and is awaiting final approval from the beneficiary. UNIDO has also provided technical assistance to the beneficiary through our International expert. As a summary there were 1. Numerous discussions on technology issues. 2. Several visits by XPS expert. Activites in 2013 are 1. Final commitment on technology. 2. Advertisement of tender. 3. Contract award. | The reason for the low disbursement is that the company is still considering technology options and has not made a decision and final commitment on the conversion technology. | 2010
ONG | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Individual | ASP | SAU | FOA | 62 | INV | 14 | A | I | HCFC-22,HCFC-142b | 1.9 |  | 0 |  | 2010-12-01 |  | 2012-12-01 | 2015-12-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 5000 | 14300 | 0 | 0 | 14300 | 0 | Several consultations have been held with ACC; in particular on technology options. Due to ACC joint venture with DOW Chemicals this has been a lengthy process. Furthermore, ACC considers their production technology proprietary. Hence, it has been agreed that the MLF grant will focus on auxiliary equipment enabling usage of flammable blowing agent - and that the modifications related to the extruder will be handled by ACC as part of their co-financing. UNIDO has prepared the TOR for the equipment and is awaiting final approval from the beneficiary. UNIDO has also provided technical assistance to the beneficiary through our International expert. As a summary there were 1. Numerous discussions on technology issues. 2. Several visits by XPS expert. Activites in 2013 are 1. Final commitment on technology. 2. Advertisement of tender. 3. Contract award. | The reason for the low disbursement is that the company is still considering technology options and has not made a decision and final commitment on the conversion technology. | 2010
ONG | UNDP | Demonstration project for conversion from HCFC-22/HCFC-142b technology to CO2 with methyl formate co-blowing technology in the manufacture of extruded polystyrene foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 64 | DEM | 507 | N | I | HCFC | 12.3 | 3.2 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 | 2013-09-01 |  |  | 1973300 | 0 | 1973300 | 1668300 | 84.54% | 305000 | 0 | 91500 | 147998 | 0 | 125122.9227 | 22875.0773 | 0 | In 2012, the project involved redesign of extruders for three models and testing, trials etc. Activities proceeding as planned. | Targeted completion by end-2013. | 2011 |  | Non-Investment
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Multi-Year | ASP | SAU | FOA | 62 | INV | 13 | A | I | HCFC | 19 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 1103578 | 0 | 1103578 | 10702.98 | 0.9698% | 1092875.02 | 0 | 20000 | 82768 | 0 | 803 | 81965 | 0 | Several consultations have been held with Al-Watania on technology options and their impact on conversion as well as existing operations. Terms of reference for the conversion has been given to Al-Watania and we are awaiting their feedback and endorsement to start the tendering process. UNIDO has prepared the TOR for the equipment and is awaiting final approval from the beneficiary. UNIDO has also provided technical assistance to the beneficiary through our international expert. As a summary there were 1. Numerous discussions on technology issues. 2. Several visits by XPS expert. The reason for the low disbursement is that the company is still considering technology options and has not made a decision and final commitment on the conversion technology. | 1. Final commitment on technology. 2. Advertisement of tender. 3. Contract award. Reason for the extension of the project duration: Consultations on technology options take longer than expected. The reason for the low disbursement is that the company is still considering technology options and has not made a decision and final commitment on the conversion technology. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Multi-Year | ASP | SAU | FOA | 62 | INV | 11 | A | I | HCFC | 28.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 615323 | 0 | 615323 | 16414.12 | 2.668% | 598908.88 | 6010.88 | 5000 | 46149 | 0 | 1231 | 44918 | 451 | Several consultations have been held with ACC; in particular on technology options. Due to ACC joint venture with DOW Chemicals this has been a lengthy process. Furthermore, ACC considers their production technology proprietary. Hence, it has been agreed that the MLF grant will focus on auxiliary equipment enabling usage of flammable blowing agent - and that the modifications related to the extruder will be handled by ACC as part of their co-financing. UNIDO has prepared the TOR for the equipment and is awaiting final approval from the beneficiary. UNIDO has also provided technical assistance to the beneficiary through our international expert. As a summary there were 1. Numerous discussions on technology issues. 2. Several visits by XPS expert. The reason for the low disbursement is that the company has only made a final commitment on the conversion technology in April 2013. The TOR for the conversion is now under development. | 1. Final commitment on technology. 2. Advertisement of tender. 3. Contract award. Reason for the extension of the project duration: Consultations on technology options take longer than expected. The reason for the low disbursement is that the company has only made a final commitment on the conversion technology in April 2013. The TOR for the conversion is now under development. |  |  | INV
CLO | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector | Individual | AFR | ALG | PHA | 37 | PRP | 57 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  |  | 2007-09-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | The TPMP preparation was cancelled by the Government of Algeria long after the work was completely prepared. The results will be used by UNIDO.
CLO | Germany | Project preparation and technical assistance at Arnatoury S.A.R.L., Sin-El-Fil | Individual | ASP | LEB | ARS | 26 | PRP | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented.
CLO | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 |  |  | 2005-11-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 750 | -750 | 0 | 0 | 0 | Funds returned to the 47th ExCom. |  |  |  | Non-INV
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of a methyl bromide project |  | LAC | ECU | FUM | 45 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 |  |  | 2010-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 1875 | -1875 | 0 | 0 | 0 | Funding returned to the MLF. |  |  |  | Non-INV
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | Project prep. cancelled at the 41st ExCom. |  |  |  | Non-INV
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. |  |  |  | Non-INV
CLO | IBRD | Preparation for HCFC phase-out investment activities (domestic air-conditioning sector) |  | ASP | PHI | REF | 59 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  |  | 2012-07-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 | 0 | 4875 | -4875 | 0 | 0 | 0 | Preparation funding returned at the 67th ExCom meeting. |  |  |  | Non-INV
CLO | UNDP | Preparation of 5 projects in the foam sector | Individual | LAC | BRA | FOA | 30 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2004-02-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2004. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 209 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation for two methyl bromide demonstration projects (soil fumigation for flowers, tomatoes, cucumbers and strawberries) | Individual | LAC | BRA | FUM | 24 | PRP | 96 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  |  | 2000-12-01 | 40000 | -31187 | 8813 | 8813 | 100% | 0 | 0 | 0 | 5200 | -4054 | 1146 | 0 | 0 | Canceled in 2000. Financially completed in 2000. |  | 1998 |  | Investment
CLO | UNDP | Preparation of 7 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 343 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 35000 | -35000 | 0 | 0 |  | 0 | 0 | 0 | 4550 | -4550 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 4 projects in the foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 8 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and curcubits) | Individual | AFR | EGY | FUM | 24 | PRP | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 1998-07-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
CLO | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | ELS | FOA | 24 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1998 |  | Investment
CLO | UNDP | Project preparation of the investment components of the RMP | Individual | AFR | ERI | REF | 47 | PRP | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  |  | 2007-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2005 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 252 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | ASP | IND | FOA | 33 | PRP | 296 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 30 | PRP | 254 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Project preparation for foam multiple sub-sectors | Individual | ASP | LAO | FOA | 45 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  |  | 2006-12-01 | 22493 | 0 | 22493 | 22493 | 100% | 0 | 0 | 0 | 1687 | 0 | 1687 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
CLO | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (tobacco) | Individual | AFR | MOZ | FUM | 27 | PRP | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1999 |  | Investment
CLO | UNDP | Formulation of the investment components of theRMP | Individual | ASP | MYA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  |  | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2001. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 78 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Preparation of one project in the flexible foam subsector | Individual | ASP | SYR | FOA | 27 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2004-01-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2002. |  | 1999 |  | Investment
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
CLO | UNDP | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 289 | A | I | HCFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-11-01 | 257000 | -257000 | 0 | 0 |  | 0 | 0 | 0 | 19275 | -19275 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2008. |  | 2008 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | KYR | FOA | 58 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  |  | 2010-12-01 | 30000 | -24996 | 5004 | 5004 | 100% | 0 | 0 | 0 | 2250 | -1874.7 | 375.3 | 0 | 0 | After technical visit in early 2010, and discussions with foam company Winterlux, the company decided to switch to non-HCFC technology itself. The further work on the formulation of investment project proposal was discontinued. MLF Secretariat was informed about this during the submission of HPMP. The PRP is cancelled and unspent funds are to be returned in 2011. |  | 2009 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | KYR | REF | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  |  | 2010-12-01 | 30000 | -23994 | 6006 | 6006 | 100% | 0 | 0 | 0 | 2250 | -1799.55 | 450.45 | 0 | 0 | After technical visit in early 2010, it was recommended to prepare a stand-alone component on technical assistance to HCFC equipment assemblers as a part of HPMP servicing sector. The further work on the formulation of investment project proposal was discontinued. MLF Secretariat was informed about the findings of the mission. Component on HCFC equipment assemblers was included in the original submission of HPMP in August 2010, but during subsequent re-submission of HPMP in December 2010, it was excluded from HPMP design in light of decision 62/14. Funds will be returned in 2011. |  | 2009 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | URT | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  |  | 2010-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 | 0 | 3750 | -3750 | 0 | 0 | 0 | No specific HCFC-141b consuming foam companies were identified by NOU during 2010 and, thus, no technical visits were to be fielded by UNDP, and the funds are to be returned to the MLF Secretariat in 2011 as PRP is cancelled. |  | 2009 |  | Investment
CLO | UNEP | Development of regional halon banking management plan for the Latin American region (Dominican Republic, El Salvador, Chile, Colombia and Peru) | Individual | LAC | LAC | HAL | 29 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2001-06-01 |  |  | 2002-07-01 | 174000 | -174000 | 0 | 0 |  | 0 | 0 | 0 | 22620 | -22620 | 0 | 0 | 0 | Project Closed |  |  |  | Non Investment
CLO | UNEP | Advance for preparation of HPMPs | RMP | GLO | GLO | PHA | 54 | PRP | 290 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-12-01 | 408000 | -408000 | 0 | 0 |  | 0 | 0 | 0 | 53040 | -53040 | 0 | 0 | 0 | Project Closed |  |  |  | Non Investment
CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | AFR | ALG | ARS | 36 | PRP | 52 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of investment project for ODS phase-out in a foam producing plant (SIBAO) | Individual | AFR | BEN | FOA | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 |  | 1995-09-01 |  |  | 1998-08-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
CLO | UNIDO | Project preparation in the aerosol sector | Individual | EUR | BHE | ARS | 30 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-04-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
CLO | UNIDO | Project preparation in the aerosol sector | Individual | LAC | BRA | ARS | 27 | PRP | 127 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 1999-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
CLO | UNIDO | Project preparation for four projects in the solvents (CTC) sector | Individual | LAC | BRA | SOL | 33 | PRP | 205 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  |  | 2003-05-01 | 30000 | -26812 | 3188 | 3188.15 | 100% | -0.15 | 0 |  | 3900 | -3486 | 414 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of umbrella project for ODS phase out in the Aerosol sector (small-scale industries) | Individual | ASP | IND | ARS | 18 | PRP | 53 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-05-01 |  |  | 1997-06-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of an investment project in the fumigant sector | Individual | ASP | IND | FUM | 39 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2004-07-01 | 2004-04-01 |  |  | 2005-12-01 | 35000 | -34038 | 962 | 962.37 | 100% | -0.37 | 0 |  | 2625 | -2553 | 72 | 0 | 0 | CLO
CLO | UNIDO | Project preparation in soil fumigation | Individual | ASP | IRA | FUM | 33 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  |  | 2003-05-01 | 25000 | -19845 | 5155 | 5155 | 100% | 0 | 0 |  | 3250 | -2581 | 669 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of a project for stored commodities (cocoa beans) | Individual | AFR | IVC | FUM | 27 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
CLO | UNIDO | Project formulation for the ODS phase-out in the refrigeration sector | Individual | AFR | IVC | REF | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  |  | 1999-11-01 | 15000 | -84 | 14916 | 14916 | 100% | 0 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | CLO
CLO | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | AFR | KEN | FUM | 30 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of a halon phase-out plan | Individual | ASP | KUW | HAL | 45 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2007-01-01 | 2006-04-01 |  |  | 2010-09-01 | 25000 | -3210 | 21790 | 21790 | 100% | 0 | 0 |  | 1875 | -241 | 1634 | 0 | 0 | CLO |  |  |  | NON-INV
CLO | UNIDO | Preparation of a demonstration project for broccoli, cucurbits, tobacco, seed beds, grain fumigation in El Salvador, Honduras and Nicaragua | Individual | LAC | LAC | FUM | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  |  | 2001-12-01 | 40000 | -29186 | 10814 | 10814 | 100% | 0 | 0 |  | 5200 | -3796 | 1404 | 0 | 0 | CLO
CLO | UNIDO | Preparation of 2 umbrella investment projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 36 | PRP | 47 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Project preparation in the commercial refrigeration sector | Individual | AFR | LIB | REF | 33 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-03-01 |  | 2002-04-01 |  |  | 2003-06-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of a sectoral phase-out plan in the solvents sector | Individual | LAC | MEX | SOL | 36 | PRP | 108 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-07-01 |  |  | 2003-05-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of investment projects in the solvent sector (TCA) | Individual | LAC | MEX | SOL | 39 | PRP | 114 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  |  | 2004-06-01 | 30000 | -18965 | 11035 | 11035.41 | 100% | -0.41 | 0 |  | 2250 | -1424 | 826 | 0 | 0 | CLO
CLO | UNIDO | Preparation of refrigerant management plan | Individual | LAC | NIC | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 |  | 1999-04-01 |  |  | 2001-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of investment project in the aerosol sector | Individual | ASP | PHI | ARS | 27 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of a national ODS phase-out plan | Individual | ASP | SYR | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-10-01 |  |  | 2003-05-01 | 60000 | -56845 | 3155 | 3155.02 | 100% | -0.02 | 0 |  | 7800 | -7390 | 410 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of an investment project in recovery and recycling sector | Individual | ASP | SYR | REF | 18 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-01-01 |  |  | 2001-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  | 1999-12-01
CLO | UNIDO | Preparation of an investment project in the domestic refrigeration sector | Individual | ASP | SYR | REF | 36 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 31 | PRP | 67 | A | I |  | 0 | 0 |  |  | 2000-07-01 |  | 2001-07-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2349 | 7651 | 7651 | 100% | 0 | 0 |  | 1300 | -307 | 993 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
CLO | UNIDO | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 288 | A | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2008-07-01 |  |  | 2008-09-01 | 390000 | -390000 | 0 | 0 |  | 0 | 0 |  | 29250 | -29250 | 0 | 0 | 0 | CLO |  |  |  | NON-INV
COM | Germany | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | ZIM | FOA | 63 | PRP | 43 | A | I | HCFC | 0 |  | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2011-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Zimbabwe identified foam manufacturers who were using pre-blended polyols and a conversion project for the manufacturers was developed and included into the HPMP, which was approved by the Excom at the 65th Excom.
COM | Japan | Preparation of a terminal phase-out management plan | Individual | ASP | MON | PHA | 45 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2005-10-01 |  | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 4407 | 0 | 4407 | 0 | 0
COM | Japan | Preparation for a demonstration project to validate the trans-critical CO2 refrigeration technology for application to ice-block makers at Austin Laz | Individual | AFR | NIR | REF | 61 | PRP | 127 | A | I | HCFC-22 | 0 |  | 0 |  | 2010-07-01 | 2010-11-01 | 2011-07-01 |  | 2012-07-01 |  | 30000 | 0 | 30000 | 27352 | 91.17% | 2648 | 0 | 0 | 3900 | 0 | 3556 | 344 | 0 | Project completed in Jul 2012. |  | 2010
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | BGD | FOA | 57 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-12-01 |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3750 | 0 | 0 | 3750 | 0 | Completed in 2012. Project preparation is complete but some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | BGD | REF | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2010-03-01 |  | 2012-09-01 |  | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | Completed in 2012. Sector survey completed in 2011/2012. | Completed in 2012. Since tonnage required for achieving Stage-I targets was met from the Foams and Servicing Sectors, no project proposals were submitted in this sector. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | BRA | REF | 57 | PRP | 289 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 6000 | 0 | 0 | 6000 | 0 | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the refrigeration manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the refrigeration manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing) | Individual | LAC | BRA | REF | 57 | PRP | 290 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 6000 | 0 | 0 | 6000 | 0 | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the air conditioning manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the air conditioning manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending. | 2009 |  | Investment
COM | UNDP | Preparation of a demonstration project for conversion from HCFC-142b and HCFC-22 technology to methyl formate and co-blowing technology in the manufacture of XPS foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 60 | PRP | 500 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2012-08-01 |  | 30000 | 0 | 30000 | 29251.22 | 97.5% | 748.78 | 0 | 748.78 | 2250 | 0 | 2193.8415 | 56.1585 | 0 | Completed in 2012. Project preparation completed in 2010 and proposal was submitted together with China's HPMP Stage-I to the 64th ExCom meeting in July 2011. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | Preparation of a demonstration project for conversion from HCFC-141b to a combination of isopropyl alcohol and hydrocarbon-based compounds in solvent cleaning applications at Zhejiang KDL Medical Equipment Group Ltd. | Individual | ASP | CPR | SOL | 60 | PRP | 497 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2012-12-01 |  | 30000 | 0 | 30000 | 25085.04 | 83.62% | 4914.96 | 0 | 4914.96 | 2250 | 0 | 1881.378 | 368.622 | 0 | Completed in 2012. Project preparation is complete but some remaining invoices to be settled in 2013. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | DOM | FOA | 57 | PRP | 44 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 |  | 60000 | 0 | 60000 | 48939.57 | 81.57% | 11060.43 | 0 | 11060.43 | 4500 | 0 | 3670.4677 | 829.5322 | 0 | Completed in 2012. All baseline information has been collected from the companies. Some payments still pending. | Completed in 2012. Pending payments have been made. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | ELS | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2012-05-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Completed in 2012. Foam sector plan was approved at 65th ExCom. Pending payments were made. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | IDS | REF | 57 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 |  | 20000 | 0 | 20000 | 16517.04 | 82.59% | 3482.96 | 0 | 3482.96 | 1500 | 0 | 1238.778 | 261.222 | 0 | Completed in 2012. Some remaining payments to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (rigid foam) | Individual | ASP | IRA | FOA | 57 | PRP | 195 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2012-08-01 |  | 30000 | 0 | 30000 | 25396.96 | 84.66% | 4603.04 | 0 | 4603.04 | 2250 | 0 | 1904.772 | 345.228 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IRA | REF | 57 | PRP | 193 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-12-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Completed in 2011. HPMP document was submitted to and approved at the 63rd Excom. | The project is being closed by June 12. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (fire-fighting and solvent sectors) | Individual | ASP | IRA | SOL | 57 | PRP | 194 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-12-01 |  | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2011. See response to IRA/FOA/57/PRP/195 above. | Project targeted for financial closure in 2012 | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | JAM | FOA | 61 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-05-01 |  | 30000 | 0 | 30000 | 29012.7 | 96.71% | 987.3 | 0 | 987.3 | 2250 | 0 | 2175.9525 | 74.0475 | 0 | Completed in 2012. Pending payments made in 2012. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | LEB | FOA | 57 | PRP | 71 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2012-09-01 |  | 25000 | 0 | 25000 | 24356.79 | 97.43% | 643.21 | 0 | 643.21 | 1875 | 0 | 1826.7593 | 48.2407 | 0 | Completed in 2012. Project preparation is complete but some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | LEB | REF | 57 | PRP | 70 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2011. HPMP document was submitted to and approved at the 64th Excom. | Project targeted for financial closure in 2012 | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | LEB | REF | 57 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2011. HPMP document was submitted to and approved at the 64th Excom. | Project targeted for financial closure in 2012 | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | MAL | FOA | 57 | PRP | 164 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-07-01 |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 7500 | 0 | 0 | 7500 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | MAL | REF | 57 | PRP | 163 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-07-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2250 | 0 | 0 | 2250 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | MAL | REF | 57 | PRP | 162 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-06-01 | 2010-03-01 |  | 2012-07-01 |  | 120000 | 0 | 120000 | 91564.78 | 76.3% | 28435.22 | 10712.46 | 28435.22 | 9000 | 0 | 6867.3585 | 2132.6415 | 803.4345 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector plan) | Individual | LAC | MEX | FOA | 58 | PRP | 144 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-04-01 |  | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Completed in 2012. All pending payments made and HPMP was submitted and approved by ExCom 64. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sectors except residential air conditioning) | Individual | ASP | PHI | REF | 59 | PRP | 87 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2010-11-01 |  | 2012-06-01 |  | 65000 | 0 | 65000 | 14941.79 | 22.99% | 50058.21 | 0 | 50058.21 | 4875 | 0 | 1120.6343 | 3754.3657 | 0 | Completed in 2012. Project preparation is complete but some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam and solvent sectors) | Individual | ASP | SRL | MUS | 57 | PRP | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-06-01 |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 3000 | 0 | 0 | 3000 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sector) | Individual | ASP | SRL | REF | 61 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2012-05-01 |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4500 | 0 | 0 | 4500 | 0 | Completed in 2012. Some remaining invoices to be settled in 2013. | Completed in 2012. | 2010 |  | Investment
COM | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in post-harvest sector | Individual | AFR | KEN | FUM | 60 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 |  | 40000 | 0 | 40000 | 36221.79 | 90.55% | 3778.21 | 3652.53 | 3000 | 3000 | 0 | 2717 | 283 | 274 | Project completed.
COM | UNIDO | Preparation of ODS disposal pilot project | Individual | EUR | TUR | DES | 57 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2012-05-01 |  | 60000 | 0 | 60000 | 58248.21 | 97.08% | 1751.79 | 0 | 1000 | 4500 | 0 | 4369 | 131 | 0 | Project completed in May 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam applications) | Individual | EUR | BHE | FOA | 63 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 |  | 30000 | 0 | 30000 | 19803.35 | 66.01% | 10196.65 | 10200 | 8000 | 2250 | 0 | 1485 | 765 | 765 | Project completed in Dec 2012. The overruns and the respective support cost will be corrected in 2013 with the financail services. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | GUA | FOA | 60 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-10-01 | 2011-04-30 |  | 2012-03-01 |  | 60000 | 0 | 60000 | 59635.53 | 99.39% | 364.47 | 0 | 300 | 4500 | 0 | 4473 | 27 | 0 | Project completed in Mar 2012.
COM | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | ASP | KUW | FOA | 63 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 59300.05 | 98.83% | 699.95 | 552.71 | 500 | 4500 | 0 | 4448 | 52 | 41 | The project was completed in December 2012. | N/A. |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning sectors) | Individual | AFR | MOR | REF | 60 | PRP | 65 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 |  | 2011-12-01 |  | 40000 | 0 | 40000 | 30551.84 | 76.38% | 9448.16 | 9448.17 | 9000 | 3000 | 0 | 2291 | 709 | 709 | Project completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | ASP | PAK | REF | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2011-07-01 |  | 120000 | 0 | 120000 | 107226.12 | 89.36% | 12773.88 | 9051.16 | 12000 | 9000 | 0 | 8042 | 958 | 679 | Project completed. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | QAT | FOA | 60 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 |  | 80000 | 0 | 80000 | 40943.51 | 51.18% | 39056.49 | 38165 | 39000 | 6000 | 0 | 3071 | 2929 | 2862 | Project completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SAU | FOA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2010-12-01 |  | 80000 | 0 | 80000 | 71619.34 | 89.52% | 8380.66 | 7714.02 | 8000 | 6000 | 0 | 5371 | 629 | 579 | Project completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | SAU | REF | 60 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2012-12-01 |  | 80000 | 0 | 80000 | 74754.98 | 93.44% | 5245.02 | 1358.97 | 1000 | 6000 | 0 | 5607 | 393 | 102 | HPMP approved at the 68th Excom, project transferred with the HPMP. Project completed in Dec 2012.
COM | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SOA | FOA | 59 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2012-12-01 |  | 150000 | 0 | 150000 | 144247.74 | 96.17% | 5752.26 | 5696.5 | 5000 | 11250 | 0 | 10819 | 431 | 427 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | AFR | SUD | REF | 59 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 58131.71 | 96.89% | 1868.29 | 1665.52 | 203 | 4500 | 0 | 4360 | 140 | 125 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | EUR | TUR | REF | 58 | PRP | 95 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2012-12-01 |  | 150000 | 0 | 150000 | 142054.62 | 94.7% | 7945.38 | 6696.33 | 7000 | 11250 | 0 | 10654 | 596 | 502.2247 | Project completed in Dec 2012. |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | VEN | FOA | 60 | PRP | 115 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-12-01 |  | 100000 | 0 | 100000 | 93943.84 | 93.94% | 6056.16 | 6052.04 | 6000 | 7500 | 0 | 7046 | 454 | 454 | Project completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning manufacturing sector) | Individual | LAC | VEN | REF | 60 | PRP | 116 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2011-12-01 |  | 100000 | 0 | 100000 | 96740.13 | 96.74% | 3259.87 | 2988.26 | 3000 | 7500 | 0 | 7256 | 244 | 224 | Project completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam component) | Individual | ASP | YEM | FOA | 63 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2011-04-01 |  | 2012-03-31 |  | 2012-12-01 |  | 60000 | 0 | 60000 | 33.72 | 0.0562% | 59966.28 | 45000 | 5000 | 4500 | 0 | 3 | 4497 | 3375 | The HPMP of Yemen has been submitted for 68th ExCom. Verification of the PU foam companies couldn't be implemented due to the political unrest and consequent travel restrictions to Yemen for more than 2 years. It has been agreed to postpone the PU component to stage II of the Yemen HPMP. HPMP approved at the 68th Excom, project transferred with the HPMP. Project completed in Dec 2012. | 1. Expert to visit the companys and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. |  |  | NON-INV
FIN | Canada | Project preparation for development of a refrigerant management plan | Individual | LAC | CUB | REF | 25 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1999-06-01 | 1999-01-01 |  | 1999-09-01 | 2000-09-01 | 22600 | 0 | 22600 | 22600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Although previous reports indicated all funds had been disbursed in 2002, US $2,600 were found to be left-over and were returned to the MLF. See letter to Sectretariat. |  | 1998 |  | Non-Inv.
FIN | Canada | Project preparation for the phase-out of methyl bromide |  | LAC | JAM | FUM | 43 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2005-09-01 | 2005-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 1125 | 0 | 1125 | 0 |  | Project proposal completed in September 2005, submitted and approved at ExCom 47. |  | 2004 |  | Non-Inv.
FIN | Canada | Project preparation for a TPMP |  | LAC | STL | PHA | 48 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 | 2008-07-01 | 30000 | -7000 | 23000 | 23000 | 100% | 0 |  | 0 | 3900 | -910 | 2990 | 0 |  | TPMP proposal completed and submitted in April 2007 for ExCom 52. Not all funds were used. Remaining funds returned to Fund. |  | 2006 |  | Non-Inv.
FIN | Canada | Preparation of update of refrigerant management plan | Individual | LAC | STL | REF | 35 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-07-01 |  | 2003-11-01 | 2003-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 |  | 0 | 975 | 0 | 975 | 0 |  | RMP Update was completed and project was submitted in Nov. 2003. |  | 2000 |  | Non-Inv.
FIN | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 100% | 0 |  | 0 | 1500 | -963 | 537 | 0 |  | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
FIN | France | Project preparation of phase out of use of ODS solvent in production of parts working in high voltage conditions |  | ASP | CPR | SOL | 29 | PRP | 327 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-07-01 | 2000-12-01 |  | 2002-09-01 | 2002-09-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 |  | 0 | 1375 | 0 | 1375 | 0 |  | Project completed.
FIN | France | Projects preparation and technical assistance in the halon sector |  | ASP | IRA | HAL | 23 | PRP | 32 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 1999-07-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation/technical assistance for MAC recycling and training in good servicing practices |  | ASP | IRA | REF | 20 | PRP | 18 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1997-08-01 | 1997-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation and technical assistance in the solvent sector |  | ASP | IRA | SOL | 23 | PRP | 23 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation for projects in commercial refrigeration production facilities |  | AFR | IVC | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 1999-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 15000 | -1636 | 13364 | 13364 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. A study on a replacement programme for centrifugal chillers was completed in 2002. It was followed by a proposal on the phase out of CFC emissions in centrifugal chillers through energy related activities. Balance returned at the 57th ExCom.
FIN | France | Refrigeration management plan preparation |  | AFR | IVC | REF | 21 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1998-03-01 | 1998-03-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Project preparation for the commercial refrigeration sector |  | ASP | LEB | REF | 20 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation to establish a CFC and HCFC recovery and recycling centre |  | ASP | LEB | REF | 20 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation in the foam sector (Fofy) |  | AFR | MLI | FOA | 25 | PRP | 04 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1998-08-01 | 1999-01-01 |  | 1998-09-01 | 1998-11-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Project preparation for the formulation of a project to implement a recycling network for CFC-11, CFC-12 and HCFC-22 |  | AFR | MOR | REF | 19 | PRP | 02 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1996-11-01 |  | 1997-04-01 | 1997-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé.
FIN | France | Project preparation for projects in the hotel and fisheries industries and recycling |  | AFR | SEN | REF | 19 | PRP | 06 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1996-12-01 | 10000 | -248 | 9752 | 9752 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Project preparation in the commercial refrigeration sector |  | ASP | SYR | REF | 26 | PRP | 35 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 25000 | -8828 | 16172 | 16172 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector | Individual | AFR | ALG | FOA | 33 | PRP | 49 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30900 | 0 | 30900 | 30900 | 100% | 0 | 0 | 0 | 4017 | 0 | 4017 | 0 | 0 | Project completed. A report has been prepared and will be used in preparation of the terminal phase out plan.
FIN | Germany | Project preparation, technical assistance in the halon sector | Individual | AFR | ALG | HAL | 31 | PRP | 42 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-01-01 | 2002-01-01 |  | 2001-06-01 | 2002-03-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project document submitted and approved.
FIN | Germany | Project preparation in the solvent sector | Individual | AFR | ALG | SOL | 33 | PRP | 48 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed. Strategy will be included in NPP.
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | BOT | REF | 39 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-12-01 | 2005-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project preparation completetd. RMP update to be submitted for approval at 45th Excom
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | EUR | CRO | HAL | 39 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2004-07-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 | 0 | 0 | 2145 | 0 | 2145 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
FIN | Germany | Preparation of a CFC phase out management plan | Individual | LAC | CUB | PHA | 37 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-07-01 | 2004-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
FIN | Germany | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and cucurbits) | Individual | AFR | EGY | FUM | 25 | PRP | 68 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1998-12-01 |  | 1998-08-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implementation of the demonstration
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | EGY | REF | 27 | PRP | 71 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 1999-09-01 | 2002-01-01 | 28700 | 0 | 28700 | 28700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ETH | REF | 37 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ETH | REF | 23 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 1999-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | Germany | Project preparation for additional activities for Gambia RMP | RMP | AFR | GAM | REF | 32 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2004-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project completed and resultant RMP update is being implemented.
FIN | Germany | Project preparation for the phase out of ODS use in the flexible molded foam sub-sector in 5 enterprises | Individual | ASP | IND | FOA | 34 | PRP | 309 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-10-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 2 resultant investment projects were submitted and approved in Mar-02
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector in 5 companies | Individual | ASP | IRA | FOA | 35 | PRP | 118 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-01-01 |  | 2002-09-01 | 2002-12-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 5 projects submitted and approved in Jul-02.
FIN | Germany | Project preparation for the development of a foam sector strategy | Individual | ASP | IRA | FOA | 37 | PRP | 154 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  | 2002-12-01 | 2003-12-01 | 51850 | 0 | 51850 | 51850 | 100% | 0 | 0 | 0 | 6741 | 0 | 6741 | 0 | 0 | Project preparation lead to sector phase out strategy, included in NPOP approved at 41st ExCom.
FIN | Germany | Preparation of a national CFC phase-out plan | Individual | ASP | IRA | PHA | 39 | PRP | 159 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-04-01 | 2004-04-01 |  | 2003-11-01 | 2003-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | National Phase Out Plan has been submitted and appproved at the 41th meeting
FIN | Germany | Development of an investment project for the phase out of methyl bromide in vegetable production | Individual | AFR | KEN | FUM | 30 | PRP | 23 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-08-01 | 2000-12-01 |  | 2002-11-01 | 2003-09-01 | 13360 | 0 | 13360 | 13360 | 100% | 0 | 0 | 0 | 1737 | 0 | 1737 | 0 | 0 | Project initially blocked by 30th ExCom Decision on Kenya. Work completed November 2002. Investtment project approved at 39th ExCom.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | KEN | REF | 23 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for the solvent sector | Individual | AFR | KEN | SOL | 35 | PRP | 26 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2002-11-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed , investment project being implemented
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | LES | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed, TPMP approved at 41st Excom
FIN | Germany | Project preparation and technical assistance at Chem Tech | Individual | AFR | MAR | ARS | 26 | PRP | 09 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2001-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for the phase out of methyl bromide use | Individual | AFR | MAR | FUM | 37 | PRP | 13 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2002-10-01 | 2003-12-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 | 0 | 0 | 1430 | 0 | 1430 | 0 | 0 | A project proposal was prepared but not accepted by the beneficiary. Assistance of beneficiary will now be unter the TPMP approved at 41st ExCom.
FIN | Germany | Project preparation for a CFC terminal phase out management plan | Individual | AFR | MAR | REF | 37 | PRP | 14 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. TPMP approved at 41st Excom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MAR | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1998-03-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | MLW | REF | 37 | PRP | 17 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2004-05-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP approved in June 04
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MLW | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation/technical assistance in the halon sector | Individual | AFR | MOR | HAL | 31 | PRP | 40 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2001-01-01 |  | 2004-12-01 | 2005-06-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project proposal completed and with consent of NOU transferred to UNIDO for implementation.
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | MOZ | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | NAM | PHA | 37 | PRP | 08 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-09-01 | 2004-08-01 | 50250 | 0 | 50250 | 50250 | 100% | 0 | 0 | 0 | 6533 | 0 | 6533 | 0 | 0 | Project completed and TPMP approved at 41st Excom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | NAM | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | AFR | NIR | HAL | 34 | PRP | 87 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 19420 | 0 | 19420 | 19420 | 100% | 0 | 0 | 0 | 2525 | 0 | 2525 | 0 | 0 | Project proposal submitted and approved by MF (37th ExCom).
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | ASP | OMA | HAL | 34 | PRP | 03 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-09-01 | 2002-01-01 |  | 2003-07-01 | 2003-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 | 0 | 2210 | 0 | 2210 | 0 | 0 | Int.consultant visited Oman, nat. consultants identified, Implemenation of the projects will be done by World Bank on request of Oman, results transferred to WB Jul-03. WB TAS-Project approved 41st ExCom.
FIN | Germany | Project preparation for the development of an ODS phase out action plan | Individual | ASP | PNG | PHA | 36 | PRP | 04 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | TPMP for PNG has been approved at the 39th ExCom
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SEY | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-07-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SEY | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-03-01 | 2001-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SWA | REF | 37 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2003-08-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. RMP update approved at 41st Excom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SWA | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation/technical assistance in soil fumigants (methyl bromide) | Individual | ASP | SYR | FUM | 32 | PRP | 70 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2001-09-01 | 2002-03-01 | 37200 | 0 | 37200 | 37200 | 100% | 0 | 0 | 0 | 4836 | 0 | 4836 | 0 | 0 | Project preparation led to project proposal for implementation, which was not accepted because of quantities of illegal MB. Syria is currently complying with its obligations. Only 8 ODP tons will still be eligeable in the future.
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | UGA | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completetd. RMP update approved at 44th ExCom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | UGA | REF | 23 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | URT | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-06-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A RMP update was submitted by Tanzania in 2005
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector | Individual | ASP | YEM | FUM | 34 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ZAM | REF | 37 | PRP | 12 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 07 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | ZIM | PHA | 37 | PRP | 25 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 | 0 | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Project prepared, submitted and then approved at the 44th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of MDI phase-out plan |  | LAC | ARG | ARS | 45 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2008-12-01 | 2005-12-01 |  | 2008-12-01 | 2008-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | With World Bank assistance an Argentinian Strategy for MDIs was prepared, presented to and approved at the 56th ExCom. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  | 1999-12-01 | Non-INV
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100% | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | The proposal is being prepare by the Bank and the INIA |  |  |  | Non-INV
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Proposal will be submitted to the 42nd ExCom Meeting. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100% | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  |  |  | Non-INV
FIN | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2005-07-01 |  | 2007-03-01 | 2007-07-01 | 135500 | 0 | 135500 | 135500 | 100% | 0 | 0 |  | 10163 | 0 | 10163 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100% | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100% | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2004-12-01 |  | 2006-04-01 | 2007-01-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 9375 | 0 | 9375 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. |  |  |  | Non-INV
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 08 | PRP | 24 | N | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). |  |  |  | Non-INV
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of a TCA phase-out project |  | LAC | ECU | SOL | 45 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2005-12-01 |  | 2006-02-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | Results from the survey and seminar carried out in Jan 06 show that there is not enough consumption of TCA in the country, and remaining consumers are changing technologies on their own. A project will not be presented to MLF. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the chiller sector and organization of a workshop |  | GLO | GLO | REF | 46 | PRP | 267 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2005-11-01 | 2005-11-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Chiller Workshop held Sep 05. Findings were used as a basis for development of IA chiller projects, including the Bank's Global Chiller Project. The Global Chiller Project was submitted for ExCom consideration in Nov 05 and US$6.88 million was approved out of the $15 million window. |  |  |  | Non-INV
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 08 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is completed Final report to be issued shortly. |  |  |  | Non-INV
FIN | IBRD | Project preparation funds for the development of a phase-out plan for the MDI sector |  | ASP | IDS | ARS | 46 | PRP | 170 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-09-01 | 2006-07-01 |  | 2008-11-01 | 2008-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 3375 | 0 | 3375 | 0 | 0 | TA for an MDI strategy submitted and approved at the 56th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Sector Plan completed and project document prepared for submission to the ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed and submitted to ExCom. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project submitted to and approved at the 38th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100% | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 07 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation for the second component of the pilot demonstration project on ODS waste management and disposal |  | LAC | MEX | DES | 58 | PRP | 143 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-31 |  | 2012-03-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | Report completed and submitted as an information document to the 66th ExCom. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100% | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support country?s request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Completed. NCPP approved at the 38th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 07 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1994-12-01 | Non-INV
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100% | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. |  |  |  | Non-INV
FIN | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2006-11-01 | 2006-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0 | Project prepared, submitted and approved at the 50th ExCom Meeting. |  |  |  | Non-INV
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation for HCFC phase-out investment activities in the foam sector |  | LAC | ARG | FOA | 64 | PRP | 166 | A | D |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2012-04-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Project approved along with the Argentina HPMP (UNIDO) at the 66th ExCom in April. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (spray foam sector) |  | ASP | CPR | FOA | 57 | PRP | 484 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam insulation for water heaters) |  | ASP | CPR | FOA | 57 | PRP | 485 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam system house) |  | ASP | CPR | FOA | 57 | PRP | 486 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-03-31 |  | 2009-11-01 | 2009-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | Demo. project approved in Nov 09. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (commercial refrigeration sector) |  | ASP | JOR | REF | 60 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-30 |  | 2011-07-01 | 2011-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (additional funding for the commercial refrigeration subsector) |  | ASP | JOR | REF | 61 | PRP | 87 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-08-01 | 2011-07-31 |  | 2011-07-01 | 2011-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV
FIN | IBRD | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning sector) |  | ASP | JOR | REF | 63 | PRP | 89 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-31 |  | 2011-08-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | HCFC air-conditioning sector plan prepared and submitted to the 64th and 65th ExCom Meetings. Sector plan approved in Nov 11. |  |  |  | Non-INV
FIN | IBRD | Preparation for a HCFC foam sector plan |  | ASP | THA | FOA | 61 | PRP | 155 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-01 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV
FIN | IBRD | Preparation for a HCFC air-conditioning sector plan |  | ASP | THA | REF | 61 | PRP | 157 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV
FIN | IBRD | Preparation for a HCFC refrigeration sector plan |  | ASP | THA | REF | 61 | PRP | 156 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HCFC survey completed, stakeholder consultations completed, technical inputs provided and initial HPMP completed. Refrigeration information woven into HPMP. Commerical refrigeration enterprises consuming HCFC-141b were included in the foam sector plan, instead of a separate sector plan. Given a strong interest of the major industry in Thailand to adopt HC technology for the refrigeration circuits, however, components are not widely available at present, the decision was to address the refrigeration circuits under Stage II HPMP. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC foam sector plan |  | ASP | VIE | FOA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. Foam sector plan and HPMP approved at the 63rd ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of a HCFC refrigeration sector plan |  | ASP | VIE | REF | 60 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. ExCom asked that the AC component be removed from the proposed HPMP and action plan at its 63rd meeting. |  |  |  | Non-INV
FIN | Japan | Project preparation assistance for enterprises in the city of Shenzhen for the elimination of CFC-113 and TCA in the production lines of LC display and TV picture tube | Individual | ASP | CPR | SOL | 29 | PRP | 307 | A | I | CFC-113andCTA | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2003-07-01 | 50000 | -30916 | 19084 | 19084 | 100% | 0 |  | 0 | 6500 | -4019 | 2481 | 0 | 0 | Completed. Project proposal prepared but activities incorporated into China Solvent Sector Plan |  | 1999
FIN | Japan | Preparation for HCFC phase-out investment activities (XPS foam manufacturing sector) |  | ASP | MON | FOA | 60 | PRP | 16 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0
FIN | Sweden | Assistance to prepare an RMP update | Individual | EUR | CRO | REF | 36 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2004-03-01 | 2004-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0 | At the 36th meeting in March 2002 Sweden received approval for assisting the Government of Croatia in updating their Refrigerant Management Plan (RMP Update). International and National consultants were contracted in June 2002. A survey of current ODS consumption and use in the servicing sector were conducted followed by a desk study and sector review. Due to ExCom decision regarding Terminal Phase-out Management Plans (TPMP) the Update was submitted in January 2003 as a TPMP, with Sweden as co-implementing agency and UNIDO as lead Implementing Agency, and approved at the 39th ExCom meeting. |  | 2002
FIN | Sweden | Assistance to prepare a terminal phase-out management plan | Individual | EUR | GEO | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | In December 2005 at the 47th Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a Terminal phase-out management plan in Georgia. The final TPMP was submitted to the 50th ExCom meeting and approved. The TPMP is implemented by UNDP as sole implementing agency. |  | 2005
FIN | Sweden | Preparation of a government strategy to reduce and eliminate the use of CFC refrigerants for servicing and installations on-site | Individual | ASP | PHI | REF | 29 | PRP | 59 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2002-08-01 | 2002-11-01 | 141400 | 0 | 141400 | 141400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Detailed discussions with the Philippine authority in charge, Department of Environment and Natural Resources (DENR), on the implementation took place May 2000. International and local consultants were contracted and in November 2000, the first meeting with the involved authorities and the private sector was conducted. The political situation in the Philippines during 2001 caused the project a delay. A RMP outline was adopted in October 2001. During 2002 the project was merged into a NCPP together with the WB. The NCPP was submitted jointly and approved in December 2002 with Sweden as co-implementing agency for TA activities related to the servicing sector. |  | 1999
FIN | Sweden | Assistance to prepare the national CFC phase-out plan (refrigeration servicing sector) | Individual | EUR | ROM | PHA | 43 | PRP | 24 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-04-01 | 2005-07-01 | 59400 | 0 | 59400 | 59400 | 100% | 0 |  |  | 7722 | 0 | 7722 | 0 | 0 | In July 2004, at the 43rd Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a national CFC phase-out plan for the servicing sector in Romania. After recruitment of consultants a mission was held in November 2004. The NCPP was prepared during the autumn 2004 and was approved at the 45th ExCom meeting in April 2005. |  | 2004
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of two projects in the integral skin foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 24 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 21 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation of an umbrella project and three other projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | ARG | FOA | 36 | PRP | 126 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for methyl bromide (tobacco) demonstration project | Individual | LAC | ARG | FUM | 24 | PRP | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in soil fumigation (tobacco) | Individual | LAC | ARG | FUM | 33 | PRP | 120 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of one project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 30 | PRP | 103 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 27 | PRP | 88 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | ARG | REF | 33 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of two project proposals in the commercial refrigeration subsector | Individual | ASP | BAH | REF | 27 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a refrigerant management plan update | Individual | ASP | BAH | REF | 43 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-03-01 |  | 2006-12-01 | 2009-07-01 | 24000 | -1463 | 22537 | 22537 | 100% | 0 | 0 | 0 | 1800 | -109.725 | 1690.275 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BAH | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan for end-users | Individual | LAC | BAR | REF | 42 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | LAC | BAR | REF | 39 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | AFR | BDI | ARS | 33 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | BDI | FOA | 33 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | BDI | PHA | 47 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -3963 | 26037 | 26037.47 | 100% | -0.47 | 0 | 0 | 2250 | -297.005 | 1953.0303 | -0.035254 | 0 | Completed in 2007. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for update of refrigerant management plan | Individual | AFR | BDI | REF | 40 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2004-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially Completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Preparation of two projects in the general foam subsector | Individual | AFR | BEN | FOA | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Formulation of a national phase out plan | Individual | ASP | BGD | PHA | 39 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BGD | REF | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-01-01 |  | 1999-09-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | BHA | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2543 | 12457 | 12457 | 100% | 0 | 0 | 0 | 1950 | -331 | 1619 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation of investment component of the refrigerant management plan | Individual | ASP | BHU | REF | 43 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BOL | FOA | 33 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BOL | FOA | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | -2187 | 22813 | 22813 | 100% | 0 | 0 | 0 | 3250 | -284 | 2966 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | BOL | FUM | 33 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (cotton and soy) | Individual | LAC | BOL | FUM | 27 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BOL | REF | 33 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration (terminal phase-out) sector | Individual | LAC | BOL | REF | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-09-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration and one in domestic refrigeration sub-sectors | Individual | LAC | BOL | REF | 24 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | BOT | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -8880 | 11120 | 11120 | 100% | 0 | 0 | 0 | 2600 | -1154 | 1446 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Preparation of four projects in the foam sector | Individual | LAC | BRA | FOA | 27 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of six projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector (SMEs) | Individual | LAC | BRA | FOA | 30 | PRP | 163 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 207 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of five projects in integral skin foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 202 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation to prepare 16 projects in the foam sector | Individual | LAC | BRA | FOA | 24 | PRP | 98 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 70000 | -12756 | 57244 | 57244 | 100% | 0 | 0 | 0 | 9100 | -1657.9987 | 7442.0013 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of 10 projects in the integral skin foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 160 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 210 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 21 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation of a CFC terminal phase-out programme | Individual | LAC | BRA | PHA | 36 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration sector | Individual | LAC | BRA | REF | 27 | PRP | 122 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 208 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 24 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-07-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of 3 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 30 | PRP | 162 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 27 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for the formulation of CTC as a process agent | Individual | LAC | BRA | SOL | 42 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for solvent and process agent sectors | Individual | LAC | BRA | SOL | 48 | PRP | 276 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 50000 | -9426.22 | 40573.78 | 40573.78 | 100% | 0 | 0 | 0 | 3750 | -706.9665 | 3043.0335 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | BRU | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment component) | Individual | LAC | BZE | REF | 42 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2007-06-01 | 20000 | -1164 | 18836 | 18836 | 100% | 0 | 0 | 0 | 1500 | -87.0018 | 1412.9983 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | AFR | CBI | REF | 42 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | CHD | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | CHD | REF | 37 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-07-01 |  | 2002-12-01 | 2005-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a project in refrigerant recovery/recycling and RMP preparation | Individual | AFR | CHD | REF | 27 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the aerosol (sterilants) subsector | Individual | LAC | CHI | ARS | 30 | PRP | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project for soil fumigation in nurseries and seed beds for apples and kiwis | Individual | LAC | CHI | FUM | 24 | PRP | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 2000-07-01 | 2003-12-01 | 25000 | -11504 | 13496 | 13496 | 100% | 0 | 0 | 0 | 3250 | -1496 | 1754 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for the formulation of commercial refrigeration project | Individual | LAC | CHI | REF | 42 | PRP | 155 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2005-04-01 |  | 2006-12-01 | 2012-04-01 | 32000 | -328.68 | 31671.32 | 31671.32 | 100% | 0 | 0 | 0 | 2400 | -24.65 | 2375.35 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2004 |  | Investment
FIN | UNDP | Formulation of solvent sectoral phase-out plan | Individual | LAC | CHI | SOL | 39 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the sterilants sector | Individual | LAC | CHI | STE | 33 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | COL | DES | 59 | PRP | 74 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2011-12-01 | 2012-08-01 | 40000 | 0 | 40000 | 31325.92 | 78.31% | 8674.08 | 0 | 0 | 3000 | 0 | 2349.444 | 650.556 | 0 | Financially completed in 2012. | Project finalized and submitted to the 66th Executive Committee Meeting. Final invoices pending. | 2009 |  | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | COL | FOA | 30 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | COL | FOA | 33 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | COL | FOA | 24 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-07-01 | 1998-12-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | COL | FOA | 36 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | COL | REF | 36 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2004-06-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | COS | FUM | 33 | PRP | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | COS | PHA | 48 | PRP | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-07-01 | 2010-07-01 | 30000 | -2379.32 | 27620.68 | 27620.68 | 100% | 0 | 0 | 0 | 2250 | -178.449 | 2071.551 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration subsector | Individual | LAC | COS | REF | 24 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of ten projects in the integral skin foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 278 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2005-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for 10 projects in the rigid and integral skin foam sub-sectors | Individual | ASP | CPR | FOA | 24 | PRP | 241 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of 16 projects in general foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 272 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration subsector (hydrocarbons) | Individual | ASP | CPR | REF | 30 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 35000 | -7211.9604 | 27788.0396 | 27788 | 100% | 0.0396 | 0 | 0 | 4550 | -937.997 | 3611.9979 | 0.0051474 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the domestic refrigeration (hydrocarbon) subsector | Individual | ASP | CPR | REF | 24 | PRP | 239 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 22 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 33 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the MDI sector | Individual | LAC | CUB | ARS | 36 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 30000 | 20000 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3900 | 1500 | 5400 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 59 | PRP | 45 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2010-11-01 |  | 2010-11-01 | 2012-04-01 | 40000 | -1261.09 | 38738.91 | 38738.91 | 100% | 0 | 0 | 0 | 3000 | -94.58 | 2905.42 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | DJI | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | DJI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | DOM | FOA | 36 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2005-07-01 | 2006-06-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | DOM | FOA | 33 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a project in the general foam subsector | Individual | LAC | DOM | FOA | 27 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | DOM | PHA | 42 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-05-01 | 2006-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 563 | 0 | 563 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | DOM | REF | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sub-sector | Individual | LAC | DOM | REF | 22 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for one project in commercial refrigeration subsector | Individual | LAC | DOM | REF | 24 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation of investment activities of the RMP | Individual | LAC | DOM | REF | 36 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the solvent sector | Individual | LAC | DOM | SOL | 36 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of terminal project in the foam sector | Individual | AFR | DRC | FOA | 39 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | DRC | FOA | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock sector | Individual | AFR | DRC | FOA | 36 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | DRC | REF | 39 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in recovery and recycling refrigeration sector | Individual | AFR | DRC | REF | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for refrigeration end-user | Individual | AFR | DRC | REF | 45 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-07-01 | 2006-12-01 | 16870 | 0 | 16870 | 16870 | 100% | 0 | 0 | 0 | 1265 | 0 | 1265 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | EGY | FOA | 21 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 40000 | -7520 | 32480 | 32480 | 100% | 0 | 0 | 0 | 5200 | -978 | 4222 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | FOA | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-01-01 |  | 1994-12-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation to prepare one halon sector programme | Individual | AFR | EGY | HAL | 24 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 2000-10-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | ELS | PHA | 48 | PRP | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-08-01 | 30000 | -4831 | 25169 | 25169.03 | 100% | -0.03 | 0 | 0 | 2250 | -362.352 | 1887.6502 | -0.00225 | 0 | Completed in 2007.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2006 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | LAC | ELS | REF | 37 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-11-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 2275 | 0 | 2275 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the refrigeration sectors | Individual | LAC | ELS | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 45000 | -3239 | 41761 | 41761 | 100% | 0 | 0 | 0 | 5850 | -421 | 5429 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for complete ODS phase-out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2006-07-01 | 2009-12-01 | 16870 | -6870 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1265 | -514.9982 | 750.0018 | 0 | 0 | Completed in 2006. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | GAB | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-07-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | GAB | REF | 37 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | GAB | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-11-01 | 2002-03-01 | 20000 | -5395 | 14605 | 14605 | 100% | 0 | 0 | 0 | 2600 | -701 | 1899 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | GAM | FOA | 21 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-05-01 | 2002-03-01 | 20000 | -6548 | 13452 | 13452 | 100% | 0 | 0 | 0 | 2600 | -851 | 1749 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | GBS | REF | 39 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 57 | PRP | 29 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-05-01 | 30000 | -4400 | 25600 | 25600 | 100% | 0 | 0 | 0 | 2250 | -330 | 1920 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | Project preparation in soil fumigation (curcubits) | Individual | AFR | GHA | FUM | 33 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | GHA | PHA | 47 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-08-01 | 30000 | -609 | 29391 | 29391 | 100% | 0 | 0 | 0 | 2250 | -46.005 | 2203.995 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2005 |  | Investment
FIN | UNDP | Preparation of 6 projects in the recovery/recycling refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 204 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 6 projects in the end-user commercial refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 205 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2005-11-01 |  | 2005-12-01 | 2010-10-01 | 122000 | -919.35 | 121080.65 | 121080.65 | 100% | 0 | 0 | 0 | 9150 | -68.9513 | 9081.0487 | 0 | 0 | Financially completed in 2010. |  | 2005 |  | Investment
FIN | UNDP | Preparation of refrigerant management plans (Bahamas, Bangladesh, Botswana, Dominican Republic, El Salvador, Gabon, Mozambique, Niger, Lesotho, Trinidad and Tobago) | Individual | GLO | GLO | REF | 22 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 140000 | -2 | 139998 | 139998 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | GUA | FOA | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment components) | Individual | AFR | GUI | REF | 42 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | GUY | PHA | 48 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-07-01 | 15000 | -12 | 14988 | 14987.66 | 100% | 0.34 | 0 | 0 | 1125 | -0.9 | 1124.0745 | 0.0255 | 0 | Completed in 2007.Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | HAI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of the RMP update proposal | RMP-Component | LAC | HON | REF | 41 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-09-01 | 15000 | -2000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1125 | -150 | 975 | 0 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | IDS | FOA | 24 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IDS | REF | 24 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IDS | REF | 33 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | IDS | REF | 36 | PRP | 137 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2740 | 17260 | 17260 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | ASP | IDS | REF | 36 | PRP | 138 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 35000 | -5430 | 29570 | 29570 | 100% | 0 | 0 | 0 | 4550 | -706 | 3844 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | IDS | REF | 21 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Preparation of two projects in aerosol sector | Individual | ASP | IND | ARS | 27 | PRP | 201 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | IND | ARS | 33 | PRP | 298 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the aerosol sector | Individual | ASP | IND | ARS | 24 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-06-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the aerosol sector | Individual | ASP | IND | ARS | 36 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | ASP | IND | FOA | 33 | PRP | 297 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IND | FOA | 33 | PRP | 299 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of 6 projects in the integral skin foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 250 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of an umbrella project in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of seven projects in rigid foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 206 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation to prepare 10 projects in the foam sector | Individual | ASP | IND | FOA | 24 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | ASP | IND | FOA | 36 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 40000 | -6328 | 33672 | 33672 | 100% | 0 | 0 | 0 | 5200 | -823 | 4377 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of ten projects in general foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 194 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the non-recycling halon sector | Individual | ASP | IND | HAL | 33 | PRP | 294 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2003-06-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 5 halon extinguisher projects | Individual | ASP | IND | HAL | 24 | PRP | 166 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IND | REF | 24 | PRP | 169 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | ASP | IND | REF | 36 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IND | REF | 33 | PRP | 293 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of five projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 27 | PRP | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 143 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 141 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 142 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 77 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of four projects in the integral skin foam subsector | Individual | ASP | IRA | FOA | 27 | PRP | 40 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the domestic refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of 3 projects in the domestic refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Prepare 2 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Preparation of three projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the manufacturing of refrigeration equipment sector (terminal phase-out) | Individual | ASP | IRA | REF | 36 | PRP | 147 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 35000 | -5431 | 29569 | 29569 | 100% | 0 | 0 | 0 | 4550 | -706 | 3844 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | JAM | REF | 30 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2002-05-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Formulation of the solvent sectoral phase out plan | Individual | LAC | JAM | SOL | 39 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | KAM | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | ASP | KAM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 15000 | -1844 | 13156 | 13156 | 100% | 0 | 0 | 0 | 1950 | -240 | 1710 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the soil fumigant sector (cut flowers) | Individual | AFR | KEN | FUM | 36 | PRP | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of solvent sectoral phase-out plan | Individual | AFR | KEN | SOL | 42 | PRP | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2007-09-01 | 2010-10-01 | 20000 | -1850.32 | 18149.68 | 18149.68 | 100% | 0 | 0 | 0 | 1500 | -138.774 | 1361.226 | 0 | 0 | Financially completed in 2010. |  | 2004 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | ASP | KYR | PHA | 47 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -908.45 | 29091.55 | 29091.55 | 100% | 0 | 0 | 0 | 2250 | -68.1337 | 2181.8663 | 0 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Formulation of a terminal phase out project in the foam sector | Individual | ASP | LAO | FOA | 39 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | LAO | FOA | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of four projects in the aerosol sector | Individual | ASP | LEB | ARS | 27 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | LEB | FOA | 33 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 12000 | -1934 | 10066 | 10066 | 100% | 0 | 0 | 0 | 1560 | -251 | 1309 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of project in the foam subsector | Individual | ASP | LEB | FOA | 27 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for one methyl bromide alternative demonstration project | Individual | ASP | LEB | FUM | 25 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-08-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | ASP | LEB | FUM | 33 | PRP | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a CFC terminal programme | Individual | ASP | LEB | PHA | 36 | PRP | 48 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-12-01 | 2007-03-01 | 15000 | -3601 | 11399 | 11399 | 100% | 0 | 0 | 0 | 1950 | -468 | 1482 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of a CFC phase-out plan | Individual | ASP | LEB | PHA | 42 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2004-12-01 | 2005-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2004 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | LES | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-06-01 | 2002-03-01 | 20000 | -2704 | 17296 | 17296 | 100% | 0 | 0 | 0 | 2600 | -352 | 2248 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-12-01 | 2007-03-01 | 20000 | -9146 | 10854 | 10854 | 100% | 0 | 0 | 0 | 2600 | -1189 | 1411 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | LIB | FOA | 33 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | -1934 | 23066 | 23066 | 100% | 0 | 0 | 0 | 3250 | -251 | 2999 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 30 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -9677.8005 | 20322.1995 | 20322 | 100% | 0.1995 | 0 | 0 | 3900 | -1257.9989 | 2641.9752 | 0.025936 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of three projects in rigid foam subsector | Individual | ASP | MAL | FOA | 27 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 24 | PRP | 108 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the soil fumigant sector | Individual | ASP | MAL | FUM | 36 | PRP | 146 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-11-01 | 10000 | -947 | 9053 | 9053 | 100% | 0 | 0 | 0 | 1300 | -123 | 1177 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of fumigant methyl bromide | Individual | ASP | MAL | FUM | 42 | PRP | 150 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-01-01 | 2006-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project (timber) | Individual | ASP | MAL | FUM | 24 | PRP | 109 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-11-01 | 2004-12-01 | 30000 | -983 | 29017 | 29017 | 100% | 0 | 0 | 0 | 3900 | -128 | 3772 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | MAL | REF | 30 | PRP | 134 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 20000 | -4121.1202 | 15878.8798 | 15879 | 100% | -0.1202 | 0 | 0 | 2600 | -536.997 | 2063.0186 | -0.015617 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of two projects in commercial refrigeration subsector | Individual | ASP | MAL | REF | 27 | PRP | 117 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of projects in the refrigeration and foam sectors | Individual | AFR | MAR | REF | 12 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MAU | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | MAU | REF | 39 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | MEX | FOA | 30 | PRP | 94 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of three projects in the foam sector | Individual | LAC | MEX | FOA | 27 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-07-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for 5 projects in the foam sector | Individual | LAC | MEX | FOA | 24 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the storage fumigant sector | Individual | LAC | MEX | FUM | 36 | PRP | 105 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 methyl bromide (flowers and crop storage) alternative demonstration projects | Individual | LAC | MEX | FUM | 24 | PRP | 80 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the recycling halon sector | Individual | LAC | MEX | HAL | 33 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for a halon sector phase out programme | Individual | LAC | MEX | HAL | 24 | PRP | 76 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-12-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MLI | PHA | 48 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2010-01-01 | 12000 | -1262 | 10738 | 10737.55 | 100% | 0.45 | 0 | 0 | 900 | -94.65 | 805.3162 | 0.03375 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 22 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide (tobacco) alternative demonstration project | Individual | AFR | MLW | FUM | 24 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-02-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | MLW | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | EUR | MOL | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -2380.8 | 9619.2 | 9619.2 | 100% | 0 | 0 | 0 | 900 | -178.56 | 721.44 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Project preparation for the RMP proposal | RMP-Component | EUR | MOL | REF | 41 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | MON | REF | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | AFR | MOR | FOA | 24 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MOR | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 80000 | -13195 | 66805 | 66805 | 100% | 0 | 0 | 0 | 10400 | -1715 | 8685 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | MOZ | REF | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -1643 | 18357 | 18357 | 100% | 0 | 0 | 0 | 2600 | -214 | 2386 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration subsector | Individual | ASP | NEP | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2001-12-01 | 20000 | -15000 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2600 | -1950 | 650 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a refrigeration recovery and recycling project | Individual | ASP | NEP | REF | 27 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-07-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for the refrigerant management plan update | Individual | ASP | NEP | REF | 43 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2005-07-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | NER | REF | 37 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-11-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | NER | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-03-01 | 2002-03-01 | 20000 | -3085 | 16915 | 16915 | 100% | 0 | 0 | 0 | 2600 | -401 | 2199 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for the formulation of transitional strategy for aerosol inhalant drug products | Individual | LAC | NIC | ARS | 42 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-07-01 | 2005-04-01 |  | 2008-03-01 | 2009-07-01 | 30000 | -44 | 29956 | 29955.76 | 100% | 0.24 | 0 | 0 | 2250 | -3.3 | 2246.682 | 0.018 | 0 | Completed in 2008.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Preparation of the RMP update proposal (investment component) | RMP-Component | LAC | NIC | REF | 41 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-11-01 | 15000 | -36 | 14964 | 14964 | 100% | 0 | 0 | 0 | 1125 | -3 | 1122 | 0 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Preparation of three projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation | Individual | AFR | NIR | FOA | 26 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 82 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of 8 projects in the general foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Preparation of seven projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-04-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | AFR | NIR | FOA | 36 | PRP | 100 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | NIR | FOA | 21 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | AFR | NIR | REF | 36 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-11-01 | 40000 | -1 | 39999 | 39999 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAN | FOA | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2637 | 12363 | 12363 | 100% | 0 | 0 | 0 | 1950 | -343 | 1607 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for update of refrigerant management plan (investment components) | Individual | LAC | PAN | REF | 40 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAR | FOA | 22 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | PAR | PHA | 47 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -2720.43 | 27279.57 | 27279.57 | 100% | 0 | 0 | 0 | 2250 | -204.0323 | 2045.9677 | 0 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | LAC | PAR | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-10-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | PAR | REF | 33 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | PER | FOA | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a project in general foam subsector | Individual | LAC | PER | FOA | 27 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | LAC | PER | FUM | 24 | PRP | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2000-06-01 | 2002-12-01 | 25000 | -863 | 24137 | 24137 | 100% | 0 | 0 | 0 | 3250 | -112 | 3138 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | LAC | PER | REF | 39 | PRP | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | ASP | PHI | FOA | 30 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 15000 | -3090.8402 | 11909.1598 | 11909 | 100% | 0.1598 | 0 | 0 | 1950 | -400.9952 | 1548.984 | 0.020785 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | ASP | PHI | FUM | 25 | PRP | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 1999-08-01 |  | 2000-12-01 | 2004-12-01 | 30000 | -358 | 29642 | 29642 | 100% | 0 | 0 | 0 | 3900 | -47 | 3853 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | PHI | REF | 21 | PRP | 47 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 2000-12-01 | 35000 | -4264 | 30736 | 30736 | 100% | 0 | 0 | 0 | 4550 | -554 | 3996 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation to prepare the second and final phase for phaseout of ODS by solvent blenders | Individual | ASP | PHI | SOL | 24 | PRP | 54 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 1999-11-01 | 25000 | -22120 | 2880 | 2880 | 100% | 0 | 0 | 0 | 3250 | -2876 | 374 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | PRC | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -11833 | 167 | 167 | 100% | 0 | 0 | 0 | 900 | -887.475 | 12.525 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | AFR | PRC | REF | 34 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-09-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | RWA | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3806 | 8194 | 8194.03 | 100% | -0.03 | 0 | 0 | 900 | -285.45 | 614.5522 | -0.00225 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | RWA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Formulation of a refrigerant management plan | Individual | AFR | RWA | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for a halon sectoral phase-out plan | Individual | AFR | SIL | HAL | 45 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2006-12-01 | 2011-11-01 | 16870 | -7907.55 | 8962.45 | 8962.45 | 100% | 0 | 0 | 0 | 1265 | -592.9491 | 672.0509 | 0 | 0 | Completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | SIL | PHA | 48 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-12-01 | 2011-11-01 | 12000 | -1361.25 | 10638.75 | 10638.75 | 100% | 0 | 0 | 0 | 900 | -102.09 | 797.91 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Formulation of refrigerant management plan | Individual | AFR | SOM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2005-11-01 | 2005-12-01 | 15000 | -14659 | 341 | 341 | 100% | 0 | 0 | 0 | 1950 | -1906 | 44 | 0 | 0 | Completed in 2005. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the fumigant sector | Individual | ASP | SRL | FUM | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2002-11-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation assistance for the methyl bromide sector | Individual | ASP | SRL | FUM | 25 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-06-01 | 2004-12-01 | 25000 | -1090 | 23910 | 23910 | 100% | 0 | 0 | 0 | 3250 | -142 | 3108 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for one project in the solvent sector | Individual | ASP | SRL | SOL | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | STP | REF | 39 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-06-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | LAC | SUR | REF | 42 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | SUR | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | SYR | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-09-01 | 2007-03-01 | 20000 | -6865 | 13135 | 13135 | 100% | 0 | 0 | 0 | 2600 | -892.45 | 1707.55 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 30 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of three projects in the domestic refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 43 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the aerosol sector | Individual | ASP | THA | ARS | 24 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the foam sector | Individual | ASP | THA | FOA | 24 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of six projects in general foam subsector | Individual | ASP | THA | FOA | 27 | PRP | 114 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | TOG | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3712.5 | 8287.5 | 8287.5 | 100% | 0 | 0 | 0 | 900 | -278.4375 | 621.5625 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | TOG | REF | 36 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 1 project in the aerosol sector | Individual | LAC | TRI | ARS | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for the RMP update | Individual | LAC | TRI | REF | 38 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2002-12-01 | 2003-12-01 |  | 2003-07-01 | 2006-06-01 | 13500 | -3905 | 9595 | 9595 | 100% | 0 | 0 | 0 | 1755 | -508 | 1247 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | UGA | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation to formulate one flexible foam sector project | Individual | AFR | URT | FOA | 24 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-03-01 | 2009-08-01 | 30000 | -18 | 29982 | 29982.4 | 100% | -0.4 | 0 | 0 | 2250 | -1.35 | 2248.68 | -0.03 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 707.85 | 5907.85 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -284.96 | 1015.04 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81.25 | 2518.75 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142.48 | 507.52 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251.42 | 1698.58 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | ARM | REF | 57 | PRP | 04 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-04-01 | 30000 | -3538.57 | 26461.43 | 26461.43 | 100% | 0 | 0 | 0 | 2250 | -265.39 | 1984.61 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BRA | FOA | 57 | PRP | 287 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-07-01 | 2012-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2012. | Completed in 2011. Sector Foam projects approved by the 64th Executive Committee Meeting. Some remaining invoices pending. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | LAC | BRA | SOL | 57 | PRP | 291 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2012-12-01 | 48000 | 0 | 48000 | 0 | 0% | 48000 | 0 | 0 | 3600 | 0 | 0 | 3600 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CHI | FOA | 57 | PRP | 167 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | 0 | 50000 | 34203.71 | 68.41% | 15796.29 | 0 | 0 | 3750 | 0 | 2565.2782 | 1184.7217 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | LAC | CHI | REF | 57 | PRP | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | 0 | 50000 | 11634.23 | 23.27% | 38365.77 | 0 | 0 | 3750 | 0 | 872.5672 | 2877.4327 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | COL | FOA | 57 | PRP | 72 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2010-03-01 |  | 2010-12-01 | 2012-05-01 | 150000 | -23032.64 | 126967.36 | 126967.36 | 100% | 0 | 0 | 0 | 11250 | -1727.45 | 9522.55 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for validation of low-cost hydrocarbon in foams | Individual | AFR | EGY | FOA | 57 | PRP | 99 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 | 2012-04-01 | 30000 | -7208 | 22792 | 22792 | 100% | 0 | 0 | 0 | 2250 | -540.6 | 1709.4 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | GEO | REF | 57 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2010-12-01 | 2011-08-01 | 30000 | -0.78 | 29999.22 | 29999.22 | 100% | 0 | 0 | 0 | 2250 | -0.06 | 2249.94 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IDS | REF | 57 | PRP | 185 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 5250 | 0 | 5250 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | NIR | FOA | 57 | PRP | 123 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-10-01 | 50000 | 0 | 50000 | 30117.01 | 60.23% | 19882.99 | 0 | 0 | 3750 | 0 | 2258.7757 | 1491.2242 | 0 | Completed. Foam sector plan submitted as part of the HPMP approved at 62nd ExCom meeting. Final invoices expected in 2011. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | AFR | SWA | REF | 57 | PRP | 14 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 30000 | -13037.08 | 16962.92 | 16962.92 | 100% | 0 | 0 | 0 | 2250 | -977.78 | 1272.22 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | ANT | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1998-09-01 | 1999-04-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3900 | -650 | 3250 | 0 | 0 | Project financially completed. ($969 plus $126 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Development of RMP | RMP | LAC | BAR | REF | 30 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-05-01 | 2005-07-01 | 30000 | -7982 | 22018 | 22018 | 100% | 0 | 0 | 0 | 3900 | -1037.66 | 2862.34 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | BEN | REF | 27 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2000-12-01 | 2001-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation request for TPMP | Individual | AFR | BKF | PHA | 47 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. ($ 631 plus $ 82 PSC returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | BKF | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | BOL | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 2001-01-01 | 1999-02-01 |  | 2001-12-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of RMP | RMP | ASP | BRU | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-11-01 | 2009-12-01 | 30000 | -15500 | 14500 | 14500 | 100% | 0 | 0 | 0 | 3900 | -2015 | 1885 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | BZE | REF | 41 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 15000 | -1250 | 13750 | 13750 | 100% | 0 | 0 | 0 | 1950 | -163 | 1787.5 | -0.5 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | CAF | REF | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2001-05-01 | 2002-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CHD | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-01-01 | 2011-10-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a TPMP | Individual | AFR | COI | PHA | 47 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | COI | REF | 27 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2000-04-01 |  | 2001-09-01 | 2001-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($2,000 plus $260 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | DJI | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-03-01 | 2009-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of refrigerant management plan | RMP | LAC | DMI | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2006-08-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2005-11-01 | 2006-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. ($17,650 plus $2,295 PSC returned ExCom 46 $ -4184 plus $ -544 returned from ExCom 48) |  |  |  | Non Investment
FIN | UNEP | Development of a refrigerant management plan | RMP | ASP | DRK | REF | 35 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2002-08-01 |  | 2003-06-01 | 2005-05-01 | 60000 | -13466 | 46534 | 46534 | 100% | 0 | 0 | 0 | 7800 | -1750.5 | 6049.42 | 0.08 | 0 | Project financially completed. ($ 5,486 plus $ 713 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Development of a total ODS phase out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-11-01 | 2006-03-01 | 15000 | -83 | 14917 | 14917 | 100% | 0 | 0 | 0 | 1950 | -11 | 1939.21 | -0.21 | 0 | Project financially completed. ($ 24,500 plus $ 3,185 returned to ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | FIJ | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1999-11-01 | 2002-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($1,811 plus $235 PSC returned to ExCom 57) |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAB | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2008-05-01 | 2009-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. ($ 10,000 plus $ 1,300 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | AFR | GAM | REF | 23 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 264 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2007-02-01 | 2011-03-01 | 40000 | -8548 | 31452 | 31452 | 100% | 0 | 0 | 0 | 5200 | -1111.24 | 4088.76 | 0 | 0 | Project completed in May 2010. First tranche was approved in November 2007 at the 53rd Meeting of the ExCom. Currently ongoing. The following activities have been delivered: 85 technicians were trained in good practices, 2 meetings with GARVA were held with technicians, a new executive was nominated among technicians, equipment was purchased for a total of USD 96,099, 51 customs officers were trained, training and public awareness materials were produced, Code of Good Practice manual for refrigeration technicians production initiated. |  |  |  | Non Investment
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | GRN | REF | 46 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-09-01 | 2009-12-01 | 15000 | -337 | 14663 | 14663 | 100% | 0 | 0 | 0 | 1950 | -43.81 | 1906.19 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a country programme/RMP | RMP | AFR | GUI | REF | 39 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2004-11-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | GUI | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 2000-01-01 | 2001-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUY | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2009-06-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | GUY | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-12-01 | 30000 | -4000 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3900 | -520 | 3380 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | HON | REF | 41 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2008-12-01 | 15000 | -628 | 14372 | 14372 | 100% | 0 | 0 | 0 | 1950 | -82 | 1868.36 | -0.36 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of country programme and national phase-out plan | RMP | ASP | IRQ | PHA | 55 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-07-01 | 2009-07-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | IVC | PHA | 48 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 15000 | -9 | 14991 | 14991 | 100% | 0 | 0 | 0 | 1950 | -1.17 | 1948.83 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | JAM | REF | 24 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-02-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | AFR | MAG | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2005-12-01 |  | 2005-06-01 | 2007-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAU | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. ($ 0 plus $ 7 PSC returned to ExCom 49$ 0 plus $ -7 PSC returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Development of an RMP | Individual | AFR | MAU | REF | 33 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2003-12-01 |  | 2003-12-01 | 2011-03-01 | 60000 | -25000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 7800 | -3250 | 4550 | 0 | 0 | Project completed in December 2010. |  |  |  | Non Investment
FIN | UNEP | Development of RMP | RMP | ASP | MDV | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-04-01 |  | 2002-09-01 | 2003-09-01 | 30000 | -1849 | 28151 | 28151 | 100% | 0 | 0 | 0 | 3900 | -240.37 | 3659.63 | 0 | 0 | Project financially completed. ($ 5,500 plus $ 715 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLI | PHA | 48 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | MLI | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. ($ 18,414 plus $ 2,394 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Preparation of the RMP update | RMP update | AFR | MLI | REF | 43 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2009-02-01 | 2005-07-01 |  | 2005-11-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | EUR | MOL | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. ($ 7,349 plus $ 955 returned at ExCom 53) |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | MOR | REF | 27 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-04-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -4984 | 25016 | 25016 | 100% | 0 | 0 | 0 | 3900 | -647.92 | 3252.08 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | MYA | REF | 29 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2000-12-01 |  | 2005-04-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | ASP | NEP | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-06-01 | 2000-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. ($ 19,400 plus $ 2,522 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | NER | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP update | LAC | NIC | REF | 41 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2004-12-01 |  | 2005-02-01 | 2007-01-01 | 15000 | -900 | 14100 | 14100 | 100% | 0 | 0 | 0 | 1950 | -117 | 1833 | 0 | 0 | Project financially completed. ($ 3,825 plus $ 497 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Project preparation for refrigerant management plan update | RMP update | LAC | PAN | REF | 40 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-03-01 | 2004-07-01 |  | 2004-10-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plans | RMP | LAC | PAN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of the refrigerant management plan update proposal | RMP Update | LAC | PER | REF | 37 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-02-01 | 2003-08-01 |  | 2004-07-01 | 2008-12-01 | 15000 | -3000 | 12000 | 12000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. ($ 8,880 plus $ 1,154 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | PRC | PHA | 48 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | -9 | 17991 | 17991 | 100% | 0 | 0 | 0 | 2340 | -1.17 | 2338.83 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | PRC | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | RWA | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of the refrigerant management plan | RMP | ASP | SAM | SEV | 25 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-12-01 |  | 2000-12-01 | 2002-06-01 | 0 | 30000 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 3900 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SEN | PHA | 48 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. ($ 37 plus $ 5 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | SEN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 2000-12-01 | 2001-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SIL | PHA | 48 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 18000 | -4986 | 13014 | 13014 | 100% | 0 | 0 | 0 | 2340 | -648.18 | 1691.82 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | LAC | STK | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-03-01 | 2008-12-01 | 15000 | -3460 | 11540 | 11540 | 100% | 0 | 0 | 0 | 1950 | -450 | 1500.2 | -0.2 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | STK | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-09-01 | 1998-03-01 |  | 1998-03-01 | 1999-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a refrigeration management plan | RMP | LAC | STL | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-03-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 | 0 | 0 | 1950 | -130 | 1820 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | STV | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2005-12-01 |  | 2005-11-01 | 2010-12-01 | 20000 | -3250.32 | 16749.68 | 16750 | 100% | -0.32 | 0 | -0.32 | 2600 | -422.54 | 2177.5 | -0.04 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | SYR | REF | 23 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | TOG | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-06-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | TOG | REF | 35 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-08-01 |  | 2002-10-01 | 2007-02-01 | 60000 | -20927 | 39073 | 39073 | 100% | 0 | 0 | 0 | 7800 | -2720.51 | 5079.49 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 6,164 plus $ 801 PSC returned to ExCom 53$ 6,000 plus $ 780 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 2001-09-01 | Non Investment
FIN | UNIDO | Preparation of a recovery and recycling projects in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia and Senegal | Individual | AFR | AFR | REF | 17 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1997-09-01 | 1999-08-01 | 45000 | -1119 | 43881 | 43881 | 100% | 0 | 0 |  | 5850 | -155 | 5695 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | ALB | PHA | 36 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-07-01 |  | 2003-12-01 | 2004-12-01 | 40000 | -458 | 39542 | 39541.55 | 100% | 0.45 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the aerosol sector | Individual | AFR | ALG | ARS | 27 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-11-01 | 2001-09-01 | 15000 | -598 | 14402 | 14402.12 | 100% | -0.12 | 0 |  | 1950 | -81 | 1869 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | AFR | ALG | FOA | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 18000 | -20 | 17980 | 17979.88 | 100% | 0.12 | 0 |  | 2340 | -6 | 2334 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | AFR | ALG | FOA | 30 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1 | 19999 | 19998.69 | 100% | 0.31 | 0 |  | 2600 | -4 | 2596 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | AFR | ALG | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -4245 | 20755 | 20755 | 100% | 0 | 0 |  | 3250 | -556 | 2694 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba-Algeria) | Individual | AFR | ALG | FOA | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -1584 | 23416 | 23416 | 100% | 0 | 0 |  | 3250 | -211 | 3039 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ALG | FUM | 22 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1998-06-01 |  | 2000-01-01 | 2000-07-01 | 8000 | -3793 | 4207 | 4207 | 100% | 0 | 0 |  | 1040 | -494 | 546 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | AFR | ALG | FUM | 34 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -11723 | 13277 | 13277.46 | 100% | -0.46 | 0 |  | 3250 | -1524 | 1726 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | ALG | PHA | 46 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-04-01 | 2006-03-01 |  | 2008-04-01 | 2008-12-01 | 25000 | -1596 | 23404 | 23404.03 | 100% | -0.03 | 0 |  | 1875 | -120 | 1755 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | AFR | ALG | REF | 27 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-10-01 | 1999-12-01 |  | 2000-11-01 | 2001-07-01 | 15000 | -11980 | 3020 | 3019.87 | 100% | 0.13 | 0 |  | 1950 | -1558 | 392 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for establishment of a National Centre for recovery and recycling CFC-11, CFC-12 and CFC-502 | Individual | AFR | ALG | REF | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1998-11-01 | 1995-06-01 |  | 1999-12-01 | 2001-11-01 | 25000 | -8254 | 16746 | 16746.19 | 100% | -0.19 | 0 |  | 3250 | -1077 | 2173 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | AFR | ALG | REF | 36 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-07-01 |  | 2004-12-01 | 2005-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | AFR | ALG | REF | 31 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-06-01 | 2002-01-01 |  | 2003-01-01 | 2003-06-01 | 60000 | -1013 | 58987 | 58987.21 | 100% | -0.21 | 0 |  | 7800 | -144 | 7656 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | LAC | ARG | FOA | 18 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -492 | 19508 | 19508 | 100% | 0 | 0 |  | 2600 | -68 | 2532 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 118 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2003-10-01 | 2003-12-01 | 35000 | -900 | 34100 | 34099.99 | 100% | 0.01 | 0 |  | 4550 | -124 | 4426 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | ARG | FOA | 27 | PRP | 84 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the foam production at BANDEX, CELPACK & PRENSIPLANT | Individual | LAC | ARG | FOA | 11 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-12-01 | 1998-08-01 | 35000 | 8990 | 43990 | 43990 | 100% | 0 | 0 |  | 4550 | 1169 | 5719 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (flowers) | Individual | LAC | ARG | FUM | 27 | PRP | 85 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 40000 | -5622 | 34378 | 34378.04 | 100% | -0.04 | 0 |  | 5200 | -738 | 4462 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (strawberries, tomatoes) | Individual | LAC | ARG | FUM | 27 | PRP | 89 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-14 | 2000-11-09 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNIDO | Preparation of umbrella project in the commercial refrigeration sector | Individual | LAC | ARG | REF | 36 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-05-01 | 2003-05-01 | 25000 | 0 | 25000 | 25000.04 | 100% | -0.04 | 0 |  | 3250 | -4 | 3246 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | ARG | REF | 36 | PRP | 127 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2004-08-01 |  | 2004-08-01 | 2004-08-01 | 100000 | 0 | 100000 | 99999.54 | 100% | 0.46 | 0 |  | 13000 | -11 | 12989 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the solvents sector (CFC-113 and TCA) | Individual | LAC | ARG | SOL | 36 | PRP | 125 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 40000 | -1126 | 38874 | 38874 | 100% | 0 | 0 |  | 5200 | -154 | 5046 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of project for retrofitting in all ice-making systems, icebin compressor systems, blast freezers, cold storage and chiller rooms | Individual | LAC | BAR | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two investment projects in the flexible foam sector | Individual | EUR | BHE | FOA | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2002-08-01 |  | 2004-01-01 | 2004-04-01 | 15000 | -738 | 14262 | 14262.04 | 100% | -0.04 | 0 |  | 1950 | -99 | 1851 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the rigid foam sector | Individual | EUR | BHE | FOA | 36 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-09-01 | 2003-04-01 |  | 2004-01-01 | 2004-12-01 | 15000 | -417 | 14583 | 14583.12 | 100% | -0.12 | 0 |  | 1950 | -57 | 1893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | EUR | BHE | FOA | 30 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-08-01 | 2001-04-01 |  | 2002-10-01 | 2003-06-01 | 15000 | -238 | 14762 | 14762.25 | 100% | -0.25 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | BHE | PHA | 36 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2003-12-01 | 2005-05-01 | 80000 | -1922 | 78078 | 78077.52 | 100% | 0.48 | 0 |  | 10400 | -266 | 10134 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the commercial/ domestic refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -8025 | 6975 | 6975.21 | 100% | -0.21 | 0 |  | 1950 | -1045 | 905 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two investment projects in the commercial refrigeration sector | Individual | EUR | BHE | REF | 36 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -3464 | 11536 | 11536.49 | 100% | -0.49 | 0 |  | 1950 | -453 | 1497 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 06 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-04-01 | 15000 | -1613 | 13387 | 13387.29 | 100% | -0.29 | 0 |  | 1950 | -212 | 1738 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (grain fumigation) | Individual | AFR | BOT | FUM | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two projects in the integral skin sector | Individual | LAC | BRA | FOA | 33 | PRP | 204 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-06-01 | 2003-03-01 | 20000 | -615 | 19385 | 19384.52 | 100% | 0.48 | 0 |  | 2600 | -84 | 2516 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for two projects in the rigid foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 206 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-06-01 | 2003-06-01 | 20000 | -130 | 19870 | 19870.32 | 100% | -0.32 | 0 |  | 2600 | -21 | 2579 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | BRA | FOA | 27 | PRP | 126 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 50000 | -9090 | 40910 | 40909.99 | 100% | 0.01 | 0 |  | 6500 | -1190 | 5310 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for elimination of CFCs in the polymer foams manufacturing | Individual | LAC | BRA | FOA | 09 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-09-01 |  | 1996-08-01 | 1999-08-01 | 150000 | -5144 | 144856 | 144856 | 100% | 0 | 0 |  | 19500 | -699 | 18801 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in methyl bromide (tobacco, flowers, horticulture) | Individual | LAC | BRA | FUM | 44 | PRP | 269 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-11-01 | 40000 | -1133 | 38867 | 38866.6 | 100% | 0.4 | 0 |  | 3000 | -85 | 2915 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigant/ methyl bromide sector (tobacco) | Individual | LAC | BRA | FUM | 27 | PRP | 165 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -3855 | 46145 | 46145 | 100% | 0 | 0 |  | 6500 | -511 | 5989 | 0 | 0 | FIN
FIN | UNIDO | Preparation of one investment project in the commercial refrigeration sector | Individual | LAC | BRA | REF | 34 | PRP | 223 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2002-08-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -4060 | 20940 | 20940.13 | 100% | -0.13 | 0 |  | 3250 | -532 | 2718 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for six projects in the commercial/domestic refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 203 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -1663 | 23337 | 23337.28 | 100% | -0.28 | 0 |  | 3250 | -221 | 3029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 30 | PRP | 159 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 25000 | -409 | 24591 | 24590.56 | 100% | 0.44 | 0 |  | 3250 | -58 | 3192 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector for four companies | Individual | LAC | BRA | REF | 27 | PRP | 119 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2001-03-01 | 2002-09-01 | 40000 | -8531 | 31469 | 31469.18 | 100% | -0.18 | 0 |  | 5200 | -1116 | 4084 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector (Tecpur, Crios, Panamante and others) | Individual | LAC | BRA | REF | 24 | PRP | 97 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 2000-07-01 | 2001-07-01 | 50000 | -2511 | 47489 | 47489 | 100% | 0 | 0 |  | 6500 | -336 | 6164 | 0 | 0 | FIN
FIN | UNIDO | Formulation of two investment projects in the commercial and domestic refrigerator sector | Individual | LAC | BRA | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-02-01 |  | 1997-12-01 | 1998-08-01 | 50000 | 87 | 50087 | 50087 | 100% | 0 | 0 |  | 6500 | 11 | 6511 | 0 | 0 | FIN
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | AFR | CMR | FUM | 24 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project proposal for phase out of CFCs at FAEM, Cameroun | Individual | AFR | CMR | REF | 11 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-04-01 | 1994-11-01 |  | 1995-02-01 | 1998-08-01 | 20000 | -2046 | 17954 | 17954 | 100% | 0 | 0 |  | 2600 | -270 | 2330 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the refrigeration sector | Individual | AFR | CMR | REF | 43 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2005-03-01 | 2005-07-01 |  | 2006-06-01 | 2006-12-01 | 25000 | -174 | 24826 | 24826.38 | 100% | -0.38 | 0 |  | 1875 | -13 | 1862 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of project for phasing out CFC-11 in the manufacture of domestic refrigerators, freezers and air-conditioners at Union Camerounaise | Individual | AFR | CMR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | AFR | CMR | REF | 24 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1999-02-01 | 1999-04-01 |  | 2001-04-01 | 2001-11-01 | 30000 | -65 | 29935 | 29934.63 | 100% | 0.37 | 0 |  | 3900 | -15 | 3885 | 0 | 0 | FIN |  |  | 1999-05-01
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | LAC | COL | FUM | 21 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-08-01 |  | 1998-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a MDI sector plan | Individual | ASP | CPR | ARS | 44 | PRP | 422 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-07-01 | 2009-05-01 | 90000 | -377 | 89623 | 89623.21 | 100% | -0.21 | 0 |  | 6750 | -28 | 6722 | 0 | 0 | FIN
FIN | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 59 | PRP | 494 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2011-05-31 |  | 2012-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 84592.8 | 99.52% | 407.2 | 0 | 1 | 6375 | 0 | 6344 | 31 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in the polystyrene/ polyethylene foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 337 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2840 | 47160 | 47160.44 | 100% | -0.44 | 0 |  | 6500 | -379 | 6121 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 338 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2627 | 47373 | 47372.77 | 100% | 0.23 | 0 |  | 6500 | -351 | 6149 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | ASP | CPR | FOA | 27 | PRP | 283 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2001-05-01 | 2002-09-01 | 50000 | -615 | 49385 | 49384.98 | 100% | 0.02 | 0 |  | 6500 | -90 | 6410 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two umbrella projects in the polystyrene/polyethylene foam sector | Individual | ASP | CPR | FOA | 33 | PRP | 371 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-10-01 |  | 2002-12-01 | 2003-12-01 | 100000 | -2686 | 97314 | 97314.17 | 100% | -0.17 | 0 |  | 13000 | -369 | 12631 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects (50 companies) in the foam sector (polysterene/polyethylene) | Individual | ASP | CPR | FOA | 24 | PRP | 240 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 100000 | -2311 | 97689 | 97689 | 100% | 0 | 0 |  | 13000 | -321 | 12679 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a methyl bromide consumption phase-out plan | Individual | ASP | CPR | FUM | 43 | PRP | 412 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2004-12-01 | 2005-05-01 | 20000 | -44 | 19956 | 19956.38 | 100% | -0.38 | 0 |  | 1500 | -6 | 1494 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a production phase-out plan in the fumigants sector (methyl bromide) | Individual | ASP | CPR | FUM | 45 | PRP | 430 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-12-01 | 2006-02-01 | 40000 | -31 | 39969 | 39969.44 | 100% | -0.44 | 0 |  | 3000 | -7 | 2993 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a sectoral strategy in the methyl bromide sector | Individual | ASP | CPR | FUM | 36 | PRP | 386 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-05-01 |  | 2003-12-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Substituting halon in fire fighting equipment at Nanjing | Individual | ASP | CPR | HAL | 09 | PRP | 194 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-04-01 | 1996-03-01 |  | 1995-03-01 | 1998-08-01 | 36000 | -6926 | 29074 | 29074 | 100% | 0 | 0 |  | 4680 | -906 | 3774 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment projects in the tobacco sector | Individual | ASP | CPR | OTH | 18 | PRP | 144 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1996-11-01 |  | 1999-12-01 | 2002-06-01 | 50000 | -1233 | 48767 | 48766.94 | 100% | 0.06 | 0 |  | 6500 | -170 | 6330 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a sectoral strategy in the tobacco sector | Individual | ASP | CPR | OTH | 24 | PRP | 237 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-11-01 | 2001-07-01 | 200000 | -8020 | 191980 | 191979.71 | 100% | 0.29 | 0 |  | 26000 | -1082 | 24918 | 0 | 0 | FIN |  |  | 1999-10-01
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 15 | PRP | 105 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-04-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 25000 | -8988 | 16012 | 16012 | 100% | 0 | 0 |  | 3250 | -1172 | 2078 | 0 | 0 | FIN
FIN | UNIDO | Preparation of 2 investment projects in the domestic (hydrocarbons) refrigeration sub-sector | Individual | ASP | CPR | REF | 31 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-08-01 | 2002-11-01 | 40000 | -17965 | 22035 | 22035 | 100% | 0 | 0 |  | 5200 | -2340 | 2860 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the domestic refrigeration (hydrocarbons) sector | Individual | ASP | CPR | REF | 30 | PRP | 339 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the transportation refrigeration sector (foam component) | Individual | ASP | CPR | REF | 30 | PRP | 341 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 40000 | 0 | 40000 | 39999.55 | 100% | 0.45 | 0 |  | 5200 | -1 | 5199 | 0 | 0 | FIN
FIN | UNIDO | Elimination of ODS used in the production of compressors for household refrigerators at Jiaxipera Compressor Co. Ltd. | Individual | ASP | CPR | REF | 09 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-06-01 | 1996-03-01 |  | 1994-12-01 | 1998-08-01 | 36000 | 4294 | 40294 | 40294 | 100% | 0 | 0 |  | 4680 | 558 | 5238 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration compressor subsector | Individual | ASP | CPR | REF | 30 | PRP | 340 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 50000 | -786 | 49214 | 49214.19 | 100% | -0.19 | 0 |  | 6500 | -112 | 6388 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment projects in the refrigeration sector with particular attention to domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 18 | PRP | 151 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-10-01 | 2000-07-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a sectoral phase-out plan in domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 36 | PRP | 385 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-07-01 |  | 2003-07-01 | 2004-04-01 | 70000 | 0 | 70000 | 70000.32 | 100% | -0.32 | 0 |  | 9100 | -12 | 9088 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | EUR | CRO | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -686 | 29314 | 29314 | 100% | 0 | 0 |  | 3900 | -95 | 3805 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the tobacco fumigation sector | Individual | EUR | CRO | FUM | 33 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -16341 | 13659 | 13658.86 | 100% | 0.14 | 0 |  | 3900 | -2127 | 1773 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (tobacco, tomatoes) | Individual | EUR | CRO | FUM | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | CRO | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-02-01 | 1999-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase out project (tobacco) | Individual | LAC | CUB | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-01-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to eliminate methyl bromide consumption (horticulture) | Individual | LAC | CUB | FUM | 43 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2006-09-01 | 30000 | -1068 | 28932 | 28931.73 | 100% | 0.27 | 0 |  | 2250 | -80 | 2170 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project (hospitals) in the commercial refrigeration sector | Individual | LAC | CUB | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-02-14 | 2001-07-01 | 50000 | -1874 | 48126 | 48126 | 100% | 0 | 0 |  | 6500 | -253 | 6247 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | UNIDO | Preparation of a phase-out project in the fumigants (methyl bromide) sector for TPO-soil fumigation | Individual | LAC | DOM | FUM | 36 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2004-03-01 | 30000 | -2722 | 27278 | 27278.42 | 100% | -0.42 | 0 |  | 3900 | -359 | 3541 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (tobacco, curcubits, flowers, tomatoes) | Individual | LAC | DOM | FUM | 25 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the solvents (CTC) sector | Individual | AFR | DRC | SOL | 45 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -1605 | 28395 | 28394.89 | 100% | 0.11 | 0 |  | 2250 | -120 | 2130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | DRK | FUM | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-01-01 | 2001-07-01 | 15000 | 8050 | 23050 | 23050 | 100% | 0 | 0 |  | 1950 | 1042 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the solvents, process agents and fumigants sector (CTC) | Individual | ASP | DRK | MUS | 39 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 40000 | -22 | 39978 | 39977.88 | 100% | 0.12 | 0 |  | 3000 | -6 | 2994 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a process agent terminal umbrella project | Individual | ASP | DRK | PAG | 48 | PRP | 42 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-05-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-12-01 | 2006-12-01 | 15000 | -11196 | 3804 | 3804.13 | 100% | -0.13 | 0 |  | 1125 | -840 | 285 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the refrigeration sector (CFC) | Individual | ASP | DRK | REF | 39 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 20000 | -267 | 19733 | 19732.67 | 100% | 0.33 | 0 |  | 1500 | -22 | 1478 | 0 | 0 | FIN
FIN | UNIDO | Preparation for four projects in the solvent (CTC) sector | Individual | ASP | DRK | SOL | 33 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-10-01 |  | 2002-12-01 | 2003-05-01 | 70000 | -17 | 69983 | 69983.13 | 100% | -0.13 | 0 |  | 9100 | -17 | 9083 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment activities in cut-flowers production | Individual | LAC | ECU | FUM | 63 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-05-01 | 2012-03-31 |  | 2012-03-01 | 2012-05-01 | 45000 | -111 | 44889 | 44889.25 | 100% | -0.25 | 0 |  | 3375 | -8 | 3367 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a MDI phase-out plan (CFC) | Individual | AFR | EGY | ARS | 45 | PRP | 90 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 50000 | -337 | 49663 | 49663.07 | 100% | -0.07 | 0 |  | 3750 | -25 | 3725 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | EGY | FUM | 30 | PRP | 77 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-12-01 | 2003-05-01 | 25000 | -858 | 24142 | 24142.35 | 100% | -0.35 | 0 |  | 3250 | -116 | 3134 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | AFR | EGY | FUM | 33 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-12-01 | 2003-05-01 | 30000 | -528 | 29472 | 29471.78 | 100% | 0.22 | 0 |  | 3900 | -75 | 3825 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | EGY | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-04-01 | 2003-09-01 |  | 2005-12-01 | 2006-12-01 | 75000 | -33 | 74967 | 74966.89 | 100% | 0.11 | 0 |  | 9750 | -4 | 9746 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in production of household refrigeration at additional four companies | Individual | AFR | EGY | REF | 13 | PRP | 34 | A | I |  | 0 | 0 |  |  | 1994-07-01 | 1994-10-01 | 1994-10-01 |  | 1995-08-01 | 1998-08-01 | 15000 | 3364 | 18364 | 18364 | 100% | 0 | 0 |  | 1950 | 437 | 2387 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector | Individual | AFR | EGY | SOL | 21 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-07-01 | 1997-06-01 |  | 2000-07-01 | 2000-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2001-03-01 | 15000 | 0 | 15000 | 14999.85 | 100% | 0.15 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 30 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-12-01 | 2001-04-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000.05 | 100% | -0.05 | 0 |  | 1950 | -1 | 1949 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | EUR | GEO | FUM | 33 | PRP | 09 | A | I | MBR | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-05-01 | 2003-05-01 | 30000 | -1001 | 28999 | 28998.87 | 100% | 0.13 | 0 |  | 3900 | -136 | 3764 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of structure in fumigation of commodities in mill factories and grain storage | Individual | EUR | GEO | FUM | 44 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 30000 | -62 | 29938 | 29937.84 | 100% | 0.16 | 0 |  | 2250 | -5 | 2245 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national halon bank | Individual | EUR | GEO | HAL | 44 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-09-01 | 15000 | -1438 | 13562 | 13561.63 | 100% | 0.37 | 0 |  | 1125 | -108 | 1017 | 0 | 0 | FIN
FIN | UNIDO | Development of Refrigeration Management Plans | Individual | GLO | GLO | REF | 22 | PRP | 134 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1997-12-01 |  | 2001-04-01 | 2001-09-01 | 60000 | -23740 | 36260 | 36260.31 | 100% | -0.31 | 0 |  | 7800 | -3094 | 4706 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2005-11-01 |  | 2006-06-01 | 2007-12-01 | 119000 | -640 | 118360 | 118360.18 | 100% | -0.18 | 0 |  | 8925 | -48 | 8877 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project formulation of demonstraton project in the methyl bromide sector | Individual | LAC | GUA | FUM | 21 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-03-01 | 1997-08-01 |  | 1999-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | AFR | GUI | FOA | 21 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -8983 | 11017 | 11017 | 100% | 0 | 0 |  | 2600 | -1170 | 1430 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | ODS phase out at a domestic refrigeration plant (Guyana Refrigeration Ltd.) | Individual | LAC | GUY | REF | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1995-09-01 |  | 1998-01-01 | 1999-08-01 | 15000 | -659 | 14341 | 14341 | 100% | 0 | 0 |  | 1950 | -89 | 1861 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | HON | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1998-04-01 | 1997-05-01 |  | 2000-12-01 | 2001-09-01 | 30000 | -11403 | 18597 | 18597.21 | 100% | -0.21 | 0 |  | 3900 | -1486 | 2414 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | LAC | HON | FUM | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-03-01 | 2002-04-01 |  | 2002-11-01 | 2003-05-01 | 30000 | -482 | 29518 | 29517.96 | 100% | 0.04 | 0 |  | 3900 | -69 | 3831 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | HON | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-11-01 | 2000-07-01 | 30000 | -7251 | 22749 | 22749 | 100% | 0 | 0 |  | 3900 | -947 | 2953 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 122 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -2204 | 22796 | 22796.41 | 100% | -0.41 | 0 |  | 3250 | -291 | 2959 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IDS | FOA | 27 | PRP | 109 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2002-01-01 | 2003-05-01 | 50000 | -177 | 49823 | 49822.81 | 100% | 0.19 | 0 |  | 6500 | -33 | 6467 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector (tobacco, tomatoes, pepper) | Individual | ASP | IDS | FUM | 23 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 1998-09-01 | 2001-07-01 | 10000 | 17659 | 27659 | 27659 | 100% | 0 | 0 |  | 1300 | 2290 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the fumigant (methyl bromide) sector in TPO-grain fumigation | Individual | ASP | IDS | FUM | 36 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a sector phase-out plan in process agents sector | Individual | ASP | IDS | PAG | 36 | PRP | 140 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-12-01 | 2004-12-01 | 60000 | -1890 | 58110 | 58109.61 | 100% | 0.39 | 0 |  | 7800 | -258 | 7542 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the process agent (pharmaceutical) sector | Individual | ASP | IND | PAG | 33 | PRP | 302 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-10-01 |  | 2003-10-01 | 2004-09-01 | 70000 | -5813 | 64187 | 64186.69 | 100% | 0.31 | 0 |  | 9100 | -769 | 8331 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 30 | PRP | 248 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 20000 | -703 | 19297 | 19297.01 | 100% | -0.01 | 0 |  | 2600 | -95 | 2505 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 36 | PRP | 346 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-04-01 |  | 2003-09-01 | 2004-09-01 | 30000 | -4889 | 25111 | 25111.42 | 100% | -0.42 | 0 |  | 3900 | -641 | 3259 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project for phasing out ODS in the refrigeration sector (project under identification | Individual | ASP | IND | REF | 23 | PRP | 159 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2002-05-01 | 25000 | 24369 | 49369 | 49369.43 | 100% | -0.43 | 0 |  | 3250 | 3158 | 6408 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the solvent sector | Individual | ASP | IND | SOL | 27 | PRP | 195 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-07-20 | 2000-11-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Formulation of CTC process cleaning agent project in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 264 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2002-03-01 | 2003-05-01 | 20000 | -261 | 19739 | 19739 | 100% | 0 | 0 |  | 2600 | -38 | 2562 | 0 | 0 | FIN
FIN | UNIDO | Preparation investment projects in the solvent (CFC 113) sector at Harbans Lal Mahotra & Sons Ltd. Calcutta | Individual | ASP | IND | SOL | 24 | PRP | 162 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 25000 | -177 | 24823 | 24822.7 | 100% | 0.3 | 0 |  | 3250 | -28 | 3222 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the solvent (CFC-113) sector | Individual | ASP | IND | SOL | 36 | PRP | 347 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-04-01 | 2004-04-01 | 30000 | -479 | 29521 | 29521.01 | 100% | -0.01 | 0 |  | 3900 | -68 | 3832 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects for SMEs in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2002-04-01 |  | 2003-06-01 | 2003-06-01 | 30000 | -29 | 29971 | 29971.09 | 100% | -0.09 | 0 |  | 3900 | -10 | 3890 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for the conversion of electronic cleaning processes from CFC-113/alcohol blended and 1,1,1 trichlorethane to non-CFC cleaning | Individual | ASP | IND | SOL | 10 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-10-01 | 1993-10-01 |  | 1998-12-01 | 2000-07-01 | 74000 | -332 | 73668 | 73668 | 100% | 0 | 0 |  | 9620 | -58 | 9562 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of an MDI project | Individual | ASP | IRA | ARS | 47 | PRP | 173 | A | I |  |  | 0 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2008-04-01 | 2008-09-01 | 70000 | 0 | 70000 | 69999.9 | 100% | 0.1 | 0 |  | 5250 | 0 | 5250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the foam sector for phasing out ODS at three enterprises including Bahaman Plastic | Individual | ASP | IRA | FOA | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-06-01 |  | 2000-09-01 | 2001-07-01 | 10000 | -2561 | 7439 | 7439 | 100% | 0 | 0 |  | 1300 | -334 | 966 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IRA | FOA | 27 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 18000 | -1160 | 16840 | 16839.62 | 100% | 0.38 | 0 |  | 2340 | -154 | 2186 | 0 | 0 | FIN
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | ASP | IRA | FOA | 34 | PRP | 106 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 20000 | -840 | 19160 | 19160.19 | 100% | -0.19 | 0 |  | 2600 | -113 | 2487 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Formulation of two umbrella investment projects in the rigid and flexible foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 148 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2003-10-01 | 2004-07-01 | 35000 | -557 | 34443 | 34442.85 | 100% | 0.15 | 0 |  | 4550 | -80 | 4470 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries) | Individual | ASP | IRA | FUM | 44 | PRP | 168 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 9830 | -1250 | 8580 | 8579.53 | 99.99% | 0.47 | 0 |  | 737 | -93 | 643 | 1 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | IRA | FUM | 23 | PRP | 33 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of 12 investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 15000 | -403 | 14597 | 14597.4 | 100% | -0.4 | 0 |  | 1950 | -55 | 1895 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 27 | PRP | 38 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -1807 | 18193 | 18192.87 | 100% | 0.13 | 0 |  | 2600 | -239 | 2361 | 0 | 0 | FIN
FIN | UNIDO | Preparation of 3 umbrella investment projects in the commercial and domestic refrigeration sector | Individual | ASP | IRA | REF | 36 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 30000 | -2109 | 27891 | 27890.98 | 100% | 0.02 | 0 |  | 3900 | -280 | 3620 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-05-01 | 2003-02-01 | 30000 | -108 | 29892 | 29891.68 | 100% | 0.32 | 0 |  | 3900 | -20 | 3880 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phase-out of CFC-11 and CFC-12 in the commercial and small domestic refrigeration industry | Individual | ASP | IRA | REF | 15 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in domestic refrigeration industry | Individual | ASP | IRA | REF | 09 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-06-01 |  | 1996-05-01 | 1998-08-01 | 50000 | 13633 | 63633 | 63633 | 100% | 0 | 0 |  | 6500 | 1772 | 8272 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the solvent sector (CTC/TCA) | Individual | ASP | IRA | SOL | 39 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | 0 | 10000 | 10000.47 | 100% | -0.47 | 0 |  | 750 | 0 | 750 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the solvent sector | Individual | ASP | IRA | SOL | 48 | PRP | 178 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-07-01 | 2007-04-01 |  | 2006-12-01 | 2007-05-01 | 15000 | -512 | 14488 | 14487.67 | 100% | 0.33 | 0 |  | 1125 | -38 | 1087 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvent sector CTC/TCA | Individual | ASP | IRA | SOL | 42 | PRP | 164 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -110 | 14890 | 14889.61 | 100% | 0.39 | 0 |  | 1125 | -8 | 1117 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the solvent (CTC) sector | Individual | ASP | IRA | SOL | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2005-12-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000.02 | 100% | -0.02 | 0 |  | 2600 | -2 | 2598 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in pre and post-harvest sectors | Individual | ASP | IRQ | FUM | 58 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-07-01 | 2010-07-31 |  | 2010-12-01 | 2011-06-01 | 40000 | -239 | 39761 | 39761.16 | 100% | -0.16 | 0 |  | 3000 | -18 | 2982 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of country programme and national phase-out plan. | Individual | ASP | IRQ | PHA | 55 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2009-07-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000.01 | 100% | -0.01 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | AFR | IVC | ARS | 44 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -1832 | 13168 | 13167.99 | 100% | 0.01 | 0 |  | 1125 | -137 | 988 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector | Individual | AFR | IVC | FUM | 39 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-11-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -198 | 9802 | 9801.98 | 100% | 0.02 | 0 |  | 750 | -16 | 734 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | IVC | PHA | 48 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2008-04-01 | 2008-12-01 | 15000 | -15 | 14985 | 14984.65 | 100% | 0.35 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the domestic refrigeration (hydrocarbon) sector for Serti | Individual | AFR | IVC | REF | 24 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-10-01 | 2000-12-01 | 20000 | -10918 | 9082 | 9082 | 100% | 0 | 0 |  | 2600 | -1421 | 1179 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Preparation of a phase out project (tobacco fumigation) | Individual | LAC | JAM | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-09-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | ASP | JOR | ARS | 30 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-08-01 | 2001-04-01 |  | 2001-01-01 | 2002-05-01 | 20000 | -7413 | 12587 | 12587.48 | 100% | -0.48 | 0 |  | 2600 | -966 | 1634 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | JOR | FUM | 23 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-03-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 27 | PRP | 45 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 1999-12-01 | 2001-03-01 | 5000 | -693 | 4307 | 4307 | 100% | 0 | 0 |  | 650 | -91 | 559 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-04-01 | 2001-04-01 |  | 2002-12-01 | 2003-08-01 | 20000 | -1759 | 18241 | 18241.11 | 100% | -0.11 | 0 |  | 2600 | -232 | 2368 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration (umbrella project) sector | Individual | ASP | JOR | REF | 33 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-04-01 |  | 2002-07-01 | 2003-09-01 | 20000 | -477 | 19523 | 19523.09 | 100% | -0.09 | 0 |  | 2600 | -66 | 2534 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | JOR | REF | 24 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-05-01 | 2000-12-01 | 30000 | -3410 | 26590 | 26590 | 100% | 0 | 0 |  | 3900 | -449 | 3451 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phase out of ODS in selected industries in the refrigeration and air-conditioning sector | Individual | ASP | JOR | REF | 10 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1993-10-01 |  | 1994-12-01 | 1998-08-01 | 90000 | -14930 | 75070 | 75070 | 100% | 0 | 0 |  | 11700 | -1956 | 9744 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (CFC-113) sector | Individual | ASP | JOR | SOL | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2002-12-01 | 2003-06-01 | 25000 | -2455 | 22545 | 22544.58 | 100% | 0.42 | 0 |  | 3250 | -324 | 2926 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | AFR | KEN | FUM | 23 | PRP | 15 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management project | Individual | ASP | KUW | PHA | 48 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-07-01 | 2008-08-01 | 25000 | -2 | 24998 | 24998.08 | 100% | -0.08 | 0 |  | 1875 | 0 | 1875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project formulation for phase out of ODS in aerosol sector (Cosmaline Industries S.A.) | Individual | ASP | LEB | ARS | 16 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -8784 | 6216 | 6216 | 100% | 0 | 0 |  | 1950 | -1143 | 807 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for the phase out of ODS in the foam sector in 2 plants (Ets. Henri Abdallah and Nasri Karam) | Individual | ASP | LEB | FOA | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-07-01 |  | 1997-03-01 | 1998-08-01 | 20000 | -7358 | 12642 | 12642 | 100% | 0 | 0 |  | 2600 | -959 | 1641 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants (strawberries) sector | Individual | ASP | LEB | FUM | 33 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -904 | 29096 | 29096.46 | 100% | -0.46 | 0 |  | 3900 | -123 | 3777 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation for phase out of ODS in the refrigeration sector (Weather-mate and OPACO Ltd.) | Individual | ASP | LEB | REF | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1997-08-01 | 1995-07-01 |  | 1997-12-01 | 2000-12-01 | 15000 | -1497 | 13503 | 13503 | 100% | 0 | 0 |  | 1950 | -197 | 1753 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two umbrella projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 33 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-01-01 | 2002-04-01 |  | 2002-07-01 | 2003-06-01 | 15000 | -229 | 14771 | 14770.5 | 100% | 0.5 | 0 |  | 1950 | -33 | 1917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation of two umbrella investment projects in the commercial refrigeration sector, covering six SME factories each | Individual | ASP | LEB | REF | 31 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1076 | 18924 | 18923.55 | 100% | 0.45 | 0 |  | 2600 | -144 | 2456 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector (methyl bromide) | Individual | AFR | LIB | FUM | 45 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-11-01 | 15000 | -1137 | 13863 | 13863.13 | 100% | -0.13 | 0 |  | 1125 | -85 | 1040 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a halon phase-out plan | Individual | AFR | LIB | HAL | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 25000 | -264 | 24736 | 24736 | 100% | 0 | 0 |  | 1875 | -20 | 1855 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | AFR | LIB | REF | 36 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-06-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 20000 | -722 | 19278 | 19277.77 | 100% | 0.23 | 0 |  | 2600 | -98 | 2502 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the Refrigeration sector | Individual | AFR | LIB | REF | 30 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2003-07-01 | 2004-04-01 | 20000 | -550 | 19450 | 19449.96 | 100% | 0.04 | 0 |  | 2600 | -76 | 2524 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the rigid foam sector | Individual | ASP | MAL | FOA | 31 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2001-07-01 |  | 2002-01-01 | 2003-05-01 | 20000 | -740 | 19260 | 19259.64 | 100% | 0.36 | 0 |  | 2600 | -100 | 2500 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (rigid polyurethane) for Chon Son, Ngui Soon, Ming Soon, Yon Tuck | Individual | ASP | MAL | FOA | 24 | PRP | 110 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 20000 | -205 | 19795 | 19795 | 100% | 0 | 0 |  | 2600 | -31 | 2569 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the foam sector (rigid polyrethane) | Individual | ASP | MAL | FOA | 27 | PRP | 118 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 25000 | -47 | 24953 | 24953.14 | 100% | -0.14 | 0 |  | 3250 | -11 | 3239 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | ASP | MAL | FOA | 18 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-02-01 |  | 1999-02-01 | 2000-07-01 | 40000 | -35 | 39965 | 39965 | 100% | 0 | 0 |  | 5200 | -13 | 5187 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the aerosol sector | Individual | EUR | MDN | ARS | 30 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2001-07-01 | 15000 | -2425 | 12575 | 12575.43 | 100% | -0.43 | 0 |  | 1950 | -318 | 1632 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in methyl bromide (tobacco, pepper, tomatoes) | Individual | EUR | MDN | FUM | 25 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | MDN | FUM | 30 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -499 | 19501 | 19500.93 | 100% | 0.07 | 0 |  | 2600 | -69 | 2531 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | MDN | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 30000 | -4462 | 25538 | 25538 | 100% | 0 | 0 |  | 3900 | -585 | 3315 | 0 | 0 | FIN
FIN | UNIDO | Preparation of ODS disposal pilot project | Individual | LAC | MEX | DES | 57 | PRP | 142 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-10-01 | 2010-12-31 |  | 2011-12-01 | 2012-04-01 | 50000 | -872 | 49128 | 49127.52 | 100% | 0.48 | 0 |  | 3750 | -65 | 3685 | 0 | 0 | Financial completion in Apr 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the rigid foam sector | Individual | LAC | MEX | FOA | 30 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-04-01 |  | 2001-10-01 | 2003-03-01 | 30000 | -838 | 29162 | 29162.18 | 100% | -0.18 | 0 |  | 3900 | -115 | 3785 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | LAC | MEX | FUM | 22 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-07-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector (methyl bromide) | Individual | LAC | MEX | FUM | 39 | PRP | 113 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-01-01 | 2005-05-01 | 50000 | 0 | 50000 | 49999.86 | 100% | 0.14 | 0 |  | 3750 | -3 | 3747 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a process agent project | Individual | LAC | MEX | PAG | 48 | PRP | 129 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -94 | 29906 | 29906.35 | 100% | -0.35 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Closure of CFC production facilities of the company Quimobasicos | Individual | LAC | MEX | PRO | 38 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-06-01 | 2004-04-01 | 38000 | -286 | 37714 | 37713.62 | 100% | 0.38 | 0 |  | 4940 | -45 | 4895 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | MEX | REF | 27 | PRP | 88 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 15000 | -2159 | 12841 | 12840.95 | 100% | 0.05 | 0 |  | 1950 | -283 | 1667 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS at several small enterprises in the commercial refrigeration | Individual | LAC | MEX | REF | 23 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-06-01 |  | 1999-11-01 | 2001-03-01 | 20000 | -49 | 19951 | 19951 | 100% | 0 | 0 |  | 2600 | -11 | 2589 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral phase-out plan in refrigeration | Individual | LAC | MEX | REF | 36 | PRP | 107 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-04-01 | 2005-05-01 | 30000 | 0 | 30000 | 30000.19 | 100% | -0.19 | 0 |  | 3900 | -1 | 3899 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | LAC | MEX | REF | 33 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2004-04-01 | 2004-12-01 | 50000 | 0 | 50000 | 49999.71 | 100% | 0.29 | 0 |  | 6500 | -3 | 6497 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | MOR | ARS | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -7939 | 12061 | 12061.37 | 100% | -0.37 | 0 |  | 2600 | -1035 | 1566 | -1 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (bananas) | Individual | AFR | MOR | FUM | 27 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -482 | 14518 | 14518.35 | 100% | -0.35 | 0 |  | 1950 | -66 | 1884 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (flowers) | Individual | AFR | MOR | FUM | 27 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -148 | 14852 | 14852.35 | 100% | -0.35 | 0 |  | 1950 | -22 | 1928 | 0 | 0 | FIN
FIN | UNIDO | Preparation of phase-out project in the methyl bromide sector | Individual | AFR | MOR | FUM | 30 | PRP | 39 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -260 | 29740 | 29739.89 | 100% | 0.11 | 0 |  | 3900 | -40 | 3860 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | MOR | REF | 27 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-09-01 | 1999-12-01 |  | 2001-04-01 | 2001-10-01 | 7000 | -1517 | 5483 | 5483.21 | 100% | -0.21 | 0 |  | 910 | -198 | 712 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector for Allom du Nord and others | Individual | AFR | MOR | REF | 24 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-09-01 | 2001-03-01 | 15000 | -4090 | 10910 | 10910 | 100% | 0 | 0 |  | 1950 | -534 | 1416 | 0 | 0 | FIN
FIN | UNIDO | Preparation of projects in commercial refrigeration | Individual | AFR | MOZ | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-08-01 | 1998-08-01 | 15000 | -1697 | 13303 | 13303 | 100% | 0 | 0 |  | 1950 | -223 | 1727 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 53 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2008-12-01 | 2009-03-01 | 12000 | -6598 | 5402 | 5401.91 | 100% | 0.09 | 0 |  | 900 | -495 | 405 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a project for the phase-out of methyl bromide soil fumigation | Individual | LAC | NIC | FUM | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-05-01 | 2003-12-01 | 30000 | -27242 | 2758 | 2757.82 | 99.99% | 0.18 | 0 |  | 3900 | -3542 | 358 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation of investment projects in the refrigeration sector | Individual | LAC | NIC | REF | 21 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-08-01 |  | 1998-05-01 | 2001-12-01 | 50000 | -8349 | 41651 | 41651.46 | 100% | -0.46 | 0 |  | 6500 | -1094 | 5406 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosols sector | Individual | AFR | NIR | ARS | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2000-10-01 | 2001-09-01 | 25000 | -9266 | 15734 | 15733.87 | 100% | 0.13 | 0 |  | 3250 | -1208 | 2042 | 0 | 0 | FIN
FIN | UNIDO | Preparation for a pilot demonstration project on ODS waste management and disposal | Individual | AFR | NIR | DES | 60 | PRP | 126 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 60000 | 0 | 60000 | 59520.33 | 99.2% | 479.67 | 0 | 1 | 4500 | 0 | 4464 | 36 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012.
FIN | UNIDO | Project preparation for three projects in the commercial refrigeration sector | Individual | AFR | NIR | REF | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1718 | 18282 | 18282.2 | 100% | -0.2 | 0 |  | 2600 | -227 | 2373 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | NIR | REF | 30 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-02-01 | 2002-09-01 | 25000 | -2212 | 22788 | 22787.85 | 100% | 0.15 | 0 |  | 3250 | -292 | 2958 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral phase-out plan in solvents | Individual | AFR | NIR | SOL | 36 | PRP | 101 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-06-01 | 2004-11-01 | 70000 | 0 | 70000 | 69999.95 | 100% | 0.05 | 0 |  | 9100 | -8 | 9092 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | OMA | PHA | 46 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2007-03-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | ASP | PAK | FUM | 24 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-12-01 | 1999-04-01 |  | 2000-01-01 | 2000-07-01 | 30000 | -21118 | 8882 | 8882 | 100% | 0 | 0 |  | 3900 | -2747 | 1153 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector | Individual | ASP | PAK | FUM | 39 | PRP | 49 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2004-04-01 | 2004-06-01 | 30000 | -9323 | 20677 | 20676.75 | 100% | 0.25 | 0 |  | 2250 | -702 | 1548 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for a halon sector phase-out plan | Individual | ASP | PAK | HAL | 40 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2003-12-01 | 2004-12-01 | 22000 | -780 | 21220 | 21219.63 | 100% | 0.37 | 0 |  | 1650 | -61 | 1589 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the refrigeration sector (CFC manufacturing) | Individual | ASP | PAK | REF | 39 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2005-05-01 | 20000 | -168 | 19832 | 19831.68 | 100% | 0.32 | 0 |  | 1500 | -15 | 1485 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | PAK | REF | 27 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-03-01 | 1999-12-01 |  | 2003-07-01 | 2003-10-01 | 30000 | -2206 | 27794 | 27794 | 100% | 0 | 0 |  | 3900 | -292 | 3608 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Preparation of two projects in the solvents sector | Individual | ASP | PAK | SOL | 36 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 20000 | -639 | 19361 | 19360.91 | 100% | 0.09 | 0 |  | 2600 | -87 | 2513 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for four projects in the solvent (CTC) sector | Individual | ASP | PAK | SOL | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | -7022 | 22978 | 22977.9 | 100% | 0.1 | 0 |  | 3900 | -918 | 2982 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the solvents sector (CTC/TCA) | Individual | ASP | PAK | SOL | 39 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 25000 | -807 | 24193 | 24192.9 | 100% | 0.1 | 0 |  | 1875 | -63 | 1812 | 0 | 0 | FIN
FIN | UNIDO | Project preparation assistance in solvent sector | Individual | LAC | PER | SOL | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -8097 | 21903 | 21903 | 100% | 0 | 0 |  | 3900 | -1057 | 2843 | 0 | 0 | FIN |  |  | 1999-01-01
FIN | UNIDO | Preparation of a recovery and recycling project in the refrigeration sector | Individual | ASP | PHI | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-01-01 |  | 1997-11-01 | 1998-08-01 | 15000 | 543 | 15543 | 15543 | 100% | 0 | 0 |  | 1950 | 71 | 2021 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | QAT | PHA | 46 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-10-01 | 2006-07-01 |  | 2007-12-01 | 2007-12-01 | 30000 | -97 | 29903 | 29903.3 | 100% | -0.3 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | EUR | ROM | FOA | 23 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-05-01 | 2001-07-01 | 10000 | 1667 | 11667 | 11667 | 100% | 0 | 0 |  | 1300 | 214 | 1514 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS at Spumotim flexible foam plant | Individual | EUR | ROM | FOA | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1996-05-01 | 15000 | 132 | 15132 | 15132 | 100% | 0 | 0 |  | 1950 | 17 | 1967 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | EUR | ROM | FUM | 23 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-03-01 | 2001-07-01 | 10000 | -780 | 9220 | 9220 | 100% | 0 | 0 |  | 1300 | -103 | 1197 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | ROM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 10000 | -322 | 9678 | 9678.05 | 100% | -0.05 | 0 |  | 1300 | -44 | 1256 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | ROM | HAL | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-04-01 | 15000 | -571 | 14429 | 14429.08 | 100% | -0.08 | 0 |  | 1125 | -43 | 1082 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation: CFC phase-out plan (aerosol and refrigeration) | Individual | EUR | ROM | PHA | 42 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-10-01 |  | 2005-08-01 | 2005-08-01 | 10000 | -1012 | 8988 | 8988.31 | 100% | -0.31 | 0 |  | 750 | -77 | 673 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a closure project in the production of CFC/CTC/MBR | Individual | EUR | ROM | PRO | 45 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-12-01 | 25000 | -3848 | 21152 | 21151.72 | 100% | 0.28 | 0 |  | 1875 | -289 | 1586 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the domestic and commercial refrigeration sector | Individual | EUR | ROM | REF | 18 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-05-01 |  | 1999-03-01 | 2000-07-01 | 20000 | -808 | 19192 | 19192 | 100% | 0 | 0 |  | 2600 | -109 | 2491 | 0 | 0 | FIN |  |  | 1999-03-01
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | ROM | REF | 24 | PRP | 14 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 30000 | -1043 | 28957 | 28957 | 100% | 0 | 0 |  | 3900 | -142 | 3758 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 at refrigerator plant at mechanical enterprises SADU and ARCTIC | Individual | EUR | ROM | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-04-01 | 1995-06-01 |  | 1996-07-01 | 1998-08-01 | 50000 | -4907 | 45093 | 45093 | 100% | 0 | 0 |  | 6500 | -647 | 5853 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the solvent sector | Individual | EUR | ROM | SOL | 39 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-10-01 | 2005-05-01 | 15000 | -785 | 14215 | 14215.32 | 100% | -0.32 | 0 |  | 1125 | -61 | 1064 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal umbrella project to phase out CTC | Individual | EUR | ROM | SOL | 44 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 20000 | -900 | 19100 | 19099.72 | 100% | 0.28 | 0 |  | 1500 | -67 | 1432 | 1 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | AFR | SEN | FOA | 18 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 | 0 |  | 1300 | -73 | 1227 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, peanuts) | Individual | AFR | SEN | FUM | 25 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-01-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | SEN | PHA | 48 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 15000 | -3043 | 11957 | 11957.21 | 100% | -0.21 | 0 |  | 1125 | -228 | 897 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a project proposal for setting up a national refrigerant recovery and recycling centre, National Halon Bank | Individual | AFR | SEY | REF | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1998-01-01 | 2000-07-01 | 15000 | -10846 | 4154 | 4154 | 100% | 0 | 0 |  | 1950 | -1411 | 539 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | SUD | ARS | 27 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 25000 | -7393 | 17607 | 17606.64 | 100% | 0.36 | 0 |  | 3250 | -965 | 2285 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | SUD | PHA | 41 | PRP | 15 | A | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 70000 | -294 | 69706 | 69706.47 | 100% | -0.47 | 0 |  | 5250 | -30 | 5220 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the domestic/commercial refrigeration sector | Individual | AFR | SUD | REF | 39 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-09-01 | 2004-04-01 |  | 2005-04-01 | 2005-08-01 | 20000 | -345 | 19655 | 19655.29 | 100% | -0.29 | 0 |  | 1500 | -28 | 1472 | 0 | 0 | FIN
FIN | UNIDO | Preparation of Refrigerant Management Plan | Individual | AFR | SUD | REF | 23 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 1998-12-01 | 2000-04-01 | 10000 | 16173 | 26173 | 26173 | 100% | 0 | 0 |  | 1300 | 2097 | 3397 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration production at FridgeMaster | Individual | AFR | SWA | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 25000 | -13308 | 11692 | 11692 | 100% | 0 | 0 |  | 3250 | -1733 | 1517 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 27 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-07-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 8000 | -1359 | 6641 | 6640.69 | 100% | 0.31 | 0 |  | 1040 | -178 | 862 | 0 | 0 | FIN
FIN | UNIDO | Preparation of at least three investment projects in the aerosol sector for phasing out ODS at three enterprises including Nweylati | Individual | ASP | SYR | ARS | 23 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2001-05-01 | 10000 | 4480 | 14480 | 14480.39 | 100% | -0.39 | 0 |  | 1300 | 579 | 1879 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | ASP | SYR | ARS | 18 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-05-01 |  | 1998-05-01 | 1999-08-01 | 25000 | -746 | 24254 | 24254 | 100% | 0 | 0 |  | 3250 | -102 | 3148 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | ASP | SYR | FOA | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-06-01 |  | 2000-12-01 | 2002-09-01 | 10000 | -362 | 9638 | 9638.11 | 100% | -0.11 | 0 |  | 1300 | -49 | 1251 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 from the manufacturing of pre-fabricated sandwich panels at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -1404 | 13596 | 13596 | 100% | 0 | 0 |  | 1950 | -185 | 1765 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for NPD in Damascus and others in rigid foam sector | Individual | ASP | SYR | FOA | 24 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-04-01 | 2002-09-01 | 15000 | -238 | 14762 | 14762.04 | 100% | -0.04 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of an investment project in the extruded polystyrene foam sector | Individual | ASP | SYR | FOA | 36 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 15000 | -80 | 14920 | 14919.91 | 100% | 0.09 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a project in the flexible foam sector | Individual | ASP | SYR | FOA | 31 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-12-01 | 2003-05-01 | 20000 | -27 | 19973 | 19973.47 | 100% | -0.47 | 0 |  | 2600 | -8 | 2592 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for phasing out of CFC-11 from the sub sector of flexible foams manufacturing | Individual | ASP | SYR | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a project in the fumigant (methyl bromide) sector for grain fumigation | Individual | ASP | SYR | FUM | 31 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2001-07-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -5357 | 14643 | 14642.91 | 100% | 0.09 | 0 |  | 2600 | -699 | 1901 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | SYR | FUM | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of CFC-phase-out plan including methyl bromide | Individual | ASP | SYR | PHA | 45 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-12-01 | 2008-12-01 | 70000 | -1900 | 68100 | 68100.06 | 100% | -0.06 | 0 |  | 5250 | -142 | 5108 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment project for phasing out CFC in manufacturing of refrigerators at Krayem Int. Co. | Individual | ASP | SYR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -711 | 14289 | 14289 | 100% | 0 | 0 |  | 1950 | -95 | 1855 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the domestic refrigeration sector | Individual | ASP | SYR | REF | 27 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2002-09-01 | 20000 | -2856 | 17144 | 17143.74 | 100% | 0.26 | 0 |  | 2600 | -375 | 2225 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | THA | FUM | 22 | PRP | 65 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-12-01 |  | 1998-05-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants (dates) sector | Individual | AFR | TUN | FUM | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -12728 | 12272 | 12271.57 | 100% | 0.43 | 0 |  | 3250 | -1655 | 1595 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | AFR | TUN | REF | 24 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 1998-12-01 | 2000-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the flexible foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 15000 | -10124 | 4876 | 4876.38 | 100% | -0.38 | 0 |  | 1950 | -1317 | 633 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sub sector | Individual | EUR | TUR | FOA | 24 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-11-01 | 2001-05-01 | 15000 | -9583 | 5417 | 5417.06 | 100% | -0.06 | 0 |  | 1950 | -1247 | 703 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-09-01 | 2001-04-01 |  | 2002-03-01 | 2002-05-01 | 15000 | -941 | 14059 | 14058.97 | 100% | 0.03 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (polyurethane) at Sungersan AS and Serra Sunger | Individual | EUR | TUR | FOA | 24 | PRP | 37 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1999-12-01 | 2000-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in ODS phase out in the foam sector | Individual | EUR | TUR | FOA | 15 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-04-01 | 2001-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -6 | 6494 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a demonstration project (flowers, tobacco) | Individual | EUR | TUR | FUM | 24 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector (horticulture) | Individual | EUR | TUR | FUM | 30 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -787 | 29213 | 29213.03 | 100% | -0.03 | 0 |  | 3900 | -108 | 3792 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral phase-out project in the solvents sector | Individual | EUR | TUR | SOL | 36 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-07-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000.37 | 100% | -0.37 | 0 |  | 6500 | -2 | 6498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | UGA | FUM | 30 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -560 | 29440 | 29440.08 | 100% | -0.08 | 0 |  | 3900 | -79 | 3821 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in aerosol sector at Mansoor Daya | Individual | AFR | URT | ARS | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 10000 | -1456 | 8544 | 8544 | 100% | 0 | 0 |  | 1300 | -191 | 1109 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production | Individual | AFR | URT | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-05-01 | 1996-05-01 | 10000 | -51 | 9949 | 9949 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flowers) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the fumigants (methyl bromide) sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -935 | 24065 | 24065.16 | 100% | -0.16 | 0 |  | 3250 | -126 | 3124 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -56 | 9944 | 9944 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -2 | 1298 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -227 | 19773 | 19772.54 | 100% | 0.46 | 0 |  | 2600 | -34 | 2566 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/ polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -37 | 19963 | 19963.34 | 100% | -0.34 | 0 |  | 2600 | -9 | 2591 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 19999.63 | 100% | 0.37 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | 0 | 25000 | 24999.54 | 100% | 0.46 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -927 | 29073 | 29073 | 100% | 0 | 0 |  | 3900 | -126 | 3774 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | 0 | 95000 | 94999.88 | 100% | 0.12 | 0 |  | 12350 | -12 | 12338 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -124 | 19876 | 19875.84 | 100% | 0.16 | 0 |  | 2600 | -20 | 2580 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressor sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -113 | 19887 | 19887.32 | 100% | -0.32 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -325 | 24675 | 24675.21 | 100% | -0.21 | 0 |  | 3250 | -47 | 3203 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -238 | 29762 | 29761.76 | 100% | 0.24 | 0 |  | 3900 | -37 | 3863 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1921 | 29 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11168 | 8832 | 8832 | 100% | 0 | 0 |  | 2600 | -1454 | 1146 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2885 | 17115 | 17114.86 | 100% | 0.14 | 0 |  | 2600 | -379 | 2221 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3268 | 16732 | 16732.05 | 100% | -0.05 | 0 |  | 2600 | -428 | 2172 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2008-04-01 | 2008-09-01 | 30000 | -453 | 29547 | 29547.47 | 100% | -0.47 | 0 |  | 2250 | -34 | 2216 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -201 | 14799 | 14799.45 | 100% | -0.45 | 0 |  | 1950 | -29 | 1921 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -15 | 14985 | 14984.86 | 100% | 0.14 | 0 |  | 1950 | -5 | 1945 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2009-09-01 | 2009-09-01 | 25000 | -9189 | 15811 | 15811.39 | 100% | -0.39 | 0 |  | 1875 | -689 | 1186 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -82 | 19918 | 19918.09 | 100% | -0.09 | 0 |  | 2600 | -15 | 2585 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7481 | 32519 | 32518.95 | 100% | 0.05 | 0 |  | 3000 | -565 | 2435 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2325 | 7675 | 7674.59 | 99.99% | 0.41 | 0 |  | 1300 | -304 | 996 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -1 | 1299 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -119 | 19881 | 19881.28 | 100% | -0.28 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2587 | 7413 | 7413.15 | 100% | -0.15 | 0 |  | 1300 | -338 | 962 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2008-12-01 | 2009-06-01 | 15000 | -1991 | 13009 | 13009.15 | 100% | -0.15 | 0 |  | 1125 | -149 | 976 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | -599 | 14401 | 14401.14 | 100% | -0.14 | 0 |  | 1125 | -47 | 1078 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the fumigant sector (grain storage) | Individual | AFR | ZIM | FUM | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-08-01 | 2007-03-01 |  | 2006-12-01 | 2007-03-01 | 20000 | -806.5 | 19193.5 | 19193.5 | 100% | 0 | 0 |  | 1500 | -60 | 1440 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -600 | 29400 | 29399.78 | 100% | 0.22 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -570 | 29430 | 29430.39 | 100% | -0.39 | 0 |  | 3900 | -80 | 3820 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | ALG | FOA | 59 | PRP | 73 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 40000 | -1724 | 38276 | 38275.82 | 100% | 0.18 | 0 |  | 3000 | -129 | 2871 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-to-air air-conditioning sector) | Individual | AFR | ALG | REF | 59 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 | 2012-12-01 | 60000 | 0 | 60000 | 59619.34 | 99.37% | 380.66 | 0 | 1 | 4500 | 0 | 4471 | 29 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing sector) | Individual | LAC | ARG | REF | 57 | PRP | 161 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2010-07-01 | 2012-05-01 | 80000 | -5 | 79995 | 79994.57 | 100% | 0.43 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air conditioning sector) | Individual | ASP | BAH | REF | 60 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 29746.36 | 99.15% | 253.64 | 0 | 1 | 2250 | 0 | 2231 | 19 | 0 | Project completed in Dec 2012. Financial completion in Dec 2012.
FIN | UNIDO | Preparation for technology demonstration project for hydrocarbon blowing agent in the extruded polystyrene (XPS) foam sector | Individual | ASP | CPR | FOA | 60 | PRP | 496 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-08-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000.01 | 100% | -0.01 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase-out of HCFC-141b in polyurethane foam production | Individual | EUR | CRO | FOA | 57 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2010-07-01 | 2010-12-01 | 40000 | -14 | 39986 | 39986.25 | 100% | -0.25 | 0 |  | 3000 | -1 | 2999 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam manufacturing sector) | Individual | LAC | ECU | FOA | 60 | PRP | 46 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2012-03-01 | 2012-05-01 | 60000 | 0 | 60000 | 59999.53 | 100% | 0.47 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Financial completion in May 2012.
FIN | UNIDO | Preparation for HCFC phase-out investment activities (appliance foam sector) | Individual | AFR | EGY | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 99626.09 | 99.63% | 373.91 | 0 | 1 | 7500 | 0 | 7472 | 28 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | ASP | IDS | SOL | 61 | PRP | 190 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-05-01 | 10000 | -353 | 9647 | 9647.1 | 100% | -0.1 | 0 |  | 750 | -26 | 724 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (room air-conditioning and compressors) | Individual | ASP | IRA | REF | 58 | PRP | 196 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-10-01 | 2010-07-31 |  | 2011-04-01 | 2012-12-01 | 45000 | 0 | 45000 | 44938.82 | 99.86% | 61.18 | 0 | 1 | 3375 | 0 | 3370 | 5 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project for the conversion of HCFC to non-HCFC technology in the manufacturing of mini-split units at Petra Engineering | Individual | ASP | JOR | REF | 56 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-04-01 | 2009-11-30 |  | 2010-12-01 | 2011-07-01 | 40000 | -327 | 39673 | 39672.83 | 100% | 0.17 | 0 |  | 3000 | -25 | 2975 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | MOR | FOA | 60 | PRP | 64 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2010-12-01 | 2011-04-01 | 60000 | -65 | 59935 | 59934.64 | 100% | 0.36 | 0 |  | 4500 | -5 | 4495 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | AFR | NIR | REF | 58 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2012-10-01 | 50000 | -2342 | 47658 | 47658.44 | 100% | -0.44 | 0 |  | 3750 | -176 | 3574 | 0 | 0 | Financial completion in Oct 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | PAK | FOA | 59 | PRP | 75 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 80000 | 0 | 80000 | 79894.17 | 99.87% | 105.83 | 0 | 1 | 6000 | 0 | 5992 | 8 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | PHI | FOA | 59 | PRP | 86 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 70000 | -5751 | 64249 | 64249.09 | 100% | -0.09 | 0 |  | 5250 | -431 | 4819 | 0 | 0 | Financial completion in Apr 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SUD | FOA | 59 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 40000 | 0 | 40000 | 39393.45 | 98.48% | 606.55 | 0 | 1 | 3000 | 0 | 2955 | 45 | 0 | Financial completion in Dec 2012. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | ASP | SYR | REF | 58 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2011-12-01 | 60000 | -1229 | 58771 | 58770.71 | 100% | 0.29 | 0 |  | 4500 | -92 | 4408 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | EUR | TUR | FOA | 58 | PRP | 94 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-04-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 150000 | -23470 | 126530 | 126530.07 | 100% | -0.07 | 0 |  | 11250 | -1760 | 9490 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning manufacturing sector) | Individual | EUR | YUG | REF | 61 | PRP | 37 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-11-01 | 2011-07-31 |  | 2011-07-01 | 2011-12-01 | 60000 | -388 | 59612 | 59611.83 | 100% | 0.17 | 0 |  | 4500 | -29 | 4471 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | NON-INV
FIN | USA | Project preparation |  | ASP | CPR | HAL | 13 | PRP | 80 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1996-01-01 |  | 1997-12-01 | 1998-04-01 | 200000 | -68517 | 131483 | 131483 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. No further activities foreseen on this project with the approval of China's Halon Sector Strategy (23rd meeting). |  | 1994 | 1997-12-01
FIN | USA | Refrigeration management demonstration project preparation |  | ASP | CPR | REF | 16 | PRP | 118 | A | I |  | 0 |  | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Technical assistance in aerosol project preparation |  | LAC | ECU | ARS | 08 | PRP | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-04-01 |  | 1993-04-01 | 1993-04-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Feasibility study for reduction of CFC-11 in rigid polyurethane foam insulation for refrigerators using water/CO2 formulation |  | LAC | ECU | FOA | 08 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 41000 | 50000 | 91000 | 91000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $50,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Project preparation for low consuming countries |  | LAC | LAC | REF | 13 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation in MAC and refrigerated transport in Central American and the Caribbean |  | LAC | LAC | REF | 19 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1998-02-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Final report submitted in June 1998. |  | 1995 | 1997-05-01
FIN | USA | Project preparation in the halon sector |  | ASP | MAL | HAL | 15 | PRP | 54 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-06-01 |  | 1995-06-01 | 1996-06-01 | 45000 | -28116 | 16884 | 16884 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation |  | LAC | MEX | SOL | 13 | PRP | 28 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 450000 | -119143 | 330857 | 330857 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
ONG | Czech Republic | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) |  | EUR | EUR | DES | 65 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2012-11-01 | 2013-03-01 |  |  | 35000 | 0 | 35000 | 21910 | 62.6% | 13090 | 7728 | 7728 | 4550 | 0 | 2848.3 | 1701.7 | 1004.64 | Inventory completed in Croatia, Montenegro and Bosnia & Herzegovina using national consultants. Turkmenistan withdraw from the project. Project proposal reviewed during stakeholder consultation in Brno, Czech Republic, 26-28 November 2012. | Project proposal submitted to ExCom 69 in March 2013 jointly with UNIDO as the lead agency. | 2011 |  | 2011
ONG | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | IDS | DES | 57 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-12-31 | 2013-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 50000 | 50000 | 3750 | 0 | 0 | 3750 | 3750 | Recruitment of qualified consulting firm proved lengthy and complicated given specialized ozone and climate knowledge/expertise required and low level of associated funding. Firm engaged Q4 2012 and business model preparation underway. Data collection, development of an inventory system for unwanted ODS and preparation of guidelines for collection, handling, packaging, transport, and procedure of final disposal consistent with existing protocols and criteria of the major voluntary carbon markets to be conducted Q1-Q3 2013. | Contract with the consultant firm was signed and first disbursement made Jan 2013. Discussions between the WB and senior level officials in each country have been held in order to engage, and ensure access to, appropriate national stakeholders. |  |  | Non-INV
ONG | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | PHI | DES | 57 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-12-31 | 2013-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 50000 | 50000 | 3750 | 0 | 0 | 3750 | 3750 | Recruitment of qualified consulting firm proved lengthy and complicated given specialized ozone and climate knowledge/expertise required and low level of associated funding. Firm engaged Q4 2012 and business model preparation underway. Data collection, development of an inventory system for unwanted ODS and preparation of guidelines for collection, handling, packaging, transport, and procedure of final disposal consistent with existing protocols and criteria of the major voluntary carbon markets to be conducted Q1-Q3 2013. | Contract with the consultant firm was signed and first disbursement made Jan 2013. Discussions between the WB and senior level officials in each country have been held in order to engage, and ensure access to, appropriate national stakeholders. |  |  | Non-INV
ONG | IBRD | Preparation for HCFC phase-out investment activities in the foam sector (additional funding) |  | LAC | ARG | FOA | 65 | PRP | 167 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-06-30 | 2014-12-01 |  |  | 120000 | 0 | 120000 | 11439 | 9.532% | 108561 | 108561 | 15000 | 9000 | 0 | 857.92 | 8142.08 | 8142.08 | Initial preparatory work launched in late 2011/early 2012 with the intention of finalising the foam sector plan for inclusion in Stage I HPMP. US $11,439 disbursed for travel and work completed. During HPMP Stage I negotiations, it was agreed, pursuant to an MFS recommendation, that the foam sector plan be prepared for inclusion in Stage II of the HPMP. Preparatory work has therefore been suspended until Stage II efforts begin. |  |  |  | Non-INV
ONG | Japan | Project preparation for a demonstration project on ODS disposal | Individual | ASP | ASP | DES | 54 | PRP | 53 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2009-04-01 | 2009-03-01 | 2012-12-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | A project document was once submitted but agreement to forward it to the ExCom for consideration was not reached with the Secretariat. Currently, the project proposal is still in the process of revision in view of the latest developments of discussion at the ExCom in accordance with the ExCom Decision 69/5 (i). |  | 2008
ONG | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | BRA | DES | 57 | PRP | 288 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 | 2014-10-01 |  |  | 40000 | 0 | 40000 | 29269.87 | 73.17% | 10730.13 | 0 | 10730.13 | 3000 | 0 | 2195.2402 | 804.7598 | 0 | Brazil is currently revising its schedule of implementation of the Domestic Refrigeration Replacement Program to also meet the requirements of the Solid Waste Management Law approved by the National Congress in 2011 and which is under specific regulation requirements by industrial sub-sectors. Important inputs from this process is needed in order to finalized the ODS Waste Management Demo for Brazil. | Implications related to the approval of the WEEE law being investigated. WEEE law is also under sector regulamentation that shall impact the Refrigerator replacement/recovery. The project is expected to be submitted in 2014. | 2009 |  | Investment
ONG | UNDP | Preparation of an ODS bank management and destruction demonstration project | Individual | EUR | GEO | DES | 64 | PRP | 32 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2012-07-01 | 2013-03-01 |  |  | 30000 | 0 | 30000 | 18973.14 | 63.24% | 11026.86 | 0 | 11026.86 | 2250 | 0 | 1422.9855 | 827.0145 | 0 | The project document was signed between UNDP and the Ministry of Environment Protection on 6 August 2012. National consultants have been recruited for data collection, analysis and preparation of the project proposal. Planned activities have been initiated and generally completed | Some final payments pending. Project document was developed and submitted for consideration of the 69th ExCom in April 2013. | 2011 |  | Non-Investment
ONG | UNDP | Preparation of a project for demonstration of a sustainable technological, financial and management model for disposal of ODS | Individual | ASP | IND | DES | 61 | PRP | 437 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 | 2014-06-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 6000 | 0 | 0 | 6000 | 0 | Stakeholder consultations continued in 2012. | Development of project proposal expected to be completed by 4Q2013. | 2010 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BOL | FOA | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 | 2015-12-01 |  |  | 50000 | 0 | 50000 | 15862.7 | 31.73% | 34137.3 | 0 | 34137.3 | 3750 | 0 | 1189.7025 | 2560.2975 | 0 | Preparation of HPMP completed. Foams sector plan to be submitted in future meeting still within Stage I, when technology issues for local SMEs are resolved. | Preparation of HPMP completed. Foams sector plan to be submitted in future meeting still within Stage I, when technology issues for local SMEs are resolved. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | COS | REF | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 | 2014-01-01 |  |  | 60000 | 0 | 60000 | 20500 | 34.17% | 39500 | 0 | 39500 | 4500 | 0 | 1537.5 | 2962.5 | 0 | The investment project for the remaining part of the companies in the foam sector in Costa Rica will be prepared and presented to the ExCom when low GWP alternatives are available for SMEs. | The investment project for the remaining part of the companies in the foam sector in Costa Rica will be prepared and presented to the ExCom when low GWP alternatives are available for SMEs. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CUB | FOA | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 | 2013-05-01 |  |  | 50000 | 0 | 50000 | 6861 | 13.72% | 43139 | 6425 | 43139 | 3750 | 0 | 514.575 | 3235.425 | 481.875 | Additional baseline information from Foam companies was collected. Final payments still pending. | Payments in the process of being made. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (manufacturing sector) | Individual | LAC | CUB | REF | 58 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 |  | 2010-07-01 | 2014-06-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3750 | 0 | 0 | 3750 | 0 | Cuba can present investment project for Frioclima before 2020. Initial work was done in 2012 to gather baseline information about the company. | International expert was hired and made a mission to Cuba to evaluate the company and prepare a technical report about the technical replacement options. Report was delivered to the Government and UNDP, and futher discussions are currently taking place regarding selection of technology. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAN | FOA | 57 | PRP | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 | 2015-01-01 |  |  | 50000 | 0 | 50000 | 2000 | 4% | 48000 | 0 | 48000 | 3750 | 0 | 150 | 3600 | 0 | HPMP approved at 65th ExCom without inclusion of reconversion projects for foam sector. Will be submitted according to Decision 63/15 when alternatives for SMEs are available. | No activities in 2013. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAR | FOA | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 | 2015-01-01 |  |  | 60000 | 0 | 60000 | 16970.44 | 28.28% | 43029.56 | 0 | 43029.56 | 4500 | 0 | 1272.783 | 3227.217 | 0 | HPMP approved at 63rd ExCom without inclusion of reconversion projects for foam sector. Will be submitted according to Decision 63/15 when alternatives for SMEs are available. | No activities in 2013. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PER | FOA | 57 | PRP | 43 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 | 2015-03-01 |  |  | 80000 | 0 | 80000 | 53834 | 67.29% | 26166 | 4200 | 26166 | 6000 | 0 | 4037.55 | 1962.45 | 315 | Survey was prepared for the foam sector in Peru. Two investment projects were prepared and presented to the MLFS prior to ExCom 68. They were later deferred. | Pending payments have been made. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | URU | FOA | 57 | PRP | 52 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 51562.28 | 85.94% | 8437.72 | 0 | 8437.72 | 4500 | 0 | 3867.171 | 632.829 | 0 | Foam sector plan will be presented jointly with stage II HPMP in 2015. | No activities in 2013. | 2009 |  | Investment
ONG | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-05-31 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 41881.46 | 49.27% | 43118.54 | 0 | 43119 | 6375 | 0 | 3141 | 3234 | 0 | Due to inconclusive results of survey of available stocks conducted in 2011, two national experts undertook a new survey in June - August 2012. UNIDO identified gaps in data collection and defined three potential project strategies, which were presented to the NOU. The NOU committed in October 2012 to complete data collection on available stocks (without concrete timeline for this) following the recommendations by the national experts, and to make a decision on the preferred project strategy at their earliest convenience. | .-Finalization of survey on available stocks, based on the information provided by the NOU (1st quarter 2013); .-Agreement on project strategy (1st quarter 2013); .-Drafting of project document (in time for submission to the 70th Meeting of the Executive Committee in 2013) Reason for the delay: Up to April 2013 UNIDO did not receive any information from the NOU |  |  | NON-INV
ONG | UNIDO | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) | Individual | EUR | EUR | DES | 65 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 | 2013-06-01 |  |  | 35000 | 0 | 35000 | 30895.75 | 88.27% | 4104.25 | 254.02 | 2000 | 2625 | 0 | 2317 | 308 | 19 | Questionnaire for data collection prepared by UNEP/UNIDO. Coordination meeting with NOUs arranged by UNEP/UNIDO in the context of the Regional Network Meeting for ECA countries (Bishkek, Kyrgyzstan, 27-30 March 2012), where agreement was reached on workplan and timeline of activities. National experts undertook data collection on the field (completion date: 31 August 2012). The Czech Republic, UNEP and UNIDO organized a stakeholder meeting to discuss an advanced draft of the project document (Brno, Czech Republic, 26-28 November 2012). Most of the funds had been obligated by the end of 2012. | The project was approved at the 69th Meeting of the Executive Committee). Reason for the delay: The date of the stakeholder meeting (26-28 November 2012) Expenditures in 2013 are related to an international expert who has worked with UNIDO on the completion of the project document that was submitted to the ExCom at its 69th session. |  |  | NON-INV
ONG | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | LEB | DES | 61 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 | 2013-12-01 |  |  | 85000 | 0 | 85000 | 83866.27 | 98.67% | 1133.73 | 700 | 700 | 6375 | 0 | 6290 | 85 | 53 | 1. Detailed survey undertaken by international expert and report submitted to UNIDO. | 1. Finalization of project document with submission to the 70th Meeting of the Executive Committee. The project is expected to be completed in 2013. Reason for the delay: the preparation of the report by the international expert took longer than expected. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | DRK | FOA | 64 | PRP | 54 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 | 2013-12-01 |  |  | 50000 | 0 | 50000 | 10064.12 | 20.13% | 39935.88 | 4064.01 | 1000 | 3750 | 0 | 755 | 2995 | 305 | The project will be included into the HPMP. However, the HPMP could not be submitted to the 67th Meeting of the Executive Committee in 2012. | Resubmission of the HPMP to the 69th Meeting of the Executive Committee in 2013. Reason for the delay: Significant delays in the collection and submission of requested data and information by local consultants. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (commercial refrigeration sector) | Individual | ASP | DRK | REF | 64 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-11-01 | 2012-07-31 | 2013-12-01 |  |  | 30000 | 0 | 30000 | 9059.01 | 30.2% | 20940.99 | 0 | 1000 | 2250 | 0 | 679 | 1571 | 0 | The project will be included into the HPMP. However, the HPMP could not be submitted to the 67th Meeting of the Executive Committee in 2012. | Resubmission of the HPMP to the 69th Meeting of the Executive Committee in 2013. Reason for the delay: Significant delays in the collection and submission of requested data and information by local consultants. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | AFR | LIB | FOA | 63 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2011-04-01 |  | 2012-03-31 | 2013-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 10000 | 4500 | 0 | 0 | 4500 | 0 | Desk study on HPMP preparation has been completed. Field inspections; identification and verification of the manufacturing facilities have not been possible to carry out. The survey could not be completed and stakeholder workshop was postponed. Impediments: Security in the country has not yet improved. Delays & reasons for delays: accumulated delay due to still unstable situation in the country. Funds disbursed is zero, since it was not possible to proceed with important preparatory activities in the Country, like survey on HCFCs consumption; verification of eligibility for funding (in all sectors including non investment activities) and project formulation. Main obstacle is security in the Country. | To recruit national consultant to help NOU with field visits; verify the consumption of HCFCs, prepare HPMP. Mission preparation is in progress. Reason for the delay: the security and social situation in the country that have not improved and stabilized. |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | LIB | PHA | 63 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-08-01 | 2012-03-31 | 2013-12-01 |  |  | 65000 | 0 | 65000 | 12762.63 | 19.63% | 52237.37 | 3201.92 | 30000 | 4875 | 0 | 957 | 3918 | 240 | Desk study on HPMP preparation has been completed. Field inspections; identification and verification of the manufacturing facilities have not been possible to carry out. The survey could not be completed and stakeholder workshop was postponed. Impediments: Security in the country has not yet improved. | To recruit national consultant; verify the consumption of HCFCs, prepare HPMP. Reason for the delay: the security and social situation in the country that have not improved and stabilized. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (aerosol and solvent sectors) | Individual | LAC | MEX | MUS | 58 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 | 2013-03-01 |  |  | 100000 | 0 | 100000 | 81862.43 | 81.86% | 18137.57 | 17600 | 17600 | 7500 | 0 | 6140 | 1360 | 1320 | The project document has been finalized end of January 2013. The project covers 8 companies and aims to completely phase out use of HCFCs in the aerosol sector in Mexico. | The proposal will be submitted as part of Stage II HPMP. Project will be completed in Mar 2013. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | MEX | REF | 58 | PRP | 145 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-06-01 | 2010-07-31 | 2013-02-01 |  |  | 150000 | 0 | 150000 | 128891.04 | 85.93% | 21108.96 | 589.45 | 20000 | 11250 | 0 | 9667 | 1583 | 44.2088 | An expert mission was organized to review the technology selection for Fersa and Frigopanel. The project was completed in February 2013. | The project will be completed in February 2013. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SYR | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 | 2013-12-01 |  |  | 40000 | 0 | 40000 | 23186.1 | 57.97% | 16813.9 | 16721.95 | 1000 | 3000 | 0 | 1739 | 1261 | 1254 | Data collection on the foam sector (rigid PU) was undertaken. Project document was submitted for discussion at the 68th Meeting of the Executive Committee. Resubmission of the HPMP at a future meeting when national conditions have improved. |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | TUN | FOA | 58 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-10-01 | 2010-07-31 | 2013-12-01 |  |  | 65000 | 0 | 65000 | 46684.87 | 71.82% | 18315.13 | 208.82 | 18000 | 4875 | 0 | 3501 | 1374 | 15.6615 | The HPMP was finalized. Agreement and endorsement from national authorities were obtained. | The HPMP will be submitted to the 71st Meeting of the Executive Committee in July 2013. Reason for the delay: 1. Government authorities requested changes in the project document. 2. The endorsement of the authorities is stilll awaited. |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | URU | REF | 60 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 | 2014-12-01 |  |  | 50000 | 0 | 50000 | 28248.31 | 56.5% | 21751.69 | 2021.58 | 1000 | 3750 | 0 | 2119 | 1631 | 152 | We continued to finalize the proposal with non-HFC alternatives. | As soon as non-HFC alternatives are available the following milestones will be completed: - Experts recruited - All technical input completed - Draft Document completed The proposal is expected to be finalized next year.
TRF | Germany | Project preparation for phasing out ODS use in Pliva Pharmaceuticals | Individual | EUR | CRO | ARS | 36 | PRP | 16 | A | I |  | 0 |  | 0 |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-04-01 | 16500 | -16500 | 0 |  | #DIV/0! | 0 | 0 | 0 | 2145 | -2145 | 0 | 0 | 0 | Project was offset against Germany contributions at the 39th meeting. Project funds have been transferred to the Croatia Halon project preparation project.
TRF | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | AFR | EGY | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Transferred in 2003. Financially Completed in 2006. |  | 2002 |  | Investment
TRF | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2007-04-01 |  |  | 2007-12-01 | 12000 | -12000 | 0 | 0 |  | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
TRF | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | PNG | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-09-01 |  |  | 1998-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production (first tranche) | Multiyear | ASP | CPR | PAG | 47 | INV | 437 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2007-09-01 |  | 15000000 | 0 | 15000000 | 15000000 | 100% | 0 | 0 | 0 | 1125000 | 0 | 1125000 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 |  | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 0 | 0 | Implemented as planned and fully disbursed. |  |  |  | INV
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 |  | 20000000 | 0 | 20000000 | 20000000 | 100% | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Annual Program completed. |  |  |  | INV
COM | UNDP | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 48 | INV | 66 | N | I | CTC | 2 | 2 | 0 | 0 | 2006-04-01 | 2009-01-01 | 2007-12-01 |  | 2012-05-01 |  | 114480 | 0 | 114480 | 114478.55 | 100% | 1.45 | 0 | 1.16 | 10303 | 0 | 10302.8695 | 0.1305 | 0 | Completed in 2012. Final technical audit was conducted. | Completed in 2012. No activities in 2013. | 2006 |  | Investment
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100% | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  |  | INV
FIN | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 | 2005-01-01 | 2074300 | -109984 | 1964316 | 1964315.95 | 100% | 0.05 | 0.05 |  | 238173 | -12098.24 | 226074.76 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at GRD Chemicals Ltd., Indore, M.P. | Individual | ASP | IND | PAG | 34 | INV | 316 | A | I | CTC | 17.9 | 17.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-04-01 | 127667 | 0 | 127667 | 127667.03 | 100% | -0.03 | 0 |  | 16597 | -9 | 16588 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | Individual | ASP | IND | PAG | 34 | INV | 303 | A | I | CTC | 23 | 23 |  |  | 2001-07-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 136786 | -3906 | 132880 | 132880.22 | 100% | -0.22 | 0 |  | 17782 | -508 | 17274 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to trichloromethane at M/S Alpha Drugs India Ltd., Patiala | Individual | ASP | IND | PAG | 32 | INV | 283 | A | I | CTC | 69.7 | 69.7 |  |  | 2000-12-01 | 2001-11-01 | 2002-06-01 |  | 2003-03-01 | 2004-04-01 | 145866 | -130 | 145736 | 145735.54 | 100% | 0.46 | 0 |  | 15453 | -38 | 15415 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to ethylene dichloride at Chiplun Fine Chemicals Ltd., Ratnagiri | Individual | ASP | IND | PAG | 34 | INV | 313 | A | I | CTC | 16.7 | 16.7 |  |  | 2001-07-01 | 2002-02-01 | 2003-02-01 |  | 2003-07-01 | 2004-09-01 | 155830 | 0 | 155830 | 155829.82 | 100% | 0.18 | 0 |  | 20258 | -2 | 20256 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | Individual | ASP | IND | PAG | 34 | INV | 314 | A | I | CTC | 34.1 | 34.1 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2008-05-01 | 238371 | -191 | 238180 | 238179.69 | 100% | 0.31 | 0 |  | 30988 | -25 | 30963 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Svis Labs Ltd., Ranipet | Individual | ASP | IND | PAG | 32 | INV | 284 | A | R | CTC | 54.2 | 54.2 |  |  | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 249547 | 0 | 249547 | 249547.11 | 100% | -0.11 | 0 |  | 25352 | -9 | 25343 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Satya Deeptha Pharmaceuticals Ltd., Humnabad | Individual | ASP | IND | PAG | 32 | INV | 287 | A | I | CTC | 27.9 | 27.9 |  |  | 2000-12-01 | 2001-11-01 | 2002-07-01 |  | 2002-12-01 | 2004-12-01 | 260133 | -659 | 259474 | 259473.58 | 100% | 0.42 | 0 |  | 33817 | -139 | 33678 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at Praddep Shetye Ltd., Alibagh | Individual | ASP | IND | PAG | 34 | INV | 311 | A | I | CTC | 133.9 | 133.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 279001 | -10 | 278991 | 278991.21 | 100% | -0.21 | 0 |  | 36270 | -1 | 36269 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Doctors Organic Chemicals Ltd., Tanuku | Individual | ASP | IND | PAG | 32 | INV | 291 | A | I | CTC | 94.6 | 94.6 |  |  | 2000-12-01 | 2002-01-01 | 2002-06-01 |  | 2002-12-01 | 2003-12-01 | 288809 | -171 | 288638 | 288638.31 | 100% | -0.31 | 0 |  | 37545 | -82 | 37463 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to cyclohexane at Amoli Organics Ltd., Mumbai | Individual | ASP | IND | PAG | 35 | INV | 338 | A | I | CTC | 38.5 | 38.5 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-08-01 | 2007-01-01 | 385367 | -1454 | 383913 | 383912.67 | 100% | 0.33 | 0 |  | 50098 | -189 | 49909 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | Individual | ASP | PAK | PAG | 35 | INV | 42 | A | I | CTC | 80 | 80 |  |  | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2008-10-01 | 2011-03-01 | 485701 | -3651 | 482050 | 482050.16 | 100% | -0.16 | 0 |  | 63141 | -474 | 62667 | 0 | 0 | FIN |  |  |  | INV
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 04 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 09 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 |  | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. |  |  |  | Non-INV
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 |  | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 09 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 04 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | UNDP | Project preparation assistance | Individual | AFR | ETH | SEV | 17 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1997-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1995 |  | Investment
CLO | UNDP | Advance for project preparation as indicated in the 1998 business plan | Individual | GLO | GLO | SEV | 23 | PRP | 154 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-03-01 |  |  | 1998-03-01 | 256000 | -256000 | 0 | 0 |  | 0 | 0 | 0 | 33280 | -33280 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
CLO | UNDP | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 176 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-03-01 |  |  | 1999-03-01 | 299000 | -299000 | 0 | 0 |  | 0 | 0 | 0 | 38870 | -38870 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1998 |  | Investment
CLO | UNDP | Project preparation advance for the year 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 190 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2003-09-01 | 250000 | -250000 | 0 | 0 |  | 0 | 0 | 0 | 32500 | -32500 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 227 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2001-12-01 |  |  | 2001-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2001. |  | 2001 |  | Investment
CLO | UNDP | Project preparation advance (2002) | Individual | GLO | GLO | SEV | 35 | PRP | 236 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2002-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2002 |  | Investment
CLO | UNIDO | Project formulation of investment projects in the foam and refrigeration sectors | Individual | AFR | CMR | SEV | 21 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  |  | 2001-07-01 | 50000 | -23644 | 26356 | 26356.43 | 100% | -0.43 | 0 |  | 6500 | -3079 | 3421 | 0 | 0 | CLO
CLO | UNIDO | Preparation of an investment project in a plant (Elasta) for the production of polyurethane flexible foam for automotive industry | Individual | LAC | ECU | SEV | 17 | PRP | 17 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1995-09-01 |  |  | 1999-12-01 | 15000 | -9243 | 5757 | 5757 | 100% | 0 | 0 |  | 1950 | -1203 | 747 | 0 | 0 | CLO
FIN | Germany | Project preparation/technical assistance in the refrigeration sector (thermostat) | Individual | ASP | CPR | SEV | 33 | PRP | 372 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2001-12-01 |  | 2002-01-01 | 2002-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed; no PCR due to project preparation only
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 04 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Funds committed in CY96 were disbursed in CY97. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 09 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Newly approved. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 07 | PRP | 21 | N | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 09 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Ongoing. |  |  |  | Non-INV
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100% | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. |  |  |  | Non-INV
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | NCPP submitted and approved at the 41st ExCom. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 04 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100% | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 08 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100% | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Foam and aerosol proposals prepared and submitted to Excom. |  |  |  | Non-INV
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation and processing complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 09 | PRP | 03 | N | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. 14 subproject proposals were prepared. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  | 1999-06-01 | Non-INV
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project preparation is completed. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 04 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 09 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 04 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. |  |  |  | Non-INV
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | Completed. |  |  | 1999-06-01 | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Ongoing |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Bank is evaluating its activities in the country. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 09 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities completed |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 06 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 09 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. Balance of funds returned to Multilateral Fund. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Umbrella Grant Agreement signed. |  |  |  | Non-INV
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | Ongoing |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed and closed. Balance returned to Multilateral Fund. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision completed. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for supervision on project implementation. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 09 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  | 1999-03-01 | Non-INV
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. |  |  |  | Non-INV
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is now complete. |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV
FIN | UNDP | Project preparation | Individual | LAC | ARG | SEV | 22 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 17 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-03-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance (1994) | Individual | LAC | ARG | SEV | 14 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-09-01 | 1995-09-01 |  | 1995-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | BGD | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BOL | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-05-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | BRA | SEV | 22 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-08-01 | 1997-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 17 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-07-01 |  | 1996-01-01 | 1997-12-01 | 75000 | -2 | 74998 | 74998 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 11 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1994-11-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | CAF | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 18 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 17 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-04-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 12 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | LAC | COS | SEV | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-04-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Assistance in project preparation | Individual | LAC | COS | SEV | 08 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-05-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | CPR | SEV | 09 | PRP | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 11 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 15 | PRP | 106 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 17 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-04-01 |  | 1996-03-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 18 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 22 | PRP | 197 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 21 | PRP | 191 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance in foams and refrigeration | Individual | LAC | DOM | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | SEV | 18 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Preparation of investment projects | Individual | AFR | EGY | SEV | 06 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1993-09-01 | 2003-04-01 | 100000 | 319 | 100319 | 100319 | 100% | 0 | 0 | 0 | 13000 | 41 | 13041 | 0 | 0 | Completed in 1993. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | GUA | SEV | 11 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 30000 | 257 | 30257 | 30257 | 100% | 0 | 0 | 0 | 3900 | 34 | 3934 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 11 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1994-11-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance in solvent, halon and refrigeration sectors | Individual | ASP | IDS | SEV | 15 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-03-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation | Individual | ASP | IND | SEV | 22 | PRP | 129 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Assistance in project preparation in all sectors | Individual | ASP | IND | SEV | 08 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 100000 | -18339 | 81661 | 81661 | 100% | 0 | 0 | 0 | 13000 | -2384 | 10616 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 12 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 18 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | IND | SEV | 21 | PRP | 109 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-11-01 | 2000-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | IRA | SEV | 08 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-11-01 | 1993-10-01 |  | 1995-03-01 | 1997-12-01 | 17935 | 0 | 17935 | 17935 | 100% | 0 | 0 | 0 | 2332 | 0 | 2332 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNDP | Project preparation in the aerosol, foam and refrigeration sectors | Individual | LAC | JAM | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 30000 | -16175 | 13825 | 13825 | 100% | 0 | 0 | 0 | 3900 | -2103 | 1797 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | JAM | SEV | 14 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 18 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 18000 | -4 | 17996 | 17996 | 100% | 0 | 0 | 0 | 2340 | -1 | 2339 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 10 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-12-01 |  | 1994-03-01 | 1997-12-01 | 50000 | 4438 | 54438 | 54438 | 100% | 0 | 0 | 0 | 6500 | 577 | 7077 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | MAL | SEV | 21 | PRP | 93 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2004-12-01 | 100000 | -34365 | 65635 | 65635 | 100% | 0 | 0 | 0 | 13000 | -4467 | 8533 | 0 | 0 | Completed in 1998. Financially Completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 12 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 15 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | MEX | SEV | 22 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 17 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1996-11-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam and solvent sectors | Individual | LAC | MEX | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 52000 | -2539 | 49461 | 49461 | 100% | 0 | 0 | 0 | 6760 | -330 | 6430 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 11 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Preparation of terms of reference for investment projects identified in the country programme | Individual | LAC | MEX | SEV | 04 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1993-12-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 2277 | 52277 | 52277 | 100% | 0 | 0 | 0 | 6500 | 296 | 6796 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 14 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-12-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | MLW | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 | 0 | 910 | 0 | 910 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation | Individual | AFR | MOR | SEV | 22 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | NIR | SEV | 17 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 11 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 18 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-03-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 13 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1996-07-01 |  | 1995-09-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 18 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-07-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 15 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1994-12-01 | 1995-12-01 |  | 1996-03-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance in recovery and recycling of refrigerant, foam and halon sectors | Individual | AFR | PRC | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | SRL | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-06-01 |  | 1996-06-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 18 | PRP | 49 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 2002-05-01 | 3000 | 0 | 3000 | 3000 | 100% | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 10 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-06-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | THA | SEV | 21 | PRP | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2001-12-01 | 100000 | -40377 | 59623 | 59623 | 100% | 0 | 0 | 0 | 13000 | -5249 | 7751 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance in foam, halon and aerosol sectors | Individual | ASP | THA | SEV | 15 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation in the aerosol, refrigeration and solvent sectors | Individual | LAC | TRI | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 40000 | -4596 | 35404 | 35404 | 100% | 0 | 0 | 0 | 5200 | -597.48 | 4602.52 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | UGA | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | URT | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1998-12-01 | 1999-12-01 | 47000 | 0 | 47000 | 47000 | 100% | 0 | 0 | 0 | 6110 | 0 | 6110 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-07-01 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Preparation of a terminal phase-out plan | RMP | LAC | BHA | SEV | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-12-01 | 2002-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Country programme/RMP project preparation | RMP | AFR | ERI | SEV | 47 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 40000 | -2000 | 38000 | 38000 | 100% | 0 | 0 | 0 | 5200 | -260 | 4940 | 0 | 0 | Project financially completed. ($ 24,380 plus $ 3,169 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Formulation of the country programme/RMP | RMP | AFR | GBS | SEV | 39 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-07-01 | 2011-03-01 | 60000 | -14454 | 45546 | 45546 | 100% | 0 | 0 | 0 | 7800 | -1879.02 | 5920.98 | 0 | 0 | Project completed in December 2010. Training of technicians in recovery and reuse of refrigerants and good servicing practices was held. The service technicians formed an association. The recovery and recycling (R&R) programme is progressing with good results. A total of 17 R&R centres were established throughout Grenada. A local consultant attended the 2010 LAC network meeting in October 2010 in Mexico City, Mexico. A national staff attended a technical workshop in Belize. |  |  |  | Non Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in the aerosol production and solvent conversion at ENAD | Individual | AFR | ALG | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -5049 | 19951 | 19951 | 100% | 0 | 0 |  | 3250 | -661 | 2589 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production at ENIEM | Individual | AFR | ALG | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-08-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -675 | 24325 | 24325 | 100% | 0 | 0 |  | 3250 | -93 | 3157 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the aerosol, foam and refrigeration sectors | Individual | AFR | ALG | SEV | 21 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-05-01 | 1997-08-01 |  | 1998-02-01 | 2002-09-01 | 50000 | -2690 | 47310 | 47309.6 | 100% | 0.4 | 0 |  | 6500 | -359 | 6140 | 1 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in small- and medium-scale industries | Individual | AFR | ALG | SEV | 17 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1996-01-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -1409 | 48591 | 48591 | 100% | 0 | 0 |  | 6500 | -193 | 6307 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | ARG | SEV | 21 | PRP | 52 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 2000-06-02 | 2002-05-01 | 32140 | 0 | 32140 | 32140.49 | 100% | -0.49 | 0 |  | 4178 | 0 | 4178 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Preparation of investment project in a plant (Elgin) consuming 60 metric tons of TCA used as a degreasing agent in the production of compressors | Individual | LAC | BRA | SEV | 17 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-05-01 | 1995-09-01 |  | 1997-10-01 | 1998-08-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | BRA | SEV | 21 | PRP | 63 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-06-01 | 2000-12-01 | 57140 | -718 | 56422 | 56422 | 100% | 0 | 0 |  | 7428 | -105 | 7323 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project formulation of investment projects in the halon sector in the 3 fire equipment factories (Xiangshan, Xiangshan No. 1 and Dalian Jinzhou) and in domestic refrigeration sectors and solvents | Individual | ASP | CPR | SEV | 17 | PRP | 132 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 1998-12-01 | 2000-07-01 | 100000 | -193 | 99807 | 99807 | 100% | 0 | 0 |  | 13000 | -46 | 12954 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the refrigeration (including compressors), solvents and methyl bromide sectors | Individual | ASP | CPR | SEV | 21 | PRP | 190 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1999-12-01 | 2002-09-01 | 182140 | -575 | 181565 | 181565.3 | 100% | -0.3 | 0 |  | 23678 | -112 | 23566 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in all sectors | Individual | ASP | DRK | SEV | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 2000-10-01 | 2001-07-01 | 70000 | -1720 | 68280 | 68280 | 100% | 0 | 0 |  | 9100 | -238 | 8862 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 175 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  | 1999-12-01 | 2001-02-01 | 169000 | -169000 | 0 | 0 |  | 0 | 0 |  | 21970 | -21970 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance for 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 189 | A | I |  | 0 | 0 |  |  | 1999-11-01 |  | 2000-04-01 |  | 2000-12-01 | 2003-05-01 | 170000 | -170000 | 0 | 0 |  | 0 | 0 |  | 22100 | -22100 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 216 | A | I |  | 0 | 0 |  |  | 2000-12-01 |  | 2001-12-01 |  | 2001-03-01 | 2001-03-01 | 139500 | -139500 | 0 | 0 |  | 0 | 0 |  | 18135 | -18135 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 35 | PRP | 234 | A | I |  | 0 | 0 |  |  | 2001-12-01 |  | 2002-03-01 |  | 2002-03-01 | 2002-03-01 | 176250 | -176250 | 0 | 0 |  | 0 | 0 |  | 22913 | -22913 | 0 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation of investment projects in the aerosol and foam sectors | Individual | ASP | IDS | SEV | 21 | PRP | 54 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 2000-10-01 | 2001-07-01 | 20000 | -4478 | 15522 | 15522 | 100% | 0 | 0 |  | 2600 | -585 | 2015 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of an investment project for phasing out ODS at three enterprises including the companies Nirwana and P.T. Success | Individual | ASP | IDS | SEV | 23 | PRP | 64 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-10-01 | 2001-07-01 | 10000 | 9025 | 19025 | 19024.96 | 100% | 0.04 | 0 |  | 1300 | 1169 | 2469 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in small and medium scale industries | Individual | ASP | IDS | SEV | 15 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-01-01 | 2002-05-01 | 80000 | -2803 | 77197 | 77197.25 | 100% | -0.25 | 0 |  | 10400 | -380 | 10020 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project formulation for phasing out ODS in the unorganized sector | Individual | ASP | IND | SEV | 10 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-05-01 | 1993-10-01 |  | 1999-12-01 | 2000-09-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of investment projects in the foam sector | Individual | ASP | IRA | SEV | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-08-01 | 32065 | 698 | 32763 | 32763 | 100% | 0 | 0 |  | 4168 | 91 | 4259 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the commercial refrigeration sector (remaining enterprises), compressors and the foam sector | Individual | ASP | IRA | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -8 | 6492 | 0 | 0 | FIN
FIN | UNIDO | ODS phase-out of a foam producing plant (Fabrique Ivoirienne de mousse et amemblement) and 2 aerosol fillers (Sicobel and Gandoor) | Individual | AFR | IVC | SEV | 17 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-02-01 | 1995-09-01 |  | 1996-10-01 | 1998-08-01 | 10000 | -388 | 9612 | 9612 | 100% | 0 | 0 |  | 1300 | -52 | 1248 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for investment projects in commercial refrigeration, air-conditioning, foam and halon sectors | Individual | ASP | JOR | SEV | 15 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 50000 | -827 | 49173 | 49173 | 100% | 0 | 0 |  | 6500 | -118 | 6382 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Identification and preparation of projects in the solvents and aerosols sectors | Individual | AFR | KEN | SEV | 17 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1995-11-01 |  | 1998-03-02 | 1999-08-01 | 15000 | -938 | 14062 | 14062 | 100% | 0 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | National phase-out plan | Individual | AFR | LIB | SEV | 38 | PRP | 21 | A | I | CFC | 0 | 0 |  |  | 2002-11-01 | 2003-09-01 | 2003-12-01 |  | 2005-06-01 | 2006-08-01 | 40000 | -468 | 39532 | 39531.5 | 100% | 0.5 | 0 |  | 5200 | -61 | 5139 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of projects in the refrigeration, aerosol and foam sector | Individual | EUR | MDN | SEV | 18 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-01-01 | 1996-03-01 |  | 2000-12-01 | 2002-05-01 | 30000 | -3675 | 26325 | 26325.22 | 100% | -0.22 | 0 |  | 3900 | -483 | 3417 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of investment projects | Individual | LAC | MEX | SEV | 18 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-08-01 |  | 1997-09-01 | 2000-07-01 | 50000 | -477 | 49523 | 49523 | 100% | 0 | 0 |  | 6500 | -72 | 6428 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in domestic refrigeration and methyl bromide sectors | Individual | AFR | MOR | SEV | 21 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-06-01 |  | 1999-09-01 | 2000-12-01 | 22150 | -1502 | 20648 | 20648 | 100% | 0 | 0 |  | 2880 | -200 | 2680 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of investment projects in the refrigeration, aerosol and foam sectors | Individual | AFR | SUD | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-03-01 | 1995-01-01 |  | 1998-04-01 | 1999-08-01 | 50000 | -5442 | 44558 | 44558 | 100% | 0 | 0 |  | 6500 | -717 | 5783 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration industry | Individual | ASP | SYR | SEV | 09 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-11-01 | 1993-09-01 |  | 1994-12-01 | 1996-05-01 | 35000 | -5 | 34995 | 34995 | 100% | 0 | 0 |  | 4550 | -8 | 4542 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the aerosol, foam, solvents and methyl bromide sectors | Individual | AFR | TUN | SEV | 21 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 1999-05-01 | 2000-12-01 | 27150 | -1020 | 26130 | 26130 | 100% | 0 | 0 |  | 3530 | -138 | 3392 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of investment projects in the aerosol, foam, domestic refrigeration and solvent sectors | Individual | AFR | TUN | SEV | 17 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1998-03-01 | 1999-08-01 | 30000 | -1697 | 28303 | 28303 | 100% | 0 | 0 |  | 3900 | -226 | 3674 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration, air conditioning and recovery/recycling | Individual | AFR | ZIM | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -463 | 39537 | 39537 | 100% | 0 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | Project preparation/technical assistance |  | LAC | ARG | SEV | 13 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation in commercial refrigeration |  | LAC | DOM | REF | 17 | PRP | 02 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1995-09-01 | 1995-09-01 | 19000 | 0 | 19000 | 19000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Support for country programme preparation and development of project proposals |  | LAC | MEX | SEV | 07 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-06-01 | 145000 | 136000 | 281000 | 281000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $136,000 credited against 1993 contributions (11th Meeting).
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1999-12-01 | Non-INV
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 07 | DEM | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  |  | Non-INV
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | CAF | REF | 20 | TAS | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-09-01 |  |  | 2001-12-01 | 66441 | -923 | 65518 | 65518 | 100% | 0 | 0 | 0 | 8637.33 | -120.334 | 8516.996 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1999-06-01 | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | URT | REF | 22 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2001-12-01 | 161554 | -153795 | 7759 | 7759 | 100% | 0 | 0 | 0 | 21002.02 | -19993 | 1009.02 | 0 | 0 | Canceled in 2000. Financially completed in 2001. |  | 1997 |  | Investment
COM | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COL | REF | 17 | TAS | 19 | N | I | CFC | 111 | 111 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-07-01 |  | 1999-07-01 |  | 787030 | -4.66 | 787025.34 | 787025 | 100% | 0.34 | 0 | 0.272 | 102313.9 | -0.9 | 102312.9558 | 0.0442 | 0 | Completed in 1999. |  | 1995 | 1999-06-01 | Investment
FIN | Australia | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | Individual | LAC | ARG | REF | 17 | TAS | 24 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1996-02-01 | 1996-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 | 2005-06-01 | 282687 | -42162 | 240525 | 240525 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed |  | 1996 | 1997-12-01
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 |  | Non-Inv.
FIN | Denmark | Establishment of a CFC recycling centre at Zhejiang Donggyang Chemical Factory |  | ASP | CPR | REF | 17 | TAS | 130 | N | I |  | 20 |  |  |  | 1995-07-01 | 1996-10-01 | 1996-07-01 | 1998-12-01 | 1998-12-01 |  | 205000 | -43947 | 161053 | 161053.25 | 100% | -0.25 |  | 0 |  |  |  | 0 |  | Completed. Project Document signed in March 1996. Procurement comtract initialed in August 1996 but contract was not signed until 1997. Major delay caused by disagreement on contractual terms. Building modification work completed by enterprise in May 1998 and equipment delivered and installed in June 1998. A seminar for evaluation and dissemination of work experience was held 15-16 December 1998. All project activities were completed in December 1998. More than 50 tons of CFC has been recovered. A few tons of CFC had further been recycled at the reclaim station. |  |  | 1996-12-01
FIN | France | Set up of a national programme of recovery and recycling CFC-12 (pilot project in Tehran) |  | ASP | IRA | REF | 23 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1999-10-01 | 1998-12-01 |  | 2004-12-01 | 2004-12-01 | 345923 | -103154.97 | 242768.03 | 242768 | 100% | 0.03 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed; balance returned at the 57th meeting.
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | ASP | LEB | REF | 23 | TAS | 21 | A | I | CFC | 62 |  | 0 |  | 1997-11-01 |  | 1998-12-01 |  | 2010-12-01 | 2012-10-01 | 425289 | 0 | 425289 | 425289 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | AFR | MOR | REF | 23 | TAS | 17 | A | I | CFC | 22 | 22 | 0 |  | 1997-11-01 | 2003-09-01 | 1998-12-01 |  | 2011-06-01 | 2012-12-01 | 355867 | 0 | 355867 | 355867 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | Germany | Recovery and recycling project | Individual | AFR | KEN | REF | 28 | TAS | 24 | A | I | CFC | 8.5 | 5 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2001-08-01 |  | 2004-05-01 | 2004-10-01 | 98725 | 0 | 98725 | 98725 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to the 44th Excom.
FIN | Germany | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | Individual | AFR | MAR | REF | 28 | TAS | 12 | A | I | CFC | 8 | 5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-06-01 |  | 2005-12-01 | 2006-09-01 | 183377 | -3647 | 179730 | 179730 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certification of R&R center. Follow-up evaluation of the performance of recycling center. Recommendation that the training institue should cooperate with the local gas dealer in utilizing the facility. PCR was submitted in 2006.
FIN | Germany | Recuperation and recycling of CFC-12 integrated with the introduction of hydrocarbon technology in the service sector | Individual | AFR | NAM | REF | 24 | TAS | 05 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-06-01 |  | 1998-06-01 | 2000-01-01 | 34400 | -244 | 34156 | 34156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Recovery and recycling of CFCs | Individual | AFR | URT | REF | 36 | TAS | 14 | A | I | CFC | 11.7 | 11.7 | 0 |  | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2008-08-01 | 2009-12-01 | 164223 | -9924 | 154299 | 154299 | 100% | 0 | 0 | 0 | 21349 | -1290.12 | 20059 | -0.12 | 0 | Under the contract the only remaining activity is the construction of the recovery and recycling center. As the local partner cannot give a concrete date of finalization of the construction we suggested to declare the project completed and return the rest of the fund to the MLF. NOU agreed to the PCR in Nov-2008. PCR has been submitted to MLF in Apr-2009. Funds will be returned to MLF.
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 07 | TAS | 22 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | INV
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 06 | INV | 04 | N | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-06-01 | INV
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100% | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | 1999-12-01 | INV
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 05 | TAS | 08 | N | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 05 | TAS | 13 | N | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. |  |  |  | INV
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 05 | DEM | 06 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 07 | TAS | 07 | N | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR provided in June 1998 |  |  | 1997-06-01 | INV
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 07 | TAS | 03 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | INV
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 07 | TAS | 04 | N | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-06-01 | INV
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1999-12-01 | INV
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | ASP | BAH | REF | 22 | TAS | 04 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 242000 | -2849 | 239151 | 239151 | 100% | 0 | 0 | 0 | 31460 | -370 | 31090 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BOL | REF | 20 | TAS | 04 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 146000 | -691 | 145309 | 145309 | 100% | 0 | 0 | 0 | 18980 | -90 | 18890 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COS | REF | 08 | TAS | 04 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1992-10-01 | 1997-01-01 | 1998-09-01 |  | 2000-06-01 | 2004-03-01 | 88000 | 233693 | 321693 | 321693 | 100% | 0 | 0 | 0 | 11440 | 30380 | 41820 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1992 | 1999-08-01 | Investment
FIN | UNDP | Acquisition of local air compressors for halon recycling machines | Individual | ASP | CPR | HAL | 12 | INV | 66 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-12-01 | 1998-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Demonstration project (refrigeration - large food stores) | RMP-Component | ASP | CPR | REF | 17 | DEM | 131 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1997-06-01 | 2002-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Non-Investment
FIN | UNDP | Survey on policy and planning measures to promote recycling of CFC | RMP-Component | ASP | CPR | REF | 11 | TAS | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-05-01 | 1994-11-01 |  | 1997-12-01 | 2000-12-01 | 100000 | -19358 | 80642 | 80642 | 100% | 0 | 0 | 0 | 13000 | -2517 | 10483 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | CUB | REF | 15 | TAS | 04 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-12-01 |  | 1997-09-01 | 1998-12-01 | 169000 | -5167 | 163833 | 163833 | 100% | 0 | 0 | 0 | 21970 | -672 | 21298 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Demonstration project in commercial refrigeration (food storage, distribution and retailing) | RMP-Component | LAC | DOM | REF | 18 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-04-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Improved servicing and maintenance within the refrigeration sector | RMP-Component | AFR | GHA | REF | 08 | TAS | 04 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-04-01 | 1998-12-01 | 328000 | 0 | 328000 | 328000 | 100% | 0 | 0 | 0 | 42640 | 0 | 42640 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Procurement of 40 halon recycling machines for demonstration | Individual | GLO | GLO | HAL | 07 | DEM | 25 | A | I | HAL | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-09-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global MACs project: Phase 2 | RMP-Component | GLO | GLO | REF | 18 | TAS | 90 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1997-11-01 |  | 1999-05-01 | 2004-01-01 | 500000 | -1 | 499999 | 499999 | 100% | 0 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | GUA | REF | 18 | TAS | 09 | A | I | CFC | 26 | 26 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-12-01 | 2002-03-01 | 256780 | -19649 | 237131 | 237131 | 100% | 0 | 0 | 0 | 33381.4 | -2554.4 | 30827 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | JAM | REF | 18 | TAS | 03 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1997-05-01 | 2000-12-01 | 172465 | -13366.44 | 159098.56 | 159099 | 100% | -0.44 | 0 | 0 | 22420.45 | -1738.4472 | 20682.06 | -0.057198 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Regional Latin America demonstration project in recovery of ODS in MACs: Phase I (Argentina, Colombia) | RMP-Component | LAC | LAC | REF | 18 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1999-05-01 | 207000 | 0 | 207000 | 207000 | 100% | 0 | 0 | 0 | 26910 | 0 | 26910 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | LES | REF | 22 | TAS | 04 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2000-12-01 | 56095 | 0 | 56095 | 56095 | 100% | 0 | 0 | 0 | 7292 | 0 | 7292 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Recovery of CFC-12 servicing of domestic refrigeration at Vitromatic Comercial y Servicios Integrados | RMP-Component | LAC | MEX | REF | 18 | TAS | 43 | N | I | CFC | 76 | 76 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1997-10-01 | 2002-12-01 | 352610 | -47579 | 305031 | 305031 | 100% | 0 | 0 | 0 | 45839.3 | -6185.3 | 39654 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MLW | REF | 19 | TAS | 05 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -311 | 106009 | 106009 | 100% | 0 | 0 | 0 | 13821.6 | -39.6 | 13782 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MOZ | REF | 22 | TAS | 06 | A | I | CFC | 6.9 | 6.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 115809 | -138 | 115671 | 115671 | 100% | 0 | 0 | 0 | 15055.17 | -18.1725 | 15036.9975 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PAN | REF | 18 | TAS | 06 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-07-01 | 2003-11-01 | 172465 | -10608 | 161857 | 161857 | 100% | 0 | 0 | 0 | 22420.45 | -1379.45 | 21041 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PER | REF | 19 | TAS | 17 | A | I | CFC | 28.6 | 28.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 2001-12-01 | 2003-04-01 | 342695 | -53108 | 289587 | 289587 | 100% | 0 | 0 | 0 | 44550.35 | -6904.35 | 37646 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | PRC | REF | 20 | TAS | 04 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 1998-10-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 201200 | -13880 | 187320 | 187320 | 100% | 0 | 0 | 0 | 26156 | -1804 | 24352 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | ASP | SRL | REF | 20 | TAS | 08 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1999-12-01 | 2001-12-01 | 352400 | -1472 | 350928 | 350928 | 100% | 0 | 0 | 0 | 45812 | -191.0023 | 45620.9977 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | UGA | REF | 19 | TAS | 05 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 56000 | -17 | 55983 | 55983 | 100% | 0 | 0 | 0 | 7280 | -2.21 | 7277.79 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 04 | N | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12.48 | 22737.52 | 0 | 0 | Completed in 1996. Financially completed in 2004. |  | 1994 |  | Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121110.9 | -8002 | 113108.9 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868.08 | -1330.9351 | 20537.1449 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 2000-07-01 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 06 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13821.6 | -31.2 | 13790.4 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNIDO | CFC-recovery, recycling and training in refrigeration | RMP | LAC | BAR | REF | 18 | TAS | 04 | A | I | CFC | 14 | 14 |  |  | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 1997-06-01 | 2000-07-01 | 165170 | -222 | 164948 | 164948 | 100% | 0 | 0 |  | 21472 | -63 | 21409 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BEN | REF | 22 | TAS | 04 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 114000 | 0 | 114000 | 114000 | 100% | 0 | 0 |  | 14820 | -13 | 14807 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BKF | REF | 22 | TAS | 05 | A | I | CFC | 15.48 | 15.48 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | FIN
FIN | UNIDO | Refrigeration recovery and recycling scheme | RMP | AFR | GAM | REF | 22 | TAS | 05 | A | I | CFC | 7.7 | 7.7 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 68000 | -243 | 67757 | 67757 | 100% | 0 | 0 |  | 8840 | -45 | 8795 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | GUI | REF | 22 | TAS | 05 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-01 | 80780 | 0 | 80780 | 80780 | 100% | 0 | 0 |  | 10501 | 0 | 10501 | 0 | 0 | FIN
FIN | UNIDO | Feasibility study for recovery/recycling of CFC refrigerants | RMP | ASP | IND | REF | 10 | TAS | 05 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-02-01 | 1993-10-01 |  | 1998-06-01 | 1999-08-01 | 55000 | -42920 | 12080 | 12080 | 100% | 0 | 0 |  | 7150 | -5582 | 1568 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC recovery and recycling scheme | RMP | ASP | PHI | REF | 22 | TAS | 49 | A | I | CFC | 60 | 60 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2002-05-01 | 557500 | -49 | 557451 | 557450.97 | 100% | 0.03 | 0 |  | 72475 | -121 | 72354 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | SEN | REF | 22 | TAS | 08 | A | I | CFC | 36.12 | 36.12 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-03-01 | 136250 | 0 | 136250 | 136250 | 100% | 0 | 0 |  | 17713 | 0 | 17713 | 0 | 0 | FIN
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 04 | A | I | CFC | 47 | 47 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -143 | 312157 | 312157 | 100% | 0 | 0 |  | 40599 | -83 | 40516 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | Deployment of halon-1211 recovery/recharge machines |  | ASP | CPR | HAL | 12 | INV | 59 | A | I | HAL | 200 | 231 | 0 |  | 1994-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1996-06-01 | 735000 | 72000 | 807000 | 807000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project (refrigeration - large food stores) |  | ASP | CPR | REF | 17 | DEM | 135 | A | I |  | 0 |  | 0 |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1998-01-01 | 1998-12-01 | 132000 | 26400 | 158400 | 158400 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-06-01
FIN | USA | Demonstration project in commercial refrigeration (food storage, distribution and retailing) |  | LAC | DOM | REF | 18 | DEM | 05 | A | I |  | 0 | 7 | 0 |  | 1995-11-01 | 1995-11-01 | 1996-12-01 |  | 1998-02-01 | 1999-10-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
TRF | UNDP | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | RMP-Component | AFR | MAR | REF | 17 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1996-07-01 |  |  | 1999-07-01 | 176350 | -162281 | 14069 | 14069 | 100% | 0 | 0 | 0 | 22925.5 | -21095.5 | 1830 | 0 | 0 | Transferred in 1999. Financially completed in 1999. |  | 1995 | 1999-07-01 | Investment
CLO | France | Implementation of the RMP: development and implementation of a tax/incentive programme |  | AFR | CAF | REF | 34 | TAS | 10 | N | I |  | 0.3 | 0.1 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  |  | 2009-04-01 | 5500 | -3904 | 1596 | 1596 | 100% | 0 |  | 0 | 715 | -508 | 207 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom)
CLO | France | Implementation of the RMP: training programme for customs officers |  | AFR | CAF | REF | 34 | TRA | 08 | N | I |  | 4.4 | 2.9 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  |  | 2009-04-01 | 77440 | -26940 | 50500 | 50500 | 100% | 0 |  | 0 | 10067 | -3502 | 6565 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
CLO | France | Implementation of the RMP: monitoring the activities of the RMP project, including registration of refrigeration service technicians, distributors and importers of CFCs |  | AFR | CAF | REF | 34 | TRA | 11 | N | I |  | 1.5 | 1 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  |  | 2009-04-01 | 26250 | -8986 | 17264 | 17264 | 100% | 0 |  | 0 | 3413 | -1168 | 2245 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
CLO | France | Implementation of the RMP: train the trainers programme for refrigeration technicians in good management practices and a training programme to address technicians in the informal sector |  | AFR | CAF | REF | 34 | TRA | 09 | A | I |  | 3.4 | 2.4 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  |  | 2009-04-01 | 60900 | -17759 | 43141 | 43141 | 100% | 0 |  | 0 | 7917 | -2309 | 5608 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
CLO | France | Implementation of the refrigerant management plan: monitoring the activities of the RMP and set up of an import/export licensing system | RMP | AFR | IVC | REF | 37 | TAS | 16 | A | I | CFC | 188.7 |  | 0 |  | 2002-07-01 |  | 2004-08-01 |  |  | 2009-04-01 | 49500 | -49500 | 0 | 0 |  | 0 |  | 0 | 4950 | -4950 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
CLO | France | Implementation of the RMP | RMP | AFR | IVC | REF | 24 | TAS | 10 | A | I | CFC | 24.8 |  | 0 |  | 1998-03-01 | 1999-10-01 | 2000-04-01 |  |  | 2009-04-01 | 227650 | -196214 | 31436 | 31436 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
COM | Germany | Implementation of the RMP: enforcement of regulations, training of customs officers, training of refrigeration service technicians, recovery and recycling, incentive programme for end-users, and public awareness | RMP Update | AFR | ANG | REF | 39 | TAS | 04 | A | I | CFC | 97.6 | 97.8 | 0 | 0 | 2003-04-01 | 2003-11-01 | 2008-04-01 |  | 2009-12-01 |  | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 87000 | 0 | 87000 | 0 | 0 | Additional Training courses in Refrigeration Sector were conducted in Huige and Huambo Provices.- A public awareness campaign has been launched in the provinces of Huila, Moxico, Huambo, Bie and Malange, with the additional aim of formation of interministerial support groups.- Working group of legal experts has been created in order to finalize and submit draft on ODS related legislation and regulations. - Survey has been undertaken in provinces and Luanda in order to identify ODS consuming companies which may qualify for Incentive programme. - R&R centre has been established in Huambo (Central Angola). 1st Customs Training was done in Luanda during January 08, 2nd & 03rd Customs Training in the towns of Namibe and Benguela respectively have been conducted during January /February 09. During Octover 2009 another R&R Centre has been established and inaugurated in Luanda.- Together with National Customs Identification Center for CFCs has been installed at Santa-Clara borderpost (border with Namibia) during November /December 09. During November 09 final training course in good refrigertion pracitses has been conducted in Ondjiva (Southern Angola) - Draft for ODS related legislation and regulation has been handed over to Council of Ministers of Angolan Government during November 2009. According to Angolan NOU approval can be expected for April /May 2010. All funds approved have been spent and project activities were terminated during December 2009, with PCR to be handed over during May/June 2010.
COM | Germany | Implementation of the RMP update | RMP Update | AFR | BOT | REF | 45 | TAS | 09 | A | I | CFC | 5.8 | 5.8 | 0 |  | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-08-01 |  | 64295 | 0 | 64295 | 64295 | 100% | 0 | 0 | 0 | 8358 | 0 | 8358 | 0 | 0 | Customs training was the only activity remaining under the project and with the approval of the ODS regulations these could be completed. 36 customs officiers were trained at the various border posts. The PCR will be submitted in 2010
COM | Germany | Implementation of the RMP update | RMP Update | AFR | SWA | REF | 41 | TAS | 08 | A | I |  | 20.9 | 20.9 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2009-10-01 |  | 74295 | 0 | 74295 | 74295 | 100% | 0 | 0 | 0 | 9658 | 0 | 9658 | 0 | 0 | A new NOU was appointed in 2009. The final customs training as last outstanding project activity was completed. PCR sent in September 2010.
COM | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | RMP Update | AFR | ZAM | REF | 42 | TAS | 13 | A | I |  | 23.3 | 23.3 | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 |  | 2009-10-01 |  | 136000 | -7474 | 128526 | 128526 | 100% | 0 | 0 | 0 | 17680 | -971.62 | 16708 | 0.38 | 0 | funds returned to MLF at 65th meeting (UNEP/ozL.Pro/ExCom/65/60 Annex IV
COM | UNDP | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | RMP-Component | LAC | BAR | REF | 43 | TAS | 11 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2004-07-01 | 2010-11-01 | 2006-12-01 |  | 2011-12-01 |  | 172611 | 0 | 172611 | 169685.68 | 98.31% | 2925.32 | 0 | 2340.256 | 15535 | 0 | 15271.721 | 263.279 | 0 | Completed in 2011. Tools and equipment delivered to Barbados. International consultant provided training to local consultants in October 2011. Final invoices pending. | Tools and equipment delivered to beneficiaries. Final invoices pending. | 2004 |  | Investment
COM | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | CBI | REF | 44 | TAS | 08 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2007-06-01 |  | 2010-12-01 |  | 75400 | -1335.75 | 74064.25 | 74064.25 | 100% | 0 | 0 | 0 | 6786 | -120.22 | 6665.78 | 0 | 0 | Completed. Equipment arrived in country, Training seminars provided. Subcontracts with service centers established for 3 islands and payments made in 2010. |  | 2004 |  | Investment
COM | UNDP | Implementation of the RMP: technical assistance project for MAC and refrigeration service and end-user sub-sectors | RMP-Component | AFR | GBS | REF | 43 | TAS | 07 | N | I | CFC | 14.3 | 14.3 | 0 | 0 | 2004-07-01 | 2009-05-01 | 2006-07-01 |  | 2011-12-01 |  | 282900 | 0 | 282900 | 281735.02 | 99.59% | 1164.98 | 0 | 931.984 | 21218 | 0 | 21130.6244 | 87.3756 | 0 | Completed in 2011. As mentioned in 2011, subcontracts with Centres ran into procedural problems, and bidding had to be re-initiated. Bidding was successful in Q3-2011 and purchase orders placed in 2011. | Final invoices pending. | 2004 |  | Investment
COM | UNDP | Implementation of the refrigerant management plan: recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | HAI | REF | 39 | TAS | 04 | A | I | CFC | 88.6 | 88.6 | 0 | 0 | 2003-04-01 | 2007-04-01 | 2006-04-01 |  | 2011-10-01 |  | 220256 | 0 | 220256 | 217016.94 | 98.53% | 3239.06 | 0 | 2591.248 | 19823 | 0 | 19531.4852 | 291.5148 | 0 | Completed in 2011. 3 missions by international expert took place in 2011. 2 train the trainers workshops were organized and 300 kits of good practices were procured and delivered to Haiti. Final invoices pending. | Completed in 2011. Tools and equipment will be delivered to technicians once they have finalized training of local technicians organized by UNEP. | 2003 |  | Investment
COM | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | MAU | REF | 41 | TAS | 11 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 |  | 100995 | -695.89 | 100299.11 | 100299.11 | 100% | 0 | 0 | 0 | 9089.55 | -62.18 | 9027.37 | 0 | 0 | Completed in 2007. |  | 2003 |  | Investment
COM | UNDP | Implementation of the RMP update: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 45 | TAS | 16 | N | I | CFC | 12.3 | 12.3 | 0 | 0 | 2005-04-01 | 2007-09-01 | 2007-04-01 |  | 2007-12-01 |  | 50000 | -1390.13 | 48609.87 | 48609.87 | 100% | 0 | 0 | 0 | 4500 | -125.11 | 4374.89 | 0 | 0 | Completed in 2007. |  | 2005 |  | Non-Investment
COM | UNDP | Implementation of the RMP: MAC recovery/recycling of CFC-12 | RMP-Component | AFR | SIL | REF | 41 | TAS | 07 | N | I | CFC | 9.4 | 9.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2006-12-01 |  | 2010-12-01 |  | 61858 | -18404.6 | 43453.4 | 43453.4 | 100% | 0 | 0 | 0 | 5567.22 | -1656.63 | 3910.59 | 0 | 0 | See SIL-06. |  | 2003 |  | Investment
COM | UNDP | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector, and recovery and recycling project | RMP-Component | AFR | SIL | REF | 41 | TAS | 05 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2009-12-01 |  | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 8316 | 0 | 8316 | 0 | 0 | Completed in 2009. |  | 2003 |  | Investment
COM | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | SIL | REF | 41 | TAS | 06 | N | I | CFC | 16.4 | 16.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2008-12-01 |  | 2010-12-01 |  | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 9662 | 0 | 9662 | 0 | 0 | Completed. The end-user incentive programme and MAC R&R component were operationally completed. Through local sub-contractors and under supervision of Government Technical Institute, twenty (20) units of commercial equipment were retrofitted. In March 2010, two resource persons (refrigeration engineers from Ghana) were sub-contracted to deliver trainings in retrofits (3-day training in capital, 30 attendees). This was followed up by a series of additional regional workshops (8 trainings) in retrofit techniques (30 participants each). All technical institutes and centers of excellence were equipped with R&R tools. |  | 2003 |  | Non-Investment
COM | UNDP | Implementation of the RMP: monitoring the activities within the RMP | RMP-Component | LAC | SUR | REF | 44 | TAS | 10 | N | I | CFC | 2 | 2 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-06-01 |  | 2011-07-01 |  | 25750 | 0 | 25750 | 25013.53 | 97.14% | 736.47 | 0 | 589.176 | 2318 | 0 | 2251.7034 | 66.2966 | 0 | Completed in 2011. Monitoring activities are on-going to support the implementation of the RMP update in Suriname. | Completed in 2011. Monitoring activities are on-going to support the implementation of the RMP update in Suriname. | 2004 |  | Non-Investment
COM | UNDP | Implementation of the RMP: technical assistance for the MAC and refrigeration service sectors | RMP-Component | LAC | SUR | REF | 44 | TAS | 09 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2007-06-01 |  | 2011-12-01 |  | 300430 | 0 | 300430 | 299857.4 | 99.81% | 572.6 | 0 | 458.08 | 22532 | 0 | 22489.0555 | 42.9445 | 0 | Completed in 2011. Reconversion kits procured and delivered. Mission by international expert took place in 2011. Phase out of CFCs in MAC and REF sectors being monitored and appears to be sustainable. | Remaining invoices have been paid. | 2004 |  | Investment
COM | UNEP | Refrigeration servicing sector CFC phase-out plan (revised 2005 annual implementation programme) | Multi-year | ASP | CPR | REF | 45 | TAS | 426 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-12-01 |  | 2010-12-01 |  | 450000 | 0 | 450000 | 436616 | 97.03% | 13384 | 0 | 13384 | 58500 | 0 | 56760.08 | 1739.92 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Implementation of the RMP: training programme on good refrigerant management practices and hydrocarbon (HC) refrigerants safe handling | Individual | ASP | KUW | REF | 37 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-09-01 | 2004-08-01 |  | 2011-12-01 |  | 95325 | 0 | 95325 | 86363 | 90.6% | 8962 | 0 | 8962 | 12392 | 0 | 11226.9635 | 1165.0365 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Implementation of the RMP update: programme for prevention of illegal CFC trade | Individual | LAC | NIC | REF | 45 | TAS | 15 | A | I | CFC | 6.2 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2008-04-01 |  | 2011-12-01 |  | 15000 | 0 | 15000 | 9000 | 60% | 6000 | 0 | 6000 | 1950 | 0 | 1170 | 780 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | RWA | REF | 41 | TRA | 07 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 |  | 50000 | 0 | 50000 | 46333 | 92.67% | 3667 | 3667 | 3667 | 6500 | 0 | 6023.29 | 476.71 | 476.71 | Project completed |  |  |  | Non Investment
COM | UNEP | Implementation of the RMP: training programme for custom officials | Individual | ASP | SYR | REF | 29 | TRA | 47 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2009-12-01 |  | 72600 | 0 | 72600 | 11263 | 15.51% | 61337 | 0 | 61337 | 9438 | 0 | 1464.19 | 7973.81 | 0 | Project completed |  |  | 2002-12-01 | Non Investment
COM | UNEP | Implementation of the RMP: training for trainers and refrigeration technician on good service practices | Individual | ASP | SYR | REF | 29 | TRA | 49 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2002-12-01 |  | 2009-12-01 |  | 201300 | -51806 | 149494 | 145200 | 97.13% | 4294 | 0 | 4294 | 26169 | -6734.78 | 18876 | 558.22 | 0 | Project completed |  |  |  | Non Investment
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | FSM | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | FSM | REF | 36 | TAS | 02 | A | I |  | 0.7 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | KIR | REF | 36 | TAS | 02 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | KIR | REF | 36 | TAS | 03 | A | I |  | 0.4 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | MAS | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | MAS | REF | 36 | TAS | 02 | A | I |  | 0.8 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | SOI | REF | 36 | TAS | 02 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | SOI | REF | 36 | TAS | 04 | A | I |  | 1.4 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TON | REF | 36 | TAS | 01 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TON | REF | 36 | TAS | 03 | A | I |  | 0.9 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TTR | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TTR | REF | 36 | TAS | 02 | A | I |  | 1.1 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TUV | REF | 36 | TAS | 02 | A | I |  | 0.1 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TUV | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Canada | Implementation of the RMP: national recovery and recycling | RMP | LAC | ANT | REF | 26 | TAS | 06 | A | I | CFC | 1 |  | 0 |  | 1998-11-01 | 2000-06-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of customs | RMP | LAC | ANT | REF | 26 | TRA | 04 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2002-10-01 | 2002-12-01 | 42940 | 0 | 42940 | 42940 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Complete. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training the trainers in good refrigerant management practices | RMP | LAC | ANT | REF | 26 | TRA | 05 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 47460 | 0 | 47460 | 47460 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: development of code of good practice for technicians | RMP Update | AFR | BEN | REF | 32 | TAS | 10 | A | I |  | 0.9 | 0.9 | 0 |  | 2000-12-01 | 2003-01-01 | 2002-12-01 |  | 2004-06-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 1300 | 0 | 1300 | 0 |  | Final copies of Code of Good Practice received by Canada. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of environmental inspectors and investigators | RMP Update | AFR | BEN | REF | 32 | TRA | 11 | A | I |  | 5 | 5 | 0 |  | 2000-12-01 | 2005-01-01 | 2003-12-01 |  | 2007-02-01 | 2007-02-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Train-the-Trainer workshop for 25 environmental inspectors completed in March 2005 and second and final workshop held in June 2006. Small remaining balance was left and Canada agreed that it be used for an ODS survey. Benin submitted survey and final expenditure report. PCR was submitted Dec. 2007. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of custom officials | RMP Update | AFR | BEN | REF | 32 | TRA | 08 | A | I |  | 5.2 | 5.2 | 0 |  | 2000-12-01 | 2003-01-01 | 2003-06-01 |  | 2006-08-01 | 2006-08-01 | 59900 | 0 | 59900 | 59900 | 100% | 0 |  | 0 | 7787 | 0 | 7787 | 0 |  | Project delayed until ODS import/export legislation was passed in April 2002. Train-the-Trainer Worshop held August 2003 and second phase followed in 2004. Canada asked that more customs officers be trained, as results are lower than under other comparabl |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practices | RMP Update | AFR | BEN | REF | 32 | TRA | 09 | A | I |  | 12.6 | 12.6 | 0 |  | 2000-12-01 | 2001-10-01 | 2002-12-01 |  | 2003-12-01 | 2004-12-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 |  | 0 | 18720 | 0 | 18720 | 0 |  | Train-the-Trainer workshop held in Jan. 2002. Phase II training and monitoring completed in 2003. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers and technicians in good refrigeration management practices | RMP | AFR | BKF | REF | 29 | TRA | 10 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-03-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 5200 | 0 | 5200 | 0 |  | Training of technicians is completed as of March 2002. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of customs officers programme | RMP | AFR | BKF | REF | 29 | TRA | 09 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2002-08-01 | 2003-01-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  | 0 | 5525 | 0 | 5525 | 0 |  | Project Complete. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: assistance in preparation of regulations and technical norms | RMP | LAC | BOL | REF | 36 | TAS | 17 | A | I |  | 1.3 | 1.3 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2003-11-01 | 2003-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  | 0 | 1690 | 0 | 1690 | 0 |  | Funds disbursed for legal consultant and workshops to develop legislation. Legislation approved in March 2004. Project completed. PCR submitted. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for customs officers and technical staff in municipalities | RMP | LAC | BOL | REF | 36 | TRA | 19 | A | I |  | 5 | 5 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2005-04-01 | 2005-04-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 |  | 0 | 6240 | 0 | 6240 | 0 |  | Train-the-trainers workshop completed in 2004. Phase II customs officers training completed in March 2005 with 83 officers trained. A total of $13,972 remained in funding after project completion and were used on other RMP components (principally the moni |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: public awareness programme on issues related to the ozone layer | RMP | LAC | BOL | REF | 36 | TAS | 20 | A | I |  | 5.4 | 5.4 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2008-03-01 | 2008-03-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 |  | 0 | 6760 | 0 | 6760 | 0 |  | Last remaining activity, production of school texts on ozone depletion, was delayed due to administration difficulties - now completed. Final report was received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for refrigeration technicians | RMP | LAC | BOL | REF | 36 | TRA | 21 | A | I |  | 5.7 | 5.7 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2005-06-01 | 2005-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Train-the Trainers workshop held in Sept. 2004. Training equipment purchased and distributed. Phase II training completed in May 2005 with 265 technicians trained. Remaining funds from 2005 were used in 2006 on other RMP components (mainly the monitoring) |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: monitoring the activities in the RMP project | RMP | LAC | BOL | REF | 36 | TAS | 22 | A | I |  | 5.9 | 5.9 | 0 |  | 2002-03-01 | 2002-09-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Monitoring database and information system installed and working, as well as ODS monitoring and reporting activities. Funds used principally for local project consultant to implement, monitor and report on project activities. All activities have been completed and final report received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: recovery and recycling | RMP | LAC | BOL | REF | 39 | TAS | 23 | A | I | CFC | 30.3 | 30.3 | 0 |  | 2003-04-01 | 2005-01-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 292000 | 0 | 292000 | 292000 | 100% | 0 |  | 0 | 37960 | 0 | 37960 | 0 |  | 1st Phase of R&R equipment was shipped to Bolivia in April 2005 and 2nd Phase in Dec. 2005. The majority of the equipment has been distributed to technicians and training has been completed. A few batches of R&R machines have not been distributed due to administrative problems, but Bolivia expects to distribute them prior to end of April 2009. |  | 2003 |  | Investment
FIN | Canada | Implementation of the RMP: policy dialogue programme and regulatory framework for phasing out ODSs | RMP | LAC | BZE | REF | 29 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2000-09-01 |  | 2001-11-01 | 2002-12-01 | 15500 | 0 | 15500 | 15500 | 100% | 0 |  | 0 | 2015 | 0 | 2015 | 0 |  | Planning and Policy Dialogue component completed Nov. 2001. Regulatory framework developed and adopted by Government. PCR submitted |  | 1999 | 2001-12-01 | Non-Inv.
FIN | Canada | Implementation of the RMP: monitoring and control of ODS and ODS based equipment and training programme for customs and other inspection officers | RMP | LAC | BZE | REF | 29 | TAS | 03 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 3640 | 0 | 3640 | 0 |  | Train-the-trainer customs workshop held in March 2002. Phase II training completed in 2003. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of trainers and refrigeration technicians in good servicing practices | RMP | LAC | BZE | REF | 29 | TRA | 02 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Train the trainers workshop held in April 2001. Subsequent training took place in 2002 and finalized in 2003. |  | 1999 |  | Non-Inv.
FIN | Canada | Refrigerant management plan formulation project | Individual | LAC | CHI | REF | 27 | TAS | 138 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-10-01 | 2001-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. RMP was submitted to the 35th EXCOM and has been approved. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for technicians and establishment of refrigeration standards | RMP | LAC | CHI | REF | 35 | TRA | 150 | A | I |  | 43 | 43 | 0 |  | 2001-12-01 | 2002-09-01 | 2004-12-01 |  | 2006-12-01 | 2007-05-01 | 260000 | 0 | 260000 | 260000 | 100% | 0 |  | 0 | 33800 | 0 | 33800 | 0 |  | Refrigeration equipment purchased and distributed to training centres. 1650 technicians trained. Code/standard of good practices completed in July 2005. Retrofit demonstration strategy developed and demonstrations completed in 2006. |  | 2001 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling programme | RMP | LAC | CHI | REF | 35 | TAS | 147 | A | I | CFC | 88 | 88 | 0 |  | 2001-12-01 | 2006-08-01 | 2005-04-01 |  | 2009-03-01 | 2010-07-01 | 531620 | -30 | 531590 | 531590 | 100% | 0 |  | 0 | 53162 | 0 | 53162 | 0 |  | All the R&R equipment has been procured and distributed, is in use. All related training activities have been completed. Monitoring of use of equipment was completed in early 2009. Project completed in Feb. 2009 and last payment to Chile was made in April 2009. $30 were remaining and returned to MLF at 61st Meeting, thus financially closing the project. |  | 2001 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation and enforcement of regulations on ODSs | RMP | LAC | CUB | REF | 29 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  | 0 | 2600 | 0 | 2600 | 0 |  | Policy workshop held May 2002. ODS regulations updated. Project errouneously reported as completed in 2003. Completion officially reported by Cuba in 2004 |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling of CFC-12 in the MAC sector (amendment to the RMP) | RMP | LAC | CUB | REF | 30 | TAS | 15 | A | I | CFC | 8 |  | 0 |  | 2000-03-01 | 2001-11-01 | 2002-04-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project erroneously reported as completed in 2003. Additional (final) training took place in 2004. Insufficient data to determine ODP phase-out. However, RMP as a whole is deemed to have contributed to a reduction in the servicing sector of about 90 ODP |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for customs officers | RMP | LAC | CUB | REF | 29 | TRA | 13 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | 667 customs officers trained. ODS Import database system established. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practice | RMP | LAC | CUB | REF | 29 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 | 10400 | 0 |  | 2650 technicians trained. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: national recovery and recycling programme | RMP | LAC | GUY | REF | 23 | TAS | 08 | A | I | CFC | 6.5 |  | 0 |  | 1997-11-01 | 1998-04-01 | 2000-12-01 |  | 2003-05-01 | 2003-05-01 | 73450 | 0 | 73450 | 73450 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completion Report submitted. |  | 1997 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of trainers in refrigeration and certification of technicians | RMP | LAC | JAM | REF | 27 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-10-01 |  | 2000-08-01 | 2001-03-01 | 50850 | 0 | 50850 | 50850 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Phase 1 (train-the trainer) completed 7-11 June 1999. Phase 2 completed in June 2000. Monitoring and evaluation completed August 2000. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: customs officers training programme | RMP | LAC | JAM | REF | 27 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-10-01 |  | 2001-11-01 | 2001-12-01 | 54240 | 0 | 54240 | 54240 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Legislation finalized in July 99. Phase 1 -train-the-trainer- completed June 2000, Phase 2 completed in Nov. 2000, Monitoring and evaluation completed in Nov. 2001. |  | 1999 | 2001-12-01 | Non-Inv.
FIN | Canada | Implementation of the RMP including training programmes for refrigeration technicians and customs officers, assistance in the design of policies and regulations and recovery and recycling | RMP | LAC | STK | REF | 24 | TAS | 04 | A | I | CFC | 2 | 2 | 0 |  | 1998-03-01 | 1999-05-01 | 2001-03-01 |  | 2006-03-01 | 2006-03-01 | 124300 | 0 | 124300 | 124300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | R&R workshop and customs training were delayed because legislation not yet place. However legislation was adopted in early 2004 and R&R project was completed. Phase I Customs Training also implemented. Final reports by country received in February 2006, |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP update | RMP Update | LAC | STL | REF | 41 | TAS | 08 | A | I |  | 7.1 | 7.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2007-05-01 | 2008-12-01 | 73450 | -122 | 73328 | 73328 | 100% | 0 |  | 0 | 9549 | -16 | 9533 | 0 |  | Project completed. 71 refrigeration technicians trained. Public service announcements were developed and broadcasted. Retrofit demonstration workshops concluded, including demonstrations of AC and vehicle retrofits. R&R equipment distributed. Though financial completion was previously reported to be May 2007, it was subsequently found that $122 were remaining. This amount, plus $16 in support costs, is to be returned to the Fund at the 58th ExCom Meeting. |  | 2003 |  | Non-Inv.
FIN | Canada | Implementation of the RMP | RMP | LAC | STL | REF | 23 | TAS | 04 | A | I | CFC | 3 | 3 | 0 |  | 1997-11-01 | 1998-03-01 | 2000-12-01 |  | 2003-12-01 | 2003-12-01 | 146900 | 0 | 146900 | 146900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | All activities completed. Project Completion Report is currently being drafted. |  | 1997 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Finland | Implementation of the RMP: assistance in the design of policies and regulations | Individual | LAC | NIC | REF | 25 | TAS | 6 | A | I | CFC | 12.8 |  | 0 |  | 1998-07-01 | 2001-09-01 | 2000-07-01 |  | 2005-12-01 | 2009-07-01 | 225430 | -76855 | 148575 | 148575 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1998
FIN | Finland | Implementation of the RMP: monitoring and evaluation of the RMP | Individual | LAC | PAN | REF | 29 | TAS | 11 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2008-12-01 |  | 33000 | -18690 | 14310 | 14310 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. |  | 2001
FIN | Finland | Implementation of the RMP: training programme for custom officers | Individual | LAC | PAN | REF | 29 | TRA | 12 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2003-05-01 | 2001-06-01 |  | 2007-12-01 |  | 70000 | -34022 | 35978 | 35978 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Balances to be returned after all pending payments have been recorded |  | 2001 | 2002-12-01
FIN | France | Implementation of the RMP update | RMP Update | AFR | ETH | REF | 44 | TAS | 14 | A | I | CFC | 12.3 |  | 0 |  | 2004-12-01 | 2005-11-01 | 2007-12-01 |  | 2010-12-01 | 2012-04-01 | 91300 | -40988.89 | 50311.11 | 50311 | 100% | 0.11 |  | 0 | 11869 | -5329 | 6540 | 0 |  | The French contribution was implemented by GIZ-Proklima. The ODS regulations were not approved despite all possible effort. However customs trainings was conducted on the use of identifiers. This project was stopped because of lack of progress.
FIN | France | Implementation of the RMP: recovery and recycling, training and demonstration project (complement) | RMP | ASP | LAO | REF | 34 | TAS | 06 | N | I | CFC | 1.2 |  | 0 |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-31 | 40800 | 0 | 40800 | 40800 | 100% | 0 |  | 0 | 2040 | 0 | 2040 | 0 |  | Lao has reported an error concerning this activity in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). With the 2 budgets combined, 3 sets of R&R equipment have been bought and handed over to three institutions, 21 sets of basic servicing equipment were bought, and the training of trainers included sessions on best practices, MAC and R&R. Furthermore, a recovery and recycling machine was built locally as part of a university training course. The project is completed.
FIN | France | Implementation of the RMP: customs training programme | RMP | ASP | LAO | REF | 34 | TRA | 04 | N | I | CFC | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2003-08-01 |  | 2010-06-01 | 2012-12-31 | 81542 | -11242 | 70300 | 70300 | 100% | 0 |  | 0 | 10600 | -1461 | 9139 | 0 |  | Project completed. | Balance return in March 2013
FIN | France | Implementation of the RMP: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II) | RMP | ASP | LAO | REF | 34 | TRA | 03 | N | I |  | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-31 | 78750 | 0 | 78750 | 78750 | 100% | 0 |  | 0 | 10237 | 0 | 10237 | 0 |  | Lao had reported an error concerning the training of technicians in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). The amount of expenses made for these 2 lines were inserted under LAO/REF/34/TRA/03. The final training was carried out in April 2009. The project is completed.
FIN | France | Implementation of the RMP: training of personnel in charge of control and monitoring of imports of ODS |  | AFR | MAG | REF | 29 | TRA | 02 | A | I | CFC | 4.4 | 3.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2003-06-01 | 2005-01-01 | 26000 | -851 | 25149 | 25149 | 100% | 0 |  | 0 | 1300 | -43 | 1257 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: recovery and recycling component | RMP | AFR | MAG | REF | 47 | TAS | 12 | A | I | CFC | 6.8 | 6 | 0 |  | 2005-11-01 | 2008-03-01 | 2007-06-01 |  | 2010-12-01 | 2005-03-01 | 40500 | 0 | 40500 | 40500 | 100% | 0 |  |  | 5265 | 0 | 5265 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: training of trainers and refrigeration technicians in good service practices |  | AFR | MAG | REF | 29 | TRA | 03 | A | I | CFC | 7.8 | 5.7 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2004-08-01 | 2005-01-01 | 46200 | -1519 | 44681 | 44681 | 100% | 0 |  | 0 | 2310 | -76 | 2234 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: set up a national recovery and recycling network |  | AFR | MAG | REF | 29 | TAS | 05 | A | I | CFC | 13.9 | 10.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2004-08-01 | 2005-01-01 | 82700 | -11895 | 70805 | 70805 | 100% | 0 |  | 0 | 4135 | -595 | 3540 | 0 |  | Project completed.
FIN | France | Refrigerant management plan update | RMP Update | AFR | MOZ | REF | 44 | TAS | 12 | A | I | CFC | 15.5 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 104512 | -33312 | 71200 | 71200 | 100% | 0 |  | 0 | 13587 | -4330.7002 | 9256.2998 | 0 |  | The French contribution was implmented by GTZ-Proklima. The project is completed.
FIN | France | Implementation of the RMP update | RMP Update | AFR | UGA | REF | 44 | TAS | 11 | A | I | CFC | 10.9 |  | 0 |  | 2004-12-01 | 2005-07-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 75000 | -12511 | 62489 | 62489 | 100% | 0 |  | 0 | 9750 | -1626.43 | 8123.57 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Refrigerant management plan update | RMP Update | AFR | URT | REF | 46 | TAS | 18 | A | I | CFC | 68.3 |  | 0 |  | 2005-07-01 | 2005-09-01 | 2008-07-01 |  | 2009-12-01 | 2012-12-01 | 157252 | -43428 | 113824 | 113824 | 100% | 0 |  | 0 | 20443 | -5645.7063 | 14797.2937 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | BOT | REF | 26 | TAS | 06 | A | I | CFC | 1.5 | 1.7 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2005-06-01 | 2006-06-01 | 70375 | 0 | 70375 | 70375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted in 2006
FIN | Germany | Implementation of the RMP: modification of legal provisions and information system | RMP | AFR | EGY | REF | 29 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | UNIDO was subcontracted. Project completed. Draft PCR submitted in September 2005.
FIN | Germany | Implementation of the RMP: implementation of measures to address the informal sector | RMP | AFR | EGY | REF | 29 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 252500 | 0 | 252500 | 252500 | 100% | 0 | 0 | 0 | 32825 | 0 | 32825 | 0 | 0 | Unido was subcontracted, training courses have been carried out successfully. Project completed. Draft PCR submitted in September 2005.
FIN | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Individual | AFR | EGY | REF | 29 | TAS | 75 | A | I | CFC | 100 | 100 | 0 |  | 1999-11-01 | 2000-04-01 | 2002-12-01 |  | 2007-12-01 | 2008-10-01 | 599500 | 0 | 599500 | 599500 | 100% | 0 | 0 | 0 | 77935 | 0 | 77935 | 0 | 0 | Project is completed. A final monitoring and evaluation workshop was organized with NOU in August 2007 to establish a network for monitoring in the whole country. PCR was approved by NOU and was sent to MLF in October 2008.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ETH | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-10-01 | 2005-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. RMP update approved in dec 2004
FIN | Germany | Implementation of the RMP update: phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | GAM | REF | 37 | TAS | 12 | A | I |  | 11.2 | 11.2 | 0 |  | 2002-07-01 | 2003-03-01 | 2005-01-01 |  | 2007-09-01 | 2009-01-01 | 76700 | -30 | 76670 | 76670 | 100% | 0 | 0 | 0 | 9971 | -4 | 9967 | 0 | 0 | Project completed and PCR submitted.
FIN | Germany | Implementation of RMPs for 14 low volume consuming countries in eastern and southern Africa | RMP | GLO | GLO | REF | 26 | TAS | 172 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-11-01 | 2005-09-01 | 815000 | 0 | 815000 | 815000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All countries completed the activities under this project. PCR is to be submitted
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | KEN | REF | 26 | TAS | 19 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. TPMP approved in Dec 2004
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | LES | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-11-01 | 2004-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted TPMP submitted and approved at 41st Excom
FIN | Germany | Implementation of the RMP: monitoring the activities in the RMP | RMP Update | AFR | LIR | REF | 41 | TAS | 08 | A | I | CFC | 1.7 | 0 | 0 |  | 2003-12-01 | 2003-12-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 | 0 | 2009 | 0 | 2009 | 0 | 0 | PCR submitted in July 2010
FIN | Germany | Implementation of the RMP: MAC recovery/recycling of CFC-12 | Individual | AFR | LIR | REF | 41 | TAS | 06 | A | I | CFC | 6.8 | 3 | 0 |  | 2003-12-01 | 2005-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 61858 | 0 | 61858 | 61858 | 100% | 0 | 0 | 0 | 8042 | 0 | 8042 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector and recovery and recycling | RMP Update | AFR | LIR | REF | 41 | TAS | 04 | A | I | CFC | 10.1 | 10.1 | 0 |  | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2009-11-01 | 2011-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 12012 | 0 | 12012 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP Update | AFR | LIR | REF | 41 | TAS | 05 | A | I | CFC | 11.7 | 1.5 | 0 |  | 2003-12-01 | 2005-04-01 | 2008-12-01 |  | 2009-12-01 | 2011-12-01 | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 13996 | 0 | 13996 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: training of trainers in code of good refrigeration practices and establishment of national refrigeration demonstration centre | Individual | AFR | LIR | REF | 41 | TRA | 03 | A | I |  | 13 | 13 | 0 |  | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | 0 | 119460 | 119460 | 100% | 0 | 0 | 0 | 15530 | 0 | 15530 | 0 | 0 | Project completed. PCR submitted in July 2010
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MAR | REF | 26 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted TPMP approved at 41st Excom
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MLW | REF | 26 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | Germany | Implementation of the RMP update: refrigeration and air-conditioning sector | Individual | AFR | MLW | REF | 43 | TAS | 20 | A | I |  | 49 | 0 | 0 |  | 2004-07-01 | 2004-10-01 | 2007-07-01 |  | 2007-12-01 | 2009-01-01 | 100000 | -561 | 99439 | 99439 | 100% | 0 | 0 | 0 | 13000 | -73 | 12927 | 0 | 0 | Project completed. PCR was submitted in September 2008. Remaining funds will be returned to the secretariat.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MOZ | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | NAM | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. TPMP approved in Dec 2003
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SEY | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. RMP Update ongoing
FIN | Germany | Phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | SEY | REF | 40 | TAS | 08 | A | I |  | 2.4 | 2.4 | 0 |  | 2003-07-01 | 2003-10-01 | 2006-12-01 |  | 2006-12-01 | 2007-10-01 | 41607 | 0 | 41607 | 41607 | 100% | 0 | 0 | 0 | 5409 | 0 | 5409 | 0 | 0 | PCR has been submitted in October 2007.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SWA | REF | 26 | TAS | 05 | A | I | CFC | 4 | 1.5 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 90375 | 0 | 90375 | 90375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted. RMP update ongoing
FIN | Germany | Implementation of the RMP: national recovery and recycling network | Individual | ASP | SYR | REF | 30 | TAS | 59 | A | I | CFC | 120 | 120 | 0 |  | 2000-03-01 | 2000-11-01 | 2002-04-01 |  | 2008-05-01 | 2009-12-01 | 742146 | 0 | 742146 | 742146 | 100% | 0 | 0 | 0 | 96479 | 0 | 96479 | 0 | 0 | All activities which were planned for 2007 (report, guide book version) were finalized and remaining project funds were allocated for additional refrigeration equipment. The project activities are completed and PCR was submitted to MLF in 2009.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | UGA | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved in Dec 2004
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | URT | REF | 26 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZAM | REF | 26 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZIM | REF | 26 | TAS | 15 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
FIN | Sweden | Implementation of the RMP: development of import/export licensing system | Individual | ASP | LAO | REF | 34 | TAS | 05 | A | I |  | 1.6 |  | 0 |  | 2001-07-01 | 2002-11-01 | 2002-09-01 |  | 2005-12-01 | 2005-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Swedish contribution in Lao PDR consists of technical assistance to prepare an import/export licensing system. International and national consultants were contracted in April 2002. After an initial delay in the signing of agreement and data collection the project is completed, we are only awaiting Lao PDR’s approval of the final report. The Decree for the "Control of the Import-Export and Consumption of ODS" was signed late 2003. A regulation for how the new Decree shall be implemented has been developed and the regulation was signed by the Minister in November 2004. SEI and the IC gave a number of suggestions on drafts on the regulation during 2004. An information brochure to all importers informing them about the licensing system was finalized during 2005. |  | 2001
FIN | Switzerland | Implementation of the RMP: demonstration project to retrofit domestic refrigerators for the use of hydrocarbon refrigerant | RMP | AFR | SEN | REF | 33 | TAS | 14 | A | I |  | 47 | 0 | 0 | 0 | 2001-03-01 | 2003-07-01 | 2001-11-01 |  | 2004-03-01 | 2004-06-01 | 71230 | 0 | 71230 | 71230 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2001
FIN | UNDP | Implementation of the RMP: Monitoring the activities included in the RMP | RMP-Component | AFR | BDI | REF | 26 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2001-07-01 | 2000-12-01 |  | 2003-11-01 | 2003-11-01 | 10450 | -415 | 10035 | 10035 | 100% | 0 | 0 | 0 | 1358.5 | -53.5 | 1305 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | BDI | REF | 41 | TAS | 16 | N | I | CFC | 2.9 | 2.9 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 20000 | -464 | 19536 | 19536 | 100% | 0 | 0 | 0 | 1800 | -42 | 1758 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 41 | TAS | 13 | N | I | CFC | 4.7 | 4.7 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 32500 | -153 | 32347 | 32347 | 100% | 0 | 0 | 0 | 2925 | -14 | 2911 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 26 | TAS | 05 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 1998-11-01 | 2001-05-01 | 2000-12-01 |  | 2003-11-01 | 2004-01-01 | 119577 | -3603 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15545.01 | -468.01 | 15077 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | ASP | BGD | REF | 29 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2005-12-01 | 2007-01-01 | 15455 | -69 | 15386 | 15386 | 100% | 0 | 0 | 0 | 2009.15 | -9.1493 | 2000.0007 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national recovery and recycling project | RMP-Component | ASP | BGD | REF | 29 | TAS | 10 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2005-07-01 | 2007-03-01 | 298270 | 0 | 298270 | 298270 | 100% | 0 | 0 | 0 | 38775 | 0 | 38775 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BHA | REF | 23 | TAS | 05 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-05-01 | 151400 | -12625 | 138775 | 138775 | 100% | 0 | 0 | 0 | 19682 | -1641 | 18041 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance in the refrigeration servicing sector | RMP-Component | ASP | BHU | REF | 45 | TAS | 06 | N | I | CFC | 0.1 | 0.1 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2006-12-01 | 2009-11-01 | 45000 | -41 | 44959 | 44958.61 | 100% | 0.39 | 0 | 0 | 4050 | -3.69 | 4046.2749 | 0.0351 | 0 | Completed in 2006.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | AFR | BKF | REF | 34 | TAS | 13 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2001-07-01 |  | 2007-08-01 |  | 2006-12-01 | 2008-09-01 | 16350 | -16350 | 0 | 0 |  | 0 | 0 | 0 | 2125.5 | -2125.5 | 0 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | BKF | REF | 32 | TAS | 11 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2006-01-01 |  | 2006-12-01 | 2008-09-01 | 132250 | -7409 | 124841 | 124841.33 | 100% | -0.33 | 0 | 0 | 17192.5 | -962.498 | 16230.0449 | -0.042902 | 0 | Completed in 2006. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | LAC | BZE | REF | 44 | TAS | 12 | N | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2007-12-01 |  | 2006-12-01 | 2007-06-01 | 44879 | -211 | 44668 | 44668 | 100% | 0 | 0 | 0 | 4039.11 | -19.11 | 4020 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | BZE | REF | 29 | TAS | 05 | A | I | CFC | 1.7 | 1.7 | 0 | 0 | 1999-11-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2003-09-01 | 61125 | 0 | 61125 | 61125 | 100% | 0 | 0 | 0 | 7946 | 0 | 7946 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | CHD | REF | 29 | TAS | 07 | A | I | No_ODP | 1 | 1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-07-01 | 2005-10-01 | 15455 | -4669 | 10786 | 10786 | 100% | 0 | 0 | 0 | 2009.15 | -607.15 | 1402 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | CHD | REF | 29 | TAS | 04 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 198252 | -36260 | 161992 | 161992 | 100% | 0 | 0 | 0 | 25772.76 | -4713.76 | 21059 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Incentive programme for commercial/industrial end-user sector | RMP-Component | AFR | CHD | REF | 38 | TAS | 09 | N | I | CFC | 6 | 6 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2010-12-01 | 2011-09-01 | 184416 | 0 | 184416 | 184416 | 100% | 0 | 0 | 0 | 23974 | 0 | 23974 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: ensuring the effectiveness of all the project proposed with the RMP project | RMP-Component | LAC | COS | REF | 41 | TAS | 31 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 60000 | -2685.69 | 57314.31 | 57314.31 | 100% | 0 | 0 | 0 | 5400 | -241.7121 | 5158.2879 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for training of customs officers | RMP-Component | LAC | COS | REF | 41 | TRA | 30 | N | I | CFC | 30.4 | 30.4 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-07-01 | 90000 | -1004.24 | 88995.76 | 88995.76 | 100% | 0 | 0 | 0 | 8100 | -90.3816 | 8009.6184 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for certification and licensing of refrigeration technicians | RMP-Component | LAC | COS | REF | 41 | TRA | 29 | N | I | CFC | 33.8 | 33.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 100000 | -796.64 | 99203.36 | 99203.36 | 100% | 0 | 0 | 0 | 9000 | -71.6976 | 8928.3024 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 28 | N | I | CFC | 60.8 | 60.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 180000 | -516.67 | 179483.33 | 179483.33 | 100% | 0 | 0 | 0 | 16200 | -46.5003 | 16153.4997 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial, industrial, and fishing fleet refrigeration end-user sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 27 | N | I | CFC | 67.5 | 67.5 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 200000 | -1012.02 | 198987.98 | 198987.98 | 100% | 0 | 0 | 0 | 18000 | -91.0818 | 17908.9182 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | DJI | REF | 37 | TAS | 03 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-04-01 | 25000 | 0 | 25000 | 25000.4 | 100% | -0.4 | 0 | 0 | 3250 | 0 | 3250.052 | -0.052 | 0 | Completed in 2007. Financially completed in 2011. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling | RMP-Component | AFR | DJI | REF | 37 | TAS | 07 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-07-01 | 136463 | -685.13 | 135777.87 | 135777.87 | 100% | 0 | 0 | 0 | 17740.19 | -89.2569 | 17650.9331 | 0 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | DOM | REF | 25 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-01-01 | 2000-08-01 |  | 2003-09-01 | 2003-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | DOM | REF | 25 | TAS | 13 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 441482 | -49014 | 392468 | 392468 | 100% | 0 | 0 | 0 | 57392.66 | -6371.66 | 51021 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | DRC | REF | 41 | TAS | 16 | N | I | CFC | 13.1 | 13.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 437102 | -231.44 | 436870.56 | 436870.56 | 100% | 0 | 0 | 0 | 32783 | -17.36 | 32765.64 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | ELS | REF | 25 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2002-01-01 | 2000-08-01 |  | 2003-06-01 | 2005-10-01 | 10500 | -1035 | 9465 | 9465 | 100% | 0 | 0 | 0 | 1365 | -135 | 1230 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | UNDP | RMP update: monitoring programme | Individual | LAC | ELS | REF | 42 | TAS | 15 | N | I | CFC | 30.5 | 30.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-08-01 | 41000 | -485 | 40515 | 40514.89 | 100% | 0.11 | 0 | 0 | 3690 | -43.65 | 3646.3401 | 0.0099 | 0 | Completed in 2008.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2004 |  | Investment
FIN | UNDP | RMP update: technical assistance for certification and licensing of refrigeration technicians | Individual | LAC | ELS | REF | 42 | TRA | 14 | N | I | CFC | 57.6 | 57.6 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 77300 | -1 | 77299 | 77298.8 | 100% | 0.2 | 0 | 0 | 6957 | 1.4552e-13 | 6956.982 | 0.018 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | RMP update: technical assistance for the refrigeration sector | Individual | LAC | ELS | REF | 42 | TAS | 13 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 231700 | -1 | 231699 | 231699.43 | 100% | -0.43 | 0 | 0 | 20853 | 1.4552e-13 | 20853.0387 | -0.0387 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | ELS | REF | 25 | TAS | 09 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-05-01 | 403925 | -26048 | 377877 | 377877 | 100% | 0 | 0 | 0 | 52510.25 | -3386.25 | 49124 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | ASP | FIJ | REF | 29 | TAS | 04 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2007-02-01 | 96755 | -500 | 96255 | 96255 | 100% | 0 | 0 | 0 | 12578.15 | -65.1492 | 12513.0008 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GAB | REF | 26 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2002-01-01 | 2000-12-01 |  | 2003-07-01 | 2003-08-01 | 12100 | -1600 | 10500 | 10500 | 100% | 0 | 0 | 0 | 1573 | -208 | 1365 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | GAB | REF | 41 | TAS | 14 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2003-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2011-11-01 | 15000 | -772.32 | 14227.68 | 14227.68 | 100% | 0 | 0 | 0 | 1350 | -69.5088 | 1280.4912 | 0 | 0 | Completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 41 | TAS | 11 | N | I | CFC | 3.3 | 3.3 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2007-07-01 | 2011-12-01 | 60277 | 0 | 60277 | 60276.74 | 100% | 0.26 | 0 | 0 | 5425 | 0 | 5424.9766 | 0.0234 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 26 | TAS | 06 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 1998-11-01 | 2001-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 232470 | -36306 | 196164 | 196164 | 100% | 0 | 0 | 0 | 30221.1 | -4720.1 | 25501 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | EUR | GEO | REF | 35 | TAS | 11 | N | I | No_ODP | 2.3 | 2.3 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2007-12-01 |  | 2005-12-01 | 2007-06-01 | 16350 | 0 | 16350 | 16350.01 | 100% | -0.01 | 0 | 0 | 2126 | 0 | 2126.0013 | -0.0013003 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | RMP-Component | EUR | GEO | REF | 35 | TAS | 10 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2005-01-01 |  | 2005-01-01 | 2007-06-01 | 101000 | -553 | 100447 | 100447 | 100% | 0 | 0 | 0 | 13130 | -72.0037 | 13057.9963 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | EUR | GEO | REF | 23 | TAS | 04 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 106750 | -2348 | 104402 | 104402 | 100% | 0 | 0 | 0 | 13877.5 | -304.5 | 13573 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GHA | REF | 32 | TAS | 16 | N | I | CFC | 1.2 | 1.2 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2007-12-01 | 2009-08-01 | 15455 | -11257 | 4198 | 4198 | 100% | 0 | 0 | 0 | 2009.15 | -1463.4507 | 545.6993 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Mobile air conditioning recovery and recycling of CFC-12 | RMP-Component | AFR | GHA | REF | 32 | TAS | 12 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-12-01 | 2006-10-01 | 98902 | -45 | 98857 | 98857 | 100% | 0 | 0 | 0 | 12857.26 | -6.26 | 12851 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | AFR | GHA | REF | 32 | TAS | 14 | N | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2006-01-01 |  | 2006-12-01 | 2009-08-01 | 198000 | -1419 | 196581 | 196580.81 | 100% | 0.19 | 0 | 0 | 25740 | -184.47 | 25555.5053 | 0.0247 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National recovery recycling project | RMP-Component | LAC | GRN | REF | 30 | TAS | 05 | A | I | CFC | 1.4 | 1.4 | 0 | 0 | 2000-03-01 | 2002-06-01 | 2001-10-01 |  | 2002-12-01 | 2003-11-01 | 33400 | 0 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4342 | 0 | 4342 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling programme (phase II) | RMP-Component | AFR | GUI | REF | 45 | TAS | 15 | N | I | CFC | 7.9 | 7.9 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2007-04-01 |  | 2007-10-01 | 2011-12-01 | 49890 | -6010.66 | 43879.34 | 43879.34 | 100% | 0 | 0 | 0 | 4490 | -540.9474 | 3949.0526 | 0 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Implementation of the refrigerant management plan: monitoring the activities in the RMP | RMP-Component | LAC | HAI | REF | 39 | TAS | 06 | N | I | CFC | 11.8 | 11.8 | 0 | 0 | 2003-04-01 | 2008-02-01 | 2006-04-01 |  | 2010-08-01 | 2011-09-01 | 29400 | -2220.48 | 27179.52 | 27179.52 | 100% | 0 | 0 | 0 | 2646 | -199.84 | 2446.16 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance programme for the promotion of good practices and recovery and recycling | RMP-Component | LAC | HON | REF | 44 | TAS | 15 | N | I | CFC | 138.6 | 138.6 | 0 | 0 | 2004-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-11-01 | 2011-11-01 | 150000 | -71.56 | 149928.44 | 149928.44 | 100% | 0 | 0 | 0 | 13500 | -6.4404 | 13493.5596 | 0 | 0 | Completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant and awareness and incentive programme for the MAC sub-sector | RMP-Component | ASP | KAM | REF | 41 | TAS | 05 | N | I | CFC | 56.2 | 56.2 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-06-01 | 625000 | -267.41 | 624732.59 | 624732.59 | 100% | 0 | 0 | 0 | 46875 | -20.0558 | 46854.9442 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | ASP | KYR | REF | 37 | TAS | 01 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-08-01 |  | 2006-12-01 | 2008-03-01 | 16500 | -1 | 16499 | 16499 | 100% | 0 | 0 | 0 | 2145 | 1.0913e-13 | 2145 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | KYR | REF | 37 | TAS | 02 | A | I | CFC | 20.6 | 20.6 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 187242 | -3510.54 | 183731.46 | 183731.46 | 100% | 0 | 0 | 0 | 24341.46 | -456.8302 | 23884.6298 | 0 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for refrigerant recovery and recycling | RMP-Component | ASP | KYR | REF | 37 | TAS | 04 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2003-10-01 | 2007-03-01 | 185175 | -1007 | 184168 | 184168 | 100% | 0 | 0 | 0 | 24072.75 | -130.7514 | 23941.9986 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme for MAC, commercial and industrial end-users | RMP-Component | AFR | MAU | REF | 41 | TAS | 12 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2011-08-01 | 100000 | 0 | 100000 | 99999.87 | 100% | 0.13 | 0 | 0 | 9000 | 0 | 8999.9883 | 0.0117 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | RMP-Component | AFR | MLI | REF | 32 | TAS | 10 | A | I | No_ODP | 3.8 | 3.8 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2005-07-01 | 2007-03-01 | 15455 | -237 | 15218 | 15218 | 100% | 0 | 0 | 0 | 2009.15 | -31.1477 | 1978.0023 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 32 | TAS | 09 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-12-01 | 2004-01-01 | 102658 | -3517.7037 | 99140.2963 | 99140 | 100% | 0.2963 | 0 | 0 | 13345.54 | -456.54 | 12888.9615 | 0.038521 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance programme | RMP-Component | EUR | MOL | REF | 44 | TAS | 12 | N | I | CFC | 55.9 | 55.9 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-07-01 | 173495 | -3 | 173492 | 173492.02 | 100% | -0.02 | 0 | 0 | 15615 | -0.27 | 15614.7318 | -0.0018001 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | EUR | MOL | REF | 25 | TAS | 02 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2002-05-01 | 2002-11-01 | 254150 | -304 | 253846 | 253846 | 100% | 0 | 0 | 0 | 33039.5 | -39.5 | 33000 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | MON | REF | 35 | TAS | 06 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2005-11-01 | 108600 | 0 | 108600 | 108600 | 100% | 0 | 0 | 0 | 14118 | 0 | 14118 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring activities included in the RMP | RMP-Component | ASP | NEP | REF | 28 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2005-01-01 | 2002-02-01 |  | 2005-12-01 | 2007-03-01 | 8894 | -3329 | 5565 | 5565 | 100% | 0 | 0 | 0 | 1156.22 | -433.2176 | 723.0024 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling, retrofit and their monitoring | RMP-Component | ASP | NEP | REF | 44 | TAS | 16 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 | 2011-11-01 | 57495 | -6049.7 | 51445.3 | 51445.3 | 100% | 0 | 0 | 0 | 5175 | -544.52 | 4630.48 | 0 | 0 | Completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | ASP | NEP | REF | 28 | TAS | 08 | A | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2003-10-01 | 2003-11-01 | 88577 | -1 | 88576 | 88576 | 100% | 0 | 0 | 0 | 11515 | 0 | 11515 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | NER | REF | 27 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 2002-01-01 | 2001-04-01 |  | 2004-12-01 | 2005-11-01 | 15455 | -3305 | 12150 | 12150 | 100% | 0 | 0 | 0 | 2009.15 | -430.1479 | 1579.0021 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | NER | REF | 27 | TAS | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2001-04-01 |  | 2003-08-01 | 2003-10-01 | 87603 | -8661 | 78942 | 78942 | 100% | 0 | 0 | 0 | 11388.39 | -1126.39 | 10262 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP update: incentive programme to promote good practices in refrigeration | RMP-Component | LAC | NIC | REF | 45 | TAS | 13 | N | I | CFC | 35.2 | 35.2 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recyling of CFC-12 refrigerant | RMP-Component | LAC | PAR | REF | 32 | TAS | 08 | A | I | CFC | 96.3 | 96.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2004-12-01 | 2005-11-01 | 285158 | -8350.9989 | 276807.0011 | 276807 | 100% | 0.0011 | 0 | 0 | 37070.54 | -1085.5433 | 35984.9965 | 0.000143 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP update: technical assistance for the refrigeration sector | RMP-Component | LAC | PER | REF | 43 | TAS | 37 | N | I | CFC | 94.9 | 94.9 | 0 | 0 | 2004-07-01 | 2007-02-01 | 2007-12-01 |  | 2009-12-01 | 2011-12-01 | 123000 | -1847.14 | 121152.86 | 121152.86 | 100% | 0 | 0 | 0 | 11070 | -166.24 | 10903.76 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | PRC | REF | 41 | TAS | 11 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2003-12-01 | 2006-07-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 118078 | 0 | 118078 | 118078 | 100% | 0 | 0 | 0 | 10627 | 0 | 10627 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: refrigeration manufacturing and centralized recovery and recycling of refrigerants | RMP-Component | AFR | RWA | REF | 41 | TAS | 08 | N | I | CFC | 12.9 | 12.9 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-01-01 | 118758 | -15641.68 | 103116.32 | 103116.32 | 100% | 0 | 0 | 0 | 10688 | -1407.7222 | 9280.2778 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities included in the RMP | RMP-Component | ASP | SRL | REF | 32 | TAS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2008-12-01 | 2010-06-01 | 15455 | -2285.64 | 13169.36 | 13169.36 | 100% | 0 | 0 | 0 | 2009.15 | -297.261 | 1711.889 | 0 | 0 | Financially completed in 2010. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | STP | REF | 44 | TAS | 10 | N | I | CFC | 1.8 | 1.8 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 110000 | -2.63 | 109997.37 | 109997.37 | 100% | 0 | 0 | 0 | 9900 | -0.2367 | 9899.7633 | 0 | 0 | Completed in 2008. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring of the activities included in the RMP | RMP-Component | AFR | TOG | REF | 38 | TAS | 05 | A | I | CFC | 1.3 | 1.3 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2007-12-01 | 2008-10-01 | 15000 | 0 | 15000 | 14999.54 | 100% | 0.46 | 0 | 0 | 1950 | 0 | 1949.9402 | 0.0598 | 0 | Completed in 2007. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration sector | RMP-Component | AFR | TOG | REF | 38 | TAS | 06 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2006-11-01 |  | 2007-12-01 | 2011-11-01 | 110000 | -3067.85 | 106932.15 | 106932.15 | 100% | 0 | 0 | 0 | 14300 | -398.8205 | 13901.1795 | 0 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of refrigerants | RMP-Component | AFR | TOG | REF | 38 | TAS | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  | 2007-12-01 | 2011-11-01 | 150000 | -575.31 | 149424.69 | 149424.69 | 100% | 0 | 0 | 0 | 19500 | -74.7903 | 19425.2097 | 0 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | TRI | REF | 23 | TAS | 09 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 213990 | -12116 | 201874 | 201874 | 100% | 0 | 0 | 0 | 27818.7 | -1575.08 | 26243.62 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | LAC | URU | REF | 34 | TAS | 37 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 |  | 2009-12-01 | 2011-02-01 | 154934 | -191.65 | 154742.35 | 154742.35 | 100% | 0 | 0 | 0 | 20141.42 | -24.9145 | 20116.5055 | 0 | 0 | Completed in 2009. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | ASP | VIE | REF | 34 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-01-01 | 21600 | -242 | 21358 | 21358 | 100% | 0 | 0 | 0 | 2808 | -31.46 | 2776.54 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 34 | TAS | 35 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-01-01 | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 35 | TAS | 39 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2007-03-01 | 290413 | -22502 | 267911 | 267911 | 100% | 0 | 0 | 0 | 37754 | -2925.284 | 34828.716 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Component | ASP | YEM | REF | 37 | TAS | 15 | A | I | CFC | 220 | 220 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2008-12-01 | 2012-06-01 | 1472730 | -36714.02 | 1436015.98 | 1436015.98 | 100% | 0 | 0 | 0 | 172000.3 | -4287.83 | 167712.47 | 0 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 44 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -473 | 29527 | 29527 | 100% | 0 | 0 | 0 | 3900 | -61 | 3838.51 | 0.49 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: three thematic meetings on issues related to the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-11-01 | 2005-04-01 |  | 2006-01-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: technical assistance for other countries not included in the strategy | Individual | ASP | ASP | REF | 36 | TAS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-01-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: policy assistance and guidance to countries for development of regulations | Individual | ASP | ASP | REF | 36 | TAS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  | 2005-12-01 | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2005-12-01 |  | 2007-12-01 | 2007-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. ($473 plus $61 returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training | Individual | ASP | BAH | REF | 26 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2001-12-01 | 2003-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 2001-05-01 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | ASP | BAH | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-05-01 | 1999-12-01 |  | 2001-12-01 | 2001-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | Individual | LAC | BAR | REF | 43 | TAS | 10 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2004-07-01 | 2005-03-01 | 2006-12-01 |  | 2011-03-01 | 2012-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 15 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-06-01 |  | 2006-07-01 | 2010-12-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 | 0 | 2925 | 0 | 2925 | 0 | 0 | Project financially completed. ($10,000 plus $1,300 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | BDI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 14 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2006-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training technicians in good management practices | Individual | AFR | BDI | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | BGD | REF | 29 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2001-12-01 |  | 2004-07-01 | 2004-07-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 | 0 | 2925 | 0 | 2925 | 0 | 0 | Project financially completed. ($ 947 plus $ 123 PSC returned to ExCom 50$ 23,754 plus $ 3,088 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and implementation of a national technicians training programme | Individual | ASP | BGD | REF | 29 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-03-01 | 2001-12-01 |  | 2004-12-01 | 2009-12-01 | 88000 | -24701 | 63299 | 63299 | 100% | 0 | 0 | 0 | 11440 | -3211.02 | 8228.87 | 0.11 | 0 | Project financially completed. ($ 4,167 plus 542 PSC returned to ExCom 50 $4,167 plus $542 returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | BHA | REF | 23 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-08-01 | 1998-02-01 |  | 2005-09-01 | 2008-12-01 | 26500 | -8334 | 18166 | 18166 | 100% | 0 | 0 | 0 | 3445 | -1084 | 2361.58 | -0.58 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | BHA | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-05-01 | 2003-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | BHU | REF | 45 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-10-01 |  | 2006-09-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for customs and enforcement officers | Individual | ASP | BHU | REF | 45 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2006-04-01 |  | 2006-09-01 | 2007-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring of the activities included in the RMP | Individual | ASP | BRU | REF | 44 | TAS | 09 | A | I | CFC | 2.9 | 2.9 | 0 | 0 | 2004-12-01 | 2008-05-01 | 2007-12-01 |  | 2010-12-01 | 2011-07-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project completed in December 2010. PCR is being finalized for submission to the MLFS. Phase I organized in Feb 2008, 13 selected refrigeration trainers and senior technicians were trained as trainers by the RMP implementation Officer and other regional resource person through one training course. The second phase of this training programme from Mar - Nov 2009 jointly conducted by Department of Environment, Parks and Recreation, Ministry of Development, and the trainers trained during the first phase, comprising of refrigeration teachers/lecturers from both Jefri Bolkiah Engineering College and Sultan Bolkiah Vocational School, 300 refrigeration technicians and other important stakeholders were trained. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | BRU | REF | 44 | TRA | 08 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and national technicians training | Individual | ASP | BRU | REF | 44 | TRA | 07 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2008-06-01 | 2006-12-01 |  | 2010-12-01 | 2011-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project completed in December 2010. PCR is being finalized for submission to the MLFS. Phase I organized in Feb 2008, 13 selected refrigeration trainers and senior technicians were trained as trainers by the RMP implementation Officer and other regional resource person through one training course. The second phase of this training programme from Mar - Nov 2009 jointly conducted by Department of Environment, Parks and Recreation, Ministry of Development, and the trainers trained during the first phase, comprising of refrigeration teachers/lecturers from both Jefri Bolkiah Engineering College and Sultan Bolkiah Vocational School, 300 refrigeration technicians and other important stakeholders were trained. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: prevention of illegal trade of CFCs | Individual | LAC | BZE | REF | 44 | TAS | 13 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 22611 | 0 | 22611 | 22611 | 100% | 0 | 0 | 0 | 2939 | 0 | 2939 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | BZE | REF | 44 | TAS | 14 | A | I | CFC | 4 | 4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 27140 | 0 | 27140 | 27140 | 100% | 0 | 0 | 0 | 3528 | 0 | 3528 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: certification and licensing of refrigeration technicians | Individual | LAC | BZE | REF | 44 | TAS | 11 | A | I | CFC | 5 | 5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 33682 | 0 | 33682 | 33682 | 100% | 0 | 0 | 0 | 4379 | 0 | 4379 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | CBI | REF | 44 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2008-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | CBI | REF | 44 | TRA | 05 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CBI | REF | 44 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 1,983 plus $ 258 returned to ExCom 50) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CHD | REF | 29 | TRA | 06 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-11-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  | 2002-10-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians in good service practices | Individual | AFR | CHD | REF | 29 | TRA | 05 | A | I | CFC | 5.1 | 5.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-12-01 | 80125 | 0 | 80125 | 80125 | 100% | 0 | 0 | 0 | 10416 | 0 | 10416 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring, evaluation and reporting of the activities in the RMP | Individual | LAC | CHI | REF | 35 | TAS | 149 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. Balance to be returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: enabling a control and regulatory network | Individual | LAC | CHI | REF | 35 | TAS | 146 | A | I | CFC | 18.4 | 18.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2002-09-01 |  | 2009-06-01 | 2011-04-01 | 111400 | 0 | 111400 | 111400 | 100% | 0 | 0 | 0 | 14482 | 0 | 14482 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: end-users and public awareness programme | Individual | LAC | CHI | REF | 35 | TAS | 148 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-07-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 22360 | 0 | 22360 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | CKI | REF | 44 | TAS | 03 | A | I | CFC | 0.5 | 0.5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2010-07-01 | 2011-07-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | The project is completed. A draft PCR has been submitted by the country, but UNEP has requested additional information to complete the report before submitting it to the MLFS. Among the main outputs of the project so far reported are: 4,601 local ESB/EPB officers and 315 Customs and enforcement officers trained, 52 Managers of on-line training system, 154 Project Management officers, and 43 MAC Audit officers under the implementation of the project The new law, “Regulation of ODS Management”, which issued and effect by State Council in 2010 was propagated via workshops and training sessions The ODS Import and Export Management office of China have given lectures on combating the illegal exports of ODS, on the ODS licensing system with the pertinent government institutions and on accessing ODS export data Awareness materials developed and widely distributed to ESB and Customs offices, borders and public establishment of a stronger relationship with press people on a regular media update regarding the ban on the export of ODS, and other general awareness programme on the implementation of Montreal Protocol. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | CKI | REF | 44 | TAS | 01 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2010-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 | 0 | 0 | 1820 | -426.01 | 1393.99 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring of RMP implementation and its impact in the service and end-users sectors | Individual | AFR | COI | REF | 35 | TAS | 05 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2001-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-07-01 | 2008-09-01 | 18000 | -2000 | 16000 | 16000 | 100% | 0 | 0 | 0 | 2340 | -260 | 2080 | 0 | 0 | Project financially completed. ($ 1,028 plus $ 134 PSC returned to ExCom 50. $ 1,190 plus $ 155 PSC returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers in identification and control of ODS imports | Individual | AFR | COI | REF | 35 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-07-01 |  | 2003-12-01 | 2006-06-01 | 39000 | -13386 | 25614 | 25614 | 100% | 0 | 0 | 0 | 5070 | -1740 | 3329.82 | 0.18 | 0 | Project financially completed. ( ) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assessment of the end-users subsector | Individual | AFR | COI | REF | 35 | TAS | 06 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-06-01 | 2006-06-01 | 30000 | -2218 | 27782 | 27782 | 100% | 0 | 0 | 0 | 3900 | -289 | 3611.66 | -0.66 | 0 | Project financially completed. ($7,093 plus $922 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer and training of refrigeration service technicians | Individual | AFR | COI | REF | 35 | TRA | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2002-07-01 |  | 2003-12-01 | 2005-12-01 | 51000 | -7093 | 43907 | 43907 | 100% | 0 | 0 | 0 | 6630 | -922.09 | 5707.91 | 0 | 0 | Project financially completed. ($10,406 plus $ 1,353 PSC returned to ExCom 50. $ 2,980 plus $ 387 returned to ExCom 53) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance to establish legislation | Individual | AFR | DJI | REF | 37 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2002-07-01 | 2004-05-01 | 2003-08-01 |  | 2004-04-01 | 2009-03-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 | 0 | 1170 | 0 | 1170 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | DJI | REF | 37 | TRA | 04 | A | I | CFC | 2.1 | 2.1 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-06-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 | 0 | 4303 | 0 | 4303 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training in good practices of refrigeration | Individual | AFR | DJI | REF | 37 | TRA | 05 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 2002-07-01 | 2004-08-01 | 2003-08-01 |  | 2006-12-01 | 2009-04-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 | 0 | 9646 | 0 | 9646 | 0 | 0 | Project financially completed. ($9,000 plus $1170 returned ExCom 37$25,200 plus $3276 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: custom training | Individual | LAC | DMI | REF | 26 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2003-06-01 | 2000-11-01 |  | 2006-04-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices | Individual | LAC | DMI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2006-06-01 | 2008-12-01 | 20000 | -3000 | 17000 | 17000 | 100% | 0 | 0 | 0 | 2600 | -390 | 2210 | 0 | 0 | Project financially completed. ($16,000 plus $2080 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | LAC | DOM | REF | 25 | TRA | 14 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2003-06-01 | 2005-01-01 | 38000 | -10000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 4940 | -1300 | 3640 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | DOM | REF | 25 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-02-01 |  | 2001-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | DRC | REF | 41 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. ($ 208 plus $ 27 PSC returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | DRC | REF | 41 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 109000 | -208 | 108792 | 108792 | 100% | 0 | 0 | 0 | 14170 | -27.04 | 14142.96 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for technicians in the refrigeration sector | Individual | AFR | DRC | REF | 41 | TRA | 15 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-10-01 |  | 2006-12-01 | 2010-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance for the development of a licensing system and training of customs officers | Individual | ASP | DRK | REF | 40 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-08-01 | 2006-01-01 | 50000 | -5486 | 44514 | 44514 | 100% | 0 | 0 | 0 | 6500 | -713 | 5786.82 | 0.18 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training | Individual | LAC | ELS | REF | 25 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2004-03-01 | 2005-02-01 | 38000 | -14300 | 23700 | 23700 | 100% | 0 | 0 | 0 | 4940 | -1859 | 3081 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | ELS | REF | 25 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 2000-02-01 |  | 2001-12-01 | 2003-07-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 | 0 | 0 | 5070 | 0 | 5070 | 0 | 0 | Project financially completed. ($ 5,000 plus $ 650 PSC returned ExCom 30) |  |  | 2000-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | FIJ | REF | 29 | TRA | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2004-07-01 | 2008-12-01 | 42500 | -1811 | 40689 | 40689 | 100% | 0 | 0 | 0 | 5525 | -235 | 5289.57 | 0.43 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | FIJ | REF | 29 | TRA | 06 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-01-01 | 2004-10-01 | 70500 | -24500 | 46000 | 46000 | 100% | 0 | 0 | 0 | 9165 | -3185 | 5980 | 0 | 0 | Project financially completed. ($ 2,165 plus $ 281 PSC returned ExCom 41) |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | GAB | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2003-12-01 | 2005-01-01 | 31000 | -10000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 4030 | -1300 | 2730 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | GAB | REF | 41 | TRA | 13 | A | I | CFC | 1.9 | 1.9 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | GAB | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-09-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. ($1,985 plus $258 returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme ( phase II) | Individual | AFR | GAB | REF | 41 | TRA | 12 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 50000 | -1985 | 48015 | 48015 | 100% | 0 | 0 | 0 | 6500 | -258.05 | 6241.95 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | AFR | GAM | REF | 29 | TAS | 08 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-10-01 | 2003-10-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for technicians in good refrigeration practices | Individual | AFR | GAM | REF | 29 | TRA | 09 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-10-01 | 2003-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring of the activities in the RMP | Individual | AFR | GBS | REF | 43 | TAS | 05 | A | I | CFC | 1 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2007-07-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. ($ 626 plus $81 PSC returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for customs officials, police, coast guards, border guards and commercial inspectors | Individual | AFR | GBS | REF | 43 | TRA | 06 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-12-01 | 70000 | -1956 | 68044 | 68044 | 100% | 0 | 0 | 0 | 9100 | -254.28 | 8845.72 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for refrigeration technicians | Individual | AFR | GBS | REF | 43 | TRA | 08 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 70000 | -626 | 69374 | 69374 | 100% | 0 | 0 | 0 | 9100 | -81.38 | 9018.62 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme in the refrigeration sector (phase III) | Individual | EUR | GEO | REF | 35 | TRA | 12 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2003-01-01 |  | 2005-11-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODS | Individual | EUR | GEO | REF | 23 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-01-01 | 1998-02-01 |  | 2005-06-01 | 2006-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in the refrigeration servicing sector | Individual | EUR | GEO | REF | 23 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-11-01 | 1998-11-01 |  | 2001-11-01 | 2006-12-01 | 50000 | -9800 | 40200 | 40200 | 100% | 0 | 0 | 0 | 6500 | -1274 | 5226 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | GHA | REF | 32 | TRA | 13 | A | I | CFC | 6.3 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2003-01-01 | 2007-04-01 | 81000 | -18194 | 62806 | 62806 | 100% | 0 | 0 | 0 | 10530 | -2365.22 | 8164.78 | 0 | 0 | Project financially completed. |  |  | 2003-06-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and Ozone Unit staff | Individual | LAC | GRN | REF | 30 | TRA | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2007-01-01 | 2009-12-01 | 36700 | -13787 | 22913 | 22913 | 100% | 0 | 0 | 0 | 4771 | -1792.31 | 2978.69 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | LAC | GRN | REF | 30 | TRA | 03 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2000-10-01 |  | 2007-01-01 | 2008-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | Non Investment
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | GUA | REF | 27 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  | 2001-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: licensing system | Individual | LAC | GUA | REF | 27 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: establishment of licensing system | Individual | LAC | GUA | REF | 35 | TAS | 23 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23200 | 0 | 23200 | 23200 | 100% | 0 | 0 | 0 | 3016 | 0 | 3016 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | GUA | REF | 35 | TAS | 25 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 31800 | 0 | 31800 | 31800 | 100% | 0 | 0 | 0 | 4134 | 0 | 4134 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | GUA | REF | 27 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2000-10-01 |  | 2002-11-01 | 2003-11-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | Project financially completed. |  |  | 2001-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | LAC | GUA | REF | 35 | TRA | 27 | A | I | CFC | 46.3 | 46.3 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2007-12-01 |  | 2009-03-01 | 2009-03-01 | 56000 | 0 | 56000 | 56000 | 100% | 0 | 0 | 0 | 7280 | 0 | 7280 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: alternatives to the use of CFC-12 in the refrigeration sector | Individual | LAC | GUA | REF | 35 | TAS | 24 | A | I | CFC | 47.9 | 47.9 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-03-01 | 2009-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 | 0 | 7540 | 0 | 7540 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: establishment and enforcement of legislation | Individual | LAC | GUA | REF | 35 | TAS | 26 | A | I | CFC | 51.2 | 51.2 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | GUI | REF | 30 | TRA | 06 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2000-03-01 | 2001-03-01 | 2001-04-01 |  | 2003-03-01 | 2007-06-01 | 42500 | -23512 | 18988 | 18988 | 100% | 0 | 0 | 0 | 5525 | -3056.56 | 2468.44 | 0 | 0 | Project financially completed. |  |  | 2003-03-01 | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities of the RMP | Individual | AFR | GUI | REF | 45 | TAS | 14 | A | I | CFC | 3.1 | 3.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs officers training in monitoring and control of ODS (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 12 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-04-01 |  | 2006-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for refrigeration technicians (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 13 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-10-01 |  | 2006-12-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | AFR | GUI | REF | 30 | TRA | 07 | A | I | CFC | 10.5 | 10.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2002-09-01 | 2003-09-01 | 66500 | 0 | 66500 | 66500 | 100% | 0 | 0 | 0 | 8645 | 0 | 8645 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training on monitoring and control of ODS and ODS using equipment | Individual | LAC | GUY | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-06-01 |  | 2003-08-01 | 2003-09-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 2080 | 0 | 2080 | 0 | 0 | Project financially completed. ($ 0 plus $ 205 returned to ExCom 49$ -205 returned to ExCom 58) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers for good refrigeration servicing practices | Individual | LAC | GUY | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 2001-04-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 5,000 plus $ 650 PSC returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance for implementation of additional activities in the RMP | Individual | LAC | GUY | REF | 35 | TAS | 10 | A | I | CFC | 45.2 | 45.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2008-01-01 | 2009-04-01 | 65500 | 0 | 65500 | 65500 | 100% | 0 | 0 | 0 | 8515 | 0 | 8515 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | LAC | HAI | REF | 39 | TRA | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2010-12-01 | 2012-04-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 | 0 | 4303 | 0 | 4303 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the technicians on good practices in refrigeration | Individual | LAC | HAI | REF | 39 | TRA | 05 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2008-12-01 | 2009-12-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 | 0 | 9646 | 0 | 9646 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: programme for prevention of illegal ODS trade | Individual | LAC | HON | REF | 44 | TAS | 17 | A | I | CFC | 21.3 | 21 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 2990 | 0 | 2990 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: programme for permanent monitoring of the RMP | Individual | LAC | HON | REF | 44 | TAS | 18 | A | I | CFC | 35.1 | 35.1 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 38000 | -5630 | 32370 | 32370 | 100% | 0 | 0 | 0 | 4940 | -731.9 | 4208.1 | 0 | 0 | Project completed in December 2010. The NOU conducted awareness sensitization to Parliamentary Committee responsible for Environment. This resulted into the country ratified all the pending amendments to the Montreal Protocol. The NOU carried out detailed survey of ODS consumption, especially HCFCs and drafted a detailed HPMP. Awareness materials like stickers, caps, calendars and leaflets were produced and distributed. The country celebrated the Ozone day and awarded prizes to the best environmental journalists. ODS issues were featured in several radio stations, the National TV station and several newspapers |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: programme for certification and licensing of refrigeration technicians | Individual | LAC | HON | REF | 44 | TRA | 16 | A | I | CFC | 86.9 | 86.9 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 | 0 | 12220 | 0 | 12220 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: implementation support and monitoring | Individual | ASP | KAM | REF | 41 | TAS | 08 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. ($ 433 plus $ 56 PSC returned to ExCom 49) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | KAM | REF | 41 | TRA | 07 | A | I | CFC | 7.6 | 7.6 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-03-01 | 85000 | -199 | 84801 | 84801 | 100% | 0 | 0 | 0 | 11050 | -26 | 11024.13 | -0.13 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: refrigeration and air-conditioning technicians training programme | Individual | ASP | KAM | REF | 41 | TRA | 06 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-03-01 | 130000 | -54 | 129946 | 129946 | 100% | 0 | 0 | 0 | 16900 | -7 | 16892.98 | 0.02 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | KUW | REF | 37 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2005-12-01 | 2005-08-01 |  | 2009-12-01 | 2010-12-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers in monitoring of ODS | Individual | ASP | KUW | REF | 37 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-01-01 |  | 2004-12-01 | 2006-12-01 | 53445 | 0 | 53445 | 53445 | 100% | 0 | 0 | 0 | 6948 | 0 | 6948 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training for customs excise and personnel involved in the monitoring of ODS/equipment | Individual | EUR | KYR | REF | 37 | TRA | 03 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2005-06-01 | 2009-06-01 | 74910 | 0 | 74910 | 74910 | 100% | 0 | 0 | 0 | 9738 | 0 | 9738 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | EUR | KYR | REF | 37 | TRA | 06 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2003-08-01 |  | 2005-08-01 | 2009-08-01 | 97900 | 0 | 97900 | 97900 | 100% | 0 | 0 | 0 | 12727 | 0 | 12727 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities contained in the RMP | Individual | ASP | LAO | REF | 34 | TAS | 07 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-12-01 | 17500 | -12500 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2275 | -1624.54 | 650 | 0.46 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | LIR | REF | 41 | TRA | 07 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-06-01 | 2008-12-01 | 40040 | -2389 | 37651 | 37651 | 100% | 0 | 0 | 0 | 5205 | -311 | 4894.4419 | -0.44193 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers and other officers to control and follow-up of ODS and its containers | Individual | AFR | MAG | REF | 47 | TRA | 10 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of maintenance technicians including small craftsmen of informal sector | Individual | AFR | MAG | REF | 47 | TRA | 11 | A | I | CFC | 4.2 | 4.2 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | MAU | REF | 41 | TAS | 13 | A | I | CFC | 1.2 | 1.2 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -834 | 29166 | 29166 | 100% | 0 | 0 | 0 | 3900 | -108 | 3791.58 | 0.42 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs excise | Individual | AFR | MAU | REF | 41 | TRA | 09 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2007-12-01 | 2008-12-01 | 39800 | -1069 | 38731 | 38731 | 100% | 0 | 0 | 0 | 5174 | -139 | 5035.03 | -0.03 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians | Individual | AFR | MAU | REF | 41 | TRA | 10 | A | I | CFC | 2.6 | 2.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2005-07-01 |  | 2007-12-01 | 2011-03-01 | 65000 | -21716 | 43284 | 43284 | 100% | 0 | 0 | 0 | 8450 | -2823.08 | 5626.92 | 0 | 0 | Project completed in July 2010. Despite security concerns in Somalia, the NOU managed to undertake ODS survey, collected data and submitted to both Ozone and Multilateral Fund Secretariats. The NOU conducted awareness raising campaigns and promoted voluntary compliance by the public. The NOU drafted ODS Regulations and got them approved by the Minister of Environment. The project was successfully completed and the new IS phase was approved for Somalia at the 59th Excom meeting. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring and review | Individual | ASP | MDV | REF | 38 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-08-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MDV | REF | 38 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-07-01 | 2008-12-01 | 35000 | -2000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 4550 | -260 | 4290 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officials and the Ozone Unit staff | Individual | ASP | MDV | REF | 38 | TRA | 08 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-05-01 |  | 2005-11-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project completed in July 2010. Final payment sent to the country in June 2010 |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance in drafting ODS-related legislation | Individual | AFR | MLI | REF | 29 | TAS | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-07-01 | 2003-08-01 | 10980 | 0 | 10980 | 10980 | 100% | 0 | 0 | 0 | 1427 | 0 | 1427 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | AFR | MLI | REF | 45 | TAS | 19 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: training programme for refrigeration service technicians (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 18 | A | I | CFC | 6.1 | 6.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2008-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: training programme for customs officers (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 17 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2007-09-01 | 2008-12-01 | 29546 | 0 | 29546 | 29546 | 100% | 0 | 0 | 0 | 3841 | 0 | 3841 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration servicing sector | Individual | AFR | MLI | REF | 29 | TRA | 08 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-05-01 | 2005-01-01 | 60000 | -18414 | 41586 | 41586 | 100% | 0 | 0 | 0 | 7800 | -2393.82 | 5406.18 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | MLI | REF | 29 | TRA | 07 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  | 2003-03-01 | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | EUR | MOL | REF | 44 | TAS | 11 | A | I | CFC | 6.4 | 6.4 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 19885 | -4233.91 | 15651.09 | 15651 | 100% | 0.09 | 0 | 0 | 2585 | -550.41 | 2034.5906 | -0.00064622 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme for good practices in the refrigeration sector | Individual | EUR | MOL | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-09-01 | 1999-08-01 |  | 2003-12-01 | 2005-12-01 | 66000 | -11000 | 55000 | 55000 | 100% | 0 | 0 | 0 | 8580 | -1430 | 7150 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training on monitoring and control of CFC and CFC using equipment | Individual | EUR | MOL | REF | 25 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2001-06-01 | 1999-08-01 |  | 2004-12-01 | 2008-01-01 | 66550 | -7349 | 59201 | 59201 | 100% | 0 | 0 | 0 | 8652 | -955 | 7696.5748 | 0.42521 | 0 | Project financially completed. |  |  | 2002-01-01 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MON | REF | 32 | TRA | 03 | A | I | CFC | 2.4 | 2.4 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-10-01 | 2005-01-01 | 65970 | -15423 | 50547 | 50547 | 100% | 0 | 0 | 0 | 8576 | -2003.95 | 6571.0334 | 1.0166 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | MON | REF | 32 | TRA | 04 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-06-01 | 2003-06-01 | 77200 | -15003 | 62197 | 62197 | 100% | 0 | 0 | 0 | 10036 | -1950.39 | 8085.61 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: preparation of ozone regulations for control of ODSs | Individual | ASP | MYA | REF | 45 | TAS | 05 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2005-04-01 | 2008-05-01 | 2005-11-01 |  | 2011-01-01 | 2011-11-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1690 | 0 | 1690 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring implementation of the RMP | Individual | ASP | MYA | REF | 45 | TAS | 06 | A | I | CFC | 8.8 | 0 | 0 | 0 | 2005-04-01 | 2008-03-01 | 2008-04-01 |  | 2011-01-01 | 2011-11-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NAU | REF | 44 | TAS | 01 | A | I | CFC | 0.2 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | -2000 | 6000 | 6000 | 100% | 0 | 0 | 0 | 1040 | -260 | 780 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NAU | REF | 44 | TAS | 03 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2010-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 | 0 | 0 | 1820 | 0 | 1820 | 0 | 0 | Project completed in March 2010 & financially completed. IS renewal was submitted to the 60th ExCom and funding was approved. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | ASP | NEP | REF | 28 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2002-10-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 | 0 | 0 | 780 | 0 | 780 | 0 | 0 | Project financially completed. |  |  | 2001-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and control of CFC and establishment of import/export licensing system | Individual | ASP | NEP | REF | 28 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2004-07-01 | 2006-02-01 | 44400 | -19400 | 25000 | 25000 | 100% | 0 | 0 | 0 | 5772 | -2522 | 3250 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in refrigeration | Individual | ASP | NEP | REF | 28 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-02-01 |  | 2004-03-01 | 2004-10-01 | 70000 | -29000 | 41000 | 41000 | 100% | 0 | 0 | 0 | 9100 | -3770 | 5330 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance to remain in compliance with the Montreal Protocol | Individual | ASP | NEP | REF | 44 | TAS | 15 | A | I | CFC | 10.8 | 5.4 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2007-12-01 |  | 2008-01-01 | 2008-10-01 | 51440 | 0 | 51440 | 51440 | 100% | 0 | 0 | 0 | 6687 | 0 | 6687 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities | Individual | AFR | NER | REF | 42 | TAS | 15 | A | I | CFC | 6 | 6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2006-04-01 |  | 2007-04-01 | 2007-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 2990 | 0 | 2990 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: training for customs technicians | Individual | AFR | NER | REF | 42 | TRA | 13 | A | I | CFC | 6.6 | 6.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2007-04-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs officers training programme | Individual | AFR | NER | REF | 27 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-08-01 | 2000-10-01 |  | 2003-12-01 | 2005-02-01 | 63000 | -24000 | 39000 | 39000 | 100% | 0 | 0 | 0 | 8190 | -3120 | 5070 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | NER | REF | 27 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2002-05-01 | 2003-05-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 | 0 | 5395 | 0 | 5395 | 0 | 0 | Project financially completed. ($1,501 plus $195 PSC returned to ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: train the trainer programme for refrigeration service technicians | Individual | AFR | NER | REF | 42 | TRA | 14 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-10-01 |  | 2006-12-01 | 2008-06-01 | 55747 | -1501 | 54246 | 54246 | 100% | 0 | 0 | 0 | 7247 | -195.13 | 7051.873 | -0.0029618 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: monitoring the activities of the RMP | Individual | LAC | NIC | REF | 45 | TAS | 16 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 30000 | -1065 | 28935 | 28935 | 100% | 0 | 0 | 0 | 3900 | -138.45 | 3761.55 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: licensing and certification system for refrigeration technicians | Individual | LAC | NIC | REF | 45 | TRA | 14 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NIU | REF | 44 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2010-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NIU | REF | 44 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2009-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 | 0 | 0 | 1820 | -426.01 | 1393.99 | 0 | 0 | Project financially completed. Balances returned to ExCom 63 |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring on assistance to develop legislation | Individual | LAC | PAN | REF | 29 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2002-12-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. ($ 6,000 plus $ 780 PSC returned ExCom 41 ($ 3,000 plus $ 390 PSC added ExCom 11)) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training and certification programme in refrigeration | Individual | LAC | PAN | REF | 29 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2008-12-01 | 2010-12-01 | 126200 | 0 | 126200 | 126200 | 100% | 0 | 0 | 0 | 16406 | 0 | 16406 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: policy dialogue programme on complementary policy and enforcement | Individual | LAC | PAR | REF | 32 | TAS | 10 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2001-09-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Individual | LAC | PAR | REF | 32 | TAS | 06 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2001-12-01 |  | 2008-12-01 | 2010-12-01 | 44920 | 0 | 44920 | 44920 | 100% | 0 | 0 | 0 | 5840 | 0 | 5840 | 0 | 0 | Project financially completed. |  |  | 2003-06-01 | Non Investment
FIN | UNEP | Implementation of the RMP: train of trainers and training of refrigeration service technicians | Individual | LAC | PAR | REF | 32 | TRA | 07 | A | I | CFC | 56.7 | 56.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-12-01 |  | 2008-12-01 | 2012-01-01 | 168020 | -2569 | 165451 | 165451 | 100% | 0 | 0 | 0 | 21843 | -333.97 | 21509.0239 | 0.0061159 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: support for a licensing system | Individual | LAC | PER | REF | 27 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2002-02-01 | 2003-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. ($ 3,000 returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | PER | REF | 27 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2002-02-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | PER | REF | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2004-05-01 | 2005-12-01 | 34000 | -13000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 4420 | -1690 | 2730 | 0 | 0 | Project financially completed. |  |  | 2001-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP update: technical assistance for prevention of illegal CFC trade | Individual | LAC | PER | REF | 43 | TAS | 36 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2010-06-01 | 2011-03-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | Project activities completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | LAC | PER | REF | 43 | TAS | 34 | A | I | CFC | 30.9 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2007-12-01 |  | 2011-10-01 | 2012-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP update: refrigeration technicians certification and licensing system | Individual | LAC | PER | REF | 43 | TAS | 35 | A | I | CFC | 66.4 | 66.4 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance for information-sharing | Individual | AFR | PRC | REF | 32 | TAS | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-01-01 |  | 2003-12-01 | 2005-02-01 | 16000 | -2967 | 13033 | 13033 | 100% | 0 | 0 | 0 | 2080 | -385.71 | 1694.29 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | PRC | REF | 32 | TRA | 09 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-12-01 |  | 2003-12-01 | 2005-01-01 | 69400 | -25378 | 44022 | 44022 | 100% | 0 | 0 | 0 | 9022 | -3299.14 | 5722.86 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | RWA | REF | 41 | TAS | 09 | A | I | CFC | 2.2 | 0 | 0 | 0 | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2012-01-01 | 20000 | -10000 | 10000 | 10000 | 100% | 0 | 0 | 0 | 2600 | -1300 | 1300 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | AFR | RWA | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration service technicians | Individual | ASP | SAM | REF | 32 | TRA | 04 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-02-01 |  | 2002-10-01 | 2003-10-01 | 48800 | -5864 | 42936 | 42936 | 100% | 0 | 0 | 0 | 6344 | -762.32 | 5581.68 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officials and NOU staff | Individual | ASP | SAM | REF | 32 | TRA | 03 | A | I | CFC | 2 | 2 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-06-01 |  | 2003-09-01 | 2003-12-01 | 53500 | -9474 | 44026 | 44026 | 100% | 0 | 0 | 0 | 6955 | -1232 | 5723.38 | -0.38 | 0 | Project financially completed. |  |  | 2003-06-01 | Non Investment
FIN | UNEP | Implementation of the RMP: activities for supporting and monitoring the RMP | Individual | AFR | SEN | REF | 33 | TAS | 15 | A | I | CFC | 29.4 | 29.4 | 0 | 0 | 2001-03-01 | 2001-07-01 | 2003-12-01 |  | 2002-05-01 | 2003-06-01 | 44500 | -37 | 44463 | 44463 | 100% | 0 | 0 | 0 | 5785 | -4.81 | 5780.19 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | SIL | REF | 41 | TAS | 09 | A | I | CFC | 2.4 | 0 | 0 | 0 | 2003-12-01 | 2010-06-01 | 2006-12-01 |  | 2008-02-01 | 2010-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 | 0 | 2009 | 0 | 2009 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | SIL | REF | 41 | TRA | 08 | A | I | CFC | 6.4 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2008-01-01 | 2011-03-01 | 41840 | -9826 | 32014 | 32014 | 100% | 0 | 0 | 0 | 5439 | -1277.02 | 4161.667 | 0.31303 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in code of good refrigeration practices/establishment of national refrigeration demonstration centre | Individual | AFR | SIL | REF | 41 | TRA | 04 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | -39463 | 79997 | 79997 | 100% | 0 | 0 | 0 | 15530 | -5130.19 | 10399.7439 | 0.066069 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | SRL | REF | 32 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2005-04-01 | 2010-12-01 | 87000 | 0 | 87000 | 87000 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Project financially completed. ($ 2,312 plus $ 301 PSC returned at ExCom 52$1,148 plus $149 PSC returned at ExCom 57) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainers and training of refrigeration service technicians including | Individual | ASP | SRL | REF | 32 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-12-01 |  | 2004-09-01 | 2009-12-01 | 219000 | -72008 | 146992 | 146992 | 100% | 0 | 0 | 0 | 28470 | -9360.52 | 19108.96 | 0.52 | 0 | Project financially completed. ($12,500 plus $ 1,625 returned ExCom 30) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance for development of a licensing system | Individual | AFR | STP | REF | 44 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-06-01 |  | 2006-12-01 | 2009-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | STP | REF | 44 | TAS | 09 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | STP | REF | 44 | TRA | 08 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2006-12-01 |  | 2008-12-01 | 2012-05-01 | 55000 | -11534 | 43466 | 43466 | 100% | 0 | 0 | 0 | 7150 | -1499.42 | 5650.58 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for custom officers | Individual | AFR | STP | REF | 44 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment | Individual | LAC | STV | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2004-03-01 | 2000-02-01 |  | 2005-02-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers for good practices in refrigeration | Individual | LAC | STV | REF | 25 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: development and strengthening of policy and regulatory framework for acceleration of compliance with the Montreal Protocol | Individual | LAC | SUR | REF | 41 | TAS | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-01-01 | 2009-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers and other relevant stakeholders in monitoring of ODS | Individual | LAC | SUR | REF | 41 | TRA | 05 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-10-01 | 2008-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good practices of refrigeration | Individual | LAC | SUR | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-07-01 |  | 2007-12-01 | 2008-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: assistance for the establishment of regulations and legislation | Individual | ASP | SYR | REF | 29 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2002-06-01 | 2007-01-01 | 25500 | -10000 | 15500 | 15500 | 100% | 0 | 0 | 0 | 3315 | -1300 | 2015 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers | Individual | AFR | TOG | REF | 38 | TRA | 09 | A | I | CFC | 3.8 | 3.8 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-05-01 |  | 2006-12-01 | 2008-02-01 | 43500 | -1003 | 42497 | 42497 | 100% | 0 | 0 | 0 | 5655 | -130.52 | 5524.61 | -0.13 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | AFR | TOG | REF | 38 | TRA | 08 | A | I | CFC | 5.7 | 5.7 | 0 | 0 | 2002-11-01 | 2003-03-01 | 2004-05-01 |  | 2006-12-01 | 2007-02-01 | 64000 | 0 | 64000 | 64000 | 100% | 0 | 0 | 0 | 8320 | 0 | 8320 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | TRI | REF | 23 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-02-01 |  | 2002-04-01 | 2003-05-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 | 0 | 3445 | 0 | 3445 | 0 | 0 | Project financially completed. ($ 25,000 plus $ 3,250 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | TRI | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-09-01 | 2003-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | I | CFC | 45.8 | 45.8 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2007-03-01 | 2009-12-01 | 65000 | -2831 | 62169 | 62169 | 100% | 0 | 0 | 0 | 8450 | -368.03 | 8081.97 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: workshop for finalization of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 | 0 | 0 | 566 | 0 | 566 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2006-02-01 | 200000 | -40959 | 159041 | 159041 | 100% | 0 | 0 | 0 | 26000 | -5324.67 | 20675.33 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 |  | 2006-12-01 | 2011-06-01 | 25000 | -5000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3250 | -650 | 2600 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2011-09-01 | 2011-12-01 | 91825 | 0 | 91825 | 91825 | 100% | 0 | 0 | 0 | 11937 | 0 | 11937 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-08-01 |  | 2008-12-01 | 2010-12-01 | 189500 | 0 | 189500 | 189500 | 100% | 0 | 0 | 0 | 24635 | 0 | 24635 | 0 | 0 | Project financially completed. ($ 391 returned to ExCom 51) |  |  |  | Non Investment
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector (includes: training in good refrigerant management practices, training of customs officers, and national recovery and recycling) | Multi-Year | AFR | ALG | REF | 37 | TAS | 55 | A | I | CFC | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-12-01 |  | 2004-06-01 | 2004-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | -6 | 25994 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector: 2004 programme | Multi-Year | AFR | ALG | REF | 42 | TAS | 59 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2007-11-01 | 2008-12-01 | 524647 | -12543 | 512104 | 512104.16 | 100% | -0.16 | 0 |  | 39349 | -941 | 38408 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): Second tranche | Multi-Year | AFR | ALG | REF | 39 | TAS | 58 | A | I | CFC | 45 | 110 |  |  | 2003-04-01 | 2004-03-01 | 2004-04-01 |  | 2005-06-01 | 2007-05-01 | 700000 | 0 | 700000 | 699999.99 | 100% | 0.01 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (first tranche) | Multi-Year | ASP | PAK | REF | 41 | TAS | 56 | A | I | CFC | 55 | 55 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2004-12-01 | 2009-12-01 | 191000 | 0 | 191000 | 191000.21 | 100% | -0.21 | 0 |  | 14325 | 0 | 14325 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (third tranche) | Multi-Year | ASP | PAK | REF | 47 | INV | 64 | A | I | CFC | 80 | 80 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2008-09-01 | 2010-09-01 | 414300 | -1421 | 412879 | 412879.45 | 100% | -0.45 | 0 |  | 31073 | -107 | 30966 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (second tranche) | Multi-Year | ASP | PAK | REF | 44 | TAS | 61 | A | I | CFC | 80 | 80 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-05-01 | 2010-09-01 | 534200 | -3137 | 531063 | 531062.64 | 100% | 0.36 | 0 |  | 40065 | -235 | 39830 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration servicing sector (includes: training in good refrigerant management practices, training of customs officers, and recovery and recycling programme) | Individual | AFR | CMR | REF | 38 | TAS | 18 | A | I | CFC | 218.4 | 218.4 |  |  | 2002-11-01 | 2003-03-01 | 2007-12-01 |  | 2007-06-01 | 2008-05-01 | 522982 | 0 | 522982 | 522982.01 | 100% | -0.01 | 0 |  | 67528 | 0 | 67528 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan: customs training | RMP | EUR | CRO | REF | 28 | TRA | 12 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2001-04-01 | 2001-08-01 |  | 2002-06-01 | 2003-07-01 | 38250 | -2227 | 36023 | 36022.65 | 100% | 0.35 | 0 |  | 4973 | -297 | 4676 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | EUR | CRO | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2003-02-01 | 2003-07-01 | 70000 | -1483 | 68517 | 68517 | 100% | 0 | 0 |  | 9100 | -207 | 8893 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | EUR | CRO | REF | 28 | TAS | 10 | A | I | CFC | 15 | 15 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2003-10-01 | 289910 | -3739 | 286171 | 286171.08 | 100% | -0.08 | 0 |  | 37688 | -545 | 37143 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | LAC | HON | REF | 28 | TRA | 05 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2002-04-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 38250 | 0 | 38250 | 38250 | 100% | 0 | 0 |  | 4973 | 0 | 4973 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | LAC | HON | REF | 28 | TRA | 06 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | LAC | HON | REF | 28 | TAS | 07 | A | I | CFC | 14.2 | 14.2 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 245900 | -951 | 244949 | 244949.04 | 100% | -0.04 | 0 |  | 31967 | -174 | 31793 | 0 | 0 | FIN |  |  | 2003-06-01 | INV
FIN | UNIDO | Refrigerant management plan: technical assistance and support to develop regulations for ODS to implement the Environment law of 1999 | RMP | ASP | JOR | REF | 28 | TAS | 49 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-03-01 | 2002-07-01 | 20000 | -2979 | 17021 | 17020.85 | 100% | 0.15 | 0 |  | 2600 | -391 | 2209 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan: customs training | RMP | ASP | JOR | REF | 28 | TRA | 48 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-07-01 | 2003-06-01 | 38250 | -187 | 38063 | 38062.56 | 100% | 0.44 | 0 |  | 4973 | -33 | 4940 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | ASP | JOR | REF | 28 | TRA | 47 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2001-08-01 |  | 2002-10-01 | 2004-03-01 | 70000 | -654 | 69346 | 69345.66 | 100% | 0.34 | 0 |  | 9100 | -99 | 9001 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | ASP | JOR | REF | 28 | TAS | 50 | A | I | CFC | 19.1 | 19.1 |  |  | 1999-07-01 | 2001-09-01 | 2001-08-01 |  | 2004-06-01 | 2005-09-01 | 311950 | -2650 | 309300 | 309299.95 | 100% | 0.05 | 0 |  | 40554 | -409 | 40145 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNIDO | Implementation of the RMP: national recovery and recycling | RMP Update | ASP | KUW | REF | 37 | TAS | 05 | A | I | CFC | 64 | 64 |  |  | 2002-07-01 | 2003-07-01 | 2005-08-01 |  | 2006-12-01 | 2008-12-01 | 448816 | -2441 | 446375 | 446375.13 | 100% | -0.13 | 0 |  | 22441 | 35588 | 58029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan: training of customs officers | RMP | EUR | MDN | REF | 28 | TRA | 15 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-03-01 |  | 2002-03-01 | 2003-05-01 | 37180 | -6973 | 30207 | 30207.28 | 100% | -0.28 | 0 |  | 4833 | -912 | 3921 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | MDN | REF | 28 | TRA | 11 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-06-01 |  | 2002-03-01 | 2003-05-01 | 70000 | -6146 | 63854 | 63853.74 | 100% | 0.26 | 0 |  | 9100 | -812 | 8288 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | MDN | REF | 28 | TAS | 10 | A | I | CFC | 13.5 | 13.5 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2002-02-01 | 2003-12-01 | 220044 | -43661 | 176383 | 176382.7 | 100% | 0.3 | 0 |  | 28606 | -5713 | 22893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: establishing conversion practice of domestic refrigerators | Individual | ASP | MYA | REF | 45 | TAS | 07 | A | I | CFC | 32.1 | 32.1 |  |  | 2005-04-01 | 2005-10-01 | 2006-10-01 |  | 2007-11-01 | 2008-07-01 | 80000 | -15 | 79985 | 79984.53 | 100% | 0.47 | 0 |  | 7200 | -1 | 7199 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | OMA | REF | 34 | TAS | 05 | A | I | CFC | 9 | 9 |  |  | 2001-07-01 | 2007-03-01 | 2004-08-01 |  | 2007-12-01 | 2008-09-01 | 20000 | -196 | 19804 | 19804 | 100% | 0 | 0 |  | 2600 | -25 | 2575 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Customs training programme | RMP Update | ASP | OMA | REF | 34 | TRA | 04 | A | I | CFC | 18.9 | 18.9 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-09-01 | 42000 | -4469 | 37531 | 37530.63 | 100% | 0.37 | 0 |  | 5460 | -589 | 4871 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Training of trainers in good refrigerant management practices | RMP Update | ASP | OMA | REF | 34 | TRA | 02 | A | I | CFC | 80 | 80 |  |  | 2001-07-01 | 2002-06-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 178000 | -1359 | 176641 | 176641.2 | 100% | -0.2 | 0 |  | 23140 | -213 | 22927 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Recovery and recycling project | RMP Update | ASP | OMA | REF | 34 | TAS | 06 | A | I | CFC | 103.3 | 103.3 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2005-12-01 | 2007-12-01 | 230000 | -502 | 229498 | 229498.29 | 100% | -0.29 | 0 |  | 29900 | -65 | 29835 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | QAT | REF | 34 | TAS | 02 | A | I | CFC | 3.7 | 3.7 |  |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2007-12-01 | 2009-05-01 | 20000 | -3392 | 16608 | 16608.46 | 100% | -0.46 | 0 |  | 2600 | -441 | 2159 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Training of customs and Ozone Unit in monitoring and control of ODS | RMP Update | ASP | QAT | REF | 34 | TRA | 04 | A | I | CFC | 9.2 | 9.2 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 50000 | -2501 | 47499 | 47499.48 | 100% | -0.48 | 0 |  | 6500 | -335 | 6165 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of RMP: Training of trainers and technicians training in good refrigerant management practices | RMP Update | ASP | QAT | REF | 34 | TRA | 05 | A | I | CFC | 19.3 | 19.3 |  |  | 2001-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-12-01 | 2006-03-01 | 105000 | -5978 | 99022 | 99022.03 | 100% | -0.03 | 0 |  | 13650 | -798 | 12852 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of RMP: National recovery and recycling project | RMP Update | ASP | QAT | REF | 34 | TAS | 03 | A | I | CFC | 54.1 | 54.1 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2006-12-01 | 2007-12-01 | 295000 | -35 | 294965 | 294964.71 | 100% | 0.29 | 0 |  | 38350 | -5 | 38345 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | EUR | ROM | REF | 28 | TRA | 17 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-10-01 |  | 2002-08-01 | 2003-10-01 | 23100 | -1349 | 21751 | 21750.58 | 100% | 0.42 | 0 |  | 3003 | -180 | 2823 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | ROM | REF | 28 | TRA | 19 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2001-01-01 | 2001-06-01 | 70000 | 0 | 70000 | 70000.07 | 100% | -0.07 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | ROM | REF | 28 | TAS | 16 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 373840 | 0 | 373840 | 373840.46 | 100% | -0.46 | 0 |  | 48599 | -69 | 48530 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP: Refrigerant recovery and recycling scheme | RMP Update | AFR | SEN | REF | 33 | TAS | 16 | A | I | CFC | 56.1 | 56.1 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2003-03-01 | 2004-04-01 | 85000 | -1970 | 83030 | 83030.13 | 100% | -0.13 | 0 |  | 11050 | -273 | 10777 | 0 | 0 | National consultant contracted to review ToR and assess the required no. and type of equipment to be delivered to service shops. The subcontract with the counterpart as per the ToR was finalized in December 2012. | National consultant report and technical specification for equipment delivery to be finalized in May 2013. The subcontract with counterpart will be processed first half of 2013. |  |  | INV
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | AFR | SUD | REF | 28 | TRA | 11 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2001-08-01 | 2001-02-01 |  | 2002-10-01 | 2004-09-01 | 38250 | -1916 | 36334 | 36333.7 | 100% | 0.3 | 0 |  | 4973 | -257 | 4716 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | AFR | SUD | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2002-06-01 |  | 2003-12-01 | 2003-12-01 | 70000 | -510 | 69490 | 69490.04 | 100% | -0.04 | 0 |  | 9100 | -81 | 9019 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | AFR | SUD | REF | 28 | TAS | 10 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2004-08-01 | 2006-09-01 | 350000 | -1732 | 348268 | 348268.38 | 100% | -0.38 | 0 |  | 45500 | -225 | 45275 | 0 | 0 | FIN
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | LAC | BAR | REF | 43 | TAS | 12 | N | I | CFC | 1.7 | 1.7 | 0 | 0 | 2004-07-01 |  | 2006-12-01 | 2013-03-01 |  |  | 26150 | 0 | 26150 | 0 | 0% | 26150 | 0 | 7845 | 2354 | 0 | 0 | 2354 | 0 | Expert hired in 2012 to finalize pending activities under the TPMP. Payments will be reflected in 2013. | Payments to expert has been made. | 2004 |  | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration service and MAC sectors | RMP-Component | ASP | BRU | REF | 44 | TAS | 10 | N | I | CFC | 52.3 | 52.3 | 0 | 0 | 2004-12-01 | 2011-12-01 | 2007-05-01 | 2013-06-01 |  |  | 390000 | 0 | 390000 | 184817.11 | 47.39% | 205182.89 | 0 | 61554.867 | 29250 | 0 | 13861.2833 | 15388.7167 | 0 | During the year 2012, 18 MAC R&R machines were procured for MAC retrofit training, and trainings were carried out to service centres in Jan 2012 and to the technical schools in Oct 2012. The Department of Environment, Parks and Recreation announced the Retrofit programme on its website and issued posters and pamphlets to authorized MAC service centres and at all Land Transport Department branches. A public awareness video on MAC retrofit was developed and distributed. | Retrofit programme is ongoing. To date a total of 44 cars have been retrofitted. It is extended till 30 June. The project will be operationally closed in Q3 2013. | 2004 |  | Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | MDV | REF | 38 | TAS | 05 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-05-01 | 2014-12-01 |  |  | 115000 | 0 | 115000 | 26644 | 23.17% | 88356 | 0 | 35342.4 | 14950 | 0 | 3463.72 | 11486.28 | 0 | Remaining funds under RMP proposed to be used to sustain zero ODS consumption and support HCFC phaseout in line with decision 60/11, mainly for providing retrofit incentives for fisheries sector. Please see response to MDV/PHA/60/INV/20 above. | Please see response to MDV/PHA/60/INV/20 above. Implementation progress is closely monitored. | 2002 |  | Non-Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration | RMP-Component | ASP | SRL | REF | 32 | TAS | 15 | N | I | CFC | 5 | 5 | 0 | 0 | 2000-12-01 | 2002-04-01 | 2006-01-01 | 2014-12-01 |  |  | 250000 | 0 | 250000 | 159626.89 | 63.85% | 90373.11 | 0 | 36149.244 | 32500 | 0 | 20751.4957 | 11748.5043 | 0 | RMP activities completed in 2010. The remaining balance is integrated into ongoing HPMP activities related to retrofit incentive scheme and technical information exchange for servicing enterprises. | Project targeted for closure in 2013. Financial closure was delayed due to administrative difficulties faced in utilising funds. | 2000 |  | Non-Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2007-10-01 | 2005-08-01 | 2013-07-01 |  |  | 57750 | 0 | 57750 | 45000 | 77.92% | 12750 | 0 | 12750 | 7508 | 0 | 5850.3896 | 1657.6104 | 0 | UNEP still follow-up with country to receive final financial statements to allow closing the project. | UNEP still follow-up with country to receive final financial statements to allow closing the project. |  |  | Non Investment
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 |  | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP- 35th ExCom |  | 2001
CLO | Belgium | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Quimica Andina |  | LAC | BOL | FOA | 28 | INV | 10 | A | I |  | 5 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2002-02-01 |  |  |  | 108480 | -108480 | 0 | 0 | 0% | 0 |  | 0 | 0 |  |  | 0 |  | Agreement between UNDP and the Belgian Government finally signed in September 2000. However, funds not yet received as of 31 December 2000. Info as of 31 May 2001: funds received in Feb. 2001. Project document not yet signed by Bolivian Govt. However, invitations to bid were sent out and bid analysi was done. However, we had to re-bid because offers did not meet specs for one machine. New bid analysis on-going. Info as of 31 December 2001: New ministry was undergoing some verification of the enterprises which were being considered for MLF funding since according to some new regulations, in order for Quimica Andina to qualify it needed to be one of the higher national consumers of CFC-11. Only if this was the case would the project be approved and the PRODOC signed. |  | 36923
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 |  | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | Cancelled. |  |  |  | INV
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 07 | INV | 28 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 07 | INV | 29 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from Inventory |  |  | 1997-03-01 | INV
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 |  | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | Project cancelled and funds returned at the 35th ExCom. |  |  |  | INV
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 |  | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled |  |  | 1998-01-01 | INV
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 |  | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | Cancelled. |  |  | 1998-01-01 | INV
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 |  | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 |  | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | Project cancelled July 2000. |  |  |  | INV
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | INV
CLO | UNDP | Elimination of the use of CFCs in the manufacture of rigid foam blocks for insulated trailers at Fruehauf | Individual | LAC | ARG | FOA | 23 | INV | 65 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2003-11-01 | 175000 | -40597 | 134403 | 134403 | 100% | 0 | 0 | 0 | 22750 | -5278 | 17472 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Grupo ACO | Individual | LAC | BRA | FOA | 34 | INV | 236 | A | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2004-08-01 |  |  | 2002-07-01 | 174139 | -174139 | 0 | 0 |  | 0 | 0 | 0 | 22638.07 | -22638.07 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2001 |  | Investment
CLO | UNDP | Phase-out of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane insulation foam at Suzhou Purification Equipment Factory | Individual | ASP | CPR | FOA | 28 | INV | 291 | N | I | CFC | 66 | 66 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  |  | 2005-12-01 | 516780 | -259989.84 | 256790.16 | 256790.16 | 100% | 0 | 0 | 0 | 66845.8 | -33462.8 | 33383 | 0 | 0 | Canceled in 2004. Financially Completed in 2005. |  | 1999 |  | Investment
CLO | UNDP | Conversion to CFC-free techology in the manufacture of rigid PUF insulated thermoware at PT Langgeng Makmur Plastic Industry Ltd. | Individual | ASP | IDS | FOA | 23 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 142000 | -142000 | 0 | 0 |  | 0 | 0 | 0 | 18460 | -18460 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2001. |  | 1997 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nobough Industrial Co. | Individual | ASP | IRA | FOA | 32 | INV | 75 | A | I | CFC | 31.8 | 21 | 0 | 0 | 2000-12-01 | 2002-01-01 | 2004-01-01 |  |  | 2003-07-01 | 248736 | -198081 | 50655 | 50655 | 100% | 0 | 0 | 0 | 32335.68 | -25750.68 | 6585 | 0 | 0 | Canceled in 2003. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 91 | A | I | CFC | 4.7 | 4.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  |  | 2005-09-01 | 36801 | -3512 | 33289 | 33289 | 100% | 0 | 0 | 0 | 4784.13 | -457.13 | 4327 | 0 | 0 | Canceled in 2004. Financially completed in 2005. |  | 2001 |  | Investment
CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | AFR | ALG | FOA | 19 | INV | 13 | A | I | CFC | 82 | 82 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  |  | 2003-03-01 | 434500 | -564 | 433936 | 433936.34 | 100% | -0.34 | 0 |  | 56485 | -163 | 56322 | 0 | 0 | CLO
CLO | UNIDO | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Barlan Metal | Individual | EUR | TUR | FOA | 18 | INV | 18 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  |  | 1997-09-01 | 804050 | -802115 | 1935 | 1935 | 100% | 0 | 0 |  | 104527 | -104276 | 251 | 0 | 0 | CLO
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | I | CFC | 16.5 | 1.1 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119558 | 8829 | 8829 | 100% | 0 | 0 |  | 16690 | -15544 | 1146 | 0 | 0 | CLO
COM | IBRD | Conversion from HCFC-141b-based to HFC-245fa-based spray polyurethane foam at Harbin Tianshuo Building Materials Co. Ltd. | Individual | ASP | CPR | FOA | 59 | INV | 493 | N | I | HCFC | 1.7 | 1.7 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2012-11-30 |  | 193808 | 0 | 193808 | 88000 | 45.41% | 105808 | 105808 | 105808 | 14536 | 0 | 6600.18 | 7935.82 | 7935.82 | Project physically completed and enterprise has successfully converted technologies. Balance, representig IOC will be disbursed in 2013 after enterprise purchases HFC-245fa for fulfilling two contracts. |  |  | 2011-12-01 | INV
COM | UNDP | Terminal umbrella project for phase-out of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | CHI | FOA | 48 | INV | 161 | N | I | CFC | 51.4 | 51.4 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-09-01 |  | 2010-12-01 |  | 429962 | 0 | 429962 | 429961.88 | 100% | 0.12 | 0 | 0.096 | 32247 | 0 | 32246.991 | 0.009 | 0 | Equipment received and distributed to the companies. Installation and commissioning completed. Project substantially completed. |  | 2006 | 2009-09-01 | Investment
COM | UNDP | Pilot project for validation of methyl formate as a blowing agent in the manufacture of polyurethane foam (phase I) | Individual | LAC | BRA | FOA | 56 | DEM | 285 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-06-01 |  | 2010-12-01 |  | 401500 | 0 | 401500 | 375722.12 | 93.58% | 25777.88 | 0 | 20622.304 | 30113 | 0 | 28179.6269 | 1933.3731 | 0 | Completed. Report submitted to the 62nd Executive Committee Meeting and discussed by the Executive Committee members. Executive Committee decision requested UNDP to provide additional data collected to the 64th Meeting; however all substantive activities initially programmed were completed. |  | 2008 | 2010-08-01 | Non-Investment
COM | UNDP | Pilot project to validate methylal as blowing agent in the manufacture of polyurethane foams (phase I) | Individual | LAC | BRA | FOA | 58 | DEM | 292 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  | 2012-12-01 |  | 464200 | 0 | 464200 | 430395.43 | 92.72% | 33804.57 | 0 | 27043.656 | 34815 | 0 | 32279.6573 | 2535.3427 | 0 | Completed in 2012. Some final payments pending. Final report of the ML pilot project was submitted and adopted at ExCom 66. All substantial project activities have been completed. | Completed in 2012. Final payments for Technical Assistance and commissioning in 2012 have been completed and will be reflected in 2013. | 2009 |  | Non-Investment
FIN | France | Conversion to non-CFC technology in the manufacture of rigid foam (sandwich panels) at Kilzi and Co. Sarl |  | ASP | LEB | FOA | 20 | INV | 14 | A | I | CFC | 22.5 | 22.5 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-11-01 | 1999-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis. |  |  | 2000-01-01
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro | Individual | ASP | IRA | FOA | 37 | INV | 156 | A | I | CFC | 20.2 | 20.2 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 158166 | 0 | 158166 | 158166 | 100% | 0 | 0 | 0 | 20562 | 0 | 20562 | 0 | 0 | Project is completed. PCR was signed by NOU in June 2007 and submitted by end 2007.
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100% | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | All three foaming machines now installed and in routine operation. |  |  | 1999-06-01 | INV
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 07 | INV | 31 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-01-31 | INV
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 07 | INV | 23 | N | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | INV
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 07 | INV | 20 | N | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | INV
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 07 | INV | 30 | N | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-16 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100% | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100% | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | Project fully completed during the last trimester of 2002. PCR is being prepared. |  |  | 2002-12-01 | INV
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100% | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | Project has been financially completed. |  |  |  | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100% | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | Project has been fully executed. PCR is being revised for submission. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 |  | 2005-01-01 | 2005-08-01 | 584727 | -170557 | 414170 | 414170 | 100% | 0 | 0 |  | 74319.97 | -21678.14 | 52641.83 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100% | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100% | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | Physically completed. Draft PCR under review. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100% | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1995-06-01 | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100% | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100% | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 |  |  |  | 1999-04-01 | INV
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1996-03-01 | INV
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100% | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | Financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100% | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100% | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | Project physically and financially completed and PCR submitted. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100% | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 07 | INV | 16 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | 1996-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 31th ExCom. |  |  | 1997-02-01 | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100% | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100% | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  |  | INV
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100% | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100% | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100% | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100% | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100% | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | Project technically and financially completed. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100% | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | Project physically and financially completed |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100% | 0 | 0 |  | 20345 | -357.5 | 19987.5 | 0 | 0 | Project technically and financially completed. PCR draft being finalized. |  |  |  | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-05-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100% | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100% | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100% | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | INV
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 100% | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 100% | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-04-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-02-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100% | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. |  |  |  | INV
FIN | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 |  | 2006-10-01 | 2006-10-01 | 718900 | -161848 | 557052 | 557052 | 100% | 0 | 0 |  | 93457 | -21040.24 | 72416.76 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV
FIN | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | I | CFC | 239.6 | 239.6 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2006-10-01 | 2006-10-01 | 1600000 | -209475 | 1390525 | 1390525 | 100% | 0 | 0 |  | 208000 | -27231.75 | 180768.25 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100% | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2000-06-01 | INV
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100% | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100% | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100% | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100% | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | Project completed. PCR submitted to the WB in May/2000. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 | 2005-03-01 | 2003-08-01 |  | 2004-08-01 | 2005-03-01 | 177741 | -79622 | 98119 | 98119 | 100% | 0 | 0 |  | 23106.33 | -10350.86 | 12755.47 | 0 | 0 | Project physically and financially completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100% | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100% | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | Project Completed. PCR submitted to the WB in Jun/2000. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100% | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100% | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100% | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100% | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100% | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR approved by the WB in Jun/2000. |  |  | 1999-08-01 | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 2001-03-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100% | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2001-03-01 | INV
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100% | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | I | CFC | 7.5 | 7.5 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 59079 | -995.9 | 58083.1 | 58083.1 | 100% | 0 | 0 |  | 7680.27 | -129.47 | 7550.8 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | I | CFC | 8.3 | 8.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 64700 | -5970 | 58730 | 58730 | 100% | 0 | 0 |  | 8411 | -776.1 | 7634.9 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | I | CFC | 8.8 | 8.8 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 68917 | -4392 | 64525 | 64525 | 100% | 0 | 0 |  | 8959.21 | -570.96 | 8388.25 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | I | CFC | 11.7 | 11.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 91477 | -5148 | 86329 | 86329 | 100% | 0 | 0 |  | 11892.01 | -669.24 | 11222.77 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 156235 | -15623.5 | 140611.5 | 140611.5 | 100% | 0 | 0 |  | 20310.55 | -2031.06 | 18279.49 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100% | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100% | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | Project completed. |  |  |  | INV
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1999-11-01 | INV
FIN | IBRD | Conversion of the foam part of Jiangsu Huaiyin Huihuang Solar Co. Ltd. from HCFC-141b to cyclopentane | Individual | ASP | CPR | FOA | 59 | DEM | 492 | N | I | HCFC | 5.1 | 5.1 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 |  | 2012-11-30 | 2012-11-30 | 786668 | 0 | 786668 | 786668 | 100% | 0 | 0 |  | 59000 | 0 | 59000 | 0 | 0 | Project completed. |  |  |  | INV
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Bina Teknik Co. | Individual | ASP | IDS | FOA | 37 | INV | 146 | A | I | CFC-11 | 22.8 |  | 0 |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2006-03-01 | 2006-03-01 | 117889 | -541 | 117348 | 117348 | 100% | 0 | 0 | 0 | 15326 | -71 | 15255 | 0 | 0 | Project completed in March 2006. |  | 2002 |  | investment
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Aneka Citra Refrigeratama Co. | Individual | ASP | IDS | FOA | 37 | INV | 145 | A | I | CFC-11 | 18.2 | 18.2 | 0 |  | 2002-07-01 | 2004-11-01 | 2004-09-01 |  | 2005-12-01 | 2006-03-01 | 142506 | -377 | 142129 | 142129 | 100% | 0 | 0 | 0 | 18526 | -49 | 18477 | 0 | 0 | Project completed. |  | 2002 |  | investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | Individual | LAC | ARG | FOA | 34 | INV | 123 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-12-01 | 2005-09-01 | 147987 | -53810 | 94177 | 94177 | 100% | 0 | 0 | 0 | 19238.31 | -6995.31 | 12243 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria | Individual | LAC | ARG | FOA | 29 | INV | 95 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2000-12-01 | 2003-04-01 | 124025 | -221 | 123804 | 123804 | 100% | 0 | 0 | 0 | 16123.25 | -29.25 | 16094 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) | Individual | LAC | ARG | FOA | 29 | INV | 94 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 127392 | 0 | 127392 | 127392 | 100% | 0 | 0 | 0 | 16561 | 0 | 16561 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco | Individual | LAC | ARG | FOA | 26 | INV | 78 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-08-01 | 2001-12-01 | 210150 | -3022 | 207128 | 207128 | 100% | 0 | 0 | 0 | 27319.5 | -392.5 | 26927 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | Individual | LAC | ARG | FOA | 29 | INV | 96 | A | I | CFC | 43.9 | 43.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-11-01 | 2004-01-01 | 234409 | 0 | 234409 | 234409 | 100% | 0 | 0 | 0 | 30473 | 0 | 30473 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. | Individual | LAC | ARG | FOA | 18 | INV | 33 | A | I | CFC | 36.5 | 36.5 | 0 | 0 | 1995-11-01 | 1997-07-01 | 1996-11-01 |  | 2001-12-01 | 2003-04-01 | 285000 | -631 | 284369 | 284369 | 100% | 0 | 0 | 0 | 37050 | -82 | 36968 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1998-01-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | Individual | LAC | ARG | FOA | 32 | INV | 113 | A | I | CFC | 49.6 | 49.6 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 320332 | -90 | 320242 | 320242 | 100% | 0 | 0 | 0 | 41643.16 | -12.16 | 41631 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Paissan, Forever, Termica) | Individual | LAC | ARG | FOA | 34 | INV | 122 | A | I | CFC | 54.9 | 54.9 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2004-08-01 |  | 2005-01-01 | 2007-01-01 | 352896 | -12969 | 339927 | 339927 | 100% | 0 | 0 | 0 | 45876.48 | -1686.4824 | 44189.9976 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano | Individual | LAC | ARG | FOA | 23 | INV | 61 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 456500 | 0 | 456500 | 456500 | 100% | 0 | 0 | 0 | 59345 | 0 | 59345 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Calofrig Asilaciones Jacobi S.A.I.C. | Individual | LAC | ARG | FOA | 22 | INV | 57 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1999-06-01 |  | 2001-12-01 | 2003-04-01 | 563750 | 0 | 563750 | 563750 | 100% | 0 | 0 | 0 | 73288 | 0 | 73288 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of sandwich polyurethane panels at Cinter, S.R.L. | Individual | LAC | ARG | FOA | 15 | INV | 14 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 2001-12-01 | 2003-09-01 | 725000 | -32679 | 692321 | 692321 | 100% | 0 | 0 | 0 | 94250 | -4248 | 90002 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
FIN | UNDP | Foam sector ODS phaseout (two enterprises: Isolcruz and Teplo) | Individual | LAC | BOL | FOA | 35 | INV | 15 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-05-01 | 2007-01-01 | 161211 | -5875 | 155336 | 155336 | 100% | 0 | 0 | 0 | 20957.43 | -764.4343 | 20192.9957 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ananda | Individual | LAC | BRA | FOA | 28 | INV | 137 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2002-04-01 | 37380 | -14147 | 23233 | 23233 | 100% | 0 | 0 | 0 | 4859.4 | -1839.4 | 3020 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Packo Plurinox | Individual | LAC | BRA | FOA | 31 | INV | 179 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2000-12-01 | 2001-12-01 | 39750 | 0 | 39750 | 39750 | 100% | 0 | 0 | 0 | 5168 | 0 | 5168 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Posto de Molas Vivian, Ltda. (Posmovil) | Individual | LAC | BRA | FOA | 27 | INV | 130 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 44700 | 0 | 44700 | 44700 | 100% | 0 | 0 | 0 | 5811 | 0 | 5811 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fabrica De Carrocerias Farage, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 129 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 52770 | 0 | 52770 | 52770 | 100% | 0 | 0 | 0 | 6860 | 0 | 6860 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Transen | Individual | LAC | BRA | FOA | 34 | INV | 224 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 61940 | -1800 | 60140 | 60140 | 100% | 0 | 0 | 0 | 8052.2 | -234.2 | 7818 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Fibrasil Ind. Commercio de Carroceria Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 158 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-05-01 | 2003-09-01 | 93425 | -32890 | 60535 | 60535 | 100% | 0 | 0 | 0 | 12145.25 | -4275.25 | 7870 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refripor | Individual | LAC | BRA | FOA | 31 | INV | 185 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2001-12-01 | 2004-01-01 | 85350 | -16916 | 68434 | 68434 | 100% | 0 | 0 | 0 | 11095.5 | -2198.5 | 8897 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Tekcor Utilidades Domesticas Ltd. | Individual | LAC | BRA | FOA | 22 | INV | 70 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1998-07-01 | 2003-05-01 | 71600 | -2957 | 68643 | 68643 | 100% | 0 | 0 | 0 | 9308 | -384 | 8924 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at C.A. Cunha | Individual | LAC | BRA | FOA | 26 | INV | 113 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-11-01 | 70100 | 0 | 70100 | 70100 | 100% | 0 | 0 | 0 | 9113 | 0 | 9113 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Brasinj Ind. E Comm. | Individual | LAC | BRA | FOA | 29 | INV | 153 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 71253 | 0 | 71253 | 71253 | 100% | 0 | 0 | 0 | 9263 | 0 | 9263 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Dalla Rosa E Cia | Individual | LAC | BRA | FOA | 22 | INV | 68 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-05-01 |  | 1999-12-01 | 2001-12-01 | 71600 | 0 | 71600 | 71600 | 100% | 0 | 0 | 0 | 9308 | 0 | 9308 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Fast Frio | Individual | LAC | BRA | FOA | 23 | INV | 92 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in rigid polyurethane foam (spray and pour in place) at SIFC | Individual | LAC | BRA | FOA | 28 | INV | 143 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2000-11-01 | 2003-05-01 | 74385 | 0 | 74385 | 74385 | 100% | 0 | 0 | 0 | 9670 | 0 | 9670 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Conter Ind. e Isolantes Termocos, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 120 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 85347 | 0 | 85347 | 85347 | 100% | 0 | 0 | 0 | 11095 | 0 | 11095 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Aquedores Cumulus S.A. | Individual | LAC | BRA | FOA | 22 | INV | 69 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 86000 | -49 | 85951 | 85951 | 100% | 0 | 0 | 0 | 11180 | -6.0004 | 11173.9996 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for electrical resistance floats at Taurus | Individual | LAC | BRA | FOA | 34 | INV | 217 | A | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 88075 | 0 | 88075 | 88075 | 100% | 0 | 0 | 0 | 11450 | 0 | 11450 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam and sprayfoam at Calorisol | Individual | LAC | BRA | FOA | 29 | INV | 154 | A | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 91477 | -33 | 91444 | 91444 | 100% | 0 | 0 | 0 | 11892.01 | -4.01 | 11888 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to water based technology in the manufacture of polyurethane foam at Refratarios Isolamentos e Pinturas (RIP) | Individual | LAC | BRA | FOA | 25 | INV | 104 | A | I | CFC | 12 | 12 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-07-01 | 2003-04-01 | 94000 | -945 | 93055 | 93055 | 100% | 0 | 0 | 0 | 12220 | -123 | 12097 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | Individual | LAC | BRA | FOA | 36 | INV | 244 | A | I | CFC | 18 | 18 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2005-12-01 | 2007-03-01 | 98416 | -3 | 98413 | 98413 | 100% | 0 | 0 | 0 | 12794.08 | -0.079998 | 12794 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at Isoblock | Individual | LAC | BRA | FOA | 26 | INV | 112 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-04-01 | 106500 | -132 | 106368 | 106368 | 100% | 0 | 0 | 0 | 13845 | -17 | 13828 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of polyurethane foam at SSM Tecnologia | Individual | LAC | BRA | FOA | 25 | INV | 109 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2003-11-01 | 106500 | 0 | 106500 | 106500 | 100% | 0 | 0 | 0 | 13845 | 0 | 13845 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Intertelhas | Individual | LAC | BRA | FOA | 29 | INV | 150 | A | I | CFC | 48.9 | 48.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2000-12-01 | 2002-11-01 | 170074 | -62845 | 107229 | 107229 | 100% | 0 | 0 | 0 | 22109.62 | -8169.62 | 13940 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isolamento Termico Brasfoam Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 157 | A | I | CFC | 61.6 | 61.6 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 110200 | -2358 | 107842 | 107842 | 100% | 0 | 0 | 0 | 14326 | -307 | 14019 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Simonaggio | Individual | LAC | BRA | FOA | 36 | INV | 245 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-09-01 | 120383 | -10640 | 109743 | 109743 | 100% | 0 | 0 | 0 | 15649.79 | -1382.79 | 14267 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam for cold room panels, freezers and coolers at Central Equipment | Individual | LAC | BRA | FOA | 34 | INV | 225 | A | I | CFC | 15.1 | 15.1 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 118233 | -8399 | 109834 | 109834 | 100% | 0 | 0 | 0 | 15370.29 | -1092.29 | 14278 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibrart | Individual | LAC | BRA | FOA | 29 | INV | 144 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 111838 | 0 | 111838 | 111838 | 100% | 0 | 0 | 0 | 14539 | 0 | 14539 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Heliotek | Individual | LAC | BRA | FOA | 36 | INV | 246 | A | I | CFC | 27.4 | 27.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 127133 | -12221 | 114912 | 114912 | 100% | 0 | 0 | 0 | 16527.29 | -1588.29 | 14939 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for surfboards at Jedda | Individual | LAC | BRA | FOA | 34 | INV | 221 | A | I | CFC | 54 | 54 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 148272 | -32257 | 116015 | 116015 | 100% | 0 | 0 | 0 | 19275.36 | -4193.36 | 15082 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane sprayfoam at Isotherm Tratamento Thermo Acoustico Ltda. | Individual | LAC | BRA | FOA | 28 | INV | 131 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 116768 | 0 | 116768 | 116768 | 100% | 0 | 0 | 0 | 15180 | 0 | 15180 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at ACS Fibra | Individual | LAC | BRA | FOA | 29 | INV | 146 | A | I | CFC | 17.4 | 17.4 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 119336 | -2316 | 117020 | 117020 | 100% | 0 | 0 | 0 | 15513.68 | -300.68 | 15213 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoprice | Individual | LAC | BRA | FOA | 34 | INV | 237 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-12-01 | 2006-10-01 | 126846 | -9673 | 117173 | 117173 | 100% | 0 | 0 | 0 | 16489.98 | -1256.98 | 15233 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for display cabinets at Vacuum Systems | Individual | LAC | BRA | FOA | 29 | INV | 148 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2001-12-01 | 2003-09-01 | 117450 | -1 | 117449 | 117449 | 100% | 0 | 0 | 0 | 15268.5 | 0.5 | 15269 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manfuacture of rigid polyurethane foam at Jose Sola | Individual | LAC | BRA | FOA | 32 | INV | 198 | A | I | CFC | 38.7 | 38.7 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2002-11-01 | 2005-09-01 | 150369 | -24740 | 125629 | 125629 | 100% | 0 | 0 | 0 | 19547.97 | -3215.97 | 16332 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Plastiron | Individual | LAC | BRA | FOA | 32 | INV | 192 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 131768 | -5277 | 126491 | 126491 | 100% | 0 | 0 | 0 | 17129.84 | -685.84 | 16444 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isojet | Individual | LAC | BRA | FOA | 36 | INV | 247 | A | I | CFC | 47.4 | 47.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 130427 | 0 | 130427 | 130427 | 100% | 0 | 0 | 0 | 16956 | 0 | 16956 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam for ice cream makers and coolers at three enterprises (A.V. Bertollo, Citrocar, Systherm) | Individual | LAC | BRA | FOA | 34 | INV | 239 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-10-01 | 2005-12-01 | 135345 | -2457 | 132888 | 132888 | 100% | 0 | 0 | 0 | 17594.85 | -318.85 | 17276 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Bernini | Individual | LAC | BRA | FOA | 23 | INV | 82 | A | I | CFC | 22.9 | 22.9 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-11-01 | 135150 | 0 | 135150 | 135150 | 100% | 0 | 0 | 0 | 17570 | 0 | 17570 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refri-Leste | Individual | LAC | BRA | FOA | 32 | INV | 193 | A | I | CFC | 30 | 30 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-09-01 | 2003-04-01 | 136840 | -232 | 136608 | 136608 | 100% | 0 | 0 | 0 | 17789.2 | -30.2 | 17759 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Plastwork Embalagens da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 149 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 144855 | -1757 | 143098 | 143098 | 100% | 0 | 0 | 0 | 18831.15 | -228.15 | 18603 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Korta Calhas | Individual | LAC | BRA | FOA | 34 | INV | 231 | A | I | CFC | 75.7 | 75.7 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 151812 | 0 | 151812 | 151812 | 100% | 0 | 0 | 0 | 19736 | 0 | 19736 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water-based technology in the manufacture of rigid polyurethane foam at Polyfoam | Individual | LAC | BRA | FOA | 31 | INV | 169 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2003-10-01 | 2005-09-01 | 178873 | -23652 | 155221 | 155221 | 100% | 0 | 0 | 0 | 23253.49 | -3075.49 | 20178 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isar | Individual | LAC | BRA | FOA | 34 | INV | 226 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 174320 | -12870 | 161450 | 161450 | 100% | 0 | 0 | 0 | 22661.6 | -1672.6 | 20989 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Rytpak | Individual | LAC | BRA | FOA | 32 | INV | 190 | A | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-03-01 | 2003-04-01 | 211410 | -22300 | 189110 | 189110 | 100% | 0 | 0 | 0 | 27483.3 | -2899.3 | 24584 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibral | Individual | LAC | BRA | FOA | 36 | INV | 250 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-03-01 | 197613 | -1856 | 195757 | 195757 | 100% | 0 | 0 | 0 | 25689.69 | -240.6929 | 25448.9971 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HFC-141b in the manufacture of rigid polyurethane foam at Danko | Individual | LAC | BRA | FOA | 34 | INV | 234 | A | I | CFC | 41.4 | 41.4 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 199684 | -3328.9989 | 196355.0011 | 196355 | 100% | 0.0011 | 0 | 0 | 25958.92 | -432.9212 | 25525.9987 | 0.000143 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of polyurethane foam at Delta Pack | Individual | LAC | BRA | FOA | 25 | INV | 110 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 202500 | 0 | 202500 | 202500 | 100% | 0 | 0 | 0 | 26325 | 0 | 26325 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoeste | Individual | LAC | BRA | FOA | 34 | INV | 227 | A | I | CFC | 64.9 | 64.9 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2006-06-01 | 237296 | -33228 | 204068 | 204068 | 100% | 0 | 0 | 0 | 30848.48 | -4320.48 | 26528 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Politermo | Individual | LAC | BRA | FOA | 31 | INV | 182 | A | I | CFC | 50.2 | 50.2 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 219136 | -2808 | 216328 | 216328 | 100% | 0 | 0 | 0 | 28487.68 | -364.68 | 28123 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bulltrade | Individual | LAC | BRA | FOA | 23 | INV | 78 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 223000 | -358 | 222642 | 222642 | 100% | 0 | 0 | 0 | 28990 | -46.9979 | 28943.0021 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Thermoblock | Individual | LAC | BRA | FOA | 34 | INV | 218 | A | I | CFC | 41.1 | 41.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 260592 | -36386 | 224206 | 224206 | 100% | 0 | 0 | 0 | 33876.96 | -4729.96 | 29147 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Frigs | Individual | LAC | BRA | FOA | 32 | INV | 201 | A | I | CFC | 90 | 90 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 311056 | -73855 | 237201 | 237201 | 100% | 0 | 0 | 0 | 40437.28 | -9601.28 | 30836 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Termobras | Individual | LAC | BRA | FOA | 32 | INV | 195 | A | I | CFC | 77 | 77 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2003-08-01 | 2005-09-01 | 294590 | -39496 | 255094 | 255094 | 100% | 0 | 0 | 0 | 38296.7 | -5134.7 | 33162 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Metallurgica Barra | Individual | LAC | BRA | FOA | 22 | INV | 71 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1997-07-01 | 2000-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isosister | Individual | LAC | BRA | FOA | 36 | INV | 254 | A | I | CFC | 82.5 | 82.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2007-03-01 | 277668 | -6748 | 270920 | 270920 | 100% | 0 | 0 | 0 | 36096.84 | -876.8439 | 35219.9961 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at three enterprises: Brafer, Invicta and Therm-Jet | Individual | LAC | BRA | FOA | 19 | INV | 44 | A | I | CFC | 38 | 38 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-07-01 | 1999-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Madef/Isoltec | Individual | LAC | BRA | FOA | 19 | INV | 43 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-12-01 | 2001-12-01 | 346000 | -64202 | 281798 | 281798 | 100% | 0 | 0 | 0 | 44980 | -8346 | 36634 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water technology in the manufacture of rigid polyurethane foam at Ser Therm | Individual | LAC | BRA | FOA | 32 | INV | 197 | A | I | CFC | 72 | 72 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 359791 | -76117 | 283674 | 283674 | 100% | 0 | 0 | 0 | 46772.83 | -9894.83 | 36878 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Repor | Individual | LAC | BRA | FOA | 36 | INV | 256 | A | I | CFC | 50.8 | 50.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2008-04-01 | 323201 | -35934 | 287267 | 287267 | 100% | 0 | 0 | 0 | 42016.13 | -4671.13 | 37345 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Zenimont | Individual | LAC | BRA | FOA | 23 | INV | 95 | A | I | CFC | 38.1 | 38.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2001-04-01 | 2002-03-01 | 298300 | 0 | 298300 | 298300 | 100% | 0 | 0 | 0 | 38779 | 0 | 38779 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Polistecom | Individual | LAC | BRA | FOA | 23 | INV | 84 | A | I | CFC | 42.6 | 42.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 | 0 | 39390 | 0 | 39390 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Panisol, S.A. (Paineis Isolantes) | Individual | LAC | BRA | FOA | 20 | INV | 53 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 1999-12-01 | 2003-11-01 | 315958 | -41 | 315917 | 315917 | 100% | 0 | 0 | 0 | 41074.54 | -4.54 | 41070 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Therm-Jet (Belo Horizonte), Zenimont and Lavale (Sao Paulo) | Individual | LAC | BRA | FOA | 12 | INV | 13 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-03-01 | 1996-02-01 | 1995-03-01 |  | 1997-07-01 | 2000-12-01 | 370000 | -15282 | 354718 | 354718 | 100% | 0 | 0 | 0 | 48100 | -1987 | 46113 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for truck bodies and panels at 9 enterprises (ABC Furgoes, Fricam Refri, Junges, Rafaeli, Refri Santos, Rondofrio, Tresmaiense, Trevosul Refrig, Verde Lago Furgoes) | Individual | LAC | BRA | FOA | 34 | INV | 235 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-12-01 | 450479 | -69602 | 380877 | 380877 | 100% | 0 | 0 | 0 | 58562.27 | -9048.27 | 49514 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam for packaging and to HCFC-141b technology for insulation applications at World Pack da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 147 | A | I | CFC | 86.6 | 86.6 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-10-01 | 405610 | 0 | 405610 | 405610 | 100% | 0 | 0 | 0 | 52729 | 0 | 52729 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Isolenge | Individual | LAC | BRA | FOA | 22 | INV | 72 | A | I | CFC | 66 | 66 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-04-01 | 2000-12-01 | 516000 | -84186.38 | 431813.62 | 431814 | 100% | -0.38 | 0 | 0 | 67080 | -10943.9994 | 56136.05 | -0.0494 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam at Polsul Group | Individual | LAC | BRA | FOA | 28 | INV | 135 | A | I | CFC | 55 | 55 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2002-11-01 | 2006-10-01 | 536892 | -24390 | 512502 | 512502 | 100% | 0 | 0 | 0 | 69058.12 | -2683.12 | 66375 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Manilit, S.A. | Individual | LAC | COL | FOA | 29 | INV | 36 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2004-01-01 | 62230 | -679 | 61551 | 61551 | 100% | 0 | 0 | 0 | 8090 | -88 | 8002 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Dinalsa | Individual | LAC | COL | FOA | 29 | INV | 38 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78625 | 0 | 78625 | 78625 | 100% | 0 | 0 | 0 | 10221 | 0 | 10221 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Tianjin Relong Insulation Pipe Plant | Individual | ASP | CPR | FOA | 29 | INV | 314 | N | I | CFC | 11.9 | 11.9 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 93190 | -5957 | 87233 | 87233 | 100% | 0 | 0 | 0 | 12115 | -773.9992 | 11341.0008 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Taiyuan No. 2 Plastic Factory | Individual | ASP | CPR | FOA | 29 | INV | 316 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 1999-11-01 | 2002-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 127790 | -7057 | 120733 | 120733 | 100% | 0 | 0 | 0 | 16613 | -916.9968 | 15696.0032 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiaxing Anti-Corrosion Factory | Individual | ASP | CPR | FOA | 28 | INV | 290 | N | I | CFC | 19.4 | 19.4 | 0 | 0 | 1999-07-01 | 2000-10-01 | 2002-02-01 |  | 2002-05-01 | 2004-06-01 | 151590 | -6492 | 145098 | 145098 | 100% | 0 | 0 | 0 | 19706.7 | -843.7 | 18863 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Zhenjiang Feichi Automobile Group, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 315 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 223900 | -11388 | 212512 | 212512 | 100% | 0 | 0 | 0 | 29107 | -1481 | 27626 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Zhifu Zhenxing Polyurethane Materials Plant | Individual | ASP | CPR | FOA | 29 | INV | 325 | N | I | CFC | 36.3 | 36.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 261480 | -24023 | 237457 | 237457 | 100% | 0 | 0 | 0 | 33992.4 | -3123.4 | 30869 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Jiangsu Chemical Research Institute | Individual | ASP | CPR | FOA | 28 | INV | 289 | N | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2001-12-01 | 2004-06-01 | 253690 | -9289 | 244401 | 244401 | 100% | 0 | 0 | 0 | 32979.7 | -1207.7 | 31772 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFC-11 used in the manufacture of rigid polyurethane foam at Tianjin Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 13 | INV | 74 | N | I | CFC | 130 | 130 | 0 | 0 | 1994-07-01 | 1998-11-01 | 1995-07-01 |  | 2001-08-01 | 2003-07-01 | 690000 | -431333 | 258667 | 258667 | 100% | 0 | 0 | 0 | 89700 | -56073 | 33627 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Qingdao No. 10 Plastic Plant | Individual | ASP | CPR | FOA | 29 | INV | 334 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 298480 | -30327 | 268153 | 268153 | 100% | 0 | 0 | 0 | 38802 | -3943 | 34859 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid and spray polyurethane foams at Xinjiang Tianye Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 229 | N | I | CFC | 92.3 | 92.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 2001-01-01 | 2004-01-01 | 300620 | -15937 | 284683 | 284683 | 100% | 0 | 0 | 0 | 39080.6 | -2071.6 | 37009 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of rigid PUF (spray) at Beijing Commercial Machinery Factory (BCMF) | Individual | ASP | CPR | FOA | 11 | INV | 54 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1998-12-01 | 2000-12-01 | 435000 | -91690 | 343310 | 343310 | 100% | 0 | 0 | 0 | 56550 | -11920 | 44630 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Henan Bingxiong Refrigeration Truck Plant | Individual | ASP | CPR | FOA | 29 | INV | 313 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2004-06-01 | 440780 | -97144 | 343636 | 343636 | 100% | 0 | 0 | 0 | 57301.4 | -12629.3999 | 44672.0001 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2003-07-01 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels, pipes and spray foams at Baoding Oil Depot & Storage Engineering Company | Individual | ASP | CPR | FOA | 23 | INV | 228 | N | I | CFC | 75.5 | 75.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-09-01 | 400960 | -34986.33 | 365973.67 | 365974 | 100% | -0.33 | 0 | 0 | 52124.8 | -4548.8033 | 47576.0396 | -0.042899 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Fushan Anti-Corrosion Insulation Engineering Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 330 | N | I | CFC | 54.4 | 54.4 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2002-08-01 | 2004-06-01 | 425950 | -15465 | 410485 | 410485 | 100% | 0 | 0 | 0 | 55373.5 | -2009.5 | 53364 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Harbin Dongguang Machinery Plant | Individual | ASP | CPR | FOA | 29 | INV | 318 | N | I | CFC | 57.1 | 57.1 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 447170 | -23615.73 | 423554.27 | 423554 | 100% | 0.27 | 0 | 0 | 58132 | -3070.0014 | 55061.9635 | 0.0351 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hanfeng Polyurethane Company | Individual | ASP | CPR | FOA | 29 | INV | 312 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 440830 | -9007 | 431823 | 431823 | 100% | 0 | 0 | 0 | 57308 | -1171 | 56137 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Penglai Polyurethane Industry Co. | Individual | ASP | CPR | FOA | 28 | INV | 297 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2001-04-01 | 2003-07-01 | 497200 | -50527 | 446673 | 446673 | 100% | 0 | 0 | 0 | 64636 | -6569 | 58067 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Guangdong Commercial Refrigeration Equipment Co. (GCREC) | Individual | ASP | CPR | FOA | 26 | INV | 258 | N | I | CFC | 60.3 | 60.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-10-01 | 2003-07-01 | 472150 | -18041 | 454109 | 454109 | 100% | 0 | 0 | 0 | 61379.5 | -2344.5 | 59035 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Anqiu Polyurethane Materials Factory | Individual | ASP | CPR | FOA | 29 | INV | 332 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 497200 | -9710.12 | 487489.88 | 487490 | 100% | -0.12 | 0 | 0 | 64636 | -1262 | 63374.0156 | -0.0156 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Kaifeng Air Separation Group Ltd. (KFAS) | Individual | ASP | CPR | FOA | 26 | INV | 260 | N | I | CFC | 68.2 | 68.2 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-04-01 | 2001-11-01 | 534090 | -14357 | 519733 | 519733 | 100% | 0 | 0 | 0 | 68749.9 | -1578.9 | 67171 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Victory Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 25 | INV | 254 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-07-01 | 2001-11-01 | 2000-08-01 |  | 2003-11-01 | 2008-10-01 | 563760 | -273 | 563487 | 563487 | 100% | 0 | 0 | 0 | 73288.8 | -34.8001 | 73253.9999 | 0 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNDP | Conversion of refrigerator manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane foam blowing agent in the production of PU insulation panels | Individual | ASP | CPR | FOA | 26 | INV | 264 | N | I | CFC | 120.5 | 120.5 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-09-01 | 2005-02-01 | 617860 | -4968 | 612892 | 612892 | 100% | 0 | 0 | 0 | 77964.6 | -626.6 | 77338 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of PU-insulated heating pipes at Tianjin Pipeline Engineering Group Co. Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 257 | N | I | CFC | 80 | 80 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-09-01 | 2005-03-01 | 626400 | -346 | 626054 | 626054 | 100% | 0 | 0 | 0 | 78904 | -44 | 78860 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels at Luoyang Refrigeration Machinery Factory | Individual | ASP | CPR | FOA | 23 | INV | 236 | N | I | CFC | 117.8 | 117.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-01-01 | 2003-07-01 | 698595 | -41580 | 657015 | 657015 | 100% | 0 | 0 | 0 | 90817.35 | -5405.35 | 85412 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of heating pipes at Jixi City Thermal Power Company | Individual | ASP | CPR | FOA | 24 | INV | 245 | N | I | CFC | 86 | 86 | 0 | 0 | 1998-03-01 | 2000-12-01 | 2000-04-01 |  | 2003-12-01 | 2008-10-01 | 673380 | -3133 | 670247 | 670247 | 100% | 0 | 0 | 0 | 87539.4 | -407.3981 | 87132.0019 | 0 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and pour-in-place polyurethane foams at Corrosionproof and Insulation Co., Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 263 | N | I | CFC | 99.1 | 99.1 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-04-01 | 2004-01-01 | 776110 | -13913 | 762197 | 762197 | 100% | 0 | 0 | 0 | 95372.1 | -1530.1 | 93842 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Hengfeng Polyurethane Spray Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 286 | N | I | CFC | 154.1 | 154.1 | 0 | 0 | 1999-07-01 | 2001-06-01 | 2002-02-01 |  | 2003-09-01 | 2005-02-01 | 1206600 | -101036 | 1105564 | 1105564 | 100% | 0 | 0 | 0 | 142726 | -11114 | 131612 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and spray polyurethane foams at Daqing Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 26 | INV | 265 | N | I | CFC | 167.8 | 167.8 | 0 | 0 | 1998-11-01 | 2001-11-01 | 2001-06-01 |  | 2003-11-01 | 2009-01-01 | 1124560 | -618 | 1123942 | 1123942 | 100% | 0 | 0 | 0 | 133701.6 | -72.5957 | 133629.0043 | 0 | 0 | Completed in 2003.Financially completed in 2009. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Paredomi (Paneles Refrigerados Dominicanos, C.A.) | Individual | LAC | DOM | FOA | 29 | INV | 21 | A | I | CFC | 60.7 | 60.7 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-04-01 | 2003-09-01 | 177670 | 0 | 177670 | 177670 | 100% | 0 | 0 | 0 | 23097 | 0 | 23097 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of rigid polyurethane foam (PUF) at Specialized Engineering Contracting Co. | Individual | AFR | EGY | FOA | 11 | INV | 18 | A | I | CFC | 15 | 15 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1994-12-01 | 1998-12-01 | 85000 | -5398 | 79602 | 79602 | 100% | 0 | 0 | 0 | 11050 | -702 | 10348 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacturing of rigid PUF at seven enterprises: GMC, Petrojet, Modern Products, Cairo General Contractors Co., Egyptian Solar Energy, Tawifika, Helwan | Individual | AFR | EGY | FOA | 15 | INV | 36 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 2000-12-01 | 2002-11-01 | 780000 | -292655 | 487345 | 487345 | 100% | 0 | 0 | 0 | 101400 | -38045 | 63355 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded rigid polyurethane foam at Cairo Light Industries Co. (Olympic Electric) | Individual | AFR | EGY | FOA | 10 | INV | 17 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-12-01 |  | 1995-11-01 | 2000-12-01 | 940000 | -28083.76 | 911916.24 | 911916 | 100% | 0.24 | 0 | 0 | 122200 | -3650.9988 | 118548.97 | 0.0312 | 0 | Completed in 1995. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Construservicios, Aplitex, and Fiberglas & Plasticos | Individual | LAC | GUA | FOA | 23 | INV | 17 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 128500 | -15778 | 112722 | 112722 | 100% | 0 | 0 | 0 | 16705 | -2051 | 14654 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray foam) at PT Ferrarindo Multi Sarana | Individual | ASP | IDS | FOA | 23 | INV | 68 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-07-01 | 32900 | -315.94 | 32584.06 | 32584 | 100% | 0.06 | 0 | 0 | 4277 | -41.0022 | 4235.99 | 0.0078001 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Converstion to CFC-free technology in the manufacture of rigid polyurethane spray foam at Metal Tunggal Prakarsamandiri | Individual | ASP | IDS | FOA | 25 | INV | 89 | A | I | CFC | 8 | 8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2002-10-01 | 43330 | 0 | 43330 | 43330 | 100% | 0 | 0 | 0 | 5633 | 0 | 5633 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converstion to CFC-free technolgoy in the manufacture of rigid polyurethane spray foam at Karya Sempati Sarana | Individual | ASP | IDS | FOA | 25 | INV | 91 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2004-01-01 | 45550 | 0 | 45550 | 45550 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Mentari Metal Pratama | Individual | ASP | IDS | FOA | 20 | INV | 47 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-09-01 |  | 1999-11-01 | 2001-12-01 | 47000 | -693 | 46307 | 46307 | 100% | 0 | 0 | 0 | 6110 | -89.9951 | 6020.0049 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF foam for cold storage at P.T. Fibrindo Carsa Pratama | Individual | ASP | IDS | FOA | 17 | INV | 32 | A | I | CFC | 11 | 11 | 0 | 0 | 1995-07-01 | 1997-03-01 | 1996-06-01 |  | 1997-12-01 | 2000-07-01 | 55000 | -5382 | 49618 | 49618 | 100% | 0 | 0 | 0 | 7150 | -700 | 6450 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at Irama Sejuk Santosa | Individual | ASP | IDS | FOA | 26 | INV | 103 | A | I | CFC | 7 | 7 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 54800 | -4604 | 50196 | 50196 | 100% | 0 | 0 | 0 | 7124 | -599 | 6525 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated boxes at P.T. Polidaya Fiberindo Indah | Individual | ASP | IDS | FOA | 26 | INV | 106 | A | I | CFC | 9.3 | 9.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 72800 | -8363 | 64437 | 64437 | 100% | 0 | 0 | 0 | 9464 | -1087 | 8377 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF spray insulation at Karya Cipta Semesta | Individual | ASP | IDS | FOA | 23 | INV | 81 | A | I | CFC | 16.4 | 16.4 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-12-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Trisakti | Individual | ASP | IDS | FOA | 26 | INV | 100 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2003-03-01 | 80037 | -6557 | 73480 | 73480 | 100% | 0 | 0 | 0 | 10404.81 | -851.81 | 9553 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at PT Hanaria Indah | Individual | ASP | IDS | FOA | 26 | INV | 93 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 101352 | -18169 | 83183 | 83183 | 100% | 0 | 0 | 0 | 13175.76 | -2361.76 | 10814 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Alpine Cool | Individual | ASP | IDS | FOA | 20 | INV | 44 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 84000 | -268 | 83732 | 83732 | 100% | 0 | 0 | 0 | 10920 | -35 | 10885 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at PT Dilihan Glory | Individual | ASP | IDS | FOA | 23 | INV | 67 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 102200 | -14362 | 87838 | 87838 | 100% | 0 | 0 | 0 | 13286 | -1867 | 11419 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated panels at P.T. Panendra Sejati | Individual | ASP | IDS | FOA | 26 | INV | 95 | A | I | CFC | 20 | 20 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 156600 | -46830 | 109770 | 109770 | 100% | 0 | 0 | 0 | 20358 | -6088 | 14270 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF insulated products at UD Samrow Foam | Individual | ASP | IDS | FOA | 23 | INV | 63 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-10-01 | 2001-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Mentari Adi Fayar | Individual | ASP | IDS | FOA | 26 | INV | 101 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-01-01 | 2004-01-01 | 111517 | 0 | 111517 | 111517 | 100% | 0 | 0 | 0 | 14497 | 0 | 14497 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray foam) at PT Sentras Varitima | Individual | ASP | IDS | FOA | 25 | INV | 86 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 1998-07-01 | 1999-07-01 | 2000-08-01 |  | 2000-07-01 | 2002-03-01 | 125000 | -5780 | 119220 | 119220 | 100% | 0 | 0 | 0 | 16250 | -751 | 15499 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Laksana | Individual | ASP | IDS | FOA | 26 | INV | 97 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-11-01 | 2004-01-01 | 122885 | -3 | 122882 | 122882 | 100% | 0 | 0 | 0 | 15975 | 0 | 15975 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Mekar Armada Jaya | Individual | ASP | IDS | FOA | 26 | INV | 98 | A | I | CFC | 24.9 | 24.9 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 149357 | -6055 | 143302 | 143302 | 100% | 0 | 0 | 0 | 19416.41 | -787.41 | 18629 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for coolers/thermoware at P.T. Perdana Merah Delima | Individual | ASP | IDS | FOA | 18 | INV | 34 | A | R | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 1999-12-01 | 173000 | -1 | 172999 | 172999 | 100% | 0 | 0 | 0 | 22490 | 1.0186e-12 | 22490 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC -free technology in the manufacture of rigid polyurethane foam (panels, blocks) at PT Aneka Cool Citratama | Individual | ASP | IDS | FOA | 23 | INV | 65 | A | I | CFC | 32.7 | 32.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 232225 | -10678 | 221547 | 221547 | 100% | 0 | 0 | 0 | 30189.25 | -1388.25 | 28801 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam, panels, blocks) at Tansri Gani | Individual | ASP | IDS | FOA | 29 | INV | 112 | A | I | CFC | 45.3 | 45.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2003-03-01 | 2005-09-01 | 354700 | -5045 | 349655 | 349655 | 100% | 0 | 0 | 0 | 46111 | -656 | 45455 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2003-07-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Panna International | Individual | ASP | IND | FOA | 23 | INV | 151 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1998-12-01 | 2000-12-01 | 48000 | -19370 | 28630 | 28630 | 100% | 0 | 0 | 0 | 6240 | -2518 | 3722 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at R.S. Insulators | Individual | ASP | IND | FOA | 27 | INV | 205 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 54800 | -10912 | 43888 | 43888 | 100% | 0 | 0 | 0 | 7124 | -1419 | 5705 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Baba Insulator | Individual | ASP | IND | FOA | 27 | INV | 202 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 59096 | -10468 | 48628 | 48628 | 100% | 0 | 0 | 0 | 7682.48 | -1361.48 | 6321 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Naorang Plast | Individual | ASP | IND | FOA | 31 | INV | 260 | A | I | CFC | 13.5 | 13.5 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 53171 | -563 | 52608 | 52608 | 100% | 0 | 0 | 0 | 6912 | -73 | 6839 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Shree Nath Plastics | Individual | ASP | IND | FOA | 27 | INV | 207 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 61370 | -7114 | 54256 | 54256 | 100% | 0 | 0 | 0 | 7978.1 | -925.1 | 7053 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products at Omkar PUF Insulation | Individual | ASP | IND | FOA | 19 | INV | 73 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 59000 | -151.48 | 58848.52 | 58849 | 100% | -0.48 | 0 | 0 | 7670 | -20.0024 | 7650.06 | -0.062397 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Cottage Industries | Individual | ASP | IND | FOA | 20 | INV | 98 | A | I | CFC | 7.8 | 7.8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 61000 | -2047 | 58953 | 58953 | 100% | 0 | 0 | 0 | 7930 | -266 | 7664 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Deccan Engineering Enterprises | Individual | ASP | IND | FOA | 20 | INV | 100 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 64000 | -3303 | 60697 | 60697 | 100% | 0 | 0 | 0 | 8320 | -429 | 7891 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Sintex Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 187 | A | D | CFC | 10.9 | 10.9 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-11-01 | 2003-04-01 | 62980 | -1589 | 61391 | 61391 | 100% | 0 | 0 | 0 | 8187.4 | -207.4 | 7980 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Reliable Rotomoulders P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 150 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 63000 | -769 | 62231 | 62231 | 100% | 0 | 0 | 0 | 8190 | -100.0021 | 8089.9979 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bansal Plastic Industries | Individual | ASP | IND | FOA | 27 | INV | 198 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 68829 | -6240 | 62589 | 62589 | 100% | 0 | 0 | 0 | 8947.77 | -810.77 | 8137 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at O.K. Industries | Individual | ASP | IND | FOA | 28 | INV | 214 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 66227 | -2012 | 64215 | 64215 | 100% | 0 | 0 | 0 | 8609.51 | -261.51 | 8348 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ashoka Metals | Individual | ASP | IND | FOA | 28 | INV | 228 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2002-03-01 | 68066 | -1587 | 66479 | 66479 | 100% | 0 | 0 | 0 | 8848.58 | -205.58 | 8643 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Delta Foams Engineering Co. | Individual | ASP | IND | FOA | 22 | INV | 130 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 2001-12-01 | 85000 | -15226 | 69774 | 69774 | 100% | 0 | 0 | 0 | 11050 | -1979 | 9071 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Prince Plastoware Ltd. | Individual | ASP | IND | FOA | 34 | INV | 333 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2004-08-01 |  | 2002-06-01 | 2003-11-01 | 74010 | -3392 | 70618 | 70618 | 100% | 0 | 0 | 0 | 9621.3 | -441.3 | 9180 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plast | Individual | ASP | IND | FOA | 20 | INV | 97 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 71000 | -104 | 70896 | 70896 | 100% | 0 | 0 | 0 | 9230 | -13 | 9217 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam in situ and spray insulation at P.K. Construction Co. | Individual | ASP | IND | FOA | 27 | INV | 196 | A | D | CFC | 10.6 | 10.6 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 1999-12-01 | 2001-12-01 | 74172 | -3275 | 70897 | 70897 | 100% | 0 | 0 | 0 | 9642.36 | -426.36 | 9216 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ganga Thermoware | Individual | ASP | IND | FOA | 27 | INV | 197 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 78864 | -5388 | 73476 | 73476 | 100% | 0 | 0 | 0 | 10252.32 | -700.32 | 9552 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Apollo Steelcrafts | Individual | ASP | IND | FOA | 34 | INV | 324 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 76925 | -3129 | 73796 | 73796 | 100% | 0 | 0 | 0 | 10000.25 | -407.25 | 9593 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bluplast Corporation | Individual | ASP | IND | FOA | 23 | INV | 156 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ramakrishna Moulders | Individual | ASP | IND | FOA | 31 | INV | 258 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-12-01 | 2003-04-01 | 78479 | -1311 | 77168 | 77168 | 100% | 0 | 0 | 0 | 10202.27 | -170.27 | 10032 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Evershine Plastic Industry | Individual | ASP | IND | FOA | 31 | INV | 277 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 80060 | -2410 | 77650 | 77650 | 100% | 0 | 0 | 0 | 10407.8 | -312.8 | 10095 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Standard Electric Appliances | Individual | ASP | IND | FOA | 28 | INV | 212 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 78136 | 0 | 78136 | 78136 | 100% | 0 | 0 | 0 | 10158 | 0 | 10158 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam insulated thermoware at Ajay Corrugating and Plastics P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 193 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 80805 | 0 | 80805 | 80805 | 100% | 0 | 0 | 0 | 10505 | 0 | 10505 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lear Insulation Engineering P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 328 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 82567 | -1581.0037 | 80985.9963 | 80986 | 100% | -0.0037 | 0 | 0 | 10733.71 | -205.706 | 10528.0044 | -0.00048099 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Viral Corporation | Individual | ASP | IND | FOA | 23 | INV | 146 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 84000 | -2736 | 81264 | 81264 | 100% | 0 | 0 | 0 | 10920 | -356 | 10564 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bhatia Plastics | Individual | ASP | IND | FOA | 34 | INV | 335 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-03-01 | 2005-10-01 | 87070 | -5398.0037 | 81671.9963 | 81672 | 100% | -0.0037 | 0 | 0 | 11319.1 | -702.1043 | 10616.9962 | -0.00048098 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam at Puff Insulators | Individual | ASP | IND | FOA | 26 | INV | 184 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-11-01 | 2002-03-01 | 83150 | 0 | 83150 | 83150 | 100% | 0 | 0 | 0 | 10810 | 0 | 10810 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Supertek International | Individual | ASP | IND | FOA | 28 | INV | 211 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 83202 | 0 | 83202 | 83202 | 100% | 0 | 0 | 0 | 10816 | 0 | 10816 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nandadeep Fibrotech P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 329 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 88526 | -3277.9967 | 85248.0033 | 85248 | 100% | 0.0033 | 0 | 0 | 11508.38 | -426.3755 | 11082.0041 | 0.00042899 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at Jayson Industries | Individual | ASP | IND | FOA | 26 | INV | 189 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 88900 | -840 | 88060 | 88060 | 100% | 0 | 0 | 0 | 11557 | -108.9998 | 11448.0002 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at UNC Plast Industries | Individual | ASP | IND | FOA | 34 | INV | 304 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2007-02-01 | 89607 | -1142 | 88465 | 88465 | 100% | 0 | 0 | 0 | 11648.91 | -147.9111 | 11500.9989 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at SR Polymers and Printers | Individual | ASP | IND | FOA | 34 | INV | 325 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 95002 | -2969.9985 | 92032.0015 | 92032 | 100% | 0.0015 | 0 | 0 | 12350.26 | -386.2617 | 11963.9981 | 0.000195 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at M-Plast | Individual | ASP | IND | FOA | 31 | INV | 259 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 93279 | -451 | 92828 | 92828 | 100% | 0 | 0 | 0 | 12126.27 | -59.27 | 12067 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Best Plastronics P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 102 | A | I | CFC | 19.5 | 19.5 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 129000 | -35002 | 93998 | 93998 | 100% | 0 | 0 | 0 | 16770 | -4550 | 12220 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Mahavir Enterprises | Individual | ASP | IND | FOA | 19 | INV | 75 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 2000-08-01 | 2001-12-01 | 94500 | -220 | 94280 | 94280 | 100% | 0 | 0 | 0 | 12285 | -27.9976 | 12257.0024 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Polyrub Industries | Individual | ASP | IND | FOA | 34 | INV | 332 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 97953 | -3143.9956 | 94809.0044 | 94809 | 100% | 0.0044 | 0 | 0 | 12733.89 | -408.893 | 12324.9965 | 0.00057199 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plastic Products | Individual | ASP | IND | FOA | 19 | INV | 71 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2000-12-01 | 2002-03-01 | 96000 | -889 | 95111 | 95111 | 100% | 0 | 0 | 0 | 12480 | -116 | 12364 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Varivar Plast Products P., Ltd. | Individual | ASP | IND | FOA | 28 | INV | 210 | A | I | CFC | 12.3 | 12.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 96184 | -1 | 96183 | 96183 | 100% | 0 | 0 | 0 | 12503.92 | 0.08 | 12504 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Sanjay Industries | Individual | ASP | IND | FOA | 31 | INV | 261 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 99277 | -2381 | 96896 | 96896 | 100% | 0 | 0 | 0 | 12906.01 | -310.01 | 12596 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Roome Plastics P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 312 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 100546 | -2008 | 98538 | 98538 | 100% | 0 | 0 | 0 | 13070.98 | -260.98 | 12810 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at N.D. Plastics | Individual | ASP | IND | FOA | 28 | INV | 226 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2001-12-01 | 101289 | -802 | 100487 | 100487 | 100% | 0 | 0 | 0 | 13167.57 | -103.5657 | 13064.0043 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Mayur Jugs P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 235 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 119412 | -16905 | 102507 | 102507 | 100% | 0 | 0 | 0 | 15523.56 | -2197.56 | 13326 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crystal Electronics and Plastics | Individual | ASP | IND | FOA | 29 | INV | 237 | A | I | CFC | 18.3 | 18.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 123343 | -20723 | 102620 | 102620 | 100% | 0 | 0 | 0 | 16034.59 | -2694.59 | 13340 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC -141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Duab International | Individual | ASP | IND | FOA | 26 | INV | 190 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-12-01 | 2001-12-01 | 104490 | 0 | 104490 | 104490 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Essa Aircons Ltd. | Individual | ASP | IND | FOA | 34 | INV | 317 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 108837 | -2995.9981 | 105841.0019 | 105841 | 100% | 0.0019 | 0 | 0 | 14148.81 | -388.805 | 13760.0048 | 0.00024701 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crown Industries | Individual | ASP | IND | FOA | 31 | INV | 263 | A | I | CFC | 22.5 | 22.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 113110 | -4382 | 108728 | 108728 | 100% | 0 | 0 | 0 | 14704.3 | -570.3 | 14134 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Alaska Industries | Individual | ASP | IND | FOA | 23 | INV | 157 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 128000 | -18370 | 109630 | 109630 | 100% | 0 | 0 | 0 | 16640 | -2388 | 14252 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF spray insulation at Beardsell Ltd. | Individual | ASP | IND | FOA | 19 | INV | 80 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 1996-05-01 | 2000-05-01 | 1997-11-01 |  | 2000-11-01 | 2002-03-01 | 129000 | -19305 | 109695 | 109695 | 100% | 0 | 0 | 0 | 16770 | -2510 | 14260 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Devisons P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 219 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 114940 | -5215 | 109725 | 109725 | 100% | 0 | 0 | 0 | 14942.2 | -678.2 | 14264 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Nissan Thermoware P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 143 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 111000 | -706 | 110294 | 110294 | 100% | 0 | 0 | 0 | 14430 | -91.9976 | 14338.0024 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Santech Industries | Individual | ASP | IND | FOA | 29 | INV | 232 | A | I | CFC | 14.7 | 14.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 115101 | -9 | 115092 | 115092 | 100% | 0 | 0 | 0 | 14963.13 | -2.13 | 14961 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF insulated thermoware at Asha Handicrafts (formerly Asian Advertisers) | Individual | ASP | IND | FOA | 19 | INV | 78 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 122500 | -6656 | 115844 | 115844 | 100% | 0 | 0 | 0 | 15925 | -865 | 15060 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Blowkings | Individual | ASP | IND | FOA | 22 | INV | 128 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 132000 | -14394 | 117606 | 117606 | 100% | 0 | 0 | 0 | 17160 | -1871 | 15289 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products in Inalsa Ltd. | Individual | ASP | IND | FOA | 19 | INV | 72 | A | I | CFC | 28.9 | 28.9 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2000-12-01 | 123000 | -4222 | 118778 | 118778 | 100% | 0 | 0 | 0 | 15990 | -549 | 15441 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Saddle Poly Products P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 233 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 119087 | -44 | 119043 | 119043 | 100% | 0 | 0 | 0 | 15481.31 | -6.31 | 15475 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Amar Enterprises | Individual | ASP | IND | FOA | 20 | INV | 96 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 120000 | -57 | 119943 | 119943 | 100% | 0 | 0 | 0 | 15600 | -7.0004 | 15592.9996 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Enertech Engineering P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 268 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2004-01-01 | 123109 | -86 | 123023 | 123023 | 100% | 0 | 0 | 0 | 16004.17 | -11.17 | 15993 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at Ras Polybuild Products P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 158 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 128000 | -136 | 127864 | 127864 | 100% | 0 | 0 | 0 | 16640 | -18.0022 | 16621.9978 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Poly Glass Fibre Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 331 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-03-01 | 2005-10-01 | 134238 | -2570.9981 | 131667.0019 | 131667 | 100% | 0.0019 | 0 | 0 | 17450.94 | -333.9409 | 17116.9988 | 0.000247 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Caryaire Equipments India P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 326 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-07-01 | 2005-11-01 | 133509 | 0 | 133509 | 133509 | 100% | 0 | 0 | 0 | 17356 | 0 | 17356 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Malanpur Entech P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 153 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 148000 | -12388 | 135612 | 135612 | 100% | 0 | 0 | 0 | 19240 | -1610 | 17630 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated termoware at Jaypee Technoplast P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 186 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 139860 | -966 | 138894 | 138894 | 100% | 0 | 0 | 0 | 18181.8 | -125.8005 | 18055.9995 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Galaxy FRP P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 192 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 144808 | -1805 | 143003 | 143003 | 100% | 0 | 0 | 0 | 18825.04 | -235.04 | 18590 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Tokyo Plast International, Ltd. | Individual | ASP | IND | FOA | 29 | INV | 231 | A | I | CFC | 30.5 | 30.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-06-01 | 2003-11-01 | 196394 | -37676 | 158718 | 158718 | 100% | 0 | 0 | 0 | 25531.22 | -4898.22 | 20633 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Nav Texfeb P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 224 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 163982 | -3561 | 160421 | 160421 | 100% | 0 | 0 | 0 | 21317.66 | -462.66 | 20855 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at National Plastics | Individual | ASP | IND | FOA | 29 | INV | 239 | A | I | CFC | 36.2 | 36.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 212481 | -39605 | 172876 | 172876 | 100% | 0 | 0 | 0 | 27622.53 | -5148.53 | 22474 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Solvay Moulding P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 334 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-07-01 | 2005-09-01 | 196885 | -15868 | 181017 | 181017 | 100% | 0 | 0 | 0 | 25595.05 | -2063.05 | 23532 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at National Flask Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 188 | A | I | CFC | 36.9 | 36.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-08-01 | 2002-03-01 | 203870 | -16186 | 187684 | 187684 | 100% | 0 | 0 | 0 | 26503.1 | -2104.1 | 24399 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Super Urethane Products P. Ltd. | Individual | ASP | IND | FOA | 22 | INV | 132 | A | I | CFC | 39.1 | 39.1 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 284000 | -36531.9 | 247468.1 | 247468 | 100% | 0.1 | 0 | 0 | 36920 | -4748.997 | 32170.99 | 0.013 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Eagle Flasks Industries Ltd. | Individual | ASP | IND | FOA | 12 | INV | 18 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1995-03-01 |  | 1996-09-01 | 2000-12-01 | 365000 | -3745.35 | 361254.65 | 361255 | 100% | -0.35 | 0 | 0 | 47450 | -486.9955 | 46963.05 | -0.0455 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF panels at Sunpra Ltd. | Individual | ASP | IND | FOA | 12 | INV | 17 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 414000 | -43773 | 370227 | 370227 | 100% | 0 | 0 | 0 | 53820 | -5690 | 48130 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam chemical systems at Polymermann (Asia) P.Ltd. | Individual | ASP | IND | FOA | 22 | INV | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2003-11-01 | 385000 | -4930 | 380070 | 380070 | 100% | 0 | 0 | 0 | 50050 | -641 | 49409 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 1999-07-01 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at 17 small and medium-sized enterprises | Individual | ASP | IND | FOA | 34 | INV | 322 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-03-01 | 2004-12-01 | 417740 | 0 | 417740 | 417740 | 100% | 0 | 0 | 0 | 54306 | 0 | 54306 | 0 | 0 | Completed in 2004. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF products at Lloyd Insulations and Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 81 | A | I | CFC | 76.7 | 76.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-09-01 | 2000-12-01 | 500000 | -35882.96 | 464117.04 | 464117 | 100% | 0.04 | 0 | 0 | 65000 | -4665.0048 | 60334.99 | 0.0052 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 28 small and medium-sized enterprises | Individual | ASP | IND | FOA | 28 | INV | 229 | A | I | CFC | 105.7 | 105.7 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2002-12-01 | 2005-09-01 | 699139 | -39114 | 660025 | 660025 | 100% | 0 | 0 | 0 | 86905.29 | -4862.29 | 82043 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCF-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at 14 enterprises | Individual | ASP | IND | FOA | 34 | INV | 321 | A | I | CFC | 178.4 | 178.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-09-01 | 2005-11-01 | 759165 | -12566 | 746599 | 746599 | 100% | 0 | 0 | 0 | 93508.15 | -1382.15 | 92126 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 24 SMEs | Individual | ASP | IND | FOA | 29 | INV | 242 | A | I | CFC | 97.7 | 97.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2003-04-01 | 2006-10-01 | 886584 | -127666 | 758918 | 758918 | 100% | 0 | 0 | 0 | 107524.2 | -8865.24 | 98658.96 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at sixteen enterprises | Individual | ASP | IND | FOA | 31 | INV | 267 | A | I | CFC | 211.1 | 211.1 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 1094567 | -75293 | 1019274 | 1019274 | 100% | 0 | 0 | 0 | 130402.4 | -8282.37 | 122120.03 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam in small and medium-sized enterprises (SMEs) | Individual | ASP | IND | FOA | 22 | INV | 133 | A | I | CFC | 290 | 290 | 0 | 0 | 1997-05-01 | 1997-12-01 | 2000-06-01 |  | 2001-12-01 | 2003-03-01 | 1404000 | -79 | 1403921 | 1403921 | 100% | 0 | 0 | 0 | 182520 | -10 | 182510 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 2000-06-01 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | LIB | FOA | 32 | INV | 07 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2005-12-01 | 2008-04-01 | 119802 | -7675 | 112127 | 112127.23 | 100% | -0.23 | 0 | 0 | 15574.26 | -998.2633 | 14576.0266 | -0.029899 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at OAL Enterprise | Individual | ASP | MAL | FOA | 23 | INV | 107 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 58300 | -19611 | 38689 | 38689 | 100% | 0 | 0 | 0 | 7579 | -2549 | 5030 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at TM Cooling Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 70 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and blocks) at Polyedge Trading | Individual | ASP | MAL | FOA | 28 | INV | 122 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2002-02-01 |  | 2000-12-01 | 2001-12-01 | 80650 | 0 | 80650 | 80650 | 100% | 0 | 0 | 0 | 10485 | 0 | 10485 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free techology in the manufacture of polyurethane foam at Hi Tech Insulation | Individual | ASP | MAL | FOA | 23 | INV | 104 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2002-03-01 | 96815 | -3942 | 92873 | 92873 | 100% | 0 | 0 | 0 | 12585.95 | -511.95 | 12074 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of pipe insulation at Ricwil Sdn Bhd | Individual | ASP | MAL | FOA | 15 | INV | 47 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 118000 | -13464 | 104536 | 104536 | 100% | 0 | 0 | 0 | 15340 | -1750 | 13590 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Amstrad | Individual | ASP | MAL | FOA | 22 | INV | 94 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 108800 | -86 | 108714 | 108714 | 100% | 0 | 0 | 0 | 14144 | -11 | 14133 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Anchor Profit Sdn Bhd | Individual | ASP | MAL | FOA | 22 | INV | 95 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam decorative products at Florafoam Marketing Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 71 | A | D | CFC | 23 | 23 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1997-06-01 | 2000-12-01 | 152000 | -1 | 151999 | 151999 | 100% | 0 | 0 | 0 | 19760 | 1.0186e-12 | 19760 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Rollbond | Individual | ASP | MAL | FOA | 22 | INV | 96 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 155500 | 0 | 155500 | 155500 | 100% | 0 | 0 | 0 | 20215 | 0 | 20215 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Frank Chee | Individual | ASP | MAL | FOA | 23 | INV | 106 | A | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 174350 | 0 | 174350 | 174350 | 100% | 0 | 0 | 0 | 22666 | 0 | 22666 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels and shipyard insulation works at Leading Refrigeration and Engineering, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 50 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 214000 | -13246 | 200754 | 200754 | 100% | 0 | 0 | 0 | 27820 | -1722 | 26098 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam for use as imitation wood at Saferay (M) SDN BHD | Individual | ASP | MAL | FOA | 15 | INV | 46 | A | I | CFC | 11 | 11 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1997-06-01 | 1998-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of polyurethane foam for pipe insulation at Allied Foam Insulation | Individual | ASP | MAL | FOA | 13 | INV | 43 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 276000 | -2955 | 273045 | 273045 | 100% | 0 | 0 | 0 | 35880 | -384 | 35496 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane insulation foam at Insafoam Insulation Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 16 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 310000 | -3393 | 306607 | 306607 | 100% | 0 | 0 | 0 | 40300 | -441 | 39859 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Termopuertos | Individual | LAC | MEX | FOA | 22 | INV | 57 | A | D | CFC | 10 | 10 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-07-01 | 2000-12-01 | 78300 | -2557 | 75743 | 75743 | 100% | 0 | 0 | 0 | 10179 | -332 | 9847 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Carmovil | Individual | LAC | MEX | FOA | 20 | INV | 48 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 80500 | -1092 | 79408 | 79408 | 100% | 0 | 0 | 0 | 10465 | -142 | 10323 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technolog in the manufacture of rigid foam at Valsa Panel | Individual | LAC | MEX | FOA | 23 | INV | 66 | A | D | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1998-07-01 | 2000-12-01 | 92000 | -312 | 91688 | 91688 | 100% | 0 | 0 | 0 | 11960 | -41 | 11919 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Paneles | Individual | LAC | MEX | FOA | 18 | INV | 41 | A | I | CFC | 81 | 81 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1997-08-01 | 2000-12-01 | 100000 | -5098.2 | 94901.8 | 94902 | 100% | -0.2 | 0 | 0 | 13000 | -662.996 | 12337.03 | -0.026 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels at Galvamet, S.A. de C.V. | Individual | LAC | MEX | FOA | 18 | INV | 42 | A | D | CFC | 88.7 | 88.7 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1996-04-01 | 1998-12-01 | 195500 | -6004.42 | 189495.58 | 189496 | 100% | -0.42 | 0 | 0 | 25415 | -781.0046 | 24634.05 | -0.054599 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Group Project Valcom (Uriel, Limas, Tecknipol, Anzaldua, and Negrete) | Individual | LAC | MEX | FOA | 26 | INV | 87 | A | I | CFC | 44.3 | 44.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-08-01 | 2002-11-01 | 314961 | -3630 | 311331 | 311331 | 100% | 0 | 0 | 0 | 40944.93 | -471.93 | 40473 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels and doors at Multypanel | Individual | LAC | MEX | FOA | 19 | INV | 46 | A | I | CFC | 306 | 306 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-08-01 | 2001-12-01 | 428000 | -85788.58 | 342211.42 | 342211 | 100% | 0.42 | 0 | 0 | 55640 | -11152.9954 | 44486.95 | 0.054599 | 0 | Completed in 1997. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Tecnopolimeros | Individual | LAC | MEX | FOA | 22 | INV | 56 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2002-11-01 | 359000 | -1642 | 357358 | 357358 | 100% | 0 | 0 | 0 | 46670 | -213 | 46457 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) - Group project (10 enterprises) | Individual | LAC | MEX | FOA | 19 | INV | 47 | A | I | CFC | 100 | 100 | 0 | 0 | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1998-11-01 | 2001-08-01 | 507500 | -43764 | 463736 | 463736 | 100% | 0 | 0 | 0 | 65975 | -5689 | 60286 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Acsa | Individual | LAC | MEX | FOA | 22 | INV | 54 | A | I | CFC | 94.4 | 94.4 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 597000 | -1890 | 595110 | 595110 | 100% | 0 | 0 | 0 | 77610 | -245 | 77365 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at group project Pumex | Individual | LAC | MEX | FOA | 23 | INV | 69 | A | I | CFC | 167.7 | 167.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 1133881 | -20532 | 1113349 | 1113349 | 100% | 0 | 0 | 0 | 147404.5 | -2668.53 | 144735.97 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Engequife by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 44 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 56391 | -146.41 | 56244.59 | 56245 | 100% | -0.41 | 0 | 0 | 7330.83 | -18.8337 | 7312.0496 | -0.053301 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion to HCFC-141b/water technology in the manufacture of rigid polyurethane spray foam at Batcomar S.A. | Individual | AFR | MOR | FOA | 25 | INV | 23 | A | I | CFC | 9.2 | 9.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-07-01 | 2002-03-01 | 72000 | -10826 | 61174 | 61174 | 100% | 0 | 0 | 0 | 9360 | -1407 | 7953 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Interfer by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 43 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 78973 | 0 | 78973 | 78973 | 100% | 0 | 0 | 0 | 10266 | 0 | 10266 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam at Panaf Isolation S.A. | Individual | AFR | MOR | FOA | 23 | INV | 15 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-09-01 | 2001-12-01 | 137000 | -3191 | 133809 | 133809 | 100% | 0 | 0 | 0 | 17810 | -415 | 17395 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manuyfacture of rigid PUF insulation products at Aluminium Manufacturing Company of Nigeria Plc (Alumaco) | Individual | AFR | NIR | FOA | 23 | INV | 26 | A | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-12-01 |  | 2001-11-01 | 2002-11-01 | 38000 | -400 | 37600 | 37600 | 100% | 0 | 0 | 0 | 4940 | -52 | 4888 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF spray insulation at Polyurethane Manufacturers Ltd. (Polyma) | Individual | AFR | NIR | FOA | 23 | INV | 29 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2004-01-01 | 80500 | -339 | 80161 | 80161 | 100% | 0 | 0 | 0 | 10465 | -44 | 10421 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Adig Plastics Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 86 | A | I | CFC | 14.3 | 14.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-04-01 | 112050 | 0 | 112050 | 112050 | 100% | 0 | 0 | 0 | 14567 | 0 | 14567 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Celplas Industries Limited | Individual | AFR | NIR | FOA | 31 | INV | 67 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-11-01 | 2002-12-01 | 215325 | 0 | 215325 | 215325 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Agric Services (Nig.), Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 95 | A | I | CFC | 43.7 | 43.7 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-08-01 | 2005-10-01 | 239160 | -262.9963 | 238897.0037 | 238897 | 100% | 0.0037 | 0 | 0 | 31090.8 | -33.7997 | 31056.9998 | 0.00048101 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam for thermoware in Eleganza Industries Ltd. at Ikeja, Lagos | Individual | AFR | NIR | FOA | 20 | INV | 14 | A | I | CFC | 48.3 | 48.3 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 314000 | -4065 | 309935 | 309935 | 100% | 0 | 0 | 0 | 40820 | -528 | 40292 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for thermoware in 3 enterprises of the Eleganza Group (Eleganza Cooler and Household Industries Ltd., Eleganza Ceramics and Cooler Industries Ltd.) | Individual | AFR | NIR | FOA | 23 | INV | 27 | A | I | CFC | 73.8 | 73.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 568000 | -25762 | 542238 | 542238 | 100% | 0 | 0 | 0 | 73840 | -3349 | 70491 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Umbrella project: Conversion to CFC-free technology in small CFC consuming enterprises using CFC in the manufacture of rigid polyurethane foam (Ashlar Industrial Corporation, Alen International, Zegal | Individual | ASP | PHI | FOA | 23 | INV | 52 | N | I | CFC | 5.1 | 5.1 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 39930 | -13985 | 25945 | 25945 | 100% | 0 | 0 | 0 | 5190.9 | -1817.9 | 3373 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at MBA Urethane Products Contractor | Individual | ASP | PHI | FOA | 22 | INV | 50 | N | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 1999-12-01 | 2003-08-01 | 113574 | -22017 | 91557 | 91557 | 100% | 0 | 0 | 0 | 14764.62 | -2861.62 | 11903 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of the use of CFCs in the manufacture of PU foam for insulation and structural purposes at Himalaya Mfg. Corp. | Individual | ASP | PHI | FOA | 19 | INV | 43 | A | D | CFC | 17 | 17 | 0 | 0 | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 101000 | -4879 | 96121 | 96121 | 100% | 0 | 0 | 0 | 13130 | -634 | 12496 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture or rigid polyurethane foam (sprayfoam) at Prescon Construction and Development | Individual | ASP | PHI | FOA | 31 | INV | 64 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-10-01 |  | 2002-09-01 | 2005-04-01 | 187926 | -25246 | 162680 | 162680 | 100% | 0 | 0 | 0 | 24430.38 | -3282.38 | 21148 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at PU Rigid Insulation Contractor | Individual | ASP | PHI | FOA | 22 | INV | 48 | N | I | CFC | 24.2 | 24.2 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1999-06-01 |  | 1999-12-01 | 2003-11-01 | 189290 | -14221 | 175069 | 175069 | 100% | 0 | 0 | 0 | 24607.7 | -1848.7 | 22759 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Nikkon Industrial Corporation | Individual | ASP | PHI | FOA | 12 | INV | 28 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-09-01 | 1998-12-01 | 315000 | -46523 | 268477 | 268477 | 100% | 0 | 0 | 0 | 40950 | -6048 | 34902 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of polyurethane insulated building elements at Metal Forming Co. | Individual | ASP | PHI | FOA | 13 | INV | 32 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 305000 | -16698 | 288302 | 288302 | 100% | 0 | 0 | 0 | 39650 | -2171 | 37479 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Century Plastics | Individual | ASP | THA | FOA | 23 | INV | 75 | A | D | CFC | 7.3 | 7.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2001-12-01 | 56750 | -2559.77 | 54190.23 | 54190 | 100% | 0.23 | 0 | 0 | 7377.5 | -332.7701 | 7044.7 | 0.0299 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.S. Plastic Container L.P. | Individual | ASP | THA | FOA | 29 | INV | 123 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 75951 | 0 | 75951 | 75951 | 100% | 0 | 0 | 0 | 9873.63 | 0 | 9873.63 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Thai Steel Door L.P. | Individual | ASP | THA | FOA | 28 | INV | 117 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at S.K. Container Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 119 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lohr Trade and Consulting PTS Ltd. | Individual | ASP | THA | FOA | 26 | INV | 103 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 93210 | -137 | 93073 | 93073 | 100% | 0 | 0 | 0 | 12117.3 | -17.813 | 12099.487 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Urethane | Individual | ASP | THA | FOA | 26 | INV | 99 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2001-12-01 | 2004-01-01 | 98645 | 0 | 98645 | 98645 | 100% | 0 | 0 | 0 | 12823.85 | 0 | 12823.85 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ohm Intertrade L.P. | Individual | ASP | THA | FOA | 26 | INV | 106 | A | I | CFC | 19 | 19 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2002-03-01 | 146350 | -6393 | 139957 | 139957 | 100% | 0 | 0 | 0 | 19025.5 | -831.09 | 18194.41 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUR foam for thermoware at Raengwa Standard Industry Co. Ltd. | Individual | ASP | THA | FOA | 19 | INV | 51 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-01-01 | 2000-12-01 | 181500 | -796 | 180704 | 180704 | 100% | 0 | 0 | 0 | 23595 | -103.48 | 23491.52 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siam Matee | Individual | ASP | THA | FOA | 20 | INV | 56 | A | I | CFC | 33.9 | 33.9 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1998-09-01 |  | 1998-09-01 | 2001-12-01 | 198000 | -13800.8 | 184199.2 | 184199 | 100% | 0.2 | 0 | 0 | 25740 | -1794.104 | 23945.87 | 0.026 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Asia Container | Individual | ASP | THA | FOA | 22 | INV | 64 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1999-11-01 | 2000-12-01 | 199000 | 0 | 199000 | 199000 | 100% | 0 | 0 | 0 | 25870 | 0 | 25870 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siriphan | Individual | ASP | THA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-09-01 | 2001-12-01 | 215000 | -5001 | 209999 | 209999 | 100% | 0 | 0 | 0 | 27950 | -650.13 | 27299.87 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Sahakij Comos L.P. | Individual | ASP | THA | FOA | 26 | INV | 101 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 255850 | -11488 | 244362 | 244362 | 100% | 0 | 0 | 0 | 33260.5 | -1493.44 | 31767.06 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of laminated rigid polyurethane foam for insulation panels at Henger Panel | Individual | ASP | THA | FOA | 12 | INV | 31 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-06-01 | 2000-12-01 | 257500 | -509 | 256991 | 256991 | 100% | 0 | 0 | 0 | 33475 | -66.17 | 33408.83 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Dacron Trade Co. | Individual | ASP | THA | FOA | 20 | INV | 55 | A | I | CFC | 47.6 | 47.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-11-01 | 2001-12-01 | 277800 | -19551 | 258249 | 258249 | 100% | 0 | 0 | 0 | 36114 | -2541.63 | 33572.37 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Ocean Plastics | Individual | ASP | THA | FOA | 22 | INV | 67 | A | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 287000 | -16390 | 270610 | 270610 | 100% | 0 | 0 | 0 | 37310 | -2130.7 | 35179.3 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Suwan Polymer L.P. | Individual | ASP | THA | FOA | 26 | INV | 100 | A | I | CFC | 58 | 58 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 298370 | -1026 | 297344 | 297344 | 100% | 0 | 0 | 0 | 38788.1 | -133.38 | 38654.72 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUF foam for thermoware at Krieng Thavorn Containers Co. Ltd. | Individual | ASP | THA | FOA | 18 | INV | 47 | A | I | CFC | 65 | 65 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 430000 | -32154 | 397846 | 397846 | 100% | 0 | 0 | 0 | 55900 | -4180.02 | 51719.98 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of laminated rigid polyurethane foam insulation panels at Modular Compound Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 29 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1996-12-01 | 2000-12-01 | 508000 | -3349 | 504651 | 504651 | 100% | 0 | 0 | 0 | 66040 | -435.37 | 65604.63 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 06 | N | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Beni Mansour | Individual | AFR | ALG | FOA | 19 | INV | 14 | A | I | CFC | 110 | 110 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 1998-12-01 | 2003-03-01 | 496650 | 0 | 496650 | 496649.82 | 100% | 0.18 | 0 |  | 64565 | -78 | 64487 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. | Individual | LAC | ARG | FOA | 28 | INV | 110 | A | I | CFC | 26.8 | 26.8 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2001-06-01 | 2002-11-01 | 111641 | -69 | 111572 | 111571.66 | 100% | 0.34 | 0 |  | 14513 | -32 | 14481 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) | Individual | LAC | ARG | FOA | 29 | INV | 97 | A | I | CFC | 30.4 | 30.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2001-06-01 | 2002-09-01 | 227048 | 0 | 227048 | 227048.01 | 100% | -0.01 | 0 |  | 29516 | -7 | 29509 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios Maximo; Baduco D and D; Bolatti; Hi-Tec Poliuretano Alberto; Najera Jose; Stefanelli Vincer, SRL) | Individual | LAC | ARG | FOA | 32 | INV | 117 | A | I | CFC | 46.1 | 46.1 |  |  | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-06-01 | 2004-09-01 | 329495 | 0 | 329495 | 329495.03 | 100% | -0.03 | 0 |  | 42834 | -36 | 42798 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Individual | EUR | BHE | FOA | 39 | INV | 15 | A | I | CFC | 33 | 33 |  |  | 2003-04-01 | 2004-04-01 | 2004-07-01 |  | 2006-12-01 | 2009-05-01 | 364650 | -15 | 364635 | 364634.54 | 100% | 0.46 | 0 |  | 27349 | -1 | 27348 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Danica Co. | Individual | LAC | BRA | FOA | 34 | INV | 222 | A | I | CFC | 146.6 | 146.6 |  |  | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2004-02-01 | 2004-06-01 | 616625 | 0 | 616625 | 616625.24 | 100% | -0.24 | 0 |  | 77829 | -84 | 77745 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | Individual | ASP | CPR | FOA | 32 | INV | 369 | A | I | CFC | 891.4 | 891.4 |  |  | 2000-12-01 | 2001-07-01 | 2003-07-01 |  | 2004-12-01 | 2006-09-01 | 3295600 | 2025174 | 5320774 | 5320774.18 | 100% | -0.18 | 0 |  | 372516 | 232769 | 605285 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Elimination of CFC-11 in manufacturing of PU rigid foam for insulation at 31 enterprises | Individual | ASP | CPR | FOA | 29 | INV | 306 | A | I | CFC | 707.3 | 707.3 |  |  | 1999-11-01 | 2000-04-01 | 2002-06-01 |  | 2003-01-01 | 2004-04-01 | 5516900 | 0 | 5516900 | 5516900.42 | 100% | -0.42 | 0 |  | 616859 | -430 | 616429 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Delta Atlantik and Samudra Plastics | Individual | ASP | IDS | FOA | 38 | INV | 152 | A | I | CFC | 18.8 | 18.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2004-11-01 | 2006-05-01 | 146388 | 0 | 146388 | 146387.89 | 100% | 0.11 | 0 |  | 19030 | -10 | 19020 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid insulation foam parts at two companies: PT Morodadi Prima and PT Tentrem Industri Karosseri | Individual | ASP | IDS | FOA | 36 | INV | 143 | A | I | CFC | 25.5 | 25.5 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-11-01 | 2007-04-01 | 164947 | -567 | 164380 | 164379.96 | 100% | 0.04 | 0 |  | 21443 | -74 | 21369 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project to phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Ganesha Rattesko and Sindari Nusatama | Individual | ASP | IDS | FOA | 38 | INV | 150 | A | I | CFC | 52 | 52 |  |  | 2002-11-01 | 2003-12-01 | 2005-06-01 |  | 2005-12-01 | 2006-12-01 | 283490 | -101 | 283389 | 283389.34 | 100% | -0.34 | 0 |  | 36854 | -13 | 36841 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Yakhchavan Co. | Individual | ASP | IRA | FOA | 37 | INV | 155 | A | I | CFC | 73.6 | 73.6 |  |  | 2002-07-01 | 2002-11-01 | 2005-03-01 |  | 2005-12-01 | 2008-12-01 | 531838 | -7193 | 524645 | 524645.32 | 100% | -0.32 | 0 |  | 68502 | -791 | 67711 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | Individual | ASP | IRA | FOA | 31 | INV | 73 | A | I | CFC | 70 | 70 |  |  | 2000-07-01 | 2001-04-01 | 2003-01-01 |  | 2005-07-01 | 2005-12-01 | 539882 | 0 | 539882 | 539882.07 | 100% | -0.07 | 0 |  | 69387 | -79 | 69308 | 0 | 0 | FIN
FIN | UNIDO | DBL project Iran. Phasing out CFC-11 through conversion of rigid PU-foam manufactured with the technique of continuous lamination at Fabis, Iran Steel, Mammoth Tehran, F.M., and Urethane Systems | Individual | ASP | IRA | FOA | 17 | INV | 11 | A | I | CFC | 1200 | 1200 |  |  | 1995-07-01 | 1995-12-01 | 1997-07-01 |  | 1998-12-01 | 2003-05-01 | 2571250 | 0 | 2571250 | 2571249.92 | 100% | 0.08 | 0 |  | 334263 | -361 | 333902 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the insulation of GRP fish boxes and flotation buoys at C.C. Chong Co. | Individual | ASP | MAL | FOA | 26 | INV | 112 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-11-01 | 1999-03-01 | 2000-06-01 |  | 2000-05-01 | 2001-09-01 | 34583 | 0 | 34583 | 34583.03 | 100% | -0.03 | 0 |  | 4496 | -1 | 4495 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology at Automated Plastic System Sdn. Bhd. in the manufacture of insulated fishing boxes | Individual | ASP | MAL | FOA | 28 | INV | 125 | A | I | CFC | 5.2 | 5.2 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-01-01 | 2001-12-01 | 40716 | 0 | 40716 | 40716.48 | 100% | -0.48 | 0 |  | 5293 | 0 | 5293 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption by conversion to HCFC-141b AT Perniagaan Hower in the manufacture of sandwich panels | Individual | ASP | MAL | FOA | 28 | INV | 124 | A | I | CFC | 5.3 | 5.3 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 41499 | -87 | 41412 | 41412.44 | 100% | -0.44 | 0 |  | 5395 | -20 | 5375 | 0 | 0 | FIN
FIN | UNIDO | The replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Ming Soon Enterprise Sdn. Bhd. | Individual | ASP | MAL | FOA | 26 | INV | 113 | A | I | CFC | 6.2 | 6.23 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-02-01 | 2002-09-01 | 48799 | 0 | 48799 | 48798.94 | 100% | 0.06 | 0 |  | 6344 | -8 | 6336 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Composites Truck Body Sdn., Bhd. | Individual | ASP | MAL | FOA | 34 | INV | 143 | A | I | CFC | 8.1 | 8.1 |  |  | 2001-07-01 | 2002-12-01 | 2004-02-01 |  | 2003-12-01 | 2003-12-01 | 63280 | -129 | 63151 | 63150.56 | 100% | 0.44 | 0 |  | 8226 | -29 | 8197 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out ODS at Summer Technologies Sdn. Bhd. | Individual | ASP | MAL | FOA | 23 | INV | 100 | A | I | CFC | 12.1 | 12.1 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 89407 | 0 | 89407 | 89407.11 | 100% | -0.11 | 0 |  | 11623 | 0 | 11623 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Kean Chong Industries Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 101 | A | I | CFC | 16.3 | 16.3 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-11-23 | 107819 | 0 | 107819 | 107819 | 100% | 0 | 0 |  | 14016 | 0 | 14016 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Visdamax Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 102 | A | I | CFC | 18.5 | 18.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 139959 | 0 | 139959 | 139958.67 | 100% | 0.33 | 0 |  | 18195 | 0 | 18195 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from manufacturing of rigid PU sandwich panels at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 06 | A | I | CFC | 67.6 | 67.6 |  |  | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1997-12-01 | 2002-05-01 | 284236 | -6661 | 277575 | 277574.83 | 100% | 0.17 | 0 |  | 36951 | -923 | 36028 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | Individual | ASP | SYR | FOA | 32 | INV | 68 | A | I | CFC | 16.4 | 16.4 |  |  | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2005-12-01 | 2006-12-01 | 126862 | -2164 | 124698 | 124697.51 | 100% | 0.49 | 0 |  | 16492 | -281 | 16211 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to cyclopenthane in the production of rigid foam panels at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 31 | INV | 61 | A | I | CFC | 61.1 | 61.1 |  |  | 2000-07-01 | 2001-04-01 | 2002-08-01 |  | 2004-10-01 | 2005-04-01 | 426104 | 0 | 426104 | 426103.9 | 100% | 0.1 | 0 |  | 55394 | -46 | 55348 | 0 | 0 | FIN |  |  | 2003-11-01
FIN | UNIDO | Investment project for phasing out CFCs at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 19 | INV | 15 | A | I | CFC | 65 | 65 |  |  | 1996-05-01 | 1996-11-01 | 1997-09-01 |  | 1998-12-01 | 2001-07-01 | 644600 | -9228 | 635372 | 635371.9 | 100% | 0.1 | 0 |  | 83798 | -1331 | 82467 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology at Purtiz Co. in the manufacture of rigid polyurethane foam for insulating purposes | Individual | EUR | TUR | FOA | 32 | INV | 72 | A | I | CFC | 52.8 | 52.8 |  |  | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-07-01 | 2004-09-01 | 301094 | -139 | 300955 | 300954.69 | 100% | 0.31 | 0 |  | 39142 | -80 | 39062 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Novemeca in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | I | CFC | 16.2 | 16.2 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -632 | 69254 | 69254.09 | 100% | -0.09 | 0 |  | 9085 | -96 | 8989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC -11 with HCFC-141b at TECNOFRIGO in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | I | CFC | 9 | 9 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | 0 | 71946 | 71946.49 | 100% | -0.49 | 0 |  | 9353 | -13 | 9340 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | I | CFC | 11.8 | 11.8 |  |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -173 | 87866 | 87865.84 | 100% | 0.16 | 0 |  | 11445 | -40 | 11404 | 1 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | 0 | 104030 | 104030 | 100% | 0 | 0 |  | 13524 | -16 | 13508 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid PU panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | I | CFC | 13.9 | 13.9 |  |  | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | 0 | 107850 | 107849.94 | 100% | 0.06 | 0 |  | 14021 | -7 | 14014 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Decocar | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | I | CFC | 16.2 | 16.2 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | 0 | 126614 | 126614.49 | 100% | -0.49 | 0 |  | 16460 | -3 | 16457 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | I | CFC | 17.8 | 17.8 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17878 | 0 | 17878 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | I | CFC | 21.6 | 21.6 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -62 | 164530 | 164529.74 | 100% | 0.26 | 0 |  | 21397 | -42 | 21355 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | I | CFC | 36.4 | 36.4 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | 0 | 198374 | 198374.15 | 100% | -0.15 | 0 |  | 25789 | -13 | 25776 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1: Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | I | CFC | 62.8 | 53.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71323 | 366694 | 366694.41 | 100% | -0.41 | 0 |  | 56942 | -9347 | 47595 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project. | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | I | CFC | 135.5 | 135.5 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 | 2006-05-01 | 851432 | -86779 | 764653 | 764652.66 | 100% | 0.34 | 0 |  | 103658 | -9679 | 93978 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | I | CFC | 75 | 75 |  |  | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2006-12-01 | 2011-05-01 | 475728 | -4430 | 471298 | 471297.59 | 100% | 0.41 | 0 |  | 61845 | -576 | 61269 | 0 | 0 | FIN |  |  |  | INV
ONG | IBRD | Conversion demonstration from HCFC-141b-based to cyclopentane-based pre-blended polyol in the manufacture of rigid polyurethane foam at Guangdong Wanhua Rongwei Polyurethane Co. Ltd | Individual | ASP | CPR | FOA | 59 | DEM | 491 | N | I | HCFC | 6.8 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 | 2013-06-01 |  |  | 1214936 | 0 | 1214936 | 589501 | 48.52% | 625435 | 625435 | 250000 | 91120 | 0 | 44212.47 | 46907.53 | 46907.53 | Zhongshan Midea completed its conversion and trial production in Feb. 2012. Baseline equipment destroyed in Jun. 2012. Three other downstream enterprises continue projects with Rongwei. |  |  |  | INV
ONG | Japan | Demonstration project to validate the use of super-critical CO2 in the manufacture of sprayed polyurethane rigid foam | Individual | LAC | COL | FOA | 60 | DEM | 75 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-04-01 |  | 2010-12-01 | 2014-01-01 |  |  | 441100 | 0 | 441100 | 304571.96 | 69.05% | 136528.04 | 54975 | 0 | 57343 | 0 | 0 | 57343 | 0 | Memorandum of agreement signed with the local counterpart. Trial protocol was established with participation of all parts involved. Equipment and chemicals were bought and delivered to Colombia. Equipment was installed and trials were conducted in 2 different locations with diverse conditions (high and low altitude, high and low temperature and humidity). | Evaluation of foam physical properties is underway. Technical seminar to show the results will be done during the semi-annual meeting of the Latin American Ozone network to be held in June 2013. | 2010
ONG | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane spray foams at Specialized Engineering Contracting Co. | Multi-year | AFR | EGY | FOA | 62 | INV | 107 | N | I | HCFC | 11.2 | 0 | 0 | 0 | 2010-12-01 |  | 2012-06-01 | 2013-12-01 |  |  | 178000 | 0 | 178000 | 0 | 0% | 178000 | 0 | 53400 | 16020 | 0 | 0 | 16020 | 0 | Initial round of technical assistance provided in February 2012 to help two (2) local system houses in blending MF locally. SECC conversion depends on additional progress in implementing FSPOP for system houses (2nd tranche was approved in December 2012 by the 68th ExCom). During fall 2012, SECC (spray equipment) visited two (2) specialized equipment suppliers, and is ready to announce ITB for procurement. | An invitation to bid has been issued and a contractor will be named during a mission in April 2013. | 2010 |  | Investment
ONG | UNDP | Validation/demonstration of low cost options for the use of hydrocarbons as foaming agent in the manufacture of polyurethane foams | Individual | AFR | EGY | FOA | 58 | DEM | 100 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-05-01 | 2010-07-01 | 2013-12-01 |  |  | 473000 | 0 | 473000 | 423445.34 | 89.52% | 49554.66 | 0 | 14866.398 | 35475 | 0 | 31758.4005 | 3716.5995 | 0 | Preblended HC storage and separation tests finalized at DOW. Shipment of the improved mixing head was delayed as the goods went to a port in Turkey instead of Egypt. This was resolved, and the mixing head was received by DOW-Mideast in 2012. | Final tests are planned in Q2 2013. Mission is planned in April 2013 to follow up.Globally, the first recipient/system house (in Mexico) has started trials with preblending CP. | 2009 |  | Non-Investment
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | 1995-06-01 | INV
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 |  | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | Cancelled. |  |  | 1999-06-01 | INV
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 |  | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | 1998-06-01 | INV
CLO | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid foam at Pavusin | Multi-Year | EUR | CRO | FOA | 59 | INV | 34 | A | I | HCFC | 2 | 0 |  |  | 2009-11-01 | 2010-06-01 | 2011-11-30 |  |  | 2012-05-01 | 271150 | -268988 | 2162 | 2162.35 | 100% | -0.35 | 0 |  | 20336 | -20174 | 162 | 0 | 0 | Financial completion in May 2012. Refund was reported to 67th ExCom, Jul 2012. FIN. |  |  |  | INV
COM | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for commercial refrigerators | Multi-year | LAC | DOM | FOA | 61 | INV | 46 | N | I | HCFC | 3.7 | 3.7 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-01-01 |  | 2012-10-01 |  | 332775 | 0 | 332775 | 303850.12 | 91.31% | 28924.88 | 27468.8 | 23139.904 | 24958 | 0 | 22788.6449 | 2169.3551 | 2060.1497 | Completed in 2012. Equipment was delivered and installed at FARCO. Initial trials with Cyclopentane was made. | Completed in 2012. Cyclopentane is now being used on a commercial scale in FARCO. | 2010 |  | Investment
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100% | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | Complete. |  |  | 1998-07-01 | INV
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | 1999-06-01 | INV
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100% | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 07 | INV | 19 | N | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Foam project |  |  | 1996-10-31 | INV
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100% | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100% | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | Project financially completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100% | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | Financially completed. |  |  |  | INV
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100% | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | Physically and financially completed. |  |  |  | INV
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1994-08-01 | INV
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1994-03-01 | INV
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100% | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV
FIN | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 |  | 2005-03-01 | 2005-08-01 | 743500 | 0 | 743500 | 743500 | 100% | 0 | 0 |  | 91785 | 0 | 91785 | 0 | 0 | Completed. |  |  |  | INV
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1996-06-01 | INV
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100% | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | Project completed; PCR submitted to 29th ExCOM. |  |  | 1997-12-01 | INV
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | 1996-11-01 | INV
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100% | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | Project completed; PCR submitted December 2000. |  |  | 1999-06-01 | INV
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 09 | INV | 10 | N | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | 1995-07-01 | INV
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100% | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | Project completed. |  |  | 2000-06-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | 1999-06-01 | INV
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | 1999-06-01 | INV
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 60 | N | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 10 | N | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100% | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 07 | INV | 06 | N | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final PCR provided in June 1998 |  |  | 1997-06-01 | INV
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100% | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV
FIN | UNDP | Eliminations of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Rheem S.A. | Individual | LAC | ARG | FOA | 22 | INV | 55 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-12-01 | 2001-12-01 | 76650 | 0 | 76650 | 76650 | 100% | 0 | 0 | 0 | 9965 | 0 | 9965 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at P.F.I. Ind. E Com. Refrigeracao Ltd. (P.F.I.) | Individual | LAC | BRA | FOA | 26 | INV | 114 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-11-01 | 64200 | 0 | 64200 | 64200 | 100% | 0 | 0 | 0 | 8346 | 0 | 8346 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Industrias Facchini, Ldta. | Individual | LAC | BRA | FOA | 22 | INV | 67 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-03-01 | 2001-11-01 | 258000 | -85574 | 172426 | 172426 | 100% | 0 | 0 | 0 | 33540 | -11125 | 22415 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Industrias Refridcol, Ltda. | Individual | LAC | COL | FOA | 29 | INV | 37 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-09-01 | 117450 | 0 | 117450 | 117450 | 100% | 0 | 0 | 0 | 15268 | 0 | 15268 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Nanjing Kanglian Industrial Corporation | Individual | ASP | CPR | FOA | 27 | INV | 279 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-03-01 | 2000-04-01 | 2001-10-01 |  | 2001-04-01 | 2002-06-01 | 234900 | -14525 | 220375 | 220375 | 100% | 0 | 0 | 0 | 30537 | -1888 | 28649 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Scib Chemical Company | Individual | AFR | EGY | FOA | 12 | INV | 27 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1995-11-01 | 2003-02-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at El Fateh | Individual | AFR | EGY | FOA | 12 | INV | 28 | A | I | CFC | 59 | 59 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2002-03-01 | 2003-01-01 | 496000 | -1 | 495999 | 495999 | 100% | 0 | 0 | 0 | 64480 | -2.6193e-12 | 64480 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Conversion to CFC free-technology at Industrial Engineering Company for Construction and Development (Icon) | Individual | AFR | EGY | FOA | 12 | INV | 29 | A | I | CFC | 51 | 51 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1999-10-01 | 2001-12-01 | 498000 | 0 | 498000 | 498000 | 100% | 0 | 0 | 0 | 64740 | 0 | 64740 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Indoklima Sarana Engineering | Individual | ASP | IDS | FOA | 26 | INV | 96 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 212193 | -43243 | 168950 | 168950 | 100% | 0 | 0 | 0 | 27585.09 | -5622.09 | 21963 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Retroactive project for phasing-out ODS consumption in the manufacture of cold room panels by conversion to HCFC-141b at FMCP Sdn. Bhd. | Individual | ASP | MAL | FOA | 28 | INV | 123 | A | R | CFC | 12.2 | 12.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-07-01 | 2001-12-01 | 45557 | 0 | 45557 | 45557 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of cold room panels and insulation slabs by conversion to HCFC-141b at PKL Insulation | Individual | ASP | MAL | FOA | 28 | INV | 121 | A | I | CFC | 8.1 | 8.1 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-12-01 | 2003-07-01 | 57019 | -1434 | 55585 | 55585 | 100% | 0 | 0 | 0 | 7412.47 | -186.47 | 7226 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase out of the use of CFC in the manufacture of rigid PU panels at Shaga Cooling Technology | Individual | ASP | MAL | FOA | 15 | INV | 56 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1996-10-01 | 2000-12-01 | 190000 | -12498 | 177502 | 177502 | 100% | 0 | 0 | 0 | 24700 | -1625 | 23075 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid panels for commercial refrigerators at Pangkat Refrigeration Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 41 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 210000 | -6736 | 203264 | 203264 | 100% | 0 | 0 | 0 | 27300 | -876 | 26424 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at RCA Group | Individual | ASP | MAL | FOA | 22 | INV | 98 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2000-12-01 | 284500 | -12922 | 271578 | 271578 | 100% | 0 | 0 | 0 | 36985 | -1680 | 35305 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane foam panels for cold storage at Wong Brothers Electrical and Refrigeration Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 38 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1999-03-01 | 2001-12-01 | 299000 | -1 | 298999 | 298999 | 100% | 0 | 0 | 0 | 38870 | -2.6193e-12 | 38870 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-05-01 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels at Rigid Foam Industries, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 49 | A | I | CFC | 19 | 19 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1997-12-01 | 2000-07-01 | 335000 | -3198 | 331802 | 331802 | 100% | 0 | 0 | 0 | 43550 | -416 | 43134 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of polyurethane insulated panel at Cycle World Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 22 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-03-01 |  | 1997-06-01 | 2000-12-01 | 353000 | -1 | 352999 | 352999 | 100% | 0 | 0 | 0 | 45890 | -2.6193e-12 | 45890 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid foam for refrigeration systems at Refrigeración Rodríguez | Individual | LAC | MEX | FOA | 25 | INV | 82 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 132650 | -31006 | 101644 | 101644 | 100% | 0 | 0 | 0 | 17244.5 | -4030.5 | 13214 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNIDO | Phasing out CFC-11 with cyclopentane at Crios Industrial Ltd. (suppliers of Eletrofrio Company) | Individual | LAC | BRA | FOA | 25 | INV | 103 | A | I | CFC | 46 | 46 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 357270 | 0 | 357270 | 357270.08 | 100% | -0.08 | 0 |  | 46445 | -50 | 46395 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Yong Tuck Refrigerators Trading Co. | Individual | ASP | MAL | FOA | 27 | INV | 120 | A | I | CFC | 8 | 8 |  |  | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2000-06-01 | 2001-09-01 | 61735 | -643 | 61092 | 61091.82 | 100% | 0.18 | 0 |  | 8026 | -97 | 7929 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption at Chong Brother Group of Companies | Individual | ASP | MAL | FOA | 28 | INV | 127 | A | I | CFC | 27.6 | 27.6 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 216108 | 0 | 216108 | 216107.83 | 100% | 0.17 | 0 |  | 28094 | -21 | 28073 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane panels for thermal insulation for cold rooms and cold storages at Izotek | Individual | EUR | TUR | FOA | 28 | INV | 65 | A | I | CFC | 74.8 | 74.8 |  |  | 1999-07-01 | 2000-08-01 | 2001-08-01 |  | 2001-08-01 | 2002-09-01 | 430721 | -4807 | 425914 | 425914.32 | 100% | -0.32 | 0 |  | 55994 | -713 | 55281 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | I | CFC | 15.3 | 15.3 |  |  | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | 0 | 115382 | 115382.29 | 100% | -0.29 | 0 |  | 15000 | -10 | 14990 | 0 | 0 | FIN
ONG | UNDP | Conversion from HCFC-141b to cyclopentane technology in manufacturing refrigeration equipment insulation foam at Walton Hi-Tech Industries Limited | Multi-year | ASP | BGD | FOA | 62 | INV | 38 | N | I | HCFC | 20.2 | 0 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 | 2013-12-01 |  |  | 1146074 | 0 | 1146074 | 600055.28 | 52.36% | 546018.72 | 0 | 163805.616 | 85956 | 0 | 45004.3816 | 40951.6184 | 0 | MoA for implementation of the project was signed in June 2012. First two installments of payments for the conversion project were released. Enterprise has completed procurement of equipment and final installation and commissioning is expected to be completed by end of Q1 in 2013. | Training of factory personnel on using HC based formulations for manufacturing refrigerator foam was conducted in February 2013. | 2010 |  | Investment
ONG | UNDP | Conversion plan from HCFCs to hydrocarbons in the production of polyurethane rigid insulation foam in the domestic refrigeration subsector (Mabe Colombia, Industrias Haceb, Challenger and Indusel S.A.) | Multi-year | LAC | COL | FOA | 60 | INV | 76 | N | I | HCFC | 56 | 56 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2013-04-01 | 2013-06-01 |  |  | 5621483 | 0 | 5621483 | 5220331.27 | 92.86% | 401151.73 | 0 | 120345.519 | 421611 | 0 | 391524.6363 | 30086.3637 | 0 | Equipment was delivered to all companies. Trials were made and full scale introduction of Cyclopentane was done at the end of 2012. | Technical assistance to companies is being provided. IOCs will be paid in 2013. | 2010 |  | Investment
ONG | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane rigid insulation foam for water heaters at Fresh Electric for Home Appliances | Multi-year | AFR | EGY | FOA | 62 | INV | 106 | N | I | HCFC | 2.4 | 0 | 0 | 0 | 2010-12-01 |  | 2012-06-01 | 2013-12-01 |  |  | 124500 | 0 | 124500 | 0 | 0% | 124500 | 0 | 37350 | 11205 | 0 | 0 | 11205 | 0 | Successful trials with imported MF completed in February 2012. Technical visit fielded in September 2012. ITB initiated and bids for equipment analyzed.The winning bid came with total higher costs, than planned, and Fresh company, due to the need to complement the gap with own resources, rejected it. | After mediation with FRESH, simplified specifications were prepared to attempt to reduce costs, were accepted by the company and re-bidding is underway. Bid opening planned during a mission in April 2013. | 2010 |  | Investment
ONG | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at Cairo Foam | Multi-year | AFR | EGY | FOA | 62 | INV | 108 | N | I | HCFC | 9.9 | 0 | 0 | 0 | 2010-12-01 |  | 2012-06-01 | 2013-12-01 |  |  | 386100 | 0 | 386100 | 0 | 0% | 386100 | 0 | 115830 | 28958 | 0 | 0 | 28958 | 0 | Two visits fielded in February and September 2012. ITB process completed, and equipment bids have been analyzed same month. Purchase contract with equipment supplier signed in December 2012 with delivery expected, as per contractual obligations, in summer 2013. | Cairo Foam is preparing infrastructure for equipment installation beginning Q3. Mission is planned in April 2013. | 2010 |  | Investment
ONG | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at MOG for Engineering and Industry | Multi-year | AFR | EGY | FOA | 62 | INV | 105 | N | I | HCFC | 13.9 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-06-01 | 2013-12-01 |  |  | 790400 | 0 | 790400 | 464043.2 | 58.71% | 326356.8 | 0 | 97907.04 | 59280 | 0 | 34803.24 | 24476.76 | 0 | Second technical visit fielded in February 2012. ITB process initiated and completed. Offers from interested equipment suppliers were received in August 2012. During a technical visit in September 2012, bids were officially opened and analyzed. | Purchase contract with equipment supplier was signed in January 2013 with delivery expected, as per contractual obligations, in summer 2013. Contractor to visit the factory in April 2013. MOG is preparing infrastructure for equipment installation. | 2010 |  | Investment
ONG | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Mabe Mexico | Multi-year | LAC | MEX | FOA | 59 | INV | 148 | N | I | HCFC | 55.8 | 55.8 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2013-08-01 | 2014-07-01 |  |  | 2428987 | 0 | 2428987 | 150539.52 | 6.198% | 2278447.48 | 0 | 911378.992 | 182174 | 0 | 11290.4625 | 170883.5375 | 0 | 2 expert visits took place in 2012 to MABE. New system for Cyclopentane developed and tested internally in MABE and is now approved for new models. Technical specs approved and published for procurement of new equipment. | International tender was published and bids were recieved. They are currently being evaluated by UNDP before the purchase order is signed. Equipment is expected to be delivered by July. | 2009 |  | Investment
ONG | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor | Multi-Year | AFR | ALG | FOA | 62 | INV | 75 | A | I | HCFC | 2.4 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 215380 | 0 | 215380 | 11369.35 | 5.279% | 204010.65 | 0 | 50000 | 19384 | 0 | 1023 | 18361 | 0 | a. Requisition for the equipment for conversion of beneficiary company CRISTOR was raised and bidding procedure opened in March 2012. The lowest technically acceptable offer received for the items in the project document was for a total cost of 359.000 USD, exceeding the total project grant by 143,620 USD. b. Further project implementation was slightly delayed due to postponed mission to the beneficiary company CRISTOR, planned for August 2012. Reason for the low disbursement is due to the fact that the first bidding was not successful and therefore no money could be spent on equipment procurement. | a. Mission took place in February 2013 to negotiate with the beneficiary and the NOU to decide on the way forward. The two main ways identified so far are to reduce the scope of supply or to get a co-financing from beneficiary. b. Bidding procedure for the necessary equipment for the conversion has been initiated in January. No companies submitted proposal under the first call. Second call for proposal is ongoing and new deadline for receiving offer is 11 May. We expect signature of the contract by mid-July. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at El-Araby Co. for Engineering Industries | Multi-Year | AFR | EGY | FOA | 62 | INV | 110 | A | I | HCFC | 11 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 456540 | 0 | 456540 | 12736.55 | 2.79% | 443803.45 | 443797 | 443797 | 34241 | 0 | 955 | 33286 | 33285 | The international bidding was finished and an equipment provider was selected. Due to the limited funds available costs of equipment had to be negotiated. Purchase order was issued in June 2012, the production site was prepared for conversion. Disbursement level at the end of 2012 does not reflect actual progress in the project. By end 2012, 100% of funds was committed. | The delivery of equipment is expected for May 2013, contract of the local works and logistic support will be finalized in the second half of 2013. Conversion schedule is confirmed, which in turn will result in total disbursement during 2013. (disbursement in 4 steps in accordance with to performance-based contract with the equipment provider). The completion of the project is envisaged for the end of 2013. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Mondial Freezers Company | Multi-Year | AFR | EGY | FOA | 62 | INV | 104 | A | I | HCFC | 6.6 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-12-01 |  |  | 436300 | 0 | 436300 | 12742.6 | 2.921% | 423557.4 | 413562.8 | 413563 | 32723 | 0 | 956 | 31767 | 31017 | The international bidding was finished and an equipment provider was selected. Due to the limited funds available costs of equipment had to be negotiated. Purchase order was issued in June 2012, the production site was prepared for conversion. Disbursement level at the end of 2012 does not reflect actual progress in the project. By end 2012, 98% of funds was committed. | The delivery of equipment is expected for May 2013, contract of the local works and logistic support will be finalized in the second half of 2013. 'Conversion schedule is confirmed, which in turn will result in total disbursement during 2013. (disbursement in 4 steps in accordance with to performance-based contract with the equipment provider). The completion of the project is envisaged for the end of 2013. |  |  | INV
ONG | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Manar | Multi-Year | AFR | MOR | FOA | 62 | INV | 67 | A | I | HCFC | 11 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2013-07-01 |  |  | 951740 | 0 | 951740 | 591318.64 | 62.13% | 360421.36 | 300621.27 | 320000 | 71381 | 0 | 44349 | 27032 | 22547 | Full equipment was delivered to MANAR in December 2012 and conversion took place. | All lines were tested in January 2013. The plant has successfully started manufacturing with the introduced technology in February. Opening ceremony was planned for April 2013, but postponed for logistic reasons. Acceptance for converted plant and inauguration ceremony is planned for this year as soon as feasible. Reason for delay: too late delivery of equipment. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at Dawlance | Multi-Year | ASP | PAK | FOA | 60 | INV | 78 | A | I | HCFC | 22.4 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 | 2013-12-01 |  |  | 1281490 | 0 | 1281490 | 803895.76 | 62.73% | 477594.24 | 125000 | 200000 | 96112 | 0 | 60292 | 35820 | 9375 | Delivery of equipment is delayed due to late specifications and agreement on scope of additional items (co-financed by beneficiaries) to fit with existing installations and with the machinery supplied through this project. Delivery of items to be purchased locally (C5 tank piping and ancillaries) and site preparatory works are progressing in line with the plan for installation. | Delivery term set for Mach 2013. Equipment was delivered in May 2013. Installation and commissioning of equipment including entire plant modification, safety certification (post safety rectification if any), start up trial, on work training. The project is expected to be completed in 2013.
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at United Refrigeration, HNR (Haier), Varioline Intercool and Shadman Electronics companies | Multi-Year | ASP | PAK | FOA | 60 | INV | 77 | A | I | HCFC | 49.2 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 | 2013-12-01 |  |  | 3559359 | 0 | 3559359 | 1798244.77 | 50.52% | 1761114.23 | 1554649.42 | 150000 | 266952 | 0 | 134868 | 132084 | 116599 | Equipment for Varioline and Haier has been delivered as planned. Installations were rescheduled for the first quarter of 2013 due to delays in the site preparations. Delivery of equipment for United Refrigeration and Shadman is delayed due late specifications and agreement on scope of additional items (co-financed by beneficiaries) to fit with existing installations and with the machinery supplied through this project. Delivery of items to be purchased locally (C5 tank piping and ancillaries) and site preparatory works are progressing in line with the plan for installation. | Delivery term set for Mach 2013. Installation and commissioning of equipment including entire plants modification, safety certification (post safety rectification if any), start up trial, on work training. The project is expected to be completed in 2013.
ONG | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of domestic refrigerators, commercial refrigerators and PU insulated composite panels (Modern, Amin, Coldair, Akadabi) | Multi-Year | AFR | SUD | FOA | 62 | INV | 28 | A | I | HCFC | 11.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2013-12-01 |  |  | 1056341 | 0 | 1056341 | 1853.67 | 0.1755% | 1054487.33 | 590422.81 | 46000 | 79226 | 0 | 139 | 79087 | 44282 | Delivery of equipment was delayed due to an error in supplier's planning. The disbursement was zero for 2012 , since the delivery of equipment was delayed against implementation plan/payment schedule of the contract. The payments will be effected in 2013 only in accordance with the progress of equipment delivery, installations and commissioning works. However, it is to be noted that by the end of 2012, almost USD 600,000 was committed through the above contract. | The new delivery term was set for mid March 2013. Preparation of the project sites for installation; commissioning, start up, on work training is planned for 2013. The project is expected to be completed in 2013. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Delta Electric Applicances | Individual | AFR | EGY | FOA | 62 | INV | 109 | A | I | HCFC | 8.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  |  |  | 422740 | 0 | 422740 | 15694.61 | 3.713% | 407045.39 | 0 | 1 | 31706 | 0 | 1177 | 30529 | 0 | The project was cancelled. |  |  |  | INV
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 07 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | 1994-06-01 | INV
COM | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 421 | A | I | CFC | 158 | 158 | 0 |  | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 |  | 101078 | 0 | 101078 | 101078 | 100% | 0 | 0 | 0 | 13140 | 0 | 13140 | 0 | 0 | All activities as per the annual working plan have been accomplished. PCR is under preperation.
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2008 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 455 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2010-01-01 |  | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 | 0 | 159030 | 0 | 159030 | 0 | 0 | Fully disbursed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2009 annual programme | Multiyear | ASP | CPR | FOA | 56 | INV | 478 | N | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2009-11-01 |  | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 | 0 | 159030 | 0 | 159030 | 0 | 0 | Completed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2007 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 454 | N | I | CFC | 551 | 551 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2009-11-01 |  | 2676000 | 0 | 2676000 | 2676000 | 100% | 0 | 0 | 0 | 240840 | 0 | 240840 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2006 annual programme | Multiyear | ASP | CPR | FOA | 47 | INV | 434 | N | I | CFC | 600 | 600 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2008-10-01 |  | 3320000 | 0 | 3320000 | 3320000 | 100% | 0 | 0 | 0 | 282800 | 0 | 282800 | 0 | 0 | Fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 9940000 | 0 | 9940000 | 9940000 | 100% | 0 | 0 | 0 | 886600 | 0 | 886600 | 0 | 0 | Annual program fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 | 0 | 961270 | 0 | 961270 | 0 | 0 | Fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2005-12-01 |  | 2005-12-01 |  | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 | 0 | 961270 | 0 | 961270 | 0 | 0 | All activities under this AP has been completed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 |  | 12570000 | 0 | 12570000 | 12570000 | 100% | 0 | 0 | 0 | 1115300 | 0 | 1115300 | 0 | 0 | Fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2009 annual programme | Multiyear | ASP | CPR | HAL | 56 | INV | 481 | N | I | HAL | 1000 | 1000 | 1500 | 1500 | 2008-11-01 | 2011-06-01 | 2009-11-30 |  | 2009-11-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Complete halon phaseout target has been met. Three remaining TA activities (studies) completed and study outputs have or will be used to develop various fire safety standards. As of late 2011, recovered & recycled halons are no longer considered as hazard |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2008 annual programme | Multiyear | ASP | CPR | HAL | 53 | INV | 456 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 |  | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 22500 | 0 | 22500 | 0 | 0 | Completed. |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2007 annual programme | Multiyear | ASP | CPR | HAL | 50 | INV | 445 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-10-01 | 2007-11-01 |  | 2008-10-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 |  | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 | 0 | 90000 | 0 | 90000 | 0 | 0 | Annual Program successfully completed with full disbursement made. |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2005-11-01 |  | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 | 0 | 135000 | 0 | 135000 | 0 | 0 | Tranche technically and financially completed |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | I | HAL | 2889 | 2889 | 2160 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3700000 | 0 | 3700000 | 3700000 | 100% | 0 | 0 | 0 | 370000 | 0 | 370000 | 0 | 0 | Annual Program completed and final disbursement for the tranche made. |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | I | HAL | 1389 | 1389 | 1980 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 |  | 4500000 | 0 | 4500000 | 4500000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | Newly Approved. |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 5900000 | 0 | 5900000 | 5900000 | 100% | 0 | 0 | 0 | 442500 | 0 | 442500 | 0 | 0 | Annual Program completed and final disbursement for tranche made. |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | I | HAL | 5370 | 5370 | 5826 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 |  | 9700000 | 0 | 9700000 | 9700000 | 100% | 0 | 0 | 0 | 970000 | 0 | 970000 | 0 | 0 | 1999 annual plan completed successfully. |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | I | HAL | 3712 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 |  | 10600000 | 0 | 10600000 | 10600000 | 100% | 0 | 0 | 0 | 1060000 | 0 | 1060000 | 0 | 0 | Annual Program fully completed and disbursed. |  |  |  | INV
COM | IBRD | Sector plan for halon phase-out in China: 2006 annual programme | Multiyear | ASP | CPR | HAL | 47 | INV | 433 | N | I | HAL | 6170 | 6170 | 10470 | 10470 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-11-01 |  | 11400000 | 0 | 11400000 | 11400000 | 100% | 0 | 0 | 0 | 855000 | 0 | 855000 | 0 | 0 | Annual program technically and financially completed. |  |  |  | INV
COM | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Multiyear | ASP | CPR | HAL | 23 | INV | 231 | N | I | HAL | 9939 | 9939 | 11739 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 |  | 12400000 | 0 | 12400000 | 12400000 | 100% | 0 | 0 | 0 | 1240000 | 0 | 1240000 | 0 | 0 | 1998 Annual Plan was successfully completed. |  |  |  | INV
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2009 annual programme | Multiyear | ASP | CPR | PAG | 57 | INV | 483 | N | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-31 |  | 2011-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | China has met last disbursement conditions. Disbursement made in May 2012. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2009 annual programme | Multiyear | ASP | CPR | PAG | 58 | INV | 488 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-31 |  | 2010-07-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 112500 | 0 | 112500 | 0 | 0 | China met all disbursement conditions. Last disbursement made in May 2012. |  |  |  | INV
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | First tranche completed. |  |  |  | INV
COM | IBRD | Process agent sector plan (phase I): 2005 annual programme | Multiyear | ASP | CPR | PAG | 46 | INV | 432 | N | I | CTC | 4556 | 4556 | 16171 | 16171 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-07-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | Fully completed and disbursed; 2005 targets met. |  |  |  | INV
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2008 annual programme | Multiyear | ASP | CPR | PAG | 54 | INV | 458 | N | I | CTC | 0 | 0 | 10594 | 10594 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 |  | 3000000 | 0 | 3000000 | 3000000 | 100% | 0 | 0 | 0 | 225000 | 0 | 225000 | 0 | 0 | Tranche fully completed and disbursed. |  |  |  | INV
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2007 annual programme | Multiyear | ASP | CPR | PAG | 51 | INV | 448 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Activities under this annual program have been completed. Disbursement has been completed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 441 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2007-12-01 |  | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | Fully completed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2007 annual programme | Multiyear | ASP | CPR | PAG | 52 | INV | 452 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-07-01 |  | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | Activities under this annual program have been completed, and the funding has been fully disbursed. |  |  |  | INV
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2008 annual programme | Multiyear | ASP | CPR | PAG | 55 | INV | 463 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 |  | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | Tranche fully completed and disbursed. |  |  |  | INV
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 440 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 |  | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 0 | 0 | Fully completed. |  |  |  | INV
COM | Japan | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 420 | A | I | CFC-12 | 0 |  | 0 |  | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2005-12-01 |  | 1000000 | 0 | 1000000 | 1027273 | 102.7% | -27273 | 0 | 0 | 130000 | 0 | 102727 | 27273 | 0 | It is to be noted that actual funds disbursed are higher than the original approval. This is due to the fact that on the request of the Government of Japan, part of the support cost was reallocated to project budget. Thus, in totality there is no over-expenditure. As per the agreement between Japan and UNIDO the approved funds are distributed as follows: USD 1,027,273 project cost and USD 102,727 support cost. |  | 2004 |  | investment
COM | Japan | Refrigeration servicing sector CFC phase-out plan (second tranche) | Multi-Year | ASP | CPR | REF | 47 | INV | 438 | A | I | CFC-12 | 511 | 511 | 0 |  | 2005-11-01 | 2006-11-01 | 2006-12-01 |  | 2012-12-01 |  | 3000000 | 0 | 3000000 | 3079062 | 102.6% | -79062 | 2737 | 2700 | 390000 | 0 | 307906.2 | 82093.8 | 0 | It is to be noted that actual funds disbursed are higher than the original approval. This is due to the fact that on the request of the Government of Japan, part of the support cost was reallocated to project budget. Thus, in totality there is no over-expenditure. As per the agreement between Japan and UNIDO the approved funds are distributed as follows: USD 3,079,062 project cost and USD 307,906 support cost. |  | 2005 |  | investment
COM | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | Multi-Year | ASP | CPR | SOL | 40 | INV | 403 | N | I | CFC/TCA/CTC | 580 | 580 | 0 | 0 | 2003-07-01 | 2005-01-01 | 2004-03-01 |  | 2005-12-01 |  | 5755000 | 0 | 5755000 | 5755000 | 100% | 0 | 0 | 0 | 431625 | 0 | 431625 | 0 | 0 | Completed in 2005. |  | 2003 | 2005-06-01 | Investment
COM | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | Multi-Year | ASP | CPR | SOL | 36 | INV | 390 | N | I | TCA/CTC/CFC | 580 | 580 | 0 | 0 | 2002-03-01 | 2005-01-01 | 2003-03-01 |  | 2005-09-01 |  | 6330000 | 0 | 6330000 | 6330000 | 100% | 0 | 0 | 0 | 633000 | 0 | 633000 | 0 | 0 | Completed in 2005. |  | 2002 | 2004-06-01 | Investment
COM | UNDP | ODS phaseout in China solvent sector: 2000 annual programme | Multi-Year | ASP | CPR | SOL | 30 | INV | 355 | N | I | TCA/CTC/CFC | 382.8 | 382.8 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-03-01 |  | 2003-05-01 |  | 6750000 | 0 | 6750000 | 6750000 | 100% | 0 | 0 | 0 | 675000 | 0 | 675000 | 0 | 0 | Completed in 2003. |  | 2000 |  | Investment
COM | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | Multi-Year | ASP | CPR | SOL | 33 | INV | 373 | N | I | TCA/CTC/CFC | 534 | 534 | 0 | 0 | 2001-03-01 | 2003-03-01 | 2002-03-01 |  | 2005-01-01 |  | 6955000 | 0 | 6955000 | 6955000 | 100% | 0 | 0 | 0 | 695500 | 0 | 695500 | 0 | 0 | Completed in 2005. |  | 2001 | 2003-09-01 | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 164 | N | I | CFC | 200 | 200 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-12-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 43400 | 0 | 43400 | 0 | 0 | Completed in 2008. |  | 2004 |  | Investment
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector ( 2nd tranche) | Multi-Year | ASP | IDS | REF | 40 | INV | 154 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-07-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 52900 | 0 | 52900 | 0 | 0 | Completed in 2004. |  | 2003 |  | Investment
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | Multi-Year | ASP | IDS | REF | 37 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-10-01 | 2002-12-01 |  | 2004-12-01 |  | 1288000 | 0 | 1288000 | 1288000 | 100% | 0 | 0 | 0 | 111920 | 0 | 111920 | 0 | 0 | Completed in 2004. |  | 2002 | 2004-12-01 | Investment
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (balance of second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 155 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-06-01 |  | 1600000 | 0 | 1600000 | 1600000 | 100% | 0 | 0 | 0 | 141100 | 0 | 141100 | 0 | 0 | Completed in 2006. |  | 2003 |  | Investment
COM | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 163 | N | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-12-01 |  | 1762000 | 0 | 1762000 | 1762000 | 100% | 0 | 0 | 0 | 156900 | 0 | 156900 | 0 | 0 | Completed in 2007. |  | 2004 |  | Investment
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (servicing) sector (second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 157 | N | I | CFC | 200 | 200 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2004-12-01 |  | 2006-12-01 |  | 1805987 | 0 | 1805987 | 1805987 | 100% | 0 | 0 | 0 | 160939 | 0 | 160939 | 0 | 0 | Completed in 2006. |  | 2003 | 2006-12-01 | Investment
COM | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | Multi-Year | ASP | IDS | REF | 38 | INV | 151 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2005-12-01 |  | 2196758 | 0 | 2196758 | 2196758 | 100% | 0 | 0 | 0 | 195708 | 0 | 195708 | 0 | 0 | Completed in 2005. |  | 2002 |  | Investment
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (first tranche) | Multi-Year | ASP | IND | FOA | 37 | INV | 353 | N | I | CFC | 162.5 | 162.5 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2003-12-01 |  | 2004-12-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Completed in 2004. |  | 2002 |  | Investment
COM | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 419 | N | I | CFC | 219.1 | 219.1 | 0 | 0 | 2008-04-01 |  | 2010-03-01 |  | 2012-11-01 |  | 47881 | 0 | 47881 | 0 | 0% | 47881 | 0 | 38304.8 | 3591 | 0 | 0 | 3591 | 0 | Completed in 2012. Remaining invoices to be settled in 2013. | Completed in 2012. Remaining invoices to be settled in 2013. | 2008 |  | Investment
COM | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 379 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-03-01 | 2005-12-01 |  | 2006-06-01 |  | 277050 | 0 | 277050 | 277050 | 100% | 0 | 0 | 0 | 20779 | 0 | 20779 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
COM | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 371 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-11-01 | 2005-04-01 |  | 2006-06-01 |  | 277200 | 0 | 277200 | 277200 | 100% | 0 | 0 | 0 | 20790 | 0 | 20790 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
COM | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 364 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-03-01 | 2004-12-01 |  | 2006-12-01 |  | 476536 | 0 | 476536 | 476536 | 100% | 0 | 0 | 0 | 43243 | 0 | 43243 | 0 | 0 | Completed in 2006. |  | 2003 | 2006-12-01 | Investment
COM | UNDP | Plan for phase out of CFCs in the refrigeration manufacturing sector (first tranche) | Multi-Year | ASP | IND | REF | 38 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2004-11-01 |  | 2006-07-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 172971 | 0 | 172971 | 0 | 0 | Completed in 2006. |  | 2002 |  | Investment
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 380 | A | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2006-01-01 | 2005-12-01 |  | 2006-04-01 | 2006-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 393 | A | I | CFC | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2007-04-01 | 2007-04-01 | 105090 | 0 | 105090 | 105090 | 100% | 0 | 0 | 0 | 13662 | 0 | 13662 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 369 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 414370 | 0 | 414370 | 414370 | 100% | 0 | 0 | 0 | 53868 | 0 | 53868 | 0 | 0 | The project infrastructure has been successfully established and all activites as per the the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 404 | A | I | CFC | 158 | 358 | 0 |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2008-04-01 | 2009-04-01 | 436200 | 0 | 436200 | 436200 | 100% | 0 | 0 | 0 | 56706 | 0 | 56706 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Multiyear | ASP | IDS | ARS | 44 | INV | 166 | N | I | CFC | 70 | 70 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-05-01 |  | 2010-06-01 | 2010-06-01 | 371910 | 0 | 371910 | 371910 | 100% | 0 | 0 |  | 27893 | 0 | 27893 | 0 | 0 | Project successfully completed and closed in Jun 2010. |  |  |  | INV
FIN | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | I | CFC | 130 | 130 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-12-01 | 100000 | 1625000 | 1725000 | 1725000 | 100% | 0 | 0 |  | 7500 | 121875 | 129375 | 0 | 0 | Project is physically and financially completed |  |  |  | INV
FIN | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2004 annual plan completed sucessfully. |  |  |  | INV
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | I | CFC | 110 | 110 | 0 | 0 | 2004-12-01 | 2006-11-01 | 2005-12-01 |  | 2005-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2005 consumption reduction target was achieved. |  |  |  | INV
FIN | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-05-01 | 1369800 | 0 | 1369800 | 1369800 | 100% | 0 | 0 |  | 121962 | 0 | 121962 | 0 | 0 | 2003 annual plan completed successfully. |  |  |  | INV
FIN | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 | 2008-01-30 | 2600000 | 0 | 2600000 | 2600000 | 100% | 0 | 0 |  | 234000 | 0 | 234000 | 0 | 0 | UNDP has confirmed that project has been completed. Final completion report still pending from UNDP. |  |  |  | INV
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (second phase) | Individual | AFR | DRC | SOL | 56 | INV | 28 | A | I | CTC-TCA | 11.7 | 11.7 | 0 |  | 2008-11-01 |  | 2009-11-01 |  | 2011-10-01 | 2012-08-01 | 144220 | -1253.81 | 142966.19 | 142966 | 100% | 0.19 | 0 |  | 18749 | -163 | 18585.58 | 0.42 | 0 | Financial completion in Aug 2012. Refund was reported to 68th ExCom, Nov 2012. FIN. |  | 2008 | 2011-12-01 | Investment
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (first phase) | Individual | AFR | DRC | SOL | 51 | INV | 25 | A | I | CTC-TCA | 8.9 | 8.9 | 0 |  | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2011-10-01 | 2012-08-01 | 288440 | 0 | 288440 | 288440 | 100% | 0 | 0 |  | 37497 | 0 | 37497.2 | -0.2 | 0 | Financial completion in Aug 2012. |  | 2007 | 2009-12-01 | Investment
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 370 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-03-31 | 2005-03-31 | 353020 | 0 | 353020 | 353020 | 100% | 0 | 0 | 0 | 45893 | 0 | 45893 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2004: Four new training cells have been established and a Training of Trainers Wokshop was held for 12 particpants. With this, 13 training cells provided in 2004 standard training programs for refrigeration service technicians. | 2004 |  | 2004
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 381 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-03-31 | 2006-03-31 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2005: In the operational year 05-06 the following number of technicians are trained: a) in Standard RSE programs: 1685 participants b) Mobile Air-Conditioning programs 130 participants c) Open Type compressor programs: 64 partic | 2005 |  | 2005
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 394 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-03-31 | 2007-03-31 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2006: In the operational year 06-07 the following number of technicians are trained: a) in Standard RSE programs: 1810 participants b) Mobile Air-Conditioning programs 238 participants c) Open Type compressor programs: 55 partic | 2006 |  | 2006
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 406 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-11-01 |  | 2008-03-31 | 2008-03-31 | 367140 | 0 | 367140 | 367140 | 100% | 0 | 0 | 0 | 47728 | 0 | 47728 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2007: In the operational year 07-08 the following number of technicians are trained: a) in Standard RSE programs: 1880 participants b) Mobile Air-Conditioning programs 275 participants c) Open Type compressor programs: 113 partic. | 2007 |  | 2007
FIN | UNDP | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Multi-year | ASP | IDS | ARS | 44 | INV | 167 | N | I | CFC | 80 | 80 | 0 | 0 | 2004-12-01 | 2005-11-01 | 2005-12-01 |  | 2006-06-01 | 2011-12-01 | 224000 | -42113 | 181887 | 181887 | 100% | 0 | 0 | 0 | 13440 | -2526.78 | 10913.22 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 395 | N | I | CFC | 428 | 428 | 0 | 0 | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2009-12-01 | 2012-11-01 | 1332377 | 0 | 1332377 | 1197810.06 | 89.9% | 134566.94 | 0 | 0 | 112417 | 0 | 101063.1477 | 11353.8523 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2005 |  | Investment
FIN | UNDP | Technical assistance for the phase-out of ODS in the solvent/sterilant sector | Individual | AFR | ZIM | SOL | 50 | TAS | 35 | N | I | TCA/CTC | 3.9 | 3.9 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-05-01 |  | 2009-12-01 | 2011-10-01 | 60000 | -1229.02 | 58770.98 | 58770.98 | 100% | 0 | 0 | 0 | 5400 | -111 | 5289 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2006 | 2010-01-01 | Non-Investment
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-year | ASP | IND | REF | 54 | TAS | 420 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2011-01-01 | 2012-01-01 | 19900 | 0 | 19900 | 19900 | 100% | 0 | 0 | 0 | 2587 | 0 | 2587 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-year | ASP | IND | REF | 47 | TAS | 396 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. ($ 10,140 plus $ 1,318 PSC returned to ExCom 50) |  |  |  | Non Investment
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-year | ASP | IND | REF | 50 | TAS | 405 | A | I | CFC | 101.5 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2008-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. ($ 3,250 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-year | ASP | IND | REF | 42 | TAS | 377 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2007-06-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 | 0 | 0 | 33319 | 0 | 33319 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-year | ASP | IND | REF | 44 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-04-01 | 2009-04-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 | 0 | 0 | 33319 | 0 | 33319 | 0 | 0 | Project financially completed. ($ 22,000 plus $ 2,860 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | National transition strategy for the phase-out of CFC propellants in MDIs | Individual | ASP | IRA | ARS | 52 | TAS | 184 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-03-01 | 2010-09-01 |  | 2011-01-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project Completed |  |  |  | Non Investment
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 419 | A | I | CFC | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -450043 | 549957 | 549956.95 | 100% | 0.05 | 0 |  | 75000 | -33753 | 41247 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC Phase-out Plan (fifth tranche) | Multi-Year | ASP | CPR | REF | 56 | INV | 474 | A | I | CFC | 680 | 680 |  |  | 2008-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 | 2011-12-01 | 700000 | -104 | 699896 | 699895.84 | 100% | 0.16 | 0 |  | 52500 | -8 | 52492 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (third tranche) | Multi-Year | ASP | CPR | REF | 51 | INV | 450 | A | I | CFC | 782 | 782 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-12-01 | 2010-05-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of ODS in the solvent sector | Multi-Year | ASP | IDS | SOL | 44 | INV | 162 | A | I | CFC CTC TCA | 100.1 | 100.1 |  |  | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-10-01 | 2009-09-01 | 1464733 | -670 | 1464063 | 1464062.74 | 100% | 0.26 | 0 |  | 108974 | -50 | 108924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 366 | A | I | CFC | 67 | 77 |  |  | 2003-12-01 | 2006-10-01 | 2005-12-01 |  | 2007-03-01 | 2009-12-01 | 173200 | -35 | 173165 | 173164.63 | 100% | 0.37 | 0 |  | 19052 | -4 | 19048 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | Multi-Year | ASP | IND | REF | 38 | INV | 359 | A | I | CFC | 40 | 59 |  |  | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2006-11-01 | 2007-12-01 | 500000 | 0 | 500000 | 499999.63 | 100% | 0.37 | 0 |  | 65000 | 0 | 65000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Supplementary plan for terminal phase-out of CTC as process agent | Individual | ASP | DRK | PAG | 49 | INV | 46 | A | I | CTC | 229.9 | 229.9 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 884399 | -799 | 883600 | 883599.54 | 100% | 0.46 | 0 |  | 66330 | -60 | 66270 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | ASP | IRA | SOL | 50 | INV | 180 | A | I | CTC TCA | 52.7 | 52.7 |  |  | 2006-11-01 | 2007-11-01 | 2008-02-01 |  | 2009-12-01 | 2012-09-01 | 856478 | -1457 | 855021 | 855021.12 | 100% | -0.12 | 0 |  | 64236 | -109 | 64127 | 0 | 0 | Financial completion in Sep 2012. Refund was reported to 68th ExCom, Dec 2012. FIN. |  |  | 2009-12-01 | INV
ONG | IBRD | Phase-out of CFC consumption in the pharmaceutical aerosol sector (2007-2008 biennial programme) | One off phaseout | ASP | CPR | ARS | 51 | INV | 447 | N | I | CFC | 485.1 | 244.7 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2011-03-01 | 2013-12-01 |  |  | 6000000 | 0 | 6000000 | 5550000 | 92.5% | 450000 | 450000 | 450000 | 450000 | 0 | 416250 | 33750 | 33750 | TA activities to establish specifications for substitutes (HFC-134a, HC, HFC-227, CO2) completed. DIA followed up with 26 beneficiary enterprises on progress in renewing registration of 49 products using substitutes with SFDA. SFDA issued its decisions on the registration of 19 products submitted by 15 enterprises. SFDA is also reviewing applications for another 25 products submitted by 17 enterprises. Two enterprises have not submitted applications while application of one enterprise (Shanghai Xinyi) was rejected by SFDA due to lack of national standards on the substitute at that time. DIA made proposals to compensate 17 enterprises that had submitted applications to SFDA for approval by 31 Dec. 2012 and to cancel contracts with 3 enterprises that did not submit applications to SFDA. | SFDA is engaging experts to review specifications and has also promulgated national standards on 16 Jan. 2013 for public consultation. Once evaluation and consultation processes completed, new standard will become effective on 1 Jul. 2013 and use of CFC in the production of non-MDI pharmaceutical products will be banned thereafter. It was agreed that DIA will organize a (i) workshop in May 2013 to inform enterprises of national standards on substitutes and (ii) final conference on non-MDI pharmaceutical aerosol in Jul. 2013(conference report to be submitted to the WB by end Jul. 2013). |  |  | INV
ONG | Japan | Sector plan to phase out HCFC-141b in the foam sector | Individual | ASP | PHI | FOA | 62 | INV | 91 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-12-01 | 2011-06-01 | 2012-12-01 | 2014-06-01 |  |  | 317350 | 0 | 317350 | 62147 | 19.58% | 255203 | 1001 | 20000 | 41256 | 0 | 8079.11 | 33176.89 | 130.13 | Contracts were signed in 2012 for the conversion of all ten eligible beneficiaries using 141-b for various applications using fixed-foam equipment. The cost for the purchased equipment and services amounted 1,458,105 USD, including transportation, installation and training. The conversion will generate a phase-out of 93.74 ODP t, for a calculated cost effectiveness of 15.6 USD/kg. - One existing spray machine (Graco/Gusmer H-20/35) was converted on a pilot basis. Cost of the conversion and upgrade of 1 pilot unit is not indicative for the calculation of ICC. Test on other available or H22 technologies (i.e. water blown, Methyl Formate, HFOs) took place in the course of 2012 at no cost for the project. Results are under evaluation in order to select the most adequate technology for the conditions in the Philippines. No information is available on overall ICC for the spray applications. - Finalization of conversion of fixed foaming equipment in the first half of 2013. Stakeholders consultation meeting to take place to discuss on the outcomes of the tests on spray foam applications and selection of appropriate technology for spray form conversion. |  | 2010
ONG | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 418 | A | I |  | 3.2 |  | 0 |  | 2008-04-01 | 2008-09-01 | 2009-03-01 | 2009-03-31 |  |  | 81141 | 0 | 81141 | 70593 | 87% | 10548 | 10548 | 10548 | 10548 | 0 | 5696 | 4852 | 4852 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2008: In the operational year 08-09 the following number of technicians are trained: a) in Standard RSE programs: 1716 participants | 2008 |  | 2008
ONG | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 403 | N | I | CFC | 639 | 639 | 0 | 0 | 2006-11-01 | 2012-02-01 | 2008-06-01 | 2013-06-01 |  |  | 167860 | 0 | 167860 | 99961.47 | 59.55% | 67898.53 | 0 | 20369.559 | 12590 | 0 | 7497.408 | 5092.592 | 0 | Remaining recovery and mini-reclaim units were distributed to Railways and Defense departments. | Project targeted for closure in 2013. | 2006 |  | Investment
ONG | UNIDO | Refrigeration servicing sector CFC phase-out plan (sixth tranche) | Multi-Year | ASP | CPR | REF | 59 | INV | 490 | A | I | CFC | 1136 | 1136 |  |  | 2009-11-01 | 2010-10-01 | 2010-11-30 | 2013-04-01 |  |  | 785000 | 0 | 785000 | 667250 | 85% | 117750 | 117750 | 50000 | 58880 | 0 | 50048 | 8832 | 8832 | The report of the survey carried out in Shenzhen has been submitted to UNIDO on 20th September 2012 and is now under evaluation. The Technical Specification for equipment procurement has been finalized on 13th September 2012 and FECO is now carrying out the procurement. Procurement completed. | PCR will be prepared in 3rdQ 2013. Project will be completed in Apr 2013. |  |  | INV
ONG | UNIDO | Refrigeration servicing sector CFC phase-out plan (fourth tranche) | Multi-Year | ASP | CPR | REF | 53 | INV | 453 | A | I | CFC | 793 | 793 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 | 2013-04-01 |  |  | 700000 | 0 | 700000 | 691491.35 | 98.78% | 8508.65 | 4571.3 | 2000 | 52500 | 0 | 51862 | 638 | 343 | The report of the survey carried out in Shenzhen has been submitted to UNIDO on 20th September 2012 and is now under evaluation. The Technical Specification for equipment procurement has been finalized on 13th September 2012 and FECO is now carrying out the procurement. Procurement completed. | PCR will be prepared in 3rdQ 2013. Project will be completed in Apr 2013. |  |  | INV
ONG | UNIDO | Sector plan to phase out HCFC-141b in the foam sector | Multi-Year | ASP | PHI | FOA | 62 | INV | 90 | A | I | HCFC | 40 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2014-06-01 |  |  | 1770650 | 0 | 1770650 | 229299.37 | 12.95% | 1541350.63 | 474642.07 | 1000000 | 132799 | 0 | 17197 | 115602 | 35598 | Contracts were signed in 2012. One existing spray machine (Graco/Gusmer H-20/35) was converted on a pilot basis. Test on other available or H22 technologies (i.e. water blown, Methyl Formate, HFOs) took place in the course of 2012 at no cost for the project. Results are under evaluation in order to select the most adequate technology for the conditions in the Philippines. | Finalization of conversion of fixed foaming equipment is planned for the first half of 2013. Stakeholders consultation meeting to take place to discuss the outcomes of the tests on spray foam applications and selection of appropriate technology. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | FOA | 67 | INV | 03 | A | I | HCFC | 24.9 | 0 |  |  | 2012-07-01 |  | 2013-07-31 | 2014-07-01 |  |  | 1850224 | 0 | 1850224 | 0 | 0% | 1850224 | 0 | 500000 | 129516 | 0 | 0 | 129516 | 0 | The project was approved at the 67th Meeting of the Executive Committee in 2012. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of workshops; assistance to the government on reporting and legislation. |  |  | INV
ONG | UNIDO | Plan for phase-out of ODS in the solvent sector | Individual | LAC | ARG | SOL | 41 | INV | 137 | A | I | CFC CTC TCA | 42 | 54 |  |  | 2003-12-01 | 2004-04-01 | 2009-12-01 | 2013-12-01 |  |  | 635986 | 0 | 635986 | 534347.41 | 84.02% | 101638.59 | 1134.25 | 100000 | 47699 | 0 | 40076 | 7623 | 85 | The survey with the aim to identify residual uses was completed in October 2012. Four companies out of six were already using alternatives and did not require support. However, two companies were still using ODS for certain applications. | The two companies identified are currently converting the processes. Finalization of the project is envisaged for the second half of 2013. Reason for the extension of the project duration: negotiation with one of the companies took longer than expected. |  |  | INV
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100% | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | Completed. PCR submitted Feb. 01. |  |  |  | INV
FIN | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | I | CFC | 14.5 | 19.94 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2005-07-01 |  | 2006-06-01 | 2006-06-01 | 288700 | -22568 | 266132 | 266132 | 100% | 0 | 0 |  | 21653 | -1692.64 | 19960.36 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV
FIN | UNDP | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | Individual | LAC | CHI | STE | 35 | INV | 151 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2005-12-01 | 2007-03-01 | 412741 | -113 | 412628 | 412628 | 100% | 0 | 0 | 0 | 53656.33 | -15.3299 | 53641.0001 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 |  | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | Cancelled - 38th ExCom |  |  |  | INV
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 |  | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | CANCELLED. Funds returned to 27th meeting. |  |  | 1996-11-01 | INV
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 |  | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | Project cancelled. |  |  | 1999-06-01 | INV
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 |  | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | Project cancellation |  |  | 1997-12-01 | INV
CLO | UNIDO | Phase out of 1,1,1 TCA at Teperman | Individual | LAC | BRA | SOL | 20 | INV | 58 | A | R |  | 0 | 0 |  |  | 1996-10-01 |  | 1998-10-01 |  |  | 2000-06-01 | 152176 | -152176 | 0 | 0 |  | 0 | 0 |  | 19783 | -19783 | 0 | 0 | 0 | CLO
CLO | UNIDO | Elimination of 1,1,1 TCA used for autoparts cleaning at Brosol | Individual | LAC | BRA | SOL | 20 | INV | 59 | A | I |  | 0 | 0 |  |  | 1996-10-01 |  | 1997-10-01 |  |  | 1999-03-01 | 178361 | -178361 | 0 | 0 |  | 0 | 0 |  | 23187 | -23187 | 0 | 0 | 0 | CLO
FIN | Germany | Conversion of TCA based cleaning process to non-ODS alternatives at the Kenya Power and Lighting Company | Individual | AFR | KEN | SOL | 39 | INV | 32 | A | I | TCA | 1.9 | 1 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2004-10-01 |  | 2007-12-01 | 2009-09-01 | 85800 | -3112 | 82688 | 82688 | 100% | 0 | 0 | 0 | 11154 | -405 | 10749 | 0 | 0 | PCR was submitted sept 2009
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -183607 | 88550 | 88550 | 100% | 0 | 0 |  | 35380.41 | -23868.91 | 11511.5 | 0 | 0 | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. |  |  |  | INV
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100% | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | 1997-12-01 | INV
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100% | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | Project is completed and closed. PCR submitted. |  |  | 1996-08-01 | INV
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100% | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | Project completed and PCR submitted Jan. 01. |  |  | 1999-06-01 | INV
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100% | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | Complete. |  |  |  | INV
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100% | -0.2 | -0.4 |  | 7396.09 | 0 | 7396.11 | -0.02 | -0.02 | Project completed. |  |  |  | INV
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1996-07-01 | INV
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 100% | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.21 | 0.06 | 0.06 | Project completed. |  |  | 1997-04-01 | INV
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100% | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-08-01 | INV
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV
FIN | UNDP | Elimination of the use of TCA in the Baoshi Electronics Corporation Shijazhuang Manufacturing Operations | Individual | ASP | CPR | SOL | 19 | INV | 172 | N | I | TCA | 7.4 | 7.4 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1998-04-01 |  | 2000-07-01 | 2003-03-01 | 284900 | -7138.15 | 277761.85 | 277762 | 100% | -0.15 | 0 | 0 | 37037 | -928 | 36109.0195 | -0.0195 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Conversion of metal cleaning processes from trichloroethane solvents to non-ODS organic solvents at Ngai Cheong Metal Industries | Individual | ASP | MAL | SOL | 11 | INV | 18 | A | I | TCA | 2 | 2 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-11-01 |  | 1995-04-01 | 1998-12-01 | 63480 | 0 | 63480 | 63480 | 100% | 0 | 0 | 0 | 8252 | 0 | 8252 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Main Plant | Individual | ASP | MAL | SOL | 11 | INV | 19 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-10-01 |  | 1994-05-01 | 1998-12-01 | 113570 | -2661 | 110909 | 110909 | 100% | 0 | 0 | 0 | 14764.1 | -346.1 | 14418 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Port Klang Plant | Individual | ASP | MAL | SOL | 11 | INV | 20 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-10-01 |  | 1995-04-01 | 1998-12-01 | 173280 | 25992 | 199272 | 199272 | 100% | 0 | 0 | 0 | 22526.4 | 3378.6 | 25905 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of the use of 111 TCA in the automobile bumper cleaning processes at Perusahaan Otomobil National Bhd. (Proton) | Individual | ASP | MAL | SOL | 12 | INV | 35 | A | I | TCA | 20 | 20 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1995-12-01 |  | 1995-04-01 | 1998-12-01 | 700439 | -59344 | 641095 | 641095 | 100% | 0 | 0 | 0 | 91057.07 | -7715.07 | 83342 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of 1,1,1 TCA from the precision cleaning processes at Lucas Diesel | Individual | LAC | MEX | SOL | 15 | INV | 36 | A | D | TCA | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-06-01 |  | 1997-07-01 | 1999-12-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 21840 | 0 | 21840 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNIDO | Conversion of ODS cleaning processes from 1,1,1 TCA to aqueous cleaning and using trichlorethane at Elgin Maquinas SA | Individual | LAC | BRA | SOL | 18 | INV | 39 | A | I | TCA | 6 | 6 |  |  | 1995-11-01 | 1996-12-01 | 1997-02-01 |  | 1997-11-01 | 1999-08-01 | 156567 | -6049 | 150518 | 150518 | 100% | 0 | 0 |  | 20354 | -818 | 19536 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used as solvent at Rodabras | Individual | LAC | BRA | SOL | 20 | INV | 60 | A | I | TCA | 4.2 | 4.2 |  |  | 1996-10-01 | 1998-09-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 151577 | -75 | 151502 | 151502 | 100% | 0 | 0 |  | 19705 | -41 | 19664 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used for the formulation of tapping fluids at Tapmatic | Individual | LAC | BRA | SOL | 20 | INV | 61 | A | I | TCA | 9.9 | 9.9 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1997-12-01 | 2001-12-01 | 194500 | -27382 | 167118 | 167117.55 | 100% | 0.45 | 0 |  | 25285 | -3594 | 21691 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Siltal | Individual | AFR | EGY | SOL | 18 | INV | 54 | A | I | TCA | 2 | 2 |  |  | 1995-11-01 | 1997-11-01 | 1996-06-01 |  | 1998-10-01 | 2000-07-01 | 48784 | -419 | 48365 | 48365 | 100% | 0 | 0 |  | 6342 | -65 | 6277 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Technopol | Individual | AFR | EGY | SOL | 19 | INV | 56 | A | I | TCA | 6 | 6 |  |  | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2000-05-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282 | 0 | 16282 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to cleaning in perchloroethylene at Abbasol | Individual | AFR | EGY | SOL | 19 | INV | 57 | A | I | TCA | 8 | 8 |  |  | 1996-05-01 | 1998-10-01 | 1997-05-01 |  | 1998-12-01 | 1999-07-01 | 154544 | 0 | 154544 | 154544 | 100% | 0 | 0 |  | 20091 | 0 | 20091 | 0 | 0 | FIN
FIN | UNIDO | Conversion of TCA used for the formulation of degreasing and contact cleaners and crack detectors to new formulations with special hydrocarbons and heavy chlorinated ester at Sien | Individual | AFR | EGY | SOL | 28 | INV | 79 | A | I | TCA | 9 | 9 |  |  | 1999-07-01 | 2000-11-01 | 2000-08-01 |  | 2002-06-01 | 2003-10-01 | 231435 | 0 | 231435 | 231435.42 | 100% | -0.42 | 0 |  | 30087 | -34 | 30053 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at Maasara Co. for engineering industries | Individual | AFR | EGY | SOL | 31 | INV | 80 | A | I | TCA | 10.7 | 10.7 |  |  | 2000-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-12-01 | 2004-03-01 | 294950 | 0 | 294950 | 294950.23 | 100% | -0.23 | 0 |  | 38344 | -4 | 38340 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the King Hussein Workshop, Zarqa | Individual | ASP | JOR | SOL | 34 | INV | 75 | A | I | TCA | 6.4 | 6.4 |  |  | 2001-07-01 | 2002-12-01 | 2003-02-01 |  | 2003-12-01 | 2004-10-01 | 191316 | 0 | 191316 | 191316.01 | 100% | -0.01 | 0 |  | 24871 | 0 | 24871 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the Royal Jordanian Air Force | Individual | ASP | JOR | SOL | 37 | INV | 76 | A | I | TCA | 10.4 | 10.4 |  |  | 2002-07-01 | 2003-11-01 | 2004-08-01 |  | 2005-12-01 | 2007-01-01 | 342757 | -17 | 342740 | 342740.39 | 100% | -0.39 | 0 |  | 44558 | -2 | 44556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of ODS cleaning processes from TCA to aqueous cleaning and cleaning in TCE at Kenyan Railways Central Workshop | Individual | AFR | KEN | SOL | 23 | INV | 14 | A | I | TCA | 6 | 6 |  |  | 1997-11-01 | 1998-08-01 | 1998-12-01 |  | 1999-12-01 | 2002-09-01 | 205524 | 0 | 205524 | 205524.21 | 100% | -0.21 | 0 |  | 26718 | 0 | 26718 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Faber Castell | Individual | LAC | PER | SOL | 20 | INV | 18 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-11-01 | 1997-10-01 |  | 1998-09-01 | 2000-12-01 | 16409 | -4827 | 11582 | 11582 | 100% | 0 | 0 |  | 2133 | -630 | 1503 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Carbolan | Individual | LAC | PER | SOL | 20 | INV | 19 | A | I | TCA | 0.4 | 0.4 |  |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 31457 | -7307 | 24150 | 24150 | 100% | 0 | 0 |  | 4089 | -954 | 3135 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Papeles Industriales | Individual | LAC | PER | SOL | 20 | INV | 20 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-12-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 47953 | -957 | 46996 | 46996 | 100% | 0 | 0 |  | 6234 | -134 | 6100 | 0 | 0 | FIN
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichloroethane (TCA) production (second stage programme) | Multiyear | ASP | CPR | PRO | 56 | INV | 480 | N | I | TCA | 0 | 0 | 79.2 | 79.2 | 2008-11-01 | 2010-11-01 | 2010-11-30 |  | 2010-11-01 | 2010-11-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | Fully completed. |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | I | TCA | 0 | 0 | 33.8 | 33.8 | 2004-07-01 | 2005-12-01 | 2008-07-01 |  | 2008-07-01 | 2010-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 105000 | 0 | 105000 | 0 | 0 | Fully completed. |  |  |  | INV
CLO | Canada | Feasibility study to establish a refrigerant conservation programme in Sichuan Province | Individual | ASP | CPR | REF | 14 | TAS | 81 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  |  | 1997-06-01 | 58400 | -58400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 04 | TAS | 135 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 |  |  |  |  | Non-INV
CLO | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | AFR | ETH | SOL | 45 | TAS | 15 | A | I | CTC TCA | 5.4 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  |  | 2007-12-01 | 40000 | -35474 | 4526 | 4526.08 | 100% | -0.08 | 0 |  | 3600 | -3193 | 407 | 0 | 0 | CLO |  |  |  | INV
COM | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Multi-Year | EUR | EUR | SEV | 60 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-04-01 |  | 2012-10-01 |  | 80500 | 0 | 80500 | 77615 | 96.42% | 2885 | 2885 | 2885 | 10465 | 0 | 10090 | 375 | 375 | ECA enforcement meetings took place in 2009 in Budapest and in 2010 in Turkmenistan. Since no follow-up project was approved for the period 2011-2012, the ECA network decided to hold probably the last ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012, partly financed from the ECA regional enforcement project and partly from the ECA network budget. In 2012, ECA enforcement activities were mainly implemented through the ECA network including the promotion of iPIC, analysis of discrepancies of reported exports to a destination country and reported consumption (Article 7) of the importing country in cooperation with the Ozone Secretariat. Customs & Enforcement Officers from China, European Union, Finland, Kyrgyzstan, Macedonia FYR, Russia, Serbia and Uzbekistan received the Ozone Protection Award 2012. During the period of July 2010 and August 2012, the award winners reported 17 successful seizures of 72 pieces of equipments and 3016 refrigerant cylinders / containers containing more than 61 metric tons of ozone-depleting chemicals and mixtures. Informal Prior Informed Consent (iPIC) consultations prior to the issuance of trade licenses avoided 16 unwanted / illegal shipments of more than 342 metric tons of ozone-depleting chemicals and mixtures. iPIC consultations and analysis of data discrepancies also revealed illegal trade of 103,5 MT which had taken place in the past. The award ceremony took place during the ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012. The ECA network maintained close cooperation maintained with WCO and its RILOs, EIA, SECI, UNCTAD, OSCE, Environment for Security and key trade partners including the European Union and China. | PCR has been submitted in March 2013. | 2010 |  | 2010
COM | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Multi-Year | EUR | EUR | SEV | 57 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 |  | 80500 | 0 | 80500 | 80500 | 100% | 0 | 0 | 0 | 10465 | 0 | 10465 | 0 | 0 | ECA enforcement meetings took place in 2009 in Budapest and in 2010 in Turkmenistan. Since no follow-up project was approved for the period 2011-2012, the ECA network decided to hold probably the last ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012, partly financed from the ECA regional enforcement project and partly from the ECA network budget. In 2012, ECA enforcement activities were mainly implemented through the ECA network including the promotion of iPIC, analysis of discrepancies of reported exports to a destination country and reported consumption (Article 7) of the importing country in cooperation with the Ozone Secretariat. Customs & Enforcement Officers from China, European Union, Finland, Kyrgyzstan, Macedonia FYR, Russia, Serbia and Uzbekistan received the Ozone Protection Award 2012. During the period of July 2010 and August 2012, the award winners reported 17 successful seizures of 72 pieces of equipments and 3016 refrigerant cylinders / containers containing more than 61 metric tons of ozone-depleting chemicals and mixtures. Informal Prior Informed Consent (iPIC) consultations prior to the issuance of trade licenses avoided 16 unwanted / illegal shipments of more than 342 metric tons of ozone-depleting chemicals and mixtures. iPIC consultations and analysis of data discrepancies also revealed illegal trade of 103,5 MT which had taken place in the past. The award ceremony took place during the ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012. The ECA network maintained close cooperation maintained with WCO and its RILOs, EIA, SECI, UNCTAD, OSCE, Environment for Security and key trade partners including the European Union and China. | PCR has been submitted in March 2013. | 2009 |  | 2009
COM | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Individual | AFR | NIR | SEV | 38 | TAS | 104 | A | I | CFC | 5.6 |  | 0 |  | 2002-11-01 | 2004-12-01 | 2003-11-01 |  | 2008-10-01 |  | 68000 | -60900 | 7100 | 7100 | 100% | 0 | 25000 | 60900 | 8840 | -7917 | 923 | 0 | 3250 | The remaining fund will be used for mission of the NOU and relevant national expert to Japan to review the program. |  | 2002
COM | Portugal | Communication and cooperation support to Portuguese speaking countries (Angola, Cape Verde, East Timor, Guinea Bissau, Mozambique and Sao Tome and Principe) | Individual | GLO | GLO | SEV | 47 | TAS | 269 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2011-07-01 |  | 90000 | 0 | 90000 | 47743 | 53.05% | 42257 | 31324 | 10933 | 11700 | 0 | 0 | 11700 | 0 | The education pack for primary schools were distributed to all Portuguese-speaking African countries in March 2011, The OzonAction Education pack for Secondary Schools will be translated and it will be distributed electronically in June 2011.
COM | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | AFR | AFR | FUM | 38 | TAS | 32 | A | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 |  | 2011-12-01 |  | 550000 | 0 | 550000 | 547888.17 | 99.62% | 2111.83 | 0 | 1689.464 | 70500 | 0 | 70229.3018 | 270.6982 | 0 | Completed in 2011. Only remaining activities for Sudan where the second phase of fumigation demonstration on three sites have been done. Demonstrations and trainings are completed. Still awaiting delivery of small items (masks, dosing meters, etc to be able to financially close the project. | Some invoices still pending. | 2002 |  | Non-Investment
COM | UNEP | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-07-01 |  | 160000 | 0 | 160000 | 150640 | 94.15% | 9360 | 0 | 9360 | 20800 | 0 | 19583.2 | 1216.8 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Monitoring the activities in the refrigeration servicing subsector | Individual | ASP | DRK | REF | 40 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 |  | 10000 | 0 | 10000 | 5000 | 50% | 5000 | 0 | 5000 | 1300 | 0 | 650 | 650 | 0 | Project completed |  |  |  | Non Investment
COM | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Individual | EUR | EUR | SEV | 60 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2012-04-01 | 2011-04-01 |  | 2012-10-01 |  | 27500 | 0 | 27500 | 27500 | 100% | 0 | 0 | 0 | 3575 | 0 | 3575 | 0 | 0 | Project completed. ECA enforcement meetings took place in 2009 in Budapest and in 2010 in Turkmenistan. Since no follow-up project was approved for the period 2011-2012, the ECA network decided to hold probably the last ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012, partly financed from the ECA regional enforcement project and partly from the ECA network budget. In 2012, ECA enforcement activities were mainly implemented through the ECA network including the promotion of iPIC, analysis of discrepancies of reported exports to a destination country and reported consumption (Article 7) of the importing country in cooperation with the Ozone Secretariat. Customs & Enforcement Officers from China, European Union, Finland, Kyrgyzstan, Macedonia FYR, Russia, Serbia and Uzbekistan received the Ozone Protection Award 2012. During the period of July 2010 and August 2012, the award winners reported 17 successful seizures of 72 pieces of equipment and 3016 refrigerant cylinders / containers containing more than 61 metric tons of ozone-depleting chemicals and mixtures. Informal Prior Informed Consent (iPIC) consultations prior to the issuance of trade licenses avoided 16 unwanted / illegal shipments of more than 342 metric tons of ozone-depleting chemicals and mixtures. iPIC consultations and analysis of data discrepancies also revealed illegal trade of 103,5 MT which had taken place in the past. The award ceremony took place during the ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012. The ECA network maintained close cooperation maintained with WCO and its RILOs, EIA, SECI, UNCTAD, OSCE, Environment for Security and key trade partners including the European Union and China. | PCR for all tranches submitted in March 2013 |  |  | Non Investment
COM | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Individual | EUR | EUR | SEV | 57 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 |  | 51250 | 0 | 51250 | 51250 | 100% | 0 | 0 | 0 | 6663 | 0 | 6663 | 0 | 0 | ECA enforcement meetings took place in 2009 in Budapest and in 2010 in Turkmenistan. Since no follow-up project was approved for the period 2011-2012, the ECA network decided to hold probably the last ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012, partly financed from the ECA regional enforcement project and partly from the ECA network budget. In 2012, ECA enforcement activities were mainly implemented through the ECA network including the promotion of iPIC, analysis of discrepancies of reported exports to a destination country and reported consumption (Article 7) of the importing country in cooperation with the Ozone Secretariat. Customs & Enforcement Officers from China, European Union, Finland, Kyrgyzstan, Macedonia FYR, Russia, Serbia and Uzbekistan received the Ozone Protection Award 2012. During the period of July 2010 and August 2012, the award winners reported 17 successful seizures of 72 pieces of equipment and 3016 refrigerant cylinders / containers containing more than 61 metric tons of ozone-depleting chemicals and mixtures. Informal Prior Informed Consent (iPIC) consultations prior to the issuance of trade licenses avoided 16 unwanted / illegal shipments of more than 342 metric tons of ozone-depleting chemicals and mixtures. iPIC consultations and analysis of data discrepancies also revealed illegal trade of 103,5 MT which had taken place in the past. The award ceremony took place during the ECA customs cooperation meeting in Istanbul, Turkey, 9-11 October 2012. The ECA network maintained close cooperation maintained with WCO and its RILOs, EIA, SECI, UNCTAD, OSCE, Environment for Security and key trade partners including the European Union and China. | PCR for all tranches submitted in March 2013 |  |  | Non Investment
COM | UNEP | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-02-01 | 2008-03-01 |  | 2011-02-01 |  | 80000 | 0 | 80000 | 35128 | 43.91% | 44872 | 0 | 44872 | 10400 | 0 | 4566.64 | 5833.36 | 0 | Project completed |  |  | 2009-10-01 | Non Investment
COM | UNEP | Formulation of national phase-out strategy | Individual | AFR | SOM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2002-08-01 |  | 2010-12-01 |  | 60000 | 0 | 60000 | 35098 | 58.5% | 24902 | 0 | 24902 | 7800 | 0 | 4562.74 | 3237.26 | 0 | Project completed |  |  | 2003-12-01 | Non Investment
FIN | Australia | Indonesian ODS control policy | Individual | ASP | IDS | SEV | 17 | TAS | 33 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-05-01 | 1996-01-01 |  | 1996-01-01 | 1996-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Canada | Halon recycling and bank management | Halon Banking | LAC | BRA | HAL | 19 | TAS | 47 | A | I |  | 21.3 | 21.3 | 0 |  | 1996-05-01 | 1996-10-01 | 1998-05-01 |  | 1999-05-01 | 1999-05-01 | 499360 | -20031 | 479329 | 479329 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented although one year later than planned. Adjustment results of exchange rate fluctuations |  | 1996 | 1998-09-01 | Non-Inv.
FIN | Canada | No-clean technology programme | Individual | ASP | CPR | SOL | 14 | TAS | 82 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  | 1994-11-01 | 1995-09-01 | 51100 | 0 | 51100 | 51100 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | GEO | FUM | 30 | TAS | 07 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-01-01 | 2004-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 2000 |  | Non-Inv.
FIN | Canada | Promoting compliance with the Montreal Protocol in countries with economies in transition (CEITs) | Individual | EUR | GEO | SEV | 27 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-03-01 |  | 2001-10-01 | 2002-06-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Translation, in French and Spanish, of the approved manual on Customs Officer Training on Substances that Deplete the Ozone Layer | Individual | GLO | GLO | SEV | 32 | TAS | 213 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2001-07-01 |  | 2002-02-01 | 2002-03-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  | 0 | 1440 | 0 | 1440 | 0 |  | Translation of manual into Spanish and French completed in early 2002. Both manuals were printed and disseminated in 2002. Project Completed. |  | 2000 |  | Non-Inv.
FIN | Canada | Initiative to help phase out the release of ODS by Asian SMEs | Individual | ASP | IND | SEV | 15 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1996-02-01 | 1996-02-01 | 109780 | 0 | 109780 | 109780 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 38 | A | I |  | 0 | 0 | 0 |  | 2007-03-01 | 2008-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 6500 | 0 | 6500 | 0 |  | This project is implemented by UNEP on behalf of Canada. A study on illegal tradeof ODS in the region was completed in June 2009 and presented to participants to UNEP LAC Network meeting in october 2009. Countries opted to test the informal Prior Informed Consent (iPIC) form as a tool to control illegal trade of ODS. Work initiated at the end of the year to complete iPIC forms for all participating countries. This last activity of the project was completed by the end of 2010. |  | 2007 | 2009-12-01 | Non-Inv.
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | MOL | FUM | 30 | TAS | 06 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-04-01 | 2004-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2004. PCR submitted |  | 2000 |  | Non-Inv.
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | Non-Inv.
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | Non-Inv.
FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | AFR | AFR | REF | 32 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-07-01 | 2002-07-01 |  | 2002-12-01 | 2002-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. Final report sent to the Secretariat in Mai 2003.
FIN | France | Technical assistance in air conditioning |  | AFR | GHA | REF | 27 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2001-04-01 | 2001-04-01 | 31500 | -5121 | 26379 | 26379 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le Ghana a présenté avec l'aide du PNUD un projet utilisant les 50% restant dans le cadre du Plan de Gestion des Réfrigérants. Il n'est donc plus possible de présenter de projets avant 2007 dans ce pays.
FIN | France | Small and medium enterprises study |  | ASP | IRA | SEV | 26 | TAS | 36 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 2002-05-01 | 1999-12-01 |  | 2005-04-01 | 2005-04-01 | 75000 | -55000 | 20000 | 20000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Closed as per decision 45/12, financial closure to be finalised. |  |  | 2002-12-01
FIN | France | Documentary on traffic in second-hand refrigerators |  | AFR | IVC | REF | 27 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-04-01 | 2000-06-01 |  | 1999-07-01 | 1999-07-01 | 12000 | -2381 | 9619 | 9619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Technical assistance in air-conditioning |  | ASP | JOR | REF | 27 | TAS | 46 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-06-01 | 2002-06-01 | 42000 | -31575 | 10425 | 10425 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le rapport d'enquête a été achevé. D'un commun accord avec le Gouvernement jordanien, le projet sera transféré à la Banque Mondiale. |  |  | 2001-11-01
FIN | France | Projects preparation and technical assistance in the foam sector |  | ASP | LEB | FOA | 19 | TAS | 07 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-08-01 | 1996-09-01 | 20000 | -495 | 19505 | 19505 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 29 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-08-01 |  | 45750 | -20966 | 24784 | 24784 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The study was completed and a draft report was handed over to the NOU (08/2001). Remaining activities could be carried out at the same time than the R&R project.Project completed.
FIN | France | Conversion of CFC-based commercial refrigeration installations in the fishing industry |  | AFR | MAU | REF | 14 | TAS | 05 | A | D | CFC | 2 |  | 0 |  | 1994-09-01 | 1999-07-01 | 1996-09-01 |  | 2000-11-01 | 2000-12-01 | 106900 | -7378 | 99522 | 99522 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-06-01
FIN | France | Technical assistance on alternative technologies for cold storage facilities |  | AFR | MOR | REF | 20 | TAS | 05 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1999-10-01 | 1999-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Technical assistance for cold storage equipment (training and demonstration project) |  | AFR | MOR | REF | 32 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-08-01 | 2012-12-01 | 114337 | 0 | 114337 | 114337 | 100% | 0 |  | 0 | 5717 | 0 | 5717 | 0 |  | Project completed
FIN | France | Technical assistance in the air-conditioning sector |  | ASP | SYR | REF | 26 | TAS | 37 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 30000 | -4018 | 25982 | 25982 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | -5500 | 34500 | 34500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | Germany | Promoting compliance with the Montreal Protocol in countries with economies in transition (Croatia and Romania) | Individual | EUR | EUR | SEV | 28 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2001-08-01 | 2003-10-01 | 67800 | -6900 | 60900 | 60900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 288 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2004-04-01 | 2004-04-01 | 240200 | 0 | 240200 | 240200 | 100% | 0 | 0 | 0 | 31226 | 0 | 31226 | 0 | 0 | India's National CFC consumption Phase-Out Plan with special refeence to the Refrigeration Service Sector was approved at the 42nd ExCom (IND/REF/42/INV/369).
FIN | Germany | Project preparation for the RMP update | RMP Update | AFR | KEN | REF | 36 | TAS | 27 | A | I |  | 203.6 |  | 0 |  | 2002-03-01 | 2003-06-01 | 2003-03-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A TPMP developed through the preparation process was approved at the 44th ExCom
FIN | Germany | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | RMP | ASP | LEB | REF | 28 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2001-11-01 | 2003-10-01 | 37550 | -3 | 37547 | 37547 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Development of a suitable strategy for the long term management of HCFCs, in particular HCFC-22 | Individual | ASP | CPR | REF | 43 | TAS | 414 | A | I |  | 0 | 0 | 0 |  | 2004-07-01 | 2004-11-01 | 2005-12-01 |  | 2007-03-01 | 2008-12-01 | 300300 | -2.8 | 300297.2 | 300297 | 100% | 0.2 | 0 | 0 | 39039 | -0.36 | 39039 | -0.36 | 0 | Project was completed and approved by the Chinese authorities. Project report was submitted to 51st ExCom. PCR was submitted in December 2008.
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 07 | TAS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-06-30 | Non-INV
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 07 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 100% | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-07-31 | Non-INV
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. |  |  |  | Non-INV
FIN | IBRD | Development of strategy/methodology for ODS disposal |  | GLO | GLO | DES | 55 | TAS | 291 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2010-05-01 | 2010-09-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Final study completed by the consultant, printed, distributed and posted on the internet. Companion piece drawing from the study that targets ozone nnits also completed. |  |  |  | Non-INV
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 08 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. |  |  |  | Non-INV
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | 1997-06-01 | Non-INV
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV
FIN | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 |  | 2006-12-01 | 2006-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Gov. of Indonesia made great progress in improving import licensing and quota system to monitor and control ODS import. Revised draft to existing regulation agreed upon by Ministry of Trade and other relevant government depts. New regulation adopted on June 22, 2006. Old regulation with provision that only one company can import ODS declared void. Standard Operating Procedures drafted to provide guidance for implementation of new regulation. Project completed. |  |  |  | INV
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | 1994-06-01 | Non-INV
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 09 | TAS | 17 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project and PCR completed. |  |  | 1999-12-01 | Non-INV
FIN | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 | 2005-03-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project preparation completed. Strategy approved at the 44th ExCom. |  |  |  | Non-INV
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 08 | TAS | 08 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. |  |  |  | Non-INV
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | Individual | ASP | ASP | SEV | 38 | TAS | 49 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-06-01 | 2003-11-01 |  | 2004-03-01 | 2005-11-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 | 0 | 16250 | 0 | 16250 | 0 | 0 | Mongolia: Public awareness and IEC activities; Task Force Meeting China/Mongolia August 2003 / Iran: 15-02-04 National Consultation Meeting. Some funds were also used for building urgent capacity in the two new Parties Afghanistan and Bhutan as part of UN |  | 2002 |  | Non-Investment
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region | Individual | ASP | ASP | SEV | 34 | TAS | 41 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 148500 | 0 | 148500 | 148500 | 100% | 0 | 0 | 0 | 19305 | 0 | 19305 | 0 | 0 | Project completed in May 2003. Balance of 25,000 USD transferred to Phase II for partly covering activities in Mongolia |  | 2001 |  | Non-Investment
FIN | Japan | Develop a strategy for the refrigeration servicing sector | Individual | ASP | CPR | REF | 31 | TAS | 359 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-07-01 | 2001-12-01 |  | 2003-12-01 | 2005-06-01 | 350000 | -1376 | 348624 | 348624 | 100% | 0 | 0 | 0 | 45500 | -179 | 45321 | 0 | 0 | Completed the data survey for the four sub-sectors and developed the first draft strategy. The national workshop was organized in July 2002 to review the draft. The second draft is being prepared as per comments received from the workshop and other source |  | 2000
FIN | Singapore | Regional methyl chloroform elimination programme for ASEAN countries |  | ASP | ASP | SOL | 11 | TAS | 12 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 |  | 1995-03-01 |  | 31976 | 0 | 31976 | 31976 | 100% | 0 | [5 empty] | 0 |  |  |  | 93
FIN | Sweden | Regional cooperation for monitoring and control of ODS consumption | Individual | ASP | ASP | SEV | 34 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-03-01 | 2005-04-01 |  | 2006-12-01 | 2008-05-01 | 250000 | 155818 | 405818 | 405818 | 100% | 0 | 0 | 0 | 0 | 20256 | 20256 | 0 | 0 | The final financial report was received from UNEP in May 2008. The final report reported a balance of USD 49,926. In July 2008 the MLF confirmed the return of the same amount as part of the Swedish contribution to the MLF. |  | 2002
FIN | Switzerland | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-04-01 | 2003-04-01 | 70796 | 0 | 70796 | 70796 | 100% | 0 | 0 | 0 | 9204 | 0 | 9204 | 0 | 0 |  |  | 2000
FIN | UNDP | Methyl bromide data collection for Africa | Individual | AFR | AFR | FUM | 17 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 |  | 1998-04-01 | 2000-12-01 | 179850 | 0 | 179850 | 179850 | 100% | 0 | 0 | 0 | 23381 | 0 | 23381 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Non-Investment
FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | AFR | AFR | SEV | 36 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-11-01 | 2005-10-01 | 30000 | -145.9989 | 29854.0011 | 29854 | 100% | 0.0011 | 0 | 0 | 3900 | -18.9999 | 3881 | 0.000143 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Technical assistance to prepare a national halon programme | Individual | LAC | ARG | HAL | 13 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-01-01 |  | 1996-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 2000-12-01 | 102000 | -64974 | 37026 | 37026 | 100% | 0 | 0 | 0 | 13260 | -8447 | 4813 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | BRA | REF | 32 | TAS | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2003-07-01 | 100000 | -1 | 99999 | 99999 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | BRA | SEV | 23 | TAS | 85 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1999-05-01 |  | 2000-07-01 | 2009-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2000. Financially completed in 2009. |  | 1997 |  | Non-Investment
FIN | UNDP | Technical assistance to phase-out ozone depleting solvents | Individual | LAC | CHI | SOL | 41 | TAS | 154 | N | I | CFC/TCA/CTC | 17.1 | 17.1 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-07-01 | 245690 | -15287.88 | 230402.12 | 230402.12 | 100% | 0 | 0 | 0 | 22112 | -1375.9 | 20736.1 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COL | REF | 32 | TAS | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2003-12-01 | 2005-10-01 | 40000 | -2578.0041 | 37421.9959 | 37422 | 100% | -0.0041 | 0 | 0 | 5200 | -335.0005 | 4865 | -0.00053302 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 | 2003-01-01 | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COS | REF | 32 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2005-12-01 | 2010-10-01 | 40000 | -14642.37 | 25357.63 | 25357.63 | 100% | 0 | 0 | 0 | 5200 | -1903.5081 | 3296.4919 | 0 | 0 | Financially completed in 2010. |  | 2000 | 2003-01-01 | Non-Investment
FIN | UNDP | Technical assistance for Guandong aerosols investment project and investigation of non-ODS filling technology and LPG purification | Individual | ASP | CPR | ARS | 06 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1996-12-01 | 1998-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100% | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in rigid polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | CPR | FOA | 10 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-05-01 | 1994-06-01 |  | 1997-07-01 | 2000-06-01 | 200000 | -574 | 199426 | 199426 | 100% | 0 | 0 | 0 | 26000 | -75 | 25925 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Technical assistance for the Beijing Household Electric Appliances Research Institute (Bheari) | Individual | ASP | CPR | FOA | 09 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-10-01 | 1995-06-01 |  | 1998-10-01 | 2003-07-01 | 0 | 444945 | 444945 | 444945 | 100% | 0 | 0 | 0 | 0 | 57843 | 57843 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Survey of production and consumption of methyl bromide in China | Individual | ASP | CPR | FUM | 12 | TAS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-03-01 |  | 1998-10-01 | 2001-12-01 | 87000 | -1791 | 85209 | 85209 | 100% | 0 | 0 | 0 | 11310 | -232 | 11078 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical study on halons usage and applications of halons substitutes | Individual | ASP | CPR | HAL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 40000 | 3345 | 43345 | 43345 | 100% | 0 | 0 | 0 | 5200 | 435 | 5635 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: current situation, revision of national codes, and education and training | Individual | ASP | CPR | HAL | 10 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1996-06-01 |  | 1998-09-01 | 2000-12-01 | 280000 | -24125 | 255875 | 255875 | 100% | 0 | 0 | 0 | 36400 | -3136 | 33264 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: transfer of technology on alternatives to halon fire protection systems | Individual | ASP | CPR | HAL | 10 | TAS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-11-01 | 1996-06-01 |  | 1999-06-01 | 2000-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-06-01 | Non-Investment
FIN | UNDP | Establishment of a quality control testing plant for using CFC-12 substitute technology in refrigeration and rigid foams | Individual | ASP | CPR | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-12-01 | 1993-12-01 |  | 1998-06-01 | 1998-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Import and promotion of applications for CFC substitute chemicals in the refrigeration sector in Southern China | RMP-Component | ASP | CPR | REF | 09 | TAS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1994-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Revision of design standards for cold storage | RMP-Component | ASP | CPR | REF | 10 | TAS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-01-01 | 1994-09-01 |  | 1999-03-01 | 2000-12-01 | 200000 | -18764.2 | 181235.8 | 181236 | 100% | -0.2 | 0 | 0 | 26000 | -2438.996 | 23561.03 | -0.026 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-03-01 | Non-Investment
FIN | UNDP | Pre-feasibility study to phase-out CFC-113 in electronic cleaning in four production lines | Individual | ASP | CPR | SOL | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-10-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 40000 | 1829 | 41829 | 41829 | 100% | 0 | 0 | 0 | 5200 | 238 | 5438 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Preparation of a sectoral financing plan for the solvents sector | Individual | ASP | CPR | SOL | 21 | TAS | 192 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2003-07-01 | 200000 | -19236 | 180764 | 180764 | 100% | 0 | 0 | 0 | 26000 | -2501 | 23499 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Cleaning applications deployment center for replication of ODS-free process across China | Individual | ASP | CPR | SOL | 12 | TAS | 61 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-03-01 | 1995-03-01 |  | 1998-05-01 | 2000-12-01 | 489400 | -66345.28 | 423054.72 | 423055 | 100% | -0.28 | 0 | 0 | 63622 | -8624.9964 | 54997.04 | -0.0364 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Non-Investment
FIN | UNDP | Development of MDI transition strategies | Individual | LAC | CUB | ARS | 36 | TAS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2004-03-01 | 2008-08-01 | 30000 | -5998 | 24002 | 24002 | 100% | 0 | 0 | 0 | 3900 | -780 | 3120 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Development of an ODS phase out strategy in the refrigeration sector | RMP-Component | LAC | CUB | REF | 13 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-07-01 |  | 1997-09-01 | 1998-12-01 | 30000 | -10000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3900 | -1300 | 2600 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance to prepare a national halon action plan and project development | Individual | AFR | EGY | HAL | 12 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-01-01 |  | 1997-03-01 | 1998-12-01 | 25000 | 1730 | 26730 | 26730 | 100% | 0 | 0 | 0 | 3250 | 225 | 3475 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 17 | N | I | MeBr | 2.1 | 2.1 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2008-12-01 |  | 2011-10-01 | 2012-06-01 | 50000 | -1096.64 | 48903.36 | 48903.36 | 100% | 0 | 0 | 0 | 4500 | -98.7 | 4401.3 | 0 | 0 | Financially completed in 2012. | The project was financially closed at the end of February 12. | 2005 |  | Non-Investment
FIN | UNDP | Technical assistance for technology transfer for phase-out of CFC-11 in flexible foam | Individual | AFR | GHA | FOA | 08 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1994-10-01 |  | 1995-06-01 | 1997-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for the CTC sector | Individual | AFR | GHA | SOL | 44 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 20000 | -284 | 19716 | 19716 | 100% | 0 | 0 | 0 | 1800 | -26 | 1774 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Technical assistance in aerosol sector | Individual | GLO | GLO | ARS | 06 | TAS | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-02-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Safety pre-assessment and post-assessment of foam and solvent projects implemented by UNDP | Individual | GLO | GLO | FOA | 12 | TAS | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 3000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3250 | 390 | 3640 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance in flexible polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Determination of cost-effective phase-out approaches for enterprises with relatively small ODS use in foams | Individual | GLO | GLO | FOA | 14 | TAS | 71 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-09-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance in rigid polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-01-01 |  | 1993-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Analysis and formulation of a halon action plan and phase out strategy for small consuming countries | Individual | GLO | GLO | HAL | 13 | TAS | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance in halons | Individual | GLO | GLO | HAL | 06 | TAS | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-01-01 |  | 1994-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global halon project | Individual | GLO | GLO | HAL | 08 | TAS | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1995-10-01 |  | 1997-12-01 | 1999-05-01 | 345133 | 0 | 345133 | 345133 | 100% | 0 | 0 | 0 | 44867 | 0 | 44867 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in MAC | RMP-Component | GLO | GLO | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1998-01-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in refrigeration sector | RMP-Component | GLO | GLO | REF | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1994-02-01 |  | 1994-09-01 | 1997-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global MAC project: Phase III | RMP-Component | GLO | GLO | REF | 24 | TAS | 159 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2002-12-01 | 2003-12-01 | 250000 | -63356 | 186644 | 186644 | 100% | 0 | 0 | 0 | 32500 | -8236 | 24264 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Global MAC project | RMP-Component | GLO | GLO | REF | 08 | TAS | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1995-10-01 |  | 1995-12-01 | 1997-12-01 | 318584 | 0 | 318584 | 318584 | 100% | 0 | 0 | 0 | 41416 | 0 | 41416 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in solvents | Individual | GLO | GLO | SOL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | MDI Transitional Strategy | Individual | ASP | IND | ARS | 41 | TAS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2008-07-01 | 2011-11-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 2250 | -2250 | 0 | 0 | 0 | Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | Individual | ASP | IND | ARS | 29 | TAS | 244 | A | I | CFC | 125 | 125 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2004-09-01 | 2008-04-01 | 155000 | -16537 | 138463 | 138463 | 100% | 0 | 0 | 0 | 20150 | -2150 | 18000 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | IND | FOA | 13 | TAS | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1998-07-01 | 1995-07-01 |  | 1999-12-01 | 2003-05-01 | 200000 | -1396 | 198604 | 198604 | 100% | 0 | 0 | 0 | 26000 | -182 | 25818 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | Individual | ASP | IND | HAL | 29 | TAS | 243 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2002-12-01 |  | 2005-12-01 | 2007-03-01 | 88000 | -3435 | 84565 | 84565 | 100% | 0 | 0 | 0 | 11440 | -447 | 10993 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Demonstration and evaluation of alternative technology for halon fire protection system and technical assistance for sectoral strategy for ODS phase out | Individual | ASP | IND | HAL | 13 | DEM | 28 | N | I | HAL | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-01 | 1997-07-01 |  | 1999-12-01 | 2003-02-01 | 309000 | -44111 | 264889 | 264889 | 100% | 0 | 0 | 0 | 40170 | -5734 | 34436 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Non-Investment
FIN | UNDP | Technical assistance to Ozone Cell, MOEF during the preparation of a refrigeration and air conditioning servicing sector strategy | RMP-Component | ASP | IND | REF | 32 | TAS | 279 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-07-01 | 2005-09-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 | 0 | 3900 | -478 | 3422 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | UNDP | Technical assistance umbrella project to phase out ODS solvent use | Individual | LAC | JAM | SOL | 42 | TAS | 20 | N | I | TCA | 0.8 | 0.8 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2006-12-01 | 2011-08-01 | 25000 | -3609.49 | 21390.51 | 21390.51 | 100% | 0 | 0 | 0 | 2250 | -324.85 | 1925.15 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Feasibility study on deodorization of local gas as a CFC substitute in cosmetics | Individual | ASP | JOR | ARS | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance and pre-feasibility study in aerosol sector | Individual | ASP | JOR | ARS | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Technical assistance project to install alternatives and phase-out methyl bromide | One-off-Phaseout | ASP | KYR | FUM | 41 | TAS | 08 | N | I | MeBr | 14.2 | 14.2 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2008-12-01 |  | 2007-12-01 | 2009-08-01 | 300000 | -407 | 299593 | 299593.04 | 100% | -0.04 | 0 | 0 | 22500 | -30.525 | 22469.478 | -0.003 | 0 | Completed in 2007.Financially completed in 2009. |  | 2003 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 1998-12-01 | 57700 | 0 | 57700 | 57700 | 100% | 0 | 0 | 0 | 7501 | 0 | 7501 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Non-Investment
FIN | UNDP | Safety and technical programme to aid manufacturers of aerosol products | Individual | ASP | MAL | ARS | 12 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1996-03-01 |  | 1995-12-01 | 2001-12-01 | 145700 | -40377 | 105323 | 105323 | 100% | 0 | 0 | 0 | 18941 | -5249 | 13692 | 0 | 0 | Completed in 1995. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | UNDP | Foam phaseout sector strategy | Individual | LAC | MEX | FOA | 31 | TAS | 96 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-01-01 |  | 2001-12-01 | 2004-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Preparatory study on halons, inventory, and proposals for revisions of existing standards | Individual | LAC | MEX | HAL | 06 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1994-04-01 |  | 1995-09-01 | 1998-12-01 | 25000 | 2223 | 27223 | 27223 | 100% | 0 | 0 | 0 | 3250 | 289 | 3539 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | MEX | SEV | 22 | TAS | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1998-05-01 |  | 1998-05-01 | 2001-12-01 | 60000 | -1400 | 58600 | 58600 | 100% | 0 | 0 | 0 | 7800 | -182 | 7618 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Non-Investment
FIN | UNDP | Technical assistance to prepare a refrigeration management plan (RMP) | RMP-Component | AFR | NIR | REF | 32 | TAS | 72 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2003-01-01 |  | 2002-12-01 | 2003-11-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | PAR | SOL | 45 | TAS | 14 | N | I | TCA/CTC | 2.4 | 2.4 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 30000 | -106.51 | 29893.49 | 29893.49 | 100% | 0 | 0 | 0 | 2700 | -9.59 | 2690.41 | 0 | 0 | Financially completed in 2012. |  | 2005 | 2008-01-01 | Non-Investment
FIN | UNDP | Technical assistance for awareness raising in the halon sector | Individual | AFR | SIL | HAL | 51 | TAS | 15 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2009-05-01 | 2008-09-01 |  | 2010-12-01 | 2012-05-01 | 15000 | -5.92 | 14994.08 | 14994.08 | 100% | 0 | 0 | 0 | 1350 | -0.53 | 1349.47 | 0 | 0 | Financially completed in 2012. |  | 2007 | 2010-01-01 | Non-Investment
FIN | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | One-off-Phaseout | ASP | SRL | FUM | 38 | TAS | 21 | N | I | MeBr | 3.3 | 3.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-11-01 |  | 2007-10-01 | 2010-06-01 | 130000 | -1.55 | 129998.45 | 129998.45 | 100% | 0 | 0 | 0 | 16900 | -0.2015 | 16899.7985 | 0 | 0 | Financially completed in 2010. |  | 2002 | 2005-11-01 | Non-Investment
FIN | UNDP | Safety and technical assistance programme to manufacturers of aerosol products | Individual | ASP | THA | ARS | 15 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1998-08-01 | 2002-03-01 | 127000 | -20 | 126980 | 126980 | 100% | 0 | 0 | 0 | 16510 | -3 | 16507 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Non-Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | -0.13 | 7019.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | I | TCA/CTC | 0.3 | 0.3 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | ARG | SEV | 45 | TAS | 144 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.4452 | 5268.5548 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | BRA | SEV | 45 | TAS | 271 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517.3339 | 14996.6661 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | COL | SEV | 45 | TAS | 62 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.4452 | 5268.5548 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IDS | SEV | 45 | TAS | 169 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1540.6936 | 8780.3064 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IND | SEV | 45 | TAS | 391 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2011-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517.3339 | 14996.6661 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IRA | SEV | 45 | TAS | 172 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.4452 | 5268.5548 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | LEB | SEV | 45 | TAS | 60 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-09-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616.2483 | 3511.7517 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | MAL | SEV | 45 | TAS | 155 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 91743 | -13695 | 78048 | 78048 | 100% | 0 | 0 | 0 | 8257 | -1232.5694 | 7024.4306 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | MEX | SEV | 45 | TAS | 127 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1540.6936 | 8780.3064 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SRL | SEV | 45 | TAS | 30 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 36697 | -5478 | 31219 | 31219 | 100% | 0 | 0 | 0 | 3303 | -493.0603 | 2809.9397 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SYR | SEV | 45 | TAS | 90 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616.2483 | 3511.7517 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -27909 | 17963 | 17963 | 100% | 0 | 0 | 0 | 4128 | -2511.518 | 1616.482 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | AFR | AFR | SEV | 32 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 |  | 2004-11-01 | 2007-12-01 | 151500 | -22085 | 129415 | 129415 | 100% | 0 | 0 | 0 | 19695 | -2871 | 16823.95 | 0.05 | 0 | Project financially completed. ($15,675 plus $ 2038 PSC returned to ExCom 50$6,410 plus $833 returned to ExCom 54) |  |  |  | Non Investment
FIN | UNEP | Sub-regional project on harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | AFR | AFR | SEV | 45 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system | Individual | LAC | ARG | SEV | 30 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-11-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  | 2003-10-01 | Non Investment
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | CBI | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2003-08-01 |  | 2004-12-01 | 2011-07-01 | 40000 | -4983 | 35017 | 35017 | 100% | 0 | 0 | 0 | 5200 | -648 | 4552.21 | -0.21 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | CHI | FUM | 30 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2011-12-01 | 25000 | -8217 | 16783 | 16783 | 100% | 0 | 0 | 0 | 3250 | -1068.21 | 2181.79 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | CMR | FUM | 34 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-07-01 |  | 2003-07-01 | 2004-07-01 | 25000 | -10136 | 14864 | 14864 | 100% | 0 | 0 | 0 | 3250 | -1317.68 | 1932.32 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | CMR | SEV | 37 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-07-01 | 2007-07-01 | 10000 | -1994 | 8006 | 8006 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 100% | 0 | 0 | 0 | 3250 | -1253.07 | 1996.93 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | Individual | ASP | CPR | FUM | 35 | TAS | 381 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2010-12-01 | 100000 | -53818 | 46182 | 46182 | 100% | 0 | 0 | 0 | 13000 | -6996 | 6003.66 | 0.34 | 0 | Project financially completed. ($ 9,093 plus $ 1182 returned to ExCom 50) |  |  | 2004-06-01 | Non Investment
FIN | UNEP | Techno-economic evaluation of methyl bromide alternatives | Individual | ASP | CPR | FUM | 35 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2008-12-01 | 80000 | -9093 | 70907 | 70907 | 100% | 0 | 0 | 0 | 10400 | -1182 | 9217.91 | 0.09 | 0 | Project financially completed. |  |  | 2004-06-01 | Non Investment
FIN | UNEP | Sectoral policy plan for methyl bromide phase-out in China | Individual | ASP | CPR | FUM | 24 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-01-01 |  | 1999-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Project financially completed ($ 29,818 plus $ 3,876 PSC returned at ExCom 52$ 24,000 plus $ 3,120 returned to ExCom 62) |  |  |  | Non Investment
FIN | UNEP | Development of policy training strategy and plan for local authorities | Individual | ASP | CPR | SEV | 27 | TAS | 268 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2000-04-01 |  | 2000-10-01 | 2001-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | DOM | FUM | 30 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -9183 | 15817 | 15817 | 100% | 0 | 0 | 0 | 3250 | -1194 | 2056.21 | -0.21 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy and technical assistance | Individual | LAC | DOM | SEV | 37 | TAS | 31 | A | I | CFC | 0.8 | 0.8 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2006-06-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Assistance in developing the RMP project proposal | Individual | AFR | DRC | REF | 32 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2002-01-01 |  | 2003-12-01 | 2010-12-01 | 60000 | -16985 | 43015 | 43015 | 100% | 0 | 0 | 0 | 7800 | -2208.4 | 5591.95 | -0.35 | 0 | Project financially completed |  |  | 2003-12-01 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ETH | FUM | 30 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -7326 | 17674 | 17674 | 100% | 0 | 0 | 0 | 3250 | -952.38 | 2297.62 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of training material for aerosol sector | Individual | GLO | GLO | ARS | 09 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of guidelines to promote safety an aerosol conversions | Individual | GLO | GLO | ARS | 39 | TAS | 246 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2003-12-01 |  | 2010-04-01 | 2011-04-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project completed in December 2010 |  |  |  | Non Investment
FIN | UNEP | Produce sector-specific video for aerosol sector | Individual | GLO | GLO | ARS | 19 | TAS | 91 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1996-12-01 |  | 1999-12-01 | 2000-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Preparation of how-to crop manual on adopting methyl bromide alternatives for cut flowers | Individual | GLO | GLO | FUM | 29 | TAS | 187 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2000-11-01 |  | 2001-12-01 | 2002-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Technical and institutional resources for methyl bromide alternatives projects | Individual | GLO | GLO | FUM | 24 | TAS | 156 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-10-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 4,000 plus $ 520 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Compilation of case studies on commercial, low-impact methyl bromide alternatives successfully implemented | Individual | GLO | GLO | FUM | 24 | TAS | 160 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Compilation of legislations for regulatory authorities from Article 5 countries that discourage methyl bromide use and promote alternatives | Individual | GLO | GLO | FUM | 24 | TAS | 155 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Methyl bromide information kit | Individual | GLO | GLO | FUM | 24 | TAS | 157 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 1998-12-01 | 1999-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. ($ 4,000 plus $ 520 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Produce a video on methyl bromide alternatives | Individual | GLO | GLO | FUM | 19 | TAS | 93 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-03-01 | 2000-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Technical sourcebook of methyl bromide alternatives | Individual | GLO | GLO | FUM | 23 | TAS | 150 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-12-01 | 2002-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Handbook for NOUs reducing reliance on methyl bromide | Individual | GLO | GLO | FUM | 23 | TAS | 151 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1998-11-01 |  | 1999-02-01 | 1999-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy development assistance to prevent future methyl bromide growth in low methyl bromide-consuming countries | Individual | GLO | GLO | FUM | 30 | TAS | 211 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2001-05-01 | 2002-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Dissemination of the existing halon banking awareness flyer | Individual | GLO | GLO | HAL | 16 | TAS | 86 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-09-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Translate the halon management: banking for the future information kit | Individual | GLO | GLO | HAL | 12 | TAS | 57 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1996-03-01 | 1999-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a "self-help" guide for small halon-consuming countries | Individual | GLO | GLO | HAL | 16 | TAS | 85 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-08-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Provide halon bank management query response, information collection and dissemination | Individual | GLO | GLO | HAL | 19 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Halon bank management query response, information collection and dissemination (1995) | Individual | GLO | GLO | HAL | 16 | TAS | 81 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-07-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Halon bank management case study logbook | Individual | GLO | GLO | HAL | 12 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1998-07-01 | 1995-03-01 |  | 2001-10-01 | 2001-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  | 1999-03-01 | Non Investment
FIN | UNEP | Halon bank management information collection and dissemination (1994) | Individual | GLO | GLO | HAL | 12 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Meeting of halon bank managers | Individual | GLO | GLO | HAL | 16 | TAS | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Development of a handbook on standards and codes of good practice for halon sector | Individual | GLO | GLO | HAL | 27 | TAS | 181 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-09-01 | 2002-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services | Individual | GLO | GLO | HAL | 21 | TAS | 115 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1998) | Individual | GLO | GLO | HAL | 23 | TAS | 145 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 | 0 | 11570 | 0 | 11570 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | International halon bank clearing-house function | Individual | GLO | GLO | HAL | 09 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-05-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Compilation of recommendations for a Code of Good Practices in refrigeration in Article 5 countries | Individual | GLO | GLO | REF | 16 | TAS | 87 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1995-09-01 |  | 1998-07-01 | 1999-04-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 | 0 | 4940 | 0 | 4940 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Guidelines for the establishment of recovery and recycling systems and related legislation for low volume ODS consuming countries | Individual | GLO | GLO | REF | 19 | TAS | 96 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2000-06-01 | 2000-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed. ($ 21,000 plus $ 2,730 PSC returned ExCom 32) |  |  | 1999-07-01 | Non Investment
FIN | UNEP | Study on drop-in substitutes for domestic refrigeration | Individual | GLO | GLO | REF | 21 | TAS | 116 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1999-08-01 | 2000-06-01 | 80000 | -21000 | 59000 | 59000 | 100% | 0 | 0 | 0 | 10400 | -2730 | 7670 | 0 | 0 | Project financially completed. ($ 104,000 plus $ 13,520 PSC returned ExCom 41) |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Preparation of training material for refrigeration sector | Individual | GLO | GLO | REF | 09 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to national activities (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 188 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Preparation of a booklet on data reporting for methyl bromide | Individual | GLO | GLO | SEV | 33 | TAS | 229 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2001-12-01 |  | 2001-11-01 | 2003-06-01 | 42500 | -2002 | 40498 | 40498 | 100% | 0 | 0 | 0 | 5525 | -260.26 | 5264.74 | 0 | 0 | Project financially completed. ($ 50,000 transferred for 5 policy projects ExCom 37 / $1,265,686.30 plus $ 105,254.90 PSC returned Excom 41 / $176,842 plus $14,147 PSC returned Excom 44 $ ,8063 plus $ 645 returned from ExCom 48) |  |  |  | Non Investment
FIN | UNEP | Adapting existing audiovisual materials to promote control of illegal trade in ODS | Individual | GLO | GLO | SEV | 30 | TAS | 208 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2003-06-01 | 2003-10-01 | 50000 | -2353 | 47647 | 47647 | 100% | 0 | 0 | 0 | 6500 | -306 | 6194.11 | -0.11 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Global public awareness and education campaign to sustain the phase out (first tranche) | Individual | GLO | GLO | SEV | 34 | TAS | 231 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-01-01 | 2003-01-01 | 60000 | -11755 | 48245 | 48245 | 100% | 0 | 0 | 0 | 7800 | -1528.15 | 6271.85 | 0 | 0 | Project financially completed. ($ 33,000 plus $ 4,304 PSC returned to ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 170 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 55000 | -6300 | 48700 | 48700 | 100% | 0 | 0 | 0 | 7150 | -819 | 6331 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Translation of OzonAction publications into other UN languages | Individual | GLO | GLO | SEV | 36 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2002-11-01 |  | 2006-11-01 | 2007-12-01 | 93000 | -34067 | 58933 | 58933 | 100% | 0 | 0 | 0 | 12090 | -4429 | 7661.29 | -0.29 | 0 | Project financially completed. ($ 24,731 plus $ 3,215 returned to ExCom 52$ 53,225 plus $ 6,919 PSC returned to ExCom 54) |  |  | 2004-07-01 | Non Investment
FIN | UNEP | Advisory and expert group meetings for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 223 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 75000 | -7392 | 67608 | 67608 | 100% | 0 | 0 | 0 | 9750 | -960.96 | 8789.04 | 0 | 0 | Project financially completed. ($ 5 plus $ 1 PSC returned ExCom 43) |  |  |  | Non Investment
FIN | UNEP | Study on development of ODS phase-out strategy for SMEs | Individual | GLO | GLO | SEV | 34 | TAS | 230 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-09-01 | 2002-12-01 |  | 2005-12-01 | 2009-09-01 | 100000 | -10000 | 90000 | 90000 | 100% | 0 | 0 | 0 | 13000 | -1300 | 11700 | 0 | 0 | Project financially completed. ($ 34,067 plus $ 4,429 PSC returned to ExCom 54) |  |  |  | Non Investment
FIN | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 29 | TAS | 198 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2005-04-01 | 2007-07-01 | 120000 | -22000 | 98000 | 98000 | 100% | 0 | 0 | 0 | 15600 | -2860 | 12740 | 0 | 0 | Project financially completed. |  |  | 2002-12-01 | Non Investment
FIN | UNEP | Development of effective awareness materials | Individual | GLO | GLO | SEV | 45 | TAS | 263 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-01-01 | 2007-12-01 | 120000 | -13267 | 106733 | 106733 | 100% | 0 | 0 | 0 | 15600 | -1725 | 13875.29 | -0.29 | 0 | Project financially completed. ($163,341 plus $13,069 PSC returned to ExCom 55$170,534 plus $13,643 PSC returned to ExCom 57$166,929 plus $13,354 PSC returned to ExCom 58$ -91,496 plus $-7,320 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Data reporting handbook to provide information to Article 5 countries and assist them with their data reporting | Individual | GLO | GLO | SEV | 24 | TAS | 158 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-01-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 163 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 | 0 | 14560 | 0 | 14560 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Prioritized sectoral data from worldwide sources in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 228 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 121000 | 0 | 121000 | 121000 | 100% | 0 | 0 | 0 | 15730 | 0 | 15730 | 0 | 0 | Project financially completed. ($ 2,002 plus $260 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 39 | TAS | 247 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-02-01 | 2004-04-01 |  | 2006-04-01 | 2007-12-01 | 200000 | -77956 | 122044 | 122044 | 100% | 0 | 0 | 0 | 26000 | -10134 | 15865.72 | 0.28 | 0 | Project financially completed. ($ 26,518 plus $ 3,447 PSC returned to ExCom 54$ 538 plus $ 70 PSC returned to ExCom 58$ 5,000 plus $ 650 returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 37 | TAS | 241 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2005-12-01 | 2006-01-01 | 200000 | -33111 | 166889 | 166889 | 100% | 0 | 0 | 0 | 26000 | -4304 | 21695.57 | 0.43 | 0 | Project financially completed. ($ 8,215 plus $ 1,068 returned to ExCom 59) |  |  | 2004-12-01 | Non Investment
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 42 | TAS | 255 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-04-01 | 2009-12-01 | 200000 | -32056 | 167944 | 167944 | 100% | 0 | 0 | 0 | 26000 | -4166.94 | 21832.72 | 0.34 | 0 | Project financially completed. ($ 30,227 plus $ 2,418 PSC returned to ExCom 55$150,831 plus $12,066 PSC returned to ExCom 57$38,734 plus $3,099 PSC returned to ExCom 58$ 144,807 plus $ 11,585 PSC returned to ExCom 59$144,807 plus $11,585 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Develop policy and customs training strategies | Individual | ASP | IND | SEV | 30 | TAS | 253 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2003-04-01 | 2005-12-01 | 50000 | -22000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 6500 | -2860 | 3640 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Overall strategy for the solvent sector to support the phase-out of ODS in SMEs | Individual | ASP | IND | SOL | 35 | TAS | 343 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-12-01 |  | 2005-06-01 | 2007-07-01 | 169000 | -10140 | 158860 | 158860 | 100% | 0 | 0 | 0 | 21970 | -1318 | 20651.8 | 0.2 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Formulation of national phase out strategy | Individual | ASP | KAM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2005-01-01 | 60000 | -433 | 59567 | 59567 | 100% | 0 | 0 | 0 | 7800 | -56 | 7743.71 | 0.29 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | KEN | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9392 | 15608 | 15608 | 100% | 0 | 0 | 0 | 3250 | -1221 | 2029.04 | -0.04 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | KEN | SEV | 37 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2005-12-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on technology assessment (in refrigeration) | Individual | LAC | LAC | REF | 16 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-01-01 | 1996-03-01 |  | 1999-05-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 14,500 plus $ 1,885 PSC returned ExCom 31) |  |  | 1999-05-01 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | MLW | FUM | 30 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9242 | 15758 | 15758 | 100% | 0 | 0 | 0 | 3250 | -1201.46 | 2048.54 | 0 | 0 | Project financially completed. ($ 5,000 plus $ 650 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | NER | SEV | 37 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2003-08-01 |  | 2004-01-01 | 2007-01-01 | 10000 | -1995 | 8005 | 8005 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | NIR | FUM | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -16990 | 8010 | 8010 | 100% | 0 | 0 | 0 | 3250 | -2208.7 | 1041.3 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy and technical assistance | Individual | ASP | OMA | SEV | 37 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2006-02-01 | 2008-12-01 | 10000 | -52 | 9948 | 9948 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | PHI | FUM | 30 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -8880 | 16120 | 16120 | 100% | 0 | 0 | 0 | 3250 | -1154 | 2095.6 | 0.4 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | RWA | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2007-03-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | SEN | FUM | 34 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 | 0 | 3250 | -1170 | 2080 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Methyl bromide communication programme | Individual | AFR | SIL | FUM | 47 | TAS | 12 | A | I | MB | 0.4 | 0.4 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2010-11-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | SIL | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-08-01 |  | 2003-12-01 | 2011-06-01 | 40000 | -23000 | 17000 | 17000 | 100% | 0 | 0 | 0 | 5200 | -2990 | 2210 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | THA | FUM | 30 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -9096 | 15904 | 15904 | 100% | 0 | 0 | 0 | 3250 | -1182.48 | 2067.52 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 | 2011-03-01 | 80000 | -40619 | 39381 | 39381 | 100% | 0 | 0 | 0 | 10400 | -5280.47 | 5119.53 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 | 0 | 0 | 3250 | -1203.67 | 2046.33 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 | 0 | 0 | 3250 | -359 | 2890.55 | 0.45 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Awareness/outreach activities on HCFC phase-out and its challenges during HPMP preparatory phase | Individual | ASP | CPR | SEV | 56 | TAS | 476 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-12-01 |  | 2011-06-01 | 2012-06-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | ASP | BAH | SOL | 45 | TAS | 14 | A | I | CTC TCA | 1.7 | 1.7 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2009-05-01 | 60000 | -15868 | 44132 | 44132.17 | 100% | -0.17 | 0 |  | 5400 | -1428 | 3972 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | AFR | BDI | SOL | 45 | TAS | 19 | A | I | TCA | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 35000 | -2129 | 32871 | 32870.94 | 100% | 0.06 | 0 |  | 3150 | -192 | 2958 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
FIN | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | Individual | LAC | BRA | FUM | 38 | TAS | 263 | A | I | MBR | 0 | 0 |  |  | 2002-11-01 | 2004-04-01 | 2003-12-01 |  | 2005-09-01 | 2006-09-01 | 40000 | -862 | 39138 | 39137.91 | 100% | 0.09 | 0 |  | 5200 | -112 | 5088 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in tobacco expansion in China | Individual | ASP | CPR | OTH | 09 | TAS | 193 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-05-01 | 1998-08-01 | 72000 | 4499 | 76499 | 76499 | 100% | 0 | 0 |  | 9360 | 585 | 9945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvents (CTC) sector | Individual | EUR | CRO | SOL | 45 | TAS | 25 | A | I | CTC | 2.3 | 2.3 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Provision of basic tools for the registered service workshops | RMP Update | ASP | DRK | REF | 40 | TAS | 29 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-09-01 | 2006-09-01 | 100000 | -10480 | 89520 | 89519.9 | 100% | 0.1 | 0 |  | 9000 | -943 | 8057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for elimination of CFCs in manufacturing foams at Advechems and El Fateh | Individual | AFR | EGY | REF | 09 | TAS | 11 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-08-01 | 1998-08-01 | 50000 | -9289 | 40711 | 40711 | 100% | 0 | 0 |  | 6500 | -1216 | 5284 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the production of household refrigerators at Electrostar & Kiriazi | Individual | AFR | EGY | REF | 09 | TAS | 63 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-03-01 | 1998-08-01 | 50000 | 6602 | 56602 | 56602 | 100% | 0 | 0 |  | 6500 | 858 | 7358 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | ELS | FUM | 45 | TAS | 18 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-09-01 | 2007-12-01 | 40000 | -2757 | 37243 | 37243.08 | 100% | -0.08 | 0 |  | 3600 | -248 | 3352 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance for the phase-out of methyl bromide for soil fumigation | Individual | EUR | GEO | FUM | 37 | TAS | 13 | A | I | MBR | 6 | 6 |  |  | 2002-07-01 | 2003-02-01 | 2006-08-01 |  | 2006-12-01 | 2009-12-01 | 220000 | -957 | 219043 | 219043.42 | 100% | -0.42 | 0 |  | 28600 | -124 | 28476 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Strategy for phasing out of ODS in low ODS-consuming countries | Individual | GLO | GLO | REF | 11 | TAS | 46 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-09-01 | 1994-11-01 |  | 1996-06-01 | 1998-08-01 | 100000 | -159 | 99841 | 99841 | 100% | 0 | 0 |  | 13000 | -41 | 12959 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | ASP | IRA | REF | 31 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-04-01 | 2002-01-01 |  | 2002-08-01 | 2003-02-01 | 70000 | -1431 | 68569 | 68568.92 | 100% | 0.08 | 0 |  | 9100 | -200 | 8900 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | KAM | FUM | 46 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 30000 | -2430 | 27570 | 27569.64 | 100% | 0.36 | 0 |  | 2700 | -219 | 2481 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | ASP | KAM | SOL | 57 | TAS | 21 | A | I | TCA | 0.3 | 0.3 |  |  | 2009-04-01 | 2010-02-01 | 2010-03-31 |  | 2010-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | AFR | KEN | SOL | 57 | TAS | 47 | A | I | CTC TCA | 0.2 | 0.2 |  |  | 2009-04-01 | 2010-12-01 | 2010-03-31 |  | 2012-07-01 | 2012-12-01 | 40000 | 0 | 40000 | 39012.44 | 97.53% | 987.56 | 0 | 1 | 3600 | 0 | 3511 | 89 | 0 | The workshop was successfully organized in Mar 2012. Project completed in Jul 2012. Financial completion in Dec 2012. |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | AFR | MAG | FUM | 45 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 40000 | -724 | 39276 | 39275.61 | 100% | 0.39 | 0 |  | 3600 | -65 | 3535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance in preparation of the national halon management plan | Individual | EUR | MDN | HAL | 37 | TAS | 19 | A | I | HAL | 32.1 | 32.1 |  |  | 2002-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-05-01 | 2004-02-01 | 25000 | -8 | 24992 | 24992.06 | 100% | -0.06 | 0 |  | 3250 | -6 | 3244 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | MEX | REF | 31 | TAS | 99 | A | I | CFC | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2002-05-01 |  | 2004-06-01 | 2004-12-01 | 100000 | -294 | 99706 | 99705.68 | 100% | 0.32 | 0 |  | 13000 | -59 | 12941 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | EUR | MOL | FUM | 45 | TAS | 13 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 30000 | -1838 | 28162 | 28161.61 | 100% | 0.39 | 0 |  | 2700 | -165 | 2535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvent and process agents (CTC & TCA ) sectors | Individual | AFR | MOR | SOL | 45 | TAS | 53 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -591 | 39409 | 39409.32 | 100% | -0.32 | 0 |  | 3600 | -53 | 3547 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | NIC | FUM | 45 | TAS | 12 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | -275 | 29725 | 29725.16 | 100% | -0.16 | 0 |  | 2700 | -25 | 2675 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of CFC phase out strategy for refrigeration and A/C industries and services | Individual | AFR | NIR | REF | 11 | TAS | 07 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1999-12-01 | 2000-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  | 1999-12-01 | NON-INV
FIN | UNIDO | Halon consumption phase-out through a technical assistance programme and a halon recycling | Individual | ASP | OMA | HAL | 46 | TAS | 12 | A | I | HAL | 6.85 | 6.85 |  |  | 2005-07-01 | 2007-02-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -4821 | 59779 | 59779.2 | 100% | -0.2 | 0 |  | 5814 | -434 | 5380 | 0 | 0 | Refund was reported to 66th ExCom, Apr 2012. FIN. |  |  | 2008-02-01 | INV
FIN | UNIDO | Training and awareness workshop in the solvent sector (CTC) | Individual | ASP | OMA | SOL | 45 | TAS | 11 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 35000 | 0 | 35000 | 34999.74 | 100% | 0.26 | 0 |  | 3150 | 0 | 3150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | PAK | FUM | 45 | TAS | 63 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 30000 | -7149 | 22851 | 22850.78 | 100% | 0.22 | 0 |  | 2700 | -643 | 2057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Strategy for ODS phase out in refrigeration industry | Individual | ASP | PAK | REF | 12 | TAS | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1995-08-01 | 1994-06-01 |  | 1998-03-01 | 2000-07-01 | 50000 | -232 | 49768 | 49768 | 100% | 0 | 0 |  | 6500 | -40 | 6460 | 0 | 0 | FIN |  |  | 1999-02-01 | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | TUN | SOL | 45 | TAS | 45 | A | I | CTC | 0.9 | 0.9 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 50000 | -18930 | 31070 | 31070.38 | 100% | -0.38 | 0 |  | 4500 | -1704 | 2796 | 0 | 0 | FIN |  |  | 2007-06-01 | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2008-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -2912 | 67088 | 67087.78 | 100% | 0.22 | 0 |  | 9100 | -392 | 8708 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | I | TCA | 1.9 | 1.9 |  |  | 2005-04-01 | 2006-04-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -1005 | 38995 | 38994.65 | 100% | 0.35 | 0 |  | 3600 | -90 | 3510 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | I | HAL | 37.1 | 37.1 |  |  | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7148 | 17852 | 17851.65 | 100% | 0.35 | 0 |  | 3250 | -933 | 2317 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | I | TCA | 0.2 | 0.2 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 35000 | -164 | 34836 | 34836.35 | 100% | -0.35 | 0 |  | 3150 | -15 | 3135 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 03 | A | I |  | 0 | 17.7 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5625 | 76475 | 76475 | 100% | 0 | 0 |  | 10673 | -747 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 40000 | -1745 | 38255 | 38254.73 | 100% | 0.27 | 0 |  | 3600 | -157 | 3443 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | Halon leak reduction demonstration |  | ASP | CPR | HAL | 16 | DEM | 121 | A | I | HAL | 221.7 | 74 | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-12-01 | 1998-06-01 | 90437 | 0 | 90437 | 90437 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Halon management resource manual |  | ASP | CPR | HAL | 11 | TAS | 53 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1a: model prototype development and testing) |  | ASP | CPR | REF | 10 | TAS | 33 | A | I |  | 0 |  | 0 |  | 1993-06-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 396110 | 0 | 396110 | 396110 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Halon-1211 management plan |  | LAC | ECU | HAL | 13 | TAS | 16 | A | I |  | 5.5 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) in Central America: El Salvador, Honduras, Nicaragua and Panama |  | LAC | LAC | REF | 24 | DEM | 27 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-06-01 | 2000-07-01 | 569000 | 0 | 569000 | 569000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training and equipment were provided in El Salvador, Honduras, Nicaragua and Panama in April - May 1999. Final report will be submitted in June 2000.
FIN | USA | Pilot sectoral study and action plan in commercial refrigeration |  | LAC | MEX | REF | 13 | TAS | 26 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 410000 | -139742 | 270258 | 270258 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Technical assistance in halon-1211 |  | LAC | PAN | HAL | 13 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 120000 | -42445 | 77555 | 77555 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Follow-up activities of the USA/Thailand/Japan conference on conservation, containment and alternatives |  | ASP | THA | SOL | 08 | TAS | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 203000 | -67000 | 136000 | 136000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Technical assistance in halon-1211 management |  | LAC | URU | HAL | 13 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Technical assistance in halon-1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | I | HAL | 2 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
ONG | France | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) |  | AFR | AFR | DES | 68 | TAS | 41 | A | I |  | 0 |  | 0 |  | 2012-12-01 |  | 2013-12-01 | 2013-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 |  | 80000 | 10400 | 0 | 0 | 10400 |  | New project.
ONG | France | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 39 | A | I | CFC | 0 |  | 0 |  | 2007-11-01 |  | 2009-11-01 | 2012-12-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 |  | 60000 | 9750 | 0 |  | 9750 |  | Although various discussions took place on this project, no concreatea actions have taken place. |  |  | 2010-12-01
ONG | IBRD | Resource mobilization for HCFC phase-out co-benefits study |  | GLO | GLO | SEV | 63 | TAS | 309 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-31 | 2013-07-01 |  |  | 180000 | 0 | 180000 | 50000 | 27.78% | 130000 | 130000 | 130000 | 16200 | 0 | 4500 | 11700 | 11700 | Resource mobilization study under preparation throughout 2012. Report still requires further inputs and an internal peer review process before it can be finalized. | Report is targeted for submission to the 70th ExCom meeting. Draft section on experience and lessons learned from the chillers program was shared with the Fund Secretariat for early input to discussions. |  |  | Non-INV
ONG | Israel | International methyl bromide compliance assistance workshop | Individual | GLO | GLO | FUM | 56 | TAS | 296 | A | D |  | 0 |  | 0 |  | 2008-11-01 |  | 2009-02-01 |  |  |  | 101200 | 0 | 101200 | 0 | 0% | 101200 | 0 | 0 | 13156 | 0 | 0 | 13156 | 0 | Not provided. |  |  |  | 2008
ONG | UNDP | Resource mobilization to maximize climate co-benefits | Individual | GLO | GLO | SEV | 63 | TAS | 306 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-04-01 | 2012-03-01 | 2013-03-01 |  |  | 200000 | 0 | 200000 | 49600.78 | 24.8% | 150399.22 | 680 | 45119.766 | 18000 | 0 | 4464.0702 | 13535.9298 | 61.2 | A status report on the project was submitted to the 66th and 67th ExCom meetings. An additional and more detailed status report will be submitted to the 69th ExCom meeting. | A status report on the project was submitted to the 66th and 67th ExCom meetings. An additional and more detailed status report has been submitted to the 69th ExCom meeting. | 2011 |  | Non-Investment
ONG | UNEP | Development of a guide for sustainable refrigerated facilities and systems, in cooperation with the American Society of Heating, Refrigeration and Air Conditioning Engineers (ASHRAE) | Individual | GLO | GLO | SEV | 66 | TAS | 314 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2014-04-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 200000 | 26000 | 0 | 0 | 26000 | 0 | UNEP and ASHRAE established taskforce to agree on the contractual arrangements for the guide. ASHRAE established Project Management Sub-Committee (PMS) to oversee the development of the Guide. ASHRAE tendered the development of the Guide amongst international specialized institutes and concluded with 2 institutes to undertake the development work. UNEP prepared list of international reviewers to support the review of the guide as it progress UNEP and ASHRAE still working out the contractual arrangements particularly the License Agreement for using the final guide | First Meeting of the Project Management Sub-Committee (PMS) concluded its first meeting in Jan-2013 in margins of ASHRAE Conference. 90% Peer Review of the Draft Guide Outline is due for completion by end of April 2013. UNEP finalized, through its legal office, the review of the license agreement and the contract between UNEP and ASHRAE is planned to be signed by May 2013 |  |  | Non Investment
ONG | UNEP | Destruction of confiscated ODS | Individual | ASP | NEP | DES | 59 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-05-01 | 2013-06-01 |  |  | 157200 | 0 | 157200 | 113901 | 72.46% | 43299 | 0 | 43299 | 20436 | 0 | 14807.13 | 5628.87 | 0 | Working on finalizing the project. | Transportation of ODS and destruction was completed and reports were being finalized for submission to UNEP. |  |  | Non Investment
ONG | UNEP | Resource mobilization to address climate co-benefits for HCFC phase-out in low-volume-consuming countries with servicing sector only, in cooperation with other agencies | Individual | GLO | GLO | SEV | 63 | TAS | 308 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2013-03-01 | 2013-03-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 13000 | 0 | 0 | 13000 | 0 | Study on financing options: Terms of Reference prepared; A consultant and UNEP is finalizing the administrative procedures to retain her; UNEP is in the process of identifying the members of the quality review team; CAP staff have conducted initial background research on co-financing issues, including existing documentation of the experiences of other agencies’ resource mobilization activities (b) Regional workshops on co-financing: internal discussions are underway within CAP to identify common agenda elements, workshop methodology, and key participants to invite to ensure a certain level of standardization and comparability across regions; CAP teams are scheduling the regional workshops in the context of the Regional Network meetings planned for 2013; an initial roster of potential invitees/partners for the workshops has been developed. | UNEP submitted an interim status report to ExCom-69 and received guidance on subsequent steps (b) Study: contract was established with consultant; initial consultations held; study outline developed; data collection underway; draft document planned for submission as INF paper to ExCom-70. Workshops: planning completed for first two workshops to be held in conjunction with Australia and FYROM Network meetings; agendas drafted; speakers invited; arrangements made for resource person. As per ExCom-70 guidance workshop component to be completed by Dec-2013. (a) Contract was signed with consultant in March 2013 (b) first disbursement occurred in May 2013. Remainder of project funds planned to be disbursed by October 2013 (i.e. date of last regional workshop on resource mobilization). |  |  | Non Investment
ONG | UNIDO | Technical assistance for the elimination of controlled uses of methyl bromide in soil fumigation | Individual | AFR | MOZ | FUM | 60 | TAS | 20 | A | I |  | 0.4 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 | 2013-12-01 |  |  | 40000 | 0 | 40000 | 52.58 | 0.1314% | 39947.42 | 0 | 10000 | 3600 | 0 | 5 | 3595 | 0 | The government of Mozambique has informed UNIDO that "the Ministry for the Coordination of Environmental Affairs in Mozambique has as priority, the national survey of Methyl Bromide. So after the national survey the Ministry will need to analyze the national survey report to know what is ongoing on Methyl Bromide issues in Mozambique, then the institution can design the type of National workshop must be done avoiding all possible impact in the national economy". It was further indicated that the cost for the survey will be around 40.000 USD (total project budget) and that "to organize national workshop [NOU] will need extra funds around USD 35 000". UNIDO was not in a position to allocate or spend money without the clearance from the official counterpart in the country. | Agreement with the NOU Mozambique to submit further fund request to the Executive Committee. UNIDO is discussing with the NOU on the scope of the project activities and the budget allocation.
ONG | UNIDO | Mobilizing co-financing for Multilateral Fund funded projects based on the "Monetization" of their climate benefits | Individual | GLO | GLO | SEV | 63 | TAS | 307 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-12-01 | 2012-09-30 | 2013-09-01 |  |  | 200000 | 0 | 200000 | 113383.28 | 56.69% | 86616.72 | 54180 | 70000 | 18000 | 0 | 10204 | 7796 | 4876 | 3 Project Documents “Improving Energy Efficiency and reducing ODS emissions in the cold storage sector in Viet Nam”, “Improving Energy Efficiency and reducing ODS emissions in the Industrial Refrigeration and Air conditioning Sector” for the Gambia and “Improving Energy Efficiency and reducing ODS emissions in the fishing sector” in Morocco have been prepared and submitted for the approval to the government representatives. Endorsement letters from the NOUs received and report submitted to the Executive Committee as per approval. | Projects finalized and submitted to potential donors for funding. The final report was submitted to the Executive Committee at the 69th Meeting as required in the decision when the proposal was approved. Thus, there were no delays in this project. |  |  | NON-INV
TRF | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 08 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 |  |  | 2005-07-01 | 64600 | -64600 | 0 | 0 |  | 0 | 0 |  | 5814 | -5814 | 0 | 0 | 0 | Project transferred to UNIDO at the 46th ExCom. |  |  |  | Non-INV
TRF | UNEP | Evaluation and risk analysis of Montreal Protocol Implementation in China | Individual | ASP | CPR | SEV | 30 | TAS | 346 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100% | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. |  |  |  | INV
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 09 | INV | 18 | N | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | 1997-09-01 | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2006-2007 | Multi-Year | ASP | CPR | OTH | 48 | INV | 442 | A | I | CFC | 300 | 300 |  |  | 2006-04-01 | 2007-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-05-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2005 | Multi-Year | ASP | CPR | OTH | 45 | INV | 427 | A | I | CFC | 200 | 200 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-03-01 | 1700000 | 0 | 1700000 | 1700000 | 100% | 0 | 0 |  | 127500 | 0 | 127500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2004 workplan | Multi-Year | ASP | CPR | OTH | 42 | INV | 409 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | 2001 Annual work programme of the tobacco sector plan | Multi-Year | ASP | CPR | OTH | 32 | INV | 366 | A | I | CFC | 90 | 90 |  |  | 2000-12-01 | 2001-06-01 | 2001-12-01 |  | 2001-12-01 | 2004-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2002 workplan | Multi-Year | ASP | CPR | OTH | 36 | INV | 388 | A | I | CFC | 120 | 200 |  |  | 2002-03-01 | 2002-08-01 | 2003-03-01 |  | 2002-12-01 | 2003-07-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan: 2003 annual work programme | Multi-Year | ASP | CPR | OTH | 39 | INV | 400 | A | I | CFC | 180 | 180 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2003-12-01 | 2005-09-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | FIN
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 05 | TRA | 07 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. |  |  | 1996-12-01 | Non-INV
COM | Japan | Training on alternative technologies to HCFCs | Individual | GLO | GLO | SEV | 59 | TRA | 297 | A | I |  | 0 |  | 0 |  | 2009-11-01 | 2010-03-01 | 2010-05-01 |  | 2011-03-01 |  | 141750 | 0 | 141750 | 141415 | 99.76% | 335 | 0 |  | 18428 | 0 | 18383.95 | 44.05 | 0 | Project completed. |  | 2009
FIN | Australia | Support to participants to the regional workshop on refrigeration and air conditioning training programme | Individual | ASP | ASP | REF | 12 | TRA | 14 | A | D |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-04-01 | 1994-05-01 | 66800 | 0 | 66800 | 66800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1994
FIN | Australia | Support to ASEAN regional conference on CFC and halons | Individual | ASP | ASP | SEV | 08 | TRA | 08 | A | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 4420 | -103 | 4317 | 4317 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1993
FIN | Australia | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | Individual | ASP | ASP | SEV | 07 | TRA | 06 | A | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-07-01 | 39394 | -4420 | 34974 | 34974 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1992
FIN | Austria | Establishment of a training centre for commercial refrigeration service technicians at Comservice S.A. |  | EUR | ROM | REF | 20 | TRA | 11 | A | I |  | 10 |  |  |  | 1996-10-01 |  | 1997-10-01 |  | 1999-02-01 | 1999-05-01 | 116628 | 0 | 116628 | 116628 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 1996
FIN | Canada | Refrigeration training workshop in the state of Sao Paulo | Individual | LAC | BRA | REF | 11 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-09-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1993 and approved in retroactive funding in November 1993. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | Canada | Montreal Protocol Technology Transfer Workshop on ODS (Phase II) | Individual | LAC | BRA | SEV | 15 | TRA | 17 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1994-09-01 | 1995-12-01 | 58390 | 0 | 58390 | 58390 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1994 and approved in retroactive funding in December 1994 |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Ozone depleting solvents workshop in Brazil | Individual | LAC | BRA | SOL | 17 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1994-05-01 | 1996-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in May 1994 and approved by retroactive funding in August 1995 |  | 1995 | 2000-01-01 | Non-Inv.
FIN | Canada | Training programme for customs officers | Individual | LAC | COL | REF | 35 | TRA | 52 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2004-07-01 |  | 2006-08-01 | 2006-08-01 | 106150 | 0 | 106150 | 106150 | 100% | 0 |  | 0 | 13799 | 0 | 13799 | 0 |  | 300 customs officers trained and monitoring and evaluation completed by June 2005. However, one final activity, reproduction of training manual was completed only by August 2006. PCR submitted in 2006. |  | 2000 |  | Non-Inv.
FIN | Canada | Activities in Sichuan Province | Individual | ASP | CPR | SEV | 11 | TRA | 52 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-10-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Workshop held in October 1993 and approved by retroactive funding in September 1994. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | NAM | REF | 20 | TRA | 3 | A | I | CFC | 5.4 | 5.4 | 0 |  | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-10-01 | 1999-10-01 | 103440 | 0 | 103440 | 103440 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1997
FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | AFR | AFR | SEV | 17 | TRA | 11 | A | D |  | 0 |  | 0 |  | 1995-07-01 | 1995-12-01 | 1996-01-01 |  | 1996-02-01 | 1996-02-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Exécuté en février 1996 en coopération ave le PNUE. Project completed.
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | ASP | LEB | REF | 23 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1999-06-01 |  | 2000-10-01 | 2000-12-01 | 52668 | 0 | 52668 | 52668 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en octobre 2000
FIN | France | No clean process improvement training for electronic assemblers who phased out the use of CFC-113 |  | ASP | MAL | SOL | 22 | TRA | 97 | A | D |  | 0 |  | 0 |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-04-01 | 1999-04-01 | 192423 | 25462 | 217885 | 217885 | 100% | 0 |  |  | 0 | 1500 | 1500 | 0 |  | Projet achevé. PCR soumis
FIN | France | Training of refrigeration technicians |  | AFR | MAU | REF | 14 | TRA | 04 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1997-07-01 | 1995-09-01 |  | 1999-06-01 | 1999-08-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 1997-05-01
FIN | France | Training and awareness of personnel involved in the task of codifying and identifying ODS and ODS-containing material |  | AFR | MAU | SEV | 14 | TRA | 03 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-10-01 | 1995-09-01 |  | 1996-11-01 | 1996-12-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | La formation a eu lieu du 02 au 04 novembre 1996. Project completed.
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | AFR | MOR | REF | 23 | TRA | 18 | A | D |  | 0 |  | 0 |  | 1997-11-01 | 1999-02-01 | 1998-06-01 |  | 2000-12-01 | 2000-12-01 | 53361 | 0 | 53361 | 53361 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Training of technicians in domestic refrigeration and air conditioning |  | AFR | SEN | REF | 21 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1998-01-01 | 1997-08-01 |  | 1998-03-01 | 1998-06-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | No clean process improvement training for electronic assemblers |  | ASP | THA | SOL | 29 | TRA | 124 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-01-01 | 2001-12-01 |  | 2002-12-01 | 2002-12-01 | 118140 | -2140 | 116000 | 116000 | 100% | 0 |  | 0 | 5907 | -107 | 5800 | 0 |  | Projet achevé
FIN | Germany | Pilot project: training programme for the refrigeration maintenance sector | Individual | LAC | BRA | REF | 34 | TRA | 228 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2004-08-01 | 2007-12-01 | 247400 | 0 | 247400 | 247400 | 100% | 0 | 0 | 0 | 32162 | 0 | 32162 | 0 | 0 | Project completed. Strategy derived from the demonstration project has been subvmitted with the National Phase Out Plan or Brazil
FIN | Germany | Travel expenses for participants to attend a regional workshop on methyl bromide alternatives for North African countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Syria, Tunisia) | Individual | GLO | GLO | FUM | 25 | TRA | 161 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-05-01 | 1999-06-01 |  | 1998-06-01 | 1999-07-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Information video: working safely with hydrocarbons in domestic and small scale commercial refrigeration | Individual | GLO | GLO | REF | 23 | TRA | 138 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-08-01 |  | 2001-01-01 | 2002-12-01 | 322050 | 0 | 322050 | 322050 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Dec 2003
FIN | Germany | Support to attend the Alternatives to CFC and Halons Technologies and Substances conference | Individual | GLO | GLO | SEV | 07 | TRA | 26 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-10-01 | 1992-10-01 |  | 1992-10-01 | 1994-10-01 | 18378 | 0 | 18378 | 18378 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Training in improved operations, service and maintenance for refrigeration technicians in using hydrocarbons | Individual | ASP | LEB | REF | 26 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-09-01 | 2002-01-01 | 49500 | -8197 | 41303 | 41303 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 07 | TRA | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-06-01 | Non-INV
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | 1997-12-01 | Non-INV
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. |  |  |  | Non-INV
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 04 | TRA | 04 | N | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-05-01 | Non-INV
FIN | Israel | International methyl bromide compliance assistance workshop (Bahamas, Barbados, Bosnia, Congo, Ecuador, Ethiopia, Moldova, Mexico, and Zambia) | Individual | GLO | GLO | FUM | 37 | TRA | 240 | A | D |  | 0 |  | 0 |  | 2002-07-01 |  | 2003-03-01 |  | 2002-12-01 |  | 98300 | -64177 | 34123 | 34123 | 100% | 0 | 0 | 0 | 9830 | -5847 | 3983 | 0 | 0 | The workshop was completed as planned. The goals were achieved and feedback from participants was very positive. The numbers of participants were lower than the maximum potential cited in the proposal. Costs were lower than expected. Two countries, Bahamas and Barbados, did not send participants. Participants from Ethiopia did not arrive due to logistical problems. Please see extended summary for further details of workshop content and outputs. * In addition to estimated disbursement stated, there will be support costs at 10%. |  | 2002 |  | 2002
FIN | Japan | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 33 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-02-01 | 2002-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Regional workshop on monitoring and control of ODS consumption for the South Asia region | Individual | ASP | ASP | SEV | 29 | TRA | 34 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-07-01 | 2001-06-01 |  | 2001-08-01 | 2002-06-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Workshop on concessional lending | Individual | GLO | GLO | SEV | 35 | TRA | 233 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2003-03-01 | 2006-07-01 | 75000 | -17294 | 57706 | 57706 | 100% | 0 | 0 | 0 | 9750 | -2248 | 7502 | 0 | 0 | Project financially completed in July 2006. |  | 2001
FIN | Singapore | Training workshop on CFC-113 and methyl chloroform substitutes and alternative technologies in ASEAN countries |  | ASP | ASP | REF | 13 | TRA | 15 | A | D |  | 0 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | AFR | AFR | SEV | 11 | TRA | 7 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 | 1994-09-01 | 1994-09-01 | 1994-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | Sweden | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 31 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2001-02-01 | 2002-05-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Regional Workshop on Control and Monitoring of ODS Consumption for the Southeast Asia/Pacific Region (funded with equal bilateral contributions from Sweden and Japan and implemented through UNEP) was held 22-27 May 2000 and was attended by ozone and customs officers from ten countries in the region. The participating countries developed a joint set of declarations and drafted national action plans for further work in their respective country. The report from the workshop was prepared by Sweden in February 2001. The project completion report prepared in coordination with UNEP was submitted 1 May 2002. The project was financially completed 27 May 2002. |  | 1999
FIN | Switzerland | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | Individual | LAC | ARG | REF | 19 | TRA | 46 | A | D |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-08-01 | 1997-10-01 |  | 1997-08-01 | 1997-10-01 | 242600 | 0 | 242600 | 242600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Balance has been compensated with separate Swiss funding |  | 1996
FIN | Switzerland | International workshop on potential for hydrocarbon-based refrigerant as replacements in existing domestic and small commercial refrigeration appliances | Individual | GLO | GLO | REF | 23 | TRA | 137 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1997-12-01 |  | 1997-09-01 | 1997-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1997
FIN | UNDP | Low-CFC foam training and demonstration programme in Asia | Individual | ASP | ASP | FOA | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -15672 | 36828 | 36828 | 100% | 0 | 0 | 0 | 6825 | -2037 | 4788 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Asia | RMP-Component | ASP | ASP | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1994-07-01 |  | 1996-08-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 08 | TRA | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100% | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Seminar/workshop in the solvent sector | Individual | LAC | COS | SOL | 08 | TRA | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | -3219 | 17901 | 17901 | 100% | 0 | 0 | 0 | 2745.6 | -417.6 | 2328 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Establishment of a training programme for centrifugal chillers and domestic refrigeration service managers and technicians | RMP-Component | ASP | CPR | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training programme for the Montreal Protocol Project Implementation Unit | Individual | LAC | ECU | SEV | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-12-01 |  | 1994-06-01 | 1997-12-01 | 100000 | 40000 | 140000 | 140000 | 100% | 0 | 0 | 0 | 13000 | 5200 | 18200 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Study tours for officials from the Ministry of the Environment, and pre-feasibility study | Individual | AFR | EGY | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-02-01 |  | 1992-06-01 | 1997-12-01 | 51000 | -6910 | 44090 | 44090 | 100% | 0 | 0 | 0 | 6630 | -898 | 5732 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Training programme for terminal phase-out of methyl bromide use, excluding QPS applications | One-off-Phaseout | AFR | GHA | FUM | 37 | TRA | 18 | N | I | MeBr | 6.3 | 6.3 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  | 2006-12-01 | 2009-08-01 | 101550 | -799 | 100751 | 100751 | 100% | 0 | 0 | 0 | 13201.5 | -103.5 | 13098 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in the Middle East/Africa | Individual | GLO | GLO | FOA | 06 | TRA | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-12-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -14413 | 38087 | 38087 | 100% | 0 | 0 | 0 | 6825 | -1874 | 4951 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in the Middle East | Individual | GLO | GLO | HAL | 06 | TRA | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-02-01 |  | 1993-12-01 | 1997-12-01 | 60000 | -20988 | 39012 | 39012 | 100% | 0 | 0 | 0 | 7800 | -2728 | 5072 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in the Middle East | RMP-Component | GLO | GLO | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1992-12-01 |  | 1996-06-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Three national policy workshops | Individual | GLO | GLO | SEV | 06 | TRA | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1996-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Two study-tours for officials and industry representatives | Individual | GLO | GLO | SEV | 06 | TRA | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1998-04-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Participation at workshops and key metings | Individual | GLO | GLO | SEV | 06 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-10-01 |  | 1995-09-01 | 1997-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Latin America | Individual | LAC | LAC | FOA | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | 1312 | 53812 | 53812 | 100% | 0 | 0 | 0 | 6825 | 171 | 6996 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in Latin America | Individual | LAC | LAC | HAL | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1994-06-01 | 1997-12-01 | 60000 | -15158 | 44842 | 44842 | 100% | 0 | 0 | 0 | 7800 | -1971 | 5829 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Latin America | Individual | LAC | LAC | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1992-09-01 | 1997-12-01 | 40000 | -16953 | 23047 | 23047 | 100% | 0 | 0 | 0 | 5200 | -2204 | 2996 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Latin America | RMP-Component | LAC | LAC | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1995-11-01 | 1994-02-01 |  | 1995-11-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training in MAC sector | RMP-Component | ASP | MAL | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-10-01 | 1993-12-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | National ODS conference | Individual | ASP | MAL | SEV | 10 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-07-01 |  | 1993-07-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | National seminar on industry and protection of the ozone layer | Individual | AFR | NIR | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-11-01 |  | 1992-12-01 | 1997-12-01 | 49650 | -23201 | 26449 | 26449 | 100% | 0 | 0 | 0 | 6454.5 | -3015.5 | 3439 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Training programme in the refrigeration sector | RMP-Component | ASP | PHI | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-04-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 64000 | -1707 | 62293 | 62293 | 100% | 0 | 0 | 0 | 8320 | -222 | 8098 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Training of Government technical staff | Individual | ASP | THA | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 50000 | 3785 | 53785 | 53785 | 100% | 0 | 0 | 0 | 6500 | 492.05 | 6992.05 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Training of Government technical staff and preliminary work on country programme | Individual | LAC | TRI | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1995-07-01 | 1997-12-01 | 53800 | 102 | 53902 | 53902 | 100% | 0 | 0 | 0 | 6994 | 13.26 | 7007.26 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427.4 | 2472.6 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | AFR | AFR | FUM | 34 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 |  | 2004-03-01 | 2009-07-01 | 80000 | -24177 | 55823 | 55823 | 100% | 0 | 0 | 0 | 10400 | -3142.71 | 7256.99 | 0.3 | 0 | Project financially completed. ($ 4,610 plus $ 599 PSC returned to ExCom 50$ 19,567 plus $ 2,544 PSC returned to ExCom 59) |  |  | 2003-09-01 | Non Investment
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | AFR | AFR | FUM | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2006-02-01 | 80000 | -16044 | 63956 | 63956 | 100% | 0 | 0 | 0 | 10400 | -2085.75 | 8314.28 | -0.03 | 0 | Project financially completed. ($10,681 plus $1,389 PSC returned ExCom 46 $ -3,506 plus $ -456 returned from ExCom 48$ 1,857 plus $ 241 returned to ExCom 50$ 7,012 plus $ 912 returned at ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | AFR | AFR | FUM | 16 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1995-09-01 | 1999-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional training workshops on policy development | Individual | AFR | AFR | FUM | 27 | TRA | 24 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 |  | 1999-12-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | AFR | AFR | FUM | 21 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1998-04-01 | 1999-03-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional training course on refrigeration for Africa | Individual | AFR | AFR | REF | 06 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-01 | 1992-12-01 |  | 1992-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1995-07-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-09-01 | 1994-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | AFR | AFR | SEV | 12 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-06-01 | 1999-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | AFR | AFR | SEV | 19 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop for Africa | Individual | AFR | AFR | SEV | 06 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1992-12-01 | 1993-12-01 | 210000 | 0 | 210000 | 210000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training of customs officers | Individual | LAC | ARG | REF | 32 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-02-01 |  | 2007-11-01 | 2008-12-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22750 | 0 | 22750 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | National train the trainer programme on good practices in refrigeration | Individual | LAC | ARG | REF | 21 | TRA | 51 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 1999-12-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 | 0 | 27950 | 0 | 27950 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Training programme for the refrigeration servicing sector (Phase III) | Individual | LAC | ARG | REF | 32 | TRA | 115 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2003-12-01 |  | 2009-07-01 | 2010-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on aerosol conversion for the SEAP region | Individual | ASP | ASP | ARS | 16 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1995-06-01 |  | 1995-05-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | ASP | ASP | FUM | 34 | TRA | 43 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2002-06-01 |  | 2003-12-01 | 2005-12-01 | 80000 | -13239 | 66761 | 66761 | 100% | 0 | 0 | 0 | 10400 | -1721.07 | 8678.93 | 0 | 0 | Project financially completed. ($2,360 plus $ 307 returned at ExCom 52) |  |  |  | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 82500 | 0 | 82500 | 82500 | 100% | 0 | 0 | 0 | 10725 | 0 | 10725 | 0 | 0 | Project financially completed. ($13,239 plus $1,721 returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 10 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-02-01 | 1999-04-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 10 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-09-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Refrigeration training workshop for Asia and the Pacific | Individual | ASP | ASP | REF | 09 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-04-01 |  | 1994-04-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for West Asia | Individual | ASP | ASP | SEV | 19 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 1999-03-01 | 80000 | -19056 | 60944 | 60944 | 100% | 0 | 0 | 0 | 10400 | -2477.28 | 7922.72 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Workshop for small and medium size enterprises on management of ODS phase-out | Individual | ASP | ASP | SEV | 12 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | Individual | ASP | ASP | SEV | 30 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-05-01 | 2003-06-01 | 150000 | -15122 | 134878 | 134878 | 100% | 0 | 0 | 0 | 19500 | -1965.86 | 17534.14 | 0 | 0 | Project financially completed. ($15,001 plus $1,950 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Regional workshop for Asia and the Pacific | Individual | ASP | ASP | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-11-01 |  | 1991-11-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training for refrigeration repair technicians | Individual | AFR | BKF | REF | 11 | TRA | 03 | A | I | CFC | 23 | 23 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1996-11-01 |  | 1996-11-01 | 1999-04-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 | 0 | 5395 | 0 | 5395 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs training) | Individual | AFR | BKF | SEV | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-10-01 | 1994-12-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 | 0 | 1885 | 0 | 1885 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs officers) | Individual | AFR | CMR | SEV | 10 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-08-01 | 1994-12-01 | 20200 | 0 | 20200 | 20200 | 100% | 0 | 0 | 0 | 2626 | 0 | 2626 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training programme in good practices in refrigeration | Individual | LAC | COL | REF | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 2003-12-01 | 2005-02-01 | 149100 | -42081.59 | 107018.41 | 107018 | 100% | 0.41 | 0 | 0 | 19383 | -5470.61 | 13912.34 | 0.05 | 0 | Project financially completed. ($9,639 plus $1,253 PSC returned ExCom 41) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Training workshop on safety aspects of CFC substitutes | Individual | ASP | CPR | SEV | 18 | TRA | 155 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1996-05-01 |  | 1996-05-01 | 1999-04-01 | 82400 | 0 | 82400 | 82400 | 100% | 0 | 0 | 0 | 10712 | 0 | 10712 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy training for local authorities (second tranche) | Individual | ASP | CPR | SEV | 37 | TRA | 392 | A | I | CFC | 16.5 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-09-01 | 2005-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy training for local authorities (first tranche for 2001) | Individual | ASP | CPR | SEV | 34 | TRA | 377 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-12-01 | 2003-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Policy training for local authorities (third tranche) | Individual | ASP | CPR | SEV | 43 | TRA | 413 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 | 0 | 43550 | 0 | 43550 | 0 | 0 | Project completed in January 2010. In addition, a total of 350 refrigeration technicians were trained A total of 250 customs officers were trained A strong system to monitor the import and export of ODS Successful review of the ODS Regulations 2000 More than 694 technicians and 250 companies are licensed with the NOU. |  |  |  | Non Investment
FIN | UNEP | Training of refrigeration service technicians in good servicing practices | Individual | ASP | DRK | REF | 40 | TRA | 27 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2008-12-01 | 70000 | -2171 | 67829 | 67829 | 100% | 0 | 0 | 0 | 9100 | -282 | 8817.77 | 0.23 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 30 | TRA | 09 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2003-06-01 |  | 2003-06-01 | 2007-07-01 | 82735 | -24380 | 58355 | 58355 | 100% | 0 | 0 | 0 | 10755 | -3169.24 | 7585.7621 | -0.0020717 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training of customs officers | Individual | AFR | GAM | SEV | 19 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  | 2002-10-01 | 2003-10-01 | 9500 | 0 | 9500 | 9500 | 100% | 0 | 0 | 0 | 1235 | 0 | 1235 | 0 | 0 | Project financially completed. |  |  | 1997-12-01 | Non Investment
FIN | UNEP | Implementation of train the trainer programme and national demonstration programme | Individual | AFR | GHA | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 1995-12-01 | 1999-04-01 | 99000 | 0 | 99000 | 99000 | 100% | 0 | 0 | 0 | 12870 | 0 | 12870 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Aerosol training workshop | Individual | GLO | GLO | ARS | 09 | TRA | 34 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Develop a technical brochure on methyl bromide | Individual | GLO | GLO | FUM | 19 | TRA | 94 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Development of training manuals for extension workers | Individual | GLO | GLO | FUM | 27 | TRA | 178 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-02-01 | 50000 | -4000 | 46000 | 46000 | 100% | 0 | 0 | 0 | 6500 | -520 | 5980 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National farmer's training and establishment of Farmer's Field School (FFS) | Individual | GLO | GLO | FUM | 27 | TRA | 179 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-04-01 |  | 2001-12-01 | 2003-12-01 | 60000 | -4000 | 56000 | 56000 | 100% | 0 | 0 | 0 | 7800 | -520 | 7280 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training modules for national training courses on good practices in refrigeration | Individual | GLO | GLO | REF | 19 | TRA | 97 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 10 | TRA | 45 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Prepare guidance to assist hotel industry in LVCs to avoid, replace, or eliminate ODS | Individual | GLO | GLO | REF | 19 | TRA | 98 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1996-12-01 |  | 1998-04-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Translation of "Training Manual on Good Practices in Refrigeration" and "Training Manual on Chillers and Refrigerant Management" into Chinese, French and Spanish | Individual | GLO | GLO | REF | 16 | TRA | 73 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1995-09-01 |  | 1997-12-01 | 1999-04-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 | 0 | 34320 | 0 | 34320 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to national activities for 2001 | Individual | GLO | GLO | SEV | 32 | TRA | 222 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. ($ 5,810 plus $ 755 PSC returned ExCom 44$ 5,945 plus $ 773 PSC returned ExCom 46) |  |  |  | Non Investment
FIN | UNEP | Support to other national training activities | Individual | GLO | GLO | SEV | 09 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Integrated enforcement training under the Montreal Protocol through green customs initiative | Individual | GLO | GLO | SEV | 52 | TAS | 283 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-09-01 | 2010-06-01 |  | 2010-12-01 | 2012-07-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed |  |  |  | Non Investment
FIN | UNEP | Support to national training activities (1994) | Individual | GLO | GLO | SEV | 13 | TRA | 70 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1996-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Updating the customs training manual | Individual | GLO | GLO | SEV | 48 | TRA | 274 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-08-01 | 2009-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop for Arabic speaking countries | Individual | GLO | GLO | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-12-01 |  | 1991-12-01 | 1992-12-01 | 246000 | -104000 | 142000 | 142000 | 100% | 0 | 0 | 0 | 31980 | -13520 | 18460 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Global enabling activity for customs training | Individual | GLO | GLO | SEV | 32 | TRA | 218 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2002-03-01 | 2003-06-01 | 165400 | -13971 | 151429 | 151429 | 100% | 0 | 0 | 0 | 21502 | -1816.23 | 19685.77 | 0 | 0 | Project financially completed. ($ 10,000 plus $1,300 support costs returned to 54th ExCom meeting.) |  |  |  | Non Investment
FIN | UNEP | Support to training activities by UNEP | Individual | GLO | GLO | SEV | 06 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1994-03-01 | 1994-12-01 | 365000 | 0 | 365000 | 365000 | 100% | 0 | 0 | 0 | 47450 | 0 | 47450 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | GUA | REF | 21 | TRA | 13 | A | I | CFC | 68.3 | 68.3 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2001-12-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training for refrigeration and air conditioning technicians | Individual | AFR | IVC | REF | 13 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1997-03-01 | 1999-04-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to a national workshop on refrigeration | Individual | AFR | KEN | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 2001-07-01 | 2001-07-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. ($ 7,000 plus $ 910 PSC returned ExCom 41) |  |  | 1999-12-01 | Non Investment
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | LAC | LAC | FUM | 27 | TRA | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-12-01 | 80000 | -4000 | 76000 | 76000 | 100% | 0 | 0 | 0 | 10400 | -520 | 9880 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional training workshop on policy development | Individual | LAC | LAC | FUM | 27 | TRA | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-03-01 |  | 2000-04-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop on non-CFC technologies for domestic refrigerator manufacturing industries | Individual | LAC | LAC | REF | 15 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-05-01 |  | 1995-05-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. ($ 9,000 plus $ 1,170 PSC returned ExCom 31) |  |  |  | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for the Caribbean region | Individual | LAC | LAC | SEV | 23 | TRA | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-11-01 |  | 1998-06-01 | 1999-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. ($ 17,257 plus $ 2,243 PSC returned ExCom 41) |  |  |  | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for Latin America and Caribbean | Individual | LAC | LAC | SEV | 19 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-04-01 | 1999-04-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Regional workshop for Latin America and the Caribbean | Individual | LAC | LAC | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-05-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Support to a sub-regional workshop on halon and halon bank management | Individual | ASP | MAL | HAL | 09 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-01-01 | 1994-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | PER | REF | 21 | TRA | 21 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2002-12-01 | 2003-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. ($ 13,000 plus $ 1,690 PSC returned Excom 46) |  |  |  | Non Investment
FIN | UNEP | Training programme for customs officials and other key stakeholders | Individual | ASP | PHI | REF | 35 | TRA | 66 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2005-12-01 | 2006-11-01 | 170250 | -3588 | 166662 | 166662 | 100% | 0 | 0 | 0 | 22133 | -466 | 21666.5495 | 0.45054 | 0 | Project financially completed. ($ 24,715 plus $ 3,213 PSC returned to ExCom 59) |  |  |  | Non Investment
FIN | UNEP | Training and upgrading for repair technicians | Individual | AFR | SEN | REF | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-11-01 |  | 1994-12-01 | 1995-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 | 0 | 7540 | 0 | 7540 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Expansion and upgrading of statistics networks for customs | Individual | AFR | SEN | SEV | 11 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1994-10-01 | 1994-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 | 2009-12-01 | 120000 | -12164 | 107836 | 107836 | 100% | 0 | 0 | 0 | 15600 | -1581 | 14018.68 | 0.32 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | Project financially completed. |  |  |  | Non Investment
FIN | UNIDO | Workshop to raise awareness on use of methyl bromide in tobacco cultivation | Individual | AFR | BKF | FUM | 34 | TRA | 14 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-01-01 | 2002-08-01 |  | 2002-12-01 | 2003-06-01 | 30000 | -7497 | 22503 | 22503.12 | 100% | -0.12 | 0 |  | 3900 | -979 | 2921 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Workshop on domestic and commercial refrigerator compressor conversion | Individual | ASP | CPR | REF | 17 | TRA | 133 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1998-08-01 | 40000 | 237 | 40237 | 40237 | 100% | 0 | 0 |  | 5200 | 31 | 5231 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an awareness workshop in the methyl bromide sector | Individual | AFR | MLI | FUM | 36 | TRA | 12 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-03 |  | 2003-07-01 | 2004-04-01 | 30000 | -596 | 29404 | 29403.72 | 100% | 0.28 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Awareness workshop and training on methyl bromide alternatives | Individual | ASP | OMA | FUM | 44 | TRA | 10 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-09-01 | 2007-10-01 | 35000 | -2078 | 32922 | 32921.71 | 100% | 0.29 | 0 |  | 3150 | -187 | 2963 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an awareness workshop on methyl bromide | Individual | LAC | PAN | FUM | 36 | TRA | 16 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-10-01 | 2003-12-01 | 30000 | -5344 | 24656 | 24656.21 | 100% | -0.21 | 0 |  | 3900 | -700 | 3200 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Workshop on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -2 | 5198 | 0 | 0 | FIN
FIN | USA | South-east Asia halon-1211 training workshop in Japan |  | ASP | ASP | HAL | 08 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1992-10-01 |  | 1992-10-01 | 1992-10-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Halon-1211 recovery/recharge training workshops |  | ASP | CPR | HAL | 11 | TRA | 57 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 271000 | 0 | 271000 | 271000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Support for the FESCAST international conference |  | ASP | CPR | SEV | 08 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1994-04-01 | 87000 | 96000 | 183000 | 183000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $96,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Regional workshops in halon-1211 training |  | GLO | GLO | HAL | 08 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 429000 | 0 | 429000 | 429000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Follow-up to regional halon-1211 workshop |  | LAC | LAC | HAL | 08 | TRA | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Conference on the elimination of ozone depleting solvents |  | ASP | MAL | SOL | 11 | TRA | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Chiller hands-on training |  | LAC | MEX | REF | 08 | TRA | 19 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 81000 | 259000 | 340000 | 340000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $259,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Cancun chiller workshop |  | LAC | MEX | REF | 13 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Mexican solvents programme to reduce CFC-113 and methyl chloroform |  | LAC | MEX | SOL | 08 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 360000 | 138000 | 498000 | 498000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $138,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | I |  | 76.1 |  | 0 |  | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Training in all ODS sectors in Venezuelan Military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
TRF | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 23 | TRA | 4 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-01-01 | 1999-12-01 |  |  | 2000-03-01 | 93490 | -93490 | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | Project transferred to UNEP at ExCom 30
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Refrigeration training programme for servicing technicians | RMP-Component | AFR | GHA | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-06-01 |  |  | 1993-06-01 | 99000 | -93800 | 5200 | 5200 | 100% | 0 | 0 | 0 | 12870 | -12194 | 676 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial and industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 06 | TRA | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Demonstration and training unit for maintenance and recharge of refrigeration and air conditioning equipment | RMP-Component | AFR | KEN | REF | 04 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1993-06-01 |  |  | 1993-06-01 | 115100 | -105248 | 9852 | 9852 | 100% | 0 | 0 | 0 | 14963 | -13682 | 1281 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100% | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  | 1998-01-01 | INV

## Multi-Year
Agency | Country | Sector Plan/National ODS Phase-Out Plan | MYA Sub-sector | Date Approved | Date Completed | Planned Date of Completion | Funds Committed by ExCom (US$) | Funds Released including Present Year by ExCom (US$) | Funds Disbursed to the Country (US$) | Total ODP Consumption to be Phase-out for the Plan | ODP Counsumption Allowed for the Reporting Year | Actual ODP Consumption for Reporting Year | Total ODP Production to be Phase-out for the Plan | ODP Production Allowed for the Reporting Year | Actual ODP Production for Reporting Year | Remarks (Achievement of Conditions of Approval, Milestones, Relevant Issues concerning next Targets) | Remarks (Latest information)
IBRD | India | Accelerated CFC Production Phase-out |  | 2008-01-04 |  | 2013-07-01 | 3169900 | 3169900 | 2113000 | 0 | 0 | 0 | 690 | 0 | 0 | Remaining $317,000 of the second tranche is expected to be released by the ExCom at its 69th Meeting in Apr. 2013 as condition set by ExCom was met (contaminated CFCs were destroyed). Final disbursement to the beneficiaries is pending approval for this second part of the second tranche. | US $317,000 of the second tranche released by the ExCom at its 69th Meeting in Apr. 2013 . WB supervision mission scheduled for late April through early May 2013.
IBRD | Antigua and Barbuda | CFC phase-out management plan |  | 2004-12-02 | 2011-12-01 | 2011-12-01 | 97300 | 97300 | 62987 | 1.8 | 0 | 0 | 0 | 0 | 0 | Project completed. | Balance of funds returned to the 69th ExCom Meeting.
IBRD | Argentina | National CFC phase-out plan |  | 2005-11-02 |  | 2013-07-01 | 500000 | 500000 | 100000 | 1.5 | 0 | 0 | 0 | 0 | 0 | WB provided its no objection to disbursement to chiller beneficiaries in early 2012 and $93,400 has been disbursed to chiller owners. Some additional delays in disbursement as well as entering into additional chiller subproject agreements had occurred due to changes in the organization at Ministry of Industry and a new project director. Four new chillers installed and are in operation. New authorities have decided to prioritize equipment replacement in industry as discussed with the WB during a Sep. 2012 mission. Companies interested in replacement have been identified. UEPRO is currently in discussions with 4 other companies owning 6 chillers interested in changing equipment. | It is expected that 1 of the 4 enterprises will sign a subgrant agreement (SGA) in about a month. Another will submit its proposal for replacement to the project coordination unit and then an SGA would be signed. The third is considering its investment options and will take a decision later in the year. Finally, the two chillers at the fourth enterprise originally considered were proven ineligible. Therefore, the enterprise will not participate in the project.
UNIDO | Argentina | National CFC phase-out plan |  | 2004-04-01 |  | 2013-12-01 | 6860850 | 6860850 | 4978516 | 1808 | 0 | 0 |  |  |  | Technical and commercial evaluation of bids finalized, purchase orders on the supply of new chillers to two public hospitals issued. | Preparation of TORs on the dismantling of old chillers and installation of new ones followed by local bidding for provision of the above civil work and engineering services. Inspection of other public hospitals and preparation of TOR on the replacement of their CFC based chillers.
IBRD | Bahamas | Terminal CFC Phaseout Plan for The Bahamas |  | 2001-12-01 | 2009-01-01 | 2009-12-01 | 560000 | 560000 | 530946 | 66 | 0 | 0 | 0 | 0 | 0 | Project completed.
UNEP | Bahrain | CFC Phase Out Plan |  | 2006-11-01 |  | 2013-11-01 | 330000 | 305000 | 80000 | 0 | 20.3 |  | 0 |  |  | All training activities and distribution of R&R equipment were completed. However final financial statement from country on 1st tranche of TPMP is pending. Detailed Study on the Feasibility of the Reclamation business in Bahrain was conducted during 2012, in coordination with UNDP to facilitate the operation of the R&R program under TPMP. All resources allocated in the 2nd tranche were transferred to the 1st tranche of the HPMP of Bahrain approved by the 68th ExCom | UNEP is following up closing the pending financial reports by the country of the 1st tranche contract. UNEP coordinated 2 preparatory meetings with NOU and UNIDO to prepare the detailed work-plan of the HPMP of Bahrain, including TPMP 2nd tranche resources, during the 1st quarter of 2013. Country contract planned to be signed by May 2013.
UNDP | Bahrain | CFC Phase Out Plan |  | 2006-11-01 | 2012-12-01 |  | 312500 | 312500 | 305653.87 | 58.71 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNDP | Belize | CFC Phase Out Plan |  | 2007-11-07 | 2010-08-01 |  | 194000 | 194000 | 193980 | 3.7 | 0 | 0 | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Belize | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 101000 | 101000 | 101000 | 0 | 3.7 | 0 | 0 |  |  | Project financially completed.
UNEP | Benin | CFC Phase Out Plan |  | 2008-07-01 | 2010-11-01 |  | 150000 | 150000 | 150000 | 0 | 9 |  | 0 |  |  | Project financially completed
UNIDO | Benin | Terminal phase-out management plan |  | 2008-07-01 | 2011-12-01 |  | 175000 | 175000 | 174600 | 7.9 | 0 | 0 |  |  |  | Project was successfully completed in 2011.
Germany | Botswana | CFC Phase Out Plan |  | 2009-04-01 | 2011-11-01 |  | 205000 | 205000 | 205000 | 1 | 0 | 0 | 0 |  |  | The NOU requested 10 additional identifiers for the customs dept. These identifiers were then provided to the various border posts and the bureau of standards. 3 customs trainings were conducted at remote border posts. Project was successfully completed with all CFCs being phased out.
UNDP | Brazil | CFC Phase Out Plan |  | 2002-07-01 |  | 2013-09-01 | 22816400 | 22816400 | 21846443 | 5801 | 0 | N.A. | N.A. | N.A. | N.A. | Recycling equipments were installed and recipient recyclers trained. Technical assistance for supermarkets energy savings and reduction of CFC emissions were concluded. Chillers equipment are under installation and will be ready for energy readings during the first quarter of 2013. An independent audit was held in December 2012 that confirmed that no CFCs were imported in 2011. | Chillers have been installed and comissioning works is being finalized. Pending payments are to be disbursed and PCR will be submitted in during 2013.
Germany | Brazil | CFC Phase Out Plan |  | 2002-07-01 | Dec-11 |  | 3883600 | 3883600 | 3883600 | 0 | 0 | 0 | 0 |  |  | M-Y-A plan completed
UNEP | Burkina Faso | CFC Phase Out Plan |  | 2006-11-11 | 2009-03-01 |  | 180000 | 203000 | 202369 | 0 | 5.4 |  | 0 |  |  | Project financially completed.
Canada | Burkina Faso | CFC Phase Out Plan |  | 2006-11-01 | 2010-12-01 |  | 165000 | 185000 | 182000 | 7.41 | 0 | 0 | 0 |  |  | Both tranches of project completed and targets met.
UNIDO | Burundi | Terminal phase-out management plan |  | 2008-07-01 |  | 2013-06-01 | 129000 | 129000 | 77802 | 3.1 | 0 | 0 |  |  |  | Joint UNIDO-UNEP mission enabled assessment of needs. Technical specifications were prepared, call for bids for supply of equipment issued, offers received and evaluated and purchase order issued. | Equipment is being shipped. Project will be closed after equipment delivery.
UNEP | Burundi | CFC Phase Out Plan |  | 2008-07-01 |  | 2013-12-01 | 115000 | 115000 | 104000 | 0 | 8.9 | 0 | 0 |  |  | The SSFA for 2nd tranche has since expired but was revised and sent to country for signature. The country has signed.
UNEP | Cambodia | CFC Phase Out Plan |  | 2007-11-01 | 2010-03-01 |  | 170000 | 170000 | 170000 | 0 | 14.1 | 0 | 0 |  |  | Project financially completed
UNDP | Cambodia | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 280000 | 280000 | 278225.94 | 13.5 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Cape Verde | CFC Phase Out Plan |  | 2008-04-01 | 2009-12-01 |  | 100000 | 100000 | 100000 | 0.3 | 0.3 | 0 | 0 |  |  | Project financially completed
France | Central African Republic | CFC Phase Out Plan |  | 2008-07-01 | 2011-12-01 |  | 100000 | 100000 | 100000 | 1.3 | 0 | 0 | 0 |  |  | In 2010, an international consultant was hired, and the equipment was tendered after the approval of the 2nd tranche of the TPMP and a re-scheduling of both tranches together. Equipment was prepared and shipped, and is foreseen to arrive in Bangui during the first quarter of 2011.
UNEP | Central African Republic | CFC Phase Out Plan |  | 2008-07-01 | 2012-12-01 |  | 105000 | 105000 | 105000 | 0 | 1.7 |  | 0 |  |  | Project completed in December 2012
UNEP | Chad | CFC Phase Out Plan |  | 2007-11-01 | 2010-03-01 |  | 171000 | 171000 | 169355 | 0 | 5.2 |  | 0 |  |  | Project completed
UNDP | Chad | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 174000 | 174000 | 163018.11 | 5.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
Canada | Chile | CFC Phase Out Plan |  | 2008-07-01 |  | 2013-03-01 | 437500 | 437500 | 422842 | 32.9 | 0 | 0 | 0 |  |  | First tranche completed by March 2012. Second tranche completed in March 2013. Targets met.
UNDP | Comoros | CFC Phase Out Plan |  | 2007-07-01 | 2010-12-01 |  | 75000 | 75000 | 74280 | 0.4 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Comoros | CFC Phase Out Plan |  | 2007-07-01 | 2011-12-01 |  | 130000 | 130000 | 124022 | 0 | 0.4 |  | 0 |  |  | Project financially completed
UNDP | Congo, DR | CFC Phase Out Plan |  | 2006-07-01 | 2011-12-01 |  | 337500 | 337500 | 329184 | 51.5 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | Congo, DR | CFC Phase Out Plan |  | 2006-07-01 | 2011-12-01 |  | 287500 | 287500 | 287500 | 0 | 99.8 |  | 0 |  |  | Project financially completed
UNDP | Costa Rica | CFC Phase Out Plan |  | 2007-07-01 | 2011-12-01 |  | 565000 | 565000 | 545500.17 | 37.53 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNIDO | Cote D'Ivoire | Terminal phase-out management plan |  | 2008-04-01 |  | 2013-06-01 | 283000 | 283000 | 259332 | 44.1 | 0 | 0 |  |  |  | In 2012 the equipment needs were assessed, the technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated, purchase order was issued and the equipment shipped. | Equipment has been delivered and a mission to Abidjan took place in February 2013. The project will be closed after the equipment distribution. Reason for the delay: The political and security situation in the country.
UNEP | Cote D'Ivoire | CFC Phase Out Plan |  | 2008-04-01 | 2012-02-01 |  | 282000 | 282000 | 277225 | 0 | 44.1 |  | 0 |  |  | Project completed in February 2012
Sweden | Croatia |  |  | 2003-04-01 | 2006-06-30 |  | 92200 | 92200 | 92200 | 13 |  |  | 0 |  |  | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. The project was completed in June 2006. PCR was submitted in April 2010.
UNIDO | Croatia | Terminal phase-out management plan for CFCs |  | 2003-04-01 | 2008-12-01 |  | 287500 | 287500 | 284954 | 85 | 0 | 0 |  |  |  | Project was successfully completed including financial closure in 2011.
UNEP | Djibouti | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-12-01 | 138000 | 138000 | 120000 | 3.15 | 3.2 |  | 0 |  |  | The SSFA has since expired but was revised and sent to country for signature. The country has signed awaiting disbursement.
UNDP | Djibouti | CFC Phase Out Plan |  | 2007-11-01 | 2009-12-01 |  | 147000 | 147000 | 144849.12 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNDP | Dominica | CFC Phase Out Plan |  | 2006-04-01 |  | 2013-07-01 | 103000 | 103000 | 58079.47 | 0.7 | 0 | N.A. | N.A. | N.A. | N.A. | Procurement process for equipment ongoing. Delays in receiving bids from potential suppliers. | No bids received yet. Contact has been made directly with an equipment supplier that has in the past delivered equipment in the Eastern Caribbean.
UNEP | Dominica | CFC Phase Out Plan |  | 2006-04-01 |  | 2013-12-01 | 114000 | 114000 | 104792 | 0 | 0.2 | 0 | 0 |  |  | Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention were addressed, maintaining zero level of CFC consumption, as well as, preventing the continuous increase in the use of HCFC-22 in the country. Activities funded with resources available at country level disbursed in 2011.
UNDP | Dominican Republic | CFC Phase Out Plan |  | 2005-04-05 | 2012-05-01 |  | 1711600 | 1711600 | 1653308 | 311.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNEP | Ecuador | CFC Phase Out Plan |  | 2010-07-01 |  | 2013-03-01 | 193155 | 193155 | 7188 | 0 |  |  | 0 |  |  | 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. NOU followed up with the Ministry of Finance to obtain the authorization for opening the special account needed for project funds management. By December 2012, the process still needed additional steps, preventing implementation of the project as planned. Expenditures expected to start in 2013 when the special account is opened. However, IAs, NOU and the Refrigeration Technician College (SECAP) drafted a training curriculum for Good Practices in Refrigeration Alternative Technologies to be launched in 2013. Review of 2011 ODS consumption by an independent auditor completed. | The special account permission has been obtained in March 2013. NOU is preparing the institutional contract wih SECAP to launch national train the trainers programme on low GWP alternatives. 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training and Brokers Workshop including 5th Amendment of Customs codes scheduled to April 22, 2013.
IBRD | Ecuador | National CFC phase-out plan |  | 2003-12-02 | 2009-09-01 | 2009-11-02 | 1689800 | 1689800 | 1194471 | 246 | 0 | 0 | 0 | 0 | 0 | Project completed. Balance of $495,329 was returned to the MLF at the 62nd ExCom Meeting.
UNIDO | Ecuador | National CFC phase-out plan |  | 2010-07-01 | 2012-03-01 |  | 280000 | 280000 | 259361 | 42 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Egypt | National CFC phase-out plan |  | 2005-07-01 |  | 2013-12-01 | 3100000 | 3100000 | 2667691 | 537 | 0 | 0 |  |  |  | 1) A data management system linking the ozone office with all other relevant Governmental institutions was set up. Equipment and software were installed and tested during first half of 2012. Training started in May 2012 and was finished in September 2012. The database started full operation with start of 2013. 2) The CFC consumption of the year 2010 was verified and found to be zero. | No further activities, funds are obligated for the conversion of AC system in railway carriages. The slight delay is due to security reasons.
UNDP | El Salvador | CFC Phase Out Plan |  | 2007-11-07 | 2011-06-01 |  | 515000 | 515000 | 514995 | 46 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | El Salvador | CFC Phase Out Plan |  | 2007-11-01 | 2012-06-01 |  | 50000 | 50000 | 50000 | 0 | 46 | Not available | 0 |  |  | National customs training manual drafted. Project technically completed. Technical and financial reports submitted by the government. | PCR to be drafted in the second quarter of the year.
UNDP | Gabon | CFC Phase Out Plan |  | 2007-07-01 | 2009-12-01 |  | 90000 | 90000 | 83283.3 | 1.5 | N.A. | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNEP | Gabon | CFC Phase Out Plan |  | 2007-07-01 | 2011-12-01 |  | 115000 | 115000 | 97507 | 0 | 1.5 |  | 0 |  |  | Project completed
UNDP | Gambia | CFC Phase Out Plan |  | 2007-11-07 | 2010-12-10 |  | 130000 | 130000 | 126999 | 3.6 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Gambia | CFC Phase Out Plan |  | 2007-11-01 | 2011-03-01 |  | 165000 | 165000 | 165000 | 0 | 3.6 |  | 0 |  |  | Project financially completed
UNDP | Georgia | CFC Phase Out Plan |  | 2006-11-01 | 2009-12-01 |  | 325000 | 325000 | 324918.06 | 8.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNDP | Ghana | CFC Phase Out Plan |  | 2006-11-01 | 2009-11-01 |  | 344894 | 344894 | 344894 | 17.5 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNEP | Grenada | CFC Phase Out Plan |  | 2006-07-01 |  | 2013-12-01 | 130000 | 117500 | 108972 | 0 | 0.9 | 0 | 0 |  |  | Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention addressed maintaining zero level of CFC consumption as well as preventing the continuous increase in the use of HCFC-22 in the country. Refrigeration Technicians trained on low-GWP technologies on a regular basis through the technician Association (GRAVA). NOO and President of the GRAVA attended international seminar in longer term alternatives that are non-ODS, energy efficient and low climate impact. Tranche 1 & 2 completed | Audited Financial reports are being prepared and reconciled by NOU in order for UNEP to release outstanding disbursements.
UNDP | Grenada | CFC Phase Out Plan |  | 2006-07-01 | 2011-11-01 |  | 120000 | 120000 | 119337 | 2.986 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNDP | Guatemala | CFC Phase Out Plan |  | 2008-11-01 |  | 2013-08-01 | 249000 | 249000 | 155183.99 | 5.9 | 0 | N.A. | N.A. | N.A. | N.A. | Equipment was procured and delivered to Guatemala. | The equipment is in the process of being delivered to the beneficiaries. Technical training of technicians took place.
UNEP | Guatemala | CFC Phase Out Plan |  | 2008-11-01 | 2012-12-01 |  | 65000 | 33000 | 23016 | 0 | 33.7 |  | 0 |  |  | Project completed in December 2012.
UNIDO | Guinea | Terminal phase-out management plan |  | 2008-07-01 |  | 2013-07-01 | 200000 | 200000 | 145115 | 2.9 | 0 | 0 |  |  |  | The procurement of equipment was initiated as planned jointly with the HPMP equipment. | Procurement of equipment was completed in the first quarter of 2013. The project is expected to be completed in 2013.
UNEP | Guinea | CFC Phase Out Plan |  | 2008-07-01 | 2011-12-01 |  | 132000 | 132000 | 131000 | 0 | 6.4 |  | 0 |  |  | Project completed
UNEP | Guinea-Bissau | CFC Phase Out Plan |  | 2008-11-01 | 2011-12-01 |  | 100000 | 100000 | 99000 | 3.9 | 3.9 |  | 0 |  |  | Project completed.
UNDP | Guyana | CFC Phase Out Plan |  | 2007-11-07 | 2011-11-01 |  | 215000 | 215000 | 214524 | 8 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011 | Completed in 2011.
UNEP | Guyana | CFC Phase Out Plan |  | 2007-11-01 | 2011-12-01 |  | 130000 | 130000 | 111434 | 0 | 8 | 1.74 | 0 |  |  | Project completed
UNDP | Haiti | CFC Phase Out Plan |  | 2009-07-01 |  | 2013-01-01 | 150000 | 150000 | 0 | 2.3 | 0 | N.A. | N.A. | N.A. | N.A. | Delays with the implementation of the TPMP activities in Haiti. A new work plan was prepared. | TORs for international consultant prepared and published.
UNEP | Haiti | CFC Phase Out Plan |  | 2009-07-01 |  | 2013-06-01 | 190000 | 125000 | 64943 | 0 | 25.4 |  | 0 |  |  | New Minister briefed on the requirements of the TPMP. Agreement was reached on the planned approach.
UNEP | Honduras | CFC Phase Out Plan |  | 2008-07-01 |  | 2013-12-01 | 198000 | 198000 | 171000 | 0 | 49.7 |  | 0 |  |  | Coordination between the National Ozone Unit and Customs Department for training and strengthening controls on ODSs and ODSs based technology imports/exports. Actions have been conducted to verify the correct tariff classification of ODSs, establishing sub-items for those that did not had a specific position according to the Harmonized Customs Code. Monitoring and reporting of all TPMP components. Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention addressed maintaining zero level of CFC consumption as well as preventing the continuous increase in the use of HCFC-22 in the country.
UNIDO | Honduras | Terminal phase-out management plan |  | 2008-07-01 | 2010-12-01 |  | 338500 | 338500 | 338005 | 39.7 | 0 | 0 |  |  |  | Project was successfully completed including financial closure in 2011.
UNDP | India | CFC Phase Out Plan | Foam | 2002-07-01 | 2006-12-01 |  | 5424577 | 5424577 | 5424577 | 639 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2006. | Completed in 2006.
UNDP | India | CFC Phase Out Plan | Refrigeration Manufacturing | 2002-11-01 | 2006-12-01 |  | 2935986 | 2935986 | 2801419 | 428 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2006. | Completed in 2006.
UNIDO | India | Plan for phase-out of CFCs in the refrigeration manufacturing sector |  | 2002-11-01 | 2007-03-01 |  | 673200 | 673200 | 673165 | 107 | 0 | 0 |  |  |  | The project was successfully completed.
Switzerland | India | CFC Phase Out Plan | Refrigeration Servicing | 2004-04-01 | 2009-03-31 |  | 1600600 | 1314601 | 1304053 | 211.4075 |  |  | 0 |  |  | Consumption reporting by Lead Agency (GTZ)
Germany | India | CFC Phase Out Plan - Refrigeration Servicing |  | 2004-04-01 | Dec-09 |  | 2415260 | 1156738 | 1156738 | 316.0018 | 59.1 | 59.1 | 0 |  |  | All project activities have been completed.
UNDP | India | CFC Phase Out Plan | Refrigeration Servicing | 2004-04-01 | 2010-08-01 |  | 1522260 | 1218341 | 1102561.47 | 219.08 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | India | CFC Phase Out Plan - Refrigeration Servicing |  | 2004-04-04 | 2011-01-01 |  | 800000 | 702500 | 702500 | 101.5157 | 1002.2 | Not available | 0 |  |  | Project financially Completed
UNDP | Iran (Islamic Republic of) | CFC Phase Out Plan | Refrigeration Manufacturing | 2004-04-01 | 2007-12-01 |  | 770000 | 770000 | 756547 | 56 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2007. | Completed in 2007.
UNIDO | Iran (Islamic Republic of) | National CFC phase-out plan |  | 2003-12-01 | 2008-04-01 |  | 3310758 | 3310758 | 3308263 | 619.6 | 0 | 0 |  |  |  | The project was successfully completed.
France | Iran (Islamic Republic of) | CFC Phase Out Plan - MAC R&R |  | 2003-12-01 | 2010-06-01 |  | 1506620 | 1506620 | 1506620 | 424.5 | 29.3 | 29.3 | 0 |  |  | The French contribution is implemented by GIZ-Proklima. Monitoring report was compiled in 2010. Project completed.
UNEP | Iran (Islamic Republic of) | CFC Phase Out Plan - Regulations |  | 2003-12-01 | 2010-12-01 |  | 140253 | 140253 | 140253 | 0 | 685.8 | Not available | 0 |  |  | Project financially completed
Germany | Iran (Islamic Republic of) | CFC Phase Out Plan - Foam, MAC Training, Management |  | 2003-12-01 | Dec-11 |  | 5289620 | 5289619 | 5289618.8425 | 608.4 | 608.4 | 608.4 | 0 |  |  | M-Y-A plan completed
France | Kenya | CFC Phase Out Plan |  | 2004-12-01 | 2012-03-01 | 2012-03-01 | 692000 | 692000 | 553967 | 138.8 | 0 | 0 | 0 |  |  | The French contribution is implemented by GTZ-Proklima. The project is completed.
UNIDO | Korea, DPR | Implementation of the NPP: recovery and recycling |  | 2005-11-01 | 2010-12-01 |  | 536000 | 536000 | 528451 | 121.7 | 0 | 0 |  |  |  | The project was successfully completed.
UNEP | Korea, DPR | CFC Phase Out Plan |  | 2005-11-01 | 2011-04-01 |  | 528000 | 528000 | 501468 | 72 | 66.3 | Not available | 0 |  |  | Project Completed
UNDP | Kyrgyzstan | CFC Phase Out Plan |  | 2006-11-01 | 2010-12-10 |  | 317000 | 317000 | 317000 | 7 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Kyrgyzstan | CFC Phase Out Plan |  | 2006-11-01 | 2011-04-01 |  | 233000 | 233000 | 233000 | 0 | 10.9 |  | 0 |  |  | Project financially completed
France | Lao, DPR | CFC Phase Out Plan |  | 2008-04-01 |  | 2013-04-01 | 320000 | 320000 | 271444 | 6.5 | 6.5 |  | 0 |  |  | In addition to previous training session, a ftraining on Good Practices in refrigerant Management and Pilot Retrofit Incentive Programme to HFC-134a System in Domestic Refrigeration, Commercial Refrigeration and MAC was also organized in Khammouane Province for the central and southern provinces in June 2011. Furthermore, with respect to the Regulations enforcement and update, a national workshop was organized in Febuary 2011 for 95 participants of Lao PDR authorities of central and provincial levels to work on the review of the Ministerial Decision on the Control of the Import-Export licensing system of the ODS in Lao PDR. A training on transit control and an annual refreshment training of custom's officers on ODS licensing system was also carried out in October 2011.
UNDP | Lebanon | CFC Phase Out Plan |  | 2004-12-01 | 2010-08-01 |  | 2091420 | 2091420 | 2091020 | 417 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
Germany | Lesotho | CFC Phase Out Plan |  | 2003-12-01 | 2009-11-01 |  | 127300 | 127300 | 127300 | 2.6 | 0.4 | 0 | 0 |  |  | Project has been completed final report being prepared. Lesotho achieved complete CFC phase out as per the Agreement with the Excom.
UNDP | Liberia | CFC Phase Out Plan |  | 2007-11-01 | 2009-12-01 |  | 132000 | 132000 | 130563.05 | 8.4 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNEP | Liberia | CFC Phase Out Plan |  | 2007-11-01 | 2011-12-01 |  | 213000 | 213000 | 208000 | 0 | 8.4 |  | 0 |  |  | Project completed
UNIDO | Libya | National phase-out plan |  | 2003-12-01 |  | 2013-12-01 | 2497947 | 2497947 | 2266233 | 450.5 | 0 | 0 |  |  |  | Equipment delivered to 2 beneficiaries (in Tripoli region) forwarding to Benghazi is pending. Trainings are pending. Purchase of refrigerant identifiers for regional offices of state environmental agency (EGA) and custom authorities has been initiated based on request of NOU and after agreement with NOU on the scope and technical parameters. Bidding is in progress. | Delivery of equipment for monitoring and inspection. Training on the operation and proper use of equipment. Mission preparation is in progress. Reason for the delay: the security and social situation in the country that have not improved and stabilized.
UNIDO | Macedonia, FYR | Terminal phase-out management plan for CFCs |  | 2005-04-01 | 2013-01-01 |  | 279081 | 279081 | 268394 | 49.34 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Malawi | CFC Phase Out Plan |  | 2007-11-01 | 2011-12-01 |  | 173000 | 173000 | 171755 | 8.7 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | Malawi | CFC Phase Out Plan |  | 2007-11-01 | 2011-12-01 |  | 172000 | 172000 | 172000 | 0 | 8.7 |  | 0 |  |  | The NOU conducted additional training for both customs officer and refrigeration technicians. 30 customs officers, 20 refrigeration technicians, and 10 police officers were trained in the control of illegal importation of ODS. Both Customs Officers and Refrigeration Technicians training schools have incorporated Montreal Protocol Issues in their training curricula and implementation of the new curricula has started. The NOU engaged into sensitisation campaign of the revised ODS Regulations to the general public. Implementation of project activities completed
UNDP | Maldives | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-12-12 | 85000 | 85000 | 85000 | 0.7 | 0 | N.A. | N.A. | N.A. | N.A. | Remaining funds under TPMP proposed to be used to sustain zero ODS consumption and support HCFC phaseout in line with decision 60/11, mainly the activity in Recovery and Reclamation. Procurement of equipment is currently in progress. During the year, advertisements were issued for procurement of equipment but no response was received from potential service providers. Government is proposing to have direct contract with single supplier for procuring equipment. | Equipment procurement process through a service provider is proposed to be completed by Q2 of 2013.
UNEP | Maldives | CFC Phase Out Plan |  | 2007-11-01 | 2010-07-01 |  | 95000 | 95000 | 95000 | 0 | 0.7 | 0 | 0 |  |  | Project financially completed
UNDP | Mali | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 322000 | 322000 | 319198 | 16.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Mali | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 198000 | 198000 | 192412 | 0 | 16.2 |  | 0 |  |  | Project financially completed
UNEP | Mauritania | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-12-01 | 155000 | 155000 | 96000 | 0 | 2.4 |  | 0 |  |  | Administrative statement still not resolved | Activities in Mauritania were frozen since 2009 awaiting completion of an audit of UNEP activities in Mauritania. Administrative statement still not resolved. UNEP regional office visiting the country at end of May 2011 to discuss issues with UNDP country office and government.()
UNDP | Mauritania | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 140000 | 140000 | 135034 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
IBRD | Mexico | National CFC phase-out plan: Chiller Subsector |  | 2005-04-01 | 2006-02-01 | 2007-04-01 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed.
UNIDO | Mexico | National CFC phase-out plan |  | 2004-04-01 | 2011-12-01 |  | 8294500 | 8294500 | 8005617 | 1535 | 0 | 0 |  |  |  | Project was successfully completed in 2011.
UNEP | Moldova | CFC Phase Out Plan |  | 2007-07-01 | 2010-06-01 |  | 215000 | 215000 | 215000 | 0 | 11 |  | 0 |  |  | Project financially completed
UNDP | Moldova | CFC Phase Out Plan |  | 2007-07-01 | 2010-12-10 |  | 305000 | 305000 | 304841 | 10 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
Japan | Mongolia | CFC Phase Out Plan |  | 2005-11-01 | 2010-12-01 | 2010-12-01 | 205000 | 205000 | 205000 | 3.3 | 0 | 0 | 0 |  |  | Completed. PCR already submitted.
UNEP | Mozambique | CFC Phase Out Plan |  | 2008-11-01 |  | 2013-12-01 | 134000 | 134000 | 107450 | 0 | 2.7 |  | 0 |  |  | Trained 70 refrigeration experts and 40 customs officers. The country procured and distributed equipment and tool kits and conducted awareness activities
UNDP | Mozambique | CFC Phase Out Plan |  | 2008-11-01 | 2011-12-01 |  | 117500 | 117500 | 116371 | 2.3 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
Germany | Namibia | CFC Phase Out Plan |  | 2003-12-01 | Dec-10 |  | 252500 | 252500 | 252500 | 12 | 5 | 0 | 0 |  |  | Project has been completed.
UNDP | Nepal | CFC Phase Out Plan |  | 2007-07-01 |  | 2013-06-01 | 100000 | 100000 | 99914 | 12 | 0 | N.A. | N.A. | N.A. | N.A. | During the year 2012, UNDP continued to follow up with NOU for completing pending activities under the project. Due to changes in NOU staffing, activities were delayed. | Second and final disbursement under LoA expected to be made in Q2 of 2013 after respective milestone is achieved.
UNEP | Nepal | CFC Phase Out Plan |  | 2007-07-01 | 2010-03-01 |  | 70000 | 70000 | 70000 | 0 | 4.1 | 3 | 0 |  |  | Project financially completed
UNDP | Nicaragua | CFC Phase Out Plan |  | 2008-11-01 | 2010-11-10 |  | 320000 | 320000 | 319958 | 3.7 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Nicaragua | CFC Phase Out Plan |  | 2008-11-01 | 2012-06-01 |  | 200000 | 200000 | 191466 | 0 | 12.4 | Not available | 0 |  |  | Project completed
UNEP | Niger | CFC Phase Out Plan |  | 2008-04-01 | 2010-12-01 |  | 149000 | 149000 | 148000 | 0 | 4.8 |  | 0 |  |  | Project financially completed
UNIDO | Niger | Terminal phase-out management plan |  | 2008-04-01 | 2012-02-01 |  | 184000 | 184000 | 183798 | 4.8 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Nigeria | National CFC phase-out plan |  | 2002-11-01 | 2008-03-01 |  | 937386 | 937386 | 937384 | 100.9 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Nigeria | CFC Phase Out Plan |  | 2002-11-01 | 2012-12-01 |  | 12193400 | 12193400 | 12175141.01 | 2388.8 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNIDO | Oman | Terminal phase-out management plan |  | 2007-07-01 | 2011-12-01 |  | 470000 | 470000 | 432704 | 35 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Panama | CFC Phase Out Plan |  | 2004-12-01 | 2010-12-01 |  | 943152 | 943152 | 942712.99 | 168.42 | 0 | 0 | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Panama | CFC Phase Out Plan |  | 2004-12-01 | 2011-06-01 |  | 50000 | 50000 | 50000 | 0 | 57.6 | 11.53 | 0 |  |  | Project financially completed
Germany | Papua New Guinea | CFC Phase Out Plan |  | 2003-04-01 | Dec-10 |  | 700000 | 700000 | 700000 | 35 | 8 | 2.2 | 0 |  |  | Project completed
UNEP | Paraguay | CFC Phase Out Plan |  | 2007-03-01 | 2011-12-01 |  | 194000 | 194000 | 194000 | 0 | 31.6 | 27.334 | 0 |  |  | Project financially completed
UNDP | Paraguay | CFC Phase Out Plan |  | 2007-03-07 | 2012-12-01 |  | 371000 | 371000 | 365690.34 | 31.58 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNIDO | Peru | Terminal phase-out management plan for Annex A Group I substances |  | 2008-07-01 |  | 2013-07-01 | 183500 | 183500 | 149316 | 15 | 0 | 0 |  |  |  | The tools for the training centres were purchased and delivered to the country in August 2012. | It is expected to release the tools from the custom ands close the project in 2013. Reason for the delay: Since the training tool were delivered to the country, UNIDO has been trying to release them from the customs but it has not been possible yet.
UNEP | Peru | CFC Phase Out Plan |  | 2008-07-01 |  | 2013-12-01 | 155000 | 77500 | 36266 | 0 | 43.4 | Not available | 0 |  |  | The ODS import/export licensing system has been updated in order to include the quotas for HCFCs as well as other adjustments needed for better functioning. This work has included the revision of all the legal framework governing ODS import, trade and use in the country, including a new set of regulations for refrigeration servicing technicians. The electronic interface between the licensing and customs system is being designed at the moment and is expected to be operative by the end of 2012. Two training and awareness seminars for customs control chain officers were held for 45 officers. Printed information and awareness material have been produced as needed for the customs training activities including the “Training Manual for Customs Officers”, the “Quick Guide for Customs Inspection of ODSs” and “Illicit Trade of ODSs” | UNEP continues to provide very close follow-up to ensure compliance management and in coordination with UNIDO as co-agency.
UNEP | Philippines | CFC Phase Out Plan |  | 2012-04-01 |  | 2014-03-01 | 1835205 | 1835205 | 103924 |  |  |  | 0 |  |  | The list of planned activities for 2012: - Project Management - Prevention of additional supply of CFCs - Elimination of CFC demand in the country - Management of unwanted ODS - Information, Education and Communication (IEC) Campaign. Progress: The NCPP PMU conducted/organized four (4) Regional Consultations nationwide to gather significant comments from the concerned stakeholders in 2012. The NCPP PMU conducted turn-over of training equipment to Training Institutes (TIs) through awarding of Deed of Donations. As to date, 136 out of 139 TIs have been completed. Submitted CFC verification audit to UNEP last 22 February 2012.
IBRD | Philippines | National CFC phase out plan |  | 2002-11-01 | 2011-06-01 | 2011-12-01 | 10216876 | 10216876 | 8381671 | 2017.6 | 0 | 0 | 0 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component.
Sweden | Philippines | CFC Phase Out Plan |  | 2002-11-01 | 2011-12-31 |  | 358534 | 358534 | 345799 | 0 |  |  | 0 |  |  | The original plan to establish a functioning Reclamation Facility in partnership with PARII was deemed not financially-viable and economically-feasible by PARII due to low amounts of reclaimable refrigerants from the servicing sector. Hence, an alternative model to establish an ODS management plan, including the collection, transport, and storage of recovered refrigerants and unwanted ODS was proposed by the PMU and included in the 2010-2011 Biennual Plan of the NCPP approved at the 60th ExCom Meeting. Procurement and selection process for equipment which complements that already procured under the reclamation scheme, as well as for contractors for ODS collection, transport and storage was not completed until 2010. Delsa Chemicals and Multi-Products Inc (DCMI), a member of PARII, the refrigerant importer association, is the contractor selected for the collection, transport and storage of recovered refrigerants for the NCPP. The contract between DENR and Delsa Chemicals was signed 13 Sep 2010 after a long negotiation on the scheme and financial requirements. Delsa Chemicals started collection of recovered refrigerants Oct 2010 and has so far 3.0 MT of various recovered refrigerants stored in their warehouse. Task expected to be completed by mid-2011.
UNIDO | Qatar | Terminal phase-out management plan |  | 2007-11-01 |  | 2013-12-01 | 312500 | 312500 | 227393 | 15 | 0 | 0 |  |  |  | Any remaining balance of the TPMP is transferred to the HPMP. | Project and remaining funding will be completed by Dec 2013. Reason for the delay: No NOU officer(s) were appointed for a long period of time.
UNEP | Qatar | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-12-01 | 120000 | 120000 | 15000 | 0 | 15.2 |  | 0 |  |  | ODS Officer of Qatar changed 3 times over the last 3 years resulting to delaying implementation of all projects. Early 2012 new ODS Officer nominated officially but no proper hand-over internally was arranged. UNEP and UNIDO made plan to re-establish the operation of the Ozone Unit in Qatar and build its capacity through several meetings and missions to quickly orient the new ODS Officer and other officials with MP and project implementation needs. 2 Orientation meetings and one national workshop arranged by UNEP during 2012. All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 | All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65). Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013
UNIDO | Romania | National CFC phase-out plan |  | 2005-04-01 | 2010-12-01 |  | 509019 | 509019 | 508121 | 99.3 | 0 | 0 |  |  |  | The project was successfully completed.
Sweden | Romania | CFC Phase Out Plan |  | 2005-04-01 | 2010-12-31 |  | 36281 | 36281 | 36281 | 0 |  |  | 0 |  |  | With ExCom decision 60/3 in April 2010, the remaining components of this project was formally handed over from Sweden to UNIDO and the contract with the international consultant was terminated. This progress report therefore only includes activities up to April 2010: The project has been suffering from a long delay even though a lot of progress was made during the last two years. The training of trainers for the vocation schools have been held and they have received the equipment needed for their training. Training of the existing workforce has also been conducted although in April 2010 a number of training sessions still remained to be undertaken. Up to April 2010, the Association of Refrigeration had given interim certificates to 19 Companies and 148 technicians (from which 89 are still under evaluation). A Governmental Decision had been sent for approval at all the signatory ministries and it was said that it would be published in the Official Journal no later than September 2010. The Governmental Decision was expected to be followed by a Ministerial Order which would establish the Association of Refrigeration as the interim certification body until 2011. With regards to the reuse scheme this activity is still not finalised. A number of seminars have been held to discuss the reuse scheme which raised a lot of interest. A survey was made of all the destruction facilities in the country to see which ones are incinerating based on the criteria of the Annex VI of the Regulation 1005/2009 regarding the ozone depleting substances. GreenWEEE was found to be the biggest integrated treatment plant for electric and electronic equipment waste (WEEE) in Romania and one of the most modern in Europe. They have 3 collection centers in the country (Lasi, Timisoara, Bucuresti). GreenWEEE can collect all the WEEE categories mentioned in the legislation (including large household appliances- refrigerators, freezers). The NOU has drafted a report for recycling systems in accordance with the EU existing legislation and based on the key aspects underlined by the consultation with the companies with interests in this field. Due to the existing economical situation the market is rather small. Also, meetings have been held with the customs and an draft instructions handbook was prepared based on the EU regulations. The additional delay is due to the initial long delay and the difficulties to speed up the process as much as needed to stick to the revised time plan. Also, the Governmental Decision was delayed and until September 2010 which further delayed the implementation of some of the measures proposed therein. Sweden also estimate that it will take time to get the reclamation system fully operational, something which will cause additional delay. Even if Romania had come quite far in April 2010 by holding stakeholder workshops and discussions and survey among the destruction facilities, this is much delayed already and it will take additional time to get it fully operational. The Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010.
UNEP | Rwanda | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-12-01 | 177000 | 177000 | 160013 | 0 | 4.6 |  | 0 |  |  | NOU conducted inspection visits to major boarders to monitor the control of ODS in collaboration with customs officials and Beaural of Standards. TPMP equipment and tools were procured and distributed. The country trained 50 Refrigeration experts and 20 customs officers | project completed
UNDP | Rwanda | CFC Phase Out Plan |  | 2007-11-01 | 2012-12-01 |  | 168000 | 168000 | 156586 | 4.6 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNEP | Saint Kitts and Nevis | CFC Phase Out Plan |  | 2006-04-01 |  | 2013-06-01 | 144000 | 130000 | 104842 | 0 | 0.6 | 0 | 0 |  |  | CAP Team conducted country mission in February 2012 to review project activities and agree on finalization of activities on the remaining funds. Applying the flexibility clause of the MYA between the Government and the ExCom, training activities on alternative technologies and reinforcement of Customs capacity were developed by means of TPMP and HPMP resources to contribute towards country’s compliance. Awareness and information activities on ODS alternative technologies and illegal trade prevention were addressed, maintaining zero level of CFC consumption, as well as, preventing the continuous increase in the use of HCFC-22 in the country.
UNDP | Saint Kitts and Nevis | CFC Phase Out Plan |  | 2006-04-01 |  | 2014-01-01 | 108000 | 105000 | 50000 | 1.8 | 0 | N.A. | N.A. | N.A. | N.A. | Action Plan is in place and definition of equipment need is being concluded to start the procurement. | Action Plan is in place and definition of equipment need is being concluded to start the procurement.
Canada | Saint Lucia | CFC Phase Out Plan |  | 2007-07-01 | 2012-03-01 |  | 205000 | 205000 | 203457 | 1.2 | 0 | 0 | 0 |  |  | Project completed by March 2012 and targets met.
UNDP | Samoa | CFC Phase Out Plan |  | 2007-11-01 |  | 2013-09-01 | 75000 | 75000 | 43950 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | During the year 2012, due to staff changes in NOU, activities relating to retrofit of MACs was delayed. NOU has also reported limited number of CFC based MACs available for retrofits. They also propose to use remaining funds under TPMP for HPMP activities in line with decision 60/11. | Project implementation progress is being closely monitored. All activities under this project are expected to be completed by end of Q3 2013.
UNEP | Samoa | CFC Phase Out Plan |  | 2007-11-01 | 2010-12-01 |  | 75000 | 75000 | 75000 | 0 | 0.7 | Not available | 0 |  |  | Project completed in December 2010 . In addition, capacity building of technicians and customs and enforcement officers played a very important role in the CFC phase out. TPMP activities provided training for technician and customs and law enforcement officers. Technician training was provided to 152 technicians in the servicing workshops that contributed in improvement of refrigeration services and adopting good practices in the domestic refrigeration and AC servicing sector. Training of more than 100 Customs, Quarantine and conservation officers contributed to implementation of ODS regulations during importation; Awareness activities have been carried out for the relevant national stakeholders including workshops to further inform them of the relevant information that they need to be aware of. Furthermore, a number of Important Ozone Issues pertaining the Phasing out of CFCs have been published in the Samoa Observer Newspaper and the main Television channel for effective awareness of the public towards Ozone issues and results of workshops. Also displays of Ozone boards were carried out at the National University of Samoa’s Open Day and Career Day for two years; The Samoa Refrigeration Engineering Association (SREA) is functioning well and collaborating with the NOU in conducting trainings and monitoring of the licensing system.
UNEP | Sao Tome & Principe | CFC Phase Out Plan |  | 2008-04-01 | 2010-12-01 |  | 75000 | 75000 | 75000 | 0 | 0.7 |  | 0 |  |  | Project financially completed
UNIDO | Sao Tome & Principe | Terminal phase-out management plan for CFCs |  | 2008-04-01 | 2011-12-01 |  | 115000 | 115000 | 114279 | 0.7 | 0 | 0 |  |  |  | The project was successfully completed.
UNEP | Senegal | CFC Phase Out Plan |  | 2007-07-01 | 2010-12-01 |  | 210000 | 210000 | 209000 | 0 | 23.4 |  | 0 |  |  | Project financially completed
Italy | Senegal | CFC Phase Out Plan |  | 2007-07-01 | 2012-12-01 |  | 355000 | 355000 | 304225 | 23.4 | 26.1 | n/a | 0 |  |  | A Purchase Order in the amount of US$ 44,512 was made in 2012 to buy Portable Refrigerant Identifiers, which is not reflected in records and will be corrected. Project completed in Dec 2012. | Revision of the completion date is related to the procurement of additional refrigerant identifiers only.
UNIDO | Serbia | National CFC phase-out plan |  | 2004-07-01 |  | 2013-12-01 | 2723222 | 2723222 | 1497813 | 327 | 0 | 0 |  |  |  | Decision of the NOU to utilize the funds for investment component (in combination with other tranches of NPP) delayed. Technical specification for consented scope of training equipment has been prepared as requested by the NOU. No procurement action has been agreed due to the pending decision of the NOU. | Purchase of equipment. Survey on the network of technical apprenticeship schools to carry out trainings. Select the schools; organize the trainings. Reason for the delay: coordinational activities took longer than expected.
Sweden | Serbia | CFC Phase Out Plan |  | 2004-07-01 | 2010-12-31 |  | 19322 | 19322 | 19322 | 0 |  |  | 0 |  |  | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010.
France | Seychelles | CFC Phase Out Plan |  | 2007-03-01 | 2010-12-01 |  | 193000 | 193000 | 139879 | 1.4 | 0 | 0 | 0 |  |  | The French contribution is implemented by GTZ-Proklima. The project is completed.
UNEP | Suriname | CFC Phase Out Plan |  | 2008-11-01 |  | 2013-12-01 | 153000 | 100000 | 85441 | 0 | 6.2 | 0 | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Two SSFAs were signed by the Government and UNEP. Fund disbursements released according to plan. Center of Excellence on low-GWP technology reinforced. HCFC quotas were issued by end of Dec. 2012. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. | 2013 annual work plan has been drafted. Quota system established. Customs Training Workshop including 5th Amendment of Customs codes has been planned for the current year.
UNDP | Suriname | CFC Phase Out Plan |  | 2008-11-01 | 2011-12-01 |  | 125000 | 125000 | 124997.63 | 6.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | Swaziland | CFC Phase Out Plan |  | 2008-11-01 |  | 2013-12-01 | 132000 | 132000 | 90017 | 0 | 3.7 |  | 0 |  |  | Country revised ODS Regulations to include HCFCs, reviewed training curricula for both customs training school and vocational training centre for refrigeration expert training. NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tool kits to some refrigeration repair workshops and refrigeration technicians. The refrigeration Association was assisted to get their constitution and get registered.
UNDP | Swaziland | CFC Phase Out Plan |  | 2008-11-01 | 2010-12-01 |  | 121500 | 121500 | 113799 | 0 | 3.69 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNIDO | Syria | National CFC phase-out plan for Syria |  | 2006-07-01 |  | 2013-12-01 | 754050 | 754050 | 620332 | 498.7 | 0 | 0 |  |  |  | No progress has been made due to the political and security situation.
UNDP | Togo | CFC Phase Out Plan |  | 2008-04-01 | 2010-12-01 |  | 157000 | 157000 | 156133.96 | 5.9 | 5.9 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNEP | Togo | CFC Phase Out Plan |  | 2008-04-01 | 2010-12-01 |  | 159000 | 159000 | 158712 | 0 | 6 |  | 0 |  |  | Project financially completed
UNDP | Trinidad and Tobago | CFC Phase Out Plan |  | 2003-07-01 | 2008-12-01 |  | 460000 | 460000 | 451587 | 77 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2008. | Completed in 2008.
IBRD | Turkey | CFC Phase-out plan for Turkey |  | 2001-12-01 | 2008-04-01 | 2009-12-01 | 9000000 | 9000000 | 8565903.15 | 977 | 0 | 0 | 0 | 0 | 0 | Refrigeration Sector Project (RSP) and overall ODS umbrella project with the World Bank physically and financially completed.
UNDP | Uruguay | CFC Phase Out Plan |  | 2006-11-01 |  | 2013-05-01 | 333000 | 333000 | 289574.9 | 29.9 | 0 | N.A. | N.A. | N.A. | N.A. | Activities to sustain complete phaseout of CFCs implemented in 2012. This includes training by international expert to local technicians, and provision of incentives/tools to local technicians. Expenditures to be reflected in 2013. | Final training will take place in April 2013.
Canada | Uruguay | CFC Phase Out Plan |  | 2006-11-01 | 2011-12-01 |  | 232000 | 232000 | 232000 | 0 | 0 | 0 | 0 |  |  | Project completed by December 2011 and targets met.
UNIDO | Venezuela | National CFC phase-out plan |  | 2004-04-01 | 2012-12-01 |  | 6240555 | 6112189 | 6064819 | 1035 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Zambia | CFC Phase Out Plan |  | 2007-11-01 | 2011-12-01 |  | 109000 | 109000 | 78510 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | Zambia | CFC Phase Out Plan |  | 2007-11-01 | 2012-03-01 |  | 136000 | 136000 | 131000 | 4.1 | 4.1 |  | 0 |  |  | Project completed
Germany | Zimbabwe | CFC Phase Out Plan |  | 2007-03-01 | 2009-03-09 |  | 565000 | 565000 | 565000 | 65 | 65 | 53.27 | 0 |  |  | project completed
USA | China | CFCs/CTC/Halon Accelerated Phase-Out Plan |  | 2004-12-01 | 2009-01-01 |  | 10000000 | 10000000 | 10000000 | NA | 1000 | 1000 | NA | 1550 | 1537 | CFC production stopped by June 30, 2007 as per agreement. Five CFC plants have been closed and dismantled. 1 CFC plant, Juhua, remains open for production of CFCs for MDIs (with 550 MT allocated for 2009 and 547 MT produced). Verification report indicates that CFC and halon production were within the agreed limits for 2008; data for 2009 shows that compliance with production phase-out target continues.
IBRD | India | CTC phase-out plan for the consumption and production sectors |  | 2003-07-01 |  | 2013-12-01 | 38100954 | 38100954 | 37204080 | 11505 | 0 | 0 | 11553 | 0 | 0 | TA workplan is pending approval. There is limited disbursements for basic functioning of the PMU until then.
Germany | India | CTC Phase Out Plan |  | 2004-04-01 | Dec-10 |  | 2000000 | 2000000 | 2000000 | 970 | 268 |  | 0 |  |  | The environment, health and safety material has been completed and capacity building with institutional stakeholders from the power sector has taken place. All project activities have been completed now.
Japan | India | CTC Phase Out Plan |  | 2004-04-01 |  | 2006-11-01 | 5000000 | 5000000 | 3381149 | 533 | 1726 |  | 0 | 1726
France | India | CTC Phase Out Plan |  | 2004-04-01 | 2009-12-01 |  | 3000000 | 3000000 | 1306950 | 1385 | 708 |  | 0 |  |  | The French contribution is implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of the activities has been training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
UNIDO | India | CTC phase-out for the consumption and production sectors |  | 2005-04-01 |  | 2013-07-01 | 3899046 | 3899046 | 3469371 | 1080 | 0 | 0 | 347 |  |  | Local supplier (Hind Erectors) dismantled old equipment and installed the new one. The installation of multiple effect evaporator awarded earlier to another local supplier (Food & Biotech) is still pending delaying the project completion. UNIDO country office is taking care of the issue as well as of the one pertaining to the low disbursement of obligated funds, related to the long overdue submission of the interim and final reports by local sub-contractors. | A joint UNIDO/NOU inspection mission to the project sites for evaluation of the project results is planned for 2013. The project is expected to be completed in 2013. Reason for the delay: Installation of equipment procured from local supplier took longer than expected.
UNIDO | Korea, DPR | Plan for terminal phase-out of CTC |  | 2003-12-01 | 2010-12-01 |  | 5684844 | 5684840 | 5680504 | 1634.2 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Pakistan | Sector phase-out plan of CTC |  | 2003-12-01 | 2009-12-01 |  | 2745665 | 2745665 | 2742074 | 489 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | China | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors |  | 2002-11-01 | 2009-12-01 |  | 5571539 | 5571539 | 5543998 | 918 | 0 | 0 |  |  |  | The project was successfully completed.
Italy | China | Domestic Refrigeration |  | 2002-11-01 | 2005-10-01 |  | 1788991 | 1788991 | 1788991 | 181 | 0 | 0 | 0 |  |  | FIN
UNIDO | Korea, DPR | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company |  | 2003-07-01 | 2009-12-01 |  | 1365011 | 1365011 | 1364978 | 56 | 0 | 0 |  |  |  | The project was successfully completed.
IBRD | China | Foam Sector |  | 2001-12-01 | 2010-12-01 | 2010-12-01 | 53846000 | 53846000 | 53846000 | 14143 | 0 | 0 | 0 | 0 | 0 | The sector plan will not be financially closed until the China-WB umbrella project (ODSIV) is completed in 2013 in order to permit continuous monitoring.
IBRD | China | Halon Sector |  | 1997-11-01 | 2011-12-01 | 2011-12-01 | 62000000 | 62000000 | 62000000 | 24480 | 0 | 0 | 30060 | 0 | 0 | Project completed. Sector plan will not be considered financially closed until the China-WB umbrella project (ODSIV) is completed in order to permit monitoring.
UNDP | Argentina | Methyl Bromide |  | 2002-03-01 | 2009-06-01 |  | 3588000 | 3588000 | 3587926.51 | 156 | 184.4 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNIDO | Chile | National phase-out of methyl bromide - terminal project |  | 2010-04-01 |  | 2013-12-01 | 1657917 | 1657917 | 598829 | 164.4 | 164.4 | not yet available |  |  |  | Grafting technology and biofumigation were introduced and consolidated in two areas: Quillota and Arica. The recruitment of a national consultant company for the strawberry sector started. | The first tranche is almost completed and the request for the second (final) tranche was approved at the 69th Meeting of the Executive Committee in April 2013. The work in the grafting, mainly in the management of grafted plants, is planned to be continued in 2013. In addition, more pilot cases are anticipated in the strawberry and in the tomato sector (biofumigation). A study tour is planned to Mexico with focus on the grafted tomato plants nurseries.
UNEP | Chile | Methyl Bromide |  | 2010-04-01 |  | 2014-04-01 | 73000 | 73000 | 68700 | 0 |  |  | 0 |  |  | 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. National consultant hired to draft adjustments on current pesticides legislation to enforcement the online traceability system. | Adjustments to current pesticides legislations are being reviewed by the Cabinet.
UNIDO | China | National phase-out of methyl bromide |  | 2003-12-01 |  | 2015-12-01 | 10789342 | 9986600 | 9286597 | 553.8 | 150 | 150 |  |  |  | The 2012 annual implementation programme associated with the 7th tranche was approved in 2012. Signed contract with international consultancy company to fine tune MB alternative technologies in ginger sector, project staff participated in study tour at Horty Fair in the Netherland and visited UNIDO's projects in Mexico to acquire new experiences to fine tune MB alternatives in China. The MB phase-out target was achieved in 2012. The ginger sector has been the sector using most of the MB still available. The tomato, cucumber and strawberry have been almost completely converted, monitoring going on in other sectors. | Develop and test new injection machines for chloropicrin, dazomet and metham sodium (all sectors), fine tune grafting technology for tomato and cucumber, monitor the situation in Taro and other rhizome crops where some MB had been used in 2012. Training and awareness programme continue as planned.
Italy | China | Methyl Bromide |  | 2005-07-01 | 2009-12-01 |  | 4000000 | 4000000 | 4000000 | 534 | 390 | 390 | 0 |  |  | FIN
UNDP | Costa Rica | Methyl Bromide |  | 2001-12-01 |  | 2014-06-01 | 4845283 | 4845283 | 4428849.93 | 342 | 140 | N.A. | N.A. | N.A. | N.A. | Biological alternatives are being introduced at commercial scale in the MB sector in Costa Rica. The 2012-13 season was the last season where MB could be used. Technical assistance and investments are being made to be ready for the 2013-14 season, which will be the first free of MB. Progress report was presented to ExCom 68. | The project is closely following the 2012-13 harvest season to trouble shoot on the problems arising with the use of new alternatives. In May, the final evaluation of the harvest season will be done.
UNIDO | Guatemala | National phase-out of methyl bromide (phase II) |  | 2009-11-01 |  | 2013-12-01 | 2243047 | 2243047 | 660821 | 265.7 | 117.7 | not yet available |  |  |  | UNIDO was requested to submit the project completion report to the Executive Committee soon after completion of the 2013 annual implementation programme. Purchase of the laboratory equipment was carried out. Farmers got support in the use of alternative fumigants. | The establishment of the laboratory is planned and the first run of the biological agents will be tested and applied.
UNEP | Guatemala | Methyl Bromide |  | 2009-11-01 |  | 2013-11-01 | 70000 | 70000 | 0 | 0 | 320.6 |  | 0 |  |  | Investment activities were implemented by UNIDO. According to the project work plan, UNEP was responsible for the non-investment activities, scheduled for 2013.
UNIDO | Honduras | National methyl bromide phase-out plan, phase II |  | 2006-11-01 | 2011-12-01 |  | 1806301 | 1806301 | 1806183 | 295.8 | 81.6 | not yet available |  |  |  | The project was successfully completed.
UNDP | Kenya | Methyl Bromide | Cut Flowers | 2002-11-01 | 2009-12-01 |  | 510660 | 510660 | 504124 | 10 |  |  | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
Germany | Kenya | Methyl Bromide |  | 2003-04-01 | 2010-01-01 |  | 574492 | 574492 | 574492 | 34 | 29 | 17.4 | 0 |  |  | The Project has been completed. PCR submitted in September 2010
UNIDO | Kenya | Technology transfer leading to methyl bromide phase-out in soil fumigation |  | 2007-11-01 | 2009-12-01 |  | 510659 | 510659 | 508771 | 53 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Lebanon | Phase-out of methyl bromide for soil fumigation in strawberry production |  | 2001-07-01 | 2009-12-01 |  | 1264450 | 1264450 | 1244912 | 50.4 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Lebanon | Methyl Bromide |  | 2001-07-01 | 2009-12-01 |  | 2567300 | 2566717 | 2566716.59 | 186.1 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2009. | Completed in 2009.
UNIDO | Libya | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others. |  | 2005-11-01 | 2010-12-01 |  | 743000 | 743000 | 743000 | 56 | 0 | 0 |  |  |  | The project was successfully completed.
Spain | Libya | Methyl Bromide |  | 2008-11-01 |  | 2013-12-01 | 500000 | 500000 | 220112 | 40 | 30 | 30 | 0 |  |  | Project implementation in Libya reverted to operational conditions. Two greenhouses purchased in 2010 have been completed in the first week of 2013 and three national experts are assisting UNIDO in monitoring activities and implementing training and awareness activities. Monitoring and planning mission by UNIDO is planned to take place as soon as clearance is received by Libyan Authorities.
UNDP | Malawi | Methyl Bromide |  | 2000-12-01 | 2006-12-01 |  | 2999824 | 2999824 | 2988303 | 129 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2006. | Completed in 2006.
UNIDO | Mexico | National methyl bromide phase-out plan |  | 2008-04-01 |  | 2013-12-01 | 6122379 | 6122379 | 4717292 | 715 | 325 | not yet available |  |  |  | The purchase of additional greenhouses and their installation took place in 2012. Strawberry farmers got continuous support. | It is planned to continue the installation of greenhouses and support the strawberry sector in the grafting. The request for the final tranche was submitted and approved at the 69th Meeting of the Executive Committee in April 2013.
Canada | Mexico | Methyl Bromide - Commodities |  | 2008-04-01 | 2012-03-01 |  | 500000 | 500000 | 500000 | 20 | 795 | 745.4 | 0 |  |  | First tranche target consumption of 795 ODP T for 2009 was met. Targets for later years are not relevant for Canada as they are associated with subsequent tranches of the project to be implemented by other agencies.
Italy | Mexico | Methyl Bromide - Soil Fumigation |  | 2008-04-01 | 2012-11-01 |  | 1000000 | 1000000 | 993996 | 70 | 0 | 0 | 0 |  |  | Project completed in Nov 2012. Financial completion in Nov 2012. | The grreenhouses are being delivered, (customs clearance). We expect that they will be installed in June-July, so that in August 2012 will be fully operational and the project finally be completed. First run of production with the new equipment will be done during 2012, and IOC will be accordingly paid.
Spain | Mexico | Methyl Bromide - Soil Fumigation |  | 2010-04-01 |  | 2014-06-01 | 1600000 | 1600000 | 799997 | 90 |  |  | 0 |  |  | Purchase of addtiional greenhouses and installed. Continue support to the strawberry farmers. To continue the installation of greenhouse, support in grafting, support the strawberry sector. Request of the final tranche at the 69th ExCom.
UNIDO | Morocco | Phase-out of methyl bromide for soil fumigation in tomato production |  | 2001-07-01 | 2011-12-01 |  | 3912949 | 3912949 | 3901324 | 389.9 | 0 | 0 |  |  |  | Project was successfully completed in 2011
UNIDO | Morocco | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits |  | 2008-11-01 |  | 2013-12-01 | 1127594 | 1127594 | 1028632 | 106.2 | 0 | not yet available |  |  |  | Mission to the composting plants was conducted in June 2012. The composting plants are operational and the production of high-quality compost as alternative to MB for green-beans is ongoing. All main activities have been completed in the year 2012 and closure ceremony was scheduled for 19 December 2012. Due to logistic reasons, the project closure could not take place in 2012 and it has been postponed to 2013. | Final workshop and project closure planned for the beginning of June 2013. Morocco has confirmed the ban on the import of Methyl Bromide.
Italy | Morocco | Methyl Bromide - Green Beans and Melon |  | 2008-11-01 |  | 2013-12-01 | 310000 | 310000 | 250186 | 0 | 260.9 | 260.9 | 0 |  |  | Mission to the composting plants was conducted in June 2012 and it was established that the composting plants are operational and the production of high-quality compost as alternative to MB for green-beans in ongoing. Final workshop and project closure planned in 2013. The achieved phase-out is within the agreed phase-out schedule.
UNIDO | Syria | Phase-out of the use of methyl bromide in grain storage |  | 2001-07-01 | 2011-12-01 |  | 1084139 | 1084139 | 1076061 | 105 | 0 | 0 |  |  |  | The project was successfully completed.
IBRD | Thailand | National methyl bromide phase-out plan |  | 2004-12-01 |  | 2013-12-01 | 2901600 | 2901600 | 1019351 | 241.8 | 18.3 | 17.04 | 0 | 0 | 0 | MB consumption for non-QPS applications of 17.04 ODP MT in 2012, did not exceed the agreed maximum allowable consumption with the ExCom. 13 type 1 subprojects were approved by PMU-DoA for financial assistance under the project. One is financially completed, 5 are physically completed, 6 are under implementation and one remaining is being appraised by Government Savings Bank (GSB). PMU-DoA conducted training on MB alternatives for 5 enterprises (Type I) that already received equipment in Aug. 12. For type 2 beneficiaries, PMU-DoA approached the Rice Mill Association to seek cooperation to disseminate project information to its members. In 2012, PMU-DOA also developed another publication on fumigation techniques namely “Conducting Fumigation Manual.” 500 copies produced and distributed to users and other stakeholders. In addition, PMU-DOA produced 500 copies of a training video on MB elimination. | A meeting with MB importers was conducted in Feb. 13 to reiterate that import of MB for non-QPS applications is not allowed starting Jan. 1, 2013. PMU-DoA approved one additional type-1 subproject, which is being appraised by GSB. For type-2 subprojects, PMU-DOA conducted first training in Jan. 2013 in Suphanburi Province with 45 enterprises in attendance. 2nd training conducted early Apr. 2013 in Loei Province. Vouchers will be issued and distributed to those who are eligible for funding to acquire IPM and basic fumigation equipment. PMU-DoA plans to have 3rd training in May 2013 in Chachoengsao Province.
UNIDO | Turkey | Phase out of methyl bromide in protected tomato, cucumber and carnation crops |  | 2001-12-01 | 2009-11-01 |  | 3408844 | 3408844 | 3329511 | 292.2 | 0 | 0 |  |  |  | The project was successfully completed.
IBRD | Vietnam | National phase-out plan for methyl bromide |  | 2006-11-01 |  | 2015-11-01 | 1098284 | 1000000 | 824875 | 85.2 | 70 |  | 0 | 0 | 0 | Vietnam successfully met its 2012 MB consumption reduction targets under the Excom Agreement. After 1st study on PH3 resistance, PMU carried out in 2012 a follow-up study to develop a national strategy on PH3 resistance management. All training centers fully equipped with fumigation and protection equipment as well as PH3 for practical training on site for fumigation service companies and owners of storage facilities. A train-the-trainers workshop for the 5 centers held in early 2012. 4 training workshops for fumigation service companies and 5 for owners of storage facilities held by 5 Regional Plant Quarantine Sub-Departments (RPQSD) assigned as the training centers. Assessment of integrated approaches for MB replacement in pre-harvest applications completed in 2012. 3 alternatives show relatively good results, especially economic efficiency, on crops chosen for the demonstrations. Alternatives evaluated to be considerably effective will be printed on leaflets and introduced on local televisions so that more growers are aware. PMU organized 2 training workshops for farmers and local technicians. 9 fumigation service companies completed purchasing of fumigation equipment since May 2012. | The MB import quota for 2013 has been issued.
Germany | Yemen | Methyl Bromide |  | 2008-11-01 |  | Dec-14 | 601450 | 601450 | 346058 | 35.9 | 20 | 13.1 | 0 |  |  | Since November 2008 to 31st December 2012, 597 farmers and 30 Extentionists were trained and 187 farms received materials of solarization and Biofumigation technologies. In addition to 240 farmers and 18 Extentionists were trained and 16 farms received materials during implementation of first stage of MB phase-out (of MLFS code YEM/FUM/41/TAS/21, 2003-2008). Licensing and quota systems are in place and total reduction of 22.73 ODP tonnes of MB was achieved during 2008-2012 (Consumption of 2007 was 35.85ODP and of 2012 was 13.12ODP). | Following-up the results of local herbs technology for soil fumigation and supervising solarization technology application by the new 100 farms in Sadah. Coordination for distribution of more 20 plastic sheets for farms in Sana'a, Dhamar, Mahweet and Hudaidah areas.
UNIDO | Zimbabwe | Total phase-out of methyl bromide used in tobacco seedlings |  | 2005-11-01 | 2008-12-01 |  | 3724972 | 3724972 | 3724970 | 170 | 0 | 0 |  |  |  | The project was successfully completed.
Germany | Afghanistan | ODS Phase Out Plan |  | 2005-11-01 | Dec-09 |  | 760806 | 760806 | 760806 | 179.82 | 179.82 | 179.82 | 0 |  |  | M-Y-A plan completed
UNEP | Afghanistan | ODS Phase Out Plan |  | 2005-11-01 | 2010-12-09 |  | 305000 | 305000 | 305000 | 0 | 57 | 0 | 0 |  |  | Project completed in December 2010.
UNEP | Albania | ODS Phase Out Plan |  | 2003-04-01 | 2006-07-01 |  | 118125 | 118125 | 107684 | 0 | 6.6 |  | 0 |  |  | Project financially completed. $6,805 plus $885 PSC returned at ExCom 53
UNIDO | Albania | National ozone depleting substances phase-out plan |  | 2003-04-01 | 2012-09-01 |  | 535000 | 535000 | 533167 | 68 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Algeria | National phase-out plan |  | 2007-11-01 |  | 2013-11-01 | 921500 | 921500 | 823444 | 284.6 | 0 | 0 |  |  |  | Due to lack of support from NOU, no real progress was made in 2012 in this project, despite regular follow-up by UNIDO HQ as well as UNIDO's office in Algiers. There were extensive preparations from UNIDO to organize the HPMP launching meeting in October 2012. However, the meeting had to be cancelled, since no confirmation was received from the government. | However, beginning of 2013 a new Environment and Sustainable Development Director has been appointed by the Government, to whom UNIDO managed to establish contact. As a result, a mission was organized in February 2013 where the whole MP portfolio was discussed. UNIDO got confirmation on the government's support in reviving the activities in an accelerated manner. As a result, it was agreed that a customs training will be organized in the first half of 2013 jointly with UNEP, being in charge of the institutional srengthening project. It is expected to be held in May or June 2013. Furthermore, bidding documents were prepared for the purchase of 10 refrigerant identifiers. Bidding was closed in March and the contract was issued in April 2013.
UNEP | Bangladesh | ODS Phase Out Plan |  | 2004-04-01 | 2008-12-01 |  | 294175 | 294175 | 294175 | 0 | 87.2 |  | 0 |  |  | Project financially completed | Project Financially completed
UNDP | Bangladesh | ODS Phase Out Plan |  | 2004-04-04 | 2012-12-01 |  | 879750 | 879750 | 874862 | 267.6 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. All activities under this project completed in the year 2012. | Completed in 2012. The project is expected to be financially closed by end of Q2 2013.
Canada | Bolivia | ODS Phase Out Plan |  | 2007-03-01 |  | 2013-07-01 | 162000 | 162000 | 162000 | 0 | 0 | 0 | 0 |  |  | First tranche fully completed. Second tranche nearly completed. Targets met.
UNDP | Bolivia | ODS Phase Out Plan |  | 2007-03-07 | 2012-10-01 |  | 378000 | 378000 | 372848.2 | 26.9 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. Final activities under the TPMP have been implemented and project is completed. | Completed in 2012. 5000 US$ from Environment Canada has been transferred to UNDP and will be implemented under this project.The remaining resources will be used for training of technicians in Bolivia.
UNIDO | Bosnia and Herzegovina | National ODS phase-out plan |  | 2003-12-01 |  | 2013-12-01 | 864160 | 864160 | 618475 | 121.1 | 0 | 0 |  |  |  | TOR on the local bidding for selection of R&R centers prepared. Following the established procedures the NOU finalized the public call for submission of proposals. | Selection of R&R centers. International bidding for R&R equipment. Evaluation of proposals and placement of the purchase order. Delivery of R&R equipment and start of R&R operation. The project is expected to be completed in 2013. Reason for the delay: The selection of the beneficiary companies by the NOU took longer than expected.
UNIDO | Cameroon | Terminal CFC/TCA phase-out management plan |  | 2006-11-01 | 2011-12-01 |  | 800000 | 800000 | 797941 | 50.6 | 0 | 0 |  |  |  | Project was successfully completed in 2011.
UNDP | Colombia | ODS Phase Out Plan |  | 2003-12-03 | 2011-12-01 |  | 4500000 | 4500000 | 4487200.6 | 805.85 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNIDO | Congo | Terminal phase-out management plan |  | 2008-04-01 |  | 2013-12-01 | 95000 | 95000 | 57882 | 3.4 | 0 | 0 |  |  |  | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). Reason for the delay: UNIDO is of the view that the impact of the project is maximized linking it to the HPMP.
UNEP | Congo | ODS Phase Out Plan |  | 2008-04-01 | 2012-01-01 |  | 110000 | 110000 | 110000 | 0 | 1.8 |  | 0 |  |  | Project completed in Jan 2012
UNDP | Cuba | ODS Phase Out Plan |  | 2005-04-05 |  | 2013-03-01 | 1559228 | 1559228 | 1473567 | 331.3 | 0 | N.A. | N.A. | N.A. | N.A. | The procurement of final batch of tools and materials was made in the end of 2012. Payment will be reflected in early 2013. | Tools and materials delivered to Cuba.
Germany | Cuba | ODS Phase Out Plan |  | 2004-07-01 |  |  | 43453 | 43453 | 43453 | 0 | 0 | 0 | 0 |  |  | Cuba requested the change of implementation agencies. The transfer to UNDP is completed.
France | Cuba | ODS Phase Out Plan |  | 2004-07-01 |  |  | 80319 | 80319 | 80319 | 0 | 94.2 |  | 0 |  |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
Canada | Cuba | ODS Phase Out Plan |  | 2004-07-01 | 2011-06-01 |  | 462000 | 462000 | 462000 | 30 | 0 | 0 | 0 |  |  | Project completed and relevant targets (for Canada, 2004 and 2005) were met.
UNEP | Equatorial Guinea | ODS Phase Out Plan |  | 2009-04-01 |  | 2013-06-01 | 180000 | 105000 | 80000 | 4.6 | 4.7 |  | 0 |  |  | The country conducted training of 30 refrigeration technicians and 20 custom officers.. The activities are ongoing satisfactorily.
UNEP | Eritrea | ODS Phase Out Plan |  | 2008-04-01 |  | 2013-07-01 | 170000 | 170000 | 80000 | 0 | 6.2 |  | 0 |  |  | NOU trained 30 refrigeration experts and 15 customs officer. The country procured and distributed tools and equipment. Conducted public awareness activities on Montreal Protocol through radio and tv. 2nd tranche SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the absence of Ozone Officer. The Government is in the process of appointing new Ozone Officer to proceeding with implementation of activities | Implementation of activities has delayed due to change of Ozone Officer. The government is in the process of appointing new Ozone Officer
UNIDO | Eritrea | Terminal phase-out management plan for CFCs |  | 2008-04-01 | 2013-03-01 |  | 175000 | 175000 | 123130 | 4.2 | 0 | 0 |  |  |  | Project completed in Mar 2013.
UNDP | Indonesia | ODS Phase Out Plan | Aerosol | 2004-12-01 | 2006-06-01 |  | 224000 | 224000 | 181887 | 80 | 0 | 0 | N.A. | N.A. | N.A. | Completed in 2006. | Completed in 2006.
UNIDO | Indonesia | Plan for terminal phase-out of ODS in the solvent sector |  | 2004-12-01 | 2008-10-01 |  | 1464733 | 1464733 | 1464063 | 100.1 | 0 | 0 |  |  |  | The project was successfully completed.
IBRD | Indonesia | Refrigeration sector phase-out plan: MAC servicing sector |  | 2002-11-02 | 2010-03-01 | 2010-03-01 | 4317000 | 4317000 | 4317000 | 915 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Indonesia | Phase-out of residual CFCs in the foam sector |  | 2004-04-01 | 2010-06-01 | 2010-06-01 | 2957564 | 2957564 | 2957564 | 352 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Indonesia | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives |  | 2004-12-31 | 2010-06-01 | 2010-06-01 | 371910 | 371910 | 371910 | 70 | 0 | 0 | 0 | 0 | 0 | Project completed.
UNDP | Indonesia | ODS Phase Out Plan | Refrigeration Manufacturing | 2002-07-01 | 2010-08-01 |  | 6398000 | 6398000 | 6391359.93 | 1141 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2010. | Completed in 2010.
UNDP | Indonesia | ODS Phase Out Plan | Refrigeration Servicing | 2002-11-01 | 2011-12-01 |  | 4912300 | 4912300 | 4903252 | 1072 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNEP | Iraq | ODS Phase Out Plan |  | 2009-07-01 |  | 2013-07-01 | 1641000 | 1641000 | 586959 | 0 | 227.6 |  | 0 |  |  | Train the trainers workshop on good practices and R&R conducted in Erbil, Iraq during May 2012 where 45 master trainers received comprehensive training. Training equipment distributed to 10 training institutes Coordination meeting, organized in Bahrain Oct-12, for PMU and orientation meeting for Finance Officials, from Ministry of Environment, on proper financial reporting according to UN requirements. Pending payments under the 1st tranche contract released after receiving proper financial and progress reports resulting in releasing 70% of the total fund under the 1st tranche contract. 2nd tranche activities are designed as continuation of the 1st tranche activities, respective resources are incorporated in the revised NPP work-plan. Contract for the 2nd tranche was pending till disbursing at least 70% of the 1st tranche resources | PMU concluded agreement with Ministry of Higher Education to train 300 technicians in Iraq over a period of 2 years i.e. 2013-2014 which is total targeted under NPP project (1st and 2nd tranches). PMU, NOU and UNEP revised the work-plan for the 2013-2014 in line with delays encountered due to administrative and logistical difficulties on ground to ensure completion of all activities by end of 2014. Revised contract will be established by May 2013 incorporating 2nd tranche resources in the agreement. Revised contract will be established by May 2013 incorporating 2nd tranche resources in the agreement
UNIDO | Iraq | National phase-out plan |  | 2009-07-01 |  | 2013-12-01 | 4656530 | 4656530 | 2573381 | 1640.8 | 0 | 0 |  |  |  | The planned training was conducted in Erbil during summer 2012. Additional equipment (3 x reclaim centers) has been tendered and evaluated. | 1. Delivery of Equipment. 2. Installation and testing. The project is expected to be completed in 2013. Reason for the delay: The customs clearance has taken longer than expected.
UNEP | Kuwait | ODS Phase Out Plan |  | 2007-07-01 |  | 2013-12-01 | 335000 | 240000 | 1757 | 0 | 72.1 |  | 0 |  |  | All remaining activities under TPMP were incorporated in the HPMP of Kuwait which approved by 66th ExCom. UNEP and NOU prepared comprehensive work-plan to start implementation of the HPMP and remaining TPMP activities | Country contract is due for signature by 1st half of 2013 for both HPMP and TPMP activities
UNIDO | Kuwait | Terminal phase-out management plan for Annex A Group I substances |  | 2007-07-01 | 2010-11-01 |  | 230000 | 220000 | 217493 | 70 | 0 | 0 |  |  |  | The project was successfully completed.
UNEP | Madagascar | ODS Phase Out Plan |  | 2007-07-01 | 2009-07-01 |  | 220000 | 220000 | 220000 | 0 | 7.2 |  | 0 |  |  | Project financially completed.
UNIDO | Madagascar | Terminal phase-out management plan |  | 2007-07-01 | 2009-12-01 |  | 125000 | 125000 | 122513 | 2.3 | 0 | 0 |  |  |  | The project was successfully completed.
IBRD | Malaysia | National CFC phaseout plan |  | 2001-12-01 | 2010-12-01 | 2010-12-01 | 11517005 | 11517005 | 11441013 | 1910.51 | 0 | 0 | 0 | 0 | 0 | Project completed.
Germany | Mauritius | ODS Phase Out Plan |  | 2003-12-01 | Dec-10 |  | 212030 | 212030 | 212030 | 4 | 1 | 0.2 | 0 |  |  | Project has been completed.
UNIDO | Montenegro | Terminal phase-out management plan |  | 2007-11-01 |  | 2013-07-01 | 270295 | 270295 | 242904 | 5.15 | 0 | 0 |  |  |  | Equipment delivered and distributed in the fourth quarter of 2012. | The project is expected to be completed in 2013.
UNEP | Saint Vincent and the Grenadines | ODS Phase Out Plan |  | 2005-11-01 | 2010-12-01 |  | 109000 | 109000 | 109000 | 0 | 0.3 | 0 | 0 |  |  | Project financially completed | Financially completed.
UNDP | Saint Vincent and the Grenadines | ODS Phase Out Plan |  | 2005-11-01 | 2012-05-01 |  | 128000 | 128000 | 127826.54 | 2.08 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNIDO | Saudi Arabia | National phase-out plan |  | 2007-11-01 |  | 2013-12-01 | 1430000 | 1430000 | 1073220 | 782 | 0 | 0 |  |  |  | All equipment was distributed during spring 2012. It was agreed to re-allocate some funds from NPP to exploration of E-licensing system as well as certification scheme for refrigeration technicians. HPMP approved at the 68th Meeting of the Executive Committee, the project transferred to the HPMP. | 1. E-licensing system as well as certification scheme for refrigeration technicians.
UNEP | Saudi Arabia | ODS Phase Out Plan |  | 2007-11-01 |  | 2013-12-01 | 405000 | 405000 | 242989 | 0 | 269.8 |  | 0 |  |  | Curricula update has been finalized. The development of national code for good practices has been initiated. However, and due to limited funding and miscommunications between respective governmental authorities, completion of the code was delayed and expected to be completed under the HPMP. a second round of train the trainers took place during April 2012 and training equipment have been distributed among participating centers. several training courses have been organized for RAC technicians in main cities where R&R equipment and tools supplied under the project have been provided. | The remaining training activities as well as the update of regulations and certification scheme will be incorporated in the HPMP action plan
UNEP | Sierra Leone | ODS Phase Out Plan |  | 2009-04-01 |  | 2013-12-01 | 150000 | 150000 | 97545 | 0 | 11.8 |  | 0 |  |  | NOU finalised review process of training curricula manual for both customs and refrigeration technicians training schools. Both training schools have started using the new curricula which include ozone modules. Revised ODS regulations were approved and enforcement is into effect | Project completed
UNDP | Sierra Leone | ODS Phase Out Plan |  | 2009-04-01 | 2011-12-01 |  | 60000 | 60000 | 54715 | 12.2 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2011. | Completed in 2011.
UNIDO | Sudan | National CFC/CTC phase-out plan |  | 2004-12-01 | 2012-03-01 |  | 1139480 | 1139480 | 1137501 | 217.4 | 0 | 0 |  |  |  | The project was successfully completed.
UNDP | Tanzania | ODS Phase Out Plan |  | 2008-04-01 |  | 2013-12-01 | 276000 | 276000 | 153092.16 | 54 | 0 | N.A. | N.A. | N.A. | N.A. | Monitoring over the operation of the zonal centres continued. In March 2012, two (2) training sessions for technicians completed (30 people each). Last tender for procurement of multi-gas identifiers had been announced twice during 2012 (after failed local tender in 2011). Initial tender during summer 2012 did not still generate enough interest from existing suppliers. Second tender was expanded in its scope in November 2012 to include standard R&R tools (recovery, containtment, leak detection) to encourage more companies to apply. | Two companies only applied (STAG and Unicorn), and review on bids was provided. Clarifications were sought from the companies before selection process could be finalized. Unicorn is the selected bidder. Equipment will consist of multi-gas analyzers and R&R tools. Equipment is expected within next 7 months.
UNEP | Tanzania | ODS Phase Out Plan |  | 2008-04-01 |  | 2013-12-01 | 209000 | 209000 | 181000 | 0 | 38.1 |  | 0 |  |  | NOU conducted inspection visits to major boarders to monitor the control of ODS in collaboration with customs officials and Beaural of Standards. TPMP equipment and tools were procured and distributed | Project completed
IBRD | Thailand | National CFC phaseout plan |  | 2001-12-01 |  | 2013-12-01 | 14728626 | 14728626 | 11763302 | 3107.52 | 0 | 0 | 0 | 0 | 0 | A Steering Committee was established in Sep. 2012 whereby all responsibilities for remaining activities under the NCPP will be transferred to it. Key priorities include hiring of personnel to perform specific duties (financial management, technical oversight of training program on R&R at vocational schools, etc.). | Steering Committee was disbanded. Responsibility for all activities under the NCPP have been transferred to within the National Ozone Unit (NOU). The project proposal for strengthening training capacity and bidding documentation were submitted to the Bank.
UNIDO | Tunisia | ODS Phase Out Plan |  | 2012-12-01 |  | 2013-12-01 | 705518 | 705518 | 0 | 172.5 | N/A | not yet available |  |  |  | The project was transferred from the World Bank to UNIDO at the 68th Meeting of the Executive Committee in 2012. | Agreement on plan of activities, drafting of technical specifications for the purchase of equipment and international bidding process will be carried out in 2013.
IBRD | Tunisia | National ODS phase-out plan |  | 2006-07-01 | 2012-06-01 | 2012-12-01 | 1135395 | 1135395 | 429877 | 342 | 0 | 0 | 0 | 0 | 0 | Umbrella project closed in June 2012. Remaining NOPP transferred to UNIDO at the 68th Meeting of the ExCom.
France | Uganda | ODS Phase Out Plan |  | 2008-07-01 | 2011-04-01 |  | 215000 | 215000 | 90225 | 1.9 | 0 | 0 | 0 |  |  | The French contribution is implemented by GTZ-Proklima. The project is completed.
IBRD | Vietnam | National CFC and halon phase-out plan |  | 2005-04-01 | 2010-12-01 | 2010-07-01 | 1260000 | 1260000 | 1259448 | 258.69 | 0 | 0 | 0 | 0 | 0 | Project completed.
UNEP | Yemen | ODS Phase Out Plan |  | 2008-07-01 |  | 2013-12-01 | 455000 | 455000 | 227600 | 0 | 269.4 |  | 0 |  |  | All remaining activities under NPP of Yemen are incorporated in the HPMP approved Dec-12 which will start in 2013 | Due to recent political development and subsequent changes of Minister of Environment & Water, as well as the Chairman of Environment Protection Authority (EPA); UNEP is waiting for clear instructions of new management to draft and process new ISP agreement.
UNIDO | Yemen | National ODS phase-out plan |  | 2008-07-01 |  | 2014-06-01 | 1370500 | 1370500 | 1098743 | 269.1 | 0 | 0 |  |  |  | No additional equipment purchases have been done within tranche 2 of the Yemen TPMP. It has been agreed that any remaining funds will be utilized in the HPMP; submitted for the 68th ExCom. | The HPMP was approved at the 68th Meeting of the Executive Committee. The project was transferred to the HPMP.
IBRD | China | CTC/PA Sector Phase I |  | 2002-11-02 | 2011-12-01 | 2011-12-01 | 65000000 | 65000000 | 65000000 | 11160.2 | 0 | 0 | 52162 | 0 | 0 | Remaining tranche of $500,000 disbursed in 2012.
IBRD | China | CTC/PA Sector Phase II |  | 2005-11-02 | 2010-07-31 | 2009-12-31 | 46500000 | 46500000 | 46500000 | 6945 | 0 | 0 | 0 | 0 | 0 | As CTC is co-produced with chloroform and the huge and increasing demand for chloroform, CTC will continue to be a challenge and require ongoing monitoring by FECO and the WB. Remaining balance of $215,000 disbursed to FECO in 2012.
IBRD | Argentina | CFC production closure plan |  | 2002-11-02 | 2009-12-01 | 2009-11-01 | 10600000 | 10600000 | 10600000 | 0 | 0 | 0 | 3020 | 0 | 0 | Project completed.
IBRD | China | CFC Production Sector |  | 1999-03-01 | 2010-12-01 | 2010-12-01 | 150000000 | 150000000 | 150000000 | 0 | 0 | 0 | 44931 | 0 | 0 | CFC production for non-essential uses stopped by July 2007 but there was still demand for CFCs for non-MDI pharmaceutical products and for the refrigeration servicing sector. The supply for those applications are from the national stock of CFCs that is managed by FECO and maybe some stocks held by dealers and former producers. Only qualified users can buy CFC from the national stock and stock of former producers - and only through the CFC procurement licensing system. Cost related to management and monitoring of CFC sales are covered by remaining funds of the sector plan. Some TA activities are still ongoing to ensure long term sustainability.
IBRD | India | CFC production sector gradual phase-out project |  | 1999-11-01 | 2011-11-01 | 2011-12-01 | 82000000 | 82000000 | 82000000 | 0 | 0 | 0 | 22588 | 0 | 0 | CFC production sector plan is now completed physically and financially.
UNIDO | Mexico | Sector plan for phasing out CFC-11 and CFC-12 production sector |  | 2003-07-01 | 2009-12-01 |  | 31850000 | 31850000 | 31849298 |  |  |  | 12355 | 0 | 0 | The project was successfully completed.
IBRD | Venezuela | Phased reduction and closure of the entire CFC production |  | 2004-12-02 | 2009-11-01 | 2009-09-01 | 16500000 | 16500000 | 16500000 | 0 | 0 | 0 | 4400 | 0 | 0 | Project completed.
UNIDO | China | Sector plan for methyl bromide production sector |  | 2005-11-01 |  | 2015-12-01 | 9790000 | 8000000 | 4333803 |  |  |  | 621 | 150 | 150 | 2012 methyl bromide production target met as planned, contracts for 2013 signed and funds disbursed accordingly. Carried out awareness activities in cooperation with the Ministry of Agriculture for controlled uses of methyl bromide. | Formulate and sign contracts for 2014 production targets, finalize final report for Phase III and formulate funds disbursement request for Phase IV. Carry out awareness activities in cooperation with AQSIQ for QPS uses of methyl bromide and with MOA for controlled uses of methyl bromide.
UNIDO | Korea, DPR | Closure of ODS production plant |  | 2002-03-01 | 2006-12-01 |  | 2566800 | 2566800 | 2566800 |  |  |  | 4280 | 0 | 0 | The project was successfully completed.
UNIDO | Romania | Sector plan for production sector |  | 2005-11-01 | 2010-12-01 |  | 6300000 | 6300000 | 6258378 |  |  |  | 175 | 0 | 0 | The project was successfully completed.
IBRD | China | TCA Sector |  | 2004-07-01 | 2010-11-01 | 2010-11-01 | 2100000 | 2100000 | 2100000 | 0 | 0 | 0 | 113 | 0 | 0 | TCA sector plan completed.
UNIDO | Algeria | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector |  | 2002-07-01 | 2007-11-01 |  | 1424647 | 1424647 | 1412104 | 245 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Pakistan | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) |  | 2003-12-01 | 2008-09-01 |  | 1139500 | 1139500 | 1134942 | 215 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | China | Refrigeration servicing sector CFC phase-out plan |  | 2004-12-01 | 2013-04-01 |  | 3435000 | 3435000 | 3308594 | 3391 | 0 | 0 |  |  |  | The report of the survey carried out in Shenzhen has been submitted to UNIDO on 20th September 2012 and is now under evaluation. The Technical Specification for equipment procurement has been finalized on 13th September 2012 and FECO is now carrying out the procurement. Procurement completed. | PCR to will be prepared in 2Q 2013. Project completed in Apr 2013.
Japan | China | Refrigeration Servicing |  | 2004-12-01 | 2012-12-01 |  | 4000000 | 4000000 | 4106335 | 511 | 3790 | n.a | 0
UNEP | China | Refrigeration Servicing |  | 2005-04-01 | 2010-12-01 |  | 450000 | 450000 | 436616 | 0 | 8672.8 | Not available | 0 |  |  | Project completed in December 2010.
UNDP | China | Solvent |  | 2000-03-01 | 2012-12-01 |  | 52000000 | 52000000 | 51999999.6 | 4031 | 0 | N.A. | N.A. | N.A. | N.A. | Completed in 2012. | Completed in 2012.
UNIDO | Nigeria | Terminal ODS phase out umbrella project in the solvent sector |  | 2004-07-01 | 2012-11-01 |  | 1575200 | 1575200 | 1560813 | 198 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | China | Tobacco Sector Plan |  | 2000-12-01 | 2007-12-01 |  | 11000000 | 11000000 | 11000000 | 1090 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Macedonia, FYR | HCFC phase-out management plan (phase I) |  | 2010-04-01 |  | 2020-12-01 | 1166955 | 416955 | 135640 | 2.18 | 0 | 0 |  |  |  | The project was approved at the 67th Meeting of the Executive Committee in 2012. A joint UNIDO/NOU team visited the country. Local consultants were recruited. The technical specifications and the scope of supply of R&R equipment were prepared and coordinated with the NOU. The international bidding was initiated. | Evaluation of bids received and placement of the purchase order. The project is expected to be completed in 2013.
UNDP | Maldives | HCFC Phase Out Plan (Stage I) |  | 2010-04-01 |  | 2014-12-01 | 420000 | 420000 | 0 | 1.41 | 3.7 | N.A. | N.A. | N.A. | N.A. | During the year 2012, consultations were held with Ministry of Fisheries and Agriculture (MoFA) on retrofit incentive scheme implementation for consumers in fisheries industry. The modalities of implementation were finalised in Q2 of 2012 and the final agreement was signed October 2012. Technical consultant is to be engaged by early 2013 for redesigning and undertaking retrofitting of HCFC based equipment. Consultations are underway for adopting not-in-kind options for converting residential air-conditioning industry (e.g., district cooling). | The recruitment of technical expert for retrofitting is in progress. The implementation plan is closely being monitored.
UNEP | Maldives | HCFC Phase Out Plan (Stage I) |  | 2010-04-01 |  | 2019-12-01 | 680000 | 529340 | 183738 | 2.29 |  |  | 0 |  |  | The list of planned activities for 2012: - HCFCs phase-out Policies and Enforcement - Plan for Gradual Reduction of HCFC - Enhanced awareness and outreach. Progress: New models of refrigerant identifiers were procured and delivered on December 2012.Second tranche request submitted for 69th ExCom, Enforcement Training conducted in March 2012 and Media Workshop organized in February 2012. | UNEP purchased and distributed 10 units of RAC equipment in Feb 2013. Second tranche request submitted for 69th ExCom, Enforcement Training conducted in March, Media Workshop in February
UNIDO | Croatia | HCFC phase-out management plan (phase I) |  | 2010-07-01 |  | 2016-12-01 | 871150 | 811150 | 148866 | 6.4 | 6.6 | not yet available |  |  |  | The project was approved at the 66th Meeting of the Executive Committee. The PAD was issued and the government was informed on accelerated payment schedule of the tranches. Installation owners for potential conversion to low-GWP technology were approached in order to work out a workable financing scheme. A mission took place in December 2012 to meet with representatives of the National Environmental Protection and Energy Efficiency Fund on the financing of the conversion of HCFC-based installations. | Another mission took place in February to work out the contract details between the Environment Fund and UNIDO for the financing of the conversion/retrofit of selected HCFC installations. All elements were agreed upon afterwards and the contract is expected to be signed in May 2013.
UNDP | Ghana | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  | 2020-12-01 | 1031311 | 400000 | 199836 | 19.97 | N.A. | N.A. | N.A. | N.A. | N.A. | Tranche 2 was approved at the July 2012 ExCom and activities have progressed well throughout the year. Following approval, project document has been amended and DOA issued to allow HPMP activities to continue. | Work plan approved for 2013 and implementation initiated. Technical workshops are being visited to check for safety processes and identifying lead workshops for the conversion scheme.
UNDP | Cambodia | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  | 2020-12-20 | 650000 | 200000 | 100000 | 5.61 | N.A. | N.A. | N.A. | N.A. | N.A. | The LOA was signed in January 2012. Activities under HPMP are progressing satisfactorily. R&R equipment procurment has commenced in August 2012. Retrofit activities are planned beginning HY1 of 2013. | Project implementation is progressing satisfactorily. Equipment distribution would be complete by Q2 of 2013.
Italy | Croatia | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  | 2013-09-01 | 210000 | 210000 | 163507 | 1.7 |  |  | 0 |  |  | Foaming equipment was installed end January 2012. Additional accessories required for the operation were purchased in the first half of 2012, but installation delayed until early 2013. Contract for the payment of incremental operating cost was signed in March 2013 and payment will be released upon presentation of invoices. Destruction of replaced equipment and finalization of the project is planned for the third quarter 2013. The company is already using water based formulation and there is no more use of HCFC-141b.
Italy | Argentina | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  | 2013-12-01 | 300000 | 300000 | 8340 | 0 | 0 | 0 | 0 |  |  | Despite the supplier's delay (Agramkow) in the release of equipment, it was delivered to Buenos Aires. The equipment customs clearance was completed and it was transferred from the customs to the warehouses of the local forwarders for further in-land transportation to the end-users. Activities in 2013 are inspection of equipment upon its delivery to the project beneficiaries. Local procurement of small equipment items. Installation, testing, training and commissioning of equipment. Release of IOCs. | The low disbursement of funds provided to the project by Italian contribution is related to the fact that procurement of main equipment has been implemented with the use of financial resources allocated to the project by the MLF.
Italy | Ghana | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  |  | 325000 | 130000 |  | 6.2948 |  |  | 0
UNEP | Cambodia | HCFC Phase Out Plan (Stage I) |  | 2010-07-01 |  | 2013-06-01 | 950000 | 150000 | 126974 | 8.19 |  |  | 0 |  |  | The list of planned activities for 2012: - Training of enforcement officers - Training of RAC technician on good practice - Information, education, and communication - Project Management & Monitoring. Progress: UNEP six units of identifiers purchased and distributed to Cambodia in Dec 2012. The train-the-trainer workshop was organized for enforcement officers in August 2012, and followed with one training workshop for enforcement officers during 24-25 December 2012 at Sihanoukville. The train-the-trainer workshop was organized for refrigeration technicians during 2-5 October 2012, followed with a technician training workshop during 26-27 December 2012 at Sihanoukville. | UNEP purchased and distributed 3 units of RAC equipment to Cambodia in Feb 2013. A training workshop to enforcement officers was organized during 21-22 February 2013 at Bavet, Svai Rieng Province, and one training workshop to technicians was organized during 29-30 January 2013 in Phnom Penh.
UNIDO | Chad | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 260000 | 135000 | 53 | 3.9 | N/A | not yet available |  |  |  | The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. | The equipment is being shipped.
UNIDO | Gabon | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 249900 | 130000 | 53 | 4.8 | N/A | not yet available |  |  |  | The technical specifications were prepared, the call for bids for supply of equipment was issued. Offers were received and evaluated and the purchase order was issued. | A new NOU has been set up. Contacts have been made to discuss activities with the new focal point. Reason for the extended project duration: The NOU was not operational for a certain period of time.
UNIDO | Pakistan | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2015-12-01 | 5008849 | 4908849 | 2663591 | 73.74 | N/A | not yet available |  |  |  | UNIDO investment component completed. Monitoring, data collection and reporting is being finalized. Report and request for 2013 Tranche was submitted to 69th Executive Committee Meeting, however on the request of the Secretariat the submission is shifted to the 70th Meeting. | Project completed in Mar 2013. The request for the next tranche will be submitted to the 70th Meeting.
UNIDO | Philipinnes | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2014-06-01 | 1770650 | 1770650 | 229299.37 | 40 | N/A | not yet available |  |  |  | Contracts were signed in 2012. One existing spray machine (Graco/Gusmer H-20/35) was converted on a pilot basis. Test on other available or H22 technologies (i.e. water blown, Methyl Formate, HFOs) took place in the course of 2012 at no cost for the project. Results are under evaluation in order to select the most adequate technology for the conditions in the Philippines. | Finalization of conversion of fixed foaming equipment is planned for the first half of 2013. Stakeholders consultation meeting to take place to discuss the outcomes of the tests on spray foam applications and selection of appropriate technology.
UNIDO | Madagascar | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 260000 | 140000 | 94075 | 2.8 | N/A | not yet available |  |  |  | TOR for equipment was finalized with NOU, contract was issued to supplier and equipment was delivered in April 2012. Train the trainers session held 14 - 17 January : 16 participants from 8 regions of Madagascar (two from each region). Training conducted by local consultant. | Wider dissemination of training will be carried out to enable technicians to perform retrofits succesfully in preparation for the retrofit incentive scheme (with l'Union des Frigoriste de Madagascar) in the following tranche and also on a workshop for technicians in the fishing industry. Equipment to be distributed to servicing centers in the 8 regions. The project is expected to be completed in 2013.
UNIDO | Togo | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 350000 | 200000 | 120733 | 3.9 | N/A | not yet available |  |  |  | Contract was issued to supplier and equipment was delivered in May 2012. Training on the use of equipment, general refrigeration practices, recycling and reclamation by supplier took place in Lome in September 2012. | Remaining funds are being spent on wider dissemination of training to enable technicians to successfully carry out retrofits in preparation for the retrofit incentive scheme planned for the following tranches. The project is expected to be completed in 2013.
UNIDO | Malawi | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 120000 | 60000 | 58425 | 1.1 | N/A | not yet available |  |  |  | TOR was finalized with NOU. After international bidding process, contract was issued to supplier. Equipment was delivered in April 2012. Training by supplier took place in Lilongwe in July 2012. The second training session took place 3 - 6 December 2012 in Lilongwe. 22 participants attended. Two training sessions similar, included retrofits of actual A/Cs. | The request for the second tranche report is planned to be submitted to the 69th Meeting of the Executive Committee. The project is expected to be completed in 2013. UNEP is the lead agency.
UNIDO | Nigeria | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2015-12-01 | 1939080 | 1100000 | 48128 | 35.4 | N/A | not yet available |  |  |  | The project was approved at the 66th Meeting of the Executive Committee in 2012. The TOR on the procurement of low pressure foaming machines prepared and coordinated with the NOU. It was agreed to accommodate first the end users located in Ibadan (29 companies) and Abuja (24 companies). However, international bidding was delayed as it was found that none of the project beneficiaries had the power supply of 380 V, 3 phases, 50 Hz required to run the new foaming equipment. NOU was requested to obtain a written commitment by project beneficiaries to ensure the adequate power supply by the time of equipment delivery. | It is expected to obtain written commitment by project beneficiaries to ensure the adequate power supply. International bidding, evaluation of proposals received and placement of purchase order. The project is expected to be completed in 2013. Reason for the delay: Power suply at the beneficiaries was not appropriate for the new equipment.
UNIDO | Burkina Faso | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 249900 | 150000 | 104517 | 3.1 | N/A | not yet available |  |  |  | After TOR for servicing equipment was finalized with NOU, tender was raised. After evaluation of offers, contract was issued to supplier. Equipment was delivered to Ougadougou in June 2012. An agreement was reached with NOU to purchase further equipment for retrofit training with remaining funds. These were purchased through local suppliers in December 2012. Two out out three purchases were delivered. | One local supplier did not deliver so the rebidding process was initiated. The request for the second tranche report is planned to be submitted to the 69th Meeting of the Executive Committee. The project is expected to be completed in 2013. UNEP is the lead agency.
UNIDO | Turkmenistan | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 652050 | 309050 | 13166 | 2.6 | N/A | not yet available |  |  |  | Agreement with the Government signed. National staff for the NOU and international experts recruited. Stakeholder meeting conducted. | Equipment delivery is planned for the first quarter of 2013. Contract for the IS component is under preparation. Workshop is planned the first half of the year. The equipment for the training curses will be purchased locally. The trainers are under recruitment. UNIDO mission is planned for May 2013.
UNIDO | Serbia | HCFC phase-out management plan (phase I) |  | 2010-12-01 |  | 2020-12-01 | 915260 | 360130 | 119324 | 3.1 | N/A | not yet available |  |  |  | Non-investment activities in connection with legislation review were under implementation. Train the trainers component and trainers certification for refrigeration service technicians took place 29 October - 6 November 2012. Both mentioned activities were built up on the latest results of the NCPP technicians training of August 2012. Non-investment activities under UNEP lead have been intensively organized jointly with NOU. Under the investment component, conversion of ALFA KLIMA was finalized in September 2012 | Field mission will be organized 2nd quarter of 2013 to asses the possibility to convert one more enterprise before second tranche aproval (having in view that the HPMP investment funding is divided in 2 tranches, and 50% of the funds are subject to approval of the 71st Meeting of the Executive Committee).
UNDP | Armenia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2015-12-15 | 594353 | 562838 | 98791.19 | 2.09 | N.A. | N.A. | N.A. | N.A. | N.A. | 2nd tranche request was approved at the 66th ExCom, and this allowed to complete ITB for SAGA. | In March 2013, tender documentation was cleared by regional procurement panel (ACP), and Transfair (Germany) was selected for equipment delivery to SAGA. Equipment is expected to arrive within 6-7 months after the contract signature around September/October 2013.
UNDP | Belize | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2020-12-01 | 66500 | 60000 | 0 | 0.24 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc was signed in 2011. In 2012, workplans and specs for procurement of tools and equipment prepared. Procurement process had to be repeated several times because of limited interest from potential suppliers. | Bidding process is progressing.
UNDP | Colombia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2015-12-01 | 6721483 | 6571483 | 5557632 | 77 | N.A. | N.A. | N.A. | N.A. | N.A. | The second tranche request was prepared and approved by the ExCom in 2012. Substantial advances with training of technicians and introduction of new alternatives for flushing. New legislation was introduced for the Domestic Refrigeration Sector. Quota system in place and working adequately. | Domestic Refrieration project technically completed, all manufacturing companies has implemented HC as blowing agent, IOC were paid for all companies. Equipment for strenghtening the R&R network and for flushing activities are in process of being distributed.
UNDP | Nigeria | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2016-12-01 | 2999750 | 1692118 | 965225 | 54.725 | N.A. | N.A. | N.A. | N.A. | N.A. | DOA for 2nd tranche prepared in October 2012 and funds allocated. PU foam conversion started in 1st tranche at VitaPUR is ongoing, with local preparatory work under way (reorganization of the facility to accomodate new equipment). | Equipment shipped from South Africa expected shortly at Vitapur. Safety audit is expected at the Pamaque facility by April 2013, with mission of international consultant and MPU staff.
UNDP | Sri Lanka | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2022-12-01 | 398866 | 180000 | 40169.34 | 3.04 | N.A. | N.A. | N.A. | N.A. | N.A. | HPMP activities are in progress. During the year 2012, the Government consulted importers and national stakeholders on development of quota system. Quotas for the year 2013 were allocated in Q4 of 2012. Training program was conducted for service technicians focusing on stopping use of HCFC-141b in RAC equipment servicing. Agreement with Regnis which uses HCFC-141b preblended polyol for manufacturing foam for conversion to HC is at advanced stages of discussion and is expected to be concluded by Q1 of 2013. Discussions are underway with enterprises assembling air-conditioners for conversion to HCFC free technologies. Baseline data from these enterprises have been verified. | On 16 February 2013, the training on 141b cleaning agent was held for enabling cessation of HCFC-141b use in cleaning. Other activities under HPMP are underway. Second tranche request for HPMP is proposed to be submitted to the 70th meeting of the Executive Committee for their consideration.
Japan | Philipinnes | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2014-06-01 | 317350 | 317350 | 62147 | 0 |  |  | 0 |  |  | Contracts were signed in 2012 for the conversion of all ten eligible beneficiaries using 141-b for various applications using fixed-foam equipment. The cost for the purchased equipment and services amounted 1,458,105 USD, including transportation, installation and training. The conversion will generate a phase-out of 93.74 ODP t, for a calculated cost effectiveness of 15.6 USD/kg. - One existing spray machine (Graco/Gusmer H-20/35) was converted on a pilot basis. Cost of the conversion and upgrade of 1 pilot unit is not indicative for the calculation of ICC. Test on other available or H22 technologies (i.e. water blown, Methyl Formate, HFOs) took place in the course of 2012 at no cost for the project. Results are under evaluation in order to select the most adequate technology for the conditions in the Philippines. No information is available on overall ICC for the spray applications. - Finalization of conversion of fixed foaming equipment in the first half of 2013. Stakeholders consultation meeting to take place to discuss on the outcomes of the tests on spray foam applications and selection of appropriate technology for spray form conversion.
Japan | Saudi Arabia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2015-12-01 | 220000 | 220000 |  | 7.1 |  |  | 0 |  |  | Several consultations have been held with ACC; in particular on technology options. Due to ACC joint venture with DOW Chemicals this has been a lengthy process. Furthermore, ACC considers their production technology proprietary. Hence, it has been agreed that the MLF grant will focus on auxiliary equipment enabling usage of flammable blowing agent - and that the modifications related to the extruder will be handled by ACC as part of their co-financing. UNIDO has prepared the TOR for the equipment and is awaiting final approval from the beneficiary. UNIDO has also provided technical assistance to the beneficiary through our International expert. As a summary there were 1. Numerous discussions on technology issues. 2. Several visits by XPS expert. Activites in 2013 are 1. Final commitment on technology. 2. Advertisement of tender. 3. Contract award.
UNEP | Armenia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 39000 | 31515 | 26000 | 0.14 | 0.14 |  | 0 |  |  | The legislation system was updated and import quotas on HCFCs are introduced. NOU has completed the translation of UNEP’s Training Manual for refrigeration technicians (E book) into Armenian language. 25 Refrigeration technicians were trained on 23 October 2012. The first part of the training was combined with the investment component under HPMP and accompanied by the distribution of R&R sets (The second part of the training is planned for autumn 2013). A national certification system for refrigeration technicians and service providers is under development. A monitoring officer has been hired to closely monitor the timely implementation of HPMP’s non‐investment component and review its effectiveness. | Upon submission of the Draft Government Resolution on Monitoring and Control of Imported HCFC-based Equipment and Products it has been proposed by the Ministry to firstly draft the Resolution on Banning CFC-based old equipment. Drafting has been initiated. It has been agreed with the Customs Service to organise a combined (e-learning and auditorium classes) training. The training materials (Customs Manual in Armenian including) were prepared and submitted to the Customs Service. The training undergoes an internal approval at the Customs Service at the moment. A round table for importers and exporters was organised on 1 February 2013 to clarify the HCFC quota system.
UNEP | Burkina Faso | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 546168 | 120000 | 111430 | 6.655 |  |  | 0 |  |  | Refrigeration training equipment purchased and refrigeration training of trainers held in April 2012. Customs training was conducted for 30 Officers. Second payment was made in Nov 2012
UNEP | Belize | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2015-12-01 | 213500 | 80000 | 30000 | 0.79 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance by CAP Team. NOU began fund-raising in order to obtain additional funds for the HPMP implementation. Examinations for technicians certification were established in 2012 by National Refrigeration Association (ARACT). Customs Training Refreshing Workshop were held in Oct. 2012, 43 participants attended. To better address specific needs, training was done at 3 hierarchical levels of the Enforcement Officers, 60 participants attended. HCFC Quotas were determined through consultation process between NOU and importers. Two RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. | 4 training workshops for customs officials took place in Jan-Feb 2013. The Cabinet approved the policy directive and amendments to the Pollution Regulations of Belize which cover ozone layer depletion. Importers of ODS and RAC equipment have been sensitized. The HCFC quota system is in place as of 1 Jan 2013. The import/export of HCFC-based equipment has been added to the licensing system. Continuous training workshops for middle and front-line enforcement personnel during the first quarter 2013.
UNEP | Chad | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-06-01 | 370000 | 100000 | 95000 | 5.5794 |  |  | 0 |  |  | The final payment was made in Oct 2012. The country conducted several trainings of refrigeration technicians
UNEP | Colombia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2014-04-01 | 100000 | 100000 | 49216 | 1.91 |  |  | 0 |  |  | SSFA disbursements were carried out through UNDP Colombia. Progress Report and Annual Implementation Plan submitted to the 66 ExCom in order to request for the second tranche of funds. Five portable ODSs and blends identifiers purchased and delivered. Updated Custom Train of Trainers programme relaunched. Seven workshops were held to train Customs Officers and 167 participants attended. Seven workshops were held to train Refrigerant distributors and 72 participants attended. 2nd tranche SSFA signed in Dec. 2012. | HCFC quota system is in progress. Imports and production of HCFC-based domestic refrigerators have been banned.
UNEP | Dominica | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2014-12-01 | 164500 | 82250 |  | 0.08 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. HCFC Quotas were determined through consultation process between NOU and importers. Twelve Enforcement and Customs Officer participated in the ODSs control Training/Refreshing Workshop. Official mission carried out to encourage Government to adopt HCFC quotas and streamline projects implementation. | Special training for custom brokers in proper classification of ODS products and refrigerants conducted in Feb. 2013, 15 participants attended. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN.
UNEP | Gabon | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 290100 | 90000 | 0 | 5.5871 |  |  | 0 |  |  | The first payment was made in Jan 2012. The country conducted training workshop for 30 refrigeration technicians and 20 custom officers.
UNEP | Grenada | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 210000 | 105000 | 19221 | 0.3 |  |  | 0 |  |  | Annual plan agreed to and in alignment with the SSFA. HCFC Quota system approved. Import/Export licensing system electronic through a ASYCUDA World. 15 RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. Official mission conducted in November 2012 to support the workshop delivery. | 2013 annual work plan has been drafted. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN. HCFC quota system being implemented.
UNEP | Madagascar | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 300000 | 70000 | 51362 | 3.2143 |  |  | 0 |  |  | The second payment was made in July 2012. The NOU conducted training of 20 Custom and 30 Refrigeration technicians.
UNEP | Malawi | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 230000 | 60000 | 50000 | 2.0437 |  |  | 0 |  |  | NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tools and equipment under the HPMP programme. | NOU conducted training workshop for 30 refrigeration technicians
UNEP | Pakistan | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 440000 | 200000 | 102956 | 5.3553 |  |  | 0 |  |  | The agreement was signed on May 2011 and initial disbursement was made on June 2011. The list of planned activities for 2012: Policy & Enforcement Capacity-building - Training for Customs officers - Procurement of equipment National Project for Training Service Technicians - Training at the provincial levels - Production of material to promote standards/ Code of Good Practices (in Urdu only) Awareness - Stakeholder awareness workshops at the provincial level Progress: The training and a side meeting with senior management of the Pakistan Customs were held at Old Customs House in Karachi (where 70% of Customs Officers in the country are posted) on September 2012 wherein 60 officers participated at the opening and 35 officers were trained from Customs and other enforcement departments including: Directorate General of Training and Research(DGTR) Karachi, DGTR (Customs), DGTR Lahore, Customs Control Appraisement Karachi, HQ Frontier Corps KPK Peshawar, General of Intelligence & Investigation-FBR, Customs Control Hyderabad, Customs Control Gwadar, DGTR (Customs), Islamabad, MCC Appraisement Karachi, Karachi International Container Terminal, Model Customs Collectorate of Preventive of Karachi and the Ozone Cell of the Ministry of Climate Change. TTT & Technicians Training was organized on September 2012, the training has been conducted in Karachi with 29 trainers and 19 technicians. New models of refrigerant identifiers were procured and delivered on December 2012. Conducted Awareness Workshop for government of Punjab and industry in Lahore on February 2013; Ozone Cell participated in national annual HVACR Exhibition. | UNEP purchased and distributed 4 units of RAC equipment in Feb 2013. Conducted Awareness Workshop for government of Punjab and industry in Lahore on 13 February; Ozone Cell participated in national annual HVACR Exhibition
UNEP | Sri Lanka | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2014-12-01 | 249000 | 125000 | 56293 | 1.89 |  |  | 0 |  |  | The agreement was signed and initial disbursement was made on December 2011. The list of planned activities for 2012: Policy, Regulations & Enforcement - Customs Train-the-Trainers - Training Service Technicians - Development of technicians training curricula for RAC technicians. Awareness - Production of awareness materials. Progress: Training for the Sri Lanka Customs officers and other law enforcement authorities on WCO HS Codes 2012 was conducted on 29 - 30 March 2012 in Colombo. On 22 August 2012, the Cabinet of Ministers of the Government of Sri Lanka considered the Cabinet Paper No.12/1126/527/010-I and granted approval to control the import and export and production of virgin Hydrochlorofluorocarbons (HCFCs) and HCFC blends with effect from 1st of January 2013 and thereafter eventually phase out per HPMP. Import of used equipment working with HCFC is banned from 1 January 2013. Controller of Import & Export has issued circular on 2 November 2012. The Ministry of Environment is planning to ban import of HCFC-141 b from 1 January 2016, and equipment working with HCFC from 1 January 2018. Newspaper advertisements were published on 26th January 2012, requesting to submit proposals to develop training curricula. Ministry of Vocational Training & Skill development and National Apprentice & Industrial Training Authority would be supporting development of training curricula. A Steering Committee would be formed in 2013 for development of the curricula. The NOU will prepare a draft model curriculum by adding new material that is relevant to HCFC phaseout to be incorporated into the curricula used by Sri Lanka Technical Colleges and vocational Training Institutes. Train the Trainers workshop was organized by UNEP in March 2012 at Bangkok and two Master Trainers from Sri Lanka joined this workshop. These master trainers would continue to support the training activities for service technicians during HPMP implementation. A three day workshop was conducted in January/February 2012 in Anuradhapura District for Technical college students and staff and RAC Technicians on good refrigeration practices. For undertaking training activities, 3 Refrigerant Recovery equipment and Accessories were distributed to Technical College, Anuradapura, Technical College Batticaloa and Eastern Technical Institute, Batticaloa. A 3day workshop on ‘Good practices in Refrigeration’ was conducted from 21-23 February 2013 at College of Technology Jaffna. 85 Technicians in Jaffna peninsula (almost all the technicians currently employed) participated for this workshop. They highly praised with the opportunity that has been received after 30 years of civil war. NOU initiative to train technicians in destitute areas was highly commended by the Government Agent in Jaffna. A 2 day training program was conducted on 29- 30 March 2012 with the participation of nearly 70 enforcement officers from Sri Lanka Customs, Department of Import & Export Controller, Board of Investment and Ministry of Environment. One unit of HCFC identification equipment was distributed on 29 March 2012 to the Department of Sri Lanka Customs (Colombo Port). Two refrigerant identifiers procured by UNEP received in February 2013 will be distributed to Sri Lanka Customs to be utilized in newly opened Port in Hambantota and in Colombo International Airport. Awareness and information outreach activities on HPMP are being carried out on an ongoing basis. Given that 25th anniversary of signature of Montreal Protocol was celebrated in the year 2012, the Ozone Day was used as an important platform for creating awareness on ODS phase-out and specifically on HPMP project activities. In addition to this, leaflets on HPMP was produced in 3 official languages and distributed at the National Exhibition in February 2012. Dockets were also designed and distributed during the year 2012. To promote technology adoption, Sri Lankan industry participated in the technology conference held in July 2012 in Bangkok. | The remaining trainings to be organized for enforcement and servicing sector is being planned and prepared in details for implementation.
UNEP | Togo | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 280000 | 70000 | 61946 | 3.1111 |  |  | 0 |  |  | Country continue to enforce ODS regulations
UNEP | Serbia | HCFC Phase Out Plan (Stage I) |  | 2010-12-01 |  | 2013-12-01 | 75500 | 26000 | 7827 | 0.25147 |  |  | 0 |  |  | Organization of the exhibition booth and forum on energy efficiency, ozone and climate friendly modern refrigeration technologies to inform and raise awareness of HCFC alternatives and technology innovation in cooperation with the Serbian Ministry of Energy, Development and Environment protection and the Serbian Society on Heating, Refrigeration and Air- Conditioning held on 5-7 December of 2012. | The publication of the article and interview in the quarterly journal of Serbia's RAC association on the improvement of energy efficiency in the latest climate and ozone friendly refrigeration technologies (the first quarter of 2013).The concept note for National Training of Customs Officers and Environment Inspectors to control HCFCs consumption in Serbia has been developed. The training is planned to be organized in the third quarter of 2013.
UNIDO | Montenegro | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2020-12-01 | 450000 | 155000 | 79475 | 0.3 | N/A | not yet available |  |  |  | Training conducted in the fourth quarter of 2012 and equipment delivered. | Preparation of 2nd tranche submission. Continuations of the training programe. Recruitment of national staff. The project is expected to be completed in 2013.
UNIDO | Benin | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2020-12-01 | 260000 | 100000 | 5628 | 3.4 | N/A | not yet available |  |  |  | A mission to Benin was organized in the first week of April 2012, whereby the implementation strategy, implementation modalities and list of equipment to be purchased have been agreed upon. After this successful mission, TORs for the purchase of equipment and tools for the service workshops were prepared and agreed upon with the NOU. Bidding was completed in October, technical and financial evaluation was finished and agreed upon in November 2012 and the contract was issued in December 2012. | The supplier was supposed to deliver the equipment within 10 weeks after the issuance of the purchase order. However, based on a recent follow-up, shipping is only expected in April 2013. The second tranche will be submitted to the 70th ExCom Meeting.
UNIDO | Honduras | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2020-12-01 | 380000 | 100000 | 43963 | 4.2 | N/A | not yet available |  |  |  | The training program of technicians continued. The country is implementing a project to replace HCFC-22 for HC-290 in the air-conditioners, already more than 50 units have been converted. Refrigeration equipment sized by the custom were also converted to HC and delivered to schools and vocational centres. Some technicians visited Colombia in study tour to learn from the HC achievement in the country. | Training in cleaning refrigeration systems is planned in May 2013. International expert will train trainers and technicians during one week. Tools for the use with HC will be purchased.
UNIDO | Iran (Islamic Republic of) | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2015-12-01 | 2506277 | 2130000 | 20483 | 24.84 | N/A | not yet available |  |  |  | The project was approved at the 68th Meeting of the Executive Committee. The Government was informed. Workplan was developed. Integral skin manufacturer assessed (3 companies) and alternative technology agreed with counterpart, small users in the panel and domestic refrigeration sectors monitored. Conversion of the latest will be addressed in 2013 (4 companies). | Procurement and installation of equipment for integral skin sector (3 companies) and remaining panel and domestic refrigeration companies (4 companies).
UNIDO | Venezuela | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2015-12-01 | 1758500 | 1258193 | 277062 | 21.5 | N/A | not yet available |  |  |  | The project was approved in July 2012. Activities were implemented in parallel with the First tranche. Contract for implementing services were prepared for the NOU. Mission was carried out to the country for project monitoring. | Training of technicians and certification program will continue. TOR for refrigeration simulators working with HC will be made. A pilot project to convert a small hotel to HC (propane) will be implemented as pilot project.
UNIDO | Congo | HCFC phase-out management plan (phase I) |  | 2011-04-01 |  | 2020-12-01 | 175000 | 100000 | 0 | 1.8 | N/A | not yet available |  |  |  | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013).
UNDP | Bhutan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2027-12-01 | 188000 | 70000 | 0 | 0.12 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc for HPMP was finalised after detailed consultations with NOU on implementation priorities during the year 2012. The main reason for the delay was finalisation of consultations on priorities and plan for implementing project activities and subsequent, administrative approval of the same. The prodoc is expected to be signed in early 2013. | HPMP prodoc was signed in February 2013. First disbursementswas made by March 2013.
UNDP | Chile | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2017-01-01 | 1497966 | 465566 | 2892.8 | 18.45 | N.A. | N.A. | N.A. | N.A. | N.A. | Project Document was signed. TORs have been developed and published. Quota system has been implemented. | Contracts and Long Term Agreements have been signed with main experts (national and international). One workshop with supermarkets companies was held, discussion on project mechanism and alternatives were carried out.
UNDP | Congo, DR | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2017-12-01 | 240000 | 100000 | 29086 | 2.9305 | NA | N.A. | N.A. | N.A. | N.A. | The purchase of equipment was finalised and it arrived in Kinshasa in November 2012. The national HPMP consultant ensured the follow-up of activities throughout the year and public awareness was raised about the results of the first phase of the HPMP. | A mission by international consultant took place in February 2013 and on this occasion the equipment was handed over during a ceremony with the NOU. Activities to be undertaken under next tranche were agreed upon with NOU and National Consultant and will be submitted to 70th ExCom.
UNDP | Georgia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2020-12-01 | 500900 | 200000 | 0 | 2.33 | N.A. | N.A. | N.A. | N.A. | N.A. | The project document was signed between UNDP and the Ministry of Environment Protection. National consultants have been recruited for updating the Code of Practice and the Syllabus of Vocational Schools and for collection/processing of data on installations using ODS solvents. The first draft of the updated Code of Practice and the syllabus for vocational schools both are developed. First draft of the strategy and a list of needed ODS free dry cleaning equipment and potential suppliers prepared with help of national and international experts. | Selection of the legal expert for Introduction of licensing and quota system for HCFCs is completed. Update of the software for Customs officers to monitor HCFC import-export is nearing completion.
UNDP | Guyana | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2017-01-01 | 48000 | 48000 | 1781.78 | 0.072727 | N.A. | N.A. | N.A. | N.A. | N.A. | UNDP project document was signed. Technical specs prepared. | Technical specs have been published. Bidding in progress
UNDP | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2017-12-01 | 4565746 | 3612000 | 662361.63 | 45.26 | N.A. | N.A. | N.A. | N.A. | N.A. | In January 2012, project document between Government and UNDP was signed. Interagency meeting on project implemenation progress was held in January 2012. PMU was established under NOU in the beginning of the year 2012 and the unit is working with lead and cooperating agencies on project implementation monitoring and support. Second tranche under HPMP of Iran was approved in November 2012. | Implementation of activities are progressing in a satisfactory manner. Currently, third tranche for HPMP of Iran is under preparation for submission to the 70th meeting of the Executive Committee.
UNDP | Kyrgyzstan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-12-14 | 52800 | 47520 | 19981.4 | 0.26 | N.A. | N.A. | N.A. | N.A. | N.A. | National expert continued providing technical support on a part-time basis. Three (3) workshops on HCFC alternatives were held in April and October 2012 (75 participants). | Workplan for 2013 formulated and endorsed by NOU. Funds for 2013 plan allocated. Discussions on development of R/R tools' specifications are currently ongoing with intentions to procure tools through a local supplier.
UNDP | Mali | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2022-12-01 | 280000 | 160000 | 126746 | 2.6 | NA | N.A. | N.A. | N.A. | N.A. | Equipment specifications and RFQ were issued and equipment purchased. Delivery of equipment (lot #1) completed in 2012. Activities progressed smoothly with support from international and national consultants. The scheme of subsidees for end-users progressed as approved, in spite of the difficult political situation in the country throughout the year. | Delivery of equipment (lot #2) in expected Q2 2013. Work plan approved for 2013. Mission by international consultant is planned once all equipment is received and security situation allows for it.
UNDP | Moldova | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-12-14 | 88000 | 79200 | 14616 | 0.23 | N.A. | N.A. | N.A. | N.A. | N.A. | Two (2) awareness raising workshops organized by NOU and Refrigeration Association in 2012. Three (3) multi-gas identifiers procured for Customs. NOU updated lists of servicing companies (and total number of technicians) and developed EU harmonized framework for new certification system and ODS use reporting system (supported by workshop). Twenty (20) sets of tools procured. Website for Refrigeration association created. Information materials prepared, printed and distributed. | Workplan for 2013 reviewed and approved with the Government. Funds for 2013 allocated.
UNDP | Paraguay | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2022-01-01 | 300000 | 168500 | 36002.51 | 2.99 | N.A. | N.A. | N.A. | N.A. | N.A. | Team of local experts were hired for the project implementation. The quota system has been established and agreed with stakeholders. Training of technicians took place. International expert made trained trainers on the use of HC. | Changes in government in the end of 2012 and upcoming elections in April has made it very difficult to implement activities in the beginning of 2013. TOR for the establishment of a R&R center had been prepared.
UNDP | Swaziland | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2014-12-01 | 667948 | 667948 | 581642.6 | 6.29 | N.A. | N.A. | N.A. | N.A. | N.A. | The project is on-track with its planned completion date. The equipment was received in 2012 and has started being installed at the Palfridge facility. However, full testing of equipment and training was not possible yet as of end of 2012 corresponded with high workload for factory, and will take place in 2013. | Local works progressed including exhaust, ventilation, enclosures, pipelines and safety equipment. International consultant will have a one-day visit in April on the occasion of another project mission in South Africa. The final safety audit visit and training by international expert is planned by July 2013.
UNDP | Timor-Leste | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2017-12-01 | 106800 | 96120 | 30000 | 0.02 | N.A. | N.A. | N.A. | N.A. | N.A. | The Letter of Agreement was signed in April 2012. The implementation plan finalized and agreed. The first disbursement was made in Oct 2012. Technical specifications of equipment for R&R were finalised. | Procurement process is underway. The procurement committeee are being established and wil review the documents for Procurement of R&R equipment. Equipment procurement is expected tobe completed by end of Q3 of 2013.
Germany | Afghanistan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 20 | 280276 | 85000 | 4500 | 3.3843 | 3.4 | 3.4 | 0 |  |  | Project Delay - Accessability of project site - HCFC survey completed - Local institutions identified - All technical input completed - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Experts recruited
Germany | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 15 | 2885815 | 2597233 | 166562 | 28.6045 | 28.6 | 28.6 | 0 |  |  | Project Delay - Procurement was delayed by bidders - HCFC survey completed - Stakeholders workshop held - Local institutions identified - Experts recruited - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | All technical input completed
Germany | Liberia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 20 | 315000 | 157500 | 63874 | 1.93 | 6 |  | 0 |  |  | Trainings of technicians have been completed. Customs trainings have also been done in remote border posts. In 2011 there was a reduction in consumption of HCFC by 0.09 ODP tons. | currently the NOU is concentrating on the awarenss strategy in order to ensure compliance with the reduction target of 2013.
Germany | Mauritius | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 25 | 1000000 | 157050 | 76917 | 10.2 | 10.6 |  | 0 |  |  | Trainings on alternative refrigerants like ammonia for trainers and hydrocarbon for technicians have been conducted. | Emphasis is currently on setting up a demo unit for training on CO2 systems for supermarkets.
Germany | Namibia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 20 | 900000 | 300000 | 95037 | 6.14 | 6.48 |  | 0 |  |  | HCFC equipment ban finally came into force in Aug 2012. Delayed implementation of controls has led to high imports of HCFCs because of industry being aware of impending restrictions. Lack of a NOU in Namibia has been a problem with only an assistant NOU not having the authority to be able to push forward activities. However customs officers have been trained and controls are in place. 4 Technician trainings have also been conducted. | Enforcement of controls is the main focus in early 2013 because of the controls.
Germany | Papua New Guinea | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 25 | 1250000 | 350000 | 61016 | 3.4 | 3.586 |  | 0 |  |  | PNG implementation faced delays due to lack of NOU and national elections. However customs trainings were conducted to ensure that controls were being enforced. | Customs trainings are still cruical in the early part of 2013 to ensure compliance. Additionally trainings on HC as alternatives is being planned.
Germany | Seychelles | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | Dec 20 | 600000 | 200000 | 88043 | 1.38 | 1.3173 |  | 0 |  |  | Seychelles has already phased out 0.4 ODP tons through its controls. Trainings have been conducted for customs officers and techncians have been trained on safe conversions of R22 systems to HCs. | Ongoing monitoring of imports as well as discussions on choosing a suitable solar AC demo technology is ongoing.
Japan | Mongolia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2020-12-01 | 130000 | 130000 | 130000 | 0.16 |  |  | 0 |  |  |  | MOU signed with XPS compaines in 2012.
France | Lao, DPR | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-06-01 | 33750 | 0 |  | 0.1 |  |  | 0 |  |  | See condition of disbursement.
UNEP | Afghanistan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2014-06-01 | 398825 | 120000 | 69254 | 4.82 |  |  | 0 |  |  | The list of planned activities for 2012: HCFC Phase-out Policies and Enforcement - Stakeholder consultations for finalising draft quota system and strengthening licensing system - Train the Trainer workshop - Procurement of equipment. Capability Certification System and Good Practice Program for the Servicing Technicians - Train the Trainers workshop. Enhanced communication and outreach - Organizing technical workshop-to raise awareness on HCFC phase-out and energy efficiency - Media Campaign for Customs/enforcement, servicing sector, and energy efficiency Progress: The HPMP project was launched in January 2012. One workshop was organized in March 2012 for customs officer wherein 49 officers from 13 customs provinces participated. Awareness activities were implemented with developed ODS identification tool for customs officers, ozone story book, customs training manual, ozone regulation booklet, HPMP brochures. HPMP qouta system was establised in April 2012. Additional workshop was organized in May 2012 for customs officer wherein 50 officers from 13 customs provinces participated. And, in June 2012, additional workshop was organized for customs officer wherein 54 officers from 13 customs provinces participated. ToT was organized in 29 May - 1 June 2012 for refrigeration technicians wherein 25 participated. One day survey of HCFC gas was carried out in Kabul city on 14 July 2012 wherein 25 workshops were surveyed.Lastly, new models of refrigerant identifiers were procured and delivered on December 2012. | The remaining training for enforcement and servicing sector is being planned under tranche one of HPMP Implementation and prepared in details for implementation for 2013.
UNEP | Region: PIC | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-03-01 | 285000 | 134000 | 125000 | 0 |  |  | 0 |  |  | The list of planned activities for 2012: - Joint meeting of ozone and customs officers meeting - iPIC - Training manual and awareness material Progress: Customs Enforcement Training completed in 6 of the Pacific Islands Countries. The training assisted participating countries for instances on the monitoring, controlling and reporting of the Trade in ODS and ODS containing technologies and with particular attention to HCFC controls. Also included in this training was HS 2012 version, reducing risk of illegal trade and review of legislative framework to be consistent with WCO and use of the new model refrigerant identifiers. Completion of the procurement of Equipment for the RAC servicing sector and for all 12 countries. Agreement was met for countries for the approach to national training and in scheduling. | Customs enforcement training in Tuvalu. Agreement for the delivery of training on Micronesia (April 21-24) 2013. Receipt of equipment for the training in the RAC sector.
UNEP | Benin | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 370000 | 85000 | 56314 | 4.8452 |  |  | 0 |  |  | The NOU conducted training activities for Custom Officer and progressing well with implementation of HPMP activities
UNEP | Bhutan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-11-01 | 282000 | 100000 | 35934 | 0.18 |  |  | 0 |  |  | The agreement was signed and initial disbursement of funds made in May 2012. The list of planned activities for 2012: HCFC Phase-out Policy and Enforcement - Procurement of equipment - Train-the-trainers workshops for enforcement officers, Information Exchange and Advocacy programmes - Design information exchange and advocacy programme - Research and Analyses. Servicing technician training and certification programme - Organization of train-the-trainer workshop of technicians - Production of training documents and materials. Progress: 3 Customs/Enforcement officers training programme was organized. ToT was organized for RAC sector. Stakeholders’ Workshop was organized. Public service announcement and poster have been completed since project approval. Developed training curriculum for vocational training schools and certification system for RAC technicians. New models of refrigerant identifiers were procured on December 2012. | UNEP purchased and distributed 3 units of RAC equipment in Feb 2013. UNEP is following up preparation for 2nd tranche request for 70th ExCom.
UNEP | Chile | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 288489 | 153217 |  | 3.55 |  |  | 0 |  |  | Consultations were concluded and final draft legislation was presented to main institutional stakeholders before submission to interministerial commission for approval. 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. Terms of reference were drafted by NOU for the implementation of the control system that will support enforcement of new legislation. In spite of some progress achieved, total disbursement rate was less than 20%. Consequently, 2nd tranche was not submitted in 2012. | HCFC quota system approved. SSFA has been cleared by Government and UNEP, pending signature.
UNEP | Cook Islands | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 99000 | 49250 | 18875 | 0.0231 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: The country organized customs training programme on 29 November – 1 December 2011 participated by 17 officers. Refrigerant identifiers provided. The procurement of equipment for the RAC servicing was done in December 2012 and training planned for August of 2013. Country has established ODS licensing and quota systems wherein it is functioning well. | The remaining training for enforcement and servicing sector is being planned and prepared in details for implementation.
UNEP | Congo, DR | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 235000 | 95000 | 85478 | 2.87 |  |  | 0 |  |  | The NOU organized one training for 40 refrigeration technicians on good refrigeration practices.
UNEP | Micronesia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 112000 | 53875 | 26068 | 0.04455 |  |  | 0 |  |  | The agreement was signed in April 2012 and initial disbursement was made in May 2012: The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training Progress: Due to changes in the NOO, required processing at national level took some time. This resulting in delays in the documentation preparation processes. The agreement was signed in April 2012 and initial disbursement was made on May 2012. Equipment was procured in December 2012. Training programme for Customs officers was organized in April 2013. | Shipment of the RAC training equipment processed. Customs training to be delivered April 21-24, 2013
UNEP | Guyana | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 18000 | 11000 | 0 | 0.027273 |  |  | 0 |  |  | New NOO joined the Ministry of Agriculture in February 2012. Implementation plan revised and approved by the government. A consultant from Trinidad & Tobago was hired to review curriculum of vocational training schools. HCFC Quota system approved. | 2013 annual work plan has been drafted. Consultant conducted country mission in Feb. 2013 to meet vocational schools and main stakeholders. HCFC quota system being implemented.
UNEP | Honduras | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2014-03-01 | 250000 | 75000 | 38355 | 2.77 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. HCFC quota system approved. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. 2 NOU officials attended Central America and Dominican Republic Training Workshop for National Ozone Units and Customs Authorities held in Nicaragua in December 2012. | 2013 annual work plan has been drafted. HCFC quota system being implemented.
UNEP | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 262000 | 262000 | 3293 | 2.597 |  |  | 0 |  |  | The agreement has been signed on April 2013 and initial disbursement has been transferred. The list of planned activities for 2012: Training programme for servicing technicians and Customs officers - Organizing training of trainers(TOT) workshops for servicing technicians - Organizing TOT workshops for Customs officers Information Exchange and Advocacy Programmes - Conducting research and analysis to improve info exchange. Progress: A three days training workshop on Good Practices in Refrigeration & Air-conditioning Servicing Sector for trainers was conducted by UNEP in close consultation and cooperation with the National Ozone Unit and GIZ from 18th to 20th February 2013 in Karadj Instructor Training Centre & Technical and Vocational Researches .Trainers of provincial vocational training centers (34 trainers from twenty provinces of the country) attended in this programme. NOU will use the capacity of trained master trainers of the provincial vocational training centers to organize similar training programs in near future for the other technicians which will help the country in reducing the consumption of HCFCs in the servicing sector. | The remaining training for enabling component are being planned and prepared in details for implementation.
UNEP | Kiribati | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 109000 | 53250 | 35250 | 0.0275 |  |  | 0 |  |  | The agreement was signed in September 2011 and initial disbursement was made on October 2011. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training HCFC import quota system and allocation of quota for 2013 established and functioning well. New model of refrigerant identifier were procured and delivered on December 2012. Organized customs training programme on 23-25Jan 2013 participated by 19 officers, partnered with OCO. The technicians training is being planned and will be organized by middle of the year. | Shipment of the RAC training equipment processed. Customs enforcement training delivered in January 23-25 2013 and participated by 19 officers. This training provided the skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012.
UNEP | Kyrgyzstan | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2014-12-01 | 35200 | 31680 | 30000 | 0.18 |  |  | 0 |  |  | The licensing and quota system to control HCFCs is operational. There were held nine training workshops - one additional for customs officers (the northern and southern regions) and two for the specialists of the refrigeration sector. There were prepared new edition of the State Program on phase-out ozone-depleting substances in the Kyrgyz Republic for the period 2011-2025 years. The NOU continues developing the technical guide book for the certification of technicians in the refrigeration and air conditioning sectors. The dissemination of logbooks was initiated during the monitoring of servicing shops. | The regulatory act was developed to set a quota for HCFCs for the year of 2013. It should be approved by the Ministry of Economy and the State Agency on Environment Protection. The NOU participated in the working group on Customs Union. The NOU officially informed the Ministry of Economy and the Customs authorities about the specific issues in controlling ODSs. The new training materials for workshops in the refrigeration sector are under development based on new materials which are received during the network and thematic meetings.
UNEP | Lao, PDR | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-03-01 | 176250 | 113625 | 41062 | 0.52 |  |  | 0 |  |  | The agreement was signed and initial disbursement was made on May 2012. The list of planned activities for 2012: Policy review and amendments of regulations - Initial meeting with Working Group, Brainstorming workshops, Legal requirement finalization workshop. Training of enforcement officers - Procurement of equipment Training of RAC technician on good practice - Procurement of equipment - Organization of train-the-trainer workshop. Progress: All meetings were organized for policy review and amendments in 2012. Procured refrigerant identifiers and distributed in Dec 2012. The train-the-trainer workshop was organized for refrigeration technicians on 26-30 November 2012 wherein 29 trainees from five institutes attended this workshop. The train-the-trainer workshop for enforcement was organized during 14-16 January 2013 wherein 58 enforcement officers from five institutes attended this workshop. | The train-the-trainer workshop was organized for enforcement officers during 14-16 January 2013. 58 trainees from five institutes attended this workshop. UNEP purchased and distributed 3 units of RAC equipment to Lao PDR in Feb 2013.
UNEP | Marshall Islands | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 113000 | 54000 | 32546 | 0.077 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on November 2012 participated by 14 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012. New NOO appointed in September of 2012 was trained in the HPMP project implementation. | Shipment of the RAC training equipment processed. Agreement reached on the scheduling of the training of RAC servicing technicians.
UNEP | Mali | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 280000 | 65000 | 37830 | 2.6 |  |  | 0 |  |  | The country continued to enforce regulations for importation of ODS. The SSFA has since expired and was revised. | The SSFA was sent to FMO for payment
UNEP | Mongolia | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 236000 | 65000 | 50500 | 0.3 |  |  | 0 |  |  | The agreement was signed in August 2011 and initial disbursement was made on October 2011. The list of planned activities for 2012: Strengthening of HCFC control policies/regulations - Introduction licensing/certification system for refrigeration/air conditioning technicians - National stakeholders consultation meeting Capability building for enforcement and customs officers - Training for Customs officers(Train-The-Trainers). Progress: Enforced quota for HCFC since 2011 according to the Air law of Mongolia wherein amended in 2012. According to the Article 25.2 of the Amendment of Air law of Mongolia, quantities/quotas of HCFC and request of its alternatives, that contained equipment for ODS importing and refrigeration servicing companies was approved by Decree of Minister of Nature, Environment & Tourism for 2011 and 2012 respectively. • The proposed HCFCs were included in the amendment of the Government Resolution#95, 2007: ‘’List of the toxic and hazardous chemicals restricted and banned for using in Mongolia’’ which was approved by Government Resoultion#145, dated on 01 December 2012.Customs training was organized during 25-27 June 2012 at the Ulaanbaatar with 25 trained. 2 training workshops for customs officers by trained trainers were conducted at the customs points during July 2012 to December 2012. A National Training curriculum involving vocational schools for the technician training was developed in English and Mongolian. The curriculum was delivered to ‘’Master Potentials‘’ National training center for technician training established with inauguration ceremony on 14 February 2012. The National training center conducted 5 training workshops during June-December 2012 with 102 trained technicians. One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Quota for HCFC-22 in 2013 was approved by Ministerial Decree and distributed to the registered importers in 02 January 2013.
UNEP | Nauru | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 74000 | 45625 | 17625 | 0.0055 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: One unit of new model of refrigerant identifier were procured and delivered on December 2012.The training programme is being planned and expected to be organized by middle of 2013. | The RAC training is being planned to be organized.
UNEP | Niue | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 73000 | 45625 | 23625 | 0.00275 |  |  | 0 |  |  | The agreement was signed and initial disbursement was made on October 2011. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training Progress: The import/export licensing system of ODS to include HCFC has been put in place and endorsed by Niue’s Cabinet Ministers on 27 August 2010. A meeting with Customs Organisation, technicians and other relevant national stakeholders were organized to develop the quota system for HCFCs.New model of refrigerant identifier were procured and delivered on December 2012. The customs training programme is planned to be organized by July 2013. Refrigerant identifier received in January 2013. Training of technicians planned in August of 2013. International trainers for both the customs and technician trainer contracted. | Shipment of the RAC training equipment.
UNEP | Paraguay | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-12-01 | 330000 | 146500 | 50027.39 | 3.29 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Agreement documents coordinated amongst the Government, UNDP and UNEP. SSFA signed in March 2012. First disbursement in April 2012. HCFC Quota system approved. Electronic Import/Export licensing system through SOFIA online system. Five workshops on Good Practices were held in 2012, 101 refrigeration technicians attended. 214 RAC technicians took the certification exam and 147 were duly certified. | 2013 annual work plan has been drafted. HCFC quota system being implemented. ODS control and Montreal Protocol Refreshing Workshop was held in the first quarter of 2013, 37 Enforcement Officers participated.
UNEP | Congo | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 175000 | 45000 | 23595 | 1.775 |  |  | 0 |  |  | Survey for 2011 data was completed. The country organized training workshops for 35 refrigeration technicians and 30 custom officers
UNEP | Samoa | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 148500 | 76250 | 50632 | 0.0748 |  |  | 0 |  |  | The agreement was signed and initial disbursement was made on August 2012. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on December 2012 participated by 18 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. New NOO appointed in August of 2012, trained on the implementation of the HPMP project. New model of refrigerant identifier were procured and delivered on December 2012. Completion of the procurement of the RAC servicing training equipment | Shipment of the RAC training equipment.
UNEP | Solomon Islands | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 195000 | 110250 | 68739 | 0.6666 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on August 2012 participated by 26 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. Two unit of new model of refrigerant identifier were procured and delivered on December 2012. Completion of procurement of RAC Servicing training equipment. | Shipment of the RAC training equipment.
UNEP | Sao Tome & Principe | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 160000 | 44000 | 24009 | 0.05 |  |  | 0 |  |  | Country conducted training workshops for 40 refrigeration technicians and 30 custom officers
UNEP | Swaziland | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 210000 | 75000 | 45010 | 1.98 |  |  | 0 |  |  | NOU procured tool kits and distributed to the technicians and repair workshops. The country trained 40 customs officers and 70 refrigeration experts. NOU conducted inspection visits to some of the boarders to check on the compliance requirement of the National's ODS Regulation enforcement. | NOU conducted national train the trainer for 30 refrigeration technicians on the safety of hydrocarbons
UNEP | Timor-Leste | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-03-01 | 164900 | 148500 | 24000 | 0.03 |  |  | 0 |  |  | The list of planned activities for 2012: - Regulatory and Policy Measures and Technical Assistance for Improvement of HCFC Data Collection and Management Procedures - Strengthening the Capacity of Customs and Enforcement Officers at Both National and Regional Level - Technical assistance activities for the refrigeration and air conditioning sector - Project Management Unit and Annual Verification. Progress: The Decree Law on the Control of Export, Import and Use of Ozone Depleting Substances (Decree Law No. 36/2012) entered into effect on 14 August 2012, and controls trade and use of ODS including HCFCs through an import quota and licensing scheme. UNEP purchased and distributed 3 units of identifiers to Timor Leste in Dec 2012. Preparatory work has been carried out to establish the nation’s first training centre for Refrigeration and Air-conditioning (RAC) Servicing and retrofitting. The first training of trainers for 5 Customs brokers on the World Customs Organization Harmonized Commodity Description and Coding System (“HS code”) was conducted. This type of training is expected to increase use of correct HS codes and increase accuracy in monitoring of trade data as well. Another training on law enforcement to Customs officers will be held after the launching of the decree law, this issue has been discussed with General Directorate for the Customs. Timor Leste Ozone logo has been designed. Some 100 books of Decree Law has been produced and distributed to stockholders related. Some 500 copies of the brochure (A4 Size, Full Colour) on the history and information on the Montreal Protocol have been produced and disseminated to stakeholders including students. The first training of trainer for custom officers on ODS issue was conducted in 25- 27 of July 2012. | The NOU conducted door by door visiting of all of HCFC importers (8 Importers), and received all their application for import license by March 2013. The NOU participated a meeting in Suai District during 3-4 April to present the Decree Law to national stakeholders. The cooperation MOU with the Vocational Training Department has drafted and being consulted for the delivery of the good practices training.
UNEP | Tonga | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 127000 | 64750 | 35763 | 0.02585 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on July 2012 participated by 40 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Shipment of the RAC training equipment. Completion of second national Montreal Protocol customs training, additional 22 officers were trained.
UNEP | Palau | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 120000 | 62375 | 36402 | 0.0572 |  |  | 0 |  |  | The SSFA has been signed and initial payment disbursed. The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Refrigerant identifier provided. The country completed customs train the trainer on 1-3 November 2012 participated by 14 officers representing customs and other enforcement officers. The procurement of technician training equipment was finalized in December 2012 and is scheduled to reach country in May 2013. Training of the RAC servicing technician planned for July. Country has established ODS licensing and quota systems and functioning well. | Shipment of the RAC training equipment
UNEP | Tuvalu | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 92000 | 47875 | 38782 | 0.0308 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Agreement on the agenda and date of training on Customs Enforcement. Completion of the procurement of the RAC service equipment One unit of new model of refrigerant identifier were procured and delivered on December 2012. | Conducted capacity for customs and law enforcement officials on January 2013 participated by 23 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO and risk reduction for illegal trade. Shipment of the RAC Servicing training equipment.
UNEP | Vanuatu | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2015-02-01 | 148500 | 76250 | 51263 | 0.13035 |  |  | 0 |  |  | The list of planned activities for 2012: - Policy setting up and enforcement - Procurement of equipment - Technician training and customs training. Progress: Conducted capacity for customs and law enforcement officials on October 2012 participated by 8 officers by providing the necessary skills and knowledge on how to effectively monitor and control ODS in trade with particular emphasis on HCFC to ensure that PIC’s comply with their obligations to the Montreal Protocol. Assisted members for instances on the implementation of the HCS 2012 version, automation of the systems and processes, development of procedures/processes and review of legislative framework to be consistent with WCO. Two unit of new model of refrigerant identifier were procured and delivered on December 2012. Training of the NOO on the HPMP project implementation. Completion of the procurement process for the RAC Servicing training equipment. | Shipment of the RAC Servicing training equipment
UNEP | Venezuela | HCFC Phase Out Plan (Stage I) |  | 2011-04-01 |  | 2013-07-01 | 136000 | 97307 | 7465 | 1.66 |  |  | 0 |  |  | 2012 annual operating plan and procurement plans were prepared by the NOU with the guidance of the CAP Team. Progress Report and Annual Implementation Plan submitted to the 67 ExCom Meeting, in order to request the second tranche. ODS revised legislation was drafted and will be approved in 2013. 2nd tranche HPMP approved in July 2012. Funds programming within UNEP accounts prepared. ODS portable identifiers to be purchased. | 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training workshop including 5th Amendment of Customs codes has been planned for the current year.
IBRD | Vietnam | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) |  | 2011-04-02 |  | 2015-12-02 | 9763820 | 3054423 | 500000 | 140.1 | n/a | n/a | 0 | 0 | 0 | PMU was established in Aug. 12. Grant Agreement was signed in Nov 12. PMU was staffed and equipped in Dec 2012. First sub-grant with one of the 12 foam enterprises was signed Dec 12. Some TA activities were initiated. | HCFC import quota was issued for 2013. Project launch workshop is scheduled in May 2013. Most subgrants are expected to be signed by the end of Jun 2013. First disbursement of US$500,000 made in Jan 2013 to the country. $292,000 disbursed to beneficiaries and for activies by the country as of end May.
UNIDO | China | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2015-12-01 | 75000000 | 45630000 | 18214917 | 520 | N/A | not yet available |  |  |  | 1. Institutional setup between UNIDO, FECO and project beneficiaries in place. 2. First round of beneficiaries identified and verified by FECO. | 1. Beneficiaries procurement capacity assessed. 2. Contracts signed between FECO and beneficiaries. 3. Conversion at xx manufacturer of R-410 A/C. 4. Conversion at xx manufacturer of R-290 A/C. 5. Conversion at 3 R-290 compressor manufacturer.
UNIDO | China | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2015-12-01 | 48650000 | 31589000 | 9617317 | 592 | N/A | not yet available |  |  |  | A detailed work plan was submitted by FECO. After comprehensive evaluation it was approved in September 2012. In March 2012 XPS companies were invited to submit individual conversion plans. 12 proposals were received. In August and September an independent audit agency was selected and the consumption baseline was verified. 11 enterprises signed sub-contracts to start conversion (all companies selected CO2 technology). The procurement capacity of 4 equipment providers was assessed. The second round of conversion was started in December 2012 by requesting companies to submit proposals. The submission of the second tranche was prepared and submitted to the MLF. | Conversion of 11 companies that signed individual phase-out agreements is planned for 2013. Preparation and endorsement of the work plan for the second tranche as soon as approved. The consumption baseline of companies that are going to submit phase-out proposals will be verified and contracts signed. In the second half of 2013 the next call for individual sub-projects will follow together with the preparation of the third tranche of the project and consecutive submission to the MLF and request for approval.
UNIDO | Central African Republic | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 250000 | 125000 | 19001 | 1.875 | N/A | not yet available |  |  |  | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013).
UNIDO | Indonesia | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2018-12-01 | 777395 | 777395 | 10015 | 8.6053 | N/A | not yet available |  |  |  | Draft agreements on implementation procedures have been communicated with beneficiaries and agreed in principle. The draft TORs were prepared. However, implementation modalities according to new financial rules of the Government of Indonesia, has not yet been settled due to lengthy process of approval throughout different ministries and Government departments (Ministry of Finance, Ministry of Planning, Bappenas). Contracting was delayed due to above mentioned reason. Action taken to eliminate the delay: UNIDO field office intervened through Ministry of Environment (Official letter) to have the project registered for "direct implementation", in accordance to new financial rules of Indonesian government for the implementation of foreign technical assistance. | Purchase of equipment Reason for the delay: the implementation modalities according to new financial rules of the Government of Indonesia, has not been settled for a long period of time due to lengthy process of approval throughout different ministries and Government departments.
UNIDO | Zambia | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 140000 | 70000 | 0 | 0.75556 | N/A | not yet available |  |  |  | TORs for the equipment for training purposes for vocational training institution and refrigerant centers have been finalized. | Bidding for training equipment was done in January and the contract will be avarded as soon as possible. Training is planned for the second quarter of 2013. A mission is planned in June 2013.
UNIDO | Cameroon | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2017-12-01 | 1182725 | 884453 | 116951 | 25.4 | N/A | not yet available |  |  |  | Subcontract with counterpart to address policy component was signed last quarter of 2012 (the outcome will consist in legislation review, training and monitoring of the achieved HPMP progress. In September 2012 train the trainer component for customs officers and the first customs training workshop was completed. Additional customs training will further take place as an outcome of the mentioned subcontract). | Follow-up of the activities defined by the subcontract with counterpart will take place in 2013. Train the trainers component for technicians is scheduled for the first half of 2013.
UNIDO | Mexico | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2018-12-01 | 4412195 | 3487537 | 197194 | 101.33 | N/A | not yet available |  |  |  | The tranche was approved in December 2012. Subsequently, still in 2012, the PAD was issued. | A UNIDO mission was organized in March 2013 to finalize the agreement on the activities and the implementation plan. Final review of the new manual for technicians on good maintenance practices was finished in April 2013 and it will be shortly printed in at least 1,000 copies. This will be the basis for Stage I HPMP service sector training activities. Training of trainers (50-60) will be organized after May in 12 public training centers selected by SEMARNAT and the Ministry of Education. This will be followed by large-scale training activities. TOR for the equipment and tools required for the training have been agreed upon with SEMARNAT end March 2013. Bidding started in April 2013. In addition, 2 training coruses will be organized for customs trainers, one in Veracruz and one in Manzanillo around May/June 2013;
UNIDO | Rwanda | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 110000 | 55000 | 6711 | 0.55 | N/A | not yet available |  |  |  | A mission to Rwanda took place in October 2012. Implementation modalities were discussed with the NOU and recycling centers visited. Strategies for upgrading those centers were discussed and detailed TOR for equipment prepared. | Bidding will be conducted during the first half of 2013. The delivery of equipment and upgrade of the recycling centers will be coordinated with UNEP (in charge of the training activities under the HPMP) to ensure that the new equipment supports the training most effectively.
UNIDO | Saint Lucia | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 112608 | 99850 | 461 | 0.05 | N/A | not yet available |  |  |  | The project was approved at the 68th Meeting of the Executive Commitee in Decemeber 2012. The Government was informed. | Training of trainers and workshop on drop-in with HC is planned to be carried out in the country.
UNIDO | Guatemala | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 345637 | 216012 | 8729 | 3.3615 | N/A | not yet available |  |  |  | The tranche was approved at the 68th Meeting of the Executive Committee in December 2012. The Government was informed. | The project site was visited in February 2013. The first activities will be the purchase of tools required to complement those supplied for the vocational centres. The TOR is ready and it is expected to purchase the tools in May 2013. An international expect is scheduled in May 2013 to visit the country and train trainers in good refrigeration practices and drop in with HC. Some pilot projects for drop-in with HC will be carried out.
UNIDO | Albania | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2020-12-01 | 230000 | 45000 | 3755 | 1.5333 | N/A | not yet available |  |  |  | R&R and refrigeration tools/equipment were procured and delivered to the NOU for further dissemination among the end users. | Delivery of procured R&R and refrigeration tools/equipment to 4 designated service centers followed by training the trainers and subsequent training of service technicians.
UNIDO | Saint Vincent and the Grenadines | HCFC phase-out management plan (stage I) |  | 2011-07-01 |  | 2025-12-01 | 124115 | 124115 | 0 | 0.073954 | N/A | not yet available |  |  |  | TOR finalized with NOU.Contract was issued to supplier in December 2012. | Equipment was shipped and supposed to arrive in summer 2013.
UNDP | Brazil | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2017-07-01 | 15506257 | 7856257 | 24628.89 | 174.3124 | N.A. | N.A. | N.A. | N.A. | N.A. | UNDP project document was signed in 2012. 5 technical missions took place to visit participating companies in Brazil. Main focus in 2012 was on Continous Panels sector where contracts were signed with the companies and important progress was made. Agreements have been reached with 2 system houses and 2 individual companies about selection of technology and terms for contracts. Remaining system houses are individual projects are making in-house trials with new alternatives. | Second tranche incorporated in the Project Document allowing the expansion of activities. New contracts are being negotiated with beneficiary companies in order to make feasible the financial transference of funds under the second tranche.
UNDP | Costa Rica | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2022-07-01 | 1153523 | 761523 | 318751.27 | 17.6 | N.A. | N.A. | N.A. | N.A. | N.A. | Two expert missions took place in 2012. Equipment was delivered in October 2012, and is being installed at MABE. | Project has been installed and test with Cyclopentane was made.
UNDP | China | HCFC Phase Out Plan (Stage I) | Industrial, Commercial and Air Conditioning (ICR) | 2011-07-01 |  | 2017-07-01 | 61000000 | 32280000 | 25380000 | 764.95 | N.A. | N.A. | N.A. | N.A. | N.A. | The prodoc was finalized and signed in December 2011. Verification of baseline of participating beneficiaries in Stage-I was carried out by September 2012. Enterprise-level phase-out agreements finalized. Second disbursement was made in December 2012. Second tranche approved in December 2012. | Enterprise-level activities, including signing of remaining agreements and related monitoring proceeding as planned.
UNDP | China | HCFC Phase Out Plan (Stage I) | National Co-ordination | 2011-07-01 |  | 2013-07-01 | 360000 | 360000 | 120000 | 4.51 | N.A. | N.A. | N.A. | N.A. | N.A. | The overall HPMP launch workshop was held in December 2011. The prodoc was signed in December 2011. | Overall coordinaton in progress as planned.
UNDP | Indonesia | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2020-07-01 | 8953902 | 4052800 | 3156.29 | 98.53 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc signed in March 2012. Stakeholder consultations continued. | Enterprise-level phase-put agreements signed.
UNDP | Jamaica | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2022-07-01 | 578450 | 237450 | 4911.08 | 7.1484 | N.A. | N.A. | N.A. | N.A. | N.A. | Project document was signed. Seal Sprayed Inc. has concluded all trials with methyl formate and retrofit process of dispensers has been initiated. RAC local Expert was identified and hired. | Technical specifications of foaming dispensers are being concluded and procurement of parts will be undertaken in May 2013. International expert on RAC was hired, and in April 2013 a first mission will be undertaken to initiate the technical assistance activities for the RAC sector.
UNDP | Lebanon | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2019-07-01 | 2495109 | 1500000 | 889076.28 | 20 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc signed in Jan 2012. Enterprise-level phase-out agreement signed. Activities progressing as planned. | N/A
UNDP | Mexico | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2020-07-01 | 13654016 | 8731513 | 827132.16 | 315.97 | N.A. | N.A. | N.A. | N.A. | N.A. | Foam MABE reconversion process: 2 expert visits took place in 2012 to MABE. New system for Cyclopentane developed and tested internally in MABE and is now approved for new models. Technical specs approved and published for procurement of new equipment. For System Houses and End-Users: 6 international expert missions took place in 2012. All local system houses have selected technologies and made trials with new low GWP alternatives. Trials are currently being made at customers' level in most advanced system houses. | Foam MABE reconversion process: International tender undertaken and bids were recieved. They are currently being evaluated by UNDP before the purchase order is signed. Equipment is expected to be delivered by July. For System Houses and End-Users: Safety Audit completed at 3 system house. Three international expert mission took place in Feb/March to provide technical assistance to system houses.
UNDP | Saint Kitts and Nevis | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2022-07-01 | 40000 | 40000 | 0 | 0.04 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc has been prepared and submitted to the Govt and is awaiting the legal advisory of the Minister prior to signature. | ProDoc has not been signed yet but is expected to be signed shortly.
UNDP | Trinidad and Tobago | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2022-07-01 | 1462733 | 559900 | 911.77 | 17.9 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc signed. RAC National Expert hired and RAC International Expert in process of being contracted. | The government is negotiating Memorandum of Agreements with beneficiaries companies to allow funds transfers and initiate sampling with Methyl Formate. PU International Expert has being hired and is advising the government on this issue. TORs for the RAC international expert published and contracting process has progressed.
Australia | Indonesia | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2016-12-01 | 300000 | 300000 | 0 | 3.67 |  |  | 0 |  |  | There were delays in signing (due to govt. internal processes) the project document between UNDP and Government of Indonesia and also the agreement between Australia and UNDP. Eventually this documentation was signed in March 2012 and December 2012 respectively. The activities in the UNDP component were prioritized for 2012. The 2012 work plan for the Australian bilateral component was moved to 2013. | Agreement with UNDP, the executing agency was signed in Dcember 2012. Preparation of 2013 work plan, jointly with Indonesia and UNDP in progress. The main activites planned are: (a) Initiation and preparation for setting up of a national level refrigerant management organization, which include a workshop in August 2013 and stakeholder meetings (b) Govt tp govt interactions for policies and regulations related to sustainable refrigerant management, includes stakholder consultations and government liaison.
Germany | Bolivia | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | Dec-20 | 315000 | 94500 | 12614 | 1.7 | 1.7 | 1.7 | 0 |  |  | Project Delay - Change of NOU - HCFC survey completed - Stakeholders workshop held - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Local institutions identified
Germany | Brazil | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | Dec-15 | 4090909 | 3681818 | 264651 | 45.9876 | 46 | 46 | 0 |  |  | Project Delay - Signing of agreement - HCFC survey completed - Stakeholders workshop held - Local institutions identified - Draft document completed - Documents signed - TOR completed - First disbursement - Consumption target met - | Experts recruited
Germany | China | HCFC Phase Out Plan (Stage I) - XPS Foam |  | 2011-07-01 |  | Dec-15 | 1350000 | 459023 | 385346 | 16.9291 | 16.9 | 16.9 | 16.9 |  |  | HCFC survey completed - Stakeholders workshop held - Local institutions identified - Experts recruited - Draft document completed - Documents signed - TOR completed - All funds disbursed - | All technical input completed
Germany | Lesotho | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | Dec-20 | 280000 | 100000 | 43248 | 1.4 |  |  | 0 |  |  | Refrigerant identifiers suitable for blends have been supplied. A customs trainer from Namibia conducted a train the trainers course. This was followed by 3 additional courses covering 7 border posts of the country.
Japan | China | HCFC Phase Out Plan (Stage I) - Servicing Sector, including enabling |  | 2011-07-01 |  | 2015-12-01 | 400000 | 160000 |  | 5.016 |  |  | 0 |  |  |  | The implementation in this sector is being done by the sector lead agency, UNEP. Refer to UNEP's progress report for details including disbursement status.
UNEP | Albania | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 85000 | 25000 | 20156 | 0.56667 |  |  | 0 |  |  | The implementation of the HCFC Phase out Management Plan has begun by the end of the year 2011.The SSFA was signed and the first payment was released. The country has initiated a development of training materials and the preparation of technical base for theoretical and practical training programme in the refrigeration sector. Two workshops were held in 2012 and 59 refrigeration technicians were trained (52 received certificates). The NOPIU also organized the Customs training with participation of 50 customs officers from various regions of the country (43 received certificates). The second and third (last) payments were also released | The quota system to control HCFCs is introduced. Extension of the licensing system to include HCFCs containing mixtures was done.
UNEP | Central African Republic | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 310000 | 75000 | 45000 | 2.325 |  |  | 0 |  |  | First payment sent in May 2012. The country conducted training of refrigeration technicians and custom officers.
UNEP | Cape Verde | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 160000 | 44000 | 6308 | 0.1 |  |  | 0 |  |  | The country has conducted training of refrigeration technicians and 30 custom officers.
UNEP | Comoros | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 160000 | 44000 | 41950 | 0.05 |  |  | 0 |  |  | The fist payment was made in June 2012. The project is ongoing satisfactorily.
UNEP | China | HCFC Phase Out Plan (Stage I) - Servicing Sector, including enabling |  | 2011-07-01 |  | 2013-07-01 | 5240000 | 2177000 | 309282.68 | 65.7102 |  |  | 0 |  |  | The agreement was signed on August 2012 and initial disbursement was made on September 2012. The list of planned activities for 2012: - Develop and Enforce the Relevant Policies and Regulations - Qualification Certificate System for Servicing Workshop - Qualification Certification System for Servicing Technicians - Formulate Standards/codes - Procure and Distribute Equipment - Training of Technicians - Policy Enforcement/Inspection, and Information System - Reward and Penalty - Pilot City - Outreach. Progress: For the implementation of the approved refrigeration servicing sector HPMP and the three enabling components, i.e. Capacity-building of national and local authorities, strengthening the HCFC import/export control, and the outreach and communication strategy, FECO and UNEP/Japan organized meetings in April 2012 and September 2012, with participation of the industry associations and national experts to discuss the scope of the work as well as budget allocation among various activities. During the year 2012, the development process for the relevant industry servicing standards and codes have been initiated in accordance with the activities plan under the HPMP. FECO/MEP organized consultation meetings with UNEP, CRAA and CHEAA to prioritize the most needed industrial codes or standards in the servicing sector, and developed relevant TORs for the organization of the development work in both RAC and ICR sector. The national stakeholders’ consultation workshop was organized jointly by FECO/MEP and UNEP/Japan during 19-20 September 2012 to review, discussing the implementation plan. The project proposal and action plan was further reviewed and discussed with national consultation workshop during 19-20 September 2012. The project contract between FECO and Shenzhen was by Nov 2012. During the launching meeting of HCFC Phase-out Management Plans in December 2012, a coordination meeting on the implementation of strategy on capacity-building of national and local authorities was held with participation of the Ozone officers from Local EPBs. Training Workshop 1: The first training workshop had been held in Ningbo City, Zhejiang Province during 24-26 April 2012. The workshop focused on strengthening the enforcement capacity of 70 local customs. Training Workshop 2: The second training workshop was held in Hangzhou City where most of HCFCs exporters were located during 1-3 August 2012. The workshop focused on training of the 95 importers and exporters on China’s HCFC import/export management system. FECO and its partner, Center for Environmental Education & Communications of Ministry of Environmental Protection (CEEC) who was contracted by FECO following evaluation of all options, organized the youth video competition among youth under 25 years old across the nation, and organized the ozone day celebration. | Under another system, the servicing technicians are required to have the compulsory certificate to be qualified to work in the servicing sector, one of the legally defined specialized sectors due to the nature of the safety concerns. FECO/MEP with assistance of UNEP, has already conducted desk study on these two systems, a feasibility study would be organized in 2013. The train the trainer approach will be adopted for the training on good practices including the recovery and recycling. Two national training centres and 10 regional training centres would be established under the HPMP. The participants for the train-the-trainer workshop will be selected from the manufacturing industry as well as the existing vocational or technical Institutes. FECO/MEP will select one city to establish a national training centre first in 2013. 2nd tranche the amendment to the PCA is being finalised in consultation with the Government for agreement.
UNEP | Guatemala | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 255800 | 126175 | 0 | 0.93851 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Second tranche submitted to the 68 ExCom. HCFC quota system drafted.
UNEP | Jamaica | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 77000 | 20000 | 9000 | 0.95156 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were implemented by the NOU. SSFA signed and first disbursement released. 2013 HCFC quotas allocated to importers. | 2013 annual work plan has been drafted. Second disbursement released. One RAC technician attended the sub-regional training in alternative refrigerants held in SKN. HCFC quota system being implemented. ODSs control Training/Refreshing Workshop was in March 2013, 10 Enforcement and Custom Officers attended.
UNEP | Rwanda | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 170000 | 42000 | 22000 | 0.85 |  |  | 0 |  |  | SSFA was signed and the NOU launched the HPMP implementation. List of equipment and tool kits agreed with IAs. Country trained 20 refrigeration experts and 15 customs officers as trainers. The NOU conducted National Refrigeration Association meeting to plan for effective implementation of HPMP activities including strengthening of certification programme | Country procured some tool kits and distributed to repair workshops and refrigeration experts
UNEP | Saint Kitts and Nevis | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2015-06-01 | 124500 | 58400 | 0 | 0.13623 |  |  | 0 |  |  | SSFA signed. Official mission to encourage the Government to adopt HCFC quotas and streamline projects implementation in February 2012. HCFC quotas issued on Dec. 2012. ODS control Training/Refreshing Workshop of 15 Enforcement and Customs Officer in November 2012. | Legal consultant hired. International consultant hired to deliver a national training workshop on alternatives to ODS. 28 RAC technician attended the sub-regional training in alternative refrigerants held in SKN. Support organization of judiciary training for second quarter 2013.
UNEP | Saint Lucia | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2015-12-01 | 51892 | 26150 | 6000 | 0.022082 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP team. First disbursement release in August 2012. Support provided to request HCFC baseline change, including verification of 2010 data. Documents to support second tranche request prepared and submitted. Customs Training Refreshing Workshop was held in Nov. 2012, 32 participants attended. HCFC quotas system approved. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. | Final activities for 1st tranche work plan being completed. HCFC quota system being implemented. 2013 annual work plan has been drafted. HCFC quota system being implemented. The customs brokers training has been planned for the current year. NOO has held discussions with customs IT unit on the disaggregation on ODS refrigerants and refrigerants products in ASYCUDA for the current year.
UNEP | Saint Vincent and the Grenadines | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2014-12-01 | 345800 | 55809 | 34450 | 0.20605 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. Two SSFAs were signed by the Government and UNEP. Fund disbursements released according to plan. Center of Excellence on low-GWP technology reinforced. HCFC quotas were issued by end of Dec. 2012. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada.
UNEP | Zambia | HCFC Phase Out Plan (Stage I) |  | 2011-07-01 |  | 2013-07-01 | 175000 | 40000 | 22000 | 0.94444 |  |  | 0 |  |  | Country trained 40 refrigeration experts and 20 customs officer. NOU procured and distributed tools and equipment. Conducted public awareness activities | Country conducted national train the trainer workshop for 20 Refrigeration experts from all provinces of Zambia
IBRD | China | HCFC phase-out management plan (polyurethane rigid foam sector plan) (stage I, first tranche) |  | 2011-07-02 |  | 2015-12-01 | 73000000 | 44379000 | 19429500 | 1615 | n/a | n/a | 0 | 0 | 0 | Appraisal mission to assess readiness of WB project documents (PIM, disbursement and procurement arrangements, subproject implementation arrangements, etc.) done in Feb. 12. Grant Agreement signed Nov. 2012. Pipeline of 32 enterprises identified as project beneficiaries to undertake conversion to either HC or water blown technology. This will result in a combined reduction of 8,869 metric tons based on 2011 data -representing 60% of the overall reduction target. | Two contracts signed during Q1 2013. An additional 12 contracts will be signed in Apr. 2013. First disbursement of $19 million to China made in April.
IBRD | Indonesia | HCFC Phase Out Plan (Stage I): Foam Sector Plan |  | 2011-07-02 |  | 2015-12-01 | 2714187 | 1500000 | 0 | 30.04 | n/a | n/a | 0 | 0 | 0 | WB internal concept review for a new grant agreement occurred in June 2012. | Appraisal was in Apr. 2013 and WB approval of the new grant agreement is slated for May 2013, at which time disbursement can start.
UNIDO | Oman | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2015-12-01 | 349120 | 314120 | 23523 | 3.7315 | N/A | not yet available |  |  |  | UNIDO international foam expert visited the four foam manufacturing companies identified under the HPMP. He assessed the needs of the companies using HCFCs in pre-blended polyols and advised on their conversion to non-ozone depleting blowing agents, as part of the technical assistance component. He also visited National Heaters Industry (NHI) LLC to discuss the technical and financial implications their conversion to water-blown technology. A draft specification was agreed upon during the mission. A final draft was sent to NHI for comments in September 2012. The specifications are still being discussed. NHI would like to clarify some issues before going ahead. | UNIDO mission took place in February 2013. Once the TOR is finalized, tender will be raised in 2013 as soon as possible. Reason for the delay: TOR for water-blown foaming machine is still to be agreed with NHI.
UNIDO | Egypt | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 2325415 | 2092840 | 38863 | 45.3 | N/A | not yet available |  |  |  | 1) Foam sector: Conversion of insulation foam for refrigeration equipment at Kiriazi. Contract for consultancy and technical services for implementation and local technical supervision of the project has been issued in Janury 2012. Detailed TOR for equipment was prepared and discussed with the company during a site visit. International bidding was concluded in August. Technical queries were cleared with the company. Due to the limited funds available for the foam part of the HPMP negotiation of the cost of equipment was carried out. Purchase order was issued in November 2012. 2) RAC sector: the enabling activities started with a brainstorming meeting in June 2012, all relevant stakeholders and Ministries participated. It was recommended to start with the survey study to analyze the needs of the sector in detail. TOR for consultancy were prepared. | 1) Foam sector: The delivery of equipment is expected for October 2013, contract of the local works and logistic support will be finalized in February 2014. The completion of this part of the HPMP is envisaged for April 2014. 2) Enabling activities in the RAC sector: Start with a consultancy study for RAC enabling activities to go into detail planning for the overall design and supervision. Selection of an educational institution to be upgraded as a training center for certification and selet two servicing companies that have experience with retrofit, recovery and recycling programmes through the NPP to undertake the HCFC-22 based RRR activities focusing on the use of hydrocarbon and other natural refrigerants. Formulation of detailed TOR for those activities.
UNIDO | Bahamas | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 151420 | 105128 | 0 | 0.82507 | N/A | not yet available |  |  |  | TOR for servicing equipment was finalized with NOU. Tender was raised. After evaluation of offers, contract was issued to the supplier in October 2012. | The shipment arrived in Nassau end of January 2013. Customs clearance is in process. A three-day training on operation and maintenance of equipment by the supplier was carried out in March. The project is expected to be completed in 2013.
UNIDO | Sierra Leone | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 100000 | 50000 | 0 | 0.27619 | N/A | not yet available |  |  |  | TOR finalized with NOU.Contract was issued to supplier in December 2012. | Equipment was shipped and supposed to arrive in May 2013. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out.
UNIDO | Equatorial Guinea | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 150000 | 75000 | 7139 | 1.0476 | N/A | not yet available |  |  |  | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013.
UNIDO | Suriname | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 106000 | 68000 | 0 | 0.34829 | N/A | not yet available |  |  |  | TOR finalized with NOU. Contract was issued to supplier in October 2012. Equipment was shipped out early January 2012. | The equipment is arrived at Paramaribo in March 2013. The NOU handled customs clearance. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out.
UNIDO | Ecuador | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 1846440 | 1531940 | 55049 | 19.84 | N/A | not yet available |  |  |  | Tools for the training centres were purchased and delivered to the country. A total of 9 vocational centres will be upgraded with tools for didactic purposes. It was agreed to train trainers from the mentioned centres in February 2013. On the other hand, the destruction machine and refrigerant reclaiming machine were installed and commissioned. The last one has been used for HCFC-22 reclaiming. | Training of 60 trainers was carried out by two UNIDO experts in February 2013. It is expected to train 30 trainers. At the same time, conferences on good refrigeration practices will be carried out. The reclaim of refrigerant will be promoted and some drop in with HC activities will be carried out.
UNIDO | Jordan | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2017-12-01 | 2259217 | 2237033 | 861439 | 8.73 | N/A | not yet available |  |  |  | Monitoring the implementation of the WB in the foam sector was carried out. Legislation was under preparation. | The legislation will be finalized. UNIDO will continue monitoring the implementation of the WB. Reason for the extended project duration: It is in line with the HCFC phase-out target of 2015.
UNIDO | Morocco | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2017-12-01 | 1286740 | 1251740 | 609946 | 16.77 | N/A | not yet available |  |  |  | Launching ceremony was conducted in June 2012. Measures to revise ODS policies as well as adoption of measures on licensing system under execution. | Training of custom authorities as well as purchase of equipment for the replacement of HCFC 141b in the flushing of refrigeration circuits sector expected to be implemented in 2013.
UNIDO | Guinea-Bissau | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 80000 | 40000 | 0 | 0.19048 | N/A | not yet available |  |  |  | Draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in December 2012. | .- Issuance of Purchase Order (January 2013); .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013.
UNIDO | Gambia | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 100000 | 50000 | 5470 | 0.15238 | N/A | not yet available |  |  |  | TOR for servicing and training equipment, finalized with NOU. Contract was issued to suppliers in December 2012. | Equipment was delivered in April 2013. The NOU facilitates the customs clearance. The project is expected to be completed in 2013, sooner than originally planned, since all the activities have been carried out.
UNIDO | Qatar | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2015-12-01 | 1726600 | 1045907 | 8033 | 49.0529 | N/A | not yet available |  |  |  | 1. HPMP approved at the 65th Meeting of the Executive Committee. 2. Cooridnation meeting with government and industry took place. 3. Workplan developed and agreeded. | 1. Expert has visisted the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by the end of 2013. Implementation with the new NOU already restarted. Reason for the extension of the project duration: No NOU officer(s) were appointed for a long period of time.
UNIDO | Senegal | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 505216 | 200000 | 2420 | 6.1736 | N/A | not yet available |  |  |  | National consultant contracted to review ToR and assess the required no. and type of equipment to be delivered to service shops. The subcontract with the counterpart as per the ToR was finalized in December 2012. | National consultant report and technical specification for equipment delivery to be finalized in May 2013. The subcontract with counterpart will be processed first half of 2013.
UNIDO | Burundi | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2020-12-01 | 160000 | 80000 | 4731 | 1.2048 | N/A | not yet available |  |  |  | Joint UNIDO-UNEP mission enabled assessment of needs. Technical specifications were prepared, call for bids for supply of equipment issued, offers received and evaluated and purchase order issued. | Equipment is being shipped.
UNIDO | Iraq | HCFC phase-out management plan (stage I) |  | 2011-11-01 |  | 2015-12-01 | 410000 | 80000 | 0 | 5.2049 | N/A | not yet available |  |  |  | Tender has been awareded, and contract has been established. | 1. Delivery of Equipment. 2. Installation and testing. The project is expected to be completed in 2013.
UNDP | Angola | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 176000 | 86222 | 3840 | 1.59 | N.A. | N.A. | N.A. | N.A. | N.A. | The project was initiated in 2012, with the signature of the Project document and the first mission completed in June by the international consultant. Consultations were held throughout 2012 with the NOU for prioritisation of activities in the first tranche. Some changes in the structure of the NOU explained also that additional time was needed in order to launch activities. | Agreement on the work plan for 2013 to accelerate implementation of activities, with a focus on customs and service technicians' training. Mission to be held in the first half of 2013 by UNDP staff with support from international consultant.
UNDP | Bangladesh | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2020-12-01 | 1201074 | 1201074 | 600055 | 20.78 | N.A. | N.A. | N.A. | N.A. | N.A. | During 2012, terms of agreement for implementation of HPMP project management components were discussed. Due to change in personnel in Government, finalisation of terms of the agreement got delayed though the draft documents were shared with Government in Q1 of 2012. Project activities for HCFC phaseout under a project for HCFC-141b consumption progressed satisfactorily through direct monitoring and supervision of NOU. | Letter of Agreement is expected to be signed by the Government in April 2012.
UNDP | China | HCFC Phase Out Plan (Stage I) | Solvent | 2011-11-01 |  | 2017-11-01 | 5000000 | 2500000 | 1250000 | 62.7 | N.A. | N.A. | N.A. | N.A. | N.A. | Project approved in November 2011. Prodoc signed in 2Q2012. Work Plan and enterprise-level agreements finalized in 4Q2012 | N/A
UNDP | Cuba | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 1747527 | 1287527 | 0 | 19.26 | N.A. | N.A. | N.A. | N.A. | N.A. | Project document was prepared and is in the process of being revised and agreed by the Government of Cuba. Second tranche approved in December 2012. | Bidding process for the foam manufacturing beneficiaries under review ready to be published.
UNDP | Dominican Republic | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 1646225 | 1476225 | 315659 | 26.28 | N.A. | N.A. | N.A. | N.A. | N.A. | Project Document for second tranche was signed in 2012. HCFC quota system and related legislation in place. Agreement was made with INDOTEP about training of technicians. | Contract with INFOTEP was signed. Memorandum of agreement signed with the 4 major polyurethane foam producers. Second tranche approved in the 69th ExCom meeting.
UNDP | Egypt | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 6195400 | 5479000 | 464043.2 | 128.6756 | N.A. | N.A. | N.A. | N.A. | N.A. | Initial mission by a group of international experts was fielded during February 2012 to initiate FSPOP and discuss MOU implementation modality with Al Fateh, Reftruck and 4 system houses. Redachem (Dubai) had facility fire and was put out of operation. It was replaced with Obegi system house which was found to be eligible. For Refrtruck, purchase order placed in December 2012 with equipment expected in July 2013. Site preparation is underway. | MOAs are being revised to reflect final comments from system houses. Mission is planned in April 2013 for follow-up support. For Al Fateh, purchase order for equipment delivery placed in January 2013 with equipment expected in August 2013. Site preparation is underway in coordination with Reftruck activities to save costs.
UNDP | El Salvador | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2022-11-01 | 699277 | 530349 | 0 | 5.8779 | N.A. | N.A. | N.A. | N.A. | N.A. | Project Document was signed. MOAs for participating enterprises have been prepared. 2 technical missions took place to discuss project implementation and selection of technology with foam companies. | MF material in the process of being procured for trials in El Salvador. MOA with the main manufacturer of polyurethane foam system ready to be signed.
UNDP | Fiji | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2022-11-01 | 199500 | 71800 | 18524.99 | 1.764 | N.A. | N.A. | N.A. | N.A. | N.A. | HPMP prodoc was finalised and signed in July 2012. The Government has implemented a quota system for controlling HCFC consumption in the country and HCFC quotas for the year 2012 have been issued to licensed importers. Procurement plan for R&R equipment was finalised in Q4 of 2012. Project Management Unit has been set-up under NOU. | Project activities are progressing satisfactorily. Procurement process has been initiated by the Government and the equipment is expected to be available in the country by middle of the year 2013.
UNDP | Malaysia | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 9587471 | 5000000 | 479524.7 | 103.02 | N.A. | N.A. | N.A. | N.A. | N.A. | Prodoc signed in March 2012. Activities will be initiated in 2013. | N/A
UNDP | Panama | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 265545 | 132773 | 731.32 | 3.78 | N.A. | N.A. | N.A. | N.A. | N.A. | UNDP project document was signed in 2012 by the Government of Panama. Implementation team in place. TORs for experts were prepared. Quota system was established. | TORS published and experts hired. Project has started up implementation of activities. Training worshop programmed. Second tranche will be requested in the 70th ExCom Meeting.
UNDP | Uruguay | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2017-11-01 | 380004 | 200000 | 25774 | 4.18 | N.A. | N.A. | N.A. | N.A. | N.A. | UNDP project document was signed in 2012. International expert was hired to do training in Uruguay. There is a focus on activities for flushing as 141b pure will be banned during Stage I of the HPMP. Quota system in place. | Second and third training by international expert has been scheduled for May and June. Equipment is in the process of being procured. Agrement with LATU for training sessions prepared.
Germany | Zimbabwe | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | Dec-20 | 1038818 | 426891 | 49454 | 11.51 |  |  | 0 |  |  | The project is a combinatin of conversion project for the foam sector and a servicing sector component. Under the foam project several discussions with the beneficiary companies was required prior to their agreement to also contribute towards the planned conversions. Upon agreement, the specifications were tendered. The equipment is now expected to arrive in May 2013. In the R&AC servicing sector component the customs training handbook was revised to reflect HCFCs. Customs trainings have been conducted as well as training of technicians on best practices to be followed when working with HCFC as well as working with hydrocarbons both R600a and R290
UNEP | Burundi | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 172000 | 45000 | 25000 | 1.2952 |  |  | 0 |  |  | SSFA signed and 1st disbursement made in March 2012. SSFA valid upto Feb. 2014.
UNEP | Bangladesh | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 355000 | 230000 |  | 3.7491 |  |  | 0 |  |  | The list of planned activities for 2012: Training of refrigeration technicians on good practice - Organization of train-the-trainer workshop. Customs training and strengthening enforcement capacity - Procurement of equipment - Local training for customs. Awareness and information outreach targeted at HCFC consumers and strengthening HCFC servicing industry associations - Publication and promotional materials (printing and distribution) Progress: The agreement is not reported signed because the Government is taking some time to get internal clearance from the Ministry of Economic and Development. UNEP is in constant touch with the MoE and is expecting to have the agreement signed in May 2013. Mission to the country were conducted by UNEP staff member in March 2012 wherein HPMP plan was discussed and agreed. | UNEP is following up the signing of the agreement and was told by April 2013.
UNEP | Bahamas | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-12-01 | 156900 | 18200 | 6155 | 0.85493 |  |  | 0 |  |  | Funds for first tranche programmed. 2012 annual operating and procurement plans have been prepared by the NOU with the guidance of the CAP Team. SSFA for training technicians during 2012 is signed. First disbursement issued. Two workshops on Good Practices about Alternatives Refrigerant delivered, 30 participants attended. Mission completed Aug 2012 to meet new authorities and agreed on further steps. HPMP launched including mass media coverage carried out in Sept 2012. HCFC Quotas were determined through consultation process between NOU and importers. | SSFA for funding Customs Training Workshops is drafted and being cleared by the Government.
UNEP | Dominican Republic | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 50000 | 50000 |  | 0.85812 |  |  | 0 |  |  | 2012 annual operating plan and procurement plan were prepared by the NOU with the guidance of the CAP Team. HPMP implementation launching workshop carried out in April 2012. HCFC quota system drafted. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. NOO, consultant and Customs officer attended Central America and Dominican Republic Training Workshop for National Ozone Units and Customs Authorities held in Nicaragua on December 2012. | SSFA cleared by Government, pending signature. 2013 work plan prepared. 2nd tranche request submitted to 69th ExCom Meeting.
UNEP | Ecuador | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-12-01 | 115000 | 30000 | 30000 | 1.2359 |  |  | 0 |  |  | Project completed in December 2012. Annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. HCFC baseline changed. HCFC license and quota system completed. Refreshing customs training workshop held in June 2012, 29 participants attended.
UNEP | El Salvador | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2015-11-01 | 375000 | 166500 | 11304 | 3.1521 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. SSFA between the Government and UNEP was drafted. | SSFA has been revised and cleared by the Government. Executive agreement to enforce the HCFC quota system is being sanctioned by Cabinet.
UNEP | Equatorial Guinea | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 165000 | 40000 | 21985 | 1.1524 |  |  | 0 |  |  | NOU trained 50 refrigeration experts and 30 customs officers. The country procured and distributed tools and equipment under the HPMP programme.
UNEP | Fiji | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2014-11-01 | 133000 | 47900 | 25000 | 1.176 |  |  | 0 |  |  | The agreement was signed in September 2012. The list of planned activities for 2012: Training of enforcement officers - Procurement of equipment - Local organization of Train-the-Trainer workshop. Training of RAC technician on good practice - Organization of train-the-trainer workshop, Information, education, and communication - Design and production of awareness materials. Progress: collection of feedback from technicians and enforcement officers on the training needs, to get prepared for the update of the training materials. The country also organized outreach and awareness activities for the HCFC phaseout during the 25th Anniversary celebration on the International Ozone Day. The train-the-trainer workshop is planned to be organized in May 2013, and the enforcement training workshop will be organised in June 2013.
UNEP | Gambia | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 110000 | 25000 | 10000 | 0.16762 |  |  | 0 |  |  | HPMP was launched and the country trained 55 Refrigeration technicians and 30 customs officers. ODS Regulations were submitted to the government for approval. | Country approved revised ODS Regulations and started preparations for hosting Network Meeting
UNEP | Guinea-Bissau | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 130000 | 35000 | 19293 | 0.30952 |  |  | 0 |  |  | The country conducted training of 30 refrigeration technicians and 20 custom officers.. The activities are ongoing satisfactorily.
UNEP | Iraq | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 770000 | 115000 | 0 | 9.7751 |  |  | 0 |  |  | As all activities under HPMP of Iraq are supplementing the NPP activities and depend on completion/implementation of NPP activities, mainly for the servicing sector, the contract for the HPMP is delayed till reaching adequate percentage of the NPP resource utilization and progress of activities. However, work-plan is prepared in details and ready for start by 2013 | Draft country contract is under review by UNEP and country and will be signed by 1st half of 2013
UNEP | Oman | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2015-11-01 | 85000 | 65000 | 0 | 1.3295 |  |  | 0 |  |  | During the reporting period, the necessary assistance have been provided to establish the PMU and its agreed teamwork and national ozone committee (NOC) to supervise the implementation of the MP related activities as well as the implementation of the HPMP. the PMU with its technical teams is now operational. the preparation of the e-licensing system for the trade on ODSs is progressing according to the plan. necessary technical support was provided to the local IT team for integrating the system into the Ministry's under development system. it is expected to complete the online system by Q4 2013. the bylaws for the implementation of the unified GCC regulations on ODSs have been drafted with assistance of UNEP and subject for final adoption. Follow up with NOU regarding their signature of the SSFA agreement for the implementation of the first stage under HPMP that was finalized and signed by UNEP during early 2012 and submitted for government signature | The SSFA agreement for the implementation of the first stage under HPMP was finalized and signed in Feb. 2013. Assistance was provided to finalize the ToRs for the national ozone committee (NOC) to supervise the implementation of the MP related activities as well as the implementation of the HPMP. the 1st meeting of the NOC was held on 5 March 2013 with UNEP and UNIDO participation. the preparation of the e-licensing system for the trade on ODSs is progressing according to the plan and expected to be completed by Q4. the bylaws for the implementation of the unified GCC regulations on ODSs are at final stage for adoption. International experts will be recruited to work with PMU to finalize the update of curricula and expedite the enforcement of the certification scheme for RAC technicians during Q3.
UNEP | Panama | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2014-01-01 | 70000 | 35000 | 1840 | 0.99718 |  |  | 0 |  |  | 2012 annual operating and procurement plans were prepared by the NOU with the guidance of the CAP Team. Consultation meetings about ODS legislation were held with importers of gases and equipment . HCFC quota were allocated. NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. | 2013 annual work plan has been drafted. HCFC quota system being implemented. ODS control and Montreal Protocol Refreshing Workshop was held in March 2013, 21 Enforcement Officers participated.
UNEP | Qatar | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 310000 | 105000 | 0 | 8.8071 |  |  | 0 |  |  | ODS Officer of Qatar changed 3 times over the last 3 years resulting to delaying implementation of all projects. Early 2012 new ODS Officer nominated officially but no proper hand-over internally was arranged. UNEP and UNIDO made plan to re-establish the operation of the Ozone Unit in Qatar and build its capacity through several meetings and missions to quickly orient the new ODS Officer and other officials with MP and project implementation needs. 2 Orientation meetings and one national workshop arranged by UNEP during 2012. All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013 | UNEP organized training program in Qatar in April 2013 on the control and monitor of ODS. UNEP and NOU started national study to assess A/C technologies and facilitate promoting long-term technologies *All activities under TPMP (1st and 2nd tranches were incorporated in the HPMP along with respective balances as approved by ExCom 65) * Final Work-plan is under review by the government and country contract is planned to be established by 1st half of 2013
UNEP | Senegal | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2014-11-01 | 530000 | 100000 | 62290 | 6.4764 |  |  | 0 |  |  | Country conducted training workshops for 40 refrigeration technicians and 30 custom officers
UNEP | Sierra Leone | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 110000 | 25000 | 10000 | 0.30381 |  |  | 0 |  |  | NOU launched the HPMP implementation. List of equipment and tool kits agreed with IAs and procurement process started. Country trained 20 refrigeration experts and 15 customs officers as trainers. The NOU conducted National Refrigeration Association meeting to plan for effective implementation of HPMP activities including strengthening of certification programme | NOU trained 15 customs officers who are based on the boarders and distributed refrigerant identifiers
UNEP | Suriname | HCFC Phase Out Plan (Stage I) |  | 2011-11-01 |  | 2013-11-01 | 104000 | 27000 | 0 | 0.34171 |  |  | 0 |  |  | 2012 annual operating plan and the procurement plan were prepared by the NOU with the guidance of the CAP Team. SSFA signed in April 2012. First disbursement released in May 2012. HPMP launched in Sep 2012. HCFC quota system in place. Three RAC technicians attended the Sub-regional training in alternative refrigerants held in Grenada. National seminar with support of National Refrigeration Association was organized for technicians on low-GWP technologies and recovery and recycling of ODS, 15 participants attended. | 2013 annual work plan has been drafted. HCFC quota system being implemented. Customs Training workshop including 5th Amendment of Customs codes has been planned for the current year. National refrigeration training workshop to be conducted through the association of technicians with support of NOU and UNEP.
IBRD | Jordan | HCFC Phase Out Plan (Stage I): Air-conditioning Sector Plan |  | 2011-11-02 |  | 2017-11-01 | 2341150 | 1070100 | 0 | 16.78 | n/a | n/a | 0 | 0 | 0 | Two WB preparation missions for a new ODS Project/Grant Agreement held Mar & Oct 12. Project implementation manual for overall new ODS project completed which includes proforma appraisal/subproject templates,subgrant agreements, and TORs for the PMU and other technical support in the AC sector. | Legislation updates and HCFC quota issued by Jan. 13. Gov. of Jordan-WB negotiations on the new GA completed Mar 13. WB approval of the new GA expected by Apr. 2013 and effectiveness to follow immediately thereafter. Subproject implementation to begin in Q2 2013.
UNIDO | Algeria | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2017-12-01 | 1993331 | 1809240 | 15990 | 14.48 | N/A | not yet available |  |  |  | Project implementation was slowed down due to postponed mission planned for August 2012. | Mission to Algeria planned for the beginning of February, in order to agree with the representatives of the MATE on plan of action for 2013.
UNEP | Antigua and Barbuda | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2015-04-01 | 51700 | 45850 | 7240 | 0.03 |  |  | 0 |  |  | HPMP launched in Sept. 2012. UNEP country mission carried out. One RAC technician attended the Sub-regional training in alternative refrigerants held in Grenada. Ministerial Order to legalize HCFC quota system drafted. | SSFA drafted. National Training workshop on RAC alternatives and associated good practices. 20 technicians trained.
IBRD | Argentina | HCFC phase-out management plan (stage I, first tranche) |  | 2012-04-01 |  | 2017-04-01 | 914612 | 914612 | 0 | 18.46 | 0 | 0 | 0 | 0 | 0 | Stage I HPMP component that is implemented through the WB as a cooperating agency includes one foam subproject that will cover 18.46 ODP tonnes of HCFC-141b phaseout at Mabe and a technical assistance activity that will establish a monitoring system for the annual production of HCFC-22 in 2013 to 2015, annual quotas for imported HCFCs and a record-keeping system for tracking stockpiles of locally produced HCFCs. Both Mabe and the TA are part of a new ozone grant agreement between the Government of Argentina and the WB which includes the broad framework of the future foam sector plan that will be prepared for inclusion in the country's Stage II HPMP. | Overall project appraisal document is nearing completion and project appraisal mission is scheduled for week of Apr. 22, 2013. MABE subproject and monitoring and reporting of HCFC-22 production are slated to be under implementation by Nov. 2013.
UNIDO | Argentina | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2017-12-01 | 9560542 | 9120930 | 154665 | 74.11 | N/A | not yet available |  |  |  | The new manual for training of service technicians prepared. Specifications and the scope of service equipment finalized and coordinated with the NOU. | Printing of the new manual for service technicians, procurement of equipment and arrangement of training workshops.
UNIDO | Bosnia and Herzegovina | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 953284 | 631282 | 68 | 6.59 | N/A | not yet available |  |  |  | The project was approved in 2012. The project document was revised by the NOU and submitted to the Government. | A mission to develop technical specifications for conversion to cyclopentane in the manufacture of panels at Alternativa was undertaken in February 2013. Equipment purchase March - June. Preparation of specifications for conversion of foam production in 6 manufacturers of commercial refrigeration equipment in Jun Equipment purchase October - December
UNEP | Brunei Darusssalam | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-04-01 | 183000 | 123000 | 31144 | 1.2432 |  |  | 0 |  |  | The agreement was signed and initial disbursement of funds made in August 2012. The list of planned activities for 2012: Training of enforcement officers - Procurement of equipment - Local training for enforcement officers Training of RAC technician on good practice - Organization of train-the-trainer workshop. Progress: The train-the-trainer workshop was organized for enforcement officers during 18-20 Sep 12, ten trainees from RCED and three from DOEPR attended his workshop. The train-the-trainer workshop was organized for refrigeration technicians during 8-11 Oct 12 at Jefri Bolkiah College of Engineering. New models of refrigerant identifiers were procured on December 2012 | The remaining training for enforcement and servicing sector are being planned and prepared in details for implementation.
UNIDO | Cote D'Ivoire | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 920000 | 460000 | 34 | 11.2522 | N/A | not yet available |  |  |  | The project was approved in 2012. PAD was issued and the Government was informed. | A mission to Abidjan took place in February 2013. A consultant will be hired to assess the needs of the center of excellence. Technical specification will be prepared and call for bids will then be issued in 2013.
UNEP | Cote D'Ivoire | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-04-01 | 905740 | 250000 | 85014 | 11.0778 |  |  | 0 |  |  | The Country organized training workshop for 30 refrigeration technicians and 20 custom officers.
UNEP | Djibouti | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2016-04-01 | 164500 | 81000 | 50000 | 0.24 |  |  | 0 |  |  | The first payment was made in August 2012. The project is ongoing satisfactorily
UNIDO | Guinea | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 320000 | 160000 | 0 | 3.9122 | N/A | not yet available |  |  |  | The project was approved in 2012. The Goverment was informed. The draft ToRs for equipment and tools were prepared by UNIDO and agreed upon by the NOU in October. The international bidding for the procurement of equipment and tools was concluded in November 2012. Purchase order was issued in December 2012. | .- Delivery of equipment (2nd quarter 2013); .- Training on the use of equipment (2nd quarter 2013). The project is expected to be completed by the end of 2013.
UNEP | Guinea | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-04-01 | 327000 | 85000 | 55019 | 3.9978 |  |  | 0 |  |  | Project approved in November 2012.
Germany | India | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | Dec-15 | 1994400 | 925452 | 505435 | 32.0095 |  |  | 0 |  |  | Stakeholder Workshop in May 2012, Development of training material, Training of Trainer programs in Dec 2012, Procurement of equipment for training partners, Regional Management Organisation contracted
UNEP | India | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2013-04-01 | 861600 | 430800 | 7112 | 13.8284 |  |  | 0 |  |  | The agreement has been signed in May 2013 and initial disbursement is being processed. The list of planned activities for 2012: Policy & Enforcement Capacity-building - Preparation of Training Materials - Training of Trainers - Enforcement studies and campaigns. Progress: Consultation meeting organized in Bangkok on December 2012 participated by NOU, NACEN and UNEP to discuss the implementation of the HPMP project (enabling). Implementation plan from 2013 to 2015 was negotiated in consultation with the NOU since 2012 and was finalized only in 2013. This was also due to finalization of the HPMP plans with other Implementing Agency's. Disbursement of funds is expected to increase significantly in 2013. Activities that have been completed in 2012 includes: • 1 Technology and Policy Workshop on HCFC Phase out in India in Delhi • Finalization of Timeline for all outputs in UNEP component • Identification of national organizations to implement enforcement training. | HPMP launched on January 2013. Implementation Plan with NOU, NACEN and Vigyan Prasar finalized. SSFAs were formulated and in consultation with the Government for agreement.
France | Kenya | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-03-01 | 900000 | 257500 | 0 | 11 |  |  | 0 |  |  | The French contribution is to be implemented by GTZ-Proklima.
UNIDO | Kuwait | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2018-12-01 | 8861677 | 3537450 | 68 | 213.9398 | N/A | not yet available |  |  |  | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Cooridnation meeting with government and industry took place. 3. Workplan developed and agreed. | 1. Expert has visisted the company and drafted a TOR. 2.TOR for Equipment will be prepared and approved. 3. TOR will be advertised. 4. Equipment should be shipped by end of 2013.
UNEP | Kuwait | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-04-01 | 1043000 | 277000 |  | 25.1802 |  |  | 0 |  |  | Country visited by UNEP and UNIDO to work-out detailed implementation plan coordination meetings with respective authorities concluded in forming 3 national teams for the codes/standards update, establishing certification scheme and control of ODS trade * National Ozone Committee concluded draft update legislation for initiating HCFC Quota by Jan 2013 and control trade of HCFC and all its blends
UNIDO | Mozambique | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 150000 | 75000 | 0 | 1.081 | N/A | not yet available |  |  |  | 1. HPMP approved at the 66th Meeting of the Executive Committee. 2. Cooridnation meeting with government and industry took place. 3. Workplan developed and agreed. | 1. Joint mission with UNEP planned for the second quarter of 2013. 2. Agreement of equipment scope and advertisement of tender. 3. Equipment supply end 2013.
UNEP | Mozambique | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2014-04-01 | 165000 | 40000 |  | 1.189 |  |  | 0 |  |  | SSFA was signed and the NOU launched the HPMP implementation. List of equipment and tool kits agreed with IA's. Action Plan for implementation was established
UNEP | Nepal | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2015-04-01 | 126000 | 63000 | 15530 | 0.384 |  |  | 0 |  |  | The SSFA has been signed and initial payment disbursed in December 2012. The list of planned activities for 2012: HCFC Phase-out Policies (HPP) - Procurement of equipment Enhanced awareness and outreach - Stakeholder Engagement/Workshops - Development of awareness materials such as posters, flyers Promote good practices in the refrigeration and air conditioning installation and servicing sector - Train-the-trainers workshop. Progress: The HPMP project was launched and Stakeholders’ workshop was organized in December 2012. One Customs poster has also been developed and distributed. One Train-the-Trainers (TTT) workshop with 33 master trainers. Technicians’ workshop was organized in December 2012. A survey on HCFC equipment in the hotel industry in Kathmandu has been completed in collaboration with the Hotel Association of Nepal. | Enforcement workshop planned for May or June
UNIDO | Nicaragua | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 222000 | 96500 | 6066 | 1.7962 | N/A | not yet available |  |  |  | The project was approved at the 66 th Meeting of the Executive Committee in 2012. The Government was informed. The first mission took place only in September since a joint mission with UNEP was required. Vocational centres were visited, some tools are required to upgrade the centres but it is planned to establish new centres in different locations. At present the centres are only in Managua. | National expert was hired for the monitoring of the project. International expert visited the country in March to train trainers and technicians in different cities. At the same time, bases for the creation of code of practice will be established by the UNIDO consultant. Once the new training centres are defined, the TOR will be prepared and tools purchased.
UNEP | Nicaragua | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2015-04-01 | 108000 | 38000 |  | 0.88036 |  |  | 0 |  |  | NOO and Customs focal point, supported by UNEP, revised their customs training programmes to include HCFC quota system. HCFC Quota system approved in Dec 2012 by Ministerial Resolution. Capacity of National Refrigeration Technicians Association was built through one-day symposium on low-GWP alternative technologies. | 2013 annual work plan has been drafted. HCFC quota system being implemented. SSFA signed by UNEP ROLAC Regional Director in April 2013.
UNIDO | Niger | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2020-12-01 | 285000 | 175000 | 13237 | 2.8449 | N/A | not yet available |  |  |  | The project was approved at the 66th Meeting of the Executive Committee. The Government was informed. Train the the trainer component for the refrigeration technicians was organized in 2012, focusing on the results of the NPP and adressing additional needs with a view to HCFCs. | Workplan for the year 2013 and Terms of Reference for subcontract with counterpart for implementation of the policy component is under agreement with counterpart.
UNEP | Niger | HCFC Phase Out Plan (Stage I) |  | 2012-04-01 |  | 2016-04-01 | 275000 | 100000 | 60000 | 2.75 |  |  | 0 |  |  | First payment was sent in July 2012. The country conducted training workshop for 30 refrigeration technicians and 20 Custom officers
UNIDO | Sudan | HCFC phase-out management plan (stage I) |  | 2012-04-01 |  | 2017-12-01 | 1456341 | 1306341 | 1854 | 16.15 | N/A | not yet available |  |  |  | The project was approved at the 66th Meeting of the Executive Committee. In December 2012 a national consultant was recruited. Technical assistance including equipment was provided to manufacturing companies in refrigeration sector. Project is implemented as planned. Training programme including purchase of training and servicing equipment is being prepared. | Refreshment trainings for different groups (custom officers; trainers at training centers (e.g. IRCC) and schools (e.g. SUST Khartoum) as a follow up to earlier established RMP. Review of training facilities; identify the needs for training programs and training equipment (for demonstration, servicing, monitoring/identification of refrigerants). Technical and public awareness workshops on alternative technologies to be considered for HPMP, Stage II.
UNDP | Brunei Darusssalam | HCFC Phase Out Plan (Stage I) |  | 2012-04-16 |  | 2022-04-16 | 132000 | 52800 | 0 | 0.89257 | NA | N.A. | N.A. | N.A. | N.A. | A draft Letter of Agreement between Brunei Government and UNDP and prodoc were prepared in Q2/Q3 of 2012 and sent to the Government in July, 2012. The Government is reviewing this agreement. This agreement is expected to be finalised by end of Q2 or early Q3 of 2013 after administrative clearance from Government. | The Government is reviewing the agreement and is expected to be finalized in Q2/Q3 of this year.
UNDP | India | HCFC Phase Out Plan (Stage I) |  | 2012-04-16 |  | 2017-04-16 | 18438490 | 10000000 | 0 | 295.93 | NA | N.A. | N.A. | N.A. | N.A. | In 2012, the prodoc was signed. Stakeholder consultations continued to get consensus on technology and financing approach. | Newly approved at the 66th ExCom.
UNDP | Nepal | HCFC Phase Out Plan (Stage I) |  | 2012-04-16 |  | 2022-04-16 | 84000 | 42000 | 0 | 0.3 | NA | N.A. | N.A. | N.A. | N.A. | During the year 2012, consultations were held with NOU of Nepal on implementation plan for HPMP. Due to changes in NOU staff, finalisation of plan got delayed, however, it is expected to be back on track in 2013. | Implementation plan is expected to be completed by Q2 of 2013.
UNIDO | Bahrain | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2020-12-01 | 2338985 | 549455 | 0 | 19.3265 | N/A | not yet available |  |  |  | Project approved at 68th ExCom in December 2012 | A mission is planned for end Feb. to agree on implementation plan with the beneficiary (Awal Gulf)
UNEP | Bahrain | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2014-12-01 | 470000 | 120000 |  | 3.8835 |  |  | 0 |  |  | Project approved in November 2012. | UNEP coordinated 2 preparatory meetings with NOU and UNIDO to prepare the detailed work-plan of the HPMP of Bahrain during the 1st quarter of 2013. Country contract planned to be signed by May 2013.
UNEP | Barbados | HCFC Phase Out Plan (Stage I) |  | 2013-04-01 |  |  | 192000 | 74000 |  | 0.88
UNIDO | Eritrea | HCFC phase-out management plan (phase I) |  | 2012-07-01 |  | 2020-12-01 | 80000 | 40000 | 0 | 0.01459 | N/A | not yet available |  |  |  | The project was approved in July 2012 at the time the TPMP were implemented and completed. As indicated in the previous project, the National Ozone Office left the country and jeopardize the implementation of the project. | The project will be implemented as second step of the TPMP. It is planned a joint mission with UNEP in April 2013. Demonstration projects with HC or alternative refrigerants is planned. The project is expected to be completed this year.
UNEP | Eritrea | HCFC Phase Out Plan (Stage I) |  | 2012-07-01 |  | 2016-07-01 | 84500 | 40000 |  | 0.01541 |  |  | 0 |  |  | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the absence of Ozone Officer. The Government is in the process of appointing new Ozone Officer to proceeding with implementation of activities
UNIDO | Ethiopia | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2020-12-01 | 140000 | 70000 | 0 | 0.85333 | N/A | not yet available |  |  |  | The project was approved at the 68th Meeting of the Executive Committee in December 2012. The government was informed. The work plan was established. | Agremeent on TOR, purchase and delivery of equipment planned to take place by the end of 2013.
UNEP | Ethiopia | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2016-12-01 | 175000 | 85000 |  | 1.0667 |  |  | 0 |  |  | SSFA prepared and sent to the country. Implementation of activities including signing of SSFA delayed due to the change of Ozone Office from Meteorological Department to Environment Protection Agency. New Ozone Officer has been appointed and CAP is training the new officer to start implementation of HPMP activities
UNDP | Haiti | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2022-12-01 | 97119 | - | 0 | 0.44 |  |  | N.A. | N.A. | N.A. | N/A | N/A
UNEP | Haiti | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2015-12-01 | 182881 | 40000 |  | 0.82296 |  |  | 0 |  |  | HPMP approved in Dec 2012. | Country mission and official launch already scheduled for second quarter of 2013. Work plan drafted, including: policy workshop, scheduling deliverables and stakeholders responsibilities.
UNIDO | Myanmar | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2020-12-01 | 60000 | 0 | 0 | 0.32143 | N/A | not yet available |  |  |  | UNIDO share of funds will be released in 2015 and implemented as per schedule.
UNEP | Myanmar | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2015-12-01 | 220000 | 159000 |  | 1.1786 |  |  | 0 |  |  | The agreement for transfer funding can’t be processed as per the ExCom decision 68/31. UNEP is following up with the country regularly on the approval of the Ozone Order. One unit of new model of refrigerant identifier were procured and delivered on December 2012. This project is newly approved in December 2012. | UNEP purchased and distributed 1 unit of RAC equipment in Feb 2013. The funds is being programming.
UNDP | Peru | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2017-12-01 | 232671 | 108000 | 0 | 3.08 | N.A. | N.A. | N.A. | N.A. | N.A. | Newly approved. | Options for the Licensing System evaluated by the Government and in April, a sector consultation will be carried between public and private sector to finalize the model and establish the Licensing and quota systems. UNDP project document has been developed.
UNEP | Peru | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2013-12-01 | 50000 | 25000 | 0 | 0.66155 |  |  | 0 |  |  | HPMP approved in Dec 2012. | Country mission and official launch already scheduled for second quarter of 2013. Annual work plan drafted.
UNEP | Philipinnes | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2015-12-01 | 230000 | 207000 | 0 | 5 |  |  | 0 |  |  | The NCPP PMU conducted/organized four (4) Regional Consultations nationwide to gather significant comments from the concerned stakeholders in 2012. The NCPP PMU conducted turn-over of training equipment to Training Institutes (TIs) through awarding of Deed of Donations. As to date, 136 out of 139 TIs have been completed. Submitted CFC verification audit to UNEP last 22 February 2012. | The NCPP PMU conducted regional workshop last 20 February 2013 with selected Regional ODS Officers in Luzon Area to discuss the initial findings on the assessment of voucher grantees. Out of the 602 target service shops to be survey, all were completed.
UNIDO | Saudi Arabia | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2020-12-01 | 12480171 | 3888501 | 27117 | 659.14 | N/A | not yet available |  |  |  | The project was approved in 2012. The Government was informed. | Consultation with NOU and UNEP held in January 2013. Expert mission for specification for 14 companies of the PU foam sector - March/April Project Management Unit established April Call for offers on equipment for 2-3 companies in the PU foam sector April-June and further 3 companies August - September National expert to collect data on SME downstream users March - June Expert misssion to develop specifications for systems houses - April/May Call for offers for further 3 companies of the PU sector June - September Procurement of equipment for the first 3 companies of the PU foam sector for the SHs July - December
UNEP | Saudi Arabia | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2015-12-01 | 720800 | 290400 |  | 32.8125 |  |  | 0 |  |  | Project approved in November 2012. | HPMP project( approved at the 68th ExCom) was launched on 19 March 2013 in Jeddah- KSA. UNEP and UNIDO organized several consultation meetings during and at the margin of the workshop. PMU is being established and detailed work-plan for implementing the approved activities including the remaining activities of NPP 2nd tranche, is being finalized.
UNIDO | Somalia | HCFC phase-out management plan (phase I) |  | 2012-07-01 |  | 2020-12-01 | 315000 | 173874 | 0 | 1.85 | N/A | not yet available |  |  |  | The project was approved at the 67th Meeting of the Executive Committee in 2012 on an exceptional basis, and without setting a precedent for any future projects, the security-related costs in addition to the funding of the first tranche of stage I of the HPMP to enable the implementation of the programme. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of of workshops.
UNIDO | South Africa | HCFC phase-out management plan (phase I) |  | 2012-07-01 |  | 2020-12-01 | 6533556 | 1960229 | 0 | 176.72 | N/A | not yet available |  |  |  | The project was approved at the 67th Meeting of the Executive Committee in 2012. The Government was informed. | Recruitment of international and national experts; preparation of technical specifications for bidding; organisation of workshops; assistance to the government on reporting and legislation.
UNIDO | Tanzania | HCFC phase-out management plan (phase I) |  | 2012-07-01 |  | 2020-12-01 | 100000 | 50000 | 0 | 0.28095 | N/A | not yet available |  |  |  | Project approved in July 2012. UNIDO approach the NOU and it was agreed to wait for the joint mission. | A joint mission is planned with UNEP in June 2013. The main plan for 2013 is to equip the vocational centres with tools and work with alternatives.
UNEP | Tanzania | HCFC Phase Out Plan (Stage I) |  | 2012-07-01 |  | 2015-07-01 | 110000 | 55000 | 0 | 0.30905 |  |  | 0 |  |  | SSFA was signed and country launched the implementation of HPMP activities. List of equipment agreed by IA and the country conducted training of 20 customs officers and 45 refrigeration experts. NOU conducted meeting of Refrigeration Association | Country procured and distributed tool kits to refrigeration experts and a few repair workshops.
IBRD | Thailand | HCFC phase-out management plan (stage I, first tranche) |  | 2012-12-01 |  | 2018-12-01 | 22749072 | 4817166 | 0 | 219.54 | n/a |  |  |  |  | First tranche was approved in Dec. 2012. A preparation mission (for a new Thailand-WB grant agreement) was launched immediately after the ExCom approval of the HPMP. | 2013 HCFC import quota was established in Jan. 2013. Thailand initiated preparation of environmental safeguard plans to ensure safe introduction of flammable materials in both foam and a/c sectors. First inter-departmental meeting was held to discuss the need to amend regulations and standards pertaining to use of mildly flammable materials as refrigerants. Consulatations with Council of Engineers to promote the use of non-HCFC-22 a/c held. GoT is encouraging a/c enterprises not eligible for funding from the MLF to also adopt lower-GWP alternatives. Several multinational companies have started preparation to offer a similar product in Thailand and for export markets. Grant Agreement expected to be approved by the WB in Oct. 2013 and disbursement will commence shortly thereafter.
Japan | Thailand | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  |  | 302965 | 302965 |  | 3.085 |  |  | 0
UNIDO | Turkey | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2017-12-01 | 14120090 | 8521240 | 473139 | 504.47 | N/A | not yet available |  |  |  | The project was approved at the 68th Meeting of the Executive Committee in November 2012. The Government was informed. | UNIDO mission and meeting with the NOU is scheduled for the second quarter of 2013. International consultant field visit to agree workplan with the SH companies to take place during the second quarter of 2013.
UNEP | Turkey | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2017-12-01 | 103450 | 103450 |  | 3.4033 |  |  | 0 |  |  | The project was approved by ExCom in December of 2012. | The discussion has been initiated on the action plan for implementation of the Customs training components under the approved HPMP.
UNIDO | Uganda | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2020-12-01 | 80000 | 40000 | 0 | 0.034043 | N/A | not yet available |  |  |  | The project was approved at the 68th Meeting of the Executive Commitee in Decemeber 2012. The Government was informed. | A joint mission with UNEP is planned in May 2013. A that the implementing activities will start.
UNEP | Uganda | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2016-12-01 | 84500 | 40500 |  | 0.035957 |  |  | 0 |  |  | Country finalised HPMP and was approved at 68 ExCom. | SSFA drafted and sent to the country for signing
UNIDO | Yemen | HCFC phase-out management plan (stage I) |  | 2012-12-01 |  | 2015-12-01 | 410000 | 410000 | 0 | 32.8415 | N/A | not yet available |  |  |  | The project was approved in 2012. The Government was informed. | Specification for supply of identifier units - April Equipment purchase - May - July Specification for upgrade of R&R units and recycle/recovery kits - August Equipment purchase - September - November
UNEP | Yemen | HCFC Phase Out Plan (Stage I) |  | 2012-12-01 |  | 2015-12-01 | 380000 | 215000 |  | 30.4385 |  |  | 0 |  |  | Project approved by 68th ExCom (Dec-12) | UNEP and UNIDO are coordinating with NOU to finalize the work-plan of all HPMP activities and remaining TPMP activities. Country contract is planned to be established by June 2013 Due to recent political development and subsequent changes of Minister of Environment & Water, as well as the Chairman of Environment Protection Authority (EPA); UNEP is waiting for clear instructions of new management to draft and process new ISP agreement.
IBRD | China | HCFC Production Phase Out Plan (Stage I) |  | 2013-04-01 |  |  | 95000000 | 24000000