## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | IRDX | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Obligated (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Obligated (US$) | Remarks | Remarks (Latest information) | Year of Contribution | Latest Planned Date of Completion | Business Plan Allocation (Investment/Non-Investment) | Disbursements made to final beneficiaries from FECO/ MEP | Inplementation Delays/Status Report Decisions (74th Meeting)
FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | AFR | AFR | FUM | 17 | TAS | 14 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-10-01 | 1995-11-01 | 38896 | 0 | 38896 | 38896 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | Individual | LAC | ARG | REF | 17 | TAS | 24 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1996-02-01 | 1996-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | Support to participants to the regional workshop on refrigeration and air conditioning training programme | Individual | ASP | ASP | REF | 12 | TRA | 14 | A | D |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-04-01 | 1994-05-01 | 66800 | 0 | 66800 | 66800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1994
FIN | Australia | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | Individual | ASP | ASP | SEV | 07 | TRA | 06 | A | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-07-01 | 39394 | -4420 | 34974 | 34974 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1992
FIN | Australia | Support to ASEAN regional conference on CFC and halons | Individual | ASP | ASP | SEV | 08 | TRA | 08 | A | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 4420 | -103 | 4317 | 4317 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1993
FIN | Australia | Additional support for the regional strategy for 11 Article 5 countries in the Pacific (PIC strategy) | Individual | ASP | ASP | SEV | 50 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2011-03-01 | 2012-05-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | completed |  | 2007
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | FSM | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | FSM | REF | 36 | TAS | 02 | A | I |  | 0.7 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
ONG | Australia | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | TAS | 196 | A | I |  | 3.7 |  | 0 |  | 2011-07-01 | 2013-08-01 | 2014-12-01 | 2016-12-01 |  |  | 300000 | 0 | 300000 | 25585 | 8.528% | 274415 | 0 | 53000 | 39000 | 0 | 39000 | 0 | 0 | Ongoing | During the year 2014, the main activities that were undertaken included (a) review and finalisation of annual work plan for the period of 2014-2016 including participation of AMRI in technical support to service sector, information outreach on regulations and technical support to service agencies on new HCFC free technologies and support of AMRI for HPMP Stage-II preparation, (b) translation of technical manuals developed by institutions in Australia on good servicing practices and safe handling of flammable refrigerants into Indonesian Bahasa in Q4-2014 (completed by Q1/Q2 of 2015 after technical review of translated materials), (c) Technical and coordination support for regulations enforcement for cessation of HCFC use as a refrigerant in equipment production in RAC sector. Meetings were held in January, June and October 2014 with AMRI representatives on activities undertaken and how future plans can be structured for facilitating HCFC management in refrigeration and air-conditioning sector. During the year 2014, priority was given for support by AMRI to HPMP activities relating to regulations enforcement in RAC sector to achieve complete phase-out of HCFC as a refrigerant in manufacturing activities. During the year 2015, outreach on HCFC free technologies covering RAC applications would be undertaken in Indonesia. | 2011
FIN | Australia | Indonesian ODS control policy | Individual | ASP | IDS | SEV | 17 | TAS | 33 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-05-01 | 1996-01-01 |  | 1996-01-01 | 1996-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | National halon management and banking programme | Individual | ASP | IND | HAL | 32 | TAS | 281 | A | I | HAL | 197.2 | 197.2 | 0 | 0 | 2000-12-01 | 2002-02-01 | 2004-01-01 |  | 2007-05-01 | 2008-05-01 | 245700 | -24100 | 221600 | 221600 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed. |  | 2000
CLO | Australia | Replacement of methyl bromide with non ozone depleting substances in grain storage | Individual | AFR | KEN | FUM | 21 | DEM | 12 | A | D |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-07-01 |  |  | 2000-06-01 | 232834 | -91869 | 140965 | 140965 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | 1996
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | KIR | REF | 36 | TAS | 02 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | KIR | REF | 36 | TAS | 03 | A | I |  | 0.4 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | MAS | REF | 36 | TAS | 02 | A | I |  | 0.8 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | MAS | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | SOI | REF | 36 | TAS | 02 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | SOI | REF | 36 | TAS | 04 | A | I |  | 1.4 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TON | REF | 36 | TAS | 01 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TON | REF | 36 | TAS | 03 | A | I |  | 0.9 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TTR | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TTR | REF | 36 | TAS | 02 | A | I |  | 1.1 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TUV | REF | 36 | TAS | 02 | A | I |  | 0.1 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TUV | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 | 2005-06-01 | 282687 | -42162 | 240525 | 240525 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed |  | 1996 | 1997-12-01
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 |  | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP- 35th ExCom |  | 2001
FIN | Austria | Establishment of a training centre for commercial refrigeration service technicians at Comservice S.A. |  | EUR | ROM | REF | 20 | TRA | 11 | A | I |  | 10 |  |  |  | 1996-10-01 |  | 1997-10-01 |  | 1999-02-01 | 1999-05-01 | 116628 | 0 | 116628 | 116628 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 1996
CLO | Belgium | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Quimica Andina |  | LAC | BOL | FOA | 28 | INV | 10 | A | I |  | 5 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2002-02-01 |  |  |  | 108480 | -108480 | 0 | 0 | 0% | 0 |  | 0 | 0 |  |  | 0 |  | Agreement between UNDP and the Belgian Government finally signed in September 2000. However, funds not yet received as of 31 December 2000. Info as of 31 May 2001: funds received in Feb. 2001. Project document not yet signed by Bolivian Govt. However, invitations to bid were sent out and bid analysi was done. However, we had to re-bid because offers did not meet specs for one machine. New bid analysis on-going. Info as of 31 December 2001: New ministry was undergoing some verification of the enterprises which were being considered for MLF funding since according to some new regulations, in order for Quimica Andina to qualify it needed to be one of the higher national consumers of CFC-11. Only if this was the case would the project be approved and the PRODOC signed. |  | 36923
FIN | Canada | Implementation of the RMP: national recovery and recycling | RMP | LAC | ANT | REF | 26 | TAS | 06 | A | I | CFC | 1 |  | 0 |  | 1998-11-01 | 2000-06-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of customs | RMP | LAC | ANT | REF | 26 | TRA | 04 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2002-10-01 | 2002-12-01 | 42940 | 0 | 42940 | 42940 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Complete. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training the trainers in good refrigerant management practices | RMP | LAC | ANT | REF | 26 | TRA | 05 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 47460 | 0 | 47460 | 47460 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed PCR submitted. |  | 1998 |  | Non-Inv.
CLO | Canada | Project preparation for a terminal phase-out management plan |  | AFR | BEN | PHA | 49 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2006-07-01 |  | 2007-07-01 |  |  | 2009-07-01 | 12000 | -12000 | 0 | 0 |  | 0 |  | 0 | 1560 | -1560 | 0 | 0 |  | TPMP has been prepared by UNEP and approved at 55th meeting, without the need for the funds approved for Canada. Therefore, Canada will ask for cancellation of this project at the 58th meeting and return related funds. |  | 2006 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: development of code of good practice for technicians | RMP Update | AFR | BEN | REF | 32 | TAS | 10 | A | I |  | 0.9 | 0.9 | 0 |  | 2000-12-01 | 2003-01-01 | 2002-12-01 |  | 2004-06-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 1300 | 0 | 1300 | 0 |  | Final copies of Code of Good Practice received by Canada. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of custom officials | RMP Update | AFR | BEN | REF | 32 | TRA | 08 | A | I |  | 5.2 | 5.2 | 0 |  | 2000-12-01 | 2003-01-01 | 2003-06-01 |  | 2006-08-01 | 2006-08-01 | 59900 | 0 | 59900 | 59900 | 100% | 0 |  | 0 | 7787 | 0 | 7787 | 0 |  | Project delayed until ODS import/export legislation was passed in April 2002. Train-the-Trainer Worshop held August 2003 and second phase followed in 2004. Canada asked that more customs officers be trained, as results are lower than under other comparabl |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practices | RMP Update | AFR | BEN | REF | 32 | TRA | 09 | A | I |  | 12.6 | 12.6 | 0 |  | 2000-12-01 | 2001-10-01 | 2002-12-01 |  | 2003-12-01 | 2004-12-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 |  | 0 | 18720 | 0 | 18720 | 0 |  | Train-the-Trainer workshop held in Jan. 2002. Phase II training and monitoring completed in 2003. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of environmental inspectors and investigators | RMP Update | AFR | BEN | REF | 32 | TRA | 11 | A | I |  | 5 | 5 | 0 |  | 2000-12-01 | 2005-01-01 | 2003-12-01 |  | 2007-02-01 | 2007-02-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Train-the-Trainer workshop for 25 environmental inspectors completed in March 2005 and second and final workshop held in June 2006. Small remaining balance was left and Canada agreed that it be used for an ODS survey. Benin submitted survey and final expenditure report. PCR was submitted Dec. 2007. |  | 2000 |  | Non-Inv.
FIN | Canada | Project preparation for the terminal phase-out management plan |  | AFR | BKF | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2006-10-01 | 2006-10-01 | 10000 | -650 | 9350 | 9350 | 100% | 0 |  | 0 | 1300 | -100 | 1200 | 0 |  | TPMP prepared and submitted with UNEP at ExCom 50. Project completed. Remaining balance of $650 and associated support costs ($100) were returned to Fund. |  | 2005 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | BKF | PHA | 50 | INV | 22 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-01-01 | 2008-03-01 |  | 2008-09-01 | 2008-10-01 | 98500 | 0 | 98500 | 98500 | 100% | 0 |  | 0 | 12805 | 0 | 12805 | 0 |  |  |  | 2006 |  | Investment
FIN | Canada | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | INV | 24 | A | I | CFC | 5.4 | 5.4 | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-12-01 | 2011-07-01 | 86500 | -3000 | 83500 | 83500 | 100% | 0 |  | 0 | 11245 | -495 | 10750 | 0 |  | Procurement of retrofit equipment and tools (2nd phase) completed in July 2009 ($57,481). $13,000 provided to Burkina Faso for awareness-raising activities and local purchase of tools. Additional technician training courses organized in 2009-beginning of 2010 by UNEP. Mission by EC in January 2010 revealed that tools had not yet been distributed to technicians, but this was subsequently reported by NOU to have been done. Project completed. $3,000 returned to the MLF with $495 in support costs, and noted at 64th ExCom meeting. |  | 2008 |  | Investment
FIN | Canada | Implementation of the RMP: training of customs officers programme | RMP | AFR | BKF | REF | 29 | TRA | 09 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2002-08-01 | 2003-01-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  | 0 | 5525 | 0 | 5525 | 0 |  | Project Complete. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers and technicians in good refrigeration management practices | RMP | AFR | BKF | REF | 29 | TRA | 10 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-03-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 5200 | 0 | 5200 | 0 |  | Training of technicians is completed as of March 2002. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Project preparation for the terminal phase-out management plan |  | LAC | BOL | PHA | 47 | PRP | 27 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-02-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | TPMP prepared, submitted to ExCom 51 and approved. Project and last payment completed in February 2007. |  | 2005 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | TAS | 28 | A | I | CFC,CTC | 15.3 | 15.3 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-12-01 |  | 2009-03-01 | 2009-04-01 | 79000 | 0 | 79000 | 79000 | 100% | 0 |  | 0 | 10270 | 0 | 10270 | 0 |  | Completion of the revision of the legal framework, diffusion of awareness-raising material, training of 159 customs officers. Inspection visits to workshops and importers took place in several cities throughout 2009 to evaluate their compliance with national legislation and verify the consumption. Most project activities completed by March 2009. A CTC workshop with users was rescheduled under second tranche to September 2009 due to coordination issues. |  | 2007 |  | Investment
FIN | Canada | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | TAS | 32 | A | I | CFC, CTC | 0 | 0 | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2013-07-01 | 2013-07-01 | 88000 | -5000 | 83000 | 83000 | 100% | 0 |  | 0 | 11440 | -650 | 10790 | 0 |  | Activities undertaken consists of a CTC information workshop (including printing and distribution of report on alternatives to CTC for laboratories); 62 inspections of servicing workshops; modifications to ODS regulations and printing regulatory text; printing of 300 copies of customs training manual; various public awareness activities, and project management. In 2012, Bolivia advised that it still held about US $7,000 in funds advanced from Canada and proposed to use them for project management and awareness-raising activities. Despite repeated attempts, Canada never received a final report on the use of these funds, but considered the project closed as of July 2013. Note that ExCom 68 approved transfer of remaining funds not transferred from Canada (US $5,000) to UNDP for HCFC activities under UNDP's final tranche of the TPMP. | No additional information up to April 29 2013. | 2009 |  | Investment
FIN | Canada | Implementation of the RMP: assistance in preparation of regulations and technical norms | RMP | LAC | BOL | REF | 36 | TAS | 17 | A | I |  | 1.3 | 1.3 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2003-11-01 | 2003-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  | 0 | 1690 | 0 | 1690 | 0 |  | Funds disbursed for legal consultant and workshops to develop legislation. Legislation approved in March 2004. Project completed. PCR submitted. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: public awareness programme on issues related to the ozone layer | RMP | LAC | BOL | REF | 36 | TAS | 20 | A | I |  | 5.4 | 5.4 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2008-03-01 | 2008-03-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 |  | 0 | 6760 | 0 | 6760 | 0 |  | Last remaining activity, production of school texts on ozone depletion, was delayed due to administration difficulties - now completed. Final report was received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: monitoring the activities in the RMP project | RMP | LAC | BOL | REF | 36 | TAS | 22 | A | I |  | 5.9 | 5.9 | 0 |  | 2002-03-01 | 2002-09-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Monitoring database and information system installed and working, as well as ODS monitoring and reporting activities. Funds used principally for local project consultant to implement, monitor and report on project activities. All activities have been completed and final report received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for customs officers and technical staff in municipalities | RMP | LAC | BOL | REF | 36 | TRA | 19 | A | I |  | 5 | 5 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2005-04-01 | 2005-04-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 |  | 0 | 6240 | 0 | 6240 | 0 |  | Train-the-trainers workshop completed in 2004. Phase II customs officers training completed in March 2005 with 83 officers trained. A total of $13,972 remained in funding after project completion and were used on other RMP components (principally the moni |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for refrigeration technicians | RMP | LAC | BOL | REF | 36 | TRA | 21 | A | I |  | 5.7 | 5.7 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2005-06-01 | 2005-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Train-the Trainers workshop held in Sept. 2004. Training equipment purchased and distributed. Phase II training completed in May 2005 with 265 technicians trained. Remaining funds from 2005 were used in 2006 on other RMP components (mainly the monitoring) |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: recovery and recycling | RMP | LAC | BOL | REF | 39 | TAS | 23 | A | I | CFC | 30.3 | 30.3 | 0 |  | 2003-04-01 | 2005-01-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 292000 | 0 | 292000 | 292000 | 100% | 0 |  | 0 | 37960 | 0 | 37960 | 0 |  | 1st Phase of R&R equipment was shipped to Bolivia in April 2005 and 2nd Phase in Dec. 2005. The majority of the equipment has been distributed to technicians and training has been completed. A few batches of R&R machines have not been distributed due to administrative problems, but Bolivia expects to distribute them prior to end of April 2009. |  | 2003 |  | Investment
FIN | Canada | Halon recycling and bank management | Halon Banking | LAC | BRA | HAL | 19 | TAS | 47 | A | I |  | 21.3 | 21.3 | 0 |  | 1996-05-01 | 1996-10-01 | 1998-05-01 |  | 1999-05-01 | 1999-05-01 | 499360 | -20031 | 479329 | 479329 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented although one year later than planned. Adjustment results of exchange rate fluctuations |  | 1996 | 1998-09-01 | Non-Inv.
FIN | Canada | Refrigeration training workshop in the state of Sao Paulo | Individual | LAC | BRA | REF | 11 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-09-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1993 and approved in retroactive funding in November 1993. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | Canada | Montreal Protocol Technology Transfer Workshop on ODS (Phase II) | Individual | LAC | BRA | SEV | 15 | TRA | 17 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1994-09-01 | 1995-12-01 | 58390 | 0 | 58390 | 58390 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1994 and approved in retroactive funding in December 1994 |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Ozone depleting solvents workshop in Brazil | Individual | LAC | BRA | SOL | 17 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1994-05-01 | 1996-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in May 1994 and approved by retroactive funding in August 1995 |  | 1995 | 2000-01-01 | Non-Inv.
FIN | Canada | Implementation of the RMP: monitoring and control of ODS and ODS based equipment and training programme for customs and other inspection officers | RMP | LAC | BZE | REF | 29 | TAS | 03 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 3640 | 0 | 3640 | 0 |  | Train-the-trainer customs workshop held in March 2002. Phase II training completed in 2003. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: policy dialogue programme and regulatory framework for phasing out ODSs | RMP | LAC | BZE | REF | 29 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2000-09-01 |  | 2001-11-01 | 2002-12-01 | 15500 | 0 | 15500 | 15500 | 100% | 0 |  | 0 | 2015 | 0 | 2015 | 0 |  | Planning and Policy Dialogue component completed Nov. 2001. Regulatory framework developed and adopted by Government. PCR submitted |  | 1999 | 2001-12-01 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of trainers and refrigeration technicians in good servicing practices | RMP | LAC | BZE | REF | 29 | TRA | 02 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Train the trainers workshop held in April 2001. Subsequent training took place in 2002 and finalized in 2003. |  | 1999 |  | Non-Inv.
FIN | Canada | Bromosorb technology in commodity fumigation | Individual | LAC | CHI | FUM | 15 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1997-04-01 | 1997-04-01 | 300000 | 17000 | 317000 | 317000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 1996-12-01 | Non-Inv.
FIN | Canada | Project preparation for a national phase-out plan |  | LAC | CHI | PHA | 50 | PRP | 162 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2008-04-01 | 2008-04-01 | 30000 | -1 | 29999 | 29999 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Chile servicing sector terminal phase-out plan preparation began in Oct 2007. Final proposal was completed by April 2008 and TPMP approved in July 2008. |  | 2006 |  | Non-Inv.
FIN | Canada | Servicing sector terminal CFC phase-out plan (first tranche) | Multi-Year | LAC | CHI | PHA | 55 | INV | 166 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-02-01 | 2011-07-01 |  | 2012-03-01 | 2012-03-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 |  | 0 | 22880 | 0 | 22880 | 0 |  | Project was completed in March 2012. 107 conversions were undertaken and verified, 480 technicians received training in good practice, and a good practice standard was developed and officially published in June 2011 by the National Norm Institute. |  | 2008 |  | Investment
FIN | Canada | Servicing sector terminal CFC phase-out plan (second tranche) | Multi-Year | LAC | CHI | PHA | 60 | INV | 173 | A | I | CFC | 32.9 | 32.9 | 0 |  | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2013-03-01 | 2013-03-01 | 261500 | 0 | 261500 | 261500 | 100% | 0 |  | 0 | 33995 | 0 | 33995 | 0 |  | Project completed March 2013. Key results include: 125 refrigeration systems retrofitted; National Registry of refrigeration technicians established; Refrigeration servicing equipment supplied to training centres; 569 technicians trained in good practices. | Project completed in March 2013. Key results included: training of 569 technicians (in addition to those trained under Phase I); development of official certification system for technicians; 98 end-user conversions; procurement of equipment for training centres ($81,000) including tools, recovery machines and refrigerant identifiers. | 2010 |  | Investment
FIN | Canada | Refrigerant management plan formulation project | Individual | LAC | CHI | REF | 27 | TAS | 138 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-10-01 | 2001-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. RMP was submitted to the 35th EXCOM and has been approved. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling programme | RMP | LAC | CHI | REF | 35 | TAS | 147 | A | I | CFC | 88 | 88 | 0 |  | 2001-12-01 | 2006-08-01 | 2005-04-01 |  | 2009-03-01 | 2010-07-01 | 531620 | -30 | 531590 | 531590 | 100% | 0 |  | 0 | 53162 | 0 | 53162 | 0 |  | All the R&R equipment has been procured and distributed, is in use. All related training activities have been completed. Monitoring of use of equipment was completed in early 2009. Project completed in Feb. 2009 and last payment to Chile was made in April 2009. $30 were remaining and returned to MLF at 61st Meeting, thus financially closing the project. |  | 2001 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for technicians and establishment of refrigeration standards | RMP | LAC | CHI | REF | 35 | TRA | 150 | A | I |  | 43 | 43 | 0 |  | 2001-12-01 | 2002-09-01 | 2004-12-01 |  | 2006-12-01 | 2007-05-01 | 260000 | 0 | 260000 | 260000 | 100% | 0 |  | 0 | 33800 | 0 | 33800 | 0 |  | Refrigeration equipment purchased and distributed to training centres. 1650 technicians trained. Code/standard of good practices completed in July 2005. Retrofit demonstration strategy developed and demonstrations completed in 2006. |  | 2001 |  | Non-Inv.
FIN | Canada | Training programme for customs officers | Individual | LAC | COL | REF | 35 | TRA | 52 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2004-07-01 |  | 2006-08-01 | 2006-08-01 | 106150 | 0 | 106150 | 106150 | 100% | 0 |  | 0 | 13799 | 0 | 13799 | 0 |  | 300 customs officers trained and monitoring and evaluation completed by June 2005. However, one final activity, reproduction of training manual was completed only by August 2006. PCR submitted in 2006. |  | 2000 |  | Non-Inv.
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | ASP | CPR | FUM | 22 | DEM | 199 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-06-01 | 1999-06-01 |  | 1998-10-01 | 1998-10-01 | 145000 | 0 | 145000 | 145000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed |  | 1997 |  | Non-Inv.
CLO | Canada | Feasibility study to establish a refrigerant conservation programme in Sichuan Province | Individual | ASP | CPR | REF | 14 | TAS | 81 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  |  | 1997-06-01 | 58400 | -58400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Activities in Sichuan Province | Individual | ASP | CPR | SEV | 11 | TRA | 52 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-10-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Workshop held in October 1993 and approved by retroactive funding in September 1994. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | Canada | No-clean technology programme | Individual | ASP | CPR | SOL | 14 | TAS | 82 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  | 1994-11-01 | 1995-09-01 | 51100 | 0 | 51100 | 51100 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2008-01-01 | 2008-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 |  | 0 | 52000 | 0 | 52000 | 0 |  | First phase of R&R equipment shipped in May 2005. Public awareness activities initiated in 2005 are continuing and include the production of technical pamphlets, videos, TV commercials, education workshops etc.. 2nd phase of R&R equipment and retrofit tools delivered in November 2007. 3rd phase completed in January 2008. Note that target and consumption indicated under columns BB and BC are for 2005. |  | 2004 |  | Investment
FIN | Canada | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 32 | A | I | CFC | 30 | 30 | 0 |  | 2005-04-01 | 2008-01-01 | 2007-04-01 |  | 2011-06-01 | 2012-05-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  | 0 | 8060 | 0 | 8060 | 0 |  | Project completed in June 2011 but Canada was awaiting final financial report from Cuba. Funds spent principally on R&R training and provision of tools and materiasl for technicians. Final financial report received in May 2012. |  | 2005 |  | Investment
FIN | Canada | Project preparation for development of a refrigerant management plan | Individual | LAC | CUB | REF | 25 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1999-06-01 | 1999-01-01 |  | 1999-09-01 | 2000-09-01 | 22600 | 0 | 22600 | 22600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Although previous reports indicated all funds had been disbursed in 2002, US $2,600 were found to be left-over and were returned to the MLF. See letter to Sectretariat. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation and enforcement of regulations on ODSs | RMP | LAC | CUB | REF | 29 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  | 0 | 2600 | 0 | 2600 | 0 |  | Policy workshop held May 2002. ODS regulations updated. Project errouneously reported as completed in 2003. Completion officially reported by Cuba in 2004 |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practice | RMP | LAC | CUB | REF | 29 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 | 10400 | 0 |  | 2650 technicians trained. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for customs officers | RMP | LAC | CUB | REF | 29 | TRA | 13 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | 667 customs officers trained. ODS Import database system established. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling of CFC-12 in the MAC sector (amendment to the RMP) | RMP | LAC | CUB | REF | 30 | TAS | 15 | A | I | CFC | 8 |  | 0 |  | 2000-03-01 | 2001-11-01 | 2002-04-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project erroneously reported as completed in 2003. Additional (final) training took place in 2004. Insufficient data to determine ODP phase-out. However, RMP as a whole is deemed to have contributed to a reduction in the servicing sector of about 90 ODP |  | 2000 |  | Non-Inv.
TRF | Canada | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 35 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2008-12-01 |  |  | 2007-03-01 | 196871 | -196871 | 0 | 0 |  | 0 |  | 0 | 25593 | -25593 | 0 | 0 |  | Project was transferred to UNDP at ExCom 51 (March 2007). Therefore there is no planned date of completion. Progress report for 2007 will show adjustment of funding approved. |  | 2005 |  | Non-Inv.
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | GEO | FUM | 30 | TAS | 07 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-01-01 | 2004-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 2000 |  | Non-Inv.
FIN | Canada | Promoting compliance with the Montreal Protocol in countries with economies in transition (CEITs) | Individual | EUR | GEO | SEV | 27 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-03-01 |  | 2001-10-01 | 2002-06-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 180 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-02-01 | 2000-04-01 |  | 2001-07-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | English version of manual completed in April 2001. Printing and dissemination has been completed. |  | 1999 |  | Non-Inv.
FIN | Canada | Translation, in French and Spanish, of the approved manual on Customs Officer Training on Substances that Deplete the Ozone Layer | Individual | GLO | GLO | SEV | 32 | TAS | 213 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2001-07-01 |  | 2002-02-01 | 2002-03-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  | 0 | 1440 | 0 | 1440 | 0 |  | Translation of manual into Spanish and French completed in early 2002. Both manuals were printed and disseminated in 2002. Project Completed. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: national recovery and recycling programme | RMP | LAC | GUY | REF | 23 | TAS | 08 | A | I | CFC | 6.5 |  | 0 |  | 1997-11-01 | 1998-04-01 | 2000-12-01 |  | 2003-05-01 | 2003-05-01 | 73450 | 0 | 73450 | 73450 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completion Report submitted. |  | 1997 |  | Non-Inv.
TRF | Canada | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 41 | INV | 158 | A | I |  | 0 |  | 0 |  | 2003-12-01 |  | 2007-12-01 |  |  | 2004-12-01 | 350000 | -350000 | 0 | 0 |  | 0 |  | 0 | 45500 | -45500 | 0 | 0 |  | Project transferred to UNIDO. |  | 2003 |  | Non-Inv.
FIN | Canada | National halon management and banking programme | Halon Banking | ASP | IND | HAL | 32 | TAS | 278 | A | I | HAL | 197.2 | 197.2 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2007-03-01 | 2007-03-01 | 245700 | 0 | 245700 | 245700 | 100% | 0 |  | 0 | 24570 | 0 | 24570 | 0 |  | Halon reclamation facility established in 2003. Canadian component annd Australian component of project completed |  | 2000 |  | Investment
FIN | Canada | Initiative to help phase out the release of ODS by Asian SMEs | Individual | ASP | IND | SEV | 15 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1996-02-01 | 1996-02-01 | 109780 | 0 | 109780 | 109780 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | Canada | Project preparation for the phase-out of methyl bromide |  | LAC | JAM | FUM | 43 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2005-09-01 | 2005-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 1125 | 0 | 1125 | 0 |  | Project proposal completed in September 2005, submitted and approved at ExCom 47. |  | 2004 |  | Non-Inv.
FIN | Canada | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | JAM | FUM | 47 | TAS | 22 | A | I | MBR | 1.2 | 1.2 | 0 |  | 2005-11-01 | 2006-09-01 | 2007-12-01 |  | 2011-11-01 | 2013-08-01 | 55530 | -7162 | 48368 | 48368 | 100% | 0 |  | 0 | 7219 | 0 | 7219 | 0 |  | Project completed in November 2011 as reported to ExCom 65. Initally, $2,733 in project costs were identified as remaining upon closure and were returned to ExCom 67 in July 2012. However, in developing PCR, Canada identified another unspent of balance $4,429 for the project and returned this amount to ExCom 70, which was when the project was considered financially closed. |  | 2005 | 2009-04-01 | Investment
FIN | Canada | Terminal phase-out management plan for CFCs: training and recovery and recycling | One-off Phase-out | LAC | JAM | PHA | 37 | TAS | 16 | A | I | CFC | 57.5 | 57.5 | 0 |  | 2002-07-01 | 2002-09-01 | 2006-01-01 |  | 2006-03-01 | 2006-03-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 |  | 0 | 31200 | 0 | 31200 | 0 |  | All activities completed by end of 2005. Final monitoring reports received in March 2006. Jamaica provided comprehensive report on R&R activities. |  | 2002 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of trainers in refrigeration and certification of technicians | RMP | LAC | JAM | REF | 27 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-10-01 |  | 2000-08-01 | 2001-03-01 | 50850 | 0 | 50850 | 50850 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Phase 1 (train-the trainer) completed 7-11 June 1999. Phase 2 completed in June 2000. Monitoring and evaluation completed August 2000. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: customs officers training programme | RMP | LAC | JAM | REF | 27 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-10-01 |  | 2001-11-01 | 2001-12-01 | 54240 | 0 | 54240 | 54240 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Legislation finalized in July 99. Phase 1 -train-the-trainer- completed June 2000, Phase 2 completed in Nov. 2000, Monitoring and evaluation completed in Nov. 2001. |  | 1999 | 2001-12-01 | Non-Inv.
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | AFR | KEN | FUM | 26 | DEM | 20 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-05-01 | 1999-12-01 |  | 2007-06-01 | 2007-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998 |  | Non-Inv.
FIN | Canada | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenada, Guyana, Jamaica, and Trinidad and Tobago) | Halon Banking | LAC | LAC | HAL | 26 | TAS | 28 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-10-01 | 2000-06-01 |  | 2005-12-01 | 2006-03-01 | 177410 | 0 | 177410 | 177410 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Establishment of halon clearing house in Trinidad and promotional brochure completed in 2005. All 6 countries finished their halon surveys. All project activities completed. Last payment to UNEP to reimburse University of West Indies for halon clearing |  | 1998 |  | Non-Inv.
FIN | Canada | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 38 | A | I |  | 0 | 0 | 0 |  | 2007-03-01 | 2008-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 6500 | 0 | 6500 | 0 |  | This project is implemented by UNEP on behalf of Canada. A study on illegal tradeof ODS in the region was completed in June 2009 and presented to participants to UNEP LAC Network meeting in october 2009. Countries opted to test the informal Prior Informed Consent (iPIC) form as a tool to control illegal trade of ODS. Work initiated at the end of the year to complete iPIC forms for all participating countries. This last activity of the project was completed by the end of 2010. |  | 2007 | 2009-12-01 | Non-Inv.
FIN | Canada | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 122 | A | I | MBR | 18.2 | 18.2 | 0 |  | 2004-04-01 | 2006-09-01 | 2006-10-01 |  | 2009-03-01 | 2009-04-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 24700 | 0 | 24700 | 0 |  | This project was implemented by UNDP on behalf of Canada. Project was nearly completed by end of 2008, with 10 companies successfully completing alternative fumigations techniques. Remaining activities for 2009 included preparing a report focused on lessons learned from the project and finalizing financial reporting. These were completed by April 2009. |  | 2004 | 2008-06-01 | Investment
FIN | Canada | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 138 | A | I | MBR | 20 | 20 | 0 |  | 2008-04-01 | 2009-09-01 | 2014-03-01 |  | 2012-03-01 | 2012-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 58527 | 0 | 58527 | 0 |  | Project was completed in March 2012 and financially closed in April 2012. |  | 2008 |  | Investment
TRF | Canada | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 149 | A | I | MBR | 0 |  | 0 |  | 2010-04-01 |  | 2011-04-01 |  |  | 2012-04-01 | 500000 | -500000 | 0 | 0 |  | 0 |  | 0 | 58527 | -58527 | 0 | 0 |  | Project was transferred to UNIDO at 63rd ExCom meeting. No expenditures will thus be made by Canada. |  | 2010 |  | Investment
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | MOL | FUM | 30 | TAS | 06 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-04-01 | 2004-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2004. PCR submitted |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP including training programmes for refrigeration technicians and customs officers, assistance in the design of policies and regulations and recovery and recycling | RMP | LAC | STK | REF | 24 | TAS | 04 | A | I | CFC | 2 | 2 | 0 |  | 1998-03-01 | 1999-05-01 | 2001-03-01 |  | 2006-03-01 | 2006-03-01 | 124300 | 0 | 124300 | 124300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | R&R workshop and customs training were delayed because legislation not yet place. However legislation was adopted in early 2004 and R&R project was completed. Phase I Customs Training also implemented. Final reports by country received in February 2006, |  | 1998 |  | Non-Inv.
FIN | Canada | Project preparation for a TPMP |  | LAC | STL | PHA | 48 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 | 2008-07-01 | 30000 | -7000 | 23000 | 23000 | 100% | 0 |  | 0 | 3900 | -910 | 2990 | 0 |  | TPMP proposal completed and submitted in April 2007 for ExCom 52. Not all funds were used. Remaining funds returned to Fund. |  | 2006 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (first tranche) | Multi-Year | LAC | STL | PHA | 52 | INV | 12 | A | I | CFC | 0 |  | 0 |  | 2007-07-01 | 2007-09-01 | 2009-07-01 |  | 2010-03-01 | 2011-07-01 | 156000 | -504 | 155496 | 155496 | 100% | 0 |  | 0 | 20280 | -10617 | 9663 | 0 |  | R&R equipment and tools delivered in March 2008 and distributed. Technicians and customs officers training were undertaken through 2008. Legal framework for R&AC Association and revised MP regulations was completed. A code of good practices in Refrigeration has been finalised. In 2009, additional training for technicians and customs officers took place. Project was completed in March 2010 with $504 unspent was returned to the Fund, along with $10,617 in unspent support costs, as noted at ExCom 64 in July 2011. |  | 2007 |  | Investment
FIN | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (second tranche) | Multi-Year | LAC | STL | PHA | 56 | INV | 15 | A | I | CFC | 1.2 | 1.2 | 0 |  | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2012-03-01 | 2013-08-01 | 49000 | -1039 | 47961 | 47961 | 100% | 0 |  | 0 | 6370 | -135 | 6235 | 0 |  | Project completed in March 2012. 109 technicians and 85 customs officers trained, equipment purchased and distributed to workshops, and clearing house established for unwanted ODS. A balance of $1,039.16 in project costs and $135 in support cost were remaining and returned to the Fund at 70th meeting, which was when project was considered financially closed. |  | 2008 |  | Investment
FIN | Canada | Implementation of the RMP | RMP | LAC | STL | REF | 23 | TAS | 04 | A | I | CFC | 3 | 3 | 0 |  | 1997-11-01 | 1998-03-01 | 2000-12-01 |  | 2003-12-01 | 2003-12-01 | 146900 | 0 | 146900 | 146900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | All activities completed. Project Completion Report is currently being drafted. |  | 1997 |  | Non-Inv.
FIN | Canada | Preparation of update of refrigerant management plan | Individual | LAC | STL | REF | 35 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-07-01 |  | 2003-11-01 | 2003-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 |  | 0 | 975 | 0 | 975 | 0 |  | RMP Update was completed and project was submitted in Nov. 2003. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP update | RMP Update | LAC | STL | REF | 41 | TAS | 08 | A | I |  | 7.1 | 7.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2007-05-01 | 2008-12-01 | 73450 | -122 | 73328 | 73328 | 100% | 0 |  | 0 | 9549 | -16 | 9533 | 0 |  | Project completed. 71 refrigeration technicians trained. Public service announcements were developed and broadcasted. Retrofit demonstration workshops concluded, including demonstrations of AC and vehicle retrofits. R&R equipment distributed. Though financial completion was previously reported to be May 2007, it was subsequently found that $122 were remaining. This amount, plus $16 in support costs, is to be returned to the Fund at the 58th ExCom Meeting. |  | 2003 |  | Non-Inv.
CLO | Canada | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 49 | TAS | 19 | A | I | MBR | 0.1 |  | 0 |  | 2006-07-01 |  | 2008-01-01 |  |  | 2009-07-01 | 30000 | -30000 | 0 | 0 |  | 0 |  | 0 | 3900 | -3900 | 0 | 0 |  | Canada will ask for cancellation of project at 58th meeting and return all related funds. Country NOU has agreed to cancellation as it has not been possible for government to sign agreement for over 18 months. |  | 2006 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | TAS | 47 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2008-01-01 | 2007-11-01 |  | 2010-07-01 | 2011-07-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 |  | 0 | 20800 | -9120 | 11680 | 0 |  | All project activities, including training and establishment of collaboration with enforcement, had been completed. Final report from NOU received. $9,120 remaining in support costs were returned to Fund, as noted at ExCom 64 in July 2011. |  | 2006 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | TAS | 51 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-03-01 | 2011-03-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  | 0 | 5460 | 0 | 5460 | 0 |  | Activities initiated in september 2009. 340 technicians trained. organization of 3 meetings with enforcement officials. Efforts to implement the technician certification scheme continued throughout the year. The online licensing system was implemented and one training workshop was held with stakeholders. Final training held in first quarter of 2011 and project completed by end of March 2011. $2,100 in support costs were erroneously reported as unspent in previous report and were in fact spent. |  | 2008 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-Year | LAC | URU | PHA | 60 | TAS | 53 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Activities were rapidly completed as they consisted mainly of 4 training workshops on good practices and strengthening of the certification system. Project completed by end of 2011 and remaining balance paid by Canada in April 2012 after final progress and expenditure reports were submitted. |  | 2010 |  | Investment
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 |  | Non-Inv.
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | Non-Inv.
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | Non-Inv.
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 |  | Non-Inv.
COM | Czech Republic | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) |  | EUR | EUR | DES | 65 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2012-11-01 |  | 2013-05-01 |  | 35000 | 0 | 35000 | 29410.27 | 84.03% | 5589.73 | 0 | 0 | 4550 | 0 | 3823.3351 | 726.6649 | 0 | Project preparation was completed in May 2013 and project proposal approved by ExCom 69. | Preparation project completed. | 2011 |  | 2011 | N.a.
FIN | Czech Republic | Regional network for 10 article 5 countries in Eastern Europe and Central Asia (jointly implemented with Hungary, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 58487 | 0 | 58487 | 58487 | 100% | 0 | 0 | 0 | 7603 | 0 | 7603 | 0 | 0 | Financially completed. | Financially completed. | 2003 |  | 2003 | N.a.
FIN | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Multi-Year | EUR | EUR | SEV | 57 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 | 2013-12-01 | 80500 | 0 | 80500 | 80500 | 100% | 0 | 0 | 0 | 10465 | 0 | 10465 | 0 | 0 | Financially completed. | Financially completed. | 2009 |  | 2009 | N.a.
COM | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Multi-Year | EUR | EUR | SEV | 60 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-04-01 |  | 2012-10-01 |  | 80500 | -2885 | 77615 | 76676.1 | 98.79% | 938.9 | 0 | 0 | 10465 | -375 | 9967.9424 | 122.0576 | 0 | Completed in October 2012. | Completed in October 2012. | 2010 |  | 2010 | N.a.
FIN | Denmark | Establishment of a CFC recycling centre at Zhejiang Donggyang Chemical Factory |  | ASP | CPR | REF | 17 | TAS | 130 | N | I |  | 20 |  |  |  | 1995-07-01 | 1996-10-01 | 1996-07-01 | 1998-12-01 | 1998-12-01 |  | 205000 | -43947 | 161053 | 161053.25 | 100% | -0.25 |  | 0 |  |  |  | 0 |  | Completed. Project Document signed in March 1996. Procurement comtract initialed in August 1996 but contract was not signed until 1997. Major delay caused by disagreement on contractual terms. Building modification work completed by enterprise in May 1998 and equipment delivered and installed in June 1998. A seminar for evaluation and dissemination of work experience was held 15-16 December 1998. All project activities were completed in December 1998. More than 50 tons of CFC has been recovered. A few tons of CFC had further been recycled at the reclaim station. |  |  | 1996-12-01
TRF | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 23 | TRA | 04 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-01-01 | 1999-12-01 |  |  | 2000-03-01 | 93490 | -93490 | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | Project transferred to UNEP at ExCom 30
FIN | Finland | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 184 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2001-11-01 | 2002-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1999 | 2001-06-01
FIN | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | NAM | REF | 20 | TRA | 03 | A | I | CFC | 5.4 | 5.4 | 0 |  | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-10-01 | 1999-10-01 | 103440 | 0 | 103440 | 103440 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1997
FIN | Finland | Implementation of the RMP: assistance in the design of policies and regulations | Individual | LAC | NIC | REF | 25 | TAS | 06 | A | I | CFC | 12.8 |  | 0 |  | 1998-07-01 | 2001-09-01 | 2000-07-01 |  | 2005-12-01 | 2009-07-01 | 225430 | -76855 | 148575 | 148575 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1998
FIN | Finland | Implementation of the RMP: monitoring and evaluation of the RMP | Individual | LAC | PAN | REF | 29 | TAS | 11 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2008-12-01 |  | 33000 | -18690 | 14310 | 14310 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. |  | 2001
FIN | Finland | Implementation of the RMP: training programme for custom officers | Individual | LAC | PAN | REF | 29 | TRA | 12 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2003-05-01 | 2001-06-01 |  | 2007-12-01 |  | 70000 | -34022 | 35978 | 35978 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Balances to be returned after all pending payments have been recorded |  | 2001 | 2002-12-01
ONG | France | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) | Individual | AFR | AFR | DES | 68 | TAS | 41 | A | I | CFC | 0 |  | 0 |  | 2012-12-01 | 2013-05-14 | 2013-12-01 | 2015-12-01 |  |  | 80000 | 0 | 80000 | 19232 | 24.04% | 60768 | 31180 | 40000 | 10400 | 0 | 2500 | 7900 | 4053 | The French bi-lateral contribution is implemented through UNIDO. Agreement signed in Feb 2013; all funds have been transferrerd to UNIDO for the implementation. | The project’s Technical Report was delivered in February 2015 after coordinating the data collection exercise by the national experts and NOUs and working together with a group of international experts. Due to the length and complexity, it was agreed by France and UNIDO that an International Expert would be recruited to Prepare a Report for Policymakers based on the information from the Technical Report. Unfortunately, the selection and recruitment of the International Expert with an adequate background took longer than anticipated, so the following activities will be implemented sequentially and completed in 2015: (-) In-depth review of the Report for Policymakers by France and UNIDO in order to obtain the document’s final version; (-) Translation of the Report for Policymakers into French; (-) Share the Technical Report and the Report for Policymakers with all five participating countries, asking them to provide their comments (with a focus on the Report for Policymakers); (-) Presentation of the Report for Policymakers at the Joint African Network Meeting to be organized by UNEP for both French-speaking and English-speaking countries; (-) If needed, correction of the Technical Report and the Report for Policymakers after presentation at the Network Meeting (we do not see this step likely); (-) Submission of the Technical Report and the Report for Policymakers as Annexes to an ExCom document to be submitted jointly by France and UNIDO; we want to do this for ExCom 75. Delays in 2014 have mainly been caused by the need of undertake several iterations between the Internationl Experts in charge of preparing the Technical Report and the Report for Policymakers and the national consultants in charge of the data collection, given the difficulties faced by the latter to collect all information required for the preparation of the Technical Report. Difficulties in collecting accurate and comprehensive information on the field are a recurring problem. In fact, this has been completely impossible in one of the participating countries (Central African Republic) due to the situation in the country. Difficulties have also been encountered in Guinea Conakry due to the impact of the Ebola outbreak in the mobility of the national expert in charge of the data collection.
FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | AFR | AFR | REF | 32 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-07-01 | 2002-07-01 |  | 2002-12-01 | 2002-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. Final report sent to the Secretariat in Mai 2003.
ONG | France | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 36 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2008-10-01 | 2009-09-01 | 2015-12-01 |  |  | 360000 | 0 | 360000 | 290330 | 80.65% | 69670 | 0 | 60000 | 46800 | 0 | 37742.9 | 9057.1 | 0 | The French bi-lateral contribution is implemented through UNIDO (initial agreement was signed in Feb 2008) and external funding is provided by the French Global Environment Facility. This project continues to encounter delays, in 2014 partly because the extension of the two financial agreements between AFD/FFEM and UNIDO was administratively completed end of February 2014 and the second tranches under both agreements were transferred to UNIDO account only in March 2014, the third payment being made in October. As far as the project is concerned, the relevant documents have been collected from the beneficiaries in Senegal and Nigeria. There was a field mission to verify the CFC chillers in Haj Abdalla Spinning Factory at the end of March 2014. Three old York CFC chillers were found and verified. Based on this new information, the work plan for Sudan has been adjusted to include this Haj Abdalla factory as the beneficiary. | The funds providing from the bilateral contribution and the last tranche of the related FFEM project are earmarked for procurement of 5 chillers in Sudan. The invitation to bids was published in January 2015 on anticipation that the FFEM tranche would arrive by the time the bidders submitted their offers. Due to administrative problems in the UNIDO electronic system (SAP) the request for last FFEM tranche was submitted only in May 2015 and the funds have only been available end of July 2015, after clarifications and supporting documents were provided to FFEM. Bidders that submitted offers for the supply of chillers in Sudan have been contacted about the validity of their submitted offers. The award of contract for the supply of chillers in Sudan is expected to occur in September and the initial payment(s) of the contract will consume the French bilateral contributions while further payments will be paid from the FFEM contribution. In that way the project will be completed by December 2015 as requested by the ExCom decision.
FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | AFR | AFR | SEV | 17 | TRA | 11 | A | D |  | 0 |  | 0 |  | 1995-07-01 | 1995-12-01 | 1996-01-01 |  | 1996-02-01 | 1996-02-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Exécuté en février 1996 en coopération ave le PNUE. Project completed.
CLO | France | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 39 | A | I | CFC | 0 |  | 0 |  | 2007-11-01 |  | 2009-11-01 |  |  | 2014-12-01 | 75000 | -75000 | 0 | 0 |  | 0 |  | 0 | 9750 | 0 |  | 9750 |  | Cancelled by decision 70/8/(c). |  |  | 2010-12-01
ONG | France | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 72 | DEM | 78 | A | I | CFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2017-06-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 |  | 10000 | 32500 | 0 | 0 | 32500 |  | The French contribution is implemented in cooperation with UNIDO. Agreement signed in March 2015 and all funds have been transferred to UNIDO for implementation. Project approved at the 72nd Meeting (May 2014) on the understanding that no further funds would be available for Algeria for any ODS disposal projects in future. The project encounters difficulties because the establishment of a working group with representatives of NOU Algeria, Group Lafarge and UNIDO was not possible due to the lack of response of the NOU for the nomination of their representative(s). | There are continued attempts to have the working group established and operational. However the NOU response is still not good.
FIN | France | Survey for halon banking management plan in West Asia (Bahrain, Lebanon, Qatar and Yemen) |  | ASP | ASP | HAL | 28 | TAS | 29 | N | D |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2000-02-01 |  | 2000-02-01 | 2002-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with Germany) |  | ASP | ASP | HAL | 30 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2004-04-01 | 2001-10-01 |  | 2004-12-01 | 2005-01-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 |  | 0 | 5875 | 0 | 5875 | 0 |  | Project completed. Final payment to GTZ in 2004.
COM | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | INV | 17 | A | I | CFC | 0.7 | 0.7 | 0 |  | 2008-07-01 | 2010-06-01 | 2009-12-01 |  | 2011-09-01 |  | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Project completed.
COM | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | INV | 19 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2010-07-01 | 2011-05-01 | 2011-07-01 |  | 2011-12-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: development and implementation of a tax/incentive programme |  | AFR | CAF | REF | 34 | TAS | 10 | N | I |  | 0.3 | 0.1 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-01 | 2009-04-01 | 5500 | -3904 | 1596 | 1596 | 100% | 0 |  | 0 | 715 | -508 | 207 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom)
FIN | France | Implementation of the RMP: monitoring the activities of the RMP project, including registration of refrigeration service technicians, distributors and importers of CFCs |  | AFR | CAF | REF | 34 | TAS | 11 | A | I |  | 1.5 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-01 | 2009-04-01 | 26250 | -8986 | 17264 | 17264 | 100% | 0 |  |  | 3413 | -1168 | 2245 | 0
FIN | France | Implementation of the RMP: training programme for customs officers |  | AFR | CAF | REF | 34 | TRA | 08 | N | I |  | 4.4 | 2.9 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-01 | 2009-04-01 | 77440 | -26940 | 50500 | 50500 | 100% | 0 |  | 0 | 10067 | -3502 | 6565 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
FIN | France | Implementation of the RMP: train the trainers programme for refrigeration technicians in good management practices and a training programme to address technicians in the informal sector |  | AFR | CAF | REF | 34 | TRA | 09 | A | I |  | 3.4 | 2.4 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-01 | 2009-04-01 | 60900 | -17759 | 43141 | 43141 | 100% | 0 |  | 0 | 7917 | -2309 | 5608 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
FIN | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 100% | 0 |  | 0 | 1500 | -963 | 537 | 0 |  | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
FIN | France | Project preparation of phase out of use of ODS solvent in production of parts working in high voltage conditions |  | ASP | CPR | SOL | 29 | PRP | 327 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-07-01 | 2000-12-01 |  | 2002-09-01 | 2002-09-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 |  | 0 | 1375 | 0 | 1375 | 0 |  | Project completed.
TRF | France | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 27 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-06-01 | 200000 | -119681 | 80319 | 80319 | 100% | 0 |  | 0 | 26000 | -15559 | 10441 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
TRF | France | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 31 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-06-01 | 200000 | -200000 | 0 | 0 |  | 0 |  | 0 | 26000 | -26000 | 0 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project was transferred to UNDP in Apr 06.
FIN | France | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ETH | PHA | 51 | PRP | 17 | A | I | CFC | 0 |  | 0 |  | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-07-01 | 2010-07-01 | 30000 | -12400 | 17600 | 17600 | 100% | 0 |  | 0 | 3900 | 0 | 2288 | 1612 |  | The French contribution was implemented by GTZ-Proklima. The survey for the preparation of the TPMP has been completed but the continued lack of regulations prevents Ethiopia from submitting the TPMP. Funds will be returned to MLF.
FIN | France | Implementation of the RMP update | RMP Update | AFR | ETH | REF | 44 | TAS | 14 | A | I | CFC | 12.3 |  | 0 |  | 2004-12-01 | 2005-11-01 | 2007-12-01 |  | 2010-12-01 | 2012-04-01 | 91300 | -40988.89 | 50311.11 | 50311 | 100% | 0.11 |  | 0 | 11869 | -5329 | 6540 | 0 |  | The French contribution was implemented by GIZ-Proklima. The ODS regulations were not approved despite all possible effort. However customs trainings was conducted on the use of identifiers. This project was stopped because of lack of progress.
FIN | France | Technical assistance in air conditioning |  | AFR | GHA | REF | 27 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2001-04-01 | 2001-04-01 | 31500 | -5121 | 26379 | 26379 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le Ghana a présenté avec l'aide du PNUD un projet utilisant les 50% restant dans le cadre du Plan de Gestion des Réfrigérants. Il n'est donc plus possible de présenter de projets avant 2007 dans ce pays.
FIN | France | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 374 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2008-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GIZ. All activities planned under this tranche have been completed. |  |  | 2007-04-01
FIN | France | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 387 | A | I | CTC | 0 |  | 0 |  | 2005-04-01 | 2008-01-01 | 2006-04-01 |  | 2009-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009. |  |  | 2008-04-01
FIN | France | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 399 | A | I | CTC | 0 |  | 0 |  | 2006-07-01 | 2009-01-01 | 2007-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | France | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 409 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2009-01-01 | 2008-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | France | Projects preparation and technical assistance in the halon sector |  | ASP | IRA | HAL | 23 | PRP | 32 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 1999-07-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
TRF | France | Halon management programme | Halon Banking | ASP | IRA | HAL | 28 | TAS | 49 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2003-08-01 |  |  | 2011-08-01 | 511175 | -397500 | 113675 | 113675 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The project transfer to UNIDO was acted by the 63rd ExCom meeting.
FIN | France | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 163 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2011-05-01 | 1006620 | 0 | 1006620 | 1006620 | 100% | 0 |  | 0 | 110728 | 0 | 110728 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 171 | A | I | CFC | 424.5 | 94.3 | 0 |  | 2005-04-01 | 2007-04-01 | 2007-04-01 |  | 2010-06-01 | 2012-04-01 | 500000 | -147981 | 352019 | 352019 | 100% | 0 |  | 0 | 55000 | 0 | 38722 | 16278 |  | The French contribution was implemented by GIZ-Proklima. Project completed. | Expenses data have been corrected.
FIN | France | Project preparation/technical assistance for MAC recycling and training in good servicing practices |  | ASP | IRA | REF | 20 | PRP | 18 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1997-08-01 | 1997-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Set up of a national programme of recovery and recycling CFC-12 (pilot project in Tehran) |  | ASP | IRA | REF | 23 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1999-10-01 | 1998-12-01 |  | 2004-12-01 | 2004-12-01 | 345923 | -103154.97 | 242768.03 | 242768 | 100% | 0.03 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed; balance returned at the 57th meeting.
FIN | France | Conversion to non-CFC facilities of 4 companies producing cars and wagons equipped with MAC-umbrella project |  | ASP | IRA | REF | 24 | INV | 34 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 2000-02-01 | 1999-04-01 |  | 2002-06-01 | 2008-09-01 | 138600 | -35471 | 103129 | 103129 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-06-01
FIN | France | Small and medium enterprises study |  | ASP | IRA | SEV | 26 | TAS | 36 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 2002-05-01 | 1999-12-01 |  | 2005-04-01 | 2005-04-01 | 75000 | -55000 | 20000 | 20000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Closed as per decision 45/12, financial closure to be finalised. |  |  | 2002-12-01
FIN | France | Project preparation and technical assistance in the solvent sector |  | ASP | IRA | SOL | 23 | PRP | 23 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to ODS-free technology at Dorcharkh Company |  | ASP | IRA | SOL | 28 | INV | 48 | A | I | CTC | 11 | 11 | 0 |  | 1999-07-01 | 2001-08-01 | 2001-08-01 |  | 2002-12-01 | 2008-10-01 | 165140 | 0 | 165140 | 165140 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project completed. 5% support costs mentioned by the financing agreement were included in the allocated amount.
FIN | France | Refrigeration management plan preparation |  | AFR | IVC | REF | 21 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1998-03-01 | 1998-03-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
CLO | France | Implementation of the RMP | RMP | AFR | IVC | REF | 24 | TAS | 10 | A | I | CFC | 24.8 |  | 0 |  | 1998-03-01 | 1999-10-01 | 2000-04-01 |  |  | 2009-04-01 | 227650 | -196214 | 31436 | 31436 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
FIN | France | Documentary on traffic in second-hand refrigerators |  | AFR | IVC | REF | 27 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-04-01 | 2000-06-01 |  | 1999-07-01 | 1999-07-01 | 12000 | -2381 | 9619 | 9619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
TRF | France | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 37 | INV | 17 | A | I | CFC | 0 |  | 0 |  | 2002-07-01 |  | 2006-08-01 |  |  | 2009-04-01 | 1000000 | -1000000 | 0 | 0 |  | 0 |  | 0 | 100000 | -100000 | 0 | 0 |  | Project transferred to UNIDO per decision 57/xx(f).
FIN | France | Project preparation for projects in commercial refrigeration production facilities |  | AFR | IVC | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 1999-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 15000 | -1636 | 13364 | 13364 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. A study on a replacement programme for centrifugal chillers was completed in 2002. It was followed by a proposal on the phase out of CFC emissions in centrifugal chillers through energy related activities. Balance returned at the 57th ExCom.
CLO | France | Implementation of the refrigerant management plan: monitoring the activities of the RMP and set up of an import/export licensing system | RMP | AFR | IVC | REF | 37 | TAS | 16 | A | I | CFC | 188.7 |  | 0 |  | 2002-07-01 |  | 2004-08-01 |  |  | 2009-04-01 | 49500 | -49500 | 0 | 0 |  | 0 |  | 0 | 4950 | -4950 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
FIN | France | Technical assistance in air-conditioning |  | ASP | JOR | REF | 27 | TAS | 46 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-06-01 | 2002-06-01 | 42000 | -31575 | 10425 | 10425 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le rapport d'enquête a été achevé. D'un commun accord avec le Gouvernement jordanien, le projet sera transféré à la Banque Mondiale. |  |  | 2001-11-01
FIN | France | Terminal CFCs phase-out management plan (first tranche) | Multi-Year | AFR | KEN | PHA | 44 | INV | 37 | A | I | CFC | 53 | 53 | 0 |  | 2004-12-01 | 2007-08-01 | 2005-12-01 |  | 2008-05-01 | 2008-07-01 | 215914 | 0 | 215914 | 215914 | 100% | 0 |  | 0 | 28069 | 0 | 28069 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed. |  |  | 2007-06-01
FIN | France | Terminal CFCs phase-out management plan (second tranche) | Multi-Year | AFR | KEN | PHA | 54 | INV | 44 | A | I | CFC | 20 |  | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-03-01 | 2012-09-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 |  | 0 | 38610 | 0 | 38610 | 0 |  | The French contribution was implemented by GTZ-Proklima. 2 trainers from local colleges were trained in a regional hydrocarbon training course in Namibia. Commercial refrigeration installations are being converted under the verification scheme. The project is completed.
FIN | France | Terminal CFCs phase-out management plan (third tranche) | Multi-Year | AFR | KEN | PHA | 57 | INV | 46 | A | I | CFC | 65.8 | 65.2 | 0 |  | 2009-04-01 | 2009-06-01 | 2010-03-01 |  | 2012-03-01 | 2012-12-01 | 179086 | -138033 | 41053 | 41053 | 100% | 0 |  | 0 | 23281 | 0 | 5337 | 17944 |  | The French contribution was implemented by GTZ-Proklima. The project is completed.
FIN | France | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | KEN | PHA | 66 | INV | 53 | A | I | HCFC | 3.1 | 19.2 | 0 |  | 2012-04-01 | 2012-05-01 | 2014-04-01 |  | 2014-07-01 | 2014-09-01 | 257500 | 0 | 257500 | 257500 | 100% | 0 |  | 0 | 31186 | 0 | 31186 | 0 |  | The French contribution is implemented by GIZ. Awareness activities were conducted in order to support NOU efforts for greater visibility of the ozone project in Kenya, a painting competition was held for children and the winning painting was made into a poster for distribution to the stakeholders. NEMA, the enforcement authority conducted a fact finding and enforcement trainings with its officers at the border posts to enable overcoming of the problems identified through the verification excercise. | Project completed
ONG | France | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | KEN | PHA | 72 | INV | 55 | A | I | HCFC | 5.2 | 27.5 | 0 |  | 2014-05-01 | 2014-07-01 | 2015-05-01 | 2015-10-01 |  |  | 200000 | 0 | 200000 | 176350 | 88.17% | 23650 |  | 23650 | 24222 | 0 | 21357.7485 | 2864.2515 |  | The NOU received 10 recovery units which were distributed for a token fee to local companies. 2 additional trainings of trainers were conducted on best practices and safe handling of refrigerants. 6 trainings targetting 123 technicians have been conducted. NEMA support on enforcement and revisiting enforcement prior to next verification excercise. | The 3rd tranche request was delayed due to lack of verification report required prior to submission request. However the verification report is now completed to allow for tranche request to be submitted at the 75th ExCom meeting. In addition the country has already conducted 4 technical trainings in 2015.
FIN | France | Project preparation for a terminal phase-out management plan for CFCs |  | ASP | LAO | PHA | 49 | PRP | 16 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2007-05-01 | 2007-07-01 |  | 2008-02-01 | 2009-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Project completed. TPMP approved by 54th ExCom.
COM | France | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | LAO | PHA | 54 | INV | 18 | A | I | CFC | 0 |  | 0 |  | 2008-04-01 | 2010-05-01 | 2010-03-01 |  | 2013-05-01 |  | 181500 | 0 | 181500 | 181500 | 100% | 0 |  |  | 23595 | 0 | 23595 | 0 |  | The project is competed. Implementation of tranches 1 and 2 were binded in order to accelerate the pace of implementation. It is to be noted that following an incident in the management of the funds, the agency support costs were in fact used for the project activities.
COM | France | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | LAO | PHA | 61 | INV | 21 | A | I | CFC | 6.5 |  | 0 |  | 2010-07-01 |  | 2011-07-01 |  | 2013-05-01 |  | 138500 | 0 | 138500 | 138500 | 100% | 0 |  | 0 | 18005 | 0 | 18005 | 0 |  | The project is competed. Implementation of tranches 1 and 2 were binded in order to accelerate the pace of implementation. It is to be noted that following an incident in the management of the funds, the agency support costs were in fact used for the project activities.
FIN | France | Implementation of the RMP: recovery and recycling, training and demonstration project (complement) | RMP | ASP | LAO | REF | 34 | TAS | 06 | N | I | CFC | 1.2 |  | 0 |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-01 | 40800 | 0 | 40800 | 40800 | 100% | 0 |  | 0 | 2040 | 0 | 2040 | 0 |  | Lao has reported an error concerning this activity in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). With the 2 budgets combined, 3 sets of R&R equipment have been bought and handed over to three institutions, 21 sets of basic servicing equipment were bought, and the training of trainers included sessions on best practices, MAC and R&R. Furthermore, a recovery and recycling machine was built locally as part of a university training course. The project is completed.
FIN | France | Implementation of the RMP: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II) | RMP | ASP | LAO | REF | 34 | TRA | 03 | N | I |  | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-01 | 78750 | 0 | 78750 | 78750 | 100% | 0 |  | 0 | 10237 | 0 | 10237 | 0 |  | Lao had reported an error concerning the training of technicians in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). The amount of expenses made for these 2 lines were inserted under LAO/REF/34/TRA/03. The final training was carried out in April 2009. The project is completed.
FIN | France | Implementation of the RMP: customs training programme | RMP | ASP | LAO | REF | 34 | TRA | 04 | N | I | CFC | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2003-08-01 |  | 2010-06-01 | 2012-12-01 | 81542 | -11242 | 70300 | 70300 | 100% | 0 |  | 0 | 10600 | -1461 | 9139 | 0 |  | Project completed. | Balance return in March 2013
FIN | France | Technical assistance for country programme and refrigerant management plan preparation |  | ASP | LAO | SEV | 27 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-12-01 |  | 2001-02-01 | 2001-02-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Le Plan de gestion des réfriférants a été approuvé en même temps que le Programme de pays à la 34ème réunion du Comité Exécutif. Project completed.
FIN | France | Projects preparation and technical assistance in the foam sector |  | ASP | LEB | FOA | 19 | TAS | 07 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-08-01 | 1996-09-01 | 20000 | -495 | 19505 | 19505 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Conversion to non-CFC technology in the manufacture of polyurethane flexible molded foam at Meuble Mode Sarl |  | ASP | LEB | FOA | 20 | INV | 10 | A | I | CFC | 9 | 9 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-03-01 | 55700 | -235 | 55465 | 55465 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Furniture and Plastic Sarl (FAP) |  | ASP | LEB | FOA | 20 | INV | 11 | A | I | CFC | 28 | 28 | 0 |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 2000-09-01 | 2000-12-01 | 128700 | 0 | 128700 | 128700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Plastiflex Sarl |  | ASP | LEB | FOA | 20 | INV | 12 | A | I | CFC | 42 | 42 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-03-01 | 1999-08-01 | 154000 | -7224 | 146776 | 146776 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Merza Foam Sarl |  | ASP | LEB | FOA | 20 | INV | 13 | A | I | CFC | 45 | 45 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-04-01 | 108172 | -950 | 107222 | 107222 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of rigid foam (sandwich panels) at Kilzi and Co. Sarl |  | ASP | LEB | FOA | 20 | INV | 14 | A | I | CFC | 22.5 | 22.5 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-11-01 | 1999-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Fomaco Sarl |  | ASP | LEB | FOA | 20 | INV | 15 | A | I | CFC | 26 | 26 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-09-01 | 1999-12-01 | 154000 | -2258 | 151742 | 151742 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Project preparation for the commercial refrigeration sector |  | ASP | LEB | REF | 20 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation to establish a CFC and HCFC recovery and recycling centre |  | ASP | LEB | REF | 20 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion of refrigeration industrial facilities |  | ASP | LEB | REF | 23 | INV | 22 | A | I | CFC | 10.4 | 10.4 | 0 |  | 1997-11-01 | 1999-01-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 166605 | -13443 | 153162 | 153162 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | ASP | LEB | REF | 23 | TAS | 21 | A | I | CFC | 62 |  | 0 |  | 1997-11-01 | 2010-04-15 | 1998-12-01 |  | 2011-03-01 | 2012-10-01 | 425289 | 0 | 425289 | 425289 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | ASP | LEB | REF | 23 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1999-06-01 |  | 2000-10-01 | 2000-12-01 | 52668 | 0 | 52668 | 52668 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en octobre 2000
FIN | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 29 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-08-01 | 2002-01-01 | 45750 | -20966 | 24784 | 24784 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The study was completed and a draft report was handed over to the NOU (08/2001). Remaining activities could be carried out at the same time than the R&R project.Project completed.
FIN | France | Implementation of the RMP: set up a national recovery and recycling network |  | AFR | MAG | REF | 29 | TAS | 05 | A | I | CFC | 13.9 | 10.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2004-08-01 | 2005-01-01 | 82700 | -11895 | 70805 | 70805 | 100% | 0 |  | 0 | 4135 | -595 | 3540 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: training of personnel in charge of control and monitoring of imports of ODS |  | AFR | MAG | REF | 29 | TRA | 02 | A | I | CFC | 4.4 | 3.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2003-06-01 | 2005-01-01 | 26000 | -851 | 25149 | 25149 | 100% | 0 |  | 0 | 1300 | -43 | 1257 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: training of trainers and refrigeration technicians in good service practices |  | AFR | MAG | REF | 29 | TRA | 03 | A | I | CFC | 7.8 | 5.7 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2004-08-01 | 2005-01-01 | 46200 | -1519 | 44681 | 44681 | 100% | 0 |  | 0 | 2310 | -76 | 2234 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: recovery and recycling component | RMP | AFR | MAG | REF | 47 | TAS | 12 | A | I | CFC | 6.8 | 6 | 0 |  | 2005-11-01 | 2008-03-01 | 2007-06-01 |  | 2010-12-01 | 2005-03-01 | 40500 | 0 | 40500 | 40500 | 100% | 0 |  |  | 5265 | 0 | 5265 | 0 |  | Project completed.
FIN | France | Country programme preparation |  | AFR | MAG | SEV | 21 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-09-01 | 1999-12-01 | 40000 | -3019 | 36981 | 36981 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
CLO | France | Phasing out the use of CFC-113 in the electronics industry through the technical promotion of no clean processes |  | ASP | MAL | SOL | 18 | INV | 78 | A | D |  | 0 |  | 0 |  | 1995-11-01 |  | 1996-11-01 |  |  | 1997-11-01 | 226600 | -226600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet annulé
FIN | France | No clean process improvement training for electronic assemblers who phased out the use of CFC-113 |  | ASP | MAL | SOL | 22 | TRA | 97 | A | D |  | 0 |  | 0 |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-04-01 | 1999-04-01 | 192423 | 25462 | 217885 | 217885 | 100% | 0 |  |  | 0 | 1500 | 1500 | 0 |  | Projet achevé.
FIN | France | Conversion of CFC-based commercial refrigeration installations in the fishing industry |  | AFR | MAU | REF | 14 | TAS | 05 | A | D | CFC | 2 |  | 0 |  | 1994-09-01 | 1999-07-01 | 1996-09-01 |  | 2000-11-01 | 2000-12-01 | 106900 | -7378 | 99522 | 99522 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-06-01
FIN | France | Training of refrigeration technicians |  | AFR | MAU | REF | 14 | TRA | 04 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1997-07-01 | 1995-09-01 |  | 1999-06-01 | 1999-08-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 1997-05-01
FIN | France | Country programme preparation |  | AFR | MAU | SEV | 13 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-07-01 | 1995-07-01 |  | 1995-07-01 | 1995-09-01 | 44000 | -4229 | 39771 | 39771 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Balance returned at 57th ExCom.
FIN | France | Institutional strengthening project proposal |  | AFR | MAU | SEV | 14 | INS | 02 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 1999-12-01 | 1999-12-01 | 38874 | -12891 | 25983 | 25983 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Training and awareness of personnel involved in the task of codifying and identifying ODS and ODS-containing material |  | AFR | MAU | SEV | 14 | TRA | 03 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-10-01 | 1995-09-01 |  | 1996-11-01 | 1996-12-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | La formation a eu lieu du 02 au 04 novembre 1996. Project completed.
ONG | France | Demonstration project for disposal of unwanted ODS | Individual | LAC | MEX | DES | 63 | DEM | 155 | A | I | CFC | 0 |  | 0 |  | 2011-04-01 | 2012-08-01 | 2013-03-01 | 2016-04-01 |  |  | 500000 | 0 | 500000 | 35389.32 | 7.078% | 464610.68 | 204531.57 | 240000 | 65000 | 0 | 4600.6116 | 60399.3884 | 26589.1041 | The French contribution is implemented in cooperation with UNIDO and at the same time as UNIDO's share of the project. Agreement AFD/UNIDO signed in Jun 2012 and all funds have been transferred to UNIDO for implementation. The project has encountered delays, essentially because the contractor selected for the disposal of a 1st batch of 74.1 metric tonnes of ODS waste didn't finalize his work. He reported on difficulties, but these could not be solved and the final destruction has not occurred. The agencies and the NOU are working on a solution. However, as a consequence, the bidding process for the destruction of the 2nd batch had to be cancelled. See UNIDO's PR for further details. | UNIDO, with the agreement of France decided to cancel the contract with the selected Contractor because of his incapacity to execute the work, and to issue a new Call for Bids. A new company showed a strong interest in carrying out the destruction and a new contract has been signed for the disposal of the 1st batch of 74.1 tonnes. Trial operations have been carried out in a cement kiln facility in order for the company to obtain the adequate disposal permit. 1 tonne has been destroyed.
FIN | France | Project preparation in the foam sector (Fofy) |  | AFR | MLI | FOA | 25 | PRP | 04 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1998-08-01 | 1999-01-01 |  | 1998-09-01 | 1998-11-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Fofy Industrie |  | AFR | MLI | FOA | 26 | INV | 05 | A | I | CFC | 19.5 | 19.5 | 0 |  | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 151000 | 0 | 151000 | 151000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Phase-out of methyl bromide use in the cut flower and banana production |  | AFR | MOR | FUM | 29 | INV | 37 | A | I | MBR | 61 | 61 | 0 |  | 1999-11-01 | 2002-06-01 | 2003-12-01 |  | 2008-07-01 | 2012-12-01 | 1006652 | -78440 | 928212 | 928212 | 100% | 0 |  |  | 120732 | -9408 | 111324 | 0 |  | This project was implemented through UNIDO on behalf of France. It is completed. |  |  | 2005-04-01
FIN | France | Project preparation for the formulation of a project to implement a recycling network for CFC-11, CFC-12 and HCFC-22 |  | AFR | MOR | REF | 19 | PRP | 02 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1996-11-01 |  | 1997-04-01 | 1997-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé.
FIN | France | Technical assistance on alternative technologies for cold storage facilities |  | AFR | MOR | REF | 20 | TAS | 05 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1999-10-01 | 1999-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | AFR | MOR | REF | 23 | TAS | 17 | A | I | CFC | 22 | 22 | 0 |  | 1997-11-01 | 2003-09-01 | 1998-12-01 |  | 2011-06-01 | 2012-12-01 | 355867 | 0 | 355867 | 355867 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | AFR | MOR | REF | 23 | TRA | 18 | A | D |  | 0 |  | 0 |  | 1997-11-01 | 1999-02-01 | 1998-06-01 |  | 2000-12-01 | 2000-12-01 | 53361 | 0 | 53361 | 53361 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Technical assistance for cold storage equipment (training and demonstration project) |  | AFR | MOR | REF | 32 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-08-01 | 2012-12-01 | 114337 | 0 | 114337 | 114337 | 100% | 0 |  | 0 | 5717 | 0 | 5717 | 0 |  | Project completed
FIN | France | Refrigerant management plan update | RMP Update | AFR | MOZ | REF | 44 | TAS | 12 | A | I | CFC | 15.5 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 104512 | -33312 | 71200 | 71200 | 100% | 0 |  | 0 | 13587 | -4331 | 9256 | 0 |  | The French contribution was implmented by GTZ-Proklima. The project is completed.
FIN | France | Project preparation for projects in the hotel and fisheries industries and recycling |  | AFR | SEN | REF | 19 | PRP | 06 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1996-12-01 | 10000 | -248 | 9752 | 9752 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Training of technicians in domestic refrigeration and air conditioning |  | AFR | SEN | REF | 21 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1998-01-01 | 1997-08-01 |  | 1998-03-01 | 1998-06-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Project preparation for a terminal phase-out management plan |  | AFR | SEY | PHA | 49 | PRP | 11 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2006-09-01 | 2007-07-01 |  | 2007-03-01 | 2007-03-01 | 20000 | -5483 | 14517 | 14517 | 100% | 0 |  | 0 | 2600 | -713 | 1887 | 0 |  | The French contribution was implemented by GTZ. Project completed
FIN | France | Terminal ODS phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 51 | INV | 12 | A | I | CFC | 0 | 0 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-06-01 | 2011-06-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 15600 | 0 | 15600 | 0 |  | The French contribution was implmented by GTZ-Proklima. Project completed.
FIN | France | Terminal ODS phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 55 | INV | 14 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-05-01 | 2009-03-01 |  | 2010-12-01 | 2012-12-01 | 60000 | -40121 | 19879 | 19879 | 100% | 0 |  | 0 | 7800 | -5216 | 2584 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal ODS phase-out management plan (third tranche) | Multi-Year | AFR | SEY | PHA | 59 | INV | 16 | A | I | CFC | 0.4 |  | 0 |  | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 13000 | -13000 | 0 | 0 |  | 0 |  | 0 | 1690 | -1690 | 0 | 0 |  | The funds were not needed to complete the project.
FIN | France | Development of a halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 50 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2004-04-01 | 2000-05-01 |  | 2001-05-01 | 2004-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 |  |  | 536 | 0 | 536 | 0 |  | Project completed.
FIN | France | Establishing a halon bank and umbrella project for 63 manufacturers |  | ASP | SYR | HAL | 34 | TAS | 78 | A | I | HAL | 284.5 |  | 0 |  | 2001-07-01 | 2004-04-01 | 2004-08-01 |  | 2004-04-01 | 2005-01-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 |  | 0 | 8050 | 0 | 8050 | 0 |  | Project completed.
FIN | France | Project preparation in the commercial refrigeration sector |  | ASP | SYR | REF | 26 | PRP | 35 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 25000 | -8828 | 16172 | 16172 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | France | Technical assistance in the air-conditioning sector |  | ASP | SYR | REF | 26 | TAS | 37 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 30000 | -4018 | 25982 | 25982 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators |  | ASP | SYR | REF | 29 | INV | 48 | A | I | CFC | 3.8 |  | 0 |  | 1999-11-01 | 2007-03-01 | 2002-12-01 |  | 2007-12-01 | 2011-05-01 | 57783 | 0 | 57783 | 57783 | 100% | 0 |  | 0 | 2889 | 0 | 2889 | 0 |  | Project completed.
CLO | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. |  | ASP | SYR | REF | 29 | INV | 53 | A | I | CFC | 2.5 |  | 0 |  | 1999-11-01 |  | 2002-12-01 |  |  | 2008-07-01 | 33359 | -33359 | 0 | 0 |  | 0 |  | 0 | 1668 | -1668 | 0 | 0 |  | Project cancelled (Decision 55/4)
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators |  | ASP | SYR | REF | 29 | INV | 54 | A | I | CFC | 3.2 | 3.2 | 0 |  | 1999-11-01 | 2005-02-01 | 2002-12-01 |  | 2005-02-01 | 2005-10-01 | 49113 | -1615 | 47498 | 47498 | 100% | 0 |  | 0 | 2456 | -81 | 2375 | 0 |  | Project completed.
FIN | France | CFC emission reduction in central air conditioning |  | ASP | SYR | REF | 29 | INV | 56 | A | I | CFC | 0.9 |  | 0 |  | 1999-11-01 | 2006-09-01 | 2002-06-01 |  | 2006-12-01 | 2009-08-01 | 143000 | -36617 | 106383 | 106383 | 100% | 0 |  | 0 | 7150 | -1831 | 5319 | 0 |  | Project completed.
FIN | France | No clean process improvement training for electronic assemblers |  | ASP | THA | SOL | 29 | TRA | 124 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-01-01 | 2001-12-01 |  | 2002-12-01 | 2002-12-01 | 118140 | -2140 | 116000 | 116000 | 100% | 0 |  | 0 | 5907 | -107 | 5800 | 0 |  | Projet achevé
ONG | France | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning manufacturing sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 57 | A | I | HCFC | 0.4 |  | 0 |  | 2014-05-01 |  | 2017-05-01 | 2017-05-01 |  |  | 97690 | 0 | 97690 | 0 | 0% | 97690 |  | 10000 | 12374 | 0 | 0 | 12374 |  | The French contribution is implemented in cooperation with UNIDO. Discussion on technical activities under this HPMP component took place among NOU, UNIDO and relevant stakeholders. | Agreement AFD/UNIDO signed in Jan 2015 and all funds have been transferred to UNIDO for implementation. Technical assistance activities are ongoing for the participating companies. Their representatives are participating in training sessions on low-GWP alternatives. Disbursements will reflect the progress significantly before the end of the year.
ONG | France | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | INV | 60 | A | I | HCFC | 0.5 |  | 0 |  | 2014-05-01 |  | 2014-05-01 | 2017-05-01 |  |  | 38000 | 0 | 38000 | 0 | 0% | 38000 |  | 10000 | 4813 | 0 | 0 | 4813 |  | The French contribution is implemented in cooperation with UNIDO. Discussion on technical activities under this HPMP component took place among NOU, UNIDO and relevant stakeholders. | Agreement AFD/UNIDO signed in Jan 2015 and all funds have been transferred to UNIDO for implementation. Under this project component, a review of the curricula of training in vocational schools has been made, as well as a needs assessment related to equipment and tools for these schools to support HPMP implementation. Implementation of a certification programmed for servicing technicians and workshops is at its initial stage. Disbursements will reflect the progress significantly before the end of the year.
FIN | France | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | UGA | PHA | 50 | PRP | 12 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2009-03-01 | 2012-12-01 | 30000 | -2264 | 27736 | 27736 | 100% | 0 |  | 0 | 3900 | -294 | 3606 | 0 |  | The French contribution was impelmented by GTZ; project completed.
FIN | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | UGA | PHA | 55 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-12-01 | 2010-12-01 |  | 2010-09-01 | 2012-12-01 | 152500 | 0 | 152500 | 152500 | 100% | 0 |  | 0 | 19825 | 0 | 19825 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | UGA | PHA | 59 | INV | 15 | A | I | CFC | 1.9 | 1.9 | 0 |  | 2009-11-01 | 2010-01-01 | 2010-11-01 |  | 2011-04-01 | 2012-12-01 | 62500 | -5571 | 56929 | 56929 | 100% | 0 |  | 0 | 8125 | 0 | 7401 | 724 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | France | Implementation of the RMP update | RMP Update | AFR | UGA | REF | 44 | TAS | 11 | A | I | CFC | 10.9 |  | 0 |  | 2004-12-01 | 2005-07-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 75000 | -12511 | 62489 | 62489 | 100% | 0 |  | 0 | 9750 | -1626 | 8124 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | France | Refrigerant management plan update | RMP Update | AFR | URT | REF | 46 | TAS | 18 | A | I | CFC | 68.3 |  | 0 |  | 2005-07-01 | 2005-09-01 | 2008-07-01 |  | 2009-12-01 | 2012-12-01 | 157252 | -43428 | 113824 | 113824 | 100% | 0 |  | 0 | 20443 | -5646 | 14797 | 0 |  | The French contribution was implemented by GIZ-Proklima. Project completed.
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | -5500 | 34500 | 34500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | I | CFC | 3.6 | 3.6 | 0 |  | 1999-07-01 | 2001-06-01 | 2001-08-01 |  | 2002-12-01 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed |  |  | 2002-12-01
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 03 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | Germany | National phase-out plan (1st tranche) | Multi-Year | ASP | AFG | PHA | 47 | INV | 06 | A | I | CFC | 28 | 28 | 0 |  | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2008-08-01 | 2010-08-01 | 118438 | 0 | 118438 | 118438 | 100% | 0 | 0 | 0 | 15397 | 0 | 15397 | 0 | 0 | The foam sector was evaluated. A strategy was worked out based on the training of technicians for one foam company. A training was conducted for Afghan technicians in Tehran, Iran in April 2008. In addition, an inspection was carried out to the foam company in Afghanistan, Kabul in 2008.
FIN | Germany | National phase-out plan (2nd tranche) | Multi-Year | ASP | AFG | PHA | 48 | INV | 07 | A | I | CFC | 151.8 | 151.8 | 0 |  | 2006-04-01 | 2006-05-01 | 2009-12-01 |  | 2009-12-01 | 2011-11-01 | 642368 | 0 | 642368 | 642368 | 100% | 0 | 0 | 0 | 83508 | 0 | 83508 | 0 | 0 | R&R equipment was delivered in Apr-2007, training and commissioning was accomplished in May 2007, 83 R&R units have been distributed until 12-2008, furhter 63 will be distributed in 2009. In addition, two train the trainer workshops were organized in 2007 and 2008.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | AFG | PHA | 60 | PRP | 11 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-03-01 | 2013-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP approved at 63rd meeting
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | AFG | PHA | 63 | INV | 13 | A | I | HCFC | 0 | 0 | 0 |  | 2011-04-01 | 2011-10-01 | 2012-03-01 | 2015-12-01 |  |  | 85000 | 0 | 85000 | 24186 | 28.45% | 60814 | 60814 | 60814 | 11050 | 0 | 3094 | 7956 |  | In 2014 the beneficiary for conversion Qasr Yakh was reassessed. Due to the fact that there was no consumption and the company was not operating HPMP activities were changed. In agreement with MLFS the budget was shifted to the reclamation and recycling component. In October a mission of UNEP and GIZ to Kabul was organised. Various potential beneficiaries such as supermarkets, workshops and vocational training centers were visited. Due to safety conditions in the country the mission was undertaken by GIZ national staff from Iran. The conitinous safety concerns repetedly led to the consideration of transferring the project to an IA. | Discussions about project transfer were held with the NOU latest at the 35 OEWG in Paris. |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | AFG | PHA | 72 | INV | 17 | A | I | HCFC | 1 |  | 0 |  | 2014-05-01 | 2014-09-01 | 2017-05-01 | 2017-05-01 |  |  | 84000 | 0 | 84000 | 3331 | 3.965% | 80669 | 30000 | 30000 | 10920 | 0 | 437 | 10483 |  | Project under evaluation of review through NOU of suitable manufacturer | Update of project activities - permanent communication and coordination. Investigation regarding a new potential beneficiary
FIN | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Halon banking | AFR | AFR | HAL | 35 | TAS | 29 | A | I | HAL | 27 | 27 | 0 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2010-12-01 | 2012-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 | 0 | 45500 | 0 | 45500 | 0 | 0 | Many of the countries phased out halons through controls and awareness. Most recently Botswana successfully phased out approx 8MT of halons.
FIN | Germany | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 34 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2009-09-01 |  | 2010-12-01 | 2011-12-01 | 192500 | 0 | 192500 | 192500 | 100% | 0 | 0 | 0 | 25025 | 0 | 25025 | 0 | 0 | Chiller has been delivered to Namibia and installed. Project and financial completion under way.
FIN | Germany | Conversion of Algeria Mousse Polyurethane (AMP) | Individual | AFR | ALG | FOA | 31 | INV | 44 | A | I | CFC | 152 | 152 | 0 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 |  | 2004-12-01 | 2007-12-01 | 565728 | 0 | 565728 | 565728 | 100% | 0 | 0 | 0 | 73545 | 0 | 73545 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 45 | A | I | CFC | 80 | 80 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 | 0 | 64792 | 0 | 64792 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of Matelas Souf to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 46 | A | I | CFC | 95 | 95 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 561379 | 0 | 561379 | 561379 | 100% | 0 | 0 | 0 | 72979 | 0 | 72979 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector | Individual | AFR | ALG | FOA | 33 | PRP | 49 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30900 | 0 | 30900 | 30900 | 100% | 0 | 0 | 0 | 4017 | 0 | 4017 | 0 | 0 | Project completed. A report has been prepared and will be used in preparation of the terminal phase out plan.
FIN | Germany | Project preparation, technical assistance in the halon sector | Individual | AFR | ALG | HAL | 31 | PRP | 42 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-01-01 | 2002-01-01 |  | 2001-06-01 | 2002-03-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project document submitted and approved.
FIN | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | AFR | ALG | HAL | 35 | TAS | 51 | A | I | HAL | 392.3 | 392.3 | 0 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2010-07-01 | 2012-07-01 | 259500 | 0 | 259500 | 259500 | 100% | 0 | 0 | 0 | 33735 | 0 | 33735 | 0 | 0 | Project is completed, PCR has been sent to Algeria 10 months ago, so far no response.
CLO | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector | Individual | AFR | ALG | PHA | 37 | PRP | 57 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  |  | 2007-09-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | The TPMP preparation was cancelled by the Government of Algeria long after the work was completely prepared. The results will be used by UNIDO.
CLO | Germany | Development of a country programme update | Individual | AFR | ALG | SEV | 43 | CPG | 60 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-09-01 | 2005-07-01 |  |  | 2007-09-01 | 13500 | 0 | 13500 | 13500 | 100% | 0 | 0 | 0 | 1215 | 0 | 1215 | 0 | 0 | The CPU update was cancelled by the Government of Algeria. The results have been used by UNIDO for the National Phase Out Plan.
FIN | Germany | Project preparation in the solvent sector | Individual | AFR | ALG | SOL | 33 | PRP | 48 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed. Strategy will be included in NPP.
FIN | Germany | Implementation of the RMP: enforcement of regulations, training of customs officers, training of refrigeration service technicians, recovery and recycling, incentive programme for end-users, and public awareness | RMP Update | AFR | ANG | REF | 39 | TAS | 04 | A | I | CFC | 97.6 | 97.8 | 0 | 0 | 2003-04-01 | 2003-11-01 | 2008-04-01 |  | 2009-12-01 | 2011-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 87000 | 0 | 87000 | 0 | 0 | Additional Training courses in Refrigeration Sector were conducted in Huige and Huambo Provices.- A public awareness campaign has been launched in the provinces of Huila, Moxico, Huambo, Bie and Malange, with the additional aim of formation of interministerial support groups.- Working group of legal experts has been created in order to finalize and submit draft on ODS related legislation and regulations. - Survey has been undertaken in provinces and Luanda in order to identify ODS consuming companies which may qualify for Incentive programme. - R&R centre has been established in Huambo (Central Angola). 1st Customs Training was done in Luanda during January 08, 2nd & 03rd Customs Training in the towns of Namibe and Benguela respectively have been conducted during January /February 09. During Octover 2009 another R&R Centre has been established and inaugurated in Luanda.- Together with National Customs Identification Center for CFCs has been installed at Santa-Clara borderpost (border with Namibia) during November /December 09. During November 09 final training course in good refrigertion pracitses has been conducted in Ondjiva (Southern Angola) - Draft for ODS related legislation and regulation has been handed over to Council of Ministers of Angolan Government during November 2009. According to Angolan NOU approval can be expected for April /May 2010. All funds approved have been spent and project activities were terminated during December 2009, with PCR to be handed over during May/June 2010.
FIN | Germany | Country programme preparation | Individual | AFR | ANG | SEV | 34 | CPG | 02 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | National consultants contracted, survey on ODS consump finalized, Country Programme prepared and submitted together with prop. for I.S. Angola. Aproved at 38th ExCom. (1st instalment of 1st tranche of IS funding of 81000) Request for 2nd instalment of IS
FIN | Germany | Establishment of the Ozone Unit | Individual | AFR | ANG | SEV | 38 | INS | 03 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-06-01 | 71682 | 141618 | 213300 | 213300 | 100% | 0 | 0 | 0 | 9319 | 18411 | 27730 | 0 | 0 | 1st phase of Institutional Strengthening project is completed. - the infrastructure of the NOU-office in Luanda has been completed, with internet and telepone / fax connection. - Regional support groups have been created in serveral of Angolas provinces in order to assist NOU in data collection, public awareness activities, etc.- ODS data up to reporting year 2006 have been submitted to both Ozone Secretariat and Multilateral Fund Secretariat. - Angola is in compliance with phase-out schedule and data reporting obligations.
FIN | Germany | Extension of the institutional strengthening project (phase II) | Individual | AFR | ANG | SEV | 50 | INS | 05 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2009-01-01 | 2011-01-01 | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 | 0 | 17472 | 0 | 17472 | 0 | 0 | NOU moved into the building of the Ministry (Urbanism & Environment). NOU collected and reported data for 2006, preparations for reporting of ODS data for 2007 has started. - After General elections in Angola restructuring of Government took place. Angolan NOU is now part of newly created Ministry of Environment. According to NOU ODS data for 2007 and 2008 have been reported to Ozone Secretariat and MFsecretariat. - All approved funds have been spent, with final payment done in January 2009. All project acitvities were completed in December 2008.
FIN | Germany | Survey for halon banking management plan in West Asia: Bahrain, Lebanon, Qatar and Yemen | Halon banking | ASP | ASP | HAL | 28 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-02-01 |  | 2000-03-01 | 2000-09-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project approved at 30th ExCom.
FIN | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | Halon banking | ASP | ASP | HAL | 30 | TAS | 36 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-02-01 | 2001-10-01 |  | 2005-04-01 | 2007-12-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 | 0 | 0 | 15275 | 0 | 15275 | 0 | 0 | Evaluation meeting Beirut 31.5.-4.6.2004; Comment on Terms, Comment on evaluation report; Calculation of operational costs of halon R&R equipment; contact addresses and quotations received for storage cylinders; discussion of alternative strategies. Proje
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BOL | PHA | 55 | PRP | 31 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | HPMP approved at 64th meeting
COM | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BOL | PHA | 64 | INV | 36 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-10-01 | 2015-07-01 | 2015-05-01 |  |  | 94500 | 0 | 94500 | 94500 | 100% | 0 | 0 | 0 | 12285 | 0 | 12285 | 0 |  | Implementation of train the trainer and RAC training as well as dissemination activities.
TRF | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | BOL | PHA | 72 | INV | 38 | A | I | HCFC | 0.5 |  | 0 |  | 2014-05-01 |  | 2016-05-01 |  |  |  | 94500 | 0 | 94500 | 0 | 0% | 94500 | 0 | 0 | 12285 | 0 | 0 | 12285 |  |  | Transferred to UNIDO at 74th Excom (May 2015)
TRF | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | BOL | PHA | 73 | TAS | 40 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2015-05-01 |  |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 0 | 3900 | 0 | 0 | 3900 |  |  | Transferred to UNIDO at 74th Excom (May 2015)
FIN | Germany | Project preparation for a terminal phase-out management plan | Individual | AFR | BOT | PHA | 55 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2008-07-01 | 2008-10-01 | 2009-01-01 |  | 2009-03-01 | 2009-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | TPMP project was approved at the 57th Excom.
FIN | Germany | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BOT | PHA | 57 | INV | 12 | A | I | CFC | 1 |  | 0 |  | 2009-04-01 | 2009-06-01 | 2011-03-01 |  | 2010-12-01 | 2012-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | 7 customs training were realised, purchase of training equipment, major public awareness on phase out of CFCs was conducted
FIN | Germany | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BOT | PHA | 60 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-11-01 | 2012-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | 10 additional refrigerant identifiers were purchased following the request from the customs dept. This was followed by 3 customs training at remote border posts of Botswana.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | BOT | PHA | 60 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 |  | 2014-03-01 | 2014-08-01 | 150000 | 0 | 150000 | 148206 | 98.8% | 1794 |  | 0 | 19500 | 0 | 19305 | 195 |  | The regulations were not approved in 2014 delaying any progress. | Regulations were approved in Feb 2015. The remaining funds will be offset against other project activities. Project transferred to UNEP. HPMP will be submitted to the 75th excom.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | BOT | REF | 26 | TAS | 06 | A | I | CFC | 1.5 | 1.7 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2005-06-01 | 2006-06-01 | 70375 | 0 | 70375 | 70375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted in 2006
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | BOT | REF | 39 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-12-01 | 2005-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project preparation completetd. RMP update to be submitted for approval at 45th Excom
FIN | Germany | Implementation of the RMP update | RMP Update | AFR | BOT | REF | 45 | TAS | 09 | A | I | CFC | 5.8 | 5.8 | 0 |  | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-08-01 | 2011-11-01 | 64295 | 0 | 64295 | 64295 | 100% | 0 | 0 | 0 | 8358 | 0 | 8358 | 0 | 0 | Customs training was the only activity remaining under the project and with the approval of the ODS regulations these could be completed. 36 customs officiers were trained at the various border posts. The PCR will be submitted in 2010
FIN | Germany | National CFC phase out plan: training of customs officers | Multi-Year | LAC | BRA | PHA | 37 | TRA | 260 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2007-12-01 | 2008-12-01 | 141200 | 0 | 141200 | 141200 | 100% | 0 | 0 | 0 | 18356 | 0 | 18356 | 0 | 0 | Training activities for 55 customs officers/instructors as well 9 staff members from the national environmental protection agency are completed. Refrigerant identifiers were purchased in 2007 and distributed to Customs officers. The project is completed.
FIN | Germany | National CFC phase-out plan: training of refrigeration mechanics in domestic and commercial refrigeration service sub-sectors (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | TRA | 261 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2006-12-01 | 2007-12-01 | 435937 | 1062863 | 1498800 | 1498800 | 100% | 0 | 0 | 0 | 56672 | 95658 | 152330 | 0 | 0 | By end of 2006 7000 technicians had been trained under this tranche. A total of 27 mobile training units have been built and are used in the field. Production of 8,000 free books with photo-training on good practices for mechanics in the commercial and do
COM | Germany | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 265 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 |  | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 63000 | 0 | 63000 | 0 | 0 | By end of 2008, more than 300 technicians had been trained under this tranche. One train the trainer course with 35 participants was conducted. A total of 12 mobile training units have been built and are used in the field. Continue to further distribute educational materials and public relation materials and to monitor and to follow up the success of training activities of technicians.
FIN | Germany | National CFC phase-out plan: third and fourth tranches | Multi-Year | LAC | BRA | PHA | 48 | INV | 277 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2011-04-01 | 2011-12-01 | 1543600 | 0 | 1543600 | 1543600 | 100% | 0 | 0 | 0 | 138924 | 0 | 138924 | 0 | 0 | Project completed
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BRA | PHA | 55 | PRP | 282 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-04-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP was approved based on a preperatory study
FIN | Germany | Preparation of a HCFC phase-out management plan (extruded polystyrene foam sector) | Individual | LAC | BRA | PHA | 57 | PRP | 286 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | HPMP was approved based on a preperatory study
ONG | Germany | HCFC phase-out management plan (refrigeration servicing sector) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 296 | A | I | HCFC | 14.8 | 2 | 0 |  | 2011-07-01 | 2011-10-01 | 2012-07-01 | 2016-12-01 |  |  | 1209091 | 0 | 1209091 | 1118436 | 92.5% | 90655 | 90655 | 90655 | 153000 | 0 | 142290 | 10710 | 10710 | Project delay, Best practice Handbook for technician training developed & designed, training institutions selected and contracted, mobile training units assembled and distributed, technical standards elaborated, technical assistance programme for end users established, website and facebook fanpage published, regional outreach, 24 technical visits to supermarkets conducted
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 68 | INV | 299 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 | 2013-12-01 | 2015-12-01 | 2016-12-01 |  |  | 2472727 | 0 | 2472727 | 785424 | 31.76% | 1687303 | 552149 | 738658 | 262000 | 0 | 83840 | 178160 | 92000 | Project Delay, 5 train-the-trainer courses carried out and 56 instructors trained, 776 technicians in commercial refrigeration trained, demonstration tools purchased, case studies for demo projects selected, identification, measurement and performance analysis equipment for refrigeration systems puchased, technical analysis of first case study conducted, adaptation of online documentation system & planning of the introductory workshop, technical publications and best practice guidelines prepared | 1616 technicians trainined in better containment of HCFCs in supermarket installations, 76 technicians trained in best practices and better containment of HCFCs in split air conditioners, additional training institution hired, technical analysis of second supermarket conducted, test phase of online doc system |  |  | INV
ONG | Germany | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | BRA | PHA | 72 | PRP | 303 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2014-05-01 | 2015-09-01 | 2015-09-01 |  |  | 30000 | 0 | 30000 | 18744 | 62.48% | 11256 | 11256 | 11256 | 3900 | 0 | 2418 | 1482 | 1463 | Servicing Sector Study elaborated, data collection and processing, stakeholder consultations
FIN | Germany | Pilot project: training programme for the refrigeration maintenance sector | Individual | LAC | BRA | REF | 34 | TRA | 228 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2004-08-01 | 2007-12-01 | 247400 | 0 | 247400 | 247400 | 100% | 0 | 0 | 0 | 32162 | 0 | 32162 | 0 | 0 | Project completed. Strategy derived from the demonstration project has been subvmitted with the National Phase Out Plan or Brazil
ONG | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | COL | PHA | 72 | PRP | 85 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2014-05-01 | 2016-05-01 | 2015-12-01 |  |  | 15000 | 0 | 15000 | 14000 | 93.33% | 1000 | 1000 | 1000 | 1950 | 0 | 1814 | 136 | 130 | Data collection and processing, stakeholder consultations, visit to possible installations for natural refrigerants training centre, discussions with technical standard organization | final stage II proposal for the servicing sector prepared
ONG | Germany | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | CPR | FOA | 73 | PRP | 553 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2015-12-01 | 2015-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 40000 | 9100 | 0 | 0 | 9100 |  |  | Interagency meeting held in July and preparatory work for September meeting forthgoing
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 469 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 201369 | 0 | 201369 | 201369 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam (additional funding) | Individual | ASP | CPR | PHA | 57 | PRP | 482 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 201370 | 0 | 201370 | 201370 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
COM | Germany | HCFC phase-out management plan (extruded polystyrene foam sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 518 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-07-01 | 2012-07-01 |  | 2013-11-01 |  | 459023 | 0 | 459023 | 459023 | 100% | 0 | 0 | 0 | 51260 | 0 | 51260 | 0 |  | HCFC survey completed - Stakeholders workshop held - Local institutions identified - Experts recruited - Draft document completed - Documents signed - TOR completed - All funds disbursed - | All technical input completed
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 69 | INV | 532 | A | I | HCFC | 0 |  | 0 |  | 2013-04-01 | 2013-09-01 | 2014-04-01 | 2015-12-01 |  |  | 390977 | 0 | 390977 | 390977 | 100% | 0 | 0 | 0 | 47059 | 0 | 47059 | 0 |  | Interagency meetings were held in July 2014 and September 2014 , alll companies to be converted have been visited | TORS auditing and whitebook in China in preparation |  |  | INV
ONG | Germany | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) | Individual | ASP | CPR | PHA | 73 | PRP | 557 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 | 2014-09-01 | 2015-12-01 | 2015-12-01 |  |  | 46900 | 0 | 46900 | 8343 | 17.79% | 38557 | 0 | 38557 | 6097 | 0 | 1097 | 5000 |  | Discussions with UNEP on servicing sector were held - decisions were made | TORs were verified and XPS standards prepared
FIN | Germany | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) | Individual | ASP | CPR | REF | 16 | INV | 115 | N | I | CFC | 174 | 174 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 1336918 | 0 | 1336918 | 1336918 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Oct 99 |  |  | 2000-01-01
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory | Individual | ASP | CPR | REF | 27 | INV | 282 | A | I | CFC | 95.5 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-04-01 |  | 2004-12-01 | 2006-10-01 | 1451137 | 0 | 1451137 | 1451137 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR has been submitted.
FIN | Germany | Conversion of the use of CFC-12 to HC in the manufacture of thermostats at Foshan Tongbao Co., Ltd. | Individual | ASP | CPR | REF | 35 | INV | 384 | A | I | CFC | 11.5 |  | 0 |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2006-10-01 | 213271 | 0 | 213271 | 213271 | 100% | 0 | 0 | 0 | 27725 | 0 | 27725 | 0 | 0 | Project completed. PCR has been submitted.
FIN | Germany | Development of a suitable strategy for the long term management of HCFCs, in particular HCFC-22 | Individual | ASP | CPR | REF | 43 | TAS | 414 | A | I |  | 0 | 0 | 0 |  | 2004-07-01 | 2004-11-01 | 2005-12-01 |  | 2007-03-01 | 2008-12-01 | 300300 | -2.8 | 300297.2 | 300297 | 100% | 0.2 | 0 | 0 | 39039 | -0.36 | 39039 | -0.36 | 0 | Project was completed and approved by the Chinese authorities. Project report was submitted to 51st ExCom. PCR was submitted in December 2008.
FIN | Germany | Project preparation/technical assistance in the refrigeration sector (thermostat) | Individual | ASP | CPR | SEV | 33 | PRP | 372 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2001-12-01 |  | 2002-01-01 | 2002-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed; no PCR due to project preparation only
TRF | Germany | Project preparation for phasing out ODS use in Pliva Pharmaceuticals | Individual | EUR | CRO | ARS | 36 | PRP | 16 | A | I |  | 0 |  | 0 |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-04-01 | 16500 | -16500 | 0 |  |  | 0 | 0 | 0 | 2145 | -2145 | 0 | 0 | 0 | Project was offset against Germany contributions at the 39th meeting. Project funds have been transferred to the Croatia Halon project preparation project.
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | EUR | CRO | HAL | 39 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2004-07-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 | 0 | 0 | 2145 | 0 | 2145 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
FIN | Germany | Sectoral phase-out programme: establishment of a halon bank | Individual | EUR | CRO | HAL | 43 | TAS | 24 | A | I | HAL | 30.1 | 30.1 | 0 |  | 2004-07-01 | 2005-01-01 | 2007-07-01 |  | 2008-10-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Having identified an enterprise, tender for Halonbank equipment has been finalized in december 2007, equipment will be delivered in May 2008. Project completed. PCR was submitted in December 2008.
FIN | Germany | Preparation of a CFC phase out management plan | Individual | LAC | CUB | PHA | 37 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-07-01 | 2004-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
TRF | Germany | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 25 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-04-01 | 120000 | -76547 | 43453 | 43453 | 100% | 0 | 0 | 0 | 15600 | -9951 | 5649 | 0 | 0 | Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emis
TRF | Germany | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 30 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-04-01 | 116000 | -116000 | 0 | 0 |  | 0 | 0 | 0 | 15080 | -15080 | 0 | 0 | 0 | see remarks under MLF No. CUB/PHA/43/TAS/25. Transfer to UNDP completed.
FIN | Germany | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and cucurbits) | Individual | AFR | EGY | FUM | 25 | PRP | 68 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1998-12-01 |  | 1998-08-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implementation of the demonstration
FIN | Germany | Four alternatives to the use of methyl bromide in horticulture (strawberries, tomatoes, cucurbits) | Individual | AFR | EGY | FUM | 26 | DEM | 69 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-12-01 | 2001-03-01 | 308000 | -81000 | 227000 | 227000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted. Balance was offset against German contribution at the 40th Meeting.
FIN | Germany | Application of methyl bromide alternatives in grain storage | Individual | AFR | EGY | FUM | 26 | DEM | 70 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | EGY | REF | 27 | PRP | 71 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 1999-09-01 | 2002-01-01 | 28700 | 0 | 28700 | 28700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | Germany | Implementation of the RMP: modification of legal provisions and information system | RMP | AFR | EGY | REF | 29 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | UNIDO was subcontracted. Project completed. Draft PCR submitted in September 2005.
FIN | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Individual | AFR | EGY | REF | 29 | TAS | 75 | A | I | CFC | 100 | 100 | 0 |  | 1999-11-01 | 2000-04-01 | 2002-12-01 |  | 2007-12-01 | 2008-10-01 | 599500 | 0 | 599500 | 599500 | 100% | 0 | 0 | 0 | 77935 | 0 | 77935 | 0 | 0 | Project is completed. A final monitoring and evaluation workshop was organized with NOU in August 2007 to establish a network for monitoring in the whole country. PCR was approved by NOU and was sent to MLF in October 2008.
FIN | Germany | Implementation of the RMP: implementation of measures to address the informal sector | RMP | AFR | EGY | REF | 29 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 252500 | 0 | 252500 | 252500 | 100% | 0 | 0 | 0 | 32825 | 0 | 32825 | 0 | 0 | Unido was subcontracted, training courses have been carried out successfully. Project completed. Draft PCR submitted in September 2005.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ETH | REF | 23 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 1999-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ETH | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-10-01 | 2005-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. RMP update approved in dec 2004
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ETH | REF | 37 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | Germany | Promoting compliance with the Montreal Protocol in countries with economies in transition (Croatia and Romania) | Individual | EUR | EUR | SEV | 28 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2001-08-01 | 2003-10-01 | 67800 | -6900 | 60900 | 60900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Germany | Project preparation for additional activities for Gambia RMP | RMP | AFR | GAM | REF | 32 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2004-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project completed and resultant RMP update is being implemented.
FIN | Germany | Implementation of the RMP update: phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | GAM | REF | 37 | TAS | 12 | A | I |  | 11.2 | 11.2 | 0 |  | 2002-07-01 | 2003-03-01 | 2005-01-01 |  | 2007-09-01 | 2009-01-01 | 76700 | -30 | 76670 | 76670 | 100% | 0 | 0 | 0 | 9971 | -4 | 9967 | 0 | 0 | Project completed and PCR submitted.
FIN | Germany | Travel expenses for participants to attend a regional workshop on methyl bromide alternatives for North African countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Syria, Tunisia) | Individual | GLO | GLO | FUM | 25 | TRA | 161 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-05-01 | 1999-06-01 |  | 1998-06-01 | 1999-07-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Information video: working safely with hydrocarbons in domestic and small scale commercial refrigeration | Individual | GLO | GLO | REF | 23 | TRA | 138 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-08-01 |  | 2001-01-01 | 2002-12-01 | 322050 | 0 | 322050 | 322050 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Dec 2003
FIN | Germany | Implementation of RMPs for 14 low volume consuming countries in eastern and southern Africa | RMP | GLO | GLO | REF | 26 | TAS | 172 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-11-01 | 2005-09-01 | 815000 | 0 | 815000 | 815000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All countries completed the activities under this project. PCR is to be submitted
FIN | Germany | Support to attend the Alternatives to CFC and Halons Technologies and Substances conference | Individual | GLO | GLO | SEV | 07 | TRA | 26 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-10-01 | 1992-10-01 |  | 1992-10-01 | 1994-10-01 | 18378 | 0 | 18378 | 18378 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Project preparation for the phase out of ODS use in the flexible molded foam sub-sector in 5 enterprises | Individual | ASP | IND | FOA | 34 | PRP | 309 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-10-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 2 resultant investment projects were submitted and approved in Mar-02
FIN | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components | Individual | ASP | IND | FOA | 36 | INV | 350 | A | I | CFC | 22 | 22 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 200282 | -26 | 200256 | 200256 | 100% | 0 | 0 | 0 | 26037 | -3 | 26034 | 0 | 0 | Project has been completed. PCR submitted in 2006. Remaining funds will be returned. |  |  | 2004-12-01
FIN | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products | Individual | ASP | IND | FOA | 36 | INV | 351 | A | I | CFC | 27 | 27 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 224812 | -9 | 224803 | 224803 | 100% | 0 | 0 | 0 | 29226 | -1 | 29225 | 0 | 0 | Project has been completed. PCR submitted in 2006 |  |  | 2004-12-01
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 375 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2007-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned with the funds from this tranche have been accomplished.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 388 | A | I | CTC | 0 | 970 | 0 |  | 2005-04-01 | 2006-01-01 | 2006-07-01 |  | 2008-12-01 | 2010-07-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 401 | A | I | CTC | 0 | 0 | 0 |  | 2006-07-01 | 2008-01-01 | 2007-07-01 |  | 2008-12-01 | 2010-07-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 410 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2008-12-01 | 2008-07-01 |  | 2010-12-01 | 2012-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | The environment, health and safety material has been completed and capacity building with institutional stakeholders from the power sector has taken place. All project activities have been completed now.
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 426 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP has been drafted and submitted to the NOU.
COM | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 66 | INV | 442 | A | I | HCFC | 0 |  | 0 |  | 2012-04-01 | 2012-05-01 | 2013-04-01 |  | 2014-12-01 |  | 925452 | 0 | 925452 | 925452 | 100% | 0 | 0 | 0 | 106440 | 0 | 106440 | 0 |  | 1. RAC Technicians Training in Installation & Servicing Room Air conditioners up to 2 ton in progress. 2. Training of Trainers (ToT) condcuted. 3. Contact established / initiated and meetings done with Instituional users - Defence and Railways for conducting training for their RAC technical staff. 4. One training for Defence - Technical staff conducted in Secunderabad. 5. Discussions with Reclamation Centre entreprenuers and preparing of action plan . 6. Discussions and proposal to DGET for Training RAC Trainers and syllabus revision. 7. IA and Core Group Meetings. 8. Planning and Co-ordination with the consultants and training partners in the field on a ongoing process. 9. Capacity building for Training Partners. 10. PMU - Servicing Sector - management ongoing, coordination with UNEP ongoing. 11. Participation and Presentation at Awareness Workshops | 1. RAC Technicians Training in Installation & Servicing Room Air conditioners up to 2 ton completed trained over 11000 technicians. 2. Follow up meetings with Instituional users - Defence and Railways for conducting training for their RAC technical staff . 3. Two training programs for Railways - Technical staff conducted in one each in Lucknow and Ghaziabad. 4. Meeting with Reclamation centre entreprenuers. 5. Reclamation Centre awareness workshops organised one each at Ludhiana and Ahemdabad. 6. Discussions and proposal to DGET for Training RAC Trainers and syllabus revision. 7. IA and Core Group Meetings in August 2015. 8. Planning and Co-ordination with the consultants and training partners in the field on a ongoing process. 9. Printing of additional copies of Technicians Handbooks 10. PMU - Servicing Sector - management ongoing, coordination with UNEP ongoing 11. Participation and Presentation at Awareness Workshops. Activites to be completed - 1. Capacity building for Training Partners, 2. Insitutional training Railways and Defence RAC Techncial Staff 3. Training of RAC Teaching staff from ITI - that will require close follow up with DGET 4. Impact Monitoring - this activity will be completed early 2016 5. PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing. 6. Participation and Presentation at Awareness Workshops
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 71 | INV | 449 | A | I | HCFC | 0 |  | 0 |  | 2013-12-01 | 2014-01-01 | 2015-12-01 | 2016-06-01 |  |  | 869508 | 0 | 869508 | 95526 | 10.99% | 773982 |  | 400000 | 100006 | 0 | 11001 | 89005 |  | Revision of training material - inventory of equipment and tools and applicances - organisation of capacity building programm - conduct technician training programmes | Impact Monitoring of training programmes - Data entry of the information / feedback report in progress |  |  | INV
ONG | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IND | PHA | 72 | PRP | 454 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2016-01-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 |  | 15000 | 2600 | 0 | 0 | 2600 |  | preparatory coordination activities
FIN | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 288 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2004-04-01 | 2004-04-01 | 240200 | 0 | 240200 | 240200 | 100% | 0 | 0 | 0 | 31226 | 0 | 31226 | 0 | 0 | India's National CFC consumption Phase-Out Plan with special refeence to the Refrigeration Service Sector was approved at the 42nd ExCom (IND/REF/42/INV/369).
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 369 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 414370 | 0 | 414370 | 414370 | 100% | 0 | 0 | 0 | 53868 | 0 | 53868 | 0 | 0 | The project infrastructure has been successfully established and all activites as per the the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 380 | A | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2006-01-01 | 2005-12-01 |  | 2006-04-01 | 2006-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 393 | A | I | CFC | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2007-04-01 | 2007-04-01 | 105090 | 0 | 105090 | 105090 | 100% | 0 | 0 | 0 | 13662 | 0 | 13662 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 404 | A | I | CFC | 158 | 358 | 0 |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2008-04-01 | 2009-04-01 | 436200 | 0 | 436200 | 436200 | 100% | 0 | 0 | 0 | 56706 | 0 | 56706 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 421 | A | I | CFC | 158 | 158 | 0 |  | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 | 2009-12-01 | 101078 | 0 | 101078 | 101078 | 100% | 0 | 0 | 0 | 13140 | 0 | 13140 | 0 | 0 | All activities as per the annual working plan have been accomplished. PCR is under preperation.
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | Individual | ASP | IRA | FOA | 34 | INV | 114 | A | I | CFC | 62 | 62 | 0 |  | 2001-07-01 | 2001-08-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 386260 | 0 | 386260 | 386260 | 100% | 0 | 0 | 0 | 50214 | 0 | 50214 | 0 | 0 | Project completed except for the certificate of destruction which is still outstanding. PCR was prepared and forwarded to the country for comment..
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | Individual | ASP | IRA | FOA | 35 | INV | 116 | A | I | CFC | 89 | 89 | 0 |  | 2001-12-01 | 2001-01-01 | 2003-05-01 |  | 2004-12-01 | 2007-12-01 | 499299 | 0 | 499299 | 499299 | 100% | 0 | 0 | 0 | 64909 | 0 | 64909 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector in 5 companies | Individual | ASP | IRA | FOA | 35 | PRP | 118 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-01-01 |  | 2002-09-01 | 2002-12-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 5 projects submitted and approved in Jul-02.
FIN | Germany | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group | Individual | ASP | IRA | FOA | 37 | INV | 150 | A | I | CFC | 23 | 23 | 0 |  | 2002-07-01 | 2002-10-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 335249 | 0 | 335249 | 335249 | 100% | 0 | 0 | 0 | 43582 | 0 | 43582 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company | Individual | ASP | IRA | FOA | 37 | INV | 151 | A | I | CFC | 77 | 77 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 387174 | 0 | 387174 | 387174 | 100% | 0 | 0 | 0 | 50333 | 0 | 50333 | 0 | 0 | Equipment has been delivered and installed, certificate of destruction was signed. Project is completed. PCR has been submitted for comment to the country.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | Individual | ASP | IRA | FOA | 37 | INV | 152 | A | I | CFC | 22 | 22 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2007-12-01 | 2009-12-01 | 185632 | -42000 | 143632 | 143632 | 100% | 0 | 0 | 0 | 24132 | -5459.96 | 18672 | 0.04 | 0 | NOU acknowledged destruction of old equipment in December 2007. PCR was approved by NOU in Oct-2009. Funds of USD 42.000 have been returned to MFS.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj | Individual | ASP | IRA | FOA | 37 | INV | 153 | A | I | CFC | 18.6 | 18.6 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 228310 | 0 | 228310 | 228310 | 100% | 0 | 0 | 0 | 29680 | 0 | 29680 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro | Individual | ASP | IRA | FOA | 37 | INV | 156 | A | I | CFC | 20.2 | 20.2 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 158166 | 0 | 158166 | 158166 | 100% | 0 | 0 | 0 | 20562 | 0 | 20562 | 0 | 0 | Project is completed. PCR was signed by NOU in June 2007 and submitted by end 2007.
FIN | Germany | Project preparation for the development of a foam sector strategy | Individual | ASP | IRA | FOA | 37 | PRP | 154 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  | 2002-12-01 | 2003-12-01 | 51850 | 0 | 51850 | 51850 | 100% | 0 | 0 | 0 | 6741 | 0 | 6741 | 0 | 0 | Project preparation lead to sector phase out strategy, included in NPOP approved at 41st ExCom.
ONG | Germany | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | IRA | FOA | 72 | PRP | 218 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 30000 | 9750 | 0 | 0 | 9750 |  | Visit to companies underway for review
FIN | Germany | Preparation of a national CFC phase-out plan | Individual | ASP | IRA | PHA | 39 | PRP | 159 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-04-01 | 2004-04-01 |  | 2003-11-01 | 2003-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | National Phase Out Plan has been submitted and appproved at the 41th meeting
FIN | Germany | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 160 | A | I | CFC | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 | 694124 | 946405 | 1640529 | 1640529 | 100% | 0 | 0 | 0 | 76354 | 104105 | 180459 | 0 | 0 | Activity progressed according to plan. So far, a total of 1500 ODP tons have been replaced with CFC-free technology. All of the funds have been disbursed and the targeted ODP phase out has been achieved. The tranche is completed, all outstanding certificates of destruction were handed in by december 2007.
FIN | Germany | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 169 | A | I | CFC | 0 | 0 | 0 |  | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2007-12-01 | 2007-12-01 | 479044 | 0 | 479044 | 479044 | 100% | 0 | 0 | 0 | 52695 | 0 | 52695 | 0 | 0 | Funds have been disbursed for the conversion of additional manufacturers in the foam sector. Certificates of destruction were handed in by Dec-2008.
FIN | Germany | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 176 | A | I | CFC | 30 | 30 | 0 |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2008-08-01 | 2011-09-01 | 1007124 | 0 | 1007124 | 1007124 | 100% | 0 | 0 | 0 | 110784 | 0 | 110784 | 0 | 0 | Funds have been disbursed for the conversion of manufacturers in the foam sector. Certificates of destruction will be collected and handed in during 2009.
FIN | Germany | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | INV | 181 | A | I | CFC | 250 | 250.3 | 0 |  | 2007-03-01 | 2007-04-01 | 2008-03-01 |  | 2009-04-01 | 2011-09-01 | 920868 | 0 | 920868 | 920868 | 100% | 0 | 0 | 0 | 101295 | 0 | 101295 | 0 | 0 | 4 tenders were contracted and production started for 2 machines by end of 2008. The other 2 installations were completed by end of 2009/ beginning 2010.
FIN | Germany | National CFC phase-out plan: 2008 annual implementation programme | Multi-Year | ASP | IRA | PHA | 54 | INV | 186 | A | I | CFC | 195.7 | 195.7 | 0 |  | 2008-04-01 | 2008-04-01 | 2009-03-01 |  | 2011-04-01 | 2011-09-01 | 729846 | 0 | 729846 | 729846 | 100% | 0 | 0 | 0 | 80283 | 0 | 80283 | 0 | 0 | project completed
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 190 | A | I | HCFC | 0 |  | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | HPMP was approved based on preparatory study
FIN | Germany | National CFC phase-out plan: 2009 annual implementation programme | Multi-Year | ASP | IRA | PHA | 57 | INV | 191 | A | I | CFC | 132.7 | 132.7 | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2011-04-01 | 2013-04-01 | 512208 | 0 | 512208 | 512208 | 100% | 0 | 0 | 0 | 56343 | 0 | 56343 | 0 |  | project finally completed, financial completion under way
FIN | Germany | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IRA | PHA | 57 | PRP | 192 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2011-04-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 |  | HPMP was approved based on preparatory study
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 201 | A | I | HCFC | 30.5 | 3 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 | 2015-05-01 |  |  | 1962400 | 0 | 1962400 | 1545090 | 78.73% | 417310 | 417310 | 417310 | 222664 | 0 | 175905 | 46759 | 46759 | Continuous Project Delay - follow up installation Karamadan - beneficiary USC opted out of conversion scheme and was replaced by the beneficiary Pakran, in agreement with MLFS - preparation of techical specification for tendering Arya Baron - technical assistance to the installation procedures | Final acceptance of equipment installation partially completed - all tendering finished, supply of equipment for Pakran and Elektrosteel Arya Baron planned for October 2015 - preparation of technical specifications for Behdor Rangin
COM | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 205 | A | I | HCFC | 1.2 | 0 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2013-12-01 |  | 100600 | 0 | 100600 | 100600 | 100% | 0 | 0 | 0 | 11415 | 0 | 11415 | 0 |  | 10 supermarkets for Demo projects selected - TORs completed - technical specifications elaborated - Workshop supermarkets organized in Oct. 2013 - | All planned activities completed
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 68 | INV | 207 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 | 2013-05-01 | 2015-12-01 | 2015-12-01 |  |  | 534233 | 0 | 534233 | 458930 | 85.9% | 75303 | 25482 | 75303 | 60617 | 0 | 52131 | 8486 | 8486 | Preparation and organisation of Interagency meeting with the service companies - follow up of pilot activities on leakage contracl and sealed systems design of supermarkets - preparation and organisation of workshop and technician training in servicing sector - elaboration of a technical guideline for servicing technicians | Editing of Iranian Cold Chain Study - follow up of converted supermarket (monitoring, leakage controll etc.) |  |  | INV
ONG | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRA | PHA | 72 | PRP | 214 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 5000 | 2600 | 0 | 0 | 2600 |  | Visit to companies underway for review
FIN | Germany | Comprehensive approach to disseminate soil solarization technology for methyl bromide substitution | Individual | ASP | JOR | FUM | 26 | DEM | 41 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-08-01 | 2002-01-01 | 232789 | 0 | 232789 | 232789 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completion report submitted
ONG | Germany | Complete phase-out of the use of methyl bromide in Jordan | Individual | ASP | JOR | FUM | 29 | INV | 54 | A | I | MBR | 180 | 164 | 0 |  | 1999-11-01 | 2000-03-01 | 2014-12-01 | 2015-12-01 |  |  | 3063000 | 0 | 3063000 | 3056904 | 99.8% | 6096 | 6096 | 6096 | 398190 | 0 | 397398 | 792 |  | Workshop for agricultrue engineering and farmers implemented - survey for Methyl Bromide project conducted - serious of farmer visits - continuous crosschecks of consumption versus quota/licence | follow up on implementation of licence and regulations
FIN | Germany | Development of an investment project for the phase out of methyl bromide in vegetable production | Individual | AFR | KEN | FUM | 30 | PRP | 23 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-08-01 | 2000-12-01 |  | 2002-11-01 | 2003-09-01 | 13360 | 0 | 13360 | 13360 | 100% | 0 | 0 | 0 | 1737 | 0 | 1737 | 0 | 0 | Project initially blocked by 30th ExCom Decision on Kenya. Work completed November 2002. Investtment project approved at 39th ExCom.
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) | Multi-Year | AFR | KEN | FUM | 39 | INV | 33 | A | I | MBR | 5 | 8 | 0 |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-04-01 | 2006-04-01 | 287247 | 0 | 287247 | 287247 | 100% | 0 | 0 | 0 | 37342 | 0 | 37342 | 0 | 0 | During 2004 the project staff was completed, a demonstration facility was set up in cooperation with the University of Nairobi, a very successful demonstration of substrates as alternative to MB was held at this facility. In sectors and areas where viable
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (second tranche) | Multi-Year | AFR | KEN | FUM | 42 | INV | 35 | A | I | MBR | 12 | 14.7 | 0 |  | 2004-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-12-01 | 2011-05-01 | 172347 | 0 | 172347 | 172347 | 100% | 0 | 0 | 0 | 22405 | 0 | 22405 | 0 | 0 | Second tranche approved at 42nd ExCom. During 2005 technology transfer activities continued through agreements with farms for the adoption of alternatives such as substrates, IPM and chemicals such as metham sodium.
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 41 | A | I | MBR | 17 | 9.7 | 0 |  | 2006-11-01 | 2007-01-01 | 2009-12-01 |  | 2010-01-01 | 2011-05-01 | 114898 | 0 | 114898 | 114898 | 100% | 0 | 0 | 0 | 14937 | 0 | 14937 | 0 | 0 | The Project has been completed. PCR submitted in September 2010
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | KEN | PHA | 58 | PRP | 49 | A | I | HCFC | 0 |  | 0 |  | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2012-04-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP document was finalised and was approved at the 66th Excom as bilateral contribution of France. | The HPMP is being successfully implemented.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | KEN | REF | 23 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | KEN | REF | 26 | TAS | 19 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. TPMP approved in Dec 2004
FIN | Germany | Recovery and recycling project | Individual | AFR | KEN | REF | 28 | TAS | 24 | A | I | CFC | 8.5 | 5 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2001-08-01 |  | 2004-05-01 | 2004-10-01 | 98725 | 0 | 98725 | 98725 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to the 44th Excom.
FIN | Germany | Project preparation for the RMP update | RMP Update | AFR | KEN | REF | 36 | TAS | 27 | A | I |  | 203.6 |  | 0 |  | 2002-03-01 | 2003-06-01 | 2003-03-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A TPMP developed through the preparation process was approved at the 44th ExCom
FIN | Germany | Project preparation for the solvent sector | Individual | AFR | KEN | SOL | 35 | PRP | 26 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2002-11-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed , investment project being implemented
FIN | Germany | Conversion of TCA based cleaning process to non-ODS alternatives at the Kenya Power and Lighting Company | Individual | AFR | KEN | SOL | 39 | INV | 32 | A | I | TCA | 1.9 | 1 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2004-10-01 |  | 2007-12-01 | 2009-09-01 | 85800 | -3112 | 82688 | 82688 | 100% | 0 | 0 | 0 | 11154 | -405 | 10749 | 0 | 0 | PCR was submitted sept 2009
CLO | Germany | Project preparation and technical assistance at Arnatoury S.A.R.L., Sin-El-Fil | Individual | ASP | LEB | ARS | 26 | PRP | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented
FIN | Germany | Training in improved operations, service and maintenance for refrigeration technicians in using hydrocarbons | Individual | ASP | LEB | REF | 26 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-09-01 | 2002-01-01 | 49500 | -8197 | 41303 | 41303 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | RMP | ASP | LEB | REF | 28 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2001-11-01 | 2003-10-01 | 37550 | -3 | 37547 | 37547 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Terminal CFC phase-out management plan (first tranche) | Multi-Year | AFR | LES | PHA | 41 | INV | 08 | A | I | CFC | 0.6 | 0.8 | 0 |  | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2005-03-01 | 2005-06-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Second tranche was requested for the TPMP.
FIN | Germany | Terminal CFC phase-out management plan (second tranche) | Multi-Year | AFR | LES | PHA | 45 | INV | 09 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2005-04-01 | 2005-04-01 | 2006-04-01 |  | 2007-12-01 | 2008-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | 3rd tranche was requested and approved.
FIN | Germany | Terminal CFC phase-out management plan (third tranche) | Multi-Year | AFR | LES | PHA | 50 | INV | 10 | A | I | CFC | 1.4 | 1.4 | 0 |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2009-11-01 | 2011-12-01 | 17300 | 0 | 17300 | 17300 | 100% | 0 | 0 | 0 | 2249 | 0 | 2249 | 0 | 0 | Project has been completed, Lesotho has achieved complete phase out as per the Agreement with the Excom on the TPMP.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | LES | PHA | 57 | PRP | 12 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-06-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP was prepared and submitted and approved at the 64th Excom. The document was developed following the completion of a detailed survey and stakeholder workshop.
COM | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LES | PHA | 64 | INV | 14 | A | I | HCFC | 0 | 0.6 | 0 |  | 2011-07-01 | 2011-08-01 | 2014-07-01 |  | 2014-12-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 |  | 58 technicians were trained in 2014 on best practices and safe handling of refrigerants. 6 recovery units have been provided. | Project completed.
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | LES | PHA | 73 | INV | 17 | A | I | HCFC | 0.35 | 0 | 0 |  | 2014-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 68000 | 0 | 68000 | 0 | 0% | 68000 | 0 | 15000 | 8840 | 0 | 0 | 8840 |  | Project approved in the last meeting of 2014. No activity conducted in 2014 | Advertising and support for the licensing and quota system. Stakeholder workshop planned for mid Aug 2015. |  |  | INV
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | LES | PHA | 73 | TAS | 18 | A | I | HCFC | 0 | 0 | 0 |  | 2014-11-01 |  | 2017-05-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 |  | Project approved in 2014, no activities conducted in 2014. | Advertising for verification consultants was completed. A consultant has been hired to start the verification process as per stipulated guidelines.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | LES | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-11-01 | 2004-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted TPMP submitted and approved at 41st Excom
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | LES | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed, TPMP approved at 41st Excom
FIN | Germany | Preparation of a HCFC phase-out management plan |  | AFR | LIR | PHA | 57 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP was submitted as planned in Dec 2010.
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LIR | PHA | 63 | INV | 18 | A | I | HCFC | 0.6 | 0.6 | 0 |  | 2011-04-01 | 2011-06-01 | 2015-03-01 | 2015-09-01 |  |  | 157500 | 0 | 157500 | 140504 | 89.21% | 16996 | 0 | 16996 | 20475 | 0 | 18223 | 2252 |  | Ebola outbreak in Liberia in 2014 led to a complete standstill for some time. However, NOU did conduct a technical training in Monrovia for 20 technicians. Also 7 recovery units were provided to the Refrigeration Association to be used among the industry. | Unfortunately the NOU suddenly passed away in 2015 which has created some delay, however, currently there are demonstration conversions to be conducted by trained technicians and with the involvement of the refrigeration association. The aim of these conversions is to help the country develop a code of practice for the R&AC industry when dealing with HCs. |  |  | INV
FIN | Germany | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector and recovery and recycling | RMP Update | AFR | LIR | REF | 41 | TAS | 04 | A | I | CFC | 10.1 | 10.1 | 0 |  | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2009-11-01 | 2011-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 12012 | 0 | 12012 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP Update | AFR | LIR | REF | 41 | TAS | 05 | A | I | CFC | 11.7 | 1.5 | 0 |  | 2003-12-01 | 2005-04-01 | 2008-12-01 |  | 2009-12-01 | 2011-12-01 | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 13996 | 0 | 13996 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: MAC recovery/recycling of CFC-12 | Individual | AFR | LIR | REF | 41 | TAS | 06 | A | I | CFC | 6.8 | 3 | 0 |  | 2003-12-01 | 2005-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 61858 | 0 | 61858 | 61858 | 100% | 0 | 0 | 0 | 8042 | 0 | 8042 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: monitoring the activities in the RMP | RMP Update | AFR | LIR | REF | 41 | TAS | 08 | A | I | CFC | 1.7 | 0 | 0 |  | 2003-12-01 | 2003-12-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 | 0 | 2009 | 0 | 2009 | 0 | 0 | PCR submitted in July 2010
FIN | Germany | Implementation of the RMP: training of trainers in code of good refrigeration practices and establishment of national refrigeration demonstration centre | Individual | AFR | LIR | REF | 41 | TRA | 03 | A | I |  | 13 | 13 | 0 |  | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | 0 | 119460 | 119460 | 100% | 0 | 0 | 0 | 15530 | 0 | 15530 | 0 | 0 | Project completed. PCR submitted in July 2010
FIN | Germany | Project preparation and technical assistance at Chem Tech | Individual | AFR | MAR | ARS | 26 | PRP | 09 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2001-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Investment project for phasing out CFCs at Chem Tech-Stella Industries, Port Louis | Individual | AFR | MAR | ARS | 27 | INV | 11 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-03-01 | 1999-03-01 | 1999-11-01 |  | 2001-06-01 | 2002-01-01 | 90400 | 0 | 90400 | 90400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted |  |  | 2000-12-01
FIN | Germany | Project preparation for the phase out of methyl bromide use | Individual | AFR | MAR | FUM | 37 | PRP | 13 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2002-10-01 | 2003-12-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 | 0 | 0 | 1430 | 0 | 1430 | 0 | 0 | A project proposal was prepared but not accepted by the beneficiary. Assistance of beneficiary will now be unter the TPMP approved at 41st ExCom.
FIN | Germany | Implementation of an ODS terminal phase out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 41 | INV | 15 | A | I | CFC | 0 | 2.6 | 0 |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-10-01 | 2006-04-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | 2 Hydrocarbon trainings have been conducted. NOU started the process of converting the New Court House through a subsidy scheme provided under the project. Next tranche has been approved.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 45 | INV | 16 | A | I | CFC | 2 | 2 | 0 |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2007-12-01 | 2008-04-01 | 62030 | 0 | 62030 | 62030 | 100% | 0 | 0 | 0 | 8064 | 0 | 8064 | 0 | 0 | 2nd tranche was approved.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (third tranche) | Multi-Year | AFR | MAR | PHA | 50 | INV | 18 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-03-01 | 2007-12-01 |  | 2010-08-01 | 2012-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | All activities under the TPMP have been completed.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | MAR | PHA | 55 | PRP | 20 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | HPMP submitted as planned in Dec 2010
COM | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 63 | INV | 21 | A | I | HCFC | 0 | 2.48 | 0 |  | 2011-04-01 | 2011-10-01 | 2014-03-01 |  | 2014-06-01 |  | 157050 | 0 | 157050 | 157050 | 100% | 0 | 0 | 0 | 18846 | 0 | 18846 | 0 |  | Specifications were developed and tender advertised for the CO2 demonstration unit for supermarkets to be installed at the local University. | Funds disbursed
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 72 | INV | 22 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2014-06-01 | 2017-05-01 | 2017-01-01 |  |  | 131400 | 0 | 131400 | 109482 | 83.32% | 21918 | 13000 | 13000 | 15851 | 0 | 13156 | 2695 |  | The CO2 demo system has been supplied. Some tools like pressure testing and flow meters were purchased for the local University. Trainer was invited to Germany to be trained on natural refrigerants (funded through non-MLF funds). Technical training curriculum has been adjusted to include natural refrigerants and safe handling of these refrigerants. Refresher customs training was conducted. | CO2 equipment installed. Training for local trainers and experts on CO2 system completed. |  |  | INV
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MAR | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1998-03-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MAR | REF | 26 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted TPMP approved at 41st Excom
FIN | Germany | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | Individual | AFR | MAR | REF | 28 | TAS | 12 | A | I | CFC | 8 | 5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-06-01 |  | 2005-12-01 | 2006-09-01 | 183377 | -3647 | 179730 | 179730 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certification of R&R center. Follow-up evaluation of the performance of recycling center. Recommendation that the training institue should cooperate with the local gas dealer in utilizing the facility. PCR was submitted in 2006.
FIN | Germany | Project preparation for a CFC terminal phase out management plan | Individual | AFR | MAR | REF | 37 | PRP | 14 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. TPMP approved at 41st Excom
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (HC demonstration and training) | Multi-Year | LAC | MEX | PHA | 73 | INV | 172 | A | I | HCFC | 4 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2020-12-01 |  |  | 325000 | 0 | 325000 |  | 0% | 325000 | 12000 | 12000 | 40750 | 0 | 0 | 40750 | 3000 | In 2014 no activities have been implemented yet. | Peparatory coordination works |  |  | INV
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MLW | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MLW | REF | 26 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | MLW | REF | 37 | PRP | 17 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2004-05-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP approved in June 04
FIN | Germany | Implementation of the RMP update: refrigeration and air-conditioning sector | Individual | AFR | MLW | REF | 43 | TAS | 20 | A | I |  | 49 | 0 | 0 |  | 2004-07-01 | 2004-10-01 | 2007-07-01 |  | 2007-12-01 | 2009-01-01 | 100000 | -561 | 99439 | 99439 | 100% | 0 | 0 | 0 | 13000 | -73 | 12927 | 0 | 0 | Project completed. PCR was submitted in September 2008. Remaining funds will be returned to the secretariat.
FIN | Germany | Three alternatives to the use of methyl bromide: enemy plants, organic amendments and grafting on resistant rootstocks in combination with an integrated pest management system in tomatoes and curcubits | Individual | AFR | MOR | FUM | 26 | DEM | 26 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 2001-10-01 | 2003-10-01 | 229523 | 0 | 229523 | 229523 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to 41st ExCom
FIN | Germany | Project preparation/technical assistance in the halon sector | Individual | AFR | MOR | HAL | 31 | PRP | 40 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2001-01-01 |  | 2004-12-01 | 2005-06-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project proposal completed and with consent of NOU transferred to UNIDO for implementation.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MOZ | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | MOZ | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | NAM | PHA | 37 | PRP | 08 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-09-01 | 2004-08-01 | 50250 | 0 | 50250 | 50250 | 100% | 0 | 0 | 0 | 6533 | 0 | 6533 | 0 | 0 | Project completed and TPMP approved at 41st Excom
FIN | Germany | Terminal phase-out management plan for CFCs | Multi-Year | AFR | NAM | PHA | 41 | INV | 10 | A | I | CFC | 9 | 10.5 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2008-05-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Namibia continues to maintain zero imports in keeping with the TPMP targets. In 2007, 3 additional customs training were organised to maintain vigilance and update the ASCUYDA ++ system. Incentive scheme is being implemented successfully with 42 cold rooms being retrofitted mainly at hospitals and schools (hostels). A total of 312 kgs of ODS has been phased out |  |  | 2006-12-01
FIN | Germany | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | NAM | PHA | 50 | INV | 12 | A | I | CFC | 3 | 3 | 0 |  | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-06-01 | 2012-12-01 | 92500 | 0 | 92500 | 92500 | 100% | 0 | 0 | 0 | 12025 | 0 | 12025 | 0 | 0 | All conversions under the incentive scheme have been completed. The project is completed and the final report is being drafted.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | NAM | PHA | 55 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP submitted as planned in Dec 2010
FIN | Germany | Preparation of a HCFC phase-out management plan (additional funding) |  | AFR | NAM | PHA | 57 | PRP | 15 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | HPMP submitted as planned in Dec 2010
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | NAM | PHA | 63 | INV | 17 | A | I | HCFC | 0.9 | 1.38 | 0 |  | 2011-04-01 | 2011-06-01 | 2014-03-01 | 2015-10-01 |  |  | 300000 | 0 | 300000 | 270791 | 90.26% | 29209 | 8700 | 20509 | 36333 | 0 | 32700 | 3633 |  | There has been some delay in implementation due to personnel changes at the NOU. In 2014, the recovery units and tools for good practices were distributed to the local industry for a 20% contribution to the costs . 7 technical trainings were conducted on best pratices and safe handling of HCs with substantial own contribution of VTCs that benefitted from receiving training equipment. | 30 demonstrations in various parts of the country are currently being conducted to show safe conversions. This is being done in cooperation with the local Refrigeration association and trained trainers. All necessary guidelines for safe handling of HCs are being followed and adhered, too. 5 customs trainings are being conducted as refresher courses given some instances of incorrect reporting of ODS imports.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | NAM | PHA | 71 | INV | 19 | A | I | HCFC | 4.23 |  | 0 |  | 2013-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 240000 | 0 | 240000 |  | 0% | 240000 | 0 | 20000 | 29067 | 0 | 0 | 29067 |  | Currently the funds available under the 1st tranche are being spent before the 2nd tranche is used. | Funds from the 1st tranche are still being spent before starting on 2nd tranche |  |  | INV
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | NAM | PHA | 73 | TAS | 21 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2017-05-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 10000 | 30000 | 3900 | 0 | 0 | 3900 |  | No activity was done in 2014 as project was approved at the end of the year. | An independent consultant has been hired to conduct the verification exercise. The verification is currently ongoing and is expected to be completed by end 2015.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | NAM | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Recuperation and recycling of CFC-12 integrated with the introduction of hydrocarbon technology in the service sector | Individual | AFR | NAM | REF | 24 | TAS | 05 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-06-01 |  | 1998-06-01 | 2000-01-01 | 34400 | -244 | 34156 | 34156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | NAM | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. TPMP approved in Dec 2003
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | AFR | NIR | HAL | 34 | PRP | 87 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 19420 | 0 | 19420 | 19420 | 100% | 0 | 0 | 0 | 2525 | 0 | 2525 | 0 | 0 | Project proposal submitted and approved by MF (37th ExCom).
FIN | Germany | Sectoral phase-out programme: establishing a halon bank | Individual | AFR | NIR | HAL | 37 | TAS | 103 | A | I | HAL | 285.3 | 285.3 | 0 |  | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2007-08-01 | 2008-10-01 | 499000 | 0 | 499000 | 499000 | 100% | 0 | 0 | 0 | 64870 | 0 | 64870 | 0 | 0 | Project is completed. PCR has been submitted to the MLF in October 2008.
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | ASP | OMA | HAL | 34 | PRP | 03 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-09-01 | 2002-01-01 |  | 2003-07-01 | 2003-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 | 0 | 2210 | 0 | 2210 | 0 | 0 | Int.consultant visited Oman, nat. consultants identified, Implemenation of the projects will be done by World Bank on request of Oman, results transferred to WB Jul-03. WB TAS-Project approved 41st ExCom.
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Azkcon Refrigeration Industries, Inc. | Individual | ASP | PHI | REF | 23 | INV | 53 | A | I | CFC | 18.9 | 18.9 | 0 |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2005-04-01 | 370258 | -75353 | 294905 | 294905 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is completed, PCR drafted by UNDP for completion and submission by GTZ. Remaining balance and interest (USD 75.353) has been returned in Dec-04 to GTZ to be reported and returned to MLF at the 45th ExCom.
FIN | Germany | Project preparation for the development of an ODS phase out action plan | Individual | ASP | PNG | PHA | 36 | PRP | 04 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | TPMP for PNG has been approved at the 39th ExCom
FIN | Germany | Terminal phase-out management plan for ODS (1st tranche) | Multi-Year | ASP | PNG | PHA | 39 | INV | 05 | A | I | CFC | 18 | 30.8 | 0 |  | 2003-04-01 | 2003-08-01 | 2005-12-01 |  | 2006-07-01 | 2006-12-01 | 480000 | 0 | 480000 | 480000 | 100% | 0 | 0 | 0 | 59700 | 0 | 59700 | 0 | 0 | PNG has successfully completed the 1st Action Plan of the TPMP and the country's consumption is well below the TPMP reduction targets.
FIN | Germany | Terminal phase-out management plan for ODS (2nd tranche) | Multi-Year | ASP | PNG | PHA | 48 | INV | 08 | A | I | CFC | 17 | 4.5 | 0 |  | 2006-04-01 | 2006-08-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | PNG has maintained compliance of zero CFC-imports. PNG has completed the incentive scheme. The final report is under preparation.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | PNG | PHA | 57 | PRP | 10 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP completed and approved
ONG | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | PNG | PHA | 63 | INV | 11 | A | I | HCFC | 0.2 | 0.2 | 0 |  | 2011-04-01 | 2011-07-01 | 2014-03-01 | 2016-11-01 |  |  | 350000 | 0 | 350000 | 315133 | 90.04% | 34867 | 18200 | 34867 | 41300 | 0 | 37170 | 4130 |  | There has been delay in implementation due to personnel changes at the Ozone office as well as a re-structuring of the once Department of Environment and Conservation being converted into the Conservation, Environment Protection Authority. Office moves and various changes in structures delayed implementation. However, 4 technical trainings on best practices have been conducted, awareness activities were organised, adverts and write ups in newspapers were done. Equipment for training institutions was provided. A stakeholder workshop was conducted to once again involve the industry into the HPMP activities more actively. | 2 technical trainings have been completed and a 3rd is still planned. Various awareness initiatives are being conducted i.e painting competition,merchandising, etc.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | PNG | PHA | 71 | INV | 12 | A | I | HCFC | 0.6 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2017-12-01 |  |  | 340000 | 0 | 340000 | 0 | 0% | 340000 | 0 | 0 | 40120 | 0 | 0 | 40120 |  | Currently the funds available under the 1st tranche are being utilised. | Funds still available from previous tranche which are being spent currently. |  |  | INV
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | PNG | PHA | 73 | TAS | 13 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2016-03-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 3900 | 0 | 0 | 3900 |  | Project was approved at the end of 2014 and therefore no action was taken in 2014 | NOU has advertised the TORS for the verification to find suitable consultants.
FIN | Germany | Extension of institutional strengthening project | Individual | ASP | PNG | SEV | 41 | INS | 06 | N | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-06-01 | 2005-12-01 |  | 2006-03-01 | 2006-06-01 | 39693 | 0 | 39693 | 39693 | 100% | 0 | 0 | 0 | 5160 | 0 | 5160 | 0 | 0 | ISP completed successfully.
FIN | Germany | Extension of the institutional strengthening project (phase III) | Individual | ASP | PNG | SEV | 48 | INS | 07 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-05-01 | 2008-04-01 |  | 2008-04-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | ISP completed successfully.
COM | Germany | Extension of the institutional strengthening project (phase IV) | Individual | ASP | PNG | SEV | 54 | INS | 09 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | The ISP has been completed and the next phase is now part of the exisiting HPMP
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | SEY | PHA | 58 | PRP | 15 | A | I | HCFC | 0 | 0 | 0 |  | 2009-07-01 | 2009-09-01 | 2010-07-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP dafted and approved.
COM | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 63 | INV | 17 | A | I | HCFC | 0.4 | 0.4 | 0.4 |  | 2011-04-01 | 2011-06-01 | 2013-03-01 |  | 2014-09-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 |  | 0 | 25333 | 0 | 25333 | 0 |  | Rather slow implementation since 2013. Office equipment and spares for the idenitfiers were requested, these were supplied. 2 technician trainings were conducted on best practices and safe use of HCs. Energy analysis was comissioned of the University building planned for demonstrating solar ACs was conducted.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 70 | INV | 19 | A | I | HCFC | 0.4 |  | 0 |  | 2013-07-01 | 2014-10-01 | 2015-07-01 | 2015-12-01 |  |  | 160000 | 0 | 160000 | 37915 | 23.7% | 122085 | 0 | 100000 | 20267 | 0 | 4864 | 15403 |  | Detailed specifications for the tender for the demo project for solar AC were developed. A fulltime NOU assistant has been hired to assist with the project activities. | Customs training has been completed. Tender for the solar AC is currently being evaluated. |  |  | INV
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SEY | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-03-01 | 2001-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SEY | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. RMP Update ongoing
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SEY | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-07-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved
FIN | Germany | Phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | SEY | REF | 40 | TAS | 08 | A | I |  | 2.4 | 2.4 | 0 |  | 2003-07-01 | 2003-10-01 | 2006-12-01 |  | 2006-12-01 | 2007-10-01 | 41607 | 0 | 41607 | 41607 | 100% | 0 | 0 | 0 | 5409 | 0 | 5409 | 0 | 0 | PCR has been submitted in October 2007.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SWA | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SWA | REF | 26 | TAS | 05 | A | I | CFC | 4 | 1.5 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 90375 | 0 | 90375 | 90375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted. RMP update ongoing
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SWA | REF | 37 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2003-08-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. RMP update approved at 41st Excom
FIN | Germany | Implementation of the RMP update | RMP Update | AFR | SWA | REF | 41 | TAS | 08 | A | I |  | 20.9 | 20.9 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2009-10-01 | 2011-10-01 | 74295 | 0 | 74295 | 74295 | 100% | 0 | 0 | 0 | 9658 | 0 | 9658 | 0 | 0 | A new NOU was appointed in 2009. The final customs training as last outstanding project activity was completed. PCR sent in September 2010.
FIN | Germany | Project preparation/technical assistance in soil fumigants (methyl bromide) | Individual | ASP | SYR | FUM | 32 | PRP | 70 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2001-09-01 | 2002-03-01 | 37200 | 0 | 37200 | 37200 | 100% | 0 | 0 | 0 | 4836 | 0 | 4836 | 0 | 0 | Project preparation led to project proposal for implementation, which was not accepted because of quantities of illegal MB. Syria is currently complying with its obligations. Only 8 ODP tons will still be eligeable in the future.
FIN | Germany | Development of halon banking management plan | Halon banking | ASP | SYR | HAL | 29 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2000-05-01 |  | 2000-05-01 | 2002-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 | 0 | 0 | 1396 | 0 | 1396 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Individual | ASP | SYR | HAL | 34 | TAS | 77 | A | I | HAL | 284.5 | 284.5 | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2005-12-01 | 2007-12-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project is completed. PCR was submitted in 2007.
FIN | Germany | Implementation of the RMP: national recovery and recycling network | Individual | ASP | SYR | REF | 30 | TAS | 59 | A | I | CFC | 120 | 120 | 0 |  | 2000-03-01 | 2000-11-01 | 2002-04-01 |  | 2008-05-01 | 2009-12-01 | 742146 | 0 | 742146 | 742146 | 100% | 0 | 0 | 0 | 96479 | 0 | 96479 | 0 | 0 | All activities which were planned for 2007 (report, guide book version) were finalized and remaining project funds were allocated for additional refrigeration equipment. The project activities are completed and PCR was submitted to MLF in 2009.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | UGA | REF | 23 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | UGA | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved in Dec 2004
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | UGA | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completetd. RMP update approved at 44th ExCom
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | URT | REF | 26 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Recovery and recycling of CFCs | Individual | AFR | URT | REF | 36 | TAS | 14 | A | I | CFC | 11.7 | 11.7 | 0 |  | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2008-08-01 | 2009-12-01 | 164223 | -9924 | 154299 | 154299 | 100% | 0 | 0 | 0 | 21349 | -1290.12 | 20059 | -0.12 | 0 | Under the contract the only remaining activity is the construction of the recovery and recycling center. As the local partner cannot give a concrete date of finalization of the construction we suggested to declare the project completed and return the rest of the fund to the MLF. NOU agreed to the PCR in Nov-2008. PCR has been submitted to MLF in Apr-2009. Funds will be returned to MLF.
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | URT | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-06-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A RMP update was submitted by Tanzania in 2005
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector | Individual | ASP | YEM | FUM | 34 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
FIN | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | I | MBR | 9.1 | 17.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2008-04-01 | 2009-10-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Farmers were trained in the usage of MB alternatives. More field visits to farmers promoting MB alternatives took place. All project activities were successfully completed. The PCR has been prepared.
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 1) | Multi-Year | ASP | YEM | FUM | 56 | INV | 32 | A | I | MBR | 5.9 | 4.8 | 0 |  | 2008-11-01 | 2008-11-01 | 2014-12-01 |  | 2010-12-01 |  | 109740 | 0 | 109740 | 109740 | 100% | 0 | 0 | 0 | 13896 | 0 | 13896 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 2) | Multi-Year | ASP | YEM | FUM | 57 | INV | 33 | A | I | MBR | 0 | 5.4 | 0 |  | 2009-04-01 | 2009-05-01 | 2014-12-01 |  | 2010-12-01 |  | 91710 | 0 | 91710 | 91710 | 100% | 0 | 0 | 0 | 11613 | 0 | 11613 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | Germany | Terminal phase-out of methyl bromide (second tranche) | Multi-Year | ASP | YEM | FUM | 62 | INV | 37 | A | I | MBR | 10 | 8.5 | 0 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 |  | 2013-08-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25325 | 0 | 25325 | 0 |  | Remaining funds from 2013 were spent in 2014
ONG | Germany | Terminal phase-out of methyl bromide (third tranche) | Multi-Year | ASP | YEM | FUM | 68 | INV | 41 | A | I | MBR | 10 | 11 | 0 |  | 2012-12-01 | 2013-08-01 | 2014-12-01 | 2015-07-01 |  |  | 200000 | 0 | 200000 | 198000 | 99% | 2000 | 0 | 2000 | 25325 | 0 | 25072 | 253 |  | The most important achievements within the reporting year 2014 can be briefed as follows: In according to agreement with Yemen Nabat for Agriculture & Development (Y.Nabat) two agricultural engineers were trained on grafting in Jordan, a modern grafting machine was imported and Y. Nabat nurseries started growing grafted nurses. On-farm training workshop on solarization, biofumigation, grafting, soilless as MBr alternatives for 32 participants was convened at the farm of Y.Nabat in Dhamar. In addition to fifteen-onsite trainings on biofumigation by radish seeds were implemented in Sadah, Dhamar, Al-Mahweet, Amran and Sana'a. Two training sessions covered by Alsaedah TV. 265 plastic sheets were distributed for eligible farmers to encourage using solarization and biofumigation technologies at 265 farms. Morover, 30 farmers received radish seeds in order to use it in combination with solarization in cold areas in Yemen. 102 farmers and 15 extentionists in several governorates trained on biofumigation, 6 farmers in Amran Governorate trained on soilless and five women trained at Sana'a & 2 agricultural engineers trained in Jordan on grafting technology. Methyl bromide consumption phase-out that achieved in 2014 was approximately 11 ODP tones. However, for meeting the 2015 control measures of the Montreal Protocol, necessary measures and procedures for amending "Cabinet Decree # (275) on controlling of ODSs" were followed in order to accommodate banning on MBr Importation. Consequently, Decree of Environment Protection Authority # (63) was issued on December 23, 2014. The Decree amendment prohibited the importation of methyl bromide for soil fumigation by January 1st, 2015. Furthermore, the Decree immediately circulated officially to the related institutions such as the Cabinet, Custom Authority, Yemen Standardization, Metrology, & Quality Control Organization, Ministry of Agriculture, Ministry of Finance, Ministry of Water and Environment, Ministry of Industry & Trade and Plant Protection. | Commercial production of grafted nurses is expected to take place in second half of 2015.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 07 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZAM | REF | 26 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ZAM | REF | 37 | PRP | 12 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting
FIN | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | RMP Update | AFR | ZAM | REF | 42 | TAS | 13 | A | I |  | 23.3 | 23.3 | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 |  | 2009-10-01 | 2011-12-01 | 136000 | -7474 | 128526 | 128526 | 100% | 0 | 0 | 0 | 17680 | -971.62 | 16708 | 0.38 | 0 | funds returned to MLF at 65th meeting (UNEP/ozL.Pro/ExCom/65/60 Annex IV
FIN | Germany | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | ZIM | FOA | 63 | PRP | 43 | A | I | HCFC | 0 |  | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Zimbabwe identified foam manufacturers who were using pre-blended polyols and a conversion project for the manufacturers was developed and included into the HPMP, which was approved by the Excom at the 65th Excom.
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | ZIM | PHA | 37 | PRP | 25 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 | 0 | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom
FIN | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2007-06-01 | 2007-10-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Project was completed and the 2nd tranche approved in March 2007
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, first tranche) | Multi-Year | AFR | ZIM | PHA | 51 | INV | 38 | A | I |  | 25 | 25 | 0 |  | 2007-03-01 | 2007-04-01 | 2009-12-01 |  | 2008-07-01 | 2008-10-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | Phase completed and 3rd tranche approved
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, second tranche) | Multi-Year | AFR | ZIM | PHA | 54 | INV | 39 | A | I | CFC | 20 | 20 | 0 |  | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2009-03-01 |  | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 20 additional conversions under the incentive scheme were completed and 3 customs trainings were conducted.
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, third tranche) | Multi-Year | AFR | ZIM | PHA | 57 | INV | 40 | A | I | CFC | 20 |  | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-06-01 |  | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 4 customs officers were trained. 61 technicans were trained in state of the art refrigeration servicing. 160 commercial refrigeration units were converted under the incentive scheme. 785 kgs of CFC refrigerant were recovered.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 59 | PRP | 42 | A | I | HCFC | 0 |  | 0 |  | 2009-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | A comprehensive survey of the R&AC use was conducted and information put together into the HPMP which included both foam and R&AC components. The project was approved at the 65th Excom.
COM | Germany | National phase-out of Annex A (Group I) substances (phase II, fourth tranche) | Multi-Year | AFR | ZIM | PHA | 60 | INV | 42 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-04-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5108 | 0 | 5108 | 0 | 0 | Zimbabwe conducted 2 technican trainings targetting 27 participants as well as 1 customs training for 21 officers on the use of idenitifers capable of monitoring blends.
COM | Germany | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing sector:Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 44 | A | I | HCFC | 4 | 4 | 0 |  | 2011-11-01 | 2011-12-01 | 2013-11-01 |  | 2014-06-01 |  | 3737 | 311173 | 314910 | 314910 | 100% | 0 | 0 | 0 | 486 | 37213 | 37699 | 0 |  | 3 companies received the planned equipment to phase out HCFC use.
COM | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 45 | A | I | HCFC | 0 | 3.6 | 0 |  | 2011-11-01 | 2012-01-01 | 2013-11-01 |  | 2014-06-01 |  | 3737 | 108244 | 111981 | 111981 | 100% | 0 | 0 | 0 | 486 | 12945 | 13431 | 0 |  | 8 VTCs received the training equipment which was requested to conduct hands-on training. Zimbabwe trainers also participated in the regional train the trainers programme in Mauritius and have conducted 4 technician training courses. | Project has been completed. 2nd tranche has been approved at the 71st excom.
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (conversion of the foam manufacturing sector: Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 47 | A | I | HCFC | 2.1 | 2.1 | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 | 2015-12-01 |  |  | 166762 | 0 | 166762 | 162890 | 97.68% | 3872 | 0 | 3872 | 19949 | 0 | 19550 | 399 |  | Equipment installed and comissioned. Companies have phased out R141b use. Training for engineers from the other companies on alternatives completed. | Final monitoring of the phase out of HCFC use and technical support to the companies to comply.
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 48 | A | I | HCFC | 1.8 |  | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 | 2015-12-01 |  |  | 109165 | 0 | 109165 | 92740 | 84.95% | 16425 | 0 | 16425 | 13059 | 0 | 11100 | 1959 |  | 5 technician trainings were completed. 20 recovery units were distributed on cost sharing basis to the industry, monitoring of the recovery network by NOU, development of a code of practice for the R&AC association to ensure standardised practices in the industry. Assistance for developing a technicians certification scheme. The country is meeting its ODS reduction limits with good enforcement and controls. | 2 technicians trainings have been completed and a customs refresher training has been completed already in 2015 |  |  | INV
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZIM | REF | 26 | TAS | 15 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | Hungary | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 02 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 41145 | 0 | 41145 | 41145 | 100% | 0 |  |  | 5349 | 0 | 5349 | 0
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Project prepared, submitted and then approved at the 44th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | D | CFC | 2 | 3 | 0 | 0 | 2004-12-01 | 2012-05-01 | 2006-12-01 |  | 2011-12-01 | 2012-05-01 | 69400 | -6413 | 62987 | 62987 | 100% | 0 | 0 |  | 6246 | -577 | 5668.83 | 0.17 | 0.17 | Project operationally completed (Dec. 11) and financially closed (May 12). |  |  |  | INV | 0
FIN | IBRD | CFC phase-out management plan (second tranche) | Multiyear | LAC | ANT | PHA | 61 | INV | 13 | N | D |  | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-05-01 | 27900 | -27900 | 0 | 0 |  | 0 | 0 |  | 2511 | -2511 | 0 | 0 | 0 | Project operationally completed (link to ANT/PHA/61/INV/13) Dec. 11 and financially closed May 12. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 | 2006-07-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 |  | 2005-02-01 | 2006-07-01 | 160160 | 0 | 160160 | 160160 | 100% | 0 | 0 |  | 20820.8 | 0 | 20820.8 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
CLO | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 |  |  | 2005-11-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 750 | -750 | 0 | 0 | 0 | Funds returned to the 47th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of MDI phase-out plan |  | LAC | ARG | ARS | 45 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2008-12-01 | 2005-12-01 |  | 2008-12-01 | 2008-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | With World Bank assistance an Argentinian Strategy for MDIs was prepared, presented to and approved at the 56th ExCom. |  |  |  | Non-INV | 0
COM | IBRD | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | ARG | ARS | 56 | INV | 159 | N | I | CFC | 118.4 | 118.4 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2012-01-31 |  | 2014-12-01 | 2014-12-01 | 2806874 | 0 | 2806874 | 2731985 | 97.33% | 74889 | 0 | 0 | 210516 | 0 | 204899.31 | 5616.69 | 5616.69 | Project completed. |  |  | 2014-12-01 | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100% | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities in the foam sector |  | LAC | ARG | FOA | 64 | PRP | 166 | A | D |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2012-04-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project approved along with the Argentina HPMP (UNIDO) at the 66th ExCom in April. |  |  |  | Non-INV | 0
CLO | IBRD | Preparation for HCFC phase-out investment activities in the foam sector (additional funding) |  | LAC | ARG | FOA | 65 | PRP | 167 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-06-30 |  |  | 2013-03-01 | 120000 | -108561 | 11439 | 11439 | 100% | 0 | 0 |  | 9000 | -8142 | 857.92 | 0.08 | 0.08 | Remainder of the preparatory funds returned to the 71st ExCom per Dec. 70/7. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 |  | 2013-06-01 | 2013-06-01 | 375000 | -62672 | 312328 | 312328 | 100% | 0 | 0 |  | 48750 | -8147.36 | 40602.64 | 0 | 0 | Project closed in 2013 following INTA's submission of a final report that clarified findings and informed of satisfactory results in both the cotton (phosphine and carbon disulfide) and citrus trials (phosphine and cold storage chambers). Despite positive results generated under lab conditions, it was determined that substitutes were not viable at commercial scale given toxicity and safety considerations and long periods of inactivity required for use of cold chambers. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | I | HAL | 200 | 200 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 |  | 2010-12-31 | 2012-07-01 | 290620 | -112794.54 | 177825.46 | 177825.46 | 100% | 0 | 0 |  | 37780.6 | -14663.3 | 23117.3 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 work programme | Multiyear | LAC | ARG | PHA | 47 | INV | 148 | N | I | CFC | 1.5 | 1.5 | 0 | 0 | 2005-11-01 | 2009-12-01 | 2006-12-01 |  | 2013-12-01 | 2013-12-01 | 500000 | -368019.6 | 131980.4 | 131980.4 | 100% | 0 | 0 |  | 37500 | -27600 | 9900 | 0 | 0 | Given overall economic situation in Argentina and the requirement imposed by Dec. 70/7, it was not possible to initiate and finalize the chiller replacements that were planned during 2013. Only one chiller conversion agreement was finalized by the end of 2013: ALPARGATAS, 4 chillers. Project was closed 31 Dec. 2013. |  |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the production of polyurethane rigid insulation foam for domestic refrigerators at Mabe) | Multiyear | LAC | ARG | PHA | 66 | INV | 171 | N | I | HCFC | 18.46 | 18.46 | 0 | 0 | 2012-04-01 |  | 2013-04-30 | 2015-11-01 |  |  | 838612 | 0 | 838612 | 0 | 0% | 838612 | 838612 | 600000 | 62896 | 0 | 0 | 62896 | 62896 | During 2014, actual project execution remained pending as the GoA countersigned the HCFC Project's Grant Agreement (GA) for Ministry of Industry only on Dec. 19, 2014. Mabe has proceeded with implementation despite the lack of effectiveness of the overall Grant Agreement (GA) as of the end of 2014. Conversion completed and phase-out achieved. Enterprise will be compensated retroactively. | The HCFC Project with the Ministry of Industry became effective on Jan. 30, 2015. However, no further advance has been reached as the Minister of Industry has not signed the decree that reestablishes the PCU after the CFC project closed execution on Dec. 30, 2014, and the grace period on Apr. 30, 2015. WB conducted a supervision mission in May 2015 in order to prompt project operalization and carry out a technical verification visit to the Mabe plant in San Luis to verify completion. Phaseout achieved. The Ministry of Industry was given until Jun. 30, 2015 to reestablish the PCU. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (monitoring and reporting of HCFC-22 production) | Multiyear | LAC | ARG | PHA | 66 | TAS | 170 | N | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2013-04-30 | 2015-12-01 |  |  | 76000 | 0 | 76000 | 0 | 0% | 76000 | 76000 | 14000 | 5700 | 0 | 0 | 5700 | 5700 | During 2014, actual project execution remained pending as the GoA countersigned the HCFC Project's Grant Agreement (GA) for Ministry of Industry only on Dec. 19, 2014. During 2014, UEPRO continued carrying out office-based monitoring and reporting of national HCFC-22 production, based on production and input information provided by the only producer, FIASA S.A. UEPRO has shared the complete 2014 monitoring reports with the NOU and WBG, stating the FIASA S.A. being in compliance with its production limits set out in the HPMP. | The HCFC Project with the Ministry of Industry became effective on Jan. 30, 2015. However, no further advance has been reached as the Minister of Industry has not signed the decree that reestablishes the PCU after the CFC project closed execution on Dec. 30, 2014, and the grace period on Ap 30, 2015. WB conducted a supervision mission in May 2015 in order to prompt project operalization and carry out a technical verification visit to the Mabe plant in San Luis. The Ministry of Industry was given until June 30, 2015 to reestablish the PCU. |  |  | Non-INV | 0
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 20000 | 0 | 20000 | 0 | 0 | An accounting and technical monitoring was carried out to verify that no CFCs were produced during 2009, and it was verified that the plant didn't operate during that period. The entire production sector project is 100% completed within expected deadlines, including destruction of equipment. Funds were fully disbursed according to the disbursement schedule and prior annual audits –technical and financial- according to UNEP’s regulations. Production cessation initially expected to be done by 2010 was done by 2007, when the company ceased definitely producing CFCs. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2004-12-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2010-11-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 200000 | 0 | 200000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2005 annual programme | Multiyear | LAC | ARG | PRO | 45 | INV | 143 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2005-04-01 | 2007-09-01 | 2006-04-01 |  | 2006-04-01 | 2010-11-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2006 annual programme | Multiyear | LAC | ARG | PRO | 50 | INV | 151 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-10-01 |  | 2007-10-01 | 2010-11-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 100000 | 0 | 100000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2007 annual programme | Multiyear | LAC | ARG | PRO | 53 | INV | 154 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2008-03-01 | 2010-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Accelerated phase-out plan for CFC production | Multiyear | LAC | ARG | PRO | 53 | INV | 155 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2008-03-01 | 2010-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2008 annual programme | Multiyear | LAC | ARG | PRO | 54 | INV | 156 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-04-01 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2009 annual programme | Multiyear | LAC | ARG | PRO | 57 | INV | 160 | N | I | CFC | 0 | 0 | 274 | 274 | 2009-04-01 | 2009-12-31 | 2010-03-31 |  | 2009-12-31 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 47000 | 0 | 47000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. PCR was sent to ExCom. |  |  | 1999-08-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1999-08-01 | INV | 0
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | 2000-03-01 | INV | 0
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 |  | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV | 0
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 |  | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV | 0
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100% | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | Project completed. |  |  | 2001-09-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100% | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | 1999-10-01 | INV | 0
FIN | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 |  | 2012-08-01 | 2012-08-01 | 686370 | 0 | 686370 | 686370 | 100% | 0 | 0 |  | 89228.1 | 0 | 89228.1 | 0 | 0 | On Aug. 22, 2012 a UEPRO representative visited Neba/Ikala and verified destruction of CFC-based equipment. With this verification action the project is completed. |  |  | 2001-09-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100% | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | 2000-11-01 | INV | 0
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 |  | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | Project cancelled at the 40th ExCom. |  |  | 1997-11-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100% | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | Project financially and physically completed. |  |  | 2000-01-01 | INV | 0
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100% | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | Project completed and funding disbursed. PCR submitted Dec. 01. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 |  | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | Cancelled - 37th ExCom |  |  |  | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 |  | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. |  |  |  | INV | 0
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | Completed. PCR has been sent |  |  |  | INV | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100% | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program was completed and presented at the 13th E.C. meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transfered to UNDP |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 |  | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | Cancelled - 38th ExCom |  |  |  | INV | 0
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -183607 | 88550 | 88550 | 100% | 0 | 0 |  | 35380.41 | -23868.91 | 11511.5 | 0 | 0 | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100% | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | Completed. PCR submitted Feb. 01. |  |  |  | INV | 0
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 04 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 08 | N | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 | 2009-06-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 |  | 31200 | 0 | 31200 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2005-12-01 | 2009-06-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal phase-out management plan: 2006-2007 biennial programme | Multiyear | LAC | BHA | PHA | 51 | INV | 14 | N | I | CFC | 25 | 25 | 0 | 0 | 2007-03-01 | 2009-06-01 | 2009-03-01 |  | 2009-01-01 | 2009-06-01 | 120000 | -29054 | 90946 | 90946 | 100% | 0 | 0 |  | 15600 | -3777.02 | 11822.98 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100% | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | Complete. |  |  | 1998-07-01 | INV | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 |  | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | Cancelled. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100% | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100% | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | All three foaming machines now installed and in routine operation. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 |  | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | Cancelled. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  | 1999-12-01 | Non-INV | 0
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100% | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. |  |  |  | Non-INV | 0
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1999-12-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | 1994-07-01 | INV | 0
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 100% | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100% | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100% | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | Refrigeration equipment installed and operating. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100% | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 |  | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100% | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | Refrigeration equipment acquired and installed. 134a production began May 98. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100% | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 |  | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1998-06-01 | INV | 0
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 |  | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 07 | INV | 19 | N | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Foam project |  |  | 1996-10-01 | INV | 0
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 07 | INV | 20 | N | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 07 | INV | 23 | N | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 07 | INV | 28 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV | 0
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 07 | INV | 29 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from Inventory |  |  | 1997-03-01 | INV | 0
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 07 | INV | 30 | N | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 07 | INV | 31 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2006-12-01 | 2007-06-01 | 348130 | -73.55 | 348056.45 | 348056.45 | 100% | 0 | 0 |  | 45256.9 | -9.57 | 45247.33 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of the whole umbrella project in Jun 07. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | The proposal is being prepare by the Bank and the INIA |  |  |  | Non-INV | 0
CLO | IBRD | Phase-out of all the remaining uses of methyl bromide in soil application pest control (first tranche) | Multiyear | LAC | CHI | FUM | 45 | INV | 158 | N | I | MBR | 1.3 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-07-01 | 691703 | -691703 | 0 | 0 |  | 0 | 0 |  | 51878 | -51878 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV | 0
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Proposal will be submitted to the 42nd ExCom Meeting. |  |  |  | Non-INV | 0
TRF | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 |  |  | 2007-03-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project transferred to UNDP in 2007 at the 51st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 07 | INV | 04 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 | 2007-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  | 2000-05-01 | INV | 0
FIN | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 | 2007-06-01 | 2800000 | -1512624 | 1287376 | 1287376 | 100% | 0 | 0 |  | 318000 | -166389 | 151611 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  |  | INV | 0
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 07 | INV | 18 | N | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-01 | INV | 0
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 07 | INV | 21 | N | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-01 | INV | 0
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 07 | INV | 24 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 07 | INV | 25 | N | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 07 | INV | 26 | N | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 07 | INV | 27 | N | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 07 | TAS | 22 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 04 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 07 | INS | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 100% | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-01 | Non-INV | 0
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 07 | TAS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-06-01 | Non-INV | 0
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 07 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 100% | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-07-01 | Non-INV | 0
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 07 | TRA | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 09 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Funds committed in CY96 were disbursed in CY97. |  |  |  | Non-INV | 0
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100% | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | Completed |  |  | 1998-10-01 | Non-INV | 0
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Newly approved. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | I | CFC | 15.42 | 15.42 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0 | Phase V of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of the institutional strengthening project (phase VI, second year) | Individual | LAC | CHI | SEV | 45 | INS | 157 | N | I | CFC | 7.7 | 7.7 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening (phase VI, year 2) | Individual | LAC | CHI | SEV | 47 | INS | 159 | N | D | CFC | 7.7 | 7.7 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2006-12-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100% | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | Project has been fully executed. PCR is being revised for submission. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100% | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | Project fully completed during the last trimester of 2002. PCR is being prepared. |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100% | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | Project has been financially completed. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 |  | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | Project cancelled and funds returned at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100% | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 |  | 2005-01-01 | 2005-08-01 | 584727 | -170557 | 414170 | 414170 | 100% | 0 | 0 |  | 74319.97 | -21678.14 | 52641.83 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
TRF | IBRD | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 47 | INV | 64 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 |  |  | 2006-04-01 | 114480 | -114480 | 0 | 0 |  | 0 | 0 |  | 10303 | -10303 | 0 | 0 | 0 | All project funds and support costs were transferred to UNDP at 48th Meeting. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100% | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | Project has been fully executed. PCR being prepared. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100% | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100% | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | I | CFC | 25.8 | 7.85 | 0 | 0 | 2002-11-01 | 2005-12-01 | 2004-12-01 |  | 2005-10-01 | 2005-12-01 | 211636 | -130071 | 81565 | 81565 | 100% | 0 | 0 |  | 27512.68 | -16909.24 | 10603.44 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100% | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100% | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  |  |  | Non-INV | 0
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 14 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 23 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 29th ExCom. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100% | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2005-07-01 |  | 2007-03-01 | 2007-07-01 | 135500 | 0 | 135500 | 135500 | 100% | 0 | 0 |  | 10163 | 0 | 10163 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV | 0
ONG | IBRD | Phase-out of CFC consumption in the pharmaceutical aerosol sector (2007-2008 biennial programme) | One off phaseout | ASP | CPR | ARS | 51 | INV | 447 | N | I | CFC | 485.1 | 485.1 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2011-03-01 | 2015-06-01 |  |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | Project in the last stages and expected to be completed by end June 15. 98% of the funds disbursed. Training workshop on new substitute specifications, TA, and administration of enterprise conversions continuously conducted. All pharmaceutical aerosol enterprises completed conversion and registered new CFC-free products and cancelled registration of CFC-based products. Contract amendments signed with 16 enterprises for further financial support for trial production and market promotion. Capacity building at the national and provincial levels undertaken. Lab testing equipment and calibration standard gas provided to facilitate alternatives' testing and producer's registration tests. By end 2014, only payments for one consulting contract and import calibration standard gas were remaining. | All remaining payments have been completed except the last payment for the calibration standard gas which is under process and is to be done by mid-June. |  |  | INV | 0
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | CPR | ARS | 62 | TAS | 505 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Verification of 2010 CFC production for EUN consumption was conducted in accordance with Dec. 60/47 at the only one remaining CFC producer starting in May 11. Report submitted to the 65th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 07 | INV | 15 | N | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. ODP phaseout target reached. |  |  | 1995-09-01 | INV | 0
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 07 | INV | 16 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1996-01-01 | INV | 0
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1995-09-01 | INV | 0
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1996-03-01 | INV | 0
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1994-08-01 | INV | 0
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1996-06-01 | INV | 0
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1994-03-01 | INV | 0
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | 1995-09-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 27th ExCom. |  |  | 1997-02-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 31th ExCom. |  |  | 1997-02-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to 30th ExCom. |  |  | 1999-01-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom in January 1999. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the 30th ExCom. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted December 2000. |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted to ExCom. |  |  | 1999-08-01 | INV | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100% | 0 | 0 |  | 41675.79 | -11 | 41665 | -0.21 | -0.21 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100% | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | Project completed; PCR submitted December 2000. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100% | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100% | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100% | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | Project completed. PCR will be submitted in January 2001. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100% | -0.29 | -0.29 |  | 27209 | 0 | 27209.04 | -0.04 | -0.04 | Project completed; PCR submitted. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100% | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | Project complete; PCR submitted to 29th ExCOM. |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100% | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | Project completed; PCR submitted to 29th ExCOM. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 |  | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100% | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 |  |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 |  | 2005-04-01 | 2005-01-01 | 301000 | 0 | 301000 | 301000 | 100% | 0 | 0 |  | 39130 | 0 | 39130 | 0 | 0 | Project completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100% | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100% | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100% | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 |  |  |  |  | INV | 0
FIN | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 |  | 2005-03-01 | 2005-08-01 | 743500 | 0 | 743500 | 743500 | 100% | 0 | 0 |  | 91785 | 0 | 91785 | 0 | 0 | Completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 |  | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100% | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | Physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100% | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 | 2005-04-01 | 536403 | 0 | 536403 | 536403 | 100% | 0 | 0 |  | 69004.33 | 0 | 69004.33 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100% | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100% | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100% | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100% | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 | 2005-03-01 | 525483 | 0 | 525483 | 525483 | 100% | 0 | 0 |  | 67803.13 | 0 | 67803.13 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 | 2005-04-01 | 473480 | 0 | 473480 | 473480 | 100% | 0 | 0 |  | 61552.4 | 0 | 61552.4 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100% | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100% | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100% | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | Project physically and financially completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 | 2005-04-01 | 440461 | 0 | 440461 | 440461 | 100% | 0 | 0 |  | 57259.93 | 0 | 57259.93 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100% | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100% | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 |  | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 1.0459e-11 | 0 | Project cancelled at the 35 th ExCom. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100% | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100% | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | I | CFC | 134.9 | 134.9 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2005-05-01 | 2005-12-01 | 609616 | 0 | 609616 | 609616 | 100% | 0 | 0 |  | 77057.76 | 0 | 77057.76 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100% | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100% | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100% | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | I | CFC | 136.67 | 136.67 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2005-03-01 | 2005-07-01 | 515970 | 0 | 515970 | 515970 | 100% | 0 | 0 |  | 66756.7 | 0 | 66756.7 | 0 | 0 | Completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 |  | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | Project cancelled at the 40th ExCom. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 |  | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100% | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | Physically completed. Draft PCR under review. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 | 2005-12-01 | 600066 | 0 | 600066 | 600066 | 100% | 0 | 0 |  | 76007.26 | 0 | 76007.26 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 | 2005-04-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 |  | 64792 | 0 | 64792 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100% | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | Financially completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 |  | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | -3.1832e-12 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 9940000 | 0 | 9940000 | 9940000 | 100% | 0 | 0 |  | 886600 | 0 | 886600 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 12570000 | 0 | 12570000 | 12570000 | 100% | 0 | 0 |  | 1115300 | 0 | 1115300 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2013-06-01 | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 |  | 961270 | 0 | 961270 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2005-12-01 |  | 2005-12-01 | 2013-06-01 | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 |  | 961270 | 0 | 961270 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2006 annual programme | Multiyear | ASP | CPR | FOA | 47 | INV | 434 | N | I | CFC | 600 | 600 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2008-10-01 | 2013-06-01 | 3320000 | 0 | 3320000 | 3320000 | 100% | 0 | 0 |  | 282800 | 0 | 282800 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2007 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 454 | N | I | CFC | 551 | 551 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 2676000 | 0 | 2676000 | 2676000 | 100% | 0 | 0 |  | 240840 | 0 | 240840 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2008 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 455 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2010-01-01 | 2013-06-01 | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 |  | 159030 | 0 | 159030 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2009 annual programme | Multiyear | ASP | CPR | FOA | 56 | INV | 478 | N | I | CFC | 3492 | 3492 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 |  | 159030 | 0 | 159030 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (spray foam sector) |  | ASP | CPR | FOA | 57 | PRP | 484 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam insulation for water heaters) |  | ASP | CPR | FOA | 57 | PRP | 485 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam system house) |  | ASP | CPR | FOA | 57 | PRP | 486 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-03-31 |  | 2009-11-01 | 2009-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | Demo. project approved in Nov 09. |  |  |  | Non-INV | 0
ONG | IBRD | Conversion demonstration from HCFC-141b-based to cyclopentane-based pre-blended polyol in the manufacture of rigid polyurethane foam at Guangdong Wanhua Rongwei Polyurethane Co. Ltd | Individual | ASP | CPR | FOA | 59 | DEM | 491 | N | I | HCFC | 6.8 | 5.96 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 | 2015-12-01 |  |  | 1214936 | 0 | 1214936 | 932489.2 | 76.75% | 282446.8 | 282446.8 | 282446.8 | 91120 | 0 | 69936.54 | 21183.46 | 21183.46 | Foshan Ouqi and Zhanjiang Aowei finished their conversions in 2014. At the time Aowei still had some quality issues with the alternative raw materials. Vanward had completed its procurement of equipment but could not complete conversion due to new technical standards and requirements for insulation foam panel. | Foshan Ouqi and Zhanjiang Aowei completed commissioning and began to fully operate with hydrocarbon pre-blended polyol in early 2015. Vanward completed installation of new equipment in Jan 15. A new energy standard for water heaters issued by the Government and water heaters must be upgraded to meet the new standard. Vanward has to increase the thickness of the foam for each of its over 100 different models. The increase in thickness depends on the dimensions and size of the water tank. Rongwei is working closely with Vanward to meet this new standard. |  |  | INV | 0
FIN | IBRD | Conversion of the foam part of Jiangsu Huaiyin Huihuang Solar Co. Ltd. from HCFC-141b to cyclopentane | Individual | ASP | CPR | FOA | 59 | DEM | 492 | N | I | HCFC | 5.1 | 5.1 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 |  | 2012-11-30 | 2012-11-30 | 786668 | 0 | 786668 | 786668 | 100% | 0 | 0 |  | 59000 | 0 | 59000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from HCFC-141b-based to HFC-245fa-based spray polyurethane foam at Harbin Tianshuo Building Materials Co. Ltd. | Individual | ASP | CPR | FOA | 59 | INV | 493 | N | I | HCFC | 1.7 | 1.7 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2012-11-30 | 2013-06-01 | 193808 | 0 | 193808 | 193808 | 100% | 0 | 0 |  | 14536 | 0 | 14536 | 0 | 0 | Project fully completed. |  |  | 2011-12-01 | INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) |  | ASP | CPR | FOA | 73 | PRP | 558 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 | 2017-06-01 |  |  | 400000 | 0 | 400000 | 0 | 0% | 400000 | 400000 | 250000 | 28000 | 0 | 0 | 28000 | 28000 | Project preparation newly approved in Nov 2014. | A simple restructuring to include the additional funding in the China-WB HCFC Phaseout umbrella Grant Agreement was processed and completed in Apr 15. Disbursement will start in 2015. |  |  | Non-INV | 0
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 07 | INV | 17 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 07 | INV | 18 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. |  |  |  | INV | 0
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100% | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100% | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Multiyear | ASP | CPR | HAL | 23 | INV | 231 | N | I | HAL | 0 | 9939 | 0 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 2013-06-01 | 12400000 | 0 | 12400000 | 12400000 | 100% | 0 | 0 |  | 1240000 | 0 | 1240000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | I | HAL | 5370 | 5370 | 5970 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 | 2013-06-01 | 9700000 | 0 | 9700000 | 9700000 | 100% | 0 | 0 |  | 970000 | 0 | 970000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | I | HAL | 5370 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 | 2013-06-01 | 10600000 | 0 | 10600000 | 10600000 | 100% | 0 | 0 |  | 1060000 | 0 | 1060000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | I | HAL | 1389 | 1389 | 1989 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 | 2013-06-01 | 4500000 | 0 | 4500000 | 4500000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | I | HAL | 2889 | 2889 | 2169 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 3700000 | 0 | 3700000 | 3700000 | 100% | 0 | 0 |  | 370000 | 0 | 370000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 5900000 | 0 | 5900000 | 5900000 | 100% | 0 | 0 |  | 442500 | 0 | 442500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 | 2013-06-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2005-11-01 | 2013-06-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2006 annual programme | Multiyear | ASP | CPR | HAL | 47 | INV | 433 | N | I | HAL | 6170 | 6170 | 10470 | 10470 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-11-01 | 2013-06-01 | 11400000 | 0 | 11400000 | 11400000 | 100% | 0 | 0 |  | 855000 | 0 | 855000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2007 annual programme | Multiyear | ASP | CPR | HAL | 50 | INV | 445 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-10-01 | 2007-11-01 |  | 2008-10-01 | 2013-06-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2008 annual programme | Multiyear | ASP | CPR | HAL | 53 | INV | 456 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 | 2013-06-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2009 annual programme | Multiyear | ASP | CPR | HAL | 56 | INV | 481 | N | I | HAL | 1000 | 1000 | 1500 | 1500 | 2008-11-01 | 2011-06-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2013-06-01 | 20000000 | 0 | 20000000 | 20000000 | 100% | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2004-12-01 |  | 2006-04-01 | 2007-01-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 9375 | 0 | 9375 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2013-06-01 | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 |  | 1200000 | 0 | 1200000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Process agent sector plan (phase I): 2005 annual programme | Multiyear | ASP | CPR | PAG | 46 | INV | 432 | N | I | CTC | 4556 | 4556 | 16171 | 16171 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-07-01 | 2013-06-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production (first tranche) | Multiyear | ASP | CPR | PAG | 47 | INV | 437 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2007-09-01 | 2013-06-01 | 15000000 | 0 | 15000000 | 15000000 | 100% | 0 | 0 |  | 1125000 | 0 | 1125000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 440 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 | 2013-06-01 | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 |  | 1200000 | 0 | 1200000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 441 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2007-12-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2007 annual programme | Multiyear | ASP | CPR | PAG | 51 | INV | 448 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 | 2013-06-01 | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 |  | 375000 | 0 | 375000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2007 annual programme | Multiyear | ASP | CPR | PAG | 52 | INV | 452 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-07-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2008 annual programme | Multiyear | ASP | CPR | PAG | 54 | INV | 458 | N | I | CTC | 0 | 0 | 10594 | 10594 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 | 2013-06-01 | 3000000 | 0 | 3000000 | 3000000 | 100% | 0 | 0 |  | 225000 | 0 | 225000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2008 annual programme | Multiyear | ASP | CPR | PAG | 55 | INV | 463 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2009 annual programme | Multiyear | ASP | CPR | PAG | 57 | INV | 483 | N | I | CTC | 6587 | 6587 | 2818 | 2818 | 2009-04-01 | 2010-01-01 | 2010-03-31 |  | 2011-12-01 | 2013-06-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2009 annual programme | Multiyear | ASP | CPR | PAG | 58 | INV | 488 | N | I | CTC | 6896 | 6896 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-31 |  | 2010-07-01 | 2013-06-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan: HCFC production sector |  | ASP | CPR | PHA | 55 | PRP | 467 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-12-31 |  | 2013-06-01 | 2013-06-01 | 473300 | 0 | 473300 | 473300 | 100% | 0 | 0 |  | 35498 | 0 | 35498 | 0 | 0 | Final disbursement was made in June 2013 after the ExCom approved the HCFC Production Sector Plan (Stage I). |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan: polyurethane foam sector |  | ASP | CPR | PHA | 55 | PRP | 468 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2011-07-01 | 2012-12-01 | 685900 | 0 | 685900 | 685900 | 100% | 0 | 0 |  | 51443 | 0 | 51443 | 0 | 0 | Last disbursement made in Dec. 2012. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (polyurethane rigid foam sector plan) (stage I, first tranche) | Multiyear | ASP | CPR | PHA | 64 | INV | 508 | N | X |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-11-01 | 2012-07-31 | 2017-06-01 |  |  | 38859000 | 0 | 38859000 | 31087200 | 80% | 7771800 | 7771800 | 7771800 | 2914000 | 0 | 2331200 | 582800 | 582800 | 23 additional subgrants were signed in 2014 making total commitment $61.263 million with 12,762.95 MT of HCFC-141b to be phased out. In addition to 9 subprojects completed in 2013, 2 additional subprojects from tranche 2 were completed in 2014. Cumulative disbursement to enterprises reached $16,012,254 and disbursement against TA activities reached $2.569 million at end of 2014. In addition, 5 system house conversion agreements were signed with committed funding of $1.75 million. | 2 system house conversion agreements were signed during the first half of 2015. It is expected that 7 additional subprojects will be completed in 2015 with a total HCFC consumption reduction of 100 ODP tons. No additional subgrants will be signed as the total resources have been committed to conversion. Unallocated funds are for TA and the PMU. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 68 | INV | 526 | N | X | HCFC | 103.8 | 103.8 | 0 | 0 | 2012-12-01 | 2013-11-01 | 2013-12-31 | 2017-06-01 |  |  | 5520000 | 0 | 5520000 | 4416000 | 80% | 1104000 | 1104000 | 500000 | 386400 | 0 | 309120 | 77280 | 77280 | 23 additional subgrants were signed in 2014 making total commitment $61.263 million with 12,762.95 MT of HCFC-141b to be phased out. In addition to 9 subprojects completed in 2013, 2 additional subprojects from tranche 2 were completed in 2014. Cumulative disbursement to enterprises reached $16,012,254 and disbursement against TA activities reached $2.569 million at end of 2014. In addition, 5 system house conversion agreements were signed with committed funding of $1.75 million. | 2 system house conversion agreements were signed during the first half of 2015. It is expected that 7 additional subprojects will be completed in 2015 with a total HCFC consumption reduction of 100 ODP tons. No additional subgrants will be signed as the total resources have been committed to conversion. Unallocated funds are for TA and the PMU. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, third tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 71 | INV | 535 | N | X | HCFC | 255.6 | 0 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2014-12-31 | 2017-06-01 |  |  | 13592000 | 0 | 13592000 | 6796000 | 50% | 6796000 | 6796000 | 2000000 | 951440 | 0 | 475720 | 475720 | 475720 | 23 additional subgrants were signed in 2014 making total commitment $61.263 million with 12,762.95 MT of HCFC-141b to be phased out. In addition to 9 subprojects completed in 2013, 2 additional subprojects from tranche 2 were completed in 2014. Cumulative disbursement to enterprises reached $16,012,254 and disbursement against TA activities reached $2.569 million at end of 2014. In addition, 5 system house conversion agreements were signed with committed funding of $1.75 million. | 2 system house conversion agreements were signed during the first half of 2015. It is expected that 7 additional subprojects will be completed in 2015 with a total HCFC consumption reduction of 100 ODP tons. No additional subgrants will be signed as the total resources have been committed to conversion. Unallocated funds are for TA and the PMU. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 73 | INV | 551 | N | X | HCFC | 76.7 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 | 2017-06-01 |  |  | 4079000 | -5195 | 4073805 | 0 | 0% | 4073805 | 4073805 | 1650000 | 285530 | 0 | 0 | 285530 | 285530 | Tranche newly approved. Progress for the entire sector plan includes signing of 23 additional subgrants in 2014 making total commitment $61.263 million with 12,762.95 MT of HCFC-141b to be phased out. In addition to 9 subprojects completed in 2013, 2 additional subprojects were completed in 2014. Cumulative disbursement to enterprises reached $16,012,254 and disbursement against TA activities reached $2.569 million at end of 2014.In addition, 5 system house conversion agreements were signed with committed funding of $1.75 million. | 2 system house conversion agreements were signed during the first half of 2015. It is expected that 7 additional subprojects will be completed in 2015 with a total HCFC consumption reduction of 100 ODP tons. No additional subgrants will be signed as the total resources have been committed to conversion. Unallocated funds are for TA and the PMU. |  |  | INV | 0
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. |  |  |  | Non-INV | 0
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 | 2013-06-01 | 10000000 | 10000000 | 20000000 | 20000000 | 100% | 0 | 0 |  | 900000 | 900000 | 1800000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 1170000 | 0 | 1170000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | I | CFC | 0 | 0 | 4320 | 4320 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 | 2013-06-01 | 6500000 | 6500000 | 13000000 | 13000000 | 100% | 0 | 0 |  | 585000 | 585000 | 1170000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | I | CFC | 0 | 0 | 3568 | 3568 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 910000 | 0 | 910000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 | 2005-11-01 | 2004-12-01 |  | 2005-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | I | TCA | 0 | 0 | 33.8 | 33.8 | 2004-07-01 | 2005-12-01 | 2008-07-01 |  | 2008-07-01 | 2010-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 105000 | 0 | 105000 | 0 | 0 | Fully completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2005 annual programme | Multiyear | ASP | CPR | PRO | 45 | INV | 428 | N | I | CFC | 0 | 0 | 6550 | 6550 | 2005-04-01 | 2005-12-01 | 2005-12-01 |  | 2006-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2006 annual programme | Multiyear | ASP | CPR | PRO | 48 | INV | 443 | N | I | CFC | 0 | 0 | 5250 | 5250 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2007 annual programme | Multiyear | ASP | CPR | PRO | 51 | INV | 449 | N | I | CFC | 0 | 0 | 6100 | 6100 | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-03-01 | 2013-06-01 | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 |  | 1800000 | 0 | 1800000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2008 annual programme | Multiyear | ASP | CPR | PRO | 54 | INV | 459 | N | I | CFC | 0 | 0 | 6850 | 6850 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-03-01 | 2013-06-01 | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 |  | 562500 | 0 | 562500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichloroethane (TCA) production (second stage programme) | Multiyear | ASP | CPR | PRO | 56 | INV | 480 | N | I | TCA | 0 | 0 | 79.2 | 79.2 | 2008-11-01 | 2010-11-01 | 2010-11-30 |  | 2010-11-01 | 2010-11-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | Fully completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2009 annual programme | Multiyear | ASP | CPR | PRO | 57 | INV | 487 | N | I | CFC | 0 | 0 | 550 | 550 | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-03-01 | 2013-06-01 | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 |  | 562500 | 0 | 562500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
ONG | IBRD | HCFC production phase-out management plan (stage I, first tranche) | Multiyear | ASP | CPR | PRO | 69 | INV | 530 | N | X |  | 0 | 0 | 0 | 0 | 2013-04-01 | 2014-12-01 | 2014-04-30 | 2015-12-01 |  |  | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 | 0 | 0 | 1344000 | 1344000 | 0 | 0 | FECO disbursed all payments for the 12 quota reduction contracts with a total value of $10.427 million. Remaining balance of 2013 tranche was used to pay against production line closure contracts for the 10% reduction target of 2015 and TA activities under the annual program. | Tranche fully disbursed. |  |  | INV | 0
FIN | IBRD | Verification of production of CFCs for essential use |  | ASP | CPR | PRO | 69 | TAS | 531 | A | I |  | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2013-08-31 |  | 2013-08-01 | 2013-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 2800 | 0 | 2800 | 0 | 0 | Verification report submitted to the 71st ExCom Meeting as planned and was considered by the Subgroup on the Production Sector. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC production phase-out management plan (stage I, second tranche) | Multiyear | ASP | CPR | PRO | 72 | INV | 540 | N | X |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-09-01 | 2015-05-31 | 2017-06-01 |  |  | 23000000 | 0 | 23000000 | 6900000 | 30% | 16100000 | 16100000 | 11000000 | 1288000 | 0 | 386400 | 901600 | 901600 | 2014 annual program and tranche approved in May 2014. Production quotas for 2014 were issued. To meet 10% reduction target for 2015, FECO signed production line closure contracts with 5 producers to phase-out 58,864 MT production quota of HCFCs (33,237 MT of HCFC-22 and 25,627 MT of HCFC-141b) with a total contract amount of $75,072,962 in Nov 2014. A total of 88,000 MT (43,000 MT of HCFC-22 and 45,000 MT of HCFC-141b) HCFC production capacity to be closed and dismantled. 2014 unaudited production figure indicates that China has met its target (2014 production verification report will be submitted to the 75th ExCom). | 2014 production data reported by producers showing that production contract targets were met. Production quotas for 2015 were issued. All environment mgmt. plans (EMPs) for dismantling closure production lines prepared by enterprises and reviewed and approved by WB. Four of 5 closed production lines have been dismantled; the other will be dismantled in Jun 15. |  |  | INV | 0
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 08 | PRP | 24 | N | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). |  |  |  | Non-INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 26th ExCom. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCOM. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the ExCom March 2000. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100% | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | Project completed; PCR submitted to the 31th ExCom. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100% | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | Project completed; Draft PCR is under review. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100% | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100% | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100% | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | Project financially completed. |  |  | 2000-08-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100% | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100% | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100% | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100% | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100% | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100% | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100% | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100% | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | Project is financially completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100% | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100% | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100% | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | Project completed. Draft PCR underway. Savings to be returned to the MLF. |  |  |  | INV | 0
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100% | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | Project was completed; PCR submitted to 30th ExCOM. |  |  |  | INV | 0
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 |  | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | Project cancelled due to financial difficulties. |  |  |  | INV | 0
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 |  | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 1.4097e-11 | 0 | Project has been cancelled. |  |  |  | INV | 0
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100% | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | Project completed. Completion report submitted. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100% | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100% | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | -291.22 | 1951465.78 | 1951465.78 | 100% | 0 | 0 |  | 224693.27 | -33.53 | 224659.74 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | I | CFC | 174.2 | 174.2 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 |  | 2005-12-01 | 2006-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 164000 | 0 | 164000 | 0 | 0 | Project is completed. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | I | CFC | 764.9 | 764.9 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 |  | 2007-12-01 | 2008-05-01 | 5250852 | 0 | 5250852 | 5250852 | 100% | 0 | 0 |  | 587593.72 | 0 | 587593.72 | 0 | 0 | Project completed. PCR prepared. |  |  |  | INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 06 | CPG | 12 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 07 | PRP | 21 | N | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 09 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 09 | TAS | 29 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | 1996-12-01 | Non-INV | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | $100,000 transferred to PPA-V. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 09 | INV | 12 | N | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. |  |  |  | INV | 0
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 09 | INV | 10 | N | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | 1995-07-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100% | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | I | MBR | 15 | 15 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 |  | 2009-06-01 | 2009-09-01 | 244244 | -20203.07 | 224040.93 | 224040.93 | 100% | 0 | 0 |  | 31751.72 | -2626.4 | 29125.32 | 0 | 0 | Second testing was completed in Jun 09. Results were positive, reconfirming that the alternative substance (Agrocelhone) is effective for pest control. National consumption of Methyl Bromide by the closing of the WB umbrella ODS project in Sep 09 was 51 ODP MT. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 |  | 2005-01-01 | 2005-02-01 | 597945 | 0 | 597945 | 597945 | 100% | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Preparation of a methyl bromide project |  | LAC | ECU | FUM | 45 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 |  |  | 2010-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 1875 | -1875 | 0 | 0 | 0 | Funding returned to the MLF. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2005-04-01 | 2010-12-01 | 777326 | 0 | 777326 | 777326 | 100% | 0 | 0 |  | 58299.45 | 0 | 58299.45 | 0 | 0 | NCPP completed. Balances of subsequent tranches returned to the MLF at the 62nd ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | LAC | ECU | PHA | 45 | INV | 36 | N | I | CFC | 85 | 85 | 0 | 0 | 2005-04-01 | 2008-10-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 439319 | -22174 | 417145 | 417145 | 100% | 0 | 0 |  | 32349 | -1632.77 | 30716.23 | 0 | 0 | NCPP completed. Balance of $22,174 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | LAC | ECU | PHA | 49 | INV | 37 | N | I | CFC | 70 | 70 | 0 | 0 | 2006-07-01 |  | 2007-12-01 |  | 2009-06-01 | 2010-12-01 | 227410 | -227410 | 0 | 0 |  | 0 | 0 |  | 17055 | -17055 | 0 | 0 | 0 | NCPP completed. Balance of $227,410 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | LAC | ECU | PHA | 52 | INV | 39 | N | I | CFC | 38 | 38 | 0 | 0 | 2007-07-01 |  | 2008-07-31 |  | 2009-06-01 | 2010-12-01 | 227411 | -227411 | 0 | 0 |  | 0 | 0 |  | 17056 | -17056 | 0 | 0 | 0 | NCPP completed. Balance of $227,411 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
TRF | IBRD | Preparation of a HCFC phase-out management plan |  | LAC | ECU | PHA | 55 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 |  |  | 2009-11-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 11250 | -11250 | 0 | 0 | 0 | Preparation activity transferred to UNEP and UNIDO at the 59th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | LAC | ECU | PHA | 56 | INV | 41 | N | I | CFC | 42 | 42 | 0 | 0 | 2008-11-01 |  | 2009-11-30 |  | 2009-09-01 | 2010-12-01 | 18334 | -18334 | 0 | 0 |  | 0 | 0 |  | 1375 | -1375 | 0 | 0 | 0 | Project completed. Balance of $18,334 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100% | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100% | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. |  |  |  | INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 06 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 09 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Ongoing. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100% | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100% | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | NCPP submitted and approved at the 41st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-02-01 | 2007-03-01 | 176800 | 0 | 176800 | 176800 | 100% | 0 | 0 |  | 13260 | 0 | 13260 | 0 | 0 | IS completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV, first year) | Individual | LAC | ECU | SEV | 51 | INS | 38 | N | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2009-04-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Phase IV completed. ISP transferred to UNEP. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV, second year) | Individual | LAC | ECU | SEV | 56 | INS | 42 | N | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-09-30 |  | 2009-09-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Ecuador has complied with all MP targets for Annex A substance phaseout and has been actively engaged in maintaining its compliance status with methyl bromide. The ISP was transferred to UNEP (starting with phase V). |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a TCA phase-out project |  | LAC | ECU | SOL | 45 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2005-12-01 |  | 2006-02-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | Results from the survey and seminar carried out in Jan 06 show that there is not enough consumption of TCA in the country, and remaining consumers are changing technologies on their own. A project will not be presented to MLF. |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 08 | INV | 08 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 04 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Development of strategy/methodology for ODS disposal |  | GLO | GLO | DES | 55 | TAS | 291 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2010-05-01 | 2010-09-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Final study completed by the consultant, printed, distributed and posted on the internet. Companion piece drawing from the study that targets ozone nnits also completed. |  |  |  | Non-INV | 0
FIN | IBRD | Assessment of CTC phase-out in the chlo-alkali sector | Individual | GLO | GLO | PHA | 52 | TAS | 280 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-07-01 | 2008-09-30 |  | 2008-06-01 | 2008-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | Study completed and presented to the 55th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 08 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the chiller sector and organization of a workshop |  | GLO | GLO | REF | 46 | PRP | 267 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2005-11-01 | 2005-11-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Chiller Workshop held Sep 05. Findings were used as a basis for development of IA chiller projects, including the Bank's Global Chiller Project. The Global Chiller Project was submitted for ExCom consideration in Nov 05 and US$6.88 million was approved out of the $15 million window. |  |  |  | Non-INV | 0
ONG | IBRD | Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines) | Individual | GLO | GLO | REF | 47 | DEM | 268 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-12-01 | 2013-12-01 | 2017-12-01 |  |  | 6884612 | -3149056 | 3735556 | 1762525 | 47.18% | 1973031 | 1973031 | 165000 | 516346 | -236179 | 117573.04 | 162593.96 | 162593.96 | India: Restructuring of the Chiller Energy Efficiency Project took place in Aug. 2014, extending the closing date to Dec. 2014. Project was not extended beyond 2014 and has now closed. Philippines: By end of 2014, 16 subgrant agreements (SGAs) for replacement of 27 chillers signed. Replacement of 18 chillers completed in 2014. Nine other chiller replacements to be completed in 2015. MLF grants disbursed to DENR to support TA activities including the recognition program launched first in 2014. In addition to the 27 chillers for which SGAs were signed, there are 25 additional chillers identified and targeted for 2015. Jordan: Project recovered 4 MT of CFC by completion. Indonesia: Project canceled. Argentina: Chiller replacement project incorporated into new GA between GoA and WB that was approved in Jul 13. Effectiveness took some time due to the need for presidential decree and other GoA processes. | India: Additional $15,933 disbursed prior to financial completion in Apr. 15. Philippines: In addition to the 27 chillers for which subgrant agreements (SGAs) were signed by end 2014, 25 additional chillers are targeted for coverage by SGAs to be signed in 2015. As of Jul 2015 US$972,582 in GEF grants disbursed to enterprises and US$547,917 in MLF grant disbursed cumulatively for TA activities. Argentina: New GA effective 30 Jan 2015 which will allow chiller replacement subproject to start this year. |  |  | Non-INV | 0
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 04 | TAS | 135 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 09 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 43 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 |  |  |  |  | Non-INV | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 |  | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100% | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 |  | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Core unit (2003) |  | GLO | GLO | SEV | 38 | TAS | 245 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2006) |  | GLO | GLO | SEV | 47 | TAS | 273 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2007) |  | GLO | GLO | SEV | 50 | TAS | 279 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-11-01 | 2007-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1580000 | -17251 | 1562749 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of one MP event and completion of reports and responses. Two pamphlets completed for the 20th MP Anniversary. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2008) |  | GLO | GLO | SEV | 53 | TAS | 286 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2008-11-01 | 2008-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1614900 | -360069 | 1254831 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the MP annual workshop for FIs and staff; reconvening the OORG (with 2 meetings held in 2008); an analytical piece on HCFC and related side-event; commissioning of a "foam decision tree," for HCFC alternatives; completion of reports and responses and providing required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2009) |  | GLO | GLO | SEV | 56 | TAS | 294 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1663347 | -204863 | 1458484 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the 13th annual workshop for FIs and staff as well as the new OORG meeting; strategic business development; completion of draft foam decision-tree report; and providing required monitoring, data collection and information for ExCom reporting. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2010) |  | GLO | GLO | SEV | 59 | TAS | 298 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1701466 | -390706 | 1310760 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 14th annual workshop for FIs and staff, the 5th new OORG meeting and two technology roundtable meetings; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2011) |  | GLO | GLO | SEV | 62 | TAS | 305 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-06-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1713000 | -390685 | 1322315 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 15th annual workshop for FIs and staff and the 6th new OORG meeting; and coordination of WB-MP activities, completion of reports and responses and providing info |  |  |  | Non-INV | 0
FIN | IBRD | Resource mobilization for HCFC phase-out co-benefits study |  | GLO | GLO | SEV | 63 | TAS | 309 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-31 |  | 2013-12-01 | 2014-11-01 | 180000 | -61165.34 | 118834.66 | 118834.66 | 100% | 0 | 0 | 0 | 16200 | -5505 | 10695.12 | -0.12 | -0.12 | Study completed. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2012) |  | GLO | GLO | SEV | 65 | TAS | 312 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 | 2013-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1724644 | -3981 | 1720663 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; holding a 7th new OORG meeting; hosting a regional ODS workshop for countries and WB staff as well as ozone day celebrations for the 25th MP anniversary, incl. a roundtable discussion and technology fair; and, coordination of WB-MP activities, completion of reports and responses and providing information needed for preparing ExCom reports. |  |  |  | Non-INV | 0
FIN | IBRD | Core unit budget (2013) |  | GLO | GLO | SEV | 68 | TAS | 318 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-31 |  | 2013-12-01 | 2014-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1725000 | -414405 | 1310595 | 0 | 0 | Activities included travel to MP-related meetings including ozone officer network meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; a regional MP workshop for clients and project teams; strategic business development and completion of reports and responses and providing data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
COM | IBRD | Core unit budget (2014) |  | GLO | GLO | SEV | 71 | TAS | 320 | A | I |  | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2014-12-31 |  | 2014-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1725000 | 0 | 1383047 | 341953 | 0 | Activities included travel to MP-related meetings including 4 network meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; hosting an MP workshop in Jun 14; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. | Financial completion (return of any balance) expected by the 75th ExCom. |  |  | Non-INV | 0
ONG | IBRD | Core unit budget (2015) |  | GLO | GLO | SEV | 73 | TAS | 326 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 | 2015-12-31 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1725000 | 0 | 0 | 1725000 | 1725000 | Activities to include travel to MP-related meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; internal knowledge work; hosting an MP workshop; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. | Core unit attended 74th ExCom and 35th OEWG Meetings, interagency coordination meeting in Feb 15, managed submissions and reporting, held a regional workshop in Jan 15 and an MP/OORG workshop May 15. |  |  | Non-INV | 0
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 08 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is completed Final report to be issued shortly. |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 08 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 |  | 2005-05-01 | 2004-10-01 | 1175340 | 0 | 1175340 | 1175340 | 100% | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | Project financially and physically completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Multiyear | ASP | IDS | ARS | 44 | INV | 166 | N | I | CFC | 70 | 70 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-05-01 |  | 2010-06-01 | 2010-06-01 | 371910 | 0 | 371910 | 371910 | 100% | 0 | 0 |  | 27893 | 0 | 27893 | 0 | 0 | Project successfully completed and closed in Jun 2010. |  |  |  | INV | 0
FIN | IBRD | Project preparation funds for the development of a phase-out plan for the MDI sector |  | ASP | IDS | ARS | 46 | PRP | 170 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-09-01 | 2006-07-01 |  | 2008-11-01 | 2008-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 3375 | 0 | 3375 | 0 | 0 | TA for an MDI strategy submitted and approved at the 56th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance to implement national transition strategy to CFC-free MDI | Individual | ASP | IDS | ARS | 56 | TAS | 184 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 13950 | 0 | 13950 | 0 | 0 | Project completed as scheduled on the basis of workplan including development of database for registration of products, review of relevant policy and regulations within Agency for Drug and Food Control, preparation of a guideline for using CFC-free MDIs; workshop held for stakeholders and relevant leaflets produced. |  |  |  | INV | 0
FIN | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | IDS | DES | 57 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2013-12-01 | 2010-12-31 |  | 2014-06-01 | 2014-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | A study on 'The Establishment of a Public-Private Financing System for Disposal of ODS for Indonesia' was completed and accepted by the client in Jun 2014. The report was submitted to the 71st ExCom as an information document. |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 07 | N | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 08 | N | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 09 | N | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100% | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 |  | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | Project is cancelled. Funds returned to 28th meeting. |  |  | 1997-10-01 | INV | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100% | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  | 2001-02-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 |  | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 |  | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. |  |  |  | INV | 0
FIN | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | I | CFC | 954 | 954 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2007-01-01 | 2007-03-01 | 4060640 | -467626.72 | 3593013.28 | 3593013.28 | 100% | 0 | 0 |  | 527883 | -60791.46 | 467091.54 | 0 | 0 | Project is physically and financially completed |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2005-04-01 | 2005-12-01 | 3538400 | -1983523.96 | 1554876.04 | 1554876.04 | 100% | 0 | 0 |  | 459992 | -257858.12 | 202133.88 | 0 | 0 | Project completed. |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100% | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV | 0
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 |  | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100% | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | Project technically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100% | 0 | 0 |  | 20345 | -357.5 | 19987.5 | 0 | 0 | Project technically and financially completed. PCR draft being finalized. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100% | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | I | CFC | 51.75 | 51.75 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 100% | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | Project technically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100% | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100% | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 |  | 2005-12-01 | 2005-12-01 | 165201 | -20510.44 | 144690.56 | 144690.56 | 100% | 0 | 0 |  | 21476.13 | -2666.36 | 18809.77 | 0 | 0 | Project financially and technically completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100% | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | Project physically and financially completed |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | I | CFC | 130 | 130 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-12-01 | 100000 | 1625000 | 1725000 | 1725000 | 100% | 0 | 0 |  | 7500 | 121875 | 129375 | 0 | 0 | Project is physically and financially completed |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (second tranche) | Multiyear | ASP | IDS | FOA | 48 | INV | 172 | N | I | CFC | 130 | 130 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78750 | 0 | 78750 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (third tranche) | Multiyear | ASP | IDS | FOA | 51 | INV | 176 | N | I | CFC | 156 | 156 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-06-01 | 2010-12-01 | 147564 | 0 | 147564 | 147564 | 100% | 0 | 0 |  | 11067 | 0 | 11067 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (fourth tranche) | Multiyear | ASP | IDS | FOA | 54 | INV | 182 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-04-01 | 2010-06-01 | 2009-03-31 |  | 2010-06-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | Project completed. |  |  |  | INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | IDS | FOA | 72 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-31 | 2016-05-31 |  |  | 150000 | 0 | 150000 | 102035.93 | 68.02% | 47964.07 | 47964.07 | 47964.07 | 10500 | 0 | 7142.52 | 3357.48 | 3357.48 | Funding released to the WB in mid-2014. Initial planning consultations with the NOU and Lead IA took place during an Oct 14 Bank mission. International WB consultant engaged. | Preparation for Stage 2 started in Jan 2015. First official WB preparation mission undertaken end-Mar/early Feb. 2015. A local consultant hired and is working with the NOU to survey Stage 2 foam companies. Stage 2 HPMP is targeted for submission to ExCom for approval at its first meeting in 2016. |  |  | Non-INV | 0
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | I | HAL | 972 | 972 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 |  | 2007-01-01 | 2007-06-01 | 486200 | -11076.12 | 475123.88 | 475123.88 | 100% | 0 | 0 |  | 63206 | -1439.9 | 61766.1 | 0 | 0 | Project is physically and financially completed |  |  |  | INV | 0
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100% | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan (foam sector) |  | ASP | IDS | PHA | 57 | PRP | 186 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-12-31 |  | 2011-07-01 | 2011-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HPMP foam sector plan prepared and approved at the 64th ExCom Meeting. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multiyear | ASP | IDS | PHA | 64 | INV | 191 | A | I | HCFC | 18.9 | 18.9 | 0 | 0 | 2011-07-01 | 2013-12-01 | 2013-03-31 | 2017-12-01 |  |  | 1500000 | 0 | 1500000 | 982000 | 65.47% | 518000 | 518000 | 96000 | 112500 | 0 | 73650 | 38850 | 38850 | By end 2014, 8 companies signed subgrant agreements (SGAs). Disbursements to two large foam producers that completed subprojects in 2014 (PT. Maspion, PT. Top Jaya) was made for a total phase-out of 15.3 ODP tons. Other companies were considering their options as contract preparation continued. Import quota system is being applied and a ban on HCFC use in the foam sector is in place. NOU held 2 workshops in 2014. NOU had some administrative difficulties with hiring of project/PMU consultants, mainly due to a new government procurement system and centralization of procurement. | Three companies have now completed conversion for a total phase-out of their average 2009/10 HCFC-141b use of 5.7 ODP tons and 3 other companies are finalizing their conversion. Other foam producers are still undecided. The NOU is planning to redirect freed-up funds to support the work of any domestic foam system houses on the formulation of HCFC substitutes. Import quota system continues to be applied and a ban on HCFC use in the foam sector is in place. The NOU continues with TA but its work, including staffing-up of the PMU, has been further hampered by national elections and the government transition process, including a merger between the Ministries of Environment and Forestry. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (foam sector plan) (stage I, second tranche) | Multiyear | ASP | IDS | PHA | 71 | INV | 202 | N | I | HCFC | 11.9 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-31 | 2017-12-01 |  |  | 942767 | 0 | 942767 | 0 | 0% | 942767 | 942767 | 350000 | 70708 | 0 | 0 | 70708 | 70708 | By end 2014, 8 companies signed subgrant agreements (SGAs). Disbursements to two large foam producers that completed subprojects in 2014 (PT. Maspion, PT. Top Jaya) was made for a total phase-out of 15.3 ODP tons. Other companies were considering their options as contract preparation continued. Import quota system is being applied and a ban on HCFC use in the foam sector is in place. NOU held 2 workshops in 2014. NOU had some administrative difficulties with hiring of project/PMU consultants, mainly due to a new government procurement system and centralization of procurement. | Three companies have now completed conversion for a total phase-out of their average 2009/10 HCFC-141b use of 5.7 ODP tons and 3 other companies are finalizing their conversion. Other foam producers are still undecided. The NOU is planning to redirect freed-up funds to support the work of any domestic foam system houses on the formulation of HCFC substitutes. Import quota system continues to be applied and a ban on HCFC use in the foam sector is in place. The NOU continues with TA but its work, including staffing-up of the PMU, has been further hampered by national elections and the government transition process, including a merger between the Ministries of Environment and Forestry. |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100% | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | PCR has been submitted. Project is physically and financially completed. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100% | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100% | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100% | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | Project is completed. PCR has been submitted. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100% | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358 | -0.1 | -0.1 | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100% | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100% | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100% | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100% | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. |  |  |  | INV | 0
FIN | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-05-01 | 1369800 | 0 | 1369800 | 1369800 | 100% | 0 | 0 |  | 121962 | 0 | 121962 | 0 | 0 | 2003 annual plan completed successfully. |  |  |  | INV | 0
FIN | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2004 annual plan completed sucessfully. |  |  |  | INV | 0
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | I | CFC | 110 | 110 | 0 | 0 | 2004-12-01 | 2006-11-01 | 2005-12-01 |  | 2005-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2005 consumption reduction target was achieved. |  |  |  | INV | 0
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fourth tranche) | Multiyear | ASP | IDS | REF | 48 | INV | 173 | N | I | CFC | 110 | 110 | 0 | 0 | 2006-04-01 | 2008-12-01 | 2007-04-01 |  | 2008-12-01 | 2010-05-01 | 126800 | 0 | 126800 | 126800 | 100% | 0 | 0 |  | 10092 | 0 | 10092 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fifth tranche) | Multiyear | ASP | IDS | REF | 51 | INV | 178 | N | I | CFC | 110 | 110 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-03-01 | 2010-05-01 | 125800 | 0 | 125800 | 125800 | 100% | 0 | 0 |  | 10002 | 0 | 10002 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 09 | PRP | 03 | N | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. 14 subproject proposals were prepared. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation and processing complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | 1997-12-01 | Non-INV | 0
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100% | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Foam and aerosol proposals prepared and submitted to Excom. |  |  |  | Non-INV | 0
FIN | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 |  | 2006-12-01 | 2006-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Gov. of Indonesia made great progress in improving import licensing and quota system to monitor and control ODS import. Revised draft to existing regulation agreed upon by Ministry of Trade and other relevant government depts. New regulation adopted on June 22, 2006. Old regulation with provision that only one company can import ODS declared void. Standard Operating Procedures drafted to provide guidance for implementation of new regulation. Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100% | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | Project is completed and closed. PCR submitted. |  |  | 1996-08-01 | INV | 0
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100% | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 |  | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | CANCELLED. Funds returned to 27th meeting. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100% | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | Project completed and PCR submitted Jan. 01. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 2000-10-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | No change in previous status |  |  | 1999-06-01 | INV | 0
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project implementation has been transferred to UNDP. |  |  | 1996-06-01 | Non-INV | 0
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100% | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100% | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100% | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | PCR finalized and submitted to ExCom. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 | 2005-01-01 | 134250 | -12102 | 122148 | 122148 | 100% | 0 | 0 |  | 17452.5 | -1573.26 | 15879.24 | 0 | 0 | Project financially completed and balance funds returned to ExCom. PCR submitted. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100% | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 100% | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | IND | ARS | 62 | TAS | 438 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-08-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Independent audit submitted to the 65th ExCom in Nov 11. Report shows that CFC producers produced less CFCs than approved by the Parties for essential use, and that these pharma grade CFCs were sold to 2 MDI manufacturers authorized by GoI to produce MDIs according to EUN Process. |  |  |  | Non-INV | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100% | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 100% | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-05-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-01-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-02-01 | INV | 0
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100% | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 100% | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100% | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | Complete. |  |  | 1993-07-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 | 2005-01-01 | 187864 | -41523 | 146341 | 146341 | 100% | 0 | 0 |  | 24422.32 | -5397.99 | 19024.33 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2000-12-01 | INV | 0
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 |  | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | Cancelled |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100% | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 100% | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100% | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100% | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | INV | 0
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 |  | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | Cancelled. |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 100% | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100% | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100% | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100% | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | Project completed. |  |  | 2000-06-01 | INV | 0
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 |  | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | Project cancelled at the 39th ExCom. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 | 2008-01-30 | 2600000 | 0 | 2600000 | 2600000 | 100% | 0 | 0 |  | 234000 | 0 | 234000 | 0 | 0 | UNDP has confirmed that project has been completed. Final completion report still pending from UNDP. |  |  |  | INV | 0
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100% | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  |  | INV | 0
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Sector Plan completed and project document prepared for submission to the ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 | 2005-01-01 | 2074300 | -109984 | 1964316 | 1964315.95 | 100% | 0.05 | 0.05 |  | 238173 | -12098.24 | 226074.76 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-07-01 |  | 5000000 | 3520843 | 8520843 | 8520843 | 100% | 0 | 0 | 0 | 375000 | 264063 | 639063 | 0 | 0 | Tranche is completed. |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 9180112 | 0 | 9180112 | 9180112 | 100% | 0 | 0 | 0 | 688508 | 0 | 688508 | 0 | 0 | Targets met, tranche completed. |  |  |  | INV | 0
COM | IBRD | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multiyear | ASP | IND | PHA | 45 | INV | 386 | N | I | CTC | 6158 | 9848 | 9827 | 9896 | 2005-04-01 | 2007-04-01 | 2006-04-01 |  | 2006-07-01 |  | 399045 | 0 | 399045 | 399045 | 100% | 0 | 0 | 0 | 29928 | 0 | 29928 | 0 | 0 | 2005 verification of CTC production and consumption completed as scheduled. Levels of CTC production and consumption in 2005, excluding the quantity stockpiled for feedstock use in the following years, are well under the agreed targets. |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multiyear | ASP | IND | PHA | 49 | INV | 400 | N | I | CTC | 232 | 232 | 232 | 232 | 2006-07-01 | 2007-11-01 | 2007-07-01 |  | 2007-07-01 |  | 9556267 | 0 | 9556267 | 9556267 | 100% | 0 | 0 | 0 | 716720 | 0 | 716720 | 0 | 0 | Tranche fully disbursed. |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multiyear | ASP | IND | PHA | 52 | INV | 408 | N | I | CTC | 420 | 420 | 420 | 420 | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-07-01 |  | 4020938 | 0 | 4020938 | 4020938 | 100% | 0 | 0 | 0 | 301570 | 0 | 301570 | 0 | 0 | Tranche completed. |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2008 annual programme | Multiyear | ASP | IND | PHA | 55 | INV | 422 | N | I | CTC | 440 | 440 | 440 | 440 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 |  | 3211875 | 0 | 3211875 | 3211875 | 100% | 0 | 0 | 0 | 240891 | 0 | 240891 | 0 | 0 | All funds disbursed and tranche completed |  |  |  | INV | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | Multiyear | ASP | IND | PHA | 58 | INV | 434 | N | I | CTC | 268 | 268 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2014-03-01 |  | 3211874 | -56874 | 3155000 | 2404907 | 76.23% | 750093 | 0 | 0 | 240891 | -4266 | 180368 | 56257 | 56257 | Funds disbursed to the financial intermediary but could not be fully released to the PMU before project closing date. | Financial completion pending return of unreleased funds to the WB from the financial intermediary in India. |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 | 2011-11-01 | 12000000 | 0 | 12000000 | 12000000 | 100% | 0 | 0 |  | 960000 | 0 | 960000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 480000 | 0 | 480000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed and submitted to ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | I | CFC | 0 | 0 | 1832 | 1832 | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2005-01-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 45 | INV | 390 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-04-01 | 2011-11-01 | 5850000 | 0 | 5850000 | 5850000 | 100% | 0 | 0 |  | 438750 | 0 | 438750 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2006 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 397 | N | I | CFC | 0 | 0 | 3389 | 3389 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: balance from the 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 398 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-05-01 | 2007-04-01 |  | 2008-07-01 | 2011-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 11250 | 0 | 11250 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2007 annual implementation plan | Multiyear | ASP | IND | PRO | 51 | INV | 407 | N | I | CFC | 0 | 0 | 3953 | 3953 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2008-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2008 annual implementation plan | Multiyear | ASP | IND | PRO | 54 | INV | 417 | N | I | CFC | 0 | 0 | 1130 | 1130 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2009 annual implementation plan | Multiyear | ASP | IND | PRO | 59 | INV | 434 | N | I | CFC | 0 | 0 | 3171 | 3171 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2011-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
COM | IBRD | Accelerated CFC production phase-out (first tranche) | Multiyear | ASP | IND | PRO | 59 | INV | 435 | N | I | CFC | 0 | 0 | 690 | 690 | 2009-11-01 | 2012-01-01 | 2010-11-30 |  | 2011-12-01 |  | 2113000 | 0 | 2113000 | 2113000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Funding disbursed to the country in Jan 2012. Next and final tranche for funding was deferred at the 66th ExCom Meeting. |  |  |  | INV | 0
COM | IBRD | Accelerated CFC production phase-out (second tranche) | Multiyear | ASP | IND | PRO | 67 | INV | 446 | N | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-31 |  | 2014-03-01 |  | 739900 | 0 | 739900 | 0 | 0% | 739900 | 0 | 0 | 213968 | 0 | 0 | 213968 | 213968 | Funds fully disbursed to the financial intermediary in the country but could not be released to the beneficiaries before project closing date. | Financial completion pending return of unreleased funds to the WB from the financial intermediary in India. |  |  | INV | 0
COM | IBRD | Accelerated CFC production phase-out (remaining of the second tranche) | Multiyear | ASP | IND | PRO | 69 | INV | 447 | N | I |  | 0 | 0 | 0 | 0 | 2013-04-01 |  | 2014-04-30 |  | 2014-03-01 |  | 317000 | 0 | 317000 | 0 | 0% | 317000 | 0 | 0 | 24032 | 0 | 0 | 24032 | 24032 | Funds fully disbursed to the financial intermediary in the country but could not be released to the beneficiaries before project closing date. | Financial completion pending return of unreleased funds to the WB from the financial intermediary in India. |  |  | INV | 0
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 08 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 100% | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100% | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-07-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 100% | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100% | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100% | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | Project completed. |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100% | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 |  |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100% | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100% | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | Complete. |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-11-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100% | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | Project completed. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100% | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 100% | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100% | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100% | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 100% | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100% | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 125370 | -75182.45 | 50187.55 | 50187.55 | 100% | 0 | 0 |  | 16298.1 | -9773.72 | 6524.38 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100% | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100% | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100% | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100% | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | Project completed. PCR will be submitted January 2001. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 132320 | -81327 | 50993 | 50993 | 100% | 0 | 0 |  | 17201.6 | -10572.51 | 6629.09 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 147300 | -95904.45 | 51395.55 | 51395.55 | 100% | 0 | 0 |  | 19149 | -12467.58 | 6681.42 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 | 2005-01-01 | 510000 | -261775.31 | 248224.69 | 248224.69 | 100% | 0 | 0 |  | 66300 | -34030.79 | 32269.21 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 | 2005-01-01 | 2724378 | -1093985 | 1630393 | 1630393 | 100% | 0 | 0 |  | 354169.14 | -142218 | 211951 | 0.14 | 0.14 | Project financially completed and balance funds returned. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100% | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100% | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100% | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100% | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100% | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  | 2000-09-01 | INV | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100% | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 |  |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100% | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 |  | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | Project has been cancelled. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 | 2005-01-01 | 722906 | 302123 | 1025029 | 1025029 | 100% | 0 | 0 |  | 93977.78 | 35611.19 | 129588.97 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 675165 | -276756 | 398409 | 398409 | 100% | 0 | 0 |  | 84268.15 | -39407.54 | 44860.61 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 2050000 | -250684.64 | 1799315.36 | 1799315.36 | 100% | 0 | 0 |  | 235500 | -28798.16 | 206701.84 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project submitted to and approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 | 2005-01-01 | 1181693 | -83277 | 1098416 | 1098416 | 100% | 0 | 0 |  | 222895 | -15708 | 207187.01 | -0.01 | -0.01 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. |  |  |  | Non-INV | 0
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100% | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | Complete. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 07 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 07 | INV | 13 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 07 | INV | 14 | N | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100% | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | Project completed. |  |  | 2002-03-01 | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100% | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100% | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100% | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. |  |  |  | INV | 0
FIN | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2005-02-01 | 2005-02-01 | 49539 | 0 | 49539 | 49539 | 100% | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | Project completed. |  |  | 2003-06-01 | INV | 0
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 07 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | 1994-06-01 | INV | 0
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Company moved to the Sudan. |  |  | 1994-06-01 | INV | 0
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 07 | INV | 08 | N | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | 1994-06-01 | Non-INV | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2001-02-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100% | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100% | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 |  | 2007-12-01 | 2008-01-01 | 382250 | 0 | 382250 | 382250 | 100% | 0 | 0 |  | 49693 | 0 | 49693 | 0 | 0 | The halon recycling center has been completed and is operational. Consistent with ExCom policies, no newly produced halons will be allowed to be imported. The ban will be enforced thru the existing import lincensing system. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 |  | 2008-01-01 | 2008-12-01 | 563000 | 0 | 563000 | 563000 | 100% | 0 | 0 |  | 71930 | 0 | 71930 | 0 | 0 | Project completed. PCR under preparation. |  |  | 2003-06-01 | INV | 0
FIN | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | I |  | 157.4 | 157.4 | 0 | 0 | 2002-11-01 | 2005-11-01 | 2009-11-01 |  | 2009-11-01 | 2009-12-01 | 590000 | 0 | 590000 | 590000 | 100% | 0 | 0 |  | 74900 | 0 | 74900 | 0 | 0 | All investment work has been undertaken. Last public awareness event held in 2009 on the achievements of the NOPP and future challenges. Training was also conducted for the solvents sector. PCR is under preparation. |  |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (air-conditioning sector plan) | Multiyear | ASP | JOR | PHA | 65 | INV | 91 | N | I | HCFC | 7.8 | 7.8 | 0 | 0 | 2011-11-01 | 2014-04-01 | 2013-11-30 | 2016-11-01 |  |  | 1070100 | 0 | 1070100 | 117600 | 10.99% | 952500 | 952500 | 550000 | 80258 | 0 | 8820.05 | 71437.95 | 71437.95 | GA signed by GoJ and WB May 13. Disbursement under the AC Sector Plan started in Jan 14 to retroactively finance project management expenditures incurred the previous year. Two subgrant agreements (SGAs) for 2 of 3 enterprises signed Feb and Sep 2014. Equipment procurement underway. Third SGA delayed because enterprise is experiencing financial difficulties. NOU/WB agreed with MEC on milestones for submitting a business plan and other documents to prove viability. Project completion date is not expected to be adversely affected. | 2013-2014 consumption verification completed under UNIDO as lead IA. Abu Haltam's equipment package is being shipped; NRC opened bids in May 15 and has selected the equipment supplier. Conditions for MEC's participation in the project set in May but not met by end of Jun 15. Subproject will be cancelled. |  |  | INV | 0
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 07 | DEM | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 07 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (commercial refrigeration sector) |  | ASP | JOR | REF | 60 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-30 |  | 2011-07-01 | 2011-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (additional funding for the commercial refrigeration subsector) |  | ASP | JOR | REF | 61 | PRP | 87 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-08-01 | 2011-07-31 |  | 2011-07-01 | 2011-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning sector) |  | ASP | JOR | REF | 63 | PRP | 89 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-31 |  | 2011-08-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | HCFC air-conditioning sector plan prepared and submitted to the 64th and 65th ExCom Meetings. Sector plan approved in Nov 11. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 04 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 07 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 09 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project preparation is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | PIU fully operational. Funds were fully disbursed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  | 1999-06-01 | Non-INV | 0
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | IS tranche completed and full funding dibursed. |  |  | 2000-12-01 | Non-INV | 0
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | CP update submitted to the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | -20000 | 113333 | 113333 | 100% | 0 | 0 |  | 17333.29 | -2600 | 14733.29 | 0 | 0 | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-06-01 | 2005-07-01 |  | 2005-06-01 | 2005-06-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Phase 6 of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (phase VI) | Individual | ASP | JOR | SEV | 46 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-31 | 147320 | 0 | 147320 | 147320 | 100% | 0 | 0 |  | 11049 | 0 | 11049 | 0 | 0 | IS Phase VI is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | JOR | SEV | 52 | INS | 81 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-07-01 |  | 2009-09-01 | 2010-01-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | IS Phase VII is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VIII) | Individual | ASP | JOR | SEV | 58 | INS | 84 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2011-03-01 | 2011-03-01 | 110500 | 0 | 110500 | 110500 | 100% | 0 | 0 |  | 8288 | 0 | 8288 | 0 | 0 | IS Phase VIII completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IX) | Individual | ASP | JOR | SEV | 62 | INS | 88 | N | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | IS Phase IX completed. |  |  |  | Non-INV | 0
COM | IBRD | Extension of institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | JOR | SEV | 68 | INS | 92 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-12-01 | 2014-12-31 |  | 2014-12-01 |  | 147333 | 0 | 147333 | 127712 | 86.68% | 19621 | 19621 | 19621 | 10313 | 0 | 8939.57 | 1373.43 | 1373.43 | In 2014, NOU facilitated issuance of instructions for controlling ODS import and export of ODS and broadening quota system for HCFC control; issued 150 approvals for HCFC imports; collected consumption data; reported to Ozone and MLF Secretariats: organized international ozone day celebrations as well as meetings of steering committees and National Ozone Committee; attended international / regional ozone meetings, including ExCom; and, conducted field visits to HCFC-using industry. New IS XI approved at the 73rd ExCom. | IS Phase X completed. US$19,621 disbursed in 2015; financial completion achieved in Apr 15. |  |  | Non-INV | 0
ONG | IBRD | Extension of institutional strengthening project (phase XI: 1/2015-12/2016) |  | ASP | JOR | SEV | 73 | INS | 93 | N | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-12-31 | 2016-12-31 |  |  | 147333 | 0 | 147333 | 0 | 0% | 147333 | 147333 | 65000 | 10313 | 0 | 0 | 10313 | 10313 | Phase XI newly approved at the 73rd ExCom. | In 2015, NOU facilitated issuance of instructions for controlling ODS import and export of ODS and broadening quota system for HCFC control; issued 200 approvals for HCFC imports, compressors etc.; reported to the MLF Secretariat: attended the 35th OEWG and regional ozone meetings; and, conducted field visits to HCFC-using industry. The NOU signed a contract for a financial auditor to audit the umbrella ODS project and collected consumption data. |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 04 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100% | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 06 | INV | 04 | N | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2012-04-01 | 1799940 | 0 | 1799940 | 1799940 | 100% | 0 | 0 |  | 140395 | 0 | 140395 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 | 2012-04-01 | 2969065 | 0 | 2969065 | 2969065 | 100% | 0 | 0 |  | 259216 | 0 | 259216 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-12-01 | 2012-04-01 | 2013100 | 0 | 2013100 | 2013100 | 100% | 0 | 0 |  | 169179 | 0 | 169179 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | I | CFC | 430 | 430 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 1688300 | 0 | 1688300 | 1688300 | 100% | 0 | 0 |  | 143947 | 0 | 143947 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | MAL | PHA | 47 | INV | 156 | N | I | CFC | 470.8 | 470.8 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2008-12-01 | 2012-04-01 | 1208300 | 0 | 1208300 | 1208300 | 100% | 0 | 0 |  | 100747 | 0 | 100747 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | MAL | PHA | 49 | INV | 157 | N | I | CFC | 120 | 120 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-12-01 | 2012-04-01 | 1013300 | 0 | 1013300 | 1013300 | 100% | 0 | 0 |  | 83197 | 0 | 83197 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | MAL | PHA | 52 | INV | 158 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 2007-07-01 | 2009-12-01 | 2008-07-31 |  | 2010-09-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | MAL | PHA | 55 | INV | 160 | N | I | CFC | 89 | 89 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2009 annual programme | Multiyear | ASP | MAL | PHA | 59 | INV | 166 | N | I | CFC | 350.7 | 350.7 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 275000 | -75992 | 199008 | 199008 | 100% | 0 | 0 |  | 24750 | -6839.28 | 17910.72 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 06 | TAS | 05 | N | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-08-01 | INV | 0
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. $5,096.82 will be returned. |  |  | 1996-01-01 | INV | 0
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100% | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100% | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100% | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100% | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | 2000-03-01 | INV | 0
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100% | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | Project fully completed. |  |  |  | INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | Completed. |  |  | 1999-06-01 | Non-INV | 0
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Ongoing |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1996-07-01 | INV | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100% | -0.2 | -0.4 |  | 7396.09 | 0 | 7396.12 | -0.03 | -0.03 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 |  | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | Project cancelled. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100% | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 100% | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.22 | 0.05 | 0.05 | Project completed. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | I | CFC | 57.3 | 63.98 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2006-12-01 |  | 2006-03-01 | 2006-03-01 | 252340 | 0 | 252340 | 252340 | 100% | 0 | 0 |  | 18925.5 | 0 | 18925.5 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV | 0
FIN | IBRD | Preparation for the second component of the pilot demonstration project on ODS waste management and disposal |  | LAC | MEX | DES | 58 | PRP | 143 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-31 |  | 2012-03-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Report completed and submitted as an information document to the 66th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 10 | N | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 60 | N | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 04 | TRA | 04 | N | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-05-01 | Non-INV | 0
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 05 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 work programme | Multiyear | LAC | MEX | PHA | 45 | INV | 124 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2007-04-01 |  | 2006-02-01 | 2006-02-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | Funds were disbursed to FIDE. These funds were added to the rotating fund created with the first tranche. By the end of 2006, 19 chillers had been replaced (the target was 10), and as of Dec 06, collection rates on loans were 100%. |  |  |  | INV | 0
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 05 | DEM | 06 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 05 | INV | 09 | N | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV | 0
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 05 | INV | 61 | N | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV | 0
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 05 | INV | 62 | N | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 05 | INV | 63 | N | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV | 0
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 05 | INV | 64 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-03-01 | INV | 0
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 05 | INV | 65 | N | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 05 | TAS | 08 | N | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV | 0
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 05 | TAS | 13 | N | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. |  |  |  | INV | 0
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 05 | TRA | 07 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. |  |  | 1996-12-01 | Non-INV | 0
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100% | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | Project completed. Indirect phaseout of 110.5 MT. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100% | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). |  |  |  | INV | 0
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100% | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 06 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 09 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Bank is evaluating its activities in the country. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 05 | INV | 11 | N | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 05 | INV | 12 | N | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-11-01 | INV | 0
FIN | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | I | CFC | 14.5 | 19.94 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2005-07-01 |  | 2006-06-01 | 2006-06-01 | 288700 | -22568 | 266132 | 266132 | 100% | 0 | 0 |  | 21653 | -1692.64 | 19960.36 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV | 0
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 09 | CPG | 17 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 09 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
TRF | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 08 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 |  |  | 2005-07-01 | 64600 | -64600 | 0 | 0 |  | 0 | 0 |  | 5814 | -5814 | 0 | 0 | 0 | Project transferred to UNIDO at the 46th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 06 | N | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 |  | 2005-02-01 | 2006-07-01 | 1247330 | -1030 | 1246300 | 1246300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 07 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2002-11-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100% | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | Project and draft PCR completed. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23796.5 | 136828.5 | 136828.5 | 100% | 0 | 0 |  | 20881 | -3093.5 | 17787.5 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | I | CFC | 239.6 | 239.6 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2006-10-01 | 2006-10-01 | 1600000 | -209475 | 1390525 | 1390525 | 100% | 0 | 0 |  | 208000 | -27231.75 | 180768.25 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 |  | 2005-02-01 | 2007-06-01 | 563339 | 0 | 563339 | 563339 | 100% | 0 | 0 |  | 73234 | 0 | 73234 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 |  | 2006-10-01 | 2006-10-01 | 718900 | -161848 | 557052 | 557052 | 100% | 0 | 0 |  | 93457 | -21040.24 | 72416.76 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100% | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | Project completed, PCR submitted June 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 |  | 2005-06-01 | 2005-09-01 | 279280 | -5612.86 | 273667.14 | 273667.14 | 100% | 0 | 0 |  | 36306.4 | -729.68 | 35576.72 | 0 | 0 | Project completed. |  |  | 2003-12-01 | INV | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | I | CFC | 106.9 | 106.9 | 0 | 0 | 2003-12-01 | 2005-11-01 | 2006-01-01 |  | 2006-12-01 | 2007-06-01 | 658973 | -12331 | 646642 | 646642 | 100% | 0 | 0 |  | 49423 | -801 | 48622 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 |  | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | Subproject cancelled. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | I | CFC | 117.6 | 117.6 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 |  | 2006-12-01 | 2006-12-01 | 841750 | 0 | 841750 | 841750 | 100% | 0 | 0 |  | 109428 | 0 | 109428 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 | 2005-02-01 | 205893 | 0 | 205893 | 205893 | 100% | 0 | 0 |  | 26766 | 0 | 26766 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 |  | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 |  | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100% | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 |  | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | Project cancelled at the 35th ExCom Meeting. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-08-01 | 2006-02-01 | 176681 | 0 | 176681 | 176681 | 100% | 0 | 0 |  | 22968.53 | 0 | 22968.53 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-11-01 | 2007-06-01 | 204736 | -21870.06 | 182865.94 | 182865.94 | 100% | 0 | 0 |  | 26615.68 | -2843.1 | 23772.9 | -0.32 | -0.32 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | I | CFC | 181.3 | 181.3 | 0 | 0 | 2004-04-01 | 2005-08-01 | 2007-04-01 |  | 2006-12-01 | 2007-06-01 | 1126855 | -49164 | 1077691 | 1077691 | 100% | 0 | 0 |  | 84514 | -3195 | 81319 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | CPU submitted and approved at the 41st ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | PHI | DES | 57 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2013-12-01 | 2010-12-31 |  | 2014-06-01 | 2014-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | A study on 'The Establishment of a Public-Private Financing System for Disposal of ODS for the Philippines' was completed and accepted by the client in June 2014. The report was submitted to the 71st ExCom as an information document. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) |  | ASP | PHI | FOA | 73 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 | 2016-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 150000 | 50000 | 10500 | 0 | 0 | 10500 | 10500 | Project preparation funds recently approved in Nov 2014. | A stakeholder meeting to discuss the coverage of the Stage II HPMP particularly for the air-conditioning sector was held in Feb 2015. Agreement on the project preparation process reached. Consultants will be engaged by Aug 2015 and survey will start Sep 15. Expected survey completion date is Dec 15; proposal to be submitted to the 76th ExCom. |  |  | Non-INV | 0
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support country’s request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | I | MBR | 9 | 9 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-12-01 |  | 2010-12-01 | 2010-12-01 | 330000 | 0 | 330000 | 330000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | Project was extended to allow transfer of activities to regular personnel of the implementing agency to ensure sustainability of MB phaseout in non-QPS applications and prevent return of stockholders to use of MB in non-QPS after project completion; facilitate coordination of activities of the FPA and BPI in monitoring QPS use of MB, Administrative Order No. 17 series of 2010 on "Guidelines for the Bureau of Plant Industry and Fertilizer and Pesticides Authority (FPA) on the Implementation of a Logbook System for Methyl Bromide QPS Uses" signed 16 Aug 2010. Regular inspection and monitoring visits conducted in selected regions; follow-thru workshops for database establishment for FPA regions held; verification and on-the-spot inspection of QPS MB consumption also conducted; consumption verification audits for 2008-2009 completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 09 | INV | 18 | N | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Completed. NCPP approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | I |  | 89.3 | 89.3 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2012-04-01 | 2858473 | 0 | 2858473 | 2858473 | 100% | 0 | 0 |  | 248663 | 0 | 248663 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2012-04-01 | 1877418 | -23495 | 1853923 | 1853923 | 100% | 0 | 0 |  | 160968 | -2014 | 158953.56 | 0.44 | 0.44 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 2160071 | 0 | 2160071 | 2160071 | 100% | 0 | 0 |  | 186006 | 0 | 186006 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | PHI | PHA | 47 | INV | 79 | N | I | CFC | 149 | 149 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2011-06-01 | 2012-04-01 | 2873197 | -1683614 | 1189583 | 1189583 | 100% | 0 | 0 |  | 248588 | -145666 | 102922.3 | -0.3 | -0.3 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | PHI | PHA | 51 | INV | 81 | N | I | CFC | 907 | 907 | 0 | 0 | 2007-03-01 | 2007-12-01 | 2008-03-01 |  | 2011-06-01 | 2012-04-01 | 337717 | -18096 | 319621 | 319621.28 | 100% | -0.28 | -0.28 |  | 20795 | -1114 | 19680.75 | 0.25 | 0.25 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | PHI | PHA | 54 | INV | 82 | N | I | CFC | 421.3 | 421.3 | 0 | 0 | 2008-04-01 |  | 2009-03-31 |  | 2011-06-01 | 2012-04-01 | 110000 | -110000 | 0 | 0 |  | 0 | 0 |  | 5500 | -5500 | 0 | 0 | 0 | Transfer of the $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | PHI | PHA | 55 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | HPMP resubmitted and approved at the 68th ExCom with UNEP as the lead IA. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | PHI | PHA | 73 | PRP | 98 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 | 2016-12-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 90000 | 60000 | 6300 | 0 | 0 | 6300 | 6300 | Project preparation funds recently approved in Nov 2014. | A stakeholder meeting to discuss the coverage of the Stage II HPMP particularly for the air-conditioning sector was held in Feb 2015. Agreement on the project preparation process reached. Consultants will be engaged by Aug 2015 and survey will start Sep 15. Expected survey completion date is Dec 15; proposal to be submitted to the 76th ExCom. |  |  | Non-INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 09 | INV | 07 | N | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 09 | INV | 08 | N | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 09 | INV | 09 | N | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100% | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 09 | INV | 19 | N | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100% | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  |  | INV | 0
CLO | IBRD | Preparation for HCFC phase-out investment activities (domestic air-conditioning sector) |  | ASP | PHI | REF | 59 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  |  | 2012-07-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 |  | 4875 | -4875 | 0 | 0 | 0 | Preparation funding returned at the 67th ExCom meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. Balance of funds returned to Multilateral Fund. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 09 | INS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed physically and financially. |  |  | 1999-12-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 09 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 09 | TAS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 09 | TAS | 17 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project and PCR completed. |  |  | 1999-12-01 | Non-INV | 0
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100% | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | Phase II completed and IS renewal approved at the 36th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 | 2005-01-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 23547.29 | 0 | 23547.29 | 0 | 0 | Phase III completed and IS renewal approved at the 42nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2005-05-01 | 90566 | 0 | 90566 | 90566 | 100% | 0 | 0 |  | 6792 | 0 | 6792 | 0 | 0 | First half of Phase IV of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of the institutional strengthening project (phase IV, second year) | Individual | ASP | PHI | SEV | 45 | INS | 78 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2006-05-01 | 90567 | 0 | 90567 | 90567 | 100% | 0 | 0 |  | 6793 | 0 | 6793 | 0 | 0 | Second half of Phase IV of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | PHI | SEV | 48 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2008-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase V completed and IS renewal approved at the 54th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | PHI | SEV | 54 | INS | 83 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-31 |  | 2010-06-01 | 2010-11-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase VI completed. IS renewed at the 60th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 60 | INS | 89 | N | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-12-31 |  | 2011-06-01 | 2011-11-01 | 158491 | -64471 | 94020 | 94020 | 100% | 0 | 0 |  | 11887 | -4835 | 7052 | 0 | 0 | Balance of IS VII transferred to UNEP in Nov 11 subsequent to the closing of the overall ODS Grant Agreement between the Philippines and the WB. |  |  |  | Non-INV | 0
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 11 | N | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | 1995-09-01 | INV | 0
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise decided not to proceed with project. Project cancelled. |  |  | 1993-09-01 | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 13 | N | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | 1997-02-01 | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 14 | N | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | 1996-07-01 | INV | 0
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 15 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise is no longer eligible for grant funding. Project cancelled. |  |  |  | INV | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. |  |  |  | Non-INV | 0
TRF | IBRD | Preparation of a HCFC phase-out management plan (refrigeration and air-conditioning sectors) |  | ASP | SRL | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-12-31 |  |  | 2010-07-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project preparation of HCFC phaseout in the refrigeration and AC sectors was transferred to UNDP at the 61st ExCom Meeting. |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR approved by the WB in Jun/2000. |  |  | 1999-08-01 | INV | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 |  | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100% | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | Project completed. PCR submitted to the WB in May/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100% | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100% | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | Project Completed. PCR submitted to the WB in Jun/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100% | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100% | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100% | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100% | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100% | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV | 0
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 |  | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | Project cancelled July 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100% | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 2001-03-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100% | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2001-03-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100% | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | Project completed. PCR submitted to the WB in Sep. 01 |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100% | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100% | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100% | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 | 2005-02-01 | 51795 | -14902 | 36893 | 36893 | 100% | 0 | 0 |  | 6733.35 | -1936.91 | 4796.09 | 0.35 | 0.35 | Project completed and PCR under review. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 | 2005-03-01 | 2003-08-01 |  | 2004-08-01 | 2005-03-01 | 177741 | -79622 | 98119 | 98119 | 100% | 0 | 0 |  | 23106.33 | -10350.86 | 12755.47 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100% | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. |  |  |  | INV | 0
FIN | IBRD | Preparation for a HCFC foam sector plan |  | ASP | THA | FOA | 61 | PRP | 155 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-01 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 | 2005-03-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project preparation completed. Strategy approved at the 44th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | I | MBR | 58.7 | 58.7 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2006-12-01 |  | 2013-12-01 | 2014-04-01 | 546991 | -22160.08 | 524830.92 | 524830.92 | 100% | 0 | 0 | 0 | 41024 | -1661.99 | 39362.01 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National methyl bromide phase-out plan (second tranche) | Multiyear | ASP | THA | FUM | 50 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2013-12-01 | 2014-04-01 | 1412214 | -508944.77 | 903269.23 | 903269.23 | 100% | 0 | 0 | 0 | 105916 | -38170.84 | 67745.16 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National methyl bromide phase-out plan (third tranche) | Multiyear | ASP | THA | FUM | 57 | INV | 152 | N | I | MBR | 183.1 | 183.1 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2012-12-31 |  | 2013-12-01 | 2014-04-01 | 942395 | -701762 | 240633 | 240633 | 100% | 0 | 0 | 0 | 70680 | -52632 | 18048 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | I | HAL | 135.85 | 135.85 | 0 | 0 | 1999-11-01 | 2006-12-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 220750 | -168490 | 52260 | 52260 | 100% | 0 | 0 |  | 28697.5 | -21904 | 6793.5 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 |  | 2010-09-01 | 2011-11-01 | 568000 | -264529 | 303471 | 303471 | 100% | 0 | 0 |  | 72480 | -33755.4 | 38724.6 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 | 2014-04-01 | 540000 | 0 | 540000 | 540000 | 100% | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 | 2014-04-01 | 5194380 | 0 | 5194380 | 5194380 | 100% | 0 | 0 | 0 | 459494 | 0 | 459494 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-03-01 | 2014-04-01 | 4011846 | 0 | 4011846 | 4011846 | 100% | 0 | 0 | 0 | 353066 | 0 | 353066 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | I | CFC | 486 | 486 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 | 2014-04-01 | 1315400 | 0 | 1315400 | 1315400 | 100% | 0 | 0 | 0 | 118386 | 0 | 118386 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | THA | PHA | 45 | INV | 144 | N | I | CFC | 962.9 | 962.9 | 0 | 0 | 2005-04-01 | 2009-12-01 | 2006-04-01 |  | 2013-12-01 | 2014-04-01 | 1330400 | -103127 | 1227273 | 1227273 | 100% | 0 | 0 | 0 | 111736 | -8661.3 | 103074.7 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual implementation plan | Multiyear | ASP | THA | PHA | 48 | INV | 146 | N | I | CFC | 243 | 243 | 0 | 0 | 2006-04-01 | 2009-12-01 | 2007-04-01 |  | 2013-12-01 | 2014-04-01 | 851600 | -502256 | 349344 | 349344 | 100% | 0 | 0 | 0 | 68644 | -40485 | 28159 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual implementation plan | Multiyear | ASP | THA | PHA | 53 | INV | 149 | N | I | CFC | 209 | 209 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2013-12-01 | 2014-04-01 | 550000 | -550000 | 0 | 0 |  | 0 | 0 | 0 | 49500 | -49500 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual implementation plan | Multiyear | ASP | THA | PHA | 55 | INV | 150 | N | I | CFC | 208 | 208 | 0 | 0 | 2008-07-01 |  | 2009-07-31 |  | 2013-12-01 | 2014-04-01 | 550000 | -550000 | 0 | 0 |  | 0 | 0 | 0 | 49500 | -49500 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | THA | PHA | 55 | PRP | 151 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | HPMP approved at the 68th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase-out plan: 2010-2012 annual implementation plan | Multiyear | ASP | THA | PHA | 60 | INV | 154 | N | I | CFC | 501.6 | 501.6 | 0 | 0 | 2010-04-01 |  | 2011-04-30 |  | 2013-12-01 | 2014-04-01 | 385000 | -385000 | 0 | 0 |  | 0 | 0 | 0 | 34650 | -34650 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | THA | PHA | 68 | INV | 161 | N | I | HCFC | 33.4 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2016-12-01 |  |  | 2343653 | 0 | 2343653 | 0 | 0% | 2343653 | 2343653 | 970702 | 164055 | 0 | 0 | 164055 | 164055 | Appraisal completed in Jan. 2014. Grant agreement (GA) negotiation completed in Feb. 14 and GA sent for counter-signing in Apr. 14. However, due to the political situation, GA signing was delayed until Nov. 14. Two PMUs established in DIW and GSB in Jan and Aug. 14 respectively. Project implementation manual prepared. 12 environment management plans completed for AC enterprises, and 1 environmental framework done for foam beneficiaries. Three subgrant agreements (SGAs) signed Nov. 14 w/AC manufacturers and 1 SGA signed in Dec. 14 w/a foam enterprise. Thru TA component and with counterpart funding, a risk assessment was done on R-32 leading to revision of a standard for use of R-32 AC in tall buildings and quota allocation meetings conducted. A tech use agreement was negotiated between Thai AC enterprises and Daikin, facilitated by GoT and WB. A study tour for Thai AC industry to Japan done Nov 14 to learn about risk assessment from Daikin. Due to GA signing delay, all expenditures incurred in 2014 will be retroactively reimbursed in 2015. | Since Jan. 2015, 3 more SGAs signed w/AC manufacturers and 3 w/foam enterprises worth a total US$4.2 million. Executing agency GSB disbursed $1,104,883 to these 10 enterprises as of 23 Mar. 15. Four out of 5 remaining a/c manufacturers will sign SGAs by end 2015. One foam enterprise will sign an SGA Jul 15. There are 6 additional foam proposals in the pipeline; 10 additional enterprises expressed interest to participate. By end 2015 at least 6 more foam SGAs will be signed. For smaller firms, DIW will invite expression of interest by Sep 15. Modalities to channel technical and financial assistance to these SMEs will be agreed prior to Jan 16. By end of 2015, all 5 foam enterprises with SGAs signed before Aug 15 will have completed conversion. GSB PMU fully staffed. One technical consultant appointed in DIW PMU. Additional staff under recruitment. 2nd tranche request submitted to 74th ExCom. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning group project) | Multiyear | ASP | THA | PHA | 68 | INV | 162 | N | I | HCFC | 11.4 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2017-12-01 |  |  | 2089100 | 0 | 2089100 | 0 | 0% | 2089100 | 2089100 | 1000000 | 146237 | 0 | 0 | 146237 | 146237 | Appraisal completed in Jan. 2014. Grant agreement (GA) negotiation completed in Feb. 14 and GA sent for counter-signing in Apr. 14. However, due to the political situation, GA signing was delayed until Nov. 14. Two PMUs established in DIW and GSB in Jan and Aug. 14 respectively. Project implementation manual prepared. 12 environment management plans completed for AC enterprises, and 1 environmental framework done for foam beneficiaries. Three subgrant agreements (SGAs) signed Nov. 14 w/AC manufacturers and 1 SGA signed in Dec. 14 w/a foam enterprise. Thru TA component and with counterpart funding, a risk assessment was done on R-32 leading to revision of a standard for use of R-32 AC in tall buildings and quota allocation meetings conducted. A tech use agreement was negotiated between Thai AC enterprises and Daikin, facilitated by GoT and WB. A study tour for Thai AC industry to Japan done Nov 14 to learn about risk assessment from Daikin. Due to GA signing delay, all expenditures incurred in 2014 will be retroactively reimbursed in 2015. | Since Jan. 2015, 3 more SGAs signed w/AC manufacturers and 3 w/foam enterprises worth a total US$4.2 million. Executing agency GSB disbursed $1,104,883 to these 10 enterprises as of 23 Mar. 15. Four out of 5 remaining a/c manufacturers will sign SGAs by end 2015. One foam enterprise will sign an SGA Jul 15. There are 6 additional foam proposals in the pipeline; 10 additional enterprises expressed interest to participate. By end 2015 at least 6 more foam SGAs will be signed. For smaller firms, DIW will invite expression of interest by Sep 15. Modalities to channel technical and financial assistance to these SMEs will be agreed prior to Jan 16. By end of 2015, all 5 foam enterprises with SGAs signed before Aug 15 will have completed conversion. GSB PMU fully staffed. One technical consultant appointed in DIW PMU. Additional staff under recruitment. 2nd tranche request submitted to 74th ExCom. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (technical assistance) | Multiyear | ASP | THA | PHA | 68 | TAS | 160 | N | I | HCFC | 1.3 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2018-12-01 |  |  | 108185 | 0 | 108185 | 0 | 0% | 108185 | 108185 | 20000 | 7575 | 0 | 0 | 7575 | 7575 | Appraisal completed in Jan. 2014. Grant agreement (GA) negotiation completed in Feb. 14 and GA sent for counter-signing in Apr. 14. However, due to the political situation, GA signing was delayed until Nov. 14. Two PMUs established in DIW and GSB in Jan and Aug. 14 respectively. Project implementation manual prepared. 12 environment management plans completed for AC enterprises, and 1 environmental framework done for foam beneficiaries. Three subgrant agreements (SGAs) signed Nov. 14 w/AC manufacturers and 1 SGA signed in Dec. 14 w/a foam enterprise. Thru TA component and with counterpart funding, a risk assessment was done on R-32 leading to revision of a standard for use of R-32 AC in tall buildings and quota allocation meetings conducted. A tech use agreement was negotiated between Thai AC enterprises and Daikin, facilitated by GoT and WB. A study tour for Thai AC industry to Japan done Nov 14 to learn about risk assessment from Daikin. Due to GA signing delay, all expenditures incurred in 2014 will be retroactively reimbursed in 2015. | Since Jan. 2015, 3 more SGAs signed w/AC manufacturers and 3 w/foam enterprises worth a total US$4.2 million. Executing agency GSB disbursed $1,104,883 to these 10 enterprises as of 23 Mar. 15. Four out of 5 remaining a/c manufacturers will sign SGAs by end 2015. One foam enterprise will sign an SGA Jul 15. There are 6 additional foam proposals in the pipeline; 10 additional enterprises expressed interest to participate. By end 2015 at least 6 more foam SGAs will be signed. For smaller firms, DIW will invite expression of interest by Sep 15. Modalities to channel technical and financial assistance to these SMEs will be agreed prior to Jan 16. By end of 2015, all 5 foam enterprises with SGAs signed before Aug 15 will have completed conversion. GSB PMU fully staffed. One technical consultant appointed in DIW PMU. Additional staff under recruitment. 2nd tranche request submitted to 74th ExCom. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multiyear | ASP | THA | PHA | 68 | TAS | 163 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-11-30 | 2018-12-01 |  |  | 276228 | 0 | 276228 | 0 | 0% | 276228 | 276228 | 60000 | 19335 | 0 | 0 | 19335 | 19335 | Appraisal completed in Jan. 2014. Grant agreement (GA) negotiation completed in Feb. 14 and GA sent for counter-signing in Apr. 14. However, due to the political situation, GA signing was delayed until Nov. 14. Two PMUs established in DIW and GSB in Jan and Aug. 14 respectively. Project implementation manual prepared. 12 environment management plans completed for AC enterprises, and 1 environmental framework done for foam beneficiaries. Three subgrant agreements (SGAs) signed Nov. 14 w/AC manufacturers and 1 SGA signed in Dec. 14 w/a foam enterprise. Thru TA component and with counterpart funding, a risk assessment was done on R-32 leading to revision of a standard for use of R-32 AC in tall buildings and quota allocation meetings conducted. A tech use agreement was negotiated between Thai AC enterprises and Daikin, facilitated by GoT and WB. A study tour for Thai AC industry to Japan done Nov 14 to learn about risk assessment from Daikin. Due to GA signing delay, all expenditures incurred in 2014 will be retroactively reimbursed in 2015. | Since Jan. 2015, 3 more SGAs signed w/AC manufacturers and 3 w/foam enterprises worth a total US$4.2 million. Executing agency GSB disbursed $1,104,883 to these 10 enterprises as of 23 Mar. 15. Four out of 5 remaining a/c manufacturers will sign SGAs by end 2015. One foam enterprise will sign an SGA Jul 15. There are 6 additional foam proposals in the pipeline; 10 additional enterprises expressed interest to participate. By end 2015 at least 6 more foam SGAs will be signed. For smaller firms, DIW will invite expression of interest by Sep 15. Modalities to channel technical and financial assistance to these SMEs will be agreed prior to Jan 16. By end of 2015, all 5 foam enterprises with SGAs signed before Aug 15 will have completed conversion. GSB PMU fully staffed. One technical consultant appointed in DIW PMU. Additional staff under recruitment. 2nd tranche request submitted to 74th ExCom. |  |  | Non-INV | 0
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 07 | TAS | 07 | N | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | -74881 | 825119 | 825119 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100% | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 |  | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | Project cancelled. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100% | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100% | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100% | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100% | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100% | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100% | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | Project completed. PCR submitted to the WB in Dec/1999. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100% | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 100% | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | Project completed. PCR submitted to the World Bank 4 September 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100% | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV | 0
FIN | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | I | CFC | 173 | 186.1 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 | 2006-07-01 | 750000 | 1717315 | 2467315 | 2467315 | 100% | 0 | 0 |  | 97500 | 208904 | 306404 | 0 | 0 | Project physically and financially completed. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 |  | 2002-12-01 |  | 2003-09-01 | 2005-04-01 | 2475000 | -2475000 | 0 | 0 |  | 0 | 0 |  | 282250 | -145520.83 | 136729.17 | 0 | 0 | Project completed. Funding of $1,198,947 was disbursed for replacing 17 chillers with the understanding that it would be paid back once energy savings were achieved. $1,198,947 was paid back in full by Thailand in 2007 directly to the Bank and was received as "other income." That amount was subsequently deducted by the Treasurer in new approvals at the 54th ExCom. |  |  |  | INV | 0
FIN | IBRD | Preparation for a HCFC refrigeration sector plan |  | ASP | THA | REF | 61 | PRP | 156 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HCFC survey completed, stakeholder consultations completed, technical inputs provided and initial HPMP completed. Refrigeration information woven into HPMP. Commerical refrigeration enterprises consuming HCFC-141b were included in the foam sector plan, instead of a separate sector plan. Given a strong interest of the major industry in Thailand to adopt HC technology for the refrigeration circuits, however, components are not widely available at present, the decision was to address the refrigeration circuits under Stage II HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for a HCFC air-conditioning sector plan |  | ASP | THA | REF | 61 | PRP | 157 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed and closed. Balance returned to Multilateral Fund. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Umbrella Grant Agreement signed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | Ongoing |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100% | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-08-01 | 2005-08-01 | 346667 | 0 | 346667 | 346667 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Remaining budget was used for public awareness activities e.g. ozone road show, publications, etc. These PR activities were conducted to promote and ensure sustainable ODS phaseout. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (phase IV) | Individual | ASP | THA | SEV | 46 | INS | 145 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-09-01 | 2007-10-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Phase IV of the IS project successfully completed. IS renewed at the 52nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | THA | SEV | 52 | INS | 148 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-06-30 |  | 2010-11-01 | 2010-11-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Capacity of NOU and government agencies have been continuously enhanced. Phase V of the IS project successfully completed. IS renewed at the 58th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | THA | SEV | 58 | INS | 153 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 | 2013-06-01 | 260001 | 0 | 260001 | 260001 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | Import and export controls of HCFCs done thru licensing system. Quota for each HCFC importer was determined. Full compliance with reporting obligations under Art. 7 and Country Programme Implementation. A memo of understanding between Customs and the Office of Vocational Education Commission signed to set up a collaboration mechanism strengthening ODS phaseout efforts. NOU participated in MP-related meetings and coordinated with UNEP to facilitate the 25th MOP and 33rd OEWG meeting in Thailand in 2013. |  |  |  | Non-INV | 0
ONG | IBRD | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | THA | SEV | 68 | INS | 159 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-12-01 | 2014-12-31 | 2016-12-01 |  |  | 346668 | 0 | 346668 | 42563.9 | 12.28% | 304104.1 | 304104.1 | 60000 | 24267 | 0 | 2979.5 | 21287.5 | 21287.5 | Total expenditures of $36,670 incurred in 2014. As the ISP falls under new WB-GoT Grant Agreement that was only signed in Nov. 14 no disbursement occurred. Amount was retroactively disbursed to DIW upon signing of the GA in 2015. Import and export controls of HCFCs done thru licensing system. Quota for each HCFC importer was determined. Full compliance with reporting obligations under Art. 7 and Country Programme Implementation. NOU participated in the 34th OEWG and 26th MOP. | NOU staffed with 3 consultants. Two technical officers are being recruited. NOU attended the 35th OEWG meeting in Bangkok. Country programme data submitted to Fund Secretariat. |  |  | Non-INV | 0
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 07 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1994-12-01 | Non-INV | 0
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-02-01 | INV | 0
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100% | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | Project completed. |  |  | 1996-12-01 | INV | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 |  | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | Project cancellation |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100% | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 04 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 07 | INV | 04 | N | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 07 | INV | 05 | N | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 07 | INV | 06 | N | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final PCR provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 | 2007-07-01 | 553400 | -131363.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 71942 | -17077.2 | 54864.79 | 0.01 | 0.01 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2007-07-01 | 529490 | -107453.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 68243.9 | -13849.21 | 54394.68 | 0.01 | 0.01 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | I | CFC | 8.8 | 8.8 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 68917 | -4392 | 64525 | 64525 | 100% | 0 | 0 |  | 8959.21 | -570.96 | 8388.25 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | I | CFC | 11.7 | 11.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 91477 | -5148 | 86329 | 86329 | 100% | 0 | 0 |  | 11892.01 | -669.24 | 11222.77 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | I | CFC | 8.3 | 8.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 64700 | -5970 | 58730 | 58730 | 100% | 0 | 0 |  | 8411 | -776.1 | 7634.9 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 156235 | -15623.5 | 140611.5 | 140611.5 | 100% | 0 | 0 |  | 20310.55 | -2031.06 | 18279.49 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | I | CFC | 7.5 | 7.5 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 59079 | -995.9 | 58083.1 | 58083.1 | 100% | 0 | 0 |  | 7680.27 | -129.47 | 7550.8 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | Project prep. cancelled at the 41st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National ODS phase-out plan (first tranche) | Multiyear | AFR | TUN | PHA | 49 | INV | 47 | N | I | CFC | 169.5 | 169.5 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2008-07-31 |  | 2012-06-01 | 2012-10-01 | 790000 | -360123 | 429877 | 429877 | 100% | 0 | 0 |  | 59250 | -27009 | 32241 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV | 0
FIN | IBRD | National ODS phase-out plan (second tranche) | Multiyear | AFR | TUN | PHA | 61 | INV | 51 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2012-06-01 | 2012-10-01 | 345395 | -345395 | 0 | 0 |  | 0 | 0 |  | 25905 | -25905 | 0 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV | 0
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 07 | TAS | 07 | N | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 08 | TAS | 08 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 08 | INS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 09 | CPG | 22 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision completed. |  |  |  | Non-INV | 0
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100% | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | I | CFC | 20.2 | 20.2 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 242667 | 0 | 242667 | 242667 | 100% | 0 | 0 |  | 18200.03 | 0 | 18200.03 | 0 | 0 | Phase III IS completed and IS IV approved at the 48th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 |  | 2006-07-01 | 2006-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 7200 | 0 | 7200 | 0 | 0 | CPU completed and National ODS Phaseout Plan approved at the 49th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV) | Individual | AFR | TUN | SEV | 48 | INS | 46 | N | I | CFC | 20.05 | 20.05 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2008-06-01 |  | 2008-12-01 | 2009-07-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | AFR | TUN | SEV | 55 | INS | 49 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-06-30 |  | 2011-06-01 | 2011-09-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Phase V IS completed. IS VI approved at the 61st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | AFR | TUN | SEV | 61 | INS | 52 | N | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2012-06-30 |  | 2012-06-01 | 2012-10-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Phase V completed. IS project transferred to UNIDO at the 66th ExCom meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100% | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | Project fully implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100% | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100% | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100% | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  |  | INV | 0
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 |  | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100% | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100% | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100% | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 100% non-CFC production started. Draft PCR prepared. |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100% | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100% | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100% | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | Installation completed. 100% non-CFC production started. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100% | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100% | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100% | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | Project fully implemented. 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100% | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | Project completed. |  |  | 2004-01-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 | 2005-07-01 | 398378 | -277445.52 | 120932.48 | 120932.48 | 100% | 0 | 0 |  | 51789.14 | -36067.98 | 15721.22 | -0.06 | -0.06 | Project completed and non-ODS production at all 5 participating companies underway. |  |  | 2004-01-01 | INV | 0
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100% | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. |  |  |  | INV | 0
FIN | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | I | MBR | 30 | 30 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 |  | 2006-06-01 | 2006-12-01 | 479040 | -1980.74 | 477059.26 | 477059.26 | 100% | 0 | 0 |  | 62275.2 | -257.5 | 62017.7 | 0 | 0 | Project completed both physically and financially. Currently, beneficiary uses CO2 and phosphine in fumigation. No more MeBr is in use. |  |  |  | INV | 0
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100% | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | I | HAL | 118 | 118 | 0 | 0 | 2002-11-01 | 2008-04-01 | 2005-11-01 |  | 2007-12-01 | 2008-04-01 | 439250 | -6992 | 432258 | 432258 | 100% | 0 | 0 |  | 57102.5 | -908.96 | 56193.54 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2008-04-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 295000 | 0 | 295000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2008-04-01 | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 |  | 175000 | 0 | 175000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2008-04-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | I | CFC | 150 | 166 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-04-01 | 750000 | -434097 | 315903 | 315903 | 100% | 0 | 0 |  | 45000 | -26046 | 18954 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2006 annual programme | Multiyear | EUR | TUR | PHA | 47 | INV | 87 | N | I | CFC | 150 | 150 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2007 annual programme | Multiyear | EUR | TUR | PHA | 50 | INV | 89 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2007-12-01 | 2008-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: Implementation status of 2007AP and verification report for CFC consumption for 2007 | Multiyear | EUR | TUR | PHA | 53 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2012-06-01 | 2013-06-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 30000 | -10500 | 19500 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 07 | TAS | 03 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 07 | TAS | 04 | N | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-06-01 | INV | 0
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 08 | INV | 07 | N | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100% | -0.31 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100% | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100% | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | 1996-04-01 | INV | 0
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 |  | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | 1996-05-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100% | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1998-09-01 | INV | 0
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100% | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100% | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100% | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | The project is completed 100% non-CFC production started. Waiting for PCR. |  |  |  | INV | 0
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  | 1999-03-01 | Non-INV | 0
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 08 | INS | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IS project extended to accommodate additional work program of ozone unit. |  |  | 1999-12-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 09 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for supervision on project implementation. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | EUR | TUR | SEV | 32 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2007-12-01 | 2008-04-01 | 200000 | -3641 | 196359 | 196359.49 | 100% | -0.49 | -0.49 |  | 26000 | -473 | 25526.73 | 0.27 | 0.27 | All activities completed and project is physically and financially closed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 260000 | -23601 | 236399 | 236399.08 | 100% | -0.08 | -0.08 |  | 19500 | -1770 | 17729.93 | 0.07 | 0.07 | Field work and information dissemination via workshops and other meetings carried out by MARA. Training programs and other project components all completed. |  |  |  | Non-INV | 0
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100% | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | Project implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100% | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | I | TCA | 15.4 | 15.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 |  | 2005-02-01 | 2005-12-01 | 518693 | -45479.16 | 473213.84 | 473213.84 | 100% | 0 | 0 |  | 67056.23 | -5538.18 | 61517.82 | 0.23 | 0.23 | All 16 projects completed. |  |  |  | INV | 0
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1999-04-01 | INV | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 2000-01-01 | INV | 0
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | I | CFC | 4.62 | 4.62 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | The project was completed in July 99 |  |  | 1999-07-01 | INV | 0
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 05 | N | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100% | -0.18 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | INV | 0
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. |  |  |  | Non-INV | 0
FIN | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | I | CFC | 0 | 0 | 1469 | 1469 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2009-11-01 | 3300000 | 0 | 3300000 | 3300000 | 100% | 0 | 0 |  | 247500 | 0 | 247500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-04-01 | 2009-11-01 | 8100000 | 0 | 8100000 | 8100000 | 100% | 0 | 0 |  | 607500 | 0 | 607500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (third tranche) | Multiyear | LAC | VEN | PRO | 48 | INV | 107 | N | I | CFC | 0 | 0 | 2931 | 2931 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 |  | 131200 | 0 | 131200 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (fourth tranche) | Multiyear | LAC | VEN | PRO | 52 | INV | 110 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2009-01-01 | 2009-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (fifth tranche) | Multiyear | LAC | VEN | PRO | 54 | INV | 111 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2008-12-01 | 2009-11-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78700 | 0 | 78700 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 09 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | INV | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | INV | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | INV | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is now complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC foam sector plan |  | ASP | VIE | FOA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. Foam sector plan and HPMP approved at the 63rd ExCom. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | VIE | FOA | 72 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-31 | 2016-05-31 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 80000 | 55000 | 5600 | 0 | 0 | 5600 | 5600 | TOR for consultant completed and vetted with GoV. Selection process to start in Jan. 15. | Survey launch workshop held in Apr.15 for stakeholders. Data collection plan and survey strategy cleared by the WB in May 15. Survey underway and expected to be completed by Sep 15. |  |  | Non-INV | 0
FIN | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2006-11-01 | 2006-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0 | Project prepared, submitted and approved at the 50th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National phase-out plan of out methyl bromide (first tranche) | Multiyear | ASP | VIE | FUM | 50 | INV | 48 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-12-01 | 2007-11-01 |  | 2011-11-01 | 2014-12-01 | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of out methyl bromide (second tranche) | Multiyear | ASP | VIE | FUM | 59 | INV | 53 | N | I | MBR | 5.2 | 5.2 | 0 | 0 | 2009-11-01 | 2011-12-01 | 2011-11-30 |  | 2012-12-01 | 2014-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (third tranche) | Multiyear | ASP | VIE | FUM | 65 | INV | 59 | N | I | MBR | 10 | 10 | 0 | 0 | 2011-11-01 | 2012-12-01 | 2013-11-30 |  | 2013-11-01 | 2014-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (fourth tranche) | Multiyear | ASP | VIE | FUM | 70 | INV | 61 | N | I | MBR | 20 | 20 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2014-07-31 |  | 2014-12-01 | 2014-12-01 | 58284 | 0 | 58284 | 58284 | 100% | 0 | 0 | 0 | 4371 | 0 | 4371 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (fifth tranche) | Multiyear | ASP | VIE | FUM | 72 | INV | 67 | N | I | MBR | 50 | 50 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2015-05-31 |  | 2014-12-01 | 2014-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | I | CFC | 40 | 40 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2007-04-01 |  | 2008-07-01 | 2011-02-01 | 495537 | 0 | 495537 | 495537 | 100% | 0 | 0 |  | 37165 | 0 | 37165 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC and halon phase-out plan (second tranche) | Multiyear | ASP | VIE | PHA | 49 | INV | 47 | N | I | CFC | 165 | 165 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-06-01 | 2011-02-01 | 586000 | 0 | 586000 | 586000 | 100% | 0 | 0 |  | 43950 | 0 | 43950 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC and halon phase-out plan (third tranche) | Multiyear | ASP | VIE | PHA | 55 | INV | 51 | N | I | CFC | 58.7 | 58.7 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2011-02-01 | 178463 | -551.92 | 177911.08 | 177911.08 | 100% | 0 | 0 |  | 13385 | -41.4 | 13343.6 | 0 | 0 | Project physically and financially completed. Unused amount of US$552 returned. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | VIE | PHA | 55 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2011-03-01 | 2011-06-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Fully completed and disbursed. Project approved at the 63rd Meeting. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 63 | INV | 56 | N | I | HCFC | 44.7 | 44.7 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-03-31 | 2016-12-01 |  |  | 2832518 | 0 | 2832518 | 2832518 | 100% | 0 | 0 | 0 | 212439 | 0 | 212439 | 0 | 0 | HCFC import quota issued for 2014. First subproject out of 12 completed May 13; another 3 completed in Aug, Sep, and Dec 14. Four enterprises are in various stages of conversion. 3 additional enterprises signed subgrant agreements by end of Dec. 14; 1 of which already started equipment procurement. 5 subprojects delayed in reporting year due to insufficient capital (3), relocation (1), or decision not to participate (1). PMU/WB modified payment method to facilitate equipment purchase. Another eligible enterprise will participate. None of these delays are expected to affect planned HPMP completion. 3 customs training workshops and 4 technical training workshops for industry held in 2014. Ban on HCFC-141b imports as of Jan. 1, 2015 put into place Dec 14. All tranche funds disbursed by Dec. 14. | HCFC import quota issued for 2015. One subproject completed in Jan 2015. Three foam companies entered into equipment contracts in Jan and Feb 2015 and are expected to complete subprojects by Sep 15. A total of 6 subprojects are ongoing, 5 completed and 1 to be appraised. No bulk HCFC-141b has or will be imported in 2015. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (Technical assistance and project management) | Multiyear | ASP | VIE | PHA | 63 | TAS | 58 | N | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-12-31 | 2016-12-01 |  |  | 221905 | 0 | 221905 | 221905 | 100% | 0 | 0 | 0 | 16643 | 0 | 16643 | 0 | 0 | HCFC import quota issued for 2014. First subproject out of 12 completed May 13; another 3 completed in Aug, Sep, and Dec 14. Four enterprises are in various stages of conversion. 3 additional enterprises signed subgrant agreements by end of Dec. 14; 1 of which already started equipment procurement. 5 subprojects delayed in reporting year due to insufficient capital (3), relocation (1), or decision not to participate (1). PMU/WB modified payment method to facilitate equipment purchase. Another eligible enterprise will participate. None of these delays are expected to affect planned HPMP completion. 3 customs training workshops and 4 technical training workshops for industry held in 2014. Ban on HCFC-141b imports as of Jan. 1, 2015 put into place Dec 14. All tranche funds disbursed by Dec. 14. | HCFC import quota issued for 2015. One subproject completed in Jan 2015. Three foam companies entered into equipment contracts in Jan and Feb 2015 and are expected to complete subprojects by Sep 15. A total of 6 subprojects are ongoing, 5 completed and 1 to be appraised. No bulk HCFC-141b has or will be imported in 2015. |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 71 | INV | 62 | N | I | HCFC | 89.4 | 0 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2015-12-31 | 2016-12-01 |  |  | 5663016 | 0 | 5663016 | 74033.42 | 1.307% | 5588982.58 | 5588982.58 | 3000000 | 424726 | 0 | 5552.5 | 419173.5 | 419173.5 | HCFC import quota issued for 2014. First subproject out of 12 completed May 13; another 3 completed in Aug, Sep, and Dec 14. Four enterprises are in various stages of conversion. 3 additional enterprises signed subgrant agreements by end of Dec. 14; 1 of which already started equipment procurement. 5 subprojects delayed in reporting year due to insufficient capital (3), relocation (1), or decision not to participate (1). PMU/WB modified payment method to facilitate equipment purchase. Another eligible enterprise will participate. None of these delays are expected to affect planned HPMP completion. 3 customs training workshops and 4 technical training workshops for industry held in 2014. Ban on HCFC-141b imports as of Jan. 1, 2015 put into place Dec 14. All tranche funds disbursed by Dec. 14. | HCFC import quota issued for 2015. One subproject completed in Jan 2015. Three foam companies entered into equipment contracts in Jan and Feb 2015 and are expected to complete subprojects by Sep 15. A total of 6 subprojects are ongoing, 5 completed and 1 to be appraised. No bulk HCFC-141b has or will be imported in 2015. |  |  | INV | 0
ONG | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | VIE | PHA | 72 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-31 | 2016-05-31 |  |  | 90000 | 0 | 90000 | 4000 | 4.444% | 86000 | 86000 | 70000 | 6300 | 0 | 280 | 6020 | 6020 | TOR for consulting firm completed and vetted with GoV. Selection process to start in Jan. 15 | Consultant selection completed Mar. 15. Survey launch workshop held in Apr.15 for stakeholders. Data collection plan and survey strategy cleared by the WB in May 15. Survey underway and expected to be completed by Sep 15. |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC refrigeration sector plan |  | ASP | VIE | REF | 60 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. ExCom asked that the AC component be removed from the proposed HPMP and action plan at its 63rd meeting. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) |  | ASP | VIE | REF | 72 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-31 | 2016-05-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 54000 | 4200 | 0 | 0 | 4200 | 4200 | TOR for consulting firm completed and vetted with GoV. Selection process to start in Jan. 15. | Consultant selection completed Mar. 15. Survey launch workshop held in Apr.15 for stakeholders. Data collection plan and survey strategy cleared by the WB in May 15. Survey underway and expected to be completed by Sep 15. |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) |  | ASP | VIE | REF | 72 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-31 | 2016-05-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 40000 | 4200 | 0 | 0 | 4200 | 4200 | TOR for consulting firm completed and vetted with GoV. Selection process to start in Jan. 15. | Consultant selection completed Mar. 15. Survey launch workshop held in Apr.15 for stakeholders. Data collection plan and survey strategy cleared by the WB in May 15. Survey underway and expected to be completed by Sep 15. |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 06 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 07 | N | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 08 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 09 | N | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | Project completed. Funds returned at the 35th ExCom. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | Israel | International methyl bromide compliance assistance workshop (Bahamas, Barbados, Bosnia, Congo, Ecuador, Ethiopia, Moldova, Mexico, and Zambia) | Individual | GLO | GLO | FUM | 37 | TRA | 240 | A | D |  | 0 |  | 0 |  | 2002-07-01 |  | 2003-03-01 |  | 2002-12-01 |  | 98300 | -64177 | 34123 | 34123 | 100% | 0 | 0 | 0 | 9830 | -5847 | 3983 | 0 | 0 | The workshop was completed as planned. The goals were achieved and feedback from participants was very positive. The numbers of participants were lower than the maximum potential cited in the proposal. Costs were lower than expected. Two countries, Bahamas and Barbados, did not send participants. Participants from Ethiopia did not arrive due to logistical problems. Please see extended summary for further details of workshop content and outputs. * In addition to estimated disbursement stated, there will be support costs at 10%. |  | 2002 |  | 2002
COM | Israel | International methyl bromide compliance assistance workshop | Individual | GLO | GLO | FUM | 56 | TAS | 296 | A | D |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-02-01 |  | 2008-12-01 |  | 101200 | 0 | 101200 | 32347.25 | 31.96% | 68852.75 | 0 | 0 | 13156 | 0 | 0 | 13156 | 0 | The workshop was fully implemented to the satisfaction of participants and organisers. |  |  |  | 2008
ONG | Italy | Phase-out of HCFC-22 in the room and unitary air-conditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 163 | A | I | HCFC | 0 | 0 | 0 |  | 2010-07-01 | 2011-06-01 | 2013-07-01 | 2016-06-01 |  |  | 300000 | 0 | 300000 | 122008 | 40.67% | 177992 | 0 | 50000 | 39000 | 0 | 15861 | 23139 | 0 | - IOC payment completed. - The consumption of HCFC-22 was completely phased out. - Technical problems with some items supplied by Agramkow were solved. - The last company pending to install the equipment started the civil work at its premises. | - UNIDO followed up with the supplier and the beneficiary company for the installation. - It is expected that the installation will be completed by end of August 2015. | 2010 |  | Investment
FIN | Italy | Total phase-out of methyl bromide used in stored commodities fumigation | Individual | AFR | CMR | FUM | 52 | INV | 27 | A | I | MBR | 14.5 | 14.5 | 0 |  | 2007-07-01 | 2008-04-01 | 2010-12-01 |  | 2011-12-01 | 2014-12-01 | 259713 | -2677 | 257036 | 257036 | 100% | 0 | 0 |  | 33763 | 0 | 33415 | 348 | 0 | Refund was reported to 74th ExCom, May 2015. FIN. |  | 2007 |  | Investment
FIN | Italy | National phase-out of methyl bromide (phase II) | Multi-Year | ASP | CPR | FUM | 46 | INV | 431 | A | I | MBR | 534 | 534 | 0 |  | 2005-07-01 | 2007-03-01 | 2015-07-01 |  | 2009-12-01 | 2009-12-01 | 4000000 | 0 | 4000000 | 4000000 | 100% | 0 | 0 |  | 470000 | 0 | 470000 | 0 | 0 | FIN |  | 2005 |  | Investment
FIN | Italy | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (first tranche) | Multi-Year | ASP | CPR | REF | 38 | INV | 393 | A | I | CFC | 181 | 181 | 0 |  | 2002-11-01 | 2003-09-01 | 2005-11-01 |  | 2005-10-01 | 2005-12-01 | 1788991 | 0 | 1788991 | 1788991 | 100% | 0 | 0 |  | 161009 | 0 | 161009 | 0 | 0 | FIN |  | 2003 |  | Investment
FIN | Italy | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid and integral skin foams at Poly-Mix | Multi-Year | EUR | CRO | FOA | 60 | INV | 35 | A | I | HCFC | 1.8 | 1.8 | 0 |  | 2010-04-01 | 2011-12-01 | 2012-04-01 |  | 2013-12-01 | 2014-12-01 | 210000 | -7455 | 202545 | 202544.87 | 100% | 0.13 | 0 |  | 27300 | 0 | 26331 | 969 | 0 | Project completed in Dec 2013. Any balances will be reported to the 75th ExCom. | All obligations have been cleared by July 2015 and the project will be financially completed no later than August 2015. | 2010 |  | Investment
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (first phase) | Individual | AFR | DRC | SOL | 51 | INV | 25 | A | I | CTC-TCA | 8.9 | 8.9 | 0 |  | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2011-10-01 | 2012-08-01 | 288440 | 0 | 288440 | 288440 | 100% | 0 | 0 |  | 37497 | 0 | 37497 | 0 | 0 | Financial completion in Aug 2012. |  | 2007 | 2009-12-01 | Investment
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (second phase) | Individual | AFR | DRC | SOL | 56 | INV | 28 | A | I | CTC-TCA | 11.7 | 11.7 | 0 |  | 2008-11-01 | 2008-12-01 | 2009-11-01 |  | 2011-10-01 | 2012-08-01 | 144220 | -1253.81 | 142966.19 | 142966 | 100% | 0.19 | 0 |  | 18749 | -163 | 18586 | 0 | 0 | Financial completion in Aug 2012. Refund was reported to 68th ExCom, Nov 2012. FIN. |  | 2008 | 2011-12-01 | Investment
COM | Italy | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | AFR | GHA | PHA | 61 | TAS | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2014-12-01 | 2014-12-01 | 2012-12-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | All Italian components have progressed in a satisfactory way, completing the work of the first tranche. The international consultant on legislative aspects completed the study for Ghana's consideration. The international consultant on the introduction of a paperless licensing system also completed the work in collaboration with the national consultant. |  |  |  | INV
COM | Italy | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GHA | PHA | 67 | INV | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-07-01 | 2014-07-01 | 2014-12-01 |  | 60000 | 0 | 60000 | 58673 | 97.79% | 1327 | 0 | 0 | 7800 | 0 | 7627.49 | 172.51 | 0 | Progress has been achieved regarding activities of Tranche 2, in particular the second phase of the consultancy on legislative improvement related to new refrigerants; and to the training of customs officers, to be fully completed in 2015. | As procurement of the identifiers of customs is now launched and advanced, the training of customs officers is about to be conducted. Legislative and regulatory support work by international consultant ongoing. |  |  | INV
ONG | Italy | HCFC phase-out management plan (stage I, third tranche) |  | AFR | GHA | PHA | 72 | INV | 37 | A | I | HCFC | 1.4 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 70000 | 0 | 70000 |  | 0% | 70000 |  | 0 | 9100 | 0 | 0 | 9100 | 0 | Planning has been initiated, particialrly as regards procurement of equipment related to this Tranche (HCFC reclaim equipment), which will be conducted in 2015. Activities of Tranche 2 had to progress and near completion before launching Tranche 3. | International consultant support ongoing to finalise planning and maximise impact of technicians and customs officers training. Definition of specifications for the reclaim equipment ongoing, in consultation with NOU.
ONG | Italy | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 424 | N | I | CFC | 139.7 | 28 | 0 |  | 2008-11-01 | 2011-03-01 | 2013-11-01 | 2015-12-31 |  |  | 2000000 | 0 | 2000000 | 1940513 | 97.03% | 59487 | 0 | 17845.83 | 230000 | 0 | 223158.995 | 6841.005 | 0 | As of 31 December 2014, all project activities are completed except a few administrative and verification procedural issues relating to CFC stocks (if any). MLFS had an independent verification mission that was conducted in February 2014 and all activities were confirmed to have been completed including satisfactory technology transfer. The enterprises are producing CFC free alternatives to CFC MDIs. Any balances will be returned to the Fund. | UNDP is working with the Governemnt for ensuring that the remaining activities are completed by end of the year 2015. CFC free MDIs are currently being produced in India by the beneficiaries.
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Flexo Foam P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 307 | A | I | CFC | 19.4 | 19.4 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 185241 | 0 | 185241 | 185241 | 100% | 0 | 0 |  | 24081 | 0 | 24081 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sutlej Coach Products P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 318 | A | I | CFC | 18 | 18 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 187400 | 0 | 187400 | 187400 | 100% | 0 | 0 |  | 24362 | 0 | 24362 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in June 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Malvika Polymers | Individual | ASP | IND | FOA | 34 | INV | 319 | A | I | CFC | 20 | 20 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 196610 | -295 | 196315 | 196315 | 100% | 0 | 0 |  | 25559 | -38 | 25521 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Oto Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 336 | A | I | CFC | 12.7 | 12.7 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 139716 | -381 | 139335 | 139335 | 100% | 0 | 0 |  | 18163 | -47 | 18116 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 137 | A | I | MBR | 70 | 70 | 0 |  | 2008-04-01 | 2009-07-01 | 2014-03-01 |  | 2012-11-01 | 2012-11-01 | 1000000 | -6004.48 | 993995.52 | 993996 | 100% | -0.48 | 0 |  | 120000 | -720.54 | 119279 | 0.46 | 0 | Project completed in Nov 2012. Financial completion in Nov 2012. |  | 2008 |  | Investment
ONG | Italy | HCFC phase-out management plan (stage II, first tranche) (reclamation of HCFC refrigerants) |  | LAC | MEX | PHA | 73 | INV | 171 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 458191 | 0 | 458191 |  | 0% | 458191 |  | 30000 | 59565 | 0 |  | 59565 |  | The project was approved at the 73rd ExCom Meeting in November 2014. UNIDO was selected as executing agency, Trust Fund Agreement was signed and funds were transferred to UNIDO by end 2014 | A study tour to Italy was organized during end April and early May for operators of reclaim center to gain experience on the effective operation of such centers in Italy. Until the end of the year, TOR will be prepared, agreed upon and bidding will start. There are no delays in implementation.
COM | Italy | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 62 | A | I | MBR | 15 | 15 | 0 |  | 2008-11-01 | 2009-07-01 | 2012-11-01 |  | 2014-12-01 |  | 310000 | 0 | 310000 | 306267.03 | 98.8% | 3732.97 | 3552.81 | 3500 | 40300 | 0 | 39815 | 485 | 462 | Project completed in Dec 2014 and PCR submitted following ExCom decision. Remaining balanced are being cleared. | Project will be financially completed upon clearing obligations. | 2008 |  | Investment
FIN | Italy | Phase out of methyl bromide in horticulture | Individual | EUR | ROM | FUM | 34 | INV | 19 | A | I | MBR | 93.9 | 93.9 | 0 |  | 2001-07-01 | 2002-02-01 | 2005-08-01 |  | 2006-12-01 | 2007-08-01 | 630517 | -996 | 629521 | 629521 | 100% | 0 | 0 |  | 79357 | -109.69 | 79247 | 0.31 | 0 | FIN |  | 2001 |  | Investment
FIN | Italy | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | INV | 24 | A | I |  | 0 | 0 | 0 |  | 2007-07-01 | 2008-06-01 | 2008-07-01 |  | 2012-12-01 | 2013-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 | Project financially completed in Dec 2013. |  | 2007 |  | Investment
FIN | Italy | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | INV | 28 | A | I | CFC | 23.4 | 23.4 | 0 |  | 2009-04-01 | 2008-06-01 | 2010-03-01 |  | 2012-12-01 | 2014-12-01 | 135000 | -4594 | 130406 | 130406 | 100% | 0 | 0 |  | 17550 | 0 | 16953 | 597 | 0 | Balance will be reported to the 75th ExCom. |  | 2009 |  | Investment
ONG | Italy | Technical assistance for the final phase-out of methyl bromide in the palm dates sector |  | AFR | TUN | FUM | 73 | TAS | 62 | A | I |  | 2.2 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2016-12-01 |  |  | 132743 | 0 | 132743 |  | 0% | 132743 |  | 50000 | 17257 | 0 |  | 17257 |  | PAD initiated and project is progressing as scheduled. | ToR for the purchase of equipment was initiated and bidding exercise initiated. Equipment planned to be delivered in the early fall 15.
FIN | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | I | CFC | 94.9 | 94.9 | 0 |  | 2001-07-01 | 2002-09-01 | 2003-10-01 |  | 2007-04-01 | 2008-12-01 | 1683135 | -91120 | 1592015 | 1592015 | 100% | 0 | 0 |  | 180348 | -10023.45 | 170325 | -0.45 | 0 | FIN |  | 2001 |  | Investment
FIN | Italy | Terminal CTC phase-out project | Individual | EUR | YUG | SOL | 56 | INV | 33 | A | I | CTC | 2.6 | 2.6 | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2010-06-01 | 2011-12-01 | 49324 | -338 | 48986 | 48986 | 100% | 0 | 0 |  | 6412 | -43.82 | 6368 | 0.18 | 0 | FIN |  | 2008 |  | Investment
ONG | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 35 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2007-06-01 | 2009-09-01 | 2015-12-01 |  |  | 700000 | 0 | 700000 | 258981.74 | 37% | 441018.26 | 5714.29 | 200000 | 91000 | 0 | 33667.6262 | 57332.3738 | 742.8577 | The delay of project completion was caused by the fact that the extension of the two financial agreements between AdF/FFEM and UNIDO has been administratively completed only at the end of February 2014 and the second tranches under both agreements were transferred to UNIDO account only in March 2014. Currently the relevant documents have been collected from the beneficiaries in Senegal and Nigeria. A field mission to verify the CFC chillers in Haj Abdalla Spinning Factory at the end of March 2014. The mission found three old York CFC chillers and verified technical information required for assistance from the project. Based on this new information, the work plan for Sudan has been adjusted to include this Haj Abdalla factory as the beneficiary. Milestones achieved: Milestone 1: Grant agreement with the Alkem Industries in Nigeria signed and funds disbursed (from AdF funds)/ Yes Milestone 2: Grant agreement with the King Fahd Palace Hotel in Senegal signed and funds disbursed (from AdF funds)/ Yes Milestone 3: Grant agreements with five beneficiaries in Egypt signed and funds disbursed (from AdF-Japan funds)/Yes Milestone 4: Mission of UNIDO International Technical Expert to the Hajabdallah factory in Sudan conducted in November 2014/Yes |  | 2006 |  | investment
ONG | Japan | Project preparation for a demonstration project on ODS disposal | Individual | ASP | ASP | DES | 54 | PRP | 53 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2009-04-01 | 2009-03-01 | 2014-05-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | A project document was once submitted but agreement to forward it to the ExCom for consideration was not reached with the Secretariat. Currently, the project proposal is still in the process of revision in view of the latest developments of discussion at the ExCom in accordance with the ExCom Decision 69/5 (i). | A project document was resubmitted but agreement to forward it to the ExCom72 for consideration was not reached with the Secretariat. According to the decision at the ExCom72, this project proposal will not be submitted again. | 2008
FIN | Japan | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 33 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-02-01 | 2002-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Regional workshop on monitoring and control of ODS consumption for the South Asia region | Individual | ASP | ASP | SEV | 29 | TRA | 34 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-07-01 | 2001-06-01 |  | 2001-08-01 | 2002-06-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region | Individual | ASP | ASP | SEV | 34 | TAS | 41 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 148500 | 0 | 148500 | 148500 | 100% | 0 | 0 | 0 | 19305 | 0 | 19305 | 0 | 0 | Project completed in May 2003. Balance of 25,000 USD transferred to Phase II for partly covering activities in Mongolia |  | 2001 |  | Non-Investment
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | Individual | ASP | ASP | SEV | 38 | TAS | 49 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-06-01 | 2003-11-01 |  | 2004-03-01 | 2005-11-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 | 0 | 16250 | 0 | 16250 | 0 | 0 | Mongolia: Public awareness and IEC activities; Task Force Meeting China/Mongolia August 2003 / Iran: 15-02-04 National Consultation Meeting. Some funds were also used for building urgent capacity in the two new Parties Afghanistan and Bhutan as part of UN |  | 2002 |  | Non-Investment
ONG | Japan | Demonstration project to validate the use of super-critical CO2 in the manufacture of sprayed polyurethane rigid foam | Individual | LAC | COL | FOA | 60 | DEM | 75 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-04-01 |  | 2010-12-01 | 2014-01-01 |  |  | 441100 | 0 | 441100 | 304572 | 69.05% | 136528 | 54975 | 0 | 57343 | 0 | 0 | 57343 | 0 | Memorandum of agreement signed with the local counterpart. Trial protocol was established with participation of all parts involved. Equipment and chemicals were bought and delivered to Colombia. Equipment was installed and trials were conducted in 2 different locations with diverse conditions (high and low altitude, high and low temperature and humidity). | Evaluation of foam physical properties is underway. Technical seminar to show the results will be done during the semi-annual meeting of the Latin American Ozone network to be held in June 2013. | 2010
ONG | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2016-06-01 |  |  | 900000 | 0 | 900000 | 48846 | 5.427% | 851154 | 638365.5 | 300000 | 109000 | 0 | 5915.7933 | 103084.2067 | 77313.155 | In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EBPs, it was decided that part of the funding will be allocated to the EBPs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. In April 2014, FECO organized a meeting with relevant provincial EBPs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. | In April 2015, an additional contract has been signed between a local EPB and FECO. In July 2015, a follow-up meeting was organized between FECO and UNIDO. | 2013 |  | Investment
COM | Japan | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 516 | A | I |  | 0 |  | 0 |  | 2011-07-01 | 2012-11-01 | 2013-07-01 |  | 2013-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 |  | 10400 |  | The launching meeting was held in Shanghai in December 2011, not only for the servicing sector but also for all the sectors.
ONG | Japan | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 68 | INV | 527 | A | I |  | 0 |  | 0 |  | 2012-12-01 | 2013-11-01 | 2013-12-01 | 2014-12-01 |  |  | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 |  | 10400 |  | Refer to multi-year sheet.
ONG | Japan | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 72 | INV | 539 | A | I |  | 0 |  | 0 |  | 2014-05-01 |  | 2015-05-01 |  |  |  | 80000 | 0 | 80000 |  | 0% | 80000 |  |  | 10400 | 0 |  | 10400
ONG | Japan | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) |  | ASP | CPR | PHA | 73 | PRP | 556 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2015-12-01 |  |  |  | 25500 | 0 | 25500 |  | 0% | 25500 |  |  | 3315 | 0 |  | 3315
FIN | Japan | Phasing out ODS in the production of compressors at Changshu Refrigerating Equipment Works | Individual | ASP | CPR | REF | 28 | INV | 302 | A | I | CFC | 75 | 75 | 0 |  | 1999-07-01 | 2001-11-01 | 2002-12-01 |  | 2004-10-01 | 2005-12-01 | 2250000 | -3142 | 2246858 | 2246858 | 100% | 0 | 0 | 0 | 257500 | -9474 | 248026 | 0 | 0 | The project was succesfully completed in October 2004. |  | 1999
FIN | Japan | Develop a strategy for the refrigeration servicing sector | Individual | ASP | CPR | REF | 31 | TAS | 359 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-07-01 | 2001-12-01 |  | 2003-12-01 | 2005-06-01 | 350000 | -1376 | 348624 | 348624 | 100% | 0 | 0 | 0 | 45500 | -179 | 45321 | 0 | 0 | Completed the data survey for the four sub-sectors and developed the first draft strategy. The national workshop was organized in July 2002 to review the draft. The second draft is being prepared as per comments received from the workshop and other source |  | 2000
FIN | Japan | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 420 | A | I | CFC-12 | 0 |  | 0 |  | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2005-12-01 | 2013-12-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 130000 | 0 | 130000 | 0 | 0 | Financial completion in Dec 2013. |  | 2004 |  | investment
FIN | Japan | Refrigeration servicing sector CFC phase-out plan (second tranche) | Multi-Year | ASP | CPR | REF | 47 | INV | 438 | A | I | CFC-12 | 511 | 511 | 0 |  | 2005-11-01 | 2006-11-01 | 2006-12-01 |  | 2012-12-01 | 2014-12-01 | 3000000 | -1580 | 2998420 | 2998420 | 100% | 0 | 0 | 0 | 390000 | -205 | 389795 | 0 | 0 | Financial completion in Dec 2014. Refund was reported to 74th ExCom, May 2015. FIN. |  | 2005 |  | investment
FIN | Japan | Project preparation assistance for enterprises in the city of Shenzhen for the elimination of CFC-113 and TCA in the production lines of LC display and TV picture tube | Individual | ASP | CPR | SOL | 29 | PRP | 307 | A | I | CFC-113andCTA | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2003-07-01 | 50000 | -30916 | 19084 | 19084 | 100% | 0 |  | 0 | 6500 | -4019 | 2481 | 0 | 0 | Completed. Project proposal prepared but activities incorporated into China Solvent Sector Plan |  | 1999
ONG | Japan | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. |  | ASP | CPR | SOL | 64 | DEM | 506 | A | I |  | 1.1 |  | 0 |  | 2011-07-01 |  | 2012-09-01 | 2013-12-01 |  |  | 205616 | 0 | 205616 | 0 | 0% | 205616 | 205616 | 205616 | 26730 | 0 |  | 26730 | 26730 | Project activities were completed in 2013 and the demonstration project outputs were shared with delegates during technology conference in June 2013. Detailed report on this project would be provided to the 73rd Excom. | None. |  |  | Investment
FIN | Japan | Workshop on concessional lending | Individual | GLO | GLO | SEV | 35 | TRA | 233 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2003-03-01 | 2006-07-01 | 75000 | -17294 | 57706 | 57706 | 100% | 0 | 0 | 0 | 9750 | -2248 | 7502 | 0 | 0 | Project financially completed in July 2006. |  | 2001
FIN | Japan | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 254 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2004-11-01 | 2004-11-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | PCR is expected to be submitted by Sweden Government in early autumn 2007. |  | 2003
FIN | Japan | Training on alternative technologies to HCFCs | Individual | GLO | GLO | SEV | 59 | TRA | 297 | A | I |  | 0 |  | 0 |  | 2009-11-01 | 2010-03-01 | 2010-05-01 |  | 2011-03-01 | 2013-12-01 | 141750 | -335 | 141415 | 141415 | 100% | 0 | 0 | 0 | 18428 | -44 | 18384 | 0 | 0 | Financial completion in Dec 2013. Refund was reported to 71st ExCom, Dec 2013. FIN. |  | 2009 |  | Non-Investment
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Aneka Citra Refrigeratama Co. | Individual | ASP | IDS | FOA | 37 | INV | 145 | A | I | CFC-11 | 18.2 | 18.2 | 0 |  | 2002-07-01 | 2004-11-01 | 2004-09-01 |  | 2005-12-01 | 2006-03-01 | 142506 | -377 | 142129 | 142129 | 100% | 0 | 0 | 0 | 18526 | -49 | 18477 | 0 | 0 | Project completed. |  | 2002 |  | investment
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Bina Teknik Co. | Individual | ASP | IDS | FOA | 37 | INV | 146 | A | I | CFC-11 | 22.8 |  | 0 |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2006-03-01 | 2006-03-01 | 117889 | -541 | 117348 | 117348 | 100% | 0 | 0 | 0 | 15326 | -71 | 15255 | 0 | 0 | Project completed in March 2006. |  | 2002 |  | investment
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 376 | N | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2014-12-01 |  |  | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 280000 | 0 | 280000 | 0 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Estimated date of completion is December 2013. | None. |  | 2006-11-01
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 389 | N | I | CTC | 0 |  | 0 |  | 2005-04-01 | 2004-01-01 | 2008-04-01 | 2014-12-01 |  |  | 2500000 | 0 | 2500000 | 881149 | 35.25% | 1618851 | 0 | 1618851 | 280000 | 0 | 98000 | 182000 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Estimated date of completion is December 2013. | None.
FIN | Japan | Preparation for HCFC phase-out investment activities (XPS foam manufacturing sector) |  | ASP | MON | FOA | 60 | PRP | 16 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0
COM | Japan | Preparation of a terminal phase-out management plan | Individual | ASP | MON | PHA | 45 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2005-10-01 |  | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 4407 | 0 | 4407 | 0 | 0
COM | Japan | Terminal phase-out management plan: first tranche | Multi-Year | ASP | MON | PHA | 47 | INV | 10 | N | I | CFC | 1.8 | 1.8 | 0 |  | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2010-09-01 |  | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0
COM | Japan | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MON | PHA | 53 | INV | 12 | A | I | CFC | 1.5 | 1.5 | 0 |  | 2007-11-01 | 2009-11-01 | 2009-11-01 |  | 2010-12-01 |  | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0
ONG | Japan | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | INV | 18 | A | I |  | 0.5 |  | 0 |  | 2011-04-01 | 2012-08-01 | 2013-03-01 | 2015-12-01 |  |  | 130000 | 0 | 130000 | 100000 | 76.92% | 30000 | 0 | 0 | 16900 | 0 | 0 | 16900 | 16900 | Refer to multi-year sheet.
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Eastern Wrought Iron Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 73 | A | I | CFC | 27.1 | 27.1 | 0 |  | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2004-11-01 | 2006-05-01 | 109345 | -3207 | 106138 | 106138 | 100% | 0 | 0 | 0 | 14215 | -417 | 13798 | 0 | 0 | Operationally completed November 2004. COC issued. Final revision issued but unspent balance and corresponding support cost still to be returned in 2007. |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Mac-Vico (Nig.) Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 74 | A | I | CFC | 28.4 | 28.4 | 0 |  | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-07-01 | 2003-10-01 | 105209 | 0 | 105209 | 105209 | 100% | 0 | 0 | 0 | 13677 | 0 | 13677 | 0 | 0 | Operationally completed July 2003, financially completed October 2003 |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Martchem Industries Limited (at 2 plants) by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 75 | A | I | CFC | 38.4 | 38.4 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2003-03-01 | 2003-10-01 | 175121 | 0 | 175121 | 175121 | 100% | 0 | 0 | 0 | 22766 | 0 | 22766 | 0 | 0 | Operationally and financially completed 2003 |  | 2000 |  | investment
FIN | Japan | Preparation for a demonstration project to validate the trans-critical CO2 refrigeration technology for application to ice-block makers at Austin Laz | Individual | AFR | NIR | REF | 61 | PRP | 127 | A | I | HCFC-22 | 0 |  | 0 |  | 2010-07-01 | 2010-11-01 | 2011-07-01 |  | 2012-07-01 | 2013-12-01 | 30000 | -2648 | 27352 | 27352 | 100% | 0 | 0 | 0 | 3900 | -344 | 3556 | 0 | 0 | Financial completion in Dec 2013. Refund was reported to 71st ExCom, Dec 2013. FIN. |  | 2010
COM | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Individual | AFR | NIR | SEV | 38 | TAS | 104 | A | I | CFC | 5.6 |  | 0 |  | 2002-11-01 | 2004-12-01 | 2003-11-01 |  | 2008-10-01 |  | 68000 | -60900 | 7100 | 7100 | 100% | 0 | 25000 | 60900 | 8840 | -7917 | 923 | 0 | 3250 | The remaining fund will be used for mission of the NOU and relevant national expert to Japan to review the program. |  | 2002
ONG | Japan | Sector plan to phase out HCFC-141b in the foam sector | Individual | ASP | PHI | FOA | 62 | INV | 91 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-12-01 | 2011-06-01 | 2012-12-01 | 2015-12-01 |  |  | 317350 | 0 | 317350 | 123600.72 | 38.95% | 193749.28 | 24580.62 | 100000 | 41256 | 0 | 16068.0936 | 25187.9064 | 3195.4806 | - 10 companies with fixed foaming equipment received assistance to convert their technologies. Installation was finalized at 8 beneficiaries (MLF component). - On spray foam sector, last tests on spray foam applications took place (Japanese component) and material for the dissemination of project results was drafted. UNIDO discussed with beneficiaries and the NOU to finalize the scope of supply for those 8 eligible beneficiaries. | - 9 companies with fixed foaming equipment successfully completed the conversion of their manufacturing technologies. UNIDO completed the certification of destruction of baseline equipment in July 2015. The equipment delivered to Blutherm was confiscated and sold back to technology provider. The money recovered will be transferred back to the MLF at project closure (MLF component). - On spray foam sector (Japanese component), UNIDO started procuring agreed items to finalize the assistance to eligible 8 eligible beneficiaries. A technical brochure resulted from the tests in the spray foam activities was launched. | 2010
ONG | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Individual | ASP | SAU | FOA | 62 | INV | 12 | A | I | HCFC-22,HCFC-142b | 5.2 |  | 0 |  | 2010-12-01 |  | 2012-12-01 | 2015-12-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 110000 | 100000 | 14300 | 0 | 0 | 14300 | 14300 | The Purchase Order for the equipment has been issued in January 2014 and first tranche of funds (50%) disbursed in February 2014. The equipment has been delivered to the project site in January 2015. The company had to conduct an engineering study for the erection of the new production facilities which was completed in October. The erection of the new facility was completed in December 2014. | Installation, start-up and commissioning was completed in March 2015 and confirmed by the Certificate of Acceptance. | 2010
ONG | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Individual | ASP | SAU | FOA | 62 | INV | 14 | A | I | HCFC-22,HCFC-142b | 1.9 |  | 0 |  | 2010-12-01 |  | 2012-12-01 | 2016-06-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 92342.38 | 100000 | 14300 | 0 | 0 | 14300 | 12004.5094 | After breakdown in communication with the company, finally the company agreed to go ahead with the procurement of the equipment. The Invitation to Bidding was published in April 2014. Offers from two qualified suppliers were received in June 2014. The technical and financial evaluation was conducted in July/August 2014 and the best technically acceptable offer was selected in September 2014. Negotiations about the contract with UNIDO Procurement Service and the supplier about details in the contract (acceptance of payment schedule,TUV certification of the equipment, change of the supplier company) extended into 2015. | The contract to the selected supplier was issued in February 2015. Technical meeting at Al-Watania was organized in June 2015. | 2010
COM | Japan | National compliance action plan: incentive programme for commercial and industrial refrigeration end-users | Individual | ASP | SRL | PHA | 43 | TAS | 26 | A | I | CFC | 5 |  | 0 |  | 2004-07-01 | 2008-12-01 | 2005-12-01 |  | 2011-12-01 |  | 144000 | 0 | 144000 | 144000 | 100% | 0 | 0 | 0 | 18720 | 0 | 18720 | 0 | 0 | PCR to be completed in 2014. | PCR will be submitted for ExCom73. | 2004 | 2007-12-01 | investment
COM | Japan | National compliance action plan: MAC recovery/recycling and retrofit | Individual | ASP | SRL | PHA | 43 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2006-12-01 | 2005-12-01 |  | 2010-09-01 |  | 123000 | 0 | 123000 | 123000 | 100% | 0 | 0 | 0 | 15990 | 0 | 15990 | 0 |  | PCR completed in 2013 and submitted. | PCR will be submitted for ExCom73. | 2004 |  | investment
COM | Japan | National compliance action plan: recovery and recycling programme | Individual | ASP | SRL | PHA | 43 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2008-10-01 | 2006-12-01 |  | 2010-12-01 |  | 290400 | 0 | 290400 | 290400 | 100% | 0 | 0 | 0 | 37752 | 0 | 37752 | 0 |  | PCR completed in 2013 and submitted. | PCR will be submitted for ExCom73. | 2004 |  | investment
COM | Japan | National compliance action plan: monitoring the activities proposed in the plan | Individual | ASP | SRL | PHA | 43 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2009-12-01 |  | 2011-12-01 |  | 108000 | 0 | 108000 | 108000 | 100% | 0 | 0 | 0 | 14040 | 0 | 14040 | 0 | 0 | PCR completed in 2013 and submitted. | PCR will be submitted for ExCom73. | 2004 |  | investment
ONG | Japan | HCFC phase-out management plan (stage I, first tranche) (technical assistance) |  | ASP | THA | PHA | 68 | TAS | 158 | A | I | HCFC-22 | 4.2 |  | 0 |  | 2012-12-01 |  | 2013-11-01 | 2017-12-01 |  |  | 302965 | 0 | 302965 | 0 | 0% | 302965 |  | 68000 | 39385 | 0 | 0 | 39385 |  |  | The main reason for the delay was politic situation in the country. Grant Agreement has been ready for counter signing by Government of Thai. Kickoff will be held in September 2014. Total funding including support costs have been transferred to the World Bank. Disbursement of this fund will be channeled through the same legal agreement between the Bank and Thailand.
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
COM | Portugal | Communication and cooperation support to Portuguese speaking countries (Angola, Cape Verde, East Timor, Guinea Bissau, Mozambique and Sao Tome and Principe) | Individual | GLO | GLO | SEV | 47 | TAS | 269 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2011-07-01 |  | 90000 | 0 | 90000 | 47743 | 53.05% | 42257 | 31324 | 10933 | 11700 | 0 | 0 | 11700 | 0 | The education pack for primary schools were distributed to all Portuguese-speaking African countries in March 2011, The OzonAction Education pack for Secondary Schools will be translated and it will be distributed electronically in June 2011.
FIN | Singapore | Training workshop on CFC-113 and methyl chloroform substitutes and alternative technologies in ASEAN countries |  | ASP | ASP | REF | 13 | TRA | 15 | A | D |  | 0 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | Singapore | Regional methyl chloroform elimination programme for ASEAN countries |  | ASP | ASP | SOL | 11 | TAS | 12 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 |  | 1995-03-01 |  | 31976 | 0 | 31976 | 31976 | 100% | 0 | [5 empty] | 0 |  |  |  | 93
FIN | Slovak Republic | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 03 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 14622 | 0 | 14622 | 14622 | 100% | 0 |  |  | 1901 | 0 | 1901 | 0
FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | AFR | AFR | SEV | 11 | TRA | 07 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 | 1994-09-01 | 1994-09-01 | 1994-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | Spain | Total phase-out of MB used in tobacco, flowers, ornamental plants, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 272 | A | I | MBR | 65.4 | 65.4 | 0 |  | 2005-07-01 | 2006-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-06-01 | 580390 | -212 | 580178 | 580178 | 100% | 0 | 0 |  | 75451 | -28 | 75423 | 0 | 0 | Financial completion in Jun 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | Spain | Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras | Individual | LAC | LAC | FUM | 47 | TAS | 37 | A | I | MBR | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-07-01 | 2008-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 |  | 10400
ONG | Spain | Technical assistance to introduce chemical alternatives in countries which have rescheduled methyl bromide phase out plan (Argentina and Uruguay) | Individual | LAC | LAC | FUM | 54 | TAS | 40 | A | I | MBR | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 | 2015-03-01 |  |  | 147400 | 0 | 147400 | 62336 | 42.29% | 85064 | 72606 | 50000 | 19162 | 0 | 8104 | 11058 | 9439 | Project completed in March 2015 |  |  |  | Investment
ONG | Spain | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others (second tranche) | Multi-Year | AFR | LIB | FUM | 56 | INV | 30 | A | I | MBR | 40 |  | 0 |  | 2008-11-01 | 2010-05-01 | 2010-11-01 | 2014-12-01 |  |  | 500000 | 0 | 500000 | 220112 | 44.02% | 279888 | 164344 | 20000 | 65000 | 0 | 28615 | 36385 | 21365 | Project about to be completed, however, the installation of the last equipment could not be done until now. It will be done as soon as the security situation allow such installation |  |  |  | Investment
FIN | Spain | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 118 | A | I | MBR | 107.2 | 107.2 | 0 |  | 2004-04-01 | 2005-10-01 | 2006-10-01 |  | 2008-12-01 | 2010-03-01 | 707965 | -24181 | 683784 | 683784 | 100% | 0 | 0 | 0 | 87876 | -2659.76 | 85216 | 0.24 | 0 | Financial completion in Mar 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | Spain | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 151 | A | I | MBR | 50 | 50 | 0 |  | 2010-04-01 | 2012-09-01 | 2012-04-01 |  | 2012-11-01 | 2012-11-01 | 800000 | 0 | 800000 | 799997 | 100% | 3 |  |  | 93000 | 0 | 93000 | 0 |  | Project completed in Nov 2012. Financial completion in Nov 2012. |  |  |  | Investment
ONG | Spain | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 161 | A | I | MBR | 80 |  | 0 |  | 2012-04-01 |  | 2013-04-01 | 2015-03-01 |  |  | 800000 | 0 | 800000 |  | 0% | 800000 |  | 50000 | 93000 | 0 |  | 93000 |  | Project activities almost completed, it remains US$ 7,000, for the organization of a final official event with the Mexican Authorities to conclude the project”. It is expected to do it sometime during the second semester 2015 |  |  |  | Investment
COM | Spain | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | PAR | FUM | 47 | TAS | 15 | A | I | MBR | 0.2 | 0.2 | 0 | 0 | 2005-11-01 | 2007-07-01 | 2007-12-01 |  | 2009-07-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 |  | 5200 |  | This Project was approved on ExCom 47th, December 2005. 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only signature of PCR is remaining and expectd by Jul 09. . 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only PCR remain for signature that is expected on July 2009. | Project is completed. All funds were exhausted. The balance of US$ 1500 is not real. Clarification of accounts between UNDP Country Office and UNEP is in progress
FIN | Sweden | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 31 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2001-02-01 | 2002-05-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Regional Workshop on Control and Monitoring of ODS Consumption for the Southeast Asia/Pacific Region (funded with equal bilateral contributions from Sweden and Japan and implemented through UNEP) was held 22-27 May 2000 and was attended by ozone and customs officers from ten countries in the region. The participating countries developed a joint set of declarations and drafted national action plans for further work in their respective country. The report from the workshop was prepared by Sweden in February 2001. The project completion report prepared in coordination with UNEP was submitted 1 May 2002. The project was financially completed 27 May 2002. |  | 1999
FIN | Sweden | Regional cooperation for monitoring and control of ODS consumption | Individual | ASP | ASP | SEV | 34 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-03-01 | 2005-04-01 |  | 2006-12-01 | 2008-05-01 | 250000 | 155818 | 405818 | 405818 | 100% | 0 | 0 | 0 | 0 | 20256 | 20256 | 0 | 0 | The final financial report was received from UNEP in May 2008. The final report reported a balance of USD 49,926. In July 2008 the MLF confirmed the return of the same amount as part of the Swedish contribution to the MLF. |  | 2002
FIN | Sweden | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-09-01 | 2004-12-01 |  | 2005-06-01 | 2005-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 3450 | 0 | 3450 | 0 | 0 | Annual report submitted and approved at the 42nd ExCom meeting. |  | 2003
FIN | Sweden | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | CRO | PHA | 42 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-12-01 | 2005-12-01 | 24700 | 0 | 24700 | 24700 | 100% | 0 |  |  | 1853 | 0 | 1853 | 0 | 0 | Annual report submitted and approved at the 46th ExCom meeting. |  | 2004
FIN | Sweden | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 27 | A | I | CFC | 13 | 13 | 0 |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-06-01 | 2006-06-01 | 21500 | 0 | 21500 | 21500 | 100% | 0 | 0 | 0 | 1613 | 0 | 1613 | 0 | 0 | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. The project was completed in June 2006. |  | 2005
FIN | Sweden | Assistance to prepare an RMP update | Individual | EUR | CRO | REF | 36 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2004-03-01 | 2004-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0 | At the 36th meeting in March 2002 Sweden received approval for assisting the Government of Croatia in updating their Refrigerant Management Plan (RMP Update). International and National consultants were contracted in June 2002. A survey of current ODS consumption and use in the servicing sector were conducted followed by a desk study and sector review. Due to ExCom decision regarding Terminal Phase-out Management Plans (TPMP) the Update was submitted in January 2003 as a TPMP, with Sweden as co-implementing agency and UNIDO as lead Implementing Agency, and approved at the 39th ExCom meeting. |  | 2002
FIN | Sweden | Assistance to prepare a terminal phase-out management plan | Individual | EUR | GEO | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | In December 2005 at the 47th Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a Terminal phase-out management plan in Georgia. The final TPMP was submitted to the 50th ExCom meeting and approved. The TPMP is implemented by UNDP as sole implementing agency. |  | 2005
FIN | Sweden | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 253 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-10-01 |  | 2006-02-01 | 2006-12-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | At the 41st meeting of the Executive Committee, the Government of Sweden in collaboration with the Government of Japan received approval for developing a Handbook related to the servicing sector. A Draft outline of the Handbook with a broader perspective in accordance with the ExCom decision was developed in March 04. Two consultants were recruited and a first full Draft was developed in Feb. 2005. The Draft was revised substantially twice before the text was sent for a review by UNEP/DTIE, Japan and the NOUs of Croatia and the Philippines in June 2005. Responses were received in Aug-Sept 2005. After taking into account the comments received, the layout and printing was organised. The printed version was received in February 2006 and the distribution to all NOUs and relevant agencies was organised by UNEP. The Handbook is available at the UNEP and SEI web pages for down load. |  | 2003
FIN | Sweden | Implementation of the RMP: development of import/export licensing system | Individual | ASP | LAO | REF | 34 | TAS | 05 | A | I |  | 1.6 |  | 0 |  | 2001-07-01 | 2002-11-01 | 2002-09-01 |  | 2005-12-01 | 2005-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Swedish contribution in Lao PDR consists of technical assistance to prepare an import/export licensing system. International and national consultants were contracted in April 2002. After an initial delay in the signing of agreement and data collection the project is completed, we are only awaiting Lao PDR’s approval of the final report. The Decree for the "Control of the Import-Export and Consumption of ODS" was signed late 2003. A regulation for how the new Decree shall be implemented has been developed and the regulation was signed by the Minister in November 2004. SEI and the IC gave a number of suggestions on drafts on the regulation during 2004. An information brochure to all importers informing them about the licensing system was finalized during 2005. |  | 2001
FIN | Sweden | National CFC phase out plan: servicing sector (first tranche) | Multi-Year | ASP | PHI | PHA | 38 | TAS | 68 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2012-04-01 | 152400 | 0 | 152400 | 152400 | 100% | 0 |  |  | 11316 | 0 | 11316 | 0 | 0 | The original plan to establish a functioning Reclamation Facility in partnership with PARII was deemed not financially-viable and economically-feasible by PARII due to low amounts of reclaimable refrigerants from the servicing sector. Hence, an alternative model to establish an ODS management plan, including the collection, transport, and storage of recovered refrigerants and unwanted ODS was proposed by the PMU and included in the 2010-2011 Biennual Plan of the NCPP approved at the 60th ExCom Meeting. Procurement and selection process for equipment which complements that already procured under the reclamation scheme, as well as for contractors for ODS collection, transport and storage was not completed until 2010. Delsa Chemicals and Multi-Products Inc (DCMI), a member of PARII, the refrigerant importer association, was the contractor selected for the collection, transport and storage of recovered refrigerants for the NCPP and has completed its work in 2011. Overall NCPP closed by the WB in Jun 2011. Reconciliation of the account indicate a total savings of US$114,046.05 for the Swedish component because disbursement for some activities under Sweden was posted under the overall NCPP under the WB instead. | Financial completion of the NCPP under the WB occurred on Apr. 12 upon return of the balance of the funds to the 66th ExCom. | 2002
FIN | Sweden | National CFC phase-out plan servicing sector: 2004 annual programme | Multi-Year | ASP | PHI | PHA | 41 | TAS | 72 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2011-11-01 | 2012-04-01 | 166134 | -114046 | 52088 | 52088 | 100% | 0 | 0 | 0 | 12952 | 0 | 12952 | 0 | 0 | See remarks above. | See remarks above. | 2003 | 2006-12-01
FIN | Sweden | National CFC phase-out plan servicing sector: 2005 annual programme | Multi-Year | ASP | PHI | PHA | 44 | TAS | 77 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2010-07-01 | 2012-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | See remarks above. | See remarks above. | 2004
FIN | Sweden | Preparation of a government strategy to reduce and eliminate the use of CFC refrigerants for servicing and installations on-site | Individual | ASP | PHI | REF | 29 | PRP | 59 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2002-08-01 | 2002-11-01 | 141400 | 0 | 141400 | 141400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Detailed discussions with the Philippine authority in charge, Department of Environment and Natural Resources (DENR), on the implementation took place May 2000. International and local consultants were contracted and in November 2000, the first meeting with the involved authorities and the private sector was conducted. The political situation in the Philippines during 2001 caused the project a delay. A RMP outline was adopted in October 2001. During 2002 the project was merged into a NCPP together with the WB. The NCPP was submitted jointly and approved in December 2002 with Sweden as co-implementing agency for TA activities related to the servicing sector. |  | 1999
FIN | Sweden | Assistance to prepare the national CFC phase-out plan (refrigeration servicing sector) | Individual | EUR | ROM | PHA | 43 | PRP | 24 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-04-01 | 2005-07-01 | 59400 | 0 | 59400 | 59400 | 100% | 0 |  |  | 7722 | 0 | 7722 | 0 | 0 | In July 2004, at the 43rd Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a national CFC phase-out plan for the servicing sector in Romania. After recruitment of consultants a mission was held in November 2004. The NCPP was prepared during the autumn 2004 and was approved at the 45th ExCom meeting in April 2005. |  | 2004
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  |  | 2010-06-01 | 119500 | -83219 | 36281 | 36281 | 100% | 0 | 0 | 0 | 15535 | -10818 | 4717 | 0 | 0 | With ExCom decision 60/3 in April 2010, the remaining components of this project was formally handed over from Sweden to UNIDO and the contract with the international consultant was terminated. This progress report therefore only includes activities up to April 2010: The project has been suffering from a long delay even though a lot of progress was made during the last two years. The training of trainers for the vocation schools have been held and they have received the equipment needed for their training. Training of the existing workforce has also been conducted although in April 2010 a number of training sessions still remained to be undertaken. Up to April 2010, the Association of Refrigeration had given interim certificates to 19 Companies and 148 technicians (from which 89 are still under evaluation). A Governmental Decision had been sent for approval at all the signatory ministries and it was said that it would be published in the Official Journal no later than September 2010. The Governmental Decision was expected to be followed by a Ministerial Order which would establish the Association of Refrigeration as the interim certification body until 2011. With regards to the reuse scheme this activity is still not finalised. A number of seminars have been held to discuss the reuse scheme which raised a lot of interest. A survey was made of all the destruction facilities in the country to see which ones are incinerating based on the criteria of the Annex VI of the Regulation 1005/2009 regarding the ozone depleting substances. GreenWEEE was found to be the biggest integrated treatment plant for electric and electronic equipment waste (WEEE) in Romania and one of the most modern in Europe. They have 3 collection centers in the country (Lasi, Timisoara, Bucuresti). GreenWEEE can collect all the WEEE categories mentioned in the legislation (including large household appliances- refrigerators, freezers). The NOU has drafted a report for recycling systems in accordance with the EU existing legislation and based on the key aspects underlined by the consultation with the companies with interests in this field. Due to the existing economical situation the market is rather small. Also, meetings have been held with the customs and an draft instructions handbook was prepared based on the EU regulations. The additional delay is due to the initial long delay and the difficulties to speed up the process as much as needed to stick to the revised time plan. Also, the Governmental Decision was delayed and until September 2010 which further delayed the implementation of some of the measures proposed therein. Sweden also estimate that it will take time to get the reclamation system fully operational, something which will cause additional delay. Even if Romania had come quite far in April 2010 by holding stakeholder workshops and discussions and survey among the destruction facilities, this is much delayed already and it will take additional time to get it fully operational. The Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2005 | 2008-12-01
FIN | Sweden | Halon management programme, halon recovery, recycling and banking | Halon banking | ASP | THA | HAL | 29 | TAS | 120 | A | I |  | 135.9 |  | 0 |  | 1999-11-01 | 2004-11-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Implementation of the halon management project completed in Sep 2010. Sweden disbursed the full project amount to the WB already in year 2000. Overall halon project financially completed Nov. 11 upon return of the savings by the WB to the 65th ExCom. |  | 1999
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 |  |  | 2010-06-01 | 148000 | -128678 | 19322 | 19322 | 100% | 0 | 0 | 0 | 19240 | -16728 | 2512 | 0 | 0 | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2004 | 2006-12-01
TRF | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 |  |  | 2006-11-01 | 134000 | -134000 | 0 | 0 |  | 0 | 0 | 0 | 17420 | -17420 | 0 | 0 | 0 | This activity was transferred to UNIDO in 2006. |  | 2005
FIN | Switzerland | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | Individual | LAC | ARG | REF | 19 | TRA | 46 | A | D |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-08-01 | 1997-10-01 |  | 1997-08-01 | 1997-10-01 | 242600 | 0 | 242600 | 242600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Balance has been compensated with separate Swiss funding |  | 1996
FIN | Switzerland | International workshop on potential for hydrocarbon-based refrigerant as replacements in existing domestic and small commercial refrigeration appliances | Individual | GLO | GLO | REF | 23 | TRA | 137 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1997-12-01 |  | 1997-09-01 | 1997-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1997
FIN | Switzerland | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-04-01 | 2003-04-01 | 70796 | 0 | 70796 | 70796 | 100% | 0 | 0 | 0 | 9204 | 0 | 9204 | 0 | 0 |  |  | 2000
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 370 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-03-01 | 2005-03-01 | 353020 | 0 | 353020 | 353020 | 100% | 0 | 0 | 0 | 45893 | 0 | 45893 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2004: Four new training cells have been established and a Training of Trainers Wokshop was held for 12 particpants. With this, 13 training cells provided in 2004 standard training programs for refrigeration service technicians. | 2004 |  | 2004
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 381 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-03-01 | 2006-03-01 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2005: In the operational year 05-06 the following number of technicians are trained: a) in Standard RSE programs: 1685 participants b) Mobile Air-Conditioning programs 130 participants c) Open Type compressor programs: 64 partic | 2005 |  | 2005
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 394 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-03-01 | 2007-03-01 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2006: In the operational year 06-07 the following number of technicians are trained: a) in Standard RSE programs: 1810 participants b) Mobile Air-Conditioning programs 238 participants c) Open Type compressor programs: 55 partic | 2006 |  | 2006
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 406 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-11-01 |  | 2008-03-01 | 2008-03-01 | 367140 | 0 | 367140 | 367140 | 100% | 0 | 0 | 0 | 47728 | 0 | 47728 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2007: In the operational year 07-08 the following number of technicians are trained: a) in Standard RSE programs: 1880 participants b) Mobile Air-Conditioning programs 275 participants c) Open Type compressor programs: 113 partic. | 2007 |  | 2007
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 418 | A | I |  | 211.1 | 0 | 0 |  | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2010-03-01 | 2010-03-01 | 81141 | 0 | 81141 | 81141 | 100% | 0 |  |  | 10548 | 0 | 10548 | 0 |  | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2008: In the operational year 08-09 the following number of technicians are trained: a) in Standard RSE programs: 1716 participants | 2008 |  | 2008
FIN | Switzerland | Implementation of the RMP: demonstration project to retrofit domestic refrigerators for the use of hydrocarbon refrigerant | RMP | AFR | SEN | REF | 33 | TAS | 14 | A | I |  | 47 | 0 | 0 | 0 | 2001-03-01 | 2003-07-01 | 2001-11-01 |  | 2004-03-01 | 2004-06-01 | 71230 | 0 | 71230 | 71230 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2001
FIN | UK | Chiller concessional lending pilot project | Individual | LAC | MEX | REF | 28 | INV | 95 | N | I | CFC | 5 | 7.8 | 0 |  | 1999-07-01 | 2001-02-22 | 2004-02-01 |  | 2004-03-01 |  | 565000 | 0 | 565000 | 565000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Phase I is completed and accomplished its objectives improving expected results: Twelve chillers were financed instead of the ten expected, with an additional two chillers financed from accumulated funds. 7.8 ODP tons were eliminated instead of 5 tons as expected. Disbursements have been made on schedule with 100% disbursement achieved in August 2002. 100% of building owners that participated in the program have made their monthly repayment on time. Energy savings were 36% higher than proposed. The project will be completed in March 2004.
FIN | UNDP | Methyl bromide data collection for Africa | Individual | AFR | AFR | FUM | 17 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 |  | 1998-04-01 | 2000-12-01 | 179850 | 0 | 179850 | 179850 | 100% | 0 | 0 | 0 | 23381 | 0 | 23380.5 | 0.5 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Non-Investment
FIN | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | AFR | AFR | FUM | 38 | TAS | 32 | A | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 |  | 2011-12-01 | 2014-02-01 | 550000 | -2112 | 547888 | 547888 | 100% | 0 | 0 | 0 | 70500 | -271 | 70229.28 | -0.28 | 0 | Financially completed in 2014. | Some invoices still pending. | 2002 |  | Non-Investment
CLO | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | AFR | AFR | HAL | 37 | TAS | 31 | A | I | Halon | 61 | 44.2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  |  | 2008-11-01 | 300000 | -81519 | 218481 | 218481 | 100% | 0 | 0 | 0 | 39000 | -10597 | 28402.53 | 0.47 | 0 | Canceled in 2008. Funds will be returned to Excom in 2011. |  | 2002 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | AFR | AFR | SEV | 36 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-11-01 | 2005-10-01 | 30000 | -146 | 29854 | 29854 | 100% | 0 | 0 | 0 | 3900 | -19 | 3881.02 | -0.019957 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ANG | PHA | 51 | PRP | 07 | A | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2010-12-01 | 2012-12-01 | 12000 | -8195 | 3805 | 3805 | 100% | 0 | 0 | 0 | 900 | -615 | 285.375 | -0.375 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | ANG | PHA | 55 | PRP | 08 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 | 2013-12-01 | 85000 | -155 | 84845 | 84845 | 100% | 0 | 0 | 0 | 6375 | -12 | 6363.375 | -0.375 | 0 | Financially completed in 2013. | Completed in 2011. Only some final payments may need to be settled in 2012, including for holding of a series of customs training workshops to strengthen control capacities at ports of entry. | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ANG | PHA | 65 | INV | 10 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 | 2015-11-01 |  |  | 86222 | 0 | 86222 | 50453 | 58.52% | 35769 | 0 | 14307.6 | 7760 | 0 | 4540.7817 | 3219.2183 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During 2014, 4 national training sessons took place in Luanda and in 3 cities in the countryside. Consultations with training centers were undertaken in order to identify specific needs of equipment to be procured Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in February 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in June 2012. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Procurement of equipment was delayed due to the time response needed by training centers to list priority equipment. A mission took place in March 2015 and an updated procurement plan was agreed to be implemented in the first half of 2015. | Since 2014, needs for tools and equipment were assessed and TOR completed. Government has approved procurement plan and UNDP is to start bidding in third quarter of 2015. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ANG | PHA | 72 | INV | 12 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 39111 | 0 | 39111 | 0 | 0% | 39111 | 0 | 15644.4 | 3520 | 0 | 0 | 3520 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During 2014, 4 national training sessons took place in Luanda and in 3 cities in the countryside. Consultations with training centers were undertaken in order to identify specific needs of equipment to be procured. Prodoc signed (actual/planned, yes/no and date):No, the original ProDoc will be amended in Jan 2015 to include the second tranche. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):0. Contract/PO/MOA agreements signed:0. First disbursement date (actual/planned):The first disbursemnet will take place in February 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Procurement of equipment was delayed due to the time response needed by training centers to list priority equipment. A mission took place in March 2015 and an updated procurement plan was agreed to be implemented in the first half of 2015. | Remaining funds from Tranches 1 and 2 were combined in order to meet the funds availability for the procurement of tools and equipment |  |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | ANG | PHA | 73 | TAS | 13 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2015-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2700 | 0 | 0 | 2700 | 0 | Newly Approved | Auditor is expected to visit Angola in the third quarter of 2015 to undertake the verification. | 2014 |  | Non-Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast | Individual | LAC | ARG | FOA | 14 | INV | 13 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-09-01 | 1995-12-01 | 1995-09-01 |  | 1999-11-01 | 2001-12-01 | 345000 | -5021 | 339979 | 339979 | 100% | 0 | 0 | 0 | 44850 | -653 | 44196.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of sandwich polyurethane panels at Cinter, S.R.L. | Individual | LAC | ARG | FOA | 15 | INV | 14 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 2001-12-01 | 2003-09-01 | 725000 | -32679 | 692321 | 692321 | 100% | 0 | 0 | 0 | 94250 | -4248 | 90001.74 | 0.26 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis | Individual | LAC | ARG | FOA | 18 | INV | 26 | A | I | CFC | 145 | 145 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2001-08-01 | 715000 | -10 | 714990 | 714990 | 100% | 0 | 0 | 0 | 92950 | -1 | 92948.7 | 0.3 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Nuvel Corp. S.A. | Individual | LAC | ARG | FOA | 18 | INV | 27 | A | I | CFC | 53 | 53 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 313500 | 0 | 313500 | 313500 | 100% | 0 | 0 | 0 | 40755 | 0 | 40755 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Mentvil S.A. | Individual | LAC | ARG | FOA | 18 | INV | 28 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1997-04-01 | 2001-12-01 | 115000 | -12796 | 102204 | 102204 | 100% | 0 | 0 | 0 | 14950 | -1663 | 13286.87 | 0.13 | 0 | Completed in 1997. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Limansky | Individual | LAC | ARG | FOA | 18 | INV | 29 | A | I | CFC | 95 | 95 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 473000 | -364 | 472636 | 472636 | 100% | 0 | 0 | 0 | 61490 | -47 | 61442.68 | 0.32 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC | Individual | LAC | ARG | FOA | 18 | INV | 30 | A | I | CFC | 64 | 64 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 341000 | -1708 | 339292 | 339292 | 100% | 0 | 0 | 0 | 44330 | -222 | 44107.96 | 0.04 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstock) at Sueño Estelar S.A. and Estelar San Luis S.A. | Individual | LAC | ARG | FOA | 18 | INV | 31 | A | I | CFC | 128.6 | 128.6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 690000 | -2837 | 687163 | 687163 | 100% | 0 | 0 | 0 | 89700 | -369 | 89331.19 | -0.19 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. | Individual | LAC | ARG | FOA | 18 | INV | 33 | A | I | CFC | 36.5 | 36.5 | 0 | 0 | 1995-11-01 | 1997-07-01 | 1996-11-01 |  | 2001-12-01 | 2003-04-01 | 285000 | -631 | 284369 | 284369 | 100% | 0 | 0 | 0 | 37050 | -82 | 36967.97 | 0.03 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1998-01-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. | Individual | LAC | ARG | FOA | 20 | INV | 48 | A | I | CFC | 92.5 | 92.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2002-11-01 | 2004-01-01 | 561000 | 0 | 561000 | 561000 | 100% | 0 | 0 | 0 | 72930 | 0 | 72930 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 1998-01-01 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 21 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Eliminations of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Rheem S.A. | Individual | LAC | ARG | FOA | 22 | INV | 55 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-12-01 | 2001-12-01 | 76650 | 0 | 76650 | 76650 | 100% | 0 | 0 | 0 | 9965 | 0 | 9964.5 | 0.5 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. | Individual | LAC | ARG | FOA | 22 | INV | 56 | A | I | CFC | 19 | 19 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-05-01 | 2004-01-01 | 118000 | -34528 | 83472 | 83472 | 100% | 0 | 0 | 0 | 15340 | -4489 | 10851 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Calofrig Asilaciones Jacobi S.A.I.C. | Individual | LAC | ARG | FOA | 22 | INV | 57 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1999-06-01 |  | 2001-12-01 | 2003-04-01 | 563750 | 0 | 563750 | 563750 | 100% | 0 | 0 | 0 | 73288 | 0 | 73287.5 | 0.5 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano | Individual | LAC | ARG | FOA | 23 | INV | 61 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 456500 | 0 | 456500 | 456500 | 100% | 0 | 0 | 0 | 59345 | 0 | 59345 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Conversion to non CFC technology in the manufacture of integral skin and flexible moulded foam at Strapur | Individual | LAC | ARG | FOA | 23 | INV | 62 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2001-08-01 | 212500 | -162380 | 50120 | 50120 | 100% | 0 | 0 | 0 | 27625 | -21109 | 6515.6 | 0.4 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. | Individual | LAC | ARG | FOA | 23 | INV | 63 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-03-01 | 2001-12-01 | 132000 | -9838 | 122162 | 122162 | 100% | 0 | 0 | 0 | 17160 | -1279 | 15881 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of rigid foam blocks for insulated trailers at Fruehauf | Individual | LAC | ARG | FOA | 23 | INV | 65 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2003-11-01 | 175000 | -40597 | 134403 | 134403 | 100% | 0 | 0 | 0 | 22750 | -5278 | 17472.39 | -0.39 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 24 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | Individual | LAC | ARG | FOA | 25 | INV | 76 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 1998-07-01 | 2000-08-01 | 2000-08-01 |  | 2002-11-01 | 2004-01-01 | 122100 | 0 | 122100 | 122100 | 100% | 0 | 0 | 0 | 15873 | 0 | 15873 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco | Individual | LAC | ARG | FOA | 26 | INV | 78 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-08-01 | 2001-12-01 | 210150 | -3022 | 207128 | 207128 | 100% | 0 | 0 | 0 | 27320 | -393 | 26926.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of two projects in the integral skin foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of an umbrella project and three other projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) | Individual | LAC | ARG | FOA | 29 | INV | 94 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 127392 | 0 | 127392 | 127392 | 100% | 0 | 0 | 0 | 16561 | 0 | 16560.96 | 0.04 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria | Individual | LAC | ARG | FOA | 29 | INV | 95 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2000-12-01 | 2003-04-01 | 124025 | -221 | 123804 | 123804 | 100% | 0 | 0 | 0 | 16123 | -29 | 16094.52 | -0.52 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | Individual | LAC | ARG | FOA | 29 | INV | 96 | A | I | CFC | 43.9 | 43.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-11-01 | 2004-01-01 | 234409 | 0 | 234409 | 234409 | 100% | 0 | 0 | 0 | 30473 | 0 | 30473.17 | -0.17 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax | Individual | LAC | ARG | FOA | 30 | INV | 106 | A | I | CFC | 50 | 50 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2003-04-01 |  | 2002-11-01 | 2004-01-01 | 252000 | 0 | 252000 | 252000 | 100% | 0 | 0 | 0 | 32760 | 0 | 32760 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | Individual | LAC | ARG | FOA | 31 | INV | 111 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2003-12-01 | 2005-09-01 | 295300 | -97042 | 198258 | 198258 | 100% | 0 | 0 | 0 | 38389 | -12615 | 25774 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | Individual | LAC | ARG | FOA | 32 | INV | 113 | A | I | CFC | 49.6 | 49.6 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 320332 | -90 | 320242 | 320242 | 100% | 0 | 0 | 0 | 41643 | -12 | 41631.46 | -0.46 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Paissan, Forever, Termica) | Individual | LAC | ARG | FOA | 34 | INV | 122 | A | I | CFC | 54.9 | 54.9 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2004-08-01 |  | 2005-01-01 | 2007-01-01 | 352896 | -12969 | 339927 | 339927 | 100% | 0 | 0 | 0 | 45876 | -1686 | 44190.5276 | -0.5276 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | Individual | LAC | ARG | FOA | 34 | INV | 123 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-12-01 | 2005-09-01 | 147987 | -53810 | 94177 | 94177 | 100% | 0 | 0 | 0 | 19238 | -6995 | 12243.31 | -0.31 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | ARG | FOA | 36 | PRP | 126 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | ARG | FOA | 38 | INV | 132 | A | I | CFC | 192.3 | 192.3 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2007-12-01 | 2013-01-01 | 1324843 | -17620 | 1307223 | 1307223 | 100% | 0 | 0 | 0 | 155733 | -2071 | 153661.5036 | 0.49645 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for methyl bromide (tobacco) demonstration project | Individual | LAC | ARG | FUM | 24 | PRP | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | Individual | LAC | ARG | FUM | 26 | DEM | 79 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-04-01 | 2003-11-01 | 273350 | -1493 | 271857 | 271857 | 100% | 0 | 0 | 0 | 35536 | -194 | 35341.41 | 0.59 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in soil fumigation (tobacco) | Individual | LAC | ARG | FUM | 33 | PRP | 120 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | Multi-Year | LAC | ARG | FUM | 36 | INV | 129 | N | I | MeBr | 29 | 29 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2002-12-01 |  | 2004-12-01 | 2012-07-01 | 1720000 | 0 | 1720000 | 1720000 | 100% | 0 | 0 | 0 | 199200 | 0 | 199200 | 0 | 0 | Financially completed in 2012. |  | 2001 | 2004-03-01 | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | Multi-Year | LAC | ARG | FUM | 40 | INV | 136 | N | I | MeBr | 21 | 21 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-03-01 |  | 2005-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2003 | 2005-07-01 | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fourth tranche) | Multi-Year | LAC | ARG | FUM | 43 | INV | 139 | N | I | MeBr | 16 | 16 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-07-01 |  | 2006-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fifth tranche) | Multi-Year | LAC | ARG | FUM | 46 | INV | 146 | N | I | MeBr | 33.3 | 33.3 | 0 | 0 | 2005-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (sixth tranche) | Multi-Year | LAC | ARG | FUM | 48 | INV | 149 | N | I | MeBr | 56.7 | 56.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2009-06-01 | 2012-07-01 | 467000 | -73 | 466927 | 466927 | 100% | 0 | 0 | 0 | 35025 | -6 | 35019.5249 | -0.52495 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | Technical assistance to prepare a national halon programme | Individual | LAC | ARG | HAL | 13 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-01-01 |  | 1996-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Non-Investment
TRF | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 157 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 |  |  | 2011-11-01 | 95750 | -43657 | 52093 | 52093 | 100% | 0 | 0 | 0 | 7181 | -3274 | 3907.25 | -0.25 | 0 | Project PRP transferred to UNIDO and remaining funds returned to MLF. | Project PRP transferred to UNIDO and remaining funds returned to MLF. | 2008 |  | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores at Market Costan S.A. | Individual | LAC | ARG | REF | 18 | INV | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1997-05-01 |  |  | 1998-07-01 | 423000 | -421642 | 1358 | 1358 | 100% | 0 | 0 | 0 | 54990 | -54813 | 176.54 | 0.46 | 0 | Canceled in 1998. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of display cabinet and walk-in freezers at Disthel | Individual | LAC | ARG | REF | 19 | INV | 45 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 196000 | -5726 | 190274 | 190274 | 100% | 0 | 0 | 0 | 25480 | -744 | 24735.62 | 0.38 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi | Individual | LAC | ARG | REF | 23 | INV | 60 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-11-01 | 2001-08-01 | 53850 | -4409 | 49441 | 49441 | 100% | 0 | 0 | 0 | 7001 | -573 | 6427.33 | 0.67 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio | Individual | LAC | ARG | REF | 23 | INV | 66 | A | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2002-11-01 | 2004-01-01 | 377350 | 0 | 377350 | 377350 | 100% | 0 | 0 | 0 | 49056 | 0 | 49055.5 | 0.5 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 | 2001-05-01 | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 27 | PRP | 88 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores AT Perito Moreno Ref. | Individual | LAC | ARG | REF | 28 | INV | 92 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 1999-07-01 | 1999-09-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 379605 | 0 | 379605 | 379605 | 100% | 0 | 0 | 0 | 49349 | 0 | 49348.65 | 0.35 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of one project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 30 | PRP | 103 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | ARG | REF | 33 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Tecnical assistance for country programme preparation | Individual | LAC | ARG | SEV | 04 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-07-01 | 1993-02-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1997-07-01 |  | 1999-12-01 | 2000-12-01 | 359500 | 0 | 359500 | 359500 | 100% | 0 | 0 | 0 | 46735 | 0 | 46735 | 0 | 0 | Financially closed in 2000. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation assistance (1994) | Individual | LAC | ARG | SEV | 14 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-09-01 | 1995-09-01 |  | 1995-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 17 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-03-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | ARG | SEV | 22 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Renewal of the institutional strengthening under the Montreal Protocol (Phase II) | Individual | LAC | ARG | SEV | 29 | INS | 98 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2003-05-01 | 2013-12-01 | 239700 | 0 | 239700 | 239700 | 100% | 0 | 0 | 0 | 31161 | 0 | 31161 | 0 | 0 | Financially completed in 2013. |  | 1999 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | ARG | SEV | 38 | INS | 130 | N | I | No_ODP | 25.7 | 25.7 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2008-10-01 | 311610 | -197 | 311413 | 311413 | 100% | 0 | 0 | 0 | 40509 | -26 | 40483.69 | -0.69 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | ARG | SEV | 45 | TAS | 144 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924 | 5268.5548 | 0.4452 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase IV) | Individual | LAC | ARG | SEV | 46 | INS | 145 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2008-05-01 | 2009-07-01 | 311567 | -521 | 311046 | 311046 | 100% | 0 | 0 | 0 | 23368 | -39 | 23328.9242 | 0.0758 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase V) | Individual | LAC | ARG | SEV | 53 | INS | 153 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-05-01 | 2011-12-01 | 311567 | 0 | 311567 | 311567 | 100% | 0 | 0 | 0 | 23368 | 0 | 23368 | 0 | 0 | Completed. National Ozone Unit monitoring elimination of use of CFCs in ARG.. Very strong licensing system allows country to have very reliable consumption data. Active public awareness programmes in place. Ozone Unit preparing for future challenges related to HCFCs. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase VI) | Individual | LAC | ARG | SEV | 59 | INS | 162 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 | 2014-04-01 | 155784 | 155783 | 311567 | 311567 | 100% | 0 | 0 | 0 | 11684 | 11684 | 23367.925 | 0.075001 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Non-Investment
COM | UNDP | Extension for institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | ARG | SEV | 65 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 |  | 2014-11-01 |  | 311567 | 0 | 311567 | 311353 | 99.93% | 214 | 0 | 171.064 | 23368 | 0 | 23351.9624 | 16.0376 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were carried out. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. IS renewal request prepared and approved. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):6 of 6. Contract/PO/MOA agreements signed:none. First disbursement date (actual/planned):The first disbursement took place in September 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | The review of imports of HCFCs in 2013 and preparation of reports to the MLFS are in progress as per the workplan. In addition, there has been follow up on existing MP funded projects in Argentina and the contract renewal of NOU's consultants. | 2011 |  | Non-investment
ONG | UNDP | Extension for institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | LAC | ARG | SEV | 71 | INS | 172 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2016-03-01 |  |  | 311567 | 0 | 311567 | 0 | 0% | 311567 | 0 | 124626.8 | 21810 | 0 | 0 | 21810 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This phase of the institutional project was approved in December 2013. In 2014, ODS consumption reports were prepared and submitted. Celebration of Ozone Day carried out. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Feb 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):6 of 6. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement will take place in January 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. | 2013 |  | Non-Investment
CLO | UNDP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2009-12-01 | 12000 | -12000 | 0 | 0 |  | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2009. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | ARM | PHA | 55 | PRP | 03 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -1549 | 83451 | 83451 | 100% | 0 | 0 | 0 | 6375 | -116 | 6258.825 | 0.17495 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ARM | PHA | 62 | INV | 06 | N | I | HCFC | 2.2 | 2.2 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2013-12-01 | 2014-08-01 | 265661 | 0 | 265661 | 265661 | 100% | 0 | 0 | 0 | 19925 | 0 | 19925 | 0 | 0 | Financially completed in 2014. | Completed in 2013. The planned milestone of conducting a mission to discuss progress over SAGA was achieved with a mission taking place in January 2014. Both, HPMP Stage I last tranche and PRP for Stage II have been prepared for submission to the 72nd Ex | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | ARM | PHA | 66 | INV | 09 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-02-01 | 2015-04-01 | 2017-01-01 |  |  | 297177 | 0 | 297177 | 253354 | 85.25% | 43823 | 0 | 17529.076 | 22288 | 0 | 19001.3388 | 3286.6612 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The situation at SAGA has not changed from 2013, and no additional progress was achieved with local constructions except for previous finishing of blender housing outside of the main facility. Multiple meetings held between NOU/UNDP and SAGA on clarifying plans, and then on attempting to convince SAGA to continue with the project. Additional consultations with Ministry of Environment (Deputy Minister)/NOU and UNDP/UNEP held in November 2014 at MOP in Paris resulted in the decision to begin prepararations to cancel the SAGA project. An action plan was developed to contact SAGA to start project cancellation. Prodoc signed (actual/planned, yes/no and date):Yes - Nov 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:An action plan was adopted to start cancelling the investment project for SAGA, which is under implementation | SAGA submitted a project cancellation letter to NOU-Armenia, and NOU informed that no last tranche for UNDP's remaining work with SAGA would be requested. Any unfunded eligible activities in the servicing sector as a part of the last third tranche would be taken from the existing balance of two first tranches of HPMP Stage I. MLF Secretariat was informed accordingly, and with the agreement, only UNEP's second and last tranche was requested at the 75th ExCom in May 2015, and approved. UNDP started cancellation process of the SAGA component by negotiating with the equipment supplier a possible return of two lines (refrigerant filling and foam) and compensation which was rejected by Transfair. UNDP is currently negotiating a transfer of this equipment to one of UNIDO's programmes with special thanks to UNIDO. Once such projects and transfer procedures are identified, and transfer is complete, UNDP will start return of obtained funds from the transfer to the MLF Secretariat. | 2012 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | ARM | PHA | 73 | PRP | 12 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1400 | 0 | 0 | 1400 | 0 | Newly Approved | Project document signed with the Government, and workplans developed. Funding allocated. A new appointment made by the Ministry of Natural Resources to NOU-Armenia. Recruitment of national experts ongoing. Mission will be planned in Q4 of 2015 to design the HPMP Stage II. | 2014 |  | Non-Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | ARM | PHA | 73 | TAS | 13 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2015-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2700 | 0 | 0 | 2700 | 0 | Newly Approved | Project document signed with the Government, and workplans developed. Funding allocated. Service tendering, selection and sub-contracting of a consultancy company is currently ongoing. | 2014 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | ARM | REF | 57 | PRP | 04 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-04-01 | 30000 | -3539 | 26461 | 26461 | 100% | 0 | 0 | 0 | 2250 | -265 | 1984.575 | 0.42495 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Asia | Individual | ASP | ASP | FOA | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -15672 | 36828 | 36828 | 100% | 0 | 0 | 0 | 6825 | -2037 | 4787.64 | 0.36 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 2000-12-01 | 102000 | -64974 | 37026 | 37026 | 100% | 0 | 0 | 0 | 13260 | -8446 | 4813.64 | 0.36 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Asia | RMP-Component | ASP | ASP | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1994-07-01 |  | 1996-08-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | BAH | PHA | 50 | INV | 16 | N | I | CFC | 38.4 | 38.4 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-12-01 |  | 2008-12-01 | 2013-05-01 | 272500 | 0 | 272500 | 272500 | 100% | 0 | 0 | 0 | 20437 | 0 | 20437 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | INV | 22 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2012-12-01 | 2014-03-01 | 40000 | -6846 | 33154 | 33154 | 100% | 0 | 0 | 0 | 3000 | -513 | 2486.55 | 0.45 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. | 2009 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BAH | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | ASP | BAH | REF | 22 | TAS | 04 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 242000 | -2849 | 239151 | 239151 | 100% | 0 | 0 | 0 | 31460 | -370 | 31090 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Preparation of two project proposals in the commercial refrigeration subsector | Individual | ASP | BAH | REF | 27 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | Individual | ASP | BAH | REF | 29 | INV | 09 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2011-12-01 | 173835 | 0 | 173835 | 173835 | 100% | 0 | 0 | 0 | 22599 | 0 | 22598.55 | 0.45 | 0 | Completed in 2004. Financially completed in 2011. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | Individual | ASP | BAH | REF | 29 | INV | 10 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-06-01 | 224478 | -51106 | 173372 | 173372 | 100% | 0 | 0 | 0 | 29182 | -6644 | 22538.14 | -0.14 | 0 | Completed in 2004. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a refrigerant management plan update | Individual | ASP | BAH | REF | 43 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-03-01 |  | 2006-12-01 | 2009-07-01 | 24000 | -1463 | 22537 | 22537 | 100% | 0 | 0 | 0 | 1800 | -110 | 1690.275 | -0.275 | 0 | Completed in 2006.Financially completed in 2009. |  | 2004 |  | Investment
CLO | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | BAR | PHA | 54 | PRP | 14 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-01 |  |  | 2010-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1125 | -1125 | 0 | 0 | 0 | TPMP will not be prepared for Barbados and funds should be returned to the MLF. Project therefore canceled. Funds to be returned in 2011. |  | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | BAR | PHA | 69 | INV | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 |  | 2016-04-01 | 2016-04-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 4500 | 0 | 0 | 4500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the government reviewed and approved the contents of the ProDoc upon final adjusments required to UNDP. The ProDoc was sent for signature by December 2014. Prodoc signed (actual/planned, yes/no and date):No, the prodoc will be signed in Mar 2015. Missions undertaken (actual/planned):0 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 2. Contract/PO/MOA agreements signed:0 of 1. First disbursement date (actual/planned):The first disbursement is planned for April 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:There has been a delay in the process of signing the Prodoc due to internal consultation process with Legal Department of GOV. A draft was approved in 2014 and sent officially to signature. It is expected that it will be signed in March 2015. | Procurement plan prepared and being reviewd by the GOV. | 2013 |  | Investment |  | To request the submission of additional status report to the 74th meeting to monitor the signing of the project document/letter of agreement and low disbursement rates of approved funds.
FIN | UNDP | Formulation of investment components of the RMP | Individual | LAC | BAR | REF | 39 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan for end-users | Individual | LAC | BAR | REF | 42 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | RMP-Component | LAC | BAR | REF | 43 | TAS | 11 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2004-07-01 | 2010-11-01 | 2006-12-01 |  | 2011-12-01 | 2014-02-01 | 172611 | -2925 | 169686 | 169686 | 100% | 0 | 0 | 0 | 15535 | -263 | 15271.75 | 0.25 | 0 | Financially completed in 2014. | Tools and equipment delivered to beneficiaries. Final invoices pending. | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | LAC | BAR | REF | 43 | TAS | 12 | N | I | CFC | 1.7 | 1.7 | 0 | 0 | 2004-07-01 |  | 2006-12-01 |  | 2013-12-01 | 2014-05-01 | 26150 | -26150 | 0 | 0 |  | 0 | 0 | 0 | 2354 | -2354 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Project team is working in the PCR and the Financially closure of the Project. | 2004 |  | Non-Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | AFR | BDI | ARS | 33 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 mixture in the manufacture of insecticides by conversion to hydrocarbon propellant at Fadi, S.A. (Fabrication d'insecticide et de product chimique) | Individual | AFR | BDI | ARS | 35 | INV | 09 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2004-12-01 |  | 2003-12-01 | 2011-12-01 | 128900 | -180 | 128720 | 128720 | 100% | 0 | 0 | 0 | 16757 | -23 | 16733.6 | 0.4 | 0 | Completed in 2003. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | BDI | FOA | 33 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Exim, S.A. | Individual | AFR | BDI | FOA | 35 | INV | 10 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2005-01-01 |  | 2003-12-01 | 2006-06-01 | 78262 | -8335 | 69927 | 69927 | 100% | 0 | 0 | 0 | 10174 | -1084 | 9090.06 | -0.06 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | BDI | PHA | 47 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -3963 | 26037 | 26037 | 100% | 0 | 0 | 0 | 2250 | -297 | 1952.775 | 0.225 | 0 | Completed in 2007. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities included in the RMP | RMP-Component | AFR | BDI | REF | 26 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2001-07-01 | 2000-12-01 |  | 2003-11-01 | 2003-11-01 | 10450 | -415 | 10035 | 10035 | 100% | 0 | 0 | 0 | 1359 | -54 | 1304.5 | 0.5 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 26 | TAS | 05 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 1998-11-01 | 2001-05-01 | 2000-12-01 |  | 2003-11-01 | 2004-01-01 | 119577 | -3603 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15545 | -468 | 15076.62 | 0.38 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for update of refrigerant management plan | Individual | AFR | BDI | REF | 40 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2004-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially Completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 41 | TAS | 13 | N | I | CFC | 4.7 | 4.7 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 32500 | -153 | 32347 | 32347 | 100% | 0 | 0 | 0 | 2925 | -14 | 2911.23 | -0.23 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | BDI | REF | 41 | TAS | 16 | N | I | CFC | 2.9 | 2.9 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 20000 | -464 | 19536 | 19536 | 100% | 0 | 0 | 0 | 1800 | -42 | 1758.24 | -0.24 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Preparation of two projects in the general foam subsector | Individual | AFR | BEN | FOA | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | Individual | AFR | BEN | FOA | 32 | INV | 12 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2003-07-01 |  | 2003-08-01 | 2005-09-01 | 143027 | -6481 | 136546 | 136546 | 100% | 0 | 0 | 0 | 18594 | -843 | 17750.51 | 0.49 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | Individual | ASP | BGD | ARS | 17 | INV | 05 | N | I | CFC | 123.6 | 123.6 | 0 | 0 | 1995-07-01 | 1998-12-01 | 1996-07-01 |  | 2002-08-01 | 2003-10-01 | 322920 | -343 | 322577 | 322577 | 100% | 0 | 0 | 0 | 41980 | -45 | 41934.6 | 0.4 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 2001-05-01 | Investment
FIN | UNDP | Formulation of a phase-out project in the MDI sector | Individual | ASP | BGD | ARS | 50 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -7050 | 22950 | 22950 | 100% | 0 | 0 | 0 | 2250 | -529 | 1721.25 | -0.25 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
COM | UNDP | Phase-out of CFC consumption in the manufacture of aerosol MDIs (Beximco, Square Pharmaceutical and Acme Pharmaceutical) | Individual | ASP | BGD | ARS | 52 | INV | 26 | N | I | CFC | 76.3 | 76.3 | 0 | 0 | 2007-07-01 | 2010-11-01 | 2011-07-01 |  | 2013-12-01 |  | 2776778 | 0 | 2776778 | 2762457 | 99.48% | 14321 | 13120.32 | 11457.048 | 208258 | 0 | 207183.9036 | 1074.0964 | 984.0223 | Completed in 2013. As planned in 2013, the milestone of paying the pending activities relating to the conversion project for Beximco and Acme was completed. Square has also procured and installed equipment for conversion of one formulation that was yet to be completed. With this, the conversion project in Square is also complete. In 2014, the major milestone will be the verification process of the conversion in Square. According to last year's ExCom decision, this project is supposed to be completed in 2013. | Completed in 2013. Verification of conversion in Square is proposed to be undertaken in May 2014. | 2007 | 2011-07-01 | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | BGD | FOA | 57 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-12-01 | 2013-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 | 0 | 3750 | -3750 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
COM | UNDP | Conversion from HCFC-141b to cyclopentane technology in manufacturing refrigeration equipment insulation foam at Walton Hi-Tech Industries Limited | Multi-year | ASP | BGD | FOA | 62 | INV | 38 | N | I | HCFC | 20.2 | 20.2 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 |  | 2014-12-01 |  | 1146074 | 0 | 1146074 | 1141311 | 99.58% | 4763 | 0 | 3810.272 | 85956 | 0 | 85598.7851 | 357.2149 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, the final project completion verification was undertaken through an international expert. The expert along with a team from UNDP country office and Government representatives, visited the site, undertook visual inspections along with review of specific reports and records relating to training etc., completed the certificate of completion for the project. With the completion of this activity, the project is considered complete and phase-out is achieved. The beneficiary, based on knowledge gained, is expected to adopt HFC free technologies in refrigerant component of domestic refrigerator manufacturing operations in future. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2011. Missions undertaken (actual/planned):Planned 2 and actual 1. TOR for consultants/subcontracts completed (actual/planned):3 TORs planned and 3 TORs actual. Contract/PO/MOA agreements signed:1 planned and 1 actual. First disbursement date (actual/planned):The first disbursement took place in June 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Safety audit consultancy firm has been appointed and will complete the audit activity in April 2014. Verification of completion of project is also expected to be completed by May 2014. | 2010 |  | Investment
FIN | UNDP | Formulation of a national phase out plan | Individual | ASP | BGD | PHA | 39 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | National ODS phase-out plan: technical assistance programme for the refrigeration servicing sub-sector (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 19 | N | I | CFC | 36 | 36 | 0 | 0 | 2004-04-01 | 2008-02-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 7200 | 0 | 7200 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National ODS phase-out plan: technical assistance for the phase-out of ODS solvents (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 20 | N | I | CTC | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National ODS phase-out plan: monitoring and management unit (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 2550 | 0 | 2550 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | BGD | PHA | 56 | PRP | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 | 2013-12-01 | 125000 | -102702 | 22298 | 22298 | 100% | 0 | 0 | 0 | 9375 | -7703 | 1672.35 | -0.35 | 0 | Financially completed in 2013. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TAS | 31 | N | I | CFC | 202.6 | 202.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2011-07-01 | 2013-10-01 | 669750 | 0 | 669750 | 669750 | 100% | 0 | 0 | 0 | 50231 | 0 | 50231 | 0 | 0 | Financially completed in 2013. | Completed in 2011. See BGD-36. | 2009 |  | Investment
FIN | UNDP | National ODS phase-out plan (fifth and sixth tranches) | Multi-year | ASP | BGD | PHA | 60 | INV | 36 | N | I | CFC | 21.9 | 21.9 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2012-12-01 | 2013-10-01 | 55000 | -4888 | 50112 | 50112 | 100% | 0 | 0 | 0 | 4125 | -367 | 3758.4 | -0.4 | 0 | Financially completed in 2013. | Completed in 2012. The project is expected to be financially closed by end of Q2 2013. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | BGD | PHA | 65 | INV | 40 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2011-11-01 |  | 2015-12-01 | 2018-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 22000 | 4125 | 0 | 0 | 4125 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, NOU closely monitored completion of the project at Walton. The project completion procedures (technical aspects) were completed. The NOU also had extensive interactions with industry associations and Government department on project implementation modalities and mechanisms to be adopted for promoting low-GWP technologies. Verification report for 2013 was completed during the year through an independent consultant. Other components relating to HPMP project for Stage-I are under implementation - particularly relating to the service sector and policy training support. The Government is also actively considering updating standards for adoption of low GWP flammable technologies and has had a consultative report prepared on the same. Prodoc signed (actual/planned, yes/no and date):N/A. Missions undertaken (actual/planned):Planned 3 and Actual 1. TOR for consultants/subcontracts completed (actual/planned):Planned 2 and Actual 2. Contract/PO/MOA agreements signed:Planned 1 and Actual 1. First disbursement date (actual/planned):None. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities under this project are progressing satisfactorily. HPMP Stage-I second tranche is approved. Verification reports for 2013 and 2014 submitted. | 2011 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BGD | REF | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-01-01 |  | 1999-09-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national recovery and recycling project | RMP-Component | ASP | BGD | REF | 29 | TAS | 10 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2005-07-01 | 2007-03-01 | 298270 | 0 | 298270 | 298270 | 100% | 0 | 0 | 0 | 38775 | 0 | 38775.1 | -0.1 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | ASP | BGD | REF | 29 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2005-12-01 | 2007-01-01 | 15455 | -69 | 15386 | 15386 | 100% | 0 | 0 | 0 | 2009 | -9 | 2000.1807 | -0.1807 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | BGD | REF | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2010-03-01 |  | 2012-09-01 | 2013-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Reconnaissance survey and training | Individual | ASP | BGD | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1993-06-01 | 1997-12-01 | 55000 | -1150 | 53850 | 53850 | 100% | 0 | 0 | 0 | 7150 | -150 | 7000.5 | -0.5 | 0 | Completed in 1993. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | BGD | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-06-01 |  | 1994-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | BGD | SEV | 14 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-09-01 | 1997-09-01 |  | 1999-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | BGD | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase II) | Individual | ASP | BGD | SEV | 29 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2001-12-01 | 2008-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2001. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | BGD | SEV | 35 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-01-01 |  | 2004-12-01 | 2008-08-01 | 100000 | -2099 | 97901 | 97901 | 100% | 0 | 0 | 0 | 13000 | -273 | 12727.13 | -0.13 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | BGD | SEV | 36 | CPG | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-10-01 |  | 2006-12-01 | 2007-03-01 | 18750 | -202 | 18548 | 18548 | 100% | 0 | 0 | 0 | 2438 | -26 | 2411.5 | 0.5 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | BGD | SEV | 44 | INS | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 130000 | -1588 | 128412 | 128412 | 100% | 0 | 0 | 0 | 9750 | -119 | 9630.9 | 0.1 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | BGD | SEV | 53 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2011-12-01 | 2012-07-01 | 130000 | -273 | 129727 | 129727 | 100% | 0 | 0 | 0 | 9750 | -20 | 9729.525 | 0.47505 | 0 | Financially completed in 2012. | The project is being financially closed by June 12. | 2007 |  | Non-Investment
COM | UNDP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | BGD | SEV | 61 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2012-06-01 |  | 2014-06-01 |  | 130000 | 0 | 130000 | 128860 | 99.12% | 1140 | 0 | 911.776 | 9750 | 0 | 9664.521 | 85.479 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, the NOU continued to implement IS project activities as per the proposed plans. Ozone day celebrations for 2014 were successfully undertaken with good participation from national stakeholders. The Government also continued to enforce licensing systems for HCFCs and has implemented a prohibition on HCFC-141b imports from January 2014. The Government also undertook technical information exchange activities on low GWP technologies and has had extensive consultations with national stakeholders on implementation issues particularly on safe adoption of low GWP alternatives in RAC sector. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in November 2011. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in January 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Monitoring of HPMP implementation and regulations, including licensing systems ongoing in Q1 of 2014. | 2010 |  | Non-Investment
ONG | UNDP | Renewal of the institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | ASP | BGD | SEV | 71 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-06-01 |  |  | 130000 | 0 | 130000 | 0 | 0% | 130000 | 0 | 52000 | 9100 | 0 | 0 | 9100 | 0 | Remarks (Short narrative description of progress made (actual/planned)):No activities planned for 2014. Activities expected to begin in 2015. Prodoc signed (actual/planned, yes/no and date):No, the prodoc is expected to be signed in July 2015. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):Planned - July 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The activities have been initiated in the beginning of 2015 and the implementation is going as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. The first disbursement is expected to be made in July 2015. | 2013 |  | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | BHA | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2543 | 12457 | 12457 | 100% | 0 | 0 | 0 | 1950 | -331 | 1619.41 | -0.41 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BHA | REF | 23 | TAS | 05 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-05-01 | 151400 | -12625 | 138775 | 138775 | 100% | 0 | 0 | 0 | 19682 | -1641 | 18040.75 | 0.25 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | BHU | PHA | 50 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-12-01 |  | 2007-03-01 | 2009-12-01 | 15000 | -10265 | 4735 | 4735 | 100% | 0 | 0 | 0 | 1125 | -770 | 355.125 | -0.125 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan | One-off-Phaseout | ASP | BHU | PHA | 52 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2010-07-01 |  | 2009-12-01 | 2011-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 3150 | 0 | 3150 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | INV | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-01-01 | 2013-12-01 |  | 2013-12-01 | 2014-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 6300 | 0 | 6300 | 0 | 0 | Financially completed in 2014. | Completed in 2013. During Q1 of 2014, project activities are being monitored. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | BHU | PHA | 70 | INV | 19 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2016-07-01 | 2017-01-01 |  |  | 42000 | 0 | 42000 | 41259 | 98.24% | 741 | 0 | 296.4 | 3780 | 0 | 3713.31 | 66.69 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the project activities under investment component were progressing in a satisfactory manner. The country is reviewing technology situation relating to HCFC alternatives and planning to implement suitable retrofit promotion schemes through their trained technicians. Prodoc signed (actual/planned, yes/no and date):Planned Sep 2013 and Actual December 2013. Missions undertaken (actual/planned):1 Planned - 0 actual. TOR for consultants/subcontracts completed (actual/planned):1 Planned - 0 Actual. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in December 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily. | 2013 |  | Investment
FIN | UNDP | Preparation of investment component of the refrigerant management plan | Individual | ASP | BHU | REF | 43 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance in the refrigeration servicing sector | RMP-Component | ASP | BHU | REF | 45 | TAS | 06 | N | I | CFC | 0.1 | 0.1 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2006-12-01 | 2009-11-01 | 45000 | -41 | 44959 | 44959 | 100% | 0 | 0 | 0 | 4050 | -4 | 4046.31 | -0.31 | 0 | Completed in 2006.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | BKF | REF | 32 | TAS | 11 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2006-01-01 |  | 2006-12-01 | 2008-09-01 | 132250 | -7409 | 124841 | 124841 | 100% | 0 | 0 | 0 | 17193 | -963 | 16229.302 | 0.698 | 0 | Completed in 2006. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | AFR | BKF | REF | 34 | TAS | 13 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2001-07-01 |  | 2007-08-01 |  | 2006-12-01 | 2008-09-01 | 16350 | -16350 | 0 | 0 |  | 0 | 0 | 0 | 2126 | -2126 | 0 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BOL | FOA | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | -2187 | 22813 | 22813 | 100% | 0 | 0 | 0 | 3250 | -284 | 2965.69 | 0.31 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BOL | FOA | 33 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Foam sector ODS phaseout (two enterprises: Isolcruz and Teplo) | Individual | LAC | BOL | FOA | 35 | INV | 15 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-05-01 | 2007-01-01 | 161211 | -5875 | 155336 | 155336 | 100% | 0 | 0 | 0 | 20957 | -764 | 20193.6957 | -0.6957 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BOL | FOA | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2014-12-01 |  | 50000 | -34137 | 15863 | 15863 | 100% | 0 | 0 | 0 | 3750 | -2560 | 1190 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The Foam sector plan to be submitted in future meeting still within Stage I, when technology issues for local SMEs are resolved. The remaining funds returned to MLF. PRP funds will be requested in 2015. Prodoc signed (actual/planned, yes/no and date):Yes, June 2009. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in March 2010. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:No alternative for HCFC-141 suitable for Bolivia conditions was identified at the time. Remaining funds returned to MLF. Will be requested in Nov 2015 | As planned, discussions were held with the local NOU to schedule activities for starting activities on foam sector. | 2009 |  | Investment
FIN | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (cotton and soy) | Individual | LAC | BOL | FUM | 27 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | BOL | FUM | 33 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal methyl bromide phase-out, excluding QPS applications | One-off-Phaseout | LAC | BOL | FUM | 35 | INV | 16 | N | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-12-01 |  | 2007-12-01 | 2011-10-01 | 221032 | -1 | 221031 | 221031 | 100% | 0 | 0 | 0 | 28734 | 0 | 28734.03 | -0.03 | 0 | Completed in 2007. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | INV | 29 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-03-01 |  | 2009-12-01 | 2013-02-01 | 151000 | 0 | 151000 | 151000 | 100% | 0 | 0 | 0 | 11325 | 0 | 11325 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | INV | 33 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2012-10-01 | 2014-04-01 | 222000 | -152 | 221848 | 221848 | 100% | 0 | 0 | 0 | 16650 | -11 | 16638.6 | 0.4 | 0 | Financially completed in 2014. | Completed in 2012. 5000 US$ from Environment Canada has been transferred to UNDP and will be implemented under this project. The remaining resources will be used for training of technicians in Bolivia. | 2009 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BOL | REF | 20 | TAS | 04 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 146000 | -691 | 145309 | 145309 | 100% | 0 | 0 | 0 | 18980 | -90 | 18890.17 | -0.17 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration and one in domestic refrigeration sub-sectors | Individual | LAC | BOL | REF | 24 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BOL | REF | 33 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration (terminal phase-out) sector | Individual | LAC | BOL | REF | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-09-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project for the commercial refrigeration manufacturing sector | Individual | LAC | BOL | REF | 42 | INV | 25 | N | I | CFC | 5.8 | 5.8 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 88840 | -130 | 88710 | 88710 | 100% | 0 | 0 | 0 | 7995 | -12 | 7983.3009 | -0.3009 | 0 | Completed in 2007. |  | 2004 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BOL | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-05-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | BOT | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -8880 | 11120 | 11120 | 100% | 0 | 0 | 0 | 2600 | -1154 | 1445.6 | 0.4 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
COM | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | BRA | DES | 57 | PRP | 288 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 |  | 2014-10-01 |  | 40000 | 0 | 40000 | 33270 | 83.17% | 6730 | 0 | 6730 | 3000 | 0 | 2495.25 | 504.75 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The full demonstration project was prepared and approved at the 72nd ExCom. Prodoc signed (actual/planned, yes/no and date):Yes, June 2009. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in February 2010. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Due to changes in the national situation related to the refrigerators replacement programme and the entrance of a new destruction facility in the market, the submission of the full project was delayed from the 71st to the 72nd ExCom. All activities were re-scheduled and duly completed by the time for submission to the 72nd ExCom. | The planned milestone of hiring the international expert has been completed and the project is being drafted. Submission is expected to the 72nd ExCom. | 2009 |  | Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | LAC | BRA | DES | 72 | DEM | 305 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2018-01-01 | 2018-01-01 |  |  | 1490600 | 0 | 1490600 | 0 | 0% | 1490600 | 0 | 596240 | 104342 | 0 | 0 | 104342 | 0 | Remarks (Short narrative description of progress made (actual/planned)):UNDP has prepared and presented the Project Document to the GOV. UNDP has assessed the project needs in terms of consultancies and TORs were prepared. Prodoc signed (actual/planned, yes/no and date):No, prodoc signature planned for April 2015. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 3. Contract/PO/MOA agreements signed:0 of 5. First disbursement date (actual/planned):The first disbursement is planned for April 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The Project document is under review by the GOV. UNDP has called for a meeting to clarify any issues with the ProDoc and has started to the process within the organization in order to have the implementation modality authorized. | Implementation plan prepared and being reviewed by the GOV. |  |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Therm-Jet (Belo Horizonte), Zenimont and Lavale (Sao Paulo) | Individual | LAC | BRA | FOA | 12 | INV | 13 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-03-01 | 1996-02-01 | 1995-03-01 |  | 1997-07-01 | 2000-12-01 | 370000 | -15282 | 354718 | 354718 | 100% | 0 | 0 | 0 | 48100 | -1987 | 46113.34 | -0.34 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam for steering wheels at Plascar | Individual | LAC | BRA | FOA | 17 | INV | 21 | A | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-12-01 |  | 1997-10-01 | 2000-07-01 | 119400 | -25268 | 94132 | 94132 | 100% | 0 | 0 | 0 | 15522 | -3285 | 12237.16 | -0.16 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Macform | Individual | LAC | BRA | FOA | 18 | INV | 27 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 243500 | -8086 | 235414 | 235414 | 100% | 0 | 0 | 0 | 31655 | -1051 | 30603.82 | 0.18 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Nacra | Individual | LAC | BRA | FOA | 18 | INV | 28 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 254500 | -47523 | 206977 | 206977 | 100% | 0 | 0 | 0 | 33085 | -6178 | 26907.01 | -0.01 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at MBR | Individual | LAC | BRA | FOA | 18 | INV | 29 | A | I | CFC | 40 | 40 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 338500 | -44421 | 294079 | 294079 | 100% | 0 | 0 | 0 | 44005 | -5775 | 38230.27 | -0.27 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Madef/Isoltec | Individual | LAC | BRA | FOA | 19 | INV | 43 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-12-01 | 2001-12-01 | 346000 | -64202 | 281798 | 281798 | 100% | 0 | 0 | 0 | 44980 | -8346 | 36633.74 | 0.26 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at three enterprises: Brafer, Invicta and Therm-Jet | Individual | LAC | BRA | FOA | 19 | INV | 44 | A | I | CFC | 38 | 38 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-07-01 | 1999-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Umbrella project covering 6 companies for the conversion to CFC-free technology in the manufacture of integral rigid skin and flexible molded polyurethane foam (Rorispuma, Indek, Flexfom, Walrod, Rigi | Individual | LAC | BRA | FOA | 19 | INV | 45 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-11-01 | 2000-07-01 | 746000 | 2 | 746002 | 746002 | 100% | 0 | 0 | 0 | 96980 | 0 | 96980.0078 | -0.0078 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free techcnology in the manufacture of polyurethane foam at Blitz Ind. Com. de Plasticos | Individual | LAC | BRA | FOA | 19 | INV | 46 | A | I | TCA/CFC | 9.8 | 9.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-07-01 | 2000-07-01 | 120000 | -36822 | 83178 | 83178 | 100% | 0 | 0 | 0 | 15600 | -4787 | 10813.14 | -0.14 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Panisol, S.A. (Paineis Isolantes) | Individual | LAC | BRA | FOA | 20 | INV | 53 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 1999-12-01 | 2003-11-01 | 315958 | -41 | 315917 | 315917 | 100% | 0 | 0 | 0 | 41075 | -5 | 41069.54 | 0.46 | 0 | Completed in 1999. Financially completed in 2003. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 21 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Giroflex | Individual | LAC | BRA | FOA | 22 | INV | 64 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-08-01 | 2002-11-01 | 177500 | 0 | 177500 | 177500 | 100% | 0 | 0 | 0 | 23075 | 0 | 23075 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyethylene foam tubing at Polipex | Individual | LAC | BRA | FOA | 22 | INV | 65 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2002-01-01 | 2002-12-01 | 191000 | 0 | 191000 | 191000 | 100% | 0 | 0 | 0 | 24830 | 0 | 24830 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Trambusti Naue | Individual | LAC | BRA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2000-11-01 | 2001-11-01 | 763600 | -2355 | 761245 | 761245 | 100% | 0 | 0 | 0 | 99268 | -306 | 98961.85 | 0.15 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Industrias Facchini, Ldta. | Individual | LAC | BRA | FOA | 22 | INV | 67 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-03-01 | 2001-11-01 | 258000 | -85574 | 172426 | 172426 | 100% | 0 | 0 | 0 | 33540 | -11125 | 22415.38 | -0.38 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Dalla Rosa E Cia | Individual | LAC | BRA | FOA | 22 | INV | 68 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-05-01 |  | 1999-12-01 | 2001-12-01 | 71600 | 0 | 71600 | 71600 | 100% | 0 | 0 | 0 | 9308 | 0 | 9308 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Aquedores Cumulus S.A. | Individual | LAC | BRA | FOA | 22 | INV | 69 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 86000 | -49 | 85951 | 85951 | 100% | 0 | 0 | 0 | 11180 | -6 | 11173.6296 | 0.3704 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Tekcor Utilidades Domesticas Ltd. | Individual | LAC | BRA | FOA | 22 | INV | 70 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1998-07-01 | 2003-05-01 | 71600 | -2957 | 68643 | 68643 | 100% | 0 | 0 | 0 | 9308 | -384 | 8923.59 | 0.41 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Metallurgica Barra | Individual | LAC | BRA | FOA | 22 | INV | 71 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1997-07-01 | 2000-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Isolenge | Individual | LAC | BRA | FOA | 22 | INV | 72 | A | I | CFC | 66 | 66 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-04-01 | 2000-12-01 | 516000 | -84186 | 431814 | 431814 | 100% | 0 | 0 | 0 | 67080 | -10944 | 56135.82 | 0.18 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technlogy in the manufacture of polyurethane foam at Plasmold | Individual | LAC | BRA | FOA | 23 | INV | 77 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 161500 | -737 | 160763 | 160763 | 100% | 0 | 0 | 0 | 20995 | -96 | 20899.1392 | -0.1392 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bulltrade | Individual | LAC | BRA | FOA | 23 | INV | 78 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 223000 | -358 | 222642 | 222642 | 100% | 0 | 0 | 0 | 28990 | -47 | 28943.4021 | -0.4021 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CMZ Poliuretanos | Individual | LAC | BRA | FOA | 23 | INV | 79 | A | I | CFC | 5.5 | 5.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 92750 | -305 | 92445 | 92445 | 100% | 0 | 0 | 0 | 12058 | -40 | 12017.8348 | 0.1652 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bruzze | Individual | LAC | BRA | FOA | 23 | INV | 80 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-11-01 |  | 2000-11-01 | 2002-03-01 | 278190 | -456 | 277734 | 277734 | 100% | 0 | 0 | 0 | 36165 | -59 | 36105.42 | 0.58 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Bernini | Individual | LAC | BRA | FOA | 23 | INV | 82 | A | I | CFC | 22.9 | 22.9 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-11-01 | 135150 | 0 | 135150 | 135150 | 100% | 0 | 0 | 0 | 17570 | 0 | 17569.5 | 0.5 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Polistecom | Individual | LAC | BRA | FOA | 23 | INV | 84 | A | I | CFC | 42.6 | 42.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 | 0 | 39390 | 0 | 39390 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mikawa & Cia | Individual | LAC | BRA | FOA | 23 | INV | 87 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 80600 | 0 | 80600 | 80600 | 100% | 0 | 0 | 0 | 10478 | 0 | 10478 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kalf Calcados | Individual | LAC | BRA | FOA | 23 | INV | 89 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-11-01 | 2003-11-01 | 101100 | 0 | 101100 | 101100 | 100% | 0 | 0 | 0 | 13143 | 0 | 13143 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Fast Frio | Individual | LAC | BRA | FOA | 23 | INV | 92 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at FJ Polymers | Individual | LAC | BRA | FOA | 23 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 89500 | -992 | 88508 | 88508 | 100% | 0 | 0 | 0 | 11635 | -129 | 11506.04 | -0.04 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Espumatec | Individual | LAC | BRA | FOA | 23 | INV | 94 | A | I | CFC | 64.6 | 64.6 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-04-01 | 2003-04-01 | 372000 | -271 | 371729 | 371729 | 100% | 0 | 0 | 0 | 48360 | -35 | 48324.77 | 0.23 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Zenimont | Individual | LAC | BRA | FOA | 23 | INV | 95 | A | I | CFC | 38.1 | 38.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2001-04-01 | 2002-03-01 | 298300 | 0 | 298300 | 298300 | 100% | 0 | 0 | 0 | 38779 | 0 | 38779 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation to prepare 16 projects in the foam sector | Individual | LAC | BRA | FOA | 24 | PRP | 98 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 70000 | -12756 | 57244 | 57244 | 100% | 0 | 0 | 0 | 9100 | -1658 | 7441.7213 | 0.2787 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Injebank | Individual | LAC | BRA | FOA | 25 | INV | 101 | A | I | CFC | 6 | 6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-04-01 | 86300 | -10846 | 75454 | 75454 | 100% | 0 | 0 | 0 | 11219 | -1410 | 9809.02 | -0.02 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to hexane and LCD technology in the manufacture of polyurethane foam at Herval | Individual | LAC | BRA | FOA | 25 | INV | 102 | A | I | CFC | 64.5 | 64.5 | 0 | 0 | 1998-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 637335 | 0 | 637335 | 637335 | 100% | 0 | 0 | 0 | 82854 | 0 | 82853.55 | 0.45 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to water based technology in the manufacture of polyurethane foam at Refratarios Isolamentos e Pinturas (RIP) | Individual | LAC | BRA | FOA | 25 | INV | 104 | A | I | CFC | 12 | 12 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-07-01 | 2003-04-01 | 94000 | -945 | 93055 | 93055 | 100% | 0 | 0 | 0 | 12220 | -123 | 12097.15 | -0.15 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Panther | Individual | LAC | BRA | FOA | 25 | INV | 105 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2000-11-01 | 2003-05-01 | 275805 | 0 | 275805 | 275805 | 100% | 0 | 0 | 0 | 35855 | 0 | 35854.65 | 0.35 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Gnatus | Individual | LAC | BRA | FOA | 25 | INV | 107 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-04-01 | 207225 | -488 | 206737 | 206737 | 100% | 0 | 0 | 0 | 26939 | -63 | 26875.81 | 0.19 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Cougar | Individual | LAC | BRA | FOA | 25 | INV | 108 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 154375 | 0 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20069 | 0 | 20068.75 | 0.25 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of polyurethane foam at SSM Tecnologia | Individual | LAC | BRA | FOA | 25 | INV | 109 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2003-11-01 | 106500 | 0 | 106500 | 106500 | 100% | 0 | 0 | 0 | 13845 | 0 | 13845 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of polyurethane foam at Delta Pack | Individual | LAC | BRA | FOA | 25 | INV | 110 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 202500 | 0 | 202500 | 202500 | 100% | 0 | 0 | 0 | 26325 | 0 | 26325 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at Isoblock | Individual | LAC | BRA | FOA | 26 | INV | 112 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-04-01 | 106500 | -132 | 106368 | 106368 | 100% | 0 | 0 | 0 | 13845 | -17 | 13828 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at C.A. Cunha | Individual | LAC | BRA | FOA | 26 | INV | 113 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-11-01 | 70100 | 0 | 70100 | 70100 | 100% | 0 | 0 | 0 | 9113 | 0 | 9113 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at P.F.I. Ind. E Com. Refrigeracao Ltd. (P.F.I.) | Individual | LAC | BRA | FOA | 26 | INV | 114 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-11-01 | 64200 | 0 | 64200 | 64200 | 100% | 0 | 0 | 0 | 8346 | 0 | 8346 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by HCFC-141b in the manufacture of integral skin foam furniture and conversion from CFC-11 to methylene chloride in the manufacture of polyurethane boxfoam at Cantegril | Individual | LAC | BRA | FOA | 26 | INV | 116 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-05-01 | 154740 | -4476 | 150264 | 150264 | 100% | 0 | 0 | 0 | 20116 | -582 | 19534.32 | -0.32 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams (microcellular) at Bicicletos Caloi, S.A. | Individual | LAC | BRA | FOA | 27 | INV | 117 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 227600 | -4765 | 222835 | 222835 | 100% | 0 | 0 | 0 | 29588 | -619 | 28968.55 | 0.45 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Conter Ind. e Isolantes Termocos, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 120 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 85347 | 0 | 85347 | 85347 | 100% | 0 | 0 | 0 | 11095 | 0 | 11095.11 | -0.11 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of integral skin foams at Spandy Peças em Poliuretano, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 125 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 261400 | -4032 | 257368 | 257368 | 100% | 0 | 0 | 0 | 33982 | -524 | 33457.84 | 0.16 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fabrica De Carrocerias Farage, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 129 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 52770 | 0 | 52770 | 52770 | 100% | 0 | 0 | 0 | 6860 | 0 | 6860.1 | -0.1 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Posto de Molas Vivian, Ltda. (Posmovil) | Individual | LAC | BRA | FOA | 27 | INV | 130 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 44700 | 0 | 44700 | 44700 | 100% | 0 | 0 | 0 | 5811 | 0 | 5811 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of four projects in the foam sector | Individual | LAC | BRA | FOA | 27 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of six projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of five projects in integral skin foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane sprayfoam at Isotherm Tratamento Thermo Acoustico Ltda. | Individual | LAC | BRA | FOA | 28 | INV | 131 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 116768 | 0 | 116768 | 116768 | 100% | 0 | 0 | 0 | 15180 | 0 | 15179.84 | 0.16 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam at Polsul Group | Individual | LAC | BRA | FOA | 28 | INV | 135 | A | I | CFC | 55 | 55 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2002-11-01 | 2006-10-01 | 536892 | -24390 | 512502 | 512502 | 100% | 0 | 0 | 0 | 69058 | -2683 | 66375.12 | -0.12 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible integral skin at Moldepol | Individual | LAC | BRA | FOA | 28 | INV | 136 | A | I | CFC | 34.8 | 34.8 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 421444 | -2 | 421442 | 421442 | 100% | 0 | 0 | 0 | 54788 | 0 | 54787.46 | 0.54 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ananda | Individual | LAC | BRA | FOA | 28 | INV | 137 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2002-04-01 | 37380 | -14147 | 23233 | 23233 | 100% | 0 | 0 | 0 | 4859 | -1839 | 3020.29 | -0.29 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in flexible molded foam, to water and methylene chloride technology in semi-rigid packaging foam, and to HCFC-141b in flexible integral skin foams at Espuma Oeste | Individual | LAC | BRA | FOA | 28 | INV | 138 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 181616 | -5766 | 175850 | 175850 | 100% | 0 | 0 | 0 | 23610 | -750 | 22860.5 | -0.5 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and integral skin foam at JNP Group | Individual | LAC | BRA | FOA | 28 | INV | 140 | A | I | CFC | 80.3 | 80.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2002-12-01 | 2006-10-01 | 823867 | -22056 | 801811 | 801811 | 100% | 0 | 0 | 0 | 100625 | -2426 | 98199.4 | -0.4 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in rigid polyurethane foam (spray and pour in place) at SIFC | Individual | LAC | BRA | FOA | 28 | INV | 143 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2000-11-01 | 2003-05-01 | 74385 | 0 | 74385 | 74385 | 100% | 0 | 0 | 0 | 9670 | 0 | 9670.05 | -0.05 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibrart | Individual | LAC | BRA | FOA | 29 | INV | 144 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 111838 | 0 | 111838 | 111838 | 100% | 0 | 0 | 0 | 14539 | 0 | 14538.94 | 0.06 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Durothan | Individual | LAC | BRA | FOA | 29 | INV | 145 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 228625 | 0 | 228625 | 228625 | 100% | 0 | 0 | 0 | 29721 | 0 | 29721.25 | -0.25 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at ACS Fibra | Individual | LAC | BRA | FOA | 29 | INV | 146 | A | I | CFC | 17.4 | 17.4 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 119336 | -2316 | 117020 | 117020 | 100% | 0 | 0 | 0 | 15514 | -301 | 15212.6 | 0.4 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam for packaging and to HCFC-141b technology for insulation applications at World Pack da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 147 | A | I | CFC | 86.6 | 86.6 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-10-01 | 405610 | 0 | 405610 | 405610 | 100% | 0 | 0 | 0 | 52729 | 0 | 52729.3 | -0.3 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for display cabinets at Vacuum Systems | Individual | LAC | BRA | FOA | 29 | INV | 148 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2001-12-01 | 2003-09-01 | 117450 | -1 | 117449 | 117449 | 100% | 0 | 0 | 0 | 15269 | 0 | 15268.37 | 0.63 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Plastwork Embalagens da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 149 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 144855 | -1757 | 143098 | 143098 | 100% | 0 | 0 | 0 | 18831 | -228 | 18602.74 | 0.26 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Intertelhas | Individual | LAC | BRA | FOA | 29 | INV | 150 | A | I | CFC | 48.9 | 48.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2000-12-01 | 2002-11-01 | 170074 | -62845 | 107229 | 107229 | 100% | 0 | 0 | 0 | 22110 | -8170 | 13939.62 | 0.38 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of rigid integral skin foam at Spray | Individual | LAC | BRA | FOA | 29 | INV | 151 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 211080 | -4717 | 206363 | 206363 | 100% | 0 | 0 | 0 | 27440 | -613 | 26827.19 | -0.19 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams at Nicos do Brasil | Individual | LAC | BRA | FOA | 29 | INV | 152 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Brasinj Ind. E Comm. | Individual | LAC | BRA | FOA | 29 | INV | 153 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 71253 | 0 | 71253 | 71253 | 100% | 0 | 0 | 0 | 9263 | 0 | 9262.89 | 0.11 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam and sprayfoam at Calorisol | Individual | LAC | BRA | FOA | 29 | INV | 154 | A | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 91477 | -33 | 91444 | 91444 | 100% | 0 | 0 | 0 | 11892 | -4 | 11887.72 | 0.28 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at ELV TEC Industria e Commercio Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 155 | A | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 134265 | 0 | 134265 | 134265 | 100% | 0 | 0 | 0 | 17454 | 0 | 17454.45 | -0.45 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin and flexible molded foams at Purtec | Individual | LAC | BRA | FOA | 29 | INV | 156 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2005-10-01 | 140769 | -3174 | 137595 | 137595 | 100% | 0 | 0 | 0 | 18300 | -413 | 17887.3493 | -0.34933 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isolamento Termico Brasfoam Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 157 | A | I | CFC | 61.6 | 61.6 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 110200 | -2358 | 107842 | 107842 | 100% | 0 | 0 | 0 | 14326 | -307 | 14019.46 | -0.46 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Fibrasil Ind. Commercio de Carroceria Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 158 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-05-01 | 2003-09-01 | 93425 | -32890 | 60535 | 60535 | 100% | 0 | 0 | 0 | 12145 | -4275 | 7869.95 | 0.05 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 10 projects in the integral skin foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 160 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector (SMEs) | Individual | LAC | BRA | FOA | 30 | PRP | 163 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 5 projects in the foam sector | Individual | LAC | BRA | FOA | 30 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2004-02-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and flexible molded foam at Fabbrini | Individual | LAC | BRA | FOA | 31 | INV | 167 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 124887 | -17316 | 107571 | 107571 | 100% | 0 | 0 | 0 | 16235 | -2251 | 13984.23 | -0.23 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Menaf | Individual | LAC | BRA | FOA | 31 | INV | 168 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 80994 | -11239 | 69755 | 69755 | 100% | 0 | 0 | 0 | 10529 | -1461 | 9068.15 | -0.15 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water-based technology in the manufacture of rigid polyurethane foam at Polyfoam | Individual | LAC | BRA | FOA | 31 | INV | 169 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2003-10-01 | 2005-09-01 | 178873 | -23652 | 155221 | 155221 | 100% | 0 | 0 | 0 | 23253 | -3075 | 20178.49 | -0.49 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Massimo | Individual | LAC | BRA | FOA | 31 | INV | 173 | A | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-09-01 | 2003-09-01 | 52279 | -5260 | 47019 | 47019 | 100% | 0 | 0 | 0 | 6796 | -684 | 6112.47 | -0.47 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and rigid foam at Injepol | Individual | LAC | BRA | FOA | 31 | INV | 175 | A | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 107678 | -9727 | 97951 | 97951 | 100% | 0 | 0 | 0 | 13998 | -1265 | 12733.63 | -0.63 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin and flexible molded foam at PPU | Individual | LAC | BRA | FOA | 31 | INV | 178 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2003-09-01 | 64568 | -5159 | 59409 | 59409 | 100% | 0 | 0 | 0 | 8394 | -671 | 7723.25 | -0.25 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Packo Plurinox | Individual | LAC | BRA | FOA | 31 | INV | 179 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2000-12-01 | 2001-12-01 | 39750 | 0 | 39750 | 39750 | 100% | 0 | 0 | 0 | 5168 | 0 | 5167.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at Mach-Plast | Individual | LAC | BRA | FOA | 31 | INV | 180 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 188951 | -12871 | 176080 | 176080 | 100% | 0 | 0 | 0 | 24564 | -1673 | 22890.4 | 0.6 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin and rigid foam at Montreal | Individual | LAC | BRA | FOA | 31 | INV | 181 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2003-08-01 |  | 2002-08-01 | 2003-09-01 | 83117 | 0 | 83117 | 83117 | 100% | 0 | 0 | 0 | 10805 | 0 | 10805.21 | -0.21 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Politermo | Individual | LAC | BRA | FOA | 31 | INV | 182 | A | I | CFC | 50.2 | 50.2 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 219136 | -2808 | 216328 | 216328 | 100% | 0 | 0 | 0 | 28488 | -365 | 28122.64 | 0.36 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin foam, flexible molded foam and rigid foam at Jetpol | Individual | LAC | BRA | FOA | 31 | INV | 183 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2003-08-01 |  | 2002-05-01 | 2003-09-01 | 214600 | -9772 | 204828 | 204828 | 100% | 0 | 0 | 0 | 27898 | -1270 | 26627.64 | 0.36 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam and rigid foam at Trantor | Individual | LAC | BRA | FOA | 31 | INV | 184 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 102234 | -5218 | 97016 | 97016 | 100% | 0 | 0 | 0 | 13290 | -678 | 12612.08 | -0.08 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refripor | Individual | LAC | BRA | FOA | 31 | INV | 185 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2001-12-01 | 2004-01-01 | 85350 | -16916 | 68434 | 68434 | 100% | 0 | 0 | 0 | 11096 | -2199 | 8896.55 | 0.45 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam, from CFC-11 to water-blown foam in flexible molded foam, and from CFC-11 to HCFC-141b in flexible integral skin foam at Multispuma | Individual | LAC | BRA | FOA | 31 | INV | 187 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 123929 | 0 | 123929 | 123929 | 100% | 0 | 0 | 0 | 16111 | 0 | 16110.77 | 0.23 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin (shoesoles) at Prosola | Individual | LAC | BRA | FOA | 31 | INV | 188 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 214118 | -165 | 213953 | 213953 | 100% | 0 | 0 | 0 | 27835 | -21 | 27814.34 | -0.34 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and flexible molded/integral skin foam at 50 small enterprises centered around their systems house Plastquim | Individual | LAC | BRA | FOA | 31 | INV | 189 | A | I | CFC | 153.4 | 153.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-12-01 | 931599 | -41480 | 890119 | 890119 | 100% | 0 | 0 | 0 | 112476 | -4563 | 107912.9 | 0.1 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Rytpak | Individual | LAC | BRA | FOA | 32 | INV | 190 | A | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-03-01 | 2003-04-01 | 211410 | -22300 | 189110 | 189110 | 100% | 0 | 0 | 0 | 27483 | -2899 | 24584.25 | -0.25 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams (shoesoles) at Megaflex | Individual | LAC | BRA | FOA | 32 | INV | 191 | A | I | CFC | 41.5 | 41.5 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-04-01 | 2003-05-01 | 205568 | -4726 | 200842 | 200842 | 100% | 0 | 0 | 0 | 26724 | -614 | 26109.46 | 0.54 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Plastiron | Individual | LAC | BRA | FOA | 32 | INV | 192 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 131768 | -5277 | 126491 | 126491 | 100% | 0 | 0 | 0 | 17130 | -686 | 16443.83 | 0.17 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refri-Leste | Individual | LAC | BRA | FOA | 32 | INV | 193 | A | I | CFC | 30 | 30 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-09-01 | 2003-04-01 | 136840 | -232 | 136608 | 136608 | 100% | 0 | 0 | 0 | 17789 | -30 | 17759.04 | -0.04 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam and to HCFC-141b for rigid polyurethane foam at Poliumetka | Individual | LAC | BRA | FOA | 32 | INV | 194 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-05-01 | 2003-09-01 | 136183 | -10263 | 125920 | 125920 | 100% | 0 | 0 | 0 | 17704 | -1334 | 16369.73 | 0.27 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Termobras | Individual | LAC | BRA | FOA | 32 | INV | 195 | A | I | CFC | 77 | 77 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2003-08-01 | 2005-09-01 | 294590 | -39496 | 255094 | 255094 | 100% | 0 | 0 | 0 | 38297 | -5135 | 33161.7 | 0.3 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-12 to isobutane technology in the manufacture of extruded polyethylene foam at Thermo-flex | Individual | LAC | BRA | FOA | 32 | INV | 196 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-10-01 | 123300 | 0 | 123300 | 123300 | 100% | 0 | 0 | 0 | 16029 | 0 | 16029 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water technology in the manufacture of rigid polyurethane foam at Ser Therm | Individual | LAC | BRA | FOA | 32 | INV | 197 | A | I | CFC | 72 | 72 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 359791 | -76117 | 283674 | 283674 | 100% | 0 | 0 | 0 | 46773 | -9895 | 36877.83 | 0.17 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manfuacture of rigid polyurethane foam at Jose Sola | Individual | LAC | BRA | FOA | 32 | INV | 198 | A | I | CFC | 38.7 | 38.7 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2002-11-01 | 2005-09-01 | 150369 | -24740 | 125629 | 125629 | 100% | 0 | 0 | 0 | 19548 | -3216 | 16331.97 | 0.03 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Frigs | Individual | LAC | BRA | FOA | 32 | INV | 201 | A | I | CFC | 90 | 90 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 311056 | -73855 | 237201 | 237201 | 100% | 0 | 0 | 0 | 40437 | -9601 | 30836.13 | -0.13 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 202 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 207 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 209 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 210 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Juntafacil | Individual | LAC | BRA | FOA | 34 | INV | 211 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2004-01-01 | 55204 | -3500 | 51704 | 51704 | 100% | 0 | 0 | 0 | 7177 | -455 | 6721.52 | 0.48 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Ornati-Luce | Individual | LAC | BRA | FOA | 34 | INV | 212 | A | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2003-11-01 | 46292 | -1550 | 44742 | 44742 | 100% | 0 | 0 | 0 | 6018 | -202 | 5816.46 | -0.46 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam at Paranoa | Individual | LAC | BRA | FOA | 34 | INV | 213 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-05-01 | 2004-01-01 | 84660 | -1 | 84659 | 84659 | 100% | 0 | 0 | 0 | 11006 | 0 | 11005.8 | 0.2 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam and rigid integral skin foam at Piatex | Individual | LAC | BRA | FOA | 34 | INV | 214 | A | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-11-01 | 83075 | 0 | 83075 | 83075 | 100% | 0 | 0 | 0 | 10800 | 0 | 10799.75 | 0.25 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of flexible molded foam and to HCFC-141b for flexible integral skin foam at Rosil | Individual | LAC | BRA | FOA | 34 | INV | 215 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 87672 | -2545 | 85127 | 85127 | 100% | 0 | 0 | 0 | 11397 | -331 | 11066.38 | -0.38 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible integral skin and flexible molded foams at Royal Rubber | Individual | LAC | BRA | FOA | 34 | INV | 216 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 120795 | -3396 | 117399 | 117399 | 100% | 0 | 0 | 0 | 15703 | -441 | 15261.87 | 0.13 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for electrical resistance floats at Taurus | Individual | LAC | BRA | FOA | 34 | INV | 217 | A | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 88075 | 0 | 88075 | 88075 | 100% | 0 | 0 | 0 | 11450 | 0 | 11449.75 | 0.25 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Thermoblock | Individual | LAC | BRA | FOA | 34 | INV | 218 | A | I | CFC | 41.1 | 41.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 260592 | -36386 | 224206 | 224206 | 100% | 0 | 0 | 0 | 33877 | -4730 | 29146.78 | 0.22 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based and HCFC-141b technology in the manufacture of rigid and flexible integral skin foam at VM | Individual | LAC | BRA | FOA | 34 | INV | 220 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-11-01 | 83902 | 0 | 83902 | 83902 | 100% | 0 | 0 | 0 | 10907 | 0 | 10907.26 | -0.26 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for surfboards at Jedda | Individual | LAC | BRA | FOA | 34 | INV | 221 | A | I | CFC | 54 | 54 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 148272 | -32257 | 116015 | 116015 | 100% | 0 | 0 | 0 | 19275 | -4193 | 15081.95 | 0.05 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Transen | Individual | LAC | BRA | FOA | 34 | INV | 224 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 61940 | -1800 | 60140 | 60140 | 100% | 0 | 0 | 0 | 8052 | -234 | 7818.2 | -0.2 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam for cold room panels, freezers and coolers at Central Equipment | Individual | LAC | BRA | FOA | 34 | INV | 225 | A | I | CFC | 15.1 | 15.1 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 118233 | -8399 | 109834 | 109834 | 100% | 0 | 0 | 0 | 15370 | -1092 | 14278.42 | -0.42 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isar | Individual | LAC | BRA | FOA | 34 | INV | 226 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 174320 | -12870 | 161450 | 161450 | 100% | 0 | 0 | 0 | 22662 | -1673 | 20988.6 | 0.4 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoeste | Individual | LAC | BRA | FOA | 34 | INV | 227 | A | I | CFC | 64.9 | 64.9 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2006-06-01 | 237296 | -33228 | 204068 | 204068 | 100% | 0 | 0 | 0 | 30848 | -4320 | 26528.48 | -0.48 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid and flexible integral skin foams at Air Micro | Individual | LAC | BRA | FOA | 34 | INV | 229 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2004-01-01 | 56490 | -2984 | 53506 | 53506 | 100% | 0 | 0 | 0 | 7344 | -388 | 6956.04 | -0.04 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Beneplast | Individual | LAC | BRA | FOA | 34 | INV | 230 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 135176 | -12534 | 122642 | 122642 | 100% | 0 | 0 | 0 | 17573 | -1629 | 15943.46 | 0.54 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Korta Calhas | Individual | LAC | BRA | FOA | 34 | INV | 231 | A | I | CFC | 75.7 | 75.7 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 151812 | 0 | 151812 | 151812 | 100% | 0 | 0 | 0 | 19736 | 0 | 19735.56 | 0.44 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam, rigid foam and flexible molded foam at Carolinas | Individual | LAC | BRA | FOA | 34 | INV | 232 | A | I | CFC | 49.7 | 49.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 237597 | -80 | 237517 | 237517 | 100% | 0 | 0 | 0 | 30888 | -10 | 30877.21 | 0.79 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam and rigid integral skin foam, and to HCFC-141b for rigid, flexible integral skin and phenolic foams at J. Dal Ponte | Individual | LAC | BRA | FOA | 34 | INV | 233 | A | I | CFC | 97.6 | 97.6 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 384134 | 0 | 384134 | 384134 | 100% | 0 | 0 | 0 | 49937 | 0 | 49937.42 | -0.42 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HFC-141b in the manufacture of rigid polyurethane foam at Danko | Individual | LAC | BRA | FOA | 34 | INV | 234 | A | I | CFC | 41.4 | 41.4 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 199684 | -3329 | 196355 | 196355 | 100% | 0 | 0 | 0 | 25959 | -433 | 25526.1487 | -0.14866 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for truck bodies and panels at 9 enterprises (ABC Furgoes, Fricam Refri, Junges, Rafaeli, Refri Santos, Rondofrio, Tresmaiense, Trevosul Refrig, Verde Lago Furgoes) | Individual | LAC | BRA | FOA | 34 | INV | 235 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-12-01 | 450479 | -69602 | 380877 | 380877 | 100% | 0 | 0 | 0 | 58562 | -9048 | 49514.54 | -0.54 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Grupo ACO | Individual | LAC | BRA | FOA | 34 | INV | 236 | A | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2004-08-01 |  |  | 2002-07-01 | 174139 | -174139 | 0 | 0 |  | 0 | 0 | 0 | 22638 | -22638 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoprice | Individual | LAC | BRA | FOA | 34 | INV | 237 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-12-01 | 2006-10-01 | 126846 | -9673 | 117173 | 117173 | 100% | 0 | 0 | 0 | 16490 | -1257 | 15232.98 | 0.02 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible microcellular foams at Hidroplas | Individual | LAC | BRA | FOA | 34 | INV | 238 | A | I | CFC | 33 | 33 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2002-11-01 | 2004-01-01 | 166211 | -5537 | 160674 | 160674 | 100% | 0 | 0 | 0 | 21607 | -720 | 20887.62 | -0.62 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam for ice cream makers and coolers at three enterprises (A.V. Bertollo, Citrocar, Systherm) | Individual | LAC | BRA | FOA | 34 | INV | 239 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-10-01 | 2005-12-01 | 135345 | -2457 | 132888 | 132888 | 100% | 0 | 0 | 0 | 17595 | -319 | 17275.44 | 0.56 | 0 | Completed in 2002. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Injetec | Individual | LAC | BRA | FOA | 34 | INV | 240 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 43334 | -2371 | 40963 | 40963 | 100% | 0 | 0 | 0 | 5633 | -308 | 5325.19 | -0.19 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Pretty Glass | Individual | LAC | BRA | FOA | 36 | INV | 243 | A | I | CFC | 17.2 | 17.2 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 91508 | -6465 | 85043 | 85043 | 100% | 0 | 0 | 0 | 11896 | -840 | 11056.04 | -0.04 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | Individual | LAC | BRA | FOA | 36 | INV | 244 | A | I | CFC | 18 | 18 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2005-12-01 | 2007-03-01 | 98416 | -3 | 98413 | 98413 | 100% | 0 | 0 | 0 | 12794 | 0 | 12793.69 | 0.31 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Simonaggio | Individual | LAC | BRA | FOA | 36 | INV | 245 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-09-01 | 120383 | -10640 | 109743 | 109743 | 100% | 0 | 0 | 0 | 15650 | -1383 | 14266.79 | 0.21 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Heliotek | Individual | LAC | BRA | FOA | 36 | INV | 246 | A | I | CFC | 27.4 | 27.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 127133 | -12221 | 114912 | 114912 | 100% | 0 | 0 | 0 | 16527 | -1588 | 14939.29 | -0.29 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isojet | Individual | LAC | BRA | FOA | 36 | INV | 247 | A | I | CFC | 47.4 | 47.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 130427 | 0 | 130427 | 130427 | 100% | 0 | 0 | 0 | 16956 | 0 | 16955.51 | 0.49 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Tecnosono | Individual | LAC | BRA | FOA | 36 | INV | 248 | A | I | CFC | 23 | 23 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2003-07-01 | 2004-01-01 | 134718 | -4512 | 130206 | 130206 | 100% | 0 | 0 | 0 | 17513 | -587 | 16926.7914 | -0.7914 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Tolling Quimica | Individual | LAC | BRA | FOA | 36 | INV | 249 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-08-01 | 2005-10-01 | 159662 | -1356 | 158306 | 158306 | 100% | 0 | 0 | 0 | 20756 | -176 | 20579.7805 | 0.21945 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibral | Individual | LAC | BRA | FOA | 36 | INV | 250 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-03-01 | 197613 | -1856 | 195757 | 195757 | 100% | 0 | 0 | 0 | 25690 | -241 | 25448.4071 | 0.5929 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam, and water-blown technology for flexible moulded foam at Arquespuma | Individual | LAC | BRA | FOA | 36 | INV | 252 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-01-01 | 207741 | 0 | 207741 | 207741 | 100% | 0 | 0 | 0 | 27006 | 0 | 27006.33 | -0.33 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isosister | Individual | LAC | BRA | FOA | 36 | INV | 254 | A | I | CFC | 82.5 | 82.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2007-03-01 | 277668 | -6748 | 270920 | 270920 | 100% | 0 | 0 | 0 | 36097 | -877 | 35219.5961 | 0.4039 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water/methylene chloride/hydrocarbon-blown technology in the manufacture of rigid and flexible foam at Toro | Individual | LAC | BRA | FOA | 36 | INV | 255 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2004-12-01 | 2005-10-01 | 279477 | 0 | 279477 | 279477 | 100% | 0 | 0 | 0 | 36332 | 0 | 36332.01 | -0.01 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Repor | Individual | LAC | BRA | FOA | 36 | INV | 256 | A | I | CFC | 50.8 | 50.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2008-04-01 | 323201 | -35934 | 287267 | 287267 | 100% | 0 | 0 | 0 | 42016 | -4671 | 37344.71 | 0.29 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid foam and flexible integral skin foam and water-blown technology for flexible moulded foam and rigid integral skin foam at Ariston Polimeros | Individual | LAC | BRA | FOA | 36 | INV | 257 | A | I | CFC | 75.1 | 75.1 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-08-01 | 2005-09-01 | 369242 | -12749 | 356493 | 356493 | 100% | 0 | 0 | 0 | 48001 | -1657 | 46344.46 | -0.46 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Indaru | Individual | LAC | BRA | FOA | 36 | INV | 258 | A | I | CFC | 93.8 | 93.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2004-06-01 | 2007-03-01 | 423121 | 0 | 423121 | 423121 | 100% | 0 | 0 | 0 | 55006 | 0 | 55005.73 | 0.27 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam, elastomers and integral skin foam for automotive applications and to HCFC-141b for furniture integral skin foam applications at Steel Plastik | Individual | LAC | BRA | FOA | 36 | INV | 259 | A | I | CFC | 46.7 | 46.7 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-12-01 | 2005-11-01 | 247882 | 0 | 247882 | 247882 | 100% | 0 | 0 | 0 | 32225 | 0 | 32224.66 | 0.34 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Pilot project for validation of methyl formate as a blowing agent in the manufacture of polyurethane foam (phase I) | Individual | LAC | BRA | FOA | 56 | DEM | 285 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-06-01 |  | 2010-12-01 | 2014-05-01 | 401500 | -25778 | 375722 | 375722 | 100% | 0 | 0 | 0 | 30113 | -1933 | 28179.6179 | 0.3821 | 0 | Financially completed in 2014. |  | 2008 | 2010-08-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BRA | FOA | 57 | PRP | 287 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-07-01 | 2012-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2012. | Completed in 2011. Sector Foam projects approved by the 64th Executive Committee Meeting. Some remaining invoices pending. | 2009 |  | Investment
FIN | UNDP | Pilot project to validate methylal as blowing agent in the manufacture of polyurethane foams (phase I) | Individual | LAC | BRA | FOA | 58 | DEM | 292 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  | 2012-12-01 | 2014-02-01 | 464200 | -33805 | 430395 | 430395 | 100% | 0 | 0 | 0 | 34815 | -2535 | 32279.62 | 0.38 | 0 | Financially completed in 2014. | Completed in 2012. Final payments for Technical Assistance and commissioning in 2012 have been completed and will be reflected in 2013. | 2009 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | BRA | FOA | 72 | PRP | 301 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 | 2016-05-01 |  |  | 150000 | 0 | 150000 | 17446 | 11.63% | 132554 | 0 | 132554.24 | 10500 | 0 | 1221.2032 | 9278.7968 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the survey of consumption of HCFC 141b was conducted, System houses and end-users were identified, stakeholder meetings were held, and company visits were conducted. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in August 2014. Missions undertaken (actual/planned):8 of 8. TOR for consultants/subcontracts completed (actual/planned):4 of 4. Contract/PO/MOA agreements signed:4 of 4. First disbursement date (actual/planned):The first disbursement took place in November 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, HCFC survey and drafted investment projects were reviewed in light of the new funding guidelines approved by the 74th ExCom. HPMP draft was put into public consultation to collect final inputs from private sector and civil society. |  |  | Non-Investment
CLO | UNDP | Project preparation for two methyl bromide demonstration projects (soil fumigation for flowers, tomatoes, cucumbers and strawberries) | Individual | LAC | BRA | FUM | 24 | PRP | 96 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  |  | 2000-12-01 | 40000 | -31187 | 8813 | 8813 | 100% | 0 | 0 | 0 | 5200 | -4054 | 1145.69 | 0.31 | 0 | Canceled in 2000. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CTC as process agent in two applications at Braskem | Individual | LAC | BRA | PAG | 54 | INV | 281 | N | I | CTC | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-12-01 | 2013-01-01 | 1178554 | -6110 | 1172444 | 1172444 | 100% | 0 | 0 | 0 | 88392 | -458 | 87933.7477 | 0.2523 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a CFC terminal phase-out programme | Individual | LAC | BRA | PHA | 36 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | INV | 262 | N | I | CFC | 1251 | 1251 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2003-12-01 |  | 2005-12-01 | 2013-12-01 | 7860000 | 0 | 7860000 | 7860000 | 100% | 0 | 0 | 0 | 687700 | 0 | 687700 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 264 | N | I | CFC | 737 | 737 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2008-12-01 | 2013-05-01 | 5720000 | 0 | 5720000 | 5720000 | 100% | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | National CFC phase-out plan: third tranche | Multi-Year | LAC | BRA | PHA | 45 | INV | 270 | N | I | CFC | 743 | 743 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2006-04-01 |  | 2009-12-01 | 2013-02-01 | 3970000 | 0 | 3970000 | 3970000 | 100% | 0 | 0 | 0 | 342500 | 0 | 342500 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National CFC phase-out plan: fourth tranche | Multi-Year | LAC | BRA | PHA | 47 | INV | 274 | N | I | CFC | 1020 | 1020 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2006-12-01 |  | 2011-10-01 | 2013-12-01 | 2856400 | 0 | 2856400 | 2856400 | 100% | 0 | 0 | 0 | 242276 | 0 | 242276 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | BRA | PHA | 50 | INV | 278 | N | I | CFC | 1050 | 1050 | 0 | 0 | 2006-11-01 | 2011-04-01 | 2009-12-01 |  | 2012-09-01 | 2013-05-01 | 1190000 | 0 | 1190000 | 1190000 | 100% | 0 | 0 | 0 | 92300 | 0 | 92300 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | LAC | BRA | PHA | 53 | INV | 280 | N | I | CFC | 576 | 576 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 870000 | 0 | 870000 | 870000 | 100% | 0 | 0 | 0 | 63500 | 0 | 63500 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | BRA | PHA | 55 | PRP | 283 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-06-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 | 0 | 10781 | 0 | 10781.25 | -0.25 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
FIN | UNDP | National CFC phase-out plan (seventh tranche) | Multi-Year | LAC | BRA | PHA | 56 | INV | 284 | N | I | CFC | 350 | 350 | 0 | 0 | 2008-11-01 | 2013-02-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 12500 | 0 | 12500 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | National CFC phase-out plan (eighth tranche) | Multi-Year | LAC | BRA | PHA | 59 | INV | 293 | N | I | CFC | 74 | 74 | 0 | 0 | 2009-11-01 | 2013-02-01 | 2011-11-01 |  | 2013-12-01 | 2013-12-01 | 100000 | 0 | 100000 | 86309 | 86.31% | 13691 | 0 | 0 | 5000 | 0 | 4315.45 | 684.55 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 295 | N | I | HCFC | 48.7 | 48.7 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2012-07-01 | 2016-01-01 |  |  | 4456257 | 0 | 4456257 | 3020544 | 67.78% | 1435713 | 0 | 574285.4 | 334219 | 0 | 226540.5761 | 107678.4239 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the project advanced in the implementation of projects at Cont. Panels companies. Four companies had designed the reconversion plans and undertook reconversion activities with support of the technology supplier. At System House projects, 50 clients supported by Purcom and Arinos had started to do initial trials on formulations. Details can be found in the Tranche Report submitted to the 74th ExCom Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2012. Missions undertaken (actual/planned):5 of 5. TOR for consultants/subcontracts completed (actual/planned):6 of 6. Contract/PO/MOA agreements signed:6 of 6. First disbursement date (actual/planned):The first disbursement took place in November 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, implementation of continuous panels sector reconversions has progressed satisfactorily. Purcom and Arinos have advanced with the implementation of end-users trials and retrofits. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | LAC | BRA | PHA | 68 | INV | 298 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2016-01-01 |  |  | 3400000 | 0 | 3400000 | 0 | 0% | 3400000 | 0 | 1360000 | 255000 | 0 | 0 | 255000 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the project advanced in the implementation of projects at Integral Skin companies. 5 companies had designed the reconversion plans and are undertaking reconversion activities with support of the technology supplier. 2 companies had agreed in the technology selection. At the System House level, all 11 System Houses were assisted with trials and testing to choose technology. UNDP is assessing their reconversion plan to authorize System House adapation and to proceed with disbursements. Details can be found in the Tranche Report submitted to the 74th ExCom Prodoc signed (actual/planned, yes/no and date):Yes, the original ProDoc was amended In March 2013 to include the second tranche. Missions undertaken (actual/planned):5 of 5. TOR for consultants/subcontracts completed (actual/planned):11 of 11. Contract/PO/MOA agreements signed:11 of 11. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, implementation of integral skin sector reconversions has progressed satisfactorily. All IS System House suppliers have started initial trials at client level. | 2012 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | BRA | PHA | 72 | PRP | 300 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-07-01 | 2016-05-01 | 2016-01-01 |  |  | 50000 | 0 | 50000 | 14435 | 28.87% | 35565 | 0 | 35565.07 | 3500 | 0 | 1010.4451 | 2489.5549 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented in 2014 included 3 consultation meetings and 12 missions to end-users to collect data for over-arching strategy. HPMP Document has been updated and reviewed by the Government. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in June 2014. Missions undertaken (actual/planned):5 of 5. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in July 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, HCFC survey and drafted investment projects were reviewed in light of the new funding guidelines approved by the 74th ExCom. HPMP draft was put into public consultation to collect final inputs from private sector and civil society. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multi-Year | LAC | BRA | PHA | 73 | INV | 306 | N | I | HCFC | 32.7 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 3000000 | 0 | 3000000 | 0 | 0% | 3000000 | 0 | 1200000 | 225000 | 0 | 0 | 225000 | 0 | Newly Approved | Implementation of PU rigid foam sector reconversions have initiated with initial trials at DSU level being undertaken by Purcom. | 2014 |  | Investment
FIN | UNDP | Demonstration programme to improve domestic refrigerator servicing and CFC recycling in service shops | Individual | LAC | BRA | REF | 06 | DEM | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-02-01 | 1993-12-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic chest freezers at Multibras, S.A. Electrodomésticos | Individual | LAC | BRA | REF | 17 | INV | 24 | N | I | CFC | 165.9 | 165.9 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-12-01 |  | 1997-12-01 | 1999-12-01 | 598499 | 0 | 598499 | 598499 | 100% | 0 | 0 | 0 | 77805 | 0 | 77804.87 | 0.13 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Multibras, S.A. | Individual | LAC | BRA | REF | 20 | INV | 57 | N | I | CFC | 1068.8 | 1068.8 | 0 | 0 | 1996-10-01 | 1997-07-01 | 1999-09-01 |  | 2001-12-01 | 2013-12-01 | 4899790 | 0 | 4899790 | 4899790 | 100% | 0 | 0 | 0 | 636973 | 0 | 636972.7 | 0.3 | 0 | Financially completed in 2013. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Artico | Individual | LAC | BRA | REF | 23 | INV | 81 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 225100 | -927 | 224173 | 224173 | 100% | 0 | 0 | 0 | 29263 | -120 | 29142.5627 | 0.4373 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Niju Ind. Com Implem Rodov Ltda. | Individual | LAC | BRA | REF | 23 | INV | 86 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 111600 | 0 | 111600 | 111600 | 100% | 0 | 0 | 0 | 14508 | 0 | 14508 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mais Frio | Individual | LAC | BRA | REF | 23 | INV | 88 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 154400 | -25 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20072 | -3 | 20068.75 | 0.25 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Increal Ltda. | Individual | LAC | BRA | REF | 23 | INV | 90 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 418000 | -4 | 417996 | 417996 | 100% | 0 | 0 | 0 | 54340 | -1 | 54339.48 | -0.48 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Friar | Individual | LAC | BRA | REF | 23 | INV | 91 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2003-04-01 | 185726 | -1023 | 184703 | 184703 | 100% | 0 | 0 | 0 | 24144 | -133 | 24011.39 | -0.39 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 24 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-07-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b (foam) and HFC-134a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at Termisa | Individual | LAC | BRA | REF | 25 | INV | 111 | A | I | CFC | 27 | 27 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2001-12-01 | 322205 | 0 | 322205 | 322205 | 100% | 0 | 0 | 0 | 41887 | 0 | 41886.65 | 0.35 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and CFC-12 by conversion to HFC-134a in the manufacture of small commercial freezers and coolers at Bebber | Individual | LAC | BRA | REF | 26 | INV | 115 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2002-04-01 | 144500 | -3024 | 141476 | 141476 | 100% | 0 | 0 | 0 | 18785 | -393 | 18392 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b technology (foam) and HFC-134a -134a technology (refrigerant) in the manufacture of refrigerated truck trailers at Artica | Individual | LAC | BRA | REF | 27 | INV | 118 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-11-01 | 2003-10-01 | 183623 | -7277 | 176346 | 176346 | 100% | 0 | 0 | 0 | 23871 | -946 | 22924.98 | 0.02 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration sector | Individual | LAC | BRA | REF | 27 | PRP | 122 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 27 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers by conversion to cyclo-pentane and HCF-134a at Metalurgica Venan Ltda. | Individual | LAC | BRA | REF | 28 | INV | 132 | N | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-02-01 |  | 2004-03-01 | 2009-07-01 | 741800 | -6793 | 735007 | 735007 | 100% | 0 | 0 | 0 | 91598 | -839 | 90759.1955 | -0.1955 | 0 | Completed in 2004.Financially completed in 2009. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11, CFC-12 and R-502 by conversion to HCFC-141b technology (foam) and HFC-134a and R-404a technology (refrigerant) in the manufacture of milk coolers and display cabinets at Incomar | Individual | LAC | BRA | REF | 28 | INV | 133 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 74529 | 0 | 74529 | 74529 | 100% | 0 | 0 | 0 | 9689 | 0 | 9688.77 | 0.23 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-402a in the manufacture of commercial refrigeration products at General Icy | Individual | LAC | BRA | REF | 28 | INV | 134 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 411139 | 0 | 411139 | 411139 | 100% | 0 | 0 | 0 | 53448 | 0 | 53448.07 | -0.07 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 3 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 30 | PRP | 162 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-404a in the manufacture of freezer rooms and panels, and rigid foam at Schmit | Individual | LAC | BRA | REF | 31 | INV | 166 | A | I | CFC | 43.3 | 43.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2002-10-01 | 2003-11-01 | 288764 | -29918 | 258846 | 258846 | 100% | 0 | 0 | 0 | 37539 | -3889 | 33650.11 | -0.11 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | BRA | REF | 32 | TAS | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2003-07-01 | 100000 | -1 | 99999 | 99999 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 208 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers. | Individual | LAC | BRA | REF | 47 | DEM | 275 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2013-04-01 | 2008-12-01 | 2017-01-01 |  |  | 1000000 | 0 | 1000000 | 40615 | 4.061% | 959385 | 0 | 383754.124 | 75000 | 0 | 3046.1017 | 71953.8982 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, a company to undertake the energy efficiency evaluation of replaced chillers was hired and it is working with the Government to assess the buildings being supported by the GEF component. Signed contracts result in USD 700,000 of project funds having been committed Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2013. Missions undertaken (actual/planned):5 of 5. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The signature of the ProDoc was delayed. Project design included cooperation with GEF funded activities being implemented by other Directorate of Ministry of Environment (MMA). So proper implementation arrangements within the (MMA) needed to be agreed before the signature of the UNDP ProDoc. Issue resolved and ProDoc was signed in 2013. Now, the project is progressing as planned | Since 2014, selection of buildings has been undertaken to initiate the energy savings assessment after chillers reconversion. Buildings were selected in the city of Brasilia. | 2005 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | BRA | REF | 57 | PRP | 289 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2013-01-01 | 80000 | -80000 | 0 | 0 |  | 0 | 0 | 0 | 6000 | -6000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the refrigeration manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing) | Individual | LAC | BRA | REF | 57 | PRP | 290 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2013-01-01 | 80000 | -80000 | 0 | 0 |  | 0 | 0 | 0 | 6000 | -6000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the air conditioning manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pe | 2009 |  | Investment
FIN | UNDP | Institutional strengthening support for the implementation of the Montreal Protocol | Individual | LAC | BRA | SEV | 10 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-03-01 | 1999-12-01 | 403100 | 0 | 403100 | 403100 | 100% | 0 | 0 | 0 | 52403 | 0 | 52403 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 11 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1994-11-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 17 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-07-01 |  | 1996-01-01 | 1997-12-01 | 75000 | -2 | 74998 | 74998 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-08-01 | 1997-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | BRA | SEV | 22 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | BRA | SEV | 23 | TAS | 85 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1999-05-01 |  | 2000-07-01 | 2009-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2000. Financially completed in 2009. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | BRA | SEV | 24 | INS | 100 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 2000-04-01 |  | 2000-11-01 | 2013-05-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Financially completed in 2013. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | LAC | BRA | SEV | 32 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2006-07-01 | 2009-07-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BRA | SEV | 43 | INS | 267 | N | I | No_ODP | 29 | 29 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2009-07-01 | 351000 | -76482 | 274518 | 274518 | 100% | 0 | 0 | 0 | 26325 | -5736 | 20588.85 | 0.15 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | BRA | SEV | 45 | TAS | 271 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517 | 14996.6661 | 0.3339 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | LAC | BRA | SEV | 52 | INS | 279 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-06-01 |  | 2010-12-01 | 2012-04-01 | 351000 | -49671 | 301329 | 301329 | 100% | 0 | 0 | 0 | 26325 | -3725 | 22599.6749 | 0.32505 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BRA | SEV | 60 | INS | 294 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2011-12-01 |  | 2013-05-01 | 2014-12-01 | 307125 | 0 | 307125 | 290484 | 94.58% | 16641 | 0 | 0 | 23034 | 0 | 21785.9453 | 1248.0547 | 0 | Financially completed in 2014. | Completed in 2013. Project operationally completed as expected against milestones. Final payments related to publications are to take place in 2014. | 2010 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | BRA | SEV | 66 | INS | 297 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2013-12-01 | 2016-04-01 |  |  | 351000 | 0 | 351000 | 136248 | 38.82% | 214752 | 0 | 85900.956 | 26325 | 0 | 10218.5708 | 16106.4292 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, a large awareness raising activity at country level was completed on HCFCs phase-out in December. The GOV is assessing pending payments to update financial figures and plan the submission of next Phase. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in June 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in June 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:A large consultancy procurement process was delayed since no bidders were found to participate. The TORs were reviewed and the bid re-launched. Company selected and the contract signed | Since 2014, the GOV has undertaken pending payments to update financial figures and plan the submission of theh next Phase. | 2012 |  | Non-Investment
FIN | UNDP | Phase out of CFC-113 at DMG used in medical equipment parts cleaning | Individual | LAC | BRA | SOL | 18 | INV | 36 | N | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1997-11-01 | 2000-12-01 | 38000 | -6 | 37994 | 37994 | 100% | 0 | 0 | 0 | 4940 | -1 | 4939.22 | -0.22 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-113 from the precision cleaning and drying process at Brasimet | Individual | LAC | BRA | SOL | 18 | INV | 37 | N | I | CFC | 1.6 | 1.6 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1996-11-01 |  | 1999-12-01 | 2000-09-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Project preparation for the formulation of CTC as a process agent | Individual | LAC | BRA | SOL | 42 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for solvent and process agent sectors | Individual | LAC | BRA | SOL | 48 | PRP | 276 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 50000 | -9426 | 40574 | 40574 | 100% | 0 | 0 | 0 | 3750 | -707 | 3043.05 | -0.05 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | LAC | BRA | SOL | 57 | PRP | 291 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2012-12-01 | 48000 | -48000 | 0 | 0 |  | 0 | 0 | 0 | 3600 | -3600 | 0 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | BRU | PHA | 66 | INV | 13 | N | I | HCFC | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2014-04-01 | 2016-01-01 |  |  | 52800 | 0 | 52800 | 30000 | 56.82% | 22800 | 22800 | 9120 | 4752 | 0 | 2700 | 2052 | 2052 | Remarks (Short narrative description of progress made (actual/planned)):In Jan and Dec 2014, the invitation bid was announced and one reclamation machine and 16 recovery machines had been procured. The delivery of equipment is planned in Jan 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2013. Missions undertaken (actual/planned):Planned in Feb 2015.. TOR for consultants/subcontracts completed (actual/planned):TOR for training consultant was being finalized in late 2014. Contract/PO/MOA agreements signed:Yes. In Jan and Dec 2014, the contract for R&R equipment had been awarded to the supplier. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | In late February 2015, a joint mission with UNEP, to participate in the R&R training and to prepare the 2nd tranche request was conducted. The 2nd tranche request was submitted to and approved at the 74th ExCom. | 2012 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | BRU | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
COM | UNDP | Implementation of the RMP: technical assistance for the refrigeration service and MAC sectors | RMP-Component | ASP | BRU | REF | 44 | TAS | 10 | N | I | CFC | 52.3 | 52.3 | 0 | 0 | 2004-12-01 | 2011-12-01 | 2007-05-01 |  | 2014-07-01 |  | 390000 | 0 | 390000 | 389447 | 99.86% | 553 | 0 | 442.376 | 29250 | 0 | 29208.5272 | 41.4728 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The last activity of Retrofit incentive programme ended in June 2013, thus the project is operationally closed. The NOU has been finalizing the PCR and financial reports for financial closure of the project. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in February 2009. Missions undertaken (actual/planned):Planned 1 and Actual 1 . TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in December 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The remaining balance of the fund will supplement the HPMP R&R procurement, which is the major milestone expected in 2014. The procurement is expected to be completed in Q2 of 2014 and then the project will be financially closed. | 2004 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | BZE | PHA | 50 | PRP | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2010-12-01 | 15000 | -1 | 14999 | 15000 | 100% | -1 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | BZE | PHA | 53 | INV | 20 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-09-01 | 2009-11-01 |  | 2009-11-01 | 2013-03-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 | 0 | 10980 | 0 | 10980 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-08-01 | 2013-03-01 | 72000 | -20 | 71980 | 71980 | 100% | 0 | 0 | 0 | 6480 | -2 | 6478.2 | -0.2 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-07-01 | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 5400 | 0 | 5400 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, some equipment (approx. 30%) has been delivered to final users. Capacitation and delivery of equipment are to be continued through 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in November 2011. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in April 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, additional equipment (approx. 45% cumulative) has been delivered to final users. | 2010 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | BZE | REF | 29 | TAS | 05 | A | I | CFC | 1.7 | 1.7 | 0 | 0 | 1999-11-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2003-09-01 | 61125 | 0 | 61125 | 61125 | 100% | 0 | 0 | 0 | 7946 | 0 | 7946.25 | -0.25 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment component) | Individual | LAC | BZE | REF | 42 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2007-06-01 | 20000 | -1164 | 18836 | 18836 | 100% | 0 | 0 | 0 | 1500 | -87 | 1412.6782 | 0.3218 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | LAC | BZE | REF | 44 | TAS | 12 | N | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2007-12-01 |  | 2006-12-01 | 2007-06-01 | 44879 | -211 | 44668 | 44668 | 100% | 0 | 0 | 0 | 4039 | -19 | 4020.11 | -0.11 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Investment
CLO | UNDP | Continuation of conversion to CFC-free technology in manufacturing of flexible polyurethane foam at Vita-Centrafrique | Individual | AFR | CAF | FOA | 19 | INV | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1997-05-01 |  |  | 2001-12-01 | 62000 | -30537 | 31463 | 31463 | 100% | 0 | 0 | 0 | 8060 | -3970 | 4090 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | CAF | REF | 20 | TAS | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-09-01 |  |  | 2001-12-01 | 66441 | -923 | 65518 | 65518 | 100% | 0 | 0 | 0 | 8637 | -120 | 8517.146 | -0.146 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | CAF | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | AFR | CBI | REF | 42 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | CBI | REF | 44 | TAS | 08 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2007-06-01 |  | 2010-12-01 | 2013-01-01 | 75400 | -1336 | 74064 | 74064 | 100% | 0 | 0 | 0 | 6786 | -120 | 6665.76 | 0.24 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | CHD | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CHD | PHA | 53 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2013-08-01 | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 | 0 | 8280 | 0 | 8280 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | INV | 20 | N | I | CFC | 5.2 | 5.2 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-08-01 | 82000 | -10982 | 71018 | 71018 | 100% | 0 | 0 | 0 | 7380 | -988 | 6391.62 | 0.38 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Preparation of a project in refrigerant recovery/recycling and RMP preparation | Individual | AFR | CHD | REF | 27 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | CHD | REF | 29 | TAS | 04 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 198252 | -36260 | 161992 | 161992 | 100% | 0 | 0 | 0 | 25773 | -4714 | 21058.96 | 0.04 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | CHD | REF | 29 | TAS | 07 | A | I | No_ODP | 1 | 1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-07-01 | 2005-10-01 | 15455 | -4669 | 10786 | 10786 | 100% | 0 | 0 | 0 | 2009 | -607 | 1402.15 | -0.15 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | CHD | REF | 37 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-07-01 |  | 2002-12-01 | 2005-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Incentive programme for commercial/industrial end-user sector | RMP-Component | AFR | CHD | REF | 38 | TAS | 09 | N | I | CFC | 6 | 6 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2010-12-01 | 2011-09-01 | 184416 | 0 | 184416 | 184416 | 100% | 0 | 0 | 0 | 23974 | 0 | 23974.08 | -0.08 | 0 | Completed in 2006. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Preparation of a project in the aerosol (sterilants) subsector | Individual | LAC | CHI | ARS | 30 | PRP | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Terminal umbrella project for phase-out of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | CHI | FOA | 48 | INV | 161 | N | I | CFC | 51.4 | 51.4 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-09-01 |  | 2010-12-01 | 2013-07-01 | 429962 | 0 | 429962 | 429962 | 100% | 0 | 0 | 0 | 32247 | 0 | 32247 | 0 | 0 | Financially completed in 2013. |  | 2006 | 2009-09-01 | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CHI | FOA | 57 | PRP | 167 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | -15796 | 34204 | 34204 | 100% | 0 | 0 | 0 | 3750 | -1185 | 2565.2999 | -0.29995 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | CHI | FOA | 73 | PRP | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 7000 | 0 | 0 | 7000 | 0 | Newly Approved | Inception workshop with participation of national stakeholders from the foam sector was conducted. International expert was hired; workplan prepared and discussed with local authorities. | 2014 |  | Non-Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project for soil fumigation in nurseries and seed beds for apples and kiwis | Individual | LAC | CHI | FUM | 24 | PRP | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 2000-07-01 | 2003-12-01 | 25000 | -11504 | 13496 | 13496 | 100% | 0 | 0 | 0 | 3250 | -1496 | 1754.48 | -0.48 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Demonstration and phase-out project for methyl bromide soil fumigation for fruit tree production and replant | One-off-Phaseout | LAC | CHI | FUM | 32 | INV | 143 | N | I | MeBr | 76.2 | 76.2 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2006-06-01 |  | 2007-12-01 | 2013-02-01 | 805000 | -454 | 804546 | 804546 | 100% | 0 | 0 | 0 | 98550 | -56 | 98494.4202 | -0.42022 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
COM | UNDP | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Individual | LAC | CHI | HAL | 51 | TAS | 164 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2010-01-01 | 2009-09-01 |  | 2014-03-01 |  | 60000 | 0 | 60000 | 58245 | 97.08% | 1755 | 0 | 1403.64 | 4500 | 0 | 4368.4087 | 131.5913 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The International expert delivered technical assistance to the countries and users of Halons in 2014. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Jan 2009. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in January 2010. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Identification of Int. Expert delayed due to problems in availability of candidates. Issues were solved and mission took place in 2013. Proper TA was given to the country and project was duly completed in 2014 | In 2014, the final report is being revised by NOU. | 2007 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CHI | PHA | 55 | PRP | 165 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2010-12-01 | 2014-05-01 | 150000 | -9 | 149991 | 149991 | 100% | 0 | 0 | 0 | 11250 | -1 | 11249.325 | -0.325 | 0 | Financially completed in 2014. |  | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | INV | 174 | N | I | HCFC | 5.7 | 4 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-01 | 2016-01-01 |  |  | 465566 | 0 | 465566 | 306035 | 65.73% | 159531 | 0 | 63812.348 | 34917 | 0 | 22952.3389 | 11964.6611 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Project activities were underway according to work plan. During 2014, training courses for customs officers and refrigeration technicians were conducted. 5 refrigerant identifiers were bought and delivered to National Customs Office. GRP manual was prepared by international expert, followed by a train-the-trainers seminar. Workshop on HCFC-141b alternatives for flushing was carried out with participation of international experts and suppliers. A workshop on HC-based refrigerants was conducted by an international expert. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Dec 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):4 of 4. Contract/PO/MOA agreements signed:4 of 8. First disbursement date (actual/planned):The first disbursement took place in December 2012. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delays in the proposal of alternatives for supermarket pilot. UNDP and NOU organized meeting and followed up with participant stakeholders. A consultant was hired to design selection scheme of proposal. | Selection scheme for participating supermarkets was prepared by local consultant and is in final revision by NOU. A mission was conducted to review workplan and discuss implementation of the project. 2 local experts participated in specialized training on natural alternatives to HCFC in Germany. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CHI | PHA | 71 | INV | 179 | N | I | HCFC | 6.6 | 0 | 0 | 0 | 2013-12-01 |  | 2015-06-01 | 2016-06-01 |  |  | 537357 | 0 | 537357 | 0 | 0% | 537357 | 0 | 214942.8 | 40302 | 0 | 0 | 40302 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Project activities were underway according to work plan. During 2014, training courses for customs officers and refrigeration technicians were conducted. 5 refrigerant identifiers were bought and delivered to National Customs Office. GRP manual was prepared by international expert, followed by a train-the-trainers seminar. Workshop on HCFC-141b alternatives for flushing was carried out with participation of international experts and suppliers. A workshop on HC-based refrigerants was conducted by an international expert. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Feb 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):4 of 4. Contract/PO/MOA agreements signed:4 of 8. First disbursement date (actual/planned):The first disbursement took place in April 2014. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delays in the proposal of alternatives for supermarket pilot. UNDP and NOU organized meeting and follow up with participant stakeholders. A consultant was hired to design sellection schemne of proposal. | Selection scheme for participating supermarkets was prepared by local consultant and is in final revision by NOU. A mission was conducted to review workplan and discuss implementation of the project. 2 local experts participated in specialized training on natural alternatives to HCFC in Germany. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | CHI | PHA | 73 | INV | 184 | N | I | HCFC | 0.3 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 295744 | 0 | 295744 | 0 | 0% | 295744 | 0 | 118297.6 | 22181 | 0 | 0 | 22181 | 0 | Newly Approved | Selection scheme for participating supermarkets was prepared by local consultant and is in final revision by NOU. A mission was conducted to review workplan and discuss implementation of the project. 2 local experts participated in specialized training on natural alternatives to HCFC in Germany. | 2014 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | CHI | PHA | 73 | PRP | 182 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3500 | 0 | 0 | 3500 | 0 | Newly Approved | Coordination meeting between local authorities and leading agency was carried out to establish workplan and schedule. Terms of reference for local expert were developed. | 2014 |  | Non-Investment
FIN | UNDP | Demonstration programme for service centre technicians on CFC-11 venting and leakage from refrigerators during operation and servicing | Individual | LAC | CHI | REF | 06 | DEM | 02 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for the formulation of commercial refrigeration project | Individual | LAC | CHI | REF | 42 | PRP | 155 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2005-04-01 |  | 2006-12-01 | 2012-04-01 | 32000 | -329 | 31671 | 31671 | 100% | 0 | 0 | 0 | 2400 | -25 | 2375.325 | -0.325 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2004 |  | Investment
FIN | UNDP | Terminal umbrella project for phase-out of the use of CFC-11, CFC-12 and R-502 (CFC-115) in the manufacture of refrigeration equipment | Individual | LAC | CHI | REF | 48 | INV | 160 | N | I | CFC | 21.7 | 21.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2009-04-01 |  | 2012-07-01 | 2014-07-01 | 282025 | -2652 | 279373 | 279373 | 100% | 0 | 0 | 0 | 21152 | -199 | 20953.1 | -0.1 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. No activities in 2013. | 2006 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | LAC | CHI | REF | 57 | PRP | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | -38366 | 11634 | 11634 | 100% | 0 | 0 | 0 | 3750 | -2877 | 872.55 | 0.44995 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Extension of institutional strengthening (phase VII) | Individual | LAC | CHI | SEV | 51 | INS | 163 | N | I | No_ODP | 15.4 | 15.4 | 0 | 0 | 2007-03-01 | 2007-04-01 | 2009-03-01 |  | 2009-07-01 | 2011-09-01 | 186550 | -372 | 186178 | 186178 | 100% | 0 | 0 | 0 | 13991 | -28 | 13963.1005 | -0.1005 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | LAC | CHI | SEV | 57 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-03-01 |  | 2011-09-01 | 2014-04-01 | 186550 | -17 | 186533 | 186533 | 100% | 0 | 0 | 0 | 13991 | -1 | 13989.73 | 0.27 | 0 | Financially completed in 2014. | NOU activily supporting the introduction of quota system for HCFCs. | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | LAC | CHI | SEV | 63 | INS | 176 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 |  | 2013-03-01 | 2014-10-01 | 186550 | 0 | 186550 | 186499 | 99.97% | 51 | 0 | 0 | 13991 | 0 | 13987.1751 | 3.8249 | 0 | Financially completed in 2014. | Project completed in 2013. The IS renewal request (phase X) was presented and approved. | 2011 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 4/2013-3/2015) | Individual | LAC | CHI | SEV | 69 | INS | 177 | N | I | non-HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2015-03-01 | 2015-03-01 |  |  | 186550 | 0 | 186550 | 121716 | 65.25% | 64834 | 0 | 25933.584 | 13058 | 0 | 8519.7966 | 4538.2034 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were underway. ODS consumption reports were prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Jul 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in August 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. | 2013 |  | Non-Investment
FIN | UNDP | Formulation of solvent sectoral phase-out plan | Individual | LAC | CHI | SOL | 39 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Technical assistance to phase-out ozone depleting solvents | Individual | LAC | CHI | SOL | 41 | TAS | 154 | N | I | CFC/TCA/CTC | 17.1 | 17.1 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-07-01 | 245690 | -15288 | 230402 | 230402 | 100% | 0 | 0 | 0 | 22112 | -1376 | 20736.0862 | -0.0862 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation in the sterilants sector | Individual | LAC | CHI | STE | 33 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | Individual | LAC | CHI | STE | 35 | INV | 151 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2005-12-01 | 2007-03-01 | 412741 | -113 | 412628 | 412628 | 100% | 0 | 0 | 0 | 53656 | -15 | 53641.6401 | -0.6401 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | COI | PHA | 52 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-07-01 | 2013-01-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 3870 | 0 | 3870 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | INV | 17 | N | I | CFC | 0.4 | 0.4 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2013-01-01 | 32000 | -720 | 31280 | 31280 | 100% | 0 | 0 | 0 | 2880 | -65 | 2815.2 | -0.2 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | LAC | COL | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-12-01 | 2011-11-01 | 30000 | -3478 | 26522 | 26522 | 100% | 0 | 0 | 0 | 2250 | -261 | 1989.15 | -0.15 | 0 | Completed in 2008. |  | 2008 |  | Investment
FIN | UNDP | Phase-out of CFC in the manufacturing of MDIs | Individual | LAC | COL | ARS | 56 | INV | 71 | N | I | CFC | 7.4 | 7.4 | 0 | 0 | 2008-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-09-01 | 2013-07-01 | 409359 | -6 | 409353 | 409353 | 100% | 0 | 0 | 0 | 30701 | 0 | 30700.997 | 0.003 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | COL | DES | 59 | PRP | 74 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2011-12-01 | 2012-08-01 | 40000 | -8674 | 31326 | 31326 | 100% | 0 | 0 | 0 | 3000 | -651 | 2349.45 | -0.45 | 0 | Financially completed in 2012. | Project finalized and submitted to the 66th Executive Committee Meeting. Final invoices pending. | 2009 |  | Investment
ONG | UNDP | Demonstration project on end of life ODS management and destruction | Individual | LAC | COL | DES | 66 | DEM | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-09-01 | 2015-04-01 | 2016-04-01 |  |  | 1195000 | 0 | 1195000 | 514843 | 43.08% | 680157 | 10052.6 | 272062.728 | 89625 | 0 | 38613.2385 | 51011.7615 | 753.945 | Remarks (Short narrative description of progress made (actual/planned)):One test burn was undertaken in Feb 2014 and results released by international laboratory on October 2014. Results were reviewed and protocols for 2nd test burn were under preparation by Dec 2014 Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Aug 2012. Missions undertaken (actual/planned):1 of 1 . TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:3 of 3. First disbursement date (actual/planned):The first disbursement took place in September 2012. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:First agreement with destruction facilities was revised due to legal process required by both parties. Agreements were signed in Jan 2014 (MOAs). Implementation schedule was adjusted and, now, the project is progressing as planned. | Since 2014, validation of the initial test burn (undertaken in Feb 2014) was completed and second test burn was scheduled for the second half of 2015. Testing protocols are being set by the implementation team and materials are being collected to be fed in this test burn. | 2012 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Manufacturas Ajover Ltda. | Individual | LAC | COL | FOA | 13 | INV | 09 | A | I | CFC | 190 | 190 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  | 1998-12-01 | 2001-12-01 | 691500 | -22425 | 669075 | 669075 | 100% | 0 | 0 | 0 | 89895 | -2915 | 86980 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
CLO | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Industria Nacional de Desechables (Inaldes) | Individual | LAC | COL | FOA | 13 | INV | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  |  | 2001-12-01 | 380500 | -373255 | 7245 | 7245 | 100% | 0 | 0 | 0 | 49465 | -48523 | 942 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1994 | 2000-03-01 | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | COL | FOA | 24 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-07-01 | 1998-12-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Manilit, S.A. | Individual | LAC | COL | FOA | 29 | INV | 36 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2004-01-01 | 62230 | -679 | 61551 | 61551 | 100% | 0 | 0 | 0 | 8090 | -88 | 8002 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Industrias Refridcol, Ltda. | Individual | LAC | COL | FOA | 29 | INV | 37 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-09-01 | 117450 | 0 | 117450 | 117450 | 100% | 0 | 0 | 0 | 15268 | 0 | 15268 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Dinalsa | Individual | LAC | COL | FOA | 29 | INV | 38 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78625 | 0 | 78625 | 78625 | 100% | 0 | 0 | 0 | 10221 | 0 | 10221 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | COL | FOA | 30 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at Olaflex with a technical assistance programme covering 10 small customers | Individual | LAC | COL | FOA | 32 | INV | 47 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2001-12-01 | 2003-10-01 | 191833 | 0 | 191833 | 191833 | 100% | 0 | 0 | 0 | 24938 | 0 | 24938.29 | -0.29 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion rom CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at 25 small enterprises centered around their systems house Espumlatex | Individual | LAC | COL | FOA | 32 | INV | 48 | A | I | CFC | 38.4 | 38.4 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2004-12-01 | 2004-12-01 | 332768 | 0 | 332768 | 332768 | 100% | 0 | 0 | 0 | 43260 | 0 | 43259.84 | 0.16 | 0 | Completed in 2004. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Retroactive funding for the conversion from CFC-11 to water-based technology in the manufacture of flexible molded and integral skin foam at Espumlatex-Promicolda | Individual | LAC | COL | FOA | 32 | INV | 49 | N | R | CFC | 11.5 | 11.5 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2001-05-01 | 2013-02-01 | 82020 | 0 | 82020 | 82020 | 100% | 0 | 0 | 0 | 4921 | 0 | 4921 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | COL | FOA | 33 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | COL | FOA | 36 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | COL | FOA | 38 | INV | 58 | A | I | CFC | 123.2 | 123.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-04-01 | 840170 | 0 | 840170 | 840170 | 100% | 0 | 0 | 0 | 102419 | 0 | 102418.7 | 0.3 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | COL | FOA | 57 | PRP | 72 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2010-03-01 |  | 2010-12-01 | 2012-05-01 | 150000 | -23033 | 126967 | 126967 | 100% | 0 | 0 | 0 | 11250 | -1727 | 9522.525 | 0.475 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Conversion plan from HCFCs to hydrocarbons in the production of polyurethane rigid insulation foam in the domestic refrigeration subsector (Mabe Colombia, Industrias Haceb, Challenger and Indusel S.A.) | Multi-year | LAC | COL | FOA | 60 | INV | 76 | N | I | HCFC | 56 | 56 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2013-04-01 |  | 2013-06-01 | 2014-01-01 | 5621483 | 0 | 5621483 | 5621226 | 100% | 257 | 0 | 0 | 421611 | 0 | 421591.737 | 19.263 | 0 | Financially Completed in 2014. | As planned, follow up to HCFC-free production and awareness activities among population promoting HCFC-free refrigerators are being conducted. | 2010 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | COL | FOA | 72 | PRP | 87 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-10-01 | 2016-05-01 | 2016-05-01 |  |  | 150000 | 0 | 150000 | 47891 | 31.93% | 102109 | 0 | 102108.57 | 10500 | 0 | 3352.4001 | 7147.5999 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included collecting information on foam sector end-users through system houses, visits to main users' facilities and preparation of draft project proposal documents. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in October 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in October 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | First draft of projects were prepared and presented to beneficiary companies and system houses. A workshop with stakeholders from the foam sector was conducted to present the newly approved guidelines. 2 follow up missions were conducted. |  |  | Non-Investment
FIN | UNDP | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 48 | INV | 66 | N | I | CTC | 2 | 2 | 0 | 0 | 2006-04-01 | 2009-01-01 | 2007-12-01 |  | 2012-05-01 | 2013-07-01 | 114480 | -1 | 114479 | 114479 | 100% | 0 | 0 | 0 | 10303 | 0 | 10303.0405 | -0.0405 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2006 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I and II) substances: first implementation programme | Multi-Year | LAC | COL | PHA | 41 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2008-12-01 | 2013-12-01 | 2146820 | 0 | 2146820 | 2146820 | 100% | 0 | 0 | 0 | 161011 | 0 | 161011 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I and II) substances: second implementation programme | Multi-Year | LAC | COL | PHA | 47 | INV | 63 | N | I | CFC | 805.9 | 805.9 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2011-12-01 | 2014-02-01 | 2353180 | -119 | 2353061 | 2353061 | 100% | 0 | 0 | 0 | 176488 | -9 | 176479.08 | -0.08 | 0 | Financially completed in 2014. | Final financial obligations being disbursed. | 2005 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COL | PHA | 55 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 173750 | -6850 | 166900 | 166900 | 100% | 0 | 0 | 0 | 13031 | -514 | 12517.2599 | -0.25985 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | INV | 77 | N | I | HCFC | 7.7 | 7.7 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2012-12-01 | 2013-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | COL | PHA | 66 | INV | 81 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2014-04-01 | 2015-01-01 |  |  | 550000 | 0 | 550000 | 501824 | 91.24% | 48176 | 0 | 19270.404 | 41250 | 0 | 37636.7992 | 3613.2007 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Most of the planned activities were carried out during 2014. The NOU continued with its activities related to training of refrigeration technicians on GRP (15 workshops and 433 trained technicians). 3 train-the-trainers workshops on GRP, HC and other natural refrigerants conducted. NOU has kept its work with end-users by organizing 12 seminar on HCFC alternatives. An awareness campaign accompanied all activities. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2 . Contract/PO/MOA agreements signed:18 of 18. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 4 workshops on good refrigeration practices conducted. 2 consultancies to standarize operation of reclaiming centers were initiated. 8 collection centers obtained their environmental license and operating in the R&R&R network. 2 follow up missions were conducted. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | COL | PHA | 72 | INV | 89 | N | I | HCFC | 2.9 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 60000 | 11250 | 0 | 0 | 11250 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The third tranche was approved in May 2014. In 2014, the ProDoc was developed and signed by the government and UNDP and the Action plan for 2015 was established. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 4 workshops on good refrigeration practices conducted. 2 consultancies to standarize operation of reclaiming centers were initiated. 8 collection centers obtained their environmental license and operating in the R&R&R network. 2 follow up missions were conducted. |  |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | COL | PHA | 72 | PRP | 86 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 | 2016-05-01 |  |  | 75000 | 0 | 75000 | 11073 | 14.76% | 63927 | 0 | 63927.25 | 5250 | 0 | 775.0925 | 4474.9075 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included the establishment of the project implementation team and the compilation of information from the HCFC consuming sector collected by other PRP projects. In addition, the NOU conducted a launching seminar with participation of main stakeholders. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in October 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in October 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Stategy prepared and discussed among stakeholders. First draft of projects were prepared and presented to beneficiary companies and interested parties. 2 follow up missions were conducted. |  |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Polarix Electrodomesticos, S.A. | Individual | LAC | COL | REF | 13 | INV | 04 | A | I | CFC | 63 | 63 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 844824 | -205206 | 639618 | 639618 | 100% | 0 | 0 | 0 | 109827 | -26677 | 83150.22 | -0.22 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Haceb, S.A. | Individual | LAC | COL | REF | 13 | INV | 05 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1386314 | -340578 | 1045736 | 1045736 | 100% | 0 | 0 | 0 | 180221 | -44275 | 135945.56 | 0.44 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Icasa, S.A. | Individual | LAC | COL | REF | 13 | INV | 06 | A | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1410680 | -358123 | 1052557 | 1052557 | 100% | 0 | 0 | 0 | 183388 | -46556 | 136832.41 | -0.41 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 to HFC-134a compresors at Compresores Andinos, S.A. | Individual | LAC | COL | REF | 13 | INV | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 313650 | -23379 | 290271 | 290271 | 100% | 0 | 0 | 0 | 40774 | -3039 | 37735.1 | -0.1 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Corporacion de Electrodomesticos, S.A. (Corelsa) | Individual | LAC | COL | REF | 13 | INV | 08 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1999-07-01 | 2000-12-01 | 853432 | -166101 | 687331 | 687331 | 100% | 0 | 0 | 0 | 110946 | -21593 | 89353.07 | -0.07 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industrias de Refrigeracion Comercial S.A. (Indufrial) | Individual | LAC | COL | REF | 15 | INV | 11 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-10-01 | 2000-12-01 | 442644 | -8866 | 433778 | 433778 | 100% | 0 | 0 | 0 | 57544 | -1153 | 56391.14 | -0.14 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Wonder S.A. | Individual | LAC | COL | REF | 15 | INV | 12 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-12-01 | 1999-12-01 | 251315 | 0 | 251315 | 251315 | 100% | 0 | 0 | 0 | 32671 | 0 | 32670.95 | 0.05 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrial Colombia S.A. (Inducol) | Individual | LAC | COL | REF | 15 | INV | 14 | A | I | CFC | 16 | 16 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2001-12-01 | 381548 | -36480 | 345068 | 345068 | 100% | 0 | 0 | 0 | 49601 | -4743 | 44858.5 | -0.5 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Friomix, S.A. | Individual | LAC | COL | REF | 17 | INV | 15 | A | D | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1999-01-01 | 1996-07-01 |  | 1999-02-01 | 2000-12-01 | 11146 | 0 | 11146 | 11146 | 100% | 0 | 0 | 0 | 1449 | 0 | 1448.98 | 0.02 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Westell Ltd. | Individual | LAC | COL | REF | 17 | INV | 16 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 227602 | -2 | 227600 | 227600 | 100% | 0 | 0 | 0 | 29588 | 0 | 29588.26 | -0.26 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COL | REF | 17 | TAS | 19 | N | I | CFC | 111 | 111 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-07-01 |  | 1999-07-01 | 2013-08-01 | 787030 | -5 | 787025 | 787025 | 100% | 0 | 0 | 0 | 102314 | -1 | 102313.0058 | -0.0058001 | 0 | Financially completed in 2013. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Unilemh Ltd. (Challenger) | Individual | LAC | COL | REF | 18 | INV | 21 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-07-01 | 155350 | -1561 | 153789 | 153789 | 100% | 0 | 0 | 0 | 20196 | -203 | 19992.57 | 0.43 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refrigeracion Supernordico Ltda. | Individual | LAC | COL | REF | 19 | INV | 22 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2004-01-01 | 162500 | -1243 | 161257 | 161257 | 100% | 0 | 0 | 0 | 21125 | -162 | 20963 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1996 |  | Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COL | REF | 32 | TAS | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2003-12-01 | 2005-10-01 | 40000 | -2578 | 37422 | 37422 | 100% | 0 | 0 | 0 | 5200 | -335 | 4864.86 | 0.13997 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 | 2003-01-01 | Non-Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | COL | REF | 36 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2004-06-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | COL | REF | 47 | DEM | 65 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2008-12-01 | 2016-03-01 |  |  | 1000000 | 0 | 1000000 | 733003 | 73.3% | 266997 | 12015.45 | 106798.868 | 75000 | 0 | 54975.2122 | 20024.7877 | 901.1587 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, Empresas Públicas de Medellín (EPM) achieved more progress with the implementation of the District Cooling project. Installation design was finalized and engineering project is now ongoing. Model financial mechanism for possible replacement of CFC-based chillers with district cooling has been designed; energy savings companies (ESCOs) and banks trained on financial mechanism. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Jan 2010. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in January 2010. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The participating company that will receive the District Cooling services took longer than expected to decide on agreeing with the Project. An International Expert was hired and a series of missions and technical assistance were delivered to clarify technical issues and to reach an agreement for the project implementation. | Designs for the cooling district were finished, company to built electromechnical component selected and started acquisition of parts. First contract of the district cooling was signed (with Gobernación de Antioquia). Technical assistance with stakeholders to improve their air coneditioning systems (in their buildings) has been given. 2 follow up missions were conducted. | 2005 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (commercial and industrial air-conditioning manufacturing sector) | Individual | LAC | COL | REF | 72 | PRP | 84 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 | 2016-05-01 |  |  | 25000 | 0 | 25000 | 2453 | 9.812% | 22547 | 0 | 22547.04 | 1750 | 0 | 171.7072 | 1578.2928 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included collecting information on air conditioning sector manufacturers, visits to main users facilities and preparation of draft project proposal documents. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in October 2014.. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1 . Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):November 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Stategy prepared and discussed among stakeholders. First draft of projects were prepared and presented to beneficiary companies and interested parties. 2 follow up missions were conducted. |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (commercial refrigeration manufacturing sector) | Individual | LAC | COL | REF | 72 | PRP | 88 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 | 2016-05-01 |  |  | 25000 | 0 | 25000 | 1248 | 4.992% | 23752 | 0 | 23752.46 | 1750 | 0 | 87.3278 | 1662.6722 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included collecting information on refrigeration sector manufacturers, and the development of an action plan document for project preparation. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in October 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):December 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | First draft of projects were prepared and presented to beneficiary companies and interested parties. 2 follow up missions were conducted. |  |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COL | SEV | 12 | CPG | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-03-01 |  | 1994-03-01 | 1994-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1994. Financially Completed in 1994. |  | 1994 |  | Non-Investment
FIN | UNDP | Institutional strengthening for implementation of the Montreal Protocol in Colombia | Individual | LAC | COL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1997-03-01 |  | 1998-03-01 | 1999-12-01 | 317790 | 0 | 317790 | 317790 | 100% | 0 | 0 | 0 | 41313 | 0 | 41312.7 | 0.3 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 12 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 17 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-04-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 18 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | COL | SEV | 24 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 2000-03-01 |  | 2000-03-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2000. Financially completed in 2007. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening: Phase 3 | Individual | LAC | COL | SEV | 30 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2002-04-01 |  | 2003-05-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | LAC | COL | SEV | 36 | CPG | 56 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-10-01 |  | 2004-06-01 | 2005-11-01 | 30000 | -415 | 29585 | 29585 | 100% | 0 | 0 | 0 | 3900 | -54 | 3846 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening (phase 4) | Individual | LAC | COL | SEV | 38 | INS | 59 | N | I | No_ODP | 22.8 | 22.8 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 275600 | -4 | 275596 | 275596 | 100% | 0 | 0 | 0 | 35828 | 0 | 35827.48 | 0.52 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | COL | SEV | 45 | INS | 61 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-12-01 | 2010-10-01 | 275600 | -14 | 275586 | 275586 | 100% | 0 | 0 | 0 | 20670 | -1 | 20668.95 | 0.05 | 0 | Financially completed in 2010. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | COL | SEV | 45 | TAS | 62 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924 | 5268.5548 | 0.4452 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COL | SEV | 52 | INS | 67 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-10-01 |  | 2010-08-01 | 2011-10-01 | 275600 | -317 | 275283 | 275283 | 100% | 0 | 0 | 0 | 20670 | -24 | 20646.225 | -0.225 | 0 | Completed. See report on IS Colombia in COL/SEV/52/INS/73. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COL | SEV | 58 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-10-01 |  | 2011-12-01 | 2013-07-01 | 160767 | 114820 | 275587 | 275587 | 100% | 0 | 0 | 0 | 12058 | 8611 | 20669.0249 | -0.02495 | 0 | Financially completed in 2013. | The NOU plays an active role in the implementation of MLF funded projects in Colombia. The NOU is in the process of establishing the qoutas for HCFCs for 2013 and include supporting legislation for HCFC phase out. Final invoices pending. | 2009 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII: 11/2011-10/2013) | Individual | LAC | COL | SEV | 64 | INS | 79 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-10-01 |  | 2013-12-01 | 2014-07-01 | 275600 | 0 | 275600 | 275600 | 100% | 0 | 0 | 0 | 20670 | 0 | 20670 | 0 | 0 | Financially completed in 2014. | The 2014 workplan and budget prepared and approved. As planned, the HCFC quotas for 2014 have been established. All pending payments were made. | 2011 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 11/2013-10/2015) | Individual | LAC | COL | SEV | 70 | INS | 83 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2015-10-01 | 2015-10-01 |  |  | 275600 | 0 | 275600 | 93233 | 33.83% | 182367 | 0 | 72946.784 | 19292 | 0 | 6526.3128 | 12765.6872 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were underway, all planned activities were conducted. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. NOU participated actively in all regional and ExCom meetings. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Oct 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):December 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 2 follow up missions were conducted. | 2013 |  | Non-Investment
FIN | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 08 | TRA | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100% | 0 | 0 | 0 | 2746 | 0 | 2745.6 | 0.4 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100% | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100% | 0 | 0 | 0 | 25155 | -15 | 25139.79 | 0.21 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | COS | FUM | 33 | PRP | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | Multi-Year | LAC | COS | FUM | 35 | INV | 25 | N | I | MeBr | 84.4 | 84.4 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2002-12-01 |  | 2005-07-01 | 2013-05-01 | 1211321 | 0 | 1211321 | 1211321 | 100% | 0 | 0 | 0 | 143245 | 0 | 143245.3 | -0.3 | 0 | Financially completed in 2013. |  | 2001 | 2004-07-01 | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranches II and III) | Multi-Year | LAC | COS | FUM | 43 | INV | 33 | N | I | MeBr | 130.8 | 130.8 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2013-02-01 | 1938114 | 0 | 1938114 | 1938114 | 100% | 0 | 0 | 0 | 145359 | 0 | 145359 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche IV) | Multi-Year | LAC | COS | FUM | 49 | INV | 36 | N | I | MeBr | 63.6 | 63.6 | 0 | 0 | 2006-07-01 | 2008-01-01 | 2008-12-01 |  | 2009-12-01 | 2013-12-01 | 969057 | 0 | 969057 | 969057 | 100% | 0 | 0 | 0 | 72679 | 0 | 72679 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche V) | Multi-Year | LAC | COS | FUM | 59 | INV | 43 | N | I | MeBr | 174 | 174 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2013-11-01 |  | 2014-06-01 |  | 726791 | 0 | 726791 | 725204 | 99.78% | 1587 | 0 | 1269.304 | 54509 | 0 | 54390.0035 | 118.9965 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, technical assistance was provided to Melon growers to assure zero use of MB. This was the first harvest with no use of MB. Trouble shooting was needed in several cases. The project is considered successfully completed as the result is expected to be sustained. The government has introduced a ban on the use of MB in agriculture in Costa Rica. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Apr 2010. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in April 2010. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Follow up activities with farmers to maintain zero consumption of MB were continued. Technical assistance is provided in areas where farmers have encountered challenges with the alternatives. | 2009 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | COS | PHA | 48 | PRP | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-07-01 | 2010-07-01 | 30000 | -2379 | 27621 | 27621 | 100% | 0 | 0 | 0 | 2250 | -178 | 2071.575 | 0.425 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | COS | PHA | 52 | INV | 37 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2008-12-01 | 2013-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-year | LAC | COS | PHA | 55 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-08-01 | 2013-05-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COS | PHA | 55 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-10-01 | 2014-04-01 | 150000 | -1958 | 148042 | 148042 | 100% | 0 | 0 | 0 | 11250 | -147 | 11103.15 | -0.15 | 0 | Financially completed in 2014. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting Some final invoices pending. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (third tranche) | Multi-Year | LAC | COS | PHA | 58 | INV | 42 | N | I | CFC | 37.5 | 37.5 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-12-01 | 2013-05-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 | 0 | 12375 | 0 | 12375 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 45 | N | I | HCFC | 14 | 14 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2014-03-01 | 593523 | 0 | 593523 | 593522 | 100% | 1 | 0 | 0 | 44514 | 0 | 44513.85 | 0.15 | 0 | Financially Completed in 2014. | Completed in 2013. PCR is being finalized. HOPs are being finalized | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2014-06-01 |  | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 12600 | 0 | 12600 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, a visit from an expert of SENA to Costa Rica to develop Curriculum for training schools was planned and executed. Train the trainers with SENA specialist in October with the participation of 17 trainers from INA in Costa Rica was implemented. An agreement with an institute to develop speciality course of Commercial and Industrial refrigeration and AC was finalized. An agreement with SENAI from Brazil on south-south collaboration was finalized. INA visted SENAI in Brazil and training of technicians in INA was implemented. This tranche can be operationally completed. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Feb 2012. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in April 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | HPMP activities continue to be implemented. An agreement was made with SENAI in Brazil to provide south-south collaboration between training schools. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | COS | PHA | 70 | INV | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-09-01 | 2015-07-01 | 2016-01-01 |  |  | 168000 | 0 | 168000 | 32832 | 19.54% | 135168 | 0 | 54067.26 | 12600 | 0 | 2462.3888 | 10137.6112 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, a visit from an expert of SENA to Costa Rica to develop Curriculum for training schools was planned and executed. Train the trainers with SENA specialist in October with the participation of 17 trainers from INA in Costa Rica was implemented. An agreement with an institute to develop speciality course of Commercial and Industrial refrigeration and AC was finalized. An agreement with SENAI from Brazil on south-south collaboration was finalized. INA visted SENAI in Brazil and training of technicians in INA was implemented. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Sept 2013. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in September 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 2015 action plan is under implementation. Third tranche request prepared and submitted. Training of custom users on online system continues. Implementation of agreement between INA and SENAI for training refrigeration and AA technicans is underway. 1 follow up mission was conducted. | 2013 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COS | REF | 08 | TAS | 04 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1992-10-01 | 1997-01-01 | 1998-09-01 |  | 2000-06-01 | 2004-03-01 | 88000 | 233693 | 321693 | 321693 | 100% | 0 | 0 | 0 | 11440 | 30380 | 41820.09 | -0.09 | 0 | Completed in 2000. Financially completed in 2004. |  | 1992 | 1999-08-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Atlas Eléctrica S.A. | Individual | LAC | COS | REF | 18 | INV | 08 | A | D | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-04-01 |  | 1998-05-01 | 1999-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration subsector | Individual | LAC | COS | REF | 24 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Omega, S.A. | Individual | LAC | COS | REF | 27 | INV | 17 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 159883 | 0 | 159883 | 159883 | 100% | 0 | 0 | 0 | 20785 | 0 | 20784.79 | 0.21 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Wimmer Hnos., S.A. | Individual | LAC | COS | REF | 27 | INV | 18 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 186217 | 0 | 186217 | 186217 | 100% | 0 | 0 | 0 | 24208 | 0 | 24208.21 | -0.21 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Hermanos González, S.A. | Individual | LAC | COS | REF | 27 | INV | 19 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-04-01 | 185168 | 0 | 185168 | 185168 | 100% | 0 | 0 | 0 | 24072 | 0 | 24071.93 | 0.07 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
CLO | UNDP | Phaseout of CFC-11and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Quena S.A. | Individual | LAC | COS | REF | 27 | INV | 20 | A | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  |  | 2002-11-01 | 219430 | -111322 | 108108 | 108108 | 100% | 0 | 0 | 0 | 28526 | -14472 | 14054.04 | -0.04 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COS | REF | 32 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2005-12-01 | 2010-10-01 | 40000 | -14642 | 25358 | 25358 | 100% | 0 | 0 | 0 | 5200 | -1904 | 3296.54 | -0.54 | 0 | Financially completed in 2010. |  | 2000 | 2003-01-01 | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial, industrial, and fishing fleet refrigeration end-user sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 27 | N | I | CFC | 67.5 | 67.5 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 200000 | -1012 | 198988 | 198988 | 100% | 0 | 0 | 0 | 18000 | -91 | 17908.92 | 0.08 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 28 | N | I | CFC | 60.8 | 60.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 180000 | -517 | 179483 | 179483 | 100% | 0 | 0 | 0 | 16200 | -47 | 16153.47 | -0.47 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: ensuring the effectiveness of all the project proposed with the RMP project | RMP-Component | LAC | COS | REF | 41 | TAS | 31 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 60000 | -2686 | 57314 | 57314 | 100% | 0 | 0 | 0 | 5400 | -242 | 5158.26 | -0.26 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for certification and licensing of refrigeration technicians | RMP-Component | LAC | COS | REF | 41 | TRA | 29 | N | I | CFC | 33.8 | 33.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 100000 | -797 | 99203 | 99203 | 100% | 0 | 0 | 0 | 9000 | -72 | 8928.27 | -0.27 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for training of customs officers | RMP-Component | LAC | COS | REF | 41 | TRA | 30 | N | I | CFC | 30.4 | 30.4 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-07-01 | 90000 | -1004 | 88996 | 88996 | 100% | 0 | 0 | 0 | 8100 | -90 | 8009.64 | 0.36 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | COS | REF | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 | 2017-01-01 |  |  | 60000 | 0 | 60000 | 25791 | 42.98% | 34209 | 0 | 34209 | 4500 | 0 | 1934.325 | 2565.675 | 0 | Remarks (Short narrative description of progress made (actual/planned)):No activities planned for 2014. The Foam Sector plan will be prepared simultaneously with the reconversion of System Houses in Colombia and other countries that are supplying Costa Rica with preblended poliols containing 141b. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2009. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):The first disbursement took place in April 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Discussion of alteranatives between NOU and international consultant have been carried out. Information requirements have been established and information is being updated. | 2009 |  | Investment
FIN | UNDP | ODS reconnaissance study | Individual | LAC | COS | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 20000 | 3422 | 23422 | 23422 | 100% | 0 | 0 | 0 | 2600 | 445 | 3044.86 | 0.14 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COS | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1992-09-01 |  | 1992-09-01 | 1997-12-01 | 20000 | 2909 | 22909 | 22909 | 100% | 0 | 0 | 0 | 2600 | 378 | 2978.17 | -0.17 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | COS | SEV | 08 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-08-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 213160 | 0 | 213160 | 213160 | 100% | 0 | 0 | 0 | 27711 | 0 | 27710.8 | 0.2 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Assistance in project preparation | Individual | LAC | COS | SEV | 08 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-05-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase II) | Individual | LAC | COS | SEV | 21 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1999-02-01 |  | 1999-02-01 | 2000-12-01 | 108087 | 0 | 108087 | 108087 | 100% | 0 | 0 | 0 | 14051 | 0 | 14051.31 | -0.31 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | LAC | COS | SEV | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-04-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol (Phase III) | Individual | LAC | COS | SEV | 27 | INS | 16 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-04-01 |  | 2001-12-01 | 2005-11-01 | 108087 | -2519 | 105568 | 105568 | 100% | 0 | 0 | 0 | 14051 | -327 | 13723.8472 | 0.1528 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | COS | SEV | 35 | INS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2004-12-01 | 2007-06-01 | 108087 | -3863 | 104224 | 104224 | 100% | 0 | 0 | 0 | 14051 | -502 | 13549.0843 | -0.0843 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | COS | SEV | 41 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 140513 | -776 | 139737 | 139737 | 100% | 0 | 0 | 0 | 10538 | -58 | 10479.8026 | 0.1974 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COS | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2008-12-01 |  | 2008-02-01 | 2009-07-01 | 140513 | -2445 | 138068 | 138068 | 100% | 0 | 0 | 0 | 10538 | -183 | 10354.6333 | 0.3667 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COS | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-09-01 | 2011-08-01 | 140513 | -12596 | 127917 | 127917 | 100% | 0 | 0 | 0 | 10538 | -945 | 9593.3426 | -0.34255 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | LAC | COS | SEV | 59 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2011-12-01 | 2014-02-01 | 70257 | 70245 | 140502 | 140502 | 100% | 0 | 0 | 0 | 5269 | 5268 | 10537.1 | -0.1 | 0 | Financially completed in 2014. | Final invoices pending. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | COS | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-12-01 |  | 2014-04-01 |  | 140513 | 0 | 140513 | 140513 | 100% | 0 | 0 | 0 | 10538 | 0 | 10538 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the monitoring and control of import licenses and quotas of HCFCs occurred. Timely reporting to the OS and MLFS. Continous awareness raising activities in Costa Rica including the celebration of International Ozone day. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in June 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, 2013 data is being revised. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | LAC | COS | SEV | 71 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-03-01 | 2015-12-01 | 2016-02-01 |  |  | 140513 | 0 | 140513 | 46755 | 33.27% | 93758 | 0 | 37503.312 | 9836 | 0 | 3272.8603 | 6563.1397 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the monitoring and control of import licenses and quotas of HCFCs occurred. Timely reporting to the OS and MLFS. Continous awareness raising activities in Costa Rica including the celebration of International Ozone day. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in March 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in March 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 1 follow up mission was conducted. | 2013 |  | Non-Investment
FIN | UNDP | Seminar/workshop in the solvent sector | Individual | LAC | COS | SOL | 08 | TRA | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | -3219 | 17901 | 17901 | 100% | 0 | 0 | 0 | 2746 | -418 | 2327.13 | 0.87 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for Guandong aerosols investment project and investigation of non-ODS filling technology and LPG purification | Individual | ASP | CPR | ARS | 06 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1996-12-01 | 1998-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100% | 0 | 0 | 0 | 8450 | -648 | 7802.47 | -0.47 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in rigid polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for the Beijing Household Electric Appliances Research Institute (Bheari) | Individual | ASP | CPR | FOA | 09 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-10-01 | 1995-06-01 |  | 1998-10-01 | 2003-07-01 | 0 | 444945 | 444945 | 444945 | 100% | 0 | 0 | 0 | 0 | 57843 | 57843 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Tianjin conversion to CFC-free technology in the manufacture of flexible polyurethane foam | Individual | ASP | CPR | FOA | 10 | INV | 32 | N | I | CFC | 180 | 180 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1994-09-01 |  | 1995-04-01 | 1998-12-01 | 1080000 | -41407 | 1038593 | 1038593 | 100% | 0 | 0 | 0 | 140400 | -5383 | 135017 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | CPR | FOA | 10 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-05-01 | 1994-06-01 |  | 1997-07-01 | 2000-06-01 | 200000 | -574 | 199426 | 199426 | 100% | 0 | 0 | 0 | 26000 | -75 | 25925 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of rigid PUF (spray) at Beijing Commercial Machinery Factory (BCMF) | Individual | ASP | CPR | FOA | 11 | INV | 54 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1998-12-01 | 2000-12-01 | 435000 | -91690 | 343310 | 343310 | 100% | 0 | 0 | 0 | 56550 | -11920 | 44630.3 | -0.3 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Investment
CLO | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Yanfeng | Individual | ASP | CPR | FOA | 13 | INV | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1995-07-01 |  |  | 1995-07-01 | 670000 | -670000 | 0 | 0 |  | 0 | 0 | 0 | 87100 | -87100 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 used in the manufacture of EPE foam sheet at Danshui Huaya Plastics Industries Co. Ltd. | Individual | ASP | CPR | FOA | 13 | INV | 73 | A | R | CFC | 160 | 160 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1995-04-01 | 1997-12-01 | 241000 | 0 | 241000 | 241000 | 100% | 0 | 0 | 0 | 31330 | 0 | 31330 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 used in the manufacture of rigid polyurethane foam at Tianjin Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 13 | INV | 74 | N | I | CFC | 130 | 130 | 0 | 0 | 1994-07-01 | 1998-11-01 | 1995-07-01 |  | 2001-08-01 | 2003-07-01 | 690000 | -431333 | 258667 | 258667 | 100% | 0 | 0 | 0 | 89700 | -56073 | 33627 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guizhou Jinchang Plastics Products Co. Ltd. | Individual | ASP | CPR | FOA | 15 | INV | 100 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 390000 | -117155 | 272845 | 272845 | 100% | 0 | 0 | 0 | 50700 | -15230 | 35470 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Hailun Plastic Packaging Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 101 | A | I | CFC | 95 | 95 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 321000 | -2 | 320998 | 320998 | 100% | 0 | 0 | 0 | 41730 | 0 | 41729.74 | 0.26 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE/PS foam sheet at Shanghai Jianhua Electro-Mechanical and Mechanical Company | Individual | ASP | CPR | FOA | 15 | INV | 102 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-11-01 | 2002-04-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Foshan No. 3 Plastic Factory | Individual | ASP | CPR | FOA | 15 | INV | 103 | A | I | CFC | 360 | 360 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 1065000 | -1 | 1064999 | 1064999 | 100% | 0 | 0 | 0 | 138450 | 0 | 138449.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shijiazhuang Plastic Cement General Factory | Individual | ASP | CPR | FOA | 15 | INV | 87 | A | I | CFC | 160 | 160 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 621000 | 0 | 621000 | 621000 | 100% | 0 | 0 | 0 | 80730 | 0 | 80730 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE foam tubing at Suzhou Plastic Works No. 7 | Individual | ASP | CPR | FOA | 15 | INV | 88 | A | I | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 358000 | -36690 | 321310 | 321310 | 100% | 0 | 0 | 0 | 46540 | -4770 | 41770.3 | -0.3 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Sino-Foreign Joint Stock Shenyang Shenrong Co. | Individual | ASP | CPR | FOA | 15 | INV | 89 | A | I | CFC | 48 | 48 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-05-01 | 2002-04-01 | 166700 | -1 | 166699 | 166699 | 100% | 0 | 0 | 0 | 21671 | 0 | 21670.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE foam sheet and netting at Feicheng Plastic Products Factory | Individual | ASP | CPR | FOA | 15 | INV | 90 | A | I | CFC | 150 | 150 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-04-01 | 2002-04-01 | 388000 | 0 | 388000 | 388000 | 100% | 0 | 0 | 0 | 50440 | 0 | 50440 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guangxing Plastics Products Co., Hubei | Individual | ASP | CPR | FOA | 15 | INV | 91 | A | I | CFC | 36 | 36 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shenzhen Shentie Plastics Tableware Products Company, Shenzhen | Individual | ASP | CPR | FOA | 15 | INV | 92 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 345000 | 0 | 345000 | 345000 | 100% | 0 | 0 | 0 | 44850 | 0 | 44850 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE netting at Hebei Sixing Polypack Products Co. Ltd., Shijiazhuang | Individual | ASP | CPR | FOA | 15 | INV | 93 | A | I | CFC | 65 | 65 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 436000 | -183121 | 252879 | 252879 | 100% | 0 | 0 | 0 | 56680 | -23806 | 32874.27 | -0.27 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Beijing Yanxi | Individual | ASP | CPR | FOA | 15 | INV | 94 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 125000 | -31250 | 93750 | 93750 | 100% | 0 | 0 | 0 | 16250 | -4063 | 12187.5 | -0.5 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Faw-Trim | Individual | ASP | CPR | FOA | 15 | INV | 95 | A | I | CFC | 28 | 28 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of integral skin polyurethane foam at Hubei Auto Engineering | Individual | ASP | CPR | FOA | 15 | INV | 96 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Dalian No. 1 | Individual | ASP | CPR | FOA | 15 | INV | 97 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1998-12-01 |  |  | 2000-07-01 | 490000 | -457910 | 32090 | 32090 | 100% | 0 | 0 | 0 | 63700 | -59528 | 4172 | 0 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinfeng | Individual | ASP | CPR | FOA | 15 | INV | 98 | A | R | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 235340 | 0 | 235340 | 235340 | 100% | 0 | 0 | 0 | 30594 | 0 | 30594.2 | -0.2 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinan | Individual | ASP | CPR | FOA | 15 | INV | 99 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 337000 | 0 | 337000 | 337000 | 100% | 0 | 0 | 0 | 43810 | 0 | 43810 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Cangzhou Foreign Trade Packaging Co. | Individual | ASP | CPR | FOA | 17 | INV | 125 | N | I | CFC | 75 | 75 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 450800 | -445 | 450355 | 450355 | 100% | 0 | 0 | 0 | 58604 | -58 | 58546.15 | -0.15 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Handan No. 7 | Individual | ASP | CPR | FOA | 17 | INV | 126 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 400950 | -446 | 400504 | 400504 | 100% | 0 | 0 | 0 | 52124 | -58 | 52065.52 | 0.48 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Joint Industrial Plastic Corporation, Buotou | Individual | ASP | CPR | FOA | 17 | INV | 127 | N | I | CFC | 90 | 90 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2001-05-01 | 604450 | -446 | 604004 | 604004 | 100% | 0 | 0 | 0 | 78579 | -58 | 78520.52 | 0.48 | 0 | Completed in 2000. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane products at Daimei | Individual | ASP | CPR | FOA | 17 | INV | 134 | N | I | CFC | 77 | 77 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-12-01 |  | 1998-12-01 | 2001-12-01 | 362600 | -43425 | 319175 | 319175 | 100% | 0 | 0 | 0 | 47138 | -5644 | 41493.63 | 0.37 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Tianjin Daqui Foam Plant | Individual | ASP | CPR | FOA | 18 | INV | 141 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 160000 | -60 | 159940 | 159940 | 100% | 0 | 0 | 0 | 20800 | -8 | 20792.2 | -0.2 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin and cold cured PUF moldings at Jiangxi Auto Engineering Plastic Plant | Individual | ASP | CPR | FOA | 18 | INV | 142 | N | I | CFC | 39 | 39 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 2001-03-01 | 2003-07-01 | 170000 | -6784 | 163216 | 163216 | 100% | 0 | 0 | 0 | 22100 | -882 | 21218.08 | -0.08 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Tianjin Gangda | Individual | ASP | CPR | FOA | 18 | INV | 143 | N | I | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1997-05-01 |  | 2000-10-01 | 2003-07-01 | 404250 | -1033 | 403217 | 403217 | 100% | 0 | 0 | 0 | 52553 | -134 | 52418.21 | 0.79 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Jiangsu Jintan Insulation Material Plant | Individual | ASP | CPR | FOA | 19 | INV | 161 | N | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 66000 | -5638 | 60362 | 60362 | 100% | 0 | 0 | 0 | 8580 | -733 | 7847.06 | -0.06 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhejiang Wanpeng Clique Co., Ltd. | Individual | ASP | CPR | FOA | 22 | INV | 202 | N | I | CFC | 120 | 120 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 412666 | -10472 | 402194 | 402194 | 100% | 0 | 0 | 0 | 53647 | -1362 | 52284.8172 | 0.1828 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhoushan Fuchuan Plastic Products Factory | Individual | ASP | CPR | FOA | 22 | INV | 206 | N | I | CFC | 61 | 61 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 403711 | -9045 | 394666 | 394666 | 100% | 0 | 0 | 0 | 52482 | -1175 | 51306.9349 | 0.0651 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels, pipes and spray foams at Baoding Oil Depot & Storage Engineering Company | Individual | ASP | CPR | FOA | 23 | INV | 228 | N | I | CFC | 75.5 | 75.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-09-01 | 400960 | -34986 | 365974 | 365974 | 100% | 0 | 0 | 0 | 52125 | -4548 | 47576.5996 | 0.4004 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid and spray polyurethane foams at Xinjiang Tianye Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 229 | N | I | CFC | 92.3 | 92.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 2001-01-01 | 2004-01-01 | 300620 | -15937 | 284683 | 284683 | 100% | 0 | 0 | 0 | 39081 | -2072 | 37008.6 | 0.4 | 0 | Completed in 2001. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels at Luoyang Refrigeration Machinery Factory | Individual | ASP | CPR | FOA | 23 | INV | 236 | N | I | CFC | 117.8 | 117.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-01-01 | 2003-07-01 | 698595 | -41580 | 657015 | 657015 | 100% | 0 | 0 | 0 | 90817 | -5405 | 85411.95 | 0.05 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of heating pipes at Jixi City Thermal Power Company | Individual | ASP | CPR | FOA | 24 | INV | 245 | N | I | CFC | 86 | 86 | 0 | 0 | 1998-03-01 | 2000-12-01 | 2000-04-01 |  | 2003-12-01 | 2008-10-01 | 673380 | -3133 | 670247 | 670247 | 100% | 0 | 0 | 0 | 87539 | -407 | 87132.1119 | -0.1119 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 10 projects in the rigid and integral skin foam sub-sectors | Individual | ASP | CPR | FOA | 24 | PRP | 241 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology int he manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Co. Plastics Factory | Individual | ASP | CPR | FOA | 25 | INV | 247 | N | I | CFC | 81 | 81 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2000-08-01 |  | 2003-05-01 | 2005-02-01 | 504630 | -4472 | 500158 | 500158 | 100% | 0 | 0 | 0 | 65602 | -581 | 65020.9 | 0.1 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride and forced cooling system in the manufacture of flexible polyurethane foam (slabstock) at Cangzhou New-Type Foam Decoration Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 250 | N | I | CFC | 67 | 67 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2001-05-01 | 2003-09-01 | 417410 | -17009 | 400401 | 400401 | 100% | 0 | 0 | 0 | 54263 | -2211 | 52052.01 | -0.01 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Victory Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 25 | INV | 254 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-07-01 | 2001-11-01 | 2000-08-01 |  | 2003-11-01 | 2008-10-01 | 563760 | -273 | 563487 | 563487 | 100% | 0 | 0 | 0 | 73289 | -35 | 73253.3099 | 0.6901 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of PU-insulated heating pipes at Tianjin Pipeline Engineering Group Co. Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 257 | N | I | CFC | 80 | 80 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-09-01 | 2005-03-01 | 626400 | -346 | 626054 | 626054 | 100% | 0 | 0 | 0 | 78904 | -44 | 78860 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Guangdong Commercial Refrigeration Equipment Co. (GCREC) | Individual | ASP | CPR | FOA | 26 | INV | 258 | N | I | CFC | 60.3 | 60.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-10-01 | 2003-07-01 | 472150 | -18041 | 454109 | 454109 | 100% | 0 | 0 | 0 | 61380 | -2345 | 59034.13 | 0.87 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Kaifeng Air Separation Group Ltd. (KFAS) | Individual | ASP | CPR | FOA | 26 | INV | 260 | N | I | CFC | 68.2 | 68.2 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-04-01 | 2001-11-01 | 534090 | -14357 | 519733 | 519733 | 100% | 0 | 0 | 0 | 68750 | -1579 | 67170.52 | 0.48 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and pour-in-place polyurethane foams at Corrosionproof and Insulation Co., Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 263 | N | I | CFC | 99.1 | 99.1 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-04-01 | 2004-01-01 | 776110 | -13913 | 762197 | 762197 | 100% | 0 | 0 | 0 | 95372 | -1530 | 93842.1 | -0.1 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion of refrigerator manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane foam blowing agent in the production of PU insulation panels | Individual | ASP | CPR | FOA | 26 | INV | 264 | N | I | CFC | 120.5 | 120.5 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-09-01 | 2005-02-01 | 617860 | -4968 | 612892 | 612892 | 100% | 0 | 0 | 0 | 77965 | -627 | 77337.6 | 0.4 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and spray polyurethane foams at Daqing Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 26 | INV | 265 | N | I | CFC | 167.8 | 167.8 | 0 | 0 | 1998-11-01 | 2001-11-01 | 2001-06-01 |  | 2003-11-01 | 2009-01-01 | 1124560 | -618 | 1123942 | 1123942 | 100% | 0 | 0 | 0 | 133702 | -73 | 133628.1243 | 0.8757 | 0 | Completed in 2003.Financially completed in 2009. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of flexible slabstock polyurethane foam at Ningbo Yongling Rubber and Plastic Co. | Individual | ASP | CPR | FOA | 26 | INV | 266 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 448560 | -20224 | 428336 | 428336 | 100% | 0 | 0 | 0 | 58313 | -2629 | 55684.18 | -0.18 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Nanjing Kanglian Industrial Corporation | Individual | ASP | CPR | FOA | 27 | INV | 279 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-03-01 | 2000-04-01 | 2001-10-01 |  | 2001-04-01 | 2002-06-01 | 234900 | -14525 | 220375 | 220375 | 100% | 0 | 0 | 0 | 30537 | -1888 | 28648.51 | 0.49 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 16 projects in general foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 272 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of ten projects in the integral skin foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 278 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2005-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Hengfeng Polyurethane Spray Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 286 | N | I | CFC | 154.1 | 154.1 | 0 | 0 | 1999-07-01 | 2001-06-01 | 2002-02-01 |  | 2003-09-01 | 2005-02-01 | 1206600 | -101036 | 1105564 | 1105564 | 100% | 0 | 0 | 0 | 142726 | -11114 | 131612.04 | -0.04 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Jiangsu Chemical Research Institute | Individual | ASP | CPR | FOA | 28 | INV | 289 | N | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2001-12-01 | 2004-06-01 | 253690 | -9289 | 244401 | 244401 | 100% | 0 | 0 | 0 | 32980 | -1208 | 31772.13 | -0.13 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiaxing Anti-Corrosion Factory | Individual | ASP | CPR | FOA | 28 | INV | 290 | N | I | CFC | 19.4 | 19.4 | 0 | 0 | 1999-07-01 | 2000-10-01 | 2002-02-01 |  | 2002-05-01 | 2004-06-01 | 151590 | -6492 | 145098 | 145098 | 100% | 0 | 0 | 0 | 19707 | -844 | 18862.7 | 0.3 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Phase-out of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane insulation foam at Suzhou Purification Equipment Factory | Individual | ASP | CPR | FOA | 28 | INV | 291 | N | I | CFC | 66 | 66 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  |  | 2005-12-01 | 516780 | -259990 | 256790 | 256790 | 100% | 0 | 0 | 0 | 66846 | -33463 | 33382.7792 | 0.2208 | 0 | Canceled in 2004. Financially Completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Penglai Polyurethane Industry Co. | Individual | ASP | CPR | FOA | 28 | INV | 297 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2001-04-01 | 2003-07-01 | 497200 | -50527 | 446673 | 446673 | 100% | 0 | 0 | 0 | 64636 | -6569 | 58067.49 | -0.49 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water blown and HCFC-141b in the manufacture of ISF at 4 SMEs (Ningbo Yongling Rubber & Plastic, Sichuan Mianyang Jinpan Automobile Parts, Zhenjiang Xingda Auto Par | Individual | ASP | CPR | FOA | 29 | INV | 304 | N | I | CFC | 17.6 | 17.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2008-10-01 | 245710 | -19126 | 226584 | 226584 | 100% | 0 | 0 | 0 | 31942 | -2486 | 29455.6694 | 0.3306 | 0 | Completed in 2003. Financially completed in 2008. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Hangzhou Fanlong Steering Wheel, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 305 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 176520 | -4703 | 171817 | 171817 | 100% | 0 | 0 | 0 | 22948 | -612 | 22336 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hanfeng Polyurethane Company | Individual | ASP | CPR | FOA | 29 | INV | 312 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 440830 | -9007 | 431823 | 431823 | 100% | 0 | 0 | 0 | 57308 | -1171 | 56136.81 | 0.19 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Henan Bingxiong Refrigeration Truck Plant | Individual | ASP | CPR | FOA | 29 | INV | 313 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2004-06-01 | 440780 | -97144 | 343636 | 343636 | 100% | 0 | 0 | 0 | 57301 | -12629 | 44672.2801 | -0.2801 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2003-07-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Tianjin Relong Insulation Pipe Plant | Individual | ASP | CPR | FOA | 29 | INV | 314 | N | I | CFC | 11.9 | 11.9 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 93190 | -5957 | 87233 | 87233 | 100% | 0 | 0 | 0 | 12115 | -774 | 11340.5708 | 0.4292 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Zhenjiang Feichi Automobile Group, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 315 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 223900 | -11388 | 212512 | 212512 | 100% | 0 | 0 | 0 | 29107 | -1481 | 27626.34 | -0.34 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Taiyuan No. 2 Plastic Factory | Individual | ASP | CPR | FOA | 29 | INV | 316 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 1999-11-01 | 2002-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 127790 | -7057 | 120733 | 120733 | 100% | 0 | 0 | 0 | 16613 | -917 | 15695.5732 | 0.4268 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Harbin Dongguang Machinery Plant | Individual | ASP | CPR | FOA | 29 | INV | 318 | N | I | CFC | 57.1 | 57.1 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 447170 | -23616 | 423554 | 423554 | 100% | 0 | 0 | 0 | 58132 | -3070 | 55061.9335 | 0.0665 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Dongfeng Automobile Body Company | Individual | ASP | CPR | FOA | 29 | INV | 319 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 111120 | -9255 | 101865 | 101865 | 100% | 0 | 0 | 0 | 14446 | -1203 | 13242.8167 | 0.1833 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Zhifu Zhenxing Polyurethane Materials Plant | Individual | ASP | CPR | FOA | 29 | INV | 325 | N | I | CFC | 36.3 | 36.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 261480 | -24023 | 237457 | 237457 | 100% | 0 | 0 | 0 | 33992 | -3123 | 30869.4 | -0.4 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Hebei Tianye Automobile Group Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 326 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 98800 | -21346 | 77454 | 77454 | 100% | 0 | 0 | 0 | 12844 | -2775 | 10069.0202 | -0.0202 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of integral skin foam at Guangzhou Haohua Automobile Carpet Plant | Individual | ASP | CPR | FOA | 29 | INV | 328 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-09-01 | 2004-06-01 | 119540 | -8640 | 110900 | 110900 | 100% | 0 | 0 | 0 | 15540 | -1123 | 14417 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Ningxian Oriental Auto Parts Plant | Individual | ASP | CPR | FOA | 29 | INV | 329 | N | I | CFC | 7.3 | 7.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 122235 | -6311 | 115924 | 115924 | 100% | 0 | 0 | 0 | 15891 | -820 | 15070.5474 | 0.4526 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Fushan Anti-Corrosion Insulation Engineering Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 330 | N | I | CFC | 54.4 | 54.4 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2002-08-01 | 2004-06-01 | 425950 | -15465 | 410485 | 410485 | 100% | 0 | 0 | 0 | 55374 | -2010 | 53363.35 | 0.65 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam and flexible molded foam at Zhongqi Jinan Auto Parts Factory | Individual | ASP | CPR | FOA | 29 | INV | 331 | N | I | CFC | 21.6 | 21.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 236130 | -8780 | 227350 | 227350 | 100% | 0 | 0 | 0 | 30697 | -1141 | 29555.6546 | 0.3454 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Anqiu Polyurethane Materials Factory | Individual | ASP | CPR | FOA | 29 | INV | 332 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 497200 | -9710 | 487490 | 487490 | 100% | 0 | 0 | 0 | 64636 | -1262 | 63373.7356 | 0.2644 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Jizhou Beinei Automobile Cushion Plant | Individual | ASP | CPR | FOA | 29 | INV | 333 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-05-01 | 2005-03-01 | 484040 | -18030 | 466010 | 466010 | 100% | 0 | 0 | 0 | 62925 | -2344 | 60581.1074 | -0.1074 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Qingdao No. 10 Plastic Plant | Individual | ASP | CPR | FOA | 29 | INV | 334 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 298480 | -30327 | 268153 | 268153 | 100% | 0 | 0 | 0 | 38802 | -3943 | 34859.49 | -0.49 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Preparation of 7 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 343 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 35000 | -35000 | 0 | 0 |  | 0 | 0 | 0 | 4550 | -4550 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 4 projects in the foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 8 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a demonstration project for conversion from HCFC-142b and HCFC-22 technology to methyl formate and co-blowing technology in the manufacture of XPS foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 60 | PRP | 500 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2012-08-01 | 2013-04-01 | 30000 | -749 | 29251 | 29251 | 100% | 0 | 0 | 0 | 2250 | -56 | 2193.825 | 0.175 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | Demonstration project for conversion from HCFC-22/HCFC-142b technology to CO2 with methyl formate co-blowing technology in the manufacture of extruded polystyrene foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 64 | DEM | 507 | N | X | HCFC | 12.3 | 12.3 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 |  | 2014-12-01 |  | 1973300 | 0 | 1973300 | 1965300 | 99.59% | 8000 | 0 | 6400 | 147998 | 0 | 147397.998 | 600.002 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the project implementation was completed and the final report was submitted to the 73rd meeting of the Executive Committee. All planned operational activities relating to the project were completed. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in Nov 2011 and was actually signed in March 2012. Missions undertaken (actual/planned):1 planned and 1 actual. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 actual. Contract/PO/MOA agreements signed:1 planned and 1 actual. First disbursement date (actual/planned):The first disbursement took place in September 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project completion activities are being closely monitored for completion of project by end of year 2014. | 2011 |  | Non-Investment
FIN | UNDP | Survey of production and consumption of methyl bromide in China | Individual | ASP | CPR | FUM | 12 | TAS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-03-01 |  | 1998-10-01 | 2001-12-01 | 87000 | -1791 | 85209 | 85209 | 100% | 0 | 0 | 0 | 11310 | -232 | 11077.74 | 0.26 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical study on halons usage and applications of halons substitutes | Individual | ASP | CPR | HAL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 40000 | 3345 | 43345 | 43345 | 100% | 0 | 0 | 0 | 5200 | 435 | 5634.85 | 0.15 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: current situation, revision of national codes, and education and training | Individual | ASP | CPR | HAL | 10 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1996-06-01 |  | 1998-09-01 | 2000-12-01 | 280000 | -24125 | 255875 | 255875 | 100% | 0 | 0 | 0 | 36400 | -3136 | 33263.75 | 0.25 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: transfer of technology on alternatives to halon fire protection systems | Individual | ASP | CPR | HAL | 10 | TAS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-11-01 | 1996-06-01 |  | 1999-06-01 | 2000-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-06-01 | Non-Investment
FIN | UNDP | Acquisition of local air compressors for halon recycling machines | Individual | ASP | CPR | HAL | 12 | INV | 66 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-12-01 | 1998-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan: industrial and commercial refrigeration sub-sectors | Individual | ASP | CPR | PHA | 55 | PRP | 460 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-03-01 | 604000 | -1450 | 602550 | 602550 | 100% | 0 | 0 | 0 | 45300 | -109 | 45191.25 | -0.25 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan: solvent sector | Individual | ASP | CPR | PHA | 55 | PRP | 461 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-02-01 | 432000 | -504 | 431496 | 431495 | 100% | 1 | 0 | 0 | 32400 | -38 | 32362.05 | -0.05 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of an overarching HPMP strategy | Individual | ASP | CPR | PHA | 55 | PRP | 464 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-08-01 | 2009-07-01 |  | 2012-08-01 | 2013-12-01 | 360000 | -6 | 359994 | 360000 | 100% | -6 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 471 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-02-01 | 84000 | -72 | 83928 | 83928 | 100% | 0 | 0 | 0 | 6300 | -5 | 6294.6 | 0.4 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (industrial and commercial refrigeration and air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 512 | N | X | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 |  | 2013-12-01 | 2013-12-01 | 25380000 | 0 | 25380000 | 25380000 | 100% | 0 | 0 | 0 | 1903500 | 0 | 1903500 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (national coordination) (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 64 | INV | 515 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 | 2016-04-01 |  |  | 360000 | 0 | 360000 | 300000 | 83.33% | 60000 | 0 | 24000 | 27000 | 0 | 22500 | 4500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project activities relating to HPMP implementation are progressing in a satisfactory manner. Fourth tranche request for HPMP was submitted and approved in 73 Excom held in November 2014. 2013 targets were satisfactorily achieved. All planned activities are progressing satisfactorily. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2011. Missions undertaken (actual/planned):1 planned and 1 actual. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in February 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily. HPMP Stage-I tranche requests for consumption sector for all sub-sectors would be submitted to the 75th Excom. | 2011 |  | Investment
ONG | UNDP | Sector plan for phase-out of HCFCs in the solvent sector (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 65 | INV | 519 | N | X | HCFC | 33 | 25 | 0 | 0 | 2011-11-01 | 2012-07-01 | 2016-10-01 | 2016-10-01 |  |  | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 187500 | 0 | 187500 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project implementation progressed satisfactorily. All beneficiaries are implementing projects in a satisfactory manner. The final tranche is expected to be submitted for the 75th Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2012. . Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in July 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities are progressing satisfactorily with most of the companies covered under solvent sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2011 |  | Investment | 1600000
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 68 | INV | 525 | N | X | HCFC | 44 | 40 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2015-12-01 | 2016-06-01 |  |  | 6900000 | 0 | 6900000 | 6900000 | 100% | 0 | 0 | 0 | 483000 | 0 | 483000 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project implementation progressed satisfactorily. 11 beneficiaries aggregating to more than 80% of the total phase-out under the plan have signed the agreement. More beneficiaries are being identified and are expected to sign the agreement for project implementation in 2015. The fourth tranche for the sector plan was approved in November 2014. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2014. Missions undertaken (actual/planned):1 planned and 1 actual. TOR for consultants/subcontracts completed (actual/planned):1 Planned and 1 Actual. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities are progressing satisfactorily with most of the companies covered under ICR sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2012 |  | Investment | 3148500
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 534 | N | X | HCFC | 224.5 | 165.2 | 0 | 0 | 2013-12-01 | 2014-06-01 | 2015-12-01 | 2015-12-01 |  |  | 8495000 | -70627 | 8424373 | 8411373 | 99.85% | 13000 | 0 | 5200 | 594650 | 0 | 593732.3709 | 917.6291 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project implementation progressed satisfactorily. 11 beneficiaries aggregating to more than 80% of the total phase-out under the plan have signed the agreement. More beneficiaries are being identified and are expected to sign the agreement for project implementation in 2015. The fourth tranche for the sector plan was approved in November 2014. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was planned to be signed in May 2014 and actually signed in June 2014. Missions undertaken (actual/planned):2 planned and 2 actual. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:5 planned and signed. First disbursement date (actual/planned):The first disbursement took place in September 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities are progressing satisfactorily with most of the companies covered under ICR sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2013 |  | Investment | 2449306
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 71 | INV | 537 | N | X | HCFC | 26.4 | 12 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2015-12-01 | 2016-06-01 |  |  | 2000000 | -2289 | 1997711 | 1600000 | 80.09% | 397711 | 0 | 159084.4 | 140000 | 0 | 112128.3309 | 27871.6691 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project implementation progressed satisfactorily. All beneficiaries are implementing projects in a satisfactory manner. The final tranche is expected to be submitted for the 75th Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in March 2014. Missions undertaken (actual/planned):2 Planned - 2 actual. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:9 planned and signed. First disbursement date (actual/planned):The first disbursement took place in April 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities are progressing satisfactorily with most of the companies covered under solvent sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2013 |  | Investment | 880000
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 550 | N | X | HCFC | 27.5 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 11075000 | -87093 | 10987907 | 0 | 0% | 10987907 | 0 | 4395162.8 | 775250 | 0 | 0 | 775250 | 0 | Newly Approved | Activities are progressing satisfactorily with most of the companies covered under ICR sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2014 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) (overarching strategy) | Individual | ASP | CPR | PHA | 73 | PRP | 545 | N | X | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 200000 | 14000 | 0 | 0 | 14000 | 0 | Newly Approved | Activities for preparation ongoing - interagency consultations to be held in Q3 of 2015 for preparation of sector strategy. | 2014 |  | Non-Investment
FIN | UNDP | Feasibility study on the application of HFC-134a technology in MACs and CFC recycling | RMP-Component | ASP | CPR | REF | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-09-01 |  | 1993-12-01 | 1997-12-01 | 40000 | -15164 | 24836 | 24836 | 100% | 0 | 0 | 0 | 5200 | -1971 | 3228.68 | 0.32 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Establishment of a quality control testing plant for using CFC-12 substitute technology in refrigeration and rigid foams | Individual | ASP | CPR | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-12-01 | 1993-12-01 |  | 1998-06-01 | 1998-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Establishment of a training programme for centrifugal chillers and domestic refrigeration service managers and technicians | RMP-Component | ASP | CPR | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Import and promotion of applications for CFC substitute chemicals in the refrigeration sector in Southern China | RMP-Component | ASP | CPR | REF | 09 | TAS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1994-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Revision of design standards for cold storage | RMP-Component | ASP | CPR | REF | 10 | TAS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-01-01 | 1994-09-01 |  | 1999-03-01 | 2000-12-01 | 200000 | -18764 | 181236 | 181236 | 100% | 0 | 0 | 0 | 26000 | -2439 | 23560.68 | 0.32 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-03-01 | Non-Investment
FIN | UNDP | Survey on policy and planning measures to promote recycling of CFC | RMP-Component | ASP | CPR | REF | 11 | TAS | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-05-01 | 1994-11-01 |  | 1997-12-01 | 2000-12-01 | 100000 | -19358 | 80642 | 80642 | 100% | 0 | 0 | 0 | 13000 | -2517 | 10483.46 | -0.46 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Demonstration project (refrigeration - large food stores) | RMP-Component | ASP | CPR | REF | 17 | DEM | 131 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1997-06-01 | 2002-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Guangdong Kelon Electrical Holding Company Ltd. | Individual | ASP | CPR | REF | 17 | INV | 123 | N | I | CFC | 767.2 | 767.2 | 0 | 0 | 1995-07-01 | 1997-04-01 | 1997-01-01 |  | 1999-06-01 | 2003-07-01 | 4483050 | -6913 | 4476137 | 4476137 | 100% | 0 | 0 | 0 | 582797 | -899 | 581897.88 | 0.12 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Changsha Zhongyi Group Corp. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 124 | A | I | CFC | 360.2 | 360.2 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 2000-09-01 | 2004-01-01 | 2961000 | -2311 | 2958689 | 2958689 | 100% | 0 | 0 | 0 | 384930 | -300 | 384629.57 | 0.43 | 0 | Completed in 2000. Financially completed in 2004. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Guingdao Haier General Freezer Company | Individual | ASP | CPR | REF | 19 | INV | 167 | N | I | CFC | 278.8 | 278.8 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2000-04-01 | 2003-07-01 | 2548280 | -22910 | 2525370 | 2525370 | 100% | 0 | 0 | 0 | 331276 | -2978 | 328298.1 | -0.1 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Henan Freezer Factory | Individual | ASP | CPR | REF | 19 | INV | 168 | N | I | CFC | 167.7 | 167.7 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2001-06-01 | 2003-09-01 | 2550605 | -54725 | 2495880 | 2495880 | 100% | 0 | 0 | 0 | 331579 | -7114 | 324464.45 | 0.55 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
CLO | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Jilin Jinouer Electric Appliances Group Co. | Individual | ASP | CPR | REF | 23 | INV | 225 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-12-01 |  |  | 2003-09-01 | 2548360 | -1223403 | 1324957 | 1324957 | 100% | 0 | 0 | 0 | 331287 | -159042 | 172244.95 | 0.05 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 | 2000-12-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Wanbao Electrical Appliance Industries Co. | Individual | ASP | CPR | REF | 23 | INV | 226 | N | I | CFC | 574.2 | 574.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2003-12-01 | 2009-07-01 | 4566985 | 0 | 4566985 | 4566985 | 100% | 0 | 0 | 0 | 593708 | 0 | 593708.1 | -0.1 | 0 | Completed in 2003.Financially completed in 2009. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Honxiang Group, Laizhou Freezer Plant | Individual | ASP | CPR | REF | 23 | INV | 232 | N | I | CFC | 301.5 | 301.5 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2003-09-01 | 2005-03-01 | 1339203 | -6776 | 1332427 | 1332427 | 100% | 0 | 0 | 0 | 174096 | -881 | 173215.4 | -0.4 | 0 | Completed in 2003. Financially completed in 2005. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic freezers at DeBao Refrigeration Equipment Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 233 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-06-01 | 1208176 | -683628 | 524548 | 524548 | 100% | 0 | 0 | 0 | 157063 | -88872 | 68191.26 | -0.26 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to cylopentane and R-134a in the manufacture of domestic freezers at Wanbao Freezer Industrial Corporation | Individual | ASP | CPR | REF | 24 | INV | 242 | N | I | CFC | 138.2 | 138.2 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-08-01 | 2004-06-01 | 1402370 | -52248 | 1350122 | 1350122 | 100% | 0 | 0 | 0 | 182308 | -6792 | 175515.8 | 0.2 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the domestic refrigeration (hydrocarbon) subsector | Individual | ASP | CPR | REF | 24 | PRP | 239 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | Individual | ASP | CPR | REF | 25 | INV | 249 | N | I | CFC | 247.8 | 247.8 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2004-11-01 | 2008-10-01 | 2238580 | -1062 | 2237518 | 2237518 | 100% | 0 | 0 | 0 | 291015 | -138 | 290877.3402 | -0.3402 | 0 | Completed in 2004. Financially completed in 2008. |  | 1998 | 2001-12-01 | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration subsector (hydrocarbons) | Individual | ASP | CPR | REF | 30 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 35000 | -7212 | 27788 | 27788 | 100% | 0 | 0 | 0 | 4550 | -938 | 3612.4079 | -0.40785 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | Individual | ASP | CPR | REF | 32 | INV | 367 | N | I | CFC | 180.8 | 180.8 | 0 | 0 | 2000-12-01 | 2003-06-01 | 2004-01-01 |  | 2004-11-01 | 2011-08-01 | 788359 | -9293 | 779066 | 779066 | 100% | 0 | 0 | 0 | 96720 | -1140 | 95579.8862 | 0.1138 | 0 | Completed in 2004. |  | 2000 |  | Investment
COM | UNDP | Demonstration project for conversion from HCFC-22 technology to HFC-32 technology in the manufacture of commercial air-source chillers/heat pumps at Tsinghua Tong Fang Artifical Environment Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 498 | N | X | HCFC | 3.4 | 3.4 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 |  | 2014-12-01 |  | 1229336 | 0 | 1229336 | 1229335 | 100% | 1 | 0 | 0.672 | 92200 | 0 | 92199.937 | 0.063 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, the project implementation was completed. The final report was submitted to 72 Excom. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in October 2010 and actually signed in January 2011. Missions undertaken (actual/planned):1 Planned and 1 Actual. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 actual. Contract/PO/MOA agreements signed:1 signed. First disbursement date (actual/planned):The first disbursement took place in March 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project completion activities are underway. The project is expected to be completed by Q4-2014. A detailed technical report provided for the consideration of 72 Excom. | 2010 |  | Investment
COM | UNDP | Demonstration project for conversion from HCFC-22 technology to Ammonia/CO2 technology in the manufacture of two-stage refrigeration systems for cold storage and freezing applications at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 499 | N | X | HCFC | 13.8 | 13.8 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 |  | 2014-12-01 |  | 3964458 | 0 | 3964458 | 3964458 | 100% | 0 | 0 | 0 | 297334 | 0 | 297334 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, the project implementation was completed. The final report was submitted to 72 Excom. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in October 2010 and actually signed in January 2011. Missions undertaken (actual/planned):2 Planned and 1 Actual. TOR for consultants/subcontracts completed (actual/planned):2 planned and 1 actual. Contract/PO/MOA agreements signed:1 signed. First disbursement date (actual/planned):The first disbursement took place in March 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project completion activities are underway. The project is expected to be completed by Q4-2014. A detailed technical report provided for the consideration of 72 Excom. | 2010 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (industrial and commercial refrigeration sector) | Individual | ASP | CPR | REF | 73 | PRP | 543 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 330000 | 0 | 330000 | 0 | 0% | 330000 | 0 | 330000 | 23100 | 0 | 0 | 23100 | 0 | Newly Approved | Activities for preparation ongoing - interagency consultations to be held in Q3 of 2015 for preparation of sector strategy. | 2014 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | CPR | SEV | 06 | CPG | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening, including establishment of the Information Clearing-house at NEPA | Individual | ASP | CPR | SEV | 06 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-04-01 | 1995-02-01 |  | 1996-12-01 | 1998-12-01 | 150000 | 299997 | 449997 | 449997 | 100% | 0 | 0 | 0 | 19500 | 39000 | 58499.61 | 0.39 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | CPR | SEV | 09 | PRP | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Survey and assessment of small CFC plant conversion possibilities | Individual | ASP | CPR | SEV | 09 | TAS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-05-01 | 1994-03-01 |  | 1998-10-01 | 2001-12-01 | 90000 | -701 | 89299 | 89299 | 100% | 0 | 0 | 0 | 11700 | -91 | 11608.7884 | 0.2116 | 0 | Completed in 1998. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 11 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | National product qualification and standards evaluation for non-ODS alternatives to CFC applications | Individual | ASP | CPR | SEV | 11 | TAS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-11-01 |  | 1998-03-01 | 2000-12-01 | 362500 | -29055 | 333445 | 333445 | 100% | 0 | 0 | 0 | 47125 | -3777 | 43347.85 | 0.15 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 15 | PRP | 106 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 17 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-04-01 |  | 1996-03-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 18 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol - Phase II | Individual | ASP | CPR | SEV | 20 | INS | 181 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 300000 | -1 | 299999 | 299999 | 100% | 0 | 0 | 0 | 39000 | 0 | 38999.87 | 0.13 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Update of the country programme and policy workshop | Individual | ASP | CPR | SEV | 21 | CPG | 188 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-03-01 |  | 1998-12-01 | 2002-06-01 | 225000 | -17054 | 207946 | 207946 | 100% | 0 | 0 | 0 | 29250 | -2217 | 27032.98 | 0.02 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 21 | PRP | 191 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 22 | PRP | 197 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol (Phase III) | Individual | ASP | CPR | SEV | 26 | INS | 262 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | ASP | CPR | SEV | 32 | INS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2003-01-01 |  | 2003-06-01 | 2008-10-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2003. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening (phase 5) | Individual | ASP | CPR | SEV | 38 | INS | 398 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2005-09-01 | 2008-10-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 50700 | 0 | 50700 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | CPR | SEV | 44 | INS | 421 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2010-10-01 | 390000 | -129 | 389871 | 389871 | 100% | 0 | 0 | 0 | 29250 | -10 | 29240.325 | -0.325 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | CPR | SEV | 50 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2010-10-01 | 390000 | -413 | 389587 | 389587 | 100% | 0 | 0 | 0 | 29250 | -31 | 29219.0251 | -0.02505 | 0 | Financially completed in 2010. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | CPR | SEV | 56 | INS | 477 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-07-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 29250 | 0 | 29250 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | ASP | CPR | SEV | 62 | INS | 504 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2013-06-01 | 2014-09-01 | 390000 | 0 | 390000 | 389428 | 99.85% | 572 | 0 | 0 | 29250 | 0 | 29207.1 | 42.9 | 0 | Financially completed in 2014. | Completed in 2013. | 2010 |  | Investment
COM | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | CPR | SEV | 68 | INS | 523 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2015-03-01 |  | 2014-12-01 |  | 390000 | 0 | 390000 | 381272 | 97.76% | 8728 | 0 | 6982.12 | 27300 | 0 | 26689.0645 | 610.9355 | 0 | Remarks (Short narrative description of progress made (actual/planned)): Completed in 2014. As planned in 2014, the monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for 2013 was reported in timely manner. The IS project - Phase XI was submitted and approved at the 73rd ExCom. Prodoc signed (actual/planned, yes/no and date):Planned in April 2013 and actual in June 2013. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project activities are continuing to be being monitored. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 1/2015-12/2016) | Individual | ASP | CPR | SEV | 73 | INS | 549 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-12-01 | 2017-01-01 |  |  | 390000 | 0 | 390000 | 0 | 0% | 390000 | 0 | 156000 | 27300 | 0 | 0 | 27300 | 0 | Newly Approved | The activities have been initiated in the beginning of 2015 and the implementation is going as planned. The first disbursement is expected to be made in mid- 2015. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2014 |  | Non-Investment
FIN | UNDP | Pre-feasibility study to phase-out CFC-113 in electronic cleaning in four production lines | Individual | ASP | CPR | SOL | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-10-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 40000 | 1829 | 41829 | 41829 | 100% | 0 | 0 | 0 | 5200 | 238 | 5437.77 | 0.23 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Dalian precision parts cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 19 | N | I | CFC | 69 | 69 | 0 | 0 | 1992-06-01 | 1996-04-01 | 1994-06-01 |  | 1996-09-01 | 1998-12-01 | 495000 | -34191 | 460809 | 460809 | 100% | 0 | 0 | 0 | 64350 | -4445 | 59905.42 | -0.42 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Dandong electronic tuner aqueous cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 20 | N | I | CFC | 20 | 20 | 0 | 0 | 1992-06-01 | 1995-07-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 495000 | -663 | 494337 | 494337 | 100% | 0 | 0 | 0 | 64350 | -86 | 64263.87 | 0.13 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at Nanjing Wire Works | Individual | ASP | CPR | SOL | 10 | INV | 36 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1993-06-01 | 1996-08-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 409000 | -511 | 408489 | 408489 | 100% | 0 | 0 | 0 | 53170 | -66 | 53103.57 | 0.43 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at the Chengdu Qianfeng Radio Instrument Factory | Individual | ASP | CPR | SOL | 10 | INV | 37 | N | I | CFC | 7.2 | 7.2 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1995-12-01 |  | 1997-12-01 | 1999-12-01 | 394700 | -13224 | 381476 | 381476 | 100% | 0 | 0 | 0 | 51311 | -1719 | 49592 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1993 |  | Investment
FIN | UNDP | ODS-free cleaning equipment manufacturing center for phasing out ODS consuming solvents across China | Individual | ASP | CPR | SOL | 12 | INV | 65 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1997-06-01 | 1996-03-01 |  | 1999-11-01 | 2002-07-01 | 524734 | -50707 | 474027 | 474027 | 100% | 0 | 0 | 0 | 68215 | -6592 | 61623.51 | -0.51 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Cleaning applications deployment center for replication of ODS-free process across China | Individual | ASP | CPR | SOL | 12 | TAS | 61 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-03-01 | 1995-03-01 |  | 1998-05-01 | 2000-12-01 | 489400 | -66345 | 423055 | 423055 | 100% | 0 | 0 | 0 | 63622 | -8625 | 54997.15 | -0.15 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Non-Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Hunan Computer Factory | Individual | ASP | CPR | SOL | 18 | INV | 152 | A | R | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 1997-12-01 | 2000-12-01 | 104700 | -18343 | 86357 | 86357 | 100% | 0 | 0 | 0 | 13611 | -2385 | 11226.41 | -0.41 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Sixth Radio Factory | Individual | ASP | CPR | SOL | 19 | INV | 169 | N | I | CFC | 4.5 | 4.5 | 0 | 0 | 1996-05-01 | 1999-09-01 | 1998-04-01 |  | 2001-08-01 | 2003-09-01 | 138400 | -14098 | 124302 | 124302 | 100% | 0 | 0 | 0 | 17992 | -1833 | 16159.26 | -0.26 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the electron gun final cleaning processes at the Tianjin Picture Tube Factory | Individual | ASP | CPR | SOL | 19 | INV | 170 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1998-04-01 |  |  | 1999-03-01 | 132600 | -132600 | 0 | 0 |  | 0 | 0 | 0 | 17238 | -17238 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Elimination of the use of CFC-113 and methyl chloroform in the color picture tube cleaning processes at the Shanghai Novel CPT. Corp. Factory | Individual | ASP | CPR | SOL | 19 | INV | 171 | N | I | CFC | 75 | 75 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1998-04-01 |  | 2002-11-01 | 2008-10-01 | 849950 | -150442 | 699508 | 699508 | 100% | 0 | 0 | 0 | 110494 | -19558 | 90935.5 | 0.5 | 0 | Completed in 2002. Financially completed in 2008. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of the use of TCA in the Baoshi Electronics Corporation Shijazhuang Manufacturing Operations | Individual | ASP | CPR | SOL | 19 | INV | 172 | N | I | TCA | 7.4 | 7.4 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1998-04-01 |  | 2000-07-01 | 2003-03-01 | 284900 | -7138 | 277762 | 277762 | 100% | 0 | 0 | 0 | 37037 | -928 | 36108.9395 | 0.0605 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai Automation Instrumentation Factory | Individual | ASP | CPR | SOL | 20 | INV | 178 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1999-08-01 | 1998-09-01 |  | 2001-03-01 | 2003-03-01 | 325000 | -5336 | 319664 | 319664 | 100% | 0 | 0 | 0 | 42250 | -694 | 41556.32 | -0.32 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai No 8 Radio Factory | Individual | ASP | CPR | SOL | 20 | INV | 186 | N | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 2000-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-09-01 | 378000 | -81073 | 296927 | 296927 | 100% | 0 | 0 | 0 | 49140 | -10539 | 38600.51 | 0.49 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Preparation of a sectoral financing plan for the solvents sector | Individual | ASP | CPR | SOL | 21 | TAS | 192 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2003-07-01 | 200000 | -19236 | 180764 | 180764 | 100% | 0 | 0 | 0 | 26000 | -2501 | 23499.32 | -0.32 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Railway Communication Equipment Factory | Individual | ASP | CPR | SOL | 22 | INV | 195 | N | I | CFC | 14.4 | 14.4 | 0 | 0 | 1997-05-01 | 1999-09-01 | 1999-06-01 |  | 2001-03-01 | 2003-03-01 | 276287 | -1 | 276286 | 276286 | 100% | 0 | 0 | 0 | 35917 | 0 | 35917.18 | -0.18 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Computer Factory | Individual | ASP | CPR | SOL | 22 | INV | 216 | N | I | CFC | 6.3 | 6.3 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-11-01 | 2003-08-01 | 116767 | -1 | 116766 | 116766 | 100% | 0 | 0 | 0 | 15180 | 0 | 15179.58 | 0.42 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Fujian Putian Vikay Electronics Co. Ltd. | Individual | ASP | CPR | SOL | 23 | INV | 224 | N | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2002-11-01 | 2008-10-01 | 619780 | -2356 | 617424 | 617424 | 100% | 0 | 0 | 0 | 80571 | -306 | 80265.1215 | -0.1215 | 0 | Completed in 2002. Financially completed in 2008. |  | 1997 |  | Investment
FIN | UNDP | Elimination of ODS used in the production lines at Irico (Caihong) Color Picture Tube Factory | Individual | ASP | CPR | SOL | 28 | INV | 287 | N | I | TCA/CFC | 202 | 202 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2003-08-01 |  | 2002-10-01 | 2004-06-01 | 2853200 | -38805 | 2814395 | 2814395 | 100% | 0 | 0 | 0 | 323852 | -4405 | 319446.6325 | 0.3675 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | ODS phaseout in China solvent sector: 2000 annual programme | Multi-Year | ASP | CPR | SOL | 30 | INV | 355 | N | I | TCA/CTC/CFC | 382.8 | 382.8 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-03-01 |  | 2003-05-01 | 2013-02-01 | 6750000 | 0 | 6750000 | 6750000 | 100% | 0 | 0 | 0 | 675000 | 0 | 675000 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
FIN | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | Multi-Year | ASP | CPR | SOL | 33 | INV | 373 | N | I | TCA/CTC/CFC | 534 | 534 | 0 | 0 | 2001-03-01 | 2003-03-01 | 2002-03-01 |  | 2005-01-01 | 2013-09-01 | 6955000 | 0 | 6955000 | 6955000 | 100% | 0 | 0 | 0 | 695500 | 0 | 695500 | 0 | 0 | Financially completed in 2013. |  | 2001 | 2003-09-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | Multi-Year | ASP | CPR | SOL | 36 | INV | 390 | N | I | TCA/CTC/CFC | 580 | 580 | 0 | 0 | 2002-03-01 | 2005-01-01 | 2003-03-01 |  | 2005-09-01 | 2013-12-01 | 6330000 | 0 | 6330000 | 6330000 | 100% | 0 | 0 | 0 | 633000 | 0 | 633000 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2004-06-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | Multi-Year | ASP | CPR | SOL | 40 | INV | 403 | N | I | CFC/TCA/CTC | 580 | 580 | 0 | 0 | 2003-07-01 | 2005-01-01 | 2004-03-01 |  | 2005-12-01 | 2013-03-01 | 5755000 | 0 | 5755000 | 5755000 | 100% | 0 | 0 | 0 | 431625 | 0 | 431625 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2005-06-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2004 annual programme | Multi-Year | ASP | CPR | SOL | 42 | INV | 410 | N | I | CFC | 733 | 733 | 0 | 0 | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2006-12-01 | 2013-07-01 | 5555000 | 0 | 5555000 | 5555000 | 100% | 0 | 0 | 0 | 416625 | 0 | 416625 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2005 annual programme | Multi-Year | ASP | CPR | SOL | 45 | INV | 429 | N | I | TCA/CTC | 635 | 635 | 0 | 0 | 2005-04-01 | 2007-02-01 | 2006-04-01 |  | 2009-12-01 | 2013-08-01 | 5680000 | 0 | 5680000 | 5680000 | 100% | 0 | 0 | 0 | 426000 | 0 | 426000 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2006 annual programme | Multi-Year | ASP | CPR | SOL | 47 | INV | 435 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2005-11-01 | 2009-05-01 | 2006-12-01 |  | 2009-12-01 | 2013-02-01 | 5055000 | 0 | 5055000 | 5055000 | 100% | 0 | 0 | 0 | 379125 | 0 | 379125 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2007 annual programme | Multi-Year | ASP | CPR | SOL | 50 | INV | 446 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-12-01 |  | 2009-12-01 | 2013-08-01 | 5480000 | 0 | 5480000 | 5480000 | 100% | 0 | 0 | 0 | 411000 | 0 | 411000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2008 annual programme | Multi-Year | ASP | CPR | SOL | 53 | INV | 457 | N | I | TCA | 85 | 85 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-09-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2009 annual programme | Multi-Year | ASP | CPR | SOL | 56 | INV | 479 | N | I | TCA | 84 | 84 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-03-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2010 annual programme | Multi-Year | ASP | CPR | SOL | 59 | INV | 495 | N | I | TCA | 85 | 85 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-08-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Preparation of a demonstration project for conversion from HCFC-141b to a combination of isopropyl alcohol and hydrocarbon-based compounds in solvent cleaning applications at Zhejiang KDL Medical Equipment Group Ltd. | Individual | ASP | CPR | SOL | 60 | PRP | 497 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2012-12-01 | 2013-04-01 | 30000 | -4915 | 25085 | 25085 | 100% | 0 | 0 | 0 | 2250 | -369 | 1881.375 | -0.375 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
COM | UNDP | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. | Individual | ASP | CPR | SOL | 64 | DEM | 511 | N | X | HCFC | 2 | 2 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 |  | 2014-12-01 |  | 352051 | 0 | 352051 | 352042 | 100% | 9 | 0 | 6.808 | 26404 | 0 | 26403.3617 | 0.63825 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The NOU has been finalizing the reports for closure of the project. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in September 2011 and actually signed in March 2012. Missions undertaken (actual/planned):1 planned and 1 Actual. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 actual. Contract/PO/MOA agreements signed:1 signed. First disbursement date (actual/planned):The first disbursement took place in September 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project targeted for completion in 2014. | 2011 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (solvents sector) | Individual | ASP | CPR | SOL | 73 | PRP | 544 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 10500 | 0 | 0 | 10500 | 0 | Newly Approved | Activities for preparation ongoing - interagency consultations to be held in Q3 of 2015 for preparaiton of sector strategy. | 2014 |  | Non-Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 22 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 33 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | Individual | LAC | CUB | ARS | 34 | INV | 18 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-05-01 |  | 2006-12-01 | 2008-04-01 | 124220 | 0 | 124220 | 124220 | 100% | 0 | 0 | 0 | 16149 | 0 | 16148.6 | 0.4 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the MDI sector | Individual | LAC | CUB | ARS | 36 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 30000 | 20000 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3900 | 1500 | 5400 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Development of MDI transition strategies | Individual | LAC | CUB | ARS | 36 | TAS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2004-03-01 | 2008-08-01 | 30000 | -5998 | 24002 | 24002 | 100% | 0 | 0 | 0 | 3900 | -780 | 3120.26 | -0.26 | 0 | Completed in 2004. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | CUB | ARS | 41 | INV | 23 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2006-09-01 |  | 2011-12-01 | 2014-05-01 | 5960000 | -373 | 5959627 | 5959627 | 100% | 0 | 0 | 0 | 447000 | -28 | 446972.02 | -0.02 | 0 | Financially completed in 2014. | One year stability test will be done in April 2012. Final registration will take place after that, if tests are successful. | 2003 | 2008-03-01 | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 59 | PRP | 45 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2010-11-01 |  | 2010-11-01 | 2012-04-01 | 40000 | -1261 | 38739 | 38739 | 100% | 0 | 0 | 0 | 3000 | -95 | 2905.4251 | -0.42505 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 62 | DEM | 46 | N | I | No_ODP | 45.3 | 45.3 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-12-01 | 2016-01-01 |  |  | 525200 | 0 | 525200 | 429105 | 81.7% | 96095 | 0 | 38437.924 | 39390 | 0 | 32182.8893 | 7207.1107 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The project advanced according to plan. The destruction truck was delivered and initial destruction tests in cement plant were conducted. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2011. Missions undertaken (actual/planned):0 of 1. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in September 2011. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:There have been delays in the analysis of chimmey emissions at cement plant due to a lack of specialized laboratories in Cuba. In order to address these delays, UNDP provided a list of laboratories that could carry out the analysis to the NOU. | Trials of installed equipment were conducted. Final adjustments based on trials results are under implementation. 1 follow up mission carried out. | 2010 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CUB | FOA | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2013-05-01 | 2014-02-01 | 50000 | -487 | 49513 | 49513 | 100% | 0 | 0 | 0 | 3750 | -37 | 3713.47 | -0.47 | 0 | Financially Completed in 2014. | Project completed in 2013. | 2009 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2005 annual implementation plan - UNDP Portion | Multi-Year | LAC | CUB | PHA | 45 | INV | 33 | N | I | CFC | 30 | 30 | 0 | 0 | 2005-04-01 | 2007-07-01 | 2006-04-01 |  | 2007-12-01 | 2013-08-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 18750 | 0 | 18750 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: balance of the 2004 and 2005 annual programmes (France and Germany) | Multi-Year | LAC | CUB | PHA | 48 | INV | 37 | N | I | CFC | 79.7 | 79.7 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-07-01 | 2013-12-01 | 512228 | 0 | 512228 | 512228 | 100% | 0 | 0 | 0 | 38417 | 0 | 38417 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2006 and 2007 annual implementation plans | Multi-Year | LAC | CUB | PHA | 53 | INV | 39 | N | I | CFC | 166.2 | 166.2 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2013-07-01 | 641000 | 0 | 641000 | 641000 | 100% | 0 | 0 | 0 | 48075 | 0 | 48075 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CUB | PHA | 56 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 | 2014-04-01 | 150000 | -1 | 149999 | 149999 | 100% | 0 | 0 | 0 | 11250 | 0 | 11249.92 | 0.08 | 0 | Financially completed in 2014. | Pending payments have been made. | 2008 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2009 and 2010 annual implementation plans | Multi-Year | LAC | CUB | PHA | 59 | INV | 44 | N | I | CFC | 53.8 | 53.8 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-12-01 |  | 2013-12-01 | 2014-03-01 | 156000 | -1176 | 154824 | 154824 | 100% | 0 | 0 | 0 | 11700 | -88 | 11611.8 | 0.2 | 0 | Financially Completed in 2014. | Project activities completed in 2013. PCR under preparation. | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-year | LAC | CUB | PHA | 65 | INV | 49 | N | I | HCFC | 13.4 | 8 | 0 | 0 | 2011-11-01 | 2013-07-01 | 2016-10-01 | 2016-10-01 |  |  | 650000 | 0 | 650000 | 196412 | 30.22% | 453588 | 0 | 181435.316 | 48750 | 0 | 14730.8782 | 34019.1217 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The planned milestone of selecting technology suppliers was achieved, awarding contracts was achieved for one company, implementation of plant convertion started as suppliers paid a visit to the company, action plan and technical specification of equipment agreed. For the other company, the NOU and supplier could not reached an agreement on commercial conditions, another supplier was contacted and discussions are underway. Import of HCF-141b in preblended polyos banned since 31/12/14. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2013. Missions undertaken (actual/planned):0 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 2. Contract/PO/MOA agreements signed:1 of 2. First disbursement date (actual/planned):The first disbursement took place in July 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Negotiations with one supplier broke as the NOU and supplier did not reach a commercial agreement. UNDP facilitated contact with other suppliers that participated in bidding process. One company was selected and contract negotiation are underway. | Pending contract was signed and construction of equipment started, so equipment for both plants are currently under construction. Preparation of plants for conversion was conducted. 1 follow up mission was carried out. | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | CUB | PHA | 65 | TAS | 48 | N | I | HCFC | 1.7 | 1.7 | 0 | 0 | 2011-11-01 | 2013-05-01 | 2016-10-01 |  | 2014-12-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the project advanced according to work plan, 16 training centers were strengthened with equipment and training tools. Activities to promote the reconversion of refrigeration systems continued, in 2014 80 systems were converted to HCFC-alternatives. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2013. Missions undertaken (actual/planned):0 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in May 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, the 2014 workplan and budget was prepared and approved. The process for purchasing equipment for workshops and training facilities launched. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-Year | LAC | CUB | PHA | 68 | INV | 50 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2016-08-01 |  |  | 537527 | 0 | 537527 | 0 | 0% | 537527 | 0 | 215010.8 | 40315 | 0 | 0 | 40315 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The planned milestone of selecting technology suppliers was achieved, awarding contracts was achieved for one company, implementation of plant conversion started as suppliers paid a visit to the company, action plan and technical especification of equipment agreed. For the other company, the NOU and supplier could not reach an agreement on commercial conditions, another supplier was contacted and discussions are underway. Import of HCFC-141b in preblended polyos banned since 31/12/14. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2013. Missions undertaken (actual/planned):0 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 2. Contract/PO/MOA agreements signed:1 of 2. First disbursement date (actual/planned):The first disbursement took place in July 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Negotiation with one supplier broke as NOU and supplier did not reach a commercial agreement. UNDP facilitated contact with other suppliers that participated in bidding process. One company was selected and contract negotiation are underway. | Conversion of commercial equipment continues, training centers around the country recieved equipment to strength technical offer. 1 follow up vist conducted. | 2012 |  | Investment
COM | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | CUB | PHA | 71 | TAS | 51 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-09-01 | 2015-03-01 |  | 2014-12-01 |  | 30000 | 0 | 30000 | 7521 | 25.07% | 22479 | 0 | 17983.368 | 2700 | 0 | 676.8711 | 2023.1289 | 0 | Remarks (Short narrative description of progress made (actual/planned)):CompIeted in 2014. In 2014, the TOR was prepared and the consultant was contracted. The milestone of preparing the verification report was achieved. Verification report sent to MLFS; the report showed that Cuba is in compliance with its agreement on reducing its HCFC consumption. Pending payment of contract deliverables. Prodoc signed (actual/planned, yes/no and date):Yes,the prodoc was signed in August 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in September 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | The initial stage of project implementation has begun. The workplan has been prepared. | 2013 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CUB | PHA | 73 | INV | 53 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 162473 | 0 | 162473 | 0 | 0% | 162473 | 0 | 64989.2 | 12185 | 0 | 0 | 12185 | 0 | Newly Approved | Conversion of commercial equipment continues, training centers around the country recieved equipment to strength technical offer. 1 follow uo vist conducted. | 2014 |  | Investment
FIN | UNDP | Development of an ODS phase out strategy in the refrigeration sector | RMP-Component | LAC | CUB | REF | 13 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-07-01 |  | 1997-09-01 | 1998-12-01 | 30000 | -10000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3900 | -1300 | 2600 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | CUB | REF | 15 | TAS | 04 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-12-01 |  | 1997-09-01 | 1998-12-01 | 169000 | -5167 | 163833 | 163833 | 100% | 0 | 0 | 0 | 21970 | -672 | 21298 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Umbrella project for elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Empco-Mincin and Segere-Sime "Dionisio Rodrigues" | Individual | LAC | CUB | REF | 23 | INV | 06 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-06-01 | 2002-03-01 | 119505 | -9086 | 110419 | 110419 | 100% | 0 | 0 | 0 | 15536 | -1181 | 14354.47 | 0.53 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2008-12-01 |  | 2010-12-01 | 2014-02-01 | 787482 | 196669 | 984151 | 984151 | 100% | 0 | 0 | 0 | 59061 | 17702 | 76763.3918 | -0.39178 | 0 | Financially completed in 2014. |  | 2005 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (manufacturing sector) | Individual | LAC | CUB | REF | 58 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 |  | 2010-07-01 | 2017-01-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3750 | 0 | 0 | 3750 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The NOU reviewed the technical report and considered alternative approaches. The challenge was to evaluate the technical replacement options for Cuba. One expert mission to place but still pending the payment. Prodoc signed (actual/planned, yes/no and date):No, the prodoc is expected to be signed in January 2015. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The NOU was evaluating different alternatives to select the one that is more suitable to Cuba's conditions. UNDP has facilitated the contact with refrigeration experts and other NOUs. | Evaluation of technology options continues, discussion between NOU and beneficiary company were conducted to discuss existing options. | 2009 |  | Investment
FIN | UNDP | Country programme preparation | Individual | LAC | CUB | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 20000 | -5000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 2600 | -650 | 1950 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of OTOZ | Individual | LAC | CUB | SEV | 10 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-10-01 | 2000-12-01 | 172000 | -5 | 171995 | 171995 | 100% | 0 | 0 | 0 | 22360 | -1 | 22358.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | CUB | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14906.58 | 0.42 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening under Montreal Protocol (phase III) | Individual | LAC | CUB | SEV | 34 | INS | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2003-08-01 |  | 2003-09-01 | 2004-12-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14906.58 | 0.42 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase 4) | Individual | LAC | CUB | SEV | 40 | INS | 22 | N | I | No_ODP | 12.3 | 12.3 | 0 | 0 | 2003-07-01 | 2003-10-01 | 2005-07-01 |  | 2006-12-01 | 2008-08-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | CUB | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-11-01 | 2007-12-01 |  | 2008-03-01 | 2009-07-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | CUB | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2010-03-01 | 2011-05-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | CUB | SEV | 59 | INS | 43 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 | 2013-02-01 | 74533 | 74533 | 149066 | 149066 | 100% | 0 | 0 | 0 | 5590 | 5590 | 11180 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | LAC | CUB | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 |  | 2014-06-01 |  | 149066 | 0 | 149066 | 148949 | 99.92% | 117 | 0 | 93.728 | 11180 | 0 | 11171.213 | 8.787 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, institutional strengthening activities were underway and all planned activities were conducted. ODS consumption reports were prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. Awareness activities around the 20th aniversary of the NOU were implemented. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in September 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 2014 workplan and budget prepared and approved. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | LAC | CUB | SEV | 71 | INS | 52 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2015-12-01 | 2016-03-01 |  |  | 149066 | 0 | 149066 | 467 | 0.3133% | 148599 | 0 | 59439.408 | 10435 | 0 | 32.7248 | 10402.2752 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were underway and all planned activities were conducted. ODS consumption reports were prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. Awareness activities around the 20th aniversary of the NOU were implemented. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):The first disbursement took place in December 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 1 follow up mission was conducted. An international workshop on alternatives to HCFC in the refrigeration sector was prepared but cancelled due to external factors. | 2013 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | DJI | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | DJI | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-01-01 | 147000 | -2151 | 144849 | 144849 | 100% | 0 | 0 | 0 | 13230 | -194 | 13036.41 | -0.41 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | DJI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | DJI | REF | 37 | TAS | 03 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling | RMP-Component | AFR | DJI | REF | 37 | TAS | 07 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-07-01 | 136463 | -685 | 135778 | 135778 | 100% | 0 | 0 | 0 | 17740 | -89 | 17651.14 | -0.14 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2009-12-01 |  | 2009-12-01 | 2013-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2013-12-01 | 2014-03-01 | 57000 | 0 | 57000 | 56208 | 98.61% | 792 | 0 | 0 | 5130 | 0 | 5058.7389 | 71.2611 | 0 | Financially Completed in 2014. | Completed in 2013. No new activities have been undertaken after December 2013. However, due to a delay with the equipment suppliers, equipment was shipped only in Jan 2014 and is being cleared from customs now. This project is operationally completed. | 2008 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (fourth tranche) | Multi-year | LAC | DMI | PHA | 61 | INV | 17 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2013-12-01 | 2014-08-01 | 6000 | -6000 | 0 | 0 |  | 0 | 0 | 0 | 540 | -540 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Demurrage services have been initiated. No new activities have been undertaken after December 2013. However, due to a delay with the equipment suppliers, equipment was shipped only in Jan 2014 and is being cleared from customs now. T | 2010 |  | Investment
FIN | UNDP | Preparation of a project in the general foam subsector | Individual | LAC | DOM | FOA | 27 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Paredomi (Paneles Refrigerados Dominicanos, C.A.) | Individual | LAC | DOM | FOA | 29 | INV | 21 | A | I | CFC | 60.7 | 60.7 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-04-01 | 2003-09-01 | 177670 | 0 | 177670 | 177670 | 100% | 0 | 0 | 0 | 23097 | 0 | 23097.52 | -0.52 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Espumas del Cibao | Individual | LAC | DOM | FOA | 29 | INV | 22 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2002-11-01 | 89712 | -1048 | 88664 | 88664 | 100% | 0 | 0 | 0 | 11663 | -136 | 11526.32 | 0.68 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Poquinsa (Poliuretano Químico Indutrial, S.A.) | Individual | LAC | DOM | FOA | 29 | INV | 24 | A | I | CFC | 4 | 4 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 24920 | 0 | 24920 | 24920 | 100% | 0 | 0 | 0 | 3240 | 0 | 3239.6 | 0.4 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | DOM | FOA | 33 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | DOM | FOA | 36 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2005-07-01 | 2006-06-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | DOM | FOA | 57 | PRP | 44 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 | 2014-03-01 | 60000 | -210 | 59790 | 59790 | 100% | 0 | 0 | 0 | 4500 | -16 | 4484.25 | -0.25 | 0 | Financially completed in 2014. | Completed in 2012. Pending payments have been made. | 2009 |  | Investment
FIN | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for commercial refrigerators | Multi-year | LAC | DOM | FOA | 61 | INV | 46 | N | I | HCFC | 3.7 | 3.7 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-01-01 |  | 2012-10-01 | 2014-02-01 | 332775 | 0 | 332775 | 332736 | 99.99% | 39 | 0 | 0 | 24958 | 0 | 24955.0375 | 2.9625 | 0 | Financially completed in 2014. | Completed in 2012. Cyclopentane is now being used on a commercial scale in FARCO. | 2010 |  | Investment
FIN | UNDP | National halon bank management plan development | Individual | LAC | DOM | HAL | 38 | TAS | 32 | N | I | Halon | 3 | 3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2007-12-01 | 2011-11-01 | 40000 | -6495 | 33505 | 33505 | 100% | 0 | 0 | 0 | 5200 | -844 | 4355.65 | 0.35 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | National halon bank management plan update | Individual | LAC | DOM | HAL | 51 | TAS | 39 | N | I | Halons | 1.2 | 1.2 | 0 | 0 | 2007-03-01 | 2013-03-01 | 2011-01-01 |  | 2013-12-01 | 2014-02-01 | 20000 | -48 | 19952 | 19952 | 100% | 0 | 0 | 0 | 1800 | -4 | 1795.68 | 0.32 | 0 | Financially completed in 2014. | Completed in 2013. Project has started procedures to be operationally closed. | 2007 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | DOM | PHA | 42 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-05-01 | 2006-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 563 | 0 | 563 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: 2005 annual implementation programme | Multi-Year | LAC | DOM | PHA | 45 | INV | 36 | N | I | CFC | 41.3 | 41.3 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-12-01 | 2013-03-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (second tranche) | Multi-Year | LAC | DOM | PHA | 48 | INV | 38 | N | I | CFC | 171 | 171 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-07-01 | 2013-09-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (third tranche) | Multi-Year | LAC | DOM | PHA | 51 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-01-01 | 2009-03-01 |  | 2008-12-01 | 2013-02-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fourth tranche) | Multi-Year | LAC | DOM | PHA | 54 | INV | 41 | N | I | CFC | 28 | 28 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 | 2013-08-01 | 211600 | 0 | 211600 | 211600 | 100% | 0 | 0 | 0 | 15870 | 0 | 15870 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | DOM | PHA | 55 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 |  | 2012-05-01 | 2014-03-01 | 150000 | -1665 | 148335 | 148335 | 100% | 0 | 0 | 0 | 11250 | -125 | 11125.125 | -0.125 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fifth tranche) | Multi-Year | LAC | DOM | PHA | 58 | INV | 45 | N | I | CFC | 70.9 | 70.9 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2012-05-01 | 2014-02-01 | 200000 | -8158 | 191842 | 191842 | 100% | 0 | 0 | 0 | 15000 | -612 | 14388.15 | -0.15 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. No activities in 2013. | 2009 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector) | Multi-year | LAC | DOM | PHA | 65 | INV | 48 | N | I | HCFC | 8.2 | 8.2 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 |  | 2014-11-01 |  | 343468 | 0 | 343468 | 343468 | 100% | 0 | 0 | 0 | 25760 | 0 | 25760 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the conversion activities in the foam production sector continued. The milestone of converting 4 enterprises was achieved. Installation process of 2 injection machines in 2 of the main producers was conducted. One mission from the intenational expert was conducted to support conversion process. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in May 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, follow up to HCFC-free production on commercial refrigeration companies and installation of new equipment is being conducted. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 65 | INV | 49 | N | I | HCFC | 0.6 | 0.2 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 | 2016-10-01 |  |  | 336532 | 0 | 336532 | 305647 | 90.82% | 30885 | 0 | 12354.128 | 25240 | 0 | 22923.5918 | 2316.4082 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the planned milestone of implementing the MOA with INFOTEP was achieved, 600 technicians trained and 25 courses carried out. 3 training centers were strengthened. It is worth noting that the Legal framework for certification of refrigeration technicians was agreed between stakeholders and launched during Ozone Day celebration. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in May 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Third tranche requested and approved. Implementation of MOA with Infotep continues. 3 workshops to End-users and refrigeration technicians were conducted. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector) | Multi-year | LAC | DOM | PHA | 69 | INV | 53 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-12-01 | 2015-04-01 | 2016-02-01 |  |  | 319982 | 0 | 319982 | 100804 | 31.5% | 219178 | 0 | 87671.044 | 23999 | 0 | 7560.4395 | 16438.5605 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the conversion activities in the foam production sector continued. The milestone of converting 4 enterprises was achieved. Installation process of 2 injection machines in 2 of the main producers was conducted. One mission from the intenational expert was conducted to support conversion process. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in December 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Instalation of injection machines completed in Paredomi. Finals trials conducted in 2 doors manufacturers facilities. Workshop with PU suppliers and end-users to disseminate new regulation on HCFC-141b based systems. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 69 | INV | 54 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 |  | 2015-04-01 | 2016-03-01 |  |  | 143468 | 0 | 143468 | 0 | 0% | 143468 | 0 | 57387.2 | 10760 | 0 | 0 | 10760 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the planned milestone of implementing the MOA with INFOTEP was achieved, 600 technicians trained and 25 courses carried out. 3 training centers were strengthened. It is worth noting that the Legal framework for certification of refrigeration technicians was agreed between stakeholders and launched during Ozone Day celebration. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement has not taken place yet. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Third tranche requested and approved. Implementation of MOA with Infotep continues. 3 workshops to End-users and refrigeration technicians were conducted. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | DOM | PHA | 72 | PRP | 55 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4200 | 0 | 0 | 4200 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included establishing of project implementation team, review o information on HCFC consuming sector collected by other PRP projects. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:0 of 1. First disbursement date (actual/planned):First payment will be made at the beginning of 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 2015 workplan is under implementation. Information on HCFC consumptions is being gathered, draft of 2nd stage HPMP strategy prepared and under discussion. |  |  | Investment
FIN | UNDP | Demonstration project in commercial refrigeration (food storage, distribution and retailing) | RMP-Component | LAC | DOM | REF | 18 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-04-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | DOM | REF | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Fabrica de Refrigeradores Comerciales, C.A. (Farco) | Individual | LAC | DOM | REF | 22 | INV | 09 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-11-01 | 2000-07-01 | 423209 | -2883 | 420326 | 420326 | 100% | 0 | 0 | 0 | 55017 | -375 | 54642.38 | -0.38 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sub-sector | Individual | LAC | DOM | REF | 22 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Metalgas S.A. by replacement with HCFC-141b and HFC-134a respectively | Individual | LAC | DOM | REF | 24 | INV | 11 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 1999-12-01 | 2001-12-01 | 316368 | -3741 | 312627 | 312627 | 100% | 0 | 0 | 0 | 41128 | -486 | 40641.84 | 0.16 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for one project in commercial refrigeration subsector | Individual | LAC | DOM | REF | 24 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Industria Continental, C.A. by replacement with HCFC-141b and HFC 134a respectively | Individual | LAC | DOM | REF | 25 | INV | 16 | A | I | CFC | 19.9 | 19.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-03-01 | 303200 | -2802 | 300398 | 300398 | 100% | 0 | 0 | 0 | 39416 | -364 | 39051.74 | 0.26 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | DOM | REF | 25 | TAS | 13 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 441482 | -49014 | 392468 | 392468 | 100% | 0 | 0 | 0 | 57393 | -6372 | 51020.84 | 0.16 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | DOM | REF | 25 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-01-01 | 2000-08-01 |  | 2003-09-01 | 2003-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Preparation of investment activities of the RMP | Individual | LAC | DOM | REF | 36 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation assistance in foams and refrigeration | Individual | LAC | DOM | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the solvent sector | Individual | LAC | DOM | SOL | 36 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | DRC | FOA | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Individual | AFR | DRC | FOA | 35 | INV | 06 | A | I | CFC | 38 | 38 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-11-01 | 2007-03-01 | 190820 | 0 | 190820 | 190820 | 100% | 0 | 0 | 0 | 24807 | 0 | 24806.6 | 0.4 | 0 | Completed in 2006. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slastock foam by conversion to methylene chloride at M.K. SPRL | Individual | AFR | DRC | FOA | 35 | INV | 07 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-04-01 | 149800 | 0 | 149800 | 149800 | 100% | 0 | 0 | 0 | 19474 | 0 | 19474 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock sector | Individual | AFR | DRC | FOA | 36 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by convesion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 10 | A | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-09-01 |  | 2005-12-01 | 2011-11-01 | 165670 | -25705 | 139965 | 139965 | 100% | 0 | 0 | 0 | 21537 | -3342 | 18195.45 | -0.45 | 0 | Completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 11 | A | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 75490 | 0 | 75490 | 75490 | 100% | 0 | 0 | 0 | 9814 | 0 | 9813.7 | 0.3 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 12 | A | I | CFC | 21 | 21 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 69920 | 0 | 69920 | 69920 | 100% | 0 | 0 | 0 | 9090 | 0 | 9089.6 | 0.4 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Formulation of terminal project in the foam sector | Individual | AFR | DRC | FOA | 39 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Terminal umbrella project for the foam sector | Individual | AFR | DRC | FOA | 41 | INV | 19 | N | I | CFC | 123 | 123 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2012-07-01 | 640820 | -22461 | 618359 | 618359 | 100% | 0 | 0 | 0 | 48062 | -1685 | 46377.4075 | -0.40745 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | AFR | DRC | PHA | 49 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 | 2013-02-01 | 193750 | 0 | 193750 | 193750 | 100% | 0 | 0 | 0 | 14531 | 0 | 14531 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | INV | 30 | N | I | CFC | 5 | 5 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-07-01 | 2013-01-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 | 0 | 5391 | 0 | 5391 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | National CFC phase-out plan (third tranche) | Multi-year | AFR | DRC | PHA | 61 | INV | 33 | N | I | CFC | 46.5 | 46.5 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2011-07-01 |  | 2011-12-01 | 2012-07-01 | 71875 | -8316 | 63559 | 63559 | 100% | 0 | 0 | 0 | 5391 | -624 | 4767.2567 | -0.25665 | 0 | Financially completed in 2012. | Completed in 2011. | 2010 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | DRC | PHA | 63 | INV | 36 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 |  | 2013-12-01 | 2014-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Financially completed in 2014. | Completed in 2013. The planned milestone of determining the activities under Tranche 2 of the HPMP has been completed. The planned milestones will include delivery of the equipment in other regions of DRC and a support mission by UNDP and the Internation | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | DRC | PHA | 70 | INV | 37 | N | I | HCFC | 2.9 | 1.1 | 0 | 0 | 2013-07-01 | 2014-06-01 | 2015-07-01 | 2016-01-01 |  |  | 116000 | 0 | 116000 | 18525 | 15.97% | 97475 | 0 | 38990.164 | 10440 | 0 | 1667.2131 | 8772.7869 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This tranche was approved by the ExCom in July 2013. Up to the beginning of 2014, the first tranche of the project was being completed, and activities for the second tranche were initiated in the second half of 2014. A key part of the activities consists in the second set of procurement of equipment for the refrigeration servicing sector. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was expected to be signed in March 2014 and was signed on time. Missions undertaken (actual/planned):No missions planned in 2014 as they were not required in 2014. Missions will be conducted when equipment is received in DRC. TOR for consultants/subcontracts completed (actual/planned):Yes (1) - ToRs for the procurement were completed with the support and review of international consultant. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):The first disbursement took place in June 2014. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:A first procurement notice was launched in June 2014 but turned out to be unsuccessful. After review and improvement of the notice, in consultation with international consultant, the notice was issued again in September, this time successfully with several applications by international suppliers (under review/assessment by end 2014). | Since 2014, the equipment procurement process has been completed. Implementation is ongoing, with preparation of the next tranche submission and of the PRP request for Stage II, with the new NOU team in place in DRC. | 2013 |  | Investment
FIN | UNDP | Project preparation in recovery and recycling refrigeration sector | Individual | AFR | DRC | REF | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | DRC | REF | 39 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | DRC | REF | 41 | TAS | 16 | N | I | CFC | 13.1 | 13.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 437102 | -231 | 436871 | 436871 | 100% | 0 | 0 | 0 | 32783 | -17 | 32765.6748 | 0.3252 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for refrigeration end-user | Individual | AFR | DRC | REF | 45 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-07-01 | 2006-12-01 | 16870 | 0 | 16870 | 16870 | 100% | 0 | 0 | 0 | 1265 | 0 | 1265 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Training programme for the Montreal Protocol Project Implementation Unit | Individual | LAC | ECU | SEV | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-12-01 |  | 1994-06-01 | 1997-12-01 | 100000 | 40000 | 140000 | 140000 | 100% | 0 | 0 | 0 | 13000 | 5200 | 18200 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of flexible polyurethane foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 08 | INV | 05 | A | I | CFC | 121 | 121 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1993-10-01 |  | 1994-01-01 | 2003-04-01 | 497000 | 3489 | 500489 | 500489 | 100% | 0 | 0 | 0 | 64610 | 454 | 65063.57 | 0.43 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacturing of moulded, flexible, semi-rigid and rigid polyurethane foam at Taki-Vita factory | Individual | AFR | EGY | FOA | 08 | INV | 06 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1995-04-01 | 2003-04-01 | 293950 | 58550 | 352500 | 352500 | 100% | 0 | 0 | 0 | 38214 | 7612 | 45825 | 1 | 0 | Completed in 1995. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of moulded polyurethane foams at Technopol Egypt SAE | Individual | AFR | EGY | FOA | 08 | INV | 07 | A | I | CFC | 55 | 55 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-04-01 | 2003-04-01 | 645000 | 31211 | 676211 | 676211 | 100% | 0 | 0 | 0 | 83850 | 4057 | 87907.43 | -0.43 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at Al-Sharif Plastic Factories | Individual | AFR | EGY | FOA | 09 | INV | 10 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-03-01 | 1998-12-01 | 1994-06-01 |  | 2001-12-01 | 2003-04-01 | 498000 | -22472 | 475528 | 475528 | 100% | 0 | 0 | 0 | 64740 | -2921 | 61818.64 | 0.36 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of molded foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 09 | INV | 12 | A | I | CFC | 28 | 28 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1993-11-01 | 2003-04-01 | 275000 | 9431 | 284431 | 284431 | 100% | 0 | 0 | 0 | 35750 | 1226 | 36976.03 | -0.03 | 0 | Completed in 1993. Financially completed in 2003. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded flexible polyurethane foam at Modern Building Carpentry Co. (Mobica) | Individual | AFR | EGY | FOA | 10 | INV | 15 | A | I | CFC | 20 | 20 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 434000 | 0 | 434000 | 434000 | 100% | 0 | 0 | 0 | 56420 | 0 | 56420 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded rigid polyurethane foam at Cairo Light Industries Co. (Olympic Electric) | Individual | AFR | EGY | FOA | 10 | INV | 17 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-12-01 |  | 1995-11-01 | 2000-12-01 | 940000 | -28084 | 911916 | 911916 | 100% | 0 | 0 | 0 | 122200 | -3651 | 118549.08 | -0.08 | 0 | Completed in 1995. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of rigid polyurethane foam (PUF) at Specialized Engineering Contracting Co. | Individual | AFR | EGY | FOA | 11 | INV | 18 | A | I | CFC | 15 | 15 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1994-12-01 | 1998-12-01 | 85000 | -5398 | 79602 | 79602 | 100% | 0 | 0 | 0 | 11050 | -702 | 10348 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam at Alex Foam (formerly Dekheila Chemical Industries Co.) | Individual | AFR | EGY | FOA | 11 | INV | 19 | A | I | CFC | 130 | 130 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1995-11-01 | 1998-12-01 | 650000 | -82388 | 567612 | 567612 | 100% | 0 | 0 | 0 | 84500 | -10710 | 73790 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam (PUF) at Horse Foam Co. | Individual | AFR | EGY | FOA | 11 | INV | 20 | A | I | CFC | 120 | 120 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-08-01 |  | 1997-03-01 | 2000-07-01 | 385000 | -107636 | 277364 | 277364 | 100% | 0 | 0 | 0 | 50050 | -13993 | 36057.32 | -0.32 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | FOA | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-01-01 |  | 1994-12-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of flexible polyurethane foam at Foam Industrial and Hyma | Individual | AFR | EGY | FOA | 12 | INV | 22 | A | I | CFC | 170 | 170 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-06-01 |  | 1997-03-01 | 2000-07-01 | 525000 | -11898 | 513102 | 513102 | 100% | 0 | 0 | 0 | 68250 | -1547 | 66703.26 | -0.26 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of rigid molded and miscellaneous PUF at 5 plants: Tiba Air, Egat Company, Solar Energy Company, Ismailia Aluminum Company, and Fu Tech Company | Individual | AFR | EGY | FOA | 12 | INV | 26 | A | I | CFC | 44.2 | 44.2 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-03-01 | 1997-11-01 | 870000 | -107668 | 762332 | 762332 | 100% | 0 | 0 | 0 | 113100 | -13997 | 99102.87 | 0.13 | 0 | Completed in 1997. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Scib Chemical Company | Individual | AFR | EGY | FOA | 12 | INV | 27 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1995-11-01 | 2003-02-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at El Fateh | Individual | AFR | EGY | FOA | 12 | INV | 28 | A | I | CFC | 59 | 59 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2002-03-01 | 2003-01-01 | 496000 | -1 | 495999 | 495999 | 100% | 0 | 0 | 0 | 64480 | 0 | 64479.87 | 0.13 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Conversion to CFC free-technology at Industrial Engineering Company for Construction and Development (Icon) | Individual | AFR | EGY | FOA | 12 | INV | 29 | A | I | CFC | 51 | 51 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1999-10-01 | 2001-12-01 | 498000 | 0 | 498000 | 498000 | 100% | 0 | 0 | 0 | 64740 | 0 | 64740 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacturing of rigid PUF at seven enterprises: GMC, Petrojet, Modern Products, Cairo General Contractors Co., Egyptian Solar Energy, Tawifika, Helwan | Individual | AFR | EGY | FOA | 15 | INV | 36 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 2000-12-01 | 2002-11-01 | 780000 | -292655 | 487345 | 487345 | 100% | 0 | 0 | 0 | 101400 | -38045 | 63354.85 | 0.15 | 0 | Completed in 2000. Financially completed in 2002. |  | 1994 | 1999-07-01 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF at El-Tawil Manufacturing Company | Individual | AFR | EGY | FOA | 15 | INV | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-12-01 |  |  | 2000-12-01 | 121000 | -91977 | 29023 | 29023 | 100% | 0 | 0 | 0 | 15730 | -11957 | 3773.26 | -0.26 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible molded PUF and integral skin foam at El Shabrawi | Individual | AFR | EGY | FOA | 18 | INV | 48 | A | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 1999-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | EGY | FOA | 21 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 40000 | -7520 | 32480 | 32480 | 100% | 0 | 0 | 0 | 5200 | -978 | 4222.4 | -0.4 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | Individual | AFR | EGY | FOA | 22 | INV | 64 | A | I | CFC | 319 | 319 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 2005-01-01 | 2007-01-01 | 1672000 | -18136 | 1653864 | 1653864 | 100% | 0 | 0 | 0 | 217360 | -2358 | 215002.32 | -0.32 | 0 | Completed in 2005. Financially completed in 2007. |  | 1997 | 2000-12-01 | Investment
FIN | UNDP | Preparation for validation of low-cost hydrocarbon in foams | Individual | AFR | EGY | FOA | 57 | PRP | 99 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 | 2012-04-01 | 30000 | -7208 | 22792 | 22792 | 100% | 0 | 0 | 0 | 2250 | -541 | 1709.4 | -0.4 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
ONG | UNDP | Validation/demonstration of low cost options for the use of hydrocarbons as foaming agent in the manufacture of polyurethane foams | Individual | AFR | EGY | FOA | 58 | DEM | 100 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-05-01 | 2010-07-01 | 2015-12-01 |  |  | 473000 | 0 | 473000 | 459257 | 97.09% | 13743 | 0 | 5497.2 | 35475 | 0 | 34444.275 | 1030.725 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, Dow still did not complete the follow-up agreed work because of restructuring at the main office in Italy and in Cairo, and further to difficult economic situations. Complementary report pending in case the project can be completed in the current situation. UNDP/NOU monitor situation regularly. Prodoc signed (actual/planned, yes/no and date):Yes - Oct 2009. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):N/A, contracts issued previously. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in May 2010. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Previous restructuring changes at Dow have not been helpful to the project completion. UNDP/NOU are monitoring the situation regularly. | Missions by senior foam expert held in April and May 2015. Due to yet unresolved difficulties with DOW institutional changes, no substantial progress had been achieved with additional tests to complete the complementary report's findings on additional operational costs savings. Currently, the complementary report is being finalized with existing data for submission to the 75th ExCom. The project is set for closure. | 2009 |  | Non-Investment
COM | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at MOG for Engineering and Industry | Multi-year | AFR | EGY | FOA | 62 | INV | 105 | N | I | HCFC | 13.9 | 13.9 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-06-01 |  | 2014-06-01 |  | 790400 | 0 | 790400 | 790400 | 100% | 0 | 0 | 0 | 59280 | 0 | 59280 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, equipment was installed but not commissioned. Project ready for commissioning and safety inspection. Hand-over protocol is planned to be signed during next regular technical oversight during Q1/2 of 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):Yes, previously on equipment supply. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in April 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | MOG is awaiting instructions on local works from the technology supplier before starting. | 2010 |  | Investment
FIN | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane rigid insulation foam for water heaters at Fresh Electric for Home Appliances | Multi-year | AFR | EGY | FOA | 62 | INV | 106 | N | I | HCFC | 2.4 | 2.4 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2013-12-01 | 2014-08-01 | 124500 | 0 | 124500 | 124500 | 100% | 0 | 0 | 0 | 11205 | 0 | 11205 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Equipment has arrived to FRESH, and is expected for installation in April 2014. | 2010 |  | Investment
COM | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane spray foams at Specialized Engineering Contracting Co. | Multi-year | AFR | EGY | FOA | 62 | INV | 107 | N | I | HCFC | 11.2 | 11.2 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2014-09-01 |  | 178000 | 0 | 178000 | 178000 | 100% | 0 | 0 | 0 | 16020 | 0 | 16020 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the project at SECC was completed, with hand-over protocol signed for the equipment, and one remaining payment related to IOCs which was in process. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):Yes, previously on equipment supply. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Project is expected for completion after the next milestone is completed, which is the next visit of international expert in Q2 2014. | 2010 |  | Investment
COM | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at Cairo Foam | Multi-year | AFR | EGY | FOA | 62 | INV | 108 | N | I | HCFC | 9.9 | 9.9 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2014-09-01 |  | 386100 | 0 | 386100 | 386100 | 100% | 0 | 0 | 0 | 28958 | 0 | 28958 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the equipment was installed and comissioned, including modification for the mixing head's carriage mechanism which was advised during a previous technical visit. Hand-over protocol to be signed during next regular technical mission during Q1/2 of 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):Yes, previously on equipment supply. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Technicians from the supplier are waiting for security clearance for travel to Egypt, before they can visit to oversee installation works. | 2010 |  | Investment
CLO | UNDP | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and curcubits) | Individual | AFR | EGY | FUM | 24 | PRP | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 1998-07-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
FIN | UNDP | Technical assistance to prepare a national halon action plan and project development | Individual | AFR | EGY | HAL | 12 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-01-01 |  | 1997-03-01 | 1998-12-01 | 25000 | 1730 | 26730 | 26730 | 100% | 0 | 0 | 0 | 3250 | 225 | 3474.9 | 0.1 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation to prepare one halon sector programme | Individual | AFR | EGY | HAL | 24 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 2000-10-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Halon management bank programme | Individual | AFR | EGY | HAL | 32 | TAS | 81 | N | I | Halon | 754 | 754 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 405000 | -3894 | 401106 | 401106 | 100% | 0 | 0 | 0 | 52650 | -506 | 52143.78 | 0.22 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-year | AFR | EGY | PHA | 65 | INV | 113 | N | I | HCFC | 42.1 | 42.1 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 | 2017-01-01 |  |  | 2000000 | 0 | 2000000 | 644794 | 32.24% | 1355206 | 0 | 542082.264 | 150000 | 0 | 48359.5755 | 101640.4245 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the Reftruck and Al Fateh projects were completed, with hand-over protocols signed and no residual pending payments remaining. Dow system house signed the MOA agreement and completed a first milestone on technology development. Technocom and Baalbaki system houses will be signing the MOAs in 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):Yes, previously on equipment supply, and MOAs with system houses. Contract/PO/MOA agreements signed:Yes, 2 of 2 for stand-alone and 1 of 3 for system houses. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Unstable situation in the country put limitations on some activities, and each mission required a special consideration and clearance by UNDSS. | Two missions completed in April and May 2015 by senior foam expert. All standalone conversion projects are now complete with the last safety audit done in May 2015. Currently, the focus is on system house level with two system houses (Dow-MidEast and Technocom) moving ahead under a signed MoA on HCFC-free formula development. Additional discussions being held with the remaining two system houses with facilitation of NOU-Egypt on signing agreed MoAs to start work in parallel to Dow-MidEast and Technocom. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-Year | AFR | EGY | PHA | 68 | INV | 117 | N | I | HCFC | 42.1 | 2 | 0 | 0 | 2012-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 2000000 | 0 | 2000000 | 0 | 0% | 2000000 | 0 | 800000 | 150000 | 0 | 0 | 150000 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This tranche was approved in December 2012. In 2014, the Reftruck and Al Fateh projects were completed, with hand-over protocols signed and no residual pending payments remaining. Dow system house signed the MOA agreement and completed a first milestone on technology development. Technocom and Baalbaki system houses will be signing the MOAs in 2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):Yes, previously on equipment supply, and MOAs with system houses. Contract/PO/MOA agreements signed:Yes, 2 of 2 for stand-alone and 1 of 3 for system houses. First disbursement date (actual/planned): Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Unstable situation in the country put limitations on some activities, and each mission required a special consideration and clearance by UNDSS. | Two missions completed in April and May 2015 by senior foam expert. All standalone conversion projects are now complete with the last safety audit done in May 2015. Currently, the focus is on system house level with two system houses (Dow-MidEast and Technocom) moving ahead under a signed MoA on HCFC-free formula development. Additional discussions being held with the remaining two system houses with facilitation of NOU-Egypt on signing agreed MoAs to start work in parallel to Dow-MidEast and Technocom. Additional visits planned for October 2015. | 2012 |  | Investment
FIN | UNDP | Phase-out of CFC in refrigeration at Koldair Company | Individual | AFR | EGY | REF | 08 | INV | 09 | A | I | CFC | 18 | 18 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-01-01 | 2003-04-01 | 272000 | -21979 | 250021 | 250021 | 100% | 0 | 0 | 0 | 35360 | -2857 | 32502.73 | 0.27 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Conversion to CFC free-technology Reftruck Company | Individual | AFR | EGY | REF | 12 | INV | 30 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1998-09-01 | 2002-11-01 | 385000 | -2692 | 382308 | 382308 | 100% | 0 | 0 | 0 | 50050 | -350 | 49700.04 | -0.04 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Misr Panel (Egyptian Company for Cold Storage Industries) | Individual | AFR | EGY | REF | 12 | INV | 31 | A | I | CFC | 74.4 | 74.4 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2001-03-01 | 2002-03-01 | 636000 | 0 | 636000 | 636000 | 100% | 0 | 0 | 0 | 82680 | 0 | 82680 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Royal Engineering, Co. | Individual | AFR | EGY | REF | 15 | INV | 44 | A | I | CFC | 20.3 | 20.3 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 539000 | -1790 | 537210 | 537210 | 100% | 0 | 0 | 0 | 70070 | -233 | 69837.2108 | -0.2108 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Port Said Metal Work, Co. (MOG) | Individual | AFR | EGY | REF | 15 | INV | 45 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1999-10-01 | 2003-02-01 | 484000 | 0 | 484000 | 484000 | 100% | 0 | 0 | 0 | 62920 | 0 | 62920 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at United Investment Corporation Inc. | Individual | AFR | EGY | REF | 18 | INV | 49 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1999-11-01 | 2003-11-01 | 493350 | -32495 | 460855 | 460855 | 100% | 0 | 0 | 0 | 64136 | -4224 | 59911.15 | 0.85 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refcat Compnay Inc. | Individual | AFR | EGY | REF | 18 | INV | 50 | A | I | CFC | 26.8 | 26.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 2000-12-01 | 409000 | -19 | 408981 | 408981 | 100% | 0 | 0 | 0 | 53170 | -2 | 53167.53 | 0.47 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at El-Mohandes | Individual | AFR | EGY | REF | 20 | INV | 58 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 2000-06-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Amiral | Individual | AFR | EGY | REF | 20 | INV | 59 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-06-01 | 1998-09-01 |  |  | 2003-11-01 | 160000 | -70081 | 89919 | 89919 | 100% | 0 | 0 | 0 | 20800 | -9111 | 11689 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
TRF | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | AFR | EGY | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Transferred in 2003. Financially Completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Study tours for officials from the Ministry of the Environment, and pre-feasibility study | Individual | AFR | EGY | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-02-01 |  | 1992-06-01 | 1997-12-01 | 51000 | -6910 | 44090 | 44090 | 100% | 0 | 0 | 0 | 6630 | -898 | 5731.7 | 0.3 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | AFR | EGY | SEV | 06 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1993-09-01 | 2003-04-01 | 100000 | 319 | 100319 | 100319 | 100% | 0 | 0 | 0 | 13000 | 41 | 13041.47 | -0.47 | 0 | Completed in 1993. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | SEV | 18 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
CLO | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | ELS | FOA | 24 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | ELS | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2012-05-01 | 2013-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | ELS | PHA | 48 | PRP | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-08-01 | 30000 | -4831 | 25169 | 25169 | 100% | 0 | 0 | 0 | 2250 | -362 | 1887.648 | 0.352 | 0 | Completed in 2007.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | ELS | PHA | 53 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-11-01 | 2013-07-01 | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ELS | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-06-01 | 2014-07-01 | 150000 | -135 | 149865 | 149865 | 100% | 0 | 0 | 0 | 11250 | -10 | 11239.87 | 0.13 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. Pending payments were made. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | INV | 26 | N | I | CFC | 46 | 46 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-06-01 | 2013-07-01 | 285000 | -5 | 284995 | 284995 | 100% | 0 | 0 | 0 | 21375 | 0 | 21374.625 | 0.375 | 0 | Financially completed in 2013. | Completed in 2011. Final activities under the TPMP completed. Follow up actions with hospitals and training institutions,. Training programme in the process of being updated to fully reflect requirements from HCFC phase out. Final invoices pending. | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase out of HCFC-141b in imported pre-blended polyols used in the foam manufacturing sector) | Multi-year | LAC | ELS | PHA | 65 | INV | 29 | N | I | HCFC | 4.9 | 3 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 | 2016-01-01 |  |  | 439277 | 0 | 439277 | 359679 | 81.88% | 79598 | 0 | 31839.36 | 32946 | 0 | 26976.0792 | 5969.9208 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the milestone of installing the equipment at Unimetal was achieved, the company converted to HC. Hecasa converted its production line to HCFC-free alternatives. A mission by the international expert was conducted to follow up project implementation and to verify Unimetal's conversion. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in July 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Material for trials was purchased and delivered to country, building where trials will be conducted was prepared; beneficiary company is ready for using MF system. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | INV | 30 | N | I | HCFC | 0.9 | 0.9 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 | 2015-11-01 |  |  | 91072 | 0 | 91072 | 85379 | 93.75% | 5693 | 0 | 2277.06 | 6830 | 0 | 6403.0763 | 426.9237 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the milestone of training on good refrigeration practices was achieved, NOU continued with training activities where courses on alternatives to HCFC were conducted. HCFC import quota for 2014 was established. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 2015 work plan is under implementation. Training of technicians on good refrigeration practices continues. Second tranche requested and approved. | 2011 |  | Investment
FIN | UNDP | Project preparation in the refrigeration sectors | Individual | LAC | ELS | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 45000 | -3239 | 41761 | 41761 | 100% | 0 | 0 | 0 | 5850 | -421 | 5428.93 | 0.07 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Prado, S.A. de C.V. | Individual | LAC | ELS | REF | 22 | INV | 03 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-06-01 | 2001-12-01 | 306229 | 0 | 306229 | 306229 | 100% | 0 | 0 | 0 | 39810 | 0 | 39809.77 | 0.23 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | ELS | REF | 25 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2002-01-01 | 2000-08-01 |  | 2003-06-01 | 2005-10-01 | 10500 | -1035 | 9465 | 9465 | 100% | 0 | 0 | 0 | 1365 | -135 | 1230 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | ELS | REF | 25 | TAS | 09 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-05-01 | 403925 | -26048 | 377877 | 377877 | 100% | 0 | 0 | 0 | 52510 | -3386 | 49124.01 | -0.01 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | LAC | ELS | REF | 37 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-11-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 2275 | 0 | 2275 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | RMP update: technical assistance for the refrigeration sector | Individual | LAC | ELS | REF | 42 | TAS | 13 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 231700 | -1 | 231699 | 231699 | 100% | 0 | 0 | 0 | 20853 | 0 | 20852.91 | 0.09 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | RMP update: monitoring programme | Individual | LAC | ELS | REF | 42 | TAS | 15 | N | I | CFC | 30.5 | 30.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-08-01 | 41000 | -485 | 40515 | 40515 | 100% | 0 | 0 | 0 | 3690 | -44 | 3646.35 | -0.35 | 0 | Completed in 2008.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2004 |  | Investment
FIN | UNDP | RMP update: technical assistance for certification and licensing of refrigeration technicians | Individual | LAC | ELS | REF | 42 | TRA | 14 | N | I | CFC | 57.6 | 57.6 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 77300 | -1 | 77299 | 77299 | 100% | 0 | 0 | 0 | 6957 | 0 | 6956.91 | 0.09 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
CLO | UNDP | Project preparation of the investment components of the RMP | Individual | AFR | ERI | REF | 47 | PRP | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  |  | 2007-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2005 |  | Investment
CLO | UNDP | Project preparation assistance | Individual | AFR | ETH | SEV | 17 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1997-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 17 | N | I | MeBr | 2.1 | 2.1 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2008-12-01 |  | 2011-10-01 | 2012-06-01 | 50000 | -1097 | 48903 | 48903 | 100% | 0 | 0 | 0 | 4500 | -99 | 4401.27 | -0.27 | 0 | Financially completed in 2012. | The project was financially closed at the end of February 12. | 2005 |  | Non-Investment
FIN | UNDP | Project preparation for complete ODS phase-out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2006-07-01 | 2009-12-01 | 16870 | -6870 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1265 | -515 | 749.8518 | 0.1482 | 0 | Completed in 2006. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Implementation of the TPMP (investment component) | One-off-Phaseout | ASP | FIJ | PHA | 47 | TAS | 15 | N | I | CFC | 0.5 | 0.5 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2012-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2012. |  | 2005 | 2009-12-01 | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 55 | PRP | 19 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-04-01 | 85000 | -1244 | 83756 | 83756 | 100% | 0 | 0 | 0 | 6375 | -93 | 6281.7 | 0.30005 | 0 | Financially completed in 2013. | Project Targeted for Completion in 2012. | 2008 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | FIJ | PHA | 65 | INV | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2014-11-01 |  | 2014-12-01 |  | 71800 | 0 | 71800 | 71028 | 98.92% | 772 | 0 | 617.968 | 6462 | 0 | 6392.4786 | 69.5214 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, R&R equipment were procured and distributed to beneficiaries. Second tranche of HPMP of Fiji was submitted to the 73rd Meeting along with the verification report. This was approved. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in April 2012 and actually signed in July 2012. Missions undertaken (actual/planned):1 Planned - 0 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned - 1 actual. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in October 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project activities are progressing satisfactorily. Second tranche preparation including verification targeted for completion by Q3 of 2014. | 2011 |  | Investment
COM | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 71 | TAS | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2015-12-01 |  | 2014-12-01 |  | 30000 | 0 | 30000 | 19499 | 65% | 10501 | 0 | 8400.592 | 2700 | 0 | 1754.9334 | 945.0666 | 0 | Remarks (Short narrative description of progress made (actual/planned)): Completed in 2014. In 2014, verification report was completed and submitted to the 73rd Excom. This was accepted by the Excom Prodoc signed (actual/planned, yes/no and date):N/A. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):1 Planned - 1 Actual. Contract/PO/MOA agreements signed:1 contract signed. First disbursement date (actual/planned):The first disbursement took place in August 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Implementation plan has been finalised and verification to be completed by Q3-2014 | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | FIJ | PHA | 73 | INV | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 37900 | 0 | 37900 | 0 | 0% | 37900 | 0 | 15160 | 3411 | 0 | 0 | 3411 | 0 | Newly Approved | Activities progressing satisfactorily. Government is working with Ozone Secretariat on baseline data change in line with decision of 73rd Excom meeting. | 2014 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | ASP | FIJ | REF | 29 | TAS | 04 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2007-02-01 | 96755 | -500 | 96255 | 96255 | 100% | 0 | 0 | 0 | 12578 | -65 | 12513.1508 | -0.1508 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | GAB | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-07-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2009-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | INV | 25 | N | I | CFC | 1.5 | 1.5 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-11-01 | 40000 | -6717 | 33283 | 33283 | 100% | 0 | 0 | 0 | 3600 | -605 | 2995.47 | -0.47 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | GAB | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-11-01 | 2002-03-01 | 20000 | -5395 | 14605 | 14605 | 100% | 0 | 0 | 0 | 2600 | -701 | 1898.65 | 0.35 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 26 | TAS | 06 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 1998-11-01 | 2001-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 232470 | -36306 | 196164 | 196164 | 100% | 0 | 0 | 0 | 30221 | -4720 | 25501.32 | -0.32 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GAB | REF | 26 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2002-01-01 | 2000-12-01 |  | 2003-07-01 | 2003-08-01 | 12100 | -1600 | 10500 | 10500 | 100% | 0 | 0 | 0 | 1573 | -208 | 1365 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | GAB | REF | 37 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 41 | TAS | 11 | N | I | CFC | 3.3 | 3.3 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2007-07-01 | 2011-12-01 | 60277 | 0 | 60277 | 60277 | 100% | 0 | 0 | 0 | 5425 | 0 | 5424.93 | 0.07 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | GAB | REF | 41 | TAS | 14 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2003-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2011-11-01 | 15000 | -772 | 14228 | 14228 | 100% | 0 | 0 | 0 | 1350 | -70 | 1280.52 | -0.52 | 0 | Completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | GAM | FOA | 21 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-05-01 | 2002-03-01 | 20000 | -6548 | 13452 | 13452 | 100% | 0 | 0 | 0 | 2600 | -851 | 1748.76 | 0.24 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Karan Foam Manufacturing Ltd. | Individual | AFR | GAM | FOA | 22 | INV | 06 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 63500 | -2619 | 60881 | 60881 | 100% | 0 | 0 | 0 | 8255 | -340 | 7914.53 | 0.47 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | GAM | PHA | 49 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -240 | 11760 | 11760 | 100% | 0 | 0 | 0 | 900 | -18 | 882 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | GAM | PHA | 53 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2008-12-01 | 2013-11-01 | 99500 | 0 | 99500 | 99500 | 100% | 0 | 0 | 0 | 8955 | 0 | 8955 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GAM | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2013-11-01 | 85000 | -8939 | 76061 | 76061 | 100% | 0 | 0 | 0 | 6375 | -670 | 5704.575 | 0.425 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | INV | 22 | N | I | CFC | 3.6 | 3.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-11-01 | 30500 | -3001 | 27499 | 27499 | 100% | 0 | 0 | 0 | 2745 | -270 | 2474.91 | 0.09 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | GBS | REF | 39 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance project for MAC and refrigeration service and end-user sub-sectors | RMP-Component | AFR | GBS | REF | 43 | TAS | 07 | N | I | CFC | 14.3 | 14.3 | 0 | 0 | 2004-07-01 | 2009-05-01 | 2006-07-01 |  | 2011-12-01 | 2014-03-01 | 282900 | -480 | 282420 | 282420 | 100% | 0 | 0 | 0 | 21218 | -36 | 21181.5 | 0.5 | 0 | Financially completed in 2014. | Final invoices pending. | 2004 |  | Investment
FIN | UNDP | Preparation of an ODS bank management and destruction demonstration project | Individual | EUR | GEO | DES | 64 | PRP | 32 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2012-07-01 |  | 2013-03-01 | 2014-10-01 | 30000 | -103 | 29897 | 29897 | 100% | 0 | 0 | 0 | 2250 | -8 | 2242.28 | -0.28 | 0 | Financially completed in 2014. | Completed in 2013. | 2011 |  | Non-Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | EUR | GEO | DES | 69 | DEM | 33 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2013-04-01 | 2014-04-01 | 2015-04-01 | 2015-04-01 |  |  | 55264 | 0 | 55264 | 14447 | 26.14% | 40817 | 0 | 16326.704 | 4974 | 0 | 1300.3143 | 3673.6857 | 0 | Remarks (Short narrative description of progress made (actual/planned)):All planned milestones for 2014 have been accomplished. i. e. after verification of the amount of the ODS waste, it was accumualted at a centralized location in Tbilisi, transferred to transport pressure containers and were exported to France for disposal by Tredi plant. Export and destruction of the waste was conducted by a Greek company Polyeco, which was selected through the international tender. This project co-disposed wastes under a larger sub-contract with Polyeco under a parallel GEF-UNDP project on obsolete POPs pesticides. The project team is awaiting for destruction certificates from Tredi, and will complete the project with final summary report. Prodoc signed (actual/planned, yes/no and date):Yes - 10 April 2014. Missions undertaken (actual/planned):1 mission was undertaken in April 2014. TOR for consultants/subcontracts completed (actual/planned):2 of 2: 1. with National Refrigeration Association; 2. with Polyeco (Greece) - hazardous waste management company. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in April 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | ODS waste destruction certificates received. NOU-Georgia and UNDP project team together will conduct a survey of available cement kilns which would be willing to upgrade their air-pollution control and ODS waste feed mechanisms to take such waste for disposal in future. Two storage cylinders are being purchased for the central R/R/R Center in Tbilisi to ensure additional waste has a place for accumulation and safe storage in future. Project will be closed after these two last activities. Final report will be completed in Q4 of 2015. | 2013 |  | Non-Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | EUR | GEO | PHA | 50 | INV | 22 | N | I | CFC | 4.8 | 4.8 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2009-11-01 |  | 2008-12-01 | 2011-10-01 | 216180 | 0 | 216180 | 216180 | 100% | 0 | 0 | 0 | 16214 | 0 | 16214 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | GEO | PHA | 53 | INV | 25 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2011-10-01 | 108820 | -82 | 108738 | 108738 | 100% | 0 | 0 | 0 | 8162 | -6 | 8155.8496 | 0.1504 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | GEO | PHA | 55 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2013-04-01 | 85000 | -1038 | 83962 | 83962 | 100% | 0 | 0 | 0 | 6375 | -78 | 6297.15 | -0.15 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | TPMP verification | Individual | EUR | GEO | PHA | 57 | TAS | 29 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 20000 | -136 | 19864 | 19864 | 100% | 0 | 0 | 0 | 1800 | -12 | 1787.76 | 0.24 | 0 | Completed. Fully formulated TPMP verification report was submitted to the MLF Secretariat in February 2010. Further, it was reviewed and approved at the 60th meeting of the Executive Committee (60/8). |  | 2009 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | GEO | PHA | 63 | INV | 30 | N | I | HCFC | 0.7 | 0.1 | 0 | 0 | 2011-04-01 | 2013-04-01 | 2014-03-01 | 2015-03-01 |  |  | 200000 | 0 | 200000 | 199139 | 99.57% | 861 | 0 | 344.244 | 15000 | 0 | 14935.4543 | 64.5457 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the ODS related regulations were revised and recommendations, alongside with the relevant legislation packages, were developed in order to improve the certification system; to control service methods; to control and execute all types of legal issues related to ozone depleting substances (import/export permit, certification, service standard implementation, etc.). Survey for the correct management of the transferred equipment was conducted for National Refrigeration Association and R/R centers. Two (2) workshops were conducted with the stakeholders to get acquainted with the new ODS regulations and create awareness amongst attended staff on their role in enforcing Montreal Protocol at the national level. Training of Custom officers was conducted and a modern-type refrigerant analyzer (Pur-chek) purchased and handed over. Prodoc signed (actual/planned, yes/no and date):Yes - 29 March, 2012. Missions undertaken (actual/planned):1 mission was undertaken in April 2014. TOR for consultants/subcontracts completed (actual/planned):13 of 14, including on solvents, Code of practice, Customs, web-site etc. One planned for Q1 2015. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | The first tranche is complete as no funding is left. This project was operationally completed in March 2015. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | GEO | PHA | 72 | INV | 35 | N | I | HCFC | 0.5 | 0 | 0 | 0 | 2014-05-01 |  | 2017-05-01 | 2017-05-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 60000 | 11250 | 0 | 0 | 11250 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, training of Trainers in RAC sector was conducted and training materials were updated. A special aluminum welding machine tender was issued, which will be handed over to the central R/R center to further improve servicing and repair methods. After capacity assessment of the vocational schools, relevant support equipment purchased and handed over. Expanded awareness campaign in different regions targeted to the school children conducted. Prodoc signed (actual/planned, yes/no and date):Originally signed 28 March, 2012, and the second tranche approved in 2014 was attached to continue smooth HPMP implementation. Missions undertaken (actual/planned):1 mission was undertaken in April 2014. TOR for consultants/subcontracts completed (actual/planned):4 of 4, including for trainings, equipment supply, capacity assessment and awareness raising. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | NOU-Georgia and UNDP are currently conducting best practice trainings. One (1) training is complete in June 2015 in a vocational school SPEKTR. 15 people trained. In Eastern Georgia, 4 training sessions planned for 2015 for 80 technicians with certification. This is being done in support of a new legislation on technician certification that will be adopted in October 2015. Demonstration and diagnostic training stand (computer controlled: via a local or internet network from other colleges) is being designed by the Refrigeration Association for use in vocational colleges. A special article is prepared for two editions (August and September) of the National Geographic magazine along with 5 internet-based blogs devoted to the HCFC phaseout in Georgia. Welding machine for aluminum purchased and delivered to the R/R center in Kutaisi, and out 3 planned sets of R/R main and ancillary equipment 1 set purchased for Kutaisi R/R center to back the planned trainings on technician certification. |  |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | EUR | GEO | REF | 23 | TAS | 04 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 106750 | -2348 | 104402 | 104402 | 100% | 0 | 0 | 0 | 13878 | -305 | 13572.26 | 0.74 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | RMP-Component | EUR | GEO | REF | 35 | TAS | 10 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2005-01-01 |  | 2005-01-01 | 2007-06-01 | 101000 | -553 | 100447 | 100447 | 100% | 0 | 0 | 0 | 13130 | -72 | 13058.0463 | -0.0463 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | EUR | GEO | REF | 35 | TAS | 11 | N | I | No_ODP | 2.3 | 2.3 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2007-12-01 |  | 2005-12-01 | 2007-06-01 | 16350 | 0 | 16350 | 16350 | 100% | 0 | 0 | 0 | 2126 | 0 | 2125.5 | 0.5 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | GEO | REF | 57 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2010-12-01 | 2011-08-01 | 30000 | -1 | 29999 | 29999 | 100% | 0 | 0 | 0 | 2250 | 0 | 2249.925 | 0.075 | 0 | Completed in 2010. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 52 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-03-01 |  | 2009-12-01 | 2011-08-01 | 60667 | -40 | 60627 | 60627 | 100% | 0 | 0 | 0 | 4550 | -3 | 4547.0001 | -5.0021e-05 | 0 | Completed in 2009. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | GEO | SEV | 57 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-06-01 |  | 2011-12-01 | 2013-04-01 | 60667 | -47 | 60620 | 60620 | 100% | 0 | 0 | 0 | 4550 | -4 | 4546.475 | -0.47505 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | EUR | GEO | SEV | 63 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-06-01 |  | 2013-06-01 | 2014-12-01 | 60667 | -148 | 60519 | 60519 | 100% | 0 | 0 | 0 | 4550 | -11 | 4538.9 | 0.1 | 0 | Financially completed in 2014. | Completed in 2013. Funds in this IS phase exhausted | 2011 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | EUR | GEO | SEV | 69 | INS | 34 | N | I | non-HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2014-03-01 | 2015-06-01 | 2015-10-01 |  |  | 60667 | 0 | 60667 | 30268 | 49.89% | 30399 | 0 | 12159.768 | 4247 | 0 | 2118.8853 | 2128.1147 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Main activities in the reporting period included HCFC import and use monitoring, data collection, and reporting to Ozone Secretariat, coordination of the HPMP and ODS waste sub-programme, in partnership with a GEF financed POPs waste export from Georgia. Starting September 2014, a four-months nation-wide campaign “I care for Ozone” was launched which has been promoting ozone-friendly technologies, including a 30-minute dedicated video for kids. Training of Customs Officers was also completed, and successful work of the department was recognized by special awards. Prodoc signed (actual/planned, yes/no and date):Yes - 10 April, 2014. Missions undertaken (actual/planned):April 2014 to country/Two field trips in-country by project management unit to Kutaisi and Kobuleti on vocational schools. TOR for consultants/subcontracts completed (actual/planned):3 of 4 - public outreach expert in April 2014, two RAC training experts in November 2014, and one planned for March 2015 on ODS data imports. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in March 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve: | A campaign was held with students of art colleges to produce a special greeting card with the Ozone Day theme which will not be for sale as other cards, but will be circulated to key ministries and other stakeholders to raise awareness. Winners will receive special gifts and souvenirs (palletes, brush sets). NOU-Georgia has prepared for the celebrations on the Ozone Day in September. In April 2015, 15 Customs officers were trained in Tbilisi, and 20 officers in Western Georgia (Kutaisi). Art 7 data collection has been supported to enable NOU-Georgia to report to the Ozone Secretariat on the HCFC consumption for 2014. | 2013 |  | Non-Investment
FIN | UNDP | MDI transition strategy | Individual | AFR | GHA | ARS | 56 | TAS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-05-01 |  | 2009-12-01 | 2011-09-01 | 30000 | -41 | 29959 | 29959 | 100% | 0 | 0 | 0 | 2700 | -4 | 2696.31 | -0.31 | 0 | Completed in 2009. |  | 2008 |  | Non-Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 57 | PRP | 29 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-05-01 | 30000 | -4400 | 25600 | 25600 | 100% | 0 | 0 | 0 | 2250 | -330 | 1920 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 63 | DEM | 33 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-03-01 | 2015-12-01 |  |  | 198000 | 0 | 198000 | 136118 | 68.75% | 61882 | 0 | 24752.744 | 17820 | 0 | 12250.6326 | 5569.3674 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The project was approved in April 2011. It was planned for completion by end of 2014, with the export of the collected unwanted stocks of ODSs. In 2014, the collection of ODSs continued with two main sources of ODSs stocks: the old refrigerators obtained through the rebate scheme put in place by the GEF project for improved energy efficiency in the RAC sector; and the second-hand refrigerators seized by customs, since the new law banning the imports of second-hand refrigerators entered into effect. This second stream collected many refrigerators but those are often not filled with CFCs. The coordination was close in 2014 with the GEF project on PCB disposal, as a joint operation of export will be organised for disposal of the unwanted chemicals. However, although planned in 2014, the export did not occur as more time was also required to collect and store all the PCB stocks in the country. Prodoc signed (actual/planned, yes/no and date):Yes - July 2011. Missions undertaken (actual/planned):0/1. One mission was planned in 2014 but was cancelled due to medical reasons and it was not possible to re-schedule it in 2014. TOR for consultants/subcontracts completed (actual/planned):Ongoing national consultancy (for implementation of the project and monitoring of the storage sites). Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in November 2011. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Some difficulties were encountered with one of the two private sector partners of the project (collecting the Refrigerators coming from the rebate scheme) as this operator was locked out of its operating site by the owner of the site during a part of 2014. Some time was lost, as well as some of the project equipment (computer), which delayed the process. This has been tackled in order to finalise the project in 2015. | The cylinders containing refrigerants (seized ODSs in workshops and from customs, collected ones from the Energy efficiency rebate scheme, reaming stocks from the TPMP) have been grouped in one location in Accra, the Centre of Excellence, and are being safely transferred to transportable cylinders. The ODS export operation is imminent, in July 2015 (along with PCBs and pesticides as part of the GEF project on PCBs). Several options for addressing foam waste are being considered and compared at the moment. | 2011 |  | Non-Investment
FIN | UNDP | Technical assistance for technology transfer for phase-out of CFC-11 in flexible foam | Individual | AFR | GHA | FOA | 08 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1994-10-01 |  | 1995-06-01 | 1997-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Umbrella project for continuation of CFC free-technology in the manufacture of flexible polyurethane foam at Ashanti, Latex Foam, Nsawam and Prestige Foam | Individual | AFR | GHA | FOA | 12 | INV | 07 | A | I | CFC | 316 | 316 | 0 | 0 | 1994-03-01 | 1997-12-01 | 1994-12-01 |  | 2000-06-01 | 2001-12-01 | 345000 | -53650 | 291350 | 291350 | 100% | 0 | 0 | 0 | 44850 | -6974 | 37875.87 | 0.13 | 0 | Completed in 2000. Financially completed in 2001. |  | 1994 | 1999-08-01 | Investment
FIN | UNDP | Project preparation in soil fumigation (curcubits) | Individual | AFR | GHA | FUM | 33 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Training programme for terminal phase-out of methyl bromide use, excluding QPS applications | One-off-Phaseout | AFR | GHA | FUM | 37 | TRA | 18 | N | I | MeBr | 6.3 | 6.3 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  | 2006-12-01 | 2009-08-01 | 101550 | -799 | 100751 | 100751 | 100% | 0 | 0 | 0 | 13202 | -104 | 13097.63 | 0.37 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | GHA | PHA | 47 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-08-01 | 30000 | -609 | 29391 | 29391 | 100% | 0 | 0 | 0 | 2250 | -46 | 2204.325 | -0.325 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GHA | PHA | 50 | INV | 24 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2009-11-01 |  | 2008-11-01 | 2011-06-01 | 204394 | 0 | 204394 | 204394 | 100% | 0 | 0 | 0 | 15330 | 0 | 15330 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GHA | PHA | 53 | INV | 26 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-11-01 | 2011-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 | 0 | 10538 | 0 | 10538 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GHA | PHA | 55 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-07-01 | 2011-02-01 | 85000 | -2468 | 82532 | 82532 | 100% | 0 | 0 | 0 | 6375 | -185 | 6189.9001 | 0.09995 | 0 | Completed. HPMP submitted and approved at 61st meeting. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | AFR | GHA | PHA | 61 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2014-12-01 |  | 2012-12-01 | 2013-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | GHA | PHA | 67 | INV | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-07-01 | 2015-09-01 |  |  | 200000 | 0 | 200000 | 96121 | 48.06% | 103879 | 0 | 41551.616 | 15000 | 0 | 7209.072 | 7790.928 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This tranche was approved in July 2012. In 2014, the funding for the third tranche was requested and approved. In 2014, it was planned that all activities would be completed under this tranche, however, some activities are still being finalised, for example, the process of procurement of customs identifiers was initiated but not completed. The agreement for the Centre of Excellence at the Accra Technical Training Centre is now in place and the centre is available for trainings. Prodoc signed (actual/planned, yes/no and date):Yes - signed prior to 2014. Missions undertaken (actual/planned):0/1. One mission was planned in 2014 but was cancelled due to medical reasons and it was not possible to re-schedule it in 2014. TOR for consultants/subcontracts completed (actual/planned):Ongoing consultancies in place (international and national). Contract/PO/MOA agreements signed:Yes (in place). First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Most of the activities in this tranche required institutional agreements to be negotiated and agreed with partner institutions, leading to processes which have taken longer than planned initially. This background work is now completed and will allow for completion of the tranche activities in 2015. | Work on the procurement of the identifiers has been ongoing. Two missions have been completed to support implementation, in February and May-June 2015. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GHA | PHA | 72 | INV | 39 | N | I | HCFC | 4.4 | 0.9 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 190000 | 0 | 190000 | 0 | 0% | 190000 | 0 | 76000 | 14250 | 0 | 0 | 14250 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the activities for this tranche were planned and ready to be implemented, but were dependant on some outputs of Tranche 2 to be completed as pre-requisites. Prodoc signed (actual/planned, yes/no and date):No, will be signed in February 2015. Missions undertaken (actual/planned):0/1. One mission was planned in 2014 but was cancelled due to medical reasons and it was not possible to re-schedule it in 2014. TOR for consultants/subcontracts completed (actual/planned):Continuation of ongoing consultancies. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):No. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:There were some delays in the implementation of the prior tranche, which should be resolved and facilitate the implementation of this tranche. (which was approved in May 2014). | Work continued for the procurement of equipment, continued strengthening of the centre of excellence, and strengthening of the technicians' capacity. Customs training is being actively prepared. |  |  | Investment
TRF | UNDP | Refrigeration training programme for servicing technicians | RMP-Component | AFR | GHA | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-06-01 |  |  | 1993-06-01 | 99000 | -93800 | 5200 | 5200 | 100% | 0 | 0 | 0 | 12870 | -12194 | 676 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
FIN | UNDP | Improved servicing and maintenance within the refrigeration sector | RMP-Component | AFR | GHA | REF | 08 | TAS | 04 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-04-01 | 1998-12-01 | 328000 | 0 | 328000 | 328000 | 100% | 0 | 0 | 0 | 42640 | 0 | 42640 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Implementation of the RMP: Mobile air conditioning recovery and recycling of CFC-12 | RMP-Component | AFR | GHA | REF | 32 | TAS | 12 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-12-01 | 2006-10-01 | 98902 | -45 | 98857 | 98857 | 100% | 0 | 0 | 0 | 12857 | -6 | 12851.26 | -0.26 | 0 | Completed in 2003. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | AFR | GHA | REF | 32 | TAS | 14 | N | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2006-01-01 |  | 2006-12-01 | 2009-08-01 | 198000 | -1419 | 196581 | 196581 | 100% | 0 | 0 | 0 | 25740 | -184 | 25555.53 | 0.47 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GHA | REF | 32 | TAS | 16 | N | I | CFC | 1.2 | 1.2 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2007-12-01 | 2009-08-01 | 15455 | -11257 | 4198 | 4198 | 100% | 0 | 0 | 0 | 2009 | -1463 | 545.8493 | 0.1507 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | GHA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 160000 | 23200 | 183200 | 183200 | 100% | 0 | 0 | 0 | 20800 | 3016 | 23816 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | GHA | SEV | 20 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-12-01 | 1999-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | AFR | GHA | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2011-12-01 | 107000 | -7725 | 99275 | 99275 | 100% | 0 | 0 | 0 | 13910 | -1004 | 12905.75 | 0.25 | 0 | Completed in 2000. Financially completed in 2011. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | AFR | GHA | SEV | 32 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2003-02-01 | 2013-03-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (phase 5) | Individual | AFR | GHA | SEV | 38 | INS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2009-08-01 | 139100 | -860 | 138240 | 138240 | 100% | 0 | 0 | 0 | 18083 | -112 | 17971.2 | -0.2 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GHA | SEV | 43 | INS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2006-07-01 |  | 2006-12-01 | 2008-08-01 | 139100 | -272 | 138828 | 138828 | 100% | 0 | 0 | 0 | 10433 | -20 | 10412.599 | 0.401 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GHA | SEV | 50 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2011-09-01 | 139100 | -71 | 139029 | 139029 | 100% | 0 | 0 | 0 | 10433 | -5 | 10427.6747 | 0.32525 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | GHA | SEV | 56 | INS | 29 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-12-01 |  | 2010-12-01 | 2012-01-01 | 139100 | -117 | 138983 | 138983 | 100% | 0 | 0 | 0 | 10433 | -9 | 10424.2245 | -0.22455 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | GHA | SEV | 62 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2014-10-01 | 139100 | -1666 | 137434 | 137434 | 100% | 0 | 0 | 0 | 10433 | -125 | 10308.04 | -0.04 | 0 | Financially completed in 2014. | Completed in 2012. Some pending payments remaining. | 2010 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | GHA | SEV | 67 | INS | 36 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-02-01 | 2014-12-01 |  | 2014-12-01 |  | 139100 | 0 | 139100 | 133659 | 96.09% | 5441 | 0 | 4352.624 | 9737 | 0 | 9356.1454 | 380.8546 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. All planned outputs under this IS phase were achieved in 2014, and impementation of the activities allowed for Ghana to remain in compliance with its Montreal Protocol obligations. Priorities remained on the operation of the quota system, collection of data for reporting purposes (collected and transmitted on time by the NOU), consultation with partners, monitoring, participation in international meetings (Ghana was member of the Implementation Committee during this year). Specific awareness raising with schools was undertaken for 2014 International Ozone Day. Prodoc signed (actual/planned, yes/no and date):Yes - Dec 2012. Missions undertaken (actual/planned):0/1. One mission was planned in 2014 but was cancelled due to medical reasons and it was not possible to re-schedule it in 2014. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Work programme was agreed for 2014. Planned activities ongoing. Report on Phase 10 and Request for Phase 11 submitted for the consideration of ExCom 72. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 1/2015-12/2016) | Individual | AFR | GHA | SEV | 72 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-12-01 | 2017-01-01 |  |  | 139100 | 0 | 139100 | 0 | 0% | 139100 | 0 | 55640 | 9737 | 0 | 0 | 9737 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The previous phase of IS was completed in December 2014, new phase starting in January 2015. Prodoc signed (actual/planned, yes/no and date):No - the prodoc is expected to be signed in Feb 2015. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):No. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):The project's first disbursement is planned for February 2015.. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | ProDoc has been signed and regular activities (collection of data, awareness raising, support to project implementation, etc) are ongoing. |  |  | Non-Investment
FIN | UNDP | Technical assistance for the CTC sector | Individual | AFR | GHA | SOL | 44 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 20000 | -284 | 19716 | 19716 | 100% | 0 | 0 | 0 | 1800 | -26 | 1774.44 | -0.44 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Technical assistance in aerosol sector | Individual | GLO | GLO | ARS | 06 | TAS | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-02-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in flexible polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in rigid polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-01-01 |  | 1993-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in the Middle East/Africa | Individual | GLO | GLO | FOA | 06 | TRA | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-12-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -14413 | 38087 | 38087 | 100% | 0 | 0 | 0 | 6825 | -1874 | 4951.31 | -0.31 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Safety pre-assessment and post-assessment of foam and solvent projects implemented by UNDP | Individual | GLO | GLO | FOA | 12 | TAS | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 3000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3250 | 390 | 3640 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Determination of cost-effective phase-out approaches for enterprises with relatively small ODS use in foams | Individual | GLO | GLO | FOA | 14 | TAS | 71 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-09-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Technical assistance in halons | Individual | GLO | GLO | HAL | 06 | TAS | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-01-01 |  | 1994-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in the Middle East | Individual | GLO | GLO | HAL | 06 | TRA | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-02-01 |  | 1993-12-01 | 1997-12-01 | 60000 | -20988 | 39012 | 39012 | 100% | 0 | 0 | 0 | 7800 | -2728 | 5071.56 | 0.44 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Procurement of 40 halon recycling machines for demonstration | Individual | GLO | GLO | HAL | 07 | DEM | 25 | A | I | HAL | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-09-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global halon project | Individual | GLO | GLO | HAL | 08 | TAS | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1995-10-01 |  | 1997-12-01 | 1999-05-01 | 345133 | 0 | 345133 | 345133 | 100% | 0 | 0 | 0 | 44867 | 0 | 44867.29 | -0.29 | 0 | Completed in 1997. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Analysis and formulation of a halon action plan and phase out strategy for small consuming countries | Individual | GLO | GLO | HAL | 13 | TAS | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
CLO | UNDP | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 289 | A | I | HCFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-11-01 | 257000 | -257000 | 0 | 0 |  | 0 | 0 | 0 | 19275 | -19275 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2008. |  | 2008 |  | Investment
FIN | UNDP | Technical assistance in MAC | RMP-Component | GLO | GLO | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1998-01-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in refrigeration sector | RMP-Component | GLO | GLO | REF | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1994-02-01 |  | 1994-09-01 | 1997-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in the Middle East | RMP-Component | GLO | GLO | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1992-12-01 |  | 1996-06-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial and industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 06 | TRA | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Global MAC project | RMP-Component | GLO | GLO | REF | 08 | TAS | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1995-10-01 |  | 1995-12-01 | 1997-12-01 | 318584 | 0 | 318584 | 318584 | 100% | 0 | 0 | 0 | 41416 | 0 | 41415.92 | 0.08 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global MACs project: Phase 2 | RMP-Component | GLO | GLO | REF | 18 | TAS | 90 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1997-11-01 |  | 1999-05-01 | 2004-01-01 | 500000 | -1 | 499999 | 499999 | 100% | 0 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Preparation of refrigerant management plans (Bahamas, Bangladesh, Botswana, Dominican Republic, El Salvador, Gabon, Mozambique, Niger, Lesotho, Trinidad and Tobago) | Individual | GLO | GLO | REF | 22 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 140000 | -2 | 139998 | 139998 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Global MAC project: Phase III | RMP-Component | GLO | GLO | REF | 24 | TAS | 159 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2002-12-01 | 2003-12-01 | 250000 | -63356 | 186644 | 186644 | 100% | 0 | 0 | 0 | 32500 | -8236 | 24263.72 | 0.28 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Preparation of 6 projects in the recovery/recycling refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 204 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 6 projects in the end-user commercial refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 205 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2005-11-01 |  | 2005-12-01 | 2010-10-01 | 122000 | -919 | 121081 | 121081 | 100% | 0 | 0 | 0 | 9150 | -69 | 9081.0749 | -0.07495 | 0 | Financially completed in 2010. |  | 2005 |  | Investment
FIN | UNDP | Initial start-up costs | Individual | GLO | GLO | SEV | 04 | TAS | 256 | A | I | CFC | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1991-12-01 |  | 1992-12-01 | 2004-07-01 | 596500 | 0 | 596500 | 596500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1992. Financially completed in 2004. |  | 2004 |  | Investment
FIN | UNDP | Three national policy workshops | Individual | GLO | GLO | SEV | 06 | TRA | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1996-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Two study-tours for officials and industry representatives | Individual | GLO | GLO | SEV | 06 | TRA | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1998-04-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Participation at workshops and key metings | Individual | GLO | GLO | SEV | 06 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-10-01 |  | 1995-09-01 | 1997-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
CLO | UNDP | Advance for project preparation as indicated in the 1998 business plan | Individual | GLO | GLO | SEV | 23 | PRP | 154 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-03-01 |  |  | 1998-03-01 | 256000 | -256000 | 0 | 0 |  | 0 | 0 | 0 | 33280 | -33280 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
CLO | UNDP | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 176 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-03-01 |  |  | 1999-03-01 | 299000 | -299000 | 0 | 0 |  | 0 | 0 | 0 | 38870 | -38870 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1998 |  | Investment
CLO | UNDP | Project preparation advance for the year 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 190 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2003-09-01 | 250000 | -250000 | 0 | 0 |  | 0 | 0 | 0 | 32500 | -32500 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 227 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2001-12-01 |  |  | 2001-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2001. |  | 2001 |  | Investment
CLO | UNDP | Project preparation advance (2002) | Individual | GLO | GLO | SEV | 35 | PRP | 236 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2002-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2002 |  | Investment
FIN | UNDP | Core Unit Support (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 243 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Core Unit Support (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 249 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNDP | Core unit (2005) | Individual | GLO | GLO | SEV | 44 | TAS | 259 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNDP | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 271 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1700000 | 0 | 1700000 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNDP | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 278 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2013-08-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1751000 | 0 | 1751000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Non-Investment
FIN | UNDP | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 285 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2013-08-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1803530 | 0 | 1803530 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Non-Investment
FIN | UNDP | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 295 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-01 |  | 2009-12-01 | 2013-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1857636 | 0 | 1857636 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 301 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1913365 | 0 | 1913365 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
FIN | UNDP | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 304 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-01 |  | 2011-12-01 | 2013-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1970766 | 0 | 1970766 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
FIN | UNDP | Resource mobilization to maximize climate co-benefits | Individual | GLO | GLO | SEV | 63 | TAS | 306 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-04-01 | 2012-03-01 |  | 2013-12-01 | 2014-06-01 | 200000 | 0 | 200000 | 64899 | 32.45% | 135101 | 0 | 0 | 18000 | 0 | 5840.91 | 12159.09 | 0 | Financially completed in 2014. | Completed in 2013. | 2011 |  | Non-Investment
FIN | UNDP | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-01 |  | 2012-12-01 | 2013-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1984561 | 0 | 1984561 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-investment
FIN | UNDP | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 316 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 |  | 2013-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1998453 | 0 | 1998453 | 0 | 0 | Financially completed in 2013. |  | 2012 |  | Non-investment
COM | UNDP | Core unit budget (2014) | Individual | GLO | GLO | SEV | 71 | TAS | 322 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2014-12-01 |  | 2014-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2012442 | 0 | 2012442 | 0 | 0 | Operationally completed in 2014. |  | 2013 |  | Non-Investment
ONG | UNDP | Core unit budget (2015) | Individual | GLO | GLO | SEV | 73 | TAS | 324 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-01 | 2015-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2026529 | 0 | 0 | 2026529 | 0 | Newly Approved |  | 2014 |  | Non-Investment
FIN | UNDP | Technical assistance in solvents | Individual | GLO | GLO | SOL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | GRN | PHA | 49 | INV | 10 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-07-01 | 2013-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | LAC | GRN | PHA | 55 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2009-12-01 | 2013-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | INV | 16 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-11-01 |  | 2011-11-01 | 2014-05-01 | 30000 | -663 | 29337 | 29337 | 100% | 0 | 0 | 0 | 2700 | -60 | 2640.33 | -0.33 | 0 | Financially completed in 2014. | Completed in 2011. Equipment to support CFC phase-out procured and delivered to beneficiaries. | 2009 |  | Investment
FIN | UNDP | Implementation of the RMP: National recovery recycling project | RMP-Component | LAC | GRN | REF | 30 | TAS | 05 | A | I | CFC | 1.4 | 1.4 | 0 | 0 | 2000-03-01 | 2002-06-01 | 2001-10-01 |  | 2002-12-01 | 2003-11-01 | 33400 | 0 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4342 | 0 | 4342 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | GUA | FOA | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Construservicios, Aplitex, and Fiberglas & Plasticos | Individual | LAC | GUA | FOA | 23 | INV | 17 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 128500 | -15778 | 112722 | 112722 | 100% | 0 | 0 | 0 | 16705 | -2051 | 14653.86 | 0.14 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | GUA | PHA | 50 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-03-01 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | INV | 35 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2010-11-01 |  | 2013-12-01 | 2014-02-01 | 249000 | -43768 | 205232 | 205232 | 100% | 0 | 0 | 0 | 22410 | -3939 | 18470.88 | 0.12 | 0 | Financially completed in 2014. | Completed in 2013. Project team is preparing the PCR and the financial closure of the project. | 2008 |  | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industria Metalurgica Centroamericana S.A. (Imca) | Individual | LAC | GUA | REF | 15 | INV | 07 | A | I | CFC | 4 | 4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-07-01 | 2000-07-01 | 155017 | -5823 | 149194 | 149194 | 100% | 0 | 0 | 0 | 20152 | -757 | 19395.22 | -0.22 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Refrigeradores de Guatemala S.A. (Refrigua) | Individual | LAC | GUA | REF | 15 | INV | 08 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1996-10-01 | 1999-12-01 | 194866 | 0 | 194866 | 194866 | 100% | 0 | 0 | 0 | 25333 | 0 | 25332.58 | 0.42 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | GUA | REF | 18 | TAS | 09 | A | I | CFC | 26 | 26 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-12-01 | 2002-03-01 | 256780 | -19649 | 237131 | 237131 | 100% | 0 | 0 | 0 | 33381 | -2554 | 30827.03 | -0.03 | 0 | Completed in 1999. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at four enterprises (Exea S.A., Productos American Vitas S.A., Termomecanica S.A., Unirefri S.A.) | Individual | LAC | GUA | REF | 23 | INV | 16 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2002-03-01 | 212000 | -24132 | 187868 | 187868 | 100% | 0 | 0 | 0 | 27560 | -3137 | 24423.33 | -0.33 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | GUA | SEV | 11 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 30000 | 257 | 30257 | 30257 | 100% | 0 | 0 | 0 | 3900 | 33 | 3933.41 | -0.41 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment components) | Individual | AFR | GUI | REF | 42 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling programme (phase II) | RMP-Component | AFR | GUI | REF | 45 | TAS | 15 | N | I | CFC | 7.9 | 7.9 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2007-04-01 |  | 2007-10-01 | 2011-12-01 | 49890 | -6011 | 43879 | 43879 | 100% | 0 | 0 | 0 | 4490 | -541 | 3949.022 | -0.022001 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | GUY | PHA | 48 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-07-01 | 15000 | -12 | 14988 | 14988 | 100% | 0 | 0 | 0 | 1125 | -1 | 1124.1 | -0.1 | 0 | Completed in 2007.Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | GUY | PHA | 53 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-11-01 | 2013-02-01 | 124000 | 0 | 124000 | 124000 | 100% | 0 | 0 | 0 | 11160 | 0 | 11160 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | INV | 19 | N | I | CFC | 8 | 8 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2012-07-01 | 91000 | -476 | 90524 | 90524 | 100% | 0 | 0 | 0 | 8190 | -43 | 8147.16 | -0.16 | 0 | Financially completed in 2012. | Completed in 2011. Equipment procured and delivered to final beneficiaries. | 2009 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | INV | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-08-01 | 2012-03-01 |  | 2014-12-01 |  | 48000 | 0 | 48000 | 47998 | 100% | 2 | 0 | 1.744 | 4320 | 0 | 4319.8038 | 0.1962 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the equipment was procured and delivered to the country. Detailed information is in the Tranche Report submitted to the 74th ExCom Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in June 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in August 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Clarifications were requested for the bidders. Purchase Order is expected to be issued soon. | 2011 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | HAI | PHA | 54 | PRP | 11 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-01 |  | 2009-07-01 | 2011-11-01 | 15000 | -1826 | 13174 | 13174 | 100% | 0 | 0 | 0 | 1125 | -137 | 988.05 | -0.05 | 0 | Completed in 2009. |  | 2008 |  | Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | INV | 14 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2009-07-01 | 2013-12-01 | 2011-07-01 |  | 2014-12-01 |  | 150000 | 0 | 150000 | 61975 | 41.32% | 88025 | 71307.6 | 70419.752 | 13500 | 0 | 5577.7779 | 7922.2221 | 6417.684 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, the milestone of conducting 3 workshops was achieved. TOR for purchasing equipment for training centeres were prepared and equipment purchased. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2013. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in December 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Initial delays due to natural disaster (earthquake) and unrest in the country. UNDP conducted a mission to organize workplan and discuss with NOU project's scope and plan of action. | As planned, a workshop on good refrigeration practices was conducted. TOR for equipment for training centers under preparation. NOU consultants visited training facilities outside Port-au-Prince to evaluate their equipment needs. | 2009 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | HAI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the refrigerant management plan: recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | HAI | REF | 39 | TAS | 04 | A | I | CFC | 88.6 | 88.6 | 0 | 0 | 2003-04-01 | 2007-04-01 | 2006-04-01 |  | 2011-10-01 | 2014-03-01 | 220256 | -3239 | 217017 | 217017 | 100% | 0 | 0 | 0 | 19823 | -292 | 19531.53 | -0.53 | 0 | Financially completed in 2014. | Completed in 2011. Tools and equipment will be delivered to technicians once they have finalized training of local technicians organized by UNEP. | 2003 |  | Investment
FIN | UNDP | Implementation of the refrigerant management plan: monitoring the activities in the RMP | RMP-Component | LAC | HAI | REF | 39 | TAS | 06 | N | I | CFC | 11.8 | 11.8 | 0 | 0 | 2003-04-01 | 2008-02-01 | 2006-04-01 |  | 2010-08-01 | 2011-09-01 | 29400 | -2220 | 27180 | 27180 | 100% | 0 | 0 | 0 | 2646 | -200 | 2446.2 | -0.2 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Preparation of the RMP update proposal | RMP-Component | LAC | HON | REF | 41 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-09-01 | 15000 | -2000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1125 | -150 | 975 | 0 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance programme for the promotion of good practices and recovery and recycling | RMP-Component | LAC | HON | REF | 44 | TAS | 15 | N | I | CFC | 138.6 | 138.6 | 0 | 0 | 2004-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-11-01 | 2011-11-01 | 150000 | -72 | 149928 | 149928 | 100% | 0 | 0 | 0 | 13500 | -6 | 13493.52 | 0.48 | 0 | Completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Multi-year | ASP | IDS | ARS | 44 | INV | 167 | N | I | CFC | 80 | 80 | 0 | 0 | 2004-12-01 | 2005-11-01 | 2005-12-01 |  | 2006-06-01 | 2011-12-01 | 224000 | -42113 | 181887 | 181887 | 100% | 0 | 0 | 0 | 13440 | -2527 | 10913.22 | -0.22 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (fire-fighting manufacturing sector) | Individual | ASP | IDS | FFI | 72 | PRP | 205 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3500 | 0 | 0 | 3500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Stage II Preparation was approved in May 2014. HPMP PRP activities to be completed by Q3/Q4 of 2015. The consultant has been identified and survey TOR has also been finalised. Contracting process is underway. Prodoc signed (actual/planned, yes/no and date):Prodoc was signed in November 2014. Missions undertaken (actual/planned):1 Planned - 0 actual. TOR for consultants/subcontracts completed (actual/planned):2 Planned - 1 Actual. Contract/PO/MOA agreements signed:1 contract planned. First disbursement date (actual/planned):The first disbursement is expected to take place in June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation is ongoing including preparation of project for fire-fighting. Consultations held with NOU in Feb 2015 on the preparation activities. Projects are expected to be finalised in Q3-Q4 of 2015. |  |  | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF foam for cold storage at P.T. Fibrindo Carsa Pratama | Individual | ASP | IDS | FOA | 17 | INV | 32 | A | I | CFC | 11 | 11 | 0 | 0 | 1995-07-01 | 1997-03-01 | 1996-06-01 |  | 1997-12-01 | 2000-07-01 | 55000 | -5382 | 49618 | 49618 | 100% | 0 | 0 | 0 | 7150 | -700 | 6450.34 | -0.34 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for coolers/thermoware at P.T. Perdana Merah Delima | Individual | ASP | IDS | FOA | 18 | INV | 34 | A | R | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 1999-12-01 | 173000 | -1 | 172999 | 172999 | 100% | 0 | 0 | 0 | 22490 | 0 | 22489.87 | 0.13 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Alpine Cool | Individual | ASP | IDS | FOA | 20 | INV | 44 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 84000 | -268 | 83732 | 83732 | 100% | 0 | 0 | 0 | 10920 | -35 | 10885.16 | -0.16 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at PT Dithon Urethane | Individual | ASP | IDS | FOA | 20 | INV | 46 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-02-01 | 2000-07-01 | 184000 | -295 | 183705 | 183705 | 100% | 0 | 0 | 0 | 23920 | -38 | 23881.65 | 0.35 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Mentari Metal Pratama | Individual | ASP | IDS | FOA | 20 | INV | 47 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-09-01 |  | 1999-11-01 | 2001-12-01 | 47000 | -693 | 46307 | 46307 | 100% | 0 | 0 | 0 | 6110 | -90 | 6019.7549 | 0.2451 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at Plysindo Inter Mouldi (PIM) | Individual | ASP | IDS | FOA | 22 | INV | 60 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1997-09-01 | 2001-12-01 | 75870 | -1848 | 74022 | 74022 | 100% | 0 | 0 | 0 | 9863 | -240 | 9622.86 | 0.14 | 0 | Completed in 1997. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF insulated products at UD Samrow Foam | Individual | ASP | IDS | FOA | 23 | INV | 63 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-10-01 | 2001-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC -free technology in the manufacture of rigid polyurethane foam (panels, blocks) at PT Aneka Cool Citratama | Individual | ASP | IDS | FOA | 23 | INV | 65 | A | I | CFC | 32.7 | 32.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 232225 | -10678 | 221547 | 221547 | 100% | 0 | 0 | 0 | 30189 | -1388 | 28801.11 | -0.11 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at PT Dilihan Glory | Individual | ASP | IDS | FOA | 23 | INV | 67 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 102200 | -14362 | 87838 | 87838 | 100% | 0 | 0 | 0 | 13286 | -1867 | 11418.94 | 0.06 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray foam) at PT Ferrarindo Multi Sarana | Individual | ASP | IDS | FOA | 23 | INV | 68 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-07-01 | 32900 | -316 | 32584 | 32584 | 100% | 0 | 0 | 0 | 4277 | -41 | 4235.92 | 0.08 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
CLO | UNDP | Conversion to CFC-free techology in the manufacture of rigid PUF insulated thermoware at PT Langgeng Makmur Plastic Industry Ltd. | Individual | ASP | IDS | FOA | 23 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 142000 | -142000 | 0 | 0 |  | 0 | 0 | 0 | 18460 | -18460 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded and integral skin PUF at PT Archigramma | Individual | ASP | IDS | FOA | 23 | INV | 71 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 106625 | -14881 | 91744 | 91744 | 100% | 0 | 0 | 0 | 13861 | -1935 | 11926.72 | -0.72 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF spray insulation at Karya Cipta Semesta | Individual | ASP | IDS | FOA | 23 | INV | 81 | A | I | CFC | 16.4 | 16.4 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-12-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded PUF at Ciptaindah Jokindo | Individual | ASP | IDS | FOA | 23 | INV | 82 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 77125 | -58 | 77067 | 77067 | 100% | 0 | 0 | 0 | 10026 | -7 | 10018.93 | 0.07 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | IDS | FOA | 24 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray foam) at PT Sentras Varitima | Individual | ASP | IDS | FOA | 25 | INV | 86 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 1998-07-01 | 1999-07-01 | 2000-08-01 |  | 2000-07-01 | 2002-03-01 | 125000 | -5780 | 119220 | 119220 | 100% | 0 | 0 | 0 | 16250 | -751 | 15498.6 | 0.4 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converstion to CFC-free technology in the manufacture of rigid polyurethane spray foam at Metal Tunggal Prakarsamandiri | Individual | ASP | IDS | FOA | 25 | INV | 89 | A | I | CFC | 8 | 8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2002-10-01 | 43330 | 0 | 43330 | 43330 | 100% | 0 | 0 | 0 | 5633 | 0 | 5632.9 | 0.1 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converstion to CFC-free technolgoy in the manufacture of rigid polyurethane spray foam at Karya Sempati Sarana | Individual | ASP | IDS | FOA | 25 | INV | 91 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2004-01-01 | 45550 | 0 | 45550 | 45550 | 100% | 0 | 0 | 0 | 5922 | 0 | 5921.5 | 0.5 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Trisakti | Individual | ASP | IDS | FOA | 26 | INV | 100 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2003-03-01 | 80037 | -6557 | 73480 | 73480 | 100% | 0 | 0 | 0 | 10405 | -852 | 9552.4 | 0.6 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Mentari Adi Fayar | Individual | ASP | IDS | FOA | 26 | INV | 101 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-01-01 | 2004-01-01 | 111517 | 0 | 111517 | 111517 | 100% | 0 | 0 | 0 | 14497 | 0 | 14497.21 | -0.21 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at Irama Sejuk Santosa | Individual | ASP | IDS | FOA | 26 | INV | 103 | A | I | CFC | 7 | 7 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 54800 | -4604 | 50196 | 50196 | 100% | 0 | 0 | 0 | 7124 | -599 | 6525.48 | -0.48 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated boxes at P.T. Polidaya Fiberindo Indah | Individual | ASP | IDS | FOA | 26 | INV | 106 | A | I | CFC | 9.3 | 9.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 72800 | -8363 | 64437 | 64437 | 100% | 0 | 0 | 0 | 9464 | -1087 | 8376.81 | 0.19 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at PT Hanaria Indah | Individual | ASP | IDS | FOA | 26 | INV | 93 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 101352 | -18169 | 83183 | 83183 | 100% | 0 | 0 | 0 | 13176 | -2362 | 10813.79 | 0.21 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated panels at P.T. Panendra Sejati | Individual | ASP | IDS | FOA | 26 | INV | 95 | A | I | CFC | 20 | 20 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 156600 | -46830 | 109770 | 109770 | 100% | 0 | 0 | 0 | 20358 | -6088 | 14270.1 | -0.1 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Indoklima Sarana Engineering | Individual | ASP | IDS | FOA | 26 | INV | 96 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 212193 | -43243 | 168950 | 168950 | 100% | 0 | 0 | 0 | 27585 | -5622 | 21963.5 | -0.5 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Laksana | Individual | ASP | IDS | FOA | 26 | INV | 97 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-11-01 | 2004-01-01 | 122885 | -3 | 122882 | 122882 | 100% | 0 | 0 | 0 | 15975 | 0 | 15975.05 | -0.05 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Mekar Armada Jaya | Individual | ASP | IDS | FOA | 26 | INV | 98 | A | I | CFC | 24.9 | 24.9 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 149357 | -6055 | 143302 | 143302 | 100% | 0 | 0 | 0 | 19416 | -787 | 18629.26 | -0.26 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam, panels, blocks) at Tansri Gani | Individual | ASP | IDS | FOA | 29 | INV | 112 | A | I | CFC | 45.3 | 45.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2003-03-01 | 2005-09-01 | 354700 | -5045 | 349655 | 349655 | 100% | 0 | 0 | 0 | 46111 | -656 | 45455 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2003-07-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based systems and HCFC-141b in the manufacture of polyurethane foam for automotive and furniture applications at P.T. Yoska Prima Inti | Individual | ASP | IDS | FOA | 29 | INV | 114 | A | I | CFC | 49.5 | 49.5 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 368868 | -221866 | 147002 | 147002 | 100% | 0 | 0 | 0 | 47953 | -28843 | 19110.25 | -0.25 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at PT Kemenangan | Individual | ASP | IDS | FOA | 35 | INV | 126 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 104817 | -2098 | 102719 | 102719 | 100% | 0 | 0 | 0 | 13626 | -273 | 13353.21 | -0.21 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | IDS | PHA | 55 | PRP | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031 | 0 | 13031.25 | -0.25 | 0 | Completed in 2009. Financially completed in 2011. |  | 2008 |  | Investment
COM | UNDP | HCFC phase-out management plan (refrigeration sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 193 | N | I | HCFC | 24.4 | 24.4 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-03-01 |  | 2014-12-01 |  | 1802807 | 0 | 1802807 | 1802807 | 100% | 0 | 0 | 0 | 135210 | 0 | 135210 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, project implementation was undertaken satisfactory in large beneficiary enterprises. Most of the large enterprises completed all milestones defined under the project. Government has enacted regulations prohibiting use of HCFCs in manufacturing products as of 1 January 2015. Prodoc signed (actual/planned, yes/no and date):Prodoc was planned to be signed in March 2012 but actually signed in Aug 2012. Missions undertaken (actual/planned):3 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned - 2 actual. Contract/PO/MOA agreements signed:3 planned and 3 signed. First disbursement date (actual/planned):The first disbursement took place in May 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | As planned, the project activities are continued to be monitored. Technical consultations on availability of key components were held in Feburary 2014. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 195 | N | I | HCFC | 14.5 | 2 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2013-03-01 | 2016-06-01 |  |  | 1995519 | 52800 | 2048319 | 1179038 | 57.56% | 869281 | 16101.75 | 347712.524 | 149664 | 3960 | 88427.8699 | 65196.1301 | 1207.6318 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, project implementation was undertaken satisifactory in large beneficiary enterprises. Most of the large enterprises completed all milestones defined under the project. Government has enacted a regulations prohibiting use of HCFCs in manufacturing products as of 1 January 2015. Prodoc signed (actual/planned, yes/no and date):Prodoc was planned to be signed in March 2012 but actually signed in Aug 2012. Missions undertaken (actual/planned):3 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned - 2 actual. Contract/PO/MOA agreements signed:5 planned and 5 signed. First disbursement date (actual/planned):The first disbursement took place in November 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Government has successfully implemented regulations for prohibiting use of HCFCs in RAC manufacturing from 1 Jan 2015. Monitoring of HCFC consumption is ongoing satisfactorily. Third tranche would be submitted to the 75th Excom | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (project management and coordination) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | TAS | 192 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-03-01 | 2016-06-01 |  |  | 201674 | 0 | 201674 | 0 | 0% | 201674 | 0 | 80669.6 | 15126 | 0 | 0 | 15126 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, project activities are being monitored. Recruitment of PMU staff was completed and PMU along with IS project closely montor project implementation and regulations. Prodoc signed (actual/planned, yes/no and date):Prodoc was planned to be signed in March 2012 but actually signed in Aug 2012. Missions undertaken (actual/planned):3 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned - 2 actual. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in November 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | PMU activities are progressing satisfactorily. PMU continues to support project implementation and monitoirng. Verification for 2013 and 2014 are expected to be completed by August 2015. | 2011 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (refrigeration sector plan) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | INV | 198 | N | I | HCFC | 24.4 | 3.1 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 1802807 | 0 | 1802807 | 0 | 0% | 1802807 | 0 | 721122.8 | 135210 | 0 | 0 | 135210 | 0 | Remarks (Short narrative description of progress made (actual/planned)):See IDS-193. Technology challenges faced by small enterprises for safe and commercially viable alternative adoption are being addressed Prodoc signed (actual/planned, yes/no and date):Planned by April 2015. Missions undertaken (actual/planned):2 planned 2 actual. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:8 planned and not signed. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:NA - Technology challenges faced in RAC sector specifically on adoption of low GWP technologies.. | Government has successfully implemented regulations for prohibiting use of HCFCs in RAC manufacturing from 1 Jan 2015. Monitoring of HCFC consumption is ongoing satisfactorily. Third tranche would be submitted to the 75th Excom | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | INV | 199 | N | I | HCFC | 14.5 | 1.8 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 1995519 | 0 | 1995519 | 0 | 0% | 1995519 | 0 | 798207.6 | 149664 | 0 | 0 | 149664 | 0 | Remarks (Short narrative description of progress made (actual/planned)):See IDS-195. Technology challenges faced by small enterprises for safe and commercially viable alternative adoption are being addressed. Prodoc signed (actual/planned, yes/no and date):Planned by April 2015. Missions undertaken (actual/planned):2 planned 2 actual. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:8 planned and not signed. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:NA - Technology challenges faced in RAC sector specifically on adoption of low GWP technologies. | Government has successfully implemented regulations for prohibiting use of HCFCs in RAC manufacturing from 1 Jan 2015. Monitoring of HCFC consumption is ongoing satisfactorily. Third tranche would be submitted to the 75th Excom | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | TAS | 200 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 201674 | 0 | 201674 | 0 | 0% | 201674 | 0 | 80669.6 | 15126 | 0 | 0 | 15126 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, project activities are being monitored. Recruitment of PMU staff was completed and PMU along with IS project closely montor project implementation and regulations. Prodoc signed (actual/planned, yes/no and date):Planned by April 2015. Missions undertaken (actual/planned):2 planned 2 actual. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | PMU activities are progressing satisfactorily. PMU continues to support project implementation and monitoring. Verification for 2013 and 2014 are expected to be completed by August 2015. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IDS | PHA | 72 | PRP | 204 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 0 | 90000 | 6300 | 0 | 0 | 6300 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, discussions were held on preparation of overarching component. This is expected to be completed by Q3/Q4 of 2015. Consultant for preparation of project including service sector has been identified and contracting process is progress. Prodoc signed (actual/planned, yes/no and date):Prodoc was signed in November 2014. Missions undertaken (actual/planned):2 missions plannned and 1 undertalen. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 actual. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):No . If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. The strategy will be prepared by Q3/Q4 2015. |  |  | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | IDS | REF | 21 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at C.V. Kulkasindo | Individual | ASP | IDS | REF | 23 | INV | 66 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 136000 | -18594 | 117406 | 117406 | 100% | 0 | 0 | 0 | 17680 | -2417 | 15262.78 | 0.22 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IDS | REF | 24 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Supply conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Gaya Teknik | Individual | ASP | IDS | REF | 25 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-12-01 | 147880 | -2358 | 145522 | 145522 | 100% | 0 | 0 | 0 | 19224 | -307 | 18917.86 | -0.86 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Aneka Froze Citratama | Individual | ASP | IDS | REF | 25 | INV | 90 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 174255 | -17790 | 156465 | 156465 | 100% | 0 | 0 | 0 | 22653 | -2313 | 20340.45 | -0.45 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of CFC-11 and CFC-12/R-502 to HCFC-141b (foam) and HFC-134a/R404a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at P.T. Intermas Pacific | Individual | ASP | IDS | REF | 25 | INV | 92 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 209300 | -20993 | 188307 | 188307 | 100% | 0 | 0 | 0 | 27209 | -2730 | 24479.5 | -0.5 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Herry Alter's | Individual | ASP | IDS | REF | 26 | INV | 102 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 438060 | -15658 | 422402 | 422402 | 100% | 0 | 0 | 0 | 56948 | -2036 | 54912.26 | -0.26 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 3 enterprises: Bali Cool, Centrum Cool and Ever Cool | Individual | ASP | IDS | REF | 26 | INV | 104 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 231800 | -1729 | 230071 | 230071 | 100% | 0 | 0 | 0 | 30134 | -225 | 29909.23 | -0.23 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, CFC-12 to HFC-134a and R-502 to R-404A technology in the manufacture of commercial refrigeration equipment at PT Algron | Individual | ASP | IDS | REF | 26 | INV | 105 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-11-01 | 158210 | 0 | 158210 | 158210 | 100% | 0 | 0 | 0 | 20567 | 0 | 20567.3 | -0.3 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Tesaguna Sejati | Individual | ASP | IDS | REF | 26 | INV | 99 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 147900 | 0 | 147900 | 147900 | 100% | 0 | 0 | 0 | 19227 | 0 | 19227 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IDS | REF | 33 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Nikoteknik | Individual | ASP | IDS | REF | 35 | INV | 131 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 238903 | -19314 | 219589 | 219589 | 100% | 0 | 0 | 0 | 31057 | -2511 | 28546.39 | -0.39 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Sapporo Mestika | Individual | ASP | IDS | REF | 35 | INV | 132 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 153768 | -4603 | 149165 | 149165 | 100% | 0 | 0 | 0 | 19990 | -598 | 19391.84 | 0.16 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Hatindo Metal Utama | Individual | ASP | IDS | REF | 35 | INV | 133 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2006-10-01 | 145894 | 0 | 145894 | 145894 | 100% | 0 | 0 | 0 | 18966 | 0 | 18966.22 | -0.22 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Leoindo Kreasi | Individual | ASP | IDS | REF | 35 | INV | 134 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 119394 | -4838 | 114556 | 114556 | 100% | 0 | 0 | 0 | 15521 | -629 | 14892.22 | -0.22 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Alfa Metalindo Agra | Individual | ASP | IDS | REF | 35 | INV | 135 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 146960 | -3500 | 143460 | 143460 | 100% | 0 | 0 | 0 | 19105 | -455 | 18649.8 | 0.2 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Gastro Gizi Sarana | Individual | ASP | IDS | REF | 35 | INV | 136 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 221049 | -6055 | 214994 | 214994 | 100% | 0 | 0 | 0 | 28736 | -787 | 27949.37 | -0.37 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | IDS | REF | 36 | PRP | 137 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2740 | 17260 | 17260 | 100% | 0 | 0 | 0 | 2600 | -356 | 2243.8 | 0.2 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | ASP | IDS | REF | 36 | PRP | 138 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 35000 | -5430 | 29570 | 29570 | 100% | 0 | 0 | 0 | 4550 | -706 | 3844.1 | -0.1 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | Multi-Year | ASP | IDS | REF | 37 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-10-01 | 2002-12-01 |  | 2004-12-01 | 2013-04-01 | 1288000 | 0 | 1288000 | 1288000 | 100% | 0 | 0 | 0 | 111920 | 0 | 111920 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2004-12-01 | Investment
FIN | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | Multi-Year | ASP | IDS | REF | 38 | INV | 151 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2005-12-01 | 2013-01-01 | 2196758 | 0 | 2196758 | 2196758 | 100% | 0 | 0 | 0 | 195708 | 0 | 195708 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector ( 2nd tranche) | Multi-Year | ASP | IDS | REF | 40 | INV | 154 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-07-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2013-04-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 52900 | 0 | 52900 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (balance of second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 155 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-06-01 | 2013-04-01 | 1600000 | 0 | 1600000 | 1600000 | 100% | 0 | 0 | 0 | 141100 | 0 | 141100 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (servicing) sector (second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 157 | N | I | CFC | 200 | 200 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2004-12-01 |  | 2006-12-01 | 2013-02-01 | 1805987 | 0 | 1805987 | 1805987 | 100% | 0 | 0 | 0 | 160939 | 0 | 160939 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2006-12-01 | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 163 | N | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-12-01 | 2013-04-01 | 1762000 | 0 | 1762000 | 1762000 | 100% | 0 | 0 | 0 | 156900 | 0 | 156900 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 164 | N | I | CFC | 200 | 200 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-12-01 | 2013-01-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 43400 | 0 | 43400 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 174 | N | I | CFC | 300 | 300 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-12-01 | 2013-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 67500 | 0 | 67500 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 175 | N | I | CFC | 200 | 200 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2007-04-01 |  | 2008-12-01 | 2013-01-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21300 | 0 | 21300 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 177 | N | I | CFC | 300 | 300 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2009-03-01 |  | 2010-12-01 | 2013-04-01 | 217000 | 0 | 217000 | 217000 | 100% | 0 | 0 | 0 | 19530 | 0 | 19530 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 179 | N | I | CFC | 172 | 172 | 0 | 0 | 2007-03-01 | 2009-02-01 | 2009-03-01 |  | 2010-12-01 | 2013-02-01 | 159555 | -9048 | 150507 | 150507 | 100% | 0 | 0 | 0 | 13160 | -746 | 12413.7264 | 0.27355 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (sixth tranche) | Multi-Year | ASP | IDS | REF | 54 | INV | 181 | N | I | CFC | 241 | 241 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2011-12-01 | 2013-04-01 | 181000 | -6640 | 174360 | 174360 | 100% | 0 | 0 | 0 | 16290 | -598 | 15692.4 | -0.4 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IDS | REF | 57 | PRP | 185 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 5250 | 0 | 5250 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | IDS | REF | 57 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 | 2013-02-01 | 20000 | -3483 | 16517 | 16517 | 100% | 0 | 0 | 0 | 1500 | -261 | 1238.775 | 0.225 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection and Ozone Depleting Substances Phase-out Unit | Individual | ASP | IDS | SEV | 10 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 1997-06-01 | 2003-04-01 | 314780 | 0 | 314780 | 314780 | 100% | 0 | 0 | 0 | 40921 | 0 | 40921.4 | -0.4 | 0 | Completed in 1997. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 11 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1994-11-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance in solvent, halon and refrigeration sectors | Individual | ASP | IDS | SEV | 15 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-03-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IDS | SEV | 23 | INS | 80 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 208650 | -265 | 208385 | 208385 | 100% | 0 | 0 | 0 | 27125 | -34 | 27090.05 | 0.95 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (Phase III) | Individual | ASP | IDS | SEV | 32 | INS | 121 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2003-01-01 |  | 2004-09-01 | 2006-08-01 | 208650 | -86 | 208564 | 208564 | 100% | 0 | 0 | 0 | 27125 | -11 | 27113.37 | 0.63 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IDS | SEV | 41 | INS | 159 | N | I | No_ODP | 22.4 | 22.4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2011-11-01 | 271245 | -703 | 270542 | 270542 | 100% | 0 | 0 | 0 | 20343 | -53 | 20290.276 | -0.27595 | 0 | Completed in 2006. |  | 2003 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IDS | SEV | 45 | TAS | 169 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1541 | 8780.3064 | -0.3064 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IDS | SEV | 47 | INS | 171 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2011-11-01 | 271245 | -101 | 271144 | 271144 | 100% | 0 | 0 | 0 | 20343 | -8 | 20335.4251 | -0.4251 | 0 | Completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IDS | SEV | 53 | INS | 180 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-12-01 | 2012-07-01 | 271245 | 0 | 271245 | 271245 | 100% | 0 | 0 | 0 | 20343 | 0 | 20343 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IDS | SEV | 59 | INS | 189 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2011-12-01 |  | 2011-12-01 | 2013-04-01 | 135623 | 134546 | 270169 | 270169 | 100% | 0 | 0 | 0 | 10172 | 10091 | 20263.2228 | -0.2228 | 0 | Financially completed in 2013. | The project is being financially closed by June 12, and activities will continue under IS-VIII. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | IDS | SEV | 65 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2013-12-01 |  | 2013-12-01 |  | 271246 | 0 | 271246 | 269729 | 99.44% | 1517 | 0 | 1213.92 | 20343 | 0 | 20229.1975 | 113.8025 | 0 | Completed in 2013. During the year 2013, IS project activities were implemented as planned. Licensing of ODS imports was closely monitored. Ozone Office staff attended regional and global meeting for discussing policy and technical issues. Ozone Day celebrations for the year 2013 were also successfully completed. | Completed in 2013. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | ASP | IDS | SEV | 71 | INS | 201 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-07-01 | 2015-12-01 | 2016-01-01 |  |  | 271246 | 0 | 271246 | 101170 | 37.3% | 170076 | 0 | 68030.276 | 18987 | 0 | 7081.8396 | 11905.1604 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, as planned, the monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for 2013 was reported in timely manner. Prodoc signed (actual/planned, yes/no and date):Planned - May 2014 and Actual June 2014. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in July 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The activities have been implemented as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2013 |  | Non-Investment
CLO | UNDP | Elimination of the use of 111 TCA and CFC-113 in the manufacture of metal and plastic motorcycle parts at PT KGD Indonesia, Inc. | Individual | ASP | IDS | SOL | 15 | INV | 25 | A | R | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1996-02-01 |  |  | 1997-05-01 | 88000 | -88000 | 0 | 0 |  | 0 | 0 | 0 | 11440 | -11440 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 19 | DEM | 69 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-09-01 | 1997-06-01 |  | 2001-11-01 | 2002-03-01 | 0 | 168783 | 168783 | 168783 | 100% | 0 | 0 | 0 | 0 | 21942 | 21941.79 | 0.21 | 0 | Completed in 2001. Financially completed in 2002. |  | 1996 | 1998-04-01 | Non-Investment
FIN | UNDP | Ultra Tech Specialty Chemicals Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 115 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Texas Enterprises aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 117 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 70000 | -4903 | 65097 | 65097 | 100% | 0 | 0 | 0 | 9100 | -637 | 8462.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerol Formulations aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 118 | A | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -791 | 68659 | 68659 | 100% | 0 | 0 | 0 | 9029 | -103 | 8925.67 | 0.33 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerosols D'Asia Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 135 | A | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -2379 | 67071 | 67071 | 100% | 0 | 0 | 0 | 9029 | -309 | 8719.5 | 0.5 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Asian Aerosols Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 136 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 90890 | -7767 | 83123 | 83123 | 100% | 0 | 0 | 0 | 11816 | -1010 | 10805.7 | 0.3 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aero Pack Products aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 138 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-04-01 | 69450 | 0 | 69450 | 69450 | 100% | 0 | 0 | 0 | 9029 | 0 | 9028.5 | 0.5 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
CLO | UNDP | Meenakshi aerosol and cosmetics conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1998-06-01 |  |  | 1998-07-01 | 98940 | -98940 | 0 | 0 |  | 0 | 0 | 0 | 12862 | -12862 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
FIN | UNDP | Aerosol conversion at Sunder Chemical | Individual | ASP | IND | ARS | 24 | INV | 167 | A | I | CFC | 15 | 15 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 59892 | -3617 | 56275 | 56275 | 100% | 0 | 0 | 0 | 7786 | -470 | 7315.96 | 0.04 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Sara-Chem Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 171 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 89164 | -29723 | 59441 | 59441 | 100% | 0 | 0 | 0 | 11591 | -3864 | 7727.33 | -0.33 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Maja Cosmetics Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 172 | A | I | CFC | 31.3 | 31.3 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 125240 | -705 | 124535 | 124535 | 100% | 0 | 0 | 0 | 16281 | -92 | 16189.55 | -0.55 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Spray Products | Individual | ASP | IND | ARS | 24 | INV | 173 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 65486 | -2975 | 62511 | 62511 | 100% | 0 | 0 | 0 | 8513 | -387 | 8126.18 | -0.18 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Chem-Verse Consultants | Individual | ASP | IND | ARS | 24 | INV | 174 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 67324 | -1872 | 65452 | 65452 | 100% | 0 | 0 | 0 | 8752 | -243 | 8509.12 | -0.12 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol Conversion at Midas Care Pharmaceuticals | Individual | ASP | IND | ARS | 24 | INV | 179 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 110880 | -2729 | 108151 | 108151 | 100% | 0 | 0 | 0 | 14414 | -355 | 14059.4 | -0.4 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the aerosol sector | Individual | ASP | IND | ARS | 24 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-06-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of two projects in aerosol sector | Individual | ASP | IND | ARS | 27 | PRP | 201 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC at Vimsons Aerosol by substituting with HAPs | Individual | ASP | IND | ARS | 28 | INV | 213 | A | I | CTC/CFC | 18.2 | 18.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-03-01 | 2002-11-01 | 66500 | -18505 | 47995 | 47995 | 100% | 0 | 0 | 0 | 8645 | -2406 | 6239 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | Individual | ASP | IND | ARS | 28 | INV | 221 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2005-09-01 | 2007-01-01 | 161518 | -15270 | 146248 | 146248 | 100% | 0 | 0 | 0 | 20997 | -1985 | 19012.2721 | -0.2721 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC by substituting with HAPs at Ruby Aerosols | Individual | ASP | IND | ARS | 28 | INV | 227 | A | I | CTC/CFC | 22.2 | 22.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2002-01-01 | 2005-11-01 | 45800 | -16 | 45784 | 45784 | 100% | 0 | 0 | 0 | 5954 | -2 | 5951.92 | 0.079972 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | Individual | ASP | IND | ARS | 29 | TAS | 244 | A | I | CFC | 125 | 125 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2004-09-01 | 2008-04-01 | 155000 | -16537 | 138463 | 138463 | 100% | 0 | 0 | 0 | 20150 | -2150 | 18000.19 | -0.19 | 0 | Completed in 2004. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | IND | ARS | 33 | PRP | 298 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the aerosol sector | Individual | ASP | IND | ARS | 36 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777.06 | -0.06 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project in the aerosol sector | Individual | ASP | IND | ARS | 38 | INV | 358 | A | I | CTC/CFC | 132.5 | 132.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-11-01 |  | 2007-03-01 | 2013-08-01 | 583000 | 0 | 583000 | 583000 | 100% | 0 | 0 | 0 | 74130 | 0 | 74130 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | MDI Transitional Strategy | Individual | ASP | IND | ARS | 41 | TAS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2008-07-01 | 2011-11-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 2250 | -2250 | 0 | 0 | 0 | Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | IND | ARS | 52 | PRP | 411 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2008-07-01 | 2010-01-01 | 100000 | -23586 | 76414 | 76414 | 100% | 0 | 0 | 0 | 7500 | -1769 | 5731.05 | -0.05 | 0 | Financially completed in 2010. |  | 2007 |  | Investment
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 423 | N | I | CFC | 564.6 | 564.6 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2013-11-01 | 2015-12-01 |  |  | 8082267 | 0 | 8082267 | 7839990 | 97% | 242277 | 0 | 96910.796 | 606170 | 0 | 587999.2265 | 18170.7735 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the project completion activities were monitored by NOU. MFS evaluation mission reviewed the project and submitted a report indicating satisfactory implementation to the 72nd Excom. The project activities are expected to be completed in 2015. Prodoc signed (actual/planned, yes/no and date):Prodoc was signed in 2009. Missions undertaken (actual/planned):2 Planned - 2 actual. TOR for consultants/subcontracts completed (actual/planned):1 TOR planned and prepared. Contract/PO/MOA agreements signed:4 MOAs signed with beneficiaris. First disbursement date (actual/planned):The first disbursement took place in May 2009. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | All major project activities have been completed and only a few verification and administrative steps remaining for completion. Discussions were held on completion of pending activities and plan finalised in Jan 2015 for completing the projects by end of the year 2015. | 2008 |  | Investment |  | Continued Monitoring
FIN | UNDP | Preparation of a project for demonstration of a sustainable technological, financial and management model for disposal of ODS | Individual | ASP | IND | DES | 61 | PRP | 437 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2013-12-01 | 2014-07-01 | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | Financially completed in 2014. | Completed in 2013. Funds to be returned to MFS in 72 Excom. | 2010 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of extruded polyethylene foam sheet at Camphor and Allied Products Ltd. | Individual | ASP | IND | FOA | 12 | INV | 16 | A | R | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1995-12-01 | 1994-09-01 |  | 1995-12-01 | 1997-12-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF panels at Sunpra Ltd. | Individual | ASP | IND | FOA | 12 | INV | 17 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 414000 | -43773 | 370227 | 370227 | 100% | 0 | 0 | 0 | 53820 | -5690 | 48130 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Eagle Flasks Industries Ltd. | Individual | ASP | IND | FOA | 12 | INV | 18 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1995-03-01 |  | 1996-09-01 | 2000-12-01 | 365000 | -3745 | 361255 | 361255 | 100% | 0 | 0 | 0 | 47450 | -487 | 46963.15 | -0.15 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of phenolic foam at Bakelite Hylam Ltd. | Individual | ASP | IND | FOA | 13 | INV | 27 | A | I | CFC | 58 | 58 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1998-11-01 | 1999-12-01 | 367000 | 0 | 367000 | 367000 | 100% | 0 | 0 | 0 | 47710 | 0 | 47710 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of polyurethane foam at U-Foam Private Ltd. | Individual | ASP | IND | FOA | 13 | INV | 30 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1997-11-01 | 2000-12-01 | 328500 | -77822 | 250678 | 250678 | 100% | 0 | 0 | 0 | 42705 | -10117 | 32588.14 | -0.14 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | IND | FOA | 13 | TAS | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1998-07-01 | 1995-07-01 |  | 1999-12-01 | 2003-05-01 | 200000 | -1396 | 198604 | 198604 | 100% | 0 | 0 | 0 | 26000 | -181 | 25818.52 | 0.48 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
CLO | UNDP | Phase out of CFCs in the manufacture of cold cured molded PUF products at Autofit P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 103125 | -103125 | 0 | 0 |  | 0 | 0 | 0 | 13406 | -13406 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plastic Products | Individual | ASP | IND | FOA | 19 | INV | 71 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2000-12-01 | 2002-03-01 | 96000 | -889 | 95111 | 95111 | 100% | 0 | 0 | 0 | 12480 | -116 | 12364.43 | -0.43 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products in Inalsa Ltd. | Individual | ASP | IND | FOA | 19 | INV | 72 | A | I | CFC | 28.9 | 28.9 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2000-12-01 | 123000 | -4222 | 118778 | 118778 | 100% | 0 | 0 | 0 | 15990 | -549 | 15441.14 | -0.14 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products at Omkar PUF Insulation | Individual | ASP | IND | FOA | 19 | INV | 73 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 59000 | -151 | 58849 | 58849 | 100% | 0 | 0 | 0 | 7670 | -20 | 7650.37 | -0.37 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of cold cured molded and integral skin PUF products at Kaygee Foams P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 74 | A | I | CFC | 33 | 33 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 217250 | -1198 | 216052 | 216052 | 100% | 0 | 0 | 0 | 28243 | -156 | 28086.76 | 0.24 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Mahavir Enterprises | Individual | ASP | IND | FOA | 19 | INV | 75 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 2000-08-01 | 2001-12-01 | 94500 | -220 | 94280 | 94280 | 100% | 0 | 0 | 0 | 12285 | -29 | 12256.3924 | -0.3924 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Phase out of the CFCs in the manufacture of cold cured molded and integral skin PUF products at Preto Foams | Individual | ASP | IND | FOA | 19 | INV | 76 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-11-01 | 2000-12-01 | 167100 | -17268 | 149832 | 149832 | 100% | 0 | 0 | 0 | 21723 | -2245 | 19478.16 | -0.16 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF insulated thermoware at Asha Handicrafts (formerly Asian Advertisers) | Individual | ASP | IND | FOA | 19 | INV | 78 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 122500 | -6656 | 115844 | 115844 | 100% | 0 | 0 | 0 | 15925 | -865 | 15059.72 | 0.28 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured and integral skin PUF moldings at Amit Polyseats Ltd. | Individual | ASP | IND | FOA | 19 | INV | 79 | A | I | CFC | 19.3 | 19.3 | 0 | 0 | 1996-05-01 | 1996-10-01 | 1997-11-01 |  | 1997-06-01 | 2000-07-01 | 243000 | -28744 | 214256 | 214256 | 100% | 0 | 0 | 0 | 31590 | -3737 | 27853.28 | -0.28 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF spray insulation at Beardsell Ltd. | Individual | ASP | IND | FOA | 19 | INV | 80 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 1996-05-01 | 2000-05-01 | 1997-11-01 |  | 2000-11-01 | 2002-03-01 | 129000 | -19305 | 109695 | 109695 | 100% | 0 | 0 | 0 | 16770 | -2510 | 14260.35 | -0.35 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF products at Lloyd Insulations and Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 81 | A | I | CFC | 76.7 | 76.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-09-01 | 2000-12-01 | 500000 | -35883 | 464117 | 464117 | 100% | 0 | 0 | 0 | 65000 | -4665 | 60335.21 | -0.21 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Meenakshi Polymers Pvt. Ltd. | Individual | ASP | IND | FOA | 19 | INV | 82 | A | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1996-11-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 214000 | -38836 | 175164 | 175164 | 100% | 0 | 0 | 0 | 27820 | -5049 | 22771.32 | -0.32 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Punjab Scooters Ltd. | Individual | ASP | IND | FOA | 19 | INV | 83 | A | I | CFC | 39 | 39 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 312200 | -23972 | 288228 | 288228 | 100% | 0 | 0 | 0 | 40586 | -3116 | 37469.64 | 0.36 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Deccan Engineering Enterprises | Individual | ASP | IND | FOA | 20 | INV | 100 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 64000 | -3303 | 60697 | 60697 | 100% | 0 | 0 | 0 | 8320 | -429 | 7890.61 | 0.39 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of EPE foam products at Vora Cork Industries | Individual | ASP | IND | FOA | 20 | INV | 101 | A | I | CFC | 39.6 | 39.6 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 2003-07-01 | 2005-09-01 | 264500 | -52153 | 212347 | 212347 | 100% | 0 | 0 | 0 | 34385 | -6780 | 27605 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Best Plastronics P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 102 | A | I | CFC | 19.5 | 19.5 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 129000 | -35002 | 93998 | 93998 | 100% | 0 | 0 | 0 | 16770 | -4550 | 12220 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at Krishna Fabrications Ltd. | Individual | ASP | IND | FOA | 20 | INV | 103 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 164000 | -21543 | 142457 | 142457 | 100% | 0 | 0 | 0 | 21320 | -2801 | 18519.41 | -0.41 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Amar Enterprises | Individual | ASP | IND | FOA | 20 | INV | 96 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 120000 | -57 | 119943 | 119943 | 100% | 0 | 0 | 0 | 15600 | -7 | 15592.5896 | 0.4104 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plast | Individual | ASP | IND | FOA | 20 | INV | 97 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 71000 | -104 | 70896 | 70896 | 100% | 0 | 0 | 0 | 9230 | -14 | 9216.48 | -0.48 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Cottage Industries | Individual | ASP | IND | FOA | 20 | INV | 98 | A | I | CFC | 7.8 | 7.8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 61000 | -2047 | 58953 | 58953 | 100% | 0 | 0 | 0 | 7930 | -266 | 7663.89 | 0.11 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at K.B. Poly Industries P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 99 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 149000 | -19595 | 129405 | 129405 | 100% | 0 | 0 | 0 | 19370 | -2547 | 16823 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam chemical systems at Polymermann (Asia) P.Ltd. | Individual | ASP | IND | FOA | 22 | INV | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2003-11-01 | 385000 | -4930 | 380070 | 380070 | 100% | 0 | 0 | 0 | 50050 | -641 | 49409.1 | -0.1 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Blowkings | Individual | ASP | IND | FOA | 22 | INV | 128 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 132000 | -14394 | 117606 | 117606 | 100% | 0 | 0 | 0 | 17160 | -1871 | 15288.78 | 0.22 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Delta Foams Engineering Co. | Individual | ASP | IND | FOA | 22 | INV | 130 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 2001-12-01 | 85000 | -15226 | 69774 | 69774 | 100% | 0 | 0 | 0 | 11050 | -1979 | 9070.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Super Urethane Products P. Ltd. | Individual | ASP | IND | FOA | 22 | INV | 132 | A | I | CFC | 39.1 | 39.1 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 284000 | -36532 | 247468 | 247468 | 100% | 0 | 0 | 0 | 36920 | -4749 | 32171.13 | -0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam in small and medium-sized enterprises (SMEs) | Individual | ASP | IND | FOA | 22 | INV | 133 | A | I | CFC | 290 | 290 | 0 | 0 | 1997-05-01 | 1997-12-01 | 2000-06-01 |  | 2001-12-01 | 2003-03-01 | 1404000 | -79 | 1403921 | 1403921 | 100% | 0 | 0 | 0 | 182520 | -10 | 182510 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 2000-06-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Nissan Thermoware P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 143 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 111000 | -706 | 110294 | 110294 | 100% | 0 | 0 | 0 | 14430 | -92 | 14338.1524 | -0.1524 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Viral Corporation | Individual | ASP | IND | FOA | 23 | INV | 146 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 84000 | -2736 | 81264 | 81264 | 100% | 0 | 0 | 0 | 10920 | -356 | 10564 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible moulded cold-cured and integral skin PU foam at Venus Auto P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 147 | A | I | CFC | 21 | 21 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 137250 | -1155 | 136095 | 136095 | 100% | 0 | 0 | 0 | 17843 | -150 | 17692.2034 | 0.7966 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at Siddhi Polymer P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 148 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 75250 | -737 | 74513 | 74513 | 100% | 0 | 0 | 0 | 9783 | -96 | 9686.581 | 0.419 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured moulded and integral skin at Shri Krishna Polyurethane Industries P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 149 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-08-01 | 2002-11-01 | 192875 | -486 | 192389 | 192389 | 100% | 0 | 0 | 0 | 25074 | -63 | 25010.75 | 0.25 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Reliable Rotomoulders P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 150 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 63000 | -769 | 62231 | 62231 | 100% | 0 | 0 | 0 | 8190 | -100 | 8089.8879 | 0.1121 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Panna International | Individual | ASP | IND | FOA | 23 | INV | 151 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1998-12-01 | 2000-12-01 | 48000 | -19370 | 28630 | 28630 | 100% | 0 | 0 | 0 | 6240 | -2518 | 3721.9 | 0.1 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Malanpur Entech P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 153 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 148000 | -12388 | 135612 | 135612 | 100% | 0 | 0 | 0 | 19240 | -1610 | 17630 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of integral skin PUF products at Legend Interiors | Individual | ASP | IND | FOA | 23 | INV | 154 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 124000 | -14125 | 109875 | 109875 | 100% | 0 | 0 | 0 | 16120 | -1836 | 14284 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at K. J. Polymers P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 155 | A | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 127550 | -353 | 127197 | 127197 | 100% | 0 | 0 | 0 | 16582 | -46 | 16535.5953 | 0.4047 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bluplast Corporation | Individual | ASP | IND | FOA | 23 | INV | 156 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Alaska Industries | Individual | ASP | IND | FOA | 23 | INV | 157 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 128000 | -18370 | 109630 | 109630 | 100% | 0 | 0 | 0 | 16640 | -2388 | 14252 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at Ras Polybuild Products P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 158 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 128000 | -136 | 127864 | 127864 | 100% | 0 | 0 | 0 | 16640 | -18 | 16622.3178 | -0.3178 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation to prepare 10 projects in the foam sector | Individual | ASP | IND | FOA | 24 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam at Puff Insulators | Individual | ASP | IND | FOA | 26 | INV | 184 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-11-01 | 2002-03-01 | 83150 | 0 | 83150 | 83150 | 100% | 0 | 0 | 0 | 10810 | 0 | 10809.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and integral skin foam products to water blown systems in flexible molded polyurethane foam at Joti Foam Pr | Individual | ASP | IND | FOA | 26 | INV | 185 | A | I | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 174290 | -287 | 174003 | 174003 | 100% | 0 | 0 | 0 | 22658 | -37 | 22620.39 | 0.61 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated termoware at Jaypee Technoplast P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 186 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 139860 | -966 | 138894 | 138894 | 100% | 0 | 0 | 0 | 18182 | -126 | 18056.1195 | -0.1195 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Sintex Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 187 | A | D | CFC | 10.9 | 10.9 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-11-01 | 2003-04-01 | 62980 | -1589 | 61391 | 61391 | 100% | 0 | 0 | 0 | 8187 | -207 | 7980.83 | -0.83 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at National Flask Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 188 | A | I | CFC | 36.9 | 36.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-08-01 | 2002-03-01 | 203870 | -16186 | 187684 | 187684 | 100% | 0 | 0 | 0 | 26503 | -2104 | 24398.92 | 0.08 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at Jayson Industries | Individual | ASP | IND | FOA | 26 | INV | 189 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 88900 | -840 | 88060 | 88060 | 100% | 0 | 0 | 0 | 11557 | -109 | 11447.6802 | 0.3198 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC -141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Duab International | Individual | ASP | IND | FOA | 26 | INV | 190 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-12-01 | 2001-12-01 | 104490 | 0 | 104490 | 104490 | 100% | 0 | 0 | 0 | 13584 | 0 | 13583.7 | 0.3 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Galaxy FRP P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 192 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 144808 | -1805 | 143003 | 143003 | 100% | 0 | 0 | 0 | 18825 | -235 | 18590.39 | -0.39 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam insulated thermoware at Ajay Corrugating and Plastics P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 193 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 80805 | 0 | 80805 | 80805 | 100% | 0 | 0 | 0 | 10505 | 0 | 10504.65 | 0.35 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam in situ and spray insulation at P.K. Construction Co. | Individual | ASP | IND | FOA | 27 | INV | 196 | A | D | CFC | 10.6 | 10.6 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 1999-12-01 | 2001-12-01 | 74172 | -3275 | 70897 | 70897 | 100% | 0 | 0 | 0 | 9642 | -426 | 9216.36 | -0.36 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ganga Thermoware | Individual | ASP | IND | FOA | 27 | INV | 197 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 78864 | -5388 | 73476 | 73476 | 100% | 0 | 0 | 0 | 10252 | -700 | 9551.88 | 0.12 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bansal Plastic Industries | Individual | ASP | IND | FOA | 27 | INV | 198 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 68829 | -6240 | 62589 | 62589 | 100% | 0 | 0 | 0 | 8948 | -811 | 8136.57 | 0.43 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Baba Insulator | Individual | ASP | IND | FOA | 27 | INV | 202 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 59096 | -10468 | 48628 | 48628 | 100% | 0 | 0 | 0 | 7682 | -1361 | 6321.64 | -0.64 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at R.S. Insulators | Individual | ASP | IND | FOA | 27 | INV | 205 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 54800 | -10912 | 43888 | 43888 | 100% | 0 | 0 | 0 | 7124 | -1419 | 5705.44 | -0.44 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Shree Nath Plastics | Individual | ASP | IND | FOA | 27 | INV | 207 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 61370 | -7114 | 54256 | 54256 | 100% | 0 | 0 | 0 | 7978 | -925 | 7053.28 | -0.28 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of ten projects in general foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 194 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of seven projects in rigid foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 206 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Varivar Plast Products P., Ltd. | Individual | ASP | IND | FOA | 28 | INV | 210 | A | I | CFC | 12.3 | 12.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 96184 | -1 | 96183 | 96183 | 100% | 0 | 0 | 0 | 12504 | 0 | 12503.79 | 0.21 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Supertek International | Individual | ASP | IND | FOA | 28 | INV | 211 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 83202 | 0 | 83202 | 83202 | 100% | 0 | 0 | 0 | 10816 | 0 | 10816.26 | -0.26 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Standard Electric Appliances | Individual | ASP | IND | FOA | 28 | INV | 212 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 78136 | 0 | 78136 | 78136 | 100% | 0 | 0 | 0 | 10158 | 0 | 10157.68 | 0.32 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at O.K. Industries | Individual | ASP | IND | FOA | 28 | INV | 214 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 66227 | -2012 | 64215 | 64215 | 100% | 0 | 0 | 0 | 8610 | -262 | 8347.51 | 0.49 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Primrose Multiplast P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 215 | A | D | CFC | 9.6 | 9.6 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 117105 | -1131 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15224 | -147 | 15076.455 | 0.545 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to CFC-free technology in the manufacture of rigid polyurethane foam chemical systems at Shivathene Linopack | Individual | ASP | IND | FOA | 28 | INV | 218 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 209000 | -16227 | 192773 | 192773 | 100% | 0 | 0 | 0 | 27170 | -2110 | 25060.49 | -0.49 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Devisons P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 219 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 114940 | -5215 | 109725 | 109725 | 100% | 0 | 0 | 0 | 14942 | -678 | 14264.2 | -0.2 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Nav Texfeb P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 224 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 163982 | -3561 | 160421 | 160421 | 100% | 0 | 0 | 0 | 21318 | -463 | 20854.66 | 0.34 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at N.D. Plastics | Individual | ASP | IND | FOA | 28 | INV | 226 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2001-12-01 | 101289 | -802 | 100487 | 100487 | 100% | 0 | 0 | 0 | 13168 | -104 | 13063.2143 | 0.7857 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ashoka Metals | Individual | ASP | IND | FOA | 28 | INV | 228 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2002-03-01 | 68066 | -1587 | 66479 | 66479 | 100% | 0 | 0 | 0 | 8849 | -206 | 8642.27 | 0.73 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 28 small and medium-sized enterprises | Individual | ASP | IND | FOA | 28 | INV | 229 | A | I | CFC | 105.7 | 105.7 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2002-12-01 | 2005-09-01 | 699139 | -39114 | 660025 | 660025 | 100% | 0 | 0 | 0 | 86905 | -4862 | 82043.29 | -0.29 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Tokyo Plast International, Ltd. | Individual | ASP | IND | FOA | 29 | INV | 231 | A | I | CFC | 30.5 | 30.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-06-01 | 2003-11-01 | 196394 | -37676 | 158718 | 158718 | 100% | 0 | 0 | 0 | 25531 | -4898 | 20633.59 | -0.59 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Santech Industries | Individual | ASP | IND | FOA | 29 | INV | 232 | A | I | CFC | 14.7 | 14.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 115101 | -9 | 115092 | 115092 | 100% | 0 | 0 | 0 | 14963 | -2 | 14961.61 | -0.61 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Saddle Poly Products P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 233 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 119087 | -44 | 119043 | 119043 | 100% | 0 | 0 | 0 | 15481 | -6 | 15475.72 | -0.72 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Coolwels Automobile Engineers | Individual | ASP | IND | FOA | 29 | INV | 234 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 133221 | -669 | 132552 | 132552 | 100% | 0 | 0 | 0 | 17319 | -87 | 17232.03 | -0.03 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Mayur Jugs P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 235 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 119412 | -16905 | 102507 | 102507 | 100% | 0 | 0 | 0 | 15524 | -2198 | 13325.52 | 0.48 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Premium Mouldings and Pressings P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 236 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 138432 | -87 | 138345 | 138345 | 100% | 0 | 0 | 0 | 17996 | -11 | 17984.69 | 0.31 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crystal Electronics and Plastics | Individual | ASP | IND | FOA | 29 | INV | 237 | A | I | CFC | 18.3 | 18.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 123343 | -20723 | 102620 | 102620 | 100% | 0 | 0 | 0 | 16035 | -2695 | 13339.59 | 0.41 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at National Plastics | Individual | ASP | IND | FOA | 29 | INV | 239 | A | I | CFC | 36.2 | 36.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 212481 | -39605 | 172876 | 172876 | 100% | 0 | 0 | 0 | 27623 | -5149 | 22473.78 | 0.22 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Reactive Polymers Ltd. | Individual | ASP | IND | FOA | 29 | INV | 240 | A | I | CFC | 29.6 | 29.6 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 354175 | -56621 | 297554 | 297554 | 100% | 0 | 0 | 0 | 46043 | -7361 | 38682.12 | -0.12 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Jaiswal Industries | Individual | ASP | IND | FOA | 29 | INV | 241 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 152070 | -14822 | 137248 | 137248 | 100% | 0 | 0 | 0 | 19769 | -1927 | 17842.14 | -0.14 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 24 SMEs | Individual | ASP | IND | FOA | 29 | INV | 242 | A | I | CFC | 97.7 | 97.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2003-04-01 | 2006-10-01 | 886584 | -127666 | 758918 | 758918 | 100% | 0 | 0 | 0 | 107524 | -8865 | 98659.2 | -0.2 | 0 | Completed in 2003. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Delite Foam and Polymers | Individual | ASP | IND | FOA | 29 | INV | 245 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 188832 | -2784 | 186048 | 186048 | 100% | 0 | 0 | 0 | 24548 | -362 | 24186.24 | -0.24 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Harjas Plastic and Metal Components P. Ltd. | Individual | ASP | IND | FOA | 29 | INV | 246 | A | I | CFC | 20.2 | 20.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-05-01 | 2003-07-01 | 246386 | -30539 | 215847 | 215847 | 100% | 0 | 0 | 0 | 32030 | -3970 | 28060.42 | -0.42 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 6 projects in the integral skin foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 250 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3044.84 | 0.16 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of an umbrella project in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3044.89 | 0.11 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 252 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ramakrishna Moulders | Individual | ASP | IND | FOA | 31 | INV | 258 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-12-01 | 2003-04-01 | 78479 | -1311 | 77168 | 77168 | 100% | 0 | 0 | 0 | 10202 | -170 | 10032.27 | -0.27 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at M-Plast | Individual | ASP | IND | FOA | 31 | INV | 259 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 93279 | -451 | 92828 | 92828 | 100% | 0 | 0 | 0 | 12126 | -59 | 12067.64 | -0.64 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Naorang Plast | Individual | ASP | IND | FOA | 31 | INV | 260 | A | I | CFC | 13.5 | 13.5 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 53171 | -563 | 52608 | 52608 | 100% | 0 | 0 | 0 | 6912 | -73 | 6838.81 | 0.19 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Sanjay Industries | Individual | ASP | IND | FOA | 31 | INV | 261 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 99277 | -2381 | 96896 | 96896 | 100% | 0 | 0 | 0 | 12906 | -310 | 12596.48 | -0.48 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crown Industries | Individual | ASP | IND | FOA | 31 | INV | 263 | A | I | CFC | 22.5 | 22.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 113110 | -4382 | 108728 | 108728 | 100% | 0 | 0 | 0 | 14704 | -570 | 14134.64 | -0.64 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at sixteen enterprises | Individual | ASP | IND | FOA | 31 | INV | 267 | A | I | CFC | 211.1 | 211.1 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 1094567 | -75293 | 1019274 | 1019274 | 100% | 0 | 0 | 0 | 130402 | -8282 | 122120.17 | -0.17 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Enertech Engineering P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 268 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2004-01-01 | 123109 | -86 | 123023 | 123023 | 100% | 0 | 0 | 0 | 16004 | -11 | 15993.17 | -0.17 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Raipur Agencies | Individual | ASP | IND | FOA | 31 | INV | 269 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 144567 | -2814 | 141753 | 141753 | 100% | 0 | 0 | 0 | 18794 | -366 | 18427.89 | 0.11 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pyarelal Coir Products Ltd. | Individual | ASP | IND | FOA | 31 | INV | 270 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 167381 | -2886 | 164495 | 164495 | 100% | 0 | 0 | 0 | 21760 | -375 | 21384.35 | 0.65 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at R.H. Industries | Individual | ASP | IND | FOA | 31 | INV | 271 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 153895 | -2700 | 151195 | 151195 | 100% | 0 | 0 | 0 | 20006 | -351 | 19655.35 | -0.35 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pinnacle Industries Ltd. | Individual | ASP | IND | FOA | 31 | INV | 272 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 186392 | 0 | 186392 | 186392 | 100% | 0 | 0 | 0 | 24231 | 0 | 24230.96 | 0.04 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Nindra Foams | Individual | ASP | IND | FOA | 31 | INV | 273 | A | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 148804 | -2244 | 146560 | 146560 | 100% | 0 | 0 | 0 | 19345 | -292 | 19052.93 | 0.07 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at SR Poly-steel P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 274 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 144299 | -1 | 144298 | 144298 | 100% | 0 | 0 | 0 | 18759 | 0 | 18758.87 | 0.13 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Enkay Foam P., Ltd. | Individual | ASP | IND | FOA | 31 | INV | 275 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 162339 | -4442 | 157897 | 157897 | 100% | 0 | 0 | 0 | 21104 | -577 | 20526.74 | 0.26 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Alka International Ltd. | Individual | ASP | IND | FOA | 31 | INV | 276 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 173155 | -6690 | 166465 | 166465 | 100% | 0 | 0 | 0 | 22510 | -870 | 21640.45 | -0.45 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Evershine Plastic Industry | Individual | ASP | IND | FOA | 31 | INV | 277 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 80060 | -2410 | 77650 | 77650 | 100% | 0 | 0 | 0 | 10408 | -313 | 10094.5 | 0.5 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Netplast Ltd. | Individual | ASP | IND | FOA | 32 | INV | 280 | A | I | CFC | 18 | 18 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-09-01 | 2005-09-01 | 177224 | -2199 | 175025 | 175025 | 100% | 0 | 0 | 0 | 23039 | -286 | 22753.12 | -0.12 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sun Steering Wheels, Ltd. | Individual | ASP | IND | FOA | 32 | INV | 285 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-02-01 | 2005-10-01 | 144379 | -2997 | 141382 | 141382 | 100% | 0 | 0 | 0 | 18769 | -390 | 18379.27 | -0.27 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sawhney Seating Systems | Individual | ASP | IND | FOA | 32 | INV | 289 | A | I | CFC | 28 | 28 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-07-01 | 2005-09-01 | 241619 | -3124 | 238495 | 238495 | 100% | 0 | 0 | 0 | 31410 | -406 | 31004.47 | -0.47 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | ASP | IND | FOA | 33 | PRP | 296 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | ASP | IND | FOA | 33 | PRP | 297 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IND | FOA | 33 | PRP | 299 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at UNC Plast Industries | Individual | ASP | IND | FOA | 34 | INV | 304 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2007-02-01 | 89607 | -1142 | 88465 | 88465 | 100% | 0 | 0 | 0 | 11649 | -148 | 11500.4489 | 0.5511 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Viking Engineers P. Ltd. | Individual | ASP | IND | FOA | 34 | INV | 305 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-10-01 | 144900 | -2745 | 142155 | 142155 | 100% | 0 | 0 | 0 | 18837 | -357 | 18480.15 | -0.15 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Roome Plastics P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 312 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 100546 | -2008 | 98538 | 98538 | 100% | 0 | 0 | 0 | 13071 | -261 | 12809.98 | 0.02 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Essa Aircons Ltd. | Individual | ASP | IND | FOA | 34 | INV | 317 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 108837 | -2996 | 105841 | 105841 | 100% | 0 | 0 | 0 | 14149 | -389 | 13759.3248 | 0.67525 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCF-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at 14 enterprises | Individual | ASP | IND | FOA | 34 | INV | 321 | A | I | CFC | 178.4 | 178.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-09-01 | 2005-11-01 | 759165 | -12566 | 746599 | 746599 | 100% | 0 | 0 | 0 | 93508 | -1382 | 92126.15 | -0.15 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at 17 small and medium-sized enterprises | Individual | ASP | IND | FOA | 34 | INV | 322 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-03-01 | 2004-12-01 | 417740 | 0 | 417740 | 417740 | 100% | 0 | 0 | 0 | 54306 | 0 | 54306.2 | -0.2 | 0 | Completed in 2004. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Apollo Steelcrafts | Individual | ASP | IND | FOA | 34 | INV | 324 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 76925 | -3129 | 73796 | 73796 | 100% | 0 | 0 | 0 | 10000 | -407 | 9593.25 | -0.25 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at SR Polymers and Printers | Individual | ASP | IND | FOA | 34 | INV | 325 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 95002 | -2970 | 92032 | 92032 | 100% | 0 | 0 | 0 | 12350 | -386 | 11964.1681 | -0.1681 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Caryaire Equipments India P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 326 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-07-01 | 2005-11-01 | 133509 | 0 | 133509 | 133509 | 100% | 0 | 0 | 0 | 17356 | 0 | 17356.17 | -0.17 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lear Insulation Engineering P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 328 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 82567 | -1581 | 80986 | 80986 | 100% | 0 | 0 | 0 | 10734 | -206 | 10528.1745 | -0.17448 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nandadeep Fibrotech P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 329 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 88526 | -3278 | 85248 | 85248 | 100% | 0 | 0 | 0 | 11508 | -426 | 11082.2541 | -0.25407 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Nu-Foam Rubber Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 330 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2003-02-01 | 2005-10-01 | 160150 | -1115 | 159035 | 159035 | 100% | 0 | 0 | 0 | 20820 | -145 | 20674.5465 | 0.45352 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Poly Glass Fibre Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 331 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-03-01 | 2005-10-01 | 134238 | -2571 | 131667 | 131667 | 100% | 0 | 0 | 0 | 17451 | -334 | 17116.7089 | 0.29115 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Polyrub Industries | Individual | ASP | IND | FOA | 34 | INV | 332 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 97953 | -3144 | 94809 | 94809 | 100% | 0 | 0 | 0 | 12734 | -409 | 12325.1664 | -0.16643 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Prince Plastoware Ltd. | Individual | ASP | IND | FOA | 34 | INV | 333 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2004-08-01 |  | 2002-06-01 | 2003-11-01 | 74010 | -3392 | 70618 | 70618 | 100% | 0 | 0 | 0 | 9621 | -441 | 9180.34 | -0.34 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Solvay Moulding P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 334 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-07-01 | 2005-09-01 | 196885 | -15868 | 181017 | 181017 | 100% | 0 | 0 | 0 | 25595 | -2063 | 23532.05 | -0.05 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bhatia Plastics | Individual | ASP | IND | FOA | 34 | INV | 335 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-03-01 | 2005-10-01 | 87070 | -5398 | 81672 | 81672 | 100% | 0 | 0 | 0 | 11319 | -702 | 10617.3662 | -0.36618 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | ASP | IND | FOA | 36 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 40000 | -6328 | 33672 | 33672 | 100% | 0 | 0 | 0 | 5200 | -823 | 4377.36 | -0.36 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (first tranche) | Multi-Year | ASP | IND | FOA | 37 | INV | 353 | N | I | CFC | 162.5 | 162.5 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2003-12-01 |  | 2004-12-01 | 2013-10-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (second tranche) | Multi-Year | ASP | IND | FOA | 41 | INV | 365 | N | I | CFC | 210 | 210 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-07-01 | 2013-10-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 | 0 | 153500 | 0 | 153500 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (third tranche) | Multi-Year | ASP | IND | FOA | 44 | INV | 384 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-12-01 | 2013-10-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | IND | FOA | 72 | PRP | 455 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 2800 | 0 | 0 | 2800 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, inception workshop for preparation activities was held in July 2014 with all agencies. Project preparation activities are underway. Consultancy contract is expected to be finalised by Q2-2015. Final HPMP for Stage-II is expected to be submitted by Q4 2015 to MFS. Prodoc signed (actual/planned, yes/no and date):To be signed in February 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 prepared. Contract/PO/MOA agreements signed:2 MOAs planned. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. Consultant recruitment completed in June 2015 and stakeholder consultations planned in Q3 of 2015. Strategy is expected to be developed by Q4 2015. |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | Individual | ASP | IND | FOA | 72 | PRP | 458 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 8400 | 0 | 0 | 8400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, Inception workshop for preparation activities was held in July 2014 with all agencies. Project preparation activities are underway. Consultancy contract is expected to be finalised by Q2-2015. Final HPMP for Stage-II is expected to be submitted by Q4 2015 to MFS. Prodoc signed (actual/planned, yes/no and date):To be signed in February 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 prepared. Contract/PO/MOA agreements signed:2 MOAs planned. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. Consultant recruitment completed in June 2015 and stakeholder consultations planned in Q3 of 2015. Strategy is expected to be developed by Q4 2015. |  |  | Non-Investment
FIN | UNDP | Demonstration and evaluation of alternative technology for halon fire protection system and technical assistance for sectoral strategy for ODS phase out | Individual | ASP | IND | HAL | 13 | DEM | 28 | N | I | HAL | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-01 | 1997-07-01 |  | 1999-12-01 | 2003-02-01 | 309000 | -44111 | 264889 | 264889 | 100% | 0 | 0 | 0 | 40170 | -5734 | 34435.57 | 0.43 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Non-Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Steelage Industries Limited Minimax Division/ Chennai | Individual | ASP | IND | HAL | 24 | INV | 163 | A | I | Halon | 116 | 116 | 0 | 0 | 1998-03-01 | 2000-05-01 | 2000-04-01 |  | 2002-01-01 | 2003-04-01 | 131915 | -41454 | 90461 | 90461 | 100% | 0 | 0 | 0 | 17149 | -5389 | 11759.93 | 0.07 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vijay Fire Protection Systems Ltd. | Individual | ASP | IND | HAL | 24 | INV | 165 | A | I | Halon | 292 | 292 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 219152 | 0 | 219152 | 219152 | 100% | 0 | 0 | 0 | 28490 | 0 | 28489.76 | 0.24 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Nitin Fire Protection Industries Ltd., Bombay | Individual | ASP | IND | HAL | 24 | INV | 168 | A | I | Halon | 212 | 212 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 165818 | 0 | 165818 | 165818 | 100% | 0 | 0 | 0 | 21556 | 0 | 21556.34 | -0.34 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of production halon-1211 fire extinguishers at Atkins, New Delhi | Individual | ASP | IND | HAL | 24 | INV | 170 | A | I | Halon | 37 | 37 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2001-05-01 | 2002-03-01 | 54760 | -739 | 54021 | 54021 | 100% | 0 | 0 | 0 | 7119 | -96 | 7022.73 | 0.27 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at New Age Industries, Bombay | Individual | ASP | IND | HAL | 24 | INV | 175 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 132248 | -292 | 131956 | 131956 | 100% | 0 | 0 | 0 | 17192 | -38 | 17154.28 | -0.28 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vimal Industrial Safety Equipment Corporation Baroda, Gujrat | Individual | ASP | IND | HAL | 24 | INV | 176 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 186152 | 0 | 186152 | 186152 | 100% | 0 | 0 | 0 | 24200 | 0 | 24199.76 | 0.24 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Ashoka Engineering Co., New Delhi | Individual | ASP | IND | HAL | 24 | INV | 177 | A | I | Halon | 34 | 34 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 50320 | 0 | 50320 | 50320 | 100% | 0 | 0 | 0 | 6542 | 0 | 6541.6 | 0.4 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 5 halon extinguisher projects | Individual | ASP | IND | HAL | 24 | PRP | 166 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Cascade Counsel Ltd. New Delhi | Individual | ASP | IND | HAL | 28 | INV | 208 | A | I | Halon | 54 | 54 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79920 | 0 | 79920 | 79920 | 100% | 0 | 0 | 0 | 10390 | 0 | 10389.6 | 0.4 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Bharat Engineering Works, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 209 | A | I | Halon | 49.5 | 49.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 73260 | -7751 | 65509 | 65509 | 100% | 0 | 0 | 0 | 9524 | -1008 | 8516.17 | -0.17 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Zenith Fire Services, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 216 | A | I | Halon | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 53280 | -3309 | 49971 | 49971 | 100% | 0 | 0 | 0 | 6926 | -430 | 6496.23 | -0.23 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Extinguisher production and elimination of its consumption of virgin halon-1301 at New Fire Engineers Pvt. Ltd. Mumbai | Individual | ASP | IND | HAL | 28 | INV | 220 | A | I | Halon | 120 | 120 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher to ABC powder and CO2 units together with the use of recycled halon-1301 in lieu of virgin product at Standard Castings Pvt. Ltd. New Delhi, under the name of Pyrosafety | Individual | ASP | IND | HAL | 28 | INV | 222 | A | I | Halon | 64.1 | 64.1 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-11-01 | 92000 | -23084 | 68916 | 68916 | 100% | 0 | 0 | 0 | 11960 | -3001 | 8959 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at M/s Kooverji Devshi and Co. Pvt. Ltd., Mumbai | Individual | ASP | IND | HAL | 28 | INV | 256 | A | I | Halon | 25.5 | 25.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-05-01 | 2002-03-01 | 37740 | 0 | 37740 | 37740 | 100% | 0 | 0 | 0 | 4906 | 0 | 4906.2 | -0.2 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | Individual | ASP | IND | HAL | 29 | TAS | 243 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2002-12-01 |  | 2005-12-01 | 2007-03-01 | 88000 | -3435 | 84565 | 84565 | 100% | 0 | 0 | 0 | 11440 | -447 | 10993.45 | -0.45 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Project preparation in the non-recycling halon sector | Individual | ASP | IND | HAL | 33 | PRP | 294 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2003-06-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 428 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-05-01 | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Financially completed in 2013. | HPMP Stage-I submitted early January for the 66th Excom meeting. Project targeted for financial completion in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (fire fighting and solvent sectors) | Individual | ASP | IND | PHA | 56 | PRP | 430 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IND | PHA | 56 | PRP | 431 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2014-03-01 | 105000 | -26034 | 78966 | 78966 | 100% | 0 | 0 | 0 | 7875 | -1953 | 5922.45 | -0.45 | 0 | Financially completed in 2014. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (air conditioning sector) | Individual | ASP | IND | PHA | 56 | PRP | 432 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 125000 | -69174 | 55826 | 55826 | 100% | 0 | 0 | 0 | 9375 | -5188 | 4186.95 | 0.05 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (refrigeration sector) | Individual | ASP | IND | PHA | 56 | PRP | 433 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 80000 | -35946 | 44054 | 44054 | 100% | 0 | 0 | 0 | 6000 | -2696 | 3304.05 | -0.05 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | IND | PHA | 66 | INV | 441 | N | I | HCFC | 145.4 | 140.4 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2013-04-01 | 2015-12-01 |  |  | 9400000 | 0 | 9400000 | 8844658 | 94.09% | 555342 | 0 | 222136.82 | 705000 | 0 | 663349.3462 | 41650.6538 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, project implementation in foam sector including systems houses progressed in a satisfactory manner. The beneficiary enterprises in foam manufacturing sector have largely completed their project activities and have procured equipment for use with HCFC free alternatives. By 2015, it is expected that all projects would be completed. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in July 2012 and actually signed in Nov 2012. Missions undertaken (actual/planned):3 missions planned and 3 actual. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:All MOAs signed. First disbursement date (actual/planned):The first disbursement took place in March 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management component) | Multi-year | ASP | IND | PHA | 66 | TAS | 440 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-05-01 | 2013-04-01 | 2017-01-01 |  |  | 600000 | 0 | 600000 | 285558 | 47.59% | 314442 | 97500 | 125776.652 | 45000 | 0 | 21416.8777 | 23583.1223 | 7312.5 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, PMU activities progresed satisfactorily. National regulations have been notified particularly relating to controls on HCFC-141b using preblended polyols. Awareness and information outreach activities have been undertaken back to back with HPMP Stage-II preparation meetings and as a part of Ozone Day celebrations. Prodoc signed (actual/planned, yes/no and date):The prodoc was planned to be signed in July 2012 and actually signed in Nov 2012. Missions undertaken (actual/planned):3 missions planned and 3 actual. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in May 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche would be submitted to the 75th Excom. PMU is coordinating project implementation monitoring in a satisfactory manner. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | IND | PHA | 71 | INV | 451 | N | I | HCFC | 117.3 | 76.2 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 6580000 | 0 | 6580000 | 0 | 0% | 6580000 | 0 | 2632000 | 460600 | 0 | 0 | 460600 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This tranche was approved in December 2013. In 2014, project implementation in foam sector including systems houses progressed in a satisfactory manner. The beneficiary enterprises in foam manufacturing sector have largely completed their project activities and have procured equipment for use with HCFC free alternatives. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (project management component) | Multi-Year | ASP | IND | PHA | 71 | TAS | 448 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 420000 | 0 | 420000 | 0 | 0% | 420000 | 0 | 168000 | 29400 | 0 | 0 | 29400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This tranche was approved in December 2013. During the year 2014, PMU activities progresed satisfactorily. National regulations have been notified particularly relating to controls on HCFC-141b using preblended polyols. Awareness and information outreach activities have been undertaken back to back with HPMP Stage-II preparation meetings and as a part of Ozone Day celebrations. Prodoc signed (actual/planned, yes/no and date): Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche would be submitted to the 75th Excom. PMU is coordinating project implementation monitoring in a satisfactory manner. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IND | PHA | 72 | PRP | 452 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3500 | 0 | 0 | 3500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, Inception workshop for preparation activities was held in July 2014 with all agencies. Project preparation activities are underway. Consultancy contract is expected to be finalised by Q2-2015. Final HPMP for Stage-II is expected to be submitted by Q4 2015 to MFS. Prodoc signed (actual/planned, yes/no and date):To be signed in February 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 prepared. Contract/PO/MOA agreements signed:2 MOAs planned. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. Consultant recruitment completed in June 2015 and stakeholder consultations planned in Q3 of 2015. Strategy is expected to be developed by Q4 2015. |  |  | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IND | REF | 24 | PRP | 169 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of five projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 27 | PRP | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 30 | PRP | 254 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Fedders Lloyd Corporation Ltd. | Individual | ASP | IND | REF | 31 | INV | 257 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 257428 | -2616 | 254812 | 254812 | 100% | 0 | 0 | 0 | 33466 | -340 | 33125.56 | 0.44 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sandlas Air-Con Systems P. Ltd. | Individual | ASP | IND | REF | 32 | INV | 282 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 228517 | -9527 | 218990 | 218990 | 100% | 0 | 0 | 0 | 29707 | -1239 | 28468.21 | -0.21 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 32 | INV | 286 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 789425 | -20719 | 768706 | 768706 | 100% | 0 | 0 | 0 | 96837 | -2279 | 94557.75 | 0.25 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Technical assistance to Ozone Cell, MOEF during the preparation of a refrigeration and air conditioning servicing sector strategy | RMP-Component | ASP | IND | REF | 32 | TAS | 279 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-07-01 | 2005-09-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 | 0 | 3900 | -478 | 3422 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IND | REF | 33 | PRP | 293 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of commercial refrigeration equipment at 5 enterprises (Ahmedabad Low Temp, Kalkura Cooling Machines, Mechelec Steel Products, Polfrost Aircon and Shri Ambica Engineering) | Individual | ASP | IND | REF | 34 | INV | 323 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-11-01 | 2005-11-01 | 323627 | -7398 | 316229 | 316229 | 100% | 0 | 0 | 0 | 42072 | -962 | 41109.51 | 0.49 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at fourteen enterprises | Individual | ASP | IND | REF | 35 | INV | 339 | A | I | CFC | 68 | 68 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2003-11-01 | 2005-10-01 | 960097 | -5024 | 955073 | 955073 | 100% | 0 | 0 | 0 | 115611 | -553 | 115057.73 | 0.26995 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ice-Make Refrigeration | Individual | ASP | IND | REF | 35 | INV | 340 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-12-01 | 157305 | -1232 | 156073 | 156073 | 100% | 0 | 0 | 0 | 20450 | -160 | 20289.65 | 0.35 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Konark Refrigeration Appliances P., Ltd. | Individual | ASP | IND | REF | 35 | INV | 341 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-09-01 | 182684 | -1327 | 181357 | 181357 | 100% | 0 | 0 | 0 | 23749 | -173 | 23575.92 | 0.08 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 35 | INV | 342 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2007-03-01 | 726448 | -9086 | 717362 | 717362 | 100% | 0 | 0 | 0 | 89909 | -999 | 88910.1 | -0.1 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | ASP | IND | REF | 36 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2243.67 | 0.33 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Plan for phase out of CFCs in the refrigeration manufacturing sector (first tranche) | Multi-Year | ASP | IND | REF | 38 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2004-11-01 |  | 2006-07-01 | 2013-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 172971 | 0 | 172971 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 364 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-03-01 | 2004-12-01 |  | 2006-12-01 | 2013-02-01 | 476536 | 0 | 476536 | 476536 | 100% | 0 | 0 | 0 | 43243 | 0 | 43243 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2006-12-01 | Investment
FIN | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 371 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-11-01 | 2005-04-01 |  | 2006-06-01 | 2013-02-01 | 277200 | 0 | 277200 | 277200 | 100% | 0 | 0 | 0 | 20790 | 0 | 20790 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 379 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-03-01 | 2005-12-01 |  | 2006-06-01 | 2013-02-01 | 277050 | 0 | 277050 | 277050 | 100% | 0 | 0 | 0 | 20779 | 0 | 20779 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (third tranche) | Multi-Year | ASP | IND | REF | 44 | INV | 383 | N | I | CFC | 141 | 141 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2012-11-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21621 | 0 | 21621 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 395 | N | I | CFC | 428 | 428 | 0 | 0 | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2009-12-01 | 2012-11-01 | 1332377 | -134567 | 1197810 | 1197810 | 100% | 0 | 0 | 0 | 112417 | -11354 | 101063.1426 | -0.14264 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2005 |  | Investment
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 403 | N | I | CFC | 639 | 639 | 0 | 0 | 2006-11-01 | 2012-02-01 | 2008-06-01 |  | 2013-12-01 | 2014-06-01 | 167860 | -67899 | 99961 | 99961 | 100% | 0 | 0 | 0 | 12590 | -5093 | 7497.37 | -0.37 | 0 | Financially completed in 2014. | Completed in 2013. | 2006 |  | Investment
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 419 | N | I | CFC | 219.1 | 219.1 | 0 | 0 | 2008-04-01 |  | 2010-03-01 |  | 2012-11-01 | 2013-02-01 | 47881 | -47881 | 0 | 0 |  | 0 | 0 | 0 | 3591 | -3591 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. Remaining invoices to be settled in 2013. | 2008 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | ASP | IND | REF | 72 | PRP | 453 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-12-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 8400 | 0 | 0 | 8400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, Inception workshop for preparation activities was held in July 2014 with all agencies. Project preparation activities are underway. Consultancy contract is expected to be finalised by Q2-2015. Final HPMP for Stage-II is expected to be submitted by Q4 2015 to MFS. Prodoc signed (actual/planned, yes/no and date):To be signed in February 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 prepared. Contract/PO/MOA agreements signed:2 MOAs planned. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. Consultant recruitment completed in June 2015 and stakeholder consultations planned in Q3 of 2015. Strategy is expected to be developed by Q4 2015. |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | IND | REF | 72 | PRP | 459 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-12-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 8400 | 0 | 0 | 8400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, Inception workshop for preparation activities was held in July 2014 with all agencies. Project preparation activities are underway. Consultancy contract is expected to be finalised by Q2-2015. Final HPMP for Stage-II is expected to be submitted by Q4 2015 to MFS. Prodoc signed (actual/planned, yes/no and date):To be signed in February 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):2 planned and 2 prepared. Contract/PO/MOA agreements signed:2 MOAs planned. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities in progress. Consultant recruitment completed in June 2015 and stakeholder consultations planned in Q3 of 2015. Strategy is expected to be developed by Q4 2015. |  |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IND | SEV | 08 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-06-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 430600 | -1671 | 428929 | 428929 | 100% | 0 | 0 | 0 | 55978 | -217 | 55760.56 | 0.44 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Assistance in project preparation in all sectors | Individual | ASP | IND | SEV | 08 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 100000 | -18339 | 81661 | 81661 | 100% | 0 | 0 | 0 | 13000 | -2384 | 10615.93 | 0.07 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IND | SEV | 09 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1993-11-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Survey of ODS use in the small scale (including tiny) and informal sectors, data base generation and ODS transition management planning | Individual | ASP | IND | SEV | 11 | TAS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-11-01 | 1994-05-01 |  | 1996-12-01 | 2001-12-01 | 120000 | -11230 | 108770 | 108770 | 100% | 0 | 0 | 0 | 15600 | -1460 | 14139.87 | 0.13 | 0 | Completed in 1996. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 12 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 18 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Institutional strengthening project for the phaseout of ODSs under the Montreal Protocol: Phase II | Individual | ASP | IND | SEV | 20 | INS | 107 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1999-03-01 | 1999-12-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | IND | SEV | 21 | PRP | 109 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-11-01 | 2000-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation | Individual | ASP | IND | SEV | 22 | PRP | 129 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Renewal of Institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol : Phase 3 | Individual | ASP | IND | SEV | 27 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2001-04-01 |  | 2001-08-01 | 2002-01-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase IV) | Individual | ASP | IND | SEV | 34 | INS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2003-08-01 |  | 2004-03-01 | 2009-01-01 | 287100 | -1304 | 285796 | 285796 | 100% | 0 | 0 | 0 | 37323 | -170 | 37153.48 | -0.48 | 0 | Completed in 2004.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | IND | SEV | 36 | CPG | 349 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-09-01 | 2003-10-01 |  | 2006-07-01 | 2007-03-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 | 2004-12-01 | Non-Investment
FIN | UNDP | Extension of institutional strengthening project: phase 5 | Individual | ASP | IND | SEV | 41 | INS | 367 | N | I | No_ODP | 30.8 | 30.8 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-07-01 | 2011-12-01 | 373230 | -2920 | 370310 | 370310 | 100% | 0 | 0 | 0 | 27992 | -219 | 27773.002 | -0.002 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IND | SEV | 45 | TAS | 391 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2011-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517 | 14996.6661 | 0.3339 | 0 | Completed in 2008. Financially completed in 2011. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IND | SEV | 47 | INS | 392 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2008-12-01 | 2013-03-01 | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992.25 | -0.25 | 0 | Financially completed in 2013. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IND | SEV | 54 | INS | 416 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2013-07-01 | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | IND | SEV | 60 | INS | 436 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2012-03-01 |  | 2012-06-01 | 2013-08-01 | 326576 | 0 | 326576 | 326576 | 100% | 0 | 0 | 0 | 24493 | 0 | 24493 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (remaining balance for phase VIII) | Individual | ASP | IND | SEV | 65 | INS | 439 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-03-01 |  | 2013-03-01 | 2013-12-01 | 46654 | 0 | 46654 | 46654 | 100% | 0 | 0 | 0 | 3499 | 0 | 3499 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 4/2012-3/2014) | Individual | ASP | IND | SEV | 66 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2014-03-01 | 2015-07-01 |  |  | 373230 | 0 | 373230 | 363783 | 97.47% | 9447 | 0 | 3778.948 | 27992 | 0 | 27283.4536 | 708.5464 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During 2014, monitoring of ongoing ODS phase-out projects and HPMP initiation activities were undertaken. Awareness activities including celebrations of International Ozone Day were satisfactorily undertaken. Ozone Office staff participated in international meetings on Montreal Protocol and related issues. CP progress and Article 7 data for 2013 was reported in timely manner. IS-X was submitted and approved at the 72nd ExCom. Prodoc signed (actual/planned, yes/no and date):Planned in July 2012 and actual in August 2012. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement took place in June 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:None. | The activities have been implementated as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2012 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | Individual | ASP | IND | SEV | 72 | INS | 457 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-03-01 | 2017-01-01 |  |  | 373230 | 0 | 373230 | 0 | 0% | 373230 | 0 | 149292 | 26126 | 0 | 0 | 26126 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During 2014, monitoring of ongoing ODS phase-out projects and HPMP initiation activities were undertaken. Awareness activities including celebrations of International Ozone Day were satisfactorily undertaken. Ozone Office staff participated in international meetings on Montreal Protocol and related issues. This is a part of the ongoing IS project activities Prodoc signed (actual/planned, yes/no and date):Planned in May 2015. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):None. Contract/PO/MOA agreements signed:None. First disbursement date (actual/planned):The first disbursement is planned for May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:None. | The activities have been implementated as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. |  |  | Non-Investment
FIN | UNDP | Preparation of four projects in the integral skin foam subsector | Individual | ASP | IRA | FOA | 27 | PRP | 40 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nobough Industrial Co. | Individual | ASP | IRA | FOA | 32 | INV | 75 | A | I | CFC | 31.8 | 21 | 0 | 0 | 2000-12-01 | 2002-01-01 | 2004-01-01 |  |  | 2003-07-01 | 248736 | -198081 | 50655 | 50655 | 100% | 0 | 0 | 0 | 32336 | -25751 | 6584.68 | 0.32 | 0 | Canceled in 2003. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to n-pentane technology in the manufacture of integral skin polyurethane foam products at Iran Polyurethane Manufacturing Co. | Individual | ASP | IRA | FOA | 32 | INV | 76 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-08-01 | 2003-11-01 | 796230 | 0 | 796230 | 796230 | 100% | 0 | 0 | 0 | 97585 | 0 | 97585.3 | -0.3 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 77 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded and integral skin polyurethane foams at Abre Sanati Iran | Individual | ASP | IRA | FOA | 34 | INV | 88 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2005-11-01 | 344407 | -7956 | 336451 | 336451 | 100% | 0 | 0 | 0 | 44773 | -1034 | 43738.91 | 0.09 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | Individual | ASP | IRA | FOA | 35 | INV | 117 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2007-02-01 | 188820 | -7749 | 181071 | 181071 | 100% | 0 | 0 | 0 | 24547 | -1007 | 23539.2136 | 0.7864 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 141 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215.11 | -0.11 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 142 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215.11 | -0.11 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 143 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (rigid foam) | Individual | ASP | IRA | FOA | 57 | PRP | 195 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2012-08-01 | 2014-02-01 | 30000 | -79 | 29921 | 29921 | 100% | 0 | 0 | 0 | 2250 | -6 | 2244.075 | -0.075 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 42 | INV | 165 | N | I | CFC | 56 | 56 | 0 | 0 | 2004-04-01 | 2005-05-01 | 2007-04-01 |  | 2007-12-01 | 2011-12-01 | 770000 | -13453 | 756547 | 756547 | 100% | 0 | 0 | 0 | 57750 | -1009 | 56741.025 | -0.02505 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-07-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 199 | N | I | HCFC | 29.3 | 29.3 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2015-03-01 |  | 2013-12-01 | 2013-12-01 | 1938500 | 0 | 1938500 | 1938500 | 100% | 0 | 0 | 0 | 145387 | 0 | 145387 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) (foam sector plan: one foam systems house) | Multi-Year | ASP | IRA | PHA | 63 | INV | 204 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2015-03-01 |  | 2014-12-01 |  | 225500 | 0 | 225500 | 0 | 0% | 225500 | 0 | 180400 | 16913 | 0 | 0 | 16913 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, consultations were held with beneficiary on technological choices. The enterprise expressed its inability to make technology choices due to technical issues and commercial considerations. The NOU and UNDP discussed this and agreed to return funds back to Excom at its 74th meeting. Prodoc signed (actual/planned, yes/no and date):Planned in November 2011 and actual in January 2012. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delays due to difficulties in technology choices. | As planned, consultations are currently underway on how we can move forward with the systems house component. | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 203 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-02-01 | 2012-03-01 |  | 2014-06-01 |  | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, the PMU activities progressed satisfactorily. Third tranche was approved subject to conditions in 72nd Excom meeting. Project activities were regularly reviewed. Prodoc signed (actual/planned, yes/no and date):Planned in November 2011 and actual in January 2012. Missions undertaken (actual/planned):4 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 completed. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | In Q1 of 2014, activities progressing as planned. HPMP third tranche funding request submitted for the consideration of 72 Excom. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 208 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-12-01 | 2015-12-01 |  |  | 1370000 | 0 | 1370000 | 1295422 | 94.56% | 74578 | 0 | 29831.2 | 102750 | 0 | 97156.65 | 5593.35 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the enterprise has procured equipment for producing R-410A based equipment. The new products have been designed and trial production and commercial production is expected to be completed by Q2 - 2015. The project is expected to be completed after final verification by Q4-2015. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):4 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 completed. Contract/PO/MOA agreements signed:1 MOA signed. First disbursement date (actual/planned):The first disbursement took place in May 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily. Last tranche request for HPMP submitted to and approved in 74th Excom. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (air conditioning sector plan and project management unit) | Multi-Year | ASP | IRA | PHA | 72 | INV | 211 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2018-12-01 |  |  | 477816 | 0 | 477816 | 0 | 0% | 477816 | 0 | 191126.4 | 35836 | 0 | 0 | 35836 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the PMU activities progressed satisfactorily. Third tranche was approved subject to conditions in 72nd Excom meeting. Project activities were regularly reviewed. Prodoc signed (actual/planned, yes/no and date):The prodoc is planned to be signed in February 2015. Missions undertaken (actual/planned):4 planned - 3 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by April 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily. Last tranche request for HPMP submitted to and approved in 74th Excom. |  |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRA | PHA | 72 | PRP | 216 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 45000 | 3150 | 0 | 0 | 3150 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, interagency meeting was held in March 2014 for discussing data collection and project completion. Consultants for preparation of project have been identifed. Contracting process is expected to be completed by May 2015 after final stages of data collection on industries. The HPMP is expected to be submitted to the 74th Excom. Prodoc signed (actual/planned, yes/no and date):The prodoc is planned to be signed by April 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned - 0 prepared. Contract/PO/MOA agreements signed:1 contract planned and to be signed in April 2015. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No . If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities are progressing well. Q3/Q4 - strategy for HPMP would be developed. |  |  | Investment
FIN | UNDP | Preparation of three projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Foroughmanesh Co. | Individual | ASP | IRA | REF | 28 | INV | 43 | A | I | CFC | 35.8 | 35.8 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 399803 | -13456 | 386347 | 386347 | 100% | 0 | 0 | 0 | 51974 | -1749 | 50225.21 | -0.21 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Tahvieh Garm va Sard Co. | Individual | ASP | IRA | REF | 28 | INV | 44 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-02-01 | 278659 | -13367 | 265292 | 265292 | 100% | 0 | 0 | 0 | 36226 | -1738 | 34487.67 | 0.33 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Movaledsarma Co. (Zagross 1) | Individual | ASP | IRA | REF | 28 | INV | 46 | A | I | CFC | 77.6 | 77.6 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2004-01-01 | 816698 | -12094 | 804604 | 804604 | 100% | 0 | 0 | 0 | 99837 | -1330 | 98506.4145 | 0.58553 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HCFC-134a technology in the manufacture of commercial refrigeration equipment at Behsarma Co. | Individual | ASP | IRA | REF | 28 | INV | 65 | A | I | CFC | 34.5 | 34.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 455593 | -13588 | 442005 | 442005 | 100% | 0 | 0 | 0 | 59227 | -1766 | 57460.75 | 0.25 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 tgo HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Electro Shargh Mazandaran Co. | Individual | ASP | IRA | REF | 29 | INV | 55 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 301715 | -31900 | 269815 | 269815 | 100% | 0 | 0 | 0 | 39223 | -4147 | 35076.08 | -0.08 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardkaran Industrial Manufacturing Co. | Individual | ASP | IRA | REF | 29 | INV | 56 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2002-03-01 | 2003-11-01 | 155405 | -6082 | 149323 | 149323 | 100% | 0 | 0 | 0 | 20203 | -791 | 19411.99 | 0.01 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Khozestan Technique Co. | Individual | ASP | IRA | REF | 29 | INV | 58 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-04-01 | 132041 | -1 | 132040 | 132040 | 100% | 0 | 0 | 0 | 17165 | 0 | 17165.33 | -0.33 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Electro Sard Azna Co,. | Individual | ASP | IRA | REF | 29 | INV | 60 | A | I | CFC | 18.7 | 18.7 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 191061 | -33421 | 157640 | 157640 | 100% | 0 | 0 | 0 | 24838 | -4345 | 20493.2 | -0.2 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3044.99 | 0.01 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 3 projects in the domestic refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2029.95 | 0.05 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Prepare 2 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2029.95 | 0.05 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fadak Refrigeration Industries | Individual | ASP | IRA | REF | 31 | INV | 66 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-11-01 | 2003-11-01 | 258937 | 0 | 258937 | 258937 | 100% | 0 | 0 | 0 | 33662 | 0 | 33661.81 | 0.19 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial and domestic refrigeration equipment at Jaleh & Segin Co. | Individual | ASP | IRA | REF | 31 | INV | 67 | A | I | CFC | 23.6 | 23.6 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 322309 | 0 | 322309 | 322309 | 100% | 0 | 0 | 0 | 41900 | 0 | 41900.17 | -0.17 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at MH Seyed Salaki Co. | Individual | ASP | IRA | REF | 31 | INV | 68 | A | I | CFC | 9.8 | 9.8 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 141590 | 0 | 141590 | 141590 | 100% | 0 | 0 | 0 | 18407 | 0 | 18406.7 | 0.3 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Baharanfarr Co. | Individual | ASP | IRA | REF | 31 | INV | 70 | A | I | CFC | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-01-01 | 2003-08-01 |  |  | 2002-11-01 | 208070 | -207415 | 655 | 655 | 100% | 0 | 0 | 0 | 27049 | -26964 | 85.15 | -0.15 | 0 | Canceled in 2002. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fereidooni Refrigerant Industries | Individual | ASP | IRA | REF | 31 | INV | 71 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-11-01 | 157454 | 0 | 157454 | 157454 | 100% | 0 | 0 | 0 | 20469 | 0 | 20469.02 | -0.02 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Hanzad Co. | Individual | ASP | IRA | REF | 34 | INV | 100 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2007-03-01 | 199627 | -28424 | 171203 | 171203 | 100% | 0 | 0 | 0 | 25952 | -3695 | 22256.3202 | 0.6798 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sana Commercial Co. | Individual | ASP | IRA | REF | 34 | INV | 109 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 156286 | -367 | 155919 | 155919 | 100% | 0 | 0 | 0 | 20317 | -48 | 20269.4704 | -0.47039 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Golsarma Co. | Individual | ASP | IRA | REF | 34 | INV | 110 | A | I | CFC | 28.3 | 28.3 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 230066 | -13115 | 216951 | 216951 | 100% | 0 | 0 | 0 | 29909 | -1705 | 28203.58 | 0.42 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Shagayegh Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 112 | A | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 137985 | -514 | 137471 | 137471 | 100% | 0 | 0 | 0 | 17938 | -67 | 17871.05 | -0.05 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Yakhchalsazi Yazd Co. | Individual | ASP | IRA | REF | 34 | INV | 82 | A | I | CFC | 30 | 30 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 248646 | -43159 | 205487 | 205487 | 100% | 0 | 0 | 0 | 32324 | -5611 | 26712.98 | 0.02 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Rezvan Co. | Individual | ASP | IRA | REF | 34 | INV | 84 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 182182 | -34099 | 148083 | 148083 | 100% | 0 | 0 | 0 | 23684 | -4433 | 19250.7264 | 0.2736 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Electro Ara Co. | Individual | ASP | IRA | REF | 34 | INV | 85 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-06-01 | 2007-02-01 | 178784 | -45309 | 133475 | 133475 | 100% | 0 | 0 | 0 | 23242 | -5890 | 17351.7297 | 0.2703 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Boloorin Yazd Refrigerator Co. | Individual | ASP | IRA | REF | 34 | INV | 86 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2005-09-01 | 212320 | -37255 | 175065 | 175065 | 100% | 0 | 0 | 0 | 27602 | -4843 | 22758.6 | 0.4 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Sarmaye Sepahan Co. | Individual | ASP | IRA | REF | 34 | INV | 87 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 148525 | 0 | 148525 | 148525 | 100% | 0 | 0 | 0 | 19308 | 0 | 19308.25 | -0.25 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Mersun Co. | Individual | ASP | IRA | REF | 34 | INV | 89 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 162891 | -25194 | 137697 | 137697 | 100% | 0 | 0 | 0 | 21176 | -3275 | 17900.83 | 0.17 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ideal Sardsir Co. | Individual | ASP | IRA | REF | 34 | INV | 90 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 187907 | -13311 | 174596 | 174596 | 100% | 0 | 0 | 0 | 24428 | -1730 | 22697.91 | 0.09 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parsa Sazan Co. | Individual | ASP | IRA | REF | 34 | INV | 91 | A | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 212845 | -60001 | 152844 | 152844 | 100% | 0 | 0 | 0 | 27670 | -7800 | 19869.85 | 0.15 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Zenoz Sanaat Co. | Individual | ASP | IRA | REF | 34 | INV | 92 | A | I | CFC | 10.2 | 10.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2003-12-01 | 140036 | 0 | 140036 | 140036 | 100% | 0 | 0 | 0 | 18205 | 0 | 18204.68 | 0.32 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Part | Individual | ASP | IRA | REF | 34 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2005-10-01 | 114770 | 0 | 114770 | 114770 | 100% | 0 | 0 | 0 | 14920 | 0 | 14920.1 | -0.1 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sepand Afroz Co. | Individual | ASP | IRA | REF | 34 | INV | 94 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 172881 | -13071 | 159810 | 159810 | 100% | 0 | 0 | 0 | 22475 | -1699 | 20775.53 | 0.47 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Yakhchalsazi Anzabi Co. | Individual | ASP | IRA | REF | 34 | INV | 95 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 138935 | -17 | 138918 | 138918 | 100% | 0 | 0 | 0 | 18062 | -2 | 18059.34 | 0.66004 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at General Industries | Individual | ASP | IRA | REF | 34 | INV | 96 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 428197 | 0 | 428197 | 428197 | 100% | 0 | 0 | 0 | 55666 | 0 | 55665.61 | 0.39 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ghaynar Khazar Co. | Individual | ASP | IRA | REF | 34 | INV | 97 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-11-01 | 2003-11-01 | 191092 | -30740 | 160352 | 160352 | 100% | 0 | 0 | 0 | 24842 | -3996 | 20845.63 | 0.37 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ojan Cooling Industries | Individual | ASP | IRA | REF | 34 | INV | 99 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2004-01-01 | 110863 | 0 | 110863 | 110863 | 100% | 0 | 0 | 0 | 14412 | 0 | 14412.19 | -0.19 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the domestic refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | Individual | ASP | IRA | REF | 35 | INV | 131 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 116646 | -327 | 116319 | 116319 | 100% | 0 | 0 | 0 | 15164 | -43 | 15120.98 | 0.02 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | Individual | ASP | IRA | REF | 35 | INV | 132 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2006-10-01 | 153447 | -30506 | 122941 | 122941 | 100% | 0 | 0 | 0 | 19948 | -3966 | 15982.11 | -0.11 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | Individual | ASP | IRA | REF | 35 | INV | 133 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2001-12-01 | 2004-06-01 | 2004-07-01 |  | 2006-04-01 | 2011-07-01 | 170125 | -2574 | 167551 | 167551 | 100% | 0 | 0 | 0 | 22116 | -335 | 21781.6338 | -0.6338 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Havasaz Manufacturing and Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 134 | A | I | CFC | 24.5 | 24.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 252294 | -19021 | 233273 | 233273 | 100% | 0 | 0 | 0 | 32798 | -2473 | 30325.5065 | -0.50654 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Mehran Sard, Co. | Individual | ASP | IRA | REF | 35 | INV | 135 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 144715 | -1097 | 143618 | 143618 | 100% | 0 | 0 | 0 | 18813 | -143 | 18670.3396 | -0.33961 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parto Shiva Sanaat | Individual | ASP | IRA | REF | 35 | INV | 136 | A | I | CFC | 23.9 | 23.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2007-01-01 | 283948 | -36625 | 247323 | 247323 | 100% | 0 | 0 | 0 | 36913 | -4761 | 32152.021 | -0.021 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | Individual | ASP | IRA | REF | 35 | INV | 137 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 152024 | -32223 | 119801 | 119801 | 100% | 0 | 0 | 0 | 19763 | -4189 | 15574.12 | -0.12 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Boroudati Maleki | Individual | ASP | IRA | REF | 35 | INV | 138 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2006-06-01 | 215052 | -178 | 214874 | 214874 | 100% | 0 | 0 | 0 | 27957 | -23 | 27933.76 | 0.24 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Fan, Co. | Individual | ASP | IRA | REF | 35 | INV | 139 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-10-01 | 267075 | -26729 | 240346 | 240346 | 100% | 0 | 0 | 0 | 34720 | -3475 | 31244.955 | 0.045005 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 140 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 125244 | 0 | 125244 | 125244 | 100% | 0 | 0 | 0 | 16282 | 0 | 16281.72 | 0.28 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing of refrigeration equipment sector (terminal phase-out) | Individual | ASP | IRA | REF | 36 | PRP | 147 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 35000 | -5431 | 29569 | 29569 | 100% | 0 | 0 | 0 | 4550 | -706 | 3843.97 | 0.03 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IRA | REF | 57 | PRP | 193 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-12-01 | 2013-01-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2013. | The project is being closed by June 12. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | IRA | REF | 72 | PRP | 217 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2100 | 0 | 0 | 2100 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, interagency meeting was held in March 2014 for discussing data collection and project completion. Consultants for preparation of project have been identifed. Contracting process is expected to be completed by May 2015 after final stages of data collection on industries. The HPMP is expected to be submitted to the 74th Excom. Prodoc signed (actual/planned, yes/no and date):The prodoc is planned to be signed by April 2015. Missions undertaken (actual/planned):4 planned - 2 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned - 0 prepared. Contract/PO/MOA agreements signed:1 contract planned and to be signed in April 2015. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Preparation activities are progressing well. Q3/Q4 - strategy for HPMP would be developed. |  |  | Non-Investment
FIN | UNDP | Study to determine production and consumption of ODS | Individual | ASP | IRA | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 30350 | 0 | 30350 | 30350 | 100% | 0 | 0 | 0 | 3946 | 0 | 3945.5 | 0.5 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1993-06-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IRA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-12-01 | 2000-12-01 | 200200 | 0 | 200200 | 200200 | 100% | 0 | 0 | 0 | 26026 | 0 | 26026 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1992 |  | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | IRA | SEV | 08 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-11-01 | 1993-10-01 |  | 1995-03-01 | 1997-12-01 | 17935 | 0 | 17935 | 17935 | 100% | 0 | 0 | 0 | 2332 | 0 | 2331.55 | 0.45 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IRA | SEV | 23 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-08-01 | 1999-12-01 |  | 2002-05-01 | 2003-11-01 | 133470 | 0 | 133470 | 133470 | 100% | 0 | 0 | 0 | 17351 | 0 | 17351.1 | -0.1 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | IRA | SEV | 32 | INS | 74 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-08-01 | 2004-01-01 | 133470 | -25 | 133445 | 133445 | 100% | 0 | 0 | 0 | 17351 | -3 | 17347.85 | 0.15 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IRA | SEV | 38 | INS | 157 | N | I | No_ODP | 14.3 | 14.3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2005-12-01 | 2007-06-01 | 173511 | -1407 | 172104 | 172104 | 100% | 0 | 0 | 0 | 22556 | -183 | 22373.5222 | -0.5222 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IRA | SEV | 44 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-03-01 | 2007-06-01 | 86755 | -1313 | 85442 | 85442 | 100% | 0 | 0 | 0 | 6507 | -98 | 6408.5508 | 0.4492 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IRA | SEV | 45 | TAS | 172 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924 | 5268.5548 | 0.4452 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V, year 2) | Individual | ASP | IRA | SEV | 47 | INS | 174 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-03-01 | 2008-09-01 | 86756 | -69 | 86687 | 86687 | 100% | 0 | 0 | 0 | 6507 | -5 | 6501.8248 | 0.1752 | 0 | Completed in 2007. Financially Completed in 2008. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | IRA | SEV | 50 | INS | 179 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-07-01 | 2009-06-01 | 86755 | -65 | 86690 | 86690 | 100% | 0 | 0 | 0 | 6507 | -5 | 6502.1247 | -0.1247 | 0 | Completed in 2008.Financially completed in 2009. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI, second year) | Individual | ASP | IRA | SEV | 53 | INS | 185 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 86756 | -87 | 86669 | 86669 | 100% | 0 | 0 | 0 | 6507 | -7 | 6500.4747 | -0.47465 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | IRA | SEV | 56 | INS | 187 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 173511 | -403 | 173108 | 173108 | 100% | 0 | 0 | 0 | 13013 | -30 | 12982.7758 | 0.2242 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | IRA | SEV | 61 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 |  | 2013-03-01 | 2014-06-01 | 173511 | 0 | 173511 | 173511 | 100% | 0 | 0 | 0 | 13013 | 0 | 13013 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | IRA | SEV | 67 | INS | 206 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-06-01 | 2014-12-01 | 2015-09-01 |  |  | 173511 | 0 | 173511 | 161451 | 93.05% | 12060 | 0 | 4824.108 | 12146 | 0 | 11301.7651 | 844.2349 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, monitoring of ongoing ODS phase-out projects and HPMP preparation activities was undertaken. HPMP project activities were monitored closely with support from PMU. Ozone Office staff attended international and regional meetings on policy and technical consultations. Ozone day celebrations for 2013 were successfully undertaken. CP progress and Article 7 data for 2013 was reported in timely manner. IS-X was submitted approved at the 72nd ExCom. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in April 2013. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in June 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The IS Phase-IX has been operationallly completed in month 2015. The IS activities continue under the IS Phase-X. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | ASP | IRA | SEV | 72 | INS | 213 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-12-01 | 2017-07-01 |  |  | 173511 | 0 | 173511 | 0 | 0% | 173511 | 0 | 69404.4 | 12146 | 0 | 0 | 12146 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, monitoring of ongoing ODS phase-out projects and HPMP preparation activities was undertaken. HPMP project activities were monitored closely with support from PMU. Ozone Office staff attended international and regional meetings on policy and technical consultations. Ozone day celebrations for 2013 were successfully undertaken. CP progress and Article 7 data for 2013 was reported in timely manner. This is an ongoing project activity. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in August 2014. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by July 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The activities have been implementated as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. |  |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (fire-fighting and solvent sectors) | Individual | ASP | IRA | SOL | 57 | PRP | 194 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-12-01 | 2013-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at West Indies Synthetics Company, Ltd (Wisynco) | Individual | LAC | JAM | FOA | 22 | INV | 06 | A | I | CFC | 81.6 | 81.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 1998-12-01 | 2000-12-01 | 596000 | -3008 | 592992 | 592992 | 100% | 0 | 0 | 0 | 77480 | -391 | 77088.96 | 0.04 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | JAM | FOA | 61 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-05-01 | 2013-06-01 | 30000 | -987 | 29013 | 29013 | 100% | 0 | 0 | 0 | 2250 | -74 | 2175.975 | 0.025 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs: retrofitting/replacement programme | Individual | LAC | JAM | PHA | 37 | TAS | 17 | N | I | CFC | 2 | 2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2006-01-01 |  | 2007-12-01 | 2011-09-01 | 140000 | -7663 | 132337 | 133772 | 101.1% | -1435 | 0 | 0 | 18200 | -996 | 17390.36 | -186.36 | 0 | Completed in 2007. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | JAM | PHA | 55 | PRP | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-08-01 | 85000 | -28035 | 56965 | 56965 | 100% | 0 | 0 | 0 | 6375 | -2103 | 4272.375 | -0.37495 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
COM | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 28 | N | I | HCFC | 3.6 | 3.6 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 |  | 2014-12-01 |  | 95450 | 0 | 95450 | 79147 | 82.92% | 16303 | 0 | 13042.656 | 7159 | 0 | 5936.2083 | 1222.7917 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. Final trials were completed in 2014 and International Expert assessed results in Dec 2014 to declare the project completed. Pending final payments. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2012. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 fo 2. First disbursement date (actual/planned):The first disbursement took place in July 2012. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Initial delay was faced in the signature of the Agreement (MOA) with recipient company due to legal revision procedures by both parties. MOA was signed in late 2012 and project commenced immediately. Company took longer than expected to carry out final trials due to internal work demand on other fronts. Project was operationally completed in Dec 2014 (pending final payments) | As per the workplan, low density samples have been procured and trials shall take place in March 2014. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 | 2015-01-01 |  |  | 142000 | 0 | 142000 | 128497 | 90.49% | 13503 | 0 | 5401.284 | 10650 | 0 | 9637.2592 | 1012.7408 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, a second "train the trainers" course took place in Montego Bay. Implementation plan for the delivery of training to technicians has been approved by GOV. HC based pilot equipment was procured and delivered to training centers Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc has been signed prior to 2014 . Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:3 of 3. First disbursement date (actual/planned):The first disbursement took place in February 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, third "train the trainers" took place in Ocho Rios. Tools were delivered to the training local in Ocho Rios and awareness activities took place in the country | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | JAM | PHA | 70 | INV | 32 | N | I | HCFC | 4.7 | 0.9 | 0 | 0 | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7500 | 0 | 0 | 7500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, a second "train the trainers" course took place in Montego Bay. Implementation plan for the delivery of training to technicians has been approved by GOV. HC based pilot equipment was procured and delivered to training centers. Prodoc signed (actual/planned, yes/no and date):Yes, the original ProDoc was amended in April 2014 to include the second tranche. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:3 of 3. First disbursement date (actual/planned):. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, third "train the trainers" took place in Ocho Rios. Tools were delivered to the training local in Ocho Rios and awareness activities took place in the country | 2013 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | JAM | REF | 18 | TAS | 03 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1997-05-01 | 2000-12-01 | 172465 | -13366 | 159099 | 159099 | 100% | 0 | 0 | 0 | 22420 | -1738 | 20682.87 | -0.87 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | JAM | REF | 30 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2002-05-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | JAM | SEV | 14 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Project preparation in the aerosol, foam and refrigeration sectors | Individual | LAC | JAM | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 30000 | -16175 | 13825 | 13825 | 100% | 0 | 0 | 0 | 3900 | -2103 | 1797.25 | -0.25 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Formulation of the solvent sectoral phase out plan | Individual | LAC | JAM | SOL | 39 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Technical assistance umbrella project to phase out ODS solvent use | Individual | LAC | JAM | SOL | 42 | TAS | 20 | N | I | TCA | 0.8 | 0.8 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2006-12-01 | 2011-08-01 | 25000 | -3609 | 21391 | 21391 | 100% | 0 | 0 | 0 | 2250 | -325 | 1925.19 | -0.19 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Technical assistance and pre-feasibility study in aerosol sector | Individual | ASP | JOR | ARS | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Feasibility study on deodorization of local gas as a CFC substitute in cosmetics | Individual | ASP | JOR | ARS | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | ASP | KAM | PHA | 50 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -9560 | 5440 | 5440 | 100% | 0 | 0 | 0 | 1125 | -717 | 408 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-Year | ASP | KAM | PHA | 53 | INV | 16 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-12-01 | 2013-01-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KAM | PHA | 55 | PRP | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2010-12-01 | 2012-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | INV | 20 | N | I | CFC | 10 | 10 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-01-01 | 85000 | -1774 | 83226 | 83226 | 100% | 0 | 0 | 0 | 6375 | -133 | 6241.95 | 0.05 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | ASP | KAM | PHA | 61 | INV | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-05-01 | 2019-12-01 | 2019-12-01 |  |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the remaining R&R and related information outreach activites were undertaken. Retrofit incentive scheme was deferred due to non-availability of suitable low-GWP technologies. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 actual. Contract/PO/MOA agreements signed:1 MOA signed. First disbursement date (actual/planned):The first disbursement took place in May 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | A few awareness outreach activities have been conducted in Q1/Q2 in 2015. The project is expected to be operationally completed by late 2015. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | KAM | PHA | 70 | INV | 28 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2013-07-01 | 2014-05-01 | 2016-07-01 | 2016-07-01 |  |  | 200000 | 0 | 200000 | 50000 | 25% | 150000 | 150000 | 60000 | 15000 | 0 | 3750 | 11250 | 11250 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the implementation plan was discussed and finalized in mid-2014. The focus will be on R&R activities and promotion of HCFC-free alternatives. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in March 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in May 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Under the 2nd tranche, several awareness outreach activities for the users, relevance stakeholders and constitutions have been conducted to promote the alternative with non ODS and climate friendly based equipment. | 2013 |  | Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | ASP | KAM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 15000 | -1844 | 13156 | 13156 | 100% | 0 | 0 | 0 | 1950 | -240 | 1710.28 | -0.28 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | KAM | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant and awareness and incentive programme for the MAC sub-sector | RMP-Component | ASP | KAM | REF | 41 | TAS | 05 | N | I | CFC | 56.2 | 56.2 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-06-01 | 625000 | -267 | 624733 | 624733 | 100% | 0 | 0 | 0 | 46875 | -20 | 46854.975 | 0.02505 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNDP | Project preparation in the soil fumigant sector (cut flowers) | Individual | AFR | KEN | FUM | 36 | PRP | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
CLO | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | Multi-Year | AFR | KEN | FUM | 38 | INV | 31 | A | I | MeBr | 10 | 10 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  |  | 2010-10-01 | 510660 | -6536 | 504124 | 504124 | 100% | 0 | 0 | 0 | 66173 | -847 | 65326.0437 | -0.0437 | 0 | Financially completed in 2010 and cancelled in 2007. |  | 2002 | 2005-07-01 | Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation (second tranche) | Multi-Year | AFR | KEN | FUM | 44 | INV | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-11-01 | 306396 | -306396 | 0 | 0 |  | 0 | 0 | 0 | 22980 | -22980 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2004 |  | Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flowers (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 40 | A | I | MeBr | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2009-12-01 |  |  | 2007-11-01 | 204263 | -204263 | 0 | 0 |  | 0 | 0 | 0 | 15320 | -15320 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
TRF | UNDP | Demonstration and training unit for maintenance and recharge of refrigeration and air conditioning equipment | RMP-Component | AFR | KEN | REF | 04 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1993-06-01 |  |  | 1993-06-01 | 115100 | -105248 | 9852 | 9852 | 100% | 0 | 0 | 0 | 14963 | -13682 | 1281 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | AFR | KEN | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-07-01 |  | 1994-06-01 | 1997-12-01 | 25000 | -2270 | 22730 | 22730 | 100% | 0 | 0 | 0 | 3250 | -295 | 2954.9 | 0.1 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | KEN | SEV | 09 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-06-01 | 2005-09-01 | 175000 | -34 | 174966 | 174966 | 100% | 0 | 0 | 0 | 22750 | -4 | 22745.58 | 0.42 | 0 | Completed in 1998. Financially completed in 2005. |  | 1993 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | KEN | SEV | 25 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-12-01 | 2003-10-01 | 116667 | 0 | 116667 | 116667 | 100% | 0 | 0 | 0 | 15167 | 0 | 15166.71 | 0.29 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | AFR | KEN | SEV | 32 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2005-09-01 | 116667 | -234 | 116433 | 116433 | 100% | 0 | 0 | 0 | 15167 | -30 | 15136.2894 | 0.7106 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | KEN | SEV | 38 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 151667 | -204 | 151463 | 151463 | 100% | 0 | 0 | 0 | 19717 | -27 | 19689.71 | 0.29 | 0 | Completed in 2004. Financially completed in 2006. |  | 2002 |  | Non-Investment
TRF | UNDP | Extension of institutional strengthening project (phase V) | Individual | AFR | KEN | SEV | 44 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  |  | 2010-10-01 | 151667 | -786 | 150881 | 150881 | 100% | 0 | 0 | 0 | 11375 | -59 | 11316.0501 | -0.0501 | 0 | Transferred in 2007. Financially completed in 2010. |  | 2004 |  | Non-Investment
TRF | UNDP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 50 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  |  | 2007-12-01 | 75833 | -75833 | 0 | 0 |  | 0 | 0 | 0 | 5688 | -5688 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Non-Investment
FIN | UNDP | Project preparation for the formulation of solvent sectoral phase-out plan | Individual | AFR | KEN | SOL | 42 | PRP | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2007-09-01 | 2010-10-01 | 20000 | -1850 | 18150 | 18150 | 100% | 0 | 0 | 0 | 1500 | -139 | 1361.25 | -0.25 | 0 | Financially completed in 2010. |  | 2004 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | KYR | FOA | 58 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  |  | 2010-12-01 | 30000 | -24996 | 5004 | 5004 | 100% | 0 | 0 | 0 | 2250 | -1875 | 375.3 | -0.3 | 0 | After technical visit in early 2010, and discussions with foam company Winterlux, the company decided to switch to non-HCFC technology itself. The further work on the formulation of investment project proposal was discontinued. MLF Secretariat was informed about this during the submission of HPMP. The PRP is cancelled and unspent funds are to be returned in 2011. |  | 2009 |  | Investment
FIN | UNDP | Technical assistance project to install alternatives and phase-out methyl bromide | One-off-Phaseout | ASP | KYR | FUM | 41 | TAS | 08 | N | I | MeBr | 14.2 | 14.2 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2008-12-01 |  | 2007-12-01 | 2009-08-01 | 300000 | -407 | 299593 | 299593 | 100% | 0 | 0 | 0 | 22500 | -31 | 22469.475 | -0.475 | 0 | Completed in 2007.Financially completed in 2009. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | ASP | KYR | PHA | 47 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -908 | 29092 | 29092 | 100% | 0 | 0 | 0 | 2250 | -68 | 2181.9001 | 0.09995 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | ASP | KYR | PHA | 50 | INV | 14 | N | I | CFC | 1 | 1 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2009-11-01 |  | 2008-12-01 | 2011-01-01 | 194000 | 0 | 194000 | 194000 | 100% | 0 | 0 | 0 | 14550 | 0 | 14550 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-year | ASP | KYR | PHA | 55 | INV | 18 | N | I | CFC | 1 | 1 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-01-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 | 0 | 4725 | 0 | 4725 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KYR | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -739 | 84261 | 84261 | 100% | 0 | 0 | 0 | 6375 | -55 | 6319.575 | 0.425 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (third tranche) | Multi-year | ASP | KYR | PHA | 60 | INV | 23 | N | I | CFC | 5 | 5 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2010 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | KYR | PHA | 63 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 |  | 2013-12-01 |  | 47520 | 0 | 47520 | 46862 | 98.62% | 658 | 0 | 526.44 | 4277 | 0 | 4217.7727 | 59.2273 | 0 | UNDP supervision mission fielded in September 2013. National expert continued to provide assistance to NOU on investment projects. No demonstration project on CO2/NH3 double-stage was possible due to high cost for imported components (compressors). In line with original plan, sixteen (16) sets of servicing tools/ equipment were purchased and then distributed to technicians/ service centers in the country. | Workplan for 2014 formulated and endorsed by NOU. Funds for 2014 plan allocated. Request for HPMP Stage I Tranche II submitted jointly with UNEP to the 72nd ExCom. HPMP Stage II PRP request was submitted to the 72nd ExCom and received recommendations from | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | KYR | PHA | 72 | INV | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 5280 | 0 | 5280 | 0 | 0% | 5280 | 0 | 2112 | 475 | 0 | 0 | 475 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, 25 units of equipment were purchased. An additional 15 units are planned to be purchased in 2015. Prodoc signed (actual/planned, yes/no and date): Yes, 28/10/2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1, on equipment purchase. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The project's first disbursement is planned on 6/02/2015. Any delays/problems (yes/no):Yes, there were problems on the agreement of the funds disbursement modality. If Yes, reasons for delay & action plan to resolve:A harmonized system of fund advance (HACT) was proposed as a solution, which is now being tested. By this system, funding advances are made with follow-up financial reporting from NOU. | Mission held in February 2015. Additional R/R equipment (10 sets) purchased and delivered to recipients as planned. Project is set for closure, and NOU-Kyrgyzstan will focus on the start-up of the newly approved HPMP Stage II. |  |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | KYR | PHA | 72 | PRP | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 | 2016-01-01 |  |  | 20000 | 0 | 20000 | 12429 | 62.14% | 7571 | 0 | 7571.38 | 1400 | 0 | 870.0034 | 529.9966 | 0 | Remarks (Short narrative description of progress made (actual/planned)):HPMP Stage II formulation works were initiated in September 2014. Four National experts were recruited in October 2014. Field visits held to all the country’s regions for data collection during September - December 2014. National consultations held in November-December 2014. HPMP Stage II to be submitted in Q1 of 2015. Prodoc signed (actual/planned, yes/no and date):Project document was signed on 28/10/2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):4 of 4, mostly for national experts on HCFC data collection and updates. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):14/11/2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Final mission and stakeholder workshop jointly with UNEP held in February 2015. HPMP Stage II submitted to and approved at the 75th ExCom in May 2015. |  |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | ASP | KYR | REF | 37 | TAS | 01 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-08-01 |  | 2006-12-01 | 2008-03-01 | 16500 | -1 | 16499 | 16499 | 100% | 0 | 0 | 0 | 2145 | 0 | 2144.87 | 0.13 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | KYR | REF | 37 | TAS | 02 | A | I | CFC | 20.6 | 20.6 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 187242 | -3511 | 183731 | 183731 | 100% | 0 | 0 | 0 | 24341 | -456 | 23885.03 | -0.03 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for refrigerant recovery and recycling | RMP-Component | ASP | KYR | REF | 37 | TAS | 04 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2003-10-01 | 2007-03-01 | 185175 | -1007 | 184168 | 184168 | 100% | 0 | 0 | 0 | 24073 | -131 | 23941.8386 | 0.1614 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | KYR | REF | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  |  | 2010-12-01 | 30000 | -23994 | 6006 | 6006 | 100% | 0 | 0 | 0 | 2250 | -1800 | 450.45 | -0.45 | 0 | After technical visit in early 2010, it was recommended to prepare a stand-alone component on technical assistance to HCFC equipment assemblers as a part of HPMP servicing sector. The further work on the formulation of investment project proposal was discontinued. MLF Secretariat was informed about the findings of the mission. Component on HCFC equipment assemblers was included in the original submission of HPMP in August 2010, but during subsequent re-submission of HPMP in December 2010, it was excluded from HPMP design in light of decision 62/14. Funds will be returned in 2011. |  | 2009 |  | Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Latin America | Individual | LAC | LAC | FOA | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | 1312 | 53812 | 53812 | 100% | 0 | 0 | 0 | 6825 | 171 | 6995.56 | 0.44 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 1998-12-01 | 57700 | 0 | 57700 | 57700 | 100% | 0 | 0 | 0 | 7501 | 0 | 7501 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in Latin America | Individual | LAC | LAC | HAL | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1994-06-01 | 1997-12-01 | 60000 | -15158 | 44842 | 44842 | 100% | 0 | 0 | 0 | 7800 | -1971 | 5829.46 | -0.46 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Latin America | RMP-Component | LAC | LAC | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1995-11-01 | 1994-02-01 |  | 1995-11-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Latin America | Individual | LAC | LAC | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1992-09-01 | 1997-12-01 | 40000 | -16953 | 23047 | 23047 | 100% | 0 | 0 | 0 | 5200 | -2204 | 2996 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Regional Latin America demonstration project in recovery of ODS in MACs: Phase I (Argentina, Colombia) | RMP-Component | LAC | LAC | REF | 18 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1999-05-01 | 207000 | 0 | 207000 | 207000 | 100% | 0 | 0 | 0 | 26910 | 0 | 26910 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | LAC | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 |  | 2010-12-01 | 2013-02-01 | 1000000 | -1000000 | 0 | 0 |  | 0 | 0 | 0 | 75000 | -75000 | 0 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | LAO | FOA | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2243.67 | 0.33 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) in the manufacture of flexible polyurethane foam (box) at Prasert Foam Co., Ltd. | Individual | ASP | LAO | FOA | 38 | INV | 10 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-08-01 | 2005-11-01 | 139343 | 0 | 139343 | 139343 | 100% | 0 | 0 | 0 | 18115 | 0 | 18114.59 | 0.41 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of a terminal phase out project in the foam sector | Individual | ASP | LAO | FOA | 39 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
CLO | UNDP | Conversion from CFC-11 in the manufacture of boxfoam (FPF) and insulated containers (RPF) in Prasert Sofa Shop Co., Ltd. | Individual | ASP | LAO | FOA | 44 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-12-01 | 184660 | -184660 | 0 | 0 |  | 0 | 0 | 0 | 16619 | -16619 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2004 |  | Investment
CLO | UNDP | Project preparation for foam multiple sub-sectors | Individual | ASP | LAO | FOA | 45 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  |  | 2006-12-01 | 22493 | 0 | 22493 | 22493 | 100% | 0 | 0 | 0 | 1687 | 0 | 1687 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Preparation of four projects in the aerosol sector | Individual | ASP | LEB | ARS | 27 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | Individual | ASP | LEB | ARS | 28 | INV | 30 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 158582 | -5069 | 153513 | 153513 | 100% | 0 | 0 | 0 | 20616 | -659 | 19956.6791 | 0.32091 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | Individual | ASP | LEB | ARS | 28 | INV | 35 | A | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 147333 | -2643 | 144690 | 144690 | 100% | 0 | 0 | 0 | 19153 | -344 | 18809.7052 | -0.70518 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | Individual | ASP | LEB | ARS | 29 | INV | 32 | A | I | CFC | 50.7 | 50.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2004-09-01 | 2005-10-01 | 314092 | -1547 | 312545 | 312545 | 100% | 0 | 0 | 0 | 40832 | -201 | 40630.8498 | 0.15025 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Preparation of project in the foam subsector | Individual | ASP | LEB | FOA | 27 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | LEB | FOA | 33 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 12000 | -1934 | 10066 | 10066 | 100% | 0 | 0 | 0 | 1560 | -251 | 1308.58 | 0.42 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | LEB | FOA | 57 | PRP | 71 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2012-09-01 | 2013-11-01 | 25000 | -643 | 24357 | 24357 | 100% | 0 | 0 | 0 | 1875 | -48 | 1826.775 | 0.225 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | LEB | FOA | 72 | PRP | 81 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1400 | 0 | 0 | 1400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the prodoc for HPMP Stage-II preparation was signed. Consultants were identified for technical inputs and survey. Contracts are expected to be signed in Q1-2015. Prodoc signed (actual/planned, yes/no and date):Planned in September 2014 and actual in December 2014. Missions undertaken (actual/planned):1 planned and 0 undertaken. TOR for consultants/subcontracts completed (actual/planned):3 planned and 3 prepared. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation is ongoing and the strategy is expected to be submitted to the 75th Excom. |  |  | Non-Investment
FIN | UNDP | Project preparation for one methyl bromide alternative demonstration project | Individual | ASP | LEB | FUM | 25 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-08-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Demonstration project of alternative to methyl bromide for soil fumigation (greenhouse) | Individual | ASP | LEB | FUM | 26 | DEM | 24 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 328200 | -2958 | 325242 | 325242 | 100% | 0 | 0 | 0 | 42666 | -385 | 42281.46 | -0.46 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | ASP | LEB | FUM | 33 | PRP | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2001 |  | Investment
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 46 | N | I | MeBr | 25.8 | 25.8 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-12-01 |  | 2004-12-01 | 2012-01-01 | 800000 | 0 | 800000 | 800000 | 100% | 0 | 0 | 0 | 98000 | 0 | 98000 | 0 | 0 | Financially completed in 2012. |  | 2001 |  | Investment
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (second tranche) | Multi-Year | ASP | LEB | FUM | 38 | INV | 51 | N | I | MeBr | 31.8 | 31.8 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2004-12-01 | 2012-01-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 76000 | 0 | 76000 | 0 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetable, cut flower and tobacco production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 53 | N | I | MeBr | 54 | 54 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-06-01 | 2012-01-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fourth tranche) | Multi-Year | ASP | LEB | FUM | 44 | INV | 58 | N | I | MeBr | 36 | 36 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2005-12-01 |  | 2008-12-01 | 2012-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 61 | N | I | MeBr | 66.4 | 66.4 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-03-01 |  | 2009-12-01 | 2012-01-01 | 210000 | 56717 | 266717 | 266717 | 100% | 0 | 0 | 0 | 15750 | 4254 | 20004.274 | -0.27395 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNDP | Preparation of a CFC terminal programme | Individual | ASP | LEB | PHA | 36 | PRP | 48 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-12-01 | 2007-03-01 | 15000 | -3601 | 11399 | 11399 | 100% | 0 | 0 | 0 | 1950 | -468 | 1481.87 | 0.13 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of a CFC phase-out plan | Individual | ASP | LEB | PHA | 42 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2004-12-01 | 2005-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2004 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (first tranche) | Multi-Year | ASP | LEB | PHA | 44 | INV | 57 | N | I | CFC | 55 | 55 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2012-01-01 | 1061420 | 0 | 1061420 | 1061420 | 100% | 0 | 0 | 0 | 79607 | 0 | 79607 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (second and third tranches) | Multi-Year | ASP | LEB | PHA | 48 | INV | 63 | N | I | CFC | 287 | 287 | 0 | 0 | 2006-04-01 | 2008-01-01 | 2007-04-01 |  | 2008-12-01 | 2012-01-01 | 865000 | 0 | 865000 | 865000 | 100% | 0 | 0 | 0 | 64875 | 0 | 64875 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fourth tranche) | Multi-Year | ASP | LEB | PHA | 53 | INV | 65 | N | I | CFC | 40 | 40 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2012-01-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fifth tranche) | Multi-year | ASP | LEB | PHA | 55 | INV | 66 | N | I | CFC | 35 | 35 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2012-01-01 | 65000 | -400 | 64600 | 64600 | 100% | 0 | 0 | 0 | 4875 | -30 | 4845 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | LEB | PHA | 55 | PRP | 67 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2011-12-01 | 2013-11-01 | 137250 | 0 | 137250 | 137250 | 100% | 0 | 0 | 0 | 10294 | 0 | 10293.75 | 0.25 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 74 | N | I | HCFC | 3 | 3 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 555000 | 0 | 555000 | 555000 | 100% | 0 | 0 | 0 | 41625 | 0 | 41625 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 76 | N | I | HCFC | 9.1 | 9.1 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 810000 | 0 | 810000 | 810000 | 100% | 0 | 0 | 0 | 60750 | 0 | 60750 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | TAS | 75 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-02-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 | 0 | 10125 | 0 | 10125 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | LEB | PHA | 70 | INV | 78 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-09-01 | 2015-07-01 | 2017-01-01 |  |  | 745589 | 0 | 745589 | 589466 | 79.06% | 156123 | 0 | 62449.288 | 55919 | 0 | 44209.7951 | 11709.2049 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, investment projects relating to foam and ref. sector were completed and all milestones achievement were verified. Monitoring of activites will be continued during the next 2 years. Technical assistance activities for foam and ref sector would also be continued and implementation of all activities under this component is expected to be completed in 2016. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in August 2013. Missions undertaken (actual/planned):2 planned and 0 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in September 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily. Third tranche request for Lebanon approved in 74th Excom. Enterprise level conversion in RAC and foam sector completed. Other technical support and information outreach activities are in progress. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | LEB | PHA | 72 | PRP | 80 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 4900 | 0 | 0 | 4900 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the prodoc for HPMP Stage-II preparation was signed. Consultants were identified for technical inputs and survey. Contracts are expected to be signed in Q1-2015. Prodoc signed (actual/planned, yes/no and date):Planned in September 2014 and actual in December 2014. Missions undertaken (actual/planned):1 planned and 0 undertaken. TOR for consultants/subcontracts completed (actual/planned):3 planned and 3 prepared. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation is ongoing and the strategy is expected to be submitted to the 75th Excom. |  |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Farjallah Co. | Individual | ASP | LEB | REF | 29 | INV | 34 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-07-01 | 200046 | 0 | 200046 | 200046 | 100% | 0 | 0 | 0 | 26006 | 0 | 26005.98 | 0.02 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | LEB | REF | 57 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 | 2013-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | LEB | REF | 57 | PRP | 70 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 | 2013-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sectors) | Individual | ASP | LEB | REF | 72 | PRP | 79 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4200 | 0 | 0 | 4200 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, the prodoc for HPMP Stage-II preparation was signed. Consultants were identified for technical inputs and survey. Contracts are expected to be signed in Q1-2015. Prodoc signed (actual/planned, yes/no and date):Planned in September 2014 and actual in December 2014. Missions undertaken (actual/planned):1 planned and 0 undertaken. TOR for consultants/subcontracts completed (actual/planned):3 planned and 3 prepared. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by May 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation is ongoing and the strategy is expected to be submitted to the 75th Excom. |  |  | Non-Investment
FIN | UNDP | Creation of an Ozone Unit | Individual | ASP | LEB | SEV | 19 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 2000-05-01 |  | 2000-12-01 | 2002-03-01 | 179000 | -63 | 178937 | 178937 | 100% | 0 | 0 | 0 | 23270 | -8 | 23261.81 | 0.19 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | ASP | LEB | SEV | 31 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2003-07-01 | 2004-12-01 | 119300 | 0 | 119300 | 119300 | 100% | 0 | 0 | 0 | 15509 | 0 | 15509 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | LEB | SEV | 36 | CPG | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2003-12-01 | 2004-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 3) | Individual | ASP | LEB | SEV | 37 | INS | 50 | N | I | No_ODP | 12.8 | 12.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-12-01 | 2009-07-01 | 155090 | -979 | 154111 | 154111 | 100% | 0 | 0 | 0 | 20162 | -127 | 20034.4281 | 0.5719 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | LEB | SEV | 44 | INS | 59 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-06-01 | 2010-10-01 | 155090 | -2835 | 152255 | 152255 | 100% | 0 | 0 | 0 | 11632 | -213 | 11419.3704 | -0.37045 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | LEB | SEV | 45 | TAS | 60 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-09-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616 | 3511.7517 | 0.2483 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | LEB | SEV | 50 | INS | 64 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 155090 | -373 | 154717 | 154717 | 100% | 0 | 0 | 0 | 11632 | -28 | 11604.0244 | -0.0244 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | LEB | SEV | 56 | INS | 68 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-03-01 |  | 2011-06-01 | 2013-02-01 | 155090 | 0 | 155090 | 155090 | 100% | 0 | 0 | 0 | 11632 | 0 | 11632 | 0 | 0 | Financially completed in 2013. | Completed in 2011. The project is being financially closed in 2012. | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | LEB | SEV | 62 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-03-01 |  | 2013-03-01 | 2013-12-01 | 155090 | 0 | 155090 | 155090 | 100% | 0 | 0 | 0 | 11632 | 0 | 11632 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 4/2013-3/2015) | Individual | ASP | LEB | SEV | 68 | INS | 77 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2015-03-01 | 2016-01-01 |  |  | 155090 | 0 | 155090 | 75369 | 48.6% | 79721 | 0 | 31888.552 | 10856 | 0 | 5275.6576 | 5580.3424 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, the NOU monitored implementation of national regulations including licensing system. NOU staff also participated in regional and international meetings on technical and policy issues. Ozone Day celebrations for the year 2013 were also conducted satisfactorily. A7 data and CP progress report for the year 2013 were also reported. IS-IX has been submitted and approved at the 73rd ExCom. Prodoc signed (actual/planned, yes/no and date):Planned in April 2013 and actual in July 2013. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in September 2013. Any delays/problems (yes/no):None. If Yes, reasons for delay & action plan to resolve:N/A. | The activities are progressing satisfactory. The NOU participated in the West Asia network meeting in March in Bahrain. The 2014 CP report was submitted in a timely manner. It is expected to be operationally completed in late-2015 | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 4/2015-3/2017) | Individual | ASP | LEB | SEV | 73 | INS | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2017-03-01 | 2017-03-01 |  |  | 155090 | 0 | 155090 | 0 | 0% | 155090 | 0 | 62036 | 10856 | 0 | 0 | 10856 | 0 | Newly Approved | The activities are expected to be initiated in late- 2015 | 2014 |  | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | LES | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-06-01 | 2002-03-01 | 20000 | -2704 | 17296 | 17296 | 100% | 0 | 0 | 0 | 2600 | -352 | 2248.48 | -0.48 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | LES | REF | 22 | TAS | 04 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2000-12-01 | 56095 | 0 | 56095 | 56095 | 100% | 0 | 0 | 0 | 7292 | 0 | 7292.35 | -0.35 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | Individual | AFR | LIB | FOA | 32 | INV | 05 | A | I | CFC | 26 | 19 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  |  | 2008-04-01 | 128097 | -106916 | 21181 | 21181 | 100% | 0 | 0 | 0 | 16653 | -13899 | 2753.2045 | 0.7955 | 0 | Canceled in 2005. Financially completed in 2008. Balance returned in 2009. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | Individual | AFR | LIB | FOA | 32 | INV | 06 | A | I | CFC | 40.3 | 40.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-12-01 | 2011-12-01 | 109810 | 0 | 109810 | 109810 | 100% | 0 | 0 | 0 | 14275 | 0 | 14275.3 | -0.3 | 0 | Completed in 2005. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | LIB | FOA | 32 | INV | 07 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2005-12-01 | 2008-04-01 | 119802 | -7675 | 112127 | 112127 | 100% | 0 | 0 | 0 | 15574 | -998 | 14576.5267 | -0.5267 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | Individual | AFR | LIB | FOA | 32 | INV | 08 | A | I | CFC | 31.4 | 31.4 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2007-04-01 | 2008-03-01 | 124860 | -97 | 124763 | 124763 | 100% | 0 | 0 | 0 | 16232 | -13 | 16219.1898 | -0.1898 | 0 | Completed in 2007. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | LIB | FOA | 32 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2000-12-01 | 2001-12-01 |  | 2001-03-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | LIB | FOA | 33 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | -1934 | 23066 | 23066 | 100% | 0 | 0 | 0 | 3250 | -251 | 2998.58 | 0.42 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | Individual | AFR | LIB | FOA | 34 | INV | 12 | A | I | CFC | 32 | 32 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2007-03-01 | 129109 | 0 | 129109 | 129109 | 100% | 0 | 0 | 0 | 16784 | 0 | 16784.17 | -0.17 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa | Individual | AFR | LIB | FOA | 34 | INV | 13 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2008-04-01 | 113727 | 0 | 113727 | 113727 | 100% | 0 | 0 | 0 | 14785 | 0 | 14784.51 | 0.49 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | Individual | AFR | LIB | FOA | 35 | INV | 14 | A | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-10-01 | 112440 | 0 | 112440 | 112440 | 100% | 0 | 0 | 0 | 14617 | 0 | 14617.2 | -0.2 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to liquid carbon dioxide (LCD) in the manufacture of flexible polyurethane foam at El Houria Unit Plant | Individual | AFR | LIB | FOA | 35 | INV | 15 | A | I | CFC | 96 | 96 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-08-01 | 2011-11-01 | 520405 | -49887 | 470518 | 470518 | 100% | 0 | 0 | 0 | 67245 | -6446 | 60798.3181 | 0.68192 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga | Individual | AFR | LIB | FOA | 35 | INV | 16 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2007-03-01 | 125640 | 0 | 125640 | 125640 | 100% | 0 | 0 | 0 | 16333 | 0 | 16333.2 | -0.2 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-12-01 | 2007-03-01 | 20000 | -9146 | 10854 | 10854 | 100% | 0 | 0 | 0 | 2600 | -1189 | 1411.02 | -0.02 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | LIR | PHA | 49 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -617 | 11383 | 11383 | 100% | 0 | 0 | 0 | 900 | -46 | 853.725 | 0.275 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | LIR | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2011-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | INV | 16 | N | I | CFC | 8.4 | 8.4 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-12-01 | 28000 | -1437 | 26563 | 26563 | 100% | 0 | 0 | 0 | 2520 | -129 | 2390.67 | 0.33 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNDP | Safety and technical programme to aid manufacturers of aerosol products | Individual | ASP | MAL | ARS | 12 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1996-03-01 |  | 1995-12-01 | 2001-12-01 | 145700 | -40377 | 105323 | 105323 | 100% | 0 | 0 | 0 | 18941 | -5249 | 13691.99 | 0.01 | 0 | Completed in 1995. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | UNDP | Conversion to hydrocarbon technology in the manufacture of aerosol products at Maya Chemical Industries Sdn., Bhd. | Individual | ASP | MAL | ARS | 17 | INV | 60 | A | R | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 37808 | 0 | 37808 | 37808 | 100% | 0 | 0 | 0 | 4915 | 0 | 4915.04 | -0.04 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Alloychem Malaysia Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 64 | A | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2001-12-01 | 2003-11-01 | 99500 | -13228 | 86272 | 86272 | 100% | 0 | 0 | 0 | 12935 | -1720 | 11215.49 | -0.49 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | Individual | ASP | MAL | ARS | 19 | INV | 85 | A | I | CFC | 250 | 250 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1998-04-01 |  | 2005-12-01 | 2011-05-01 | 1486660 | -149074 | 1337586 | 1337586 | 100% | 0 | 0 | 0 | 193266 | -19380 | 173886.18 | -0.18 | 0 | Completed in 2005. |  | 1996 | 2001-12-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam sheet at Jumaya Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 10 | INV | 11 | A | R | CFC | 150 | 150 | 0 | 0 | 1993-06-01 | 1993-12-01 | 1994-12-01 |  | 1993-12-01 | 1997-12-01 | 235811 | 62 | 235873 | 235873 | 100% | 0 | 0 | 0 | 30655 | 8 | 30663.49 | -0.49 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Key Asset Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 15 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-11-01 |  | 1995-02-01 | 1998-12-01 | 690000 | -15755 | 674245 | 674245 | 100% | 0 | 0 | 0 | 89700 | -2048 | 87652 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane insulation foam at Insafoam Insulation Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 16 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 310000 | -3393 | 306607 | 306607 | 100% | 0 | 0 | 0 | 40300 | -441 | 39859 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Island Resources Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 17 | A | I | TCA/CFC | 16.5 | 16.5 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-04-01 | 1998-12-01 | 230000 | -14204 | 215796 | 215796 | 100% | 0 | 0 | 0 | 29900 | -1846 | 28054 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polysterene and polyethylene foam sheet at Associated Air-Pack Industries, Sdb. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 21 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 234000 | 17126 | 251126 | 251126 | 100% | 0 | 0 | 0 | 30420 | 2226 | 32646 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of polyurethane insulated panel at Cycle World Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 22 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-03-01 |  | 1997-06-01 | 2000-12-01 | 353000 | -1 | 352999 | 352999 | 100% | 0 | 0 | 0 | 45890 | 0 | 45889.87 | 0.13 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-12 in the manufacture of EPS/EPE foam sheet at Pulai Lamipak Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 23 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1994-12-01 |  | 1996-08-01 | 2002-03-01 | 355000 | -17066 | 337934 | 337934 | 100% | 0 | 0 | 0 | 46150 | -2219 | 43931 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin, spoiler and moulded flexible foam at P.U. Tech Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 24 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 198000 | 0 | 198000 | 198000 | 100% | 0 | 0 | 0 | 25740 | 0 | 25739.74 | 0.26 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin polyurethane foam at P.U. Mate Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 25 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 113000 | -9294 | 103706 | 103706 | 100% | 0 | 0 | 0 | 14690 | -1208 | 13482 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam at Pexafoam Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 26 | A | I | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 2003-09-01 | 195000 | -5077 | 189923 | 189923 | 100% | 0 | 0 | 0 | 25350 | -660 | 24690.0147 | -0.0147 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at N.L.Y. Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 27 | A | I | CFC | 55 | 55 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 130000 | -14651 | 115349 | 115349 | 100% | 0 | 0 | 0 | 16900 | -1905 | 14995 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of flexible polyurethane foam (slabstock) at small scale producers | Individual | ASP | MAL | FOA | 12 | INV | 33 | A | I | CFC | 80 | 80 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-03-01 |  | 1998-08-01 | 2000-12-01 | 1045000 | -55552 | 989448 | 989448 | 100% | 0 | 0 | 0 | 135850 | -7222 | 128628.24 | -0.24 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane foam panels for cold storage at Wong Brothers Electrical and Refrigeration Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 38 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1999-03-01 | 2001-12-01 | 299000 | -1 | 298999 | 298999 | 100% | 0 | 0 | 0 | 38870 | 0 | 38869.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-05-01 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Eversoft Foam Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 39 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1996-12-01 | 1998-12-01 | 185000 | -1 | 184999 | 184999 | 100% | 0 | 0 | 0 | 24050 | 0 | 24049.87 | 0.13 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Nian Aik Foam Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 40 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 245000 | -53100 | 191900 | 191900 | 100% | 0 | 0 | 0 | 31850 | -6903 | 24947 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid panels for commercial refrigerators at Pangkat Refrigeration Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 41 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 210000 | -6736 | 203264 | 203264 | 100% | 0 | 0 | 0 | 27300 | -876 | 26424.32 | -0.32 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of polyurethane foam for pipe insulation at Allied Foam Insulation | Individual | ASP | MAL | FOA | 13 | INV | 43 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 276000 | -2955 | 273045 | 273045 | 100% | 0 | 0 | 0 | 35880 | -384 | 35495.85 | 0.15 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at Phoenix Base Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 44 | A | I | CFC | 61 | 61 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-06-01 |  | 1995-02-01 | 1998-12-01 | 165000 | 12784 | 177784 | 177784 | 100% | 0 | 0 | 0 | 21450 | 1662 | 23112 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam for use as imitation wood at Saferay (M) SDN BHD | Individual | ASP | MAL | FOA | 15 | INV | 46 | A | I | CFC | 11 | 11 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1997-06-01 | 1998-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of pipe insulation at Ricwil Sdn Bhd | Individual | ASP | MAL | FOA | 15 | INV | 47 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 118000 | -13464 | 104536 | 104536 | 100% | 0 | 0 | 0 | 15340 | -1750 | 13590 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of moulded and flexible PU foams at Dream Products Snd. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 48 | A | D | CFC | 15 | 15 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-11-01 |  | 1998-09-01 | 2000-07-01 | 66500 | -154 | 66346 | 66346 | 100% | 0 | 0 | 0 | 8645 | -20 | 8624.98 | 0.02 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels at Rigid Foam Industries, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 49 | A | I | CFC | 19 | 19 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1997-12-01 | 2000-07-01 | 335000 | -3198 | 331802 | 331802 | 100% | 0 | 0 | 0 | 43550 | -416 | 43134.26 | -0.26 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels and shipyard insulation works at Leading Refrigeration and Engineering, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 50 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 214000 | -13246 | 200754 | 200754 | 100% | 0 | 0 | 0 | 27820 | -1722 | 26098 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of the use of CFC in the manufacture of rigid PU panels at Shaga Cooling Technology | Individual | ASP | MAL | FOA | 15 | INV | 56 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1996-10-01 | 2000-12-01 | 190000 | -12498 | 177502 | 177502 | 100% | 0 | 0 | 0 | 24700 | -1625 | 23075.26 | -0.26 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured PUF molded products at Urethane Technologies Sdn., Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 61 | A | D | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-07-01 |  | 1997-12-01 | 2000-12-01 | 199000 | -7010 | 191990 | 191990 | 100% | 0 | 0 | 0 | 25870 | -911 | 24958.7 | 0.3 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Artwright Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 65 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2002-03-01 | 90320 | 0 | 90320 | 90320 | 100% | 0 | 0 | 0 | 11742 | 0 | 11741.6 | 0.4 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured/integral skin PUF molded at Muda Murni Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 66 | A | I | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2000-12-01 | 236500 | -52362 | 184138 | 184138 | 100% | 0 | 0 | 0 | 30745 | -6807 | 23937.94 | 0.06 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of molded/integral skin PUF at Bristol Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 67 | A | I | CFC | 8 | 8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-02-01 | 2000-07-01 | 123400 | -475 | 122925 | 122925 | 100% | 0 | 0 | 0 | 16042 | -61 | 15980.51 | 0.49 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Sze Chuan Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 68 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at TM Cooling Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 70 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam decorative products at Florafoam Marketing Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 71 | A | D | CFC | 23 | 23 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1997-06-01 | 2000-12-01 | 152000 | -1 | 151999 | 151999 | 100% | 0 | 0 | 0 | 19760 | 0 | 19759.87 | 0.13 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology for the manufacture of flexible polyurethane foam at Nite Beauty Industries | Individual | ASP | MAL | FOA | 19 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-06-01 | 1999-12-01 | 36875 | 0 | 36875 | 36875 | 100% | 0 | 0 | 0 | 4794 | 0 | 4793.75 | 0.25 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC -free technology for the manufacture of flexible polyurethane foam at Far East Foam Industries | Individual | ASP | MAL | FOA | 19 | INV | 89 | A | I | CFC | 41.2 | 41.2 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-09-01 | 2001-12-01 | 209000 | -2275 | 206725 | 206725 | 100% | 0 | 0 | 0 | 27170 | -296 | 26874.25 | -0.25 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Amstrad | Individual | ASP | MAL | FOA | 22 | INV | 94 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 108800 | -86 | 108714 | 108714 | 100% | 0 | 0 | 0 | 14144 | -11 | 14132.82 | 0.18 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Anchor Profit Sdn Bhd | Individual | ASP | MAL | FOA | 22 | INV | 95 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Rollbond | Individual | ASP | MAL | FOA | 22 | INV | 96 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 155500 | 0 | 155500 | 155500 | 100% | 0 | 0 | 0 | 20215 | 0 | 20215 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at RCA Group | Individual | ASP | MAL | FOA | 22 | INV | 98 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2000-12-01 | 284500 | -12922 | 271578 | 271578 | 100% | 0 | 0 | 0 | 36985 | -1680 | 35305.14 | -0.14 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free techology in the manufacture of polyurethane foam at Hi Tech Insulation | Individual | ASP | MAL | FOA | 23 | INV | 104 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2002-03-01 | 96815 | -3942 | 92873 | 92873 | 100% | 0 | 0 | 0 | 12586 | -512 | 12073.49 | 0.51 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Heng Huat Furniture | Individual | ASP | MAL | FOA | 23 | INV | 105 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 269500 | 0 | 269500 | 269500 | 100% | 0 | 0 | 0 | 35035 | 0 | 35035 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Frank Chee | Individual | ASP | MAL | FOA | 23 | INV | 106 | A | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 174350 | 0 | 174350 | 174350 | 100% | 0 | 0 | 0 | 22666 | 0 | 22665.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at OAL Enterprise | Individual | ASP | MAL | FOA | 23 | INV | 107 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 58300 | -19611 | 38689 | 38689 | 100% | 0 | 0 | 0 | 7579 | -2549 | 5029.57 | 0.43 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CT Foam | Individual | ASP | MAL | FOA | 23 | INV | 99 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 236000 | 0 | 236000 | 236000 | 100% | 0 | 0 | 0 | 30680 | 0 | 30680 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 24 | PRP | 108 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of polyurethane foam at Tenaga | Individual | ASP | MAL | FOA | 25 | INV | 111 | A | I | CFC | 23 | 23 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 308800 | 0 | 308800 | 308800 | 100% | 0 | 0 | 0 | 40144 | 0 | 40144 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Minply | Individual | ASP | MAL | FOA | 26 | INV | 115 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 158050 | -3297 | 154753 | 154753 | 100% | 0 | 0 | 0 | 20547 | -429 | 20117.89 | 0.11 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Grorich | Individual | ASP | MAL | FOA | 26 | INV | 116 | A | I | CFC | 32.9 | 32.9 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 174150 | 0 | 174150 | 174150 | 100% | 0 | 0 | 0 | 22640 | 0 | 22639.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of three projects in rigid foam subsector | Individual | ASP | MAL | FOA | 27 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of cold room panels and insulation slabs by conversion to HCFC-141b at PKL Insulation | Individual | ASP | MAL | FOA | 28 | INV | 121 | A | I | CFC | 8.1 | 8.1 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-12-01 | 2003-07-01 | 57019 | -1434 | 55585 | 55585 | 100% | 0 | 0 | 0 | 7412 | -186 | 7226.05 | -0.05 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and blocks) at Polyedge Trading | Individual | ASP | MAL | FOA | 28 | INV | 122 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2002-02-01 |  | 2000-12-01 | 2001-12-01 | 80650 | 0 | 80650 | 80650 | 100% | 0 | 0 | 0 | 10485 | 0 | 10484.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Retroactive project for phasing-out ODS consumption in the manufacture of cold room panels by conversion to HCFC-141b at FMCP Sdn. Bhd. | Individual | ASP | MAL | FOA | 28 | INV | 123 | A | R | CFC | 12.2 | 12.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-07-01 | 2001-12-01 | 45557 | 0 | 45557 | 45557 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922.41 | -0.41 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Masterfoam Products | Individual | ASP | MAL | FOA | 29 | INV | 130 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 208900 | 0 | 208900 | 208900 | 100% | 0 | 0 | 0 | 27157 | 0 | 27157 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible polyurethane foam at Kemas Mekar Sdn Bhd | Individual | ASP | MAL | FOA | 29 | INV | 131 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 385900 | -11270 | 374630 | 374630 | 100% | 0 | 0 | 0 | 50167 | -1465 | 48701.9 | 0.1 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 30 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -9678 | 20322 | 20322 | 100% | 0 | 0 | 0 | 3900 | -1258 | 2642.1052 | -0.10516 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam and to LCD technology in the manufacture of flexible molded foam at Sy Heng Huat | Individual | ASP | MAL | FOA | 31 | INV | 136 | A | I | CFC | 46.2 | 46.2 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-01-01 | 2003-11-01 | 272235 | 0 | 272235 | 272235 | 100% | 0 | 0 | 0 | 35391 | 0 | 35390.55 | 0.45 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD and water-based technology in the manufacture of flexible molded foam at Unique Field | Individual | ASP | MAL | FOA | 31 | INV | 137 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 109990 | 0 | 109990 | 109990 | 100% | 0 | 0 | 0 | 14299 | 0 | 14298.7 | 0.3 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible molded foam at Pointray | Individual | ASP | MAL | FOA | 31 | INV | 138 | A | I | CFC | 24.3 | 24.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 130896 | -27 | 130869 | 130869 | 100% | 0 | 0 | 0 | 17016 | -4 | 17012.97 | -0.97 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | MAL | FOA | 57 | PRP | 164 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-08-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 100000 | -66756 | 33244 | 33244 | 100% | 0 | 0 | 0 | 7500 | -5007 | 2493.3 | -0.3 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | MAL | FOA | 72 | PRP | 175 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-09-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 10500 | 0 | 0 | 10500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, discussions were held on project preparation steps for Stage-II. The TORs for consultants have been prepared and survey is underway. Technical consultant recruitment process is expected to be concluded by May 2015. HPMP Stage-II is expected to be submitted to 75 Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 0 signed. Contract/PO/MOA agreements signed:1 planned and 0 signed. First disbursement date (actual/planned):Planned in June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation are ongoing. The strategy is expected to be finalised in Q4 of 2015. |  |  | Non-Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project (timber) | Individual | ASP | MAL | FUM | 24 | PRP | 109 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-11-01 | 2004-12-01 | 30000 | -983 | 29017 | 29017 | 100% | 0 | 0 | 0 | 3900 | -128 | 3772.21 | -0.21 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on Malaysian timbers | Individual | ASP | MAL | FUM | 29 | DEM | 129 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2006-07-01 | 2010-10-01 | 230000 | -8078 | 221922 | 221922 | 100% | 0 | 0 | 0 | 29900 | -1050 | 28849.86 | 0.14 | 0 | Financially completed in 2010. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the soil fumigant sector | Individual | ASP | MAL | FUM | 36 | PRP | 146 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-11-01 | 10000 | -947 | 9053 | 9053 | 100% | 0 | 0 | 0 | 1300 | -123 | 1176.89 | 0.11 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of fumigant methyl bromide | Individual | ASP | MAL | FUM | 42 | PRP | 150 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-01-01 | 2006-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Technical assistance programme to install alternatives and phase-out all remaining non-QPS uses of methyl bromide | Individual | ASP | MAL | FUM | 43 | TAS | 151 | N | I | MeBr | 8.7 | 8.7 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2007-12-01 |  | 2011-07-01 | 2012-05-01 | 200000 | -10971 | 189029 | 189029 | 100% | 0 | 0 | 0 | 18000 | -987 | 17012.61 | 0.39 | 0 | Financially completed in 2012. | The project is expected to be financially closed by June 12. | 2004 |  | Non-Investment
FIN | UNDP | Converson of production of portable fire extinguishers at Eversafe | Individual | ASP | MAL | HAL | 18 | INV | 72 | A | D | Halon | 574 | 574 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 2002-03-01 | 179586 | -4214 | 175372 | 175372 | 100% | 0 | 0 | 0 | 23346 | -548 | 22798.36 | -0.36 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | MAL | PHA | 55 | PRP | 161 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-01 | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031 | 0 | 13031 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | MAL | PHA | 65 | INV | 169 | N | I | HCFC | 49.3 | 49.3 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2016-10-01 |  | 2013-12-01 | 2013-12-01 | 4327247 | 0 | 4327247 | 4327247 | 100% | 0 | 0 | 0 | 324544 | 0 | 324544 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the servicing sector) | Multi-year | ASP | MAL | PHA | 65 | TAS | 168 | N | I | HCFC | 4.4 | 4.4 | 0 | 0 | 2011-11-01 | 2013-02-01 | 2016-10-01 |  | 2013-12-01 | 2013-12-01 | 359845 | 0 | 359845 | 359845 | 100% | 0 | 0 | 0 | 26988 | 0 | 26988 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (management and coordination) | Multi-year | ASP | MAL | PHA | 65 | TAS | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2016-10-01 | 2016-10-01 |  |  | 312908 | 0 | 312908 | 203970 | 65.19% | 108938 | 108938.18 | 43575.272 | 23468 | 0 | 15297.6713 | 8170.3287 | 8170.3287 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, project management activities progressed satisfactorily. PMU assisted in coordination of MLFS evaluation mission in August 2014. Further, project implementation was regularly monitored for achievement of milestones. Prodoc signed (actual/planned, yes/no and date):Planned in January 2012 and actual in May 2012. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Project management and coordination activities are progressing satisfactorily. Verification of 2013 and 2014 is expected to be completed by July 2015. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | MAL | PHA | 71 | INV | 172 | N | I | HCFC | 35.8 | 26.8 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2015-12-01 | 2015-07-01 |  |  | 3140476 | 0 | 3140476 | 2165320 | 68.95% | 975156 | 0 | 390062.572 | 235536 | 0 | 162399.1746 | 73136.8254 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, enterprises actively pursued their conversion project. Most of the enterprises have procured equipment and were almost at the final stages of commercial production of HCFC free products. Systems houses also tested formulations which are HCFC free. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in March 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 TOR planned and prepared. Contract/PO/MOA agreements signed:Ongoing and same as previous contracts for first stage. First disbursement date (actual/planned):The first disbursement took place in April 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (technical assistance for the servicing sector) | Multi-Year | ASP | MAL | PHA | 71 | TAS | 173 | N | I | HCFC | 3.2 | 2 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2015-07-01 |  |  | 261156 | 0 | 261156 | 0 | 0% | 261156 | 0 | 104462.4 | 19587 | 0 | 0 | 19587 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, enterprises actively pursued their conversion project. Most of the enterprises have procured equipment and were almost at the final stages of commercial production of HCFC free products. Systems houses also tested formulations which are HCFC free. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in February 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 TOR planned and prepared. Contract/PO/MOA agreements signed:Ongoing and same as previous contracts for first stage. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (management and coordination) | Multi-Year | ASP | MAL | PHA | 71 | TAS | 174 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2015-07-01 |  |  | 227091 | 0 | 227091 | 0 | 0% | 227091 | 0 | 90836.4 | 17031 | 0 | 0 | 17031 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, enterprises actively pursued their conversion project. Most of the enterprises have procured equipment and were almost at the final stages of commercial production of HCFC free products. Systems houses also tested formulations which are HCFC free. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in March 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 TOR planned and prepared. Contract/PO/MOA agreements signed:Ongoing and same as previous contracts for first stage. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | MAL | PHA | 72 | PRP | 176 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-09-01 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 65000 | 4550 | 0 | 0 | 4550 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, discussions were held on project preparation steps for Stage-II. The TORs for consultants have been prepared and survey is underway. Technical consultant recruitment process is expected to be concluded by May 2015. HPMP Stage-II is expected to be submitted to 75 Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 0 signed. Contract/PO/MOA agreements signed:1 planned and 0 signed. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation are ongoing. The strategy is expected to be finalised in Q4 of 2015. |  |  | Investment
FIN | UNDP | Training in MAC sector | RMP-Component | ASP | MAL | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-10-01 | 1993-12-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of home refrigerators at Sharp Roxy Appliance Corp. | Individual | ASP | MAL | REF | 12 | INV | 29 | A | D | CFC | 65 | 65 | 0 | 0 | 1994-03-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 962000 | -103353 | 858647 | 858647 | 100% | 0 | 0 | 0 | 125060 | -13436 | 111624.11 | -0.11 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at United Refrigerator Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 37 | A | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-12-01 | 2003-07-01 | 351200 | -11852 | 339348 | 339348 | 100% | 0 | 0 | 0 | 45656 | -1541 | 44115.24 | -0.24 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of refrigeration products at Oyl Appliances | Individual | ASP | MAL | REF | 13 | INV | 42 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-12-01 |  | 1997-12-01 | 2002-03-01 | 625100 | -38549 | 586551 | 586551 | 100% | 0 | 0 | 0 | 81263 | -5011 | 76251.63 | 0.37 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at Lian Pang Refrigerator and Electrical Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 45 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-07-01 |  | 1998-10-01 | 2003-09-01 | 201100 | -1 | 201099 | 201099 | 100% | 0 | 0 | 0 | 26143 | 0 | 26142.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Umbrella project for elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration at 4 small enterprises: Lim Yew, Exquisite, FMC, Noblelane | Individual | ASP | MAL | REF | 18 | INV | 73 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2001-12-01 | 2003-04-01 | 680000 | -49438 | 630562 | 630562 | 100% | 0 | 0 | 0 | 88400 | -6427 | 81973.18 | -0.18 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1997-10-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Sanyo Industries (Malaysia) Berhad | Individual | ASP | MAL | REF | 18 | INV | 74 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 183260 | -1 | 183259 | 183259 | 100% | 0 | 0 | 0 | 23824 | 0 | 23823.67 | 0.33 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufature of polyurethane foam at Kwang Tai Refrigeration | Individual | ASP | MAL | REF | 23 | INV | 103 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-04-01 | 316000 | -9988 | 306012 | 306012 | 100% | 0 | 0 | 0 | 41080 | -1298 | 39781.56 | 0.44 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation of two projects in commercial refrigeration subsector | Individual | ASP | MAL | REF | 27 | PRP | 117 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and R502 consumption at Thermo Cooling Engineering, Sdn. Bhd. | Individual | ASP | MAL | REF | 28 | INV | 126 | A | I | CFC | 5.9 | 5.9 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 46502 | -1900 | 44602 | 44602 | 100% | 0 | 0 | 0 | 6045 | -247 | 5798.26 | -0.26 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 and R-502 in the manufacture of commercial refrigerators by conversion HCFC-141b, HCFC-22 and HFC-404a at Gai Hin Refrigeration Sdn. Bhd. | Individual | ASP | MAL | REF | 29 | INV | 128 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 354147 | -16712 | 337435 | 337435 | 100% | 0 | 0 | 0 | 46039 | -2173 | 43866.55 | -0.55 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | MAL | REF | 30 | PRP | 134 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 20000 | -4121 | 15879 | 15879 | 100% | 0 | 0 | 0 | 2600 | -536 | 2063.9386 | 0.061377 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at eleven small and sedium-sized enterprises | Individual | ASP | MAL | REF | 32 | INV | 140 | A | I | CFC | 64.8 | 64.8 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 960658 | -29788 | 930870 | 930870 | 100% | 0 | 0 | 0 | 115672 | -3276 | 112396.4 | -0.4 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at three enterprises (SKE Fookmei, Master Shanghai Turnparts and Maltar Industries) | Individual | ASP | MAL | REF | 32 | INV | 141 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-11-01 | 2005-09-01 | 505184 | -12891 | 492293 | 492293 | 100% | 0 | 0 | 0 | 65570 | -1418 | 64152.24 | -0.24 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | MAL | REF | 57 | PRP | 162 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-06-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | MAL | REF | 57 | PRP | 163 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-08-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | ASP | MAL | REF | 72 | PRP | 177 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-09-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3500 | 0 | 0 | 3500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, discussions were held on project preparation steps for Stage-II. The TORs for consultants have been prepared and survey is underway. Technical consultant recruitment process is expected to be concluded by May 2015. HPMP Stage-II is expected to be submitted to 75 Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 0 signed. Contract/PO/MOA agreements signed:1 planned and 0 signed. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation are ongoing. The strategy is expected to be finalised in Q4 of 2015. |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | MAL | REF | 72 | PRP | 178 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-09-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 3500 | 0 | 0 | 3500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, discussions were held on project preparation steps for Stage-II. The TORs for consultants have been prepared and survey is underway. Technical consultant recruitment process is expected to be concluded by May 2015. HPMP Stage-II is expected to be submitted to 75 Excom. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):3 planned - 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 0 signed. Contract/PO/MOA agreements signed:1 planned and 0 signed. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-II preparation are ongoing. The strategy is expected to be finalised in Q4 of 2015. |  |  | Non-Investment
FIN | UNDP | Institutional strengthening in relation to projects on reduction of ozone depleting substances | Individual | ASP | MAL | SEV | 09 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-12-01 | 2003-04-01 | 322520 | -15703 | 306817 | 306817 | 100% | 0 | 0 | 0 | 41928 | -2041 | 39886.21 | 0.79 | 0 | Completed in 1996. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 10 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-12-01 |  | 1994-03-01 | 1997-12-01 | 50000 | 4438 | 54438 | 54438 | 100% | 0 | 0 | 0 | 6500 | 577 | 7076.94 | 0.06 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | National ODS conference | Individual | ASP | MAL | SEV | 10 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-07-01 |  | 1993-07-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 12 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 15 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 18 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 18000 | -4 | 17996 | 17996 | 100% | 0 | 0 | 0 | 2340 | -1 | 2339 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 20 | INS | 91 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-10-01 |  | 1998-10-01 | 2003-04-01 | 215000 | -5523 | 209477 | 209477 | 100% | 0 | 0 | 0 | 27950 | -718 | 27232.01 | -0.01 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | MAL | SEV | 21 | PRP | 93 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2004-12-01 | 100000 | -34365 | 65635 | 65635 | 100% | 0 | 0 | 0 | 13000 | -4467 | 8533 | 0 | 0 | Completed in 1998. Financially Completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | MAL | SEV | 26 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-05-01 | 215000 | -36884 | 178116 | 178116 | 100% | 0 | 0 | 0 | 27950 | -4795 | 23155 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase IV) | Individual | ASP | MAL | SEV | 32 | INS | 142 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2005-03-01 | 2009-07-01 | 215000 | -10994 | 204006 | 204006 | 100% | 0 | 0 | 0 | 27950 | -1429 | 26520.78 | 0.22 | 0 | Completed in 2005.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 38 | INS | 148 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 279500 | -17133 | 262367 | 262367 | 100% | 0 | 0 | 0 | 36335 | -2227 | 34107.71 | 0.29 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | MAL | SEV | 44 | INS | 153 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2008-07-01 | 2011-12-01 | 279500 | 0 | 279500 | 279500 | 100% | 0 | 0 | 0 | 20963 | 0 | 20963 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | MAL | SEV | 45 | TAS | 155 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 91743 | -13695 | 78048 | 78048 | 100% | 0 | 0 | 0 | 8257 | -1233 | 7024.4306 | -0.4306 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | MAL | SEV | 53 | INS | 159 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 279500 | -2001 | 277499 | 277499 | 100% | 0 | 0 | 0 | 20963 | -150 | 20812.9214 | 0.0786 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | MAL | SEV | 58 | INS | 165 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-11-01 |  | 2011-12-01 | 2014-03-01 | 139750 | 139518 | 279268 | 279268 | 100% | 0 | 0 | 0 | 10481 | 10464 | 20944.6 | 0.4 | 0 | Financially completed in 2014. | The project is being financially closed in 2012. | 2009 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | ASP | MAL | SEV | 64 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 | 2016-01-01 |  |  | 279500 | 0 | 279500 | 217304 | 77.75% | 62196 | 0 | 24878.32 | 20963 | 0 | 16298.2037 | 4664.7963 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, the NOU monitored implementation of national regulations including licensing system. NOU staff also participated in regional and international meetings on technical and policy issues. Ozone Day celebrations for the year 2013 were also conducted satisfactorily. A7 data and CP progress report for the year 2013 were also reported. Prodoc signed (actual/planned, yes/no and date):Planned December 2011 and actual February 2012. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in December 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The IS Phase-IX has been operationallly completed in March 2014. The IS activities continue under the IS Phase-X. | 2011 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | ASP | MAL | SEV | 70 | INS | 171 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-07-01 | 2014-11-01 | 2015-12-01 | 2017-01-01 |  |  | 279500 | 0 | 279500 | 19929 | 7.13% | 259571 | 0 | 103828.496 | 19565 | 0 | 1395.0132 | 18169.9868 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, the NOU monitored implementation of national regulations including licensing system. NOU staff also participated in regional and international meetings on technical and policy issues. Ozone Day celebrations for the year 2013 were also conducted satisfactorily. A7 data and CP progress report for the year 2013 were also reported. NOU activities are similar to previous phase as they are a part of ongoing project. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2013. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in November 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The implementation is going as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2013 |  | Non-Investment
FIN | UNDP | Conversion of metal cleaning processes from trichloroethane solvents to non-ODS organic solvents at Ngai Cheong Metal Industries | Individual | ASP | MAL | SOL | 11 | INV | 18 | A | I | TCA | 2 | 2 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-11-01 |  | 1995-04-01 | 1998-12-01 | 63480 | 0 | 63480 | 63480 | 100% | 0 | 0 | 0 | 8252 | 0 | 8252.4 | -0.4 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Main Plant | Individual | ASP | MAL | SOL | 11 | INV | 19 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-10-01 |  | 1994-05-01 | 1998-12-01 | 113570 | -2661 | 110909 | 110909 | 100% | 0 | 0 | 0 | 14764 | -346 | 14418.1 | -0.1 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Port Klang Plant | Individual | ASP | MAL | SOL | 11 | INV | 20 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-10-01 |  | 1995-04-01 | 1998-12-01 | 173280 | 25992 | 199272 | 199272 | 100% | 0 | 0 | 0 | 22526 | 3379 | 25905.36 | -0.36 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the integral circuit lead frame cleaning processes at San Matech Sdn. Bhd. | Individual | ASP | MAL | SOL | 12 | INV | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-07-01 |  |  | 1995-07-01 | 141000 | -141000 | 0 | 0 |  | 0 | 0 | 0 | 18330 | -18330 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of 111 TCA in the automobile bumper cleaning processes at Perusahaan Otomobil National Bhd. (Proton) | Individual | ASP | MAL | SOL | 12 | INV | 35 | A | I | TCA | 20 | 20 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1995-12-01 |  | 1995-04-01 | 1998-12-01 | 700439 | -59344 | 641095 | 641095 | 100% | 0 | 0 | 0 | 91057 | -7715 | 83342.07 | -0.07 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Aerosol conversion at Compagnie Manufacturiere de Produits Cosmetiques Ltee. | Individual | AFR | MAR | ARS | 12 | INV | 03 | A | D | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-06-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 62150 | 0 | 62150 | 62150 | 100% | 0 | 0 | 0 | 8080 | 0 | 8079.5 | 0.5 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Preparation of projects in the refrigeration and foam sectors | Individual | AFR | MAR | REF | 12 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Blyfridge Ltd. | Individual | AFR | MAR | REF | 15 | INV | 05 | A | I | CFC | 2 | 2 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 197208 | -20442 | 176766 | 176766 | 100% | 0 | 0 | 0 | 25637 | -2657 | 22979.58 | 0.42 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at A.H. Bahemia | Individual | AFR | MAR | REF | 15 | INV | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 213500 | -25495 | 188005 | 188005 | 100% | 0 | 0 | 0 | 27755 | -3314 | 24440.65 | 0.35 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
TRF | UNDP | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | RMP-Component | AFR | MAR | REF | 17 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1996-07-01 |  |  | 1999-07-01 | 176350 | -162281 | 14069 | 14069 | 100% | 0 | 0 | 0 | 22926 | -21096 | 1829.5 | 0.5 | 0 | Transferred in 1999. Financially completed in 1999. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MAU | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MAU | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-03-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | INV | 22 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-12-01 | 2013-03-01 | 55000 | -4966 | 50034 | 50034 | 100% | 0 | 0 | 0 | 4950 | -447 | 4503.06 | -0.06 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | MAU | REF | 39 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | MAU | REF | 41 | TAS | 11 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2013-09-01 | 100995 | -696 | 100299 | 100299 | 100% | 0 | 0 | 0 | 9090 | -63 | 9026.91 | 0.09 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme for MAC, commercial and industrial end-users | RMP-Component | AFR | MAU | REF | 41 | TAS | 12 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2011-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | MDV | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -8440 | 6560 | 6560 | 100% | 0 | 0 | 0 | 1125 | -633 | 492 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 53 | INV | 15 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2007-11-01 | 2011-04-01 | 2009-11-01 | 2015-12-01 |  |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, these activities were under implementation. Equipment procurement has been completed. The equipment would be distributed to beneficiaries in early 2015. Training will also be provided to the servicinig enterprises. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in December 2010. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 prepared. Contract/PO/MOA agreements signed:1 signed. First disbursement date (actual/planned):The first disbursement took place in April 2011. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Start up was delayed due to administrative approval process. But activities progressing satisfactorily.. | Reclamation centre operationalisation is underway. Technical support has been requested from India where reclamation centers are in operations - study tour is expected to be undertaken for this in Q3-2015. | 2007 |  | Investment
ONG | UNDP | HCFC phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 60 | INV | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2013-06-01 | 2019-12-01 | 2019-12-01 |  |  | 400000 | 0 | 400000 | 236570 | 59.14% | 163430 | 0 | 65371.976 | 30000 | 0 | 17742.7545 | 12257.2455 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, the focus was on implementation of R&R program and retrofit incentive scheme focusing on fisheries sector. The latter program was implemented with available and cost-effectively feasible technologies and these are primarily HFC based. The fisheries sector is actively engaged in identification of low-GWP, safe and cost effective options and technical information was shared on available retrofit technologies. Further, NOU discussed with air-conditioning dealers and distributors for selling low GWP technologies (e.g., R-290 based, R-32 based) in their market in 2015 and beyond Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in September 2011. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 completed. Contract/PO/MOA agreements signed:1 contract planned and 1 signed. First disbursement date (actual/planned):The first disbursement took place in June 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Technology challenge on retrofit options for fisheries. Technical information is being shared with industry over the last 3 years and the industry is actively engaged in searching for options.. | HPMP Stage-I targets are being satisfactorily met. Country still facing challenges in retrofit options (mainly low GWP refrigerants) for existing fishing vessels and working closely with UNDP and tech experts on this. Project for demonstration of low GWP has been approved in the 74th Excom and this is expected to provide solutions for Maldives. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | MDV | PHA | 69 | INV | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2015-04-01 | 2016-04-01 |  |  | 20000 | 0 | 20000 | 4100 | 20.5% | 15900 | 0 | 6360 | 1500 | 0 | 307.5 | 1192.5 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, the focus was on implementation of R&R program and retrofit incentive scheme focusing on fisheries sector. The latter program was implemented with available and cost-effectively feasible technologies and these are primarily HFC based. The fisheries sector is actively engaged in identification of low-GWP, safe and cost effective options and technical information was shared on available retrofit technologies. Further, NOU discussed with air-conditioning dealers and distributors for selling low GWP technologies (e.g., R-290 based, R-32 based) in their market in 2015 and beyond Prodoc signed (actual/planned, yes/no and date):The prodoc was signed prior to 2014. Missions undertaken (actual/planned):1 planned and 1 undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 completed. Contract/PO/MOA agreements signed:1 contract planned and 1 signed. First disbursement date (actual/planned):The first disbursement took place in August 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | HPMP Stage-I targets are being satisfactorily met. Country still facing challenges in retrofit options (mainly low GWP refrigerants) for existing fishing vessels and working closely with UNDP and tech experts on this. Project for demonstration of low GWP has been approved in the 74th Excom and this is expcted to provide solutions for Maldives. | 2013 |  | Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | MDV | REF | 38 | TAS | 05 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-05-01 | 2016-01-01 |  |  | 115000 | 0 | 115000 | 26644 | 23.17% | 88356 | 0 | 35342.4 | 14950 | 0 | 3463.72 | 11486.28 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In the year 2014, project activities progressed satisfactorily. We hope to conclude the project in 2015 and disburse committed money for this program. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed prior to 2014. Missions undertaken (actual/planned):None. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 prepared. Contract/PO/MOA agreements signed:Contract signed in 2012. First disbursement date (actual/planned):The first disbursement took place in July 2004. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Technology choice is a challenge. | Implementation ongoing and expected to be completed by end of this year. | 2002 |  | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Paneles | Individual | LAC | MEX | FOA | 18 | INV | 41 | A | I | CFC | 81 | 81 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1997-08-01 | 2000-12-01 | 100000 | -5098 | 94902 | 94902 | 100% | 0 | 0 | 0 | 13000 | -663 | 12337.26 | -0.26 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels at Galvamet, S.A. de C.V. | Individual | LAC | MEX | FOA | 18 | INV | 42 | A | D | CFC | 88.7 | 88.7 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1996-04-01 | 1998-12-01 | 195500 | -6004 | 189496 | 189496 | 100% | 0 | 0 | 0 | 25415 | -781 | 24634.26 | -0.26 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels and doors at Multypanel | Individual | LAC | MEX | FOA | 19 | INV | 46 | A | I | CFC | 306 | 306 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-08-01 | 2001-12-01 | 428000 | -85789 | 342211 | 342211 | 100% | 0 | 0 | 0 | 55640 | -11153 | 44487.13 | -0.13 | 0 | Completed in 1997. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) - Group project (10 enterprises) | Individual | LAC | MEX | FOA | 19 | INV | 47 | A | I | CFC | 100 | 100 | 0 | 0 | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1998-11-01 | 2001-08-01 | 507500 | -43764 | 463736 | 463736 | 100% | 0 | 0 | 0 | 65975 | -5689 | 60285.68 | 0.32 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Carmovil | Individual | LAC | MEX | FOA | 20 | INV | 48 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 80500 | -1092 | 79408 | 79408 | 100% | 0 | 0 | 0 | 10465 | -142 | 10323.04 | -0.04 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Umbrella project for conversion to CFC-free technology in the manufacture of polyurethane shoe soles (seven enterprises) | Individual | LAC | MEX | FOA | 20 | INV | 49 | A | I | CFC | 95 | 95 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 2001-08-01 | 2003-04-01 | 1201590 | -3434 | 1198156 | 1198156 | 100% | 0 | 0 | 0 | 156207 | -446 | 155760.28 | 0.72 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Acsa | Individual | LAC | MEX | FOA | 22 | INV | 54 | A | I | CFC | 94.4 | 94.4 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 597000 | -1890 | 595110 | 595110 | 100% | 0 | 0 | 0 | 77610 | -245 | 77364.74 | 0.26 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Industrias Pol-Rym S.A. de C.V., (IPR) | Individual | LAC | MEX | FOA | 22 | INV | 55 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1998-11-01 |  | 1998-11-01 | 2001-12-01 | 421500 | -4909 | 416591 | 416591 | 100% | 0 | 0 | 0 | 54795 | -638 | 54156.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Tecnopolimeros | Individual | LAC | MEX | FOA | 22 | INV | 56 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2002-11-01 | 359000 | -1642 | 357358 | 357358 | 100% | 0 | 0 | 0 | 46670 | -213 | 46456.59 | 0.41 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Termopuertos | Individual | LAC | MEX | FOA | 22 | INV | 57 | A | D | CFC | 10 | 10 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-07-01 | 2000-12-01 | 78300 | -2557 | 75743 | 75743 | 100% | 0 | 0 | 0 | 10179 | -332 | 9846.59 | 0.41 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technolog in the manufacture of rigid foam at Valsa Panel | Individual | LAC | MEX | FOA | 23 | INV | 66 | A | D | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1998-07-01 | 2000-12-01 | 92000 | -312 | 91688 | 91688 | 100% | 0 | 0 | 0 | 11960 | -41 | 11919.44 | -0.44 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at group project Pumex | Individual | LAC | MEX | FOA | 23 | INV | 69 | A | I | CFC | 167.7 | 167.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 1133881 | -20532 | 1113349 | 1113349 | 100% | 0 | 0 | 0 | 147405 | -2669 | 144735.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin foam at Air Design | Individual | LAC | MEX | FOA | 23 | INV | 71 | A | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 80500 | -1178 | 79322 | 79322 | 100% | 0 | 0 | 0 | 10465 | -153 | 10311.5984 | 0.4016 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid foam (spray) and integral skin foam at Con Espuma | Individual | LAC | MEX | FOA | 23 | INV | 72 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 96100 | -2230 | 93870 | 93870 | 100% | 0 | 0 | 0 | 12493 | -290 | 12203.1 | -0.1 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Group Project (Orca) | Individual | LAC | MEX | FOA | 23 | INV | 73 | A | I | CFC | 190 | 190 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-11-01 | 1471500 | -154071 | 1317429 | 1317429 | 100% | 0 | 0 | 0 | 191295 | -20029 | 171265.77 | 0.23 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 5 projects in the foam sector | Individual | LAC | MEX | FOA | 24 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid foam for refrigeration systems at Refrigeración Rodríguez | Individual | LAC | MEX | FOA | 25 | INV | 82 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 132650 | -31006 | 101644 | 101644 | 100% | 0 | 0 | 0 | 17245 | -4031 | 13213.5 | 0.5 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to water-based technology in the manufacture of integral skin foam at Moldecor, S.A. de C.V. | Individual | LAC | MEX | FOA | 25 | INV | 84 | A | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2000-04-01 | 2001-12-01 | 86500 | -845 | 85655 | 85655 | 100% | 0 | 0 | 0 | 11245 | -110 | 11135.0253 | -0.0253 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Group Project Valcom (Uriel, Limas, Tecknipol, Anzaldua, and Negrete) | Individual | LAC | MEX | FOA | 26 | INV | 87 | A | I | CFC | 44.3 | 44.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-08-01 | 2002-11-01 | 314961 | -3630 | 311331 | 311331 | 100% | 0 | 0 | 0 | 40945 | -472 | 40472.93 | 0.07 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Preparation of three projects in the foam sector | Individual | LAC | MEX | FOA | 27 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-07-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | MEX | FOA | 30 | PRP | 94 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b or water-blown technology in rigid polyurethane foam (spray) and to water based formulations in integral skin foam at Comsisa | Individual | LAC | MEX | FOA | 31 | INV | 98 | A | I | CFC | 68.7 | 68.7 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2003-08-01 |  | 2003-10-01 | 2004-01-01 | 424050 | 0 | 424050 | 424050 | 100% | 0 | 0 | 0 | 55127 | 0 | 55126.5 | 0.5 | 0 | Completed in 2003. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Foam phaseout sector strategy | Individual | LAC | MEX | FOA | 31 | TAS | 96 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-01-01 |  | 2001-12-01 | 2004-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Foam sector ODS phaseout plan (first trnache) | Individual | LAC | MEX | FOA | 35 | INV | 103 | N | I | CFC | 145 | 145 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2003-07-01 |  | 2004-11-01 | 2009-08-01 | 833150 | 0 | 833150 | 833150 | 100% | 0 | 0 | 0 | 101647 | 0 | 101646.5 | 0.5 | 0 | Completed in 2004.Financially completed in 2009. |  | 2000 |  | Investment
FIN | UNDP | Foam sector ODS phase-out plan (second tranche) | Individual | LAC | MEX | FOA | 42 | INV | 117 | N | D | CFC | 192 | 192 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2007-12-01 | 2009-08-01 | 1109120 | -78998 | 1030122 | 1030122 | 100% | 0 | 0 | 0 | 83184 | -5925 | 77259.15 | -0.15 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Pilot project for validation of methyl formate in microcellular polyurethane applications (phase I) | Individual | LAC | MEX | FOA | 56 | DEM | 141 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-06-01 |  | 2010-11-01 | 2012-12-01 | 291500 | -1418 | 290082 | 290082 | 100% | 0 | 0 | 0 | 21862 | -106 | 21755.6524 | 0.3476 | 0 | Financially completed in 2012. |  | 2008 | 2011-01-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector plan) | Individual | LAC | MEX | FOA | 58 | PRP | 144 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-04-01 | 2013-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Mabe Mexico | Multi-year | LAC | MEX | FOA | 59 | INV | 148 | N | I | HCFC | 55.8 | 55.8 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2013-08-01 |  | 2014-12-01 |  | 2428987 | 0 | 2428987 | 2374401 | 97.75% | 54586 | 0 | 43668.752 | 182174 | 0 | 178080.0551 | 4093.9449 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, installation of equipment in remaining plant has been completed and the company is now fully operational with Cyclopentane. A safety audit took place in June 2014. The only pending activity is the final safety audit of the full plant and the hand-over protocol. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in Nov 2009. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in March 2010. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, equipment has been installed and the main line is now operating safely with cyclopentane. Technical tests will take place in April 2014. | 2009 |  | Investment
FIN | UNDP | Project preparation for 2 methyl bromide (flowers and crop storage) alternative demonstration projects | Individual | LAC | MEX | FUM | 24 | PRP | 80 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for structural fumigation in Mexico | Individual | LAC | MEX | FUM | 26 | DEM | 86 | A | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2010-10-01 | 2013-04-01 | 498300 | -87984 | 410316 | 410316 | 100% | 0 | 0 | 0 | 64779 | -11438 | 53341.08 | -0.08 | 0 | Financially completed in 2013. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the storage fumigant sector | Individual | LAC | MEX | FUM | 36 | PRP | 105 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparatory study on halons, inventory, and proposals for revisions of existing standards | Individual | LAC | MEX | HAL | 06 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1994-04-01 |  | 1995-09-01 | 1998-12-01 | 25000 | 2223 | 27223 | 27223 | 100% | 0 | 0 | 0 | 3250 | 289 | 3538.99 | 0.01 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for a halon sector phase out programme | Individual | LAC | MEX | HAL | 24 | PRP | 76 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-12-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the recycling halon sector | Individual | LAC | MEX | HAL | 33 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | National halon management and banking programme | Individual | LAC | MEX | HAL | 35 | TAS | 104 | A | I | Halon | 230 | 230 | 0 | 0 | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2007-12-01 | 2011-07-01 | 500000 | -55842 | 444158 | 444158 | 100% | 0 | 0 | 0 | 65000 | -7259 | 57740.54 | 0.46 | 0 | Completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 140 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2009-11-01 | 2012-06-01 | 69500 | -6719 | 62781 | 62781 | 100% | 0 | 0 | 0 | 5213 | -504 | 4708.5749 | 0.42505 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector plan for systems houses and local customers) (stage I, first tranche) | Multi-Year | LAC | MEX | PHA | 64 | INV | 159 | N | I | HCFC | 66.8 | 66.8 | 0 | 0 | 2011-07-01 | 2011-08-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 2502526 | 0 | 2502526 | 2502526 | 100% | 0 | 0 | 0 | 187689 | 0 | 187689 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan for systems houses and local customers) | Multi-Year | LAC | MEX | PHA | 68 | INV | 165 | N | I | HCFC | 101.5 | 65.2 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2014-12-01 | 2016-12-01 |  |  | 3800000 | 0 | 3800000 | 2065279 | 54.35% | 1734721 | 15704 | 693888.324 | 285000 | 0 | 154895.9392 | 130104.0608 | 1177.8 | Remarks (Short narrative description of progress made (actual/planned)):The second tranche was approved in December 2012. The implementation of the projects at the national system houses has been completed and the focus in 2014 was on final clients. A substantial number of clients are in the process of being reconverted. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):6 of 6. TOR for consultants/subcontracts completed (actual/planned):5 of 5. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in February 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:There have been some challenges with the new systems and the System Houses are continously improving their new non-ODS low GWP systems. UNDP has provided continous Technical Assistance to all local System Houses. The international System houses have also progressed with the implementation although at a lower speed. In the last trimester of 2014. a special effort was put in place to advance the implementation of international system houses and 3 missions took place with international experts in November and December. | Since 2014, reconversion work at downstream user (DSU) level has been progressing with the National SHs. For the international SHs, Polioles/BASF had signed MOA with the project and have started trials with end-users; DOW has also agreed with the terms of MOA and document is in process of signature (in the meanwhile, their clients alread started to receive technical assistance preparation for trials) and Bayer is reviewing the terms of the MOA to engage in the reconversion process. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Multi-Year | LAC | MEX | PHA | 71 | INV | 168 | N | I | HCFC | 101.5 | 33.2 | 0 | 0 | 2013-12-01 |  | 2016-06-01 | 2016-06-01 |  |  | 3800000 | 0 | 3800000 | 0 | 0% | 3800000 | 0 | 1520000 | 285000 | 0 | 0 | 285000 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The third tranche was approved in December 2013. The implementation of the projects at the national system houses has been completed and the focus in 2014 was on final clients. A substantial number of clients are in the process of being reconverted. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2014. Missions undertaken (actual/planned):6 of 6. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):None. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, reconversion work at downstream user (DSU) level has been progressing with the National SHs. For the international SHs, Polioles/BASF had signed MOA with the project and have started trials with end-users; DOW has also agreed with the terms of MOA and document is in process of signature (in the meanwhile, their clients alread started to receive technical assistance preparation for trials) and Bayer is reviewing the terms of the MOA to engage in the reconversion process. | 2013 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Ensambladora de Refrigeradores (Enresa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 30 | A | I | CFC | 47 | 47 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 867033 | -51481 | 815552 | 815552 | 100% | 0 | 0 | 0 | 112714 | -6693 | 106021.77 | -0.77 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Astral (Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 31 | A | I | CFC | 344 | 344 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 2439932 | -80899 | 2359033 | 2359033 | 100% | 0 | 0 | 0 | 317191 | -10517 | 306674.33 | -0.33 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at (Comasa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 32 | A | D | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-12-01 |  | 1995-11-01 | 1998-12-01 | 1188724 | -152860 | 1035864 | 1035864 | 100% | 0 | 0 | 0 | 154534 | -19872 | 134662.1 | -0.1 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
CLO | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at Fabricacion de Compresores S.A. (Facosa, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-06-01 |  |  | 1996-05-01 | 584000 | -581001 | 2999 | 2999 | 100% | 0 | 0 | 0 | 75920 | -75530 | 389.87 | 0.13 | 0 | Canceled in 1996. Financially completed in 1996. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Supermatic, S.A. (Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 34 | A | I | CFC | 366 | 366 | 0 | 0 | 1994-12-01 | 1996-03-01 | 1996-06-01 |  | 1997-04-01 | 2000-12-01 | 2017517 | -5120 | 2012397 | 2012397 | 100% | 0 | 0 | 0 | 262277 | -666 | 261611.6 | -0.6 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Estufas y Refrigeradores Nacionales S.A. (Erna, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 35 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-09-01 | 2000-12-01 | 1038309 | -49630 | 988679 | 988679 | 100% | 0 | 0 | 0 | 134980 | -6452 | 128528.3 | -0.3 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Recovery of CFC-12 servicing of domestic refrigeration at Vitromatic Comercial y Servicios Integrados | RMP-Component | LAC | MEX | REF | 18 | TAS | 43 | N | I | CFC | 76 | 76 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1997-10-01 | 2002-12-01 | 352610 | -47579 | 305031 | 305031 | 100% | 0 | 0 | 0 | 45839 | -6185 | 39654.03 | -0.03 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Preparation of terms of reference for investment projects identified in the country programme | Individual | LAC | MEX | SEV | 04 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1993-12-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 2277 | 52277 | 52277 | 100% | 0 | 0 | 0 | 6500 | 296 | 6796.01 | -0.01 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 11 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 14 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-12-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Extension of institutional strengthening | Individual | LAC | MEX | SEV | 17 | INS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-12-01 |  | 1996-10-01 | 2003-11-01 | 47500 | 47500 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6175 | 6175 | 12350 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1995 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 17 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1996-11-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODSs under the Montreal Protocol | Individual | LAC | MEX | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-10-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in the foam and solvent sectors | Individual | LAC | MEX | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 52000 | -2539 | 49461 | 49461 | 100% | 0 | 0 | 0 | 6760 | -330 | 6429.93 | 0.07 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | MEX | SEV | 22 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | MEX | SEV | 22 | TAS | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1998-05-01 |  | 1998-05-01 | 2001-12-01 | 60000 | -1400 | 58600 | 58600 | 100% | 0 | 0 | 0 | 7800 | -182 | 7618 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project | Individual | LAC | MEX | SEV | 25 | INS | 83 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-07-01 |  | 2000-07-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 31 | INS | 97 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-08-01 | 2003-11-01 | 190000 | -45584 | 144416 | 144416 | 100% | 0 | 0 | 0 | 24700 | -5926 | 18774 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Preparation of the country programme update | Individual | LAC | MEX | SEV | 38 | CPG | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-10-01 | 48046 | -17955 | 30091 | 30091 | 100% | 0 | 0 | 0 | 6246 | -2334 | 3911.8225 | 0.17749 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | MEX | SEV | 45 | TAS | 127 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1541 | 8780.3064 | -0.3064 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Elimination of 1,1,1 TCA from the precision cleaning processes at Lucas Diesel | Individual | LAC | MEX | SOL | 15 | INV | 36 | A | D | TCA | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-06-01 |  | 1997-07-01 | 1999-12-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 21840 | 0 | 21840 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-113 from the textile cleaning processes at Procesadora y Revitalizadora | Individual | LAC | MEX | SOL | 15 | INV | 37 | A | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-09-01 |  | 1996-08-01 | 2000-12-01 | 71337 | -1889 | 69448 | 69448 | 100% | 0 | 0 | 0 | 9274 | -246 | 9028.24 | -0.24 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MLI | PHA | 48 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2010-01-01 | 12000 | -1262 | 10738 | 10738 | 100% | 0 | 0 | 0 | 900 | -95 | 805.35 | -0.35 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-12-01 | 2013-07-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 12900 | 0 | 12900 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | INV | 28 | N | I | CFC | 16.2 | 16.2 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2010-12-01 | 2013-07-01 | 150000 | -2802 | 147198 | 147198 | 100% | 0 | 0 | 0 | 11250 | -210 | 11039.85 | 0.15 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLI | PHA | 63 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-12-01 |  | 160000 | 0 | 160000 | 150571 | 94.11% | 9429 | 0 | 7543.2 | 12000 | 0 | 11292.825 | 707.175 | 0 | Completed in 2013. In spite of the continued difficult political situation in the country, implementation continued as planned. The planned milestones of receiving the last batch of equipment for this Tranche by the country and the distribution of the equipment to beneficiaries have been completed. Report of Tranche 1 was submitted to ExCom 71 and accepted. | Completed in 2013. Mission by international consultant and UNDP is planned once all equipment is received and security situation allows for it. This may be used as opportunity to organise workshop for awareness and training purposes. | 2011 |  | Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 32 | TAS | 09 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-12-01 | 2004-01-01 | 102658 | -3518 | 99140 | 99140 | 100% | 0 | 0 | 0 | 13346 | -457 | 12888.3015 | 0.69852 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | RMP-Component | AFR | MLI | REF | 32 | TAS | 10 | A | I | No_ODP | 3.8 | 3.8 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2005-07-01 | 2007-03-01 | 15455 | -237 | 15218 | 15218 | 100% | 0 | 0 | 0 | 2009 | -31 | 1978.3423 | -0.3423 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP update: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 45 | TAS | 16 | N | I | CFC | 12.3 | 12.3 | 0 | 0 | 2005-04-01 | 2007-09-01 | 2007-04-01 |  | 2007-12-01 | 2013-07-01 | 50000 | -1390 | 48610 | 48610 | 100% | 0 | 0 | 0 | 4500 | -125 | 4374.9 | 0.1 | 0 | Financially completed in 2013. |  | 2005 |  | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 22 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | Individual | AFR | MLW | FOA | 26 | INV | 12 | A | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 156500 | -17548 | 138952 | 138952 | 100% | 0 | 0 | 0 | 20345 | -2281 | 18063.76 | 0.23998 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide (tobacco) alternative demonstration project | Individual | AFR | MLW | FUM | 24 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-02-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of all non-essential and non-QPS methyl bromide (release of first tranche) | Multi-Year | AFR | MLW | FUM | 32 | DEM | 15 | N | I | MeBr | 19.3 | 19.3 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2001-12-01 |  | 2001-12-01 | 2011-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2001. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | Multi-Year | AFR | MLW | FUM | 34 | INV | 16 | N | I | MeBr | 20.9 | 20.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2002-08-01 |  | 2004-12-01 | 2011-12-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (release of third tranche) | Multi-Year | AFR | MLW | FUM | 40 | INV | 18 | N | I | MeBr | 41.1 | 41.1 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2011-12-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 56250 | 0 | 56250 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (fourth tranche) | Multi-Year | AFR | MLW | FUM | 43 | INV | 21 | N | I | MeBr | 47.7 | 47.7 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2011-12-01 | 849824 | -11521 | 838303 | 838303 | 100% | 0 | 0 | 0 | 63737 | -864 | 62872.9222 | 0.07775 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLW | PHA | 53 | INV | 25 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 | 2013-02-01 | 125500 | 0 | 125500 | 125500 | 100% | 0 | 0 | 0 | 11295 | 0 | 11295 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | INV | 29 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-12-01 | 2012-10-01 | 47500 | -1245 | 46255 | 46255 | 100% | 0 | 0 | 0 | 4275 | -112 | 4162.95 | 0.05 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | MLW | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MLW | REF | 19 | TAS | 05 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -311 | 106009 | 106009 | 100% | 0 | 0 | 0 | 13822 | -40 | 13781.17 | 0.83 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | MLW | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 | 0 | 910 | 0 | 910 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | MDI transition strategy | Individual | EUR | MOL | ARS | 54 | TAS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-08-01 | 2009-09-01 |  | 2010-12-01 | 2012-07-01 | 30000 | -18 | 29982 | 29982 | 100% | 0 | 0 | 0 | 2700 | -2 | 2698.38 | -0.38 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | EUR | MOL | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -2381 | 9619 | 9619 | 100% | 0 | 0 | 0 | 900 | -179 | 721.425 | -0.425 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | MOL | PHA | 52 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-07-01 |  | 2008-11-01 | 2013-01-01 | 152500 | 0 | 152500 | 152500 | 100% | 0 | 0 | 0 | 11438 | 0 | 11438 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | MOL | PHA | 55 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-07-01 | 85000 | -3117 | 81883 | 81883 | 100% | 0 | 0 | 0 | 6375 | -234 | 6141.2249 | -0.22495 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | INV | 23 | N | I | CFC | 10 | 10 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 152500 | -159 | 152341 | 152341 | 100% | 0 | 0 | 0 | 11438 | -12 | 11426.0745 | -0.0745 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOL | PHA | 63 | INV | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 | 2015-12-01 |  |  | 79200 | 0 | 79200 | 78252 | 98.8% | 948 | 0 | 379.088 | 7128 | 0 | 7042.7052 | 85.2948 | 0 | Remarks (Short narrative description of progress made (actual/planned)):HCFCs controls introduced with annual quota effective starting 01.01.2013. Technicians training and certification system harmonized with F-Gas EU framework. Three (3) advanced portable refrigerant identifiers purchased and delivered to the Customs Department, and a specialized training on the use of this equipment organized by NOU-Moldova. Twenty six (26) Customs officers received training. Handbook for Customs Officers has been updated with new information on ODSs in general, and HCFC and HCFC equipment. Twenty one (21) in 2014 according to the new mentioned F-Gas. Twenty (2) equipment sets purchased and delivered to service centers to qualified technicians. Tranche 2 being prepared for. Prodoc signed (actual/planned, yes/no and date):Yes - July 2011. Missions undertaken (actual/planned):0 of 0. Missions are planned later for HPMP Stage II formulation. TOR for consultants/subcontracts completed (actual/planned):5 of 5, including legislative improvements, trainings for Customs/technicians and equipment supply. Contract/PO/MOA agreements signed:Yes. First disbursement date (actual/planned):The first disbursement took place in August 2011. Any delays/problems (yes/no):Yes, baseline changes were expected, but not approved by ImpCom in 2014. If Yes, reasons for delay & action plan to resolve:Lower import limits triggered HCFC stockpiling in 2012 before freeze, and reductions in HPMP funding expected in Stage II due to lower HCFC consumption category. | Funds under Tranche 1 of HPMP Stage 1 almost fully disbursed and 2014 report outlines the activities which were implemented. This first tranche is set for closure. During Q1 of 2015, NOU-Moldova and UNDP prepared a request for the last tranche under HPMP-Stage I. The last tranche was submitted to and approved at the 75th ExCom. Mission planned for late July 2015 to enable the start of last tranche of HPMP Stage I which was approved in May 2015. | 2011 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | MOL | PHA | 72 | PRP | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1400 | 0 | 0 | 1400 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Stage II preparation was approved in May 2014. No activities took place in 2014. The main activities are planned in 2015. Prodoc signed (actual/planned, yes/no and date):No. Missions undertaken (actual/planned):0/0 in 2014. One mission planned for 2015 together with UNEP. TOR for consultants/subcontracts completed (actual/planned):No. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | National experts were recruited to enable HCFC data collection by sector. Draft data area now available for review, and a stakeholder workshop on HPMP Stage II design is planned in late July 2015. HPMP Stage II may be submitted to the 76th ExCom in 2016. |  |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | MOL | PHA | 73 | TAS | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2015-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2700 | 0 | 0 | 2700 | 0 | Newly Approved | Project budgets were set in financial system, and a national expert was recruited to do the verification. The process is now ongoing and will deliver a draft report by August/September 2015. A mission is planned in late July 2015. | 2014 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | EUR | MOL | REF | 25 | TAS | 02 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2002-05-01 | 2002-11-01 | 254150 | -304 | 253846 | 253846 | 100% | 0 | 0 | 0 | 33040 | -40 | 32999.98 | 0.02 | 0 | Completed in 2002. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for the RMP proposal | RMP-Component | EUR | MOL | REF | 41 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance programme | RMP-Component | EUR | MOL | REF | 44 | TAS | 12 | N | I | CFC | 55.9 | 55.9 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-07-01 | 173495 | -3 | 173492 | 173492 | 100% | 0 | 0 | 0 | 15615 | 0 | 15614.73 | 0.27 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | MON | REF | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | MON | REF | 35 | TAS | 06 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2005-11-01 | 108600 | 0 | 108600 | 108600 | 100% | 0 | 0 | 0 | 14118 | 0 | 14118 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of integral skin and cold cured molded PUF products at Maghreb Elastoplast | Individual | AFR | MOR | FOA | 20 | INV | 04 | A | D | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1997-09-01 | 2000-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15599.57 | 0.43 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MOR | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 80000 | -13195 | 66805 | 66805 | 100% | 0 | 0 | 0 | 10400 | -1715 | 8685 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richbond S.A. | Individual | AFR | MOR | FOA | 22 | INV | 08 | A | I | CFC | 150 | 150 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-06-01 |  |  | 2004-12-01 | 470625 | -40036 | 430589 | 430589 | 100% | 0 | 0 | 0 | 61181 | -5205 | 55976.5913 | -0.5913 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Dolidol | Individual | AFR | MOR | FOA | 22 | INV | 10 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 1999-06-01 |  |  | 2003-12-01 | 475822 | -61553 | 414269 | 414269 | 100% | 0 | 0 | 0 | 61857 | -8002 | 53854.86 | 0.14 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | Individual | AFR | MOR | FOA | 23 | INV | 12 | A | I | CFC | 85 | 85 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2005-09-01 | 517300 | -5023 | 512277 | 512277 | 100% | 0 | 0 | 0 | 67249 | -653 | 66596.01 | -0.01 | 0 | Canceled in 2004. Financially completed in 2005. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture fo flexible foam (slabstock) at Salidor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 13 | A | I | CFC | 48 | 48 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richdor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 14 | A | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 62300 | 0 | 62300 | 62300 | 100% | 0 | 0 | 0 | 8099 | 0 | 8099 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam at Panaf Isolation S.A. | Individual | AFR | MOR | FOA | 23 | INV | 15 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-09-01 | 2001-12-01 | 137000 | -3191 | 133809 | 133809 | 100% | 0 | 0 | 0 | 17810 | -415 | 17395 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Molen Industrie S.A. | Individual | AFR | MOR | FOA | 23 | INV | 16 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-12-01 | 1999-12-01 |  | 2002-06-01 | 2003-11-01 | 56070 | 0 | 56070 | 56070 | 100% | 0 | 0 | 0 | 7289 | 0 | 7289.1 | -0.1 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Mousse d'Or S.A. | Individual | AFR | MOR | FOA | 23 | INV | 19 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 280350 | 0 | 280350 | 280350 | 100% | 0 | 0 | 0 | 36446 | 0 | 36445.5 | 0.5 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | AFR | MOR | FOA | 24 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
CLO | UNDP | Conversion to LCD technology in the manufacture of flexible foam (slabstock) to replace CFC-11 at Bonbino Confort | Individual | AFR | MOR | FOA | 25 | INV | 22 | A | I | CFC | 90 | 90 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  |  | 2004-12-01 | 490200 | 0 | 490200 | 490200 | 100% | 0 | 0 | 0 | 63726 | 0 | 63726 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b/water technology in the manufacture of rigid polyurethane spray foam at Batcomar S.A. | Individual | AFR | MOR | FOA | 25 | INV | 23 | A | I | CFC | 9.2 | 9.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-07-01 | 2002-03-01 | 72000 | -10826 | 61174 | 61174 | 100% | 0 | 0 | 0 | 9360 | -1407 | 7952.62 | 0.38 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Interfer by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 43 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 78973 | 0 | 78973 | 78973 | 100% | 0 | 0 | 0 | 10266 | 0 | 10266.49 | -0.49 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Engequife by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 44 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 56391 | -146 | 56245 | 56245 | 100% | 0 | 0 | 0 | 7331 | -19 | 7311.8496 | 0.1504 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Project preparation | Individual | AFR | MOR | SEV | 22 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
CLO | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (tobacco) | Individual | AFR | MOZ | FUM | 27 | PRP | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | INV | 15 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2008-11-01 | 2010-10-01 | 2010-11-01 |  | 2011-12-01 | 2012-02-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 | 0 | 9045 | 0 | 9045 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-02-01 | 17000 | -1129 | 15871 | 15871 | 100% | 0 | 0 | 0 | 1530 | -102 | 1428.39 | -0.39 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | MOZ | REF | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -1643 | 18357 | 18357 | 100% | 0 | 0 | 0 | 2600 | -214 | 2386.41 | -0.41 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MOZ | REF | 22 | TAS | 06 | A | I | CFC | 6.9 | 6.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 115809 | -138 | 115671 | 115671 | 100% | 0 | 0 | 0 | 15055 | -18 | 15037.2275 | -0.2275 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
CLO | UNDP | Formulation of the investment components of theRMP | Individual | ASP | MYA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  |  | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | NEP | PHA | 50 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-07-01 | 2011-11-01 | 15000 | -10146 | 4854 | 4854 | 100% | 0 | 0 | 0 | 1125 | -761 | 364.05 | -0.05 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | NEP | PHA | 52 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-06-01 | 75000 | -86 | 74914 | 74914 | 100% | 0 | 0 | 0 | 6750 | -8 | 6742.26 | -0.26 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | INV | 26 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-09-01 | 2011-03-01 |  | 2013-12-01 | 2014-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Second and final disbursement under LoA expected to be made in Q2 of 2014 after respective milestone is achieved. | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | NEP | PHA | 66 | INV | 30 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2012-04-01 |  | 2015-04-01 | 2016-01-01 |  |  | 42000 | 0 | 42000 | 0 | 0% | 42000 | 0 | 16800 | 3780 | 0 | 0 | 3780 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The implementation plan was discussed and finalized in July 2014. The changes in the procurement plan were discussed and being finalized. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in December 2013. Missions undertaken (actual/planned):Planned in mid-2015. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned in March 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:There were delays in the procurement process. The NOU has requested UNDP to undertake the procurement and make the payment for the training consultant. Also there was a change in the procurement plan. Follow-up actions have been taken to resolve the matters.. | The first disbursement of USD8,000 (out of USD42,000) for R&R training has been made in May 2015. This was delayed due to the earthquake happened in April 2015. Also due to the earthquake, the procurement process for R&R equipment has been delayed. A planned mission is also postponed to late 2015 at the time of R&R training upon the arrival of R&R equipment in the country. | 2012 |  | Investment
FIN | UNDP | Preparation of a refrigeration recovery and recycling project | Individual | ASP | NEP | REF | 27 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-07-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration subsector | Individual | ASP | NEP | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2001-12-01 | 20000 | -15000 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2600 | -1950 | 650 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring activities included in the RMP | RMP-Component | ASP | NEP | REF | 28 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2005-01-01 | 2002-02-01 |  | 2005-12-01 | 2007-03-01 | 8894 | -3329 | 5565 | 5565 | 100% | 0 | 0 | 0 | 1156 | -433 | 723.5324 | -0.5324 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | ASP | NEP | REF | 28 | TAS | 08 | A | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2003-10-01 | 2003-11-01 | 88577 | -1 | 88576 | 88576 | 100% | 0 | 0 | 0 | 11515 | 0 | 11515.01 | -0.01 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for the refrigerant management plan update | Individual | ASP | NEP | REF | 43 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2005-07-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling, retrofit and their monitoring | RMP-Component | ASP | NEP | REF | 44 | TAS | 16 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 | 2011-11-01 | 57495 | -6050 | 51445 | 51445 | 100% | 0 | 0 | 0 | 5175 | -545 | 4630.4527 | -0.4527 | 0 | Completed in 2009. |  | 2004 |  | Investment
TRF | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2007-04-01 |  |  | 2007-12-01 | 12000 | -12000 | 0 | 0 |  | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | NER | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-03-01 | 2002-03-01 | 20000 | -3085 | 16915 | 16915 | 100% | 0 | 0 | 0 | 2600 | -401 | 2199 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | NER | REF | 27 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 2002-01-01 | 2001-04-01 |  | 2004-12-01 | 2005-11-01 | 15455 | -3305 | 12150 | 12150 | 100% | 0 | 0 | 0 | 2009 | -430 | 1579.5321 | -0.5321 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | NER | REF | 27 | TAS | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2001-04-01 |  | 2003-08-01 | 2003-10-01 | 87603 | -8661 | 78942 | 78942 | 100% | 0 | 0 | 0 | 11388 | -1126 | 10262.39 | -0.39 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | NER | REF | 37 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-11-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of transitional strategy for aerosol inhalant drug products | Individual | LAC | NIC | ARS | 42 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-07-01 | 2005-04-01 |  | 2008-03-01 | 2009-07-01 | 30000 | -44 | 29956 | 29956 | 100% | 0 | 0 | 0 | 2250 | -3 | 2246.7 | 0.3 | 0 | Completed in 2008.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | NIC | PHA | 49 | PRP | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-07-01 |  | 2008-09-01 | 2010-01-01 | 15000 | -1042 | 13958 | 13958 | 100% | 0 | 0 | 0 | 1125 | -78 | 1046.85 | 0.14995 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-11-01 | 2013-02-01 | 320000 | -42 | 319958 | 319958 | 100% | 0 | 0 | 0 | 24000 | -3 | 23996.8499 | 0.15005 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of the RMP update proposal (investment component) | RMP-Component | LAC | NIC | REF | 41 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-11-01 | 15000 | -36 | 14964 | 14964 | 100% | 0 | 0 | 0 | 1125 | -3 | 1122.3 | -0.3 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP update: incentive programme to promote good practices in refrigeration | RMP-Component | LAC | NIC | REF | 45 | TAS | 13 | N | I | CFC | 35.2 | 35.2 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Royal Foam Products | Individual | AFR | NIR | FOA | 20 | INV | 12 | A | D | CFC | 43 | 43 | 0 | 0 | 1996-10-01 | 1998-08-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 34000 | -600 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4420 | -78 | 4342 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Teju Industries Limited | Individual | AFR | NIR | FOA | 20 | INV | 13 | A | D | CFC | 47 | 47 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-10-01 | 2003-01-01 | 75000 | -6859 | 68141 | 68141 | 100% | 0 | 0 | 0 | 9750 | -892 | 8858.33 | -0.33 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam for thermoware in Eleganza Industries Ltd. at Ikeja, Lagos | Individual | AFR | NIR | FOA | 20 | INV | 14 | A | I | CFC | 48.3 | 48.3 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 314000 | -4065 | 309935 | 309935 | 100% | 0 | 0 | 0 | 40820 | -528 | 40291.55 | 0.45 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Sara Products Limited | Individual | AFR | NIR | FOA | 20 | INV | 15 | A | D | CFC | 27.7 | 27.7 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1999-07-01 | 2001-12-01 | 107000 | -2075 | 104925 | 104925 | 100% | 0 | 0 | 0 | 13910 | -270 | 13639.6363 | 0.3637 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | NIR | FOA | 21 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Winco Foam Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 21 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 117200 | -321 | 116879 | 116879 | 100% | 0 | 0 | 0 | 15236 | -42 | 15194.27 | -0.27 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Bajabure Industrial Complex Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 22 | A | I | CFC | 32.3 | 32.3 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2002-11-01 | 135400 | -11117 | 124283 | 124283 | 100% | 0 | 0 | 0 | 17602 | -1445 | 16157 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Elico Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 23 | A | I | CFC | 25.7 | 25.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 133900 | -13658 | 120242 | 120242 | 100% | 0 | 0 | 0 | 17407 | -1776 | 15631.46 | -0.46 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Mouka Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 24 | A | I | CFC | 30.3 | 30.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2004-01-01 | 143600 | -3462 | 140138 | 140138 | 100% | 0 | 0 | 0 | 18668 | -450 | 18217.94 | 0.06 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Safa Foam Products (Nig) Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 25 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-12-01 |  | 2003-08-01 | 2006-10-01 | 146400 | 0 | 146400 | 146400 | 100% | 0 | 0 | 0 | 19032 | 0 | 19032 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manuyfacture of rigid PUF insulation products at Aluminium Manufacturing Company of Nigeria Plc (Alumaco) | Individual | AFR | NIR | FOA | 23 | INV | 26 | A | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-12-01 |  | 2001-11-01 | 2002-11-01 | 38000 | -400 | 37600 | 37600 | 100% | 0 | 0 | 0 | 4940 | -52 | 4888 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for thermoware in 3 enterprises of the Eleganza Group (Eleganza Cooler and Household Industries Ltd., Eleganza Ceramics and Cooler Industries Ltd.) | Individual | AFR | NIR | FOA | 23 | INV | 27 | A | I | CFC | 73.8 | 73.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 568000 | -25762 | 542238 | 542238 | 100% | 0 | 0 | 0 | 73840 | -3349 | 70490.94 | 0.06 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Ugochukwu Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 28 | A | I | CFC | 118.6 | 118.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-07-01 | 2002-11-01 | 407600 | 0 | 407600 | 407600 | 100% | 0 | 0 | 0 | 52988 | 0 | 52988 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF spray insulation at Polyurethane Manufacturers Ltd. (Polyma) | Individual | AFR | NIR | FOA | 23 | INV | 29 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2004-01-01 | 80500 | -339 | 80161 | 80161 | 100% | 0 | 0 | 0 | 10465 | -44 | 10420.93 | 0.07 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Orbit Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 31 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-07-01 | 2003-11-01 | 135200 | -1 | 135199 | 135199 | 100% | 0 | 0 | 0 | 17576 | 0 | 17576 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 32 | A | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 2001-10-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 84600 | 0 | 84600 | 84600 | 100% | 0 | 0 | 0 | 10998 | 0 | 10998 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 | 2003-12-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Okin Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 33 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-11-01 | 2002-11-01 | 133200 | 0 | 133200 | 133200 | 100% | 0 | 0 | 0 | 17316 | 0 | 17316 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Marta Industries (Nig.) Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 34 | A | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 130600 | -1299 | 129301 | 129301 | 100% | 0 | 0 | 0 | 16978 | -169 | 16809.13 | -0.13 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 35 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 142300 | -1210 | 141090 | 141090 | 100% | 0 | 0 | 0 | 18499 | -157 | 18341.7 | 0.29997 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Chemical and Wire Manufacturers Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 36 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-01-01 | 2003-11-01 | 164500 | 0 | 164500 | 164500 | 100% | 0 | 0 | 0 | 21385 | 0 | 21385 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 | 2003-07-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Bodefoam Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 37 | A | I | CFC | 35.3 | 35.3 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 136400 | 0 | 136400 | 136400 | 100% | 0 | 0 | 0 | 17732 | 0 | 17732 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Group Enterprises Nig. Ltd. (Polly Foam) | Individual | AFR | NIR | FOA | 26 | INV | 38 | A | I | CFC | 26 | 26 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 128900 | -2349 | 126551 | 126551 | 100% | 0 | 0 | 0 | 16757 | -305 | 16451.63 | 0.37 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pesaco Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 39 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1998-11-01 | 2000-08-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 126400 | 0 | 126400 | 126400 | 100% | 0 | 0 | 0 | 16432 | 0 | 16432 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Yinka-Oba Foam Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 42 | A | I | CFC | 30 | 30 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2003-08-01 | 2005-10-01 | 185300 | -629 | 184671 | 184671 | 100% | 0 | 0 | 0 | 24089 | -82 | 24007.23 | -0.23001 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Universal Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 43 | A | I | CFC | 30.6 | 30.6 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-11-01 | 135300 | 0 | 135300 | 135300 | 100% | 0 | 0 | 0 | 17589 | 0 | 17589 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation | Individual | AFR | NIR | FOA | 26 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Preparation of three projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of seven projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-04-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at United Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 46 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-07-01 | 2001-10-01 | 2002-02-01 |  | 2003-08-01 | 2007-01-01 | 137310 | -6098 | 131212 | 131212 | 100% | 0 | 0 | 0 | 17850 | -793 | 17057.5733 | -0.5733 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Tinuola Bay Industries Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 47 | A | I | CFC | 21 | 21 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-09-01 | 2003-09-01 | 119410 | 0 | 119410 | 119410 | 100% | 0 | 0 | 0 | 15523 | 0 | 15523.3 | -0.3 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Diamond Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 49 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2001-11-01 | 2002-11-01 | 112150 | 0 | 112150 | 112150 | 100% | 0 | 0 | 0 | 14580 | 0 | 14579.5 | 0.5 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to liquid carbon dioxide blown technology in the manufacture of molded flexible polyurethane foam at Automotive Component Industries Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 50 | A | I | CFC | 37 | 37 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 204761 | 0 | 204761 | 204761 | 100% | 0 | 0 | 0 | 26619 | 0 | 26618.93 | 0.07 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Rubez (Nig.) Ltd. (Current Foam) | Individual | AFR | NIR | FOA | 29 | INV | 55 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2002-12-01 |  | 2003-08-01 | 2005-11-01 | 89803 | -65 | 89738 | 89738 | 100% | 0 | 0 | 0 | 11674 | -8 | 11666.39 | -0.39 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafco Industries Limited | Individual | AFR | NIR | FOA | 29 | INV | 56 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-12-01 | 2006-06-01 | 58559 | 0 | 58559 | 58559 | 100% | 0 | 0 | 0 | 7613 | 0 | 7612.67 | 0.33 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Vono Products PLC | Individual | AFR | NIR | FOA | 29 | INV | 57 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 173782 | 0 | 173782 | 173782 | 100% | 0 | 0 | 0 | 22592 | 0 | 22591.66 | 0.34 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride blown technology in the manufacture of flexible polyurethane foam at Betaday Industries Ltd. | Individual | AFR | NIR | FOA | 29 | INV | 58 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 104495 | -1 | 104494 | 104494 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584.22 | -0.22 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to mehtylene chloride in the manufacture of flexible polyurethane foam at Vito Company (Nig.) Ltd., Victory Foam | Individual | AFR | NIR | FOA | 29 | INV | 59 | A | I | CFC | 26 | 26 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 133560 | -188 | 133372 | 133372 | 100% | 0 | 0 | 0 | 17363 | -24 | 17338.36 | 0.64 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 8 projects in the general foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2001. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Sokoto Foam Factory (Nig.) Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 65 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-12-01 | 2005-09-01 | 141421 | -4328 | 137093 | 137093 | 100% | 0 | 0 | 0 | 18385 | -563 | 17821.73 | 0.27 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manfuacture of flexible slabstock foam by conversion to methylene chloride at Abeokuta Commercial and Industrial Co. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 66 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 118468 | -382 | 118086 | 118086 | 100% | 0 | 0 | 0 | 15401 | -50 | 15351.18 | -0.18 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Celplas Industries Limited | Individual | AFR | NIR | FOA | 31 | INV | 67 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-11-01 | 2002-12-01 | 215325 | 0 | 215325 | 215325 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992.25 | -0.25 | 0 | Completed in 2002. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Climax Ind. Ltd. (Ely Foam) | Individual | AFR | NIR | FOA | 31 | INV | 68 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 173362 | -575 | 172787 | 172787 | 100% | 0 | 0 | 0 | 22537 | -75 | 22462.31 | -0.31 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Wappah Foam Limited | Individual | AFR | NIR | FOA | 31 | INV | 69 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 130081 | -4 | 130077 | 130077 | 100% | 0 | 0 | 0 | 16911 | -1 | 16909.53 | 0.47 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafa Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 70 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-12-01 | 2006-10-01 | 124667 | -9881 | 114786 | 114786 | 100% | 0 | 0 | 0 | 16207 | -1285 | 14921.71 | 0.29 | 0 | Completed in 2002. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 78 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 82 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Atuchukwu Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 83 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 118488 | -1 | 118487 | 118487 | 100% | 0 | 0 | 0 | 15403 | 0 | 15403.44 | -0.44 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Apaco Foam and Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 84 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 147018 | 0 | 147018 | 147018 | 100% | 0 | 0 | 0 | 19112 | 0 | 19112.34 | -0.34 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Gasfa Industries Nig., Ltd. (Meka Foam) | Individual | AFR | NIR | FOA | 34 | INV | 85 | A | I | CFC | 40.5 | 40.5 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2003-08-01 | 2005-09-01 | 238843 | -9895 | 228948 | 228948 | 100% | 0 | 0 | 0 | 31050 | -1286 | 29763.59 | 0.41 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Adig Plastics Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 86 | A | I | CFC | 14.3 | 14.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-04-01 | 112050 | 0 | 112050 | 112050 | 100% | 0 | 0 | 0 | 14567 | 0 | 14566.5 | 0.5 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Rima Foam Products Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 88 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-06-01 | 119036 | -582 | 118454 | 118454 | 100% | 0 | 0 | 0 | 15475 | -76 | 15398.68 | 0.32 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 89 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2005-11-01 | 126531 | -13568 | 112963 | 112963 | 100% | 0 | 0 | 0 | 16449 | -1764 | 14685.1932 | -0.19323 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
CLO | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 91 | A | I | CFC | 4.7 | 4.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  |  | 2005-09-01 | 36801 | -3512 | 33289 | 33289 | 100% | 0 | 0 | 0 | 4784 | -457 | 4327.13 | -0.13 | 0 | Canceled in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bibafoam Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 92 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-10-01 | 114685 | 0 | 114685 | 114685 | 100% | 0 | 0 | 0 | 14909 | 0 | 14909.05 | -0.05 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bamako Industrial, Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 94 | A | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2005-11-01 | 114510 | -3460 | 111050 | 111050 | 100% | 0 | 0 | 0 | 14886 | -450 | 14436.3 | -0.3 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Agric Services (Nig.), Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 95 | A | I | CFC | 43.7 | 43.7 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-08-01 | 2005-10-01 | 239160 | -263 | 238897 | 238897 | 100% | 0 | 0 | 0 | 31091 | -34 | 31056.6098 | 0.39018 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Individual | AFR | NIR | FOA | 35 | INV | 96 | A | I | CFC | 199.2 | 199.2 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2007-02-01 | 1062808 | 0 | 1062808 | 1062808 | 100% | 0 | 0 | 0 | 126909 | 0 | 126908.9 | 0.1 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | AFR | NIR | FOA | 36 | PRP | 100 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | NIR | FOA | 57 | PRP | 123 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-10-01 | 50000 | -19883 | 30117 | 30117 | 100% | 0 | 0 | 0 | 3750 | -1491 | 2258.5657 | 0.4343 | 0 | Completed. Foam sector plan submitted as part of the HPMP approved at 62nd ExCom meeting. Final invoices expected in 2011. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | NIR | FOA | 72 | PRP | 139 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 5600 | 0 | 0 | 5600 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This preparatory phase was delayed due to the need to complete key activities related to Stage 1 first, and in particular the completion of the transition to methyl formate through the setting up and operationalisation of the system house. Prodoc signed (actual/planned, yes/no and date):No. Missions undertaken (actual/planned):No. TOR for consultants/subcontracts completed (actual/planned):No. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Due to the need to complete some stage 1 actvities | With the approval of the guidelines for Stage 2, preparatory work for stage 2 has accelerated. |  |  | Non-Investment
FIN | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | Multi-Year | AFR | NIR | PHA | 38 | INV | 106 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2006-12-01 | 2013-10-01 | 5013929 | 0 | 5013929 | 5013929 | 100% | 0 | 0 | 0 | 449318 | 0 | 449318 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2005-12-01 | Investment
FIN | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | NIR | PHA | 41 | INV | 108 | N | I | CFC | 830 | 830 | 0 | 0 | 2003-12-01 | 2007-03-01 | 2004-12-01 |  | 2007-12-01 | 2013-10-01 | 2976827 | 0 | 2976827 | 2976827 | 100% | 0 | 0 | 0 | 264834 | 0 | 264834 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | NIR | PHA | 44 | INV | 112 | N | I | CFC | 850.7 | 850.7 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-09-01 | 2013-10-01 | 2077141 | 0 | 2077141 | 2077141 | 100% | 0 | 0 | 0 | 183863 | 0 | 183863 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | NIR | PHA | 54 | INV | 117 | N | I | CFC | 1179.8 | 1179.8 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-09-01 | 2013-10-01 | 1286303 | 0 | 1286303 | 1286303 | 100% | 0 | 0 | 0 | 111407 | 0 | 111407 | 0 | 0 | Financially completed in 2013. | Completed in 2011. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | NIR | PHA | 55 | PRP | 119 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 121 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | AFR | NIR | PHA | 57 | INV | 122 | N | I | CFC | 200 | 200 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2011-11-01 | 2013-10-01 | 385000 | 0 | 385000 | 385000 | 100% | 0 | 0 | 0 | 32770 | 0 | 32770 | 0 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | National CFC phase-out plan (seventh and eighth tranche) | Multi-Year | AFR | NIR | PHA | 59 | INV | 125 | N | I | CFC | 264.6 | 264.6 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2012-12-01 | 2013-10-01 | 454200 | -18259 | 435941 | 435941 | 100% | 0 | 0 | 0 | 36518 | -1468 | 35049.9635 | 0.036464 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2011-12-01 |  | 2012-10-01 | 2013-03-01 | 855603 | 0 | 855603 | 855603 | 100% | 0 | 0 | 0 | 64170 | 0 | 64170 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam, refrigeration air-conditioning servicing and coordination) | Multi-year | AFR | NIR | PHA | 66 | INV | 132 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2013-04-01 |  | 2014-11-01 |  | 836515 | 0 | 836515 | 836515 | 100% | 0 | 0 | 0 | 62739 | 0 | 62739 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):This project was approved in April 2012. Although initial completion was planned within one year, it was completed by end of 2014 due in particular to some challenges in the procurement of the required equipment in the foam component of the tranche. The activity at the Automotive Component Industry (ACI) was succesfully completed in reporting period, as planned. Prodoc signed (actual/planned, yes/no and date):Yes - November 2012. Missions undertaken (actual/planned):1/1 (planned and completed in August 2014, with international consultant). TOR for consultants/subcontracts completed (actual/planned):In place (National and International Consultants). Contract/PO/MOA agreements signed:Yes (both for refrigeration and foam components). First disbursement date (actual/planned):The first disbursement took place in November 2012. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Some delays were experienced, particularly for the delivery of the tank at the Vitapur facility, but were addressed to allow completion of this tranche. | A monitoring mission by International consultant and UNDP is planned for May 2014, on the occasion of the launch of production at refrigerant and foam factories. This will also support the kick-off of activities under Tranche 3. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam) | Multi-Year | AFR | NIR | PHA | 71 | INV | 135 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-11-01 | 2015-12-01 | 2016-01-01 |  |  | 503829 | 0 | 503829 | 46854 | 9.3% | 456975 | 0 | 182789.86 | 37787 | 0 | 3514.06 | 34272.94 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Activities for this tranche are ongoing, although expenditures are still at a limited level, reflecting some delays in implementation. In the Refrigeration component, official launch of the Pamaque facility is under preparation and logistical improvements to the operation of the plant have been completed. For the foam component, the laboratory has been completed at the Vitapur site and after initial trials, full launch of production is expected. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed prior to 2014. Missions undertaken (actual/planned):1/1 (planned and completed in August 2014, with international consultant). TOR for consultants/subcontracts completed (actual/planned):In place (National and International Consultants). Contract/PO/MOA agreements signed:Yes (both for refrigeration and foam components). First disbursement date (actual/planned):The first disbursement took place in November 2014. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The fine tuning of the launch of the use of methyl formate at the foam plant has taken more time than expected. Additional visit by international technical expert will help complete this component. | Mission by International consultant was held in April 2015, facilitating the progress of activities at the two foam companies. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | NIR | PHA | 72 | PRP | 138 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 0 | 90000 | 6300 | 0 | 0 | 6300 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The Stage II preparatory funding was approved in May 2014. Delays have been incurred due to the timing of the completion of Stage I activities. This part of the preparatory phase must be developed in coordination with sector components (foam, as well as the PRP implemenetd by UNIDO). Prodoc signed (actual/planned, yes/no and date):No. Missions undertaken (actual/planned):No. TOR for consultants/subcontracts completed (actual/planned):No. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The need for coordination with all components of the PRP for Stage 2 of the HPMP. With completion of key activities in Stage 1 in 2015, this wil be resolved. | With the approval of the guidelines for Stage 2, preparatory work for stage 2 has accelerated. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | AFR | NIR | PHA | 73 | INV | 140 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 503829 | 0 | 503829 | 0 | 0% | 503829 | 0 | 201531.6 | 37787 | 0 | 0 | 37787 | 0 | Newly Approved | This is being coordinated with the final activity completion of the 3rd tranche, and benefitted from the visit of the international expert in April 2015. | 2014 |  | Investment
FIN | UNDP | Technical assistance to prepare a refrigeration management plan (RMP) | RMP-Component | AFR | NIR | REF | 32 | TAS | 72 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2003-01-01 |  | 2002-12-01 | 2003-11-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | AFR | NIR | REF | 36 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-11-01 | 40000 | -1 | 39999 | 39999 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
FIN | UNDP | National seminar on industry and protection of the ozone layer | Individual | AFR | NIR | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-11-01 |  | 1992-12-01 | 1997-12-01 | 49650 | -23201 | 26449 | 26449 | 100% | 0 | 0 | 0 | 6455 | -3016 | 3438.37 | 0.63 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | NIR | SEV | 09 | INS | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-01-01 | 1996-03-01 |  | 2001-01-01 | 2003-09-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | NIR | SEV | 17 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (phase II) | Individual | AFR | NIR | SEV | 34 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-08-01 | 2009-07-01 | 200000 | -851 | 199149 | 199149 | 100% | 0 | 0 | 0 | 26000 | -111 | 25889.37 | -0.37 | 0 | Completed in 2003.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | AFR | NIR | SEV | 36 | CPG | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-10-01 |  | 2007-12-01 | 2011-11-01 | 241493 | -10289 | 231204 | 231204 | 100% | 0 | 0 | 0 | 31394 | -1338 | 30056.5238 | -0.5238 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | NIR | SEV | 40 | INS | 107 | N | I | No_ODP | 21.5 | 21.5 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2012-04-01 | 260000 | -100 | 259900 | 259900 | 100% | 0 | 0 | 0 | 19500 | -8 | 19492.5 | -0.5 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | NIR | SEV | 48 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2007-12-01 | 2012-04-01 | 260000 | -195 | 259805 | 259805 | 100% | 0 | 0 | 0 | 19500 | -15 | 19485.375 | -0.375 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | AFR | NIR | SEV | 54 | INS | 118 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2010-12-01 | 2013-03-01 | 260000 | -3767 | 256233 | 256233 | 100% | 0 | 0 | 0 | 19500 | -282 | 19217.475 | 0.525 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | NIR | SEV | 62 | INS | 130 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-11-01 |  | 2013-07-01 | 2014-02-01 | 260000 | 0 | 260000 | 257992 | 99.23% | 2008 | 0 | 0 | 19500 | 0 | 19349.3933 | 150.6067 | 0 | Financially Completed in 2014. | Completed in 2013. | 2010 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | AFR | NIR | SEV | 68 | INS | 134 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-11-01 |  | 2014-12-01 |  | 260000 | 0 | 260000 | 260000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. Phase 7 was completed as planned in 2014, and smooth operation of the National Ozone Office allowed for the good implementation of the HPMP as well as other projects, and reporting on time - allowing for compliance to be maintained. Specific cooperation was conducted with the Ozone Secretriat to reflect in the Artical 7 database the HCFCs contained in polyols, as imported and appropriately reported by Nigeria. Additionally a specific report assessing in the long run the impact of the Institutional Strengthening programme in Nigeria was completed by the end of this Phase, in parallel to the submisison of the request for extension of the programme (approval obtained for Phase 8 in November 2014). Prodoc signed (actual/planned, yes/no and date):Yes - August 2013. Missions undertaken (actual/planned):Yes (in August 2014, as planned). TOR for consultants/subcontracts completed (actual/planned):No. Contract/PO/MOA agreements signed:No. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Delegation of Authority issued, implementation will be initiated shortly, with the Project Document revision. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | AFR | NIR | SEV | 73 | INS | 141 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 260000 | 0 | 260000 | 0 | 0% | 260000 | 0 | 104000 | 18200 | 0 | 0 | 18200 | 0 | Newly Approved | Project document for this phase has bene signed, activities ongoing (data gathering and reporting, support to projects, awareness, etc.) | 2014 |  | Non-Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | PAK | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-11-01 | 2011-11-01 | 60000 | -9096 | 50904 | 50904 | 100% | 0 | 0 | 0 | 4500 | -682 | 3817.8 | 0.2 | 0 | Completed in 2008. |  | 2008 |  | Investment
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | PAK | ARS | 56 | INV | 71 | N | I | CFC | 83.8 | 83.8 | 0 | 0 | 2008-11-01 | 2011-03-01 | 2011-11-01 | 2016-01-01 |  |  | 449996 | 0 | 449996 | 128440 | 28.54% | 321556 | 0 | 128622.4 | 33750 | 0 | 9633.0856 | 24116.9144 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, GSK progressed with project activities and by early 2015, they are expected to get Govt. approval on their new products. The final verification will be undertaken in early 2015 and the project will be completed. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in January 2010. Missions undertaken (actual/planned): 1 missionplanned and undertaken. TOR for consultants/subcontracts completed (actual/planned):1 planned and 1 completed. Contract/PO/MOA agreements signed:1 MOA signed. First disbursement date (actual/planned):The first disbursement took place in March 2011. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delays relating to enterprise and tech transfer. | Project is expected to be completed by Q4 of 2015. Verificaiton of completion of conversion at the beneficiary is expected to be completed by then. | 2008 |  | Investment |  | Continued Monitoring
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | PAK | SEV | 14 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 2001-12-01 | 2003-05-01 | 259000 | -4042 | 254958 | 254958 | 100% | 0 | 0 | 0 | 33670 | -525 | 33144.54 | 0.46 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | PAK | SEV | 35 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2004-01-01 |  | 2004-01-01 | 2007-06-01 | 172666 | -102 | 172564 | 172564 | 100% | 0 | 0 | 0 | 22447 | -13 | 22433.3237 | 0.6763 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project: phase 3 | Individual | ASP | PAK | SEV | 41 | INS | 54 | N | I | No_ODP | 18.6 | 18.6 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-11-01 | 224467 | -2476 | 221991 | 221991 | 100% | 0 | 0 | 0 | 16835 | -186 | 16649.3003 | -0.3003 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | PAK | SEV | 51 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-03-01 | 2009-04-01 |  | 2008-09-01 | 2011-12-01 | 112233 | 0 | 112233 | 112233 | 100% | 0 | 0 | 0 | 8418 | 0 | 8417.5 | 0.5 | 0 | Completed in 2008. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV, second year) | Individual | ASP | PAK | SEV | 53 | INS | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-10-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 112234 | -17571 | 94663 | 94663 | 100% | 0 | 0 | 0 | 8418 | -1318 | 7100.1046 | -0.1046 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | PAK | SEV | 57 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2011-03-01 |  | 2011-06-01 | 2013-03-01 | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 16835 | 0 | 16835 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | PAK | SEV | 62 | INS | 81 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2013-03-01 |  | 2013-04-01 | 2013-12-01 | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 16835 | 0 | 16835 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | ASP | PAK | SEV | 68 | INS | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-03-01 | 2016-01-01 |  |  | 224467 | 0 | 224467 | 141115 | 62.87% | 83352 | 0 | 33340.796 | 15713 | 0 | 9878.2456 | 5834.7544 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, IS project primarily focused on monitoring ODS consumption in country and managing ongoing implementation of CFC MDI phase-out project and HPMP. Ozone Day celebrations were also undertaken during the year 2014. The Government continued to closely monitor licensing system and import controls of ODSs particularly HCFCs and CFCs for MDI manufacturing. NOU also participated in regional network meetings and global meetings relating to Montreal Protocol. CP progress report and Article 7 data report for 2013 were submitted by NOU. IS-VIII has been submitted and approved at the 73rd ExCom. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in May 2013. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in May 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The IS Phase-VII has been operationallly completed in March 2015. The IS activities continue under the IS Phase-VIII. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 4/2015-3/2017) | Individual | ASP | PAK | SEV | 73 | INS | 91 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2017-03-01 | 2017-03-01 |  |  | 224467 | 0 | 224467 | 0 | 0% | 224467 | 0 | 89786.8 | 15713 | 0 | 0 | 15713 | 0 | Newly Approved | The activities have been initiated in April 2015 and the implementation is going as planned. The first disbursement has been made in X 2015. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2014 |  | Non-Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible and rigid polyurethane foam at Plastifoam, S.A., Profomsa, and Thermofoam, S.A. | Individual | LAC | PAN | FOA | 13 | INV | 05 | A | I | CFC | 26 | 26 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1999-08-01 | 2002-10-01 | 155000 | -13140 | 141860 | 141860 | 100% | 0 | 0 | 0 | 20150 | -1708 | 18441.8 | 0.2 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAN | FOA | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2637 | 12363 | 12363 | 100% | 0 | 0 | 0 | 1950 | -343 | 1607.19 | -0.19 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at Productos Moldeados America S.R. Ltda. (Plasticos Modernos) | Individual | LAC | PAN | FOA | 22 | INV | 09 | A | I | CFC | 16.2 | 16 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2003-11-01 | 339296 | -213326 | 125970 | 125970 | 100% | 0 | 0 | 0 | 44108 | -27732 | 16376.1 | -0.1 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAN | FOA | 57 | PRP | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 |  | 2013-12-01 | 2014-02-01 | 50000 | -48000 | 2000 | 2000 | 100% | 0 | 0 | 0 | 3750 | -3600 | 150 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Remaining funds have been returned to MLF. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | PAN | FOA | 72 | PRP | 37 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 5600 | 0 | 0 | 5600 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the milestone of setting up the administrative arrangements was achieved, the implementing team was set up and an action plan was discussed with the national counterparts. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):First payment will be made at the beginning of 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | International consultants were hired, NOU started collecting information on actual HCFC consumption and applications. Initial findings were shared with international consultant to conduct analysis on possible alternatives and approaches. |  |  | Non-Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | INV | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-04-01 | 2005-12-01 |  | 2008-12-01 | 2013-01-01 | 250152 | 0 | 250152 | 250152 | 100% | 0 | 0 | 0 | 18762 | 0 | 18762 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-Year | LAC | PAN | PHA | 47 | INV | 24 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-01-01 | 238000 | 0 | 238000 | 238000 | 100% | 0 | 0 | 0 | 17850 | 0 | 17850 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-Year | LAC | PAN | PHA | 50 | INV | 26 | N | I | CFC | 66 | 66 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2010-08-01 | 2013-01-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PAN | PHA | 55 | PRP | 28 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 | 2013-11-01 | 150000 | -6455 | 143545 | 143545 | 100% | 0 | 0 | 0 | 11250 | -484 | 10765.799 | 0.201 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 65th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (fourth and fifth tranches) | Multi-Year | LAC | PAN | PHA | 56 | INV | 29 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-11-01 | 2010-02-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 255000 | -439 | 254561 | 254561 | 100% | 0 | 0 | 0 | 19125 | -33 | 19092.075 | -0.07505 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | LAC | PAN | PHA | 65 | INV | 32 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2016-10-01 |  | 2013-12-01 | 2014-09-01 | 132773 | 0 | 132773 | 132773 | 100% | 0 | 0 | 0 | 9958 | 0 | 9958 | 0 | 0 | Financially completed in 2014. | 2014 workplan and budget prepared and approved. HCFC quotas for 2014 established. 1 train-the-trainers workshop conducted. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | PAN | PHA | 70 | INV | 34 | N | I | HCFC | 1.8 | 0.4 | 0 | 0 | 2013-07-01 | 2014-07-01 | 2015-07-01 | 2015-11-01 |  |  | 100907 | 0 | 100907 | 70233 | 69.6% | 30674 | 0 | 12269.424 | 7568 | 0 | 5267.4906 | 2300.5094 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, planned activities were related to training on good refrigeration practices, which was achieved. Quota system is working properly and quota for 2014 set. Verification report was conducted, showing that the country is complying with its reduction commitments. Purchasing of Nitrogen tools and filters for phasing out HCFC-141b in flushing was carried out. Inventory of refrigeration equipment in local hospital was completed. All planned milesones in 2014 were achieved. Prodoc signed (actual/planned, yes/no and date):Yes, it was signed before 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in December 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Second tranche implementation report and third tranche request were prepared and submitted. Implementation of 2015 workplan is underway, 2 workshops on good refrigeration practices were conducted; meetings with customs authorities, HCFC importerts and users have been carried out. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | PAN | PHA | 72 | PRP | 38 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4200 | 0 | 0 | 4200 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the milestone of setting up the administrative arrangements was achieved, the implementing team was set up and an action plan was discussed with the national counterparts. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):First payment will be made at the begining of 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | TORs for national consultant were prepared and published. National consultant was hired and started with collecting information on actual HCFC consumption and applications. Stakeholders workshop held. |  |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PAN | REF | 18 | TAS | 06 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-07-01 | 2003-11-01 | 172465 | -10608 | 161857 | 161857 | 100% | 0 | 0 | 0 | 22420 | -1379 | 21041.41 | -0.41 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Project preparation for update of refrigerant management plan (investment components) | Individual | LAC | PAN | REF | 40 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 11 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
ONG | UNDP | Extension of institutional strengthening project (phase VI: 12/2013-11/2015) | Individual | LAC | PAN | SEV | 71 | INS | 36 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-11-01 | 2016-02-01 |  |  | 149500 | 0 | 149500 | 22889 | 15.31% | 126611 | 0 | 50644.496 | 10465 | 0 | 1602.2132 | 8862.7868 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were carried out and all planned activities were conducted. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. NOU participated actively in all regional meetings. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in May 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in August 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. NOU participated in fair specialized in refrigeration to increase awareness of local and regional stakeholders on Montreal Protocol goals and Ozone layer issues. 1 follow up mission conducted. | 2013 |  | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAR | FOA | 22 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of polyurethane foam at Superspuma Del Paraguay SAIC, Suenolar, La Asuncena, and Industrias Cel | Individual | LAC | PAR | FOA | 23 | INV | 04 | A | I | CFC | 55.5 | 55.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-10-01 | 405600 | -118208 | 287392 | 287392 | 100% | 0 | 0 | 0 | 52728 | -15367 | 37361.22 | -0.22 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAR | FOA | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 | 2017-01-01 |  |  | 60000 | 0 | 60000 | 16970 | 28.28% | 43030 | 0 | 43030 | 4500 | 0 | 1272.75 | 3227.25 | 0 | Remarks (Short narrative description of progress made (actual/planned)):No planned activities in 2014 as we are waiting for low GWP alternatives to be available for SMEs. Thus, all planned milestones were achieved in 2014. Prodoc signed (actual/planned, yes/no and date):No. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):The first disbursement took place in July 2009. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The country is waiting for alternatives to HCFC-141b that are suitable for SMEs. UNDP has put in contact NOU with experts to analyze possible options. It is expected that during 2015 a strategy will be prepared. | 2015 workplan prepared, discussed and approved by national authorities. National consultant hired. Information on HCFC consumption on the foam sector was gathered and analyzed. 1 mission from the international expert was conducted to review collected information and discussed alternatives technologies with stakeholders. | 2009 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | PAR | PHA | 47 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -2720 | 27280 | 27280 | 100% | 0 | 0 | 0 | 2250 | -204 | 2045.9999 | 5.0001e-05 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | INV | 17 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2010-12-01 |  | 2009-12-01 | 2013-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | PAR | PHA | 57 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2012-05-01 | 2014-03-01 | 65000 | -14983 | 50017 | 50017 | 100% | 0 | 0 | 0 | 4875 | -1124 | 3751.27 | -0.27 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | INV | 23 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2011-07-01 |  | 2011-07-01 | 2013-07-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 14250 | 0 | 14250 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-year | LAC | PAR | PHA | 60 | INV | 26 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 2010-04-01 | 2011-12-01 | 2011-04-01 |  | 2012-12-01 | 2014-12-01 | 21000 | -5 | 20995 | 20995 | 100% | 0 | 0 | 0 | 1575 | 0 | 1574.62 | 0.38 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | INV | 29 | N | I | HCFC | 0.9 | 0.1 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2015-05-01 |  |  | 168500 | 0 | 168500 | 113056 | 67.1% | 55444 | 0 | 22177.748 | 12638 | 0 | 8479.5077 | 4158.4923 | 0 | Remarks (Short narrative description of progress made (actual/planned)):NOU was reconfigured in 2013 with good results, which led to improving the implementation of the project. In 2014, the milestones related to training on good refrigeration practices were achieved amd certification framework was strengthened. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in February 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in April 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | 1st tranche implementation report and 2nd tranche request prepared, submitted and approved. 1 workshop on good refrigeration practices and alternatives to HCFC was prepared and conducted by international expert. | 2011 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | LAC | PAR | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-10-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recyling of CFC-12 refrigerant | RMP-Component | LAC | PAR | REF | 32 | TAS | 08 | A | I | CFC | 96.3 | 96.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2004-12-01 | 2005-11-01 | 285158 | -8351 | 276807 | 276807 | 100% | 0 | 0 | 0 | 37071 | -1086 | 35984.8966 | 0.10344 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | PAR | REF | 33 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal umbrella project to phase out CFC-11 and CFC-12 consumption in the manufacture of commercial refrigeration equipment by replacement with HCFC-141b and HFC-134a at 11 SMEs | Individual | LAC | PAR | REF | 34 | INV | 12 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2005-02-01 |  | 2005-12-01 | 2007-03-01 | 410379 | -27448 | 382931 | 382931 | 100% | 0 | 0 | 0 | 53349 | -3568 | 49781.0481 | -0.0481 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | PAR | SOL | 45 | TAS | 14 | N | I | TCA/CTC | 2.4 | 2.4 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 30000 | -107 | 29893 | 29893 | 100% | 0 | 0 | 0 | 2700 | -10 | 2690.37 | -0.37 | 0 | Financially completed in 2012. |  | 2005 | 2008-01-01 | Non-Investment
FIN | UNDP | Elimination of CFC-12 in the production of polystyrene foam at Productos Moldeados America SR, Ltd. (Promola) | Individual | LAC | PER | FOA | 17 | INV | 09 | A | D | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1998-11-01 | 1999-12-01 | 294960 | 0 | 294960 | 294960 | 100% | 0 | 0 | 0 | 38345 | 0 | 38344.8 | 0.2 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Preparation of a project in general foam subsector | Individual | LAC | PER | FOA | 27 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | PER | FOA | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Foam sector ODS phaseout plan (covering 5 enterprises: Molflex; Zetaflex; EMSA; Metusa; Polishoes) | Individual | LAC | PER | FOA | 35 | INV | 30 | A | I | CFC | 33.8 | 33.8 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2006-12-01 | 2008-04-01 | 325277 | 0 | 325277 | 325277 | 100% | 0 | 0 | 0 | 42286 | 0 | 42286.01 | -0.01 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PER | FOA | 57 | PRP | 43 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2013-08-01 | 2014-02-01 | 80000 | -26166 | 53834 | 53834 | 100% | 0 | 0 | 0 | 6000 | -1962 | 4037.55 | 0.45 | 0 | Financially completed in 2014. | Completed in 2013. Funds returned to the ExCom | 2009 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | LAC | PER | FUM | 24 | PRP | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2000-06-01 | 2002-12-01 | 25000 | -863 | 24137 | 24137 | 100% | 0 | 0 | 0 | 3250 | -112 | 3137.81 | 0.19 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of methyl bromide in soil fumigation | One-off-Phaseout | LAC | PER | FUM | 31 | INV | 28 | N | I | MeBr | 4 | 4 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-11-01 | 209770 | 0 | 209770 | 209770 | 100% | 0 | 0 | 0 | 27270 | 0 | 27270.1 | -0.1 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | PER | PHA | 50 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-12-01 | 2010-01-01 | 15000 | -2400 | 12600 | 12600 | 100% | 0 | 0 | 0 | 1125 | -180 | 945 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
TRF | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | PER | PHA | 55 | INV | 41 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-01 |  |  | 2011-07-01 | 183500 | -183500 | 0 | 0 |  | 0 | 0 | 0 | 13763 | -13763 | 0 | 0 | 0 | TPMP transferred to UNIDO. | TPMP transferred to UNIDO. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PER | PHA | 55 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2012-12-01 | 2014-03-01 | 150000 | -28052 | 121948 | 121948 | 100% | 0 | 0 | 0 | 11250 | -2104 | 9146 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Expert mission to take place in April 2013 to discuss pending approval of quota system for HCFCs. UNDP prodoc has been prepared. | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2016-04-01 |  |  | 108000 | 0 | 108000 | 0 | 0% | 108000 | 0 | 43200 | 9720 | 0 | 0 | 9720 | 0 | Remarks (Short narrative description of progress made (actual/planned)):By Dec 2014, theProDoc has been approved by all stakeholders and is now waiting signature of the Government. The RAC expert has assessed the needs and is finalizing procurement plan and TORs. Prodoc signed (actual/planned, yes/no and date):No, the prodoc hasn't been signed yet. It is planned for April 2015. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 3. Contract/PO/MOA agreements signed:0 of 3. First disbursement date (actual/planned):The first disbursement planned for in April 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delay in signing the Project Document by the Government of Peru. One mission took place and constant conference calls were held to clarify missing points. | Since 2014, the ProDoc was signed and local implementation team is under final stages of recruitment. Plan for estabilshment of HCFC-141b alternative flushing training center is being assessed by the GOV. | 2012 |  | Investment |  | To request the submission of additional status report to the 75th meeting to monitor the signing of the project document/letter of agreement and low disbursement rates of approved funds.
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Alfa S.A. | Individual | LAC | PER | REF | 15 | INV | 03 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-09-01 | 2000-12-01 | 252727 | -567 | 252160 | 252160 | 100% | 0 | 0 | 0 | 32855 | -74 | 32780.8 | 0.2 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Andina Industrial S.A. | Individual | LAC | PER | REF | 15 | INV | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  |  | 2002-06-01 | 229816 | -75350 | 154466 | 154466 | 100% | 0 | 0 | 0 | 29876 | -9795 | 20081.08 | -0.08 | 0 | Canceled in 2000. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coldex S.A. | Individual | LAC | PER | REF | 15 | INV | 05 | A | I | CFC | 67.4 | 67.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1998-01-01 | 2000-12-01 | 748966 | -102197 | 646769 | 646769 | 100% | 0 | 0 | 0 | 97366 | -13286 | 84079.97 | 0.03 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Lenche S.A. (Inlensa) | Individual | LAC | PER | REF | 15 | INV | 06 | A | I | CFC | 6 | 6 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 2002-09-01 | 2003-11-01 | 201443 | -29670 | 171773 | 171773 | 100% | 0 | 0 | 0 | 26188 | -3857 | 22330.49 | 0.51 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Reunidas S.A. (Inresa) | Individual | LAC | PER | REF | 15 | INV | 07 | A | D | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  |  | 2003-01-01 | 267641 | -91077 | 176564 | 176564 | 100% | 0 | 0 | 0 | 34793 | -11840 | 22953.33 | -0.33 | 0 | Canceled in 1999. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrial Selva S.A. (Indusel) | Individual | LAC | PER | REF | 15 | INV | 08 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2002-03-01 | 412098 | -331 | 411767 | 411767 | 100% | 0 | 0 | 0 | 53573 | -43 | 53529.71 | 0.29 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Master Service, S.A. | Individual | LAC | PER | REF | 19 | INV | 13 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-02-01 | 2002-04-01 | 140000 | -10839 | 129161 | 129161 | 100% | 0 | 0 | 0 | 18200 | -1409 | 16790.93 | 0.07 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest feezers at Compañia Peruana de Máquinas para Coser S.A. (Copemaco) | Individual | LAC | PER | REF | 19 | INV | 14 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 193834 | 0 | 193834 | 193834 | 100% | 0 | 0 | 0 | 25198 | 0 | 25198.42 | -0.42 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers and refrigerators at Formetal | Individual | LAC | PER | REF | 19 | INV | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  |  | 2001-12-01 | 118000 | -64335 | 53665 | 53665 | 100% | 0 | 0 | 0 | 15340 | -8364 | 6976.45 | -0.45 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Col-Frio S.A. | Individual | LAC | PER | REF | 19 | INV | 16 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 175000 | -468 | 174532 | 174532 | 100% | 0 | 0 | 0 | 22750 | -61 | 22689.1412 | -0.1412 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PER | REF | 19 | TAS | 17 | A | I | CFC | 28.6 | 28.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 2001-12-01 | 2003-04-01 | 342695 | -53108 | 289587 | 289587 | 100% | 0 | 0 | 0 | 44550 | -6904 | 37646.31 | -0.31 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | LAC | PER | REF | 39 | PRP | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP update: technical assistance for the refrigeration sector | RMP-Component | LAC | PER | REF | 43 | TAS | 37 | N | I | CFC | 94.9 | 94.9 | 0 | 0 | 2004-07-01 | 2007-02-01 | 2007-12-01 |  | 2009-12-01 | 2011-12-01 | 123000 | -1847 | 121153 | 121153 | 100% | 0 | 0 | 0 | 11070 | -166 | 10903.77 | 0.23 | 0 | Completed in 2009. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 13 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1996-07-01 |  | 1995-09-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 18 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-03-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-use at small manufacturers of flexible foam | Individual | ASP | PHI | FOA | 12 | INV | 26 | N | I | CFC | 35 | 35 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1999-12-01 | 2003-04-01 | 745000 | -262154 | 482846 | 482846 | 100% | 0 | 0 | 0 | 96850 | -34080 | 62769.98 | 0.02 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Phase-out of the residual use of CFC in the manufacture of extruded polystyrene foam sheet in 3 companies: Concept Packaging Co., Amtes Co., and Q.C. Styropackaging Co. | Individual | ASP | PHI | FOA | 12 | INV | 27 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-12-01 | 1995-03-01 |  | 1997-12-01 | 1999-05-01 | 505000 | -230578 | 274422 | 274422 | 100% | 0 | 0 | 0 | 65650 | -29975 | 35674.86 | 0.14 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Nikkon Industrial Corporation | Individual | ASP | PHI | FOA | 12 | INV | 28 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-09-01 | 1998-12-01 | 315000 | -46523 | 268477 | 268477 | 100% | 0 | 0 | 0 | 40950 | -6048 | 34902 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible polyurethane foam at Foamcraft Incorporated | Individual | ASP | PHI | FOA | 13 | INV | 31 | A | I | CFC | 90 | 90 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1998-05-01 | 2001-12-01 | 185000 | -19094 | 165906 | 165906 | 100% | 0 | 0 | 0 | 24050 | -2482 | 21567.78 | 0.22 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of polyurethane insulated building elements at Metal Forming Co. | Individual | ASP | PHI | FOA | 13 | INV | 32 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 305000 | -16698 | 288302 | 288302 | 100% | 0 | 0 | 0 | 39650 | -2171 | 37479.26 | -0.26 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the residual use of CFC in the manufacture of extruded polystyrene foam sheet at Styrotech Co. | Individual | ASP | PHI | FOA | 13 | INV | 34 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 60000 | -2297 | 57703 | 57703 | 100% | 0 | 0 | 0 | 7800 | -299 | 7501.39 | -0.39 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of flexible polyurethane (slabstock) at Mandaue Foam Industries Inc. | Individual | ASP | PHI | FOA | 17 | INV | 37 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-12-01 |  | 1997-06-01 | 2000-07-01 | 217000 | -9332 | 207668 | 207668 | 100% | 0 | 0 | 0 | 28210 | -1213 | 26996.84 | 0.16 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of PUF foam at RGC Foam Group (Polyfoam/Uratex) | Individual | ASP | PHI | FOA | 18 | INV | 62 | A | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1997-05-01 |  | 1997-06-01 | 2000-07-01 | 650000 | -3624 | 646376 | 646376 | 100% | 0 | 0 | 0 | 84500 | -471 | 84029 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of the use of CFCs in the manufacture of PU foam for insulation and structural purposes at Himalaya Mfg. Corp. | Individual | ASP | PHI | FOA | 19 | INV | 43 | A | D | CFC | 17 | 17 | 0 | 0 | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 101000 | -4879 | 96121 | 96121 | 100% | 0 | 0 | 0 | 13130 | -634 | 12496 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at PU Rigid Insulation Contractor | Individual | ASP | PHI | FOA | 22 | INV | 48 | N | I | CFC | 24.2 | 24.2 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1999-06-01 |  | 1999-12-01 | 2003-11-01 | 189290 | -14221 | 175069 | 175069 | 100% | 0 | 0 | 0 | 24608 | -1849 | 22758.97 | 0.03 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at MBA Urethane Products Contractor | Individual | ASP | PHI | FOA | 22 | INV | 50 | N | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 1999-12-01 | 2003-08-01 | 113574 | -22017 | 91557 | 91557 | 100% | 0 | 0 | 0 | 14765 | -2862 | 11902.41 | 0.59 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Soutech | Individual | ASP | PHI | FOA | 23 | INV | 51 | N | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 1999-12-01 | 2003-04-01 | 326750 | -1799 | 324951 | 324951 | 100% | 0 | 0 | 0 | 42478 | -234 | 42243.63 | 0.37 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Umbrella project: Conversion to CFC-free technology in small CFC consuming enterprises using CFC in the manufacture of rigid polyurethane foam (Ashlar Industrial Corporation, Alen International, Zegal | Individual | ASP | PHI | FOA | 23 | INV | 52 | N | I | CFC | 5.1 | 5.1 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 39930 | -13985 | 25945 | 25945 | 100% | 0 | 0 | 0 | 5191 | -1818 | 3372.85 | 0.15 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | ASP | PHI | FOA | 30 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 15000 | -3091 | 11909 | 11909 | 100% | 0 | 0 | 0 | 1950 | -401 | 1548.534 | 0.46598 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture or rigid polyurethane foam (sprayfoam) at Prescon Construction and Development | Individual | ASP | PHI | FOA | 31 | INV | 64 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-10-01 |  | 2002-09-01 | 2005-04-01 | 187926 | -25246 | 162680 | 162680 | 100% | 0 | 0 | 0 | 24430 | -3282 | 21148.38 | -0.38 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | ASP | PHI | FUM | 25 | PRP | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 1999-08-01 |  | 2000-12-01 | 2004-12-01 | 30000 | -358 | 29642 | 29642 | 100% | 0 | 0 | 0 | 3900 | -47 | 3853.46 | -0.46 | 0 | Completed in 2000. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Demonstration, training and policy development on alternatives to methyl bromide for banana soil fumigation | Individual | ASP | PHI | FUM | 26 | DEM | 57 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-07-01 | 2003-07-01 | 231000 | -214534 | 16466 | 16466 | 100% | 0 | 0 | 0 | 30030 | -27889 | 2141 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Umbrella project for the conversion of production of portable halon fire extinguishers of members companies of Fire Protectors Federation Inc. | Individual | ASP | PHI | HAL | 18 | INV | 38 | N | I | Halon | 77 | 77 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 2000-09-01 | 2003-04-01 | 114108 | -8935 | 105173 | 105173 | 100% | 0 | 0 | 0 | 14834 | -1162 | 13672.49 | -0.49 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Training programme in the refrigeration sector | RMP-Component | ASP | PHI | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-04-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 64000 | -1707 | 62293 | 62293 | 100% | 0 | 0 | 0 | 8320 | -222 | 8097.61 | 0.39 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Phase out of CFC in the manufacture of commercial refrigerators and ice boxes at Unimagna Philippines, Inc. | Individual | ASP | PHI | REF | 13 | INV | 33 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 1015700 | -54324 | 961376 | 961376 | 100% | 0 | 0 | 0 | 132041 | -7062 | 124979 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Matsushita Electric Philippines Corporation (Mepco) | Individual | ASP | PHI | REF | 18 | INV | 39 | A | R | CFC | 47 | 47 | 0 | 0 | 1995-11-01 | 1996-06-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 112244 | -4513 | 107731 | 107731 | 100% | 0 | 0 | 0 | 14592 | -587 | 14005.03 | -0.03 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Umbrella project for conversion from CFC-11 foam blowing agent into HCFC-141b, and CFC-12 and R-502 refrigerants into HFC-134a and HFC-404a at Gomeco, Chee Puck and Well Built | Individual | ASP | PHI | REF | 19 | INV | 44 | N | I | CFC | 28 | 28 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1998-04-01 |  | 2000-09-01 | 2003-04-01 | 156475 | -38769 | 117706 | 117706 | 100% | 0 | 0 | 0 | 20342 | -5040 | 15301.78 | 0.22 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | PHI | REF | 21 | PRP | 47 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 2000-12-01 | 35000 | -4264 | 30736 | 30736 | 100% | 0 | 0 | 0 | 4550 | -554 | 3995.68 | 0.32 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sectors except residential air conditioning) | Individual | ASP | PHI | REF | 59 | PRP | 87 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2010-11-01 |  | 2012-06-01 | 2014-02-01 | 65000 | -50058 | 14942 | 14942 | 100% | 0 | 0 | 0 | 4875 | -3754 | 1121 | 0 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | PHI | SEV | 08 | CPG | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 39820 | 39820 | 79640 | 79640 | 100% | 0 | 0 | 0 | 5177 | 5177 | 10353.2 | 0.8 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-07-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Survey of ODS usage, data base generation and technical assistance for ODS phase-out for small-scale enterprises | Individual | ASP | PHI | SEV | 11 | TAS | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1996-09-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 15 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1994-12-01 | 1995-12-01 |  | 1996-03-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 18 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC-113, 1,1,1 trichloroethane (TCA), CFC-11 and CFC-12 at multiple corporations that manufacture special formulations for various industrial markets | Individual | ASP | PHI | SOL | 19 | INV | 46 | N | I | TCA/CFC | 53.6 | 53.6 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1998-06-01 | 2003-09-01 | 642800 | -181667 | 461133 | 461133 | 100% | 0 | 0 | 0 | 83564 | -23617 | 59947.29 | -0.29 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Project preparation to prepare the second and final phase for phaseout of ODS by solvent blenders | Individual | ASP | PHI | SOL | 24 | PRP | 54 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 1999-11-01 | 25000 | -22120 | 2880 | 2880 | 100% | 0 | 0 | 0 | 3250 | -2876 | 374.4 | -0.4 | 0 | Completed in 1998. Financially completed in 1999. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-113, l,l,l trichloroethane and CFC-12 at multiple corporations that manufacture special formulations for industrial markets (Ariad Industrial Co., Cloisonne, Redisol, Rodler) | Individual | ASP | PHI | SOL | 25 | INV | 56 | A | I | TCA/CFC | 18.4 | 18.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2003-04-01 | 334600 | -93314 | 241286 | 241286 | 100% | 0 | 0 | 0 | 43498 | -12131 | 31367.18 | -0.18 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | PRC | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -11833 | 167 | 167 | 100% | 0 | 0 | 0 | 900 | -887 | 12.525 | 0.475 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | PRC | REF | 20 | TAS | 04 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 1998-10-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 201200 | -13880 | 187320 | 187320 | 100% | 0 | 0 | 0 | 26156 | -1804 | 24351.6 | 0.4 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | AFR | PRC | REF | 34 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-09-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | PRC | REF | 41 | TAS | 11 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2003-12-01 | 2006-07-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 118078 | 0 | 118078 | 118078 | 100% | 0 | 0 | 0 | 10627 | 0 | 10627 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Project preparation assistance in recovery and recycling of refrigerant, foam and halon sectors | Individual | AFR | PRC | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | RWA | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3806 | 8194 | 8194 | 100% | 0 | 0 | 0 | 900 | -285 | 614.55 | 0.45 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | RWA | PHA | 53 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-11-01 | 2009-11-01 |  | 2010-12-01 | 2013-06-01 | 124500 | 0 | 124500 | 124500 | 100% | 0 | 0 | 0 | 11205 | 0 | 11205 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | INV | 17 | N | I | CFC | 4.6 | 4.6 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2012-12-01 | 2013-06-01 | 43500 | -11414 | 32086 | 32086 | 100% | 0 | 0 | 0 | 3915 | -1027 | 2887.74 | 0.26 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Formulation of a refrigerant management plan | Individual | AFR | RWA | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | RWA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: refrigeration manufacturing and centralized recovery and recycling of refrigerants | RMP-Component | AFR | RWA | REF | 41 | TAS | 08 | N | I | CFC | 12.9 | 12.9 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-01-01 | 118758 | -15642 | 103116 | 103116 | 100% | 0 | 0 | 0 | 10688 | -1408 | 9280.249 | -0.249 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2014-02-01 | 45000 | -1050 | 43950 | 43950 | 100% | 0 | 0 | 0 | 4050 | -95 | 3955.5 | -0.5 | 0 | Financially completed in 2014. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2011-03-01 |  | 2013-12-01 | 2014-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 2700 | -2700 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2009 |  | Investment
FIN | UNDP | Project preparation for a halon sectoral phase-out plan | Individual | AFR | SIL | HAL | 45 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2006-12-01 | 2011-11-01 | 16870 | -7908 | 8962 | 8962 | 100% | 0 | 0 | 0 | 1265 | -593 | 672.0172 | -0.017157 | 0 | Completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Technical assistance for awareness raising in the halon sector | Individual | AFR | SIL | HAL | 51 | TAS | 15 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2009-05-01 | 2008-09-01 |  | 2010-12-01 | 2012-05-01 | 15000 | -6 | 14994 | 14994 | 100% | 0 | 0 | 0 | 1350 | -1 | 1349.46 | -0.46 | 0 | Financially completed in 2012. |  | 2007 | 2010-01-01 | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | SIL | PHA | 48 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-12-01 | 2011-11-01 | 12000 | -1361 | 10639 | 10639 | 100% | 0 | 0 | 0 | 900 | -102 | 797.9249 | 0.07505 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | INV | 20 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2010-12-01 | 2013-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | AFR | SIL | PHA | 61 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2011-12-01 | 2013-07-01 | 20000 | -5285 | 14715 | 14715 | 100% | 0 | 0 | 0 | 1800 | -476 | 1324.35 | -0.35 | 0 | Financially completed in 2013. | Completed in 2011. Additional equipment has been distributed to the centres of excellence; the Kenema Polytechnic and the Magburuka Polytechnic (FEB 2012). Refresher trainings were also conducted for the Refrigerator Engineer Association on good refriger | 2010 |  | Investment
FIN | UNDP | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector, and recovery and recycling project | RMP-Component | AFR | SIL | REF | 41 | TAS | 05 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-02-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 8316 | 0 | 8316 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | SIL | REF | 41 | TAS | 06 | N | I | CFC | 16.4 | 16.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2008-12-01 |  | 2010-12-01 | 2013-02-01 | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 9662 | 0 | 9661.5 | 0.5 | 0 | Financially completed in 2013. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: MAC recovery/recycling of CFC-12 | RMP-Component | AFR | SIL | REF | 41 | TAS | 07 | N | I | CFC | 9.4 | 9.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2006-12-01 |  | 2010-12-01 | 2013-02-01 | 61858 | -18405 | 43453 | 43453 | 100% | 0 | 0 | 0 | 5567 | -1656 | 3910.77 | 0.23 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Formulation of refrigerant management plan | Individual | AFR | SOM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2005-11-01 | 2005-12-01 | 15000 | -14659 | 341 | 341 | 100% | 0 | 0 | 0 | 1950 | -1906 | 44 | 0 | 0 | Completed in 2005. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at International Cosmetic Ltd. (ICL) | Individual | ASP | SRL | ARS | 18 | INV | 07 | A | I | CFC | 5 | 5 | 0 | 0 | 1995-11-01 | 1997-04-01 | 1996-11-01 |  | 2001-08-01 | 2003-11-01 | 38968 | -5599 | 33369 | 33369 | 100% | 0 | 0 | 0 | 5066 | -728 | 4337.97 | 0.03 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | Project preparation assistance for the methyl bromide sector | Individual | ASP | SRL | FUM | 25 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-06-01 | 2004-12-01 | 25000 | -1090 | 23910 | 23910 | 100% | 0 | 0 | 0 | 3250 | -142 | 3107.91 | 0.09 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for eradication of tea nematodes in Sri Lanka | Individual | ASP | SRL | FUM | 27 | DEM | 13 | A | I | MeBr | 3.9 | 3.9 | 0 | 0 | 1999-03-01 | 2000-07-01 | 2001-04-01 |  | 2007-10-01 | 2012-06-01 | 310200 | -7844 | 302356 | 302356 | 100% | 0 | 0 | 0 | 40326 | -1020 | 39306.28 | -0.28 | 0 | Financially completed in 2012. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the fumigant sector | Individual | ASP | SRL | FUM | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2002-11-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777.06 | -0.06 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | One-off-Phaseout | ASP | SRL | FUM | 38 | TAS | 21 | N | I | MeBr | 3.3 | 3.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-11-01 |  | 2007-10-01 | 2010-06-01 | 130000 | -2 | 129998 | 129998 | 100% | 0 | 0 | 0 | 16900 | 0 | 16899.74 | 0.26 | 0 | Financially completed in 2010. |  | 2002 | 2005-11-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam and solvent sectors) | Individual | ASP | SRL | MUS | 57 | PRP | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-06-01 | 2013-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 3000 | -3000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | SRL | PHA | 55 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-06-01 | 112250 | -5029 | 107221 | 107221 | 100% | 0 | 0 | 0 | 8419 | -377 | 8041.5638 | 0.4362 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | INV | 40 | N | I | HCFC | 0.4 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 | 2015-12-01 |  |  | 180000 | 0 | 180000 | 156372 | 86.87% | 23628 | 0 | 9451.392 | 13500 | 0 | 11727.864 | 1772.136 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, HPMP activities were progressing satisfactorily. Regnis completed conversion and Metechno is expected to complete conversion by middle of 2015. Activities were undertaken to engage private sector on HPMP activities relating to introduction of low GWP technologies in air-conditioning sector. R&R equipment were distributed to users and the usage levels are being monitored. Prodoc signed (actual/planned, yes/no and date):Plannned in July 2011 and actual in November 2011. Missions undertaken (actual/planned):2 missions plannned and undertalen. TOR for consultants/subcontracts completed (actual/planned):1 planned and completed. Contract/PO/MOA agreements signed:1 MOA signed and completed. First disbursement date (actual/planned):The first disbursement took place in December 2011. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Actvities planned have been completed. Monitoring of the use of Recovery and Reclamation equipment which was distributed late 2014 has been continued. The operation mechanism of Recovery and Reclamation is being discussed and finalized with the stakeholders. The reclamation centre is expected to be operational in late 2015. | 2010 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | SRL | PHA | 70 | INV | 44 | N | I | HCFC | 0.4 | 0 | 0 | 0 | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 4500 | 0 | 0 | 4500 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, HPMP activities were progressing satisfactorily. Regnis completed conversion and Metechno is expected to complete conversion by middle of 2015. Activities were undertaken to engage private sector on HPMP activities relating to introduction of low GWP technologies in air-conditioning sector. R&R equipment were distributed to users and the usage levels are being monitored. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in March 2014. Missions undertaken (actual/planned):2 missions plannned and undertalen. TOR for consultants/subcontracts completed (actual/planned):1 planned and completed. Contract/PO/MOA agreements signed:1 MOA signed and completed. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | Monitoring of the use of Recovery and Reclamation equipment which was distributed late 2014 has been continued. The operation mechanism of Recovery and Reclamation is being discussed and finalized with the stakeholders. The reclamation centre is expected to be operational in late 2015. | 2013 |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | SRL | PHA | 71 | TAS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-05-01 | 2016-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2700 | 0 | 0 | 2700 | 0 | Remarks (Short narrative description of progress made (actual/planned)):No activities in 2014. Not initiated as there is no tranche in 2014 Prodoc signed (actual/planned, yes/no and date):Planned to be signed in August 2015. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):N/A. If Yes, reasons for delay & action plan to resolve:N/A. | The funding for verificaiton report of HPMP Stage-I, to be submitted to the 77th ExCom. The activity will be initiatied in late-2015. | 2013 |  | Non-Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Associated Electrical Corporation (AEC) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 04 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1998-08-01 | 2000-12-01 | 250114 | -912 | 249202 | 249202 | 100% | 0 | 0 | 0 | 32515 | -119 | 32396.26 | -0.26 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Glacio Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 05 | A | I | CFC | 6.8 | 6.8 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 239500 | -26843 | 212657 | 212657 | 100% | 0 | 0 | 0 | 31135 | -3490 | 27645.13 | -0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Regnis (Lanka) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 06 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 284324 | -18407 | 265917 | 265917 | 100% | 0 | 0 | 0 | 36962 | -2393 | 34569.12 | -0.12 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | ASP | SRL | REF | 20 | TAS | 08 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1999-12-01 | 2001-12-01 | 352400 | -1472 | 350928 | 350928 | 100% | 0 | 0 | 0 | 45812 | -191 | 45620.5477 | 0.4523 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
COM | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration | RMP-Component | ASP | SRL | REF | 32 | TAS | 15 | N | I | CFC | 5 | 5 | 0 | 0 | 2000-12-01 | 2002-04-01 | 2006-01-01 |  | 2014-12-01 |  | 250000 | 0 | 250000 | 241823 | 96.73% | 8177 | 0 | 6541.32 | 32500 | 0 | 31437.0355 | 1062.9645 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The procurement of equipment for HPMP implementation was completed in mid-2014. Thus the project is being financially closed by July 2015. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in February 2001. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in April 2002. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | In Q1-2014, activities under implementation are being monitored. Project to be closed in 2014. | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities included in the RMP | RMP-Component | ASP | SRL | REF | 32 | TAS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2008-12-01 | 2010-06-01 | 15455 | -2286 | 13169 | 13169 | 100% | 0 | 0 | 0 | 2009 | -297 | 1711.9922 | 0.0078006 | 0 | Financially completed in 2010. |  | 2000 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sector) | Individual | ASP | SRL | REF | 61 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2012-05-01 | 2013-12-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 4500 | -4500 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | SRL | SEV | 06 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-09-01 |  | 1994-03-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | SRL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1997-03-01 |  | 1997-10-01 | 2003-09-01 | 154680 | 0 | 154680 | 154680 | 100% | 0 | 0 | 0 | 20108 | 0 | 20108.4 | -0.4 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | SRL | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-06-01 |  | 1996-06-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | SRL | SEV | 23 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-11-01 | 1999-12-01 |  | 1999-12-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13405.6 | 0.4 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase III) | Individual | ASP | SRL | SEV | 29 | INS | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2002-02-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 4) | Individual | ASP | SRL | SEV | 37 | INS | 20 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-08-01 | 2010-06-01 | 134056 | -2678 | 131378 | 131378 | 100% | 0 | 0 | 0 | 17427 | -348 | 17079.1456 | -0.1456 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | SRL | SEV | 43 | INS | 22 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-12-01 | 2008-10-01 | 134056 | -14 | 134042 | 134042 | 100% | 0 | 0 | 0 | 10054 | -1 | 10052.95 | 0.05 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SRL | SEV | 45 | TAS | 30 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 36697 | -5478 | 31219 | 31219 | 100% | 0 | 0 | 0 | 3303 | -493 | 2809.9397 | 0.0603 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | SRL | SEV | 50 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2008-11-01 | 2011-01-01 | 134056 | -1295 | 132761 | 132761 | 100% | 0 | 0 | 0 | 10054 | -97 | 9956.8769 | 0.1231 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | SRL | SEV | 55 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-11-01 | 134056 | -14374 | 119682 | 119682 | 100% | 0 | 0 | 0 | 10054 | -1078 | 8975.9714 | 0.0286 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | SRL | SEV | 61 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-12-01 |  | 2012-12-01 | 2013-07-01 | 134056 | -456 | 133600 | 133600 | 100% | 0 | 0 | 0 | 10054 | -34 | 10019.8007 | 0.19932 | 0 | Financially completed in 2013. | Completed in 2012. Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | SRL | SEV | 67 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-06-01 | 2014-12-01 |  | 2014-12-01 |  | 134056 | 0 | 134056 | 132949 | 99.17% | 1107 | 0 | 885.28 | 9384 | 0 | 9306.5373 | 77.4627 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. During the year 2014, IS project primarily focused on monitoring ODS consumption in country and implementation of HPMP. Ozone Day celebrations were also undertaken during the year 2014. The Government continued to closely monitor licensing system and import controls of HCFCs and other ODSs. NOU also participated in regional network meetings and global meetings relating to Montreal Protocol. CP progress report and Article 7 data report for 2013 were submitted by NOU. IS-X has been submitted and approved at the 72nd ExCom. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in February 2013. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in June 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | In Q1-2014, payments under performance based payment mechanism for Regnis was released. Other activities are being monitored. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | ASP | SRL | SEV | 72 | INS | 46 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-12-01 | 2017-01-01 |  |  | 134056 | 0 | 134056 | 0 | 0% | 134056 | 0 | 53622.4 | 9384 | 0 | 0 | 9384 | 0 | Remarks (Short narrative description of progress made (actual/planned)):During the year 2014, IS project primarily focused on monitoring ODS consumption in country and implementation of HPMP. Ozone Day celebrations were also undertaken during the year 2014. The Government continued to closely monitor licensing system and import controls of HCFCs and other ODSs. NOU also participated in regional network meetings and global meetings relating to Montreal Protocol. CP progress report and Article 7 data report for 2013 were submitted by NOU. Prodoc signed (actual/planned, yes/no and date):Planned in October 2014 and signed in December 2014. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):Planned by June 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The activities have been implementated as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. |  |  | Non-Investment
FIN | UNDP | Project preparation for one project in the solvent sector | Individual | ASP | SRL | SOL | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2009-11-01 | 2009-12-01 |  | 2009-12-01 | 2013-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
COM | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 |  | 2014-01-01 |  | 55000 | -55000 | 0 | 0 |  | 0 | 0 | 0 | 4950 | -4950 | 0 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. All activities cancelled as per ExCom decision. Funds returned to MLF. Prodoc signed (actual/planned, yes/no and date):N/A. Missions undertaken (actual/planned):N/A. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):N/A. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Multiple delays. All activites were cancelled as per ExCom decision. | NOU team is monitoring the supplier. Equipment is expected to be delivered by April/May 2014 (when financial obligation can be paid). | 2008 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 16 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2017-01-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 16000 | 3600 | 0 | 0 | 3600 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the List of equipment and technical specifications completed. Bid to start in March 2015 so equipment can be purchased and delivered to the company. Prodoc signed (actual/planned, yes/no and date):No, the prodoc hasn't been signed yet. It is planned for March 2015. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:1 of 2. First disbursement date (actual/planned):The first disbursement planned for May 2015. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delay in signing the Project Document by the Government. ProDoc was signed and implementation scheduled adjusted | Since 2014, the List of equipment and technical specifications completed. The prodoc is planned to be signed in August 2015. | 2011 |  | Non-Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | STP | REF | 39 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-06-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | STP | REF | 44 | TAS | 10 | N | I | CFC | 1.8 | 1.8 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 110000 | -3 | 109997 | 109997 | 100% | 0 | 0 | 0 | 9900 | 0 | 9899.73 | 0.27 | 0 | Completed in 2008. |  | 2004 |  | Investment
FIN | UNDP | Terminal phase out management plan for CFCs (first phase) | Multi-Year | LAC | STV | PHA | 47 | INV | 11 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2005-11-01 | 2007-08-01 | 2006-12-01 |  | 2008-12-01 | 2013-03-01 | 101000 | 0 | 101000 | 101000 | 100% | 0 | 0 | 0 | 9090 | 0 | 9090 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | INV | 15 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2008-11-01 | 2010-11-01 | 2009-11-01 |  | 2012-05-01 | 2014-02-01 | 27000 | -173 | 26827 | 26827 | 100% | 0 | 0 | 0 | 2430 | -16 | 2414.43 | -0.43 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | SUR | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2007-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1125 | -188 | 937.5 | -0.5 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | INV | 16 | N | I | CFC | 6.2 | 6.2 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-06-01 |  | 2011-12-01 | 2013-06-01 | 125000 | -2 | 124998 | 124998 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250.0333 | -0.033301 | 0 | Financially completed in 2013. | Remaining invoices have been paid. | 2008 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | SUR | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | LAC | SUR | REF | 42 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the MAC and refrigeration service sectors | RMP-Component | LAC | SUR | REF | 44 | TAS | 09 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2007-06-01 |  | 2011-12-01 | 2013-02-01 | 300430 | -573 | 299857 | 299857 | 100% | 0 | 0 | 0 | 22532 | -43 | 22489.0255 | -0.0255 | 0 | Financially completed in 2013. | Remaining invoices have been paid. | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities within the RMP | RMP-Component | LAC | SUR | REF | 44 | TAS | 10 | N | I | CFC | 2 | 2 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-06-01 |  | 2011-07-01 | 2013-06-01 | 25750 | -736 | 25014 | 25014 | 100% | 0 | 0 | 0 | 2318 | -66 | 2251.7457 | 0.25429 | 0 | Financially completed in 2013. | Completed in 2011. Monitoring activities are on-going to support the implementation of the RMP update in Suriname. | 2004 |  | Non-Investment
FIN | UNDP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -5091 | 9909 | 9909 | 100% | 0 | 0 | 0 | 1125 | -382 | 743.175 | -0.17495 | 0 | Completed in 2008. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-12-01 | 2013-06-01 | 81500 | 0 | 81500 | 81500 | 100% | 0 | 0 | 0 | 7335 | 0 | 7335 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | INV | 16 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2011-11-01 | 2013-06-01 | 40000 | -7701 | 32299 | 32299 | 100% | 0 | 0 | 0 | 3600 | -693 | 2906.91 | 0.09 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | INV | 19 | N | I | HCFC | 7.7 | 7.7 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-09-01 |  | 2013-11-01 | 2014-03-01 | 667948 | 0 | 667948 | 667920 | 100% | 28 | 0 | 0 | 50096 | 0 | 50093.8625 | 2.1375 | 0 | Financially Completed in 2014. | Completed in 2013. Two final wrap-up steps are planned for 2014: official signature of the HOP to be completeted in Q1, with invitations of stakeholders, including lead HPMP agency (UNEP). Some doors are still manufactured on old door line due to new lin | 2011 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | AFR | SWA | REF | 57 | PRP | 14 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 30000 | -13037 | 16963 | 16963 | 100% | 0 | 0 | 0 | 2250 | -978 | 1272.225 | -0.225 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
CLO | UNDP | Preparation of one project in the flexible foam subsector | Individual | ASP | SYR | FOA | 27 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2004-01-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ammar Industrial Establishment | Individual | ASP | SYR | REF | 26 | INV | 33 | A | I | CFC | 56 | 56 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 331080 | -222 | 330858 | 330858 | 100% | 0 | 0 | 0 | 43040 | -29 | 43011.54 | -0.54 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of domestic and commercial refrigeration equipment and foam sandwich panels at Ahmad Al-Hafez Al-Waha Refrigerator Co. | Individual | ASP | SYR | REF | 26 | INV | 38 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 330486 | 0 | 330486 | 330486 | 100% | 0 | 0 | 0 | 42963 | 0 | 42963.18 | -0.18 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at El-Effendi Refrigerator Plant | Individual | ASP | SYR | REF | 26 | INV | 39 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2007-01-01 | 182802 | -25050 | 157752 | 157752 | 100% | 0 | 0 | 0 | 23764 | -3256 | 20507.7956 | 0.2044 | 0 | Completed in 2003. Financially completed in 2007. |  | 1998 |  | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of three projects in the domestic refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 43 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Ihsan Co. | Individual | ASP | SYR | REF | 28 | INV | 46 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-01-01 | 2003-05-01 | 497250 | -16958 | 480292 | 480292 | 100% | 0 | 0 | 0 | 64643 | -2205 | 62437.96 | 0.04 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigerarion equipment at seven enterprises | Individual | ASP | SYR | REF | 29 | INV | 52 | A | I | CFC | 51.9 | 51.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2003-08-01 | 2005-09-01 | 743419 | -20056 | 723363 | 723363 | 100% | 0 | 0 | 0 | 91776 | -2206 | 89570.02 | -0.02 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 30 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2029.95 | 0.05 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Al-Wattar Home Appliances Co. | Individual | ASP | SYR | REF | 31 | INV | 64 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-05-01 | 2004-01-01 | 235860 | 0 | 235860 | 235860 | 100% | 0 | 0 | 0 | 30662 | 0 | 30661.8 | 0.2 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Assalam Refrigerator Co. | Individual | ASP | SYR | REF | 31 | INV | 65 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 144309 | 0 | 144309 | 144309 | 100% | 0 | 0 | 0 | 18760 | 0 | 18760.17 | -0.17 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alfa Refrigerators Co. | Individual | ASP | SYR | REF | 31 | INV | 66 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-03-01 | 114461 | -2201 | 112260 | 112260 | 100% | 0 | 0 | 0 | 14880 | -286 | 14593.7987 | 0.2013 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Dolphin Refrigerators | Individual | ASP | SYR | REF | 31 | INV | 67 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 113045 | 0 | 113045 | 113045 | 100% | 0 | 0 | 0 | 14696 | 0 | 14695.85 | 0.15 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Raed Refrigeration | Individual | ASP | SYR | REF | 32 | INV | 69 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-09-01 | 2005-11-01 | 211800 | 0 | 211800 | 211800 | 100% | 0 | 0 | 0 | 27534 | 0 | 27534 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Refrigeration House Co. | Individual | ASP | SYR | REF | 34 | INV | 79 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 2001-07-01 | 2002-11-01 | 2004-08-01 |  | 2003-09-01 | 2007-01-01 | 253653 | 0 | 253653 | 253653 | 100% | 0 | 0 | 0 | 32975 | 0 | 32974.89 | 0.11 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Individual | ASP | SYR | REF | 35 | INV | 81 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2001-12-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2006-06-01 | 166323 | -8826 | 157497 | 157497 | 100% | 0 | 0 | 0 | 21622 | -1147 | 20474.99 | 0.01 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | SYR | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-09-01 | 2007-03-01 | 20000 | -6865 | 13135 | 13135 | 100% | 0 | 0 | 0 | 2600 | -892 | 1707.55 | 0.45 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Sector phase out plan for CFCs in the refrigeration manufacturing sector (except domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 86 | A | I | CFC | 246.2 | 246.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-05-01 | 1665188 | -565631 | 1099557 | 1099557 | 100% | 0 | 0 | 0 | 191422 | -65022 | 126399.7819 | 0.2181 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SYR | SEV | 45 | TAS | 90 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616 | 3511.7517 | 0.2483 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Safety and technical assistance programme to manufacturers of aerosol products | Individual | ASP | THA | ARS | 15 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1998-08-01 | 2002-03-01 | 127000 | -20 | 126980 | 126980 | 100% | 0 | 0 | 0 | 16510 | -3 | 16507 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Packserv Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 45 | A | D | CFC | 155 | 155 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 474705 | -1221 | 473484 | 473484 | 100% | 0 | 0 | 0 | 61712 | -159 | 61552.65 | 0.35 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Sanit & Sons Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 46 | A | I | CFC | 194 | 194 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 2000-04-01 | 2002-03-01 | 582100 | 0 | 582100 | 582100 | 100% | 0 | 0 | 0 | 75673 | 0 | 75673 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | P-Tech Manuchem Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 83 | A | I | CFC | 37.3 | 37.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2001-12-01 | 115830 | -8432 | 107398 | 107398 | 100% | 0 | 0 | 0 | 15058 | -1096 | 13961.9 | 0.1 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | J.M.T. Laboratories Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 84 | A | I | CFC | 36.6 | 36.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2003-11-01 | 127920 | -5082 | 122838 | 122838 | 100% | 0 | 0 | 0 | 16630 | -661 | 15968.94 | 0.06 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the aerosol sector | Individual | ASP | THA | ARS | 24 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Standard Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 94 | A | I | CFC | 41 | 41 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 138380 | -5000 | 133380 | 133380 | 100% | 0 | 0 | 0 | 17989 | -650 | 17339.4 | -0.4 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Mary Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 96 | A | I | CFC | 40 | 40 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 136400 | -4295 | 132105 | 132105 | 100% | 0 | 0 | 0 | 17732 | -558 | 17174 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
CLO | UNDP | Elimination of CFC-114 in the manufacture of extruded polystyrene foam sheet and profiles at Thermaflex Insulation Asia Co. Ltd. | Individual | ASP | THA | FOA | 11 | INV | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-07-01 |  |  | 2001-07-01 | 220000 | -220000 | 0 | 0 |  | 0 | 0 | 0 | 28600 | -28600 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 2001. |  | 1993 |  | Investment
FIN | UNDP | Elimination of the use of CFC-12 and CFC-114 in the manufacture of extruded low density polyethylene foam sheet at Mic-Cell Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 27 | A | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-11-01 | 2001-12-01 | 339500 | -1726 | 337774 | 337774 | 100% | 0 | 0 | 0 | 44135 | -224 | 43910.62 | 0.38 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of laminated rigid polyurethane foam insulation panels at Modular Compound Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 29 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1996-12-01 | 2000-12-01 | 508000 | -3349 | 504651 | 504651 | 100% | 0 | 0 | 0 | 66040 | -435 | 65604.63 | 0.37 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at 2 companies (Tahi Poly Seal Material Industries Co. Ltd, and Food Box Co. Ltd.): Phase I | Individual | ASP | THA | FOA | 12 | INV | 30 | A | R | CFC | 100 | 100 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1995-03-01 |  | 1995-02-01 | 2000-12-01 | 455000 | -2639 | 452361 | 452361 | 100% | 0 | 0 | 0 | 59150 | -343 | 58807 | 0 | 0 | Completed in 1995. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of laminated rigid polyurethane foam for insulation panels at Henger Panel | Individual | ASP | THA | FOA | 12 | INV | 31 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-06-01 | 2000-12-01 | 257500 | -509 | 256991 | 256991 | 100% | 0 | 0 | 0 | 33475 | -66 | 33408.83 | 0.17 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible polyurethane foam at Lucky Group | Individual | ASP | THA | FOA | 13 | INV | 35 | A | I | CFC | 187 | 187 | 0 | 0 | 1994-07-01 | 1997-12-01 | 1995-07-01 |  | 1999-11-01 | 2003-07-01 | 605000 | -1836 | 603164 | 603164 | 100% | 0 | 0 | 0 | 78650 | -239 | 78411.32 | -0.32 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at Ponsri | Individual | ASP | THA | FOA | 13 | INV | 36 | A | I | CFC | 125 | 125 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1995-07-01 |  | 1996-06-01 | 2002-03-01 | 340000 | -6035 | 333965 | 333965 | 100% | 0 | 0 | 0 | 44200 | -784 | 43415.74 | 0.26 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF cold cured mouldings, integral skin mouldings and rigid PUF articles at Thai Union PU Co. Ltd. | Individual | ASP | THA | FOA | 15 | INV | 41 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1996-12-01 | 2000-12-01 | 525000 | -72931 | 452069 | 452069 | 100% | 0 | 0 | 0 | 68250 | -9481 | 58768.97 | 0.03 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF slabstock and cold cured mouldings st Somboon Paisarn 85 Company Ltd. | Individual | ASP | THA | FOA | 15 | INV | 42 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-11-01 |  | 1998-11-01 | 2000-12-01 | 225000 | -5000 | 220000 | 220000 | 100% | 0 | 0 | 0 | 29250 | -650 | 28600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of flexible PUF slabstock at Karn Yang Yeen Yong Industry Ltd. | Individual | ASP | THA | FOA | 15 | INV | 44 | A | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-11-01 |  | 1999-04-01 | 2000-12-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 | 0 | 22100 | 0 | 22100 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUF foam for thermoware at Krieng Thavorn Containers Co. Ltd. | Individual | ASP | THA | FOA | 18 | INV | 47 | A | I | CFC | 65 | 65 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 430000 | -32154 | 397846 | 397846 | 100% | 0 | 0 | 0 | 55900 | -4180 | 51719.98 | 0.02 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUR foam for thermoware at Raengwa Standard Industry Co. Ltd. | Individual | ASP | THA | FOA | 19 | INV | 51 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-01-01 | 2000-12-01 | 181500 | -796 | 180704 | 180704 | 100% | 0 | 0 | 0 | 23595 | -103 | 23491.52 | 0.48 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Dacron Trade Co. | Individual | ASP | THA | FOA | 20 | INV | 55 | A | I | CFC | 47.6 | 47.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-11-01 | 2001-12-01 | 277800 | -19551 | 258249 | 258249 | 100% | 0 | 0 | 0 | 36114 | -2542 | 33572.37 | -0.37 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siam Matee | Individual | ASP | THA | FOA | 20 | INV | 56 | A | I | CFC | 33.9 | 33.9 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1998-09-01 |  | 1998-09-01 | 2001-12-01 | 198000 | -13801 | 184199 | 184199 | 100% | 0 | 0 | 0 | 25740 | -1794 | 23945.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid and integral skin polyurethane foam at Bangkok Foam Group | Individual | ASP | THA | FOA | 22 | INV | 63 | A | I | CFC | 90.6 | 90.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2001-12-01 | 480500 | 0 | 480500 | 480500 | 100% | 0 | 0 | 0 | 62465 | 0 | 62465 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Asia Container | Individual | ASP | THA | FOA | 22 | INV | 64 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1999-11-01 | 2000-12-01 | 199000 | 0 | 199000 | 199000 | 100% | 0 | 0 | 0 | 25870 | 0 | 25870 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siriphan | Individual | ASP | THA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-09-01 | 2001-12-01 | 215000 | -5001 | 209999 | 209999 | 100% | 0 | 0 | 0 | 27950 | -650 | 27299.87 | 0.13 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Ocean Plastics | Individual | ASP | THA | FOA | 22 | INV | 67 | A | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 287000 | -16390 | 270610 | 270610 | 100% | 0 | 0 | 0 | 37310 | -2131 | 35179.3 | -0.3 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam at Chareon Porn | Individual | ASP | THA | FOA | 23 | INV | 68 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | -29 | 93471 | 93471 | 100% | 0 | 0 | 0 | 12155 | -4 | 12151.23 | -0.23 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam (boxfoam) at Thai International | Individual | ASP | THA | FOA | 23 | INV | 69 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 | 0 | 12155 | 0 | 12155 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Novochem | Individual | ASP | THA | FOA | 23 | INV | 70 | A | I | CFC | 19.7 | 19.7 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2002-08-01 | 2004-01-01 | 196600 | 0 | 196600 | 196600 | 100% | 0 | 0 | 0 | 25558 | 0 | 25558 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane boxfoam at Nun Charoen | Individual | ASP | THA | FOA | 23 | INV | 71 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Century Plastics | Individual | ASP | THA | FOA | 23 | INV | 75 | A | D | CFC | 7.3 | 7.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2001-12-01 | 56750 | -2560 | 54190 | 54190 | 100% | 0 | 0 | 0 | 7378 | -333 | 7044.7 | 0.3 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the foam sector | Individual | ASP | THA | FOA | 24 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to LCD technology (flexible) and water based technology (integral skin) in the manufacture of polyurethane foam at Duriflex | Individual | ASP | THA | FOA | 25 | INV | 90 | A | I | TCA/CFC | 21.2 | 21.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2001-12-01 | 278800 | -285 | 278515 | 278515 | 100% | 0 | 0 | 0 | 36244 | -37 | 36206.9456 | 0.0544 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to low index/additive technology and methylene chloride in the manufacture of flexible polyurethane boxfoam at City Foam Co., Ltd. | Individual | ASP | THA | FOA | 25 | INV | 91 | A | I | CFC | 42 | 42 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2000-12-01 | 156100 | 0 | 156100 | 156100 | 100% | 0 | 0 | 0 | 20293 | 0 | 20293 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Suwan Polymer L.P. | Individual | ASP | THA | FOA | 26 | INV | 100 | A | I | CFC | 58 | 58 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 298370 | -1026 | 297344 | 297344 | 100% | 0 | 0 | 0 | 38788 | -133 | 38654.72 | 0.28 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Sahakij Comos L.P. | Individual | ASP | THA | FOA | 26 | INV | 101 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 255850 | -11488 | 244362 | 244362 | 100% | 0 | 0 | 0 | 33261 | -1493 | 31767.06 | 0.94 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at P. Chongcharoen | Individual | ASP | THA | FOA | 26 | INV | 102 | A | I | CFC | 24 | 24 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 130500 | -256 | 130244 | 130244 | 100% | 0 | 0 | 0 | 16965 | -33 | 16931.72 | 0.28 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lohr Trade and Consulting PTS Ltd. | Individual | ASP | THA | FOA | 26 | INV | 103 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 93210 | -137 | 93073 | 93073 | 100% | 0 | 0 | 0 | 12117 | -18 | 12099.487 | -0.487 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam (flexible molded, integral skin) at World Plaster/Europlan Furniture Co. | Individual | ASP | THA | FOA | 26 | INV | 105 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 135800 | -5000 | 130800 | 130800 | 100% | 0 | 0 | 0 | 17654 | -650 | 17004 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ohm Intertrade L.P. | Individual | ASP | THA | FOA | 26 | INV | 106 | A | I | CFC | 19 | 19 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2002-03-01 | 146350 | -6393 | 139957 | 139957 | 100% | 0 | 0 | 0 | 19026 | -831 | 18194.41 | 0.59 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam at J.S. Industry Co. Ltd. | Individual | ASP | THA | FOA | 26 | INV | 98 | A | I | CFC | 93.2 | 93.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 418800 | -15974 | 402826 | 402826 | 100% | 0 | 0 | 0 | 54444 | -2077 | 52367.38 | -0.38 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Urethane | Individual | ASP | THA | FOA | 26 | INV | 99 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2001-12-01 | 2004-01-01 | 98645 | 0 | 98645 | 98645 | 100% | 0 | 0 | 0 | 12824 | 0 | 12823.85 | 0.15 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Preparation of six projects in general foam subsector | Individual | ASP | THA | FOA | 27 | PRP | 114 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Thai Steel Door L.P. | Individual | ASP | THA | FOA | 28 | INV | 117 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to low index additive (LIA) technology in the manufacture of flexible polyurethane foam at P.T. Foam Chiengmai L.P. | Individual | ASP | THA | FOA | 28 | INV | 118 | A | I | CFC | 12.7 | 12.7 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79120 | 0 | 79120 | 79120 | 100% | 0 | 0 | 0 | 10286 | 0 | 10285.6 | 0.4 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at S.K. Container Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 119 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA (flexible), to water-based technology (flexible molded, structural and integral skin) and HCFC-141b technology (rigid) at Great Foam Products, Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 122 | A | I | CFC | 22.1 | 22.1 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 231843 | -23 | 231820 | 231820 | 100% | 0 | 0 | 0 | 30140 | -3 | 30136.6 | 0.4 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.S. Plastic Container L.P. | Individual | ASP | THA | FOA | 29 | INV | 123 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 75951 | 0 | 75951 | 75951 | 100% | 0 | 0 | 0 | 9874 | 0 | 9873.63 | 0.37 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Elimination in the use of CFC in the manufacture of commercial refrigerators at Sanden Refrigerator Co. Ltd. | Individual | ASP | THA | REF | 13 | INV | 33 | A | I | CFC | 21 | 21 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1998-06-01 | 1999-12-01 | 533800 | 0 | 533800 | 533800 | 100% | 0 | 0 | 0 | 69394 | 0 | 69394 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Training of Government technical staff | Individual | ASP | THA | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 50000 | 3785 | 53785 | 53785 | 100% | 0 | 0 | 0 | 6500 | 492 | 6992.05 | -0.05 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection Unit | Individual | ASP | THA | SEV | 09 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-12-01 | 1996-03-01 |  | 2002-01-01 | 2003-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1993 | 1997-12-01 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 10 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-06-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance in foam, halon and aerosol sectors | Individual | ASP | THA | SEV | 15 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 18 | PRP | 49 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 2002-05-01 | 3000 | 0 | 3000 | 3000 | 100% | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | THA | SEV | 21 | PRP | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2001-12-01 | 100000 | -40377 | 59623 | 59623 | 100% | 0 | 0 | 0 | 13000 | -5249 | 7751 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol | Individual | ASP | THA | SEV | 25 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-07-01 | 2000-07-01 |  | 2003-04-01 | 2003-05-01 | 266667 | -225128 | 41539 | 41539 | 100% | 0 | 0 | 0 | 34667 | -29267 | 5400.07 | -0.07 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
ONG | UNDP | CFC and HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | INV | 07 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-10-01 | 2012-03-01 | 2016-07-01 |  |  | 96120 | 0 | 96120 | 61120 | 63.59% | 35000 | 20000 | 14000 | 8651 | 0 | 5500.9272 | 3150.0728 | 1800.0416 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, there were difficulties with the procurement process of the Recovery and Reclamation equipment. The potential supplier for Recovery and Reclamation equiment had been closed for the business, thus the procurement process had to be re-done. The procurement plan was being reviewed and discussed for changes. Prodoc signed (actual/planned, yes/no and date):The prodoc was signed in January 2012. Missions undertaken (actual/planned):Mission undertaken in November 2014. TOR for consultants/subcontracts completed (actual/planned):N/A. Contract/PO/MOA agreements signed:N/A. First disbursement date (actual/planned):The first disbursement took place in October 2012. Any delays/problems (yes/no):The potential supplier for Recovery and Reclamation equiment had been closed for the business, thus the procurement process had to be re-done. . If Yes, reasons for delay & action plan to resolve:The procurement plan was reviewed and discussed for changes so that another local vendor could supply the equipment.. | The procurement plan for R&R activity is being reviewed and finalized by the NOU. | 2011 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | TLS | PHA | 72 | PRP | 11 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 0 | 10000 | 700 | 0 | 0 | 700 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The TOR for the consultant was prepared and finalized in mid-2014. The joint mission with UNEP was undertaken in Nov 2014 to discuss the implementation of Stage-II HPMP preparation. The NOU and a local consultant have been working on the data collection. Prodoc signed (actual/planned, yes/no and date):The prodoc is expected to be signed in April 2015. Missions undertaken (actual/planned):Mission undertaken in November 2014. TOR for consultants/subcontracts completed (actual/planned):Completed in October 2014. Contract/PO/MOA agreements signed:N/A (to be signed by UNEP). First disbursement date (actual/planned):Planned by July 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A. | The first data collection for Stage-II preparation has been completed in early 2015. The result of the data collection is to be sent by the NOU. Upon the receipt of a draft Stage-II HPMP document, the disbursement will be made to the NOU for organizing the workshops and consultations with the stakeholders. |  |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | TOG | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3713 | 8287 | 8288 | 100% | -1 | 0 | 0 | 900 | -278 | 621.6 | 0.4 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-03-01 |  | 2010-12-01 | 2013-03-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 8550 | 0 | 8550 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | INV | 20 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2010-12-01 | 2013-03-01 | 62000 | -866 | 61134 | 61134 | 100% | 0 | 0 | 0 | 5580 | -78 | 5502.06 | -0.06 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | TOG | REF | 36 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring of the activities included in the RMP | RMP-Component | AFR | TOG | REF | 38 | TAS | 05 | A | I | CFC | 1.3 | 1.3 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2007-12-01 | 2008-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration sector | RMP-Component | AFR | TOG | REF | 38 | TAS | 06 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2006-11-01 |  | 2007-12-01 | 2011-11-01 | 110000 | -3068 | 106932 | 106932 | 100% | 0 | 0 | 0 | 14300 | -399 | 13901.16 | -0.16 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of refrigerants | RMP-Component | AFR | TOG | REF | 38 | TAS | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  | 2007-12-01 | 2011-11-01 | 150000 | -575 | 149425 | 149425 | 100% | 0 | 0 | 0 | 19500 | -75 | 19425.25 | -0.25 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 1 project in the aerosol sector | Individual | LAC | TRI | ARS | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Individual | LAC | TRI | ARS | 25 | INV | 12 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2004-12-01 | 2005-10-01 | 119570 | 0 | 119570 | 119570 | 100% | 0 | 0 | 0 | 15544 | 0 | 15544.1 | -0.1 | 0 | Completed in 2004. Financially completed in 2007. |  | 1998 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | TRI | PHA | 40 | INV | 16 | N | I | CFC | 42.9 | 42.9 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2006-03-01 |  | 2006-12-01 | 2013-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 16500 | 0 | 16500 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | LAC | TRI | PHA | 49 | INV | 20 | N | I | CFC | 34.1 | 34.1 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2008-12-01 |  | 2008-12-01 | 2013-10-01 | 240000 | -8413 | 231587 | 231622 | 100% | -35 | 0 | 0 | 18000 | -631 | 17371.625 | -2.625 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Audit for an ongoing terminal phase-out management plan | Individual | LAC | TRI | PHA | 51 | TAS | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-11-01 | 20000 | -7261 | 12739 | 12739 | 100% | 0 | 0 | 0 | 1500 | -545 | 955.425 | -0.425 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | TRI | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | TRI | PHA | 59 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2012-06-01 | 2013-12-01 | 65000 | -3297 | 61703 | 61703 | 100% | 0 | 0 | 0 | 4875 | -247 | 4627.725 | 0.275 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 26 | N | I | HCFC | 2.5 | 0 | 0 | 0 | 2011-07-01 | 2013-08-01 | 2013-07-01 | 2016-01-01 |  |  | 173800 | 0 | 173800 | 68771 | 39.57% | 105029 | 0 | 42011.484 | 13035 | 0 | 5157.8467 | 7877.1533 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, the Vetter Boxes were fully reconverted. Seal Spray is doing trials. Other 3 companies are assessing samples from US and MEX to decide on provider and initiate reconversion. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2012. Missions undertaken (actual/planned):2 of 2. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:7 of 7. First disbursement date (actual/planned):The first disbursement took place in August 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Initial delay was faced in the signature of the Agreement (MOA) with recipient companis due to doubts from the recipients in the conversion processes. MOAs were signed in late 2013 and project commenced immediately. One company completed its reconversion in 2014. Others had their implementation schedule adjusted and the project is progressing as planned now. | Since 2014, the Vetter Boxes was completed. Other 4 companies are preparing conversion plans. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-12-01 | 2013-07-01 | 2016-01-01 |  |  | 386100 | 0 | 386100 | 125533 | 32.51% | 260567 | 19626.07 | 104226.852 | 28958 | 0 | 9415.1278 | 19542.8722 | 1471.9807 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, HC equipment were procured and installed in the training centers and a schedule to expand RAC training was approved by GOV. Sensitization seminars had been expanded to more 50 people. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2012. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):2 of 2. Contract/PO/MOA agreements signed:2 of 2. First disbursement date (actual/planned):The first disbursement took place in December 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, local trainings were expanded to end-users. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | TRI | PHA | 71 | TAS | 30 | N | I | HCFC | 4.2 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 198000 | 0 | 198000 | 0 | 0% | 198000 | 0 | 79200 | 14850 | 0 | 0 | 14850 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The second tranche was approved in December 2013. The procurement plan of tools was approved by Dec 2014. Prodoc signed (actual/planned, yes/no and date):No, the prodoc hasn't been signed yet. It will be signed in Feb 2015. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1 . Contract/PO/MOA agreements signed:0 of 2. First disbursement date (actual/planned):The first disbursement will take place in February 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Since 2014, procurement of tools was completed and delivery is expected for the third quarter of 2015. 3rd Tranche is expected to be requested to the 75th ExCom. | 2013 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | TRI | REF | 23 | TAS | 09 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 213990 | -12116 | 201874 | 201874 | 100% | 0 | 0 | 0 | 27819 | -1575 | 26243.62 | 0.38 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for the RMP update | Individual | LAC | TRI | REF | 38 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2002-12-01 | 2003-12-01 |  | 2003-07-01 | 2006-06-01 | 13500 | -3905 | 9595 | 9595 | 100% | 0 | 0 | 0 | 1755 | -508 | 1247 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Training of Government technical staff and preliminary work on country programme | Individual | LAC | TRI | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1995-07-01 | 1997-12-01 | 53800 | 102 | 53902 | 53902 | 100% | 0 | 0 | 0 | 6994 | 13 | 7007.26 | -0.26 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | TRI | SEV | 06 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1995-07-01 | 1997-12-01 | 25000 | 1200 | 26200 | 26200 | 100% | 0 | 0 | 0 | 3250 | 156 | 3406 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | TRI | SEV | 20 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 2000-12-01 | 2003-06-01 | 66000 | -5223 | 60777 | 60777 | 100% | 0 | 0 | 0 | 8580 | -679 | 7901.01 | -0.01 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-12-01 | Non-Investment
FIN | UNDP | Project preparation in the aerosol, refrigeration and solvent sectors | Individual | LAC | TRI | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 40000 | -4596 | 35404 | 35404 | 100% | 0 | 0 | 0 | 5200 | -597 | 4602.52 | 0.48 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | LAC | TRI | SEV | 32 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2011-12-01 | 44000 | -3632 | 40368 | 40368 | 100% | 0 | 0 | 0 | 5720 | -472 | 5247.84 | 0.16 | 0 | Completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase 3) | Individual | LAC | TRI | SEV | 38 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2006-12-01 | 2011-12-01 | 57200 | -507 | 56693 | 56693 | 100% | 0 | 0 | 0 | 7436 | -66 | 7370.09 | -0.09 | 0 | Completed in 2006. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | LAC | TRI | SEV | 44 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-05-01 | 2011-12-01 | 60000 | -448 | 59552 | 59552 | 100% | 0 | 0 | 0 | 4500 | -34 | 4466.036 | -0.035997 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | TRI | SEV | 50 | INS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2012-06-01 | 2014-02-01 | 60000 | -3073 | 56927 | 56927 | 100% | 0 | 0 | 0 | 4500 | -230 | 4269.52 | 0.48 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2006 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | TRI | SEV | 59 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-10-01 | 2011-12-01 |  | 2013-12-01 |  | 30000 | 30000 | 60000 | 49237 | 82.06% | 10763 | 0 | 8610.392 | 2250 | 2250 | 3692.7757 | 807.2242 | 0 | Completed in 2013. Project has been successfully operationally completed as milestones in Dec 2013. Follow up on the implementation of MP funded projects is ongoing. The National Ozone Unit is implementing its HPMP and carrying out awareness activities to support HCFC phase out. | Completed in 2013. Final financial payments are being reviwed. | 2009 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | TRI | SEV | 68 | INS | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2014-12-01 | 2015-08-01 |  |  | 60000 | 0 | 60000 | 21525 | 35.88% | 38475 | 0 | 15389.812 | 4200 | 0 | 1506.7829 | 2693.2171 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were carried out and all planned activities were conducted. ODS consumption reports prepared and submitted. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in June 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in August 2013. Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:One procurement process has been delayed due to lack of supplier. TORs reviewed and process re launched | Since 2014, IS oversought and supported HPMP implementation with several field activities. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | LAC | TRI | SEV | 73 | INS | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-12-01 | 2017-01-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 4200 | 0 | 0 | 4200 | 0 | Newly Approved | Since 2014, ProDoc prepared and agreed. Document was sent to GOV´s signature and is expected to be signed by the third quarter in 2015. | 2014 |  | Non-Investment
FIN | UNDP | Validation of the use of HFO-1234ze as blowing agent in the manufacture of extruded polystyrene foam boardstock (phase I) | Individual | EUR | TUR | FOA | 60 | DEM | 96 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-02-01 |  | 2011-12-01 | 2014-03-01 | 165000 | -391 | 164609 | 164609 | 100% | 0 | 0 | 0 | 14850 | -35 | 14814.81 | 0.19 | 0 | Financially completed in 2014. | Completed in 2011. All tests have been completed. An initial draft technology report was prepared in February 2012. The project is considered as completed. The final technology report will be submitted to 67th ExCom | 2010 |  | Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | UGA | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | UGA | REF | 19 | TAS | 05 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 56000 | -17 | 55983 | 55983 | 100% | 0 | 0 | 0 | 7280 | -2 | 7277.79 | 0.21 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | UGA | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation to formulate one flexible foam sector project | Individual | AFR | URT | FOA | 24 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at H.K. Foam Ltd. | Individual | AFR | URT | FOA | 26 | INV | 10 | A | I | CFC | 2 | 2 | 0 | 0 | 1998-11-01 | 2003-01-01 | 2000-12-01 |  |  | 2003-11-01 | 113700 | -105743 | 7957 | 7957 | 100% | 0 | 0 | 0 | 14781 | -13747 | 1034.41 | -0.41 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1998 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pan Africa Enterprises Ltd. | Individual | AFR | URT | FOA | 26 | INV | 11 | A | I | CFC | 35 | 35 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  |  | 2004-03-01 | 213800 | 0 | 213800 | 213800 | 100% | 0 | 0 | 0 | 27794 | 0 | 27794 | 0 | 0 | Canceled in 2002. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Plyfoam Limited | Individual | AFR | URT | FOA | 31 | INV | 13 | A | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-07-01 | 2002-07-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 175134 | 0 | 175134 | 175134 | 100% | 0 | 0 | 0 | 22767 | 0 | 22767.42 | -0.42 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | URT | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  |  | 2010-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 | 0 | 3750 | -3750 | 0 | 0 | 0 | No specific HCFC-141b consuming foam companies were identified by NOU during 2010 and, thus, no technical visits were to be fielded by UNDP, and the funds are to be returned to the MLF Secretariat in 2011 as PRP is cancelled. |  | 2009 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | URT | PHA | 50 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -3240 | 8760 | 8760 | 100% | 0 | 0 | 0 | 900 | -243 | 656.9999 | 5.0001e-05 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | INV | 23 | N | I | CFC | 15.9 | 15.9 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-01 |  | 2013-12-01 | 2014-08-01 | 204000 | 0 | 204000 | 204000 | 100% | 0 | 0 | 0 | 15300 | 0 | 15300 | 0 | 0 | Financially completed in 2014. | Completed in 2013. UNDP supervision mission held in February 2014. Project is closed and PCR preparation works are underway. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | INV | 28 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 2009-07-01 | 2012-01-01 | 2011-07-01 |  | 2013-12-01 | 2014-02-01 | 72000 | -20327 | 51673 | 48198 | 93.28% | 3475 | 0 | 0 | 5400 | -1525 | 3614.4024 | 260.5976 | 0 | Financially Completed in 2014. | Completed in 2013. UNDP supervision mission held in February 2014. Project is closed and PCR preparation works are underway. | 2009 |  | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | URT | REF | 22 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2001-12-01 | 161554 | -153795 | 7759 | 7759 | 100% | 0 | 0 | 0 | 21002 | -19993 | 1009.02 | -0.02 | 0 | Canceled in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | URT | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1998-12-01 | 1999-12-01 | 47000 | 0 | 47000 | 47000 | 100% | 0 | 0 | 0 | 6110 | 0 | 6110 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | 0 | 7019.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | I | CFC | 10 | 10 | 0 | 0 | 2004-07-01 | 2006-04-01 | 2007-07-01 |  | 2009-12-01 | 2013-12-01 | 427023 | -6 | 427017 | 427017 | 100% | 0 | 0 | 0 | 32027 | 0 | 32026.9887 | 0.01125 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 06 | N | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 09 | N | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664 | 25335.83 | 0.17 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | URU | FOA | 57 | PRP | 52 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2013-01-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | URU | FOA | 72 | PRP | 62 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 68000 | 0 | 68000 | 0 | 0% | 68000 | 0 | 68000 | 4760 | 0 | 0 | 4760 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included establishing project arrangement and preparing the project document. Prodoc signed (actual/planned, yes/no and date):No, the prodoc hasn't been signed yet. It will be signed in Jan 2015.. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):The first disbursement will take place in March 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | TOR for national consultant were prepared and launched. General strategy and workplan were discussed with the NOU and other local authorities. 1 follow up mission conducted. |  |  | Non-Investment
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4960 | 0 | 4959.5 | 0.5 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | I | Halon | 2.7 | 2.7 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149 | 0 | 3149.25 | -0.25 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-03-01 | 2009-08-01 | 30000 | -18 | 29982 | 29982 | 100% | 0 | 0 | 0 | 2250 | -1 | 2248.65 | 0.35 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | INV | 46 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2013-08-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | URU | PHA | 55 | PRP | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-12-01 | 2013-07-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | INV | 50 | N | I | CFC | 69.7 | 69.7 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2013-09-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-year | LAC | URU | PHA | 60 | INV | 54 | N | I | CFC | 29.9 | 29.9 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | URU | PHA | 65 | INV | 57 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2015-11-01 |  | 2013-06-01 | 2013-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | URU | PHA | 68 | INV | 58 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2014-10-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. The project achieved its planned activities related to training on good refrigeration practices, 2 one-week workshops were conducted in Montevideo and other cities. Verification report for 2013 was completed, showing that the country is in compliance of its reduction obligations. Prodoc signed (actual/planned, yes/no and date):Yes, it was signed before 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in November 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, the milestone of preparing and approving the 2014 workplan and budget was achieved. Third tranche funds included in budget. HCFC quotas for 2014 were established. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | URU | PHA | 71 | INV | 59 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-06-01 | 2016-01-01 |  |  | 115000 | 0 | 115000 | 66918 | 58.19% | 48082 | 0 | 19232.844 | 8625 | 0 | 5018.8417 | 3606.1582 | 0 | Remarks (Short narrative description of progress made (actual/planned)):The project achieved its planned activities related to training on good refrigeration practices, 2 one-week workshops were conducted in Montevideo and other cities. Verification report for 2013 was completed, showing that the country is in compliance of its reduction obligations. Prodoc signed (actual/planned, yes/no and date):Yes, the original ProDoc was amended in July 2014 to include the third tranche. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:1 of 1. First disbursement date (actual/planned):The first disbursement took place in Aug 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Implementation of 2105 workplan is underway, meetings with customs authorities and technical counterpart (LATU) were conducted. 1 follow up mission was conducted. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | URU | PHA | 72 | PRP | 61 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4200 | 0 | 0 | 4200 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included establishing project arrangement and preparing the project document. Prodoc signed (actual/planned, yes/no and date):No, the prodoc hasn't been signed yet. It will be signed in Jan 2015. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):0 of 0. Contract/PO/MOA agreements signed:0 of 0. First disbursement date (actual/planned):The first disbursement will take place in March 2015. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | TOR for national consultant were prepared and launched. General strategy and workplan were discussed with the NOU and other local authorities. 1 follow up mission was conducted. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | LAC | URU | PHA | 73 | INV | 63 | N | I | HCFC | 2.3 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2016-11-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 8000 | 1500 | 0 | 0 | 1500 | 0 | Newly Approved | Implementation of 2105 workplan is underway, meetings with customs authorities and technical counterpart (LATU) were conducted. 1 follow up mission was conducted. | 2014 |  | Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 04 | N | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12 | 22737.52 | 0.48 | 0 | Completed in 1996. Financially completed in 2004. |  | 1994 |  | Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | LAC | URU | REF | 34 | TAS | 37 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 |  | 2009-12-01 | 2011-02-01 | 154934 | -192 | 154742 | 154742 | 100% | 0 | 0 | 0 | 20141 | -25 | 20116.46 | -0.46 | 0 | Completed in 2009. |  | 2001 |  | Investment
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1697 | 129 | 1825.46 | 0.54 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106 | 202 | 3307.72 | 0.28 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -2 | 15078 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2006-01-01 | 2009-08-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 19604 | 0 | 19604 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | URU | SEV | 49 | INS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-10-01 |  | 2010-08-01 | 2012-07-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | URU | SEV | 56 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2010-10-01 |  | 2011-12-01 | 2013-02-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | URU | SEV | 65 | INS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-02-01 | 2013-12-01 |  | 2014-06-01 |  | 150800 | 0 | 150800 | 150796 | 100% | 4 | 0 | 3.2 | 11310 | 0 | 11309.7 | 0.3 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were carried out and all planned activities were conducted. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. NOU participated actively in all regional meetings. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2012. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:3 of 3. First disbursement date (actual/planned):The first disbursement took place in February 2012. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, the 2014 workplan and budget prepared and approved. HCFC quotas for 2014 established. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | LAC | URU | SEV | 71 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2016-02-01 |  |  | 150800 | 0 | 150800 | 51050 | 33.85% | 99750 | 0 | 39899.896 | 10556 | 0 | 3573.5182 | 6982.4818 | 0 | Remarks (Short narrative description of progress made (actual/planned)):In 2014, institutional strengthening activities were carried out and all planned activities were conducted. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. NOU participated actively in all regional meetings. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in July 2014. Missions undertaken (actual/planned):0 of 0. TOR for consultants/subcontracts completed (actual/planned):3 of 3. Contract/PO/MOA agreements signed:3 of 3. First disbursement date (actual/planned):The first disbursement took place in August 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 1 follow up mission conducted. | 2013 |  | Non-Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | I | TCA/CTC | 0.3 | 0.3 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | VEN | FOA | 72 | PRP | 126 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 | 2016-05-01 |  |  | 150000 | 0 | 150000 | 1215 | 0.81% | 148785 | 0 | 148785.01 | 10500 | 0 | 85.0493 | 10414.9507 | 0 | Remarks (Short narrative description of progress made (actual/planned)):PRP activities implemented during 2014 included establishing project arrangement and preparing the project document. One mission of the intenational expert took place to establish work plan and required information. The launching event of the foam sector phase out strategy was conducted, main stakeholders participated. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in September 2014. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):1 of 1. Contract/PO/MOA agreements signed:0 of 1. First disbursement date (actual/planned):The first disbursement took place in December 2014. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | Meetings with stakeholders were conducted to review technology options. Discussions with NOU on possible strategies for the foam sector took place. 1 mission was conducted by the international expert and cooperating agency. |  |  | Non-Investment
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427 | 2472.6 | 0.4 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 708 | 5907.85 | 0.15 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204 | 206796 | 206796 | 100% | 0 | 0 | 0 | 28600 | -1717 | 26883.48 | -0.48 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387 | 47887.84 | 0.16 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | I | No_ODP | 0.7 | 0.7 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186 | 21873.54 | 0.46 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16071 | 0 | 16070.99 | 0.01 | 0 | Completed in 2001. Financially completed in 2002. |  | 1995 | 2000-12-01 | Investment
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320 | 75569.5856 | 0.4144 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | I | CFC | 65.5 | 65.5 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89093 | -856 | 88236.85 | 0.15 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1997-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29936 | -6665 | 23271.04 | -0.04 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -455 | 14118.26 | -0.26 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -338 | 24362.13 | -0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -379 | 161996 | 161996 | 100% | 0 | 0 | 0 | 21109 | -49 | 21059.48 | 0.52 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121111 | -8002 | 113108.9 | 0.1 | 0 | Completed in 2003. Financially completed in 2003. |  | 1997 | 1999-06-01 | Investment
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42795 | 0 | 42794.96 | 0.04 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-07-01 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-07-01 | 285480 | -981 | 284499 | 284499 | 100% | 0 | 0 | 0 | 37112 | -127 | 36985.4 | -0.4 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 285480 | 0 | 285480 | 285480 | 100% | 0 | 0 | 0 | 21411 | 0 | 21411 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -27909 | 17963 | 17963 | 100% | 0 | 0 | 0 | 4128 | -2512 | 1616.482 | -0.482 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | VEN | SEV | 49 | INS | 108 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2008-07-01 |  | 2008-12-01 | 2011-10-01 | 285480 | -1 | 285479 | 285479 | 100% | 0 | 0 | 0 | 21411 | 0 | 21410.925 | 0.07505 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase IX) | Individual | LAC | VEN | SEV | 56 | INS | 113 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2010-12-01 |  | 2010-12-01 | 2013-02-01 | 285480 | -2637 | 282843 | 282843 | 100% | 0 | 0 | 0 | 21411 | -198 | 21213.225 | -0.225 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase X) | Individual | LAC | VEN | SEV | 62 | INS | 117 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2013-03-01 | 2014-12-01 | 285480 | 0 | 285480 | 262924 | 92.1% | 22556 | 0 | 0 | 21411 | 0 | 19719.3 | 1691.7 | 0 | Financially completed in 2014. | Project completed in 2013. | 2010 |  | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | VEN | SEV | 68 | INS | 122 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-12-01 |  | 2014-12-01 |  | 285480 | 0 | 285480 | 283726 | 99.39% | 1754 | 0 | 1403.032 | 19984 | 0 | 19861.2322 | 122.7678 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. In 2014, institutional strengthening activities were carried out and all planned activities were conducted. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2014 HCFC import quota set. Prodoc signed (actual/planned, yes/no and date):Yes, the prodoc was signed in April 2013. Missions undertaken (actual/planned):1 of 1. TOR for consultants/subcontracts completed (actual/planned):4 of 4. Contract/PO/MOA agreements signed:4 of 4. First disbursement date (actual/planned):The first disbursement took place in April 2013. Any delays/problems (yes/no):No. If Yes, reasons for delay & action plan to resolve:N/A | As planned, the 2014 workplan and budget was prepared and approved. HCFC quotas for 2014 established. | 2012 |  | Non-investment
ONG | UNDP | Renewal of institutional strengthening project (phase XII: 1/2015-12/2016) | Individual | LAC | VEN | SEV | 73 | INS | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-12-01 | 2017-01-01 |  |  | 285480 | 0 | 285480 | 0 | 0% | 285480 | 0 | 114192 | 19984 | 0 | 0 | 19984 | 0 | Newly Approved | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 1 follow up mission conducted. | 2014 |  | Non-Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 07 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2439 | 235991 | 235991 | 100% | 0 | 0 | 0 | 30996 | -317 | 30678.83 | 0.17 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344 | -42 | 14302.6 | -0.6 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37066 | -343 | 36722.27 | 0.73 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -285 | 1015.04 | -0.04 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 | 2008-10-01 | 49720 | 0 | 49720 | 49720 | 100% | 0 | 0 | 0 | 6464 | 0 | 6463.6 | 0.4 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 | 2007-03-01 | 125400 | 0 | 125400 | 125400 | 100% | 0 | 0 | 0 | 16302 | 0 | 16302 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81 | 2518.75 | 0.25 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868 | -1331 | 20537.1449 | -0.1449 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 2000-07-01 | Non-Investment
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142 | 507.52 | 0.48 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 34 | TAS | 35 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-01-01 | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | ASP | VIE | REF | 34 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-01-01 | 21600 | -242 | 21358 | 21358 | 100% | 0 | 0 | 0 | 2808 | -31 | 2776.54 | 0.46 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 35 | TAS | 39 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2007-03-01 | 290413 | -22502 | 267911 | 267911 | 100% | 0 | 0 | 0 | 37754 | -2925 | 34828.716 | 0.284 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251 | 1698.58 | 0.42 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Component | ASP | YEM | REF | 37 | TAS | 15 | A | I | CFC | 220 | 220 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2008-12-01 | 2012-06-01 | 1472730 | -36714 | 1436016 | 1436016 | 100% | 0 | 0 | 0 | 172000 | -4288 | 167712.4678 | -0.46784 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2011-12-01 | 2013-02-01 | 109000 | -30490 | 78510 | 78510 | 100% | 0 | 0 | 0 | 9810 | -2744 | 7065.9 | 0.1 | 0 | Financially completed in 2013. | Completed in 2011. | 2007 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 06 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13822 | -31 | 13790.4 | 0.6 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27671 | -1319 | 26351.98 | 0.02 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Technical assistance for the phase-out of ODS in the solvent/sterilant sector | Individual | AFR | ZIM | SOL | 50 | TAS | 35 | N | I | TCA/CTC | 3.9 | 3.9 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-05-01 |  | 2009-12-01 | 2011-10-01 | 60000 | -1229 | 58771 | 58771 | 100% | 0 | 0 | 0 | 5400 | -111 | 5289.0018 | -0.0017999 | 0 | Completed in 2009. Financially completed in 2011. |  | 2006 | 2010-01-01 | Non-Investment
FIN | UNEP | National phase-out plan (1st tranche) | Multi-year | ASP | AFG | PHA | 47 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 305000 | 0 | 305000 | 305000 | 100% | 0 | 0 |  | 39650 | 0 | 39650 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | AFG | PHA | 55 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | AFG | PHA | 63 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2012-03-01 | 2015-12-01 |  |  | 120000 | 0 | 120000 | 89353 | 74.46% | 30647 |  | 30647 | 15600 | 0 | 11612 | 3988 | 0 | Brief progress report (actual/planned): 147 Customs officers trainned in 2014. NOU developed the 2014 annual plan for strengthening the measures for controlling HCFCs import and consumption. Stakeholders consultations including one with registered importers and goods transporting companies were organized. Legal arrangement (actual/ planned): Implementation delay has required a rephasing of UNEP agreement with the government in the last Q of 2014. First mission (actual/ planned): Jan. 2012. TOR completed (actual/ planned): N/A. First disbursement date: 08/12/2011. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: No funds transfer to the beneficiary due to UNEP internal review of funds transfer modality. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. 4 units of refrigerants identifiers delivered in 2nd quarter of 2015. Implementation halted 2nd quarter of 2015 due to lack of funds in the country and new fund transfer modality by UNEP HQs not finalised. Legal arrangement (actual/ planned): Draft SSFA prepared, but processing pending.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | AFG | PHA | 72 | TAS | 16 | A | I | HCFC-22 | 1.37 |  |  |  | 2014-05-01 |  | 2017-05-31 | 2017-05-31 |  |  | 118000 |  | 118000 | 0 | 0% | 118000 |  | 118000 | 15340 | 0 | 0 | 15340 | 0 | Brief progress report (actual/planned): implementation not started. Legal arrangements (actual/ planned): Agreement for tranche 2 has been prepared, no funds has been transferred due to UNEP internal review on transfer modality. First mission (actual/ planned): 3rd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date (actual/ planned): 3rd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Due to no funds transfer to the beneficiary due to UNEP internal review of funds transfer modality. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Implementation yet to start.
FIN | UNEP | Preparation of the country programme/RMP project | Individual | ASP | AFG | SEV | 43 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 |  | 2005-10-01 | 2011-12-01 | 60000 | -18155 | 41845 | 41845 | 100% | 0 |  |  | 7800 | -2360.15 | 5440 | -0.15 | 0
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | AFG | SEV | 43 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2005-07-01 | 2007-04-01 | 40000 | -13 | 39987 | 39987 | 100% | 0 |  |  | 5200 | 0 | 5198 | 2 | 0
FIN | UNEP | Start up of institutional strengthening project | Individual | ASP | AFG | SEV | 46 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 |  | 2005-10-01 | 2006-10-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | ASP | AFG | SEV | 47 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | AFG | SEV | 53 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2009-11-01 | 2009-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | AFG | SEV | 58 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 81250 | 68750 | 150000 | 150000 | 100% | 0 |  |  | 10562.5 | 0 | 10562.5 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V: 12/2011-11/2013) | Individual | ASP | AFG | SEV | 64 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed | Project is financially completed
ONG | UNEP | Extension of institutional strengthening project (phase VI: 12/2013-11/2015) | Individual | ASP | AFG | SEV | 70 | INS | 15 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-11-01 | 2015-11-01 |  |  | 150000 | 0 | 150000 | 40000 | 26.67% | 110000 |  | 110000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system was implemented in 2014 along with the consumption verification that highlighted areas that need to be strengthened. The NOU took first steps to join iPIC. NOU maintained records of imports and made regular checks with the Customs Department. The 2014 Article 7 data was reported to the Ozone Secretariat. Ozone Day celebrations were held. Legal arrangements(actual/planned): SSFA has been signed in March 2014 and two payments made to the country. Initial stages of project implementation(actual/planned): N/A since Project is ongoing. Intermediate goals achieved (actual/planned): Assisting in the implementation of stage I of the HPMP, introducing HCFC quota system from 2013 onwards, import restrictions for all HCFCs except HCFC-22 (as planned) First disbursement date (actual/planned): April 2014 as planned. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | NOU organized meetings with national stakeholders on developing quota guidelines for 2015. However the funds disbursement processes are being changed to be more transparent as a result of which from December 2014 no funds have been disbursed till date. The project will be completed in December 2015. Continue the NOU operation in 2016-2017 with IS renewal in the 74th Excom in May 2015
FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | AFR | AFR | FUM | 16 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1995-09-01 | 1999-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | AFR | AFR | FUM | 21 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1998-04-01 | 1999-03-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 35750 | 0 | 35750 | 0 | 0
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | AFR | AFR | FUM | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2006-02-01 | 80000 | -16044 | 63956 | 63956 | 100% | 0 | 0 |  | 10400 | -2085.72 | 8314 | 0.28 | 0
FIN | UNEP | Regional training workshops on policy development | Individual | AFR | AFR | FUM | 27 | TRA | 24 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 |  | 1999-12-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | AFR | AFR | FUM | 34 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 |  | 2004-03-01 | 2009-07-01 | 80000 | -24177 | 55823 | 55823 | 100% | 0 | 0 |  | 10400 | -3143.01 | 7257 | -0.01 | 0 |  |  |  | 2003-09-01
FIN | UNEP | Regional training course on refrigeration for Africa | Individual | AFR | AFR | REF | 06 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-01 | 1992-12-01 |  | 1992-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1995-07-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-09-01 | 1994-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Regional workshop for Africa | Individual | AFR | AFR | SEV | 06 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1992-12-01 | 1993-12-01 | 210000 | 0 | 210000 | 210000 | 100% | 0 | 0 |  | 27300 | 0 | 27300 | 0 | 0
FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | AFR | AFR | SEV | 12 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-03-01 | 2000-03-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 |  | 23400 | 0 | 23400 | 0 | 0
FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | AFR | AFR | SEV | 12 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-06-01 | 1999-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | AFR | AFR | SEV | 16 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-01-01 | 232200 | 0 | 232200 | 232200 | 100% | 0 | 0 |  | 30186 | 0 | 30186 | 0 | 0
FIN | UNEP | African Network (1996) | Individual | AFR | AFR | SEV | 19 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299400 | 0 | 299400 | 299400 | 100% | 0 | 0 |  | 38922 | 0 | 38922 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | AFR | AFR | SEV | 19 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | African Region Network (1997) | Individual | AFR | AFR | SEV | 21 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 411000 | -33344 | 377656 | 377656 | 100% | 0 | 0 |  | 53430 | -4335 | 49095 | 0 | 0
FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | AFR | AFR | SEV | 23 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 |  | 1998-12-01 | 2000-03-01 | 431000 | -21369 | 409631 | 409631 | 100% | 0 | 0 |  | 56030 | -2778 | 53252 | 0 | 0
FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | AFR | AFR | SEV | 26 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 431000 | -14398 | 416602 | 416602 | 100% | 0 | 0 |  | 56030 | -1872 | 54158 | 0 | 0
FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | AFR | AFR | SEV | 29 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-01-01 | 452550 | -30254 | 422296 | 422296 | 100% | 0 | 0 |  | 58832 | -3933 | 54899 | 0 | 0
FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | AFR | AFR | SEV | 32 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 464000 | -36863 | 427137 | 427137 | 100% | 0 | 0 |  | 60320 | -4792 | 55528 | 0 | 0
FIN | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | AFR | AFR | SEV | 32 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 |  | 2004-11-01 | 2007-12-01 | 151500 | -22085 | 129415 | 129415 | 100% | 0 | 0 |  | 19695 | -2871 | 16824 | 0 | 0
FIN | UNEP | Sub-regional project on harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | AFR | AFR | SEV | 45 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0
FIN | UNEP | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-07-01 | 2013-12-01 | 160000 | -2684 | 157316 | 157316 | 100% | 0 | 0 |  | 20800 | -349 | 20451 | 0 | 0 | Project Financially Complete
FIN | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Multi-year | EUR | ALB | PHA | 39 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2005-08-01 | 2007-04-01 | 35700 | -278 | 35422 | 35422 | 100% | 0 | 0 |  | 4641 | -36 | 4605 | 0 | 0
FIN | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Multi-year | EUR | ALB | PHA | 39 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2006-07-01 | 2010-12-01 | 82425 | -10163 | 72262 | 72262 | 100% | 0 | 0 |  | 10715 | -1322 | 9393 | 0 | 0 |  |  |  | 2005-07-01
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ALB | PHA | 64 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-01-01 | 2013-07-01 |  | 2013-07-01 | 2014-07-14 | 25000 | 0 | 25000 | 24954.14 | 99.82% | 45.86 | 0 |  | 3250 | 0 | 3244.0382 | 5.9618 | 0 | Financially completed. | Financially completed.
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | ALB | PHA | 70 | TAS | 26 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-07-01 |  | 2014-12-14 |  | 20000 | 0 | 20000 | 19992.27 | 99.96% | 7.73 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Brief progress report (actual/planned): Three training workshops are organized in the country: 1. Training of Technicians on Good Practice in Refrigeration, 27 – 28 February 2014, ABA Business Center, Tirana 2. Training of Technicians on Good Practice in Refrigeration, 28 – 30 April 2014, Hotel “Majestic”, DURRES 3. Training of Technicians on Good Practice in Refrigeration, 28 – 30 October 2014, University “PAVARESIA”, VLORE The trainings workshops were attended by 87 technicians from service sector of refrigeration and 69 of them received certificates (planned about 60 technicians to be trained). The Customs training workshop on monitoring and control of Ozone Depleting Substances was organized on 2 – 3 October 2014, in Hotel Victoria, Tirana. This workshop was organized with the assistance of the international resource person, Dr. Janusz Kozakiewicz. UNEP was requested to attend the meeting and assist the NOU in running the workshop. Participants were 20 officers (as planned) from the General Directorate of Customs (customs officers from various points of entry and customs sections - computer and data processing unit, document processing unit, administration unit, enforcement officer etc.). The representatives of the Refrigeration Association were also present (one was also acting as National Consultant). The meetings between the NOPIU, UNEP and other stakeholders on implementation of the IS and HPMP projects on 4 of October of 2014 (back to back). The activities under the project are completed. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the Ministry and UNEP in December of 2013 (as planned) First mission (actual/planned): n/a – NOPIU implements all activities at national level. Involvement of international experts upon request from the NOU TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in January of 2014 (as planned) All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The NOPIU in cooperation with UNEP and UNIDO has drafted the final report and request for the third tranche. The request will be sent for ExCom-75 as the country should finalize the verification report in cooperation with UNIDO as a lead agency. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the Ministry and UNEP in December of 2013 (as planned) First mission (actual/planned): n/a – NOPIU implements all activities at national level. Involvement of international experts upon request from the NOU TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in January of 2014 (as planned) All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
FIN | UNEP | Preparation of country programme | Individual | EUR | ALB | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-06-01 | 2005-12-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 |  | 7800 | -3770 | 4030 | 0 | 0 |  |  |  | 2002-09-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | ALB | SEV | 35 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (second year) | Individual | EUR | ALB | SEV | 38 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 |  | 2005-07-01 | 2007-06-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | EUR | ALB | SEV | 46 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2007-07-01 |  | 2006-07-01 | 2008-03-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | EUR | ALB | SEV | 49 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-08-01 | 2008-06-01 |  | 2008-06-01 | 2010-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | EUR | ALB | SEV | 54 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-06-01 |  | 2011-06-01 | 2012-06-01 | 109200 | -63 | 109137 | 109137 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | EUR | ALB | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-06-01 |  | 2012-12-01 | 2013-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | EUR | ALB | SEV | 66 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 |  | 2014-06-14 |  | 109200 | 0 | 109200 | 101626.81 | 93.06% | 7573.19 | 6684.92 | 6685 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system is in place. Import quotas and permits are strictly controlled by the Government. The Government introduced the rule that imported ODSs are allowed to enter the country only through the customs check points that have certified personnel. Article 7 data was collected and the report submitted on time to OS for the year of 2013. CP report was prepared and submitted to MFS on time for the year of 2013. Consultations meetings with Albanian Refrigerant Association conducted to enable effective implementation of HPMP. The renewal request has been prepared and approved by ExCom (IS phase VI). Legal arrangements (actual/planned): Agreement signed in October 2012. Initial stages of project implementation (actual/planned): The project was implemented as planned. No delays. Intermediate goals achieved (actual/planned): Article 7 and CP data was collected and reports submitted to OS and MLFS for the year of 2013 on time. Project completion and follow up: Project completed First disbursement date (actual/planned): October 2012 (as planned) All funds disbursed (yes/no): All funds are disbursed. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: NO If Yes, will delay have impact on project completion date (yes/no): Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 7/2014-6/2016) | Individual | EUR | ALB | SEV | 72 | INS | 28 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-10-01 | 2016-06-01 | 2016-06-30 |  |  | 109200 |  | 109200 | 40300 | 36.9% | 68900 | 0 | 68900 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): On the occasion of World Ozone Day, NOPIU has organized the Ozone Week: 16 – 22 September. A number of activities took place during the week: 1. Students of “Edith Durham” secondary school in Tirana organized a special activities devoted to the International Day for the Preservation of the Ozone. Dea Kozma, a honors student, read out the UN Secretary-General’s Message. 2 The Deputy Minister of Environment, Mrs. Oliana Ifti, delivered a public statement regarding the International Ozone Day. 3. NOPIU and Dëshmoret e Lirisë, secondary school, jointly organized a painting competition among school students. About 30 students participated in the competition. 4. Students of “Deshmoret e Lirise” secondary school also gave a musical performance with different musical instruments. Activities at the school were attended by Mrs. Oliana Ifti, Deputy Minister of Environment, representatives of the Ministry of Environment and Ministry of Education. This event was covered by all the main media channels. 5. A football tournament was organized amongst Tirana’s high schools during the Ozone Week. The final match of the tournament took place on September 20th, 2014 at Dinamo Stadium. The winner received the International Ozone Day Championship Cup. 6. The logo and the message of the International Ozone Day – “Ozone Layer Protection: The Mission Continues” – were shown up continuously for four days (September 16th-20th) on a big outdoor screen mounted Tirana’s highest building - ABA Business Centre – situated in center of the city. 7. A number of programmes were broadcasted by TV and radio. Policy Dialogue” - One day meeting of Mr. Janusz Kozakiewics, International consultant, with Albanian Authorities on national policy regarding ozone depleting substances – organized on 1 October 2014. The objective of Policy Dialogue was to provide an in depth comparative analysis of Albania’s Montreal Protocol related policies & legislation with the ODS legislation in the European Union and to provide a set of recommendations on how to strengthen and harmonize relevant policies & legislation in Albania in view of the possible future accession of Albania to the European Union. Meeting with Mr. Julian Beqiri, Director of National Agency of Environment and his staff on 18 December 2014. During this meeting was discussed about the improvement of ODS legislation related to the import quotas, import licensing, export licensing. The Steering Committee Meeting has been organized on 22 December, 2014 Legal arrangements (actual/planned): Agreement signed in August 2014. Initial stages of project implementation (actual/planned): All activities are planned and the Project currently ongoing Intermediate goals achieved (actual/planned): The Ozone day was celebrated and all activities are implemented on time. Project completion and follow up: Project ongoing First disbursement date (actual/planned): August 2014 (as planned) All funds disbursed (yes/no): The first payment is disbursed. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: NO If Yes, will delay have impact on project completion date (yes/no): Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): Meeting with Law Department and Environment Department of Ministry of Environment on 20 January. During this meeting the participants discussed about the recommendations from the “Policy Dialogue” and the steps to be taken to improve the existing ODS legislation. The NOPIU has initiated the CP and Article 7 data collection. CP data was submitted to MLFS on time. Article 7 data will be provided also on time before 30 June of 2015. Materials, Posters, Leaflets were published and distributed during this period of time: Poster “Protecting Ozone, protecting you – The Mission goes on” in English language ( different sizes - 100 copies), Poster “Protecting Ozone, protecting you – The mission goes on” in Albanian language (different sizes - 200 copies); and Leaflet on “Ozone Layer Protection, Vienna Convention and Montreal Protocol” (500 copies). Legal arrangements (actual/planned): Agreement signed in August 2014. Initial stages of project implementation (actual/planned): All activities are planned and the Project currently ongoing Intermediate goals achieved (actual/planned): CP and Article 7 data was collected . Project completion and follow up: Project ongoing First disbursement date (actual/planned): August 2014 (as planned) All funds disbursed (yes/no): The first and second payments are disbursed. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: NO If Yes, will delay have impact on project completion date (yes/no): Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
FIN | UNEP | Country programme preparation | Individual | AFR | ALG | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 |  | 1993-11-01 | 1994-12-01 | 15000 | 3000 | 18000 | 18000 | 100% | 0 | 0 |  | 1950 | 390 | 2340 | 0 | 0
FIN | UNEP | Institutional support for ODS phase-out | Individual | AFR | ALG | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 |  | 1999-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 |  | 38610 | 0 | 38610 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ALG | SEV | 27 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2003-06-01 | 90010 | 0 | 90010 | 90010 | 100% | 0 | 0 |  | 11701 | 0 | 11701 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | AFR | ALG | SEV | 37 | INS | 54 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2006-07-01 | 2007-07-01 | 257000 | -1 | 256999 | 256999 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ALG | SEV | 48 | INS | 64 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2012-08-01 | 257400 | 0 | 257400 | 257400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ALG | SEV | 57 | INS | 69 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 |  | 2014-07-01 | 2014-12-01 | 257400 | 0 | 257400 | 231660 | 90% | 25740 | 25740 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country received first payment in january 2014. Art5 data report for 2013 and CP data for 2013 have been provided in May 2014 and September 2014. 2014 Ozone day was celebrated. Meeting of the steeering Committee organized in February 2014 for the assessment of the licensing system and quota issued in 2013. Another meeting of the steering commitee organized in December 2014 to fixed and allocate the 2015 quota.Legal arrangements (actual/planned): Agreement signed in April 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2014 __ All funds disbursed (yes/no): _ Final payment being _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2014-11/2016) | Individual | AFR | ALG | SEV | 73 | INS | 81 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 257400 |  | 257400 | 0 | 0% | 257400 | -5.8265e-13 | 52000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on 12 May 2015
FIN | UNEP | Project preparation for a terminal phase-out management plan | Individual | AFR | ANG | PHA | 51 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2012-03-01 | 2013-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
TRF | UNEP | Preparation of country programme | Individual | AFR | ANG | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2002-04-01 |  |  | 2002-04-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Project Financially Complete
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | ANG | SEV | 63 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2013-01-01 | 2013-07-01 | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 4/2013-3/2015) | Individual | AFR | ANG | SEV | 69 | INS | 11 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-11-01 | 2015-03-01 | 2015-03-01 |  |  | 134400 | 0 | 134400 | 69950 | 52.05% | 64450 | 18700 | 18700 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and functioning. The NOU conducted a workshop to allocate annual quotas to importers which was attended by 35 participants. The NOU conducted Customs Enforcement workshop to strengthen ODS import control in four provinces, namely Luanda, Cabinda, Bengueala and Cunene with participation of about 100 enforcement agents. The training of 60 technicians in the refrigeration and air conditioning sector on good refrigeration practices was conducted. The NOU submitted 2013 Country Programme and Article 7 Data reports in May 2014. The NOU worked with National Institutions and created 16 extension groups for supporting training and sensitization on ODS phase-out in all provinces of Angola. A new Customs Tariff for ODS entered into force in March 2014. The NOU participated at the 17th Joint ODSONET/AF meeting held in March 2014. The NOU celebrated the 2014 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings held in 2014.__ Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in July of 2013 ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities completed__ First disbursement date (actual/planned): __November 2013_ All funds disbursed (yes/no): _NO__ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | IS Renewal request for the next IS phase was prepared and submitted to ExCom 74 in Feb 2015. The NOU compiled and submitted 2014 ODS data and Country Programme report in May 2015. The country submitted IS reports and received third disbursement in Feb 2015.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ANT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 |  | 2013-03-01 | 2014-12-30 | 85000 | -8216 | 76784 | 76784 | 100% | 0 | 0 | 0 | 11050 | -1068 | 9981.92 | 0.08 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ANT | PHA | 66 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2015-04-01 | 2015-12-30 |  |  | 45850 | 0 | 45850 | 27235 | 59.4% | 18615 | 18615 | 15000 | 5961 | 0 | 3541 | 2420 | 0 | Brief progress report (actual/planned): ___Four workshops have been held and 35 customs officers have been trained. Other 50 more customs officers are already planned to be trained under current stage of the HPMP; An R&AC Train the Trainers Workshop has been held and 10 Technicians have been trained in installation, servicing and retrofitting (if applicable) to current HCFC-based and R-410A systems; forty R&AC technicians have been trained by trainers in four workshops; specialized radio and TV messages targeted to refrigeration technicians, demonstration activity on alternatives to HCFC during ozone day celebration, and distribution of public awareness material . Legal arrangements (actual/planned): SSFA signed in Nov-13___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): First disbursement in Nov-13___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Outsanding progress and financial reports, next disbursement to be processed once UMOJA is operative. NOO focused on the preparation of the HPMP second stage. Workplan agreed, information collection ongoing and stakeholders meeting convened for the preparatory mission in Jun-2015
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) |  | LAC | ANT | PHA | 73 | PRP | 17 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-11-01 | 2015-12-30 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 0 | Newly approved project | ToR for consultant drafted in Jan-2015. ToR approved in Feb-2015. Contract signed in Mar-2015. Workplan with deliverables agreed in Apr-2015. Mission to country planned for Jun-2015 to update the HCFC survey, agree on the strategy 2015-2020 and draft the proposal.
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | ANT | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1998-09-01 | 1999-04-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 |  | 3900 | -650 | 3250 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | ANT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1998-09-01 | 1999-06-01 | 30000 | -969 | 29031 | 29031 | 100% | 0 | 0 |  | 3900 | -125.97 | 3774 | 0.03 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | ANT | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-09-01 | 2001-12-01 |  | 2002-12-01 | 2004-10-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 | 0 |  | 4680 | 0 | 4680 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ANT | SEV | 38 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-06-01 | 2009-06-01 | 31200 | -13 | 31187 | 31187 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | ANT | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | ANT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2014-12-01 | 2015-12-31 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported CP data and Article 7 data on time. NOO attended the Caribbean Network meeting in Suriname in Apr-2014, and the Joint Network meeting of Latin America and the Caribbean in the Dominican Republic in Dec-2014. Celebration of International Ozone Day ___Initial stages of project implementation (actual/planned): Progressing well___ Intermediate goals achieved (actual/planned): Yes ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement in September 2013.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: | SSFA of Phase V signed in Apr-2015. First disbursement will be processed under UMOJA and once all outstanding activities and balance are completed. 2014 CP Data reported on time. NOO participated in the Caribbean Network Meeting in the Bahamas, Mar-2015. NOO discuss and agreed on workplan for HPMP second stage preparation. Country gathering necessary information and convening stakeholder meeting before preparatory mission in Jun-2015.
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | LAC | ANT | SEV | 73 | INS | 16 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 24000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. Draft approved and signed by UNEP in Mar-2015. SSFA signed by country in Apr-2015. First disbursement will be processed under UMOJA in Jun-2015
FIN | UNEP | National train the trainer programme on good practices in refrigeration | Individual | LAC | ARG | REF | 21 | TRA | 51 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 1999-12-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 |  | 27950 | 0 | 27950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Training of customs officers | Individual | LAC | ARG | REF | 32 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-02-01 |  | 2007-11-01 | 2008-12-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0
FIN | UNEP | Training programme for the refrigeration servicing sector (Phase III) | Individual | LAC | ARG | REF | 32 | TRA | 115 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2003-12-01 |  | 2009-07-01 | 2010-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0
FIN | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system | Individual | LAC | ARG | SEV | 30 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-11-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2003-10-01
CLO | UNEP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2008-11-01 | 18000 | -18000 | 0 | 0 |  | 0 | 0 | 0 | 2340 | -2340 | 0 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ARM | PHA | 62 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2011-12-01 |  | 2013-12-01 | 2014-12-14 | 31515 | 0 | 31515 | 31515 | 100% | 0 | 0 |  | 4097 | 0 | 4097 | 0 | 0 | All project activities are completed. The final report and last tranche request was prepared. The NOU and UNDP (lead agency) should submit the verification report. Financially completed. | Financially completed.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | ARM | PHA | 73 | PRP | 11 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 10000 |  | 10000 | 0 | 0% | 10000 | 8000 | 2000 | 1300 | 0 | 0 | 1300 | 0 | Approved in November of 2014. | Brief progress report (actual/planned): Preparation of a HCFC phase-out management plan (stage II) was approved at 73rd Meeting of the Executive Committee of the Multilateral Fund in November of 2014. The national consultant was hired by UNEP. The consultant will collect, review, and finalize in cooperation with the NOU and UNEP the information regarding policy, legislation, application of standards and safety requirements, availability of low GWP alternatives, and training activities. The main result will be a final report covering all elements for development of the project proposal “Preparation of a HCFC phase-out management plan (stage II)”. The NOU, UNDP and UNEP are planning to organize the stakeholders’ consultation meeting in the second half of the year of 2015. Legal arrangements (actual/planned): The national consultant was hired by UNEP. First mission (actual/planned): NOU implements all activities at national level. Involvement of international experts upon request from the NOU TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): NO (planned in the second half of the year of 2015) All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
FIN | UNEP | Regional workshop on aerosol conversion for the SEAP region | Individual | ASP | ASP | ARS | 16 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1995-06-01 |  | 1995-05-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Regional workshop on methyl bromide for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 82500 | 0 | 82500 | 82500 | 100% | 0 |  |  | 10725 | 0 | 10725 | 0 | 0
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | ASP | ASP | FUM | 34 | TRA | 43 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2002-06-01 |  | 2003-12-01 | 2005-12-01 | 80000 | -13239 | 66761 | 66761 | 100% | 0 |  |  | 10400 | -1721 | 8679 | 0 | 0
FIN | UNEP | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | Individual | ASP | ASP | HAL | 30 | TRA | 38 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2002-10-01 | 2001-10-01 |  | 2004-12-01 | 2006-12-01 | 50000 | -2360 | 47640 | 47640 | 100% | 0 |  |  | 6500 | -307 | 6193 | 0 | 0
FIN | UNEP | Development of HCFC phase-out management plan for PIC countries through regional approach | Individual | ASP | ASP | PHA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-09-01 |  | 2011-12-01 | 2013-12-01 | 494600 | 0 | 494600 | 494600 | 100% | 0 |  |  | 64298 | 0 | 64298 | 0 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche) | Multi-year | ASP | ASP | PHA | 63 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-12-01 |  |  | 134000 | 0 | 134000 | 125000 | 93.28% | 9000 |  | 9000 | 17420 | 0 | 15629 | 1791 | 0 | Brief progress report (actual/planned): UNEP continued to provide support to assist the countries to strengthen their existing legislation and regulations to effectively control imports and exports of HCFCs and HCFC-based equipment (licensing and quota system, iPIC, provision of policy advice, high level political support, development of legislation/regulations, training and capacity building, and synergy with others). UNEP OzonAction partnered with other parts of UNEP, namely the Division of Environment Law Enforcement (DLEC) and UNEP Chemicals organized the Second Joint Meeting of Ozone Officers and Customs Officer of Pacific Islands Countries in March 2014 in Tonga back-to-back with the Meeting of the PIC Network and the Workshop for Customs Officers on Controlling of Environmentally Sensitive Commodities in PIC. In collaboration with the Australia-Pacific Technical College-Samoa office (APTC), the second regional RAC technician training was organized in August 2014 in Fiji back-to-back with the PIC Thematic Meeting on HPMPs Implementation. Legal arrangement: The SSFA has been signed in May 2011 with OCO; August 2011 with SPREP; and December 2011 with SCT. First Mission: May 2011 TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | The second tranche of Regional PIC HPMP including 12 national HPMP was submitted and approved by the ExCom 74 in May 2015. UNEP keeps regular communication with the countries to complete the remaining tasks under the first tranche. Upon request by PIC countries, UNEP is developing a simple (field use) manual on good practices for servicing RAC equipment using flammable refrigerant. A thematic meeting on the implementation of the HPMP stage 1 second tranche is planned in August 2015.
FIN | UNEP | Refrigeration training workshop for Asia and the Pacific | Individual | ASP | ASP | REF | 09 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-04-01 |  | 1994-04-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 10 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-02-01 | 1999-04-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 10 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-09-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Implementation of the PIC Strategy: three thematic meetings on issues related to the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-11-01 | 2005-04-01 |  | 2006-01-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the PIC Strategy: technical assistance for other countries not included in the strategy | Individual | ASP | ASP | REF | 36 | TAS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-01-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the PIC Strategy: policy assistance and guidance to countries for development of regulations | Individual | ASP | ASP | REF | 36 | TAS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2005-12-01
FIN | UNEP | Implementation of the PIC Strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2005-12-01 |  | 2007-12-01 | 2007-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 44 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -473 | 29527 | 29527 | 100% | 0 |  |  | 3900 | -61 | 3839 | 0 | 0
ONG | UNEP | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | Individual | ASP | ASP | REF | 69 | DEM | 56 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-08-01 | 2014-06-01 | 2015-12-01 |  |  | 155000 | 0 | 155000 | 53514 | 34.53% | 101486 | 46928.38 | 54558.1 | 20150 | 0 | 6957 | 13193 | 6100.6894
FIN | UNEP | Regional workshop for Asia and the Pacific | Individual | ASP | ASP | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-11-01 |  | 1991-11-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 |  |  | 31980 | 0 | 31980 | 0 | 0
FIN | UNEP | Workshop for small and medium size enterprises on management of ODS phase-out | Individual | ASP | ASP | SEV | 12 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | ODS officers network for Asia and the Pacific (1995) | Individual | ASP | ASP | SEV | 16 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 2000-03-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Networking and Training (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | West Asian Network (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-12-01 | 169200 | -24323 | 144877 | 144877 | 100% | 0 |  |  | 21996 | -3161.99 | 18834 | 0.01 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for West Asia | Individual | ASP | ASP | SEV | 19 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 1999-03-01 | 80000 | -19056 | 60944 | 60944 | 100% | 0 |  |  | 10400 | -2477.28 | 7923 | -0.28 | 0
FIN | UNEP | West Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 |  |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | South Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 199000 | -109950 | 89050 | 89050 | 100% | 0 |  |  | 25870 | -14293 | 11577 | 0 | 0
FIN | UNEP | Asia Regional Networks for SEAP and East Asia (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 209000 | -48604 | 160396 | 160396 | 100% | 0 |  |  | 27170 | -6318.52 | 20851 | 0.48 | 0
FIN | UNEP | West Asian regional network (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Asia Regional Networks (South-East and Pacific and South Asia) | Individual | ASP | ASP | SEV | 26 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 |  |  | 27170 | 0 | 27170 | 0 | 0
FIN | UNEP | West Asian Region Network (1999) | Individual | ASP | ASP | SEV | 26 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Asia and the Pacific Regional networks (South East Asia and Pacific and South Asia) (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 219450 | -18941 | 200509 | 200509 | 100% | 0 |  |  | 28529 | -2462.33 | 26067 | -0.33 | 0
FIN | UNEP | West Asian region network (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2005-12-01 | 120750 | -15000 | 105750 | 105750 | 100% | 0 |  |  | 15698 | -1950 | 13748 | 0 | 0
FIN | UNEP | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | Individual | ASP | ASP | SEV | 30 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-05-01 | 2003-06-01 | 150000 | -15122 | 134878 | 134878 | 100% | 0 |  |  | 19500 | -1965.86 | 17534 | 0.14 | 0
FIN | UNEP | West Asian regional network (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 124000 | -15001 | 108999 | 108999 | 100% | 0 |  |  | 16120 | -1950.13 | 14170 | -0.13 | 0
FIN | UNEP | South East Asia and the Pacific and South Asia regional networks (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2002-06-01 | 2003-06-01 | 225000 | -20468 | 204532 | 204532 | 100% | 0 |  |  | 29250 | -2660.84 | 26589 | 0.16 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | BAH | PHA | 50 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-06-01 | 2008-07-01 |  | 2014-12-01 |  | 210000 | -130000 | 80000 | 80000 | 100% | 0 |  | 0 | 27300 | -16900 | 10400 | 0 | 0 | Project Completed | Project Completed
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BAH | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2013-08-01 | 2014-05-14 | 105000 | -25917 | 79083 | 79083 | 100% | 0 |  |  | 13650 | -3369 | 10281 | 0 | 0 | Project financialy Completed | Project financialy Completed
TRF | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2011-11-01 |  | 2014-12-01 |  | 95000 | -95000 | 0 | 0 |  | 0 |  | 0 | 12350 | 0 | 0 | 12350 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 68/33, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 68/33, respective progress is under the HPMP project
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Multi-year | ASP | BAH | PHA | 68 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2014-12-01 | 2015-12-01 |  |  | 120000 | 0 | 120000 | 51015 | 42.51% | 68985 |  | 68985 | 15600 | 0 | 133 | 15467 | 0 | Brief progress report (actual/planned): - Enact the new ODS Regulation 54/2014 for the control of ODS and start preparing the respective bylaws under the enforcement component of the HPMP - Concluding the executing arrangements at the national level where Bahrain Society of Engineers (BSE) will be the main executing agency under the supervision of the Supreme Council of Environment (SCE) - Finalize and sign the country contracts - Form Project Steering Committee composed of SCE and BSE with advisory role to UNEP • Legal arrangements(actual/planned): Two legal instruments signed; one with the Bahrain Society of Engineers and one with the Supreme Council for Environment • First mission (actual/planned): No mission needed since UNEP-ROWA is based in Bahrain • TOR completed(actual/planned): TORs for the technical components were drafted and reviewed by the Project Steering Committee • First disbursement date (actual/planned): First disbursement under both legal instruments will be in 2015 since contracts signed end of 2014 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in concluding national executing arrangements, signing the contracts and start of work. After signature of contracts end of 2014, expedited work-plan is agreed to compensate delays • If Yes, will delay have impact on project completion date (yes/no): Yes, impact on submission the 2nd tranche by one year • Any ongoing problems (yes/no): No • If Yes, is any action required by ExCom: No | # Finalize the preparatory arrangements for the technical components of reviewing/updating the national standards and the establishment of national certification scheme # Processing the first payments of the country contracts (expected to be received by the country by end of June 2015) # Develop special publication on the enforcement of the new ODS Regulation as part of the enforcement campaign under the HPMP and design special enforcement sessions for different stakeholders # Start forming the working group of updating the national certification scheme in cooperation with the Ministry of Labor |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | ASP | BAH | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-05-01 | 1999-12-01 |  | 2001-12-01 | 2001-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training | Individual | ASP | BAH | REF | 26 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2001-12-01 | 2003-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2001-05-01
FIN | UNEP | Country programme preparation | Individual | ASP | BAH | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-06-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | ASP | BAH | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | BAH | SEV | 31 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | BAH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | BAH | SEV | 47 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | BAH | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | BAH | SEV | 60 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-12-01 |  | 2012-12-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | BAH | SEV | 68 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-11-01 | 2014-11-01 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The senior management in the Supreme Councel for Enviroment (SCE) have been updated on the progress in achieving MP obligations and NOU received the required support for implementation planned activities. A national committee has been established from related government & private authorities to enforce the quota system through distributing the imported HCFCs amongst registered companies & end users. The ISP continued implementing activities under its ISP specifically the NOU has had several meetings with the Bahrain Society of Engineering (BSE) and CAP in order to sign an agreement with BSE to implement capacity building components of HPMP . They conducted national activities in celebration of the Ozone Day. In Sep-2014 the King of Bahrain issued national law no. 54 on monitoring and control of ODS. This law was in agreement with the GCC unified regulation on monitoring and control of ODS. Legal arrangements (actual/planned): Legal instrument was signed in Sep-2014 and first payment of disbursed. Initial stages of project implementation (actual/planned): Although legal instrument signed late, NOU continued project implementation. NOU did not submit the required report to transfer the second payment. Intermediate goals achieved (actual/planned): Article 7 and CP data was collected and reports submitted to OS and MLFS for the year of 2013. Project completion and follow up: Project is being implemented and is expected to complete with some delay. First disbursement date (actual/planned): US$ 30,000 was disbursed in November 2014 for current cycle. All funds disbursed (yes/no): No. Project ongoing & delayed. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay was faced in processing of legal instrument initially due to retirement of ODS Officer & UNEP changes as advised previously, including OFO’s agreement to accept the ISP format to be used. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No, as agreement was signed and first payment disbursed, implementation progressing. If Yes, is any action required by ExCom: No. | Over 2015 based on the national law on implementation of Montreal Protocol issued in line with the GCC unified legislation, the Supreme Council established a committee consisting of several private and governmental authorities in order to enforce the law. The committee met and discussed establishing by-laws to enforce this law. NOU also progressed on HPMP component related to the Bahrain Society of Engineers (BSE), in order to implement over 2015. NOU remains active in participating in regional and international related meetings. NOU and senior officials of the Supreme Council are attending international and regional workshops relating to HFCs also.
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | BAR | PHA | 54 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2010-10-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BAR | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-01-01 | 2009-07-01 |  | 2013-12-01 | 2014-12-31 | 85000 | -33141 | 51859 | 51859 | 100% | 0 | 0 | 0 | 11050 | -4308 | 6742 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | BAR | PHA | 69 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-09 | 2016-04-01 | 2016-04-01 |  |  | 74000 | 0 | 74000 | 20000 | 27.03% | 54000 | 54000 | 54000 | 9620 | 0 | 0 | 9620 | 4875 | Brief progress report (actual/planned): the Draft Terms of Reference (TOR) for the Policy and Legislative Component of the HPMP and the TOR for the Capacity Building Component of the HPMP have been finalized, and are pending approval by the Permanent Secretary before requests for proposals are disseminated.___ Legal arrangements (actual/planned): SSFA signed in Dec-13___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): First disbursement in Dec-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in government administrative processes have delayed expeditures ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | A meeting was held with the Environmental Protection Department, Ministry of Environment and Drainage; the Refrigeration and Air Conditioning Association of Barbados; and the Samuel Jackman Prescod Polytechnic on Feb-2015 to discuss how elements of the Capacity building component of the HPMP would be implemented. PS approved TORs in Jun-2015, requests for proposals will be disseminated.
FIN | UNEP | Development of RMP | RMP | LAC | BAR | REF | 30 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-05-01 | 2005-07-01 | 30000 | -7982 | 22018 | 22018 | 100% | 0 | 0 |  | 3900 | -1037.66 | 2862 | 0.34 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | Individual | LAC | BAR | REF | 43 | TAS | 10 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2004-07-01 | 2005-03-01 | 2006-12-01 |  | 2011-03-01 | 2012-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | BAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-12-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | BAR | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1997-12-01 |  | 1998-12-01 | 1999-10-01 | 136000 | -1050 | 134950 | 134950 | 100% | 0 | 0 |  | 17680 | -136 | 17544 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BAR | SEV | 26 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2005-12-01 | 2005-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of Institutional strengthening project (phase III) | Individual | LAC | BAR | SEV | 42 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2007-11-01 | 2009-07-01 | 58500 | -560 | 57940 | 57940 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase III, year 2) | Individual | LAC | BAR | SEV | 46 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2008-01-01 | 2007-07-01 |  | 2011-03-01 | 2012-06-01 | 58500 | 0 | 58500 | 58500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BAR | SEV | 61 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-06-01 |  | 2013-07-01 | 2013-12-31 | 117000 | -2760 | 114240 | 114240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | BAR | SEV | 68 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2015-02-01 | 2015-12-31 |  |  | 117000 | 0 | 117000 | 46800 | 40% | 70200 | 70200 | 46800 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): 2013 CP data and Article 7 data reported on time to the Multilateral Fund and Ozone Secretariats on Mar-2014. The NOU continued to liaise with the licensing and enforcement offices to ensure that trade in Ozone Depleting Substances was effectively monitored and managed. The NOU disseminated information on the Customs (List of Prohibited and Restricted Imports and Exports) Order 2009 and the Amendment Order 2010, process to import restricted refrigerant, Customs Quick tool to additional Customs Brokers and Owners of Refrigeration and Air Conditioning companies as part of public awareness activities. NOU, one representative from the Barbados National Standards Institution and the President of the Refrigeration and Air Conditioning (RAC) Association of Barbados participated in the workshop on Standards in RAC sector in the context of the HCFC Phase out in the Caribbean Region, Oct-2014. Barbados participated in the Caribbean Netwok meeting in Suriname, Apr-2014 and in the Latin American and Caribbean Ozone Officers Meeting in the Dominican Republic Dec-2014.___ Legal arrangements (actual/planned): Agreement signed in Jul-2013.___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement issued Aug-2013.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in government administrative processes have delayed expeditures ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | NOU gathered, collected and cross-checked data with Department of Commerce and Plant Quarantine Unit. Country Programme implementation and Article 7 data reported on Apr-2015. A Training Session on the use of the HCFC Quota Tracking Spreadsheet developed by the NOU was held for Licensing Officers on the Feb-2015. NOU consulted with representatives from the Plant Quarantine Unit and the Plant Pathology Unit on the issue of possible collaborative initiatives that could be undertaken concerning Methyl Bromide Alternatives on Feb-2015. A meeting was held with the Department of Commerce and Consumer Affairs on Jan-2015 to discuss the administration of the Licensing and Quota System. A meeting of the National Ozone Steering Committee was held on May-2015. The NOU was represented at a meeting of the Refrigeration and Air Conditioning Association on Jan-2015 during which plans from the implementation of the HPMP were presented and discussions on the need to strengthen the RAC Association and the way forward with respect to alternative refrigerants were held. A presentation on the importance of the Ozone Layer was made to fifteen (15) children from a local community at the Community Centre on Feb-2015. Barbados participated in the Caribbean Ozone Officers' Network Meeting held in The Bahamas March 25-27, 2015.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BDI | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 |  | 9620 | 0 | 9620 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2011-12-01 |  | 2013-12-01 | 2014-12-01 | 41000 | -270 | 40730 | 40730 | 100% | 0 | 0 |  | 5330 | -35 | 5295 | 0 | 0 | Project Financially Complete
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BDI | PHA | 65 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 3646 | 2204 | 1950 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) |  | AFR | BDI | PHA | 73 | TAS | 31 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 | -5.8265e-13 | 15000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on 21 April 2015
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan |  | AFR | BDI | PHA | 73 | TAS | 32 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2015-11-30 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 | -5.8265e-13 | 0 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): __ .Discussions with the country started in December 2014. and TOR drafted in December 2014 in collaboration with the country. Consultant identified in March 2015 and country informed Legal arrangements (actual/planned): (Yes/No): No_ First mission (actual/planned): __ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | UNEP organized a mission in March 2015 to discuss the TOR and the way to deal with the verification report.
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | BDI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: training technicians in good management practices | Individual | AFR | BDI | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 14 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2006-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 15 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-06-01 |  | 2006-07-01 | 2010-12-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 |  | 2925 | 0 | 2925 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | AFR | BDI | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-05-01 |  | 1998-09-01 | 1999-03-01 | 40000 | -10000 | 30000 | 30000 | 100% | 0 | 0 |  | 5200 | -1300 | 3900 | 0 | 0
FIN | UNEP | Establishment of an Ozone Unit | Individual | AFR | BDI | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2002-07-01 | 2003-07-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | AFR | BDI | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-12-01 | 2005-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BDI | SEV | 44 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | BDI | SEV | 50 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | BDI | SEV | 57 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-12-01 | 2011-03-01 |  | 2013-03-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2014-12/2015) | Individual | AFR | BDI | SEV | 71 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA sent to country in June 2014 for signature. Country reported 2013 Art 7 and 2013 CP data . Country celebrated the 2014 Ozone day. NOU coordinated the 3 refrigeration workshops for 75 participants and the two Customs trainig workshop for 40 customs officers organized under the HPMP in 2014. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): October 2014 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _No. Payment request in April 2014 but returned by FMO, for SSFA BAC to be put in UMOJA codes.__ All funds disbursed (yes/no): _ n/a_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | SSFA to be re-initiated with 60,000$
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | BEN | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2007-07-01 |  | 2007-10-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2009-07-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BEN | PHA | 57 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | TAS | 22 | A | I |  | 0 | 0 | 0 |  | 2009-11-01 | 2009-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BEN | PHA | 63 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 85000 | -3686 | 81314 | 81313.59 | 100% | 0.41 | 0 |  | 11050 | -479 | 10571 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | BEN | PHA | 70 | TAS | 28 | A | I |  | 1.4 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Brief progress report (actual/planned):Country signed the SSFA in June 2014. Country organized 2 workshops training for refrigeration technicians in August 2014 in Porto Novo (53 technicians) and Cotonou (101 technicians). A total of 154 technicians trained. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | In April 2015, Organisation in Cotonou of 1 workshop for30 refrigeration technicians on HCFCs recovery and good practices and 3 more in May 2015 in the other regions for 75 participants.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | BEN | REF | 27 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2000-12-01 | 2001-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | BEN | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1995-10-01 | 1995-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | BEN | SEV | 18 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | BEN | SEV | 28 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-09-01 | 2001-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | BEN | SEV | 33 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | BEN | SEV | 40 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | AFR | BEN | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-06-01 | 2008-06-01 |  | 2008-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | AFR | BEN | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-12-01 |  | 2011-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | AFR | BEN | SEV | 62 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-04-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | BEN | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in March 2014. Country reported in September 2014 the 2013 CP data report and 2013 data Art 7. Country celebrated also the Ozone day in September 2014. Legal arrangements (actual/planned): Agreement signed in March 2014. All activities under the SSFA are completed (as planned) Not yet___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ Final payment being _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country submitted activity and expenditure report on IS implementation in March 2015 and UNEP raised the second payment in April 2015.
FIN | UNEP | Formulation of a transition strategy for MDI | Individual | ASP | BGD | ARS | 50 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Transition strategy for phasing out use of CFCs in the manufacturing of MDIs | Individual | ASP | BGD | ARS | 52 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2011-07-01 |  | 2011-12-01 | 2012-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2007-12-01
FIN | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-04-01 | 2009-04-01 | 39500 | 0 | 39500 | 39500 | 100% | 0 |  |  | 5135 | 0 | 5135 | 0 | 0 |  |  |  | 2007-12-01
FIN | UNEP | National ODS phase-out plan: training programme for custom officers (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 |  |  | 2730 | 0 | 2730 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BGD | PHA | 56 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TRA | 32 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 177175 | 0 | 177175 | 177175 | 100% | 0 |  |  | 23033 | 0 | 23033 | 0 | 0
FIN | UNEP | National ODS phase-out plan (fifth and sixth tranches) | Multi-Year | ASP | BGD | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-12-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 |  |  | 3445 | 0 | 3445 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | BGD | PHA | 65 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-12-01 | 2013-11-01 | 2015-12-01 |  |  | 230000 | 0 | 230000 | 54170 | 23.55% | 175830 |  | 175830 | 29900 | 0 | 10696 | 19204 | 0 | Brief progress report (actual/planned): Amendment done to the “Ozone Depleting Substances (Control) Rules, 2004”. So far 614 technicians trained by 4 master trainers through 12 Training workshops. 1,000 copies of 5 booklets on good servicing practice printed in Bengali. Factsheet on energy efficiency and servicing sector printed and distributed. Legal arrangement (actual/ planned): SSFA signed in November 2013. First mission (actual/ planned): 8-11/08/2010. TOR completed (actual/ planned): N/A. First disbursement date: 16/12/2013. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delayed in signing the agreement. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Enforcement Training organized in Feb. 2015. DoE and NBR agreed to prepare a MoU for inter-agency collaboration on Montreal Protocol enforcement. Customs Quick Tool and the “Training Manual: Green Trade for the Protection of the Ozone Layer” were prepared and distributed. 5 units of refrigerants identifiers delivered in 2nd quarter of 2015. Legal arrangement (actual/ planned): In May 2015, additional US$60,000 transferred to the government.
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | BGD | REF | 29 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2001-12-01 |  | 2004-07-01 | 2004-07-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 |  |  | 2925 | 0 | 2925 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and implementation of a national technicians training programme | Individual | ASP | BGD | REF | 29 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-03-01 | 2001-12-01 |  | 2004-12-01 | 2009-12-01 | 88000 | -24701 | 63299 | 63299 | 100% | 0 |  |  | 11440 | -3211.02 | 8229 | -0.02 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BHA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 |  | 2013-12-01 | 2014-12-30 | 85000 | -5892 | 79108 | 79108 | 100% | 0 | 2.1827e-13 |  | 11050 | -766 | 10284 | 0 | 2.8375e-14 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2013-12-01 | 2014-01-31 | 18200 | 0 | 18200 | 18200 | 100% | 0 | 0 |  | 2366 | 0 | 2366 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | BHA | PHA | 71 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-11-01 | 2016-04-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 15000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Generic TORs drafted for contracting in 2015 closer to the submission of corresponding tranche ___ Legal arrangements (actual/planned): ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Generic ToRs approved in Feb-2015. Contracting of new consultants should follow new procedures under UMOJA. Contracting process will start in Jun-2015 when UMOJA goes live.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | BHA | PHA | 71 | TAS | 21 | A | I |  | 0.2 |  | 0 |  | 2013-12-01 | 2014-10-31 | 2016-12-01 | 2016-12-31 |  |  | 49550 | 0 | 49550 | 1290 | 2.603% | 48260 | 0 | 12065 | 6442 | 0 | 0 | 6442 | 0 | Brief progress report (actual/planned): SSFA was not signed by the Government. The SSFA was drafted and was signed by UNEP. The country informed that the procedure requires the approval of Cabinet Ministers. It needs extra time. Legal arrangements (actual/planned): SSFA drafted in Jan-2014 and sent to country for considerations___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve:. ___ If Yes, will delay have impact on project completion date (yes/no): yes ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Follow up on IS SSFA signature in Feb-2015, Mar-2015 and Apr-2015. Country sent an amended version of SSFA approved by Cabinet in May-2015; this will require a new UNEP's signature of the amended version. Country also requested to modify some clauses; these proposed modifications required consultation with the legal department. Legal department answered requested modification to the agreement in Jun-2015. Agreement as cleared by legal department sent to country for their consideration in Jun-2015.
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | BHA | REF | 23 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-08-01 | 1998-02-01 |  | 2005-09-01 | 2008-12-01 | 26500 | -8334 | 18166 | 18166 | 100% | 0 | 0 |  | 3445 | -1084 | 2361 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | BHA | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-05-01 | 2003-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | BHA | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | BHA | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-03-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a terminal phase-out plan | RMP | LAC | BHA | SEV | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-12-01 | 2002-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project: phase 2 (one year) | Individual | LAC | BHA | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-04-01 |  | 2006-07-01 | 2007-07-01 | 21666 | 0 | 21666 | 21666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase II ) | Individual | LAC | BHA | SEV | 42 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2006-07-01 | 2009-07-01 | 21667 | 0 | 21667 | 21667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III ) | Individual | LAC | BHA | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-06-01 | 2008-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BHA | SEV | 61 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2012-06-01 |  | 2014-01-01 | 2014-12-31 | 60000 | 0 | 60000 | 59950 | 99.92% | 50 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financialy completed. Renewal approved at 72nd ExCom. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2014-3/2016) | Individual | LAC | BHA | SEV | 72 | INS | 22 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-03-31 | 2016-03-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Renewal request prepared on Feb-2014. Renewal request submitted and comments from MLFS addressed in Apr-2014. Renewal approved in May-2014. ___ Legal arrangements (actual/planned): Draft SSFA prepared in May-2014 and sent to country for comments in Jun-2014. Draft SSFA submitted for the consideration and approval of Cabinet in Jul-2014. Adjustments required by country on the text in Aug-2014 and Sep-2014. SSFA approved for signature in Oct-2014. SSFA signed by UNEP and sent to country for signature in Nov-2014 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): .___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA by PS requires previous approval of Cabinet. Adjustments requested to the text were addressed by UNEP as early as possible. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: n/a. | Follow up on SSFA signature in Feb-2015, Mar-2015 and Apr-2015. Country sent an amended version of SSFA approved by Cabinet in May-2015; this will require a new UNEP's signature of the amended version. Country also requested to modify some clauses; these proposed modifications required consultation with the legal department. Legal department answered requested modification to the agreement in Jun-2015. Agreement as cleared by legal department sent to country for their consideration in Jun-2015. Country organized the 2015 Caribbean Network Meeting in Mar-2015.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | BHU | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan | Individual | ASP | BHU | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BHU | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2010-12-01 | 2011-04-01 | 30000 | -4803 | 25197 | 25197 | 100% | 0 |  |  | 3900 | -624 | 3276 | 0 | 0 | Project is financially completed | Project is financially completed
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | ASP | BHU | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-12-01 | 2011-04-01 | 55000 | -11314 | 43686 | 43686 | 100% | 0 |  |  | 7150 | -1471 | 5679 | 0 | 0 | Project is financially completed | Project is financially completed
COM | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-12-01 |  | 2013-11-01 |  | 100000 | 0 | 100000 | 97745 | 97.75% | 2255 |  | 2255 | 13000 | 0 | 10886 | 2114 | 0 | Brief progress report (actual/planned): Procurement of the 2nd set of equipment. Legal arrangement (actual/ planned): The SSFA signed in March 2012, was completed and closed in the 1st quarter of 2014. First mission (actual/ planned): 8-11/06/2010. TOR completed (actual/ planned): N/A. First disbursement date: May 2012. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): 3 units of refrigerants identifiers with UNEP pending delivery. Financial reporting within UNEP pending to close this project.
ONG | UNEP | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | BHU | PHA | 70 | TAS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2016-07-01 | 2016-07-01 |  |  | 70000 | 0 | 70000 | 32500 | 46.43% | 37500 |  | 37500 | 9100 | 0 | 0 | 9100 | 0 | Brief progress report (actual/planned): The first-ever Certificate Course Curriculum for Refrigeration and Air Conditioning developed. The National Stakeholder Workshop on HPMP and climate and energy linkages held in June 2014. Officials from MOLHR took part in the workshop o Good Practices of RAC Servicing in Manila, Philippines, in May 2014. A two week Training of Trainers at TTI Thimphu held in August 2014. In 2014 alone, over 80 Customs officers, Customs brokers and officers from Department of Trade received training on ODS control with special focus on HCFCs. Legal arrangement (actual/ planned): The agreement was signed in May 2014. First mission (actual/ planned): March 2012. TOR completed (actual/ planned): N/A. First disbursement date: 12/06/2014 All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delayed reporting by the government. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. Awareness event with the Hotels Associations organized in January 2015. National Customs Manual was launched on the World Customs Day on 26 January 2015. 3 units of refrigerants identifiers procured in 2nd quarter of 2015. Legal arrangement (actual/ planned): As of 22 May 2015, additional US$33,000 is pending transfer to the government.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | BHU | PHA | 73 | TAS | 22 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-05-01 | 2016-04-01 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Agreement on implementation modality and a general timeline reached with the government. Legal arrangement (actual/planned): DMFA (agreement) drafted. First mission (actual/ planned): The 4th quarter of 2015. TOR completed (actual/ planned): A consultant to be hired in the 4th quarter of 2015. First disbursement date: The 4th quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/ planned): DMFA signed in March 2015. TOR being prepared. An international consultant identified.
FIN | UNEP | Implementation of the RMP: train the trainer programme for customs and enforcement officers | Individual | ASP | BHU | REF | 45 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2006-04-01 |  | 2006-09-01 | 2007-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | BHU | REF | 45 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-10-01 |  | 2006-09-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Preparation of country programme/RMP project | Individual | ASP | BHU | SEV | 43 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  | 2005-07-01 | 2006-08-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | BHU | SEV | 43 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-07-01 | 2006-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I) | Individual | ASP | BHU | SEV | 46 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2008-07-01 |  | 2007-07-01 | 2008-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | BHU | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | BHU | SEV | 58 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | BHU | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-11-01 |  | 2013-11-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed | Project is financially completed
ONG | UNEP | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | BHU | SEV | 71 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 |  | 45000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project is running smoothly under the able guidance and leadership of the ozone officer. Very good quality of implementation. The Government should take steps to further strengthen the adaptation of curriculum in the Technical College. This is a very good initiative of the Government. Capacity building of national stakeholders is strengthened through for example, training of customs (9-11 Jan 2015), border dialogues on enforcement (Nov.2014), regular consultation with Steering Committee of national stakeholders and sectoral committees of Line Ministeries and key HCFC consumers like Customs, Ministry of Labour, Hotel Association, clearing agents. Ozone Day was celebrated in 2014 and A7 data for 2014 submitted to the Ozone Secretariat.Two instructors from Technical Training Institute attended a training programme on Room Air Conditioners Service Technicians 8-9 March 2014 in Guwahati, India. Legal arrangements(actual/planned): The SSFA was signed in April 2014 and the first payment of USD 15000 was released in June 2014. Initial stages of project implementation(actual/planned): N/A since Project is ongoing. Intermediate goals achieved (actual/planned): Assisting in the implementation of stage I of the HPMP, implementing HCFC quota system from 2013 onwards, import restrictions for all HCFCs including HCFC-22 (as planned) First disbursement date (actual/planned): June 2014 as planned. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Capacity building of national stakeholders was strengthened through training of customs (9-11 Jan 2015), border dialogues on enforcement (January 2015), regular consultation with Steering Committee of national stakeholders and sectoral committees of Line Ministeries and key HCFC consumers like Customs, Ministry of Labour, Hotel Association, clearing agents. One major output of a successful implementation of IS project was timely submission of A7 data in April 2015. Continue the NOU operation with IS renewal in the 74th Excom in May 2015
FIN | UNEP | Project preparation request for TPMP | Individual | AFR | BKF | PHA | 47 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | BKF | PHA | 50 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 100900 | -631 | 100269 | 100269 | 100% | 0 | 0 |  | 13117 | -82.03 | 13035 | -0.03 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 102100 | 0 | 102100 | 102100 | 100% | 0 | 0 |  | 13273 | 0 | 13273 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BKF | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | AFR | BKF | PHA | 56 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | BKF | PHA | 57 | TAS | 28 | A | I |  | 0 |  | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15397 | 203 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | BKF | PHA | 70 | TAS | 33 | A | I |  | 2 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 15600 | 0 | 0 | 15600 | 0 | Brief progress report (actual/planned): SSFA done with 2014 budget of USD60, 000. Country signed the SSFA in March 2014. Country organized 3 workshops training for refrigeration technicians in November 2014 in Ouagadougou and Bobo-Dioulasso: a total of 77 technicians trained. Also 3 workshops training were organized to train custom officers in Ouagadougou, Bobo-Dioulasso and Tenkodogo in December 2014: a total of 54 customs were trained. Legal arrangements (actual/planned): Agreement signed in March 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _August 2014 __ All funds disbursed: YES_ .__ Any delay? (yes/no): No ___ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | 2014 CP data and 2015 Art7 data reported. Training of 25 Customs officer on identification of HCFC organised in Ouaga in March 2015. 30 refrigeration technicians trained on recovery and recycling in March 2015.
FIN | UNEP | Training for refrigeration repair technicians | Individual | AFR | BKF | REF | 11 | TRA | 03 | A | I | CFC | 23 | 23 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1996-11-01 |  | 1996-11-01 | 1999-04-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 |  | 5395 | 0 | 5395 | 0 | 0
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | BKF | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | BKF | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-11-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0
FIN | UNEP | Establishment of the Ozone Board | Individual | AFR | BKF | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-12-01 | 1996-11-01 |  | 1997-06-01 | 1996-02-01 | 83500 | 0 | 83500 | 83500 | 100% | 0 | 0 |  | 10855 | 0 | 10855 | 0 | 0
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs training) | Individual | AFR | BKF | SEV | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-10-01 | 1994-12-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 |  | 1885 | 0 | 1885 | 0 | 0
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | BKF | SEV | 22 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 1999-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | BKF | SEV | 27 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-07-01 | 2001-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase IV) | Individual | AFR | BKF | SEV | 33 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-01-01 | 2003-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase 5) | Individual | AFR | BKF | SEV | 38 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | BKF | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | BKF | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | BKF | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | BKF | SEV | 62 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | BKF | SEV | 68 | INS | 32 | A | I |  | 0 |  | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 | 2015-12-01 |  |  | 72410 | 0 | 72410 | 39210 | 54.15% | 33200 | 0 | 33200 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country submitted final expenditure and activity report December 2014. Country submitted an IS renewal in December 2014. 2013 CP data and 2013 CP data reported in September 2014. 2014 Ozone day celebrated in September 2014 in collaboration with the Ozone secretariat. Ozone Secretariat sponsored some awareness activities organized in September 2014. Legal arrangements (actual/planned): Agreement signed in January 2013. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in feb 2013 __ All funds disbursed (yes/no): Yes_ Final payment in January 2015_ Any delay? (yes/no): YES___ If Yes, reasons for delay & action plan to resolve: Change of NOO ___ If Yes, will delay have impact on project completion date (yes/no): _YES __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Final payment of 16434$ sent on January 2015
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | BOL | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 2001-01-01 | 1999-02-01 |  | 2001-12-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Completion of country programme preparation | Individual | LAC | BOL | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1995-10-01 | 1999-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Ozone Governmental Commission (COGO) | Individual | LAC | BOL | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 1999-12-01 | 91000 | 0 | 91000 | 91000 | 100% | 0 | 0 |  | 11830 | 0 | 11830 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BOL | SEV | 26 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 |  | 7887 | 0 | 7887 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | BOL | SEV | 34 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 |  | 7887 | 0 | 7887 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project | Individual | LAC | BOL | SEV | 40 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | BOL | SEV | 47 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BOL | SEV | 53 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | BOL | SEV | 59 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-12-01 |  | 2012-06-01 | 2013-12-01 | 39434 | 39434 | 78868 | 78868 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 8/2012-7/2014) | Individual | LAC | BOL | SEV | 67 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-11-01 | 2014-07-01 |  | 2014-12-31 | 2014-12-31 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report: NOO attended the Network meetings and back to back bilateral sessions were carried to cover information gaps of government officers. The implementation of the SSFA (agreement) completed with six months of delays. Intermediate goals achieved as planned for the year 2014: (a) Progress and financial reports prepared by the NOU. (b) Third cash advance released; (c) 2014 budget and work plan duly implemented; (d) ODSs license system implemented; (e) NOO collected ODS data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (f) Article 7 data and CP progress report data submitted in 2014; (g) NOU is responsible for providing support to the HPMP implementation. (h) On 16 September, the Minister of Environment cellebrated the International Ozone Day trough a thematic Fair on the Ozone Layer Protection with the attendance of students from vocational an middle schools, universities and RAC technicians associations. (i) Project renewal submitted to the 73 ExCom meeting. Legal arrangements (actual/planned): November 2012/Planned for October 2012. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: November 2012/ Planned for November 2012. All funds disbursed? Yes. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Despite UNEP providing capacity building and support to bring new NOO to speed up project implementation, frequent changes of NOU are attempting against building national capacity. If Yes, will delay have impact on project completion date? Yes, 6 months of delays are expected due to delays in signing the agreement. Any ongoing problems? Yes. If Yes, is any action required by ExCom: ExCom may encourage the country to appoint (and keep on board) a dedicated NOO with high degree in: managerial skills, environmental sound technology and related know-how. | Project financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase IX: 12/2014-11/2016) | Individual | LAC | BOL | SEV | 73 | INS | 39 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-30 |  |  | 78867 | 0 | 78867 | 0 | 0% | 78867 | 0 | 31546 | 0 | 0 | 0 | 0 | 0 | Newly approved project. Work Plan and budget drafted in December 2014. | Brief progress report: Legal arrangement was signed by UNEP in April 2015/initially planned for February 2015. Signature of the government is still in progress, since two Minsitries have to sign this legal agreememt in Bolivia. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: N/A. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: There is no NOO in Bolivia since March 2015. Frequent turn over of NOOs is attempting against the continuity of the ISP. Political intervention of the ExCom is recomended. If Yes, will delay have impact on project completion date? Yes, at least six months delays expected . Any ongoing problems? Yes. If Yes, is any action required by ExCom: ExCom may encourage the country to appoint (and keep on board) a dedicated NOO with high degree in: managerial skills, environmental sound technology and related know-how.
FIN | UNEP | Country programme preparation | Individual | AFR | BOT | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1994-07-01 |  | 1994-06-01 | 1994-12-01 | 30000 | 10000 | 40000 | 40000 | 100% | 0 | 0 |  | 3900 | 1300 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the Ozone Office) | Individual | AFR | BOT | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1997-07-01 |  | 2003-12-01 | 2003-12-01 | 90200 | 0 | 90200 | 90200 | 100% | 0 | 0 |  | 11726 | 0 | 11726 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | BOT | SEV | 41 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-06-01 | 2005-12-01 |  | 2008-02-01 | 2012-12-01 | 78173 | 0 | 78173 | 78173 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BOT | SEV | 53 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2011-05-01 | 2009-11-01 |  | 2014-12-01 |  | 78173 | 0 | 78173 | 78173 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The Country collected 2013 ODS data and submitted to OS and MFS. The NOU celebrated 2014 international ozone day through newsletter articles on ozone issues, dissemination of ozone messages through three mobile networks and speech read by the Minister on the ozone day. The NOU organised 2 National Ozone Steering Committee meetings to discuss the allocation of quotas for 2015 inorder for the country to meet 2015 HCFC target. NOU participated in all Regional Network and Montreal Protocol meetings._ Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in March 2011. Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities completed__ First disbursement date (actual/planned): The first disbursement was made in April 2011_ All funds disbursed (yes/no): _Yes_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country delayed in approving and establishing HCFC ODS Regulation including licensing and quota system__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project completed
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | AFR | BOT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2015-12-01 |  |  | 78173 | 0 | 78173 | 0 | 0% | 78173 | 0 | 78173 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The country established and operationalised HCFC licensing and quota system. The country collected 2014 ODS data. The NOU celebrated 2014 international ozone day through newsletter articles on ozone issues, conducted schools competition on ozone stories and ozone songs. NOU undertook the survey of all importers of HCFC and registered all the importers for 2015. NOU participated in all Regional Network and Montreal Protocol meetings..__ Legal arrangements(actual/planned): SSFA was signed by country in April, 2015. Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities completed__ First disbursement date (actual/planned): The first disbursement was (20,570.60) made in April, 2015._ All funds disbursed (yes/no): _NO__ Any delay?(yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: Country could not start implementation of project before establishing licensing and quota system, a condition for approval of the project__ If Yes, will delay have impact on project completion date (yes/no): _Yes_ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | The NOU drafted HPM and submitted to UNEP for review, the HPMP is scheduled for submission to the 75 Ex-com. NOU processed the HCFC quota allocation for 2015 ; hosted a tv debate on the country's readiness to meet 2015 HCFC phase-out target. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BRU | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-06-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | BRU | PHA | 66 | TAS | 12 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2015-08-01 |  |  | 123000 | 0 | 123000 | 79322 | 64.49% | 43678 |  | 43678 | 15990 | 0 | 5762 | 10228 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented since 2013 and continued in 2014. The NOU continues to conduct regular checks with retailers and servicing workshops to inspect whether HCFC containers are properly labelled as required. In 2014, additional 9 training workshops were organized to train 121 RAC technicians at the training center established under HPMP, Jefri Bolkiah Vocational School. The certification system has been implemented in conjunction with the training workshops of RAC technicians on code of good practice. Only RAC technician passed the theoretical and practical examination will be certified by Department of Environment, Park and Recreation, which houses the NOU. In total, 191 RAC technicians were trained and certified from 15 workshops under HPMP since 2013. As the Department of Mechanical and Electrical (DME) has already had the certification system for technical companies that would like to obtain the government projects, DEPR initiated the discussion with DME to standardize or harmonize the certification program so that a single certification system would be in place so that it would accommodate works in the private as well as government sectors. Moreover, to support HCFC phase-out effort in the country, requirement of ODS-free equipment installation in tender issued by the government has been applied to all types of RAC equipment. DEPR also initiated the dialogue with DME as well as the Energy Department on the ban of HCFC based equipment. In 2014, posters on non-HCFC based air-conditioner were developed and produced to emphasize the use of non-HCFC based air conditioners Legal arrangements (actual/planned): The SSFA has been signed in August 2012. First Mission: September 2012. TOR completed: N/A First disbursement date: December 2012 All funds disbursed (yes/no): No, the last funds will be released by August 2015. Any delay? (yes/no): Yes. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Training workshops of RAC technicians is planned in 2015, but will be organized when the second tranche of HPMP is released to the country. As a follow-up to the discussion in 2014, the meeting between DEPR, DME and Energy Department concluded that the ban on equipment would fall under the purview of the Energy Department under their Energy, Efficiency and Conservation Act (EEC). If the regulation is established, the grace period would be one year after announcement. This includes the amendment to the existing Custom’s Act-Prohibition and Restriction on Imports and Exports 2006 to ban the import of HCFC-based RAC equipment. Moreover, DEPR is reviewing the existing regulations to determine whether there are any restrictions on the use of flammable refrigerant in RAC sector the country. DEPR is consulting with relevant authorities to examine when (i) the restriction to sale refrigerant to only certified technicians and (ii) the mandatory requirement that only certified technicians will be allowed to handle or service RAC equipment can be put in place. The second tranche was approved at the 74th ExCom meeting in May 2015. 2014 CP data was submitted online.
FIN | UNEP | Development of RMP | RMP | ASP | BRU | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-11-01 | 2009-12-01 | 30000 | -15500 | 14500 | 14500 | 100% | 0 |  |  | 3900 | -2015 | 1885 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring of the activities included in the RMP | Individual | ASP | BRU | REF | 44 | TAS | 09 | A | I | CFC | 2.9 | 2.9 | 0 | 0 | 2004-12-01 | 2008-05-01 | 2007-12-01 |  | 2010-12-01 | 2011-07-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 |  |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and national technicians training | Individual | ASP | BRU | REF | 44 | TRA | 07 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2008-06-01 | 2006-12-01 |  | 2010-12-01 | 2011-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | BRU | REF | 44 | TRA | 08 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  |  | 4420 | 0 | 4420 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | BRU | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-01 | 1996-03-01 |  | 1998-09-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Creation of a Brunei Ozone Office | Individual | ASP | BRU | SEV | 26 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2004-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | BRU | SEV | 43 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2011-06-01 | 2006-07-01 |  | 2012-12-01 | 2013-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of the institutional strengthening project (phase III: 1/2013-12/2014) | Individual | ASP | BRU | SEV | 67 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-08-01 | 2014-07-01 |  | 2014-12-01 |  | 70000 | 0 | 70000 | 69726 | 99.61% | 274 |  | 274 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. The NOU conducted iPIC that, allowed Brunei Darussalam to confirm the imports/exports, mostly with Singapore and Malaysia prior to the approval of the import permits. NOU maintained records of imports and made regular checks with the Royal Customs and Excise Department to verify and reconciled the import figures. The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. NOU organized meetings with Royal Customs and Excise Department on the introduction and use of the E-permit system under Brunei Darussalam National Single Window for application of import and export of ODSs, which helped to strengthen the licensing system. For Ozone Day celebration in 2014, the NOU created a short video promoting the use of non-ODS based equipment in daily activities and advertised in the national television’s channel. Along with the video, the NOU also developed posters on the use of non-ODS based equipment distributed to government buildings and schools. The project was completed in December 2014. Legal arrangements (actual/planned): Agreement signed in July 2014. Initial stages of project implementation (actual/planned): The activities were conducted as planned, even though the SSFA was signed later. Intermediate goals achieved (actual/planned): Yes, including operating of the NOU; Assisting in the implementation of stage I of the HPMP, introducing HCFC quota system from 2013 onwards, introducing labeling requirements, import restrictions for all HCFCs except HCFC-22, certification for refrigeration and air-conditioning technicians and restrictions on the establishment of new manufacturing capacity for products using HCFCs, and data. (as planned) First disbursement date: August 2014. All funds disbursed (yes/no): Yes Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delayed in signing of the agreement. UNEP proposed to amend the agrment for retroactive payment in light of Excom decisions, and careful review of the progress made and the expenditure incurred; Keeping constant communication with the Government in following up various issues. If Yes, will delay have impact on project completion date (yes/no): No. Finally the NOU speed up the implementation to be back on track. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Projects is completed. Continue the NOU operation with IS Phase IV
ONG | UNEP | Renewal of the institutional strengthening project (phase IV: 1/2015-12/2016) | Individual | ASP | BRU | SEV | 73 | INS | 15 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-31 | 2016-12-31 |  |  | 70000 |  | 70000 | 0 | 0% | 70000 |  | 70000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved project at the 73rd Meeting in November 2014. After the ExCom approval, UNEP worked with the NOU to draft the SSFA. Legal arrangements (actual/planned): No. Initial stages of project implementation (actual/planned): N/A Intermediate goals achieved (actual/planned): Operating of the NOU; assisting in the implementation of stage I of the HPMP, implementation of HCFC licensing and quota system, introducing labeling requirements, import restrictions for all HCFCs except HCFC-22, certification for refrigeration and air-conditioning technicians and restrictions on the establishment of new manufacturing capacity for products using HCFCs, and data. (as planned) First disbursement date: N/A All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The draft SSFA has been prepared and finalized. SSFA is being processed for UNEP signature, which will be then submitted to government for counter-signing. The licensing and quota system and iPIC are being implemented in 2015. The total quota of HCFCs for 2015 has been set below the 10% reduction obligation under the MP. NOU keep close communication with the Royal Customs and Excise Department during the shipment clearance and to monitor the import statistics of ODS. 2014 Country Programme has been timely reported.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | BZE | PHA | 50 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2007-09-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | BZE | PHA | 53 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2010-12-01 | 2011-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BZE | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-31 | 85000 | -4226 | 80774 | 80774 | 100% | 0 | 0 |  | 11050 | -549 | 10501 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2015-12-01 |  | 2014-05-31 | 2014-12-31 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Brief progress report (actual/planned): the quota system is being implemented administratively. One 5-day train the trainers workshop on alternative refrigerants to HCFC Jan-2014; 13 trainers trained. Development of the RAC asociation website. Printing of brochures targeting the hotel sector. Quotas for 2015 assigned in Dec 2014. The NOU works hand in hand with refrigeration technicians association (ARACT) to ensure that from the month of October through December, a one day Training session is held for each district of the country. After the training session, the technicians take the admission exam and if they pass the exam, the technicians are granted their licenses to be able to practice refrigeration and air conditioning servicing. In early 2014 the vocational institute (ITVETS) has undertaken trials with AC’s and refrigerators using HCs. Last disbursement processed in May-2014. ___ Legal arrangements (actual/planned): Agreement signed in May 2011, amended in July 2013.___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): June 2011, second and third payment made in March and December 2013 respectively. Last disbursement made in May 2014.___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no):no ___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): n/a. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | The quota system is being implemented administratively since January 2013. In May-2015, the Cayo Center for Employment Training held a demonstration on the conversion of mobile air conditioning units, and refrigeration equipment to hydrocarbon refrigerant; some refrigeration and air conditioning technicians were able to attend. Unveiling of a billboard that promotes traning, membership and licensing of technicians in refrigeration and air conditioning servicing. Brochures and other awareness material s to encourage the phase out of HCFCs in the hotel sector are still being disseminated. Over forty eight (48) Customs Officers were trained in March and April 2015. Training was conducted in all the border points and included the enforcement unit in Orange Walk Town, Belize. Since Mar-2015, the NOU is conducting a monitoring exercise which aims to identify whether there were any stockpiles of CFC refrigerants in the market. All funds disbursed. Project is completed.
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | BZE | REF | 41 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 15000 | -1250 | 13750 | 13750 | 100% | 0 | 0 |  | 1950 | -163 | 1787 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: certification and licensing of refrigeration technicians | Individual | LAC | BZE | REF | 44 | TAS | 11 | A | I | CFC | 5 | 5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 33682 | 0 | 33682 | 33682 | 100% | 0 | 0 |  | 4379 | 0 | 4379 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: prevention of illegal trade of CFCs | Individual | LAC | BZE | REF | 44 | TAS | 13 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 22611 | 0 | 22611 | 22611 | 100% | 0 | 0 |  | 2939 | 0 | 2939 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | BZE | REF | 44 | TAS | 14 | A | I | CFC | 4 | 4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 27140 | 0 | 27140 | 27140 | 100% | 0 | 0 |  | 3528 | 0 | 3528 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | BZE | SEV | 24 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-02-01 |  | 1999-11-01 | 2000-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Creation of the national ozone unit | Individual | LAC | BZE | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2003-01-01 | 2004-10-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | BZE | SEV | 40 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-07-01 | 2007-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | LAC | BZE | SEV | 46 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-07-01 | 2007-07-01 |  | 2008-09-01 | 2009-09-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BZE | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-07-01 | 2011-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | BZE | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-12-01 |  | 2013-03-01 | 2014-03-01 | 38350 | 38350 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | BZE | SEV | 66 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2013-12-01 | 2014-12-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): CP Progress Report and Article 7 data reported in a timely manner. Last disbursement processed in Dec-2013. Terminal report and renewal request prepared by NOU with UNEP's assistance, and submitted to 72nd ExCom. Project completed .___ Legal arrangements (actual/planned): Agreement signed in Aug 2012.___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement issued Aug 2012.___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): n/a. ___ Any ongoing problems (yes/no): n/a. ___ If Yes, is any action required by ExCom: n/a. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VII: 4/2014-3/2016) | Individual | LAC | BZE | SEV | 72 | INS | 28 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-11-30 | 2016-03-01 | 2016-06-30 |  |  | 76700 | 0 | 76700 | 30680 | 40% | 46020 | 46020 | 30680 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Renewal request prepared on Feb-2014. Renewal request submitted and comments from MLFS addressed in Apr-2014. Renewal approved in May-2014. NOU requested amendment to the action plan originally approved in Jun-2014. Chief Officer of MLFS provided clarifications on this request on Jun-2015. Revised action plan of Belize's IS was notified to ExCom 73 in Jul-2015. ___ Legal arrangements (actual/planned): Draft SSFA prepared in Jul-2014 and sent to country for comments. Adjustments required by country on the text in Aug-2014. SSFA approved for signature in Sep-2014. Required amendment of budget codes to UMOJA codes in Sep-2014. SSFA signed by UNEP and sent to country for signature in Oct-2014. Country signature in Oct-2014 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Nov-2014 .___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: n/a. | Submitted 2014 CP data report on April 2015. The NOU participated in public awareness activities in collaboration with the Department of the Environment on the National Agriculture and Trade Show (May-2015) in Belmopan. The interaction and dissemination of information to the students, public officers, and the general public was successful. Belize attended the English Speaking Caribbean and Haiti Ozone Officers Regional Meeting held in Bahamas, Mar-2015; the HFC Management Workshop and the 35th OEWG of the Parties to the Montreal Protocol in Thailand, Apr-2015.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CAF | PHA | 49 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CAF | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-12-01 |  | 2011-01-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-12-01 | 2013-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CAF | PHA | 64 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2016-07-01 |  |  | 75000 | 0 | 75000 | 45000 | 60% | 30000 | 0 | 4973 | 9750 | 0 | 5850 | 3900 | 3253.51 | Brief progress report (actual/planned): _No activities undertaken in 2014 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):Project implementation started with training of 25 refrigeration technicians and 20 customs officer in 2013___ Intermediate goals achieved (actual/planned): _yes__ Project completion and follow up:implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursment sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | UNEP contacted the Minister and the Environment Director in Febraury 2015 in Cairo and send letter to the Minister of Environment and the Minister of Industry. UNEP is expecting guidance from the Government.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | CAF | PHA | 71 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-05-01 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): _No activities undertaken in 2014 because of political unrest and travel restrictions. UNEP is to contract Consultant but because of travel restriction and the unrest in the country , Consultant is not yet contracted. _ Legal arrangements(actual/planned):No legal arragement with the Country ___Initial stages of project implementation(actual/planned): NO___ Intermediate goals achieved (actual/planned): _NO__ Project completion and follow up: NO___ First disbursement date (actual/planned): No disbursment ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | UNEP contacted the Minister and the Environment Director in Febraury 2015 in Cairo and send letter to the Minister of Environment and the Minister of Industry. UNEP is expecting guidance from the Government.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | CAF | REF | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2001-05-01 | 2002-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | CAF | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-06-01 |  | 1995-10-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Establishment of the National Technical Ozone Group (Ozone Unit) | Individual | AFR | CAF | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 2000-06-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 |  | 5928 | 0 | 5928 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | CAF | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2004-10-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 |  | 3952 | 0 | 3952 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | AFR | CAF | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2006-01-01 | 2007-04-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CAF | SEV | 45 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-06-01 | 2007-04-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | CAF | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2012-03-01 | 2011-03-01 |  | 2013-03-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | CAF | SEV | 68 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _No activities undertaken in 2014 because of political unrest and travel restriction _ Legal arrangements(actual/planned):No ___Initial stages of project implementation(actual/planned): NO___ Intermediate goals achieved (actual/planned): _NO__ Project completion and follow up: NO___ First disbursement date (actual/planned): No disbursment ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | UNEP contacted the Minister and the Environment Director in Febraury 2015 in Cairo and send letter to the Minister of Environment and the Minister of Industry. UNEP is expecting guidance from the Government. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CBI | PHA | 50 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2011-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | CBI | PHA | 54 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2009-12-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CBI | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -19552 | 65448 | 65448 | 100% | 0 | 0 |  | 11050 | -2542 | 8508 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | CBI | PHA | 59 | TAS | 15 | A | I | CFC-12 | 0.3 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2010-11-01 |  | 2011-11-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CBI | PHA | 64 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2014-07-01 | 44000 | -3710 | 40290 | 24000 | 59.57% | 16290 | 16290 |  | 5720 | -482 | 5238 | 0 | 0 | Brief progress report (actual/planned): UNEP amended the SSFA for extention till Dec 2014. Amended SSFA signed by country and sent to FMO for records in July 2014. Country to submit interim HPMP reports in September 2014 and UNEP processed the 2nd payment ($10,000) in October 2014. Legal arrangements (actual/planned): Agreement signed in February 2012. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2012 __ All funds disbursed (yes/no): _ Final payment being processed in June of 2014.__ Any delay? (yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: Delay in implementing activities, SSFA amended for extension. ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | CBI | PHA | 71 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 35000 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): UNEP initiated the SSFA for signature _ Legal arrangements(actual/planned): The SSFA to be signed in July 2015. Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): __no_ Project completion and follow up: _No__ First disbursement date (actual/planned): All funds disbursed (yes/no): _no_ Any delay?(yes/no): _no_ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA awaiting finalization
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | CBI | REF | 44 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2008-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | CBI | REF | 44 | TRA | 05 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CBI | REF | 44 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | CBI | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2003-08-01 |  | 2004-12-01 | 2011-07-01 | 40000 | -4983 | 35017 | 35017 | 100% | 0 | 0 |  | 5200 | -648 | 4552 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | CBI | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2005-06-01 | 2003-04-01 |  | 2007-11-01 | 2011-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | CBI | SEV | 44 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-09-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | CBI | SEV | 50 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2008-11-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CBI | SEV | 57 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2011-03-01 |  | 2013-03-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | AFR | CBI | SEV | 71 | INS | 17 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in June 2014. Country sent 2013 Art.7 and CP data. Ozone day celebrated. Awareness campaigns raised in schools in Praia in September 2014. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement scheduled in July 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country sent 2014 Art.7 and CP data in February 2015.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CHD | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-01-01 | 2011-10-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | CHD | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 | 2011-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 | 0 | 12220 | 0 | 12220 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CHD | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2012-12-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-03-01 | 2013-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 | 0 | 10010 | 0 | 10010 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 |  | 2013-06-01 | 2014-06-01 | 100000 | -5000 | 95000 | 95000 | 100% | 0 | 0 |  | 13000 | -650 | 12350 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | CHD | PHA | 70 | TAS | 24 | A | I |  | 1.6 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 46500 | 46500 | 9100 | 0 | 0 | 9100 | 0 | Brief progress report (actual/planned): SSFA revised and signed by the country in June 2014. Country organized a training workshop for 25 law enforcement officers in N’Djamena in September 2014 and a training workshop for 25 refrigeration technicians in N’Djamena. Country organized 2 workshops training for refrigeration technicians in October 2014 in Mongo (15 technicians trained) and Moundou (20 technicians trained); also trained 50 refrigeration technicians in December 2014 in N’Djamena. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement planned in July 2014 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Training workshop for 13 refrigeration technicians and 12 customs officers organized in May 2015.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | AFR | CHD | PHA | 73 | TAS | 26 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-05-01 | 2015-11-30 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 | -5.8265e-13 | 0 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): __ Consultant identified in March 2015 and country informed . TOR available . CAP advised the country to anticipate by gathering all required information and supporting document. BNO took advantage of the Customs training workshops to request importers and customs officers to avail all proofs of HCFCs imports and to prepare the field. Legal arrangements (actual/planned): (Yes/No): No_ First mission (actual/planned): __ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Country started a survey in March 2015.
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians in good service practices | Individual | AFR | CHD | REF | 29 | TRA | 05 | A | I | CFC | 5.1 | 5.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-12-01 | 80125 | 0 | 80125 | 80125 | 100% | 0 | 0 |  | 10416 | 0 | 10416 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CHD | REF | 29 | TRA | 06 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-11-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  | 2002-10-01
FIN | UNEP | Country programme preparation | Individual | AFR | CHD | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-05-01 | 1996-03-01 |  | 1998-05-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | AFR | CHD | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2001-07-01 |  | 2004-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | CHD | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CHD | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2011-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CHD | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-12-01 | 2006-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 1/2012-12/2013) | Individual | AFR | CHD | SEV | 65 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 |  | 2013-08-01 | 2014-12-14 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2014-12/2015) | Individual | AFR | CHD | SEV | 71 | INS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | CHI | FUM | 30 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2011-12-01 | 25000 | -8217 | 16783 | 16783 | 100% | 0 | 0 |  | 3250 | -1068.21 | 2182 | -0.21 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | National phase-out of methyl bromide, terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | TAS | 172 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2014-04-01 | 2015-12-31 |  |  | 73000 | 0 | 73000 | 27812 | 38.1% | 45188 | 45000 | 18000 | 9490 | 0 | 2929 | 6561 | 0 | Brief progress report: An informative booklet with applicable alternatives to MB was designed and distributed among producers of strawberries in May-14. Discussions on the agreement related to the web-based MB tracking system with Servicio Agricola y Ganadero (SAG) has been resumed by the NOU. Mission in Jun-14 to discuss and agree on funding and activities to be carried out. Additional discussions took place between the NOU and SAG on the agreement. A revised version of the SSFA was sent to UNEP in Sep-2014 that required consultation with legal departement. A counterproposal of SSFA with legal department observations was sent to NOU fro their consideration on Oct-2014. An additional modification to the SSFA was requested by NOU in Nov-2014. UNEP's legal department agreed with this modification and SSFA is ready for signature, Dec-14 . Legal arrangements: SSFA signed in July 2013.___ First mission: n/a___TOR completed (actual/planned): N/A. First disbursement date: August 2010. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: terms of the agreement were modified by SAG and NOU several times. Those changes required the clearance of legal department of UNEP. Consultations with legal department of UNEP on modifications proposed by counterparts were requested and followed-up ina prompt manner. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | Rephasal of corresponding budget line in 2015 was requested in Jan-2015: this is necessary to create the obligation in the system and for signature of the RD. RD signed in Jan-2015. SSFA sent to country for signatures in Feb-2015. Follow up on signatures in Apr-2015. Both SAG and Minsitry of Environment (NOU) have signed the agreement. Agreement was sent to Ministry of Foreign Affairs for cleareance before Comptroller's final approval to start implementation. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | TAS | 175 | A | I |  | 1.9 | 0 | 0 | 0 | 2011-04-01 | 2013-08-01 | 2012-03-01 | 2015-12-31 |  |  | 153217 | 0 | 153217 | 83848.34 | 54.73% | 69368.66 | 37006 | 17016 | 19918 | 0 | 1897 | 18021 | 3339.007 | Brief progress report: Seminars (2) for refrigerant’s importers and custom agents; continued training courses for Customs Officers, along the country; 5 portable identifiers for the National Customs Service; contact with potential importers of controlled products (containing ODS) to inform them about the obligation of reporting under current legislation; consultancy to identify all those products/equipment, which should report their import/export activities to the registry on the web platform in compliance of the Supreme Decree N° 75/2012; consultancy to design and implement the software for the registry of controlled products signed in July 2014; labelling norm “This product damages the ozone layer”; consultancy to develop norms for generation, storage, transport, treatment, or recycling of ODS and other controlled substances, according to Article 14 of Law 20.096; consultancies to: (a) identify which R&AC subsectors could implement Cleaner Production Agreements and, (b) to identify energy efficient equipment, study the feasibility to implement energy efficiency labels and design of these labels. Legal arrangements: The SSFA was signed in May 2013, while no specific date established in the project document. First mission: It was carried out in July 2013 while no specific date was established in the project document. TOR completed (actual/planned): N/A. First disbursement date: First disbursement carried out in August 2013 while it was planned for October 2011. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Implementation modalities varied, according to activities, between direct implementation and financial authorizations that demanded long discussions before agreement on legal text with Government, UNDP and UNEP. This implied for instance the identification, selection and contracting of consultancy services by UNEP which is a long demanding process from the adminsitrative point of view. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Balance to be included as part of planning of activities for second tranche. Mission to be planned once UMOJA goes live in second semester of 2015
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CHI | PHA | 71 | TAS | 180 | A | I |  | 0.5 |  | 0 |  | 2013-12-01 |  | 2014-12-01 | 2016-06-30 |  |  | 40127 | 0 | 40127 | 0 | 0% | 40127 | 0 | 20063 | 5217 | 0 | 0 | 5217 | 0 | Brief progress report: Activities will be merged with those outstanding of first tranche. Legal arrangements: A new agreement will be signed once outstanding activities of first tranche are near completion. First disbursement date (actual/planned): Planned for 2015. All funds disbursed? No. Any delay? Yes. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | 2015 annual implementation and procurement plan being drafted. Mission planned for July 2015 to finalize workplan and implementation modalities under UMOJA.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | CHI | PHA | 73 | PRP | 181 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-30 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 5000 | 2600 | 0 | 0 | 2600 | 0 | Newly approved project | Mission planned for Jul-2015 to discuss and agree on workplan and progress on tranche implementation.
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | CHI | PHA | 73 | TAS | 185 | A | I | CFC-22 | 2.1 |  |  |  | 2014-11-01 |  | 2015-11-30 | 2016-12-30 |  |  | 27022 | 0 | 27022 | 0 | 0% | 27022 | 0 | 5000 | 3513 | 0 | 0 | 3513 | 0 | Newly approved project | Mission planned for Jul-2015 to discuss and agree on workplan and progress on tranche implementation.
FIN | UNEP | Implementation of the RMP: enabling a control and regulatory network | Individual | LAC | CHI | REF | 35 | TAS | 146 | A | I | CFC | 18.4 | 18.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2002-09-01 |  | 2009-06-01 | 2011-04-01 | 111400 | 0 | 111400 | 111400 | 100% | 0 | 0 |  | 14482 | 0 | 14482 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: end-users and public awareness programme | Individual | LAC | CHI | REF | 35 | TAS | 148 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-07-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 |  | 22360 | 0 | 22360 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: monitoring, evaluation and reporting of the activities in the RMP | Individual | LAC | CHI | REF | 35 | TAS | 149 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Cook Islands) | Multi-Year | ASP | CKI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-12-01 |  |  | 49250 | 0 | 49250 | 46125 | 93.65% | 3125 |  | 3125 | 6403 | 0 | 4014 | 2389 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted. The license requirement for technician in handling HCFCs and for workshop/dealer in storing and sales of HCFCs has been implemented in 2014. Cook Islands was in the process of amending the regulation to ban the import of HCFC-based equipment. Refrigerant identifier was handed over to Customs for inspection. National training workshop for RAC technicians was organized in January 2014 with 30 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in December 2011. First Mission: August 2013 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online.
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | CKI | REF | 44 | TAS | 01 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2010-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 |  |  | 1820 | -426.01 | 1394 | -0.01 | 0
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | CKI | REF | 44 | TAS | 03 | A | I | CFC | 0.5 | 0.5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2010-07-01 | 2011-07-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  |  | 1040 | 0 | 1040 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | CKI | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-10-01 | 2005-12-01 |  | 2007-01-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase I) | Individual | ASP | CKI | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-01-01 | 2007-11-01 |  | 2008-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | CKI | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-05-01 | 2008-11-01 |  | 2011-01-01 | 2011-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | CKI | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2010-12-01 |  | 2011-03-01 | 2011-06-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | CKI | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | CKI | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-12-01 | 2014-12-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project completed in December 2014. New NOU appointed in May of 2013 following afer a 12 months of vacancy. NOU coordinated the finalization of the regulation amendments. Manage the Ongoing implementation of the electronic system for managing ODS import permits and licenses a. Completed the formalization of the existing cooperation with the customs department through the signature of a memorandum of understanding with Customs. Completed customs officers training in August 2013 and 16 officers were trained. Completed procurement of refrigerant identifiers in August of 2013. Completed and being enforced import control/ban on the HCFC-based equipment. Completed servicing technicians training in January of 2014 with 28 trained technicians, refresher training done in Samoa November 2013. NOO coordinates all meetings, provided secretarial services in supporting the operation of the established refrigeration and air-conditioning association. Ongoing through regular communication and training in good refrigeration practices. 2013 and 2014 data timely submitted to both Secretariats. CP on-line data submission. NOU attended the PIC 2014 regional meetings in Tonga and Fiji. NOU attended the 2014 Tonga and Fiji network meetings and the 26 MOP. Legal Arrangement: Agreement signed in Dec. 2012 First Disbursement Date: First payment in Dec 2013. All funds disbursed (yes/no): Yes . Projects completed and with final payments made in December of 2014. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delayed in signing the agreement and lost of NOU. UNEP mainatined constant communication with the country, and build the capacity of the new ozone officer and other national stakeholders. If Yes, will delay have impact on project completion date (yes/no) No. Any ongoing problems (yes/no): No. | Project completed in December 2014. Project prepared and submitted to the 72nd ExCom. NOU as lead national agency for the HPMP successful managed implementation, prepared and submitted required documents to meet the 74th Ex Com. Com. 2014 CP data timely submitted and on line. 2014 Artilce 7 data submitted in May 2015. New IS phase begins in Jan 2015.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | CKI | SEV | 72 | INS | 10 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project approved at the 72nd Ex. Com Legal Arrangement: SSFA signed on April 2015. First Payment made April 2015. Stable, continued NOU and functioning as part of the instituional system of Government. All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Country timely submitted CP 2014 data on line. 2014 Article 7 data submitted in May 2015.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | CMR | FUM | 34 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-07-01 |  | 2003-07-01 | 2004-07-01 | 25000 | -10136 | 14864 | 14864 | 100% | 0 | 0 |  | 3250 | -1317.68 | 1932 | 0.32 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | CMR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-06-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs officers) | Individual | AFR | CMR | SEV | 10 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-08-01 | 1994-12-01 | 20200 | 0 | 20200 | 20200 | 100% | 0 | 0 |  | 2626 | 0 | 2626 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Monitoring Commission | Individual | AFR | CMR | SEV | 11 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-10-01 | 1996-11-01 |  | 1997-10-01 | 1997-06-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 |  | 20930 | 0 | 20930 | 0 | 0
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | CMR | SEV | 22 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-12-01 | 2000-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | AFR | CMR | SEV | 28 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Policy and technical assistance | Individual | AFR | CMR | SEV | 37 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-07-01 | 2007-07-01 | 10000 | -1994 | 8006 | 8006 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | CMR | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (second year of phase IV) | Individual | AFR | CMR | SEV | 44 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase V | Individual | AFR | CMR | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | CMR | SEV | 53 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | CMR | SEV | 59 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-12-01 |  | 2012-12-01 | 2013-12-01 | 69766 | 69766 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | CMR | SEV | 65 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed
ONG | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | AFR | CMR | SEV | 71 | INS | 37 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2015-12-01 | 2015-12-01 |  |  | 139532 | 0 | 139532 | 69766 | 50% | 69766 | 0 | 69776 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2014. A meeting of the National Ozone Committee organized in December 2014 in order to fixe and allocate the 2015 quota on HCFC imports. Another one organized in July 2015 for the assessment of the licensing system. The BNO coordinated the implementation of activities under HPMP. Legal arrangements (actual/planned): Agreement signed in April 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2014 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Second payment initiated in May 2015.
FIN | UNEP | Project preparation for a TPMP | Individual | AFR | COI | PHA | 47 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | COI | PHA | 52 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2011-12-01 | 77000 | -5978 | 71022 | 71022 | 100% | 0 | 0 |  | 10010 | -777.14 | 9232 | 0.86 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | COI | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-11-01 | 2012-11-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | COI | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 |  | 2013-09-01 | 2014-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | COI | PHA | 70 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 35000 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): SSFA sent to the country in may 2014 for signature. Awarness workshop on HCFCs alternatives organized in Moroni (Nov 14) and Moheli (Dec 14). Workshop to launch HPMP tranche 2 organized in October 14. Legal arrangements (actual/planned): June 2014. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _n/a - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): July 2014__ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): two refrigeration workshop of 60 technicians organized in Moroni and Anjouan in February 2015. One workshop for 25 customs officers organised in Mohehi in March 2015. Legal arrangements (actual/planned): AAll activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): Planned in June 2015 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | COI | REF | 27 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2000-04-01 |  | 2001-09-01 | 2001-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring of RMP implementation and its impact in the service and end-users sectors | Individual | AFR | COI | REF | 35 | TAS | 05 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2001-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-07-01 | 2008-09-01 | 18000 | -2000 | 16000 | 16000 | 100% | 0 | 0 |  | 2340 | -260 | 2080 | 0 | 0
FIN | UNEP | Implementation of the RMP: assessment of the end-users subsector | Individual | AFR | COI | REF | 35 | TAS | 06 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-06-01 | 2006-06-01 | 30000 | -2218 | 27782 | 27782 | 100% | 0 | 0 |  | 3900 | -289 | 3611 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer and training of refrigeration service technicians | Individual | AFR | COI | REF | 35 | TRA | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2002-07-01 |  | 2003-12-01 | 2005-12-01 | 51000 | -7093 | 43907 | 43907 | 100% | 0 | 0 |  | 6630 | -922 | 5708 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers in identification and control of ODS imports | Individual | AFR | COI | REF | 35 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-07-01 |  | 2003-12-01 | 2006-06-01 | 39000 | -13386 | 25614 | 25614 | 100% | 0 | 0 |  | 5070 | -1740 | 3330 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | COI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1997-11-01 | 1999-01-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 |  | 4290 | 0 | 4290 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Unit | Individual | AFR | COI | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 2000-12-01 |  | 2001-03-01 | 2001-12-01 | 27800 | 0 | 27800 | 27800 | 100% | 0 | 0 |  | 3614 | 0 | 3614 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | COI | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 18533 | 0 | 18533 | 18533 | 100% | 0 | 0 |  | 2409 | 0 | 2409 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | COI | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24093 | 0 | 24093 | 24093 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | COI | SEV | 45 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | COI | SEV | 51 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-05-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | COI | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2011-03-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | COI | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 |  | 2013-07-01 | 2014-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | AFR | COI | SEV | 70 | INS | 22 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2015-06-01 | 2015-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2014. Country reported 2013 Art.5 data and 213 CP data. 2013 Ozone day was celebrated. Legal arrangements (actual/planned): Agreement signed in April 2014. All activities under the SSFA are completed (as planned) n/a___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2014 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country reported 2014 Art.5 data and 2014 CP data. NOU coordinatate the two refrigeration workshop of 60 technicians organized in Moroni and Anjouan in February 2015 and the Customs workshop for 25 customs officers organised in Mohehi in March 2015.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 |  | 2014-12-01 | 2014-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 4584 | 1916 | 0 | Brief progress report: The implementation of the HPMP (first tranche) is completed. All funds are disbursed. Intermediate goals achieved in 2014 are as planned: (a) HCFC quota system implemented; (b) HCFC baseline kept; (c) Banning of imports and production of HCFC-based domestic refrigeration appliances implemented; (d) Five custom and enforcement officers workshops delivered. (e) A total of 115 front line officers trained in HCFCs controls. Legal arrangements (actual/planned): The signature of SSFA to implement the first tranche activities was completed in July 2012, while it initially was planned in May 2011. In December 2012, the SSFA was amended to include activities approved in the second tranche. First mission: July 2014 while no specific date was established in the project document. TOR completed: N/A. First disbursement date: June 2012/ Planned for June 2011. All funds disbursed? Yes. Any delay? Yes. The first tranche was initially planned to be completed in December 2012. Completion date was December 2014. If Yes, reasons for delay & action plan to resolve: Administrative reasons. Late start of the project is due to the signature of agreement. However, in 2013 and 2014 project implementation pace was improved. If Yes, will delay have impact on project completion date: Yes, 24 months delay. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | COL | PHA | 66 | TAS | 80 | A | I |  | 1.5 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2015-12-31 |  |  | 50000 | 0 | 50000 | 39128 | 78.26% | 10872 | 9496 | 9496 | 6500 | 0 | 3375 | 3125 | 0 | Brief progress report: The implementation of the HPMP (second tranche) is progressing without significant delays. Disbursements released through the UNDP country office according to the advance of activities. Intermediate goals achieved in 2014 are as planned: (a) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port; (b) The NOU and Customs collected data on ODSs trade across the country through monitoring the facilities of ODS suppliers in order to prevent ODS illegal trade; (c) A specific study on HCFCs used in Colombian-flagged ships was completed. The study is aimed to gain a better understanding of HCFC uses in this sub-sector and also facilitate the assessment of new measures to prevent the ODSs illegal trade. Legal arrangements (actual/planned): The signature of SSFA to implement the first tranche activities was completed in July 2012, while it initially was planned in May 2011. In December 2012, the SSFA was amended to include activities approved in the second tranche. A second amendment was signed in May 2014. First mission: July 2014 while no specific date was established in the project document. TOR completed: N/A. First disbursement date: December 2012/ Planned for October 2012. All funds disbursed? No. Any delay? Late start of the project has been partially recovered. The HPMP was initially planned to be completed in April 2014. Completion date has now been rescheduled for December 2015. If Yes, reasons for delay & action plan to resolve: Administrative reasons. Late start of the project is due to the signature of agreement. If Yes, will delay have impact on project completion date: Yes, an 8 months delay expected. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | Brief progress report: The implementation of the HPMP (second tranche) is progressing without significant delays. Disbursements released through the UNDP country office according to the advance of activities in April 2015. Intermediate goals achieved in 2015 are as planned: (a) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port; (b) The NOU and Customs collected data on ODSs trade across the country through monitoring the facilities of ODS suppliers in order to prevent ODS illegal trade; (c) National manual to Customs trained has been published. Legal arrangements (actual/planned): The signature of SSFA to implement the first tranche activities was completed in July 2012, while it initially was planned in May 2011. In December 2012, the SSFA was amended to include activities proved in the second tranche. A second amendment was signed in May 2014. First mission: July 2014 while no specific date was established in the project document. TOR completed: N/A. First disbursement date: December 2012/ Planned for October 2012. All funds disbursed? No. Any delay? Late start of the project has been partially recovered. The HPMP was initially planned to be completed in April 2014. Completion date has now been rescheduled for December 2015. If Yes, reasons for delay & action plan to resolve: Administrative reasons. Late start of the project is due to the signature of agreement. If Yes, will delay have impact on project completion date: Yes, an 8 months delay expected. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A
FIN | UNEP | Training programme in good practices in refrigeration | Individual | LAC | COL | REF | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 2003-12-01 | 2005-02-01 | 149100 | -42081.59 | 107018.41 | 107018 | 100% | 0.41 | 0 |  | 19383 | -5470.61 | 13912 | 0.39 | 0 | Project financially completed. | Project financially completed. |  | 1999-12-01
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 100% | 0 | 0 |  | 3250 | -1253 | 1997 | 0 | 0 |  | Project financially completed.
FIN | UNEP | Sectoral policy plan for methyl bromide phase-out in China | Individual | ASP | CPR | FUM | 24 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-01-01 |  | 1999-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 19500 | 0 | 19500 | 0 | 0
FIN | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | Individual | ASP | CPR | FUM | 35 | TAS | 381 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2010-12-01 | 100000 | -53818 | 46182 | 46182 | 100% | 0 |  |  | 13000 | -6996 | 6004 | 0 | 0 |  |  |  | 2004-06-01
FIN | UNEP | Techno-economic evaluation of methyl bromide alternatives | Individual | ASP | CPR | FUM | 35 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2008-12-01 | 80000 | -9093 | 70907 | 70907 | 100% | 0 |  |  | 10400 | -1182 | 9218 | 0 | 0 |  |  |  | 2004-06-01
FIN | UNEP | Preparation of a HCFC phase-out management plan: refrigeration servicing sub-sector | RMP | ASP | CPR | PHA | 55 | PRP | 465 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 |  |  | 48750 | 0 | 48750 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan: enabling components | RMP | ASP | CPR | PHA | 55 | PRP | 472 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 | 0
COM | UNEP | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | TAS | 517 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-07-01 |  | 2014-12-01 |  | 1579000 | 0 | 1579000 | 1579000 | 100% | 0 |  | 0 | 176703 | 0 | 52755 | 123948 | 5148 | Project completed. Complinace sustained. | Project completed
COM | UNEP | HCFC phase-out management plan(stage I, second tranche) (refrigeration servicing sector including enabling programme) | Multi-year | ASP | CPR | PHA | 68 | TAS | 528 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-10-01 | 2013-12-01 |  | 2014-12-01 |  | 598000 | 0 | 598000 | 598000 | 100% | 0 |  | 0 | 66921 | 0 | 0 | 66921 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector including enabling programme) | Multi-Year | ASP | CPR | PHA | 72 | TAS | 541 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-10-01 | 2015-05-31 | 2015-12-31 |  |  | 1104000 |  | 1104000 | 310100 | 28.09% | 793900 |  | 793900 | 123547 | 0 | 0 | 123547 | 0 | Brief progress report (actual/planned): Code/standards development plan in the servicing sector for both the industrial/commercial refrigeration and air conditioing, and room air conditioniner sectors were finalized in 2014 following consultations, revisions; The training material on good practices was developed, revised and completed by the end of 2014; Organized a public bidding process for the selection of the national/regional training centers following government rules/procudures, and contracted 6 training institutions, i.e. 2 as national training centers, 4 as regional training centers; Organized kick-off training workshop in Shanghai on 1 July 2014 with 40 participants; Organized a two-day Train-the-Trainers workshop on 17-18 September 2014 at Guangzhou Light Industrial Mechanic School with 50 participants; The training centers were prepared to organize the their training, and completed their equipment procuremen following FECO's advice; Shanghai Jigao Vocational Training School, Guangzhou Light Industrial Mechanic School, Shougang Institute Technology (SGIT) organized their training to technicians. The Vocational Training and Qualification Certification Association of China finalized their feasibility study to incorporate requirements on environmental practices into the existing qualification certification syllabus of refrigeration servicing technicians; FECO/MEP and CRAA commenced a joint work in July 2014 to revise the existing voluntary system and to encourage more participation in the existing scheme. The CRAA engaged the stakeholders for their input; Organized Ozone2Climate Industry Roadshow and Roundtable in Beining in April 2014; Coordinated the implementation of Shenzhen Pilot project as planned; Organized a Launch Meeting and Training Workshop in March 2014 in Beijing with around 100 participants from 35 provinces, autonomous regions and municipalities and selected cities; organized a workshop to train government officers on ozone issue in Chongqing, December 2014, with 40 participants from 12 west and south-west provinces; Organized a training workshop targeting the ODS importer and exporters in Guangzhou on 20-22 April 2014 with 70 participants; Organized a training workshop targeting the officers from Local License Bureaus under the Ministry of Commerce (MoC) in Xining City on 24-27 June 2014with 100 participants; The capacity building of four Custom’s Branches at Huangpu, Shanghai, Ningbo, and Urumqi was completed by the end of 2014. Each Custom’s Branch held a series of training courses. Memo of Understanding was signed with the Anti-smuggling Bureau of General Administration of China Customs (GACC) in November 2014 to extend to 10 more Custom Branches such as Shenzhen, Nanjing, Qingdao, Nanning, Harbin, Xiamen, etc. Delegations from Bangladesh, Democratic People’s Republic of Korea, Pakistan, and the Philippines visited China in 2014 to discuss ODS import/export management and control. In these visits, each delegation visited China covered their own expenses. However, a small amount of funds from the HPMP China (Stage I) was used to cover local expenses for FECO/MEP to participate in the local visit to allow investigation into ODS illegal trade cases. From 3- 10 December 2014, six members from FECO, MOC and GACC visited Singapore and Indonesia to discuss and exchange ODS import and export management experience and how to enhance the capacity building of enforcement officers. The China-Lao’s Roundtable Dialogue was jointly organized by UNEP and FECO/MEP from December 23-25 2014 in Mengla city, Yunan Province. About 50 participants, of whom 90% were from the local Customs of both China and Lao, took part in the roundtable discussion. A Public Service Announcement (PSA) on ozone layer protection was initiated for development; On the occasion of the commissioning of the demonstration project in Yantai Moon Group in March 2014, Midea R290 production line in July 2014 and the signing ceremony of Qingdao Haier Group in March 2014, members of major national press, including Xinhua News Agency, were invited to cover these events. FECO/MEP organized a range of activities for the 2014 celebration of the International Day for the Preservation of the Ozone Layer (“Ozone Day”), including organisation of a coordination meeting with international agencies on 11-12 September 2014, an important meeting with the participant of Mr. Zhai Qing, the Vice Minister of MEP, Ms. Tina Birmpili, the Executive Secretary of the Ozone Secretariat, international and domestic partners and media journalists on 15 September, and a table tennis match with the name of ozone layer protection. During the Ozone Day celebration meeting, FECO/MEP announced the bidding results for the closure of 5 HCFC production lines for the 2015 10% reduction of HCFCs. Legal arrangements(actual/planned): PCA amended in Oct 2014. First mission (actual/planned): Sep 2014; First disbursement date (actual/planned):Oct 2014; All funds disbursed (yes/no): no Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: There was delay in signing Amendmnet, but project activities were being implemented. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): N0 | FECO/MEP is planning to select 5-8 more training centres nationwide in other provinces; The training centres organized training workshops like Shandong Institute of Commerce and Technology in March 2015. organized a workshop to train government officers on ozone issue in Fuzhou, Fujian province, January 2015, with 40 participants from the south and south-east provinces. The procured 30 sets of the latest model of portable refrigerants identifiers are expected to be delivered by June 2015.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) | Multi-Year | ASP | CPR | PHA | 73 | PRP | 555 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-12-31 | 2015-12-31 |  |  | 217600 |  | 217600 | 0 | 0% | 217600 |  | 217600 | 28288 | 0 | 0 | 28288 | 0 | Brief progress report (actual/planned): Newly approved project at the 73rd Meeting in November 2014. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned): N/A. Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): No. Any ongoing problems (yes/no): No. | Reached agreement with China on the arrangement of the stage II HPMP preparation, including the planing, budget etc; signed SSFA with FECO in May 2015. Initiated the survey in May 2015.
FIN | UNEP | Refrigeration servicing sector CFC phase-out plan (revised 2005 annual implementation programme) | Multi-year | ASP | CPR | REF | 45 | TAS | 426 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-12-01 |  | 2010-12-01 | 2013-12-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 |  |  | 58500 | 0 | 58500 | 0 | 0
FIN | UNEP | Training workshop on safety aspects of CFC substitutes | Individual | ASP | CPR | SEV | 18 | TRA | 155 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1996-05-01 |  | 1996-05-01 | 1999-04-01 | 82400 | 0 | 82400 | 82400 | 100% | 0 |  |  | 10712 | 0 | 10712 | 0 | 0
FIN | UNEP | Development of policy training strategy and plan for local authorities | Individual | ASP | CPR | SEV | 27 | TAS | 268 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2000-04-01 |  | 2000-10-01 | 2001-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
TRF | UNEP | Evaluation and risk analysis of Montreal Protocol Implementation in China | Individual | ASP | CPR | SEV | 30 | TAS | 346 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project financially completed.
FIN | UNEP | Policy training for local authorities (first tranche for 2001) | Individual | ASP | CPR | SEV | 34 | TRA | 377 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-12-01 | 2003-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 |  |  | 35750 | 0 | 35750 | 0 | 0
FIN | UNEP | Policy training for local authorities (second tranche) | Individual | ASP | CPR | SEV | 37 | TRA | 392 | A | I | CFC | 16.5 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-09-01 | 2005-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 |  |  | 26000 | 0 | 26000 | 0 | 0
FIN | UNEP | Policy training for local authorities (third tranche) | Individual | ASP | CPR | SEV | 43 | TRA | 413 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 |  |  | 43550 | 0 | 43550 | 0 | 0.0052
FIN | UNEP | Awareness/outreach activities on HCFC phase-out and its challenges during HPMP preparatory phase | Individual | ASP | CPR | SEV | 56 | TAS | 476 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-12-01 |  | 2011-06-01 | 2012-06-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  |  | 18200 | 0 | 18200 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | EUR | CRO | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | EUR | CRO | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 101200 | 0 | 101200 | 101200 | 100% | 0 | 0 |  | 13156 | 0 | 13156 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | CRO | SEV | 29 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2001-12-01 |  | 2002-03-01 | 2003-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 |  | 8710 | 0 | 8710 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (phase III) | Individual | EUR | CRO | SEV | 36 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2004-04-01 |  | 2004-12-01 | 2007-05-01 | 87900 | 0 | 87900 | 87900 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | EUR | CRO | SEV | 41 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2006-12-01 | 2008-05-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | EUR | CRO | SEV | 47 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2008-04-01 |  | 2008-11-01 | 2009-11-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | EUR | CRO | SEV | 56 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-04-01 | 2011-01-01 |  | 2011-07-01 | 2012-07-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VII) | Individual | EUR | CRO | SEV | 63 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2014-12-14 |  | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The HCFC quota is introduced according to schedule under ODS and F-gas Regulation (OG,92/12). Submitted iPIC form on Croatia import/export. Article 7 and CP data was collected and reports submitted to OS and MLFS for the year of 2013 on time Legal arrangements (actual/planned): Agreement signed in December 2011. All three payments were released under the SSFA. Initial stages of project implementation (actual/planned): All activities are completed Intermediate goals achieved (actual/planned): Article 7 and CP data was collected and reports submitted to OS and MLFS for the year of 2013 on time. The ozone day was celebrated (as planned). Steering Committee meetings were organized. Project completion and follow up: Project completed First disbursement date (actual/planned): January 2012 (Planned in December of 2011 but UNEP accounts were already closed) All funds disbursed (yes/no): Yes, all funds disbursed Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: _ If Yes, will delay have impact on project completion date (yes/no): Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Completed.
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 4/2013-3/2015) | Individual | EUR | CRO | SEV | 69 | INS | 39 | A | I |  | 0 |  | 0 |  | 2013-04-01 |  | 2015-03-01 | 2015-08-01 |  |  | 87707 | 0 | 87707 | 0 | 0% | 87707 | 87389 | 87389 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): With accession of Croatia to EU, the country had to adopt the EU Regulations and harmonize Croatian legislation with the European legislation. In the year 2014, the Ministry adopted: a new Regulation on ODS and F-gases (Official Gazette (OG) 92/14) and Air Protection Act – adjustment and amendment (OG, 130/11, 47/14). As a part of introducing and education of service technicians regarding new EU and Croatian legislations on ODS-s and F-gases Ministry produced brochure named “Basic information regarding implementation of regulations on ozone depleting substances and fluorinated greenhouse gases”. This brochure summarizes the changes and new obligations that occurred with the entry into force of new regulations and to service technicians will facilitate its application. The Ministry has organized workshop for all environmental inspectors from Croatia. The workshop was held on 6 and 7 of November of 2014 in Zagreb. 67 inspectors participated in this workshop. During this workshop inspectors were introduced with Regulations regarding ODSs and F-gases and with their duties during inspectional supervision of the companies and institutions that use refrigeration, air conditioning and fire protection systems, companies who service refrigeration, air-conditioners and heat pumps and fire-fighting systems and RRR centers and halon bank. On the occasion of International Day for the Preservation of the Ozone Layer, the Ministry organized press conference on which were presented results regarding protection of the ozone layer in Croatia and all related activities regarding ODS phase-out and HFC phase-down and information about new ozone an climate friendly technologies. On 15 of September, the Minister held a cabinet press conference emphasizing the importance of Ozone Layer protection and continuation of activities also for climate mitigation. On the press conference were also presented other successes of Croatia in the phasing out of ozone depleting substances and our goal to continue with this mission as the slogan itself says: Ozone Layer Protection – the Mission Goes On. To introduce and educate the youngest about the layer that protects Earth from UV rays, Ministry sent sketch-book, newsletter with ozone games and links for the Ministry’s WEB page Ozonko to all kindergartens in Zagreb. Legal arrangements (actual/planned): Agreement was signed in January 2014. Initial stages of project implementation (actual/planned): Legislation was updated. Ozone Day was celebrated. Training was carried out as planned. Intermediate goals achieved (actual/planned): Yes Project completion and follow up: Project ongoing First disbursement date (actual/planned): The first payment was released in March of 2014. All funds disbursed (yes/no): NO Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): The HCFC quota is introduced according to schedule under ODS and F-gas Regulation. Submitted iPIC form on Croatia import/export. Article 7 data was collected and the report to be submitted on time to OS for the year of 2014. The second payment was released in January of 2015.
FIN | UNEP | Country programme | Individual | EUR | CYP | SEV | 22 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-05-01 |  | 1997-05-01 | 1997-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | DJI | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-03-01 | 2009-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-year | AFR | DJI | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-03-01 |  | 2012-12-01 | 2013-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DJI | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2013-05-01 | 2014-05-01 | 30000 | -10747 | 19253 | 19253 | 100% | 0 | 1.4566e-13 |  | 3900 | -1397 | 2503 | 0 | 1.8936e-14 | Project Completed
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | DJI | PHA | 58 | PRP | 16 | A | I |  | 0 | 0 | 0 |  | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2013-12-01 | 2014-12-01 | 55000 | -9987 | 45013 | 45012.93 | 100% | 0.07 | 0 |  | 7150 | -1298 | 5852 | 0 | 0 | Project Complete
FIN | UNEP | Terminal phase out management plan for CFCs (second tranche) | Multi-Year | AFR | DJI | PHA | 59 | TAS | 17 | A | I | CFC-12 | 3.2 | 3.2 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DJI | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 | 2016-04-01 |  |  | 81000 | 0 | 81000 | 50000 | 61.73% | 31000 | 0 | 5000 | 10530 | 0 | 9880 | 650 | 0 | Brief progress report (actual/planned): Country has organized a training workshop for 35 refrigeration technicians in October 2014 in Djibouti. Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in August 2012 __ All funds disbursed (yes/no): _ Final payment being processed in July 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Has 26,000$ balance. Country organized a training workshop for 35 refrigeration technicians and 30 enforcement officers in March 2015 in Djibouti
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | DJI | REF | 37 | TRA | 04 | A | I | CFC | 2.1 | 2.1 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-06-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 |  | 4303 | 0 | 4303 | 0 | 0
FIN | UNEP | Implementation of the RMP: training in good practices of refrigeration | Individual | AFR | DJI | REF | 37 | TRA | 05 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 2002-07-01 | 2004-08-01 | 2003-08-01 |  | 2006-12-01 | 2009-04-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 |  | 9646 | 0 | 9646 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance to establish legislation | Individual | AFR | DJI | REF | 37 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2002-07-01 | 2004-05-01 | 2003-08-01 |  | 2004-04-01 | 2009-03-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | AFR | DJI | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-07-01 | 2007-01-01 | 60000 | -34200 | 25800 | 25800 | 100% | 0 | 0 |  | 7800 | -4446 | 3354 | 0 | 0 |  |  |  | 2002-07-01
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | DJI | SEV | 37 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-08-01 |  | 2006-04-01 | 2007-04-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | DJI | SEV | 48 | INS | 09 | A | I |  | 0 | 0.9 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2008-04-01 |  | 2009-04-01 | 2010-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | DJI | SEV | 57 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2011-07-01 | 2012-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | DJI | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 |  | 2013-04-01 | 2014-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase V: 7/2013-6/2015) | Individual | AFR | DJI | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2015-06-01 | 2015-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013 Art5 data and 2013 CP data. 2013 Ozone day was celebrated. Legal arrangements (actual/planned): Agreement signed in April 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country reported 2014 Art5 data and 2014 CP data
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-12-01 |  | 2010-11-01 | 2011-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | DMI | PHA | 57 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -17869 | 67131 | 67131 | 100% | 0 | 0 |  | 11050 | -2323 | 8727 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal CFC phase-out management plan (fourth tranche) | Multi-Year | LAC | DMI | PHA | 61 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | DMI | PHA | 62 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2013-04-01 | 2014-12-01 | 2016-12-30 |  |  | 82250 | 0 | 82250 | 10061 | 12.23% | 72189 | 0 | 24063 | 10693 | 0 | 906 | 9787 | 1820.0851 | Brief progress report (actual/planned): NOU requested UNEP to contract consultant services for training and coordination of HPMP. The request for contracting consultant services coincided with financial closure of 2014. UNEP followed up with NOU in the beginning of 2015 but no further communication received on this matter. ___ Legal arrangements (actual/planned): SSFA signed in Sept 2013.___ First mission (actual/planned): ___ TOR completed (actual/planned): TORs for regional and national consultants have been drafted. ___ First disbursement date (actual/planned): First disbursement in Apr 2013.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes.___ If Yes, reasons for delay & action plan to resolve: Outstanding progress and financial reports to process further disbursements of SSFA. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: n/a.___ | Agreement expired in January 2015. Financial and progress reports sent on February 2015. Next disbursement coud not be processsed because progress report required additional information. NOU has been contacted several times to provide additional information but has not responded. Mission approved for 2Q of 2015. UMOJA travel restrictions. Mission re-scheduled for July 2015 once UMOJA is operative. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Implementation of the RMP: custom training | Individual | LAC | DMI | REF | 26 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2003-06-01 | 2000-11-01 |  | 2006-04-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices | Individual | LAC | DMI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2006-06-01 | 2008-12-01 | 20000 | -3000 | 17000 | 17000 | 100% | 0 | 0 |  | 2600 | -390 | 2210 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of refrigerant management plan | RMP | LAC | DMI | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2006-08-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | DMI | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-08-01 |  | 1998-09-01 | 1999-07-01 | 40000 | -16000 | 24000 | 24000 | 100% | 0 | 0 |  | 5200 | -2080 | 3120 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | DMI | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-07-01 | 2001-12-01 |  | 2004-02-01 | 2005-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | DMI | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-12-01 | 2007-04-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | LAC | DMI | SEV | 45 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-10-01 | 2008-01-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | DMI | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DMI | SEV | 56 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DMI | SEV | 62 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-08-01 | 2012-11-01 |  | 2014-02-01 | 2014-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Renewal approved at 72nd ExCom. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 4/2014-3/2016 ) | Individual | LAC | DMI | SEV | 72 | INS | 21 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-03-01 | 2016-03-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Renewal request prepared on Feb-2014. Renewal request submitted and comments from MLFS addressed in Apr-2014. Renewal approved in May-2014. Country reported CP data and Article 7 data on time. NOO attended the Caribbean Network meeting in Suriname Apr-2014, and the Joint Network meeting of Latin America and the Caribbean in the Dominican Republic Dec-2014. Celebration of International Ozone Day ___ Legal arrangements (actual/planned): Draft SSFA prepared in Sep-2014 and sent to country for comments. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Country requested UNEP to contract consultant services to implement activities; ROLAC to consult Paris based on OIOS Audit. General elections held in Dec-2014. Mission planned for 1Q of 2015 ___ If Yes, will delay have impact on project completion date (yes/no): yes ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: n/a. | Follow-up on progress in Jan-2015. Mission approved but had to be postponed. Country sent HPMP reports on Feb-2015; additional information required on the progress report in Feb-2015. Follow up with country during Network meeting in Mar-2015: country again requested UNEP to contract consultant services to implement activities but ramp-down and black-out periods in UMOJA would not allow to do this; in any case it is not recommended given the poor response from the country and the relative stability of the NOO. UNEP to undertake the approved mission and discuss with authorities modalities of implementation of IS activities, once NOU provides and adequate date, and person to contact. Mission to take place once UMOJA is live in Jun-2015.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | DOM | FUM | 30 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -9183 | 15817 | 15817 | 100% | 0 | 0 |  | 3250 | -1194 | 2056 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | DOM | PHA | 65 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2013-11-01 |  | 2013-11-01 | 2013-12-31 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-year | LAC | DOM | PHA | 69 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2013-04-01 |  | 2015-04-01 | 2016-06-30 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 10000 | 3250 | 0 | 0 | 3250 | 0 | Brief progress report: The HPMP second tranche implementation was approved in July 2013. Its implementation has been deferred to 2015 because there was no tranche for UNEP and the country decided to continue implementation of the second tranche (non-investment components) in the year of 2015. Legal arrangements: N/A. First disbursement date (actual/planned): No disbursements/Planned for October of 2015 (some delays because of UMOJA). All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: A managerial decisions is the reason for the late start of the project. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The Government continued to enforce the ODS rules and regulations that have been established since 2012, with regard to HCFCs. A policy to ban the import of HCFC-141b contained in imported pre-blended polyols will be in effect from 1 January 2016, and a draft resolution to ban the use of HCFC-141b for flushing in the refrigeration servicing sector has been prepared, and is expected to be completed by end of 2015. In cooperation with Implementing Agencies the progress report and annual implementation plan were submitted to request the third tranche. The NOU and UNEP agreed on specifications to purchase ODSs identifiers. Bidding process expected to be completed by the second half of 2015. Legal arrangements: N/A. First disbursement date (actual/planned): No disbursements/Planned for 2015. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: A managerial decisions is the reason for the late start of the project. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | LAC | DOM | REF | 25 | TRA | 14 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2003-06-01 | 2005-01-01 | 38000 | -10000 | 28000 | 28000 | 100% | 0 | 0 |  | 4940 | -1300 | 3640 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | DOM | REF | 25 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-02-01 |  | 2001-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2000-12-01
FIN | UNEP | Country programme preparation | Individual | LAC | DOM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1996-03-01 |  | 1995-07-01 | 1995-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the National Commission for the Ozone (Cogo) | Individual | LAC | DOM | SEV | 17 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1998-10-01 |  | 2000-02-01 | 2001-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 20150 | 0 | 20150 | 0 | 0 | Project financially completed. | Project financially completed. |  | 1998-10-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | DOM | SEV | 29 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 103000 | 0 | 103000 | 103000 | 100% | 0 | 0 |  | 13390 | 0 | 13390 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Policy and technical assistance | Individual | LAC | DOM | SEV | 37 | TAS | 31 | A | I | CFC | 0.8 | 0.8 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2006-06-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | DOM | SEV | 39 | INS | 34 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2006-11-01 | 2007-04-01 | 134333 | -1 | 134332 | 134332 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DOM | SEV | 48 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2009-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DOM | SEV | 56 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2010-11-01 |  | 2011-04-01 | 2011-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | DOM | SEV | 62 | INS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | DOM | SEV | 68 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-12-01 |  | 2014-12-31 |  | 134333 | 0 | 134333 | 83000 | 61.79% | 51333 | 51333 | 51333 | 0 | 0 | 0 | 0 | 0 | Brief progress report: NOO attended the Network meetings and the back to back bilateral sessions carried to monitor project implementation. Intermediate goals achieved as planned for the year 2014. (a) Progress and financial reports prepared by the NOU. (b) second & third cash advances released; (c) 2014 budget and work plan duly implemented; (d) ODSs license system implemented; (e) NOO collected ODS data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (f) Article 7 data and CP progress report data submitted in 2014; (g) NOU is responsible for providing support to the HPMP implementation. (h) On 16 September, the Minister of Environment cellebrated the International Ozone Day trough an oficial ceremony for awarding the RAC asosciation, and foam companies converted to non-HCFC technology . (i) Project renewal submitted to the 73 ExCom meeting. Legal arrangements (actual/planned): April 2013/Planned for April 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): April 2013/Planned for April 2013. All funds disbursed? Yes. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? N/A. If Yes, is any action required by ExCom: N/A | Project Completed in December 2014. All funds disbursed. NOO submitted all progress and financial report. UNON should change status of the last cash advance as a "disbursement completed" before financial completion.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | LAC | DOM | SEV | 73 | INS | 56 | A | I |  | 0 |  |  |  | 2014-11-01 | 2014-11-14 | 2016-12-31 | 2016-12-31 |  |  | 134333 | 0 | 134333 | 26866 | 20% | 107467 | 107467 | 26866 | 0 | 0 | 0 | 0 | 0 | Newly approved project. Work Plan and budget drafted in December 2014. | Brief progress report: Intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. Legal arrangement: signed in April 2015/initially planned for February 2015. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: May 2015. All funds disbursed? No. Any delay? Minor delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? No. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | National CFC phase-out plan (first tranche) | Multi-year | AFR | DRC | PHA | 49 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-12-01 |  | 2009-07-01 | 2010-12-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 |  | 18688 | 0 | 18688 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DRC | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-03-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 |  | 9344 | 0 | 9344 | 0 | 0
FIN | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | DRC | PHA | 61 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-09-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 |  | 9344 | 0 | 9344 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DRC | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 95000 | 0 | 95000 | 90000 | 94.74% | 5000 | 5000 |  | 12350 | 0 | 12349.9987 | 0.0013 | 0 | Project Completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | DRC | PHA | 70 | TAS | 38 | A | I |  | 2.9 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-07-01 | 2015-07-01 |  |  | 116500 | 0 | 116500 | 90000 | 77.25% | 26500 | 0 | 26500 | 15145 | 0 | 0 | 15145 | 0 | Brief progress report (actual/planned): In 2014, country trained 50 customs officers and 75 refrigeration technicians in Kisangani .Legal arrangements (actual/planned): Agreement signed in January 2014. All activities under the SSFA are completed (as planned) n/a___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in january 2014 __ All funds disbursed (yes/no): _ .__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Due to major changes in the National Ozone Unit there were no activities in 2015 to date.
FIN | UNEP | Assistance in developing the RMP project proposal | Individual | AFR | DRC | REF | 32 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2002-01-01 |  | 2003-12-01 | 2010-12-01 | 60000 | -16985 | 43015 | 43015 | 100% | 0 | 0 |  | 7800 | -2208.4 | 5592 | -0.4 | 0 |  |  |  | 2003-12-01
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | DRC | REF | 41 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for technicians in the refrigeration sector | Individual | AFR | DRC | REF | 41 | TRA | 15 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-10-01 |  | 2006-12-01 | 2010-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | DRC | REF | 41 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 109000 | -208 | 108792 | 108792 | 100% | 0 | 0 |  | 14170 | -27.04 | 14143 | -0.04 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | DRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Creation of an Ozone Office | Individual | AFR | DRC | SEV | 27 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2003-06-01 | 2000-04-01 |  | 2000-12-01 | 2004-04-01 | 32270 | 0 | 32270 | 32270 | 100% | 0 | 0 |  | 4195 | 0 | 4195 | 0 | 0
FIN | UNEP | Institutional strengthening project (renewal) | Individual | AFR | DRC | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-09-01 | 2005-12-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 8390 | 0 | 8390 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | DRC | SEV | 46 | INS | 22 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2005-07-01 | 2007-01-01 | 2007-07-01 |  | 2007-07-01 | 2009-07-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | DRC | SEV | 52 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-06-01 |  | 2009-06-01 | 2011-11-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | DRC | SEV | 58 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2011-08-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 48405 | 0 | 48405 | 48405 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | DRC | SEV | 62 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-12-01 |  | 2013-06-01 | 2014-06-01 | 64540 | 0 | 64540 | 64540.3 | 100% | -0.3 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | AFR | DRC | SEV | 71 | INS | 39 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 | 2015-12-01 |  |  | 64540 | 0 | 64540 | 32270 | 50% | 32270 | 32270 | 32270 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country has just signed the SSFA in June 2014. Country reported 2013 Art7 and 2013 CP data. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement planned in July 2014 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Due to major changes in the National Ozone Unit there were no activities in 2015 to date
FIN | UNEP | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2005-11-01 | 2006-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (first tranche) | Multi-year | ASP | DRK | PHA | 47 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2008-07-01 | 2009-07-01 | 234600 | 0 | 234600 | 234600 | 100% | 0 |  |  | 30498 | 0 | 30498 | 0 | 0
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (second tranche) | Multi-year | ASP | DRK | PHA | 49 | TAS | 44 | A | I | CFC | 54 | 54 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-12-01 |  | 2008-03-01 | 2011-11-01 | 163400 | -16532 | 146868 | 146868 | 100% | 0 |  |  | 21242 | -2149 | 19093 | 0 | 0
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (third tranche) | Multi-Year | ASP | DRK | PHA | 51 | TAS | 47 | A | I | CFC | 18 | 18 | 0 |  | 2007-03-01 | 2009-04-01 | 2008-03-01 |  | 2011-03-01 | 2012-03-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (fourth tranche) | Multi-Year | ASP | DRK | PHA | 54 | TAS | 50 | A | I | CFC | 19 | 19 | 0 | 0 | 2008-04-01 | 2011-01-01 | 2009-03-01 |  | 2011-04-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 64 | PRP | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 |  | 2013-12-01 | 2014-12-01 | 35000 | 0 | 35000 | 26000 | 74.29% | 9000 |  |  | 4550 | 0 | 3380 | 1170 | 0 | Project is financially completed | Project is financially completed
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (policy, and refrigeration servicing) | Multi-Year | ASP | DRK | PHA | 73 | TAS | 58 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 43500 |  | 43500 | 8591.6 | 19.75% | 34908.4 |  | 34908.4 | 5655 | 0 | 0 | 5655 | 0 | Brief progress report (actual/planned): Discussions with UNIDO and NCCE on developing an implementation plan and for disbursement of funds. A study tour to Beijing and cities in Guangdong Province to learn about HCFCs alternatives and phase-out approaches. Legal arrangement (actual/ planned): Because of the UN sanctions no funds can be transferred to the country. So no legal arrangement as yet. First mission (actual/ planned): UNIDO mission in 2nd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: N/A. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Severe delay, mainly due to UN sanctions and inability to transfer funds to the country for in country activities. UNEP is coordinating with the Lead Agency UNIDO to expedite the implementation and finalise fund transfer modality. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: To decide the approach to be followed for implementation. | Brief progress report (actual/planned): An implementation plan finalised and discussions with UNDP and NCCE on fund transfer approaches. A multi disciplinary team participated ina two day discussions with CAP adn UNIDO on strengthening the licensing and quota system and discusse investment component time lines on 27-28 April 2015 in Bangkok. A study tour to India to learn about HCFCs alternatives and phase-out approaches being planned for August 2015. Legal arrangement (actual/ planned): Because of the UN sanctions no funds can be transferred to the country. So no legal arrangement as yet. First mission (actual/ planned): UNIDO mission in 2nd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: N/A. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Severe delay, mainly due to UN sanctions and inability to transfer funds to the country for in country activities. UNEP is coordinating with the Lead Agency UNIDO to expedite the implementation and finalise fund transfer modality. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: To decide the approach to be followed for implementation.
FIN | UNEP | Development of a refrigerant management plan | RMP | ASP | DRK | REF | 35 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2002-08-01 |  | 2003-06-01 | 2005-05-01 | 60000 | -13466 | 46534 | 46534 | 100% | 0 |  |  | 7800 | -1750 | 6050 | 0 | 0
FIN | UNEP | Monitoring the activities in the refrigeration servicing subsector | Individual | ASP | DRK | REF | 40 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2005-12-01 | 10000 | -5000 | 5000 | 5000 | 100% | 0 |  |  | 1300 | -650 | 650 | 0 | 0 | Project is financially completed | Project is financially completed
FIN | UNEP | Training of refrigeration service technicians in good servicing practices | Individual | ASP | DRK | REF | 40 | TRA | 27 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2008-12-01 | 70000 | -2171 | 67829 | 67829 | 100% | 0 |  |  | 9100 | -282 | 8818 | 0 | 0
FIN | UNEP | Assistance for the development of a licensing system and training of customs officers | Individual | ASP | DRK | REF | 40 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-08-01 | 2006-01-01 | 50000 | -5486 | 44514 | 44514 | 100% | 0 |  |  | 6500 | -713 | 5787 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | DRK | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 1996-10-01 | 1997-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Cell | Individual | ASP | DRK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 2000-02-01 |  | 2000-12-01 | 2003-06-01 | 142560 | 0 | 142560 | 142560 | 100% | 0 |  |  | 18533 | 0 | 18533 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | ASP | DRK | SEV | 32 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-08-01 | 2003-01-01 |  | 2003-10-01 | 2003-12-01 | 95040 | 0 | 95040 | 95040 | 100% | 0 |  |  | 12355 | 0 | 12355 | 0 | 0
FIN | UNEP | Preparation of country programme update | Individual | ASP | DRK | SEV | 36 | CPG | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2003-04-01 |  | 2003-10-01 | 2005-05-01 | 30000 | -684 | 29316 | 29316 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | DRK | SEV | 41 | INS | 31 | A | I | CFC | 10.2 | 9.8 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2010-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | DRK | SEV | 47 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | DRK | SEV | 53 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phases VI and VII: 1/2010-12/2013) | Individual | ASP | DRK | SEV | 68 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-04-01 | 2013-12-01 | 2015-12-01 |  |  | 260000 | 0 | 260000 | 46235 | 17.78% | 213765 |  | 213765 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): With a view to keep the momentum in the country in 2014 and also in view of the non compiance decision of MOP, NCCE sent a formal endorsement of the workplan for IS project so that UNEP can initiate the activities directly. This letter dated 27 August 2014 was sent by NCCE on 1 September 2014. Based on this request and in agreement with the Paris Office of OzonAction, CAP started the implementation of some of the capacity building activities inside the country and outside with regional partners. NCCE continued to use its internal resources to manage the Ozone Cell and conduct other activities like assistance in formulating the HPMP, local organization of activities, data collection etc. UNEP in collaboration with UNIDO has organized certain technical assistance events and awareness activities by direct implementation. The Government has used their counterpart contribution (as mentioned in the IS project) for providing local logistical support for these activities. It was agreed with NCCE that until such transfer issues are sorted out, UNEP should continue to expend the funds in consultation with NCCE on capacity building activities like the China visit, awareness workshops of technicans and foam stakeholders, Ozone day celebrations in 2014 along with a media workshop in Pyongyang in 2014. However as advised by the MLFS, no further activities are being organised as of now and further guidance is being awaited from the Excom. However the country is in non compliance and there IS renewals requests since 1.1.2014 are not being submitted as the old funds are still remaining.Legal arrangements(actual/planned): Could not be signed because of UN sanctions on transfer of funds to the Government. Initial stages of project implementation(actual/planned): Project could not take off because of the sanctions. So UNEP implementing directly a few activities. Intermediate goals achieved (actual/planned): To a certain extent. Project completion and follow up: Project delayed. First disbursement date (actual/planned): N/A All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Because of UN sanctions funds cannot be transferred to the Government. UNEP consulting with UNDP and other UN Agencies in tn the country to explore fund transfer mechanisms. Meanwhile direct implementatuion of certain activities under the project being carried out by UNEP. If Yes, will delay have impact on project completion date (yes/no):Yes Any ongoing problems (yes/no): Fund transfer mechanism.If Yes, is any action required by ExCom: Excom monitoring the project and will need to decide what to do with this project since funds cannot be transferred. | CAP with support from UNIDO organized on 27-28 April 2015 a consultation for the inter‐ministry delegation from the Democratic People's Republic of Korea with the aim of accelerating national efforts to reduce production and consumption of HCFCs. During the two day consultation, the delegates carried out an in‐depth and multi‐agency analysis of the existing and future policies and their enforcement to control both the production and the import of HCFCs. Find a way to move forward on this project and bring the country back to compliance |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2014-07-30 | 2014-11-01 |  | 2014-12-31 | 2014-12-31 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 |  | 1625 | 0 | 0 | 1625 | 0 | Brief progress report: National Consultant hired to draft the banning of MB uses in soil fumigation. Decree approved and enforced. Legal arrangements: N/A. First disbursement date (actual/planned): July 2014 while it was initially expected to May 2012. All funds disbursed? Yes. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons duly solved in the year 2014. In Ecuador, the special bank account to receive project funds was opened only by end of 2013, which prevented an early transference of funds to the Government. Instead of cash advacne releasing, UNEP provided the service to hire the national consultant for drafting the Decree. If Yes, will delay have impact on project completion date? No. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ECU | PHA | 59 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 | 2013-12-01 | 75000 | -173 | 74827 | 74827 | 100% | 0 | 0.01 |  | 9750 | -22 | 9728 | 0 | 0.0013 | Project financially completed. | Project financially completed.
FIN | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 92835 | -75452 | 17383 | 17383 | 100% | 0 | 0 |  | 12069 | -9809 | 2260 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2013-05-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 92835 | -38222 | 54613 | 53962 | 98.81% | 651 | 0 |  | 12069 | -4968.86 | 7015.06 | 85.08 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-09-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 7485 | -272 | 7213 | 7213 | 100% | 0 | 0 |  | 973 | -35 | 938 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2012-12-01 | 2013-12-31 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | ECU | PHA | 70 | TAS | 59 | A | I |  | 0.4 |  | 0 |  | 2013-07-01 | 2014-02-05 | 2016-07-01 | 2016-07-01 |  |  | 20000 | 0 | 20000 | 15186 | 75.93% | 4814 | 0 | 2500 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report: Project progressed satisfactorily. National Consultant hired to assist in the liason between NOO and Customs. Intermediate goals achieved in 2014 are as planned: (a) HCFC quota system implemented; (b) HCFC baseline kept; (c) Customs training delivered to 32 customs officers. (d) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port. Legal arrangements: N/A. Funds directly administered by UNEP ROLAC as requested by the NOU. First disbursement date (actual/planned): January 2014/Planned for December 2013. All funds disbursed? No. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: Project progressed satisfactorily. National Consultant hired to assist in the liason between NOO and Customs. Intermediate goals achieved in 2015 are as planned: (a) HCFC quota system implemented; (b) HCFC baseline kept; (c) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port. Legal arrangements: N/A. Funds directly administered by UNEP ROLAC as requested by the NOU. First disbursement date (actual/planned): January 2014/Planned for December 2013. All funds disbursed? No. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | ECU | SEV | 59 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-03-01 | 2011-11-01 | 2015-12-31 |  |  | 95767 | 81034 | 176801 | 16855.02 | 9.533% | 159945.98 | 55000 | 55000 | 12449.71 | 0 | 2191.1526 | 10258.5574 | 0 | Brief progress report: A new cash advance issued in August 2014. Intermediate goals achieved as follow: (a) ODSs license system implemented; (b) NOO collected ODS data and cross-checked information with Customs before submission of 2012 Country Programme and Article 7 Reports. (c) Article 7 data and CP progress report data submitted in April and September 2013; (d) NOU is responsible for providing support to the HPMP implementation and the MB total phase-out project. (e) On 16 September, the Ministry sent press releases about the ozone layer. Legal arrangements: First legal arrangement was signed in 2011, but expired in 2013. A revised SSFA was signed in July 2014. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): March 2012/Planned for May 2010. A new cash advance released in August 2014. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons prevented the project implementation as approved. Low disbursements due to the difficulty for opening a special banking account to receive grants. Some direct payments from UNEP ROLAC were issued. However, direct implementation of the ISP is not cost/effective in the long term because UNEP is a Non-Resident Agency in Ecuador. Finally, the banking account was operationally by end of 2013. If Yes, will delay have impact on project completion date? Estimated 24 months of project delays, since planned completion date is December 2013. Any ongoing problems? No, the Bank Account is now opened. If Yes, is any action required by ExCom? N/A. | Brief progress report: The SSFA (agreement) signed in 2014 is progressing but with some delays related to progress and financial reports. Intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Legal arrangements: First legal arrangement was signed in 2011, but expired in 2013. A revised SSFA was signed in July 2014. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): March 2012/Planned for May 2010. A new cash advance released in August 2014. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons prevented the project implementation as approved. Low disbursements due to the difficulty for opening a special banking account to receive grants. Some direct payments from UNEP ROLAC were issued. However, direct implementation of the ISP is not cost/effective in the long term because UNEP is a Non-Resident Agency in Ecuador. Finally, the banking account was operationally by end of 2013. If Yes, will delay have impact on project completion date? Estimated 24 months of project delays, since planned completion date is December 2013. Any ongoing problems? No, the Bank Account is now opened. If Yes, is any action required by ExCom? N/A.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | AFR | EGY | PHA | 73 | PRP | 122 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-11-01 | 2015-11-30 |  |  | 20000 |  | 20000 | 0 | 0% | 20000 | -5.8265e-13 | 15000 | 2600 | 0 | 0 | 2600 | 0 | Newly approved project | SSFA for the newly approved project was prepared in March 2015 and shared with the country for comments. SSFA has now been finalised awaiting country to sign
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | ELS | PHA | 53 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2008-11-01 |  | 2009-06-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 |  | 2012-06-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | TAS | 28 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 | 2016-12-01 |  |  | 166500 | 0 | 166500 | 31372.23 | 18.84% | 135127.77 | 51560 | 30000 | 5850 | 0 | 397 | 5453 | 832.5622 | Brief progress report: Meetings with ODS importers for 2014 quota allocation; preparation and signing of Executive Agreement No. 52, setting up quota system and reduction targets; diffusion through media of the actions performed with support of the MLF of the Montreal Protocol to protect the ozone layer in the framework of the International Day for the Preservation of the Ozone Layer in 2014; training of customs officers on prevention of ODS illegal trade and use of refrigerant identifiers. Legal arrangements (actual/planned): Tri-partite agreement signed by the Government, UNEP, and UNDP Country Office in November 2013. First mission (actual/planned): It was carried out in July 2013, while no specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): Financial authorization issued in November 2013. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: UNEP’s HPMP components and ISP were incorporated into a UNDP ProDoc for implementation of activities, but investment activities were prioritized. However, all planned activities will be completed during last half of 2014 and 2015. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | Progress and financial report sent on Feb-2015. Second financial authorization processed in Apr-2015. Agreement expired. Drafting of new agreement ongoing and to be implemented after UMOJA goes live.
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | ELS | REF | 25 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 2000-02-01 |  | 2001-12-01 | 2003-07-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 | 0 |  | 5070 | 0 | 5070 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2000-12-01
FIN | UNEP | Implementation of the RMP: customs training | Individual | LAC | ELS | REF | 25 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2004-03-01 | 2005-02-01 | 38000 | -14300 | 23700 | 23700 | 100% | 0 | 0 |  | 4940 | -1859 | 3081 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | ELS | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-06-01 |  | 1997-03-01 | 1999-01-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 |  | 5200 | -650 | 4550 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Area of policies for the protection of the ozone layer (institutional strengthening) | Individual | LAC | ELS | SEV | 22 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 2000-05-01 |  | 2001-06-01 | 2001-12-01 | 66900 | 0 | 66900 | 66900 | 100% | 0 | 0 |  | 8697 | 0 | 8697 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | ELS | SEV | 32 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-03-01 | 2004-05-01 | 44600 | 0 | 44600 | 44600 | 100% | 0 | 0 |  | 5798 | 0 | 5798 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ELS | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2006-10-01 | 57980 | 0 | 57980 | 57980 | 100% | 0 | -5.0893e-13 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | ELS | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-06-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (year 1 of phase V) | Individual | LAC | ELS | SEV | 52 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-09-01 |  | 2009-09-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (year 2 of phase V) | Individual | LAC | ELS | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | EQG | PHA | 56 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | -10528 | 74472 | 69472 | 93.29% | 5000 | 5000 |  | 11050 | -1369 | 9681 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | EQG | PHA | 57 | TAS | 04 | A | I | CFC-12 | 4.6 | 4.6 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-09-01 |  | 2013-12-01 | 2014-12-01 | 105000 | -25000 | 80000 | 80000 | 100% | 0 | 0 |  | 13650 | -3250 | 10400 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | EQG | PHA | 65 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 21985 | 54.96% | 18015 | 0 | 18015 | 5200 | 0 | 2858 | 2342 | 2341.95 | Brief progress report (actual/planned): One refrigeration workshop for 25 participants on recovery and recycling was organized in August 2014. Also an awarness workshop for importer of refrigerant has been organized in October 2014._ Legal arrangements (actual/planned): Agreement signed in February 2012. . __ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2012__ All funds disbursed (yes/no): _ No. SSFA has a balance of US$13,000.__ Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: The delay was due to the problems encountered by the Implementing Agencies to travel to Malabo but UNEP decided to use an Expert from a neighboring country (Gabon) to start activities ___ If Yes, will delay have impact on project completion date (yes/no): _NO __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | UNEP CAP organized a mission to Malabo in March 2015. A workshop for 20 Customs officers on identification of ODS and application of the quota system organized in Malabo in March 2015.
FIN | UNEP | Project preparation for a country programme/refrigerant management plan | Individual | AFR | EQG | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-03-01 | 2007-07-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Start-up of institutional strengthening project | Individual | AFR | EQG | SEV | 49 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-12-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | EQG | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 | 2015-12-01 |  |  | 80000 | 0 | 80000 | 24250.3 | 30.31% | 55749.7 | 0 | 55750 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013. 2013 Ozone day was celebrated .Legal arrangements (actual/planned): Agreement signed in January 2011. All activities under the SSFA are completed (as planned) no___ First mission (actual/planned): _ N/A - Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 2011 __ All funds disbursed (yes/no): NO_ Final payment _ Any delay? (yes/no): YES__ If Yes, reasons for delay & action plan to resolve: UNEP renewed SSFA to extend it up to 2015 to allow the country to implement activities.__ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country reported 2014. Art5 data and CP data for 2014. NOU coordinated also the organization of the worksop organised under the HPMP implemention for Customs officers.
COM | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2011-02-01 | 2010-03-01 |  | 2014-12-31 |  | 100000 | -20000 | 80000 | 80000 | 100% | 0 | 0 | 0 | 13000 | -2600 | 10400 | 0 | 0 | Brief progress report (actual/planned): The country did not have an Ozone Officer for a long time, to coordinate and implement Ozone projects resulting in long project delay. The Project Funds were returned to ExCom in 2014. The Government appointed an Ozone officer in June 2014. The newly recruited Ozone Officer participated at the Regional Network Meetings organized in 2014. CAP undertook a Joint mission with UNIDO in December 2014 to conduct a National Training Workshop on Certification and Standards in the Refrigeration and Air Conditioning Sector and to train the Ozone unit on speedy implementation of all Montreal Protocol activities. Legal arrangements(actual/planned): SSFA was signed and first payment was made in February 2011. Initial stages of project implementation(actual/planned): Achieved__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): The first disbursement was made in February 2011_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2014 data on ODS imports and consumption is ongoing.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ERI | PHA | 55 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2013-07-01 | 2014-07-01 | 85000 | -15000 | 70000 | 55000 | 78.57% | 15000 | 15000 |  | 11050 | -1950 | 9100 | 0 | 0 | Project Completed
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 |  | 2014-12-01 | 2014-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ERI | PHA | 67 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-12-14 | 2016-07-01 | 2016-07-01 |  |  | 40000 | 0 | 40000 | 2818 | 7.045% | 37182 | 0 | 37182 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): Country recruited Ozone Officer in June 2014. CAP undertook a mission in Dec 2014 to train Ozone Officer on speedy implementation of the Montreal Protocol activities and prepared all pending reports. Legal arrangements(actual/planned): SSFA was prepared and signed by the country. Initial stages of project implementation(actual/planned): Not achieved due to the delay in appointing ozone officer__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): Disbursement has delayed due to the launch of UMOJA_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA was signed by country, awaiting first disbursement and disbursement delayed due to the launch of UMOJA. Country has registered all the importesr of HCFC for 2015 |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | ERI | SEV | 47 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2008-02-01 | 2009-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Country programme/RMP project preparation | RMP | AFR | ERI | SEV | 47 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 40000 | -2000 | 38000 | 38000 | 100% | 0 | 0 |  | 5200 | -260 | 4940 | 0 | 0
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | ERI | SEV | 54 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2010-05-01 | 2010-03-01 | 2015-07-01 |  |  | 40000 | 0 | 40000 | 22007.85 | 55.02% | 17992.15 | 0 | 17992 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The country has been without an Ozone Officer for a long time, resulting in delay in implementation of activities in the country. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in April 2010. Initial stages of project implementation(actual/planned): Not achieved due to the delay in appointing ozone officer__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): The first disbursement was made in May 2010, not as planned._ All funds disbursed (yes/no): NO, Country submitted all the reports awaiting disbursement of final payment_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | NOU registered all importers of HCFC for 2015, supported the planning meeting of the Refrigeration Association and undertook inspection visits to shops to check what type of refrigerant is sold on the market
ONG | UNEP | Institutional strengthening (phase II: 1/2013-12/2014) | Individual | AFR | ERI | SEV | 68 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-11-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country recruited Ozone Officer in June 2014. CAP undertook a mission in Dec 2014 to train Ozone Officer on speedy implementation of the Montreal Protocol activities and prepared all pending reports. Legal arrangements(actual/planned): SSFA was prepared and signed by the country. Initial stages of project implementation(actual/planned): Not achieved due to the delay in appointing ozone officer__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): Disbursement has delayed due to the launch of UMOJA_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA was signed by country, awaiting first disbursement. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2014 data on ODS imports and consumption is ongoing. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ETH | FUM | 30 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -7326 | 17674 | 17674 | 100% | 0 | 0 |  | 3250 | -952.38 | 2298 | -0.38 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ETH | PHA | 56 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2013-07-01 | 2014-07-01 | 85000 | -23581 | 61419 | 46419 | 75.58% | 15000 | 0 |  | 11050 | -3065 | 7985 | 0 | 0 | Project Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ETH | PHA | 68 | TAS | 21 | A | I |  | 0.3 | 0 | 0 | 0 | 2012-12-01 | 2013-06-01 | 2016-12-01 | 2016-12-01 |  |  | 85000 | 0 | 85000 | 80000 | 94.12% | 5000 | 0 | 5000 | 11050 | 0 | 7150 | 3900 | 3250 | Brief progress report (actual/planned): _Country conducted National Customs training where asbout 90 customs officers from various boarders were trained. Country trained 30 Refrigeration technicians in standards and certification during the Regional Workshop which was hosted by the country.__ Legal arrangements(actual/planned): SSFA signed and first payment sent in June 2013___ First mission (actual/planned): __UNEP conducted a Joint mission with UNIDO in December 2013 and met all stakeholders involved in the implementation of the project to plan for the speedy implementation of activities.Another mission by CAP to conduct customs officer training was done inAugust 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): first payment sent in June 2013___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): __Yes_ If Yes, reasons for delay & action plan to resolve: _The project experienced some delays due to the change of the Montreal Protocol Focal Point from Meteorological Department to Minsitry of Environment. CAP trained the new NOU and implementation of activities is on track.__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | NOU registered all importers of HCFC for 2015, advertised for quota allocation for 2015 HCFC importation and conducted inspection visists to various boarders to check how customs officers are enforcing the control measures of HCFC imporation
FIN | UNEP | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 30 | TRA | 09 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2003-06-01 |  | 2003-06-01 | 2007-07-01 | 82735 | -24380 | 58355 | 58355 | 100% | 0 | 0 |  | 10755 | -3169.24 | 7586 | -0.24 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | ETH | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of national ozone cell for the implementation of Montreal Protocol in Ethiopia | Individual | AFR | ETH | SEV | 20 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-01-01 | 1999-11-01 | 60500 | 0 | 60500 | 60500 | 100% | 0 | 0 |  | 7865 | 0 | 7865 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (phase 3 year 2) | Individual | AFR | ETH | SEV | 29 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 40300 | 0 | 40300 | 40300 | 100% | 0 | 0 |  | 5239 | 0 | 5239 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project for a one year period (phase 3) | Individual | AFR | ETH | SEV | 39 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2006-12-01 | 2009-05-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2005-12-01 |  | 2008-12-01 | 2009-12-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 50 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-07-01 | 2008-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ETH | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 | 2015-12-01 |  |  | 32500 | 27500 | 60000 | 33000 | 55% | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU was relocated to a different institution, Environmental Protection Authority, in March 2014 and experienced delay due to institutional transfers, change of Banking systems and recruitment of a new ozone officer. The NOU hosted two African Regional Network meetings in 2014 and attended all Montreal Protocol Meetings. The country celebrated 2014 Ozone day and submitted 2013 Article 7 data and Country Programme report. Legal arrangements(actual/planned): The SSFA was signed in May 2011. Initial stages of project implementation(actual/planned): Achieved__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): The first disbursement ($19,500) was made in May 2011, second disbursement ($13,500) was sent in Feb 2014._ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country changed Focal Point for Montreal Protocol, hence the new Ozone Unit took long time to be familiar with Montreal Protocol activities__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Collection of the 2014 data on ODS imports and consumption is ongoing.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2015-12/2016) | Individual | AFR | ETH | SEV | 73 | INS | 23 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 12000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA for the newly approved project (IS Phase VI) was prepared in March 2015 and sent to country for signature. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned)N/A__ Intermediate goals achieved (actual/planned): _N/A_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):N/A,_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for the newly approved project (IS Phase VI) was prepared in March 2015 and sent to country for signature.
ONG | UNEP | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | Individual | EUR | EUR | DES | 69 | DEM | 13 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-09-01 | 2015-04-01 | 2015-12-01 |  |  | 75000 | 0 | 75000 | 33475.34 | 44.63% | 41524.66 |  | 41525 | 9750 | 0 | 505 | 9245 | 883.701 | Brief progress report (actual/planned): UNEP in cooperation with Montenegro organized the meeting on aggregation of ODSs stocks for further disposal and improvements in the refrigerants recovery and recycling system in Montenegro held on 14 and 15 October of 2014. UNEP financed two experts from Croatia to participate in the meeting as resource persons. The similar national workshop was organized in Bosnia and Herzegovina on 22 and 23 October of 2014. UNEP also financed two experts from Croatia to participate in the meeting as resource persons. The main objective of the meetings were to disseminate excellent experiences of the collection and aggregation system applied in Croatia and to assist both countries in further enhancement of the collection efforts during the project life and beyond. Croatia has implemented activities under the sub-component of the project on targeted Inspections for Complying with the RRR Scheme). The training for environment inspectors was organized on 6-7 November in Zagreb. In total, 70 environment inspectors were trained by three international resource persons: two from Slovenia and one from Austria. This activity was done in conformity with ECA destruction project work plan and supported by HPMP. Furthermore, UNEP in cooperation with Croatia organized one day national training on ODSs waste management in Republic of Croatia on 9 December of 2015. The main goal was to review and discuss key steps for implementation of disposal activities in Croatia: data survey, laboratory analysis, training activities, aggregation, transportation, verification, destruction, and monitoring. UNEP organized 2 days midterm meeting (B&H, Croatia, Montenegro, UNEP and UNIDO) on 10-11 December of 2014. The main goal of the meeting was to review the implementation of the project activities in all three countries (Bosnia and Herzegovina, the Republic of Croatia, and Montenegro) and facilitate the completion of all additional work for a disposal of the second as well as the last batch of the ODS stocks in the participatory countries. Legal arrangements (actual/planned): N/a The project is directly managed and implemented by UNEP Initial stages of project implementation (actual/planned): The start-up meeting was organized and action plan was endorsed by participatory countries. (According to the project document). Intermediate goals achieved (actual/planned): Work programme for the years of 2014-2015 (first half) was fully implemented Project completion and follow up: Project ongoing First disbursement date (actual/planned): September, 2013 as planned All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): UNEP has started arrangements for the little study/evaluation for joint efforts ODSs and POPs waste destruction within the country. The countries requested UNEP to explore the possibilities to hire a consultant (short term) to make such evaluation. UNEP and UNIDO has initiated in cooperation with participatory countries the preparation of the report as well as a leaflet. The leaflet will demonstrate both advantages and disadvantages of the regional approach and lessons learned for other A5 LVC countries. UNEP in cooperation with Montenegro has started preparing the final meeting under the ECA destruction project to be organized in October of 2015 (exact dates will depend on MOP/ExCom dates). Two days meeting will be hosted by Montenegro. Participants agreed to invite representatives of Turkey and Georgia as resource persons to present the lessons learn from the respective destruction projects. Legal arrangements (actual/planned): N/a The project is directly managed and implemented by UNEP Initial stages of project implementation (actual/planned): The start-up meeting was organized and action plan was endorsed by participatory countries. (According to the project document). Intermediate goals achieved (actual/planned): Work programme for the years of 2014-2015 (first half) was fully implemented Project completion and follow up: Project ongoing First disbursement date (actual/planned): September, 2013 as planned All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
FIN | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | Individual | EUR | EUR | SEV | 39 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 53666 | 0 | 53666 | 53666 | 100% | 0 | 0 |  | 6977 | 0 | 6977 | 0 | 0
FIN | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Individual | EUR | EUR | SEV | 57 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 | 2013-12-01 | 51250 | 0 | 51250 | 51250 | 100% | 0 | 0 |  | 6663 | 0 | 6663 | 0 | 0
FIN | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Individual | EUR | EUR | SEV | 60 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2012-04-01 | 2011-04-01 |  | 2012-10-01 | 2013-12-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 | 0 |  | 3575 | 0 | 3575 | 0 | 0
FIN | UNEP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0
FIN | UNEP | Development of a total ODS phase out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-11-01 | 2006-03-01 | 15000 | -83 | 14917 | 14917 | 100% | 0 |  |  | 1950 | -11 | 1939 | 0 | 0
FIN | UNEP | Implementation of the TPMP (non-investment component) | Individual | ASP | FIJ | PHA | 47 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2009-12-01 |  | 2010-01-01 | 2011-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | FIJ | PHA | 65 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2014-11-01 |  | 2014-12-01 |  | 47900 | 0 | 47900 | 47900 | 100% | 0 |  | 0 | 6227 | 0 | 6227 | 0 | 0 | Brief progress report (actual/planned): The second tranche of HPMP was approved at the 73rd ExCom Meeting in November 2014. In 2014, a total of 119 RAC technicians were trained at National Training & Productivity Centre from the workshops in April, May, October and November. All trained technicians granted licenses are recorded within NOU database. In May 2014, the training of enforcement officers was organized in the Central Division and 17 officers were trained. Moreover, enforcement officers were trained on the job and through WCO- UNEP e- learning. Refrigerant identifiers procured under HPMP have been kept at the NOU. When the ODS shipment arrives, the Customs contacted the NOU to bring refrigerant identifier for inspection during the Customs clearance. Four sets of refrigerant identifiers would be distributed once the contract between NOU and the Customs is vetted by the Solicitor- General’s Office. Ongoing awareness raising and monitoring activities of HPMP were held in 2014. Awareness materials were developed time to time upon need basis especially for Customs/ Shipping agents and Enforcement Officers. Materials included pamphlets, posters and Customs booklet for identification of ODS. The project was completed in December 2014. Legal arrangement: The SSFA has been signed in September 2012. TOR completed: N/A First disbursement date: September 2012 All funds disbursed (yes/no): Yes, the last payment was made in December 2014 Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Project completed. The last payment has been made to Fiji in December 2014. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | FIJ | PHA | 73 | TAS | 28 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 24400 |  | 24400 | 0 | 0% | 24400 |  | 24400 | 3172 | 0 | 0 | 3172 | 0 | Brief Progress report: Newly approved project at the 73rd Meeting in November 2014. After the ExCom approval, UNEP worked with the NOU to draft the SSFA. Legal arrangements (actual/planned): No.TOR completed: N/A First disbursement date: N/A. All funds disbursed (yes/no): No. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | UNEP and the country prepared and agreed on a detailed work plan of the second tranche of HPMP (2015-2016), which was finalized in February 2015. The draft SSFA has been prepared based on agreed work plan and is being reviewed by the Solicitor- General’s Office. 2014 CP data timely submitted online.
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | FIJ | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1999-11-01 | 2002-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | FIJ | REF | 29 | TRA | 06 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-01-01 | 2004-10-01 | 70500 | -24500 | 46000 | 46000 | 100% | 0 |  |  | 9165 | -3185 | 5980 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | FIJ | REF | 29 | TRA | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2004-07-01 | 2008-12-01 | 42500 | -1811 | 40689 | 40689 | 100% | 0 |  |  | 5525 | -235 | 5290 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | FIJ | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -2165 | 22835 | 22835 | 100% | 0 |  |  | 3250 | -281 | 2969 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | FIJ | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1997-03-01 |  | 2000-07-01 | 2001-12-01 | 65890 | 0 | 65890 | 65890 | 100% | 0 |  |  | 8566 | 0 | 8566 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | FIJ | SEV | 29 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2001-12-01 |  | 2002-05-01 | 2007-03-01 | 43930 | 0 | 43930 | 43930 | 100% | 0 |  |  | 5711 | 0 | 5711 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | ASP | FIJ | SEV | 37 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2004-08-01 | 2008-12-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | FIJ | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV- year 2) | Individual | ASP | FIJ | SEV | 47 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | FIJ | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-11-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | FIJ | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | FIJ | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2012-11/2014) | Individual | ASP | FIJ | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-07-01 | 2014-11-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project completed in December 2014. NOU coordinated the amendment of the memorandum of understanding with the customs department. Orgnaised the national stakeholder consultation processes, working with stakeholders on incorporating HCFC-based equipment into the phase-out strategy and for preparation and approval of annual quotas for creation of a national council on HCFC quota assessment. The NOU is responsible for the maangement of the HPMP:Technicians’ training and implementation of the recovery and recycling programme, custom officers’ training and strengthening border control, amendment and improvement of the memorandum of understanding with the customs department, working with stakeholders on incorporating HCFC-based equipment into the phase-out strategy, creation of a national council on HCFC quota assessment, periodic data collection and reporting, implementation of the public awareness outreach programme. Article 7 and CP data timely submitted. In Augsut of 2014, Fiji hosted the PIC regional HCFC thematic meeting. Legal Arrangement: SSFA singed in June 2013 First Disbursement Date: July 2013 All funds disbursed (yes/no): Yes Any delay? (yes/no): No delay. Any ongoing problems (yes/no): No. Project remewed at the 72nd Ex. Com. | Project completed in December 2014.
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 12/2014-11/2016) | Individual | ASP | FIJ | SEV | 72 | INS | 26 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-11-01 | 2016-11-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: New Project: Stable, continued NOU and functioning as part of the instituional system of Government. Progress of Activities for 2014 reported under phase V111 and HPMP Stage 1 second tranche approved at the 73rd Ex. Com. NOU Fiji is responsible for HPMP including: management of licensing/permitting system and iPIC mechanism, country has completed both the phase I of the Training of the Service Technicians and Training of the Enforcement Officers . Fiji is also ready to provide capacity building assistance to its neighbouring PICs under the south- south cooperation scheme on the implementation of the Montreal Protocol. Article 7 and CP data timely submitted and compliance sustained. As per the decision of the 73rd Ex. Com. NOU prepared and submitted to the OS request for change in HCFC base line. NOU attended the Tonga 2104 meeting and Fiji Hosted the 2014 HCFC PIC regional thematic meeting. Legal Arrangement: SSFA signed on April 2015. First disbursement date: April 2015. All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Agreement signed on April 2015.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Micronesia) | Multi-Year | ASP | FSM | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-09-01 | 2015-03-01 | 2015-12-01 |  |  | 53875 | 0 | 53875 | 50174 | 93.13% | 3701 |  | 3701 | 7004 | 0 | 5260 | 1744 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. Federal States of Micronesia (FSM) has not yet adopted the 2012 HS code because the FSM National Government along with the four state governments were undergoing major tax reform process including the upgrading of 2012 HS code. Custom officers have been trained on the migrating of the 2012 HS code. The permit system for storage and sales of HCFCs and requirement for HCFC handlers to be certified for enrolling in RAC sector has been in place. The government also conducted the RAC Certification Program under piloting stage. The banning process on selected HCFC-based equipment was still under discussion as there was a need to provide some reliable data to assess the impact of such ban. An Assessment Survey was conducted to get data to analyse the impact. Refrigerant identifier was handed over to Customs for inspection. Additional 3 RAC Associations were established in 2014 making FSM to have RAC Associations in all stages. Two refresher training workshops for RAC technicians were organized in May and November 2014. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in April 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: September 2012 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Migrating of 2012 HS code awaits results from FSM Congress and FSM President on the future prospects of the proposed tax reform scheme. The full scheme of certification program will be launched after evaluation and improvement by the OEEM and COM-FSM. The Assessment Survey was completed. NOU has requested legal advice from Department of Justice on amending the current ODS regulation to include the banning of HCFC-based equipment. NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online.
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | FSM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | -2761.13 | 31238.87 | 31239 | 100% | -0.13 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | FSM | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-07-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (2nd year of phase II) | Individual | ASP | FSM | SEV | 58 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | FSM | SEV | 61 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | FSM | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-07-01 | 2014-12-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project completed in December 2014. NOU has established a strong working relationship with Custom office, College of Micronesia, state Environment Protection agencies and other key stakeholder in the private sector to implement the Montreal Protocol and HPMP. In 2013 awareness videos were aired on TV station as well as radio talk show, other campaign materials such as banners, flyers, poster and bumper stickers were display. for 2014 we are planning to have fun walk on each state and to RAC member of each state to test the auto mobiles. Ongoing enforcement of the quota system and issued annually to approved importers. Working closely with the Customs Department to strengthen border control. Ongoing, quality and timely data submission, data collection and reporting under the Montreal Protocol regime. Management of Annual consultation in each of the 4 States of the FSM, consultation with stakeholders to mobilize support of the HPMP implementation. (actual/planned): N/A since Project is ongoing. Intermediate goals achieved (actual/planned): Assistance in the implementation of the HPMP including enforcement of the quota system, working closely with the Customs Department to strengthen border control and data collection and reporting under the Montreal Protocol regime, consultation with stakeholders to mobilize support of the HPMP implementation, and data reporting to the Fund and Ozone Secretariats. (as planned) . NOU has established a strong working relationship with Custom office, College of Micronesia, state Environment Protection agencies and other key stakeholder in the private sector to implement the Montreal Protocol and HPMP. In 2013 awareness videos were aired on TV station as well as radio talk show, other campaign materials such as banners, flyers, poster and bumper stickers were display. For 2014 NOU had fun walk on each state and to RAC member of each state to test the auto mobiles. Ongoing enforcement of the quota system and issued annually to approved importers. Working closely with the Customs Department to strengthen border control. Ongoing, quality and timely data submission, data collection and reporting under the Montreal Protocol regime. Management of Annual consultation in each of the 4 States of the FSM, consultation with stakeholders to mobilize support of the HPMP implementation. Legal Arrangement: SSFA signed on February 2013, completed in Dec 2014 . First Disbursement Date: July 2013 All funds disbursed (yes/no): Yes Any delay? (yes/no): No delay. Any ongoing problems (yes/no): No. Stable NOU. | Project completed as of Dec. 2014.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | FSM | SEV | 72 | INS | 09 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project approved at the 72nd Ex. Com. Legal Arrangement: SSFA signed in March 2015. First payment made as per SSFA. Apri, 2015 All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Agreement signed in March 2015. First payment made as per SSFA. Country timely submitted CP 2014 data on line and Article 7 report to the Ozone Secretariat.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAB | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2008-05-01 | 2009-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2010-07-01 | 2012-07-01 | 65000 | -2493 | 62507 | 62507 | 100% | 0 | 0 |  | 8450 | -324 | 8126 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GAB | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-01-01 | 2012-01-01 | 85000 | -4947 | 80053 | 80053 | 100% | 0 | 0 |  | 11050 | -643 | 10407 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 50000 | 0 | 50000 | 35047.5 | 70.09% | 14952.5 | 0 |  | 6500 | 0 | 4550 | 1950 | 1950 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2013-01-01 | 2013-12-01 | 2015-12-01 |  |  | 90000 | 0 | 90000 | 53250.64 | 59.17% | 36749.36 | 0 | 1740.36 | 11700 | 0 | 6923 | 4777 | 4551.17 | Brief progress report (actual/planned): 35 Refrigeration technicians have been trained on 16 September 2014. A workshop of 20 customs officers and 5 enforcement Officers from trade department has been organized on 21 September 2013. Two awareness workshop of around 200 participants have been organized in June 2014 in Libreville and Port Gentile .___ 2.__ Legal arrangements (actual/planned): Agreement signed in November 2011. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in Jan. 2012. Payment cancelled in June 2013 due to non-liquidation by UNDP, and re-issued in June 2013 __ All funds disbursed (yes/no): Yes. _ Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: Change of NOO ___ If Yes, will delay have impact on project completion date (yes/no): _ No, because a new Coordinator has been appointed and activities implementation started with a chronogram to to implement all activities under the SSFA by end of November 2014 __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ Completed. Final payment ($35,000) sent. Aug. 2014 | Project completed and second tranche was approved. SSFA drafted and country contacted for signature.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GAB | PHA | 73 | TAS | 30 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-09-01 | 2016-09-30 |  |  | 46000 |  | 46000 | 0 | 0% | 46000 | -5.8265e-13 | 20000 | 5980 | 0 | 0 | 5980 | 0 | Brief progress report (actual/planned): __SSFA Drafted . Legal arrangements (actual/planned):SSFA to be signed in July 2015. Any delay (Yes/No): Yes_ First mission (actual/planned): N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): n/a___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Country contacted for signature of the SSFA and discussions on the schedule of activities.
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | GAB | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-09-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | GAB | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2003-12-01 | 2005-01-01 | 31000 | -10000 | 21000 | 21000 | 100% | 0 | 0 |  | 4030 | -1300 | 2730 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme ( phase II) | Individual | AFR | GAB | REF | 41 | TRA | 12 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 50000 | -1985 | 48015 | 48015 | 100% | 0 | 0 |  | 6500 | -258.05 | 6242 | -0.05 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | GAB | REF | 41 | TRA | 13 | A | I | CFC | 1.9 | 1.9 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | GAB | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-05-01 | 1997-06-01 | 10000 | 33000 | 43000 | 43000 | 100% | 0 | 0 |  | 1300 | 4290 | 5590 | 0 | 0
FIN | UNEP | Creation of a National Ozone Technical Group | Individual | AFR | GAB | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2001-12-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 |  | 5928 | 0 | 5928 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | GAB | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 |  | 3952 | 0 | 3952 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | AFR | GAB | SEV | 37 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2005-02-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | GAB | SEV | 44 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAB | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAB | SEV | 56 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GAB | SEV | 62 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 27000 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | GAB | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Coordination of the organization of: a Workshop for 25 customs officers on identification of ODS in June 2014; Training of 50 refrigeration technicians on recovery and conversion technics in September 2014. Press Briefings on the SAO in September 2014; Meeting with trade and Finance Ministries on the use of quota system. ___ 2.__ Legal arrangements (actual/planned): Agreement signed in February 2014. activities under the SSFA started inMarch 2014 ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in February 2014__ All funds disbursed (yes/no): _ No. __ Any delay? (yes/no): No ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): _NO __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | June 5 : Organisation of a workshop of 40 participant on the existing quopta and licensing system. Organization in February 2015 of a survey on HCFCs import for the year 2014. Report of 2014 CP data in June 2015
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAM | PHA | 49 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-08-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | GAM | PHA | 53 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 93000 | 0 | 93000 | 93000 | 100% | 0 | 0 |  | 12090 | 0 | 12090 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 |  | 9360 | 0 | 9360 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 | 2016-11-01 | 2014-12-01 |  | 25000 | 0 | 25000 | 15739.84 | 62.96% | 9260.16 | 0 | 5000 | 3250 | 0 | 2600 | 650 | 0 | Brief progress report (actual/planned): _The NOU conducted training for 60 refrigeration technicians and 40 Custom Officers on ODS control. The country procurred and distributed toolkits to the Refrigeration Association. NOU conducted inspection visists to the fish factories to check what refrigerants are being used and discuss with companies on the switch to ODS alternatives . Implementation of first tranche activities completed and country is processing to start implementation of second tranche activities. Legal arrangements(actual/planned):SSFA was signed in March 2012___ First mission (actual/planned): __UNEP conducted first mission in May 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement ($10,000) was made in April 2012.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Project completed and second tranche was approved. SSFA drafted and country contacted for signature.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | GAM | PHA | 71 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-11-01 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): _The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. Verification will be done in 2016, when the country request for third HPMP tranche. Legal arrangements(actual/planned):N/A___ First mission (actual/planned): __N/A. TOR completed(actual/planned): _YES__ First disbursement date (actual/planned): N/A.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. The actually verification will be done in 2016.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GAM | PHA | 71 | TAS | 28 | A | I |  | 0.1 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 23000 | 0 | 23000 | 0 | 0% | 23000 | 0 | 23000 | 2990 | 0 | 0 | 2990 | 0 | Brief progress report (actual/planned): Plan of action for HPMP tranche was agreed between the country and UNEP. SSFAwass drafted, finalised and signed by UNEP and the country. Disbursement of funds being processed . Legal arrangements(actual/planned): SSFA was signed in May 2015. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | NOU registered the 2015 HCFC annual quota and importers. The Assistant Ozone Officer resigned and the country has already recruited a new Assistant Ozone Officer. CAP planning a mission to speedly train the new Assistant Ozone Officer.
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | AFR | GAM | REF | 23 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | AFR | GAM | REF | 29 | TAS | 08 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-10-01 | 2003-10-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for technicians in good refrigeration practices | Individual | AFR | GAM | REF | 29 | TRA | 09 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-10-01 | 2003-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | GAM | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-06-01 |  | 1995-10-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | GAM | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-09-01 | 2000-09-01 | 42200 | 0 | 42200 | 42200 | 100% | 0 | 0 |  | 5486 | 0 | 5486 | 0 | 0
FIN | UNEP | Training of customs officers | Individual | AFR | GAM | SEV | 19 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  | 2002-10-01 | 2003-10-01 | 9500 | 0 | 9500 | 9500 | 100% | 0 | 0 |  | 1235 | 0 | 1235 | 0 | 0 |  |  |  | 1997-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | GAM | SEV | 30 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | GAM | SEV | 41 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2006-03-01 | 2007-03-01 | 36573 | 0 | 36573 | 36573 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | GAM | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | -29 | 59971 | 59971 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAM | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAM | SEV | 61 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-10-01 | 2012-06-01 |  | 2012-10-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 8/2012-7/2014) | Individual | AFR | GAM | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-01-01 | 2014-06-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU conducted training for 60 refrigeration technicians and 40 Custom Officers on ODS control. The NOU celebrated the ozone day and conducted awareness programme in seven Radio stations, engaged schools in several competitions and printed 500 T-shirts. The NOU prepared and submitted 2013 ODS data and CP report and participated in all network meetings and OEWG/MOP meetings. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in September 2012. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made in October 2012 as planned_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Implemenntation of project activities completed, SSFA for the newly approved project ) IS Phase VIII) was prepared and sent to country for signature
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2014-6/2016) | Individual | AFR | GAM | SEV | 72 | INS | 29 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-06-01 | 2016-06-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 15000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and signed by the country. Disbursement of funds beeing processed . Legal arrangements(actual/planned): SSFA was signed in May 2015. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on in May 2015 awaiting first disbursement
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GBS | PHA | 50 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GBS | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 | 2013-12-01 | 62500 | -18 | 62482 | 62482 | 100% | 0 | 0 |  | 8125 | -2 | 8123 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GBS | PHA | 57 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2013-12-01 | 2014-12-01 | 85000 | -18021 | 66979 | 66979 | 100% | 0 | 0 |  | 11050 | -2343 | 8707 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GBS | PHA | 60 | TAS | 13 | A | I | CFC-12 | 3.9 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 35000 | 0 | 35000 | 34297 | 97.99% | 703 | 0 |  | 4550 | 0 | 4459 | 91 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GBS | PHA | 71 | TAS | 17 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2016-12-01 | 2016-12-01 |  |  | 52000 | 0 | 52000 | 14757.44 | 28.38% | 37242.56 | 37243 | 37243 | 6760 | 0 | 0 | 6760 | 0 | Brief progress report (actual/planned):Country has organized two workshop training for 20 refrigeration technicians each, in Bafata and Gabou, in March 2014 and a training workshop for 20 customs officers in May 2014 in Bissau. Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ .__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Organnisation in March 2015 of a refrigeration workshop for 30 technicians on recovery and HCFCs alternative. Planning of a Customs training workshop in bafata and Gabu in September 2015.
FIN | UNEP | Implementation of the RMP: monitoring of the activities in the RMP | Individual | AFR | GBS | REF | 43 | TAS | 05 | A | I | CFC | 1 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2007-07-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training for customs officials, police, coast guards, border guards and commercial inspectors | Individual | AFR | GBS | REF | 43 | TRA | 06 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-12-01 | 70000 | -1956 | 68044 | 68044 | 100% | 0 | 0 |  | 9100 | -254 | 8846 | 0 | 0
FIN | UNEP | Implementation of the RMP: training for refrigeration technicians | Individual | AFR | GBS | REF | 43 | TRA | 08 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 70000 | -626 | 69374 | 69374 | 100% | 0 | 0 |  | 9100 | -81 | 9019 | 0 | 0
FIN | UNEP | Establishment of ozone unit | Individual | AFR | GBS | SEV | 39 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2010-01-01 | 2004-04-01 |  | 2004-07-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Formulation of the country programme/RMP | RMP | AFR | GBS | SEV | 39 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-07-01 | 2011-03-01 | 60000 | -14454 | 45546 | 45546 | 100% | 0 | 0 |  | 7800 | -1879.02 | 5921 | -0.02 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening project) | Individual | AFR | GBS | SEV | 43 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | GBS | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2011-11-01 | 2012-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase III: 7/2102-6/2014) | Individual | AFR | GBS | SEV | 67 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013 .2014 Ozone day was celebrated. SSFA expired in Aug. 2014. Has $27,000 balance L egal arrangements (actual/planned): Agreement signed in September 2012. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in September 2012 __ All funds disbursed (yes/no): _ Final payment planned in July 2014_ Any delay? (yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: Slowness in reporting__ If Yes, will delay have impact on project completion date (yes/no): _ more assistance__ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Collection of the 2014 data on ODS imports. Organization of One meeting of the steering committee. Coordination of the HPMP refrigeration workshop organized in Bissau in March 2015.
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 12/2014-11/2016) | Individual | AFR | GBS | SEV | 73 | INS | 18 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on 28 February 2015
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODS | Individual | EUR | GEO | REF | 23 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-01-01 | 1998-02-01 |  | 2005-06-01 | 2006-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in the refrigeration servicing sector | Individual | EUR | GEO | REF | 23 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-11-01 | 1998-11-01 |  | 2001-11-01 | 2006-12-01 | 50000 | -9800 | 40200 | 40200 | 100% | 0 | 0 |  | 6500 | -1274 | 5226 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme in the refrigeration sector (phase III) | Individual | EUR | GEO | REF | 35 | TRA | 12 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2003-01-01 |  | 2005-11-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | EUR | GEO | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1997-11-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | GEO | SEV | 23 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 2000-12-01 |  | 2001-05-01 | 2001-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | GEO | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-08-01 | 2003-01-01 |  | 2003-02-01 | 2003-12-01 | 46700 | 0 | 46700 | 46700 | 100% | 0 | 0 |  | 6071 | 0 | 6071 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | EUR | GEO | SEV | 39 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2004-12-01 | 2008-12-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: phase IV | Individual | EUR | GEO | SEV | 45 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
TRF | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 51 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2009-03-01 |  |  | 2007-12-01 | 60667 | -60667 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Transferred to UNDP. | Transferred to UNDP.
FIN | UNEP | Implementation of train the trainer programme and national demonstration programme | Individual | AFR | GHA | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 1995-12-01 | 1999-04-01 | 99000 | 0 | 99000 | 99000 | 100% | 0 | 0 |  | 12870 | 0 | 12870 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | GHA | REF | 32 | TRA | 13 | A | I | CFC | 6.3 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2003-01-01 | 2007-04-01 | 81000 | -18194 | 62806 | 62806 | 100% | 0 | 0 |  | 10530 | -2365.22 | 8165 | -0.22 | 0 |  |  |  | 2003-06-01
FIN | UNEP | Country programme preparation | Individual | AFR | GHA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Preparation of training material for aerosol sector | Individual | GLO | GLO | ARS | 09 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Aerosol training workshop | Individual | GLO | GLO | ARS | 09 | TRA | 34 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Produce sector-specific video for aerosol sector | Individual | GLO | GLO | ARS | 19 | TAS | 91 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1996-12-01 |  | 1999-12-01 | 2000-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Development of guidelines to promote safety an aerosol conversions | Individual | GLO | GLO | ARS | 39 | TAS | 246 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2003-12-01 |  | 2010-04-01 | 2011-04-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0
FIN | UNEP | MDI regional workshops/CAP | Individual | GLO | GLO | ARS | 52 | TAS | 282 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2008-07-01 |  | 2009-12-01 | 2012-06-01 | 200000 | -49311 | 150689 | 150689 | 100% | 0 | 0 |  | 16000 | -3944.88 | 12055 | 0.12 | 0
FIN | UNEP | Produce a video on methyl bromide alternatives | Individual | GLO | GLO | FUM | 19 | TAS | 93 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-03-01 | 2000-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Develop a technical brochure on methyl bromide | Individual | GLO | GLO | FUM | 19 | TRA | 94 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Technical sourcebook of methyl bromide alternatives | Individual | GLO | GLO | FUM | 23 | TAS | 150 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-12-01 | 2002-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Handbook for NOUs reducing reliance on methyl bromide | Individual | GLO | GLO | FUM | 23 | TAS | 151 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1998-11-01 |  | 1999-02-01 | 1999-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Compilation of legislations for regulatory authorities from Article 5 countries that discourage methyl bromide use and promote alternatives | Individual | GLO | GLO | FUM | 24 | TAS | 155 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Technical and institutional resources for methyl bromide alternatives projects | Individual | GLO | GLO | FUM | 24 | TAS | 156 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-10-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Methyl bromide information kit | Individual | GLO | GLO | FUM | 24 | TAS | 157 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 1998-12-01 | 1999-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Compilation of case studies on commercial, low-impact methyl bromide alternatives successfully implemented | Individual | GLO | GLO | FUM | 24 | TAS | 160 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Development of training manuals for extension workers | Individual | GLO | GLO | FUM | 27 | TRA | 178 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-02-01 | 50000 | -4000 | 46000 | 46000 | 100% | 0 | 0 |  | 6500 | -520 | 5980 | 0 | 0
FIN | UNEP | National farmer's training and establishment of Farmer's Field School (FFS) | Individual | GLO | GLO | FUM | 27 | TRA | 179 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-04-01 |  | 2001-12-01 | 2003-12-01 | 60000 | -4000 | 56000 | 56000 | 100% | 0 | 0 |  | 7800 | -520 | 7280 | 0 | 0
FIN | UNEP | Preparation of how-to crop manual on adopting methyl bromide alternatives for cut flowers | Individual | GLO | GLO | FUM | 29 | TAS | 187 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2000-11-01 |  | 2001-12-01 | 2002-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Policy development assistance to prevent future methyl bromide growth in low methyl bromide-consuming countries | Individual | GLO | GLO | FUM | 30 | TAS | 211 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2001-05-01 | 2002-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0
FIN | UNEP | International halon bank clearing-house function | Individual | GLO | GLO | HAL | 09 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-05-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Halon bank management information collection and dissemination (1994) | Individual | GLO | GLO | HAL | 12 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Halon bank management case study logbook | Individual | GLO | GLO | HAL | 12 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1998-07-01 | 1995-03-01 |  | 2001-10-01 | 2001-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Translate the halon management: banking for the future information kit | Individual | GLO | GLO | HAL | 12 | TAS | 57 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1996-03-01 | 1999-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Halon bank management query response, information collection and dissemination (1995) | Individual | GLO | GLO | HAL | 16 | TAS | 81 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-07-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Meeting of halon bank managers | Individual | GLO | GLO | HAL | 16 | TAS | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Development of a "self-help" guide for small halon-consuming countries | Individual | GLO | GLO | HAL | 16 | TAS | 85 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-08-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Dissemination of the existing halon banking awareness flyer | Individual | GLO | GLO | HAL | 16 | TAS | 86 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-09-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Provide halon bank management query response, information collection and dissemination | Individual | GLO | GLO | HAL | 19 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 |  | 3770 | 0 | 3770 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services | Individual | GLO | GLO | HAL | 21 | TAS | 115 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (1998) | Individual | GLO | GLO | HAL | 23 | TAS | 145 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 |  | 11570 | 0 | 11570 | 0 | 0
FIN | UNEP | Development of a handbook on standards and codes of good practice for halon sector | Individual | GLO | GLO | HAL | 27 | TAS | 181 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-09-01 | 2002-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Study on challenges associated with halon banking in developing countries | Individual | GLO | GLO | HAL | 52 | TAS | 281 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2013-07-01 | 2014-12-01 | 40000 | -4000 | 36000 | 36000 | 100% | 0 | 0 |  | 5200 | -520 | 4680 | 0 | 0
CLO | UNEP | Advance for preparation of HPMPs | RMP | GLO | GLO | PHA | 54 | PRP | 290 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-12-01 | 408000 | -408000 | 0 | 0 |  | 0 | 0 | 0 | 53040 | -53040 | 0 | 0 | 0
FIN | UNEP | Preparation of training material for refrigeration sector | Individual | GLO | GLO | REF | 09 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 |  | 20800 | 0 | 20800 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 10 | TRA | 45 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Compilation of recommendations for a Code of Good Practices in refrigeration in Article 5 countries | Individual | GLO | GLO | REF | 16 | TAS | 87 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1995-09-01 |  | 1998-07-01 | 1999-04-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0
FIN | UNEP | Translation of "Training Manual on Good Practices in Refrigeration" and "Training Manual on Chillers and Refrigerant Management" into Chinese, French and Spanish | Individual | GLO | GLO | REF | 16 | TRA | 73 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1995-09-01 |  | 1997-12-01 | 1999-04-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0
FIN | UNEP | Guidelines for the establishment of recovery and recycling systems and related legislation for low volume ODS consuming countries | Individual | GLO | GLO | REF | 19 | TAS | 96 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2000-06-01 | 2000-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Training modules for national training courses on good practices in refrigeration | Individual | GLO | GLO | REF | 19 | TRA | 97 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Prepare guidance to assist hotel industry in LVCs to avoid, replace, or eliminate ODS | Individual | GLO | GLO | REF | 19 | TRA | 98 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1996-12-01 |  | 1998-04-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Study on drop-in substitutes for domestic refrigeration | Individual | GLO | GLO | REF | 21 | TAS | 116 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1999-08-01 | 2000-06-01 | 80000 | -21000 | 59000 | 59000 | 100% | 0 | 0 |  | 10400 | -2730 | 7670 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 264 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2007-02-01 | 2011-03-01 | 40000 | -8548 | 31452 | 31452 | 100% | 0 | 0 |  | 5200 | -1111 | 4089 | 0 | 0
COM | UNEP | Global technical assistance programme in the chiller sector | Individual | GLO | GLO | REF | 48 | TAS | 275 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2010-09-01 | 2009-04-01 |  | 2013-07-01 |  | 200000 | -103040 | 96960 | 88587.86 | 91.37% | 8372.14 | 0 | 8372 | 26000 | -13395 | 12605 | 0 | 0
FIN | UNEP | Information exchange and technology transfer (1991-1992) | Individual | GLO | GLO | SEV | 04 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-12-01 |  | 1993-06-01 | 1993-12-01 | 526000 | 0 | 526000 | 526000 | 100% | 0 | 0 |  | 68380 | 0 | 68380 | 0 | 0
FIN | UNEP | Advisory group meeting (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-03-01 | 1992-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Regional workshop for Arabic speaking countries | Individual | GLO | GLO | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-12-01 |  | 1991-12-01 | 1992-12-01 | 246000 | -104000 | 142000 | 142000 | 100% | 0 | 0 |  | 31980 | -13520 | 18460 | 0 | 0
FIN | UNEP | OzonAction Information Clearing-house (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 430000 | 0 | 430000 | 430000 | 100% | 0 | 0 |  | 55900 | 0 | 55900 | 0 | 0
FIN | UNEP | Preparation of technical documents and newsletter | Individual | GLO | GLO | SEV | 06 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 320000 | 0 | 320000 | 320000 | 100% | 0 | 0 |  | 41600 | 0 | 41600 | 0 | 0
FIN | UNEP | Advisory group meeting (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-02-01 |  | 1993-03-01 | 1993-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Travel (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Support to training activities by UNEP | Individual | GLO | GLO | SEV | 06 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1994-03-01 | 1994-12-01 | 365000 | 0 | 365000 | 365000 | 100% | 0 | 0 |  | 47450 | 0 | 47450 | 0 | 0
FIN | UNEP | Support to networking activities | Individual | GLO | GLO | SEV | 09 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1993-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Travel (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Advisory group meeting (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | Information Exchange Clearing-house System (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-06-01 | 1996-07-01 | 705000 | 0 | 705000 | 705000 | 100% | 0 | 0 |  | 91650 | 0 | 91650 | 0 | 0
FIN | UNEP | Support to other national training activities | Individual | GLO | GLO | SEV | 09 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Development of a training strategy | Individual | GLO | GLO | SEV | 09 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Updating OAIC diskette and on-line system (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Outreach at conferences and workshops (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Information dissemination (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 49 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 380000 | 0 | 380000 | 380000 | 100% | 0 | 0 |  | 49400 | 0 | 49400 | 0 | 0
FIN | UNEP | Sectoral data collection (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1997-03-01 | 1999-02-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 |  | 27950 | 0 | 27950 | 0 | 0
FIN | UNEP | Quality review technology catalogs | Individual | GLO | GLO | SEV | 12 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-04-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Information papers and fact sheets for evaluation of technical options to replace ODS | Individual | GLO | GLO | SEV | 12 | TAS | 53 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1999-12-01 | 2000-01-01 | 60000 | -3500 | 56500 | 56500 | 100% | 0 | 0 |  | 7800 | -455 | 7345 | 0 | 0 |  |  |  | 1998-12-01
FIN | UNEP | Translation of the "Protecting the Ozone Layer" sectoral technical brochures | Individual | GLO | GLO | SEV | 12 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-09-01 | 1999-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Informal Advisory Group meeting (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 58 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Ad hoc Group meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Meeting of the consultants (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 60 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1995-07-01 | 1995-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Travel (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Query-response service (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 67 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | OzonAction newsletter and special supplements (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 68 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0
FIN | UNEP | Support to national training activities (1994) | Individual | GLO | GLO | SEV | 13 | TRA | 70 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1996-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Update the OAIC diskette version (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Information papers and fact sheets to assist evaluation of technical options to replace ODS (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Develop sector specific videos | Individual | GLO | GLO | SEV | 16 | TAS | 75 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-05-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Update Technology Sourcebooks and quality review updated material | Individual | GLO | GLO | SEV | 16 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2002-04-01
FIN | UNEP | Disseminate information (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 77 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 |  | 31850 | 0 | 31850 | 0 | 0
FIN | UNEP | Provide direct query-response service (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 79 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Collect sectoral data from worldwide sources (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 82 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-08-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 |  | 23400 | 0 | 23400 | 0 | 0
FIN | UNEP | Informal advisory group meeting (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 83 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Ad hoc group meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 88 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1997-06-01 | 1999-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Travel (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 89 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-09-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Collect sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 19 | TAS | 100 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-12-01 | 1999-01-01 | 104500 | 0 | 104500 | 104500 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0
FIN | UNEP | Provide direct query-response service (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 101 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0
FIN | UNEP | Support to national activities (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 102 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-05-01 | 1999-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Ad hoc Group meetings | Individual | GLO | GLO | SEV | 19 | TAS | 103 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Deliver OAIC-DV and other OzonAction Programme information through World Wide Web home page site on a one year trial basis | Individual | GLO | GLO | SEV | 19 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 |  | 1885 | 0 | 1885 | 0 | 0
FIN | UNEP | Continue to maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 19 | TAS | 105 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Prepare an inventory and assessment of environmentally sound and economically viable technologies and know-how conducive to phase out of ODS | Individual | GLO | GLO | SEV | 19 | TAS | 106 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 2000-12-01 | 1996-08-01 |  | 2004-04-01 | 2005-12-01 | 50000 | -27500 | 22500 | 22500 | 100% | 0 | 0 |  | 6500 | -3575 | 2925 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Travel (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 107 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 19 | TAS | 108 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 |  | 31850 | 0 | 31850 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 110 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0
CLO | UNEP | Training modules on management of ODS phase out in SMEs | Individual | GLO | GLO | SEV | 19 | TAS | 112 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  |  | 2006-12-01 | 40000 | -19000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 5200 | -2470 | 2730 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 19 | TAS | 99 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-04-01 | 1999-01-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0
FIN | UNEP | Prepare information papers and case studies | Individual | GLO | GLO | SEV | 19 | TRA | 109 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 2001-09-01 | 2001-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 | 0 |  | 5980 | 0 | 5980 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Produce handbook on technology options especially for SMEs | Individual | GLO | GLO | SEV | 19 | TRA | 111 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-11-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Disseminate information | Individual | GLO | GLO | SEV | 19 | TRA | 113 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-05-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 |  | 35100 | 0 | 35100 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Training modules on policy design and setting up of legislation | Individual | GLO | GLO | SEV | 19 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 21 | TAS | 118 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Provide direct query-response service (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 21 | TAS | 120 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-02-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 21 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-01-01 |  | 1997-12-01 | 1999-01-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 |  | 43550 | 0 | 43550 | 0 | 0
FIN | UNEP | Advisory and expert group meetings | Individual | GLO | GLO | SEV | 21 | TAS | 122 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 123 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Travel (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 124 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Update the OAIC diskette version including "Simple Search" versions of prioritized OzonAction publications | Individual | GLO | GLO | SEV | 21 | TAS | 125 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-10-01 | 2000-06-01 | 63000 | -15400 | 47600 | 47600 | 100% | 0 | 0 |  | 8190 | -2002 | 6188 | 0 | 0
FIN | UNEP | Deliver OzonAction newsletter and other information through the World Wide Web home page | Individual | GLO | GLO | SEV | 21 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Update existing technical brochure series to include 1994/95 TOC data | Individual | GLO | GLO | SEV | 21 | TAS | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 2001-01-01 | 2002-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Develop awareness materials for 1999 freeze to support national initiatives on awareness raising | Individual | GLO | GLO | SEV | 21 | TAS | 128 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Translate prioritized OzonAction Programme documents into French and Spanish | Individual | GLO | GLO | SEV | 21 | TAS | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-12-01 |  | 1998-12-01 | 1999-08-01 | 40000 | -1191 | 38809 | 38809 | 100% | 0 | 0 |  | 5200 | -155 | 5045 | 0 | 0
FIN | UNEP | Develop a handbook on the practical use of policy instruments | Individual | GLO | GLO | SEV | 21 | TAS | 130 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-11-01 | 1997-12-01 |  | 2003-06-01 | 2005-12-01 | 50000 | -10000 | 40000 | 40000 | 100% | 0 | 0 |  | 6500 | -1300 | 5200 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 21 | TAS | 131 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Preparation of refrigerant management plans/country programmes for VLVC/LVC | Individual | GLO | GLO | SEV | 22 | CPG | 132 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1997-12-01 |  | 2002-03-01 | 2007-01-01 | 200000 | -73040 | 126960 | 126960 | 100% | 0 | 0 |  | 26000 | -9495 | 16505 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 23 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-08-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 23 | TAS | 139 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 |  | 14560 | 0 | 14560 | 0 | 0
FIN | UNEP | Update the OAIC diskette version (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 140 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 23 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Provide direct query-response service (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 142 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through World Wide Web home page site | Individual | GLO | GLO | SEV | 23 | TAS | 143 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Advisory and expert group meetings (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 144 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -10000 | 65000 | 65000 | 100% | 0 | 0 |  | 9750 | -1300 | 8450 | 0 | 0
FIN | UNEP | Travel (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 146 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -2950 | 72050 | 72050 | 100% | 0 | 0 |  | 9750 | -383 | 9367 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 23 | TAS | 147 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-07-01 | 347000 | -1750 | 345250 | 345250 | 100% | 0 | 0 |  | 45110 | -228 | 44882 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 152 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Translate and print three guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 23 | TAS | 153 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 2002-12-01 | 2003-08-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0
FIN | UNEP | Support to national activities (1998) | Individual | GLO | GLO | SEV | 23 | TRA | 148 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-10-01 |  | 1998-10-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Data reporting handbook to provide information to Article 5 countries and assist them with their data reporting | Individual | GLO | GLO | SEV | 24 | TAS | 158 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-01-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through world wide web home page site (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 162 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 163 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 |  | 14560 | 0 | 14560 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 164 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 |  | 11570 | 0 | 11570 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 165 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 26 | TAS | 166 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 26 | TAS | 167 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Provide direct query-response service (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 168 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Advisory and expert group meetings (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 169 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 75000 | -3500 | 71500 | 71500 | 100% | 0 | 0 |  | 9750 | -455 | 9295 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 170 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 55000 | -6300 | 48700 | 48700 | 100% | 0 | 0 |  | 7150 | -819 | 6331 | 0 | 0
FIN | UNEP | Travel (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 171 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Support to national activities for 1999 | Individual | GLO | GLO | SEV | 26 | TAS | 173 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 26 | TAS | 174 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 347000 | 0 | 347000 | 347000 | 100% | 0 | 0 |  | 45110 | 0 | 45110 | 0 | 0
FIN | UNEP | Develop fact sheet describing win-win technology options relative to Kyoto and Montreal Protocols | Individual | GLO | GLO | SEV | 27 | TAS | 182 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2000-04-01 |  | 2002-12-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Update regulations to control ozone depleting substances | Individual | GLO | GLO | SEV | 27 | TAS | 183 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2001-09-01 | 2001-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Update the OAIC CD-Rom | Individual | GLO | GLO | SEV | 29 | TAS | 186 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-01-01 | 2002-01-01 | 69300 | 0 | 69300 | 69300 | 100% | 0 | 0 |  | 9009 | 0 | 9009 | 0 | 0
FIN | UNEP | Support to national activities (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 188 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 192 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 29 | TAS | 193 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 117600 | 0 | 117600 | 117600 | 100% | 0 | 0 |  | 15288 | 0 | 15288 | 0 | 0
FIN | UNEP | Travel (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 194 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 195 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 357000 | 0 | 357000 | 357000 | 100% | 0 | 0 |  | 46410 | 0 | 46410 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 196 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 93450 | 0 | 93450 | 93450 | 100% | 0 | 0 |  | 12149 | 0 | 12149 | 0 | 0
FIN | UNEP | Provide direct query-response service (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 197 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 84000 | 0 | 84000 | 84000 | 100% | 0 | 0 |  | 10920 | 0 | 10920 | 0 | 0
FIN | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 29 | TAS | 198 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2005-04-01 | 2007-07-01 | 120000 | -22000 | 98000 | 98000 | 100% | 0 | 0 |  | 15600 | -2860 | 12740 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Advisory and expert group meetings (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 199 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 200 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2002-03-01 | 364000 | 0 | 364000 | 364000 | 100% | 0 | 0 |  | 47320 | 0 | 47320 | 0 | 0
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 201 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through worldwide web home page site (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 202 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 26250 | 0 | 26250 | 26250 | 100% | 0 | 0 |  | 3413 | 0 | 3413 | 0 | 0
FIN | UNEP | Organizing a global video competition on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 206 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2000-09-01 |  | 2002-11-01 | 2006-01-01 | 60000 | -42676 | 17324 | 17324 | 100% | 0 | 0 |  | 7800 | -5547.92 | 2252.08 | 0 | 0 |  |  |  | 2001-10-01
FIN | UNEP | Translation and printing of OzonAction documents into French, Spanish and Arabic | Individual | GLO | GLO | SEV | 30 | TAS | 207 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-05-01 | 2001-03-01 |  | 2001-12-01 | 2002-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Adapting existing audiovisual materials to promote control of illegal trade in ODS | Individual | GLO | GLO | SEV | 30 | TAS | 208 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2003-06-01 | 2003-10-01 | 50000 | -2353 | 47647 | 47647 | 100% | 0 | 0 |  | 6500 | -306 | 6194 | 0 | 0
FIN | UNEP | New awareness raising activities and materials for dissemination to the general public | Individual | GLO | GLO | SEV | 30 | TAS | 209 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-02-01 |  | 2001-12-01 | 2002-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Develop materials to educate children on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 210 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2004-07-01 | 2006-02-01 | 100000 | -10448 | 89552 | 89552 | 100% | 0 | 0 |  | 13000 | -1359 | 11641 | 0 | 0 |  |  |  | 2003-07-01
FIN | UNEP | Provide international halon bank management information clearinghouse services in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 214 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 9880 | 0 | 9880 | 0 | 0
FIN | UNEP | Travel for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 215 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Provide direct query-response service in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 217 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 |  | 11180 | 0 | 11180 | 0 | 0
FIN | UNEP | Disseminate awareness material, technical, and policy information in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 219 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 346000 | -13916 | 332084 | 332084 | 100% | 0 | 0 |  | 44980 | -1809 | 43171 | 0 | 0
FIN | UNEP | Deliver OzonAction Newsletter and other information through world wide web home page site in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 220 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 221 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 280000 | -5051 | 274949 | 274949 | 100% | 0 | 0 |  | 36400 | -657 | 35743 | 0 | 0
FIN | UNEP | Advisory and expert group meetings for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 223 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 75000 | -7392 | 67608 | 67608 | 100% | 0 | 0 |  | 9750 | -960.96 | 8789 | 0.04 | 0
FIN | UNEP | Regional awareness raising and South-South assistance | Individual | GLO | GLO | SEV | 32 | TAS | 224 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2001-12-01 |  | 2004-12-01 | 2006-01-01 | 191000 | -26212 | 164788 | 164788 | 100% | 0 | 0 |  | 24830 | -3408 | 21422 | 0 | 0 |  |  |  | 2003-07-01
FIN | UNEP | Maintain contact database of experts and mailing list for OzonAction programme publications in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 225 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 226 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 55000 | -5 | 54995 | 54995 | 100% | 0 | 0 |  | 7150 | -1 | 7149 | 0 | 0
FIN | UNEP | Prioritized sectoral data from worldwide sources in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 228 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 121000 | 0 | 121000 | 121000 | 100% | 0 | 0 |  | 15730 | 0 | 15730 | 0 | 0
FIN | UNEP | Global enabling activity for customs training | Individual | GLO | GLO | SEV | 32 | TRA | 218 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2002-03-01 | 2003-06-01 | 165400 | -13971 | 151429 | 151429 | 100% | 0 | 0 |  | 21502 | -1816 | 19686 | 0 | 0
FIN | UNEP | Support to national activities for 2001 | Individual | GLO | GLO | SEV | 32 | TRA | 222 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a booklet on data reporting for methyl bromide | Individual | GLO | GLO | SEV | 33 | TAS | 229 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2001-12-01 |  | 2001-11-01 | 2003-06-01 | 42500 | -2002 | 40498 | 40498 | 100% | 0 | 0 |  | 5525 | -260 | 5265 | 0 | 0
FIN | UNEP | Study on development of ODS phase-out strategy for SMEs | Individual | GLO | GLO | SEV | 34 | TAS | 230 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-09-01 | 2002-12-01 |  | 2005-12-01 | 2009-09-01 | 100000 | -10000 | 90000 | 90000 | 100% | 0 | 0 |  | 13000 | -1300 | 11700 | 0 | 0
FIN | UNEP | Global public awareness and education campaign to sustain the phase out (first tranche) | Individual | GLO | GLO | SEV | 34 | TAS | 231 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-01-01 | 2003-01-01 | 60000 | -11755 | 48245 | 48245 | 100% | 0 | 0 |  | 7800 | -1528 | 6272 | 0 | 0
CLO | UNEP | Development of tracking system for ODS and ODS-based equipment | Individual | GLO | GLO | SEV | 34 | TAS | 232 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2002-12-01 |  |  | 2005-03-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2002 budget | Individual | GLO | GLO | SEV | 35 | TAS | 237 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2002-12-01 |  | 2002-12-01 | 2005-01-01 | 5351450 | -1500591.3 | 3850858.7 | 3850859 | 100% | -0.3 | 0 |  | 428116 | -120047 | 308069 | 0 | 0
FIN | UNEP | Translation of OzonAction publications into other UN languages | Individual | GLO | GLO | SEV | 36 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2002-11-01 |  | 2006-11-01 | 2007-12-01 | 93000 | -34067 | 58933 | 58933 | 100% | 0 | 0 |  | 12090 | -4429 | 7661 | 0 | 0 |  |  |  | 2004-07-01
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 37 | TAS | 241 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2005-12-01 | 2006-01-01 | 200000 | -33111 | 166889 | 166889 | 100% | 0 | 0 |  | 26000 | -4304 | 21696 | 0 | 0 |  |  |  | 2004-12-01
FIN | UNEP | Compliance Assistance Programme: 2003 budget | Individual | GLO | GLO | SEV | 38 | TAS | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-07-01 | 5830885 | -466383 | 5364502 | 5364502 | 100% | 0 | 0 |  | 466471 | -37311 | 429160 | 0 | 0
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 39 | TAS | 247 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-02-01 | 2004-04-01 |  | 2006-04-01 | 2007-12-01 | 200000 | -77956 | 122044 | 122044 | 100% | 0 | 0 |  | 26000 | -10134 | 15866 | 0 | 0
FIN | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | Individual | GLO | GLO | SEV | 39 | TAS | 248 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-03-01 |  | 2008-05-01 | 2009-05-01 | 75000 | -8215 | 66785 | 66785 | 100% | 0 | 0 |  | 9750 | -1067.95 | 8682 | 0.05 | 0 |  |  |  | 2005-09-01
FIN | UNEP | Compliance Assistance Programme: 2004 budget | Individual | GLO | GLO | SEV | 41 | TAS | 252 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 6757900 | -190217 | 6567683 | 6567683 | 100% | 0 | 0 |  | 540632 | -15218 | 525414 | 0 | 0
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 42 | TAS | 255 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-04-01 | 2009-12-01 | 200000 | -32056 | 167944 | 167944 | 100% | 0 | 0 |  | 26000 | -4167 | 21833 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2005 budget | Individual | GLO | GLO | SEV | 44 | TAS | 260 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-12-01 | 7157544 | -304536 | 6853008 | 6853008 | 100% | 0 | 0 |  | 572604 | -24363 | 548241 | 0 | 0
FIN | UNEP | Assistance for regional awareness raising (2005) | Individual | GLO | GLO | SEV | 45 | TAS | 262 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2008-12-01 | 2012-11-01 | 200000 | -60190 | 139810 | 139810 | 100% | 0 | 0 |  | 26000 | -7825 | 18175 | 0 | 0
FIN | UNEP | Development of effective awareness materials | Individual | GLO | GLO | SEV | 45 | TAS | 263 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-01-01 | 2007-12-01 | 120000 | -13267 | 106733 | 106733 | 100% | 0 | 0 |  | 15600 | -1725 | 13875 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2006 budget | Individual | GLO | GLO | SEV | 47 | TAS | 270 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-04-01 | 7770000 | -364599 | 7405401 | 7405401 | 100% | 0 | 0 |  | 621600 | -29167 | 592433 | 0 | 0
FIN | UNEP | Updating the customs training manual | Individual | GLO | GLO | SEV | 48 | TRA | 274 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-08-01 | 2009-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2007 budget | Individual | GLO | GLO | SEV | 50 | TAS | 276 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2007-12-01 |  | 2007-12-01 | 2009-12-01 | 8003000 | -409308 | 7593692 | 7593692 | 100% | 0 | 0 |  | 640240 | -32745 | 607495 | 0 | 0
FIN | UNEP | Integrated enforcement training under the Montreal Protocol through green customs initiative | Individual | GLO | GLO | SEV | 52 | TAS | 283 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-09-01 | 2010-06-01 |  | 2010-12-01 | 2012-07-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2008 budget | Individual | GLO | GLO | SEV | 53 | TAS | 284 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 8243090 | 0 | 8243090 | 8243090 | 100% | 0 | 0 |  | 659447 | 0 | 659447 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2009 budget | Individual | GLO | GLO | SEV | 56 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 8490000 | -3520.35 | 8486479.65 | 8486480 | 100% | -0.35 | 0 |  | 679200 | -282 | 678918 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2010 budget | Individual | GLO | GLO | SEV | 59 | TAS | 299 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-01-01 | 2010-12-01 |  | 2010-12-01 | 2013-12-01 | 8745000 | -169753 | 8575247 | 8575247 | 100% | 0 | 0 |  | 699600 | -13580 | 686020 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2011 budget | Individual | GLO | GLO | SEV | 62 | TAS | 302 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2011-12-01 |  | 2011-12-01 | 2013-12-01 | 9007000 | -585999 | 8421001 | 8421001 | 100% | 0 | 0 |  | 720560 | -46880 | 673680 | 0 | 0
ONG | UNEP | Resource mobilization to address climate co-benefits for HCFC phase-out in low-volume-consuming countries with servicing sector only, in cooperation with other agencies | Individual | GLO | GLO | SEV | 63 | TAS | 308 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-04-01 | 2013-03-01 | 2015-12-01 |  |  | 100000 | 0 | 100000 | 77567.5 | 77.57% | 22432.5 | 400 | 22433 | 13000 | 0 | 7445 | 5555 | 52 |  |  |  | 2014-12-01
COM | UNEP | Compliance Assistance Programme: 2012 budget | Individual | GLO | GLO | SEV | 65 | TAS | 313 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 |  | 8987000 | -400388 | 8586612 | 8514497.38 | 99.16% | 72114.62 | -7.9581e-13 | 72115 | 718960 | -35648 | 651982 | 31330 | -6.1046e-14
FIN | UNEP | Development of a guide for sustainable refrigerated facilities and systems, in cooperation with the American Society of Heating, Refrigeration and Air Conditioning Engineers (ASHRAE) | Individual | GLO | GLO | SEV | 66 | TAS | 314 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 |  | 2014-12-01 | 2014-12-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0
COM | UNEP | Compliance Assistance Programme: 2013 budget | Individual | GLO | GLO | SEV | 68 | TAS | 315 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-01-01 | 2013-12-01 |  | 2013-12-01 |  | 9158000 | -915833 | 8242167 | 8127736.46 | 98.61% | 114430.54 | 0 | 0 | 732640 | -73267 | 614570 | 44803 | 0
ONG | UNEP | Compliance Assistance Programme: 2014 budget | Individual | GLO | GLO | SEV | 71 | TAS | 321 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-01-01 | 2014-12-01 | 2015-12-01 |  |  | 9338000 | 0 | 9338000 | 7818628 | 83.73% | 1519372 | 0 | 0 | 747040 | 0 | 0 | 747040 | 0
ONG | UNEP | Compliance Assistance Programme: 2015 budget | Individual | GLO | GLO | SEV | 73 | TAS | 323 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-12-01 | 2015-12-31 |  |  | 9459000 |  | 9459000 | 2143249.06 | 22.66% | 7315750.94 | 836927.76 | 836928 | 756720 | 0 | 0 | 756720 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | LAC | GRN | PHA | 49 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 37000 | 0 | 37000 | 37000 | 100% | 0 | 0 |  | 4810 | 0 | 4810 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GRN | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 |  | 2013-06-01 | 2013-06-01 | 85000 | -2650 | 82350 | 82350 | 100% | 0 | 0 |  | 11050 | -344 | 10706 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | GRN | PHA | 55 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 |  | 2013-12-01 | 2013-12-01 | 32500 | -8528 | 23972 | 23972 | 100% | 0 | 0 |  | 4225 | -1109 | 3116 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GRN | PHA | 62 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 | 2016-06-30 |  |  | 105000 | 0 | 105000 | 52032.07 | 49.55% | 52967.93 | 0 | 5000 | 13650 | 0 | 6207 | 7443 | 4589 | Brief progress report (actual/planned): HCFC electronic licensing system and quota system in place. Quotas for 2014 assigned in Nov-13. Mandatory reporting of HCFC and HCFC-based equipment importers in compliance during 2014. Fiscal policy already in place to included tax exemptions for EE appliances. Certification systems for technicians completed: level I and level II competency skils approved by the National Training Agency. Development of standards for refrigerants and equipment is ongoing. 30 technicians trained in good refrigeration practices. 20 customs officers trained .___ Legal arrangements (actual/planned): Agreement signed in Aug-13___ First mission (actual/planned): Mission in Nov-13___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Aug-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes ___ If Yes, reasons for delay & action plan to resolve: agreement expired in Jul-2014. Country undertaking activities with funds available.___ If Yes, will delay have impact on project completion date (yes/no): no ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | As of May2015 activities are taking place with funds available. Discussions to include AC equipment in EE fiscal policy ongoing. Progress and financial reports to be submited by country once funds are exhausted. New agreement/implementation modalities to be discussed with country once UMOJA goes live. |  | INV/18
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | LAC | GRN | REF | 30 | TRA | 03 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2000-10-01 |  | 2007-01-01 | 2008-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2002-06-01
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and Ozone Unit staff | Individual | LAC | GRN | REF | 30 | TRA | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2007-01-01 | 2009-12-01 | 36700 | -13787 | 22913 | 22913 | 100% | 0 | 0 |  | 4771 | -1792 | 2979 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2002-12-01
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | GRN | REF | 46 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-09-01 | 2009-12-01 | 15000 | -337 | 14663 | 14663 | 100% | 0 | 0 |  | 1950 | -44 | 1906 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | GRN | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-08-01 |  | 1999-10-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed. |  | 1999-12-01
FIN | UNEP | Creation of a National Ozone Unit | Individual | LAC | GRN | SEV | 30 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2003-06-01 | 2003-04-01 |  | 2006-08-01 | 2014-12-31 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening project | Individual | LAC | GRN | SEV | 44 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | GRN | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-11-01 |  | 2010-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GRN | SEV | 60 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 |  | 2013-12-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | LAC | GRN | SEV | 67 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-08-01 | 2014-07-01 | 2015-12-31 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 0 | 30405 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): . Customs brokers training as part of ozone day celebrations. Country reported CP Data and Article 7 data on time. NOU participated in Caribbean Network Meeting in Suriname Mar-14, the Joint Network Meeting of LAC in the Dominican Republic Dec-14. Consistent use of Radio, TV Newspaper and social media to promote Ozone Layer protection. Produced brochures, t-shirts, book marks, factsheets for distribution . NOO attended OEWG and MOP meetings in 2014. NOO is ExCom member. ___ Legal arrangements (actual/planned): Agreement signed in Aug-2013,___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement in Aug-2013 ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Draft progress and financial report sent on Jun-2015. Last disbursement will be processsed once UMOJA is operative. Preparation of terminal report ongoing. Renewal submission planned for 75 ExCom.
FIN | UNEP | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2013-11-01 |  | 2014-12-14 | 2014-12-14 | 70000 | -70000 | 0 | 0 |  | 0 | 0 | 0 | 9100 | -9100 | 0 | 0 | 0 | Brief progress report: No progress. The identification of the partner to implement the technical assistance was not completed. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. A bilateral meeting with the NOO was carried-out at the margin of the LA Network Meeting in June 2013. In December 2013, an official mission to Guatemala was conducted in order to define the disbursement mechanisms to be adopted. However, the government decision was not made. A follow up mission carried out in 2014 but no immediate results achieved. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. Legal arrangements: Not signed/Planned for April 2010. First disbursement date (actual/planned): No disbursement/Planned for May 2010. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: The Government of Guatemala did not opened a special bank account for implementing the Montreal Protocol projects. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Project balance to be returned to Multilateral Funds.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUA | PHA | 50 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2008-11-01 |  | 2012-12-01 | 2013-12-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 |  | 4290 | 0 | 4290 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUA | PHA | 57 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 |  | 2013-12-01 | 2013-12-01 | 75000 | -49373 | 25627 | 25627 | 100% | 0 | 0 |  | 9750 | -6418 | 3332 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | GUA | PHA | 64 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2015-12-01 |  |  | 28250 | 0 | 28250 | 0 | 0% | 28250 | 0 | 28250 | 3673 | 0 | 0 | 3673 | 0 | Brief progress report: No progress. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Since January 2012, the implementation of UNEP projects was stopped because the new Minister of Enironment informed UNEP on a substantive and financial review process of the previous administration work plan and activities. UNEP specifically received a letter asking to cancel all agreements signed by the former administration and indicating that in due course new arrangements would be communicated. After 18 months of no progress in project implementation, a bilateral meeting between RNC of Latin America and the NOO was held at the margin of the Network Meeting carried out in June 2013. However, the meeting did not allow reaching a firm conclusion about how to reassume the HPMP and ISP implementation. In December 2013, an official mission to Guatemala was carried out by UNEP to oversee the situation directly on HCFC quota system approval. In January 2014, a new Minister of Environment was designated in Guatemala. For that reason a second official mission was carried out in July 2014. The RNC met new authorities in the Ministry and did follow up on the conclusions and recommendations of previous country mission carried out in December 2013. The Minister of the Environment suggested to ask to the UNDP Country office to manage the payments of services. A draft Agreement was prepared and submitted to the Division of International Cooperation of the Ministry as instructed by the Minister. However, no answer received from the Government. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Brief progress report: Slow progress. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: In June 2014, a country mission was carried out to held a meeting with the Minister of Environment and the International Cooperation Officer. After that, the Government was focused on the HCFC non-compliance situation. HCFC quotas system has been approved. However, no progress in the funds disbursement level . The Minister of Environment informed that the administration of funds should be carried out through UNEP ROLAC or UNDP Country Office. Due to no definition about who is the responsible person for HPPM implementation, UNEP has not had a valid counterpart to plan and execute activities. Another official mission is planned to second half of 2015. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | GUA | REF | 21 | TRA | 13 | A | I | CFC | 68.3 | 68.3 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2001-12-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | GUA | REF | 27 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2001-12-01
FIN | UNEP | Implementation of the RMP: licensing system | Individual | LAC | GUA | REF | 27 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | GUA | REF | 27 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2000-10-01 |  | 2002-11-01 | 2003-11-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 |  | 4420 | 0 | 4420 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2001-12-01
FIN | UNEP | Implementation of the RMP: establishment of licensing system | Individual | LAC | GUA | REF | 35 | TAS | 23 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23200 | 0 | 23200 | 23200 | 100% | 0 | 0 |  | 3016 | 0 | 3016 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: alternatives to the use of CFC-12 in the refrigeration sector | Individual | LAC | GUA | REF | 35 | TAS | 24 | A | I | CFC | 47.9 | 47.9 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-03-01 | 2009-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | GUA | REF | 35 | TAS | 25 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 31800 | 0 | 31800 | 31800 | 100% | 0 | 0 |  | 4134 | 0 | 4134 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: establishment and enforcement of legislation | Individual | LAC | GUA | REF | 35 | TAS | 26 | A | I | CFC | 51.2 | 51.2 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | LAC | GUA | REF | 35 | TRA | 27 | A | I | CFC | 46.3 | 46.3 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2007-12-01 |  | 2009-03-01 | 2009-03-01 | 56000 | 0 | 56000 | 56000 | 100% | 0 | 0 |  | 7280 | 0 | 7280 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | GUA | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | GUA | SEV | 10 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-12-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 |  | 22360 | 0 | 22360 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | GUA | SEV | 22 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2000-05-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | LAC | GUA | SEV | 28 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-12-01 | 2003-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2002-06-01
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | GUA | SEV | 35 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-09-01 | 2004-01-01 |  | 2004-03-01 | 2007-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | LAC | GUA | SEV | 43 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2010-06-01 | 2010-12-01 | 62400 | 0 | 62400 | 62400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | LAC | GUA | SEV | 53 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2011-12-01 | 124800 | 0 | 124800 | 124800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of the institutional strengthening project (phase VII) | Individual | LAC | GUA | SEV | 61 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-11-01 | 2012-06-01 | 2016-12-30 |  |  | 124800 | 0 | 124800 | 22960 | 18.4% | 101840 | 0 | 45096 | 0 | 0 | 0 | 0 | 0 | Brief progress report: 2014 Intermediate goals achieved as follow: (a) NOO collected ODS data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (b) Article 7 data and CP progress report data submitted in 2014. (c) Due country follow in non-compliance an action plan to return to compliance was submitted to the Meeting of the Parties. (f) HCFC quota system approved and enforced. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Since January 2012, the implementation of UNEP projects was stopped because the new Minister of Enironment informed UNEP on a substantive and financial review process of the previous administration work plan and activities. UNEP specifically received a letter asking to cancel all agreements signed by the former administration and indicating that in due course new arrangements would be communicated. After 18 months of no progress in project implementation, a bilateral meeting between RNC of Latin America and the NOO was held at the margin of the Network Meeting carried out in June 2013. However, the meeting did not allow reaching a firm conclusion about how to reassume the HPMP and ISP implementation. In December 2013, an official mission to Guatemala was carried out by UNEP to oversee the situation directly on HCFC quota system approval. In January 2014, a new Minister of Environment was designated in Guatemala. For that reason a second official mission was carried out in July 2014. The RNC met new authorities in the Ministry and did follow up on the conclusions and recommendations of previous country mission carried out in December 2013. The Minister of the Environment suggested to ask to the UNDP Country office to manage the payments of services. A draft Agreement was prepared and submitted to the Division of International Cooperation of the Ministry as instructed by the Minister. However, no answer received from the Government. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Brief progress report: HCFC quota system is enforced. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Since January 2012, the implementation of UNEP projects was stopped because the new Minister of Enironment informed UNEP on a substantive and financial review process of the previous administration work plan and activities. UNEP specifically received a letter asking to cancel all agreements signed by the former administration and indicating that in due course new arrangements would be communicated. After 18 months of no progress in project implementation, a bilateral meeting between RNC of Latin America and the NOO was held at the margin of the Network Meeting carried out in June 2013. However, the meeting did not allow reaching a firm conclusion about how to reassume the HPMP and ISP implementation. In December 2013, an official mission to Guatemala was carried out by UNEP to oversee the situation directly on HCFC quota system approval. In January 2014, a new Minister of Environment was designated in Guatemala. For that reason a second official mission was carried out in July 2014. The RNC met new authorities in the Ministry and did follow up on the conclusions and recommendations of previous country mission carried out in December 2013. The Minister of the Environment suggested to ask to the UNDP Country office to manage the payments of services. A draft Agreement was prepared and submitted to the Division of International Cooperation of the Ministry as instructed by the Minister. However, no answer received from the Government. An additional country mission is planned for second half of 2015. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GUI | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 |  | 9620 | 0 | 9620 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GUI | PHA | 56 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2011-12-01 | 2012-12-01 | 58000 | -1000 | 57000 | 57000 | 100% | 0 | 0 |  | 7540 | -130 | 7410 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | GUI | PHA | 66 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2015-12-01 |  |  | 85000 | 0 | 85000 | 80019 | 94.14% | 4981 | 0 | 4981 | 11050 | 0 | 10402 | 648 | 0 | Brief progress report (actual/planned): In 2014, country trained 25 refrigeration technicians in Matam in January 2014; 16 refrigeration technicians in Kaloum in February 2014; 27 refrigeration technicians in Dixinn in November 2014; 29 refrigeration technicians trained in Dubreka in December 2014; Also 12 enforcement officers and 8 environmental officers in May 2014 in Conakry___ 2.__ Legal arrangements (actual/planned): Agreement signed in June 2012. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): _ No. SSFA has a balance of US$5,000.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __2014 | Country conducted a survey on import of HCFCs and submitted in january 2015 a verification report on its consumption of 2013. Country organized a big event on identification of HCFCs and HCFCs based equipment in June 2015.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GUI | PHA | 72 | TAS | 29 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-05-01 | 2016-05-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 0 | 7800 | 0 | 0 | 7800 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | There is no activities yet because the release of Funding is pending on the verification report which is not yet submitted.
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | GUI | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 2000-01-01 | 2001-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | GUI | REF | 30 | TRA | 06 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2000-03-01 | 2001-03-01 | 2001-04-01 |  | 2003-03-01 | 2007-06-01 | 42500 | -23512 | 18988 | 18988 | 100% | 0 | 0 |  | 5525 | -3056.56 | 2468 | 0.44 | 0 |  |  |  | 2003-03-01
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | AFR | GUI | REF | 30 | TRA | 07 | A | I | CFC | 10.5 | 10.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2002-09-01 | 2003-09-01 | 66500 | 0 | 66500 | 66500 | 100% | 0 | 0 |  | 8645 | 0 | 8645 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Preparation of a country programme/RMP | RMP | AFR | GUI | REF | 39 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2004-11-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities of the RMP | Individual | AFR | GUI | REF | 45 | TAS | 14 | A | I | CFC | 3.1 | 3.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs officers training in monitoring and control of ODS (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 12 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-04-01 |  | 2006-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for refrigeration technicians (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 13 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-10-01 |  | 2006-12-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | GUI | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-10-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | GUI | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | GUI | SEV | 28 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | GUI | SEV | 34 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | GUI | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: (phase V) | Individual | AFR | GUI | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2009-02-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: (phase VI) | Individual | AFR | GUI | SEV | 56 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GUI | SEV | 63 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 60000 | -121 | 59879 | 59878.8 | 100% | 0.2 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | AFR | GUI | SEV | 70 | INS | 28 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-06-01 | 2015-06-01 |  |  | 60000 | 0 | 60000 | 46500 | 77.5% | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013. 2014 Ozone day was celebrated. Coordination of HPMP activities( Three workshops for refrigeration technicians and two workshops for customs officers). Organisation of four meting of the steering committee. Coordination of the national survey of HCFC consumption.Legal arrangements (actual/planned): Agreement signed in Januaryr 2014. All activities under the SSFA are completed (as planned) no___ First mission (actual/planned): _ N/A - Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 2014 __ All funds disbursed (yes/no): NO_ Final payment _ Any delay? (yes/no): No__ If Yes, reasons for delay & action plan to resolve:__ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Organisation of a survey on HCFCs import and elaboration of a verification report for the 2013 consumption.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUY | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2009-06-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | GUY | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2009-03-01 |  | 2010-05-01 | 2011-05-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUY | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -17218 | 67782 | 67782 | 100% | 0 | 0 |  | 11050 | -2238 | 8812 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 72000 | -18566 | 53434 | 53434 | 100% | 0 | 0 | 0 | 9360 | -2414 | 6946 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-03-01 | 2012-03-01 |  | 2014-12-14 | 2014-12-14 | 11000 | 0 | 11000 | 10932.3 | 99.38% | 67.7 | 0 |  | 1430 | 0 | 667 | 763 | 0 | Brief progress report (actual/planned): Two (2) customs workshops were conducted. Thirty (30) customs officers and customs officials participated in these workshops. Licensing system is in place; a component on the Montreal Protocol and ODS monitoring have been included in the regular upgrade for customs training; a total of ninety nine (99) technicians participated in the eight workshops facilitated by a national trainer who was trained under the Terminal Phase out Management Plan (TPMP); a one-day workshop on alternative technologies was held on September 2014. Thirty Four (34) technicians from various regions in Guyana participated; a full-time refrigeration and air conditioning programme was introduced at the Kuru Kuru Training Center in September 2014. Currently 19 (17 males and 2 females) students are enrolled in this programme; three training modules were developed to support the introduction of the Caribbean Vocational Qualification Level 1 Standard for Refrigeration and Air Conditioning; television, radio programmes and published articles to educate stakeholders on the Montreal Protocol’s phase out activities as well as to educate importers on national legislation with regard to importation of ozone depleting substances and equipment which contain them. ___ Legal arrangements (actual/planned): n/a___ First mission (actual/planned): ___ TOR completed (actual/planned): Nov-2012. Revised Oct-2014___ First disbursement date (actual/planned): Mar-2013/Dec-13 ___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): no. ___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: n/a.___ | Training consultant submitted last report and payment processed in March-2015. Project financially completed.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | GUY | PHA | 73 | PRP | 23 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-11-01 | 2015-12-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | ToR for consultant drafted in Jan-2015. ToR approved in Feb-2015. Contract signed in Mar-2015. Workplan with deliverables agreed in Apr-2015. Mission to country planned for Jun-2015 to update the HCFC survey, agree on the strategy 2015-2020 and draft the proposal.
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | GUY | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-12-01 | 30000 | -4000 | 26000 | 26000 | 100% | 0 | 0 |  | 3900 | -520 | 3380 | 0 | 0 | Project financially completed. | Project financially completed. |  | 1999-05-01
FIN | UNEP | Implementation of the RMP: training of trainers for good refrigeration servicing practices | Individual | LAC | GUY | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 2001-04-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training on monitoring and control of ODS and ODS using equipment | Individual | LAC | GUY | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-06-01 |  | 2003-08-01 | 2003-09-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: assistance for implementation of additional activities in the RMP | Individual | LAC | GUY | REF | 35 | TAS | 10 | A | I | CFC | 45.2 | 45.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2008-01-01 | 2009-04-01 | 65500 | 0 | 65500 | 65500 | 100% | 0 | 0 |  | 8515 | 0 | 8515 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | GUY | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 |  | 5200 | -650 | 4550 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Creation of the National Ozone Action Unit | Individual | LAC | GUY | SEV | 23 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 2000-11-01 |  | 2001-08-01 | 2007-03-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | GUY | SEV | 34 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2005-02-01 | 2003-08-01 |  | 2008-09-01 | 2009-09-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GUY | SEV | 48 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 56333 | 0 | 56333 | 56333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | GUY | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | GUY | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-11-01 | 2014-12-01 |  | 2014-12-14 | 2014-12-14 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Quota system for 2014 was published in the Gazette. Annual CP progress report and preliminary Article 7 data was submitted in May 2014; coordination, monitoring and reporting of HPMP activities. Support provided to national refrigeration association (GARVA). Several public awareness activities took place: school workshop (10 primary & 10 secondary schools in Georgetown of approx. 100 students). Technicians Workshop on alternatives was held on September 17 as part of International Ozone Day 2014 activities. Guyana was represented by the NOO in the Caribbean Ozone Officers Meeting held in Suriname April-2014 and the Joint LAC Meeting held in the Dominican Republic December-2014. ___ Legal arrangements (actual/planned): Agreement signed in Nov 2013. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement in Nov 2013.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): n/a. ___ Any ongoing problems (yes/no): n/a. ___ If Yes, is any action required by ExCom: n/a. | Last progress and financial report sent on Feb-2015. Progress report required additional information. Progress report cleared on Mar-2015. Last disbursement processed in Apr-2015. Project financially completed.
FIN | UNEP | Sectoral phase-out programme: Establishing a halon management plan | Individual | LAC | HAI | HAL | 50 | TAS | 10 | A | I | Halon | 1.5 | 1.5 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2009-11-01 |  | 2008-11-01 | 2009-11-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 |  | 3250 | -1170 | 2080 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | HAI | PHA | 54 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2010-12-01 | 2012-04-01 | 15000 | -2038 | 12962 | 12962 | 100% | 0 | 0 |  | 1950 | -265 | 1685 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HAI | PHA | 57 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 |  | 2013-12-01 | 2013-12-01 | 85000 | -30997 | 54003 | 53918 | 99.84% | 85 | 0 |  | 11050 | -4030 | 7009.34 | 10.66 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-06-01 |  | 2013-06-01 | 2013-06-01 | 125000 | -13659 | 111341 | 110351 | 99.11% | 990 | 0 |  | 16250 | -1775.67 | 14345.63 | 128.7 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HAI | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 | 2016-12-01 |  |  | 40000 | 0 | 40000 | 15271.28 | 38.18% | 24728.72 | 0 | 8243 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): three workshops on Good Refrigeration Management Practices, Recovery, Recycling, Retrofitting and Alternative Technologies of Ozone Depleting Substances, were held during July and October 2014, with participation of 27 and 38 informal refrigeration servicing technicians, respectively. Organization of workshops count with the support of the Apex Technical Institute (main vocational institute of Haiti). Specialized training delivered to 127 Customs and Border Control enforcement personnel were provided in two workshops held in May and July, 2014.___ Legal arrangements (actual/planned): UNEP is providing direct administrative services to Haiti with the support of UNEP's and UNDP's national offices.___ First mission (actual/planned): ___TOR completed (actual/planned): ___ All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country towards the end of the year, second tranche request was not submitted to the 73 ExCom. UNEP followed up with NOU on outstanding report, endorsement letter with wording required by the ExCom. Examples of second tranche requests already approved were facilitated to NOU. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___ | Follow-up communications with NOU in Jan-2015. Political instability remains, NOO is not able to reach office because of street protests and blockages. New Minister appointed in Feb-2015. Government have planned and will focus on parliamentarian, municipal and presidential elections to take place between July and November 2015. New Minister appointed in early June 2015.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | HAI | PHA | 73 | TAS | 19 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-05-01 | 2015-12-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 5000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Generic ToRs approved in Feb-2015. Contracting of new consultants should follow new procedures under UMOJA. Contracting process starting in Jun-2015 when UMOJA goes live.
FIN | UNEP | Implementation of the RMP: train the technicians on good practices in refrigeration | Individual | LAC | HAI | REF | 39 | TRA | 05 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2008-12-01 | 2009-12-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 |  | 9646 | 0 | 9646 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | LAC | HAI | REF | 39 | TRA | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2010-12-01 | 2012-04-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 |  | 4303 | 0 | 4303 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of country programme | Individual | LAC | HAI | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-04-01 |  | 2003-07-01 | 2005-06-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 |  | 7800 | -3770 | 4030 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | HAI | SEV | 38 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-07-01 | 2003-12-01 |  | 2004-08-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project (phase I, years 2 and 3) | Individual | LAC | HAI | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-09-01 | 2008-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | HAI | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-09-01 | 2011-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | HAI | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 | 2015-12-01 |  |  | 54167 | 45834 | 100001 | 50816 | 50.82% | 49185 | 0 | 27203 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported CP data and Article 7 data on time. NOO attended the Caribbean Network meeting in Suriname, and the Joint Network meeting of Latin America and the Caribbean in the Dominican Republic. Celebration of International Ozone Day and other public awareness activities. Support training activities of customs officers and informal refrigeration technicians ___Initial stages of project implementation (actual/planned): enforceable HCFC quota system is not in place___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First financial authorization in May-14 once outstanding reports of previous IS phase were sent by NOU and cleared by UNEP.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: UNEP mission in June-2014 adressed concerns expressed by NOO regarding use of IS funds. It also served to identify the urgent need to hire a legal expert to draft legislation regarding quotas for HCFCs. Sample ToR were sent to NOU for processing. Political instability of the country prevented NOU to move the contracting forward___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no ___ If Yes, is any action required by ExCom: . ___ | Follow-up communications with NOU in Jan-2015. Political instability remains, NOO is not able to reach office because of street protests and blockages. New Minister appointed in Feb-2015. Government have planned and will focus on parliamentarian, municipal and presidential elections to take place between July and November 2015. New Minister appointed in early June 2015.
FIN | UNEP | Additional emergency assistance for institutional strengthening | Individual | LAC | HAI | SEV | 61 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2011-06-01 |  | 2014-12-31 | 2014-12-31 | 20000 | 0 | 20000 | 18531.92 | 92.66% | 1468.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Balance to be returned. | Project financially completed.
FIN | UNEP | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 | 2010-12-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 |  | 1950 | -325 | 1625 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HON | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 35000 | -17500 | 17500 | 17116 | 97.81% | 384 | 0 |  | 4550 | -2275 | 2225.08 | 49.92 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-12-01 |  | 2011-12-01 | 2011-12-01 | 146000 | 0 | 146000 | 146000 | 100% | 0 | -1.1369e-12 |  | 18980 | 0 | 18980 | 0 | -1.4779e-13 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-31 | 52000 | 0 | 52000 | 43268 | 83.21% | 8732 | 0 |  | 6760 | 0 | 5623 | 1137 | 1135.16 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2014-03-01 | 2016-06-30 |  |  | 75000 | 0 | 75000 | 7047.2 | 9.396% | 67952.8 | 0 | 27182 | 9750 | 0 | 5353 | 4397 | 4396.86 | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. No new disbursements requested from the Government in the year. However, intermediate goals achieved as planned for the year 2014: ODSs license system implemented; NOO collected ODSs data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. Article 7 data and CP progress report data submitted; NOU is responsible for the HPMP implementation. On 16 October, the NOU organized an awareness raising activity to celebrate the International Ozone Day. With the presence of mass media, the Minister of Environment awarded main partners and relevant stakeholders for their contribution to the Ozone layer protection. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal will be postponed until the level of expenditures reaches the 80% of project budget. Any ongoing problems? No. If Yes, is any action required by ExCom? Difficulties sorted out by middle of 2014 year. | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. Government has not requested any dibursment in the year. However, intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal to be submitted to the 75 ExCom. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | HON | PHA | 70 | TAS | 38 | A | I |  | 0.8 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-06-30 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Brief progress report: The HPMP second tranche implementation was approved in July 2013. Its implementation has been deferred after the first tranche is completed. Legal arrangements (actual/planned): No signature/Initially planned for November 2013. First disbursement date (actual/planned): No disbursements/Planned for December 2013. All funds disbursed? N/A. Any delay? Yes. If Yes, will delay have impact on project completion date? An impact on the project completion is expected since the first tranche implementation is delayed. If Yes, reasons for delay & action plan to resolve: The potential delay is due to a managerial decision for greater accountability. A country mission carried out in 2014 to explain national authorities on the nature of Multilateral Fund projects and Montreal Protocol country commitments. Any ongoing problems? No- The organization chart of the Ministry was reformulated and activities of HPMP(I) resumed but it was not completed yet. If Yes, is any action required by ExCom? No | Brief progress report: The HPMP second tranche implementation was approved in July 2013. Its implementation has been deferred after the first tranche is completed. Legal arrangements (actual/planned): No signature/Initially planned for November 2013. First disbursement date (actual/planned): No disbursements/Planned for December 2013. All funds disbursed? N/A. Any delay? Yes. If Yes, will delay have impact on project completion date? An impact on the project completion is expected since the first tranche implementation is delayed. If Yes, reasons for delay & action plan to resolve: The potential delay is due to a managerial decision for greater accountability. A country mission carried out in 2014 to explain national authorities on the nature of Multilateral Fund projects and Montreal Protocol country commitments. Any ongoing problems? No- The organization chart of the Ministry was reformulated and activities of HPMP(I) resumed but it was not completed yet. If Yes, is any action required by ExCom? No
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | HON | REF | 41 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2008-12-01 | 15000 | -628 | 14372 | 14372 | 100% | 0 | 0 |  | 1950 | -82 | 1868 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: programme for prevention of illegal ODS trade | Individual | LAC | HON | REF | 44 | TAS | 17 | A | I | CFC | 21.3 | 21 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: programme for permanent monitoring of the RMP | Individual | LAC | HON | REF | 44 | TAS | 18 | A | I | CFC | 35.1 | 35.1 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 38000 | -5630 | 32370 | 32370 | 100% | 0 | 0 |  | 4940 | -732 | 4208 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: programme for certification and licensing of refrigeration technicians | Individual | LAC | HON | REF | 44 | TRA | 16 | A | I | CFC | 86.9 | 86.9 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 |  | 12220 | 0 | 12220 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | HON | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1996-06-01 | 1999-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Ozone Unit Cell for the institutional strengthening programme | Individual | LAC | HON | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1999-10-01 |  | 2001-06-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | HON | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-05-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | HON | SEV | 40 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-07-01 | 2005-07-01 |  | 2005-07-01 | 2007-02-01 | 57200 | -1 | 57199 | 57199 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | HON | SEV | 45 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-05-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | HON | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | HON | SEV | 57 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | HON | SEV | 68 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2014-02-01 | 2016-03-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 24000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. However, intermediate goals achieved as planned for the year 2014: ODSs license system implemented; NOO collected ODSs data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. Article 7 data and CP progress report data submitted; NOU is responsible for the HPMP implementation. On 16 October, the NOU organized an awareness raising activity to celebrate the International Ozone Day. With the presence of mass media, the Minister of Environment awarded main partners and relevant stakeholders for their contribution to the Ozone layer protection. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal will be postponed until the level of expenditures reaches the 80% of project budget. Any ongoing problems? No. If Yes, is any action required by ExCom? n.a. | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. However, intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Half year progress and financial report submitted to UNEP. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal to be submitted to the 75 ExCom. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
COM | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | IND | ARS | 56 | TAS | 425 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2013-11-01 |  | 2014-12-01 |  | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 15600 | 0 | 6058 | 9542 | 0 | All activities completed and PCR submitted | Project completed
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IND | PHA | 56 | PRP | 429 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (enabling activities) | Multi-year | ASP | IND | PHA | 66 | TAS | 443 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2013-04-01 | 2015-12-01 |  |  | 250000 | 0 | 250000 | 145000 | 58% | 105000 |  | 105000 | 30402 | 0 | 10089 | 20313 | 0 | Brief progress report (actual/planned): meetings between NACEN, DRI, Ozone Cell and UNEP to agree on terms of cooperation. Legal arrangement (actual/ planned): Part of the funds included in the SSFA for second tranche that ahs not been signed as yet. First mission (actual/ planned): Feb. 2013. TOR completed (actual/ planned): N/A. First disbursement date: 3rd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delay in signing of the agreement with UNEP due to inter-Ministry negotiation of terms. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): 30 units of refrigerants identifiers delivered in 2nd quarter of 2015. The SSFA still not signed
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | IND | PHA | 66 | TAS | 445 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-08-01 | 2013-04-01 | 2015-12-01 |  |  | 180800 | 0 | 180800 | 140000 | 77.43% | 40800 |  | 40800 | 21986 | 0 | 0 | 21986 | 0 | Brief progress report (actual/planned): RAC & refrigerant dealer awareness workshops in Delhi, Jan. 2014. In Feb. 2014, Refrigeration & Air-Conditioning Servicing Sector Society (RASSS) was officially registered (No. 4367 of 2014) under the Societies Registration Act (XXI of 1860) and as amended by Punjab Amendment Act, 1957. Posters and flyers on good servicing produced and distributed. Draft website on HPMP developed. Legal arrangement (actual/ planned): The 1st SSFA signed in May 2013, was completed and closed. First mission (actual/ planned): Feb. 2013. TOR completed (actual/ planned): N/A. First disbursement date: 25/06/2013. All funds disbursed (yes/no): no. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Project on hold in 2015 due to lack of funds in the country. Regional and Dealers workshops in Bangalore, Lucknow, Chennai, Jaipur, Bhopal, postponed. Legal arrangement (actual/ planned): The 2nd SSFA not signed yet.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and enabling activities) | Multi-year | ASP | IND | PHA | 71 | TAS | 450 | A | I |  | 3.6 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 344640 | 0 | 344640 | 0 | 0% | 344640 |  | 344640 | 41910 | 0 | 0 | 41910 | 0 | Brief progress report (actual/planned): not started. Legal arrangement (actual/ planned): Agreements drafted but not signed . First mission (actual/ planned): Proposed in the 3rd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: Potentially in 3rd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delay in signing of the agreement between the country and UNEP. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Legal arrangement (actual/ planned): The SSFA still not signed.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IND | PHA | 72 | PRP | 456 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-05-01 | 2016-05-31 |  |  | 20000 |  | 20000 | 0 | 0% | 20000 |  | 20000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): Negotiation with the government on implementation modality. National Stakeholders Workshop on overall HPMP stage II and bilateral meetings with servicing/ enabling partners and stakeholders in July 2014. Legal arrangement (actual/planned): N/A. First mission (actual/ planned): July 2014. TOR completed (actual/ planned): N/A. First disbursement date: N/A. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: lengthy negotiation with the government on implementation modality. If Yes, will delay have impact on project completion date (yes/no): no. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): A local consultant identified in the 2nd quarter of 2015. National stakeholders consultation to be held in mid Aug. 2015.
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-year | ASP | IND | REF | 42 | TAS | 377 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2007-06-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 |  |  | 33319 | 0 | 33319 | 0 | 0
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-year | ASP | IND | REF | 44 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-04-01 | 2009-04-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 |  |  | 33319 | 0 | 33319 | 0 | 0
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-year | ASP | IND | REF | 47 | TAS | 396 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-year | ASP | IND | REF | 50 | TAS | 405 | A | I | CFC | 101.5 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2008-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-year | ASP | IND | REF | 54 | TAS | 420 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2011-01-01 | 2012-01-01 | 19900 | 0 | 19900 | 19900 | 100% | 0 |  |  | 2587 | 0 | 2587 | 0 | 0
FIN | UNEP | Develop policy and customs training strategies | Individual | ASP | IND | SEV | 30 | TAS | 253 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2003-04-01 | 2005-12-01 | 50000 | -22000 | 28000 | 28000 | 100% | 0 |  |  | 6500 | -2860 | 3640 | 0 | 0
FIN | UNEP | Overall strategy for the solvent sector to support the phase-out of ODS in SMEs | Individual | ASP | IND | SOL | 35 | TAS | 343 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-12-01 |  | 2005-06-01 | 2007-07-01 | 169000 | -10140 | 158860 | 158860 | 100% | 0 |  |  | 21970 | -1318 | 20652 | 0 | 0
FIN | UNEP | National transition strategy for the phase-out of CFC propellants in MDIs | Individual | ASP | IRA | ARS | 52 | TAS | 184 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-03-01 | 2010-09-01 |  | 2011-01-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | National CFC phase-out plan: 2004 annual implementation programme | Multi-year | ASP | IRA | PHA | 41 | TAS | 161 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 140253 | 0 | 140253 | 140253 | 100% | 0 |  |  | 18233 | 0 | 18233 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IRA | PHA | 56 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-01-01 | 2012-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 200 | A | I |  | 3.2 | 0 | 0 | 0 | 2011-04-01 | 2013-08-01 | 2015-03-01 | 2016-06-01 |  |  | 262000 | 0 | 262000 | 107965 | 41.21% | 154035 |  | 94035 | 34060 | 0 | 14035 | 20025 | 0 | Brief progress report (actual/planned): Interagency meeting in March 2014. Awareness and training workshop for custom officers in DoE in March 2014. The National Ozone Committee (NOC) meeting held in 1st quarter 2014 for HCFCs quota allocation. The Customs Officers Training Workshop held in March 2014 with resource people from national enforcement authorities, UNDP, UNIDO, GIZ and UNEP. The NOU with help of national resource people commenced provincial-level Customs training in Aug. 2014. Legal arrangement (actual/ planned): The SSFA signed in March 2013. As result of return of US$60,000 agreed with ExCom, the country and UNEP revised the implementation plan for the remaining activities in the last Q of 2014. First mission (actual/ planned): 5-7/09/2011. TOR completed (actual/ planned): N/A. First disbursement date: 29/08/2013. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Lengthy inter-agency negotiation of terms within the country. UNEP solicited assistance from UN Resident Coordinator's Office. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Two servicing technicians workshops in Mazandaran Province in Feb. 2015, in cooperation with Provincial DoE of Mazandaran Province and the Mazandaran Technical and Vocational Training Organization (TVTO). Implementation delayed since Jan. 2015 due to negotiations on activity re-programming, post- return of funds to MLF. Legal arrangement (actual/ planned): A new SSFA yet to be signed.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IRA | PHA | 72 | PRP | 212 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-05-01 | 2016-05-01 |  |  | 25000 |  | 25000 | 20928 | 83.71% | 4072 |  | 25000 | 3250 | 0 | 0 | 3250 | 0 | Brief progress report (actual/planned): negotiation with the government on implementation modality. Legal arrangement (actual/planned): N/A. First mission (actual/ planned): The 3rd quarter of 2015. TOR completed (actual/ planned): TOR was ready by July 2014, but delay in selecting candidates. Agreement was not reached in 2014. First disbursement date: N/A. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: lengthly negotiation on draft TOR and suitable candidates for consultancy. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Bilateral meetings with IAs, NOU and stakeholders. Detailed plan of implementation drafted. Legal arrangement (actual/planned): N/A. First mission (actual/ planned): The 3rd quarter of 2015. TOR completed (actual/ planned): A local consultant hired in May 2015. First disbursement date: June 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | Preparation of country programme update | Individual | ASP | IRA | SEV | 36 | CPG | 145 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 26250 | -3250 | 23000 | 23000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Preparation of country programme and national phase-out plan | RMP | ASP | IRQ | PHA | 55 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-07-01 | 2009-07-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 | 0
ONG | UNEP | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2012-07-01 | 2016-12-01 |  |  | 1136000 | 0 | 1136000 | 880460 | 77.51% | 255540 |  | 255540 | 147680 | 0 | 76198 | 71482 | 0 | Brief progress report (actual/planned): - Training of Customs and respective authorities is completed resulting in 195 officers trained - National technical and vocational curricula are updated and entered into service from the academic year of 2014-2015. Final printed versions of the curricula are also developed and copies handed to UNEP for record - The training programme on refrigeration good practices is completed in 2014 concluding in 81 sessions were conducted (in 3 years) on which 1931 Participants representing domestic, light commercial and MAC servicing workshops were trained in 8 training centers in different governorates in Iraq. - Specialized workshop on updating the national certification scheme for technicians organized in Amman, Jordan during Sept 2014 and attended by 18 local experts and 3 international speakers - Coordination meeting for the PMU team to review/adjust the work-plan and technical/financial reports organized twice in margins with technical events i.e. Erbil-May 2014 and Amman- Sept 2014 • Legal arrangements(actual/planned): - Country contract already established in 2010 and amended later to incorporate 2nd tranche with 1st tranche in once contract • First mission (actual/planned): Two missions conducted in 2014, one to evaluate the training programs (customs and good practices) in Erbil, Iraq May 2014 and another one in Amman, Jordan Sept 2014 for organizing the Certification Scheme workshop. Both missions included coordination meetings with PMU representatives • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): Third payment against NPP contract was made in 2014 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes, • If Yes, reasons for delay & action plan to resolve: several delays due to political and institutional difficulties in Iraq resulted in delay in disbursing transferred funds during 2014. Financial disbursement started to get back to normal by beginning of 2015 • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Yes, financial closure of the project is expected to be by 2016 due to financial and auditing requirements under the country contract • If Yes, is any action required by ExCom: Yes, Request to amend the date of the completion of the project to be end of 2016 instead of end of 2015 is sought from ExCom | # Remaining refrigeration good practices training is continuing aiming at completing the project by 3rd quarter of 2015 # Pending financial reports are submitted by the government and disbursement of due payments to different stakeholders under NPP are made by PMU/MoE # The certification scheme committee completed the draft certification modules and its under review # UNEP organized the final coordination meeting for NPP project attended by PMU, NOU and UNIDO (May 2015 in Amman) and revised the work-plan of remaining activities and cash-flow of remaining balances
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | IRQ | PHA | 60 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2011-12-01 | 2014-05-14 | 100000 | -25671 | 74329 | 74329 | 100% | 0 |  |  | 13000 | -3337 | 9663 | 0 | 0 | Project financialy Completed | Project financialy Completed
ONG | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2012-03-01 | 2016-12-01 |  |  | 505000 | 0 | 505000 | 339900 | 67.31% | 165100 |  | 165100 | 65650 | 0 | 2581 | 63069 | 2.9559e-14 | Brief progress report (actual/planned): - Training of Customs and respective authorities is completed resulting in 195 officers trained - National technical and vocational curricula are updated and entered into service from the academic year of 2014-2015. Final printed versions of the curricula are also developed and copies handed to UNEP for record - The training programme on refrigeration good practices is completed in 2014 concluding in 81 sessions were conducted (in 3 years) on which 1931 Participants representing domestic, light commercial and MAC servicing workshops were trained in 8 training centers in different governorates in Iraq. - Specialized workshop on updating the national certification scheme for technicians organized in Amman, Jordan during Sept 2014 and attended by 18 local experts and 3 international speakers - Coordination meeting for the PMU team to review/adjust the work-plan and technical/financial reports organized twice in margins with technical events i.e. Erbil-May 2014 and Amman- Sept 2014 • Legal arrangements(actual/planned): - Country contract already established in 2010 and amended later to incorporate 2nd tranche with 1st tranche in once contract • First mission (actual/planned): Two missions conducted in 2014, one to evaluate the training programs (customs and good practices) in Erbil, Iraq May 2014 and another one in Amman, Jordan Sept 2014 for organizing the Certification Scheme workshop. Both missions included coordination meetings with PMU representatives • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): Third payment against NPP contract was made in 2014 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes, • If Yes, reasons for delay & action plan to resolve: several delays due to political and institutional difficulties in Iraq resulted in delay in disbursing transferred funds during 2014. Financial disbursement started to get back to normal by beginning of 2015 • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Yes, financial closure of the project is expected to be by 2016 due to financial and auditing requirements under the country contract • If Yes, is any action required by ExCom: Yes, Request to amend the date of the completion of the project to be end of 2016 instead of end of 2015 is sought from ExCom | # Remaining refrigeration good practices training is continuing aiming at completing the project by 3rd quarter of 2015 # Pending financial reports are submitted by the government and disbursement of due payments to different stakeholders under NPP are made by PMU/MoE # The certification scheme committee completed the draft certification modules and its under review # UNEP organized the final coordination meeting for NPP project attended by PMU, NOU and UNIDO (May 2015 in Amman) and revised the work-plan of remaining activities and cash-flow of remaining balances
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2016-12-01 |  |  | 115000 | 0 | 115000 | 0 | 0% | 115000 |  | 115000 | 14144 | 0 | 0 | 14144 | 0 | Brief progress report (actual/planned): Project start delayed due to delay in NPP since all HPMP activities are continuation of the NPP. Revised work-plan concluded with NOU taking into consideration progress in NPP related activities. • Legal arrangements(actual/planned): - Country contract drafted and sent for signature by end of 2014 • First mission (actual/planned): No dedicated mission • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): N/A • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract, country contract is ready for signature by end of 2014. • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Yes, local institutional and political challenges • If Yes, is any action required by ExCom: No | # Country contract signed and first payment is under processing (expected by end of June 2015) # UNEP/UNIDO organized coordination meeting for PMU/NOU (Amman, May 2015) and agreed on detailed work-plan for expediting the implementation of the HPMP # 2nd tranche of the HPMP is drafted, reviewed and submitted to ExCom-74 which approved it. # UNEP/UNIDO and country agreed to amend the duration of Stage-I till 2017 and the request for 2nd tranche was drafted/approved accordingly |  |  |  |  | To request the submission of additional status report to the 74th meeting to monitor low disbursement rates of approved funds noting that the agreement was signed on 26 March 2015 for this project approved in November 2011.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IRQ | PHA | 73 | PRP | 21 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 45000 |  | 45000 | 0 | 0% | 45000 |  | 45000 | 5850 | 0 | 0 | 5850 | 0 | Brief progress report (actual/planned): Newly approved project | • Brief progress report (actual/planned): - Initial work-plan for the preparation of stage-II is shared with the country - Coordination meeting is organized with the country and agreed on the contractual arrangements and timeframe of implementation - TORs for the local experts and data to be collected during the preparation of Stage-II is under development by UNEP and UNIDO in consultation with the country • Legal arrangements(actual/planned): - Draft legal agreement is under preparation • Initial stages of project implementation(actual/planned): Coordination meeting and initial work-plan made • Intermediate goals achieved (actual/planned): N/A • Project completion and follow up: Planned to be completed by end of 2016 • First disbursement date (actual/planned): 2015 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Extension of the duration of stage-I of the HPMP to be till 2017 as per ExCom-74 • If Yes, will delay have impact on project completion date (yes/no): Project completion is shifted by one year to be end of 2016 • Any ongoing problems (yes/no): No • If Yes, is any action required by ExCom: No
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | IRQ | SEV | 54 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2010-03-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Institutional strengthening (phase I) | Individual | ASP | IRQ | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2011-03-01 |  | 2012-12-01 |  | 240000 | -1359 | 238641 | 238641 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project completed, awaiting for the final audited report | Project completed, awaiting for the final audited report
ONG | UNEP | Extension of institutional strengthening project (phase II: 6/2013-5/2015) | Individual | ASP | IRQ | SEV | 69 | INS | 18 | A | I |  | 0 |  | 0 |  | 2013-04-01 |  | 2015-03-01 | 2015-12-15 |  |  | 240000 | 0 | 240000 | 100000 | 41.67% | 140000 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU is supervising the implementation of the HPMP and the operation of the PMU, NOU provided support to PMU in terms of concluding the financial and technical reports plus it attended the UNEP-UNIDO- PMU coordination meetings (2 meetings) in 2014. NOU also provided policy support to the establishment the operation of the certification committee which is managed by PMU. NOU also provided support to PMU in communication with different authorities to clear the project shipments for investment components. NOU printed awareness material to raise awareness on Montreal Protocol and distributed amongst senior officers and technicians. Legal arrangements (actual/planned): Legal instrument was signed in Jan-2014, but country could not access the funds of first payment due to internal political issues i.e. the parliament did not endorse/approve the government budget which included the funds transferred by UNEP to the Ministry. This delayed receipt of progress/expenditure reports. PCA expired end May-2015./ Initial stages of project implementation (actual/planned): Although delay was faced with release of funding by parliament, the NOU continues to operate as best possible. Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for the year of 2013. Project completion and follow up: Project is being implemented and is delayed and new legal instrument is required as per UNEP guidelines. First disbursement date (actual/planned): First payment disbursed in Feb-2014, US$100,000 . All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay was due to first late release of funds through the parliament and more delay expected as new legal instrument needs to be drafted. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes, since new legal instrument has to be drafted. If Yes, is any action required by ExCom: No. | NOU continues supervising the implementation of the HPMP and the operation of the PMU, NOU provided support to PMU in terms of concluding the financial and technical reports plus it attended the UNEP-UNIDO- PMU coordination meeting (Amman- May 2015). NOU also provided support to PMU in communication with different authorities to clear the project shipments for investment components. NOU supported UNEP in finalizing the proposal for the 2nd tranche of the HPMP and the verification report including compiling and verifying data of importation with different authorities. NOU continue to operate normally and submit reports in due course, CP report for 2014 was timely submitted to MFS and A7 report is under preparation and will be early submitted. NOU is preparing for the submission of Phase-III of ISP in cooperation with UNEP.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | IVC | PHA | 48 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 15000 | -9 | 14991 | 14991 | 100% | 0 | 0 |  | 1950 | -1 | 1949 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 173000 | 0 | 173000 | 173000 | 100% | 0 | 0 |  | 22490 | 0 | 22490 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | IVC | PHA | 57 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2012-02-01 | 2013-02-01 | 85000 | -18026 | 66974 | 66974 | 100% | 0 | 8.8818e-15 |  | 11050 | -2343 | 8707 | 0 | 1.1546e-15 | Project Financially Complete
FIN | UNEP | TPMP verification | Individual | AFR | IVC | PHA | 57 | TAS | 31 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-02-01 | 2013-12-01 | 109000 | 0 | 109000 | 109000 | 100% | 0 | 0 |  | 14170 | 0 | 14170 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-04-01 | 2015-12-01 |  |  | 250000 | 0 | 250000 | 142965.85 | 57.19% | 107034.15 | 0 | 101990.55 | 30260 | 0 | 11254 | 19006 | 6661.5574 | Brief progress report (actual/planned): Three (3) workshops for customs officers and environment inspectors have been organized between March and May 2014: in Abidjan (37 officers), in Daloa (38 officers) and in San-Pedro (25 officers). A total of one hundred (l00) officers have been trained in 2014. Three refrigerant identifiers were purchased and are being used as training tool kit. Three more workshops for one hundred and seven (107) refrigeration technicians and thirteen (13) marine officers have been organised between March and May 2014 in Abidjan, Divo and San-Pedro. 2.__ Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _ ExCom approval was US$250,000; it was split into 2 SSFAs, for US$145,000 and US$105,000 respectively, each to run for one year. 1st disbursement done in September 2012 __ All funds disbursed (yes/no): yes. .__ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: The main reason was the war in Cote d`Ivoire. Situation returned to normal and First SSFA completed. Second SSFA signed by country on 19/02/2015___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | SSFA for 145,000$ completed. SSFA for 100,000$ signed by the country on 19/02/2015
FIN | UNEP | Training for refrigeration and air conditioning technicians | Individual | AFR | IVC | REF | 13 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1997-03-01 | 1999-04-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 9880 | 0 | 9880 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | IVC | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-03-01 | 1994-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the Ozone Secretariat) | Individual | AFR | IVC | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-01-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 122810 | -300 | 122510 | 122510 | 100% | 0 | 0 |  | 15965 | -39 | 15926 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | IVC | SEV | 26 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2004-04-01 | 2004-12-01 | 81800 | 0 | 81800 | 81800 | 100% | 0 | 0 |  | 10634 | 0 | 10634 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | IVC | SEV | 43 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-09-01 | 2005-07-01 |  | 2005-11-01 | 2007-08-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III, year 2) | Individual | AFR | IVC | SEV | 48 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | IVC | SEV | 53 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-06-01 | 2011-06-01 | 106340 | 0 | 106340 | 106340 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | IVC | SEV | 62 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 106340 | 0 | 106340 | 106340 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | IVC | SEV | 68 | INS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 | 2015-12-01 |  |  | 106340 | 0 | 106340 | 81104.93 | 76.27% | 25235.07 | 0 | 50438.79 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013 Art5 data and 213 CP data. 2014 Ozone day was celebrated. Legal arrangements (actual/planned): Agreement signed in January 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in February 2013 __ All funds disbursed (yes/no): Yes_ Final payment sent in August 2014_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country submitted progress report and renewal of IS in June 2015. Country submitted also 2014 CP data report in April 2015. Country took advantage of the Word Environment day to organize a conference at the main university of Abidjan on HCFC, HCFC based equipment and the HCFCs phase out calendar.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | AFR | IVC | SEV | 73 | INS | 39 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 106340 |  | 106340 | 0 | 0% | 106340 | -5.8265e-13 | 40000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on 16 April 2015
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 | 2015-12-31 |  |  | 20000 | 0 | 20000 | 16000 | 80% | 4000 | 0 | 4000 | 2600 | 0 | 2087 | 513 | 0 | Brief progress report (actual/planned): Gazetting of The Trade (Montreal Protocol) (Trade in Ozone Depleting Controlled Substances) Order, 2014 (24 November 2014); existing labeling standards amended to include HCFCs;the Bureau of Standards convened a labelling sub-committee which started the review and amendment of the 'Jamaican Standard Specification for The labelling of commodities Part 29: Labelling of products and equipment containing or manufactured using ozone depleting substances and/or their substitutes' to include HCFCs. The draft amended standard will then be submitted to the Standards and Technical Committee of the Standards Council for a recommendation on approval of the draft standard; three days of training for the Jamaica Customs Officers: the first two days training were theoretical while the other was a practical session and included the use of the refrigerant identifier. A one day workshop was organized with Officers from the Ministry of Health, Trade Board , Ministry of Industry, Investment and Commerce on the HCFC quota system and Montreal Protocol in general. ___ Legal arrangements (actual/planned): SSFA signed in Apr-12 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): First financial authorization issued in Apr-2012___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: completion of outstanding activities with balance from 2013 ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Submission of progress and financial reports in Mar-2015. No new obligation could be raised because of UMOJA ramp-down and black-out periods. New agreement to be discusssed in Jun-2015 once UMOJA is operative.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | JAM | PHA | 70 | TAS | 33 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-12-01 |  |  | 18000 | 0 | 18000 | 1645 | 9.139% | 16355 | 0 | 6442 | 2340 | 0 | 0 | 2340 | 0 | Brief progress report (actual/planned): Gazetting of The Trade (Montreal Protocol) (Trade in Ozone Depleting Controlled Substances) Order, 2014 (24 November 2014); existing labeling standards amended to include HCFCs;the Bureau of Standards convened a labelling sub-committee which started the review and amendment of the 'Jamaican Standard Specification for The labelling of commodities Part 29: Labelling of products and equipment containing or manufactured using ozone depleting substances and/or their substitutes' to include HCFCs. The draft amended standard will then be submitted to the Standards and Technical Committee of the Standards Council for a recommendation on approval of the draft standard; three days of training for the Jamaica Customs Officers: the first two days training were theoretical while the other was a practical session and included the use of the refrigerant identifier. A one day workshop was organized with Officers from the Ministry of Health, Trade Board , Ministry of Industry, Investment and Commerce on the HCFC quota system and Montreal Protocol in general. ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: completion of outstanding activities with balance from 2013 ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | No new obligation could be raised because of UMOJA ramp-down and black-out periods. New agreement with balance from first tranche to be discusssed in Jun-2015.
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | JAM | REF | 24 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-02-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | JAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening through creation of a National Ozone Unit | Individual | LAC | JAM | SEV | 20 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-05-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | JAM | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-01-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | JAM | SEV | 35 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-08-01 | 2004-10-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | JAM | SEV | 40 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-01-01 | 2007-01-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | JAM | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2008-02-01 |  | 2008-06-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | JAM | SEV | 55 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | JAM | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-11-01 |  | 2013-10-01 |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | Project completed. Last payment made in Oct-13. | Project completed.
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | JAM | SEV | 68 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-04-28 | 2014-12-01 | 2015-12-31 |  |  | 60000 | 0 | 60000 | 23744.22 | 39.57% | 36255.78 | 36256 | 24000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The final draft of the Ministerial Order under the Trade Act cited as the ‘Trade (Montreal Protocol) (Trade in Ozone Depleting Controlled Substances), Order 2014 was prepared by the Chief Parliamentary Counsel. The draft Order regulates importation of HCFCs, export of HCFCs and importation of equipment containing HCFCs; 2013 data on importation was reported to the Ozone Secretariat on time and the 2013 Progress on Country Programme implementation was reported to the Multilateral Fund Secretariat on time; celebrate ozone day 2014: An article titled, ‘Ozone layer protection, the mission goes on’ in keeping with the theme for the day, was written and published in The Daily Gleaner and Jamaica Observer, a total of 90X30 seconds radio commercials on the Montreal Protocol were aired on three radio stations, participation of Ozone Officer, refrigeration expert and standards expert in the sub-regional Thematic Workshop on Standards in Refrigeration and Air conditioning sector for the Caribbean-Panama City, October 2014; participation of NOO in the Joint Annual Meeting of the Ozonaction Networks of Latin America and the Caribbean, Dominican Republic, December 2014, and the Regional Meeting of the Caribbean Ozone Officers Network, Suriname, April 2014, the Workshop on hydro-fluorocarbons (HFC) Management , and the 34th OEWG, Paris July 2014. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First financial authorization in Jun-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Amendment of SSFA before expiration in Mar-2015 to allow completion of activities. Amendment signed in Apr-2015. Financial authorization processed in Apr-2015. Renewal request under prepartion and to be submitted to 75 ExCom.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | KAM | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-09-01 | 2008-01-01 | 15000 | -11 | 14989 | 14989 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-year | ASP | KAM | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2009-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KAM | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-07-01 | 2011-07-01 | 125000 | -3750 | 121250 | 121250 | 100% | 0 |  |  | 16250 | -488 | 15762 | 0 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
COM | UNEP | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | ASP | KAM | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2019-12-01 |  | 2013-12-01 |  | 150000 | 0 | 150000 | 144211 | 96.14% | 5789 |  | 7405 | 19500 | 0 | 18747 | 753 | 0 | Project completed. Only financial report pending to close this project. | Project completed. Only financial report pending to close this project.
ONG | UNEP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | KAM | PHA | 70 | TAS | 26 | A | I |  | 0.9 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2016-07-01 | 2016-07-01 |  |  | 100000 | 0 | 100000 | 45200 | 45.2% | 54800 |  | 54800 | 13000 | 0 | 0 | 13000 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented since 2013 and continued in 2014. NOU conducted monthly spot check of the retailers, import companies and service workshops located in Phnom Penh and quarterly for those located in the provinces. The Customs Handbook has been translated into local (Khmer) language and is under reviewing. NOU initiated the discussion with the General Department of Customs and Excise on how to put training courses on the Montreal Protocol in place, but there was no conclusion reached. In 2014, workshops for enforcement officers were held on 26-27 Feb. 2014 at Battambang Province with 32 participants and on 24-25 June 2014 at Kampong Cham province with 35 participants. In total, about 170 enforcement officers were trained from 5 workshops organized since the implementation of Cambodia HPMP. For RAC technicians training, NOU organized 2 training workshops, i.e. on 19-20 March 2014 at Kampong Cham province with 32 participants and on 25-26 November 2014 in Phnom Penh with 36 participants. In total, about 193 RAC Technicians were trained from 6 workshops organized since the implementation of Cambodia HPMP. UNEP training manual has been translated and distributed to the vocational training schools and RAC technicians attended the training. Round table discussion with National TV Channel on the implementation HPMP was conducted on 12 September 2014 and rebroadcasted on 15, 16 and 17 September 2014. Legal arrangements (actual/planned): The SSFA was signed in March 2014. First Mission: Feb 2014. TOR completed: N/A First disbursement date: March 2014. All funds disbursed (yes/no): No, the last funds will be released by Dec 2016. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Training workshops of enforcement officers and RAC technicians are planned in 2015. It is planned that 500 Customs handbooks in local language will be publicized in 2015. NOU is discussing with the Department of Customs and Excise to include training on the Montreal Protocol in place. NOU have discussed with some of vocational training school on how to enforce the certification requirement of RAC technician and to recruit more centers in specific provinces and the standard testing procedure have in place. 2014 CP data was submitted online.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | KAM | PHA | 73 | TAS | 29 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-05-01 | 2015-11-30 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Newly approved project at the 73rd Meeting in November 2014. After the ExCom approval, UNEP coordinated with the government to discuss feasible options to conduct the verification of HCFCs consumption as per the country context. Several options were explored and the government was in the process of deciding the best option. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned): N/A. Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): No. Any ongoing problems (yes/no): No. | Discussion with the government has been made to conduct the verification of HCFC consumption. Given that the third tranche of Cambodia HPMP is scheduled in the first meeting in 2016 and there was no HCFC verification submitted to the ExCom, it was agreed with the government that the verification of HCFC consumption will cover CY 2013, 2014 and 2015. It was agreed that private independent auditor will be contracted to undertake the assignment. Contract with the consultant will be made through UNDP Cambodia or through UNEP directly.
FIN | UNEP | Implementation of the RMP: implementation support and monitoring | Individual | ASP | KAM | REF | 41 | TAS | 08 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: refrigeration and air-conditioning technicians training programme | Individual | ASP | KAM | REF | 41 | TRA | 06 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-03-01 | 130000 | -54 | 129946 | 129946 | 100% | 0 |  |  | 16900 | -7 | 16893 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | KAM | REF | 41 | TRA | 07 | A | I | CFC | 7.6 | 7.6 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-03-01 | 85000 | -199 | 84801 | 84801 | 100% | 0 |  |  | 11050 | -26 | 11024 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | ASP | KAM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2005-01-01 | 60000 | -433 | 59567 | 59567 | 100% | 0 |  |  | 7800 | -56 | 7744 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | KAM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | KAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-01-01 | 2006-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | KAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KAM | SEV | 53 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-10-01 | 2010-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | KAM | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 61028 | 51639 | 112667 | 112667 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI:12/2011-11/2013) | Individual | ASP | KAM | SEV | 64 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase VII:1/2014-12/2015) | Individual | ASP | KAM | SEV | 70 | INS | 27 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-12-01 | 2015-12-01 |  |  | 112667 | 0 | 112667 | 56333.5 | 50% | 56333.5 |  | 56333.5 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. Meeting with importers on the strengthening of the implementation of the licensing system was held in Jan 2014, July 2014 and with service workshops in October 2014. The NOU conducted iPIC that, allowed Cambodia to confirm the imports/exports prior to the approval of the import permits. According to Cambodia licensing system, HCFCs and RAC equipment import and export were licensed from the NOU. NOU also kept constant communication with the agencies at check points to combat illegal trade. NOU maintained records of imports and made regular checks with the Department Customs and Excise to verify and reconcile the import figures. The 2013 Article 7 data report and Country Programme Implementation progress report were prepared and submitted to the Ozone Secretariat (June 2014) and Multilateral Fund Secretariat (April 2014) respectively. The Steering Committee meeting was organized in March 2014 to discuss the lesson learned from the implementation of HPMP first tranche and to dicsuss incentive and disincentive on control the import of the HCFCs based equipment. International Ozone Day celebration was organized on 16 September 2014 in Phnom Penh and the statement of Prime Minister was broadcasted on 15, 16 September 2014 on TV Channels. Awareness meeting with Kampong Chamber was organized in June 2014 to educate the stakeholders to understand on the importance of the ozone layer protection, and what have been done for the implementation of Montreal Protocol in Cambodia. L | The licensing and quota system and iPIC are being implemented in 2015. NOU keeps close communication with the Department of Customs and Excise during the shipment clearance and to monitor the import statistics of ODS. 2014 Country Programme has been timely reported.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | KEN | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9392 | 15608 | 15608 | 100% | 0 | 0 |  | 3250 | -1221 | 2029 | 0 | 0
FIN | UNEP | Support to a national workshop on refrigeration | Individual | AFR | KEN | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 2001-07-01 | 2001-07-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Policy and technical assistance | Individual | AFR | KEN | SEV | 37 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2005-12-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 52 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase VI) | Individual | AFR | KEN | SEV | 55 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-06-01 |  | 2010-12-01 | 2011-12-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | KEN | SEV | 58 | INS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 107431 | 0 | 107431 | 107431 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | KEN | SEV | 62 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 |  | 2013-08-01 | 2014-12-01 | 151667 | 0 | 151667 | 151667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of institutional strengthening project (phase IX: 4/2013-3/2015) | Individual | AFR | KEN | SEV | 69 | INS | 54 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-02-01 | 2015-03-01 | 2015-12-01 |  |  | 151667 | 0 | 151667 | 37800 | 24.92% | 113867 | 0 | 151667 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU conducted a one day sensitization and consultation workshop on ODS control measures for regulatory agencies. NOU conducted visits to monitor border posts to check on any illegal importation of ODS with a view to tightening enforcement. NOU conducted three Refrigeration training workshops on safe use of hydrocarbons and a total 85 technicians were trained. Kenya Refrigeration Association formed and registered as “Association of Heating Refrigeration and Air-Conditioning Engineers- Kenya”. The NOU commemorated the International Ozone Day and engaged students on painting competition, distributed posters. NOU collected, compiled and submitted 2013 Article 7 data and Country programme report.. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in December 2013 . Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The 1st disbursement ($37,800) was made in Feb 2014, the 2nd payment ($38,100) was made in September 2014, and the 3rd disbursement ($37967) was made in March 2015. _ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | The NOU collected and reported the 2014 data on ODS imports and consumption to both Ozone Secretariat and Multilateral Fund Secretariat
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Kiribati) | Multi-Year | ASP | KIR | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-12-01 |  |  | 53250 | 0 | 53250 | 51829 | 97.33% | 1421 |  | 1421 | 6923 | 0 | 4853 | 2070 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. The Customs Office has upgraded its HS code to 2012 HS code since April 2014. Requirement for storage and handling of HCFCs has been put in place. However, the standard/requirement for handling HCFCs was being developed by Sub-committee established under the National Ozone Committee, which would be submitted to the Parliament for approval to fully enforce this permit system. NOU and the Office of Attorney General worked to amend specific sections of regulation related to restricted goods to include the HCFC based products. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The Sub-committee for Establishment of RAC Association was established and the NOU has worked closely with the Office of Attorney General to finalize the TOR for RAC Association. A refresher training workshop for RAC technicians was organized in April 2014 with 28 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in August 2011. First Mission: August 2014 TOR completed: N/A First disbursement date: October 2011 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Reasons for delay is due to national institutional procedures for obtaining required approvals. UNEP CAP conducted mission in August of 2014, to meet with high level officials on the status of project impletation and seeking to find mechanisms for expediting implementation. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Training New NOU in the HPMP management including reporting requirements (progress and financial report).
FIN | UNEP | Country programme preparation | Individual | ASP | KIR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | KIR | SEV | 36 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | KIR | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-01-01 | 2007-03-01 |  | 2008-12-01 | 2009-12-01 | 7666 | 0 | 7666 | 7666 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | KIR | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-02-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | KIR | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | KIR | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | KIR | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-11-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 |  | 45000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: NOU worked with national fishing sector and the Paficfic islands fisheries forum to access the use of ODS in nationally registered fishing and international shipping vessels; ; and data reporting to the Fund and Ozone Secretariats. Brief progress report (actual/planned). Country is working with the Kiribiti Institute of Technology (KIT) for the development of a RAC servicing module to be offered by the KIT college. 2014 completed iPIC, 2015 in development and training on the use of the iPIC. The NOO organize and facilitate regular meetings with the servicing sectors. Ongoing awareness raising and targeting the RAC servicing sector. Ongoing discussion with the Ministry of Finance also due to high cost of energy already the sector in purchasing more energy efficient alternatives, NOU prepared and timely submitted the required reports for the HPMP stage 1 tranche 2 submission deadlines of the the 74th Ex. Com. 2013 data reporting to the Fund and Ozone Secretariats submitted. 2014 CP data submitted and on line. NOU attended PIC 2014 regional workshops on Tonga and Fiji and also attend the MOP 26th. Legal Arrangement: Agreement (SSFA) signed in August 2014. First disbursement date: Nov 2014. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Reasons for delay is due to national institutional procedures for obtaining required approvals. UNEP CAP conducted mission in August of 2014, to meet with high level officials on the status of project impletation and seeking to find mechanisms for expediting implementation. If Yes, will delay have impact on project completion date (yes/no) No. Any ongoing problems (yes/no): No. Country sustained its complinace obligations with the Montreal Protocol. | New NOO appointed in March of 2015. 2014 country programme timely submitted on line in 2015.
TRF | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | ASP | KUW | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2008-11-01 |  | 2014-12-01 |  | 240000 | -238243 | 1757 | 1757 | 100% | 0 |  | 18243 | 31200 | -30971.59 | 228 | 0.41 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KUW | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-12-01 | 2014-05-14 | 125000 | -16223 | 108777 | 108777 | 100% | 0 |  |  | 16250 | -2109 | 14141 | 0 | 0 | Project financialy Completed | Project financialy Completed
FIN | UNEP | TPMP verification | Individual | ASP | KUW | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2014-11-01 | 2014-11-14 | 20000 | -20000 | 0 | 0 |  | 0 |  |  | 2600 | -2600 | 0 | 0 | 0 | Project Completed, Verification of TPMP of Kuwait is merged with HPMP 1st tranche verification since TPMP funds relocated to HPMP as per decision 66/47 | Project Completed, Verification of TPMP of Kuwait is merged with HPMP 1st tranche verification since TPMP funds relocated to HPMP as per decision 66/47 |  | 2012-07-01 |  |  | Continued Monitoring
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | Multi-Year | ASP | KUW | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 | 2015-12-01 |  |  | 277000 | 0 | 277000 | 161860 | 58.43% | 115140 |  | 115140 | 33126 | 0 | 0 | 33126 | 0 | Brief progress report (actual/planned): - Country contract concluded and signed end of 2014 along with revised work-plan to accommodate delay in start - Standards and Certification Committees started work in 2014 and draft work-plan is made by both committees - National Ozone Committee started to draft the bylaws and procedures to enforce the new ODS legislation which is part of Kuwait new Environment Law 42/2014 - Customs Authority and NOU prepared training plan for train customs and trade authorities during 2015 - UNEP/UNIDO and country started to prepare the 2nd tranche of the HPMP for submission to the 74th ExCom • Legal arrangements(actual/planned): - Signed end of 2014 • First mission (actual/planned): UNEP conducted one mission in 2014 • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): To be made in 2015 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract, country contract signed end of 2014 • If Yes, will delay have impact on project completion date (yes/no): Yes, 2nd tranche delayed by one year • Any ongoing problems (yes/no): No • If Yes, is any action required by ExCom: No | # First payment of the country country contract is disbursed # National workshop on the enforcement of the new ODS legislation is organized (March 2015), and attended b y UNEP/UNIDO, for all governmental authorities # National committees and working teams started functioning expedite # UNEP/UNIDO and NOU prepared and submitted, to ExCom-74, the 2nd tranche of the HPMP of Kuwait which is approved. # Complete the verification report for the submission of the 2nd tranche # UNEP/UNIDO conducted one mission to country and met with different stakeholders i.e. Customs, standards, Certification Authority, foam industry and National Ozone Committee to agree on the revised work-plan for the HPMP implementation including activities under 2nd tranche which will overlap with 1st tranche activities. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | KUW | REF | 37 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2005-12-01 | 2005-08-01 |  | 2009-12-01 | 2010-12-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 |  |  | 3510 | 0 | 3510 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers in monitoring of ODS | Individual | ASP | KUW | REF | 37 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2004-01-01 |  | 2004-12-01 | 2006-12-01 | 53445 | 0 | 53445 | 53445 | 100% | 0 |  |  | 6948 | 0 | 6948 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme on good refrigerant management practices and hydrocarbon (HC) refrigerants safe handling | Individual | ASP | KUW | REF | 37 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-09-01 | 2004-08-01 |  | 2011-12-01 | 2014-11-14 | 95325 | -8962 | 86363 | 86363 | 100% | 0 |  |  | 12392 | -1165 | 11227 | 0 | 0 | Project financialy Completed | Project financialy Completed
FIN | UNEP | Preparation of country programme | Individual | ASP | KUW | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-06-01 |  | 2002-07-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening and capacity building | Individual | ASP | KUW | SEV | 37 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-03-01 | 2005-08-01 |  | 2006-01-01 | 2008-12-01 | 121520 | 0 | 121520 | 121520 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | KUW | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | KUW | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KUW | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 57048 | 48272 | 105320 | 105320 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | ASP | KUW | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-11-01 | 2014-11-01 | 2015-12-15 |  |  | 105320 | 0 | 105320 | 60000 | 56.97% | 45320 | 0 | 45320 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Over 2013 there was a gap in implementation due to lack of officially assigned ODS Officer, although the NOU continued to operate through a consultant, therefore remaining active during international and regional meetings. Over 2014 the National Focal Point & ODS Officer were officially nominated and remained active in related meetings, particularly concerning HCFC low GWP alternatives in high-ambient countries. E-licensing received approval to start establishing system from high level officers of EPA and is under process. Quota system is enforced in 2014. NOU organized a regional event on district cooling in cooperation with Kuwait University, ASHRAE, UNEP & UNIDO. The Kuwait Environment Law no. 54/2014 was issued in July-2014, with dedicated articles on control of ODS. The National Ozone Committee (NOC) & NOU discussed and proposed legal content on ODS control under the Kuwait Environment Law. Legal arrangements (actual/planned): Agreement signed in Feb-2014 with one disbursement. SSFA with UNEP extends implementation period over 2015. Initial stages of project implementation (actual/planned): Delayed over official nomination of NOU & due to internal changes in management of EPA of Kuwait. Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for the year of 2013. Project completion and follow up: Project is being implemented and is expected to complete with by end 2015. First disbursement date (actual/planned): First payment of $60,000 disbursed in Nov-2014. All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay was due to changes at the EPA of Kuwait. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | NOU and UNEP finalized the proposal for the 2nd tranche of the HPMP and the verification report including compiling and verifying data of importation with different authorities. NOU worked with UNEP to adjust the work-plan of the HPMP and its time frame of implementation. NOU worked with the national ozone committee to establish local technical committees for Standards and Certification programs under the HPMP. NOU also concluded work-plan with the customs authority of Kuwait to start 3-years training program on the control of HCFC and combat illegal trade. NOU started the process to strategically restructure the Ozone Unit under EPA of Kuwait to accommodate work-load of implementing HPMP and advanced phase-out commitments under HPMP in the upcoming years.
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | KYR | PHA | 50 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-07-01 | 2009-07-01 | 142600 | 0 | 142600 | 142600 | 100% | 0 | 0 |  | 18538 | 0 | 18538 | 0 | 0
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | KYR | PHA | 55 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-02-01 | 2011-12-01 | 65100 | 0 | 65100 | 65100 | 100% | 0 | 0 |  | 8463 | 0 | 8463 | 0 | 0
FIN | UNEP | TPMP verification report | Individual | EUR | KYR | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | KYR | PHA | 60 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-04-01 | 2011-07-01 | 25300 | 0 | 25300 | 25300 | 100% | 0 | 0 |  | 3289 | 0 | 3289 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | KYR | PHA | 63 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-12-01 |  | 2014-05-01 |  | 31680 | 0 | 31680 | 31680 | 100% | 0 | 0 | 0 | 4118 | 0 | 4118 | 0 | 0 | Financially completed. | Financially completed.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | KYR | PHA | 72 | PRP | 31 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-03-01 | 2015-05-01 | 2015-05-01 |  |  | 10000 |  | 10000 | 9552.68 | 95.53% | 447.32 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | Brief progress report (actual/planned): The NOU has started the survey on: 1. Country’s policy and legislation relevant to HCFCs phase out and propose the new supporting policy and legislative measures according to the MP schedule for phase out of HCFCs. 2. Overview and activities regarding the training and certification of refrigeration technicians. 3. Overview and propose activities regarding the training programme for customs and other enforcement officers including environment inspectors. 4. The current situation for safe handling of refrigerants, containment, recovery and recycling and reuse of recovered refrigerants in Kyrgyzstan. 5. Review needs on additional actions for introduction of low GWP alternatives to HCFCs into the country in terms of safety/application standards, training, economic incentives Legal arrangements (actual/planned): The SSFA was signed in November of 2014. Initial stages of project implementation (actual/planned): The project is ongoing Intermediate goals achieved (actual/planned): The Ozone Center has initiated activities required for preparation of the HPMP stage 2 as planned Project completion and follow up: Project ongoing First Disbursement date (actual/planned): The first payment was released in November of 2014 as planned. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): HPMP stage II was drafted by the NOU, UNDP and UNEP in accordance with the format of the Executive Committee of the Multilateral Fund of the Montreal Protocol on the basis of analysis of current consumption of ozone-depleting substances by various industries and sectors of the country. The draft was available early January of 2015. The Kyrgyz Republic has developed the HCFC Phase out Management Plan (stage 2) taking into account the requirements of the Customs Union and the Eurasian Economic Community on the consumption of HCFCs for total phase out of HCFCs by 2020 similar to other parties of the Eurasian Economic Community. The stakeholder’s consultation meeting was organized on 10-12 February of 2015. UNDP and UNEP participated and assisted in finalizing the document. The HPMP stage 2 draft was finalized on time and sent to MLFS. After the comments and inputs from MLFS, the project was put forward at ExCom-74. The project is approved by ExCom held on 18-22 May, 2015 in Montreal, Canada. Legal arrangements (actual/planned): The SSFA was signed in in November of 2014. Initial stages of project implementation (actual/planned):All activities are implemented on time Intermediate goals achieved (actual/planned): The HPMP stage 2 developed and approved Project completion and follow up: Project completed First Disbursement date (actual/planned): The first payment was released in in November of 2014 as planned. The second and last payment was released in April of 2015. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | KYR | PHA | 72 | TAS | 32 | A | I | HCFC-22 | 0.16 |  |  |  | 2014-05-01 | 2014-07-01 | 2015-05-01 | 2015-05-01 |  |  | 3520 |  | 3520 | 3520 | 100% | 0 | 0 | 0 | 458 | 0 | 0 | 458 | 0 | Brief progress report (actual/planned): The NOU continued the training programme on the good practices in refrigeration including the recovery and recycling and development of capacity of refrigeration technicians for handling and right management of the recycled refrigerants and those for final disposal. Two training workshops were held for refrigeration specialists: Cholpon-Ata city, 24-25.10. 2014 (34 participants) Osh city, 18-19.11.2014 (38 participants). During the two-day workshops, participants learned about the country's legal framework for the protection of the ozone layer and measures for its restoration, implementation of the Kyrgyz Republic’s obligations to reduce ODS (ozone depleting substances) under the Montreal Protocol. The best methods of cooling equipment and servicing of HVAC equipment, the main alternatives to HCFCs were considered. The NOU supported the organization of the annual meeting of the Refrigeration Association in 2014. The Eighth National Congress "Ecoholod" Republican Public Association was held in Bosteri. The Congress was attended by 42 experts on 15-16 October 2014. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the country and UNEP in July of 2014 (as planned). First mission (actual/planned): N/A – NOU implements all activities at the national level without involvement of international experts. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in August of 2014 (as planned) All funds disbursed (yes/no): Yes, all funds were disbursed Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The last payment was released in January 2015 as all activities were finalized in 2014. All activities are completed. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the country and UNEP in July of 2014 (as planned). First mission (actual/planned): N/A – NOU implements all activities at the national level without involvement of international experts. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in July of 2014 (as planned) All funds disbursed (yes/no): Yes, all funds were disbursed Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
FIN | UNEP | Implementation of the RMP: training for customs excise and personnel involved in the monitoring of ODS/equipment | Individual | EUR | KYR | REF | 37 | TRA | 03 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2005-06-01 | 2009-06-01 | 74910 | 0 | 74910 | 74910 | 100% | 0 | 0 |  | 9738 | 0 | 9738 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | EUR | KYR | REF | 37 | TRA | 06 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2003-08-01 |  | 2005-08-01 | 2009-08-01 | 97900 | 0 | 97900 | 97900 | 100% | 0 | 0 |  | 12727 | 0 | 12727 | 0 | 0
FIN | UNEP | Country programme | Individual | EUR | KYR | SEV | 37 | CPG | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2002-07-01 |  | 2002-07-01 | 2002-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | KYR | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2005-08-01 |  | 2004-12-01 | 2011-03-01 | 133650 | 0 | 133650 | 133650 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | EUR | KYR | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | KYR | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | KYR | SEV | 55 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-01-01 |  | 2010-07-01 | 2011-07-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | KYR | SEV | 61 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-13 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financially completed. | Financially completed.
COM | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | EUR | KYR | SEV | 68 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2014-12-01 |  | 2014-12-14 |  | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The Ozone Centre has initiated the CP and Article 7 data collection. CP and Article 7 data was submitted to MLFS and OS on time. Organized regular Steering Committee meetings in 2014. The Committee heard the annual report on the activities of the Ozone Center. The Committee coordinated activities and approves long-term plans of action. At the last meeting, 18 representatives of ministries and departments as members of the commission participate in the work. The NOU supported on 15-16 March, 2014, the eighth national Congress of the Republican Public Association «Ecoholod» in Bosteri village. The meeting was attended by 42 experts. The staff of Ozone Center and RCYCECT carried out an information campaign "Protect yourself from the sun" on 7-12 July, 2014, in the Issyk-Kul region, Kyrgyzstan. In 2014, the NOU produced: 1. Poster "Potential negative effects of solar UV radiation on human health", in Russian and Kyrgyz languages, 1000 PCs. 2. Poster "Line of behaviors for the sustainable development of society", in Russian and Kyrgyz languages, 1000 PCs. 3. Poster "Necessary habits each day at work" in Russian and Kyrgyz languages, 500 PCs. 4 Pocket Book "Stand up to protect the ozone layer", in Russian, 500 PCs. and Comics "Ozzy Ozone", in Russian, 500 PCs. Legal arrangements (actual/planned): The SSFA was signed in January of 2013. Initial stages of project implementation (actual/planned): All activities were initiated on time as planned. Intermediate goals achieved (actual/planned): The CP and Article 7 data were collected and submitted on time. Steering Committee meetings were organized. Ozone Day was celebrated. Public awareness campaign was carried out. Project completion and follow up: Project completed First disbursement date (actual/planned): The first payment was released in February of 2013. The last payment was released in August 2014. All funds disbursed (yes/no): YES Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | EUR | KYR | SEV | 73 | INS | 33 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 115830 |  | 115830 | 0 | 0% | 115830 | 115830 | 57915 | 0 | 0 | 0 | 0 | 0 | Approved in November of 2014. | Brief progress report (actual/planned): The NOU in cooperation with UNDP and UNEP has developed HPMP stage 2. The project has been approved by ExCom-74. The NOU has initiated the CP and Article 7 data collection. CP data was submitted to MLFS on time. Article 7 data will be provided also on time before 30 June of 2015. The NOU has initiated the work to update ODS legislation since the country declared to join the Eurasian Union (Belarus, Russian Federation and Kazakhstan). Legal arrangements (actual/planned): The SSFA was signed in January of 2015. Initial stages of project implementation (actual/planned): The project is ongoing Intermediate goals achieved (actual/planned): The Ozone Center has initiated the collection of data for A7 and CP reporting for the year of 2014 as planned Project completion and follow up: Project ongoing First Disbursement date (actual/planned): The first payment was released in March of 2015. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
FIN | UNEP | Regional workshop on methyl bromide for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Regional training workshop on policy development | Individual | LAC | LAC | FUM | 27 | TRA | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-03-01 |  | 2000-04-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | LAC | LAC | FUM | 27 | TRA | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-12-01 | 80000 | -4000 | 76000 | 76000 | 100% | 0 | 0 |  | 10400 | -520 | 9880 | 0 | 0
CLO | UNEP | Development of regional halon banking management plan for the Latin American region (Dominican Republic, El Salvador, Chile, Colombia and Peru) | Individual | LAC | LAC | HAL | 29 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2001-06-01 |  |  | 2002-07-01 | 174000 | -174000 | 0 | 0 |  | 0 | 0 | 0 | 22620 | -22620 | 0 | 0 | 0
FIN | UNEP | Regional workshop on non-CFC technologies for domestic refrigerator manufacturing industries | Individual | LAC | LAC | REF | 15 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-05-01 |  | 1995-05-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Regional workshop on technology assessment (in refrigeration) | Individual | LAC | LAC | REF | 16 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-01-01 | 1996-03-01 |  | 1999-05-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Regional workshop for Latin America and the Caribbean | Individual | LAC | LAC | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-05-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 |  | 31980 | 0 | 31980 | 0 | 0
FIN | UNEP | Support to regional network for OzonAction/ODS focal points | Individual | LAC | LAC | SEV | 09 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-03-01 | 2000-12-01 | 130000 | -9000 | 121000 | 121000 | 100% | 0 | 0 |  | 16900 | -1170 | 15730 | 0 | 0
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1994) | Individual | LAC | LAC | SEV | 12 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1995-03-01 | 2000-12-01 | 224000 | -14500 | 209500 | 209500 | 100% | 0 | 0 |  | 29120 | -1885 | 27235 | 0 | 0
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1995) | Individual | LAC | LAC | SEV | 16 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-05-01 | 1996-03-01 |  | 1995-08-01 | 2000-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 |  | 38870 | 0 | 38870 | 0 | 0
FIN | UNEP | Networking and Training in Latin American Region Network (including English-speaking Caribbean) | Individual | LAC | LAC | SEV | 19 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299000 | -57167 | 241833 | 241833 | 100% | 0 | 0 |  | 38870 | -7431.71 | 31438 | 0.29 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for Latin America and Caribbean | Individual | LAC | LAC | SEV | 19 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-04-01 | 1999-04-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 |  | 13650 | 0 | 13650 | 0 | 0
FIN | UNEP | Latin American Region Network (1997) | Individual | LAC | LAC | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 380000 | -38093 | 341907 | 341907 | 100% | 0 | 0 |  | 49400 | -4952 | 44448 | 0 | 0
FIN | UNEP | Latin America Region Networks for LAC South, LAC Central, and Caribbean (1998) | Individual | LAC | LAC | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 399000 | -53324 | 345676 | 345676 | 100% | 0 | 0 |  | 51870 | -6932 | 44938 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for the Caribbean region | Individual | LAC | LAC | SEV | 23 | TRA | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-11-01 |  | 1998-06-01 | 1999-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Latin America Region Network (South America, Central America and the Caribbean) | Individual | LAC | LAC | SEV | 26 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-12-01 | 2000-12-01 | 399000 | -55099 | 343901 | 343901 | 100% | 0 | 0 |  | 51870 | -7163 | 44707 | 0 | 0
FIN | UNEP | Latin America and the Caribbean regional networks (South America, Central America, Caribbean) (2000) | Individual | LAC | LAC | SEV | 29 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 418950 | -30000 | 388950 | 388950 | 100% | 0 | 0 |  | 54464 | -3900 | 50564 | 0 | 0
FIN | UNEP | South American, Central American and the Caribbean regional networks (2001) | Individual | LAC | LAC | SEV | 32 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 429000 | -17257 | 411743 | 411743 | 100% | 0 | 0 |  | 55770 | -2243 | 53527 | 0 | 0
COM | UNEP | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-02-01 | 2008-03-01 |  | 2011-02-01 |  | 80000 | -4109 | 75891 | 75891.07 | 100% | -0.07 | 0 | 0 | 10400 | -534 | 9866 | 0 | 0 |  |  |  | 2009-10-01
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | LAO | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-01-01 | 2012-01-01 | 150000 | -15089 | 134911 | 134911 | 100% | 0 |  |  | 19500 | -1962 | 15718 | 1820 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | LAO | PHA | 63 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-12-01 |  |  | 113625 | 0 | 113625 | 83199 | 73.22% | 30426 |  | 30426 | 14771 | 0 | 7451 | 7320 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented in 2014 for the first year. PCD and the customs officers have jointly inspected type of refrigerant for all shipments to ensure that refrigerant being imported is the same as those allowed by the government. RAC technicians training workshop was organized during 17-19 December 2014 in Champasack Province with 37 RAC technicians from servicing workshops trained. RAC Association was established in 2014. PCD and the training centers initiated the discussion with the RAC Association on its roles in the design and implementation of RAC technician certification system. PCD conducted one industry awareness workshops and develop dissemination tools for customs officers, importers and distributors of HCFCs and RAC equipment to raise awareness of licensing system and mandatory labelling requirement for HCFC cylinders. Legal arrangements (actual/planned): The SSFA has been signed in May 2012. First Mission: June 2012. TOR completed: N/A First disbursement date: Oct 2011 All funds disbursed (yes/no): No, last disbursement will be on Dec 2015. Any delay? (yes/no): Yes. But it will not affect the country's compliance status. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Refresher train-the-trainer workshops of enforcement officers and RAC technicians are planned in 2015/2016. PCD will also collaborate with concerned ministries and the RAC Association to examine when the restriction to sale refrigerant to only certified technicians can be put in place. This includes the possible timeline for the mandatory requirement that only certified technicians will be allowed to handle or service RAC equipment. PCD will be working closely with RAC Association and the Ministry of Labour and Social Welfare regarding this activity. The NOU plans to conduct regular checks with retailers and servicing workshops to inspect whether HCFC containers are properly labelled as required. The second tranche was approved at the 74th ExCom meeting in May 2015. 2014 CP data was submitted online.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | LAO | PHA | 71 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-05-01 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): In close consultation with the Pollution Control Department (PCD) , joint effort was made to identify the potential private independent auditors that could be selected to perform the audit. However, as verification of HCFC consumption is different from the financial audit, it was impossible to identify the potential private companies that have proper qualification on both the Montreal Protocol and the auditing experience. As a result, the verification of HCFC consumption could not be conducted in 2014. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned):No. Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Difficult to identify the qualified private companies to conduct the verification. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. | In consultation with the Ministry of Natural Resource and Environment, the Inspection Department was identified to conduct the verification in light of the Excom Guidance. The draft DFMA between UNEP and Inspection Department is being finalized.
FIN | UNEP | Implementation of the RMP: monitoring the activities contained in the RMP | Individual | ASP | LAO | REF | 34 | TAS | 07 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-12-01 | 17500 | -12500 | 5000 | 5000 | 100% | 0 |  |  | 2275 | -1624.54 | 650 | 0.46 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | LAO | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-07-01 |  | 2001-07-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit for implementing the phase-out of ODS under the Montreal Protocol | Individual | ASP | LAO | SEV | 34 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-08-01 | 2006-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | LAO | SEV | 43 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | LAO | SEV | 50 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | LAO | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-11-01 |  | 2010-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | LAO | SEV | 61 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of the institutional strengthening project (phase VI: 12/2012-11/2014) | Individual | ASP | LAO | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-11-01 |  | 2014-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The Minister Decision on ODS Control has provided a solid foundation for PCD to strengthen the implementation of import/export licensing system, label HCFC cylinders, including report data and cross check data with the Customs Department in order to effectively control HCFCs. It also included explicit control on import, export or transit of all types of HFC and RAC equipment including HCFC-based equipment for which license must be issued by the Pollution Control Department (PCD). The Customs Department has updated its ASYCUDA system to include all types of ODSs as the restricted goods to facilitate risk profiling management. When HS code for ODS is entered into the system, the customs officer will be alerted of the need to have valid license issued by PCD in additional to the Customs’ requirements. NOU maintained records of imports and made regular checks with the Customs Department to verify and reconcile the import figures. The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. To celebrate international ozone day celebration, NOU provided information and broadcast through TV and radio from 13-17 September 2014. Project was completed in November 2014. Legal arrangements (actual/planned): The SSFA was signed in February 2013. Initial stages of project implementation (actual/planned): N/A. Intermediate goals achieved (actual/planned): Enforcement of the revised regulation including the HCFC import quota system scheduled to enter into force by 1 January 2013, coordinating the implementation of HPMP stage I, cooperation with the Ministry of Industry and Commerce and the Customs Department to ensure effective control of ODS consumption and prevent illegal trade, data reporting to the Fund and Ozone Secretariats. (as planned) First disbursement date: March 2013. All funds disbursed (yes/no): Yes Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Project was completed in November 2014.
ONG | UNEP | Renewal of the institutional strengthening project (phase VII: 12/2014-11/2016) | Individual | ASP | LAO | SEV | 72 | INS | 26 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-11-30 | 2016-11-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): UNEP coordinated with the government to prepare and finalize the SSFA, which was subsequently signed in December 2014. Legal arrangements (actual/planned): The SSFA has been signed in December 2014. Initial stages of project implementation (actual/planned): N/A since Project is ongoing. Intermediate goals achieved (actual/planned): Enforcement of the revised regulation including the HCFC import quota system, mandatory labeling requirement, coordinating the implementation of HPMP stage I, cooperation with the Ministry of Industry and Commerce and the Customs Department to ensure effective control of ODS consumption and prevent illegal trade, supporting the RAC Association for sustaining ODS phase-out, data reporting to the Fund and Ozone Secretariats. First disbursement in May 2015 All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The first payment has been made to the government in 2015. The licensing and quota system and iPIC are being implemented in 2015. The total quota of HCFCs for 2015 has been set according to the 10% reduction obligation under the MP. NOU keep close communication with the Customs Department during the shipment clearance and to monitor the import statistics of ODS. 2014 Country Programme has been timely reported.
FIN | UNEP | Country programme preparation | Individual | ASP | LEB | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-07-01 |  | 1996-05-01 | 1995-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | LES | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | LES | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1999-10-01 |  | 1999-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | LES | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-12-01 |  | 2005-04-01 | 2007-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LES | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LES | SEV | 53 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-05-01 | 2009-11-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | LES | SEV | 62 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | LES | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-07-01 | 2014-11-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU conducted a workshop jointly with the national Bureau of Statistics for HCFCs importers to enhance methods of data collection. The NOU conducted training for 30 refrigeration technicians on safe use of Hydrocarbon for the Southern region of Lesotho. The NOU participated in regional network and Montreal Protocol meetings. NOU celebrated the International ozone day, created awareness on ODS phase-out and distributed awareness materials (calendars, T-shirts, car stickers ) to the public. The NOU submitted 2013 ODS data and CP report. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in February 2013 as planned. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made in July 2013 . _ All funds disbursed (yes/no): YES_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Collection of the 2014 data on ODS imports and consumption is ongoing. Project completed and new IS phase was approved at the 73 Ex-com
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | AFR | LES | SEV | 73 | INS | 16 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and sent to the county for signing. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | LIR | PHA | 49 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | LIR | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 131500 | 0 | 131500 | 131500 | 100% | 0 | 0 |  | 17095 | 0 | 17095 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 81500 | -5000 | 76500 | 76500 | 100% | 0 | 0 |  | 10595 | -650 | 9945 | 0 | 0 | Project Completed
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | LIR | REF | 41 | TRA | 07 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-06-01 | 2008-12-01 | 40040 | -2389 | 37651 | 37651 | 100% | 0 | 0 |  | 5205 | -311 | 4894 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | LIR | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2000-07-01 |  | 2003-09-01 | 2008-12-01 | 50000 | -17000 | 33000 | 33000 | 100% | 0 | 0 |  | 6500 | -2210 | 4290 | 0 | 0 |  |  |  | 2003-12-01
FIN | UNEP | Establishment of the ozone unit | Individual | AFR | LIR | SEV | 41 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2007-12-01 | 127820 | 0 | 127820 | 127820 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | LIR | SEV | 51 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LIR | SEV | 57 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 |  | 2010-11-01 | 2011-11-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LIR | SEV | 63 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-10-01 | 2014-12-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2013-3/2015)) | Individual | AFR | LIR | SEV | 69 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 | 2015-12-01 |  |  | 85213 | 0 | 85213 | 46213 | 54.23% | 39000 | 0 | 58500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The country conducted a meeting to determine and allocate 68 metric tonnes of ODS to importers. The NOU conducted random inspection of storage facilities of ODS to ensure that advantage was not taken of the Ebola Crisis to illegally bring into the country contaminated or sub-standard refrigeration products and gases. Despite the Ebola Crisis which affected the country, the NOU carried out awareness programme on ODS phase-out and celebrated the Ozone Day and participated in Montreal Protocol meetings. The NOU compiled and submitted 2013 Article 7 data and CP report. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in February 2013 as planned. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):1st payment ($26,713) was disbursed in December 2013; and 2nd payment ($19,500) was disbursed in September 2014. T . _ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2014 data on ODS imports and consumption is ongoing.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAG | PHA | 49 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-07-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 133000 | 0 | 133000 | 133000 | 100% | 0 | 0 |  | 17290 | 0 | 17290 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAG | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-01-01 | 2011-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-03-01 | 2011-07-01 | 87000 | 0 | 87000 | 87000 | 100% | 0 | 0 |  | 11310 | 0 | 11310 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 8450 | 650 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MAG | PHA | 70 | TAS | 24 | A | I |  | 0.9 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 56000 | 70000 | 9100 | 0 | 0 | 9100 | 0 | Brief progress report (actual/planned): Three refrigeration workshops training of refrigeration technicians have been organized between November and December 2014 in Toamasina, Taolagnaro and Antsirabe: 66 refrigeration technicians trained. Two workshops training for customs officers have been organized between November and December 2014 in Toamasina, Taolagnaro: 30 customs trained. Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned) not yet___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ __ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Organisation of a survey on HCFC consumption in February 2015. One refrigeration workshop on HCFCs alternatives for 30 refrigeration technicians organized in March 2015. A conference on HCFCs alternatives organized during environment day.
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | AFR | MAG | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2005-12-01 |  | 2005-06-01 | 2007-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers and other officers to control and follow-up of ODS and its containers | Individual | AFR | MAG | REF | 47 | TRA | 10 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of maintenance technicians including small craftsmen of informal sector | Individual | AFR | MAG | REF | 47 | TRA | 11 | A | I | CFC | 4.2 | 4.2 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Creation of a Ozone Unit | Individual | AFR | MAG | SEV | 29 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2004-07-01 | 2007-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MAG | SEV | 43 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2008-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | MAG | SEV | 49 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-07-01 | 2008-06-01 |  | 2009-06-01 | 2010-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAG | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-07-01 | 2013-12-01 | 32879 | 27821 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | AFR | MAG | SEV | 67 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2015-12-01 |  |  | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013. Ozone day was celebrated .Country sent a Final progress report to allow UNEP to renew the IS. Coordination of Three refrigeration workshops training of refrigeration technicians and two workshops training for customs officer. L egal arrangements (actual/planned): Agreement signed in October 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in October 2012 __ All funds disbursed (yes/no): _ Final payment done in June 2013_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Report of the 2014 data reports and organisation of a national survey of HCFC consumption. Organisation of two meetings of the steering committee.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2014-11/2016) | Individual | AFR | MAG | SEV | 73 | INS | 25 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 60700 |  | 60700 | 0 | 0% | 60700 | -5.8265e-13 | 33350 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Country contacted. Discussions with the country on activities and date of implementation.
FIN | UNEP | Support to a sub-regional workshop on halon and halon bank management | Individual | ASP | MAL | HAL | 09 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-01-01 | 1994-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Complement for country programme preparation | Individual | AFR | MAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-06-01 |  | 1993-06-01 | 1993-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ozone depleting substances | Individual | AFR | MAR | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-08-01 | 1996-06-01 |  | 2004-12-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | MAR | SEV | 45 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-04-01 |  | 2007-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2012-03-01 | 2009-11-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU procurred and distributed awareness materials (brochures, rulers, pens, caps, t-shirt). Collected 2013 data and reported to OS and MFS.The country celebrated Ozone Day through ozone competition for primary and secondary schools, drama and poems and hosted SIDS workshop for customs officers back to back with the Ozone Day Celebrations. NOU monitored implementation of HPMP activities inline with the action plan. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in May 2011. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made in June 201._ All funds disbursed (yes/no): YES_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project completed and new phase was approved at Ex-com 73. SSFA has been drafted awaiting signing by the country
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2015-12/2016) | Individual | AFR | MAR | SEV | 73 | INS | 23 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 |  | 0% | 60000 |  | 15000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA not yet signed. UNEP continues negotiations with county and expects signature by September 2015. Country collected data and reported 2014 CP and A7 to MLFs and OS.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Marshall Islands) | Multi-year | ASP | MAS | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-12-01 |  |  | 54000 | 0 | 54000 | 45603 | 84.45% | 8397 |  | 8397 | 7020 | 0 | 5203 | 1817 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. However, Marshall Islands has not yet adopted the 2012 HS code. The Customs Act has been reviewed for amendments and 2012 HS code has been considered as priority the country. It is expected that the RMI Customs would adopt the 2012 HS code by the last quarter of 2015. A permit system for importers or businesses entity that sale ODS in the regulation has been put in place. A permit system for handling ODS has not been established and would be enforced after the establishment of RAC Association. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The establishment of RAC Association was on-going. RAC servicing tools equipment/tools have not yet distributed to RAC technicians due to the need to finalize the legal agreement for distributing equipment and it would link with RAC Association. The recovery machines have been disseminated to technicians who made the application to NOU from time to time to follow the good practice. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in April 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Change in senior level management and no immediate replacement. UNEP maintained constant communication with interim senior management encouraging the early appointment of required staff. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: No | The refresher training of RAC technicians was organized during 17-20 February 2015 with 15 participants attending the training. Refresher training for enforcement officers was originally planned during the week of 23-27 February 2015. However, the refresher training was postponed. NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online.
FIN | UNEP | Country programme preparation | Individual | ASP | MAS | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 |  |  | 5200 | -3250 | 1950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | MAS | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-08-01 | 2009-12-01 | 34000 | -822 | 33178 | 33178 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | MAS | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-02-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | MAS | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | MAS | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | MAS | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | MAS | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-07-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 |  | 45000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: NOU prepared and provided to required reports for the HPMP Stage 1 Tranche 2 submission as planned for the Ex. Com 74. 2013 CP and Article 7 data timely submitted, country sustained compliance. NOU attended regional network meeting in Tonga and Fiji (2014) Country timely submitted CP 2014 data on line. NOU prepared the required HPMP progress reports to allow for submission as part of the PIC regional HPMP sumbitted at the Ex. Com 74. Legal arrangements: Legal Document signed on the May 2014 Initial stages of project implementation (actualplanned): N/A. Intermediate goals achieved (actual): Strengthen the capacity of customs officers for the enforcement of the licensing and quota system on ODS import/export control, and to more effectively engage the national stakeholders for the implementation of the other HPMP activities; and data reporting to the Fund and Ozone Secretariats. First dsibursement date: July 2014 All funds disbursed (yes/no): No Any delay (yes/): Yes. If Yes, reasons for delay & action plan to resolve: Change in senior level management and no immediate replacement. UNEP maintained constant communication with interim senior management encouraging the early appointment of required staff . If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. If Yes, is any action required by ExCom: No. | 2014 country programme timely submitted on line in 2015. NOU vacated office in April of 2015. UNEP is working with Government to encourage early selection of new NOO and to provide for reduced disruption of implementation activities.
FIN | UNEP | Country programme preparation | Individual | EUR | MAT | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-06-01 |  | 1995-07-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAU | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MAU | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-03-01 | 2011-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAU | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2016-12-01 |  |  | 85000 | 0 | 85000 | 25000 | 29.41% | 60000 | 0 | 60000 | 11050 | 0 | 3250 | 7800 | 0 | All activities supended due to ongoing UN audit. | UN audit being finalised. CAP team in consultation with NOU started negotiating new contract in order to resume activites |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the submission of the HCFC phase-out management plan.
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2013-12-01 | 2014-12-01 | 59000 | -59000 | 0 | 0 |  | 0 | 0 |  | 7670 | -7670 | 0 | 0 | 0 | All activities supended due to ongoing UN audit. | UN audit being finalised. CAP team in consultation with NOU started negotiating new contract in order to resume activites
FIN | UNEP | Development of an RMP | Individual | AFR | MAU | REF | 33 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2003-12-01 |  | 2003-12-01 | 2011-03-01 | 60000 | -25000 | 35000 | 35000 | 100% | 0 | 0 |  | 7800 | -3250 | 4550 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | MAU | REF | 41 | TAS | 13 | A | I | CFC | 1.2 | 1.2 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -834 | 29166 | 29166 | 100% | 0 | 0 |  | 3900 | -108 | 3792 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs excise | Individual | AFR | MAU | REF | 41 | TRA | 09 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2007-12-01 | 2008-12-01 | 39800 | -1069 | 38731 | 38731 | 100% | 0 | 0 |  | 5174 | -139 | 5035 | 0 | 0
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians | Individual | AFR | MAU | REF | 41 | TRA | 10 | A | I | CFC | 2.6 | 2.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2005-07-01 |  | 2007-12-01 | 2011-03-01 | 65000 | -21716 | 43284 | 43284 | 100% | 0 | 0 |  | 8450 | -2823 | 5627 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | MAU | SEV | 33 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2004-01-01 | 2003-04-01 |  | 2004-01-01 | 2007-01-01 | 25900 | 0 | 25900 | 25900 | 100% | 0 | 0 |  | 3367 | 0 | 3367 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MAU | SEV | 43 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 33670 | 0 | 33670 | 33670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAU | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2008-06-01 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 59113 | 98.52% | 887 | 0 | 887.01 | 0 | 0 | 0 | 0 | 0 | All activities supended due to ongoing UN audit. | UN audit being finalised. CAP team in consultation with NOU started negotiating new contract in order to resume activites
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | MAU | SEV | 57 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 14.3 | 0.02383% | 59985.7 | 0 | 59986 | 0 | 0 | 0 | 0 | 0 | All activities supended due to ongoing UN audit. | UN audit being finalised. CAP team in consultation with NOU started negotiating new contract in order to resume activites |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | MDV | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-11-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MDV | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 85000 | -2971 | 82029 | 72029 | 87.81% | 10000 |  |  | 11050 | -386.23 | 9364 | 1299.77 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MDV | PHA | 58 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
COM | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 60 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2019-12-01 |  | 2013-12-01 |  | 355940 | 0 | 355940 | 355940 | 100% | 0 |  | 0 | 46272 | 0 | 38966 | 7306 | 0 | Brief progress report (actual/planned): Procurement of the 2nd set of equipment. Legal arrangement (actual/ planned): The SSFA signed in June 2010, was completed and closed in the 1st quarter of 2014. First mission (actual/ planned): 8-11/06/2010. TOR completed (actual/ planned): 31/12/2011. First disbursement date: 07/09/2010. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): 6 units of refrigerants identifiers delivered in 2nd quarter of 2015. Only financial reporting within UNEP pending to close this project.
ONG | UNEP | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | MDV | PHA | 69 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-11-01 | 2015-04-01 | 2015-04-01 |  |  | 173400 | 0 | 173400 | 87200 | 50.29% | 86200 |  | 86200 | 22542 | 0 | 0 | 22542 | 0 | Brief progress report (actual/planned): Two enforcement trainings in February and October 2014; Inauguration of the first-ever national Refrigeration and Air-conditioning Association on the Ozone Day 2014 Celebration; Two In-house Training Workshops on Good Service Practices in Refrigeration and Airconditioning for Resorts in Sep. and in Nov. 2014; Signing of a MOU between the Faculty of Engineering Technology of Maldives National University and the Ministry of Environment and Energy for sustaining the technician training efforts; Side event during 26th MOP to highlight the challenges Maldives and other SIDS are facing in the fishery sector. Legal arrangement (actual/ planned): The SSFA signed in August 2014. First mission (actual/ planned): 01-03/06/2014. TOR completed (actual/ planned): N/A. First disbursement date: 14/11/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued. Inter-agency negotiations on establishing technician certification scheme and equipment/ product labelling. Legal arrangement (actual/ planned): As of 22 May 2015, additional US$72,200 is pending transfer to the government.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | MDV | PHA | 73 | TAS | 26 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-05-01 | 2015-11-30 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Agreement on implementation modality and a general timeline reached with the government. Legal arrangement (actual/planned): DMFA drafted. First mission (actual/ planned): The 2nd quarter of 2015. TOR completed (actual/ planned): A consultant to be hired in the 2nd quarter of 2015. First disbursement date: The 2nd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Agreement on implementation modality and a general timeline reached with the government in the 1st quarter of 2015. Legal arrangement (actual/planned): DMFA signed in March 2015. First mission (actual/ planned): July 2015 TOR completed (actual/ planned): A consultant hired in the 2nd quarter of 2015. First disbursement date: May 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | Development of RMP | RMP | ASP | MDV | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-04-01 |  | 2002-09-01 | 2003-09-01 | 30000 | -1849 | 28151 | 28151 | 100% | 0 |  |  | 3900 | -240 | 3660 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring and review | Individual | ASP | MDV | REF | 38 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-08-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MDV | REF | 38 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-07-01 | 2008-12-01 | 35000 | -2000 | 33000 | 33000 | 100% | 0 |  |  | 4550 | -260 | 4290 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officials and the Ozone Unit staff | Individual | ASP | MDV | REF | 38 | TRA | 08 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-05-01 |  | 2005-11-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | MDV | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -5500 | 19500 | 19500 | 100% | 0 |  |  | 3250 | -715 | 2535 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | MDV | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1997-03-01 |  | 2002-05-01 | 2005-12-01 | 41250 | 0 | 41250 | 41250 | 100% | 0 |  |  | 5363 | 0 | 5363 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | MDV | SEV | 37 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2004-08-01 |  | 2004-10-01 | 2005-12-01 | 35753 | 0 | 35753 | 35753 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | MDV | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2005-11-01 | 2007-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | MDV | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | MDV | SEV | 56 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | MDV | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | MDV | SEV | 67 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-04-01 | 2014-11-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was completed successfully by 31.12.2014 and the 72nd Excom approved the Phase VIII that ahs been initiated for implementation from 1.1.2015. In 2014, Enforcement training program for the customs officers was held from 10th to 11th February 2014. The main objective of this workshop was to provide the necessary skills to monitor and control the import of controlled or banned ozone depleting substances and detection and prevention of illegal trade of these substances.Stakeholder consultation was held on 2nd June 2014 regarding the implementation of HPMP and update on tax incentives and alternative technologies. The training sessions was delivered by representatives from UNDP and UNEP. A7 data for 2014 has been submitted before the deadline. | Project is completed
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | ASP | MDV | SEV | 72 | INS | 25 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-11-01 | 2016-11-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): This project has been approved in May 2014. Draft SSFA developed for discussions with the country. Legal arrangements(actual/planned): Legal ararngements initiated. Initial stages of project implementation(actual/planned): Planned. Intermediate goals achieved (actual/planned): N/A. Project completion and follow up: Will be completed in 2016. First disbursement date (actual/planned): in 2015. All funds disbursed (yes/no): N/A. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | The SSFA has been finalized and signed. The first payment is cleared but could not be made because of the transition to UMOJA. The licensing and quota system and iPIC are being implemented in 2015. The total quota of HCFCs for 2015 has been set below the 35% reduction obligation under the complete phase out agreement. 2014 A 7 and Country Programme has been timely reported.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLI | PHA | 48 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2011-03-01 | 120000 | -5587.86 | 114412.14 | 114412 | 100% | 0.14 | 0 |  | 15600 | -726.42 | 14874 | -0.42 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLI | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 |  | 2013-06-01 | 2014-07-01 | 85000 | -11106 | 73894 | 73894 | 100% | 0 | 0 |  | 11050 | -1444 | 9606 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2009-03-01 |  | 2010-12-01 | 2011-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MLI | PHA | 63 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 65000 | -3170 | 61830 | 61830 | 100% | 0 | 0 |  | 8450 | -412 | 8038 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MLI | PHA | 71 | TAS | 33 | A | I |  | 0.8 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2016-12-01 | 2016-12-01 |  |  | 55000 | 0 | 55000 | 30000 | 54.55% | 25000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | Brief progress report (actual/planned): Four refrigeration workshops training of refrigeration technicians have been organized between August and October 2014 in Bamako: 114 refrigeration technicians trained. Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | One worshop for 30 Refrigeration technicians and 20 customs officers on identification of HCFCs and HCFC based equipment organized in March 2015 .Awareness workshop on HCFCs and HCFCs based equipment organised in June 2015.
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | MLI | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance in drafting ODS-related legislation | Individual | AFR | MLI | REF | 29 | TAS | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-07-01 | 2003-08-01 | 10980 | 0 | 10980 | 10980 | 100% | 0 | 0 |  | 1427 | 0 | 1427 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | MLI | REF | 29 | TRA | 07 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  | 2003-03-01
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration servicing sector | Individual | AFR | MLI | REF | 29 | TRA | 08 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-05-01 | 2005-01-01 | 60000 | -18414 | 41586 | 41586 | 100% | 0 | 0 |  | 7800 | -2394 | 5406 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Preparation of the RMP update | RMP update | AFR | MLI | REF | 43 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2009-02-01 | 2005-07-01 |  | 2005-11-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | AFR | MLI | REF | 45 | TAS | 19 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training programme for customs officers (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 17 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2007-09-01 | 2008-12-01 | 29546 | 0 | 29546 | 29546 | 100% | 0 | 0 |  | 3841 | 0 | 3841 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training programme for refrigeration service technicians (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 18 | A | I | CFC | 6.1 | 6.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2008-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | MLI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-05-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Institutional strengthening project for Mali | Individual | AFR | MLI | SEV | 24 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | MLI | SEV | 35 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-03-01 | 2007-06-01 | 46667 | 0 | 46667 | 46667 | 100% | 0 | 0 |  | 6067 | 0 | 6067 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | MLI | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MLI | SEV | 50 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | MLI | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | MLI | SEV | 63 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  | 2012-12-01 | 2013-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2013-6/2015) | Individual | AFR | MLI | SEV | 70 | INS | 32 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2015-06-01 | 2015-06-01 |  |  | 60677 | 0 | 60677 | 0 | 0% | 60677 | 47177 | 47177 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013. Ozone day was celebrated in September 2014 . NNO coordinated all HPMP training activities activities. Organization of an awareness workshop on Ozne in june 2014. Conferences at University of Bamako of HCFCs, HCFC based equipment and available alternatives.L egal arrangements (actual/planned): Agreement signed in January 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in February 2014 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Sumisson of the 2013 data reports and coordination of the HPMP workshop for refrigareation technicians and Customs officers.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | MLW | FUM | 30 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9242 | 15758 | 15758 | 100% | 0 | 0 |  | 3250 | -1201 | 2049 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLW | PHA | 50 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-02-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MLW | PHA | 53 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLW | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-03-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2011-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 10010 | 0 | 10010 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 6500 | 1300 | 0 | Project Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MLW | PHA | 70 | TAS | 34 | A | I |  | 0.7 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2016-07-01 | 2016-07-01 |  |  | 55000 | 0 | 55000 | 20000 | 36.36% | 35000 | 20000 | 20000 | 7150 | 0 | 0 | 7150 | 0 | Brief progress report (actual/planned): _Country implementing second tranche activities. NOU conducted training for both customs officer and refrigeration technicians. 40 customs officers and 30 refrigeration technicians were trained.The NOU conducted inspection visist to Songwe Boarder (Malawi/Tanzania boarder) to check on how customs officers and beaural of standards officers are enforcing the HCFC control measures and conducted briefing session with enforcement officers at the boarder. Legal arrangements (actual/planned): SSFA was signed and first disbursement was made in February, 2014. Any delay (Yes/No): There is delay in processing for second disbursement due to the launch of UMOJA, country submitted all the required reports for processing of second disbursement._ First mission (actual/planned): __CAP planning for a mission to the country_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in February 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | The NOU registered all the importers and allocated the 2015 quotas to the importers.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | MLW | PHA | 71 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-05-01 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): _The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. Verification will be done in 2016, when the country request for third HPMP tranche. Legal arrangements(actual/planned):N/A___ First mission (actual/planned): __N/A. TOR completed(actual/planned): _YES__ First disbursement date (actual/planned): N/A.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. The actually verification will be done in 2016.
FIN | UNEP | Country programme preparation | Individual | AFR | MLW | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-05-01 | 1993-05-01 |  | 1994-03-01 | 1994-12-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 |  | 3900 | -650 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | MLW | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1997-03-01 |  | 1998-10-01 | 1999-10-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 10010 | 0 | 10010 | 0 | 0
FIN | UNEP | Request for renewal of institutional strengthening | Individual | AFR | MLW | SEV | 25 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-06-01 |  | 2000-12-01 | 2003-12-01 | 51350 | 0 | 51350 | 51350 | 100% | 0 | 0 |  | 6676 | 0 | 6676 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | MLW | SEV | 31 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-01-01 | 2005-12-01 | 51300 | 0 | 51300 | 51300 | 100% | 0 | 0 |  | 6669 | 0 | 6669 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | MLW | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | MLW | SEV | 47 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2007-12-01 |  | 2007-12-01 | 2008-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | MLW | SEV | 53 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | MLW | SEV | 59 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 36147 | 30586 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VIII: 4/2012-3/2014) | Individual | AFR | MLW | SEV | 66 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2014-12-01 |  | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU conducted training of 60 RAC technicians in the Southern, Central and Northern local regions . Two training workshops were conducted in Blantyre and Lilongwe for custom officers and 50 custom, in total, officers were trained. Country celebrated 2014 International Ozone day through newsletter articles on ozone issues, dissemination of ozone messages through TNM and Zain mobile networks and speech read by the Minister on the ozone day.The NOU collected and subimitted 2013 ODS data and CP report. TV and radio programmes on ozone were featured and aired on local TV and radio stations. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in June, 2012 . Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made inJuly 2012 . _ All funds disbursed (yes/no): Yes. Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project completed and new phase was approved at Ex-com 72
ONG | UNEP | Extension of institutional strengthening project (phase IX: 4/2014-3/2016) | Individual | AFR | MLW | SEV | 72 | INS | 36 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-03-01 | 2016-03-31 |  |  | 66733 |  | 66733 | 0 | 0% | 66733 | -5.8265e-13 | 34733 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and sent to the county for signing. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | EUR | MOL | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-year | EUR | MOL | PHA | 52 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2009-12-01 | 2010-12-01 | 74500 | 0 | 74500 | 74500 | 100% | 0 | 0 |  | 9685 | 0 | 9685 | 0 | 0
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-06-01 | 2000-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 |  | 18265 | 0 | 18265 | 0 | 0
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | MOL | PHA | 72 | PRP | 27 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2015-05-01 | 2015-11-01 |  |  | 10000 |  | 10000 | 0 | 0% | 10000 | 7370 | 10000 | 1300 | 0 | 0 | 1300 | 0 | Brief progress report (actual/planned): The TOR for a national consultant was developed by UNEP and NOU. UNEP in cooperation with the NOU has advertised the position for the national consultancy in October-November of 2014. The national consultant was recruited in November of 2014. The NOU and the consultant started collecting, reviewing, and finalizing the information regarding policy, legislation, application of standards and safety requirements, availability of low GWP alternatives, and training activities. Legal arrangements (actual/planned): The SSA contract with a national consultant was signed in November of 2014. Initial stages of project implementation (actual/planned): The project is ongoing Intermediate goals achieved (actual/planned): The NOU and the national consultant have initiated activities required for preparation of the HPMP stage 2 as planned Project completion and follow up: Project ongoing First Disbursement date (actual/planned): No All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): HPMP stage II was drafted by the NOU, UNDP and UNEP in accordance with the format of the Executive Committee of the Multilateral Fund of the Montreal Protocol on the basis of analysis of current consumption of ozone-depleting substances by various industries and sectors of the country. The draft was available in February of 2015. The Moldova, Rep has developed the HCFC Phase out Management Plan (stage 2) taking into account the requirements of Associated Agreement with the EU. The stakeholder’s consultation meeting to be organized on 6-8 July of 2015. UNDP and UNEP plan to participate and assist in finalizing the document. The HPMP stage 2 document will be submitted to ExCom-75. Legal arrangements (actual/planned): The SSA contract with a national consultant was signed in November of 2014. Initial stages of project implementation (actual/planned): The project is ongoing Intermediate goals achieved (actual/planned): The NOU and the national consultant have provided the draft of Non-investment activities of HPMP stage 2 Project completion and follow up: Project ongoing First Disbursement date (actual/planned): March of 2015 All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
FIN | UNEP | Implementation of the RMP: train the trainers programme for good practices in the refrigeration sector | Individual | EUR | MOL | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-09-01 | 1999-08-01 |  | 2003-12-01 | 2005-12-01 | 66000 | -11000 | 55000 | 55000 | 100% | 0 | 0 |  | 8580 | -1430 | 7150 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Implementation of the RMP: training on monitoring and control of CFC and CFC using equipment | Individual | EUR | MOL | REF | 25 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2001-06-01 | 1999-08-01 |  | 2004-12-01 | 2008-01-01 | 66550 | -7349 | 59201 | 59201 | 100% | 0 | 0 |  | 8652 | -955 | 7697 | 0 | 0 |  |  |  | 2002-01-01
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | EUR | MOL | REF | 44 | TAS | 11 | A | I | CFC | 6.4 | 6.4 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 19885 | -4233.91 | 15651.09 | 15651 | 100% | 0.09 | 0 |  | 2585 | -550 | 2035 | 0 | 0
FIN | UNEP | Country programme | Individual | EUR | MOL | SEV | 25 | CPG | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 1998-07-01 |  | 1998-07-01 | 1998-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | MOL | SEV | 25 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2002-07-01 | 2004-05-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (Phase II) | Individual | EUR | MOL | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2004-04-01 |  | 2004-07-01 | 2007-06-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MOL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-03-01 | 2007-03-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | MOL | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | MOL | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-07-01 |  | 2011-12-01 | 2011-12-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MOL | SEV | 61 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 |  | 2012-12-01 | 2013-12-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | EUR | MOL | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 | 2015-08-01 |  |  | 69334 | 0 | 69334 | 46611.81 | 67.23% | 22722.19 | 15265.95 | 15266 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Article 7 data was collected and the report is being prepared and will be submitted to OS on time. CP report was prepared and submitted to MFS on time for the year of 2014. Handbook for Customs Officers has been updated with skills required for the monitoring and control of imports & exports of HCFCs and the equipment containing or relying on them, as well as the skills for detecting and preventing illegal trade and properly use of the refrigerant identifier systems. On the occasion of World Ozone Day, Moldova’s National Ozone Unit in collaboration with the Ministry of Environment (MOE) has organized and implemented the following activities: Participation of Vice-Minister of Environment at the TV emission “Buna Dimineata/Good Morning” on 16th of September 2014, broadcasting time 7:30. Press conference with participation of NOU, Public Association of Refrigeration Technicians, main importers and distributors of refrigeration equipment and mass-media representatives was organized on 12th of September 2014. Round table discussion with participation of Ozone Office Coordinator in the format “ECO-TERRA”, under the topic “HPMP – Results & Perspectives” have been broadcasted - 60 min. on 16th of September 2014. Training video for RAC technicians: Introduction of HCFC alternatives was broadcasted on TV on 15th of September 2014. An Ecological hour - “Ozone Layer Protection: The Mission Goes On” - was organized in a range of gymnasiums within the country on 16th of September 2014. Legal arrangements (actual/planned): The SSFA was signed in September of 2012. Initial stages of project implementation (actual/planned): All activities were initiated on time as planned. Intermediate goals achieved (actual/planned): CP and Article 7 data is collected. Public awareness carried out. Project completion and follow up: Project ongoing First disbursement date (actual/planned): The first payment was released in November of 2012. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): There is a slight delay from the NOU in requesting the last payment under this phase. The NOU needs to submit the progress and financial report. All activities are implemented on time. There are changes in the Government. Legal arrangements (actual/planned): The SSFA was signed in September of 2012. Initial stages of project implementation (actual/planned): All activities were initiated on time as planned. Intermediate goals achieved (actual/planned): All activities are implemented on time. Project completion and follow up: Project ongoing First disbursement date (actual/planned): The first payment was released in September of 2012. All funds disbursed (yes/no): NO Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolved: There is a slight delay from the NOU in requesting the last payment under this phase. The NOU has been informed to make all efforts in requesting the last payment. There are changes in the Government. If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2014-6/2016) | Individual | EUR | MOL | SEV | 72 | INS | 28 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-06-01 | 2016-06-30 |  |  | 69334 |  | 69334 | 0 | 0% | 69334 | 0 | 69334 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved in May of 2014. Consultations meetings (organized together with Public Refrigerant Association of the Republic of Moldova and main importers, as well as with the Technical University of Moldova) were conducted in December of 2014 to enable effective implementation of HPMP (Stage I). Also, the NOU has updated its website and improved performance. Legal arrangements (actual/planned): The SSFA was signed in November of 2014. Initial stages of project implementation (actual/planned): All activities were initiated on time as planned. Intermediate goals achieved (actual/planned): N/aProject completion and follow up: Project ongoing First disbursement date (actual/planned): The first payment was released in December of 2014. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a | Brief progress report (actual/planned): Annual quota for quantitative restrictions for HCFCs imports (in order to achieve 10% reduction of HCFC by 2015), starting from 01/01/2013 based on the base line data was introduced. The annual quota for the year of 2015 has been distributed to importers. Moldova, Rep is a member of iPIC system The Steering Committee Meeting was held on 24 January of 2015. The meeting evaluated the annual report (for 2014) presented by the importers, that have been obtained an Authorizations for 2014 and distribution of the import annual quotas for 2015. Article 7 data was collected and the report is being prepared and will be submitted to OS on time. CP report was prepared and submitted to MFS on time for the year of 2014. Legal arrangements (actual/planned): The SSFA was signed in November of 2014. Initial stages of project implementation (actual/planned): All activities were initiated on time as planned. Intermediate goals achieved (actual/planned): CP and Article 7 data is collected. Public awareness carried out. Project completion and follow up: Project ongoing First disbursement date (actual/planned): The first payment was released in December of 2014. All funds disbursed (yes/no): NO Any delay? (yes/no): NO If Yes, reasons for delay & action plan to resolved: N/a If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/a
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MON | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-03-01 | 2011-08-01 | 85000 | -3023 | 81977 | 81977 | 100% | 0 |  |  | 11050 | -393 | 9357 | 1300 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 |  | 2013-12-01 | 2014-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | MON | PHA | 71 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-11-01 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Agreement on implementation modality reached with the government. Legal arrangement (actual/planned): DMFA drafted in December 2014. First mission (actual/ planned): September 2015. TOR completed (actual/ planned): Yes. First disbursement date: N/A. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Agreement on implementation modality and a general timeline reached with the government in the 1st quarter of 2015. Legal arrangement (actual/planned): DMFA signed in March 2015. First mission (actual/ planned): September 2015. TOR completed (actual/ planned): A consultant hired in the 2nd quarter of 2015. First disbursement date: May 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | MON | PHA | 71 | TAS | 22 | A | I |  | 0.1 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2016-12-01 | 2016-12-01 |  |  | 65000 | 0 | 65000 | 23000 | 35.38% | 42000 |  | 42000 | 8450 | 0 | 0 | 8450 | 0 | Brief progress report (actual/planned): Government Resolution issued on the list of (non-ODS and HCFCs) environmentally friendly techniques and equipments. Government memo on use of non-HCFCs and non-HFC alternatives in new international airport in Ulaanbaatar. Legal arrangement (actual/ planned): The SSFA signed in June 2014. First mission (actual/ planned): September 2015. TOR completed (actual/ planned): N/A. First disbursement date: June 2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Servicing training equipment procurement arranged. HCFCs quota 2015 issued and the information shared through iPIC. 2 units of refrigerants identifiers procured in 2nd quarter of 2015. Legal arrangement (actual/ planned): Additional US$18,000 is to be transferred to the government in the 3rd quarter of 2015.
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MON | REF | 32 | TRA | 03 | A | I | CFC | 2.4 | 2.4 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-10-01 | 2005-01-01 | 65970 | -15423 | 50547 | 50547 | 100% | 0 |  |  | 8576 | -2004 | 6572 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | MON | REF | 32 | TRA | 04 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-06-01 | 2003-06-01 | 77200 | -15003 | 62197 | 62197 | 100% | 0 |  |  | 10036 | -1950 | 8086 | 0 | 0
FIN | UNEP | Country programme formulation | Individual | ASP | MON | SEV | 20 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | MON | SEV | 28 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-08-01 |  | 2002-08-01 | 2003-09-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | ASP | MON | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | MON | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-07-01 | 2007-07-01 | 57200 | -2 | 57198 | 57198 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | MON | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-06-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | MON | SEV | 55 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | MON | SEV | 60 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | ASP | MON | SEV | 64 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 |  | 2013-12-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Renewal of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | ASP | MON | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): All activities are being implemented and objectives achieved as per the related Excom decisions. The Ozone Cell is working smoothly and effectively.The overall quality of implementation and execution has been of a very high order and all obligations and reporting was completed in a timely manner. The Government needs to follow up closely on the XPS foam conversion as part of Japan’s investment component of the approved HPMP.The project has organised activities to strengthen capacity of technicians for the good practice servicing of ODS based equipments and customs officers for banned ODS import/export. Montreal Protocol Enforcement Training Programme for the Customs officer, State Inspectors of border inspection agency and also customs brokers was organized by the National Ozone Authority of Mongolia (NOA/PMU) with assistance from the General Customs Administration (GCA) on 08-09 September 2014 at the customs point in Zamin –Uud, Dornogobi province (South border with China far from over 700 km from Ulaanbaatar which is isolated region). Ozone Day was celebrated in 2014 and A7 and CP data has been submitted in a timely manner for 2014. Legal arrangements(actual/planned): SSFA signed and two payments made already. Initial stages of project implementation(actual/planned): N/A as ongoing project. Intermediate goals achieved (actual/planned): Assisting in the implementation of stage I of the HPMP, implementing HCFC quota system from 2013 onwards and raising awareness of national stakeholders. Project completion and follow up: Project will be completed by the end of the year and is regularly being followed up. First disbursement date (actual/planned): 17/03/2014. All funds disbursed (yes/no): No. Any delay?(yes/no): No.If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | The notification of the issued quota to the importers has been sent to the importers (Jan’2015). List of Alternatives to the HCFCs that controlled under the Montreal Protocol has developed and included to the draft of renewal of the Government Resolution No 104 in May 2015. A procurement officer from Government Procurement Agency of Mongolia participated in the Workshop on Promoting Public Procurement of Climate Friendly Alternatives to HFCs in Asia Pacific in Goyang City, Republic of Korea on 10-13 March 2015. A short Training programme on handling of ODS and their alternative refrigerants for technicians has conducted by training center for the refrigeration technicians named “Masters Potentials” with request of end users in cooperation with PMU/NOA (Mar’2015). -Delivered presentations and trainings for the trainees in cooperation with the training center for the refrigeration technicians named “Masters Potentials”. (Mar’2015) -Monitoring of the training under the training center has been carried out by PMU periodically. (Mar’2015). The recommendations on Ozone and Climate friendly public procurement of Refrigeration and Air-Conditioning equipments and technology and its annex was delivered by the Procurement Department, Implementation Agency of the Government of Mongolia to its department units distributed all over 9 districts in the city and 21 provinces of the country. (Mar’2015). Submitted A7 data for 2014. This Phase of IS will be completed in November 2015. The next phase of IS (Phase IX) has been approved by the 74th Excom. held in May 2015.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | MOR | REF | 27 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-04-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -4984 | 25016 | 25016 | 100% | 0 | 0 |  | 3900 | -648 | 3252 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | MOR | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-05-01 |  | 1996-05-01 | 1996-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Creation of Ozone Unit | Individual | AFR | MOR | SEV | 19 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1999-05-01 |  | 2004-07-01 | 2007-02-01 | 179000 | 0 | 179000 | 179000 | 100% | 0 | 0 |  | 23270 | 0 | 23270 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MOR | SEV | 43 | INS | 49 | A | I | CFC | 12.8 | 0 | 0 | 0 | 2004-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MOR | SEV | 53 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2015-12-01 |  |  | 156000 | 0 | 156000 | 117820.16 | 75.53% | 38179.84 | 0 | 38179.72 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): 2nd payment ($38,250) sent in Dec. 2009. SSFA renewed and reviewed again by FMO in Nov 2012. Has $38,250 final balance but No activities undertaken since 2013.___ Legal arrangements(actual/planned): SSFA signed in 2008___Initial stages of project implementation(actual/planned):SSFA signed, first and second payment released ___ Intermediate goals achieved (actual/planned): _Yes __ Project completion and follow up: No___ First disbursement date (actual/planned): _First disbursment done in 2008__ All funds disbursed (yes/no): No___ Any delay?(yes/no): __Yes_ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Letters sent to the Morocco government to seek advise if we should continue the IS . UNEP still waiting for the government response
ONG | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | MOR | SEV | 59 | INS | 63 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2011-11-01 | 2015-12-01 |  |  | 84500 | 71500 | 156000 | 0 | 0% | 156000 | 0 | 156000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _No activities in 2014__ Legal arrangements(actual/planned): _Sent to country for comment and signature since 2013__Initial stages of project implementation(actual/planned): _Project activities not started__ Intermediate goals achieved (actual/planned): _Country in compliance without IS__ Project completion and follow up: _UNEP sent letter to the Minister of Environment to find out if Morocco is still interested by IS__ First disbursement date (actual/planned): __No disbursment yet_ All funds disbursed (yes/no): __No_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: __No signature of the agreement_ If Yes, will delay have impact on project completion date (yes/no): Yes___ Any ongoing problems (yes/no): No signature of the agreement___ If Yes, is any action required by ExCom: MLFS to contact the government___ | Letters sent to the Morocco government to seek advise if we should continue the IS . UNEP still waiting for the government response |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MOZ | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-11-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MOZ | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2009-11-01 | 2011-03-01 | 75000 | -7550 | 67450 | 67450 | 100% | 0 | 0 |  | 9750 | -982 | 8768 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | MOZ | PHA | 58 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-12-01 | 2013-12-01 | 55000 | -15987 | 39013 | 39012.93 | 100% | 0.07 | 0 |  | 7150 | -2078 | 5072 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2013-09-01 | 2014-12-01 | 59000 | 0 | 59000 | 59000 | 100% | 0 | 0 |  | 7670 | 0 | 5200 | 2470 | 2470 | Project Completed
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MOZ | PHA | 66 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2014-04-01 |  | 2014-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Brief progress report (actual/planned): _The country conducted 3 regional (Maputo, Biera, Nacala)training workshops for refrigeration technicians and a total of 85 technicians were trained. The NOU conducted regional training workshops (Manica, Nampula, Sofala provinces) and a total of 120 enforcement officers (customs officers, boarder patrol Police and clearing agents ) were trained. Legal arrangements (actual/planned): SSFA was signed in May 2013. Any delay (Yes/No): Country experienced some delays at the UNDP country office in transferring of funds to the country_ First mission (actual/planned): __CAP first mission to the country to launch the implementation of HPMP activities was conducted in May, 2014._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in June 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | first trache implementation completed and the country is processing to start implementation of second trache which was approved at Ex-com 73
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | MOZ | PHA | 73 | TAS | 25 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-06-01 | 2016-06-30 |  |  | 35000 |  | 35000 | 0 | 0% | 35000 | -5.8265e-13 | 20000 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): __ SSFA finalised and sent to the country for signing. Legal arrangements (actual/planned)N/A. Any delay (Yes/No): No_ First mission (actual/planned): __NO._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: Launch of UMOJA__ If Yes, will delay have impact on project completion date (yes/no): _NO__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
FIN | UNEP | Country programme | Individual | AFR | MOZ | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | MOZ | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1997-12-01 |  | 2003-12-01 | 2005-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 |  | 12012 | 0 | 12012 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | MOZ | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-03-01 | 2005-12-01 |  | 2007-01-01 | 2008-12-01 | 80080 | 0 | 80080 | 80080 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MOZ | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2008-11-01 |  | 2009-07-01 | 2010-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MOZ | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 7/2011-6/2013) | Individual | AFR | MOZ | SEV | 64 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 |  | 2013-06-01 | 2014-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | AFR | MOZ | SEV | 70 | INS | 24 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 | 2015-06-01 |  |  | 80800 | 0 | 80800 | 62107.85 | 76.87% | 18692.15 | 18692 | 18692 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU conducted 3 training workshops for 40 RAC technicians in Niassa, Tete and Zambezi provinces . Two training workshops were conducted for custom officer and 50 custom officers were trained. Country celebrated 2014 International Ozone day, the Minsiter read out a speech for the ozone day which was marked by traditional dances, drama, poems and ozone songs. The NOU collected and subimitted 2013 ODS data and CP report to OS and MLFS. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in January 2014 as planned. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made in May 2014 . _ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Collection of the 2014 data on ODS imports and consumption commenced and the NOU will submit the data soon to both OS and MLFS.
FIN | UNEP | Preparation of a terminal phase-out management plan | RMP | ASP | MYA | PHA | 55 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2008-12-01 |  | 2011-06-01 | 2011-12-01 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MYA | PHA | 57 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 42500 | -1961 | 40539 | 32753 | 80.79% | 7786 |  |  | 5525 | -225 | 4257.89 | 1042.11 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | MYA | PHA | 68 | TAS | 14 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2016-12-01 |  |  | 159000 | 0 | 159000 | 0 | 0% | 159000 |  | 159000 | 20670 | 0 | 0 | 20670 | 0 | Brief progress report (actual/planned): This is a long delayed project following its approval by Excom at its 68th meeting, mainly due to the condition attached to the project when it was approved, i.e. the Ozone Order needs to be in place as per Excom decision 68/31. Following the Ozone Order in place in later April 2014, the draft SSFA was submitted to Myanmar for review and comments. Due to the long internal procedures, the government completed its reviewing process of the draft SSFA by December 2014. Legal arrangements (actual/planned): The SSFA is waiting for the government co-signature to become effective. First Mission: Feb 2014. First disbursement date: N/A All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: the delay in signing SSFA due to the long review process of the country. UNEP maintained regular communications with the government to expedite the signing of SSFA. UNEP conducted missions in Feb, Sep 2014, and April 2015 to build the capacity of the NOU/stakeholders, and get the country prepared for the implementation after effectiveness of the SSFA. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): Yes. The country is in the process of obtaining the Cabinet approval to sign SSFA. If Yes, is any action required by ExCom: No. | The SSFA was signed by UNEP in February 2015 and is in the process of the Cabinet approval which is prerequisite for signatory. UNEP is following up with the government to expedite the signatory of SSFA to allow the transfer of funds for the implementation of HPMP activities. In the meantime, UNEP conducted a mission in April 2015 for the preparation of HPMP implementation. A national stakeholder workshop as well as meetings with key stakeholders (Myanmar Engineering Society, Customs Department) were organized to discuss the action plan for HPMP implementation. It was agreed that a train-the-trainer workshop for customs and enforcement officers will be organized in August 2015, while a train-the-trainer workshop on good practices for servicing will be organized in September 2015. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | MYA | PHA | 73 | TAS | 16 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-05-01 | 2015-11-30 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Newly approved project at the 73rd Meeting in November 2014. After the ExCom approval, UNEP coordinated with the government to discuss feasible options to conduct the verification of HCFCs consumption as per the country context. Several options were explored and the government was in the process of deciding the best option. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned): N/A Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): No. Any ongoing problems (yes/no): No. | Discussion with the government has been made before and during the mission on April 2015. Given that the second tranche of Myanmar HPMP is scheduled in the last meeting of 2015, UNEP ROAP proposed the government that the verification of HCFC consumption will cover CY 2013 and 2014. It was agreed that verification of HCFC consumption will be conducted by private auditing company that has registered with the Myanmar Auditing Council.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | MYA | REF | 29 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2000-12-01 |  | 2005-04-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: preparation of ozone regulations for control of ODSs | Individual | ASP | MYA | REF | 45 | TAS | 05 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2005-04-01 | 2008-05-01 | 2005-11-01 |  | 2011-01-01 | 2011-11-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring implementation of the RMP | Individual | ASP | MYA | REF | 45 | TAS | 06 | A | I | CFC | 8.8 | 0 | 0 | 0 | 2005-04-01 | 2008-03-01 | 2008-04-01 |  | 2011-01-01 | 2011-11-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 |  |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | MYA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Establishment of the national Ozone Cell for implementing the phase out of ODSs under the Montreal Protocol | Individual | ASP | MYA | SEV | 29 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2007-07-01 | 2002-12-01 |  | 2009-12-01 | 2011-03-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 |  |  | 9880 | 0 | 9880 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | MYA | SEV | 58 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | MYA | SEV | 62 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase III: 1/2012-12/2013) | Individual | ASP | MYA | SEV | 64 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-08-01 | 2013-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 24068 | 40.11% | 35932 |  | 35943 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Following the enactment of the Ozone Order 2014, Myanmar continued its licensing and quota system for HCFCs import/export under the Ozone Order. The license would be issued by Ministry of Commerce (MOC) subject to the endorsement letter from the Environmental Conservation Department (ECD) of the Ministry of Environmental Conservation and Forestry (MOECAF). The meeting with importers was organized to inform the effectiveness of the Ozone Order. Moreover, the Ozone Order also included the import and export of HCFC-based equipment, which is yet to be enforced. The Myanmar Customs Department has already adopted 2012 HS Code to control the import and export of goods. The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. New ozone officer was appointed in Sep 2014. Legal arrangements (actual/planned): The SSFA has been signed in November 2012. Initial stages of project implementation (actual/planned): N/A, since Project is ongoing. Intermediate goals achieved (actual/planned): Yes, prepared the HPMP and submitted for approval; data reported to the Fund and Ozone Secretariats; Ozone Order was enforced. First disbursement date: August 2013 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delayed in signing the agreement, submitting progress/expenditure report, changing of ozone officer. UNEP is in constant communication with the country, and build the capacity of the new ozone officers and other national stakeholders. UNEP has proposed a new SSFA to replace the expired SSFA. If Yes, will delay have impact on project completion date (yes/no) Yes. Any ongoing problems (yes/no): No. | The licensing and quota system are being implemented in 2015. UNEP has encouraged Myanmar to join iPIC to strengthen the control of import and export of ODS. Country sent two Ozone staff for capacity building in March 2015 under south-south cooperation with Thailand with assistance of UNEP. The SSFA was renewed and signed. NOU has agreed to establish a focal point from the Customs Department and the Ministry of Commerce to enhance the day-to-day communication. International ozone day celebration will be organized back-to-back with train-the-trainer workshop on good practices for RAC servicing. NOU is reconciling import and export statistics to report the 2014 Country Programme.
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | ASP | MYA | SEV | 71 | INS | 15 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved by the ExCom at the 71st meeting in 2013. Due to the foreseen long internal process, UNEP prepared and submitted the draft SSFA for the government review and comments. Based on the draft SSFA for IS Project Phase IV, the starting date has been expected starting from January 2016. | The Environmental Conservation Department (ECD) has translated the draft SSFA of IS Project Phase IV into local language. The draft SSFA for IS Project Phase IV is being reviewed by the Ministry of National Planning and Economic Development and the General Attorney Office from which the comments will be notified to UNEP for finalization accordingly.
FIN | UNEP | Country programme preparation | Individual | AFR | NAM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-04-01 | 1996-03-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | AFR | NAM | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 2000-02-01 | 2001-12-01 | 61765 | 0 | 61765 | 61765 | 100% | 0 | 0 |  | 8029 | 0 | 8029 | 0 | 0 |  |  |  | 1998-11-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | NAM | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 41177 | 0 | 41177 | 41177 | 100% | 0 | 0 |  | 5353 | 0 | 5353 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | NAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 53530 | 0 | 53530 | 53530 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | NAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NAM | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NAM | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2013-11-01 |  | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Complete
COM | UNEP | Extension of institutional strengthening project (phase VII: 4/2012-3/2014) | Individual | AFR | NAM | SEV | 66 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-01-01 | 2014-03-01 |  | 2014-07-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country collected 2013 ODS data and submitted to OS and MFS. The NOU commemorated international ozone day through school competition, drama, poems and debates. The NOU produced and distributed awareness materials such t-shirts, calendars, caps, brochures . The country registered all the importers of HCFC for 2015 and organised a consultative meeting on meeting 2015 HCFC phase-out target. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in August 2012. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first disbursement was made in September 2012 . _ All funds disbursed (yes/no): YES_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project completed and new phase was approved at Ex-com 73
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | AFR | NAM | SEV | 73 | INS | 20 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 15000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and sent to the county for signing. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Nauru) | Multi-Year | ASP | NAU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-12-01 |  |  | 45625 | 0 | 45625 | 43748 | 95.89% | 1877 |  | 1877 | 5931 | 0 | 3656 | 2275 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted by the Customs. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. National training workshop for RAC technicians was organized in May 2014 with 10 participants. RAC servicing tools equipment/tools have not yet distributed to RAC technicians, but planned to be implemented in 2015. Due to very small number of technicians (7) and limited scope of the industry in the countries, national RAC Association may not be practical. Instead, the technicians will use the website for PIC RAC Association to allow for information exchange. The SSFA has been signed in August 2012. First Mission: August 2014 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: L ost of NOU in May of 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP conducted country mission in September of 2014, to meet with high level officials on reaching an agreement for resumption of Montreal Protocol work. The Environment Division gave its committment. UNEP continued with emails and phone calls communications. UNEP maintained constant communication with interim senior management encouraging the recruitment of required staff . If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: yes, to encourage to address implementation and implications to compliance. | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. UNEP met with Minister of Foreign Affairs and Senior international office in May of 2015 (in Bangkok), to give a detailed presentation on project, delays being encountered and requesting the support from this office on implementation.
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NAU | REF | 44 | TAS | 01 | A | I | CFC | 0.2 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | -2000 | 6000 | 6000 | 100% | 0 |  |  | 1040 | -260 | 780 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NAU | REF | 44 | TAS | 03 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2010-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 |  |  | 1820 | 0 | 1820 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NAU | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NAU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-01-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | NAU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NAU | SEV | 60 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-11-01 | 2011-12-01 |  | 2012-01-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | ASP | NAU | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-04-01 | 2014-07-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 |  | 36000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: 2013 Article 7 and CP data submitted. NOU set up the quota system to enter into force from 1 January 2013 only one importer registered for imports of refrigerants. Ongoing, regular meetings between the NOO and Customs department and planning to enhance cooperation with the Customs Department to strengthen its data collection and reporting. NOO manages the meets of the national ozone steering committee. As manager of the HPMP, the NOU has completed customs officers training in October of 2013 officers training, attended regional refresher training done in Tonga March 2014. RAC technician training completed in May 2014. NOU prepared required documents for the preparation of the HPMP Stage 1 tranche 2. Legal arrangements: Agreement signed in March 2013. First payment made in April 2013. All funds disbursed (yes/no): No Any delay (yes/no): Yes, lost of NOU in May of 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP conducted country mission in September of 2014, to meet with high level officials on reaching an agreement for resumption of Montreal Protocol work. The Environment Division gave its committment. UNEP continued with emails and phone calls communications. UNEP also met with Minister of Foreign Affairs in May of 2015, again seeking the support of this office for the Montreal Protocol implementation and on compliance obligations to the Montreal Protocol. UNEP maintained constant communication with interim senior management encouraging the recruitment of required staff . If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. If Yes, is any action required by ExCom: Yes, to encourage to address implementation and implications to compliance. | UNEP met with Minister of Foreign Affairs in May of 2015, again seeking the support of this office for the Montreal Protocol implementation and on compliance obligations to the Montreal Protocol. UNEP will follow with an official letter seeking support from government and continues to seek out possible mechanisms to allow for implementation.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 8/2014-7/2016) | Individual | ASP | NAU | SEV | 72 | INS | 09 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-07-01 | 2016-07-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Draft SSFA send to country for review and approval in August of 2014. Unable to get progressive, measurable responces from country for the finalisation of the agreement. Any delay (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Lost of NOU in May of 2014. No nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP conducted country mission in September of 2014, to meet with high level officials on reaching an agreement for resumption of Montreal Protocol work. The Environment Division gave its committment to address the recruitment of suitable national . UNEP continued with emails and phone calls communications. All funds disbursed (yes/no): No. Any ongoing problems (yes/no): Yes. Slow rate of implementation. Required high level intervention on the implementation of the Montreal Protocol. If Yes, is any action required by ExCom: Yes, to encourage to address implementation and implications to compliance. | UNEP met with Minister of Foreign Affairs in May of 2015, again seeking the support of this office for the Montreal Protocol implementation and on compliance obligations to the Montreal Protocol. UNEP will follow with an official letter seeking support from government and continues to seek out possible mechanisms to allow for implementation.
ONG | UNEP | Destruction of confiscated ODS | Individual | ASP | NEP | DES | 59 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-05-01 | 2015-12-01 |  |  | 157200 | 0 | 157200 | 133901 | 85.18% | 23299 |  | 23300 | 20436 | 0 | 17407 | 3029 | 0 | Brief progress report (actual/planned): 22000 of the 89000 credits have been sold by the company in the VCM. This has been a major achievement of 2014. The project was scheduled to be closed in 2015 with the publication of a manual and closing workshop. However the recent earthquake has impacted the project adversely. Legal arrangements(actual/planned): Ongoing and only last payment to be made to the country under the SSFA and to the company that destroyed the ODS. Initial stages of project implementation(actual/planned): Ongoing though delayed. Intermediate goals achieved (actual/planned): All goals achieved. Project completion and follow up: Remaining closing the project actiivities were to be completed by December 2014 as reported in the alst progress report. However, there were delays at the country level because of institutional changes in 2014. First disbursement date (actual/planned): Ongoing and all payments made except the alst payment . All funds disbursed (yes/no): No Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Institutional changes in the ozone office in 2013 and limited capapcity of the new Ozone Officer during 2014. If Yes, will delay have impact on project completion date (yes/no): Yes. because of the recent earthquake the project completion date may need to be shifted to September 2016. Any ongoing problems (yes/no): Sale of credits in the voluntary market affected by the crash in this amrket that ahs delayed the sale for more than two years and also impacted on final closure of the project. Sale of remaining credits may take a year or so. If Yes, is any action required by ExCom: To extend the project completion date to december 2016 because of the uniqueness of the project as a first of its kind in a LVC and the very first MLF project to get carbon credits. Sale of remaining credits will bring lessons and good learnings to the MLF. | Expediting the implementation to complete the planned activities by December 2015 though with the earhtquake this planning may need to be adjusted to carry over the remaining activities to 2016. |  |  |  |  | Continued Monitoring
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | NEP | PHA | 50 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2008-01-01 | 2008-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | NEP | PHA | 52 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-04-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | NEP | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-01-01 | 2012-12-01 | 85000 | -13954 | 71046 | 65730 | 92.52% | 5316 |  |  | 11050 | -1814 | 8544.9 | 691.1 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | NEP | PHA | 66 | TAS | 29 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2015-04-01 | 2016-03-01 |  |  | 63000 | 0 | 63000 | 30318 | 48.12% | 32682 |  | 32682 | 8190 | 0 | 3280 | 4910 | 0 | Brief progress report (actual/planned): 147 Customs officers trainned in 2014. NOU developed the 2014 annual plan for strengthening the measures for controlling HCFCs import and consumption. Stakeholders consultations including one with registered importers and goods transporting companies were organized. Legal arrangement (actual/ planned): The SSFA signed in November 2012. Implementation delay has required a rephasing of UNEP agreement with the government in the last Q of 2014. First mission (actual/ planned): 25-27/06/2012. TOR completed (actual/ planned): N/A. First disbursement date: 28/11/2012. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: national inter-agency coordination requiring extra time. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: Take note of major earthquakes on 25 April and 12 May 2015 and its implication to project implementation capacity. | Brief progress report (actual/planned): 2 units of refrigerants identifiers procured in 2nd quarter of 2015 and are with UNEP pending delivery. Two major earthquakes on 25 April and 12 May 2015 and aftershocks continuing have destroyed/ damaged the NOU premises. Further delay in implemantion is expected. Legal arrangement (actual/ planned): Revised SSFA signed in March 2015, and the first disbursement under the new agreement done in early May 2015.
FIN | UNEP | Development of refrigerant management plan | RMP | ASP | NEP | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-06-01 | 2000-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | ASP | NEP | REF | 28 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2002-10-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  |  | 780 | 0 | 780 | 0 | 0 |  |  |  | 2001-12-01
FIN | UNEP | Implementation of the RMP: training of trainers in refrigeration | Individual | ASP | NEP | REF | 28 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-02-01 |  | 2004-03-01 | 2004-10-01 | 70000 | -29000 | 41000 | 41000 | 100% | 0 |  |  | 9100 | -3770 | 5330 | 0 | 0
FIN | UNEP | Implementation of the RMP: training in monitoring and control of CFC and establishment of import/export licensing system | Individual | ASP | NEP | REF | 28 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2004-07-01 | 2006-02-01 | 44400 | -19400 | 25000 | 25000 | 100% | 0 |  |  | 5772 | -2522 | 3250 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Implementation of the RMP: assistance to remain in compliance with the Montreal Protocol | Individual | ASP | NEP | REF | 44 | TAS | 15 | A | I | CFC | 10.8 | 5.4 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2007-12-01 |  | 2008-01-01 | 2008-10-01 | 51440 | 0 | 51440 | 51440 | 100% | 0 |  |  | 6687 | 0 | 6687 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | NEP | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of an Ozone Unit | Individual | ASP | NEP | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2001-12-01 |  | 2002-05-01 | 2003-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | NEP | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-08-01 | 2007-06-01 | 53733 | 0 | 53733 | 53733 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | NEP | SEV | 44 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | NEP | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2008-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | NEP | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | NEP | SEV | 61 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | NEP | SEV | 67 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-11-01 | 2015-09-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 |  | 36000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): This project has been completed and the remaining obligations are being finalised by the country. However the earthquake has impacted the final reconciliation of accounts. Legal arrangements(actual/planned): All completed. Initial stages of project implementation(actual/planned): Project closed Intermediate goals achieved (actual/planned): Yes. Project completion and follow up: Project completed by end of 2014 and only final obligations being completed which have been delayed because of the earthquake. and the shift in UNEP's financial system to UMOJA. First disbursement date (actual/planned): march 2013 All funds disbursed (yes/no): Yes. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): The financial clsure by the country is taking time because of the earthquake. If Yes, is any action required by ExCom: N/A | Phase VIII has started but the earthquake in April 2015 has adversely impacted the implementation. The office building of NBSM where Ozoen Cell is housed is closed and Ozone Cell opertaions have been suspended for the time being. UNEP is in close touch with the Ozone officer who has been sleeping in the open and is not being able to go to the office.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | ASP | NEP | SEV | 72 | INS | 32 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-11-01 | 2016-12-01 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): This project has been approved in May 2014. Draft SSFA developed for discussions with the country. Legal arrangements(actual/planned): Legal ararngements initiated. Initial stages of project implementation(actual/planned): Planned. Intermediate goals achieved (actual/planned): N/A. Project completion and follow up: Will be completed in 2016. First disbursement date (actual/planned): in 2015. All funds disbursed (yes/no): N/A. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Phase VIII has started. The SSFA has been finalized and signed. The first payment is cleared but could not be made because of the transition to UMOJA. The earthquake in April 2015 has adversely impacted the implementation. The office building of NBSM where Ozoen Cell is housed is closed and Ozone Cell opertaions have been suspended for the time being. UNEP is in close touch with the Ozone officer who has been sleeping in the open and is not being able to go to the office.
FIN | UNEP | Technical assistance in CTC management | Individual | ASP | NEP | SOL | 47 | TAS | 17 | A | I | CTC | 0.9 | 0.9 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-01-01 | 2008-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | NER | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2010-03-01 |  | 2010-04-01 | 2011-03-01 | 81000 | -1000 | 80000 | 80000 | 100% | 0 | 0 |  | 10530 | -130 | 10400 | 0 | 0
FIN | UNEP | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2010-12-01 | 2012-07-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 |  | 8840 | 0 | 8840 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | TAS | 27 | A | I |  | 1 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 | 2016-04-01 |  |  | 100000 | 0 | 100000 | 99062 | 99.06% | 938 | 0 | 938.07 | 13000 | 0 | 12878 | 122 | 0 | Brief progress report (actual/planned): Four refrigeration workshops training have been organized in 2014 in Niamey, Maradi, Zinder and Agadez: about 110 refrigeration technicians and 80 customs officers trained in 2014. Legal arrangements (actual/planned): Agreement signed in July 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): _ Final payment being processed in July 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Organistion of an awareness day on Ozone in June 2015. Elaboration of a manuel on Ozone for kids in May 2015.Capacity-building of teachers from four schools of vocational and technical training by providing the UNEP document on "Good practices in individual air conditioning".
FIN | UNEP | Implementation of the RMP: customs officers training programme | Individual | AFR | NER | REF | 27 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-08-01 | 2000-10-01 |  | 2003-12-01 | 2005-02-01 | 63000 | -24000 | 39000 | 39000 | 100% | 0 | 0 |  | 8190 | -3120 | 5070 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | NER | REF | 27 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2002-05-01 | 2003-05-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 |  | 5395 | 0 | 5395 | 0 | 0
FIN | UNEP | Implementation of the RMP update: monitoring of the activities | Individual | AFR | NER | REF | 42 | TAS | 15 | A | I | CFC | 6 | 6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2006-04-01 |  | 2007-04-01 | 2007-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training for customs technicians | Individual | AFR | NER | REF | 42 | TRA | 13 | A | I | CFC | 6.6 | 6.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2007-04-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP update: train the trainer programme for refrigeration service technicians | Individual | AFR | NER | REF | 42 | TRA | 14 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-10-01 |  | 2006-12-01 | 2008-06-01 | 55747 | -1501 | 54246 | 54246 | 100% | 0 | 0 |  | 7247 | -195 | 7052 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | NER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1994-12-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Creation of an Ozone Secretariat | Individual | AFR | NER | SEV | 15 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1997-12-01 |  | 1999-05-01 | 1999-10-01 | 74800 | 0 | 74800 | 74800 | 100% | 0 | 0 |  | 9724 | 0 | 9724 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | NER | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-06-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | NER | SEV | 33 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Policy and technical assistance | Individual | AFR | NER | SEV | 37 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2003-08-01 |  | 2004-01-01 | 2007-01-01 | 10000 | -1995 | 8005 | 8005 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | NER | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NER | SEV | 47 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NER | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 64827 | -545 | 64282 | 64282 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | NER | SEV | 59 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 35115 | 29713 | 64828 | 64828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | NER | SEV | 65 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 |  | 2013-08-01 | 2014-08-01 | 64828 | 0 | 64828 | 64828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | AFR | NER | SEV | 71 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2015-12-01 | 2015-12-01 |  |  | 64828 | 0 | 64828 | 32414 | 50% | 32414 | 0 | 64828 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in may 2014. Country reported 2013. Art5 data and CP data for 2013. Capacity-building of teachers from four schools of vocational and technical training by providing the UNEP document on "Good practices in individual air conditioning". Agreement signed in May 2014. All activities under the SSFA are completed (as planned) _ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Coordination of the elaboration of a manuel on Ozone for kids in May 2015. Organisation of the Capacity-building of teachers from four schools of vocational and technical training by providing the UNEP document on "Good practices in individual air conditioning".
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | NIC | PHA | 49 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-06-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2010-11-01 |  | 2012-06-01 | 2013-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | NIC | PHA | 60 | TAS | 25 | A | I | CFC-12 | 2 | 2 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2012-04-01 | 2013-12-01 | 70000 | -2934 | 67066 | 67066 | 100% | 0 | 0 |  | 9100 | -381.42 | 8718.58 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | NIC | PHA | 66 | TAS | 26 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2013-07-01 | 2015-04-01 | 2015-12-01 |  |  | 38000 | 0 | 38000 | 33000 | 86.84% | 5000 | 5000 | 5000 | 4940 | 0 | 1950 | 2990 | 2340 | Brief progress report: The SSFA (agreement) implementation carried out without significant delays. Second and third disbursements released. Intermediate goals achieved as planned for the year 2014: a) in coordination with Customs General Direction, random road controls were implemented in three different sites, in Yalaguina, Las Manos and El Espino, to monitor the public transportation units to avoid the illegal trade of ODSs. In the roads of Nueva Segovia and Madriz: 57 vehicles and trucks in Yalaguina (October 5), in El Espino (October 30) and in Las Manos (Sep. 28), in coordination with the police and army, it was found one cylinder of HCFC-22 in possession of one person not authorized to import and with no quota issued. b) A training workshop and update on the upgraded controls to avoid the illegal trade of ODS carried out in July 2014 in the city of Managua. The trainees were 20 new officers of the Custom General Direction. This training workshop was aimed at public servants on new import and export requirements of ODS in order to guarantee the controls of HCFCs and related technology. Legal arrangements: signed in June 2013/planned September 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): July 2013/October 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report: HPMP progress report and 2nd tranche Annual Implementation plan submitted to the 74 ExCom meeting. Legal arrangements: signed in June 2013/planned September 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): July 2013/October 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | NIC | PHA | 73 | TAS | 30 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-11-30 | 2015-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. Work Plan and budget drafted in December 2014. | Brief progress report: Verification report is implemented as planned. TOR and identification of Consultants completed in February 2015/Planned Feb 2015. Consultant hired in March 2015. Country mission conducted in April 2015/planned March 2015. Draft report delivered in May 2015. Final Report to be delivered in July 2015. Legal arrangement: N/A. First disbursement date: April 2015. All funds disbursed? No. Any delay? Minor delays in hiring consultants that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? No. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | Preparation of the RMP update proposal | RMP update | LAC | NIC | REF | 41 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2004-12-01 |  | 2005-02-01 | 2007-01-01 | 15000 | -900 | 14100 | 14100 | 100% | 0 | 0 |  | 1950 | -117 | 1833 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: programme for prevention of illegal CFC trade | Individual | LAC | NIC | REF | 45 | TAS | 15 | A | I | CFC | 6.2 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2008-04-01 |  | 2011-12-01 | 2012-12-31 | 15000 | -6000 | 9000 | 9000 | 100% | 0 | 0 |  | 1950 | -780 | 1170 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: monitoring the activities of the RMP | Individual | LAC | NIC | REF | 45 | TAS | 16 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 30000 | -1065 | 28935 | 28935 | 100% | 0 | 0 |  | 3900 | -138 | 3762 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: licensing and certification system for refrigeration technicians | Individual | LAC | NIC | REF | 45 | TRA | 14 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | NIC | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-10-01 |  | 1996-11-01 | 1999-03-01 | 40000 | -3825 | 36175 | 36175 | 100% | 0 | 0 |  | 5200 | -497 | 4703 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | NIC | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2002-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2000-05-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | NIC | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2002-08-01 |  | 2003-09-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | NIC | SEV | 39 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-10-01 | 2005-04-01 |  | 2007-03-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | NIC | SEV | 49 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-06-01 |  | 2009-09-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | NIC | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-12-01 |  | 2012-03-01 | 2013-12-01 | 30000 | 30000 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | NIC | SEV | 66 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-03-01 |  | 2014-03-01 | 2014-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | LAC | NIC | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2016-03-01 |  |  | 60000 | 0 | 60000 | 20696 | 34.49% | 39304 | 39304 | 20000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: NOO attended the Network meetings and the back to back bilateral sessions carried to monitor project implementation. Intermediate goals achieved as planned for the year 2014. (a) Progress and financial reports prepared by the NOU. (b) First cash advance released; (c) 2014 budget and work plan duly implemented; (d) ODSs license system implemented; (e) NOO collected ODS data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (f) Article 7 data and CP progress report data submitted in 2014; (g) NOU is responsible for providing support to the HPMP implementation. (h) On 16 September, the Minister of Environment cellebrated the International Ozone Day trough an oficial ceremony for awarding the winners of a national children painting contest. Legal arrangements (actual/planned): July 2014/May 2014. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): August 2014/Planned for June 2014. All funds disbursed? No. Any delay? No significant delays. If Yes, will delay have impact on project completion date? Minor delays. Hpwever, Project renewal to be submitted to the 75 ExCom meeting. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The SSFA (agreement) implementation is progressing without significant delays. Second disbursement released. Intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Half year progress and financial report submitted to UNEP. Legal arrangements (actual/planned): July 2014/May 2014. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): August 2014/Planned for June 2014. All funds disbursed? No. Any delay? No significant delays. If Yes, will delay have impact on project completion date? Yes. However, Project renewal to be submitted to the 75 ExCom meeting. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | NIR | FUM | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -16990 | 8010 | 8010 | 100% | 0 | 0 |  | 3250 | -2209 | 1041 | 0 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Niue) | Multi-year | ASP | NIU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 | 2015-12-01 |  |  | 45625 | 0 | 45625 | 27388 | 60.03% | 18237 |  | 18237 | 5931 | 0 | 3160 | 2771 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014, but no request for the import of HCFC. Based on 2014 Country Programme, Niue maintained zero HCFC consumption. Report to be submitted on time and on the required quality. The Niue Customs has adopted the 2012 HS code for the ODS import and export control. Refrigerant identifier was handed over to Customs for inspection. National training workshop for RAC technicians was organized in May 2014 with 12 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. Due to very small number of technicians (3) and limited scope of the industry in the countries, national RAC Association may not be practical. Instead, the technicians will use the website for PIC RAC Association and align with Tonga RAC Association to allow for information exchange. Ongoing awareness raising and monitoring of HPMP implementation. The SSFA has been signed in September 2011. First Mission: August 2013 TOR completed: N/A First disbursement date: October 2011 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Lost of NOU since May of 2013. No new NOU since appointed. NEP maintained constant communication with interim senior management encouraging the early appointment of required staff and to address delays. New NOU planned to be recrutied in the second half of 2015. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: No | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted. Training New NOU in the HPMP management including reporting requirements (progress and financial report). Assisted the NOU in the preparation of legal draft required for the private sector use and date management of the RAC equipment provided under the HPMP
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NIU | REF | 44 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2009-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 |  |  | 1820 | -426 | 1394 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NIU | REF | 44 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2010-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  |  | 1040 | 0 | 1040 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NIU | SEV | 44 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-06-01 | 2007-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NIU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 15000 | -4900 | 10100 | 10100 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | NIU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NIU | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | NIU | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-09-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | NIU | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 |  | 45000 | 0 | 0 | 0 | 0 | 0 | Brief progress reports: Progress: Slow rate in IS project implementation. Country through the Department of Environment prepared the required reports to support the HPMP tranche 2 submission. CP data for 2014 submitted. Country for the third year has reported zero consumption of ODS. Country attended regional network and customs training meeting in Tonga 2014. 2014 international ozone day report submitted. Government is using inhouse huuman resources for implementation of project. All activities are implemented through the staff of the National Environment office and supervised by the Head of department. Legal agreement (SSFA) signed in April 2014. First payment in May of 2014. All funds disbursed (yes/no): No, IS balance as of May 2015 of USD 45,000. Amy delays? (yes/no): Yes If yes, reasons for delay & action plann to resolve: Lost of NOU since May of 2013. No new NOU since appointed. UNEP maintained constant communication with interim senior management encouraging the early appointment of required staff and to address delays. New NOU planned to be recrutied in the second half of 2015. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. If Yes, is any action required by ExCom: No. | 2014 country programme submitted to Multilateral Fund Secretariat in 2015.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | OMA | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-06-01 | 2009-07-01 |  | 2011-12-01 | 2014-05-14 | 50000 | -11000 | 39000 | 39000 | 100% | 0 |  |  | 6500 | -1430 | 5070 | 0 | 0 | Project financialy Completed | Project financialy Completed
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | TAS | 22 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2015-11-01 | 2015-11-01 |  |  | 65000 | 0 | 65000 | 42899 | 66% | 22101 |  | 22101 | 8450 | 0 | 3055 | 5395 | 3055 | Brief progress report (actual/planned): The NOC established by ministerial decision No. 121/2012 holds regular meetings which highly contributed to the enhancement of the ODS decision making on a more participatory fashion. Oman enacted an updated ODS regulations by ministerial decision no. 107/2013 as required by the unified GCC regulations. Oman currently operates a strict licensing and quota system that includes HCFCs. All preparatory works including the design and components of the database for a web based licensing system have been completed during 2013. Due to the ministry's plan to integrate this system into a more comprehensive national licensing system for all chemicals which is being currently finalized, it is expected to have this activity completed during early 2015. The RAC curricula reviewed and updated as required to include the latest developments related to HCFCs phase out. Several technical and policy meetings took place to discuss and agree on the CoP and to finalize the institutional requirements for setting up a sound certification system for RAC technicians including the review of the existing vocational standards to meet with the current requirements under the HPMP. The CoP was drafted and is being finalized in close consultation with relevant bodies. General outlines of a certification system have been drafted and an international consultant worked closely with UNEP and respective national authorities in developing the required standards, working procedures and tools including tools for assessment. A study tour was organized to the Philippines to exchange experiences on operating such certification systems. A train the trainers training workshop on certification and good practices was held during 7-11 Sept. 2014 in Muscat with participation of 20 trainers from all governorates along with a regional experts meeting on certification. Legal arrangements (actual/planned): The SSFA agreement for the implementation of the first stage under HPMP was finalized and signed in Feb. 2013 and still valid till Nov 2015. mission (actual/planned): several missions to the country took place during 2014 to finalize CoP and certification systems expedite implementation of other planned activities - TOR completed (actual/planned): completed - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): 1st disbursement done in Q2 2013 All funds disbursed (yes/no): No, second payment is pending due to late submission of financial progress report. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the LS. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | The development of e-Licensing is being finalized as part of a global licensing process within the ministry and it's expected to be completed during 2015. however, the ministry is currently granting electronic permissions via a specialized portal of the Customs dept. ; the updated ODS regulations are being enforced effectively through full engagement of NOC and stakeholders. A meeting organized in Feb 2015 with the NOC, NOU and UNIDO to discuss and follow up the progress in implementing the remaining activities under 1st stage and agree on steps required to complete the project as planned by 2015; a steady progress is being made towards finalizing all technical and set up arrangements for adopting the national certification scheme for RAC technicians. A follow up meeting organized in Feb 2015 with the Oman Occupational Standards and Certification Center to review the progress made and to provide technical support for finalizing the certification system for adoption by the respective bodies in Oman. a full package of technical and procedural requirement for certification have been prepared and submitted to respective authorities for adoption. it is hoped that the system to be adopted during 2015.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | OMA | PHA | 73 | PRP | 26 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-11-01 | 2015-11-30 |  |  | 27000 |  | 27000 | 0 | 0% | 27000 |  | 27000 | 3510 | 0 | 0 | 3510 | 0 | Brief progress report (actual/planned): Newly approved project | Brief progress report (actual/planned): UNEP-UNIDO coordination meeting with NOU and NOC organized in Feb. 2015 to discuss and agree action plan for preparation. Country contract for stage II preparation is being finalized for signature. A mission is planned in July to expedite implementation and conduct consultation with all concerned stakeholders.
FIN | UNEP | Policy and technical assistance | Individual | ASP | OMA | SEV | 37 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2006-02-01 | 2008-12-01 | 10000 | -52 | 9948 | 9948 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | PAK | ARS | 56 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2011-11-01 |  | 2011-11-01 | 2012-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | PAK | PHA | 55 | PRP | 69 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 60000 | -1019 | 58981 | 57055 | 96.73% | 1926 |  |  | 7800 | -132 | 7417.15 | 250.85 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 |  |  | 26000 | 0 | 22754 | 3246 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | PAK | PHA | 70 | TAS | 84 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2014-07-01 | 2015-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 |  | 200000 | 26000 | 0 | 0 | 26000 | 0 | Brief progress report (actual/planned): Consultative Meeting of HCFC Importers/Industries in Karachi and site visits to 3 companies in July 2014. In Aug. 2014, a study tour to Beijing and cities in Guangdong Province to learn about HCFCs alternatives and phase-out approaches. 1 face-to-face meeting (May 2014) and 1 virtual meeting (Aug. 2014) held between Pakistan and Afghanistan authorities to discuss ODS trade issues. Press coverage on HCFCs quota, etc. Legal arrangement (actual/ planned): The SSFA signed in Oct. 2013. First mission (actual/ planned): The 3rd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: 20/03/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Severe delay, mainly due to prolonged absense of a NOO. UNEP is coordinating with UNDP to expedite the appointment of a new NOO. High-level bilateral meeting organized in May 2015 to reiterate to the government urgency of resolving the problem. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): In Jan. 2015, a half-day servicing sector awareness workshop held (32 participants). HCFCs quota 2015 issued and the information shared through iPIC. Agreement between NOU and Sindh Technical Education and Vocational Training Authority (STEVTA) drafted.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | PAK | PHA | 72 | PRP | 88 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-10-01 | 2015-05-01 | 2016-04-01 |  |  | 48000 |  | 48000 | 35638 | 74.25% | 12362 |  | 12362 | 6240 | 0 | 0 | 6240 | 0 | Brief progress report (actual/planned): Draft documents prepared. Data collaction on-going. Legal arrangement (actual/planned): N/A. First mission (actual/ planned): To be done in Oct. 2015. TOR completed (actual/ planned): A local consultant hired in Oct. 2014. First disbursement date: Oct. 2014. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: absense of NOO. If Yes, will delay have impact on project completion date (yes/no): close coordination with UNIDO and UNDP and official communications with senior governmental officers. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | The draft is under preparation and consultations with UNIDO as lead agency are ongoing. The country considers to submit the project at the first meeting of ExCom in 2016.
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | PAK | PHA | 73 | TAS | 90 | A | I | HCFC-22 | 5.4 |  |  |  | 2014-11-01 |  | 2015-11-01 | 2017-03-01 |  |  | 40000 |  | 40000 | 0 | 0% | 40000 |  | 40000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): Implementation yet to start. Legal arrangement (actual/planned): Agreement prepared. First mission (actual/ planned): The 4th quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: The 3rd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: absense of NOO to process the agreement. If Yes, will delay have impact on project completion date (yes/no): no. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Agreement with the government signed in June 2015, but disbursement pending.
FIN | UNEP | Country programme preparation | Individual | ASP | PAK | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1996-06-01 | 1996-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-year | LAC | PAN | PHA | 47 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-year | LAC | PAN | PHA | 50 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-09-01 | 2007-11-01 |  | 2011-06-01 | 2011-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | PAN | PHA | 65 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2015-12-31 |  |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | -1.4779e-12 | 0 | 4550 | 0 | 4135 | 415 | -1.9213e-13 | Brief progress report: The implementation of the tranche is progressing well. Intermediate goals achieved in the first tranche are as planned for 2014: (a) Capacity building and awareness rising of public and private stakeholders in several regions of Panama. (b) The Government of Panama granted annual HCFC import licenses to 33 importers. (c) In addition, the ban on imports of pure HCFC-141b for use in the refrigeration servicing sector entered into force on 1 January 2014. Legal arrangements: CAP staff is implementing the project directly based on an official request from the Director of Environmental Health, who is the Montreal Protocol Focal Point in Panama. First mission: N/A. Regional CAP staff is based in Panama. 2 meetings carried out during the year for providing support to NOU with planning and mid-term review, while no specific actions established in the project document. TOR completed (actual/planned): N/A. Direct payments were issued to suppliers and contractors. First disbursement date: June 2012/Planned for May 2012. All funds disbursed: No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reassons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | Brief progress report: The implementation of the tranche is progressing well. The NOU participates in the committee on standards for HC and will support the preparation of regulations for HC-based refrigerants. In cooperation with Implementing Agencies the progress report and annual implementation plan were submitted to request the third tranche. Legal arrangements: CAP staff is implementing the project directly based on an official request from the Director of Environmental Health, who is the Montreal Protocol Focal Point in Panama. First mission: N/A. Regional CAP staff is based in Panama. A meeting carried out for providing support to NOU with planning of 2015 activities. TOR completed (actual/planned): N/A. Direct payments were issued to suppliers and contractors. First disbursement date: June 2012/Planned for May 2012. All funds disbursed: No. Any delay? Some delays. If Yes, reasons for delay & action plan to resolve: Administrative reasons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | PAN | PHA | 70 | TAS | 35 | A | I |  | 0.7 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-07-01 | 2016-06-01 |  |  | 26600 | 0 | 26600 | 10976.2 | 41.26% | 15623.8 | 0 | 6200 | 3458 | 0 | 0 | 3458 | 0 | Brief progress report: Project implementation as expected. Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port . NOU is in close coordination with Customs Officer to detect ODSs illegal trade shipments and to exchange information related to HCFCs license systema. 18 customs officers trained in HCFC licensing and quotas and the correct use of ODS identifiers in two worshops in Feb-14. 24 customs brokers were trained in ODS controls and classification in Mar-14. Legal arrangements: Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. First disbursement date (actual/planned): January 2014/Planned for January 2014. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The implementation of the HPMP (second tranche) is progressing with minor delays. Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port . NOU is in close coordination with Customs Officer to detect ODSs illegal trade shipments and to exchange information related to HCFCs license systema. Legal arrangements: Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. First disbursement date (actual/planned): January 2014/Planned for January 2014. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
FIN | UNEP | Development of refrigerant management plans | RMP | LAC | PAN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: monitoring on assistance to develop legislation | Individual | LAC | PAN | REF | 29 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2002-12-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training and certification programme in refrigeration | Individual | LAC | PAN | REF | 29 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2008-12-01 | 2010-12-01 | 126200 | 0 | 126200 | 126200 | 100% | 0 | 0 |  | 16406 | 0 | 16406 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Project preparation for refrigerant management plan update | RMP update | LAC | PAN | REF | 40 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-03-01 | 2004-07-01 |  | 2004-10-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | PAN | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | -3000 | 27000 | 27000 | 100% | 0 | 0 |  | 3900 | -390 | 3510 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | PAN | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-04-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 | 0 |  | 22425 | 0 | 22425 | 0 | 0 | Project financially completed. | Project financially completed. |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PAN | SEV | 31 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2002-08-01 |  | 2002-12-01 | 2004-10-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening (phase 3) | Individual | LAC | PAN | SEV | 38 | INS | 17 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2007-01-01 | 2010-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAN | SEV | 44 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2009-09-01 | 2006-12-01 |  | 2011-12-01 | 2011-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase V: 11/2011-10/2013) | Individual | LAC | PAN | SEV | 65 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2013-08-01 |  | 2014-12-31 | 2014-12-31 | 149500 | 0 | 149500 | 145628.32 | 97.41% | 3871.68 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | PAR | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-04-01 | 2011-04-01 | 85000 | -6789 | 78211 | 78152 | 99.92% | 59 | 0 |  | 11050 | -883 | 10159.76 | 7.24 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-07-01 | 2011-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-Year | LAC | PAR | PHA | 60 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-10-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | TAS | 28 | A | I |  | 0.9 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2016-06-01 |  |  | 146500 | 0 | 146500 | 102027 | 69.64% | 44473 | 0 | 44473 | 19045 | 0 | 13264 | 5781 | 0 | Brief progress report: The SSFA (agreement) implementation carried out without significant delays. Intermediate goals achieved as planned for the year 2014: a) Banned the imports of HCFCs-based equipment for lower BTU ranges is in force. A Customs Code was established for the correct classification of the HCFC based equipment. Currently, the online control system has been updated to implement the HCFCs import quotas system as well as for the prohibition of equipment based on HCFCs. b) A meeting with environmental enforcement officers to inform about the banning of R-22 based RAC equipment carried out on November 27, 2014, attended by 29 participants. ODSs illegal trade control and prevention measures seminar carried out on October 15, 2014, attended by 28 environmental enforcement officers. Training on HCFC quota system operations carried out on July 31, 2014, attended by 20 environmental enforcement officers. On 22/04/2014 a seminar aimed to Customs Agents was carried out in Asunción del Paraguay. 15 enterprises who handle ODSs shipments attended the seminar carried out to inform on Customs Codes for registering respective imports. c) Training courses for front line officers carried out to explain the new HCFCs law and the HCFC illegal trade modalities. The courses were held in different cities of the country. A total of 78 front line officers aware on different aspects of HCFCs and HCFCs-based equipment verification methodology. These courses also facilitated coordination links and communication between Customs and the NOU. Legal arrangements: signed in April 2012/planned April 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report: HPMP progress report and 2nd tranche Annual Implementation plan submitted to the 74 ExCom meeting. Legal arrangements: signed in April 2012/planned April 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | PAR | PHA | 73 | TAS | 32 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2015-05-01 | 2015-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. Work Plan and budget drafted in December 2014. | Brief progress report: Verification report is implemented as planned. TOR and identification of Consultants completed in February 2015/Planned Feb 2015. Consultant hired in March 2015. Country mission conducted in April 2015/planned March 2015. Draft report delivered in May 2015. Final Report to be delivered in June 2015. Legal arrangement: N/A. First disbursement date: April 2015. All funds disbursed? No. Any delay? Minor delays in hiring consultants that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? No. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Individual | LAC | PAR | REF | 32 | TAS | 06 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2001-12-01 |  | 2008-12-01 | 2010-12-01 | 44920 | 0 | 44920 | 44920 | 100% | 0 | 0 |  | 5840 | 0 | 5840 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2003-06-01
FIN | UNEP | Implementation of the RMP: policy dialogue programme on complementary policy and enforcement | Individual | LAC | PAR | REF | 32 | TAS | 10 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2001-09-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: train of trainers and training of refrigeration service technicians | Individual | LAC | PAR | REF | 32 | TRA | 07 | A | I | CFC | 56.7 | 56.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-12-01 |  | 2008-12-01 | 2012-01-01 | 168020 | -2569 | 165451 | 165451 | 100% | 0 | 0 |  | 21843 | -333.97 | 21509 | 0.03 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | PAR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-10-01 |  | 1996-10-01 | 1999-05-01 | 43000 | -4000 | 39000 | 39000 | 100% | 0 | 0 |  | 5590 | -520 | 5070 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening | Individual | LAC | PAR | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 2000-02-01 |  | 2001-07-01 | 2001-12-01 | 66300 | 0 | 66300 | 66300 | 100% | 0 | 0 |  | 8619 | 0 | 8619 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | PAR | SEV | 32 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-01-01 | 2004-09-01 | 44200 | 0 | 44200 | 44200 | 100% | 0 | 0 |  | 5746 | 0 | 5746 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | PAR | SEV | 39 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2005-04-01 |  | 2009-07-01 | 2010-12-01 | 57460 | 0 | 57460 | 57460 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | PAR | SEV | 61 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 |  | 2013-03-01 |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | Project Completed in 2013. All funds disbursed. NOO submitted all progress and financial report. Cross checking of accounts between UNDP and UNON is in progress. Financial completion is pending. | Project Completed in 2013. NOO submitted all progress and financial report. All funds disbursed. Cross checking of accounts between UNDP and UNON is in progress. Financial completion is pending.
COM | UNEP | Extension of institutional strengthening project (phase VI: 7/2012-6/2014) | Individual | LAC | PAR | SEV | 66 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 |  | 2014-06-01 |  | 60000 | 0 | 60000 | 45081 | 75.13% | 14919 | 14919 | 14919 | 0 | 0 | 0 | 0 | 0 | Brief progress report: NOO attended the Network meetings and the back to back bilateral sessions carried to monitor project implementation. The implementation of the SSFA (agreement) completed with six months of delays. Intermediate goals achieved as planned for the year 2014. (a) Progress and financial reports prepared by the NOU. (b) Third cash advance released; (c) 2014 budget and work plan duly implemented; (d) ODSs license system implemented; (e) NOO collected ODS data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (f) Article 7 data and CP progress report data submitted in 2014; (g) NOU is responsible for providing support to the HPMP implementation. (h) On 16 September, the Minister of Environment cellebrated the International Ozone Day trough press releases and conferences on the implementation of Montreal Protocol in Paraguay. (i) Project renewal submitted to the 72 ExCom meeting. Legal arrangements (actual/planned): June 2012/Planned for June 2012. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: July 2012/ Planned for July 2012. All funds disbursed? Yes. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | Project Completed in December 2014. All funds disbursed. NOO submitted all progress and financial report. Cross checking of accounts between UNDP and UNON is in progress. Financial completion is pending.
ONG | UNEP | Extension of institutional strengthening project (phase VII: 7/2014-6/2016) | Individual | LAC | PAR | SEV | 72 | INS | 31 | A | I |  | 0 |  |  |  | 2014-05-01 | 2014-12-14 | 2016-06-30 | 2016-06-30 |  |  | 60000 | 0 | 60000 | 24035 | 40.06% | 35965 | 35965 | 24000 | 0 | 0 | 0 | 0 | 0 | Newly approved project. Work Plan and budget drafted in December 2014. | Brief progress report: Intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible of the HPMP implementation. Legal arrangement: completelly signed April 2015/initially planned for October 2014. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: First cash advance reeleased in May 2015. All funds disbursed? No. Any delay? Six months delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? No. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | PER | PHA | 50 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 55 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 |  | 2013-12-01 | 2013-12-01 | 77500 | -41234 | 36266 | 36266 | 100% | 0 | 0 |  | 10075 | -5361 | 4714 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2016-06-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 20000 | 3250 | 0 | 0 | 3250 | 0 | Brief Progress No progress. Legal arrangements: SSFA is not signed. UNEP submitted the document which was signed in the year of 2013. The Government did not sign the agreement even in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Oct 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of HCFCs license system. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. UNEP and UNDP joint country mission conducted in July 2013 to streamline HPMP implementation. Clarifications provided to the NOU Head about the pre-requisite of HCFC license/quota system is established before launching the HPMP implementation. ODSs revised liecense/quota system issued in September 2013 in order to meet the HCFCs baseline. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. | Brief Progress: No disbursements. Legal arrangements: The Government signed the agreement in May 2015. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Oct 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of HCFCs license system. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. UNEP and UNDP joint country mission conducted in July 2013 to streamline HPMP implementation. Clarifications provided to the NOU Head about the pre-requisite of HCFC license/quota system is established before launching the HPMP implementation. ODSs revised liecense/quota system issued in September 2013 in order to meet the HCFCs baseline. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | PER | REF | 21 | TRA | 21 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2002-12-01 | 2003-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: support for a licensing system | Individual | LAC | PER | REF | 27 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2002-02-01 | 2003-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | PER | REF | 27 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2002-02-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | PER | REF | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2004-05-01 | 2005-12-01 | 34000 | -13000 | 21000 | 21000 | 100% | 0 | 0 |  | 4420 | -1690 | 2730 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2001-12-01
FIN | UNEP | Preparation of the refrigerant management plan update proposal | RMP Update | LAC | PER | REF | 37 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-02-01 | 2003-08-01 |  | 2004-07-01 | 2008-12-01 | 15000 | -3000 | 12000 | 12000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | LAC | PER | REF | 43 | TAS | 34 | A | I | CFC | 30.9 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2007-12-01 |  | 2011-10-01 | 2012-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: refrigeration technicians certification and licensing system | Individual | LAC | PER | REF | 43 | TAS | 35 | A | I | CFC | 66.4 | 66.4 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 |  | 11180 | 0 | 11180 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP update: technical assistance for prevention of illegal CFC trade | Individual | LAC | PER | REF | 43 | TAS | 36 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2010-06-01 | 2011-03-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 3380 | 0 | 3380 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | PER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1995-07-01 | 1995-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | PER | SEV | 17 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1998-10-01 |  | 2000-08-01 | 2001-08-01 | 154000 | 0 | 154000 | 154000 | 100% | 0 | 0 |  | 20020 | 0 | 20020 | 0 | 0 | Project financially completed. | Project financially completed. |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PER | SEV | 29 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2002-06-01 | 2011-03-01 | 102700 | -30102 | 72598 | 72598 | 100% | 0 | 0 |  | 13351 | -3913 | 9438 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | PER | SEV | 37 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2011-06-01 | 2004-08-01 | 2016-06-01 |  |  | 133510 | 0 | 133510 | 116485 | 87.25% | 17025 | 17025 | 17025 | 0 | 0 | 0 | 0 | 0 | Brief Progress: No disbursements. Legal arrangements: The SSFA signed in 2011 is expired. Remaining budget to be obligated after the new SSFA is signed. UNEP submitted the document signed in 2013. The Governmentdid not sign the agreement in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Dic 2002/July 2011. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of clarity in who should be the Montreal Protocol in the Country. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. | Brief Progress: No disbursements. Legal arrangements: The SSFA signed in 2011 is expired. Remaining budget to be obligated after the new SSFA is signed. UNEP submitted the document signed in 2013. The Governmentdid not sign the agreement in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Dic 2002/July 2011. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of clarity in who should be the Montreal Protocol in the Country. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No.
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | PER | SEV | 68 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2014-12-01 | 2016-12-01 |  |  | 133510 | 0 | 133510 | 0 | 0% | 133510 | 42995 | 42995 | 0 | 0 | 0 | 0 | 0 | Brief progress report: No disbursements. Intermediate project goals achieved as follow: (a) ODSs license system implemented; (b) NOO collected ODSs data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. (c) Article 7 data and CP progress report data submitted; (d) On 16 September, the NOU organized an awareness raising activity ny means of mass media press releases. Legal arrangements: UNEP submitted a SSFA signed in 2013. The Government did not sign the agreement in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): June 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of clarity in who should be the Montreal Protocol in the Country. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. | Brief progress report: No disbursements. Intermediate project goals achieved as follow: (a) ODSs license system implemented; (b) NOO collected ODSs data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. Legal arrangements: UNEP submitted a SSFA signed in 2013. The Government did not sign the agreement in 2014. The SSFA was signed by the Ministry of Industry in May 2015. It is expected the signature of UNDP County Office is completed in July 2015. Due to fund management is planned through the office of UNDP in Peru, this signature is a pre-requisite to release funds to the country. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): June 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of clarity in who should be the Montreal Protocol in the Country. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | PHI | FUM | 30 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -8880 | 16120 | 16120 | 100% | 0 |  |  | 3250 | -1154 | 2096 | 0 | 0
ONG | UNEP | National CFC phase-out plan: Final implementation plan | Multi-Year | ASP | PHI | PHA | 66 | TAS | 94 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-05-01 | 2014-03-01 | 2015-12-01 |  |  | 1835205 | -1077221 | 757984 | 750000 | 98.95% | 7984 |  | 51630 | 154294 | -66785 | 36396 | 51113 | 0 | Brief progress report (actual/planned): Assisted the conduction of the audit report, and prepared all the internal and extenal reports as required by the MLF and the government for the close of NCPP project. Prepared and submitted the final payment request. The PCA was signed in October 2012 and amended in October 2013. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The last disbursement from UNEP to the country was delayed due to the discrepancy of Excom decisions on the approved amount to NCPP. If Yes, will delay have impact on project completion date (yes/no): No, as all substiantial activities have already been completed. Any ongoing problems (yes/no): Yes. If Yes, is any action required by ExCom: Yes, Excom needed to make decision on the approved amount for NCPP. This was addressed at the 74th Ex. Com. | The new decision of Excom was made at the 74th meeting. The last payment then could be released, and the project could be financially completed soon.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PHI | PHA | 68 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 | 2015-12-01 |  |  | 207000 | 1077221 | 1284221 | 207000 | 16.12% | 1077221 |  | 1033575 | 26910 | 124364 | 0 | 151274 | 0 | Brief progress report (actual/planned): The licensing and quota system was implemented in 2014. Despite a delay in transferring the first payment, which was made in June 2014, activities were implemented (i) preparation of Term of Reference (TOR) for hiring consultant/expert or (ii) coordination/meeting with other stakeholders to get their inputs to finalize the customs training manuals or intervention with policy. Procurement of equipment for servicing shops has not yet undertaken in 2014, but selection criteria of beneficiaries who will receive financial support is finalized in late 2014. The key achievements during the reporting period were organization of the training workshops for key stakeholders e.g. one train-the-trainer workshop and four workshops for Customs and enforcement officers, one train-the-trainer workshop and four workshops for RAC technicians and orientation/training on environmental laws and policy updates etc. The Code of Practices (COP) has been revised to include handling and servicing of flammable refrigerants such as HFC-32 and hydrocarbon R290) and was integrated to the training curriculum for service technicians. Collection, Transport and Storage (CTS) schemes was finalized in December 2014 to identified depository sites. Legal arrangements: The PCA has been signed in December 2013. First Mission: 2012. TOR completed: N/A First disbursement date: June 2014 All funds disbursed (yes/no): No, last disbursement will be on December 2015. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Slow rate of implementation. UNEP continues to work with country to expedite project. High level meetings held in the margins of the MOP26 with the UnderSecretary of Environment and Head of UNEP OzonAction seeking to address project implementation. At the end of 2014, UNEP OzonAction assigened additional CAP staff resources to support project management. If Yes, will delay have impact on project completion date (yes/no): yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No | The second payment as of PCA has been transferred to the government to implement the activities planned in March of 2015. Procurement of equipment for the CTS has been conducted and the award has been issued to the bidding winner. The procurement of equipment for servicing workshops will be implemented in 2015. Country mission to review status and support implementation was conducted in March of 2015.
FIN | UNEP | Training programme for customs officials and other key stakeholders | Individual | ASP | PHI | REF | 35 | TRA | 66 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2005-12-01 | 2006-11-01 | 170250 | -3588 | 166662 | 166662 | 100% | 0 |  |  | 22133 | -466 | 21667 | 0 | 0
FIN | UNEP | Information exchange programme | Individual | ASP | PHI | SEV | 11 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1995-12-01 |  | 2000-12-01 | 2003-07-01 | 200000 | -1488 | 198512 | 198512 | 100% | 0 |  |  | 26000 | -193 | 25807 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | PHI | SEV | 64 | INS | 92 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-10-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 65 | INS | 93 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 64471 | 0 | 64471 | 64471 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | ASP | PHI | SEV | 70 | INS | 96 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-09-01 | 2015-12-01 | 2015-12-01 |  |  | 181133 | 0 | 181133 | 90566.5 | 50% | 90566.5 |  | 90566.5 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system was strictly implemented in 2014. NOU conducted regular monitoring of HCFC importers including warehouse inspection. There has been continuous coordination with the Bureau of Customs (BOC) regarding the import/export of ODS. The NOU hosted the South-South Cooperation Study Tour on the Certification Schemes for Refrigeration and Airconditiong (RAC) Technicians and Accreditation of Service Shops. The IS Project supports the continuous implementation of the stand alone investment project on HCFC-141b phase out in the foam sector in coordination with UNIDO and continuous coordination meeting with BOC for the conduct of the Train-the-Trainers Workshop for BOC and Other Enforcement Agencies for the HPMP implementation. The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. Public awareness raising activity such as the publication of DAO no. 25 s. 2013 in a major newspaper was carried out in 2014. The NOU took the leadership in developing regional notebook and poster, which were distributed to all other countries in South-east Asia network. Legal arrangements (actual/planned): The SSFA was signed in April 2014. Initial stages of project implementation (actual/planned): NOU is operating well. Intermediate goals achieved (actual/planned): implementation of the licensing and quota system; ensure that investment project on HCFC-141b phase-out in the foam sector and the HPMP be implemented as planned; develop stage II of HPMP including investment projects; monitor ODS imports; conducting public awareness activities; and data reporting to the Fund and Ozone Secretariats. First disbursement date: September 2014. All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The licensing and quota system and iPIC are being implemented in 2015. NOU keep close communication with concerned stakeholders to control the import and export of ODS. 2014 Country Programme has been timely reported.
TRF | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | PNG | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-09-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 |  | 0 |  | 0 | 3900 | -3900 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed. |  | 2009-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | PNG | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-02-01 | 1995-10-01 |  | 1996-05-01 | 1999-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Creation of an Ozone Unit | Individual | ASP | PNG | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1999-05-01 |  | 2003-12-01 | 2009-10-01 | 45800 | -24715 | 21085 | 21085 | 100% | 0 |  |  | 5954 | -3213 | 2741 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | PRC | PHA | 48 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | -9 | 17991 | 17991 | 100% | 0 | 0 |  | 2340 | -1 | 2339 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2011-03-01 | 2012-03-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 |  | 8840 | 0 | 8840 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | PRC | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-10-01 | 2011-04-01 |  | 2012-01-01 | 2013-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2014-03-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5200 | 650 | 0 | Project Complete | HPMP tranche 2 approved
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | PRC | PHA | 71 | TAS | 26 | A | I |  | 0.4 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 20000 | 20000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Country signed the SSFA in January 2014: Agreement signed in January 2014. Two workshops for 60 refrigeration technicians organised in Brazavill between July and December 2014. One workshop for Customs officers organized in Pointe Noire in Ocober 2014. All activities under the SSFA are completed (as planned) _ First mission (actual/planned): _ June 2014- Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country organized a workshop for 25 Customs officers at the main port of Brazaville in March 2015 and submitted an activity report to UNEP for a second payment. A conference on HCFCs based equipment was organized in June 2015.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | PRC | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance for information-sharing | Individual | AFR | PRC | REF | 32 | TAS | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-01-01 |  | 2003-12-01 | 2005-02-01 | 16000 | -2967 | 13033 | 13033 | 100% | 0 | 0 |  | 2080 | -386 | 1694 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | PRC | REF | 32 | TRA | 09 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-12-01 |  | 2003-12-01 | 2005-01-01 | 69400 | -25378 | 44022 | 44022 | 100% | 0 | 0 |  | 9022 | -3299 | 5723 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | PRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  | 1995-07-01 | 1996-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | PRC | SEV | 17 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 2000-12-01 | 2001-12-01 | 62920 | 0 | 62920 | 62920 | 100% | 0 | 0 |  | 8180 | 0 | 8180 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | PRC | SEV | 32 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 41950 | 0 | 41950 | 41950 | 100% | 0 | 0 |  | 5454 | 0 | 5454 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | PRC | SEV | 39 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2005-12-01 | 54531 | 0 | 54531 | 54531 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extensionl of the institutional strengthening project (phase IV) | Individual | AFR | PRC | SEV | 45 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-04-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | PRC | SEV | 51 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | PRC | SEV | 57 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | PRC | SEV | 64 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 |  | 2013-10-01 | 2014-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | PRC | SEV | 71 | INS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-07-01 | 2009-03-01 |  | 2014-07-01 | 2014-05-14 | 65000 | -45000 | 20000 | 15000 | 75% | 5000 |  |  | 8450 | -5850 | 1950 | 650 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | QAT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-01-01 | 2009-07-01 |  | 2011-08-01 | 2014-05-14 | 30000 | -1000 | 29000 | 29000 | 100% | 0 |  |  | 3900 | -130 | 3770 | 0 | 0 | Project financialy Completed | Project financialy Completed
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-11-01 |  | 2014-12-01 |  | 55000 | -55000 | 0 | 0 |  | 0 |  | 0 | 7150 | 0 | 0 | 7150 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | TAS | 17 | A | I |  | 1.3 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 | 2016-12-01 |  |  | 105000 | 0 | 105000 | 0 | 0% | 105000 |  | 105000 | 13650 | 0 | 0 | 13650 | 0 | Brief progress report (actual/planned): - Country contract for UNEP's non-investment activities remains pending waiting country comments and input on the work-plan. Investment components for the foam conversion are almost completed by UNIDO as it deals directly with the private sector. - Several follow-ups and side-meetings with NOU and officials in margins of regional. International events - Preparation for the 2nd tranche request was made by UNIDO and UNEP along with verification for 2013 data aiming to submit the 2nd tranche to the 73rd ExCom but no support letter was provided by country. Same for the ExCom-74 - UNIDO and UNEP submitted the request for the preparation of Stage-II of the HPMP which is approved by ExCom-73 • Legal arrangements(actual/planned): No signed yet • First mission (actual/planned): Three attempts for joint missions with UNIDO to the country were postponed • TOR completed(actual/planned): TORs for technical components were drafted and handed to NOU for comments/inputs and action • First disbursement date (actual/planned): No • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract and responses from the country • If Yes, will delay have impact on project completion date (yes/no): Yes, 2nd tranche delayed by 2 years • Any ongoing problems (yes/no): Yes, message from ExCom would be helpful to alert the country about delays consequences • If Yes, is any action required by ExCom: No | # Meeting with MoE officials in margins of network meeting to push for country action and feedback. New ODS Officer is likely to be appointed shortly. # Plans are made to visit the country during the 3rd quarter of 2015 and bring the project back on track.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | QAT | PHA | 73 | PRP | 20 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 20000 |  | 20000 | 0 | 0% | 20000 |  | 20000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): Newly approved project | • Brief progress report (actual/planned): - Work not started yet due to delay in start Stage-I • Legal arrangements(actual/planned): No • Initial stages of project implementation(actual/planned): No • Intermediate goals achieved (actual/planned): N/A • Project completion and follow up: Planned to be completed by end of 2016 • First disbursement date (actual/planned): 2015 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in start of Stage-I • If Yes, will delay have impact on project completion date (yes/no): Project completion is likely to be shifted by one year to be end of 2016 • Any ongoing problems (yes/no): Yes, slowness of response from the country • If Yes, is any action required by ExCom: No
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | RWA | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | RWA | PHA | 53 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | RWA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-07-01 | 2012-07-01 | 85000 | -5000 | 80000 | 80000 | 100% | 0 | 0 |  | 11050 | -650 | 10400 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2013-04-01 | 2014-06-01 | 67000 | -6987 | 60013 | 60012.93 | 100% | 0.07 | 0 |  | 8710 | -909 | 7801 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2016-07-01 | 2014-12-01 |  | 42000 | 0 | 42000 | 22000 | 52.38% | 20000 | 15000 | 15000 |  | 0 | 4810 | -4810 | 0 | Brief progress report (actual/planned): __Country implementing second tranche activities. NOU conducted training for both customs officer and refrigeration technicians. 40 customs officers and 30 refrigeration technicians were trained. NOU conducted inspection visists to major boarders and conducted briefings with all the enforcement officers at the boarders on the enforcement of national ODS legislation. Legal arrangements (actual/planned): SSFA was signed in July 2012. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visited the Country in June, 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in August, 2012.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Project completed and country implementing second tranche
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | RWA | PHA | 70 | TAS | 22 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-07-01 | 2016-07-01 | 2016-07-01 |  |  | 40000 | 0 | 40000 | 19317.4 | 48.29% | 20682.6 | 20683 | 20683 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): __The NOU trained 70 technician in the use of hydrocarbon refrigerant as alternative to HCFC. Country hosted Regional workshop on certification and standards and certified 5 technicians using European Standards. A total of 30 custom officers were trained on monitoring and control of ODS. NOU organised 2 meetings of the Refrigeration Association to discuss on certification of informal technicians and on additional training for technicains based in outside the Capital Kigali.Legal arrangements (actual/planned): SSFA was signed in April 2014. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visited the Country in June, 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in July, 2014.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Country processed allocation of 2015 HCFC quotas, conducted the planning meeting of the refrigeration association and conducted inspection visits to major reatail shops of refrigerants
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | RWA | REF | 41 | TAS | 09 | A | I | CFC | 2.2 | 0 | 0 | 0 | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2012-01-01 | 20000 | -10000 | 10000 | 10000 | 100% | 0 | 0 |  | 2600 | -1300 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | AFR | RWA | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | RWA | REF | 41 | TRA | 07 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 | 2013-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | RWA | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2007-03-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 |  | 6500 | -4550 | 1950 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2003-04-01 |  | 2005-01-01 | 2007-03-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 41 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2007-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 64600 | 0 | 64600 | 64600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | RWA | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2010-12-01 | 60000 | -3852.45 | 56147.55 | 56148 | 100% | -0.45 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | RWA | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-03-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | RWA | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-06-01 |  | 2013-04-01 | 2014-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase V: 7/2013-6/2015) | Individual | AFR | RWA | SEV | 70 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 | 2015-06-01 |  |  | 60000 | 0 | 60000 | 46500 | 77.5% | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU conducted random monitoring of border posts to check on illegal importation of ODS. A local company was contracted to control illegal importation of HCFC and to work alongside Rwanda Bureau of Standards. NOU submitted 2013 ODS data and CP report. The NOU celebrated 2014 International Ozone Day and participated in all Montreal Protocol meetings. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in December 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment ($19,500) was sent. Feb. 2014, 2nd payment ($13,500) was sent. Sept. 2014._ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Collection of the 2014 data on ODS imports and consumption is ongoing. NOU registered all importers of HCFC for 2015 calender year and processed for quota allocation
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | SAM | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-06-01 | 2008-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 | 2010-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Samoa) | Multi-Year | ASP | SAM | PHA | 63 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-12-01 |  |  | 76250 | 0 | 76250 | 71252 | 93.45% | 4998 |  | 4998 | 9913 | 0 | 7915 | 1998 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted. The provisions for licensing for storage, sale, distribution, purchasing and handling of ODSs including HCFCs have been put in place. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. RAC Association was re-established under the support of NOU through HPMP. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. The recovery machines have been kept at the NOU tool bank and released to technician upon request from time to time. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in August 2012. TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards.
FIN | UNEP | Implementation of the RMP: training of customs officials and NOU staff | Individual | ASP | SAM | REF | 32 | TRA | 03 | A | I | CFC | 2 | 2 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-06-01 |  | 2003-09-01 | 2003-12-01 | 53500 | -9474 | 44026 | 44026 | 100% | 0 |  |  | 6955 | -1232 | 5723 | 0 | 0 |  |  |  | 2003-06-01
FIN | UNEP | Implementation of the RMP: training of refrigeration service technicians | Individual | ASP | SAM | REF | 32 | TRA | 04 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-02-01 |  | 2002-10-01 | 2003-10-01 | 48800 | -5864 | 42936 | 42936 | 100% | 0 |  |  | 6344 | -762 | 5582 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | SAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1995-06-01 |  | 1997-05-01 | 1999-02-01 | 35000 | -4850 | 30150 | 30150 | 100% | 0 |  |  | 4550 | -631 | 3919 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Committee | Individual | ASP | SAM | SEV | 22 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-04-01 | 2000-06-01 |  | 2003-04-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of the refrigerant management plan | RMP | ASP | SAM | SEV | 25 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-12-01 |  | 2000-12-01 | 2002-06-01 | 0 | 30000 | 30000 | 30000 | 100% | 0 |  |  | 0 | 3900 | 3900 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 2) | Individual | ASP | SAM | SEV | 39 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2005-04-01 |  | 2006-01-01 | 2009-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SAM | SEV | 47 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | SAM | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | SAM | SEV | 58 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-10-01 |  | 2011-12-01 | 2011-12-01 | 35000 | 25000 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI: 11/2011-10/2013) | Individual | ASP | SAM | SEV | 64 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-10-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase VII: 11/2013-10/2015) | Individual | ASP | SAM | SEV | 70 | INS | 17 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-10-01 | 2015-10-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project being implemented satisfactorily. NOO is the lead national responsible for all activities approved under the HPMP tranche 1. Project implementation is proceeding satisfactorily. NOO managed all HPMP implementation requirements both nationally and sub-regionally as part of the PIC regional HPMP and including: the national capacity building and including Customs, RAC technicians and other targeted stakeholders. National Montreal Protocol legislation completed, Refrigeration Association registered and actively functioning. NOO organised and manged quarterly meetings held with national ozone steering committee. Implementation of the HPMP to meet 2014 HCFC freeze target; the NOU is institutionalised into as part of government and with the NOO supervised and managed under designated high level public sector officers ; 2013 data reporting to the Fund and Ozone Secretariats completed as planned. 2014 CP data submitted on -line. NOU prepared and submitted IS terminal and renewal reports for the 74th Ex. Com. Legal Arrangement: SSFA signed on March of 2014: First Disbursement May 2014. All funds disbursed (yes/no): No Any delay? (yes/no): No . Any ongoing problems (yes/no): No. | The NOU, now a section titled Ozone Section under the Meteorology department in the Ministry of Natural Resources, Environment (MNRE), has established working mechanisms with the public and private sector stakeholders and developed a more institutional approach rather than a project to project approach. Regular meetings of the national ozone steering committee and Stakeholder committee took place to share knowledge of project activities and enhance linkages with the NOU’s activities. Efforts were made to strengthen and facilitate data collection processes to improve the quality and ensure the timeliness of Article 7 and country programme data. Coordination between Customs and the NOU has improved greatly since the Joint Customs and Ozone Officers Meeting in Tonga in March 2014. The licensing and quota system for HCFCs was effectively implemented and shipments are inspected for any illegal imports. The implementation of activities under the institutional strengthening programme is well underway and most objectives in phase VII have been successfully achieved. NOU is also the manager of the HPMP. NOU prepared and submitted required reports for the HPMP Stage 1 Tranche 2 (74th meeting). NOU also prepared and submitted IS for renewal to the 74th Ex. Com.
FIN | UNEP | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-01-01 | 2009-03-01 |  | 2014-12-01 | 2014-11-14 | 364500 | -131861 | 232639 | 232639 | 100% | 0 |  |  | 47385 | -17142 | 30243 | 0 | 0 | Brief progress report (actual/planned): draft bylaws for the enforcement of the updated GCC regulations on ODS has been prepared and circulated in Nov. 2013 for inputs from all concerned authorities. a follow up consultation meeting took place in Riyadh during May 2014 to continue discussions with stakeholders on the draft update of the ODS bylaws and to advance the preparation of the certification scheme; Steady progress has been made towards the update of the RAC curricula and code of practice, and adoption of national certification scheme for RAC technicians. A study visit to the Philippines has been organized during Feb. 2014 where 2 national official experts from the NOU and the VET authority participated to get exposed to the advanced experience of the Philippines with regards to the operation of such scheme and related accreditation systems for servicing sector. International expert has been recruited to assist in developing and adopting an operational certification scheme including occupational standards, entry and final tests and required procedures. A refresher TT training workshop organized during July 2014 along with consultation workshop for all stakeholders. Technicians training will follow in 2015 when agreement reached with the vocational training authority; Engagement of stakeholders has been strengthened through supporting regular meeting of the NOC. Activities for Customs are pending the finalization and adoption of the updated bylaws. The remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting Legal arrangements (actual/planned): SSFA with the NOU expired. However, UNEP has been working with the country to expedite implementation and explore other options for funds transfer. mission (actual/planned): several missions to KSA during 2014 to expedite implementation - TOR completed (actual/planned): completed - with CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in Jan 2009 All funds disbursed (yes/no): No, Remaining funds have been returned. Any delay? (yes/no): n/a as activities have been integrated in the HPMP If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Project completed and the remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SAU | PHA | 55 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-02-01 | 2009-07-01 |  | 2013-12-01 | 2014-05-14 | 65000 | -9234 | 55766 | 55766 | 100% | 0 |  |  | 8450 | -1200 | 7250 | 0 | 0 | Project financialy Completed | Project financialy Completed
FIN | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2011-07-01 |  | 2014-07-01 | 2014-11-14 | 40500 | -2646 | 37854 | 37854 | 100% | 0 |  |  | 5265 | -343.98 | 4921.02 | 0 | 0 | Brief progress report (actual/planned): The remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting; a draft bylaws for the enforcement of the updated GCC regulations on ODS have been prepared and circulated in Nov. 2013 for inputs from all concerned authorities. a follow up consultation meeting is planned during May 2014; recruitment of an international expert has been initiated to assist in the update of the RAC curricula and code of practice, and adoption of national certification scheme for RAC technicians; the engagement of stakeholders have been strengthened through supporting regular meeting of the NOC. The NOC met in Nov. 2013 with UNEP participation. Activities for Customs are pending the finalization and adoption of the updated bylaws. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities at national level is not signed yet due to difficulties faced by the NOU to open a special account to receive projects funds. However, UNEP has been working with the country to expedite implementation and explore other options for funds transfer mission (actual/planned): several missions to KSA during 2013 to expedite implementation in with first mission in Feb 2013 to launch the HPMP - TOR completed (actual/planned): completed - with CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in Jan 2009 All funds disbursed (yes/no): No, Remaining funds as of Dec 013 will be returned Any delay? (yes/no): n/a as activities have been integrated in the HPMP If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Project completed and the remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-10-01 | 2015-12-01 | 2015-12-01 |  |  | 233674 | 0 | 233674 | 22985 | 9.836% | 210689 |  | 210689 | 28946 | 0 | 222 | 28724 | 0 | Brief progress report (actual/planned): A follow up consultation meeting took place in Riyadh during May 2014 to continue discussions with stakeholders on the draft updated ODS bylaws and to advance the preparation of the certification scheme; slow progress towards the update of the code of practice while the RAC curricula updated, and adoption of the certification scheme for RAC technicians. A study visit to the Philippines has been organized during Feb. 2014 where 2 national experts participated to exchange experience about the operation of such scheme and related accreditation systems for servicing sector. International expert recruited to assist in developing and adopting an operational certification scheme including guidance for updating the national occupational standards, entry and final tests and required procedures. A refresher TT training workshop organized during July 2014 along with consultation workshop for all stakeholders. Technicians training will follow in 2015 when agreement reached with the vocational training authority; Engagement of stakeholders has been strengthened through supporting regular meeting of the NOC. Activities for Customs are pending the finalization and adoption of the updated bylaws. Activities for Customs are pending the finalization and adoption of the updated bylaws. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities at national level is not signed yet due to difficulties faced by the NOU to open a special account to receive projects funds. However, UNEP continued to implement directly as feasible and explore other options for funds transfer mission (actual/planned): several missions to KSA during 2014 to expedite implementation of planned activities. - TOR completed (actual/planned): completed - with CAP staff implementing directly key activities First disbursement date (actual/planned): 1st disbursement done in Oct. 2013 All funds disbursed (yes/no): No, Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: delay countersignature of the required SSFA for implementing project activities at national level. If Yes, will delay have impact on project completion date (yes/no): UNEP is still trying to agree with the country on the best options for expediting implementation to absorb the delays faced so far. Any ongoing problems (yes/no): the NOU has been unable to open a special account for receiving project's funds If Yes, is any action required by ExCom: n/a- different alternative modalities are being explored to resolve the problem | UNEP continued efforts with the country to resolve the issue of SSFA signature. however, UNEP continued assistance to adopt the updated ODS regulations. It was agreed to have all control measures and provisions included in one package for easy reference and better enforcement; The NOU, in cooperation with the NOC and concerned authorities, strictly enforced the agreed control measures including the new quota system to control the imports of HCFCs that was put in operation since January 2013. Extensive discussions and analysis took place to conclude on the possible ban on imports of HCFCs containing products, taking into account the availability of alternative technologies suitable to the circumstances in the country. A ban of disposable cylinders is currently being discussed and will be taken into account when adopting the updated regulations by 2015 as required by HPMP. Initiated support for development of a national strategy to encourage end-users of RAC equipment to carry out leak detection, repair and maintenance to minimize ODS emissions will be follow-up during the HPMP implementation; Preparation for customs training to take place during 2015 the trainings in 2015 as per the new requirements under the updated ODS regulations. Moreover, additional advanced identifiers (5 units) are being purchased for subsequent distribution after training.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-07-14 | 2015-12-01 | 2015-12-01 |  |  | 56726 | 0 | 56726 | 4014 | 7.076% | 52712 |  | 52712 | 7027 | 0 | 0 | 7027 | 0 | Brief progress report (actual/planned): The country agreement was still not signed resulting in delays in delivery. necessary follow up with the country to expedite contract signature to facilitate timely implementation and delivery as per the agreed plan; however, steady progress was made and two policy and technical workshops for the foam sector to assist in raising awareness of the PU end users and provide them along with the system house companies with the required TA and advice in concert with the phase out investment activities planned for the sector. the workshop organized during April 2014 jointly with UNIDO Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities at national level is not signed yet. (actual/planned): first mission in Feb 2013 to launch the HPMP with consultation meeting with the foam sector - TOR completed (actual/planned): completed - with CAP staff implementing directly key activities First disbursement date (actual/planned): May 2014 All funds disbursed (yes/no): No, Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: delay countersignature of the required SSFA for implementing project activities at national level. If Yes, will delay have impact on project completion date (yes/no): UNEP is trying to agree with the country on the best options for expediting implementation to absorb the delays faced so far. Any ongoing problems (yes/no): the country agreement is not signed yet. If Yes, is any action required by ExCom: n/a- different alternative modalities are being explored with the country to resolve the account problem | The country agreement was still not signed resulting in additional delays. UNEP continued to provide necessary technical and policy support to the NOU and foam sector. efforts made to follow up with the country concerning contract signature. Coordination with UNIDO continued as to ensure timely and sound HCFCs phase out in the foam sector
COM | UNEP | Institutional strengthening (establishment of Ozone Unit) | Individual | ASP | SAU | SEV | 53 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2010-11-01 |  | 2013-02-01 |  | 300000 | 0 | 300000 | 250000 | 83.33% | 50000 |  | 50000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Project completed but not financially closed with final payment (US$50,000) pending due to difficulty faced by the NOU to open a dedicated account for the project. Legal arrangements (actual/planned): a new legal instrument is required for transferring the remaining funds; Initial stages of project implementation (actual/planned): Not Applicable; Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for 2012. Project completion and follow up: Project implementation on hold. First disbursement date (actual/planned): First payment disbursed end 2008. All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Yes. Project not closed with final payment outstanding of US$50,000. If Yes, reasons for delay & action plan to resolve: Last payment of US$50K is still pending for a dedicated bank account to be open. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Following the change of top management in Country, the old bank accounts were seized and we are waiting for NOU to advise of new bank account for transferring funds. Process is complicated and time consuming. If Yes, is any action required by ExCom: No. | The last payment is pending the signature of the new SSFA which is under processing.
ONG | UNEP | Extension of the institutional strengthening project (phase II: 7/2012-6/2014) | Individual | ASP | SAU | SEV | 67 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-01 | 2016-03-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 |  | 200000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU is active in related international and regional meetings, particularly meetings relating to HFC issues. The NOU is functioning and implementing planned activities though of the persisting problem of receiving project funds due to lack of dedicated bank account. The NOU is securing funds for the planned activities through the PME resources in loan basis until the funds transfer issue is resolved. Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for 2013. Project completion and follow up: ongoing. First disbursement date (actual/planned): No funds disbursed. All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Yes with difficulty. If Yes, reasons for delay & action plan to resolve: No legal instrument can be established without bank account information and UNEP is working with the NOU to expedite the process of opening of a new AC. Legal arrangements (actual/planned): No legal instrument signed with Saudi Arabia, due to no bank account information received yet. Initial stages of project implementation (actual/planned): If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. waiting for NOU to advise of new bank account for transferring funds. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): NOU has been proactive in implementing and monitoring the implementation of the ongoing HPMP related projects including the development and/or updating the ODS policies and regulations to achieve the agreed phase out targets. The Quota and licensing systems have been strictly enforced during the reporting period. Several awareness and capacity building events have been organized in partnerships with concerned partners and stakeholders. NOU is active in related international and regional meetings, particularly meetings relating to HFC issues. Legal arrangements (actual/planned): No legal instrument signed with Saudi Arabia, due to no bank account information received yet. Initial stages of project implementation (actual/planned): NA. Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for 2013. Project completion and follow up: Project implementation still ongoing though of delayed expenditures. First disbursement date (actual/planned): No funds disbursed. All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: No legal instrument can be established without bank account information. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. waiting for NOU to advise of new bank account for transferring funds. The NOU advised that a new account has been opened recently and that they will provide the same soon. If Yes, is any action required by ExCom: No. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | SEN | FUM | 34 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 |  | 3250 | -1170 | 2080 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SEN | PHA | 48 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 109500 | -1000 | 108500 | 108500 | 100% | 0 | 0 |  | 14235 | -130 | 14105 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 |  | 13065 | 0 | 13065 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | TAS | 30 | A | I |  | 1.2 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2014-11-01 | 2015-12-01 |  |  | 100000 | 0 | 100000 | 99023 | 99.02% | 977 | 0 | 977.5 | 12887 | 0 | 12761 | 126 | 0 | Brief progress report (actual/planned): Country trained 30 customs officers in May 2014 in Dakar; also trained 91 refrigeration technicians between January and March 2014 in Saint-Louis, Kaolack and Kolda. Legal arrangements (actual/planned): Agreement signed in March 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2012 __ All funds disbursed (yes/no): _ Final payment being processed in march 2013.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | NOU organized two meeting of the Ozone steering committee. Verification report is being finalised and consultant has already submitted the draft.
FIN | UNEP | Training and upgrading for repair technicians | Individual | AFR | SEN | REF | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-11-01 |  | 1994-12-01 | 1995-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | SEN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 2000-12-01 | 2001-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: activities for supporting and monitoring the RMP | Individual | AFR | SEN | REF | 33 | TAS | 15 | A | I | CFC | 29.4 | 29.4 | 0 | 0 | 2001-03-01 | 2001-07-01 | 2003-12-01 |  | 2002-05-01 | 2003-06-01 | 44500 | -37 | 44463 | 44463 | 100% | 0 | 0 |  | 5785 | -4.81 | 5780 | 0.19 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | SEN | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1993-11-01 | 1993-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Ozone Focal Point | Individual | AFR | SEN | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1996-11-01 |  | 1997-12-01 | 1999-09-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0
FIN | UNEP | Expansion and upgrading of statistics networks for customs | Individual | AFR | SEN | SEV | 11 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1994-10-01 | 1994-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 3380 | 0 | 3380 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | SEN | SEV | 23 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-02-01 | 2000-02-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 |  | 15210 | 0 | 15210 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | SEN | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-12-01 |  | 2001-12-01 | 2003-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 |  | 15210 | 0 | 15210 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (Phase IV) | Individual | AFR | SEN | SEV | 36 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 5 | Individual | AFR | SEN | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | SEN | SEV | 47 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | SEN | SEV | 53 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | SEN | SEV | 59 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 82388 | 69713 | 152101 | 152101 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | AFR | SEN | SEV | 65 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 |  | 2013-09-01 | 2013-09-01 | 152101 | 0 | 152101 | 152101 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | AFR | SEN | SEV | 71 | INS | 33 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2015-12-01 |  |  | 152101 | 0 | 152101 | 76051 | 50% | 76050 | 0 | 76050 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013. Art5 data and CP data for 2013. Ozone day was celebrated in September 2014. Country just signed the SSFA in June 2014: Agreement signed in June 2014. BNO coordinated the organiztion of on Customs training in may 2014 and three refrigeration trainning workshops between March and July 2014. All activities under the SSFA are completed (as planned) _ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st in August 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Second payment of 36,051 sent to the Country in May 2015.
FIN | UNEP | Country programme preparation | Individual | AFR | SEY | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1994-07-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | SEY | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-03-01 | 1997-07-01 |  | 2000-07-01 | 2000-07-01 | 31900 | 0 | 31900 | 31900 | 100% | 0 | 0 |  | 4147 | 0 | 4147 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEY | SEV | 31 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2002-08-01 |  | 2004-12-01 | 2005-12-01 | 21267 | 0 | 21267 | 21267 | 100% | 0 | 0 |  | 2765 | 0 | 2765 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SEY | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SEY | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-07-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | SEY | SEV | 63 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2011-03-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | AFR | SEY | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 | 2015-06-01 |  |  | 60000 | 0 | 60000 | 18949.88 | 31.58% | 41050.12 | 27550.12 | 27550 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU submitted 2013 ODS data and CP report. The NOU commemorated international ozone day through school competition, drama and poems.The NOU produced and distributed awareness materials such t-shirts, calenders, caps, brochures and debates and participated in allthe Network meetings.NOU organised a meeting of all importers to plan for 2015 HCFC quotas . Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in October 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):First payment ($19,500) was made in Feb. 2014 ._ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | NOU collected 2014 data on ODS imports and consumption and reported on time to both OS and MLFS. NOU registered all importers of HCFC for 2015.
FIN | UNEP | Methyl bromide communication programme | Individual | AFR | SIL | FUM | 47 | TAS | 12 | A | I | MB | 0.4 | 0.4 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2010-11-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SIL | PHA | 48 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 18000 | -4986 | 13014 | 13014 | 100% | 0 | 0 |  | 2340 | -648 | 1692 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SIL | PHA | 56 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-10-01 | 2010-06-01 |  | 2012-07-01 | 2013-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SIL | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2011-07-01 |  | 2013-12-01 | 2014-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | Project Financially Complete
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-11-01 |  | 2013-11-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 2600 | 650 | 0 | Brief progress report (actual/planned): __Country implementing second tranche activities. NOU conducted training for both customs officer and refrigeration technicians. The project has trained a total of 100 technicians and 80 customs officers. The NOU commenced certification process for technicians and the scheme is running successfully.. Legal arrangements (actual/planned): SSFA was signed in February 2013. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visited the Country in June, 2013 to launch the project implementation_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in April 2013.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Project completed and country implementing second tranche
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SIL | PHA | 70 | TAS | 27 | A | I |  | 0.1 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2016-07-01 | 2016-07-01 |  |  | 23000 | 0 | 23000 | 11137.87 | 48.43% | 11862.13 | 2000 | 2000 | 2990 | 0 | 0 | 2990 | 0 | Brief progress report (actual/planned): __The NOU trained 50 technicians in the use of hydrocarbon refrigerant as alternative to HCFC. A total of 20 custom officers were trained on monitoring and control of ODS. The NOU procurred and distributed toolkits to the major repair workshops and to a few technicians. Implementation of activities has delayed dur to the Ebola outbreak. Legal arrangements (actual/planned): SSFA was signed in March 2014. Any delay (Yes/No): No_ First mission (actual/planned): __CAP can not visist the country due to Ebola outbreak_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in May 2014.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _Yes_ If Yes, reasons for delay & action plan to resolve: Ebola outbreak has delayed implementation of activities_ If Yes, will delay have impact on project completion date (yes/no): _YESS__ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: __NO_ | Most activities are delayed due to Ebola situation in the country
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | SIL | REF | 41 | TAS | 09 | A | I | CFC | 2.4 | 0 | 0 | 0 | 2003-12-01 | 2010-06-01 | 2006-12-01 |  | 2008-02-01 | 2010-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 |  | 2009 | 0 | 2009 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in code of good refrigeration practices/establishment of national refrigeration demonstration centre | Individual | AFR | SIL | REF | 41 | TRA | 04 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | -39463 | 79997 | 79997 | 100% | 0 | 0 |  | 15530 | -5130 | 10400 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | SIL | REF | 41 | TRA | 08 | A | I | CFC | 6.4 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2008-01-01 | 2011-03-01 | 41840 | -9826 | 32014 | 32014 | 100% | 0 | 0 |  | 5439 | -1277 | 4162 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | SIL | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-08-01 |  | 2003-12-01 | 2011-06-01 | 40000 | -23000 | 17000 | 17000 | 100% | 0 | 0 |  | 5200 | -2990 | 2210 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (phase I) | Individual | AFR | SIL | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, one year) | Individual | AFR | SIL | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2007-01-01 | 2008-12-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, 2nd year) | Individual | AFR | SIL | SEV | 51 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SIL | SEV | 54 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SIL | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2012-06-01 | 2015-12-01 |  |  | 85800 | 0 | 85800 | 65850 | 76.75% | 19950 | 19950 | 19950 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place. The NOU continued nationwide sensitization and awareness raising. The NOU developed 7 radio and 3 TV jingles in Krio, Temne and Mende, the widely spoken languages in Sierra Leone and were aired at Radio Maria in Makeni, Kiss 104 in Bo and SLBC radio and TV in Freetown. . Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in January 2011. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned): First disbursement ($25,950) was made in April 2011, 2nd disbursement was ($19,950) was made in July 2012, and 3rd disbursement ($19,950) was made in Feb 2013.._ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _Ebola outbreak limited implementation of projcet activities_ If Yes, will delay have impact on project completion date (yes/no): _YES_ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: NO__ | Implementation of activities delayed due to Ebola outbreak.
ONG | UNEP | Extension of institutional strengthening project (phase V: 4/2013-3/2015) | Individual | AFR | SIL | SEV | 69 | INS | 26 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 | 2015-03-01 |  |  | 85800 | 0 | 85800 | 25950 | 30.24% | 59850 | 25950 | 25950 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The NOU conducted RAC trainings for 35 RAC technicians on good refrigeration practices in Makeni and Magbukara in the Northern region of the country. The NOU conducted customs training for 24 custom officers and other law enforcement agents at Gablamuya (Sierra Leone-Guinea) borders and for 17 customs officers at Gendema ( Sierraa Leone – Liberian borders. The NOU compiled and submitted 2013 ODS data and CP report. The NOU maintained very high public awareness through jungles in the main lingua franca, radio discussions and TV now aired on the national radio &TV concerning ODS. The NOU celebrated the 2014 International Ozone day and participated in all Regional Network and Montreal Protocol meetings. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in January 2011. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned): First disbursement ($25,950) was made in April 2011, 2nd disbursement was ($19,950) was made in July 2012, and 3rd disbursement ($19,950) was made in Feb 2013.._ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _Ebola outbreak limited implementation of projcet activities_ If Yes, will delay have impact on project completion date (yes/no): _YES_ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: NO__ | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2014 data on ODS imports and consumption is ongoing.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Solomon Islands) | Multi-Year | ASP | SOI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-12-01 |  |  | 110250 | 0 | 110250 | 106690 | 96.77% | 3560 |  | 3560 | 14333 | 0 | 10716 | 3617 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. The Customs and Excise has adopted the 2012 HS code for the import and export control. Permit requirement for selling of ODS, non-ODS and RAC equipment has been put in place . The permit requirement is also applied to handle and store the HCFCs. The license requirement for handling of HCFCs by technicians had been informed to technicians during the technician trainings. However, license for handling of ODS including HCFCs will enter into effect when the RAC Association is established. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The NOU has been working with concerned stakeholders to establish a formal RAC association in the country. A meeting with stakeholders was organized in Feb 2014 to form the association. A meeting with RAC technicians was organized in Dec 2014 to discuss the operation of association. RAC technician receiving a tools kit signed Agreement with the Energy Division as a pre-requisite receipt of tools. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in August 2011. First Mission: March 2014 TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Refresher training for enforcement officers in the Solomon Islands was organized on 4 March 2015 in Honiara (16 trainees). Refresher training for RAC technicians in the Solomon Islands will be organized on 26 March 2015 in Honiara (20 trainees). NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. This was approved at the 74th Ex. Com. 2014 CP dta timely submitted online.
FIN | UNEP | Country programme preparation | Individual | ASP | SOI | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | SOI | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | SOI | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-12-01 |  | 2008-12-01 | 2010-12-01 | 6833 | 0 | 6833 | 6833 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | SOI | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | SOI | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | SOI | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | SOI | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 23500 | 39.17% | 36500 |  | 36500 | 0 | 0 | 0 | 0 | 0 | Brief progres report: Project is being implementated as planned: Stable NOU. The NOU continues to focus on the implementation of the approved HPMP as per the planned scheduled and have the responsibility to complete the implementation of Stage 1 Tranche 1 and prepared the required submission for Stage 2 tranche 1 including address all comments of UNEP as implementing agency including: organisation and delivery of the training in good practices for RAC service sector, development and implementation of policies for building sustainable training RAC servicing technicians for the country, organisation of refresher courses for Customs and other enforcement officers and integration of the Montreal Protocol into the national developmental priorities and in particular energy efficiency management and climate adaptation. Timely submission of Article 7 and CP data. CP data were reported on-line. Apart from the above, to continue with the enforcement of the ODS licensing and quota system for HCFC so as to maintain the Montreal protocol compliance management programs. Solomon Islands will continue to strengthen and implement the enforcement of existing acts, Licensing and HCFC quota systems, and annual renewal of the informal prior informed consent procedures (iPIC). Implementation and enforcement of the licensing or certification system for the RAC servicing technicians who are handling HCFC, import and export, sales and workshops who store HCFC and other gas in their facilities. Strengthening of the National Refrigeration Industry Association (SIRAC) will be an important goal for this phase VI. The NOU will continue to be responsible for the management of the HPMP, and will continuously conduct regular awareness activities to focus on the end users as well as the public. The message would be to link the HCFC phase-out with climate benefit, energy efficiency and climate change policy and in accordance to Decisions 1XX/6 of the Montreal Protocol. Timely submission of data reporting requirement to the Ozone and Multilateral Fund Secretariats and participation in regional and international meetings, workshops and events supporting the work of the Montreal Protocol will be of priority. Legal Arrangement: SSFA signed on March 2014. First Payment Jan 2014. All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | NOU prepared and submitted IS terminal and renewal reports for the 74 Ex. Com. 2014 country programme timely submitted on line in 2015.
FIN | UNEP | Formulation of national phase-out strategy | Individual | AFR | SOM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2002-08-01 |  | 2010-12-01 | 2013-12-01 | 60000 | -24902 | 35098 | 35098 | 100% | 0 | 0 |  | 7800 | -3237.01 | 4563 | -0.01 | 0 |  |  |  | 2003-12-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SOM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2008-12-01 | 2009-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Committee (institutional strengthening) | Individual | AFR | SOM | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2005-12-01 |  | 2010-07-01 | 2011-07-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening (first phase) | Individual | AFR | SOM | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-02-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 30000 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase II: 1/2013-12/2014) | Individual | AFR | SOM | SEV | 68 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-11-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 19502.32 | 32.5% | 40497.68 | 40498 | 40498 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU submitted 2013 ODS data and CP report . NOU prepared some awareness materials that were distributed to the public during the Ozone day celebrations. Implementation of activities has delayed due to the political situation in the country. The NOU can not access some parts of the country. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in August 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned): First disbursement ($25,950) was made in April 2013., _ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _There is delay in implementation of activities due to political instability in the country_ If Yes, will delay have impact on project completion date (yes/no): _YES_ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: NO__ | Collection of the 2014 data on ODS imports and consumption is ongoing. The Minister of Environment visited Nairobi and met with CAP staff to discuss implementation of activities in Somalia and plan for effective deliverly of services in the country in view of the political instability.
FIN | UNEP | National compliance action plan: halon bank management | Individual | ASP | SRL | PHA | 43 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-06-01 | 2009-12-01 |  | 2009-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 2007-12-01
FIN | UNEP | National compliance action plan: enhancement of national capacity to monitor trade and prevent illegal trade of ODS | Individual | ASP | SRL | PHA | 43 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2009-12-01 |  | 2008-12-01 | 2009-12-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 |  |  | 17550 | 0 | 17550 | 0 | 0
FIN | UNEP | National compliance action plan: extension training of the established refrigeration technicians | Individual | ASP | SRL | PHA | 43 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 174600 | 0 | 174600 | 174600 | 100% | 0 |  |  | 22698 | 0 | 22698 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SRL | PHA | 55 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 25000 | -5412 | 19588 | 19558 | 99.85% | 30 |  |  | 3250 | -703.56 | 2546.44 | 0 | 0 | Project is financially completed. | Project is financially completed.
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 |  | 2014-12-01 |  | 125000 | 0 | 125000 | 125000 | 100% | 0 |  | 0 | 16250 | 0 | 13441 | 2809 | 0 | Brief progress report (actual/planned): Procurement of the 2nd set of equipment. Legal arrangement (actual/ planned): The SSFA signed in June 2010, was completed and closed at the end of 2013. First mission (actual/ planned): 15-17/04/2009. TOR completed (actual/ planned): N/A. First disbursement date: 28/12/201. All funds disbursed (yes/no): yes. Any 1delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): 1 unit of refrigerants identifier delivered in 2nd quarter of 2015. Only financial reporting within UNEP pending to financialy close this project.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | SRL | PHA | 70 | TAS | 43 | A | I |  | 0.5 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2016-07-01 | 2016-07-01 |  |  | 24000 | 0 | 24000 | 16000 | 66.67% | 8000 |  | 8000 | 3120 | 0 | 0 | 3120 | 0 | Brief progress report (actual/planned): In 2014, Technician Training workshop on Good Practices in Refrigeration with 79 technicians; 45 Customs Officers trained; Production and dissemination of awareness and training materials such as ‘Ozone 20+’ magazine, 2012 HS Code poster, work ethics for technicians; NOU participation in 2 national industry exhibitions; HCFC phaseout message/ information dissemination. Legal arrangement (actual/ planned): The SSFA signed in Dec. 2013. First mission (actual/ planned): 20-24/09/2012. TOR completed (actual/ planned): N/A. First disbursement date: 20/03/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. Servicing training in February 2015. Montreal Protocol module has become part of Sri Lankan Customs mandatory training. In 2015, the primary focuses are: to conclude the work with Industry Associations and to produce/ disseminate non-print awareness materials. Legal arrangement (actual/ planned): In April 2015, additional US$8,000 transferred to the government.
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | SRL | REF | 32 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2005-04-01 | 2010-12-01 | 87000 | -5412 | 81588 | 81588 | 100% | 0 |  |  | 11310 | 0 | 11310 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainers and training of refrigeration service technicians including | Individual | ASP | SRL | REF | 32 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-12-01 |  | 2004-09-01 | 2009-12-01 | 219000 | -52448 | 166552 | 146992 | 88.26% | 19560 |  |  | 28470 | -6818 | 19108.96 | 2543.04 | 0
ONG | UNEP | Preparation of a HCFC phase-out management plan | Individual | AFR | SSD | PHA | 70 | PRP | 02 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-08-01 | 2013-07-01 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 10010.41 | 33.37% | 19989.59 | 4989.59 | 4990 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): __ The NOU started collection of HCFC data in preparation for HPMP project drafting. Due to political unrest in the country, the NOU is not able to complete the process as other parts of the country can not be reached.The country has drafted Environmental Management Act and control of ODS is included in the Act.The Act is expected to be approved by Parliament before the end of this year. Legal arrangements (actual/planned):SSFA was signed between the country and UNEP in June, 2014 Any delay (Yes/No): No_ First mission (actual/planned): __CAP unable to visist the country due to security situation as a result of political unrest_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First payment $10,000 was made in August 2014..___ All funds disbursed (yes/no): _NO_ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: Political unrest__ If Yes, will delay have impact on project completion date (yes/no): _YES__ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: _NO__ | NOU is processing the recruitment of an international consultant to assist in the drafting of the HPMP project document in time for submission to the 75 Ex-com |  |  |  |  | To request the submission of additional status reports to the 75th meeting to monitor: (a) the submission of the HCFC phase-out management plan; (b) the actions taken towards the establishment of the licensing system for ODS imports and exports.
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | SSD | SEV | 68 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2013-07-01 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 25003.99 | 62.51% | 14996.01 | 0 | 14996 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The country conducted awareness meetings on ODS Phase-out. Ozone news was featured on the radio station and also featured in the local newspapers. The NOU celebrated 2014 International Ozone Day and participated in all Montreal Protocol meetings. Implementation of activities has delayed due to political unrest in the country. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in February 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment ($25,000 was sent in April 2013. All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _Political unrest_ If Yes, will delay have impact on project completion date (yes/no): _YES__ Any ongoing problems (yes/no): __YES . If Yes, is any action required by ExCom: _NO__ | NOU is finalising collection of 2014 ODS data to submit to both OS and MLFS on time.
FIN | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | STK | FUM | 50 | TAS | 11 | A | I | MB | 0.8 | 0.8 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2008-12-01
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2009-12-01 |  | 2010-06-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STK | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 85000 | -17992 | 67008 | 67008 | 100% | 0 | 0 |  | 11050 | -2331 | 8719 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2013-07-01 | 2013-07-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 17 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 | 2013-04-01 | 2015-07-01 | 2015-06-01 |  |  | 58400 | 0 | 58400 | 58400 | 100% | 0 | 0 | 0 | 7592 | 0 | 5790 | 1802 | 0 | Brief progress report (actual/planned): HCFCs license system in place, HCFC quota assigned January 2014. Licensing regulations updated to include the HCFC blends in 2014. Draft standards manual developed in 2014; World Environment Day celebrations included ozone layer protection issues and highlighting the activities of the HPMP. Awareness on the need to switch to energy efficient, low global warming potential (GWP) alternatives was also raised among the general public and the RAC sector.___ Legal arrangements (actual/planned): Agreement signed in Jul-12___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Jul-12 ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Project completed. Second tranche request prepared in Mar-2015. Comments from the MLFS addressed in Apr-2015. Second tranche approved in May-2015 by ExCom 74. Legal agreement under preparation.
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | STK | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-09-01 | 1998-03-01 |  | 1998-03-01 | 1999-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | LAC | STK | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-03-01 | 2008-12-01 | 15000 | -3460 | 11540 | 11540 | 100% | 0 | 0 |  | 1950 | -450 | 1500 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | STK | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-12-01 | 1999-12-01 | 35000 | -12500 | 22500 | 22500 | 100% | 0 | 0 |  | 4550 | -1625 | 2925 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Institutional strengthening | Individual | LAC | STK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 2000-02-01 |  | 2006-09-01 | 2007-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STK | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-08-01 | 2005-04-01 |  | 2007-08-01 | 2008-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | STK | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | STK | SEV | 59 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2013-07-01 | 2013-07-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Last payment made in May-13. | Project financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | STK | SEV | 68 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-06-01 | 2014-12-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country Programme implementation and Article 7 data reported on time. HCFC Quotas for 2013 and 2014 issued to registered importers; Improvement in identification of refrigerants through stricter licensing system. Customs provided with identification equipment to improve monitoring at the country’s many ports. The Steering Committee contributed to the successful implementation of HPMP and supports HCFC phase out, and provided feedback on the development of Standards for the RAC sector. Air-conditioning & Refrigeration Association membership increased and support work of NOU through technical assistance in standards and alternative refrigerants. Ozone day celebrations included: 30 seconds radio spots, Exhibition in the Capitol’s Square, School visits, Interviews on radio to keep ozone layer issues a priority for policy makers, and ozone layer protection a priority for the general public; participation of Ozone Officer in the Joint Annual Meeting of the Ozonaction Networks of Latin America and the Caribbean, Dominican Republic, December 2014, the Regional Meeting of the Caribbean Ozone Officers Network, Suriname, April 2014, the Workshop on hydro-fluorocarbons (HFC) Management , and the 34th OEWG, Paris July 2014. Renewal request prepared and submitted to the 73 ExCom. IS renewal approved in Dec-2014___ Legal arrangements (actual/planned): SSFA signed in May-13 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement issued Jun-13. ___ All funds disbursed (yes/no): no___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: outstanding progress and financial reports, low disbursement rate because of new authorities. Follow-up with country and activities are ongoing. ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | SSFA expired in Mar-2015. Balance to be merged in a new agreement that includes next IS phase approved. Draft SSFA prepared and sent to Paris for approval in May-2015.
ONG | UNEP | Extension of institutional strengthening project (phase VI: 1/2015-12/2016) | Individual | LAC | STK | SEV | 73 | INS | 19 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-31 | 2016-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. No comments from country recieved. Draft sent for approval of signature by UNEP in May-2015.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STL | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-02-01 | 2009-07-01 |  | 2012-12-01 | 2012-12-01 | 85000 | -2532 | 82468 | 82468 | 100% | 0 | 0 |  | 11050 | -329 | 10721 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2012-07-01 |  | 2013-08-01 | 2013-08-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 | 2015-12-31 |  |  | 13150 | 0 | 13150 | 10500 | 79.85% | 2650 | 2650 | 2650 | 1710 | 0 | 0 | 1710 | 0 | Brief progress report (actual/planned): 44 technicians trained in good refrigeration practices. 40 technicians certified and issued 'Certified Technician' ID cards. 50 Customs and Marine Police Officers trained in the application of the HCFC licensing and Quota Systems. Customs quick tool and Customs desk book distributed to all Customs officers. Training for 20 shipping agencies on harmonized systems codes. Meetings with importers to discuss progress in HPMP implementation and quota controls. Posters on sale restrictions to only certified technicians distributed to retailers.___ Legal arrangements (actual/planned): SSFA signed in Jun-2014 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): June-2014___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Progress and financial reports sent on Apr-2015. Reports cleared in Apr-2015. Second payment processed and issued in Apr-2015
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | STL | PHA | 71 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-05-01 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 5000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): ToRs drafted. Contracting will take place in 2015 with the submission of third tranche as per ExCom decision.___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no):no ___ If Yes, is any action required by ExCom: ___ | Generic ToRs approved in Feb-2015. Contracting of new consultants should follow new procedures under UMOJA. Contracting process starting in Jun-2015 when UMOJA goes live.
FIN | UNEP | Development of a refrigeration management plan | RMP | LAC | STL | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-03-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 | 0 |  | 1950 | -130 | 1820 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | STL | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-10-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Establishment of an Ozone Cell | Individual | LAC | STL | SEV | 21 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 2000-02-01 |  | 2000-08-01 | 2001-08-01 | 36580 | 0 | 36580 | 36580 | 100% | 0 | 0 |  | 4755 | 0 | 4755 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | STL | SEV | 30 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2002-04-01 |  | 2002-06-01 | 2003-07-01 | 24400 | 0 | 24400 | 24400 | 100% | 0 | 0 |  | 3172 | 0 | 3172 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | STL | SEV | 37 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-06-01 | 2005-12-01 | 31200 | 0 | 31200 | 31200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | LAC | STL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-10-01 | 2006-07-01 |  | 2007-04-01 | 2009-09-01 | 31200 | -400 | 30800 | 30800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | STL | SEV | 49 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | LAC | STL | SEV | 55 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | STL | SEV | 62 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-11-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | STL | SEV | 68 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-01-01 |  | 2014-12-31 | 2014-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): 2013 Country Programme implementation and 2013 Article 7 data collected, verified and reported on time. HCFC quotas for 2014 issued to registered importers in Jan-2014; Import/export of ODS and ODS based equipment and refrigerants monitored; Customs provided NOU with privileged access to ASYCUDA World which allows for monitoring at the convenience of the NOU; NOU participated in iPIC. Steering committee consulted on matters as needed. Provided guidance to the revision of the Regulations and Act through consultative meetings and one-on-one discussions. NOU provided support to the National Refrigeration and Air Condition Association (NARA) through technical assistance and guidance . 2014 Ozone Day celebrations focused on illegal trade in HCFCs and the signing of an MOU between the Ministry, Customs Department and the Caribbean Customs Law Enforcement Council (CCLEC) ; participation of Saint Lucia in the the Caribbean Ozone Officers Network, Suriname, April 2014, the Joint Annual Meeting of the Ozonaction Networks of Latin America and the Caribbean, Dominican Republic, December 2014, the Workshop on hydro-fluorocarbons (HFC) Management , the 34th OEWG, Paris July 2014, and the MOP. Renewal request prepared and submitted to the 73 ExCom. IS renewal approved in Dec-2014___ Legal arrangements (actual/planned): SSFA signed in May-13 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement issued Jun-13. ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Project completed. Last disbursement made in Nov-2014
ONG | UNEP | Renewal of institutional strengthening project (phase IX: 1/2015-12/2016) | Individual | LAC | STL | SEV | 73 | INS | 23 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-31 | 2016-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. Comments from country received and incorporated in Mar-2015. Draft approved for signature by UNEP in Apr-2015. SSFA signature can only be processed once UMOJA goes live in Jun-2015. First disbursement will be processed under UMOJA in Jun-2015.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | STP | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-06-01 | 2009-12-01 | 30000 | -8 | 29992 | 29992 | 100% | 0 | 0 |  | 3900 | -1 | 3899 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 54000 | 0 | 54000 | 54000 | 100% | 0 | 0 |  | 7020 | 0 | 7020 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | STP | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-03-01 | 2012-03-01 | 85000 | -15000 | 70000 | 70000 | 100% | 0 | 0 |  | 11050 | -1950 | 9100 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 | 0 |  | 2730 | 0 | 2730 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | STP | PHA | 57 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | STP | PHA | 63 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 44000 | -4988 | 39012 | 39012.44 | 100% | -0.44 | 0 |  | 5720 | -649 | 5071 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | STP | PHA | 70 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2016-07-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 25000 | 25000 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2014: Agreement signed in May 2014. Three workshops of 60 participants on recovery and recycling of HCFCs organized between May and December 2014. Two customs training workshop on HCFC identification organzed between June and Agust 2014. Two assement reports on the implementation of the HPMP also provied by National Consultants. All activities under the SSFA are completed (as planned) _ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Country trained 20 refrigeration technicians and 10 police officers in February 2015
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | STP | PHA | 71 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-05-01 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Consultants identified, TOR done in collaboration with the country and UNEP are working on the concracts___ Legal arrangements(actual/planned): __n/a_Initial stages of project implementation(actual/planned):n/a ___ Intermediate goals achieved (actual/planned): Consultant to be hired in June 2015 and Draft report awailable in November 2015 ___ Project completion and follow up: ___ First disbursement date (actual/planned): _n/a__ All funds disbursed (yes/no): n/a ___ Any delay?(yes/no): _no__ If Yes, reasons for delay & action plan to resolve: _n/a__ If Yes, will delay have impact on project completion date (yes/no): No___ Any ongoing problems (yes/no): _Yes . Country is french speaking and verification report provided in French__ If Yes, is any action required by ExCom: _ExCom to consider verification report in French language | Country started a survey in March 2015 in order to compile all supporting documents of the 2013-2014 import. CAP organized a mission to Sao Tome in March 2015 to assist and guide the BNO on the required information.
FIN | UNEP | Implementation of the RMP: assistance for development of a licensing system | Individual | AFR | STP | REF | 44 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-06-01 |  | 2006-12-01 | 2009-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | STP | REF | 44 | TAS | 09 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for custom officers | Individual | AFR | STP | REF | 44 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | STP | REF | 44 | TRA | 08 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2006-12-01 |  | 2008-12-01 | 2012-05-01 | 55000 | -11534 | 43466 | 43466 | 100% | 0 | 0 |  | 7150 | -1499 | 5651 | 0 | 0
FIN | UNEP | Preparation of country programme and refrigerant management plan | Individual | AFR | STP | SEV | 36 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2007-12-01 | 30000 | -3538 | 26462 | 26462 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | STP | SEV | 38 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | STP | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2006-06-01 | 2008-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | STP | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-12-01 |  | 2011-02-01 | 2012-06-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | STP | SEV | 63 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | AFR | STP | SEV | 71 | INS | 23 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2015-12-01 |  |  | 60666 | 0 | 60666 | 0 | 0% | 60666 | 0 | 60666 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in June 2014: Agreement signed in June 2014. Country reported 2013 Art5 data and CP data for 2013. Ozone day was celebrated. Coordination of two refrigeration workshops and on customs training workshop. Organisation of three steering committe meeting.All activities under the SSFA are completed (as planned) _ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement planned in June 2014 __ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Organisation in february 2015 of a steering committee meeting on the annual quota. Country reported in April 2015 it 2014 CP dat report. In June 2015 a Conference on HCFC phase out and HCFC based equipment was organized at Refrigeration referral training center.
FIN | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-Year | LAC | STV | PHA | 47 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2010-12-01 | 2011-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 |  | 8710 | 0 | 8710 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STV | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2013-06-01 | 2013-06-01 | 85000 | -3537 | 81463 | 81463 | 100% | 0 | 0 |  | 11050 | -460 | 10590 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase out management plan for CFCs (fourth tranche) | Multi-Year | LAC | STV | PHA | 61 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 | 0 |  | 1820 | 0 | 1820 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | TAS | 19 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 | 2012-10-01 | 2014-12-01 |  | 2014-12-01 | 2014-12-01 | 55809 | 0 | 55809 | 54992.12 | 98.54% | 816.88 | 0 |  | 7255 | 0 | 7149.0031 | 105.9969 | 0 | Brief progress report (actual/planned): All importers of refrigerants were invited to register with the NOU. A total of 24 registered importers were formally informed by the NOU, Ministry of Health, Wellness and the Environment of their 2014 quota for the importation of HCFCs and are in compliance; a total of 25 technicians were successfully trained in retrofitting, safe handling and storage of refrigerants in May 2014; 10 Customs Brokers and Importers participated in procedures for imports license and quota systems on Feb-2014; 14 Senior frontline Customs Officers were trained in Phase I Safe Storage and Handling of ODS, Import license and Quota Systems as well as Protecting St. Vincent and the Grenadines Borders from Illegal Trade of ODSs in Apr-2014; Refrigerant posters designed, printed and distributed to stakeholders to guide them in acknowledging ODS imported in the country; article placed in the newspapers on Jun-2014 directed at importers of refrigerants highlighting the regulations for importing refrigerants; the Technical College, division of Technical and Vocational Education was supported to be the first fully equipped and comprehensive refrigeration and Air-conditioning Technicians Training Centre in St.Vincent and the Grenadines .___ Legal arrangements (actual/planned): n/a___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: n/a.___ | Project financially completed.
FIN | UNEP | Implementation of the RMP: training of trainers for good practices in refrigeration | Individual | LAC | STV | REF | 25 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment | Individual | LAC | STV | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2004-03-01 | 2000-02-01 |  | 2005-02-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | STV | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2005-12-01 |  | 2005-11-01 | 2010-12-01 | 20000 | -3250.32 | 16749.68 | 16750 | 100% | -0.32 | 0 |  | 2600 | -423 | 2177 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Country programme preparation | Individual | LAC | STV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-08-01 |  | 1998-05-01 | 1999-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Creation of the National Ozone Unit | Individual | LAC | STV | SEV | 25 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-06-01 |  | 2004-03-01 | 2005-12-01 | 30300 | 0 | 30300 | 30300 | 100% | 0 | 0 |  | 3939 | 0 | 3939 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 42 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-03-01 | 2005-04-01 |  | 2005-03-01 | 2005-12-01 | 13130 | 0 | 13130 | 13130 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2008-03-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | STV | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2008-11-01 |  | 2010-01-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | STV | SEV | 58 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase IV, additional funding) | Individual | LAC | STV | SEV | 62 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2011-08-01 |  | 2011-12-01 | 2012-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | LAC | STV | SEV | 66 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2014-03-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | -9.0949e-13 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 11/2014-10/2016) | Individual | LAC | STV | SEV | 73 | INS | 22 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-10-01 | 2016-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 30000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. Comments from country received and incorporated in Mar-2015. Draft approved in Mar-2015 and signed by UNEP in Apr-2015. SSFA signed by country in Apr-2015. First disbursement will be processed under UMOJA in Jun-2015.
FIN | UNEP | Country programme preparation | Individual | AFR | SUD | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1994-03-01 | 1994-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | SUD | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1997-03-01 |  | 1999-07-01 | 1999-12-01 | 168300 | 0 | 168300 | 168300 | 100% | 0 | 0 |  | 21879 | 0 | 21879 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | SUD | SEV | 28 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-12-01 | 2001-12-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 |  | 14586 | 0 | 14586 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | SUD | SEV | 34 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 |  | 14586 | 0 | 14586 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase IV | Individual | AFR | SUD | SEV | 42 | INS | 16 | A | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-04-01 | 2009-06-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 145860 | 0 | 145860 | 145860 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase V | Individual | AFR | SUD | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-04-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 109395 | 0 | 109395 | 109395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase VI | Individual | AFR | SUD | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 145860 | 0 | 145860 | 145860 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Financially Complete
ONG | UNEP | Extension of institutional strengthening (phase VII: 4/2013-3/2015) | Individual | AFR | SUD | SEV | 69 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 | 2015-03-01 |  |  | 145860 | 0 | 145860 | 75680 | 51.89% | 70180 | 0 | 105270 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU conducted RAC training workshops for 130 technicians. The NOU distributed 24 sets of equipment to best practicing shops and 4 sets of equipment to vocational centers. Two training workshops were conducted for custom officers with 60 officers trained. The NOU submitted 2013 ODS data and CP report. The NOU celebrated 2014 International Ozone day and participated in all Regional Network and Montreal Protocol meetings . Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in August 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned)First payment ($40,590) was made in Dec 2013, and 2nd disbursement ($35090) was made in Oct 2014 ._ All funds disbursed (yes/no): NO,The country has submitted reports and awaiting disbursement of 3rd payment _ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2014 data on ODS imports and consumption is ongoing.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | SUR | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | SUR | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-07-01 | 2011-07-01 | 85000 | -1049 | 83951 | 82047 | 97.73% | 1904 | 0 |  | 11050 | -136 | 10666.11 | 247.89 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-06-01 |  | 2013-12-01 | 2013-12-01 | 100000 | -527 | 99473 | 99473 | 100% | 0 | 0 |  | 13000 | -69 | 12931 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2014-07-07 | 2013-11-01 |  | 2014-12-01 | 2014-12-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 0 | 3510 | 3510 | Brief progress report (actual/planned): Capacity building programme including training of 60 customs officers on illegal trade and identification of ODS and ODS-based equipment, and training of 140 technicians in handling, installation and servicing of equipment operating with R-410A, R-290 and other alternative refrigerants; capacity building of both customs and technicians is an on-going process. Frequent exchange of information with Customs who are making use of refrigerant identifiers during inspections. Refrigeration association (ARVAS) has trained and certified more than 100 technicians out of a total of 200 nationwide. Awareness programme for phasing-out the use of HCFCs and high-GWP refrigerants as commercially viable technologies become available; strengthening of the recovery and recycling programme in operation through the distribution of recovery units, multifunction recovery, recycling, evacuation and charging units, multi-refrigerant analyzer, recovery cylinders, vacuum pumps, tools and spares; monitoring and evaluating the implementation of the HPMP to ensure effectiveness of all the activities proposed within the HPMP.___ Legal arrangements (actual/planned): SSFA signed in Apr-2012 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Apr-2012___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: change of NOO delayed submission of progress and financial reports. UNEP assisted NOU with reporting and processing of disbursements ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Project completed. Last disbursement made in Jul-2014. Second tranche request prepared in Feb-Mar 2015. Submitted and comments from MLFS addressed in Apr-2015. Second tranche approved in May-2015 by 74 ExCom.
FIN | UNEP | Implementation of the RMP: development and strengthening of policy and regulatory framework for acceleration of compliance with the Montreal Protocol | Individual | LAC | SUR | REF | 41 | TAS | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-01-01 | 2009-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training of customs officers and other relevant stakeholders in monitoring of ODS | Individual | LAC | SUR | REF | 41 | TRA | 05 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-10-01 | 2008-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training of trainers in good practices of refrigeration | Individual | LAC | SUR | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-07-01 |  | 2007-12-01 | 2008-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Preparation of country programme | Individual | LAC | SUR | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-06-01 |  | 2003-08-01 | 2005-05-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 |  | 6500 | -4550 | 1950 | 0 | 0 | Project financially completed. | Project financially completed. |  | 2003-07-01
FIN | UNEP | Institutional strengthening and capacity building: establishment of the Ozone Unit | Individual | LAC | SUR | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2009-06-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | SUR | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2010-04-01 | 2011-04-01 | 73333 | 0 | 73333 | 73333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | SUR | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 39722 | 33611 | 73333 | 73333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Extension of the institutional strengthening project (phase IV: 7/2012-6/2014) | Individual | LAC | SUR | SEV | 67 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 |  | 2014-07-14 |  | 73333 | 0 | 73333 | 61458.4 | 83.81% | 11874.6 | 11875 | 11875 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): 2013 Country Programme implementation and 2013 Article 7 data collected, verified and reported on time. The Country implements the licensing system which includes the quota system for HCFCs under the Trade Act and it takes the form of a prohibition order contained in a State Decree Negative List issued in 1999 and amended by the Council of Ministers in February 2006. Quota is set at 30 in 2014 and is issued on a ‘first come, first served’ basis with preference given to annual regular importers.Illegal trade in ODS including HCFC monitored through permanent interactions with the Customs Department and Refrigeration Technicians Association. The Steering committee includes NOU, Ministry of Trade & Industry, Customs, Bureau of Public Health and Technicians Association; the Steering Committee meets at least twice per year to advise on programme implementation. NOU hold discussions with refrigeration association (ARVAS) focusing on limiting use of ODS and encouraging the use of alternative refrigerants. 2014 Ozone Day celebrations included providing information to some 200 students and youth organizations in the District of Saramacca (outside of Paramaribo) on the ozone layer depletion and how they can contribute to its protection; organization and hosting of the Caribbean Ozone Officers Network in Paramaribo, Suriname, April 2014. Renewal request prepared and submitted to the 73 ExCom. IS renewal approved in Dec-2014___ Legal arrangements (actual/planned): SSFA signed in May-13 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): First disbursement issued Jun-13. ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. Revised draft sent for approval in May-2015. Implementation will be once UMOJA goes live.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2014-11/2016) | Individual | LAC | SUR | SEV | 73 | INS | 21 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-30 |  |  | 73333 | 0 | 73333 | 0 | 0% | 73333 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Newly approved project | SSFA drafted in Jan-2015. Draft submitted for consideration of country in Feb-2015. No comments from country received. Draft sent for approval of signature by UNEP in May-2015.
FIN | UNEP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SWA | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-11-01 |  | 2011-07-01 | 2012-07-01 | 85000 | -5001 | 79999 | 79999 | 100% | 0 | -2.1672e-13 |  | 11050 | -650 | 10400 | 0 | -2.8173e-14 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-01 | 75000 | -4984 | 70016 | 70016.38 | 100% | -0.38 | 1.6023e-12 |  | 9750 | -648 | 9102 | 0 | 2.083e-13 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 |  | 2013-06-01 | 2013-06-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 | -1.4553e-12 |  | 7410 | 0 | 7410 | 0 | -1.8919e-13 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-03-01 | 2016-07-01 | 2014-12-01 |  | 75000 | 0 | 75000 | 55000 | 73.33% | 20000 | 0 | 20000 | 9750 | 0 | 8451 | 1299 | 0 | Brief progress report (actual/planned): __Country implementing second tranche activities. NOU conducted additional training for both customs officer and refrigeration technicians. A total of 60 technicians and 40 customs officers were trained. The Country started implemtation of certification scheme for technician.The NOU organised 2 meetings of the Refrigeration Association to discuss on the formal registration of the Association and on additional training of informal sector technicians. NOU conducted random inspection of retail shops of refrigerants and found out that all shops visted were selling pure refrigerants . Legal arrangements (actual/planned): SSFA was signed in December 2011. Any delay (Yes/No): No_ First mission (actual/planned): __N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in December 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Project completed and country implementing second tranche.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SWA | PHA | 70 | TAS | 20 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2016-07-01 | 2016-07-01 |  |  | 55000 | 0 | 55000 | 20000.65 | 36.36% | 34999.35 | 0 | 34999 | 7150 | 0 | 0 | 7150 | 0 | Brief progress report (actual/planned): __ The country conducted awareness meeting on ODS Phase-out. The NOU supported the registration of the Association and conducted two meetings for the Association. 25 customs officers were trained on the control of ODS importation and 45 technicains were trained on the use of ODS alternatives. NOU visited the Palfridge Fridge Factory to follow up on the completion of Conversion project of the factory, a project funded by Multilateral Fund Secretariat. Legal arrangements (actual/planned):SSFA was signed in January 2014. Any delay (Yes/No): No_ First mission (actual/planned): CAP visited the country in October 2014 to monotor implementation of second tranche and had meetings with the Refrigeration Association, customs officers and management of SEA__N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in April 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU processed the allocation of 2015 HCFC quotas , conducted stakeholders' consultative meetings on 2015 HCFC 10% reduction target. NOU registered all importers of HCFC for 2015
FIN | UNEP | Country programme preparation | Individual | AFR | SWA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1994-12-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | SWA | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1998-12-01 |  | 2003-12-01 | 2007-02-01 | 67320 | 0 | 67320 | 67320 | 100% | 0 | 0 |  | 8752 | 0 | 8752 | 0 | 0 |  |  |  | 1998-03-01
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | SWA | SEV | 41 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2007-12-01 | 2009-10-01 | 58344 | 0 | 58344 | 58344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SWA | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | -1.4553e-12 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SWA | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 |  | 2013-02-01 |  | 32500 | 27500 | 60000 | 47500 | 79.17% | 12500 | 0 | -0.39 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country collected 2013 ODS data and submitted to OS and MFS. The NOU commemorated international ozone day through newsleller articles on ozone issues, school competition, drama and poems.The NOU produced and distributed awareness materials such t-shirts, calenders, caps, brochures and debates. The NOU participated in all Network meetings and other global Montreal Protocol meetings. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in January 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment was sent in February 2013,_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Country collected 2014 ODS data and reported to both Ozone Secretariat and Multilateral Fund Secretariat. Project completed and NOU processing implemention of new IS phase
ONG | UNEP | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | AFR | SWA | SEV | 71 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-11-01 | 2016-11-16 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Plan of action was agreed between the counrty and UNEP. SSFA was drafted, finalised and sent to the county for signature Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA still not signed. UNEP expects to obtain signature by September. NOU conducted random inspection visist to retail shops for refrigerants to check the quality of refrigerants being sold on the market . Country collected 2014 ODS data and reported to both Ozone Secretariat and Multilateral Fund Secretariat.
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | SYR | REF | 23 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance for the establishment of regulations and legislation | Individual | ASP | SYR | REF | 29 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2002-06-01 | 2007-01-01 | 25500 | -10000 | 15500 | 15500 | 100% | 0 |  |  | 3315 | -1300 | 2015 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for custom officials | Individual | ASP | SYR | REF | 29 | TRA | 47 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2009-12-01 | 2014-05-14 | 72600 | -61337 | 11263 | 11263 | 100% | 0 |  |  | 9438 | -7974 | 1464 | 0 | 0 | Project financialy Completed | Project financialy Completed |  | 2002-12-01
FIN | UNEP | Implementation of the RMP: training for trainers and refrigeration technician on good service practices | Individual | ASP | SYR | REF | 29 | TRA | 49 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2002-12-01 |  | 2009-12-01 | 2014-05-14 | 201300 | -53036 | 148264 | 145200 | 97.93% | 3064 |  |  | 26169 | -6895 | 18876 | 398 | 0 | Project financialy Completed | Project financialy Completed
FIN | UNEP | Country programme preparation | Individual | ASP | SYR | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-11-01 | 1993-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | THA | FUM | 30 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -9096 | 15904 | 15904 | 100% | 0 |  |  | 3250 | -1182 | 2068 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I) | Individual | EUR | TKM | SEV | 46 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-10-01 | 2008-07-01 |  | 2008-02-01 | 2010-12-01 | 115693 | 0 | 115693 | 115693 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-04-01 |  | 2010-07-01 | 2011-07-01 | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | TKM | SEV | 61 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-09-01 |  | 2012-09-01 | 2013-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | ASP | TLS | PHA | 59 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Preparation of HCFC phase-out management plan | RMP | ASP | TLS | PHA | 59 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | ASP | TLS | PHA | 61 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-06-01 | 2010-11-01 |  | 2011-12-01 | 2012-12-01 | 55000 | -1745 | 53255 | 53255 | 100% | 0 |  |  | 7150 | -227 | 6923 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | HCFC and CFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-06-01 | 2012-03-01 | 2015-12-01 |  |  | 93500 | 0 | 93500 | 49236 | 52.66% | 44264 |  | 44264 | 12155 | 0 | 5724 | 6431 | 0 | Brief progress report (actual/planned): The Customs training workshop was organized during 21 - 23 of January 2014 with 17 customs officer and one person from Industry department. The stakeholders’ consultation meeting was conducted on 24 of January 2014 to discuss the HPMP implementation. National training workshop in good practices conducted in June 2014 and with south/south support from senior trainer of Indonesia- 12 technicians completed the training and from this 5 were selected to be national trainers. Following the consultation meeting conducted in November 2014 among the National Ozone Unit (NOU), State Secretary of Environment (SEMA), United Nation Environmental Programme (UNEP) , United Nation Development Programme (UNDP) and the Centro Nacional Formacão Professional (CNFP), it was agreed that CNFP and NOU would sign an agreement to list the roles/responsibility for the cooperation on the delivery of the training programme, while UNEP and UNDP will provide their technical assistance for the cooperation. The certificate system for the technician who handle ODS refrigerant was also discussed, and it was agreed to further explore the possibility to jointly establish such system by the NOU and CNFP. The Customs and enforcement training has been conducted in December 2014 and with the support of the Indonesia NOU. Legal arrangements (actual/planned): The SSFA was signed in March 2012 and has been closed in December 2013. First disbursement date: June 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow implementation in follow up activities after the initial activities conducted by UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes, the revised project completion date of HPMP Stage I is expected to be in December 2016. Any ongoing problems (yes/no): No, the implementation is progressing If Yes, is any action required by ExCom: N/A | The MOU between the NOU and the Centro Nacional Formacão Professional (CNFP) On training of technician on good service practices and retrofitting was drafted in 2015. In May 2015, two senior RAC trainers received refresher training in good refrigeration servicing skills in Malaysia. UNEP held high level meetings with the Vice Minister of Envionment, NOU and his technical team in May of 2015, to present on the status of Montreal Protocol implementation and seeking the support of his good office to expedite approved projects. At this meeting held in Bangkok, the Vice Minister gave his support for the Montreal Protocol implementation. 2014 CP data timely submitted online.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | TLS | PHA | 69 | TAS | 09 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-06-01 | 2015-04-01 | 2015-12-01 |  |  | 55000 | 0 | 55000 | 44000 | 80% | 11000 |  | 11000 | 7150 | 0 | 0 | 7150 | 0 | Brief progress report (actual/planned): The balance from the first tranche was transferred to the SSFA of the second tranche to facilitate project implementation and monitoring. The Customs training workshop was organized during 21 - 23 of January 2014 with 17 customs officer and one person from Industry department. The stakeholders’ consultation meeting was conducted on 24 of January 2014 to discuss the HPMP implementation. National training workshop in good practices conducted in June 2014 and with south/south support from senior trainer of Indonesia- 12 technicians completed the training and from this 5 were selected to be national trainers. Following the consultation meeting conducted in November 2014 among the National Ozone Unit (NOU), State Secretary of Environment (SEMA), United Nation Environmental Programme (UNEP) , United Nation Development Programme (UNDP) and the Centro Nacional Formacão Professional (CNFP), it was agreed that CNFP and NOU would sign an agreement to list the roles/responsibility for the cooperation on the delivery of the training programme, while UNEP and UNDP will provide their technical assistance for the cooperation. The certificate system for the technician who handle ODS refrigerant was also discussed, and it was agreed to further explore the possibility to jointly establish such system by the NOU and CNFP. The Customs and enforcement training has been conducted in December 2014 and with the support of the Indonesia NOU. Legal arrangements (actual/planned): The SSFA was signed in June 2014. TOR completed: N/A First disbursement date: June 2014 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow implementation in follow up activities after the initial activities conducted by UNEP. If Yes, will delay have impact on project completion date (yes/no): No, the implementation is progressing. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | The MOU between the NOU and the Centro Nacional Formacão Professional (CNFP) On training of technician on good service practices and retrofitting was drafted in 2015. In May 2015, two senior RAC trainers received refresher training in good refrigeration servicing skills in Malaysia. UNEP held high level meetings with the Vice Minister of Envionment, NOU and his technical team in May of 2015, to present on the status of Montreal Protocol implementation and seeking the support of his good office to expedite approved projects. At this meeting held in Bangkok, the Vice Minister gave his support for the Montreal Protocol implementation. 2014 CP data timely submitted online.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | TLS | PHA | 72 | PRP | 12 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-05-31 | 2016-05-31 |  |  | 20000 |  | 20000 | 0 | 0% | 20000 |  | 20000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): UNEP together with UNDP conducted country mission in November of 2014 with the objectives of reviewing the status of preparation, roles of UNEP and UNDP and agree on revised plan of action due to delays. At this mission stakeholder meeting was held and UNEP advised on requirements and processes for data collection including. Agreement was reached with NOU that that a suitable local consultation can be contracted to expedite the required national activities. During this mission high level meeting was held and draft plan of action agree to for preparation of project. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned): N/A Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): Yes . Any ongoing problems (yes/no): Yes, slow rate of implementation nationally. Slow rate of implementation. Required high level intervention on the implementation of the Montreal Protocol. | Due to administration diffficulties, the agreed time line for project submission at the Nov 2015 Ex. Com has to be reviewed. UNEP held high level meetings with the Vice Minister of Envionment, NOU and his technical team in May of 2015, this meeting presented on the status of Montreal Protocol implementation and seeking the support of his good office to expidite approved projects. At this meeting held in Bangkok, the Vice Minister gave his support for the Montreal Protocol implementation. UNEP planned country mission in July of 2015 to work with country on revised plan on action for the project preparation.
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | TLS | SEV | 56 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-11-01 |  | 2010-11-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase II, year 1) | Individual | ASP | TLS | SEV | 61 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2011-12-01 |  | 2011-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase II, year 2: 1/2012-12/2012) | Individual | ASP | TLS | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of institutional strengthening (phase III: 4/2013-3/2015) | Individual | ASP | TLS | SEV | 69 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-05-01 | 2015-03-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 |  | 45000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The SSFA was signed in March 2014 and initial payment has been transferred. The licensing and quota system was enforced in 2014. The MOU between the Ministry of Commerce, Industry and Environment (MCIA) and the Ministry of Finance (MOF) was drafted. The MOU aims to set up cooperation between MCIA and the MoF to reinforce the import and export control of ODSs as well as combating and preventing illegal traffic and or transaction of ODSs. The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. Legal arrangements (actual/planned): The SSFA was signed in March 2014. Initial stages of project implementation (actual/planned): N/A since Project is ongoing. Intermediate goals achieved (actual/planned): Implementing the HPMP activities; further strengthening the enforcement of the Decree Law to ensure successful implementation of the ODS import/export licensing/quota system; celebration of Ozone day and data reporting to the Fund and Ozone Secretariats. First disbursement date: May 2014. All funds disbursed (yes/no): No Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: the internal coordination process delayed the implementation. UNEP is working with the country to recruit administrative staff under the NOU. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. The recuritment process is long, and UNEP is following up with the country reguarly. If Yes, is any action required by ExCom: No. | The licensing and quota system are being implemented in 2015. NOU keep close communication with concerned stakeholders to control the import and export of ODS. 2014 Country Programme has been timely reported.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | TOG | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-06-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 89000 | -292 | 88708 | 88708 | 100% | 0 | 0 |  | 11570 | -38 | 11532 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | TOG | PHA | 56 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | -14308 | 70692 | 70692 | 100% | 0 | 0 |  | 11050 | -1860 | 9190 | 0 | 0 | Project Financially Complete
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 8703 | 397 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | TOG | PHA | 71 | TAS | 25 | A | I |  | 0.9 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 45000 | 5850 | 0 | 0 | 5850 | 0 | Brief progress report (actual/planned): __Plan of action was agreed between the counrty and UNEP. SSFA was drafted, finalised and sent to the county for signature. Legal arrangements (actual/planned):SSFA to be signed in April 2015. Any delay (Yes/No): No_ First mission (actual/planned): N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): n/a___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA now signed, in April 2015 .Disbursment is being processed. Consultation workshops were held for distribution of 2015 quotas.
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | TOG | REF | 35 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-08-01 |  | 2002-10-01 | 2007-02-01 | 60000 | -20927 | 39073 | 39073 | 100% | 0 | 0 |  | 7800 | -2721 | 5079 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | AFR | TOG | REF | 38 | TRA | 08 | A | I | CFC | 5.7 | 5.7 | 0 | 0 | 2002-11-01 | 2003-03-01 | 2004-05-01 |  | 2006-12-01 | 2007-02-01 | 64000 | 0 | 64000 | 64000 | 100% | 0 | 0 |  | 8320 | 0 | 8320 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers | Individual | AFR | TOG | REF | 38 | TRA | 09 | A | I | CFC | 3.8 | 3.8 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-05-01 |  | 2006-12-01 | 2008-02-01 | 43500 | -1003 | 42497 | 42497 | 100% | 0 | 0 |  | 5655 | -131 | 5524 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | TOG | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-02-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Office | Individual | AFR | TOG | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-07-01 | 2004-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | AFR | TOG | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-08-01 | 2007-02-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | TOG | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2006-12-01 |  | 2007-09-01 | 2009-03-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | TOG | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-09-01 | 2008-11-01 |  | 2009-11-01 | 2010-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | TOG | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-06-01 | 2010-12-01 |  | 2011-12-01 | 2012-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | TOG | SEV | 62 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | AFR | TOG | SEV | 68 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 | 2015-12-01 |  |  | 60666 | 0 | 60666 | 47171.06 | 77.76% | 13494.94 | 13495 | 13495 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2013 Art5 data and CP data for 2013 in April 2014 . BNO coordinated the organisation of 4 refrigeration workshop for 100 technicians and the organization of three customs training workshop for 75 customs officers. BNO conducted a survey on the HCFC consumption in February 2014. L egal arrangements (actual/planned): Agreement signed in March 2013. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2013 __ All funds disbursed (yes/no): _ Final payment done in march 2014_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | BNO conducted a survey in March 2015 on HCFC consumption and reported 2014 consuption in May 2015.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | AFR | TOG | SEV | 73 | INS | 26 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60666 |  | 60666 | 0 | 0% | 60666 | -5.8265e-13 | 33350 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA for the newly approved project was prepared in March 2015 and sent to the country for signature , Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA signed by country on 17 April 2015
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tonga) | Multi-Year | ASP | TON | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2015-12-01 |  |  | 64750 | 0 | 64750 | 57976 | 89.54% | 6774 |  | 6774 | 8418 | 0 | 6119 | 2299 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. The Tonga Customs has adopted the 2012 HS code in February 2014. Provisions of permit system for technicians to handle controlled substances and for workshops/dealers to store and sell controlled substances have been put in place. The regulation also includes the labelling requirement of controlled substances. Refrigerant identifier was handed over to Customs for inspection. RAC Association has been established since November 2013. A refresher training workshop for RAC technicians was organized in December 2014 with 25 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. The recovery machines have been kept at the NOU tool bank and released to technician upon request from time to time. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in August 2011. TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards.
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TON | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2009-01-01 | 19700 | 0 | 19700 | 19700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TON | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-02-01 | 2007-03-01 |  | 2008-12-01 | 2009-01-01 | 6566 | 0 | 6566 | 6566 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TON | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-03-01 | 2008-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TON | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TON | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | TON | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 45000 | 75% | 15000 |  | 15000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report:NOO managed implementation to assist in the approval of ODS amendment by Legislative Assembly. Revised versions approved in 2014, NOO implemented and enforced the ODS Act and Regulations.Conducted refresher training for law enforcement officials to be completed in second half of 2014 and to include Customs officials. Based on 2013 data, Tonga has reduced the consumption of HCFCs by 73 per cent of the HCFC baseline for consumption. The country fulfilled its data reporting obligations to the Ozone Secretariat and Multilateral Fund Secretariats in a timely manner. The IS project and stage I of the HPMP were implemented in a complementary manner as the NOU is responsible for both projects and compliance was sustained through the application of a combination of legislative, capacity building and public/sector specific awareness raising activities. HCFC supply was controlled through strengthening and enforcement of the licensing system, the entry into force in February 2014 of the World Customs Organization (WCO) recommended changes to the Harmonized System (2012); implementation and enforcement of the HCFC quota system from 1 January 2013; implementation of the permit system for handling, storage and sales of HCFC; strengthening of the use of iPIC online; training of the custom and enforcement officers. Tonga hosted the Sixth Meeting of Pacific Islands Countries (PIC) Network of Ozone Officers and Training of Customs Officers in March 2014. HCFC demand was successfully controlling through: training courses for RAC technicians on good practices; strengthening of the refrigeration and air conditioning industry association through engagements, meetings and workshops and communication to create an enabling environment. 2014 CP data submitted on line and draft Article 7 data submitted to UNEP CAP for review before final submission. Legal arrangements: SSFA signed in March 2014, first Payment March 2014. payments are made in accordance to SSFA. All funds disbursed (yes/no): No. Any delay? (yes/no): No, the implementation is back on track. Any ongoing problems (yes/no): No. | In May of 2015, Tonga won the Asia Environmental Enforcement Award (AEEA) and based on the enforcement management processes of a case of illegal shipment of R22. IS renewal and terminal reports were prepared and submitted to the 74th Ex. Com. 2014 country programme timely submitted on line in 2015. Draft 2014 Article 7 data submitted to UNEP CAP for review before final submission.
ONG | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 65 | TAS | 28 | A | I |  | 0.2 | 0 | 0 | 0 | 2011-11-01 |  | 2012-11-01 | 2015-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 5000 | 3250 | 0 | 0 | 3250 | 0 | Brief progress report (actual/planned): Adjustements on the ToR required to follow technical assistance support as originally approved .___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): adjusted ToR drafting___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay? (yes/no): yes ___ If Yes, reasons for delay & action plan to resolve: ToR required adjustments to be consistent with original proposal approved. UNEP and NOU reached a common understanding and ToRs are being adjusted ___ If Yes, will delay have impact on project completion date (yes/no): yes ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Programming of funds in Jan-2015. Interchange regarding ToRs for technical assistance proposal took place during Feb-Mar 2015. ToRs agreed by UNEP and NOU. Contracting will take place once UMOJA go-live in Jun-2015. |  |  |  |  | Continued Monitoring
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | TRI | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-09-01 | 2003-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | TRI | REF | 23 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-02-01 |  | 2002-04-01 | 2003-05-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 |  | 3445 | 0 | 3445 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche Palau) | Multi-Year | ASP | TTR | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 | 2015-12-01 |  |  | 62375 | 0 | 62375 | 60552.28 | 97.08% | 1822.72 |  | 1822.72 | 8109 | 0 | 5986 | 2123 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. The Palau Customs has adopted the 2012 HS code in January 2014. Provisions of service license for RAC technicians and storage license of ODSs including HCFCs both in bulk and containing in equipment have been in place. NOU has worked on additional amendments to include ban on importation of used HCFC based-equipment. Refrigerant identifier was handed over to Customs for inspection. RAC Industries and Technicians has been established since September 2013. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in February 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No, last disbursement will be made by December 2015, project being timely implemented. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. 2014 CP data timely submitted online. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards.
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TTR | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TTR | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-12-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TTR | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TTR | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TTR | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | TTR | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-11-01 | 2015-11-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project being implemented satisfactorily. The Government of Palau sustained the effective functioning of its NOU. The NOU is functioning as both the NOO and HPMP project officer. The work of the NOU has become institutionalised into the operations of government and closely integrated with the implementation of the country’s HPMP for which it is also responsible. The NOU timely reported ODS data to the Ozone and Fund Secretariats indicating sustained compliance with the Montreal Protocol and with country programme data being submitted on-line. The 2013 Article 7 data reported a 31 per cent reduction in HCFC consumption in the RAC servicing sector, the only ODS consuming sector in Palau. Other activities included: effective enforcement of the ODS permits and licensing systems, control of illegal trade in ODS customs training and institutional integration including data sharing between enforcement agencies; stakeholder meetings comprising both the public and private sectors on a quarterly basis; assistance with the development and registration of the Palau RAC Association and continuing assistance to support the new body; all activities agreed to under the first tranche of stage 1 of the HPMP for Palau, were successfully implemented; preparation of relevant reports and including renewal documents for the second tranche of stage 1 of the HPMP as part of the regional HPMP for the 12 Pacific Islands countries; and preparation and delivery of public awareness materials to targeted groups such as RAC technicians and also the general publicNewly approved project and to implement the established licensing and quota system and the amended regulations; raise awareness of the HCFC phase-out through increased school and community activities; establish an memorandum of understanding with the Public Landfills to mandate removal of refrigerants from any equipment prior to disposal thus utilizing the technician association to issue certificate acknowledging recovery of refrigerants; strengthen enforcement at the entry point through more collaboration work with the customs and other key stakeholders.Legal arrangements (actual/planned) Project SSFA signed in Jan 2014. First Payment April 2014. All funds disbursed (yes/no): No. Any delay? (yes/no): No, the implementation is back on track. Any ongoing problems (yes/no): No. | NOU prepared and submitted IS terminal and renewal reports for the 74 Ex. Com. 2014 country programme timely submitted on line in 2015.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | TAS | 56 | A | I | HCFC-22 | 0.37 |  |  |  | 2014-05-01 |  | 2014-05-01 | 2015-12-01 |  |  | 30000 |  | 30000 | 0 | 0% | 30000 | -5.8265e-13 | 20000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): __ SSFA signed by country on 29 April 2015 Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): __ SSFA signed by country on 29 April 2015 Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 101 | A | I |  | 11 | 0 | 0 | 0 | 2012-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 103450 | 0 | 103450 | 64403.17 | 62.26% | 39046.83 | 1194.7 | 1195 | 13449 | 0 | 0 | 13449 | 0 | Brief progress report (actual/planned): UNEP in cooperation with the NOU of Turkey decided to organize two consecutive workshops was (1) to train at the Training-of -Trainers workshop in Istanbul the group of 30 officers representing different customs points and provincial environmental directorates in the country who would be later supposed to train their colleagues and (2) to check the training skills of few trainers selected from that group by letting them conduct the workshop in Izmir under supervision of International Consultant. The advantage of such system is that the sustainability of the results of customs training can be better secured provided that the customs authorities will decide to organize a series of next training workshops on a provincial level utilizing the skills and knowledge of officers trained at the Training-of-Trainers workshop. The Agenda and Concept Note for both workshops were prepared and the international consultant was recruited. All logistics were agreed and UNDP country office informed about the travel and DSA for both meetings. Legal arrangements (actual/planned): The project is directly managed and implemented by UNEP First mission (actual/planned): Not planned TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): The first disbursement is planned for February 2015. All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The National Training of Trainers workshop for Customs officers (ToT) was organized on 25-27 February of 2015 in Istanbul, Turkey and the Training workshop for other customs officers was organized on 2-3 March of 2015 in Izmir, Turkey. The main objective of the training programme was to provide the customs and enforcement officers of Turkey with the necessary practical skills and knowledge to identify HCFCs and HCFCs containing equipment. It was important to enable customs officers to get acquainted with the ODSs regulations and other legislation regarding ozone issues and create awareness amongst customs officers on their role in enforcing Montreal Protocol at the national level. An additional special objective of TOT workshop was to make the participants acquainted with the methodology of dealing with the issues at the training workshops they will be supposed to conduct in the future in their capacity as trainers. The idea of holding two consecutive customs training workshops on monitoring and control of ODS trade – one designed as special ToT workshop and the other as the “standard” customs training workshop – was proved to be perfect. It is therefore recommended that similar approach is taken to customs trainings foreseen in the HPMPs in other developing countries. Legal arrangements (actual/planned): The project is directly managed and implemented by UNEP First mission (actual/planned): Not planned TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): The first disbursement was done in February 2015. All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tuvalu) | Multi-Year | ASP | TUV | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2015-12-01 |  |  | 47875 | 0 | 47875 | 44398 | 92.74% | 3477 |  | 3477 | 6224 | 0 | 5049 | 1175 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014.The Department of Customs has adopted the 2012 HS code for the import and export control. Tuvalu was in the process of amending the Ozone Depleting Substance Regulation to control the import/export of HCFC-based equipment and to include provision regarding requirement of handling license and renewal of license. The amendment was on its last stage of getting signed after approved by cabinet. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. A refresher training workshop for customs and enforcement officers was organized in November 2014 with 20 participants. TOR for RAC Association was being finalized in close collaboration with the Attorney General Office. RAC servicing tools equipment/tools have not yet distributed to RAC technicians due to the need to link with the established RAC Association. However, equipment was released to technicians who made the application to NOU from time to time. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in November 2011. First Mission: August 2014 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No, last disbursement will be released by December 2015. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted on line. Training New NOU in the HPMP management including reporting requirements (progress and financial report).
FIN | UNEP | Country programme preparation | Individual | ASP | TUV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 |  |  | 5200 | -3250 | 1950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TUV | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase II) | Individual | ASP | TUV | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 7583 | 0 | 7583 | 7583 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase II) | Individual | ASP | TUV | SEV | 56 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | TUV | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
COM | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | TUV | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-11-01 | 2014-12-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief Progress report: Project Completed in December 2014. 2014 quotas being managed to assist in implementing the HCFC import/export quota system from 1 January 2013. NOO meets regularly with the Customs departs and as part of the national stakeholder meetings for strengthening its cooperation with the Department of Customs for data collection and illegal trade control. Customs training completed and refresher training planned for March 2014, technicians training to be completed in April 2014. Ongoing awareness raising, 2013 World Ozone Activities celebrated. Interim committee is established and managed by the NOO an operational industry association from 2013. As part of the HPMP tranche 1 stage 1, NOU managed the implementing the HCFC import/export quota system from 1 January 2013, strengthening its cooperation with the Department of Customs for data collection and illegal trade control, implementing technician and customs training, awareness-raising activities; an operational industry association from 2013; and data reporting to the Fund and Ozone Secretariats. Legal arrangements (actual/planned) Agreement signed in December 2012. First Payment November 2013. All funds disbursed (yes/no): Yes. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. Project renewed at the 72nd Ex. Com. | Project completed in December 2014. New NOU appointed in March of 2015. New NOU has begun to be trained on the required task of the NOU and including the requirements for the management of the HPMP. SSFA signed on April 2015. First Payment made as per SSFA. Country timely submitted CP 2014 data on line. Draft 2014 Article 7 data submitted to UNEP CAP for review before final submission.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | TUV | SEV | 72 | INS | 10 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Change in NOU with mimimal instituional transfers. New NOU appointed in March of 2015. UNEP is working with Government to build the required capaicity of the new NOU. Country timely submitted CP 2014 data on line. Draft 2014 Article 7 data submitted to UNEP CAP for review before final submission. Legal arrangement: SSFA signed on April 2015. First Payment made as per SSFA April 2015. All funds disbursed (yes/no): No. Any delay? (yes): Yes- delays in obtaining final approval on legal aggreement and on signing. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No : New NOU is effective. | New NOU appointed in March of 2015. New NOU has begun to be trained on the required task of the NOU and including the requirements for the management of the HPMP. SSFA signed on April 2015. First Payment made as per SSFA. Country timely submitted CP 2014 data on line. Draft 2014 Article 7 data submitted to UNEP CAP for review before final submission.
COM | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | UGA | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2013-07-01 | 2014-12-01 | 30000 | -8248 | 21752 | 15184.07 | 69.81% | 6567.93 | 0 |  | 3900 | -1072 | 2828 | 0 | 0 | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-12-14 | 2016-12-01 | 2016-12-01 |  |  | 40500 | 0 | 40500 | 2771.24 | 6.843% | 37728.76 | 10000 | 10000 | 5265 | 0 | 0 | 5265 | 1300 | Brief progress report (actual/planned): __ NOU organized National Workshop for main stakeholders to discuss the implementation of HPMP activities. NOU conducted a survey of equipment available in the vocational training centres in-order to determine the need for new equipment to be procured under the HPMP. A total of 50 Customs Officers were trained in the implementation and enforcement of ODS control measures and 30 RAC technicians were trained in the use of ODS alternatives. Legal arrangements (actual/planned):SSFA was signed in July 2013. Any delay (Yes/No): No_ First mission (actual/planned): __N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in October 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Country conducted steering committee meeting to process HCFC quota allocations for 2015 and registered all importers of HCFC for 2015
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | UGA | PHA | 71 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-05-01 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): _The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. Verification will be done in 2016, when the country request for third HPMP tranche Legal arrangements(actual/planned):N/A___ First mission (actual/planned): __N/A. TOR completed(actual/planned): _YES__ First disbursement date (actual/planned): N/A.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | The process for identifying a consultant to undertake the verification has commenced and it will be finalised before the end of 2015. The actually verification will be done in 2016.
FIN | UNEP | Country programme preparation | Individual | AFR | UGA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1994-06-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the ODS unit) | Individual | AFR | UGA | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1997-07-01 |  | 2014-12-01 | 2014-12-01 | 64515 | -37741 | 26774 | 26774 | 100% | 0 | 0 |  | 8387 | 0 | 3871 | 4516 | 0 | Brief progress report (actual/planned): Country got new IS phase. Despite lack of IS funds, country still implementing Montreal Protocol activities. NOU collected ODS data for 2014 and produced awareness materails which were distributed to the public. The country celebrated international ozone day and participated in all Network meetings and other global Montreal Protocol meetings. Legal arrangements(actual/planned): old project. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):old project,_ All funds disbursed (yes/no): Yes, balance of funds returned to Ex-com_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project financially completed, balance of funds returned to Ex-com. |  | 1999-12-01
ONG | UNEP | Institutional strengthening (phase II: 1/2015-12/2016) | Individual | AFR | UGA | SEV | 73 | INS | 19 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 37226 |  | 37226 | 0 | 0% | 37226 | -5.8265e-13 | 18000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and sent to the county for signing. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | URT | PHA | 50 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-11-01 | 2013-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 |  | 2210 | 0 | 2210 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-03-01 | 2011-06-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 |  | 17030 | 0 | 17030 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | URT | PHA | 57 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 |  | 2013-07-01 | 2014-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Project completed
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2013-12-01 | 2014-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0 | Project Financially Complete
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | TAS | 31 | A | I |  | 0.1 | 0 | 0 | 0 | 2012-07-01 | 2013-02-01 | 2015-07-01 | 2015-07-01 |  |  | 55000 | 0 | 55000 | 35000 | 63.64% | 20000 | 0 | 5000 | 7150 | 0 | 4550 | 2600 | 1950 | Brief progress report (actual/planned): __ The country conducted regional training workshops and trained a total of 65 refrigeration and air-conditioning experts from Mbeya and Mwanza regions. A total of 80 customs officers from Arusha and Dodoma regions were trained in the enforcement of ODS control measures. The country has completed implementation of first tranche activities and second tranche request is being prepared. Legal arrangements (actual/planned):SSFA was signed in January 2013. Any delay (Yes/No): No_ First mission (actual/planned): __First mission by CAP to launch the HPMP and conduct training for technicians was made jointly done with UNIDO in June, 2013._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in February 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU registered all importers for 2015 and processed the allocation of 2015 HCFC quotas.
FIN | UNEP | Country programme preparation | Individual | AFR | URT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1996-07-01 | 1999-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | URT | SEV | 20 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1999-10-01 |  | 2004-12-01 | 2007-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | URT | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | URT | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | URT | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | AFR | URT | SEV | 66 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2015-12-01 |  |  | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU registered all importers of HCFC for 2015 and processed the allocation of HCFC import quotas. The NOU collected and reported 2013 ODS data to both OS and MFS. The country celebrated Ozone day through conducting of drama, poems and organized schools competition on ozone issues. Implementation of activities completed and country got a new IS project approved. . Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in July 2012. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment was sent in July 2012,_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Collection of the 2014 data on ODS imports and consumption commenced and NOU will submit to both OS and MLFS 2014 ODS data on time. Project completed and country processing to start implementation of new IS pahse
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 4/2014-3/2016) | Individual | AFR | URT | SEV | 72 | INS | 32 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-03-01 | 2016-03-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 | -5.8265e-13 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA finalised and sent to the county for signing. Legal arrangements(actual/planned): NO. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA for newly approved project drafted and sent to country for signature
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | I | CFC | 45.8 | 45.8 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2007-03-01 | 2009-12-01 | 65000 | -2831 | 62169 | 62169 | 100% | 0 | 0 |  | 8450 | -368.03 | 8082 | -0.03 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Vanuatu) | Multi-Year | ASP | VAN | PHA | 63 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2015-03-01 | 2015-12-01 |  |  | 76250 | 0 | 76250 | 71919 | 94.32% | 4331 |  | 4331 | 9913 | 0 | 7955 | 1958 | 0 | Brief progress report (actual/planned): The licensing and quota system has been enforced in 2014. The Vanuatu Customs & Inland Revenue (VCIR) has adopted the 2012 HS code, which will be effective from 1 January 2015 onwards. The provisions for licensing for storage, sale and handling of HCFCs have been put in place. NOU has worked with concerned agencies to ban all HCFC-based equipment (both new and used). Refrigerant identifiers were handed over to Customs for inspection. A refresher training workshop for customs and enforcement officers was organized in September 2014. The RAC Association of Technicians has been established since March 2011. About 40% of servicing tools were handed-over to technicians and the remaining would be distributed to technicians upon finalization of eligibility criteria. Ongoing awareness raising and monitoring of HPMP implementation. Legal arrangement: The SSFA has been signed in August 2011. First Mission: May 2012 TOR completed: N/A First disbursement date: August 2011 All funds disbursed (yes/no): No, last disbursement will be disbursed by December 2015. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted on line. Held meeting with the NOU and UNEP CAP staff in the margins of the OEWG April 2015 to discuss possible revision need of the HPMP and taking into consideration the devastation on the built infrastructure following Cyclon Pam in early 2015. Refresher RAC sector training to be delivered in July 2015 in three of the islands in Vanuatu.
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2008-12-01 | 2009-11-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | VAN | SEV | 54 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-02-01 | 2009-03-01 |  | 2011-01-01 | 2011-06-01 | 6750 | 0 | 6750 | 6750 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | VAN | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | VAN | SEV | 62 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
COM | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | VAN | SEV | 67 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-12-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Project Completed in December 2014. Stable and continued NOU and NOO. Assist in enforcing the quota system for HCFC import/export control from 1 January 2013, and implementing customs and technician training programmes, active participation in the informal prior informed consent on trade of ODS to prevent any illegal trade including ensuring timely annual renewal, conducting awareness-raising activities on ozone protection, submitting timely country programme programme reports and the Article 7 data reports to the Fund and Ozone Secretariats. . Assist in enforcing the quota system for HCFC import/export control from 1 January 2013, and implementing customs and technician training programmes, active participation in the informal prior informed consent on trade of ODS to prevent any illegal trade, conducting awareness-raising activities on ozone protection, submitting timely 2013 country programme programme reports and the Article 7 data reports to the Fund and Ozone Secretariats. Attend all regional network meetings. Compliance sustained (as planned) Legal Agreement signed on Nov 2012 First Payment on March 2013. All funds disbursed (yes/no): Yes Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | NOU as lead agency responsible for the HPMP prepared and submmited required HPMP reports as required for for the 74th Ex. Com. 2014 country programme timely submitted on line in 2015. Complinace requirements maintained.
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | VAN | SEV | 72 | INS | 11 | A | I |  | 0 |  |  |  | 2014-05-01 |  | 2016-12-01 | 2016-12-31 |  |  | 60000 |  | 60000 | 0 | 0% | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | Brief project report: Stable and continued NOU and NOO. NOU is part of the instituional structure of the Environment division and reports to the Head of Environment. The NOU is responsible for the management of the implementation of the HPMP. Assist in enforcing the quota system for HCFC import/export control, and implementing customs and technician training programmes, active participation in the informal prior informed consent on trade of ODS to prevent any illegal trade including ensuring timely annual renewal, conducting awareness-raising activities on ozone protection, submitting timely country programme reports and the Article 7 data reports to the Fund and Ozone Secretariats for reporting year 2014. NOU attended the April 2015 HFC international work shop and OEWG held in Bangkok Thailand. Compliance Sustained. Legal arrangements (actual/planned) SSFA Signed on the in February of 2015, first disbursement made on in April of 2015. All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | SSFA Signed on the in February of 2015, first disbursement made on in April of 2015. Timely submission of country programme report on line and the Article 7 data reports to the Fund and Ozone Secretariats for reporting year 2014. NOU attended the April 2015 HFC international work shop and OEWG held in Bangkok Thailand.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-01 |  | 2014-12-14 | 2014-12-14 | 50646 | -39968 | 10678 | 10678.1 | 100% | -0.1 | -4.5475e-13 | 0 | 6584 | 0 | 1388 | 5196 | -5.9117e-14 | Brief progress report: No disbursements in 2014. UNEP submitted a signed agreement with remaining budget but the Government did not sign it in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2011/Nov 2011. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: NOO changes in 2014. A request of changing the signatory of the agreement (by Chief of NOU instead of Minister) was not acceptable to UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. The NOU requested the funds are transferred to UNIDO in April 2015. If Yes, is any action required by ExCom: Transfer project balances from UNEP to UNIDO | Government asked project balances are transferred from UNEP to UNIDO |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
TRF | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-01 |  | 2014-12-14 | 2014-12-14 | 46661 | 0 | 46661 | 0 | 0% | 46661 | 0 | 0 | 6066 | 0 | 0 | 6066 | 0 | The implementation of HPMP second tranche deferred up to first tranche is completed- | Government asked project balances are transferred from UNEP to UNIDO |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
TRF | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | TAS | 123 | A | I |  | 0.3 |  | 0 |  | 2013-07-01 |  | 2015-07-01 |  | 2014-12-14 | 2014-12-14 | 25125 | 0 | 25125 | 0 | 0% | 25125 | 0 | 0 | 3266 | 0 | 0 | 3266 | 0 | The implementation of HPMP third tranche deferred up to first tranche is completed- | Government asked project balances are transferred from UNEP to UNIDO |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the agreement signing and low disbursement rates of approved funds.
FIN | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 | 2009-12-01 | 120000 | -12164 | 107836 | 107836 | 100% | 0 | 0 |  | 15600 | -1581 | 14019 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 | 2011-03-01 | 80000 | -40619 | 39381 | 39381 | 100% | 0 | 0 |  | 10400 | -5280 | 5120 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Implementation of the RMP: workshop for finalization of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 |  |  | 566 | 0 | 566 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2006-02-01 | 200000 | -40959 | 159041 | 159041 | 100% | 0 |  |  | 26000 | -5325 | 20675 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-01 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 |  |  | 17846 | 0 | 17846 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 |  |  | 3510 | 0 | 3510 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 |  |  | 11898 | 0 | 11898 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | ASP | VIE | SEV | 33 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 |  |  | 11898 | 0 | 11898 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | A | I | CFC | 9.8 | 10.2 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2005-07-01 | 2007-12-01 | 118976 | -20 | 118956 | 118956 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | VIE | SEV | 52 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-06-01 |  | 2009-06-01 | 2009-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | VIE | SEV | 57 | INS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-06-01 |  | 2011-06-01 | 2011-11-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | VIE | SEV | 63 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-06-01 |  | 2013-06-01 | 2014-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Project is financially completed. | Project is financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 7/2013-6/2015) | Individual | ASP | VIE | SEV | 68 | INS | 60 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-06-01 | 2015-06-01 |  |  | 118976 | 0 | 118976 | 59488 | 50% | 59488 |  | 59488 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system was implemented in 2014. Quota and import permits for methyl bromide for QPS and non QPS purposes were issued separately by the Department of Plan Protection. NOU reviewed statistics of HCFC import/export to monitor the actual import/export of HCFCs monthly. Collected customs records and customs declarations of ODS import shipments and monitored the application of HS code for HCFCs and HFCs to avoid the case of misapplication. Policy recommendations had been issued by MONRE not to allow establishment of new manufacturing facilities using HCFC; not to allow expansion of production of the existing HCFC based manufacturing facilities and to reduce new installations of HCFC based refrigeration equipment in cold stores in May 2014. NOU conducted joint ozone – customs enforcement to review the statistics and to discuss the movement of ODS along the border.The 2013 Article 7 and Country Programme Implementation were reported to the Ozone Secretariat and Multilateral Fund Secretariat respectively. Published and distributed 1500 copies of each of 3rd and 4th for 2013 and 1st quarterly Ozone newsletters for 2014. Legal arrangements (actual/planned): The SSFA has been signed in April 2014. Initial stages of project implementation (actual/planned): NOU is operating well. Intermediate goals achieved (actual/planned): Improving customs control of HCFC import, especially import of pre-blended HCFC-141b polyols; implementing, coordinating, integrating and supervising all activities for implementation of the Montreal Protocol and HPMP, and methyl bromide phase-out plans in particular; and data reporting to the Fund and Ozone Secretariats. First disbursement date: June 2014 All funds disbursed (yes/no): No. Any delay? (yes/no): No, the implementation is back on track. Any ongoing problems (yes/no): No. | The licensing and quota system are being implemented in 2015. NOU keep close communication with concerned stakeholders to control the import and export of ODS. Government plans to ban import of bulk of HCFC-141b following the completion of the investment activities in foam sector. The 2014 country programme progress report was submitted.
ONG | UNEP | Extension of the institutional strengthening project (phase X: 7/2015-6/2017) | Individual | ASP | VIE | SEV | 73 | INS | 68 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2017-06-30 | 2017-06-30 |  |  | 118976 |  | 118976 | 0 | 0% | 118976 |  | 118976 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved project at the 73rd Meeting in November 2014. After the ExCom approval, UNEP worked with the NOU to draft the SSFA. Legal arrangements(actual/planned): No. Initial stages of project implementation(actual/planned): N/A Intermediate goals achieved (actual/planned): No. Any delay?(yes/no): No. Any ongoing problems (yes/no): No. | Continue discussion with the NOU was made to finalize the SSFA since the beginning of the year. The draft SSFA has been prepared and submitted to the government for review and comments. The implementation period of SSFA for IS Project phase X will follow the implementation priod as approved by the ExCom.
FIN | UNEP | Project preparation for a national phase-out management plan | RMP | ASP | YEM | PHA | 50 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-04-01 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | YEM | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2013-12-01 | 2014-11-14 | 125000 | -108600 | 16400 | 16400 | 100% | 0 |  |  | 16250 | -14118 | 2132 | 0 | 0 | Project financialy Completed | Project financialy Completed
ONG | UNEP | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2010-12-01 | 2016-12-01 |  |  | 315000 | 0 | 315000 | 232213 | 73.72% | 82787 |  | 82787 | 40950 | 0 | 30188 | 10762 | 0 | Remaining obligated resources that couldn’t be disbursed earlier under old country contract are now part of the ongoing country contract and are in now in process of disbursement during 2015 subject to improvement of stability in the country. Pending procurement of customs identifiers is also in process and delivery is also subject to stability in the country. | Remaining obligated resources that couldn’t be disbursed earlier under old country contract are now part of the ongoing country contract and are in now in process of disbursement during 2015 subject to improvement of stability in the country. Pending procurement of customs identifiers is also in process and delivery is also subject to stability in the country.
COM | UNEP | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 |  | 2011-04-01 |  | 2014-12-01 |  | 140000 | 0 | 140000 | 0 | 0% | 140000 |  | 140000 | 18200 | 0 | 0 | 18200 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 40 | A | I |  | 11.6 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2016-12-01 |  |  | 215000 | 0 | 215000 | 0 | 0% | 215000 |  | 215000 | 27950 | 0 | 0 | 27950 | 0 | Brief progress report (actual/planned): - Country contract was signed at end of 2014 incorporating relocated balances from NPP as per ExCom decision 68/53. First payment planned in 2015 - Country made detailed work-plan for the implementation of the HPMP which is was pending the funds disbursement • Legal arrangements(actual/planned): Signed end of 2014 • First mission (actual/planned): No mission possible to Yemen for the last 3 years due to security considerations • TOR completed(actual/planned): TORs for technical components were drafted and handed to NOU for comments/inputs and action • First disbursement date (actual/planned): No • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract • If Yes, will delay have impact on project completion date (yes/no): Yes, stage-I is likely to be extended beyond 2015 • Any ongoing problems (yes/no): Yes, special consideration for the implementation in Yemen given the current conflict situation • If Yes, is any action required by ExCom: No | # UNEP/UNIDO organized coordination meeting with NOU of Yemen (March 2015) in Bahrain where a detailed work-plan for expediting HPMP activities was concluded # Conflict started in Yemen end of March 2015 resulting in putting all activities on pause status due to high risks and deteriorated security situation in most areas of the country # Country contract payment was ready to be transferred but recent conflict resulted in postponing the payment after consultation with NOU till verifying the condition of the project special bank account. |  |  |  |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | YEM | PHA | 73 | PRP | 44 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-11-01 | 2016-11-30 |  |  | 50000 |  | 50000 | 0 | 0% | 50000 |  | 50000 | 6500 | 0 | 0 | 6500 | 0 | Brief progress report (actual/planned): Newly approved project | • Brief progress report (actual/planned): - Initial work-plan for the preparation of stage-II is shared with the country - Coordination meeting is organized with the country and agreed on the contractual arrangements and timeframe of implementation - TORs for the local experts and data to be collected during the preparation of Stage-II is under development by UNEP and UNIDO in consultation with the country • Legal arrangements(actual/planned): - Draft legal agreement is under preparation • Initial stages of project implementation(actual/planned): Coordination meeting and initial work-plan made • Intermediate goals achieved (actual/planned): N/A • Project completion and follow up: Planned to be completed by end of 2016 (subject to country stability) • First disbursement date (actual/planned): 2015 (subject to country stability) • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Security and conflict situation in the country • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Planned project completion will be assessed subject to country situation before ExCom-75 • If Yes, is any action required by ExCom: No
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2001-09-01
FIN | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 |  | 2006-12-01 | 2011-06-01 | 25000 | -5000 | 20000 | 20000 | 100% | 0 |  |  | 3250 | -650 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2007-10-01 | 2005-08-01 |  | 2010-12-01 | 2014-11-14 | 57750 | -12750 | 45000 | 45000 | 100% | 0 |  |  | 7508 | -1658 | 5850 | 0 | 0 | Project Completed | Project Completed
FIN | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-08-01 |  | 2008-12-01 | 2010-12-01 | 189500 | 0 | 189500 | 189500 | 100% | 0 |  |  | 24635 | 0 | 24635 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2011-09-01 | 2011-12-01 | 91825 | 0 | 91825 | 91825 | 100% | 0 |  |  | 11937 | 0 | 11937 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 |  |  | 15340 | 0 | 15340 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | YEM | SEV | 41 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 104000 | -391 | 103609 | 103609 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV-supplementary request) | Individual | ASP | YEM | SEV | 48 | INS | 25 | A | I | CFC | 5.4 | 0 | 0 | 0 | 2006-04-01 | 2006-06-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | YEM | SEV | 53 | INS | 27 | A | I | CFC | 14 | 14 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 170000 | -392 | 169608 | 169608 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | YEM | SEV | 59 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 92083 | 77916 | 169999 | 169999 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | YEM | SEV | 68 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-01-01 | 2014-12-01 |  | 2014-12-14 |  | 169999 | 0 | 169999 | 136000 | 80% | 33999 |  | 33999 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Project completed with HCFC licensing system in place since Jan-2013, including procedures for licensing/quota system. However due to Yemen’s political and security unrest, movement within country was limited and therefore the follow up on enforcement cannot be ensured. NOU organized many national meetings and workshops, as well as participated actively in meetings of MP international and regional. Due to the unrest, NOU was obliged to hold meetings with IAs out of Yemen, therefore limiting the stakeholder participation. Legal arrangements (actual/planned): Agreement completed and payments disbursed. Initial stages of project implementation (actual/planned): Activities completed as reported in terminal report. Intermediate goals achieved (actual/planned): Article 7 and CP data was collected and reports submitted to OS and MLFS for the year of 2013. Project completion and follow up: Project completed, but not financially closed. Country is unable to confirm status of final payment disbursed by UNEP in Jan-2015. First disbursement date (actual/planned): First payment against SSFA was made in Jan-2014 and all funds disbursed, but NOU cannot trace UNEP’s final payment. All funds disbursed (yes/no): Yes (but final payment not traced by NOU). Project ongoing & delayed Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: Delay by country in actual receipt of last payment, as they are unable to trace funds, which shows disbursed, last payment Jan-2015. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No. | Project completed, but not financially closed. Security situation deteriorated in Yemen since March 2015 due the local armed conflict which led to pause most of NOU activities on ground. UNEP will keep monitoring the situation in Yemen in the upcoming months especially with regards to financial transactions and operation of NOU and would report back to ExCom accordingly.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | ASP | YEM | SEV | 73 | INS | 43 | A | I |  | 0 |  |  |  | 2014-11-01 |  | 2016-12-01 | 2016-12-31 |  |  | 169999 |  | 169999 | 0 | 0% | 169999 |  | 169999 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved project | Legal instrument delayed due to country escalation of politicial insecurity. Key staff of NOU are unable to return to Yemen after attending the Main Meeting in Bahrain during Mar-2015.
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-02-01 | 2012-12-01 |  | 2014-12-01 |  | 26000 | 0 | 26000 | 18712.76 | 71.97% | 7287.24 | 6318.2 | 6318 | 3380 | 0 | 2432.6588 | 947.3412 | 821.366 | Brief progress report (actual/planned): It was organized the exhibition booth and discussion forum on ozone and climate-friendly technologies during the 45th International Congress and Exhibition on Heating, Refrigerating and Air Conditioning in Belgrade, Serbia, 3-5 December of 2014. The Ministry, UNEP and the KGH association included the special “ozone pages” into the quarterly produced HVAC&R journal by KGH association (in Serbian and English languages). The tranche activities are completed. Legal arrangements (actual/planned): The project is directly implemented by UNEP First mission (actual/planned): December of 2011 as planned TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): November 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | TAS | 43 | A | I |  | 0.2 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 27500 | 0 | 27500 | 0 | 0% | 27500 | 0 | 27500 | 3575 | 0 | 0 | 3575 | 0 | Brief progress report (actual/planned): UNEP and the NOU have planned the activities: the first sub-component on preparation, printing and dissemination of the check-lists, templates for reporting, log-books and other enforcement related materials. The NOU has requested to obtain the best practices from EU countries regarding the check list for environment inspectorate. The NOU will print and disseminate the check list among environment inspectors. Under the second sub-component was agreed to organize 4 national meetings with the Environmental Inspection, as a follow up activity on the initial training. The third sub-component on training for operators of the ODS installations and ODS waste centers to enforce requirements of national legislation will be implemented by the end of the tranche. The last sub-component which is awareness raising is implemented through organizing the annual exhibition booth and 1 day forum on environmentally friendly modern refrigeration technologies jointly with the Ministry of Environment, the Serbian HVAC&R association KGH and UNEP. Legal arrangements (actual/planned): The project is directly implemented by UNEP First mission (actual/planned): No. NOU implements all activities at national level. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): NO, planning stage All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): There are delays in the implementation as the Ozone officer left the Ministry. The new Ozone Officer has been recently appointed by the Government and UNEP plans to re-start implementing activities in the second half of the year of 2015. Legal arrangements (actual/planned): The project is directly implemented by UNEP First mission (actual/planned): No. NOU implements all activities at national level. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): No All funds disbursed (yes/no): NO Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: The appointment of the new Ozone Officer If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 | 0 |  | 3250 | -1204 | 2046 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | ZAM | PHA | 50 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 |  | 12220 | 0 | 12220 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ZAM | PHA | 56 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2013-04-01 | 2014-04-01 | 85000 | -5000 | 80000 | 80000 | 100% | 0 | 0 |  | 11050 | -650 | 10400 | 0 | 0 | Project completed
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ZAM | PHA | 57 | TAS | 23 | A | I | CFC-12 | 4.1 | 4.1 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2012-03-01 | 2013-03-01 | 42000 | -5000 | 37000 | 37000 | 100% | 0 | 0 |  | 5460 | -650 | 4810 | 0 | 0 | Project completed
FIN | UNEP | TPMP verification | Individual | AFR | ZAM | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2010-03-01 |  | 2013-04-01 | 2014-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project Financially Complete |  |  | 2011-12-01
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 |  | 2013-07-01 |  | 40000 | -1365 | 38635 | 35000 | 90.59% | 3635 | 0 | 5000 | 5200 | -177 | 4550 | 473 | 0 | Brief progress report (actual/planned): __ The NOU implementing certification scheme for RAC technicians and certified 25 refrigeration experts on the refrigeration and air-conditioning services. The NOU conducted 4 training workshops for customs officers and a total 80 officers were trained. The NOU conducted 3 meetings of the Refrigeration Association and conducted joint annual inspection visits to major retail shops of refrigerants to check on the quality of refrigerants that are available on the market. Legal arrangements (actual/planned):SSFA was signed in February 2012. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visisted the country in October 2014._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made inApril 2012.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU processed the allocation of 2015 HCFC quotas , conducted stakeholders' consultative meetings on 2015 HCFC 10% reduction target. Implementation of project activities completed and country processing implementation of second tranche activities.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ZAM | PHA | 71 | TAS | 28 | A | I |  | 0.3 |  | 0 |  | 2013-12-01 |  | 2016-12-01 | 2016-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): __ Plan of action was agreed between the counrty and UNEP. SSFA was drafted, finalised and sent to the county for signature. Legal arrangements (actual/planned):SSFA not yet signed . Any delay (Yes/No): No_ First mission (actual/planned): __NO._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _NO__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA not yet signed. UNEP continues negotiations with county and expects signature by September 2015.
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 09 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 | 0 |  | 9828 | 0 | 9828 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 | 2008-12-01 | 50400 | 0 | 50400 | 50400 | 100% | 0 | 0 |  | 6552 | 0 | 6552 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 |  | 2009-03-01 | 2011-03-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ZAM | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-11-01 | 2011-03-01 |  | 2012-03-01 | 2013-12-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | AFR | ZAM | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-11-01 | 2016-11-01 |  |  | 65520 | 0 | 65520 | 0 | 0% | 65520 | 0 | 65520 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ Plan of action was agreed between the counrty and UNEP. SSFA was drafted, finalised and sent to the county for signature . Legal arrangements (actual/planned):SSFA not yet signed. Any delay (Yes/No): No_ First mission (actual/planned): __NO._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _NO__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | SSFA not yet signed. UNEP continues negotiations with county and expects signature by September 2015. Country collected data and reported 2014 CP and A7 to MLFs and OS.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 | 0 |  | 3250 | -359 | 2891 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 | 0 |  | 22237 | 0 | 22237 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 |  | 14824 | 0 | 14824 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 |  | 14824 | 0 | 14824 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-11-01 | 2009-06-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | ZIM | SEV | 50 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-06-01 | 2008-11-01 |  | 2011-07-01 | 2011-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | AFR | ZIM | SEV | 59 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2013-03-01 | 2014-03-01 | 80297 | 67944 | 148241 | 148241 | 100% | 0 | 0 |  | 10438.61 | 0 | 10439 | -0.39 | 0 | Project completed.
ONG | UNEP | Renewal of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | AFR | ZIM | SEV | 69 | INS | 46 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-11-01 | 2015-03-01 | 2015-03-01 |  |  | 148242 | 0 | 148242 | 50000 | 33.73% | 98242 | -5.8265e-13 | 98242 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU conducted two training workshops for RAC technician and trained 30 technicians. The NOU collected and reported 2013 ODS data to both OS and MFS . The country celebrated Ozone day through conducting and created awareness to the general public. . Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in November, 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment was sent in November, 2013,_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Country collected and submitted to both Ozone Secretariat and Multilateral Fund Secretariat 2014 data on ODS imports and consumption. NOU organised a meeting with all importers to discuss the quota allocation for 2015.Project completed and new IS phase was approved at the 71 Ex-com
ONG | UNIDO | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | Individual | AFR | AFR | FUM | 54 | DEM | 40 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-06-01 | 2010-03-31 | 2015-12-01 |  |  | 306812 | 0 | 306812 | 148781.69 | 48.49% | 158030.31 | 18924.33 | 40000 | 23011 | 0 | 11159 | 11852 | 1419 | - TUNISIA: Meeting with date packing facilities and representatives from the food association (GIF) took place in Tunis between 11 and 14 March, including visit to packing houses. GIF, NOU and UNIDO are working on a plan of action for the tests to be conducted in the season 2014. The results from the test and experience from them will be used in the preparation of the final phase-out project (planned to be submitted to the last ExCom meting in 2014). - NOU Algeria requested UNIDO to support a PRP request for the total MB phase-out to the ExCom Meeting in May. - Plan of action for 2014 tests was finalized and necessary equipment delivered to test the application of CO2+PH3. - Tests were conducted between November 2014 and January 2015 and data collection took place. - ALGERIA: There is still lack of expertise in Algeria which makes the decision on the project execution more difficult. - Decision and agreement with NOUs on the best way of proceeding with the demonstration project, due to lack of identification of national experts by NOUs. Milestones achieved: Milestone 1: Legal arrangements - Not relevant Milestone 2: Initial stages of project implementation began - Yes (for Tunisia only) Milestone 3: Intermediate goals achieved - Yes (for Tunisia only) Milestone 4: Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: Activities in Tunisia followed the agreed path. For Algeria the situation is still not moving, though that was expected as well. Actions towards next goals: Tunisia: finalize tests; arrange dissemination materials/strategy; test other technologies (e.g. vacuum, EF) Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Lack of expertise in Algeria Any impact on project completion date: Yes If yes, implications: Planned project completion date needed to be extended to allow implementation of activities. Any action required by Executive Committee? No | TUNISIA: '- Tests on the application of CO2+PH3 were completed and results drafted in a scientific paper for publication. - Results were presented to interested local companies in a workshop in Tunisia. - Results and lessons learned were able to support the design of the conversion project. ALGERIA: UNIDO communicated with the NOU to identify a proper local expert to support in the project implementation. Milestones achieved: Milestone 1: Legal arrangements - Not relevant Milestone 2: Initial stages of project implementation began - Yes (for Tunisia only) Milestone 3: Intermediate goals achieved - Yes (for Tunisia only) Milestone 4: Project completion and follow-up - No Actions towards next goals: Finalize the dissemination of results. Support the test of other technologies (e.g. vacuum and EF), based on the interest from the local companies. Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Lack of expertise in Algeria Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a recovery and recycling projects in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia and Senegal | Individual | AFR | AFR | REF | 17 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1997-09-01 | 1999-08-01 | 45000 | -1119 | 43881 | 43881 | 100% | 0 | 0 |  | 5850 | -155 | 5695 | 0 | 0 | FIN
COM | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 37 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2009-09-01 |  | 2014-12-14 |  | 747500 | 0 | 747500 | 727564.25 | 97.33% | 19935.75 | 18937.35 | 18937.35 | 56063 | 0 | 54567 | 1496 | 1420 | - The delay caused by the fact that the extension of the two financial agreements between AdF/FFEM and UNIDO have been administratively completed only at the end of February 2014 and the second tranches under both agreements were transferred to UNIDO account only in March 2014. - Currently the relevant documents have been collected from the beneficiaries in Senegal and Nigeria. - A field mission took place to verify the CFC chillers in Haj Abdalla Spinning Factory at the end of March 2014. The mission found three old York CFC chillers and verified technical information required for assistance from the project. Based on this new information, the work plan for Sudan has been adjusted to include this Haj Abdalla factory as the beneficiary. Milestones achieved: Milestone 1: Grant agreement with the Alkem Industries in Nigeria signed and funds disbursed (from AdF funds) - Yes Milestone 2: Grant agreement with the King Fahd Palace Hotel in Senegal signed and funds disbursed (from AdF funds) - Yes Milestone 3: Grant agreements with five beneficiaries in Egypt signed and funds disbursed (from AdF-Japan funds) - Yes Milestone 4: Mission of UNIDO International Technical Expert to the Hajabdallah factory in Sudan conducted in November 2014 - Yes Activities planned but not implemented, reasons and strategy: The MP part of the project has been operationally completed as of December 2014. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes due to delays in previous years. Any action required by Executive Committee? No | - The MP part of the project is operationally completed as of December 2014. - Financial completion is underway. |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | ALB | PHA | 36 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-07-01 |  | 2003-12-01 | 2004-12-01 | 40000 | -458 | 39542 | 39541.55 | 100% | 0.45 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | EUR | ALB | PHA | 39 | INV | 10 | A | I | CTC | 2.3 | 2.3 |  |  | 2003-04-01 | 2005-09-01 | 2005-04-01 |  | 2005-12-01 | 2007-09-01 | 45000 | -192 | 44808 | 44807.85 | 100% | 0.15 | 0 |  | 3375 | -14 | 3361 | 0 | 0 | FIN
FIN | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | Multi-Year | EUR | ALB | PHA | 39 | TAS | 05 | A | I | CFC | 6.8 | 6.8 |  |  | 2003-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-12-01 | 2008-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | EUR | ALB | PHA | 39 | TAS | 08 | A | I | MBR | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2005-09-01 | 20000 | -319 | 19681 | 19681.27 | 100% | -0.27 | 0 |  | 1500 | -26 | 1474 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ozone depleting substances phase-out plan: programme management and auditing | Multi-Year | EUR | ALB | PHA | 39 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2005-04-01 | 2009-12-01 |  | 2007-12-01 | 2008-07-01 | 16068 | 0 | 16068 | 16068 | 100% | 0 | 0 |  | 1205 | 0 | 1205 | 0 | 0 | FIN |  |  | 2009-12-01 | NON-INV
FIN | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | EUR | ALB | PHA | 46 | INV | 11 | A | I | CFC | 25 | 25 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-04-01 | 2010-12-01 | 172322 | 0 | 172322 | 172322.01 | 100% | -0.01 | 0 |  | 12924 | 0 | 12924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase out plan (3rd tranche) | Multi-Year | EUR | ALB | PHA | 50 | INV | 14 | A | I | CFC | 21 | 21 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 72322 | 0 | 72322 | 72321.85 | 100% | 0.15 | 0 |  | 5424 | 0 | 5424 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase out plan (fourth and fifth tranches) | Multi-Year | EUR | ALB | PHA | 54 | INV | 15 | A | I | CFC | 13 | 13 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2011-01-01 | 2012-05-01 | 64644 | -17 | 64627 | 64627.39 | 100% | -0.39 | 0 |  | 4848 | -1 | 4847 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | ALB | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 30000 | -74 | 29926 | 29926.15 | 100% | -0.15 | 0 |  | 2250 | -6 | 2244 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | EUR | ALB | PHA | 57 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2011-06-01 | 2012-10-01 | 55000 | -897 | 54103 | 54102.72 | 100% | 0.28 | 0 |  | 4125 | -67 | 4058 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ODS Phase out plan (sixth tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 19 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-05-01 | 2012-12-01 | 22322 | -438 | 21884 | 21883.81 | 100% | 0.19 | 0 |  | 1674 | -33 | 1641 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS Phase out plan (seventh tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 20 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-09-01 | 2013-10-01 | 22322 | -867 | 21455 | 21454.56 | 100% | 0.44 | 0 |  | 1674 | -65 | 1609 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ALB | PHA | 64 | INV | 22 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-03-01 | 2013-07-31 | 2015-03-01 |  |  | 45000 | 0 | 45000 | 43209.39 | 96.02% | 1790.61 | 1000 | 791 | 4050 | 0 | 3889 | 161 | 90 | - Technical specifications of sets of R&R equipment and tools developed in cooperation with counterpart; - Bidding and purchase of equipment was completed; - Training of trainers and service technicians workshops on the use of R&R equipment and good practice in servicing refrigeration appliances was initiated and is taking place as per envisaged schedule. Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2: Training accomplished - Yes Milestone 3: Legislation up-dated initiated - Yes Actions towards next goals: work plan development for the year 2015 and new tranche release submission in 2015 Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislation up-date for certification scheme was initiated but not finalized due to required time for the approval process in the Government. The activity will continue in 2015 and approval process will be finalized in 2016 Any recurring problem? No Any impact on project completion date: Yes Administrative restructuring and change of NOU Officer in Albania caused few months of delay, however, the delay was compensated through revised work plan agreed in December 2014 and active involvement of NOU newly appointed officer first half of 2015. Any action required by Executive Committee? No | - Tranche I implementation was completed in March 2015 Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2: Training accomplished - Yes Milestone 3: Legislation up-dated initiated - Yes Actions towards next goals: Work plan development for the year 2015 and new tranche release submission in 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislation up-date for certification scheme was initiated but not finalized due to required time for the approval process in the Government. The activity will continue in 2015 under tranche II and approval process will be finalized in 2016 Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Administrative restructuring and change of NOU Officer in Albania caused few months of delay, however, the delay was compensated through revised work plan agreed in December 2014 and active involvement of NOU newly appointed officer first half of 2015. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | ALB | PHA | 70 | INV | 25 | A | I | HCFC | 0.4 | 0.4 |  |  | 2013-07-01 |  | 2015-07-31 | 2015-12-30 |  |  | 92000 | 0 | 92000 | 0 | 0% | 92000 | 0 | 30000 | 8280 | 0 | 0 | 8280 | 0 | - Technical specifications of additional sets of R&R equipment and tools coordinated. - Training of trainers and service technicians workshops on the use of R&R equipment and good practice in servicing the refrigeration appliances are being coordinated with the new management of the NOU. - A meeting has been held with the new NOU in November 2014 during the MoP to progress implementation. - Work plan has been agreed upon. Milestone 1: Equipment delivered - Yes Milestone 2: Training accomplished - Yes Milestone 3: Legislation up-dated initiated - Yes Actions towards next goals: Work plan development for the year 2015 and new tranche release submission in 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislation up-date for certification scheme was initiated but not finalized due to required time for the approval process in the Government. The activity will continue in 2015 and approval process will be finalized in 2016. Any impact on project completion date: Yes Administrative restructuring and change of NOU Officer in Albania caused few months of delay, however, the delay was compensated through revised work plan agreed in December 2014 and active involvement of NOU newly appointed officer first half of 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Tranche II implementation was initiated and disbursement reached 35% by June 2015. - Technical specification for additional equipment purchase was developed and delivery will take place second half of 2015. - Verification report in view of tranche II submission will be finalized by September 2015. Milestones achieved: Milestone 1: Equipment specification development - Yes Milestone 2: Specific legislation on certification scheme - No Milestone 3: Equipment delivery - No Activities planned but not implemented, reasons and strategy: New legislation for certification scheme is under development and it is expected to be completed by the end of 2015. Equipment delivery is scheduled for second half of 2015 Actions towards next goals: Progress report for Tranche II submission is under development in view of its consideration by the 75th Meeting of the ExCom. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislation up-date for certification scheme was initiated but not finalized due to required time for the approval process in the Government. The activity will continue in 2015 and approval process will be finalized in 2016. Any recurring problem? No Any impact on project completion date: Yes Yes. Instead of July 2014, the project is planned to be finalized in 2015. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | ALB | PHA | 71 | TAS | 27 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-05-01 | 2015-05-31 | 2015-12-15 |  |  | 30000 | 0 | 30000 | 4761.8 | 15.87% | 25238.2 | 0 | 20000 | 2700 | 0 | 429 | 2271 | 0 | - Selection of an independent local institution to carry out the verification audit is coordinated with the NOU. Milestones achieved: Milestone 1: Development of ToR for conducting the verification report - Yes Milestone 2: Selection of contractor - Yes Actions towards next goals: Verification report to be completed in 2015, including 2014 data that will become available during the 2nd quarter of 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Yes. The project is planned to be finalized in December 2015. The verification report must include 2014 consumption data that were not available in 2014, in view of submission of tranche 3 request, as per ExCom Agreement If yes, implications: (narrative): The verification report was scheduled to include 2014 consumption data, as a consequence, it could not be finalized as of December 2014 as such data become available first quarter of 2015 Any action required by Executive Committee? No | - Verification report was contracted with national consultant and is under development. - The verification report will be finalized for the consideration of the 75th Meeting of the ExCom. Milestones achieved: Milestone 1: Contracting verification report - Yes Milestone 2: Submission of the verification report - No Activities planned but not implemented, reasons and strategy: Activity is initiated and will be completed in September 2015. Actions towards next goals: Verification report to be considered by the 75th Meeting of the ExCom. Was there any delay during the reporting year? Yes Yes. Instead of December 2014, the project is planned to be finalized in December 2015. The verification report has to include 2014 consumption data, as a consequence, it could not be finalized as of December 2014 as such data became available only first quarter of 2015 Any recurring problem? No Any impact on project completion date: Yes If yes, implications: (narrative):NA Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Phasing out of CFCs at Entreprise Nationale des Detergents (ENAD) | Individual | AFR | ALG | ARS | 18 | INV | 12 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 2002-05-01 | 614850 | 0 | 614850 | 614850.15 | 100% | -0.15 | 0 |  | 79931 | -46 | 79885 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | AFR | ALG | ARS | 20 | INV | 15 | A | I | CFC | 22.5 | 22.5 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 82018 | 0 | 82018 | 82018 | 100% | 0 | 0 |  | 10662 | -2 | 10660 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | AFR | ALG | ARS | 20 | INV | 16 | A | I | CFC | 51.4 | 51.4 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2001-12-01 | 164623 | 0 | 164623 | 164623.06 | 100% | -0.06 | 0 |  | 21401 | -13 | 21388 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ets. Wouroud | Individual | AFR | ALG | ARS | 20 | INV | 17 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 187772 | -420 | 187352 | 187352 | 100% | 0 | 0 |  | 24410 | -93 | 24317 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | AFR | ALG | ARS | 20 | INV | 18 | A | I | CFC | 19.2 | 19.2 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  |  | 2002-05-01 | 56790 | -3005 | 53785 | 53785 | 100% | 0 | 0 |  | 7383 | -402 | 6981 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFCs at Ets. COPHYD | Individual | AFR | ALG | ARS | 20 | INV | 19 | A | I | CFC | 15 | 15 |  |  | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1997-07-01 | 1999-08-01 | 53024 | -1291 | 51733 | 51733 | 100% | 0 | 0 |  | 6893 | -178 | 6715 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | AFR | ALG | ARS | 25 | INV | 28 | A | I | CFC | 38.4 | 38.4 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2000-12-01 | 2002-08-01 | 147807 | -316 | 147491 | 147490.52 | 100% | 0.48 | 0 |  | 19215 | -72 | 19143 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | AFR | ALG | ARS | 27 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-11-01 | 2001-09-01 | 15000 | -598 | 14402 | 14402.12 | 100% | -0.12 | 0 |  | 1950 | -81 | 1869 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | AFR | ALG | ARS | 28 | INV | 38 | A | I | CFC | 18.1 | 18.1 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-07-01 | 2002-09-01 | 77145 | -78 | 77067 | 77066.69 | 100% | 0.31 | 0 |  | 10029 | -26 | 10003 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | AFR | ALG | ARS | 28 | INV | 41 | A | I | CFC | 19 | 19 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2002-02-01 | 2003-05-01 | 73691 | -74 | 73617 | 73617 | 100% | 0 | 0 |  | 9580 | -25 | 9555 | 0 | 0 | FIN |  |  | 2002-03-01
CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | AFR | ALG | ARS | 36 | PRP | 52 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO |  |  |  | INV
COM | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-05-31 |  | 2014-12-31 |  | 85000 | 0 | 85000 | 74791.32 | 87.99% | 10208.68 | 4677.34 | 9000 | 6375 | 0 | 5609 | 766 | 351 | - Project document and endorsement letter were submitted for discussion at the 72nd Meeting of the ExCom. Milestones achieved: Milestone 1: Yes - Project approved at 72nd ExCom Meeting Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Difficult coordination between NOU, UNIDO and relevant stakeholders. Any impact on project completion date: Yes If yes, implications: Project submitted to the ExCom later than expected. Any action required by Executive Committee? No |  |  |  | NON-INV
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 72 | DEM | 79 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2016-12-31 | 2017-06-30 |  |  | 375059 | 0 | 375059 | 0 | 0% | 375059 | 0 | 50000 | 26254 | 0 | 0 | 26254 | 0 | Approved at the 72nd Meeting of the ExCom in May 2014 on the understanding that no further funds would be available for Algeria for any ODS disposal projects in future. Activities planned but not implemented, reasons and strategy: Establishment of a working group with representatives of NOU Algeria, Group Lafarge and UNIDO was not possible due to lack of response from the NOU for the nomination of their representative(s). Any ensuing activity could not be undertaken due to the lack of response from the NOU. Actions towards next goals: Continued attempts to have the working group established and operational. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Establishment of a working group with representatives of NOU Algeria, Group Lafarge and UNIDO was not possible due to lack of response from the NOU for the nomination of their representative(s). UNIDO continues its attempts to have the working group established and operational. Any recurring problem? Yes If yes, description of the problem/s: Limited responsiveness from NOU. Any impact on project completion date: Yes If yes, implications: Delay on project implementation and completion. Any action required by Executive Committee? No | - Continued attempts to have the working group established and operational. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Establishment of a working group with representatives of NOU Algeria, Group Lafarge and UNIDO was not possible due to lack of response from the NOU for the nomination of their representative(s). UNIDO continues its attempts to have the working group established and operational. Any recurring problem? Yes If yes, description of the problem/s: Limited responsiveness from NOU. Any impact on project completion date: Yes If yes, implications: Delay on project implementation and completion. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of an investment project for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba-Algeria) | Individual | AFR | ALG | FOA | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -1584 | 23416 | 23416 | 100% | 0 | 0 |  | 3250 | -211 | 3039 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | AFR | ALG | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -4245 | 20755 | 20755 | 100% | 0 | 0 |  | 3250 | -556 | 2694 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | AFR | ALG | FOA | 19 | INV | 13 | A | I | CFC | 82 | 82 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  |  | 2003-03-01 | 434500 | -564 | 433936 | 433936.34 | 100% | -0.34 | 0 |  | 56485 | -163 | 56322 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Beni Mansour | Individual | AFR | ALG | FOA | 19 | INV | 14 | A | I | CFC | 110 | 110 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 1998-12-01 | 2003-03-01 | 496650 | 0 | 496650 | 496649.82 | 100% | 0.18 | 0 |  | 64565 | -78 | 64487 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 21 | A | I | CFC | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1998-06-01 |  |  | 2002-09-01 | 61880 | -55372 | 6508 | 6508.1 | 100% | -0.1 | 0 |  | 8044 | -7199 | 845 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 at Snam flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 22 | A | I | CFC | 32 | 32 |  |  | 1997-05-01 | 1997-11-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 88360 | -408 | 87952 | 87952.11 | 100% | -0.11 | 0 |  | 11487 | -71 | 11416 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 23 | A | I | CFC | 24 | 24 |  |  | 1997-05-01 | 1997-10-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 98770 | -1411 | 97359 | 97359.2 | 100% | -0.2 | 0 |  | 12840 | -203 | 12637 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 23 | INV | 25 | A | I | CFC | 95 | 95 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-10-01 | 2003-07-01 | 553480 | -1430 | 552050 | 552049.87 | 100% | 0.13 | 0 |  | 71952 | -299 | 71653 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Matelas Djurdjura | Individual | AFR | ALG | FOA | 25 | INV | 27 | A | I | CFC | 28 | 28 |  |  | 1998-07-01 | 1998-12-01 | 1999-08-01 |  | 2001-07-01 | 2002-09-01 | 82608 | -753 | 81855 | 81855.45 | 100% | -0.45 | 0 |  | 10739 | -115 | 10624 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Maghreb Mousse | Individual | AFR | ALG | FOA | 26 | INV | 29 | A | I | CFC | 24 | 24 |  |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 2001-07-01 | 2002-09-01 | 96492 | -500 | 95992 | 95992.28 | 100% | -0.28 | 0 |  | 12544 | -85 | 12459 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | AFR | ALG | FOA | 27 | INV | 33 | A | I | CFC | 22 | 22 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2004-03-01 | 120060 | 0 | 120060 | 120059.99 | 100% | 0.01 | 0 |  | 15608 | 0 | 15608 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | AFR | ALG | FOA | 27 | INV | 34 | A | I | CFC | 20 | 20 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2003-07-01 | 110179 | -38 | 110141 | 110140.55 | 100% | 0.45 | 0 |  | 14323 | -27 | 14296 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | AFR | ALG | FOA | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 18000 | -20 | 17980 | 17979.88 | 100% | 0.12 | 0 |  | 2340 | -6 | 2334 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | AFR | ALG | FOA | 28 | INV | 37 | A | I | CFC | 20 | 20 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 97986 | -66 | 97920 | 97919.63 | 100% | 0.37 | 0 |  | 12738 | -29 | 12709 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | AFR | ALG | FOA | 28 | INV | 39 | A | I | CFC | 18 | 18 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 99477 | -104 | 99373 | 99373.32 | 100% | -0.32 | 0 |  | 12932 | -34 | 12898 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | AFR | ALG | FOA | 30 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1 | 19999 | 19998.69 | 100% | 0.31 | 0 |  | 2600 | -4 | 2596 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | ALG | FOA | 59 | PRP | 73 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 40000 | -1724 | 38276 | 38275.82 | 100% | 0.18 | 0 |  | 3000 | -129 | 2871 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor | Multi-Year | AFR | ALG | FOA | 62 | INV | 75 | A | I | HCFC | 2.4 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2016-07-01 |  |  | 215380 | 0 | 215380 | 11369.35 | 5.279% | 204010.65 | 2724.58 | 5000 | 19384 | 0 | 1023 | 18361 | 245 | - No progresses from December 2013. - UNIDO is negotiating with the bidders in order to select the least expensive and technically acceptable offer, considering the available budget, as per UNIDO's regulations. - UNIDO informed the ExCom on the option to proceed with a revised scope of supply. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes (bidding done 2 times and always exceeding the project grant) Milestone 4: Contracts awarded - No Activities planned but not implemented, reasons and strategy: Implementation was stuck because of the lack of project grants. ExCom was informed about that, including the option to proceed with a revised scope of supply (one full line instead of partial conversion of three lines). Actions towards next goals: Waiting for the ExCom feedback on a revised scope of supply (one full line instead of partial conversion of three lines). Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Project grant not enough to cover the actual conversion costs. Any impact on project completion date: Yes If yes, implications: Company was not able to be converted; no impact on country's compliance (as stated by the NOU); need to extend the grant validity. Any action required by Executive Committee? Yes. To endorse the revised scope of supply (one full line instead of partial conversion of three lines). | - ExCom endorsed the revised scope of supply (one full line instead of partial conversion of three lines). UNIDO has contacted the beneficiary and NOU on this regard to allow the action on the conversion. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: No (bidding to be re-initiated) Milestone 4: Contracts awarded - No Actions towards next goals: Pursue the beneficiary to finalize the technical specification for the intervention and initiate the bidding exercise. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ALG | FUM | 22 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1998-06-01 |  | 2000-01-01 | 2000-07-01 | 8000 | -3793 | 4207 | 4207 | 100% | 0 | 0 |  | 1040 | -494 | 546 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | AFR | ALG | FUM | 34 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -11723 | 13277 | 13277.46 | 100% | -0.46 | 0 |  | 3250 | -1524 | 1726 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance to phase out methyl bromide in pulses disinfestations | Individual | AFR | ALG | FUM | 50 | TAS | 65 | A | I | MBR | 1.6 | 1.6 |  |  | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2010-05-01 | 51000 | -1274 | 49726 | 49725.97 | 100% | 0.03 | 0 |  | 4590 | -115 | 4475 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Project preparation in the fumigants sector (high-moisture dates) | Individual | AFR | ALG | FUM | 72 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-05-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 1000 | 2450 | 0 | 0 | 2450 | 0 | - Project approved at the 72nd Meeting of the ExCom in May 2014. - UNIDO contacted the NOU to agree on a plan of action, who informed UNIDO that the Ministry of Agriculture needs to be informed and consulted but the NOU to agree on a cooperation modality. No feedback was received on the details of such a cooperation among institutions in Algeria. - UNIDO expressed its availability to execute the project preparation as soon as positive feedback is received. Activities planned but not implemented, reasons and strategy: No action took place so far. No planning was done because feedback from Ministry of Agriculture is missing. Actions towards next goals: Pursue the NOU to get the agreement with the Ministry of Agriculture. Was there any delay during the reporting year? Yes If yes, reasons and action plan: As above Any recurring problem? Yes If yes, description of the problem/s: Lack of positive response from the NOU. Any impact on project completion date: Yes If yes, implications: Project was not prepared as per common policies (12 months from PRP grant approval). Any action required by Executive Committee? No | - UNIDO contacted the NOU to agree on a plan of action. - NOU informed that the Ministry of Agriculture needs to be informed and consulted but the NOU to agree on a cooperation modality. - No feedback was received on the details of such a cooperation among institutions in Algeria. - UNIDO expressed its availability to execute the project preparation as soon as positive feedback is received. Activities planned but not implemented, reasons and strategy: No action took place so far. No planning was done because feedback from Ministry of Agriculture is missing. Actions towards next goals: Pursue the NOU to get the agreement with the Ministry of Agriculture. Was there any delay during the reporting year? Yes If yes, reasons and action plan: As above Any recurring problem? Yes If yes, description of the problem/s: Lack of positive response from the NOU Any impact on project completion date: Yes If yes, implications: Project was not prepared as per common policies (12 months from PRP grant approval). Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | ALG | PHA | 46 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-04-01 | 2006-03-01 |  | 2008-04-01 | 2008-12-01 | 25000 | -1596 | 23404 | 23404.03 | 100% | -0.03 | 0 |  | 1875 | -120 | 1755 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for an ODS phase-out management plan | Individual | AFR | ALG | PHA | 51 | PRP | 66 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2007-11-01 | 2007-12-01 | 15000 | -882 | 14118 | 14118.22 | 100% | -0.22 | 0 |  | 1125 | -66 | 1059 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | ALG | PHA | 53 | INV | 67 | A | I | CFC TCA | 130.5 | 130.5 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2010-04-01 | 2012-07-01 | 723500 | 0 | 723500 | 723500.02 | 100% | -0.02 | 0 |  | 54263 | 0 | 54263 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | ALG | PHA | 55 | PRP | 68 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 85000 | -255 | 84745 | 84744.79 | 100% | 0.21 | 0 |  | 6375 | -19 | 6356 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan (second tranche) | Multi-Year | AFR | ALG | PHA | 58 | INV | 71 | A | I | CFC CTC TCA | 154 | 154 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2013-12-01 | 2014-07-01 | 198000 | -3610 | 194390 | 194390.17 | 100% | -0.17 | 0 |  | 14850 | -271 | 14579 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | ALG | PHA | 58 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2012-12-01 | 2012-12-01 | 65000 | -22 | 64978 | 64978.26 | 100% | -0.26 | 0 |  | 4875 | -2 | 4873 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | Multi-Year | AFR | ALG | PHA | 66 | INV | 76 | A | I | HCFC | 8.3 | 0 |  |  | 2012-04-01 | 2013-01-01 | 2013-04-30 | 2017-06-01 |  |  | 1379460 | 0 | 1379460 | 13251.33 | 0.9606% | 1366208.67 | 1677.55 | 3000 | 103460 | 0 | 994 | 102466 | 125.8162 | - Since the selected technology is completely new, more time was required for the beneficiary to produce a prototype and to get agreement on the TOR. For that reason UNIDO could not start the bidding. UNIDO was informed by Condor that it was planning a mission to its component suppliers in the second half of April 2014 to discuss in detail the availability of R32 and possibly R290 components in the short and medium term. - Subsequently, in June 2014, UNIDO fielded another mission to Condor to agree on the finalization of the TOR for the conversion and update the implementation plan. While the TOR was updated by UNIDO afterwards, the beneficiary has not cleared the TOR during the reporting period. Milestones achieved: First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: No (Draft ToR prepared, but not yet agreed by the beneficiary); Bids prepared & request: No Contract awarded: No Equipment delivered & installed: No Commissioning & trial runs: No Activities planned but not implemented, reasons and strategy: The delay is due to the introduction of a new technology, which requires extensive preparatory work by the beneficiary, preparation of prototype, negotiation with component suppliers and training of company staff. Actions towards next goals: Undertake a joint mission with the component supplier to agree on the way forward. Was there any delay during the reporting year? Yes If yes, reasons and action plan: See above. Any recurring problem? Yes If yes, description of the problem/s: See above. Any impact on project completion date: Yes If yes, implications: HCFC-22 quota would be required for longer period. Any action required by Executive Committee? No. UNIDO will try to progress during 2015, otherwise there might be a need for change of technology choice. | - As reported to the 74th Meeting of the ExCom, disbursement level was not expected to increase significantly during 2015. Disbursement level is still less than 10%. Revised TOR was sent to the beneficiary's review and comments. UNIDO was informed by Condor in May 2015 that they received a prototype from the component supplier without refrigerant charge. However, it is to be noted that Condor is currently investigating the possibility of R290 as alternative instead of R32. However, since R290 is not available in the country, Condor submitted a request to local authorities in order to import R290, which is a lengthy procedure and the refrigerant might not be available before August 2015. Thus, testing can only be undertaken after August. In the meantime, UNIDO is in contact with Condor to get an agreement on the TOR and to start bidding at the earliest possibility. Since both R32 and R290 are flammable and as designed in the project document, whichever technology is selected, Condor and UNIDO would have to comply with ATEX safety standards. Reasons for low disbursements: Slow progress due to new technology, long lead time required before a decision is taken by the company management on the actual conversion activities. Milestones achieved: First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: No (Draft ToR prepared, but not yet agreed by the beneficiary); Bids prepared & request: No Contract awarded: No Equipment delivered & installed: No Commissioning & trial runs: No Activities planned but not implemented, reasons and strategy: UNIDO planned to agree on the TOR during the reporting period, however, no agreement reached yet due to the long lead time required before a decision is taken by the company management on the actual conversion activities. Together with the component supplier a joint field visit is planned to be organized on the 3rd or 4th quarter 2015. Actions towards next goals: Increase the dialog with the beneficiary and undertake a mission. Was there any delay during the reporting year? Yes If yes, reasons and action plan: See above. Any recurring problem? Yes. If yes, description of the problem/s: The introduction of a new technology requires extensive preparatory work by the beneficiary, preparation of prototype, negotiation with component suppliers and training of company staff. Any impact on project completion date: Yes, the project is delayed. If yes, implications: The company will require HCFC-22 quota for a longer period. In addition, if the disbursement rate does not achieve 20%, the country will face difficulties in getting the next tranche for the servicing sector approved. Any action required by Executive Committee? Yes: The disbursement level of this project should be treated separately from the HPMP, allowing submission of the next funding tranche of the service sector HPMP. |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | Multi-Year | AFR | ALG | PHA | 66 | INV | 77 | A | I | HCFC | 2.8 | 0 |  |  | 2012-04-01 | 2012-10-01 | 2013-04-30 | 2017-03-01 |  |  | 214400 | 0 | 214400 | 22516.34 | 10.5% | 191883.66 | 6970.94 | 15000 | 16080 | 0 | 1689 | 14391 | 522.8205 | - Through the available official channels, UNIDO has officially contacted the NOU on various pending issues related to MP projects with UNIDO. - Activities planned for 2014: agree with the NOU on a plan of action and on the launching ceremony. Purchase equipment for servicing sector and for flushing, conduct training to technicians; start the revision of legislation in order to set-up the necessary policy instruments. Activities planned but not implemented, reasons and strategy: Agreement with NOU on project scope and planning could not be finalized. Actions towards next goals: Liaise with the NOU on a concrete plan of action. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of responsiveness by the NOU. Plan of action is to insist in liaising with the NOU to get a positive feedback on the pending activities. Any recurring problem? Yes If yes, description of the problem/s: Lack of responsiveness from NOU Any impact on project completion date: Yes If yes, implications: NOU confirmed that delay will not impact on country's compliance. Tranche implementation is delayed and original tranche submission was missed. Any action required by Executive Committee? Yes; to urge optimal conditions for implementation to allow progresses in implementation of project activities. | - NOU was contacted to provide feedback on various pending issues from previous years. Activities planned but not implemented, reasons and strategy: Agreement with NOU on project scope and planning could not be finalized. Actions towards next goals: Liaise with the NOU on a concrete plan of action. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Reason is the lack of responsiveness by the NOU. Plan of action is to insist in liaising with the NOU to get a positive feedback on the pending activities. Any recurring problem? Yes If yes, description of the problem/s: Lack of responsiveness from NOU. Any impact on project completion date: Yes If yes, implications: NOU confirmed that delay will not impact on country's compliance. Tranche implementation is delayed and original tranche submission was missed. Any action required by Executive Committee? Yes; to urge optimal conditions for implementation to allow progresses in implementation of project activities |  |  | INV
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electromenager, ENIEM | Individual | AFR | ALG | REF | 15 | INV | 09 | A | I | CFC | 425 | 425 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2002-09-01 | 6589550 | -82919 | 6506631 | 6506630.78 | 100% | 0.22 | 0 |  | 856642 | -12121 | 844521 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for establishment of a National Centre for recovery and recycling CFC-11, CFC-12 and CFC-502 | Individual | AFR | ALG | REF | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1998-11-01 | 1995-06-01 |  | 1999-12-01 | 2001-11-01 | 25000 | -8254 | 16746 | 16746.19 | 100% | -0.19 | 0 |  | 3250 | -1077 | 2173 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Replacement of CFC-12 with HFC 134a for commercial refrigeration at Enapat | Individual | AFR | ALG | REF | 25 | INV | 26 | A | I | CFC | 9.2 | 9.2 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 1998-12-01 | 2000-12-01 | 139932 | -16937 | 122995 | 122995 | 100% | 0 | 0 |  | 18191 | -2227 | 15964 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem | Individual | AFR | ALG | REF | 26 | INV | 30 | A | I | CFC | 12.8 | 12.8 |  |  | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 167332 | -2890 | 164442 | 164441.7 | 100% | 0.3 | 0 |  | 21753 | -409 | 21343 | 1 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | AFR | ALG | REF | 27 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-10-01 | 1999-12-01 |  | 2000-11-01 | 2001-07-01 | 15000 | -11980 | 3020 | 3019.87 | 100% | 0.13 | 0 |  | 1950 | -1558 | 392 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | AFR | ALG | REF | 31 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-06-01 | 2002-01-01 |  | 2003-01-01 | 2003-06-01 | 60000 | -1013 | 58987 | 58987.21 | 100% | -0.21 | 0 |  | 7800 | -144 | 7656 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | Individual | AFR | ALG | REF | 32 | INV | 47 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-07-01 | 2003-05-01 |  | 2003-12-01 | 2004-12-01 | 351768 | -5863 | 345905 | 345904.94 | 100% | 0.06 | 0 |  | 45730 | -834 | 44896 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | AFR | ALG | REF | 36 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-07-01 |  | 2004-12-01 | 2005-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | AFR | ALG | REF | 37 | INV | 56 | A | I | CFC | 18.6 | 18.6 |  |  | 2002-07-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2006-12-01 | 224320 | -22701 | 201619 | 201618.86 | 100% | 0.14 | 0 |  | 29162 | -2952 | 26210 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector (includes: training in good refrigerant management practices, training of customs officers, and national recovery and recycling) | Multi-Year | AFR | ALG | REF | 37 | TAS | 55 | A | I | CFC | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-12-01 |  | 2004-06-01 | 2004-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | -6 | 25994 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): Second tranche | Multi-Year | AFR | ALG | REF | 39 | TAS | 58 | A | I | CFC | 45 | 110 |  |  | 2003-04-01 | 2004-03-01 | 2004-04-01 |  | 2005-06-01 | 2007-05-01 | 700000 | 0 | 700000 | 699999.99 | 100% | 0.01 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector: 2004 programme | Multi-Year | AFR | ALG | REF | 42 | TAS | 59 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2007-11-01 | 2008-12-01 | 524647 | -12543 | 512104 | 512104.16 | 100% | -0.16 | 0 |  | 39349 | -941 | 38408 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures ( refrigeration sector terminal project) | Individual | AFR | ALG | REF | 44 | INV | 62 | A | I | CFC | 72.8 | 72.8 |  |  | 2004-12-01 | 2006-03-01 | 2007-04-01 |  | 2012-12-01 | 2014-07-01 | 589000 | -3630 | 585370 | 585370.14 | 100% | -0.14 | 0 |  | 44175 | -272 | 43903 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-to-air air-conditioning sector) | Individual | AFR | ALG | REF | 59 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 | 2012-12-01 | 60000 | -381 | 59619 | 59619.34 | 100% | -0.34 | 0 |  | 4500 | -29 | 4471 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production at ENIEM | Individual | AFR | ALG | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-08-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -675 | 24325 | 24325 | 100% | 0 | 0 |  | 3250 | -93 | 3157 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the aerosol production and solvent conversion at ENAD | Individual | AFR | ALG | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -5049 | 19951 | 19951 | 100% | 0 | 0 |  | 3250 | -661 | 2589 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in small- and medium-scale industries | Individual | AFR | ALG | SEV | 17 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1996-01-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -1409 | 48591 | 48591 | 100% | 0 | 0 |  | 6500 | -193 | 6307 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project formulation of investment projects in the aerosol, foam and refrigeration sectors | Individual | AFR | ALG | SEV | 21 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-05-01 | 1997-08-01 |  | 1998-02-01 | 2002-09-01 | 50000 | -2690 | 47310 | 47309.6 | 100% | 0.4 | 0 |  | 6500 | -359 | 6140 | 1 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise nationale des Detergents (ENAD-Lames) | Individual | AFR | ALG | SOL | 17 | INV | 10 | A | I | CFC | 5.6 | 5.6 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-06-01 | 2001-03-01 | 109900 | -606 | 109294 | 109294 | 100% | 0 | 0 |  | 14287 | -101 | 14186 | 0 | 0 | FIN
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | ANT | PHA | 73 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2015-11-30 | 2015-11-30 |  |  | 10000 | 0 | 10000 | 2350 | 23.5% | 7650 | 0 | 7650 | 700 | 0 | 165 | 535 | 0 | - The project preparation was approved at the 73rd Meeting of the ExCom in November 2014. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO mission to the country took place in June 2015. - The general strategy for the Second Phase of the HPMP was defined and submitted to the Lead Agency for the preparation of the project document. - Project is planned to be submitted to the 75th Meeting of the ExCom. Milestones achieved: Milestone 1: Technical mission for the project preparation. Yes Milestone 2: Project strategy for investment component. Yes Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the foam production at BANDEX, CELPACK & PRENSIPLANT | Individual | LAC | ARG | FOA | 11 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-12-01 | 1998-08-01 | 35000 | 8990 | 43990 | 43990 | 100% | 0 | 0 |  | 4550 | 1169 | 5719 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Bandex S.A. | Individual | LAC | ARG | FOA | 13 | INV | 09 | A | I | CFC | 214 | 214 |  |  | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1995-11-01 | 1998-08-01 | 517630 | -555 | 517075 | 517075 | 100% | 0 | 0 |  | 67292 | -179 | 67113 | 0 | 0 | FIN
FIN | UNIDO | Phase out of ODS at CELPACK S.A. | Individual | LAC | ARG | FOA | 13 | INV | 10 | A | I | CFC | 135 | 135 |  |  | 1994-07-01 | 1994-12-01 | 1995-07-01 |  | 1995-12-01 | 1998-08-01 | 503094 | 377 | 503471 | 503471 | 100% | 0 | 0 |  | 65402 | 49 | 65451 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | LAC | ARG | FOA | 18 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -492 | 19508 | 19508 | 100% | 0 | 0 |  | 2600 | -68 | 2532 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Mallol Saic | Individual | LAC | ARG | FOA | 20 | INV | 47 | A | I | CFC | 36.5 | 36.5 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2003-12-01 | 2004-03-01 | 299344 | 0 | 299344 | 299343.73 | 100% | 0.27 | 0 |  | 38915 | -53 | 38862 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNIDO | Phasing out of CFC-12 at Multiespuma Saic | Individual | LAC | ARG | FOA | 20 | INV | 49 | A | I | CFC | 60 | 60 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2000-12-01 | 2001-11-01 | 282438 | -11981 | 270457 | 270457.47 | 100% | -0.47 | 0 |  | 36717 | -1613 | 35104 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | ARG | FOA | 27 | PRP | 84 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. | Individual | LAC | ARG | FOA | 28 | INV | 110 | A | I | CFC | 26.8 | 26.8 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2001-06-01 | 2002-11-01 | 111641 | -69 | 111572 | 111571.66 | 100% | 0.34 | 0 |  | 14513 | -32 | 14481 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) | Individual | LAC | ARG | FOA | 29 | INV | 97 | A | I | CFC | 30.4 | 30.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2001-06-01 | 2002-09-01 | 227048 | 0 | 227048 | 227048.01 | 100% | -0.01 | 0 |  | 29516 | -7 | 29509 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios Maximo; Baduco D and D; Bolatti; Hi-Tec Poliuretano Alberto; Najera Jose; Stefanelli Vincer, SRL) | Individual | LAC | ARG | FOA | 32 | INV | 117 | A | I | CFC | 46.1 | 46.1 |  |  | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-06-01 | 2004-09-01 | 329495 | 0 | 329495 | 329495.03 | 100% | -0.03 | 0 |  | 42834 | -36 | 42798 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 118 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2003-10-01 | 2003-12-01 | 35000 | -900 | 34100 | 34099.99 | 100% | 0.01 | 0 |  | 4550 | -124 | 4426 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration Project: Open and closed circuit non-soil cultivation as main alternatives to the use of methyl bromide in tomato, cut flowers and strawberry production | Individual | LAC | ARG | FUM | 23 | DEM | 71 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-06-01 | 2002-09-01 | 481800 | -19112 | 462688 | 462687.69 | 100% | 0.31 | 0 |  | 62634 | -2580 | 60054 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (flowers) | Individual | LAC | ARG | FUM | 27 | PRP | 85 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 40000 | -5622 | 34378 | 34378.04 | 100% | -0.04 | 0 |  | 5200 | -738 | 4462 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (strawberries, tomatoes) | Individual | LAC | ARG | FUM | 27 | PRP | 89 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-14 | 2000-11-09 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | Individual | LAC | ARG | FUM | 30 | INV | 105 | A | I | MBR | 331 | 241 |  |  | 2000-03-01 | 2000-07-01 | 2015-01-01 | 2015-10-01 |  |  | 3183390 | 0 | 3183390 | 3077955.29 | 96.69% | 105434.71 | 103561.92 | 105431.18 | 360173 | 0 | 348575 | 11598 | 11392 | - Involvement of a high level international consultant. - Data was collected and included in a draft report. Was there any delay during the reporting year?: Yes, some delays happened in data collection and compilation, now seems to be solved Any recurring problem?: The delay of the submission of the final report If yes, description of the problem/s: (narrative): Delays in starting the trial, consequently delay in data collection, and compilation. Any impact on project completion date: Completion date has been postponed. Any action required by Executive Committee?: NO project will be completed this year. | - All the activities have been completed. - The project is about to be finalized, waiting for consultant's report.
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | ARG | PHA | 42 | INV | 138 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2008-12-01 | 2012-12-01 | 2740000 | 0 | 2740000 | 2740000.01 | 100% | -0.01 | 0 |  | 205500 | 0 | 205500 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
COM | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | ARG | PHA | 47 | INV | 147 | A | I | CFC | 100 | 100 |  |  | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2013-12-01 |  | 1850000 | 0 | 1850000 | 1712689.18 | 92.58% | 137310.82 | 137272.69 | 100000 | 138750 | 0 | 128452 | 10298 | 10295 |  |  |  |  | INV
ONG | UNIDO | National CFC phase-out plan: 2007 work programme | Multi-Year | LAC | ARG | PHA | 50 | INV | 150 | A | I | CFC | 200 | 200 |  |  | 2006-11-01 | 2007-09-01 | 2007-11-01 | 2015-10-01 |  |  | 1103500 | 0 | 1103500 | 1038335.59 | 94.09% | 65164.41 | 63844.11 | 60000 | 82763 | 0 | 77875 | 4888 | 4788 | - The project is about to be completed. Activities planned but not implemented, reasons and strategy: (narrative): Activities done in relation to the HPMP, as Dec 66/42 (h). The HPMP continues as reported to the 74th Meeting of the ExCom, (second tranche approved). We are reviewing the obligations and expenditures of this project before final completion. | - As per Dec 73/8, project could be extended due to reallocation of funds to HPMP. - Project will be completed after the obligation review. |  |  | INV
ONG | UNIDO | National CFC phase-out plan: 2008 work programme | Multi-Year | LAC | ARG | PHA | 53 | INV | 152 | A | I | CFC | 1509.5 | 1509.5 |  |  | 2007-11-01 | 2008-12-01 | 2009-12-31 | 2015-10-01 |  |  | 1167350 | 0 | 1167350 | 440015.08 | 37.69% | 727334.92 | 678274.28 | 300000 | 87551 | 0 | 33001 | 54550 | 50871 | The project is about to be completed. Activities planned but not implemented, reasons and strategy: (narrative): Activities done in relation to the HPMP, as Dec 66/42 (h). The HPMP continues as reported to the 74th Meeting of the ExCom, (second tranche approved). We are reviewing the obligations and expenditures of this project before final completion. | - As per Dec 73/8, project could be extended due to reallocation of funds to HPMP. - Project will be completed after the obligation review. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 64 | PRP | 165 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-02-01 | 2012-07-01 |  | 2012-04-01 | 2013-04-01 | 43657 | -759 | 42898 | 42898.47 | 100% | -0.47 | 0 |  | 3274 | -57 | 3217 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | ARG | PHA | 66 | INV | 169 | A | I | HCFC | 7.1 | 7.1 |  |  | 2012-04-01 | 2013-05-01 | 2013-04-30 | 2015-12-01 |  |  | 685388 | 0 | 685388 | 444819.13 | 64.9% | 240568.87 | 57142.24 | 105703.65 | 51404 | 0 | 33361 | 18043 | 4285.668 | - Training equipment was delivered and training workshops were organized - Training activities continued in 2014. - Distribution of kits | - In the beginning of 2015 training activities have continued. - The 74th Meeting of the ExCom in May 2015 approved the second tranche. - Budget allocation was prepared for the second tranche. - The first activity was a training in the city of Rosario. |  |  | INV
CLO | UNIDO | Phasing out of CFCs in the manufacturing plant of domestic refrigerators of Radio Victoria Catamarca, S.A. | Individual | LAC | ARG | REF | 22 | INV | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  |  | 2001-07-01 | 599896 | -454313 | 145583 | 145583 | 100% | 0 | 0 |  | 77986 | -59090 | 18896 | 0 | 0 | CLO
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Frare S.A., Buenos Aires | Individual | LAC | ARG | REF | 23 | INV | 64 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-05-01 | 2002-09-01 | 514384 | -2300 | 512084 | 512084.45 | 100% | -0.45 | 0 |  | 66870 | -405 | 66465 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Bambi S.A., Santa Fe | Individual | LAC | ARG | REF | 23 | INV | 67 | A | I | CFC | 30.6 | 30.6 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 515258 | 0 | 515258 | 515257.55 | 100% | 0.45 | 0 |  | 66984 | -24 | 66960 | 0 | 0 | FIN
FIN | UNIDO | Preparation of umbrella project in the commercial refrigeration sector | Individual | LAC | ARG | REF | 36 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-05-01 | 2003-05-01 | 25000 | 0 | 25000 | 25000.04 | 100% | -0.04 | 0 |  | 3250 | -4 | 3246 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | ARG | REF | 36 | PRP | 127 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2004-08-01 |  | 2004-08-01 | 2004-08-01 | 100000 | 0 | 100000 | 99999.54 | 100% | 0.46 | 0 |  | 13000 | -11 | 12989 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing sector) | Individual | LAC | ARG | REF | 57 | PRP | 161 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2010-07-01 | 2012-05-01 | 80000 | -5 | 79995 | 79994.57 | 100% | 0.43 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-22 in the room and unitary airconditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 164 | A | I | HCFC | 53.5 | 53.5 |  |  | 2010-07-01 | 2010-12-01 | 2013-07-31 | 2016-04-01 |  |  | 8435542 | 0 | 8435542 | 7092283.81 | 84.08% | 1343258.19 | 1050188.75 | 500000 | 632666 | 0 | 531921 | 100745 | 78764 | - IOC payment completed. - The consumption of HCFC-22 was completely phased out. - Technical problems with some items supplied by Agramkow were solved. - The last company pending to install the equipment started the civil work at its premises. | - UNIDO followed up with the supplier and the beneficiary company for the installation. - It is expected that the installation will be completed by end of August 2015. |  |  | INV
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | ARG | SEV | 21 | PRP | 52 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 2000-06-02 | 2002-05-01 | 32140 | 0 | 32140 | 32140.49 | 100% | -0.49 | 0 |  | 4178 | 0 | 4178 | 0 | 0 | FIN |  |  | 1999-06-01
CLO | UNIDO | Preparation of country programme update | Individual | LAC | ARG | SEV | 39 | CPG | 134 | A | I |  | 0 | 0 |  |  | 2003-04-01 |  | 2004-10-01 |  |  | 2005-08-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of an investment project in the solvents sector (CFC-113 and TCA) | Individual | LAC | ARG | SOL | 36 | PRP | 125 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 40000 | -1126 | 38874 | 38874 | 100% | 0 | 0 |  | 5200 | -154 | 5046 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Plan for phase-out of ODS in the solvent sector | Individual | LAC | ARG | SOL | 41 | INV | 137 | A | I | CFC CTC TCA | 42 | 54 |  |  | 2003-12-01 | 2004-04-01 | 2009-12-01 |  | 2013-12-01 |  | 635986 | 0 | 635986 | 628916.86 | 98.89% | 7069.14 | 0 | 1 | 47699 | 0 | 47169 | 530 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
FIN | UNIDO | Institutional strengthening (phase I) | Individual | EUR | ARM | SEV | 57 | INS | 05 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 |  | 2010-12-01 | 2012-12-01 | 120000 | -1188 | 118812 | 118811.98 | 100% | 0.02 | 0 |  | 9000 | -89 | 8911 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | ARM | SEV | 62 | INS | 08 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-03-31 |  | 2012-12-01 | 2014-07-01 | 120000 | 0 | 120000 | 120000.34 | 100% | -0.34 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase III: 4/2013-3/2015) | Individual | EUR | ARM | SEV | 68 | INS | 10 | N | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2014-12-31 |  | 2014-12-01 |  | 120000 | 0 | 120000 | 105020.05 | 87.52% | 14979.95 | 6295.99 | 14577 | 8400 | 0 | 7351 | 1049 | 440.7193 | - Ministry of Env. was restructured in December 2013 - January 2014. - In February 2014 UNIDO received confirmation that NOU staff is maintained to ensure continuity for the project implementation. - Contracts for NCs were released for the first half of 2014, work plan for the year 2014 was agreed in March 2014 and implementation was continuous in line with the activities planned (as per project document). Milestones achieved: Milestone 1: NOU staff contracted - Yes Milestone 2: Awareness activities organized - Yes Milestone 3: Terminal report prepared and submitted to 74th ExCom - Yes Actions towards next goals: IS extension request to be submitted to the 74th Meeting of the ExCom Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project was operationally completed and financial completion will be achieved during 2015. Milestones achieved: Milestone 1: Completion of the project - Yes Actions towards next goals: Initiation of IS extension approved as of July 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase IV: 4/2015-3/2017) | Individual | EUR | ARM | SEV | 73 | INS | 14 | N | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2017-03-31 | 2017-03-31 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 40000 | 8400 | 0 | 0 | 8400 | 0 | - Project approved at the 73rd Meeting of the ExCom in November 2014. - PAD created and work plan for the year 2015 agreed with the Government. Milestones achieved: Milestone 1: PAD release - Yes Milestone 2: Review of Work plan for the year 2015 - Yes Actions towards next goals: Work plan for the year 2015 agreed. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Implementation initiated in January 2015. - NOU Staff was contracted. - Awareness activities work plan for the year 2015 completed. Milestones achieved: Milestone 1: NOU consultants contracts for the year 2015 released - Yes Milestone 2: Awareness activities implementation - No Activities planned but not implemented, reasons and strategy: Relevant awareness activities are scheduled in September 2015 (on the occasion of the International Ozone Day) Actions towards next goals: Follow-up on completed activities in 2015 and review of work plan for the year 2016. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Promoting low-global warming potential refrigerants for airconditioning sectors in high-ambient temperature countries in West Asia | Individual | ASP | ASP | REF | 69 | DEM | 57 | A | I |  | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-06-30 | 2015-12-01 |  |  | 365000 | 0 | 365000 | 65307.96 | 17.89% | 299692.04 | 216731.43 | 100000 | 25550 | 0 | 4572 | 20978 | 15171.2001 | - Agreements confirming prototype matrix with OEMs and technology providers signed and sent for countersignature. - Agreement between AHRI and UNIDO signed by both parties. - Sample refrigerant and compressors being shipped to respective OEMs. - Design of prototypes has commenced. - Independent testing facility was selected via international bidding process. Funds are committed to contract with facility. - As payments are tied to completed tests, these have not yet been disbursed. Payments are to be released after completion of every 1/3 tests, proportionally. Milestones achieved: Milestone 1 - Yes - Agreement on prototype matrix, between participating OEMs, technology providers, UNEP and UNIDO. Milestone 2 - Yes - Bids for testing facility prepared and tested. Milestone 3 - Yes - Contract awarded to testing facility Milestone 4 - No - Building of prototypes Milestone 5 - No - Testing of prototypes Activities planned but not implemented, reasons and strategy: The building of prototypes was delayed as the delivery of sample refrigerants and compressors to respective OEMs is taking longer than anticipated, due to special transport requirements for specific refrigerants, customs clearance, etc. Actions towards next goals: Request assistance from respective NOUs/Governments to facilitate clearance of samples. Was there any delay during the reporting year? Yes. If yes, reasons and action plan: Delivery of samples took longer than anticipated. Also building, and duration for shipment of prototypes to testing facility must be taken into account. Testing is therefore delayed. Any recurring problem? No Any impact on project completion date: Yes. Slight delay of 8 months Any action required by Executive Committee? No | - Prototypes are being built and are undergoing preliminary tests at respective OEM testing sites. - Prototypes that have been built and have undergone initial testing have been shipped to the testing facility. - Testing on prototypes commenced in July 2015. Continuous process, until all prototypes have been tested: receiving sample refrigerants, compressors; building of prototypes; shipment of prototypes to testing facility. Milestones achieved: Milestone 1 - Yes - Agreement on prototype matrix, between participating OEMs, technology providers, UNEP and UNIDO Milestone 2 - Yes - Bids for testing facility prepared and tested. Milestone 3 - Yes - Contract awarded to testing facility Milestone 4: Building of prototypes - underway Milestone 5: Testing of prototypes - underway *Milestones 4 and 5 are being executed simultaneously. Actions towards next goals: Ensure testing is conducted according to TOR. Final report being drafted. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delivery of samples took longer than anticipated. Also building, and duration for shipment of prototypes to testing facility must be taken into account. Testing is therefore delayed. Any recurring problem? No Any impact on project completion date: Yes, Slight delay of 8 months Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | BAH | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 45000 | -291 | 44709 | 44708.92 | 100% | 0.08 | 0 |  | 3375 | -22 | 3353 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-22 from the manufacturing of central air conditioning and window air conditioning at Awal Gulf manufacturing company) | Multi-Year | ASP | BAH | PHA | 68 | INV | 27 | A | I | HCFC | 3.7 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2014-12-31 | 2017-07-01 |  |  | 387855 | 0 | 387855 | 5464.86 | 1.409% | 382390.14 | 3865.67 | 20000 | 27150 | 0 | 383 | 26767 | 270.5969 | The list of equipment proposed by UNIDO was review by the beneficiary and discussions were held. - TOR have subsequently been prepared for the procurement of equipment. | - TOR have been prepared for the procurement of equipment but the procurement process has been suspended as UNIDO was contacted by UNDP to explore the possibility of transferring equipment purchased for the SAGA project (being cancelled). - UNIDO see that the Bahraini company could be interested. They have been informed and a review of the equipment is ongoing. Milestones achieved: First mission held: Yes Agreement signed: Yes TOR for equipment completed: Yes Activities planned but not implemented, reasons and strategy: procurement process suspended to explore to explore the opportunity of equipment transfer from the SAGA project Any impact on project completion date: Yes If yes, implications: The conversion can be delayed due to the delay in the test and trials for the selection of the alternative technology |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (reclamation facility) | Multi-Year | ASP | BAH | PHA | 68 | TAS | 26 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2020-12-31 | 2020-12-01 |  |  | 161600 | 0 | 161600 | -0.14 | -8.663e-05% | 161600.14 | -0.33 | 20000 | 11312 | 0 | 0 | 11312 | -0.0231 | - TOR for reclamation center prepared and shared with NOU before issuing a call for proposals. Milestones achieved: Mission undertaken: Yes TOR for the reclamation center completed: Yes Call for bids for the selection the company issued: No Procurement of equipment for the reclamation center: No Activities planned but not implemented, reasons and strategy: Procurement of equipment for the reclamation center was not initiated as the beneficiary was not yet selected through local bidding. UNIDO is encouraging the NOU to issue the call for bids and has provided the text to be published in the newspapers in Bahrain Was there any delay during the reporting year? Yes If yes, reasons and action plan: A change of the Ozone officer occurred in 2014. Local call for bids not issued by NOU. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - A mission has been conducted to support the NOU in the local call for bids process. - Criteria for the selection of the company to host the center have been developed and the call has been published. Milestones achieved: Mission undertaken: Yes TOR for the reclamation center completed: Yes Call for bids for the selection the company issued: Yes Procurement of equipment for the reclamation center: No Activities planned but not implemented, reasons and strategy: Procurement of equipment for the reclamation center was not initiated as the beneficiary was not yet selected through local bidding. To avoid further delay, the procurement of equipment will be initiated in parallel with the selection of the company to host the center instead of doing it after the beneficiary is known as first planned. Actions towards next goals: Initiate procurement of equipment in parallel with the selection of the beneficiary Was there any delay during the reporting year? Yes If yes, reasons and action plan: A change of the Ozone officer occurred in 2014. Local call for bids not issued by NOU before July 2015, hence beneficiary not yet selected. The action plan is to initiate the procurement of equipment in parallel with the selection of the beneficiary Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air conditioning sector) | Individual | ASP | BAH | REF | 60 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 30000 | -254 | 29746 | 29746.36 | 100% | -0.36 | 0 |  | 2250 | -19 | 2231 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | ASP | BAH | SOL | 45 | TAS | 14 | A | I | CTC TCA | 1.7 | 1.7 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2009-05-01 | 60000 | -15868 | 44132 | 44132.17 | 100% | -0.17 | 0 |  | 5400 | -1428 | 3972 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
FIN | UNIDO | Preparation of project for retrofitting in all ice-making systems, icebin compressor systems, blast freezers, cold storage and chiller rooms | Individual | LAC | BAR | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | CFC-recovery, recycling and training in refrigeration | RMP | LAC | BAR | REF | 18 | TAS | 04 | A | I | CFC | 14 | 14 |  |  | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 1997-06-01 | 2000-07-01 | 165170 | -222 | 164948 | 164948 | 100% | 0 | 0 |  | 21472 | -63 | 21409 | 0 | 0 | FIN
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | INV | 24 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-11-01 | 2009-12-31 |  | 2010-11-01 | 2012-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 6840 | 0 | 6840 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | INV | 27 | A | I | CFC | 3.1 | 3.1 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 |  | 2013-12-01 | 2013-12-01 | 53000 | -201 | 52799 | 52799.48 | 100% | -0.48 | 0 |  | 4770 | -18 | 4752 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BDI | PHA | 65 | INV | 29 | A | I | HCFC | 0.4 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2016-11-30 | 2016-11-01 |  |  | 80000 | 0 | 80000 | 65611.49 | 82.01% | 14388.51 | 0 | 1000 | 7200 | 0 | 5905 | 1295 | 0 | - Equipment was distributed and is in use Milestones achieved: Equipment procured, delivered and distributed: Yes Actions towards next goals: Discuss the next tranche with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment was distributed and is in use Milestones achieved: Equipment procured, delivered and distributed: Yes Actions towards next goals: Discuss the second tranche with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | AFR | BDI | SOL | 45 | TAS | 19 | A | I | TCA | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 35000 | -2129 | 32871 | 32870.94 | 100% | 0.06 | 0 |  | 3150 | -192 | 2958 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
CLO | UNIDO | Preparation of investment project for ODS phase-out in a foam producing plant (SIBAO) | Individual | AFR | BEN | FOA | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 |  | 1995-09-01 |  |  | 1998-08-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | INV | 19 | A | I | CFC | 3.9 | 3.9 |  |  | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2009-12-01 | 2011-12-01 | 106000 | -400 | 105600 | 105599.57 | 100% | 0.43 | 0 |  | 9540 | -36 | 9504 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | INV | 23 | A | I | CFC | 4 | 4 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 | 2012-12-01 | 69000 | 0 | 69000 | 68999.81 | 100% | 0.19 | 0 |  | 6210 | 0 | 6210 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BEN | PHA | 63 | INV | 26 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-04-01 | 2013-03-31 |  | 2014-12-01 |  | 100000 | 0 | 100000 | 91704.51 | 91.7% | 8295.49 | 8053.7 | 8000 | 7500 | 0 | 6878 | 622 | 604 | The tranche was operationally completed in December 2014. | The tranche will be financially completed upon clearance of all outstanding obligations. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) UNIDO | Multi-Year | AFR | BEN | PHA | 70 | INV | 27 | A | I | HCFC | 1 | 0 |  |  | 2013-07-01 |  | 2016-07-31 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 17920.8 | 30000 | 3000 | 0 | 0 | 3000 | 1344.06 | - As a follow-up to the meeting held with the NOU in November 2013 on the organization of the training, UNIDO also suggested to replace any tools, which are defect as well as to purchase some A/C demonstration units with R290 technology to raise awareness on the risks and requirements of the installation and operation of flammable alternatives. The NOU discussed the above proposal with the national ozone committee and new minister and confirmed its agreement. UNIDO initiated bidding for the tools and the A/C units and contracts were awarded in December 2014. Milestones achieved: ToR for equipment purchase agreed upon: Yes, June 2014; Bids prepared & requested: Yes, September 2014; Contract awarded: Yes, December 2014; Equipment delivered: No Training of trainers organized: No Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Clearance of goods upon arrival and organization of training, distribution of equipment. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - Equipment has reached Benin early April, but despite the supplier's and UNIDO's advance information to UNDP Cotonou, customs clearance was delayed until after 15 May 2015. Currently, training of trainers is being organized in one of the excellence centers for servicing in Cotonou, after which equipment will be distributed to service technicians. The training will have a special session on the proper installation and servicing of R290 air conditioners. For this purpose, 3 AC units designed for R290 were delivered end June 2015, which will be distributed to the 3 excellence centers in Benin for further training in future. Training was scheduled for 10-14 August, but had to be postponed last-minute due to consultant's unavailability to travel. Milestones achieved: ToR for equipment purchase agreed upon: Yes, June 2014; Bids prepared & requested: Yes, September 2014; Contract awarded: Yes, December 2014; Equipment delivered: Yes, May 2015; Training of trainers organized: No; Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Organization of training activities and distribution of equipment afterwards. Was there any delay during the reporting year? No, except for the 2 months customs clearance of the equipment, which had no impact of the completion date of the tranche. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BEN | REF | 22 | TAS | 04 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 114000 | 0 | 114000 | 114000 | 100% | 0 | 0 |  | 14820 | -13 | 14807 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | INV | 18 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-05-01 | 2013-11-30 | 2015-12-01 |  |  | 105128 | 0 | 105128 | 93103 | 88.56% | 12025 | 0 | 11961 | 9462 | 0 | 8379 | 1083 | 0 | - Remaining funds to be added to the 2nd tranche and used towards some reclamation equipment after further consultation with the NOU. - Left open to enable to use funds together with the 2nd tranche. | - After re-assessment of the needs of the service sector in the country, a training programme was planned for technicians. - Funds from both the 1st tranche and 2nd tranche were earmarked for this programme. - Left open to enable to use funds together with the 2nd tranche. Milestones achieved: Milestone 1: Training and certification for RAC technicians took place June-July 2015 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | BHA | PHA | 71 | INV | 20 | A | I | HCFC | 0.2 | 0 |  |  | 2013-12-01 |  | 2016-12-31 | 2015-12-01 |  |  | 10464 | 0 | 10464 | 0 | 0% | 10464 | 0 | 10189 | 942 | 0 | 0 | 942 | 0 | - Funds to be used towards some reclamation equipment after further consultation with NOU. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Same as 1st tranche above |  |  | INV
CLO | UNIDO | Project preparation in the aerosol sector | Individual | EUR | BHE | ARS | 30 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-04-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | EUR | BHE | FOA | 30 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-08-01 | 2001-04-01 |  | 2002-10-01 | 2003-06-01 | 15000 | -238 | 14762 | 14762.25 | 100% | -0.25 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two investment projects in the flexible foam sector | Individual | EUR | BHE | FOA | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2002-08-01 |  | 2004-01-01 | 2004-04-01 | 15000 | -738 | 14262 | 14262.04 | 100% | -0.04 | 0 |  | 1950 | -99 | 1851 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | Individual | EUR | BHE | FOA | 35 | INV | 08 | A | I | CFC | 21 | 21 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 101950 | -1506 | 100444 | 100444.19 | 100% | -0.19 | 0 |  | 13254 | -196 | 13058 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the rigid foam sector | Individual | EUR | BHE | FOA | 36 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-09-01 | 2003-04-01 |  | 2004-01-01 | 2004-12-01 | 15000 | -417 | 14583 | 14583.12 | 100% | -0.12 | 0 |  | 1950 | -57 | 1893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Individual | EUR | BHE | FOA | 39 | INV | 15 | A | I | CFC | 33 | 33 |  |  | 2003-04-01 | 2004-04-01 | 2004-07-01 |  | 2006-12-01 | 2009-05-01 | 364650 | -15 | 364635 | 364634.54 | 100% | 0.46 | 0 |  | 27349 | -1 | 27348 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam applications) | Individual | EUR | BHE | FOA | 63 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 | 2014-04-01 | 30000 | -355 | 29645 | 29644.89 | 100% | 0.11 | 0 |  | 2250 | -27 | 2223 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling vegetables and flower production sector | Individual | EUR | BHE | FUM | 41 | INV | 17 | A | I | MBR | 11.8 | 11.8 |  |  | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 229000 | -3337 | 225663 | 225662.9 | 100% | 0.1 | 0 |  | 20610 | -300 | 20310 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of halon consumption | Individual | EUR | BHE | HAL | 42 | TAS | 18 | A | I | HAL | 4.1 | 4.1 |  |  | 2004-04-01 | 2004-06-01 | 2006-04-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -403 | 64197 | 64196.77 | 100% | 0.23 | 0 |  | 5814 | -36 | 5778 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | BHE | PHA | 36 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2003-12-01 | 2005-05-01 | 80000 | -1922 | 78078 | 78077.52 | 100% | 0.48 | 0 |  | 10400 | -266 | 10134 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan (first trance) | Multi-Year | EUR | BHE | PHA | 41 | INV | 16 | A | I | CFC TCA | 0 | 27.3 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2006-12-01 | 2009-05-01 | 265300 | -1999 | 263301 | 263301.14 | 100% | -0.14 | 0 |  | 19898 | -150 | 19748 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS Phase-out Plan: second tranche | Multi-Year | EUR | BHE | PHA | 44 | INV | 21 | A | I | CFC TCA | 0 | 31.1 |  |  | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2013-12-01 | 2014-08-01 | 295860 | -8124 | 287736 | 287735.57 | 100% | 0.43 | 0 |  | 22190 | -609 | 21580 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan (third tranche) | Multi-Year | EUR | BHE | PHA | 52 | INV | 22 | A | I | CFC | 121.1 | 121 |  |  | 2007-07-01 | 2008-12-01 | 2008-07-31 |  | 2013-12-01 | 2014-08-01 | 303000 | -15044 | 287956 | 287956.25 | 100% | -0.25 | 0 |  | 22725 | -1128 | 21597 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | BHE | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2012-04-01 | 2013-10-01 | 150000 | -1728 | 148272 | 148272.01 | 100% | -0.01 | 0 |  | 11250 | -130 | 11120 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 66 | INV | 26 | A | I | HCFC | 0.2 | 0 |  |  | 2012-04-01 | 2013-11-01 | 2013-04-30 | 2015-12-16 |  |  | 76070 | 0 | 76070 | 50996.11 | 67.04% | 25073.89 | 11487.6 | 25074 | 5705 | 0 | 3825 | 1880 | 861.57 | - A national consultant has been appointed to review the existing “Ozone Legislation” in Bosnia and Herzegovina and Licensing / Quota System for import / export of ODSs and equipment / goods containing / using ODSs. The consultant also prepared the document "Approval of quota permits for import of HCFC" that was approved by the Ministry and based on its annual quotas for HCFC import in 2014 have been issued. - A consultant will be appointed to prepare Code of Good Practice in Refrigeration, as well as to assist with establishment of the Refrigeration Association. - As explained before, the relatively lower rate of disbursement comes from the strategy for the HPMP implementation since the Government of BiH has selected the foam sector as the first priority. - Now the conversion of the foam sector is coming to completion, hence the implementation of this project will speed up. Milestones achieved: Milestone 1: Review of Ozone legislation and the L&Q system - Yes Milestone 2: Preparation of quota permits for HCFC import - Yes Milestone 3: Preparation of Code of Good Practice in Refrigeration - No Milestone 4: Training programme for custom & maritime officers - Yes Milestone 5: Programme for certification of refrigeration service technicians - Yes Activities planned but not implemented, reasons and strategy: The preparation of the Code of Good Practice had to be delayed due to health problems of the national expert. The work is scheduled for the 2nd half of 2015. Actions towards next goals: The activities under the 2nd tranche will include implementation of the training workshops for customs & maritime officers and implementation of certification for refrigeration service technicians. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delay in preparation of Code of Good Practice in Refrigeration due to health problems of the national expert. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project implementation is ongoing in 2015, targeting completion in December. Milestones achieved: Milestone 1: Request for proposals published - Yes Milestone 2: Contract awarded to selected supplier - Yes Milestone 3: Customs clearance process completed: On-going Milestone 4: Delivery of equipment completed - No Milestone 5: Receipt and commissioning of the equipment - No Activities planned but not implemented, reasons and strategy: None Was there any delay during the reporting year? Yes If yes, reasons and action plan: 1. Commissioning of the equipment at Alternativa was delayed because the supplier and the beneficiary could not reach agreement on the respective scope of work for the installation. This was finally resolved with the assistance of UNIDO foam expert. 2.One of the 6 SMEs (Ordagic D.O.O. Srebrenik) refused to cooperate with the NOU on procurement of the refrigeration equipment and therefore was dropped from the procurement event. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The completion of all activities in the foam sector was delayed by almost one year. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion to cyclopentane in the manufacture of panels at Alternativa, and conversion to methyl formate (foam) and non-HCFCs refrigerant in 6 manufacturers of commercial refrigeration equipment) | Multi-Year | EUR | BHE | PHA | 66 | INV | 27 | A | I | HCFC | 5.1 | 5.1 |  |  | 2012-04-01 | 2013-01-01 | 2013-04-30 | 2015-12-15 |  |  | 555212 | 0 | 555212 | 502347.08 | 90.48% | 52864.92 | 52555.77 | 30000 | 41641 | 0 | 37676 | 3965 | 3941.6827 | - The equipment for Alternativa has been delivered on 21 March 2014. - The foaming equipment for 6 SMEs was delivered on 22 April 2014. - Commissioning of the foaming line at Alternativa was on-going from September to December 2014, commissioning of the foaming equipment at 6 SMEs took place in September 2014. - Training of the 6 SMEs on foaming with methyl formate by UNIDO foam expert was conducted in September 2014. - National consultant was appointed to prepare technical specification for the refrigeration part of the SME project in April-June 2014. - Verification of the 2013 HCFC consumption was conducted by a national consultant in March 2014. - The HPMP Tranche Request was submitted to the 72 ExCom and 2nd tranche received in August 2014. Milestones achieved: Milestone 1: Equipment for Alternatives delivered and commissioned - Yes Milestone 2: Foaming equipment for 6 SMEs delivered and commissioned - Yes Milestone 3: Training on foaming with for 6 SMEs by UNIDO foam expert conducted - Yes Milestone 4: Final commissioning and safety certification of „ALTERNATIVA“ HCFC-conversion project - No Milestone 5: Technical specification for refrigeration equipment for 6 SMEs prepared - Yes Activities planned but not implemented, reasons and strategy: Due to delays in installation and trials for the foaming line at Alternativa, the safety certification had to be delayed and will be implemented in September 2015. Actions towards next goals: Procurement of refrigeration equipment for 5 SMEs covered partially by the balance from the 1st tranche and the 2nd tranche. Was there any delay during the reporting year? Yes If yes, reasons and action plan: 1. Commissioning of the pentane foaming line at Alternativa was delayed since the supplier and the beneficiary could not agree on the scope of work to be done by each of them. Commissioning of one foaming machine was delayed since the machine was damaged by a flooding in BiH in August 2014. Quotation from the supplier for the repair of the damaged part was received and the repair scheduled for 2015. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The last payments for the respective contracts for Alternativa and 6 SMEs withheld until the commissioning issues are fully resolved. Any action required by Executive Committee? No | Safety review and certification by international consultant planned for September 2015. Operational completion planned by December 2015. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 72 | INV | 29 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2016-12-31 | 2017-03-01 |  |  | 128979 | 0 | 128979 | 0 | 0% | 128979 | 0 | 40000 | 9029 | 0 | 0 | 9029 | 0 | - Project approved at the 72nd Meeting of the ExCom in May 2014. - Noted that the Agreement was updated to reflect the change in support costs owing to the new administrative cost regime; that there were indications in the verification report that the country might have had a consumption of 580 ODP kg of HCFCs in 2013 above the maximum allowable consumption limit established in the Agreement; that further work was required to establish the actual consumption of Bosnia and Herzegovina in 2013; and that Bosnia and Herzegovina had undertaken the necessary steps to return to compliance with the Agreement in 2014 and future years. - Approved on the understanding that 10 per cent of the agreed funding for the second tranche was withheld in line with decision 54/34 until the exact consumption in the year 2013 had been established; and that on the basis of the actual 2013 consumption, whether and at what level a penalty would have to be applied, up to the limit of the funds withheld from the second tranche would be considered. Milestones achieved: Milestone 1: Preparation of Technical Specification for refrigeration equipment for 6 SMEs - Yes Milestone 2: Publication of Request for Proposals - No Milestone 3: Contract Award for selected supplier - No Milestone 4: Delivery of equipment to 6 SMEs - No Milestone 5: Training workshops for custom officers and maritime agents - No Activities planned but not implemented, reasons and strategy: Due to delays in preparation of technical specification, the procurement was initiated only early 2015. Actions towards next goals: Procurement on-going Was there any delay during the reporting year? Yes: One of the SMEs (Ordagic D.O.O. from Srebrenik) refused to cooperate with the NOU despite effort by the NOU and national expert. If yes, reasons and action plan: Only 5 SMEs included in procurement of refrigeration equipment. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Procurement of refrigeration equipment for 5 SMEs initiated in February 2015, offers received from 3 qualified suppliers, contracts awarded for supply of equipment to two suppliers (split of the required list for better price) in April 2015. - Customs clearance process initiated in June 2015, delivery expected in July 2015. Milestones achieved: Milestone 1: Publication of Request for Proposals: Yes Milestone 2: Contract Award for selected supplier: Yes Activities planned but not implemented, reasons and strategy: The customs clearance process initiated. Training programmes outlines and training events scheduled for 4th Q 2015 and 1st Q 2016. Actions towards next goals: Delivery of equipment. Training activities for customs officers and maritime agents. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation in the commercial/ domestic refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -8025 | 6975 | 6975.21 | 100% | -0.21 | 0 |  | 1950 | -1045 | 905 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 06 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-04-01 | 15000 | -1613 | 13387 | 13387.29 | 100% | -0.29 | 0 |  | 1950 | -212 | 1738 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | Individual | EUR | BHE | REF | 35 | INV | 09 | A | I | CFC | 29 | 29 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2005-12-01 | 2006-12-01 | 536956 | -795 | 536161 | 536160.65 | 100% | 0.35 | 0 |  | 69065 | -87 | 68978 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerants CFC-12 and R-502 with HFC-134a and R-404A, and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment and cold refrigeration chambers at Soko | Individual | EUR | BHE | REF | 35 | INV | 10 | A | I | CFC | 17.4 | 17.4 |  |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-05-01 | 159707 | -818 | 158889 | 158888.79 | 100% | 0.21 | 0 |  | 20762 | -139 | 20623 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two investment projects in the commercial refrigeration sector | Individual | EUR | BHE | REF | 36 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -3464 | 11536 | 11536.49 | 100% | -0.49 | 0 |  | 1950 | -453 | 1497 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a, CFC-11 with HCFC-141b, and TCA with non-cleaning process in the manufacture of commercial refrigeration equipment, panels, and heat exchangers at three enterprises (Soko Paneli, Soko IPV and Kuca Leda) | Individual | EUR | BHE | REF | 39 | INV | 14 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 2003-04-01 | 2003-11-01 | 2004-07-01 |  | 2005-12-01 | 2007-09-01 | 175283 | -5869 | 169414 | 169413.92 | 100% | 0.08 | 0 |  | 15775 | -528 | 15247 | 0 | 0 | FIN
FIN | UNIDO | Country Programme Preparation | Individual | EUR | BHE | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | -2 | 10398 | 0 | 0 | FIN
FIN | UNIDO | Establishment of an Ozone Unit | Individual | EUR | BHE | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2001-05-01 | 2002-04-01 |  | 2004-12-01 | 2005-12-01 | 110000 | -5291 | 104709 | 104708.57 | 100% | 0.43 | 0 |  | 14300 | -709 | 13591 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Extension of institutional strengthening: phase II | Individual | EUR | BHE | SEV | 43 | INS | 19 | N | I |  | 0 | 0 |  |  | 2004-07-01 | 2008-12-01 | 2006-07-01 |  | 2011-12-01 | 2014-07-01 | 95333 | -1592 | 93741 | 93741.41 | 100% | -0.41 | 0 |  | 7150 | -119 | 7031 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of the institutional strengthening project (phase III: 3/2012-2/2014) | Individual | EUR | BHE | SEV | 65 | INS | 25 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2014-02-28 |  | 2013-12-01 |  | 95333 | 0 | 95333 | 95328.67 | 100% | 4.33 | 0 | 1 | 7150 | 0 | 7150 | 0 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase IV: 3/2014-2/2016) | Individual | EUR | BHE | SEV | 71 | INS | 28 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-02-29 | 2016-02-01 |  |  | 95333 | 0 | 95333 | 44223.1 | 46.39% | 51109.9 | 0.02 | 23770.97 | 6673 | 0 | 3096 | 3577 | 0.0014 | - NOU NCs contracts for the year 2014 were released. - ODSs data collection activities and ODSs data validation for the year 2013 were initiated in January 2014. - Work plan on awareness activities in 2014 was agreed with counterpart. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Brief report: NOU staff has been maintained and NOU experts contracts were extended over 2015 year. Office equipment has been delivered as per the project planning. Awareness activities are scheduled to take place with the occasion of International Ozone Day, 16 September 2015 Milestones achieved: Milestone 1: NOU staff contracts released - Yes Milestone 2: Office equipment delivered - Yes Milestone 3: Awareness activities on the occasion of international ozone day - No Activities planned but not implemented, reasons and strategy: Awareness activities are scheduled to be implemented in September 2015 Actions towards next goals: Follow-up on the activities as per the project document and detailed work plan for the year 2016 Was there any delay during the reporting year?: No Any recurring problem? : No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Workshop to raise awareness on use of methyl bromide in tobacco cultivation | Individual | AFR | BKF | FUM | 34 | TRA | 14 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-01-01 | 2002-08-01 |  | 2002-12-01 | 2003-06-01 | 30000 | -7497 | 22503 | 22503.12 | 100% | -0.12 | 0 |  | 3900 | -979 | 2921 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | INV | 30 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2015-12-01 |  |  | 150000 | 0 | 150000 | 138968.4 | 92.65% | 11031.6 | 796.33 | 5000 | 13500 | 0 | 12507 | 993 | 72 | - Since there were no funds for investment component in the 2nd tranche, the NOU requested the remaining funds to be used to upgrade the capacity of the training center to carry out demonstrations on the safe installation, operation and maintenance of hydrocarbon ACs. Milestones achieved: Milestone 1: No Was there any delay during the reporting year? Yes If yes, reasons and action plan: There were internal problems in the Ministry of Environment. The person known to UNIDO as the Ozone Officer was removed therefore no new activities could be initiated. A new Ozone Officer has since been appointed. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date should be extended to December 2016. Any action required by Executive Committee? No | - A new Ozone Officer has since been appointed. - Activities will continue in the 2nd half of 2015 after the Ozone Officer has reviewed the needs of the service sector. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, expected completion in December 2015. If yes, implications: No implications. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BKF | REF | 22 | TAS | 05 | A | I | CFC | 15.48 | 15.48 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (grain fumigation) | Individual | AFR | BOT | FUM | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: non-soil cultivation techniques, bio-fumigation with solarization, and application of various mixtures of other chemicals in low doses in tomatoes and curcubits | Individual | AFR | BOT | FUM | 25 | DEM | 05 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-11-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 146300 | 0 | 146300 | 146300.01 | 100% | -0.01 | 0 |  | 19019 | 0 | 19019 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in the aerosol sector | Individual | LAC | BRA | ARS | 27 | PRP | 127 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 1999-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of investment projects for elimination of CFCs in the polymer foams manufacturing | Individual | LAC | BRA | FOA | 09 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-09-01 |  | 1996-08-01 | 1999-08-01 | 150000 | -5144 | 144856 | 144856 | 100% | 0 | 0 |  | 19500 | -699 | 18801 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Frisokar Equipamentos Plasticos Ltd. | Individual | LAC | BRA | FOA | 17 | INV | 26 | A | I | CFC | 42 | 42 |  |  | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1997-10-01 | 2000-07-01 | 267948 | -13521 | 254427 | 254427 | 100% | 0 | 0 |  | 34833 | -1810 | 33023 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with cyclopentane at Crios Industrial Ltd. (suppliers of Eletrofrio Company) | Individual | LAC | BRA | FOA | 25 | INV | 103 | A | I | CFC | 46 | 46 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 357270 | 0 | 357270 | 357270.08 | 100% | -0.08 | 0 |  | 46445 | -50 | 46395 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | BRA | FOA | 27 | PRP | 126 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 50000 | -9090 | 40910 | 40909.99 | 100% | 0.01 | 0 |  | 6500 | -1190 | 5310 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polyethylene foams for thermal insulation and food packaging purposes at Epex Co. | Individual | LAC | BRA | FOA | 28 | INV | 141 | A | I |  | 0 | 0 |  |  | 1999-07-01 |  | 2001-08-01 |  |  | 2001-07-01 | 632391 | -632391 | 0 | 0 |  | 0 | 0 |  | 79563 | -79563 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown and HCFC-141b technology at Sector Co. in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | LAC | BRA | FOA | 31 | INV | 186 | A | I | CFC | 17.7 | 17.7 |  |  | 2000-07-01 | 2001-11-01 | 2003-01-01 |  | 2002-12-01 | 2003-02-01 | 130490 | 0 | 130490 | 130489.64 | 100% | 0.36 | 0 |  | 16964 | -7 | 16957 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two projects in the integral skin sector | Individual | LAC | BRA | FOA | 33 | PRP | 204 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-06-01 | 2003-03-01 | 20000 | -615 | 19385 | 19384.52 | 100% | 0.48 | 0 |  | 2600 | -84 | 2516 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for two projects in the rigid foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 206 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-06-01 | 2003-06-01 | 20000 | -130 | 19870 | 19870.32 | 100% | -0.32 | 0 |  | 2600 | -21 | 2579 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Danica Co. | Individual | LAC | BRA | FOA | 34 | INV | 222 | A | I | CFC | 146.6 | 146.6 |  |  | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2004-02-01 | 2004-06-01 | 616625 | 0 | 616625 | 616625.24 | 100% | -0.24 | 0 |  | 77829 | -84 | 77745 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project: three alternatives to the use of methyl bromide: non-soil cultivation, solarization and low-dose chemicals | Individual | LAC | BRA | FUM | 22 | DEM | 73 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2000-05-01 | 2002-09-01 | 393800 | -28111 | 365689 | 365689.05 | 100% | -0.05 | 0 |  | 51194 | -3730 | 47464 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigant/ methyl bromide sector (tobacco) | Individual | LAC | BRA | FUM | 27 | PRP | 165 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -3855 | 46145 | 46145 | 100% | 0 | 0 |  | 6500 | -511 | 5989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out methyl bromide in the entire Tobacco Sector | Individual | LAC | BRA | FUM | 28 | INV | 142 | A | I | MBR | 84.4 | 84.4 |  |  | 1999-07-01 | 2000-06-01 | 2002-08-01 |  | 2001-12-01 | 2002-10-01 | 2344440 | -19971 | 2324469 | 2324468.93 | 100% | 0.07 | 0 |  | 267888 | -2602 | 265286 | 0 | 0 | FIN
FIN | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | Individual | LAC | BRA | FUM | 38 | TAS | 263 | A | I | MBR | 0 | 0 |  |  | 2002-11-01 | 2004-04-01 | 2003-12-01 |  | 2005-09-01 | 2006-09-01 | 40000 | -862 | 39138 | 39137.91 | 100% | 0.09 | 0 |  | 5200 | -112 | 5088 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in methyl bromide (tobacco, flowers, horticulture) | Individual | LAC | BRA | FUM | 44 | PRP | 269 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-11-01 | 40000 | -1133 | 38867 | 38866.6 | 100% | 0.4 | 0 |  | 3000 | -85 | 2915 | 0 | 0 | FIN
FIN | UNIDO | Total phase-out of MB used in tobacco, flowers, ornamentals, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 273 | A | I | MBR | 153.2 | 153.2 |  |  | 2005-07-01 | 2005-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-12-01 | 1450251 | -454 | 1449797 | 1449797.43 | 100% | -0.43 | 0 |  | 108769 | -34 | 108735 | 0 | 0 | FIN |  |  | 2008-12-01 | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | BRA | PHA | 72 | PRP | 302 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-12-31 | 2015-12-01 |  |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 0 | 5000 | 700 | 0 | 0 | 700 | 0 | - The project preparation was approved at the 72nd ExCom Meeting in May 2014. By that time TORs have been prepared and consultants were recruited by end July 2014. The survey was finished in November 2014 and the results were presented to the NOU in December 2014. Milestones achieved: First mission/working arrangements achieved: Yes, June 2014; ToR for HCFC survey completed: Yes, May 2014; Experts recruited: Yes, July 2014; Stakeholders workshop held: Yes, several. HCFC survey completed: Yes, November 2014 All technical input completed: No. Draft document completed: No. Activities planned but not implemented, reasons and strategy: Everything as planned or faster. Actions towards next goals: Preparation of project document. Was there any delay during the reporting year?: No Any recurring problem? No. Any action required by Executive Committee? No. | - Based on the results of the survey, UNIDO prepared a draft strategy for the refrigeration and AC sector, which was presented to the NOU as well as to local stakeholders early February 2015. - After the stakeholder meeting and the inter-agency coordination meeting mid February, UNIDO has finalized all technical inputs and submitted the final draft document to the NOU early March 2015 to allow internal review and finalization of the HPMP. Milestones achieved: First mission/working arrangements achieved: Yes, June 2014; ToR for HCFC survey completed: Yes, May 2014; Experts recruited: Yes, July 2014; Stakeholders workshop held: Yes, several; HCFC survey completed: Yes, November 2014; All technical input completed: March 2015; Draft document completed: March 2015; Activities planned but not implemented, reasons and strategy: Everything as planned or faster. Actions towards next goals: Provide clarifications during internal approval process and update project document as required. Make preparatory activities with project beneficiaries and submission of Stage II HPMP by the lead agency to the 75th ExCom Meeting. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Conversion of the assembly of refrigeration compressors to phase out CFC-12 and CFC/HCFC-502 by using HFC-134a and R-404a at Elgin Maquinas SA | Individual | LAC | BRA | REF | 17 | INV | 20 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-10-01 | 1999-07-01 |  | 1998-12-01 | 2001-07-01 | 460339 | 0 | 460339 | 460339 | 100% | 0 | 0 |  | 59844 | 0 | 59844 | 0 | 0 | FIN
FIN | UNIDO | Formulation of two investment projects in the commercial and domestic refrigerator sector | Individual | LAC | BRA | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-02-01 |  | 1997-12-01 | 1998-08-01 | 50000 | 87 | 50087 | 50087 | 100% | 0 | 0 |  | 6500 | 11 | 6511 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-12 by HFC-134a as refrigerant and CFC-11 by cyclopentane as foam blowing agent in commercial refrigeration equipment for supermarkets at Eletrofrio S/A | Individual | LAC | BRA | REF | 20 | INV | 54 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-07-01 | 1998-10-01 |  | 1999-12-01 | 2001-12-01 | 610650 | 0 | 610650 | 610650.1 | 100% | -0.1 | 0 |  | 79385 | -63 | 79322 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFC-12 by HFC-134a and CFC-11 by cyclopentane in the production of commercial refrigeration equipment at Refrigeracao Rubra | Individual | LAC | BRA | REF | 23 | INV | 83 | A | I | CFC | 21.8 | 0 |  |  | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-10-01 | 320540 | -199780 | 120760 | 120760 | 100% | 0 | 0 |  | 41670 | -25996 | 15674 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the commercial refrigeration sector (Tecpur, Crios, Panamante and others) | Individual | LAC | BRA | REF | 24 | PRP | 97 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 2000-07-01 | 2001-07-01 | 50000 | -2511 | 47489 | 47489 | 100% | 0 | 0 |  | 6500 | -336 | 6164 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with cyclopentane in the production of commercial refrigeration equipment at Panamante Refrigeracao | Individual | LAC | BRA | REF | 25 | INV | 106 | A | I | CFC | 34.3 | 0 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  |  | 2002-09-01 | 377202 | -140248 | 236954 | 236954 | 100% | 0 | 0 |  | 49036 | -18281 | 30755 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the commercial refrigeration sector for four companies | Individual | LAC | BRA | REF | 27 | PRP | 119 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2001-03-01 | 2002-09-01 | 40000 | -8531 | 31469 | 31469.18 | 100% | -0.18 | 0 |  | 5200 | -1116 | 4084 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134A and CFC-11 with HFC-141b at five commercial refrigeration companies (Arparna, Begel, Belliere, Genaredx and Katz Refrigeracao) (umbrella project) | Individual | LAC | BRA | REF | 28 | INV | 139 | A | I | CFC | 26 | 26 |  |  | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 485916 | -115476 | 370440 | 370440.15 | 100% | -0.15 | 0 |  | 63169 | -15088 | 48081 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 30 | PRP | 159 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 25000 | -409 | 24591 | 24590.56 | 100% | 0.44 | 0 |  | 3250 | -58 | 3192 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Ingecold Ltda. | Individual | LAC | BRA | REF | 31 | INV | 170 | A | I | CFC | 1.7 | 1.7 |  |  | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 25320 | -20 | 25300 | 25300.02 | 100% | -0.02 | 0 |  | 3292 | -8 | 3284 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Klima Ltda. | Individual | LAC | BRA | REF | 31 | INV | 171 | A | I | CFC | 5.7 | 5.7 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 86464 | -13509 | 72955 | 72955.26 | 100% | -0.26 | 0 |  | 11240 | -1771 | 9469 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Tecnigel Ltda | Individual | LAC | BRA | REF | 31 | INV | 172 | A | I | CFC | 2.5 | 2.5 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 34000 | -640 | 33360 | 33359.5 | 100% | 0.5 | 0 |  | 4420 | -90 | 4330 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 and R-502 with HFC-134a and HFC-404A as well as of CFC-11 with HCFC-141 at Kalten Ltd. | Individual | LAC | BRA | REF | 31 | INV | 174 | A | I | CFC | 8.1 | 8.1 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2004-04-01 | 2004-09-01 | 122151 | -6158 | 115993 | 115993.1 | 100% | -0.1 | 0 |  | 15880 | -825 | 15055 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Metalplan Ltda. | Individual | LAC | BRA | REF | 31 | INV | 176 | A | I | CFC | 1.9 | 1.9 |  |  | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 28885 | 0 | 28885 | 28885.21 | 100% | -0.21 | 0 |  | 3755 | -3 | 3752 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Domnick Hunter Ltda. | Individual | LAC | BRA | REF | 31 | INV | 177 | A | I | CFC | 1.2 | 1.2 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 17971 | 0 | 17971 | 17971 | 100% | 0 | 0 |  | 2336 | 0 | 2336 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for six projects in the commercial/domestic refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 203 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -1663 | 23337 | 23337.28 | 100% | -0.28 | 0 |  | 3250 | -221 | 3029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Umbrella project for four enterprises converting from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a at EZ Industria, Menoncin, Unifrio and from CFC-12 to HFC-134a at Croydon | Individual | LAC | BRA | REF | 34 | INV | 219 | A | I | CFC | 30.18 | 30.18 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-04-01 | 2004-12-01 | 469452 | -94888 | 374564 | 374564.24 | 100% | -0.24 | 0 |  | 61029 | -12413 | 48616 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the commercial refrigeration sector | Individual | LAC | BRA | REF | 34 | PRP | 223 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2002-08-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -4060 | 20940 | 20940.13 | 100% | -0.13 | 0 |  | 3250 | -532 | 2718 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Umbrella project for two enterprises converting from CFC-11 and HCFC-141b and from CFC-12 to HFC-134a at Argi and Hornburg | Individual | LAC | BRA | REF | 35 | INV | 241 | A | I | CFC | 11.2 | 11.2 |  |  | 2001-12-01 | 2002-11-01 | 2004-05-01 |  | 2004-10-01 | 2005-05-01 | 108050 | -12441 | 95609 | 95608.63 | 100% | 0.37 | 0 |  | 14047 | -1638 | 12409 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning manufacturing sector) | Individual | LAC | BRA | REF | 72 | PRP | 304 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-06-01 | 2015-12-31 | 2015-12-31 |  |  | 150000 | 0 | 150000 | 24761.68 | 16.51% | 125238.32 | 51531.85 | 70000 | 10500 | 0 | 1733 | 8767 | 3607 | - The project preparation was approved at the 72nd ExCom Meeting in May 2014. By that time TORs have been prepared and consultants were recruited by end July 2014. The survey was finished in November 2014 and the results were presented to the NOU in December 2014. Milestones achieved: First mission/working arrangements achieved: Yes, June 2014; ToR for HCFC survey completed: Yes, May 2014; Experts recruited: Yes, July 2014; Stakeholders workshop held: Yes, several. HCFC survey completed: Yes, November 2014 All technical input completed: No. Draft document completed: No. Activities planned but not implemented, reasons and strategy: Everything as planned or faster. Actions towards next goals: Preparation of project document. Was there any delay during the reporting year?: No Any recurring problem? No. Any action required by Executive Committee? No. | - Based on the results of the survey, UNIDO prepared a draft strategy for the refrigeration and AC sector, which was presented to the NOU as well as to local stakeholders early February 2015. - After the stakeholder meeting and the inter-agency coordination meeting mid February, UNIDO has finalized all technical inputs and submitted the final draft document to the NOU early March 2015 to allow internal review and finalization of the HPMP. Milestones achieved: First mission/working arrangements achieved: Yes, June 2014; ToR for HCFC survey completed: Yes, May 2014; Experts recruited: Yes, July 2014; Stakeholders workshop held: Yes, several; HCFC survey completed: Yes, November 2014; All technical input completed: March 2015; Draft document completed: March 2015; Activities planned but not implemented, reasons and strategy: Everything as planned or faster. Actions towards next goals: Provide clarifications during internal approval process and update project document as required. Make preparatory activities with project beneficiaries and submission of Stage II HPMP by the lead agency to the 75th ExCom Meeting. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in a plant (Elgin) consuming 60 metric tons of TCA used as a degreasing agent in the production of compressors | Individual | LAC | BRA | SEV | 17 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-05-01 | 1995-09-01 |  | 1997-10-01 | 1998-08-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | BRA | SEV | 21 | PRP | 63 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-06-01 | 2000-12-01 | 57140 | -718 | 56422 | 56422 | 100% | 0 | 0 |  | 7428 | -105 | 7323 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Conversion of ODS cleaning processes from 1,1,1 TCA to aqueous cleaning and using trichlorethane at Elgin Maquinas SA | Individual | LAC | BRA | SOL | 18 | INV | 39 | A | I | TCA | 6 | 6 |  |  | 1995-11-01 | 1996-12-01 | 1997-02-01 |  | 1997-11-01 | 1999-08-01 | 156567 | -6049 | 150518 | 150518 | 100% | 0 | 0 |  | 20354 | -818 | 19536 | 0 | 0 | FIN
CLO | UNIDO | Phase out of 1,1,1 TCA at Teperman | Individual | LAC | BRA | SOL | 20 | INV | 58 | A | R |  | 0 | 0 |  |  | 1996-10-01 |  | 1998-10-01 |  |  | 2000-06-01 | 152176 | -152176 | 0 | 0 |  | 0 | 0 |  | 19783 | -19783 | 0 | 0 | 0 | CLO
CLO | UNIDO | Elimination of 1,1,1 TCA used for autoparts cleaning at Brosol | Individual | LAC | BRA | SOL | 20 | INV | 59 | A | I |  | 0 | 0 |  |  | 1996-10-01 |  | 1997-10-01 |  |  | 1999-03-01 | 178361 | -178361 | 0 | 0 |  | 0 | 0 |  | 23187 | -23187 | 0 | 0 | 0 | CLO
FIN | UNIDO | Elimination of 1,1,1 TCA used as solvent at Rodabras | Individual | LAC | BRA | SOL | 20 | INV | 60 | A | I | TCA | 4.2 | 4.2 |  |  | 1996-10-01 | 1998-09-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 151577 | -75 | 151502 | 151502 | 100% | 0 | 0 |  | 19705 | -41 | 19664 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used for the formulation of tapping fluids at Tapmatic | Individual | LAC | BRA | SOL | 20 | INV | 61 | A | I | TCA | 9.9 | 9.9 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1997-12-01 | 2001-12-01 | 194500 | -27382 | 167118 | 167117.55 | 100% | 0.45 | 0 |  | 25285 | -3594 | 21691 | 0 | 0 | FIN
CLO | UNIDO | Project preparation for four projects in the solvents (CTC) sector | Individual | LAC | BRA | SOL | 33 | PRP | 205 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  |  | 2003-05-01 | 30000 | -26812 | 3188 | 3188.15 | 100% | -0.15 | 0 |  | 3900 | -3486 | 414 | 0 | 0 | CLO |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CAF | PHA | 64 | INV | 21 | A | I | HCFC | 0.5 | 0 |  |  | 2011-07-01 | 2012-09-01 | 2016-07-31 | 2017-07-01 |  |  | 125000 | 0 | 125000 | 19000.74 | 15.2% | 105999.26 | 87576.93 | 10000 | 9375 | 0 | 1425 | 7950 | 6568 | - The situation in the country was not improved to allow for resuming project implementation. - UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Activities planned but not implemented, reasons and strategy: Delivery of equipment is planned as soon as the situation in the country improves, but the situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. Actions towards next goals: Delivery of equipment is planned as soon as the situation in the country improves. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Any recurring problem? Yes If yes, description of the problem/s: High social and political instability in the country. Any impact on project completion date: Yes If yes, implications: Project implementation and completion delayed indefinitely. Any action required by Executive Committee? No | - The situation in the country was not improved to allow for resuming project implementation. - UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Activities planned but not implemented, reasons and strategy: Delivery of equipment is planned as soon as the situation in the country improves, but the situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. Actions towards next goals: Delivery of equipment is planned as soon as the situation in the country improves. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Any recurring problem? Yes If yes, description of the problem/s: High social and political instability in the country. Any impact on project completion date: Yes If yes, implications: Project implementation and completion delayed indefinitely. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2015-12-01 |  |  | 135000 | 0 | 135000 | 124162.44 | 91.97% | 10837.56 | 5670.19 | 5670 | 10125 | 0 | 9312 | 813 | 425 | - A joint UNIDO-UNEP training that was envisaged did not materialize. - Further needs for equipment were discussed with NOU and subsequently purchased from a local supplier. Milestones achieved: Equipment procured: Yes Actions towards next goals: Discuss the next tranche (due in 2016) with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: There is no delay in the project implementation and the postponing of the completion date is to be able to prepare the submission of the request for the next tranche which is due in 2016. Any action required by Executive Committee? No | - The additional equipment purchased locally was delivered to the N'Djamena reference center and is in use for training purposes. Milestones achieved: Equipment delivered: Yes Actions towards next goals: Discuss the next tranche (due in 2016) with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: (narrative):There is no delay in the project implementation and the postponing of the completion date is to be able to prepare the submission of the request for the next tranche which is due in 2016. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation in the elimination of methyl bromide in soil fumigation | Individual | LAC | CHI | FUM | 57 | PRP | 169 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-05-01 | 2010-03-31 |  | 2010-12-01 | 2011-03-01 | 50000 | -152 | 49848 | 49847.63 | 100% | 0.37 | 0 |  | 3750 | -11 | 3739 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out of methyl bromide - terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | INV | 171 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2014-04-30 |  | 2013-12-01 | 2013-12-01 | 1100000 | 0 | 1100000 | 1100000.41 | 100% | -0.41 | 0.22 |  | 82500 | 0 | 82500 | 0 | 0 | FIN
ONG | UNIDO | National phase-out of methyl bromide, terminal project (second tranche) | Multi-Year | LAC | CHI | FUM | 69 | INV | 178 | A | I | MBR | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-12-31 | 2015-12-01 |  |  | 557917 | 0 | 557917 | 379163.41 | 67.96% | 178753.59 | 63798.22 | 140941.4 | 41844 | 0 | 28437 | 13407 | 4784.8665 | - A study tour for the strawberry farmers was organized in February 2014. - Some workshops for the strawberry sector were organized in March and April 2014. - Information and data were compiled for dissemination and promotion of alternatives in the country. | - In January 2015 a workshop was organized to celebrate the achievement: no more MB in the country - The strawberry component is being finalized. - A manual has been prepared on alternatives of MB used in the production of strawberries. - Two last workshops with the participation of international experts took place in June 2015. - The final activities will be the dissemination of the results at universities, in publications, and through general awareness raising campaign on the success of the project and the production without methyl bromide. |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at Scimpos | Individual | AFR | CMR | FOA | 23 | INV | 10 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-06-01 | 541350 | -491 | 540859 | 540859.12 | 100% | -0.12 | 0 |  | 70376 | -176 | 70200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sonopol | Individual | AFR | CMR | FOA | 23 | INV | 11 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-02-01 | 506310 | 0 | 506310 | 506309.62 | 100% | 0.38 | 0 |  | 65820 | -30 | 65790 | 0 | 0 | FIN
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | AFR | CMR | FUM | 24 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide: non-soil cultivation techniques and application of various mixtures of other chemicals in low doses in tobacco | Individual | AFR | CMR | FUM | 25 | DEM | 16 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 160600 | -1033 | 159567 | 159566.82 | 100% | 0.18 | 0 |  | 20878 | -167 | 20711 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the total phase-out of methyl bromide in all remaining uses | Individual | AFR | CMR | FUM | 50 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -60 | 29940 | 29939.69 | 100% | 0.31 | 0 |  | 2250 | -4 | 2245 | 1 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | CMR | PHA | 49 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-08-01 | 2007-07-01 |  | 2006-11-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (first tranche) | Multi-Year | AFR | CMR | PHA | 50 | INV | 26 | A | I | CFC TCA | 12.7 | 12.7 |  |  | 2006-11-01 | 2007-01-01 | 2008-07-01 |  | 2008-12-01 | 2011-12-01 | 600000 | -486 | 599514 | 599514.01 | 100% | -0.01 | 0 |  | 45000 | -36 | 44964 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (second tranche) | Multi-Year | AFR | CMR | PHA | 54 | INV | 29 | A | I | CFC CTC | 13.9 | 13.9 |  |  | 2008-04-01 | 2009-02-01 | 2009-03-31 |  | 2009-12-01 | 2010-12-01 | 105000 | -1 | 104999 | 104999.08 | 100% | -0.08 | 0 |  | 7875 | 0 | 7875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | CMR | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 85000 | -3079 | 81921 | 81920.91 | 100% | 0.09 | 0 |  | 6375 | -231 | 6144 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (third tranche) | Multi-Year | AFR | CMR | PHA | 58 | INV | 31 | A | I | CFC TCA | 24 | 24 |  |  | 2009-07-01 | 2010-11-01 | 2010-07-31 |  | 2011-12-01 | 2012-12-01 | 95000 | -1572 | 93428 | 93428.21 | 100% | -0.21 | 0 |  | 7125 | -118 | 7007 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | CMR | PHA | 58 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 65000 | -364 | 64636 | 64636.28 | 100% | -0.28 | 0 |  | 4875 | -27 | 4848 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 34 | A | I | HCFC | 15.7 | 15.7 |  |  | 2011-07-01 | 2012-04-01 | 2015-07-31 | 2015-12-15 |  |  | 310900 | 0 | 310900 | 261641 | 84.16% | 49259 | 0 | 40000 | 23318 | 0 | 19623 | 3695 | 0 | - Conversion of foam enterprises was achieved (equipment was delivered and training performed by the supplier on the use of methyl format technology). - Additional training for SMEs in the foam sector was performed, including field demonstration activity. Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2: Training for SMEs - Yes Milestone 3: Conversion to methyl format technology in place - Yes Actions towards next goals: Additional training for SMEs has been scheduled for the remaining project balance to address the SMEs sector in 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The delivery of equipment and training was delayed 6 months due to stakeholders availability for participating in the training programme. Any recurring problem? No Any impact on project completion date: Yes. If yes, implications: Completion date is delayed against original forecast due to training activities for SMES that required longer time period for organization than initially planned and due to additional training required. Any action required by Executive Committee? No | - Additional training on the use of Methyl Formate is scheduled to take place in August 2015. - For additional equipment (spare-parts) local bidding was organized and the contract will be finalized in August 2015. - Additional equipment (spare-parts) will be delivered to ensure proper use of the delivered portable foaming machines. - Foam component implementation to be finalized during current year. Milestones achieved: Milestone 1: National consultant contracting for additional training - Yes Milestone 2: Additional equipment delivered - No Actions towards next goals: Operational completion by end of 2015 and financial completion first quarter 2016. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date is delayed against original forecast due to training activities for SMES that required longer time period for organization than initially planned and due to additional training required. Training has been scheduled to take place 1st week of August 2015, and additional spare parts delivery will be achieved last quarter of 2015 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 35 | A | I | HCFC | 6.4 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2015-07-31 | 2015-12-01 |  |  | 573553 | 0 | 573553 | 505944.37 | 88.21% | 67608.63 | 7983.22 | 20000 | 43016 | 0 | 37946 | 5070 | 599 | - Technicians training workshops as a follow up of train the trainer component were initiated in the last quarter of 2013 and continued during 2014. - Quota system implementation in 2014 took into account the revised ExCom agreement upon approval of the second tranche of HPMP. - Customs officers training programme (concept development and workshop in 2014) under planning process. Milestones achieved: Milestone 1: Contract with counterpart for training activities achieved - Yes Milestone 2: Customs training achieved - Yes Actions towards next goals: Terms of Reference for equipment delivery to be elaborated based on the service workshop needs and as a follow up of the training activities organized Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - ToR for equipment purchase for servicing sector agreed with counterpart upon training activities outcome. - Bidding for contract with supplier for equipment purchase ongoing. - Equipment delivery scheduled second half of 2015. Milestones achieved: Milestone 1: Equipment purchase contract release - No Milestone 2: Equipment delivery - No Activities planned but not implemented, reasons and strategy: Purchase contract to be summarized by August 2015; Equipment delivery scheduled last quarter 2015. Actions towards next goals: Preparation of the progress report for the tranche 3 submission for the consideration of the 75th Meeting of the ExCom. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Submission of the tranche 3 request to the 74th Meeting of the ExCom was rescheduled for the 75th Meeting, as ODS consumption data for the year 2014, subject to Verification Report, were not yet available in the first quarter of 2015. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No Instead of July 2015, the project is planned to be finalized in December 2015. Training activities organization was rescheduled in 2015. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, second tranche) | Multi-Year | AFR | CMR | PHA | 71 | INV | 38 | A | I | HCFC | 2 | 0 |  |  | 2013-12-01 | 2014-11-01 | 2015-12-31 | 2017-03-01 |  |  | 180000 | 0 | 180000 | 8531.33 | 4.74% | 171468.67 | -8661.62 | 30000 | 13500 | 0 | 640 | 12860 | -649.6215 | - Work plan for stage II covering 2014 - 2015 was agreed with counterpart in July 2014. - Technical specification development for recovery/recycling network and equipment delivery was developed. Milestones achieved: Milestone 1: Work plan for the implementation of Tranche II - additional training activities - Yes Milestone 2: ToR for equipment purchase - Yes Actions towards next goals: Early data collection activities in view of elaboration of Consumption Verification Report for the year 2014 initiated. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Development of ToR for continuing the training activities in servicing sector has been agreed with counterpart. - Contract to be released during the 3rd quarter of 2015 and additional training workshops to take place in the second half of 2015. - Verification report in view of the 3rd tranche submission was contracted as of July 2015. Milestones achieved: Milestone 1: ToR for additional training in servicing sector - Yes Milestone 2: Training activities in servicing sector - No Milestone 3: Verification report for the consumption data for the years 2013 - 2014 - No Activities planned but not implemented, reasons and strategy: Training activities are planned for the second half of 2015, upon contract signature. Verification Report for ODS consumption data to be finalized in September 2015. Actions towards next goals: Preparation of the progress report for the tranche 3 submission for the consideration of the 75th Meeting of the ExCom. Was there any delay during the reporting year? Yes, new planned completion date is March 2017. If yes, reasons and action plan: Submission of the tranche 3 request to the 74th Meeting of the ExCom was rescheduled for the 75th Meeting as ODS consumption data for the year 2014, subject to Verification Report, were not yet available in the first quarter of 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of an investment project proposal for phase out of CFCs at FAEM, Cameroun | Individual | AFR | CMR | REF | 11 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-04-01 | 1994-11-01 |  | 1995-02-01 | 1998-08-01 | 20000 | -2046 | 17954 | 17954 | 100% | 0 | 0 |  | 2600 | -270 | 2330 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC at FAEM.SA | Individual | AFR | CMR | REF | 13 | INV | 05 | A | I | CFC | 62 | 62 |  |  | 1994-07-01 | 1995-11-01 | 1996-01-01 |  | 1996-06-01 | 2000-04-01 | 1935860 | -42791 | 1893069 | 1893069 | 100% | 0 | 0 |  | 251662 | -5953 | 245709 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project for phasing out CFC-11 in the manufacture of domestic refrigerators, freezers and air-conditioners at Union Camerounaise | Individual | AFR | CMR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Union Camerounaise d'Entreprise | Individual | AFR | CMR | REF | 18 | INV | 07 | A | I | CFC | 115.1 | 115.1 |  |  | 1995-11-01 | 1996-12-01 | 1997-03-01 |  | 2001-12-01 | 2002-12-01 | 1321400 | -20877 | 1300523 | 1300522.5 | 100% | 0.5 | 0 |  | 171782 | -2982 | 168800 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | AFR | CMR | REF | 24 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1999-02-01 | 1999-04-01 |  | 2001-04-01 | 2001-11-01 | 30000 | -65 | 29935 | 29934.63 | 100% | 0.37 | 0 |  | 3900 | -15 | 3885 | 0 | 0 | FIN |  |  | 1999-05-01
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration servicing sector (includes: training in good refrigerant management practices, training of customs officers, and recovery and recycling programme) | Individual | AFR | CMR | REF | 38 | TAS | 18 | A | I | CFC | 218.4 | 218.4 |  |  | 2002-11-01 | 2003-03-01 | 2007-12-01 |  | 2007-06-01 | 2008-05-01 | 522982 | 0 | 522982 | 522982.01 | 100% | -0.01 | 0 |  | 67528 | 0 | 67528 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the refrigeration sector | Individual | AFR | CMR | REF | 43 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2005-03-01 | 2005-07-01 |  | 2006-06-01 | 2006-12-01 | 25000 | -174 | 24826 | 24826.38 | 100% | -0.38 | 0 |  | 1875 | -13 | 1862 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Project formulation of investment projects in the foam and refrigeration sectors | Individual | AFR | CMR | SEV | 21 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  |  | 2001-07-01 | 50000 | -23644 | 26356 | 26356.43 | 100% | -0.43 | 0 |  | 6500 | -3079 | 3421 | 0 | 0 | CLO
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | LAC | COL | FUM | 21 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-08-01 |  | 1998-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in banana growing at Cenibanano | Individual | LAC | COL | FUM | 26 | DEM | 32 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2002-12-01 | 2003-06-01 | 123200 | -377 | 122823 | 122823.29 | 100% | -0.29 | 0 |  | 16016 | -74 | 15942 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in the methyl bromide sector | Individual | LAC | COL | FUM | 55 | TAS | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2010-07-01 |  | 2009-12-01 | 2011-05-01 | 40000 | -620 | 39380 | 39380.46 | 100% | -0.46 | 0 |  | 3600 | -56 | 3544 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a MDI sector plan | Individual | ASP | CPR | ARS | 44 | PRP | 422 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-07-01 | 2009-05-01 | 90000 | -377 | 89623 | 89623.21 | 100% | -0.21 | 0 |  | 6750 | -28 | 6722 | 0 | 0 | FIN
ONG | UNIDO | Sector plan for phase-out of CFCs consumption in MDI sector | Individual | ASP | CPR | ARS | 56 | INV | 473 | A | I | CFC | 322.5 | 0 |  |  | 2008-11-01 | 2009-10-01 | 2013-12-31 | 2015-12-01 |  |  | 13500000 | 0 | 13500000 | 12105539.96 | 89.67% | 1394460.04 | 1075400.78 | 1072000 | 1012500 | 0 | 907915 | 104585 | 80655 | - The work plan was modified in 2014 and approved by UNIDO in June 2014. - In September and October, UNIDO approved the TOR of site supervision of MDI manufactures for CFC consumption in 2012 and 2013 and TOR for patent analysis of non-CFC MDI. - A bidding process following UNIDO’s general procurement procedure was completed in June 2014, and a contractor was selected for both bids. - Workshops to discuss NOMINATION OF THE AEROSOL METERED-DOSE INHALER (MDI) AS AN ESSENTIAL USE FOR 2015 were held. Milestones achieved: Milestone 1: Yes - ODS Phase-out contracts signed by 30 June 2014 with all enterprises to be covered under the project Milestone 2: Yes - Reported annual CFCs consumption in 2013 is below the approved essential use exemption Milestone 3: Yes - Verified CFC consumption in 2012 is below the approved essential use exemption granted for the year Milestone 4: Yes - ODS licensing system is operational and effective Milestone 5: Yes - Public awareness is continue Actions towards next goals: (-) To conduct the TA activity--Sites supervision of MDI manufactures for CFC consumption in 2012 and 2013; (-) To complete the TA activity “Quality comparison research of HFA-134a for domestic and foreign MDI application”; (-) To complete and maintain the monitoring information system (MIS) including Project management system and CFC licensing system; (-) To complete the non-CFC MDI patent analysis; (-) To draft CFC alternative technical standards; (-) To continue the public awareness TA activities. Was there any delay during the reporting year? No Any recurring problem? N Any impact on project completion date: No Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Yes - TOR on Public Awareness of CFCs Phase-out Plan in China's MDI sector finalized and Call for Bids on-going Milestone 2: Yes - TOR on Site Supervision on CFCs Consumption in 2014 and 2015 finalized and Call for Bids on-going Actions towards next goals: Finalize bidding processes and award respective contracts. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  | 2015-12-01 | INV
FIN | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 59 | PRP | 494 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2011-05-31 |  | 2012-12-01 | 2012-12-01 | 85000 | -407 | 84593 | 84592.8 | 100% | 0.2 | 0 |  | 6375 | -31 | 6344 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-06-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 100% | 0 | 0 |  | 85952 | 0 | 85952 | 0 | 0 | - In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EPBs, it was decided that part of the funding will be allocated to the EPBs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. - In April 2014, FECO organized a meeting with relevant provincial EPBs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. Milestones achieved: Milestone 1: Yes - Preparation of a revised Implementation Plan Milestone 2: Yes - Contracts signed with 5 participating EPBs Milestone 2: Yes - 1st batch of 800 kg. of CFC-12 destroyed Actions towards next goals: (-) EPBs to submit Progress Report and province-specific Implementation Plans; (-) Visits to provinces to check progress in implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delays in signature of contracts between FECO and local EPBs (solved). Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs by end of August 2015; (-) Meeting of local EPBs, FECO and UNIDO scheduled in September 2015. Was there any delay during the reporting year? No, but to ensure successful completion of the project, completion date was revised to June 2017. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of investment projects (50 companies) in the foam sector (polysterene/polyethylene) | Individual | ASP | CPR | FOA | 24 | PRP | 240 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 100000 | -2311 | 97689 | 97689 | 100% | 0 | 0 |  | 13000 | -321 | 12679 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 25 enterprises (umbrella project) | Individual | ASP | CPR | FOA | 25 | INV | 248 | A | I | CFC | 1146 | 1146 |  |  | 1998-07-01 | 1998-12-01 | 2000-01-01 |  | 2000-12-01 | 2002-09-01 | 4488516 | 0 | 4488516 | 4488515.76 | 100% | 0.24 | 0 |  | 583507 | -341 | 583166 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | ASP | CPR | FOA | 27 | PRP | 283 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2001-05-01 | 2002-09-01 | 50000 | -615 | 49385 | 49384.98 | 100% | 0.02 | 0 |  | 6500 | -90 | 6410 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 27 enterprises (Umbrella Project) | Individual | ASP | CPR | FOA | 28 | INV | 301 | A | I | CFC | 825.7 | 825.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 5289441 | 0 | 5289441 | 5289440.76 | 100% | 0.24 | 0 |  | 591839 | -187 | 591652 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNIDO | Elimination of CFC-11 in manufacturing of PU rigid foam for insulation at 31 enterprises | Individual | ASP | CPR | FOA | 29 | INV | 306 | A | I | CFC | 707.3 | 707.3 |  |  | 1999-11-01 | 2000-04-01 | 2002-06-01 |  | 2003-01-01 | 2004-04-01 | 5516900 | 0 | 5516900 | 5516900.42 | 100% | -0.42 | 0 |  | 616859 | -430 | 616429 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the polystyrene/ polyethylene foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 337 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2840 | 47160 | 47160.44 | 100% | -0.44 | 0 |  | 6500 | -379 | 6121 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 338 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2627 | 47373 | 47372.77 | 100% | 0.23 | 0 |  | 6500 | -351 | 6149 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | Individual | ASP | CPR | FOA | 32 | INV | 369 | A | I | CFC | 891.4 | 891.4 |  |  | 2000-12-01 | 2001-07-01 | 2003-07-01 |  | 2004-12-01 | 2006-09-01 | 3295600 | 2025174 | 5320774 | 5320774.18 | 100% | -0.18 | 0 |  | 372516 | 232769 | 605285 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for two umbrella projects in the polystyrene/polyethylene foam sector | Individual | ASP | CPR | FOA | 33 | PRP | 371 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-10-01 |  | 2002-12-01 | 2003-12-01 | 100000 | -2686 | 97314 | 97314.17 | 100% | -0.17 | 0 |  | 13000 | -369 | 12631 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian) | Individual | ASP | CPR | FOA | 34 | INV | 375 | A | I | CFC | 191.6 | 191.6 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-07-01 | 2005-12-01 | 1087764 | -80453 | 1007311 | 1007310.63 | 100% | 0.37 | 0 |  | 129654 | -9025 | 120628 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | Individual | ASP | CPR | FOA | 34 | INV | 376 | A | I | CFC | 750 | 750 |  |  | 2001-07-01 | 2002-02-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 2808338 | 0 | 2808338 | 2808337.9 | 100% | 0.1 | 0 |  | 318917 | 0 | 318917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | One-off Phase Out | ASP | CPR | FOA | 35 | INV | 379 | A | I | CFC | 359 | 359 |  |  | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 2450123 | -2605 | 2447518 | 2447518.19 | 100% | -0.19 | 0 |  | 279514 | -287 | 279227 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal umbrella project for the elimination of CFC-12 in manufacturing of EPE foam packaging nets at 30 enterprises | One-off Phase Out | ASP | CPR | FOA | 36 | INV | 387 | A | I | CFC | 849.3 | 849.3 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-12-01 | 2010-04-01 | 1525648 | 2800061 | 4325709 | 4325709 | 100% | 0 | 0 |  | 171352 | 314476 | 485828 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for technology demonstration project for hydrocarbon blowing agent in the extruded polystyrene (XPS) foam sector | Individual | ASP | CPR | FOA | 60 | PRP | 496 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-08-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000.01 | 100% | -0.01 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | CPR | FOA | 73 | PRP | 546 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-06-01 | 2016-06-30 |  |  | 260000 | 0 | 260000 | 0 | 0% | 260000 | 0 | 80000 | 18200 | 0 | 0 | 18200 | 0 | Project approved at the 73rd Meeting of the ExCom in November 2014. | - Preparation of Stage II HPMP in the XPS foam sector progresses as planned. - A contract has been signed between FECO and UNIDO for implementation of the project preparation, and the data collection exercise has begun. - Partial results were discussed during the coordination meeting of the preparation of Stage II HPMP held in Beijing, China (3-4 July 2015). Milestones achieved: Milestone 1: Yes - Contract signed between FECO and UNIDO for implementation of the PRP. Milestone 2: Yes - Questionnaires distributed among a representative sample of companies, with a feedback ratio of about 70% so far. Milestone 3: Yes - 37 enterprises selected for field survey. Milestone 4: Yes - Coordination meeting of the preparation of Stage II HPMP held in Beijing, China (3-4 July 2015). Actions towards next goals: (-) Completion of data collection and site visits; (-) Data analysis; (-) Document preparation; (-) Stakeholder consultations; (-) Project document finalization. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Demonstration project on alternatives to the use of methyl bromide in soil fumigation | Individual | ASP | CPR | FUM | 22 | DEM | 201 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-08-01 | 443300 | -13942 | 429358 | 429358.46 | 100% | -0.46 | 0 |  | 57629 | -1901 | 55728 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral strategy in the methyl bromide sector | Individual | ASP | CPR | FUM | 36 | PRP | 386 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-05-01 |  | 2003-12-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out of methyl bromide (first tranche) | Multi-Year | ASP | CPR | FUM | 41 | INV | 407 | A | I | MBR | 364 | 364 |  |  | 2003-12-01 | 2004-04-01 | 2007-03-01 |  | 2007-12-01 | 2008-09-01 | 4086600 | -1 | 4086599 | 4086599.43 | 100% | -0.43 | 0 |  | 306495 | 0 | 306495 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a methyl bromide consumption phase-out plan | Individual | ASP | CPR | FUM | 43 | PRP | 412 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2004-12-01 | 2005-05-01 | 20000 | -44 | 19956 | 19956.38 | 100% | -0.38 | 0 |  | 1500 | -6 | 1494 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a production phase-out plan in the fumigants sector (methyl bromide) | Individual | ASP | CPR | FUM | 45 | PRP | 430 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-12-01 | 2006-02-01 | 40000 | -31 | 39969 | 39969.44 | 100% | -0.44 | 0 |  | 3000 | -7 | 2993 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | ASP | CPR | FUM | 52 | INV | 451 | A | I | MBR | 65.2 | 65.2 |  |  | 2007-07-01 | 2008-02-01 | 2008-07-31 |  | 2008-09-01 | 2008-09-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, third tranche) | Multi-Year | ASP | CPR | FUM | 55 | INV | 462 | A | I | MBR | 124.6 | 124.6 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2010-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, fourth tranche) | Multi-Year | ASP | CPR | FUM | 58 | INV | 489 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2010-12-01 | 1300000 | 0 | 1300000 | 1300000 | 100% | 0 | 0 |  | 97500 | 0 | 97500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, fifth tranche) | Multi-Year | ASP | CPR | FUM | 61 | INV | 501 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2011-12-01 | 2012-12-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | National phase-out of methyl bromide (phase II, sixth tranche) | Multi-Year | ASP | CPR | FUM | 64 | INV | 509 | A | I | MBR | 26 | 33 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 |  | 2013-12-01 |  | 500000 | 0 | 500000 | 499997.51 | 100% | 2.49 | 0.17 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
COM | UNIDO | National phase-out of methyl bromide (phase II, seventh tranche) | Multi-Year | ASP | CPR | FUM | 67 | INV | 522 | A | I | MBR | 50 | 76 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 |  | 2013-12-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
COM | UNIDO | National phase-out of methyl bromide (phase II, eighth tranche) | Multi-Year | ASP | CPR | FUM | 71 | INV | 538 | A | I |  | 0 | 50 |  |  | 2013-12-01 | 2014-08-01 | 2014-12-31 |  | 2014-12-01 |  | 500000 | 0 | 500000 | 325000 | 65% | 175000 | 175000 | 100000 | 37500 | 0 | 24375 | 13125 | 13125 | The project activities were successfully completed by the end of 2014 following the below activities: '- Commercial and large scale distribution of newly designed PIC injection equipment and Dazomet application equipment, '- Commercial application of IMP protocol, '- Training and awareness of new crop management and IMP protocol, '- Systematic data collection and evaluation. | The project activities were successfully completed by the end of 2014. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, ninth tranche) | Multi-Year | ASP | CPR | FUM | 72 | INV | 542 | A | I | MBR | 50 | 50 |  |  | 2014-05-01 |  | 2015-12-31 | 2015-12-01 |  |  | 302742 | 0 | 302742 | 0 | 0% | 302742 | 302742 | 200000 | 22706 | 0 | 0 | 22706 | 22706 | The Government of China, the Government of Italy and UNIDO were requested to submit the project completion report to the Executive Committee to the first meeting in 2016. | Project implementation according to the time schedule. 8 model farms are set up in the ginger and yam sector for large scale commercial application of MB alternatives, including the use of new application equipment (for Dazomet and for chloropicrin). Continuous monitoring of MB alternatives applications in all sectors and the compilation of final report for all sectors are ongoing. |  |  | INV
FIN | UNIDO | Substituting halon in fire fighting equipment at Nanjing | Individual | ASP | CPR | HAL | 09 | PRP | 194 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-04-01 | 1996-03-01 |  | 1995-03-01 | 1998-08-01 | 36000 | -6926 | 29074 | 29074 | 100% | 0 | 0 |  | 4680 | -906 | 3774 | 0 | 0 | FIN
FIN | UNIDO | Conversion from halon 1211 to ABC dry powder and foam water spray at Nanjing Fire Fighting Equipment Factory | Individual | ASP | CPR | HAL | 15 | INV | 104 | A | I | HAL | 1110 | 1480 |  |  | 1994-12-01 | 1995-10-01 | 1996-12-01 |  | 1996-12-01 | 2000-12-01 | 496000 | 0 | 496000 | 496000 | 100% | 0 | 0 |  | 64480 | -53 | 64427 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in tobacco expansion in China | Individual | ASP | CPR | OTH | 09 | TAS | 193 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-05-01 | 1998-08-01 | 72000 | 4499 | 76499 | 76499 | 100% | 0 | 0 |  | 9360 | 585 | 9945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Formulation of investment projects in the tobacco sector | Individual | ASP | CPR | OTH | 18 | PRP | 144 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1996-11-01 |  | 1999-12-01 | 2002-06-01 | 50000 | -1233 | 48767 | 48766.94 | 100% | 0.06 | 0 |  | 6500 | -170 | 6330 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a sectoral strategy in the tobacco sector | Individual | ASP | CPR | OTH | 24 | PRP | 237 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-11-01 | 2001-07-01 | 200000 | -8020 | 191980 | 191979.71 | 100% | 0.29 | 0 |  | 26000 | -1082 | 24918 | 0 | 0 | FIN |  |  | 1999-10-01
FIN | UNIDO | 2001 Annual work programme of the tobacco sector plan | Multi-Year | ASP | CPR | OTH | 32 | INV | 366 | A | I | CFC | 90 | 90 |  |  | 2000-12-01 | 2001-06-01 | 2001-12-01 |  | 2001-12-01 | 2004-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2002 workplan | Multi-Year | ASP | CPR | OTH | 36 | INV | 388 | A | I | CFC | 120 | 200 |  |  | 2002-03-01 | 2002-08-01 | 2003-03-01 |  | 2002-12-01 | 2003-07-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan: 2003 annual work programme | Multi-Year | ASP | CPR | OTH | 39 | INV | 400 | A | I | CFC | 180 | 180 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2003-12-01 | 2005-09-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | FIN
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2004 workplan | Multi-Year | ASP | CPR | OTH | 42 | INV | 409 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2005 | Multi-Year | ASP | CPR | OTH | 45 | INV | 427 | A | I | CFC | 200 | 200 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-03-01 | 1700000 | 0 | 1700000 | 1700000 | 100% | 0 | 0 |  | 127500 | 0 | 127500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2006-2007 | Multi-Year | ASP | CPR | OTH | 48 | INV | 442 | A | I | CFC | 300 | 300 |  |  | 2006-04-01 | 2007-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-05-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (XPS foam sector) | Individual | ASP | CPR | PHA | 55 | PRP | 466 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-10-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 84000 | 0 | 84000 | 84000.02 | 100% | -0.02 | 0 |  | 6300 | 0 | 6300 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (Room air-conditioning sector) | Individual | ASP | CPR | PHA | 55 | PRP | 470 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 500000 | -2 | 499998 | 499997.65 | 100% | 0.35 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 513 | A | X |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2015-12-01 |  |  | 36430000 | 0 | 36430000 | 32786916.75 | 90% | 3643083.25 | 3643000 | 1000000 | 2732250 | 0 | 2459019 | 273231 | 273225 | - Under this tranche 8 lines are planned to be converted to R290, 7 lines to R410A and 1 compressor line to R290. - Conversion to R410A of six production lines was completed in 2014. - Bidding was completed for all R290 conversions under the tranche and main equipment have been delivered for 4 lines by the end of 2014. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Partially Yes (for 4 R290 lines) Conversion completed: 6 lines converted to R410A TUV certification and national acceptance completed: Yes, for 3 companies. Activities planned but not implemented, reasons and strategy: One company withdrew its application to convert to R410A. No issues, since phase-out is covered by the other enterprises. Actions towards next goals: Implement remaining milestones at beneficiary companies: complete conversions, TUV certification etc. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Some production lines had to be moved to other location due to safety requirements. Any recurring problem? No Any impact on project completion date: Tranche is expected to be completed by end 2015. Any action required by Executive Committee? No | - Conversion to R290 at 3 enterprises' production lines (Gree Zhuhai, Changhong Mianyang) was completed so far in 2015. - Conversion at 3 companies (Midea Foshan, TCL Zhongshan, Haier Chongqing) partially completed. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes, partially (for six R290 lines) Conversion completed: Yes partially (3 R290 lines and 6 R410A lines) TUV certification and national acceptance completed: Yes partially Actions towards next goals: Complete conversions at all companies. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: December 2015. Any action required by Executive Committee? No |  |  | INV | 11423055
ONG | UNIDO | Sector plan for phase-out of HCFCs in the extruded polystyrene foam sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 514 | A | X |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2015-12-15 |  |  | 21372000 | 0 | 21372000 | 19234716.79 | 90% | 2137283.21 | 2137200 | 100000 | 1602900 | 0 | 1442604 | 160296 | 160290 | - By November 2013, the 12 beneficiaries linked to Tranche 1 have all signed the performance-based sub-contracts with FECO. The total value of the 12 sub-contracts is 19,724,880 US dollars, which will result in 3929.96 metric tonnes of HCFCs to be eliminated. In accordance with the sub-contracts, the beneficiaries initiated works upon signature of the contracts, and the duration of the conversion is 24 months. In the course of the sub-contract implementation, beneficiaries are obliged to strictly follow the detailed implementation plans approved by FECO/MEP. - In order to improve the effectiveness and efficiency of equipment commission to be conducted by beneficiaries and to facilitate the verification of equipment delivery, ISA, jointly with FECO/MEP, organized a workshop in Shanghai on April 21 2014, with the intent of providing the beneficiaries with guidance and technical assistance on the aspects of verification procedure and equipment commission. Representatives from FECO/MEP, ISA and beneficiaries attended this workshop. At the meeting, FECO/MEP introduced the procedure of verification of equipment delivery, and ISA highlighted the key points as well as the technical concerns to which beneficiaries need attach attention when they conduct the equipment commissions by themselves. - By mid-August 2014, 9 beneficiaries, out of 12 charged by Tranche 1, have already finished their equipment procurement and signed the contracts with suppliers. Among the 9 companies, there are 5 companies having received all the equipment purchased. - In March 2014, FECO/MEP, with the joint participation of UNIDO, GIZ, the international expert and the selected accounting firm, conducted the verifications of equipment delivery to 2 companies. - In May 2014, FECO/MEP, with ISA and the accounting firm conducted the same verification on a third company. Milestones achieved: Milestone 1: Yes - Workshop to provide beneficiaries with guidance and technical assistance on the aspects of verification procedure and equipment commission Milestone 2: Yes - Equipment procurement finalized by 9 beneficiaries Milestone 3: Yes - Equipment received by 5 beneficiaries Milestone 4: Yes - Verification of equipment delivery at 3 companies Actions towards next goals: (-) Complete equipment delivery at beneficiaries (-) Conduct verification of equipment delivery Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - 3 remaining beneficiaries under Tranche 1 have already finished their equipment procurement and signed the contracts with suppliers. Milestones achieved: Milestone 1: Yes - Equipment procurement finalized by 3 remaining beneficiaries Actions towards next goals: (-) Finalize conversion of all companies under Tranche I Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 8786176
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 68 | INV | 524 | A | X | HCFC | 176 | 0 |  |  | 2012-12-01 | 2013-10-01 | 2013-12-31 | 2015-12-01 |  |  | 9200000 | 0 | 9200000 | 4600000 | 50% | 4600000 | 3680000 | 1000000 | 644000 | 0 | 322000 | 322000 | 257600 | - Under this tranche 1 R290 line, 1 R410A line and 2 R290 compressor conversions are planned. - Contracts with all companies have been signed and equipment have been delivered for all companies. - With the exception of 1 compressor line, all conversions have been completed by end 2014. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes (3 companies), No (1 company) TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Technical verification of completed lines and initiation of TUV certification and national acceptance. Was there any delay during the reporting year? No major delays. 3 companies were converted and the last one is also close to completion. The only slight delay is with the national acceptance, which needs to be coordinated with many other ongoing activities. Any recurring problem? No Any action required by Executive Committee? No | - Technical verification of the converted lines was done in June 2015. - Conversion of the remaining compressor line is expected to be completed by end 2015. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes (3 companies), No (1 company) TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Completion of R290 compressor line and initiation of technical verification and national acceptance. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No |  |  | INV | 2881428
ONG | UNIDO | Sector plan for phase-out of HCFCs in the extruded polystyrene foam sector (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 69 | INV | 529 | A | X | HCFC | 0 | 0 |  |  | 2013-04-01 | 2013-10-01 | 2014-04-30 | 2016-04-16 |  |  | 10217000 | 0 | 10217000 | 9195300 | 90% | 1021700 | 0 | 200000 | 715190 | 0 | 643671 | 71519 | 0 | - A total of 6 beneficiaries were included in the scope of supply of tranche 2, signing contract on November 2014. - No conversion was finalized in 2014 but 9 procurement contracts were signed for 9 beneficiaries in 2014. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Complete the conversion at 6 beneficiaries and monitor project progresses. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Validity of grant needs to be extended to allow finalization of conversion at beneficiaries' facilities. Details were reported in the tranche submission. Any action required by Executive Committee? No | - Supplier has been identified for all 6 beneficiaries. - 3 received the equipment and 3 beneficiaries completed the installation. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Complete the conversion at 6 beneficiaries and monitor project progresses. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 2762856
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 533 | A | X | HCFC | 47.8 | 0 |  |  | 2013-12-01 | 2014-09-01 | 2016-06-01 | 2017-06-01 |  |  | 3998000 | 0 | 3998000 | 1199400 | 30% | 2798600 | 799600 | 390000 | 279860 | 0 | 83958 | 195902 | 55972 | - During UNIDO's mission to China (March 2014), UNIDO and the Foreign Economic Cooperation Office of the Ministry of Environmental Protection of the Government of China (FECO/MEP) discussed the Implementation Plan for the 3rd Tranche of the XPS sector in the country. - After this, UNIDO approved the proposal submitted by FECO/MEP. - Upon the evaluation of the project implementation plan and the findings of the procurement capacity assessment conducted in 2013, one company was selected as the beneficiary of conversion project charged by Tranche 3. The performance-based sub-contract was signed between FECO/MEP and the company with the contract value of 3,769,060 US dollars, which will result in 1,059.53 metric tonnes of HCFCs to be phased out. Milestones achieved: Milestone 1: Yes - Procurement Plan submitted by the beneficiary Actions towards next goals: (-) Equipment procurement to be finalized by the selected beneficiary (-) Equipment to be received by the selected beneficiary (-) Verification of equipment delivery at the selected beneficiary Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Beneficiary to be converted under this Tranche has received the equipment Milestones achieved: Milestone 1: Yes - Equipment received by beneficiary Actions towards next goals: (-) Completion of trial runs; (-) National acceptance of equipment. Was there any delay during the reporting year?: No, but completion of all conversion activities might require more time and thus, completion date is extended to June 2017. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 812859
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 536 | A | X | HCFC | 49.1 | 0 |  |  | 2013-12-01 | 2014-09-01 | 2016-06-01 | 2017-06-01 |  |  | 8495000 | 0 | 8495000 | 2530200 | 29.78% | 5964800 | 1693966.83 | 1000000 | 594650 | 0 | 177114 | 417536 | 118577.6781 | - Under this tranche 4 lines will be converted to R290. - Work plan has been agreed upon for R290 RAC production lines conversion for all beneficiaries. - A UNIDO mission was undertaken in April 2014 to verify the production lines. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes for 3 lines Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: To deliver equipment and start conversions. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Some production lines had to be moved to another location due to safety requirements. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Progress was made, equipment was delivered for the conversion of 3 lines and bidding has been completed for the remaining 1 line for which contract signature is expected by September. - During inspection it was found that two companies do not meet safety requirements of the local Administration of Work Safety and thus, the buildings with the R290 tanks have to be adjusted. - Additional inspections will be carried out by the local government in September 2015. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes for 3 lines Equipment delivered and converted: Yes, main equipment delivered for 3 lines TUV certification issued: No Actions towards next goals: Sign procurement contracts for 1 line and start conversion at the other lines. Was there any delay during the reporting year? Only slight delays due to location of the new equipment due to safety requirements. The project extension is due to the fact that longer time is required for the complete conversion. If yes, reasons and action plan: As above. Any recurring problem? No. |  |  | INV | 1811644
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 547 | A | X | HCFC | 75 | 0 |  |  | 2014-11-01 |  | 2017-12-31 | 2017-12-31 |  |  | 6330000 | 0 | 6330000 | 0 | 0% | 6330000 | 0 | 1900000 | 443100 | 0 | 0 | 443100 | 0 | - The Treasurer was requested to offset future transfers to UNIDO by US$43,782 representing additional interest accrued by the Government of China in 2012 and interest accrued up to 31 December 2013 from funds previously transferred for the implementation of the XPS foam sector plan for China in line with decision 69/24. - Project approved at the 73rd Meeting of the Excom in November 2014. - Two companies were included in the scope of the tranche. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Complete the conversion at 2 beneficiaries and monitor project progresses. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - 2 beneficiaries signed agreement on the scope of supply and initiated conversion activities. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Complete the conversion at 2 beneficiaries. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 548 | A | X | HCFC | 44 | 0 |  |  | 2014-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 9625000 | 0 | 9625000 | 0 | 0% | 9625000 | 0 | 1000 | 673750 | 0 | 0 | 673750 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014 and subsequently the PAD was issued and the Government was informed about the approval. - The Treasurer was requested to offset future transfers to UNIDO by US$67,293 representing additional interest accrued by the Government of China in 2012 and interest accrued up to 31 December 2013 from funds previously transferred for the implementation of the RAC sector plan for China in line with decision 69/24. UNIDO took relevant actions to recover the interest. Milestones achieved: First mission undertaken/working arrangements agreed: No. TOR completed/bidding organized: No. Contract for equipment signed: No. Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: Undertake first mission, agree on working arrangements and tranche work plan. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Working arrangements were agreed upon early 2015 and first mission was undertaken in February 2015. The current tranche will support China for the conversion of 4 lines to R290. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: No. Contract for equipment signed: No. Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: Sign contracts with beneficiaries and initiate bidding. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Currently we estimate tranche completion at the end of 2017. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Sector plan for methyl bromide production sector (first tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 436 | A | I | MBR | 0 | 0 | 231 | 231 | 2005-11-01 | 2006-06-01 | 2008-12-01 | 2015-12-31 |  |  | 3000000 | 0 | 3000000 | 2975906.39 | 99.2% | 24093.61 | 23303.7 | 22000 | 225000 | 0 | 223193 | 1807 | 1748 | The project was reinstated by the ExCom to ONGOING in 2013 since there has been an going contract on technical assistance for which the final payment is scheduled in December 2015. | - Pending payment to be completed. - Project to be closed by the end of 2015. |  |  | INV
COM | UNIDO | Sector plan for methyl bromide production sector (second tranche) | Multi-Year | ASP | CPR | PRO | 56 | INV | 475 | A | I |  | 0 | 0 | 214 | 214 | 2008-11-01 | 2009-02-01 | 2011-11-30 |  | 2013-03-01 |  | 3000000 | 0 | 3000000 | 2356830.23 | 78.56% | 643169.77 | 642054.67 | 500000 | 225000 | 0 | 176762 | 48238 | 48154 |  |  |  |  | INV
COM | UNIDO | Sector plan for methyl bromide production sector (third tranche) | Multi-Year | ASP | CPR | PRO | 64 | INV | 510 | A | I | MBR | 0 | 0 | 126 | 126 | 2011-07-01 | 2013-04-01 | 2014-07-31 |  | 2014-12-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | The project was successfully completed by the end of 2014 following the below activities: - 'Carry out independent audit and formulate report for the period 2011-2013 and - Request the disbursement of the IV and last tranche for the period 2014 - 2015, - Fourth tranche approved at the 73 ExCom Nov 2014 | The project was successfully completed by the end of 2014. |  |  | INV
ONG | UNIDO | Sector plan for methyl bromide production sector (fourth tranche) | Multi-Year | ASP | CPR | PRO | 73 | INV | 552 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2018-12-31 | 2018-12-01 |  |  | 1790000 | 0 | 1790000 | 0 | 0% | 1790000 | 0 | 300000 | 134000 | 0 | 0 | 134000 | 0 | Approved on the understanding that the Government of China would continue to use existing balances to undertake activities for the phase-out of MB production, and that all project activities will be completed no later than 31 December 2018. The Government of China and UNIDO was requested to submit annual reports on the status of implementation the sector plan for the phase-out of MB production and the project completion report to the Executive Committee no later than the first meeting in 2019. | Contract issued to FECO for the implementation of the tranche IV, contracts for three MB producers signed, subcontract for provision of technical assistance services under preparation. |  |  | INV
FIN | UNIDO | Elimination of ODS used in the production of compressors for household refrigerators at Jiaxipera Compressor Co. Ltd. | Individual | ASP | CPR | REF | 09 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-06-01 | 1996-03-01 |  | 1994-12-01 | 1998-08-01 | 36000 | 4294 | 40294 | 40294 | 100% | 0 | 0 |  | 4680 | 558 | 5238 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 15 | PRP | 105 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-04-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 25000 | -8988 | 16012 | 16012 | 100% | 0 | 0 |  | 3250 | -1172 | 2078 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 by hydrocarbon isobutane and cyclopentane at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 17 | INV | 119 | A | I | CFC | 360 | 360 |  |  | 1995-07-01 | 1996-03-01 | 1997-07-01 |  | 2003-12-01 | 2004-12-01 | 2790320 | 0 | 2790320 | 2790320.21 | 100% | -0.21 | 0 |  | 362742 | -1 | 362741 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Workshop on domestic and commercial refrigerator compressor conversion | Individual | ASP | CPR | REF | 17 | TRA | 133 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1998-08-01 | 40000 | 237 | 40237 | 40237 | 100% | 0 | 0 |  | 5200 | 31 | 5231 | 0 | 0 | FIN
FIN | UNIDO | Conversion of compressor production for domestic refrigerators from CFC-12 to hydrocarbon refrigerant at Jiaxipera compressor factory | Individual | ASP | CPR | REF | 18 | INV | 145 | A | I | CFC | 96 | 96 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 1490000 | 0 | 1490000 | 1490000.07 | 100% | -0.07 | 0 |  | 193700 | 0 | 193700 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at Hangzhou Huari Refrigerator Co. | Individual | ASP | CPR | REF | 18 | INV | 147 | A | I | CFC | 338 | 338 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 2827911 | -13884 | 2814027 | 2814027.14 | 100% | -0.14 | 0 |  | 367628 | -2384 | 365244 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Formulation of investment projects in the refrigeration sector with particular attention to domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 18 | PRP | 151 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-10-01 | 2000-07-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Phasing out ODS at the X'ian Yuan Dong Compressor Co., Xi'an | Individual | ASP | CPR | REF | 19 | INV | 164 | A | I |  | 0 | 0 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1999-06-01 | 2000-12-01 | 1599000 | -5860 | 1593140 | 1593140 | 100% | 0 | 0 |  | 207870 | -1090 | 206780 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Phasing out ODS at the compressor factory of the Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | REF | 19 | INV | 165 | A | I | CFC | 60 | 60 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1998-12-01 | 2002-05-01 | 899030 | 0 | 899030 | 899030.28 | 100% | -0.28 | 0 |  | 116874 | -33 | 116841 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Aucma Electric Appliances Group Co. | Individual | ASP | CPR | REF | 20 | INV | 173 | A | I | CFC | 708 | 708 |  |  | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 1998-12-01 | 2002-07-01 | 2914904 | 0 | 2914904 | 2914904.08 | 100% | -0.08 | 0 |  | 378938 | -192 | 378746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Household Refrigerator Compressor Factory of the Guangzhou Wanbao Compressor Group | Individual | ASP | CPR | REF | 20 | INV | 185 | A | I | CFC | 3 | 3 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 1999-10-01 | 2002-09-01 | 2250000 | 0 | 2250000 | 2250000.13 | 100% | -0.13 | 0 |  | 292500 | -35 | 292465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigeration plant of Hefei Meiling | Individual | ASP | CPR | REF | 22 | INV | 196 | A | I | CFC | 849 | 849 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1998-12-01 | 2002-09-01 | 3247877 | -44594 | 3203283 | 3203282.91 | 100% | 0.09 | 0 |  | 422224 | -6457 | 415767 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Hualing refrigerator plant | Individual | ASP | CPR | REF | 22 | INV | 204 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-04-01 | 879788 | -207466 | 672322 | 672322 | 100% | 0 | 0 |  | 114372 | -27109 | 87263 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group | Individual | ASP | CPR | REF | 22 | INV | 207 | A | I | CFC | 423 | 423 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 2394178 | -10688 | 2383490 | 2383489.52 | 100% | 0.48 | 0 |  | 311243 | -1880 | 309362 | 1 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Zel Tianjin Compressor Co., Ltd. | Individual | ASP | CPR | REF | 22 | INV | 211 | A | I | CFC | 30 | 30 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 1999-07-01 | 962175 | 0 | 962175 | 962175 | 100% | 0 | 0 |  | 125083 | 0 | 125083 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Yuhuan Compressor Factory in Kanmen Town in Yuhuan County, South East China | Individual | ASP | CPR | REF | 23 | INV | 219 | A | I | CFC | 116 | 116 |  |  | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1465155 | -9186 | 1455969 | 1455969.4 | 100% | -0.4 | 0 |  | 190470 | -1494 | 188976 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zhejiang Rongsheng Electric Co. Ltd., Zhejiang, Deqing Country | Individual | ASP | CPR | REF | 23 | INV | 220 | A | I | CFC | 177.8 | 177.8 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1053910 | -67809 | 986101 | 986101.04 | 100% | -0.04 | 0 |  | 137008 | -9018 | 127990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Changshu Refrigerating Equipment Works (Baixue), Changsu | Individual | ASP | CPR | REF | 23 | INV | 221 | A | I | CFC | 425.7 | 425.7 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 3548775 | -521956 | 3026819 | 3026819.15 | 100% | -0.15 | 0 |  | 461341 | -68478 | 392863 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | Individual | ASP | CPR | REF | 23 | INV | 222 | A | I | CFC | 132 | 132 |  |  | 1997-11-01 | 1998-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 1469029 | -1564 | 1467465 | 1467464.62 | 100% | 0.38 | 0 |  | 190974 | -4672 | 186302 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the freezer plant of Xing Xing Electric Appliances Industrial Co. | Individual | ASP | CPR | REF | 23 | INV | 223 | A | I | CFC | 348 | 348 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2002-04-01 | 3346941 | -334438 | 3012503 | 3012503.12 | 100% | -0.12 | 0 |  | 435102 | -44097 | 391005 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Hefei Hualing Electronic Co., Ltd. | Individual | ASP | CPR | REF | 25 | INV | 253 | A | I | CFC | 82.8 | 82.8 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 785984 | -8264 | 777720 | 777719.64 | 100% | 0.36 | 0 |  | 102178 | -1235 | 100943 | 0 | 0 | FIN
CLO | UNIDO | Conversion from CFC-12 to isobutane technologies and products at the compressor factory of the Hangli Refrigeration Ltd., in Hangzhou, China | Individual | ASP | CPR | REF | 26 | INV | 256 | A | I | CFC | 0 | 0 |  |  | 1998-11-01 | 1999-11-01 | 2001-12-01 |  |  | 2003-12-01 | 861000 | -180793 | 680207 | 680207 | 100% | 0 | 0 |  | 104710 | -20006 | 84704 | 0 | 0 | CLO
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b foam blowing agent and CFC-12 with HFC-134a in the manufacture of domestic refrigerators/ freezers at the Beijing Freezing Equipment Factory. | Individual | ASP | CPR | REF | 26 | INV | 259 | A | I | CFC | 35.3 | 35.3 |  |  | 1998-11-01 | 1999-09-01 | 2000-12-01 |  | 2000-12-01 | 2002-09-01 | 280901 | -8254 | 272647 | 272647.45 | 100% | -0.45 | 0 |  | 36517 | -1129 | 35388 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Moganshan Electric Appliances Co. | Individual | ASP | CPR | REF | 29 | INV | 308 | A | I | CFC | 667.6 | 667.6 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 2769118 | -754390 | 2014728 | 2014727.99 | 100% | 0.01 | 0 |  | 314603 | -83334 | 231269 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejian Electrical Equipment Co. | Individual | ASP | CPR | REF | 29 | INV | 336 | A | I | CFC | 199 | 199 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-09-01 | 2189782 | -42893 | 2146889 | 2146888.98 | 100% | 0.02 | 0 |  | 250876 | -4718 | 246158 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the domestic refrigeration (hydrocarbons) sector | Individual | ASP | CPR | REF | 30 | PRP | 339 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration compressor subsector | Individual | ASP | CPR | REF | 30 | PRP | 340 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 50000 | -786 | 49214 | 49214.19 | 100% | -0.19 | 0 |  | 6500 | -112 | 6388 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the transportation refrigeration sector (foam component) | Individual | ASP | CPR | REF | 30 | PRP | 341 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 40000 | 0 | 40000 | 39999.55 | 100% | 0.45 | 0 |  | 5200 | -1 | 5199 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and HFC-134a in the production of refrigerators at Banshen Electric Appliances Co. | Individual | ASP | CPR | REF | 31 | INV | 357 | A | I | CFC | 563 | 563 |  |  | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-06-01 | 2005-04-01 | 2988840 | -196425 | 2792415 | 2792415.49 | 100% | -0.49 | 0 |  | 338772 | -22093 | 316679 | 0 | 0 | FIN
FIN | UNIDO | Preparation of 2 investment projects in the domestic (hydrocarbons) refrigeration sub-sector | Individual | ASP | CPR | REF | 31 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-08-01 | 2002-11-01 | 40000 | -17965 | 22035 | 22035 | 100% | 0 | 0 |  | 5200 | -2340 | 2860 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Little Swan Electric (Jingzhou) Co. Ltd. | Individual | ASP | CPR | REF | 32 | INV | 365 | A | I | CFC | 211.9 | 211.9 |  |  | 2000-12-01 | 2001-06-01 | 2003-12-01 |  | 2004-05-01 | 2005-09-01 | 2392316 | 0 | 2392316 | 2392316.08 | 100% | -0.08 | 0 |  | 273155 | -253 | 272902 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral phase-out plan in domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 36 | PRP | 385 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-07-01 |  | 2003-07-01 | 2004-04-01 | 70000 | 0 | 70000 | 70000.32 | 100% | -0.32 | 0 |  | 9100 | -12 | 9088 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-Year | ASP | CPR | REF | 38 | INV | 394 | A | I | CFC | 600 | 600 |  |  | 2002-11-01 | 2003-09-01 | 2007-05-01 |  | 2007-06-01 | 2007-12-01 | 3400000 | 0 | 3400000 | 3399999.51 | 100% | 0.49 | 0 |  | 299200 | 0 | 299200 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (second tranche) | Multi-Year | ASP | CPR | REF | 41 | INV | 406 | A | I | CFC | 318 | 318 |  |  | 2003-12-01 | 2006-12-01 | 2007-12-01 |  | 2009-12-01 | 2010-04-01 | 2171539 | -27541 | 2143998 | 2143997.51 | 100% | 0.49 | 0 |  | 192239 | -2460 | 189779 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 419 | A | I | CFC | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -450043 | 549957 | 549956.95 | 100% | 0.05 | 0 |  | 75000 | -33753 | 41247 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (third tranche) | Multi-Year | ASP | CPR | REF | 51 | INV | 450 | A | I | CFC | 782 | 782 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-12-01 | 2010-05-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (fourth tranche) | Multi-Year | ASP | CPR | REF | 53 | INV | 453 | A | I | CFC | 793 | 793 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 |  | 2013-12-01 | 2014-07-01 | 700000 | -2861 | 697139 | 697138.75 | 100% | 0.25 | 0 |  | 52500 | -215 | 52285 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC Phase-out Plan (fifth tranche) | Multi-Year | ASP | CPR | REF | 56 | INV | 474 | A | I | CFC | 680 | 680 |  |  | 2008-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 | 2011-12-01 | 700000 | -104 | 699896 | 699895.84 | 100% | 0.16 | 0 |  | 52500 | -8 | 52492 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (sixth tranche) | Multi-Year | ASP | CPR | REF | 59 | INV | 490 | A | I | CFC | 1136 | 1136 |  |  | 2009-11-01 | 2010-10-01 | 2010-11-30 |  | 2013-12-01 | 2013-12-01 | 785000 | 0 | 785000 | 785000 | 100% | 0 | 0 |  | 58880 | 0 | 58880 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Demonstration sub-project for conversion of room airconditioning compressor manufacturing from HCFC-22 to propane at Guangdong Meizhi Co. | Individual | ASP | CPR | REF | 61 | DEM | 502 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 |  | 2013-12-01 |  | 1875000 | 0 | 1875000 | 1674244.47 | 89.29% | 200755.53 | 200736.87 | 200000 | 140625 | 0 | 125568 | 15057 | 15055 | Project will be financially completed upon clearance of all obligations. |  |  |  | INV
COM | UNIDO | Demonstration sub-project for conversion from HCFC-22 to propane at Midea Room Air-conditioning Manufacturing Company | Individual | ASP | CPR | REF | 61 | DEM | 503 | A | I | HCFC | 13.2 | 13.2 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 |  | 2014-12-01 |  | 4026507 | 0 | 4026507 | 2793283.51 | 69.37% | 1233223.49 | 1197619.17 | 1230000 | 301988 | 0 | 209496 | 92492 | 89821 | - The conversion demonstration project was successfully completed and detailed final report submitted to the 73rd ExCom Meeting. - Experience gained by Midea have been and are being disseminated at various national and international conferences and workshops: • During network meetings; • Annual international conference of RAC manufacturers in China, which was held end October/early November; • UNIDO ATMOsphere Technology Summit that was held in June 2013 in Vienna; • Conferences on HCFC alternatives in high ambient conditions; Milestones achieved: First mission, working arrangements and TOR agreed: Yes Contract signed: Yes Equipment delivered and installed: Yes Trials done and TUV certification received: Yes National acceptance received: Yes Activities planned but not implemented, reasons and strategy: N /A. Actions towards next goals: N/A Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - The project has been successfully completed and detailed final report submitted to the 73rd ExCom Meeting. |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (room and air-conditioner and domestic heat pump sectors) | Individual | ASP | CPR | REF | 73 | PRP | 554 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-06-01 | 2016-06-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 0 | 80000 | 21000 | 0 | 0 | 21000 | 0 | - The project was approved at the 73rd Meeting of the Executive Committee in November 2014. - PAD was issued in December 2014 that allowed start-up of project activities. Milestones achieved: Working arrangements agreed: No; ToR for the Stage II HPMP preparation prepared and agreed: No; Contract signed: No; HCFC survey completed: No; All technical input completed: No Draft document completed: No Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Preparation of working arrangements and ToR. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - Working arrangements were agreed upon in February 2015, ToR and bidding was finalized in April 2015. - First inter-agency coordination meeting was organized early July 2015 discussing first results of the survey. - Next coordination meeting is planned for September 2015 and HPMP is planned to be submitted to the 76th Meeting of the Executive Committee. Milestones achieved: Working arrangements agreed: Yes, February 2015; ToR for the Stage II HPMP preparation prepared and agreed: Yes, March 2015; Contract signed: Yes, May 2015; HCFC survey completed: No; All technical input completed: No Draft document completed: No Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Finalization of survey and preparation of draft strategy by November 2015. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Project formulation of investment projects in the halon sector in the 3 fire equipment factories (Xiangshan, Xiangshan No. 1 and Dalian Jinzhou) and in domestic refrigeration sectors and solvents | Individual | ASP | CPR | SEV | 17 | PRP | 132 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 1998-12-01 | 2000-07-01 | 100000 | -193 | 99807 | 99807 | 100% | 0 | 0 |  | 13000 | -46 | 12954 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the refrigeration (including compressors), solvents and methyl bromide sectors | Individual | ASP | CPR | SEV | 21 | PRP | 190 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1999-12-01 | 2002-09-01 | 182140 | -575 | 181565 | 181565.3 | 100% | -0.3 | 0 |  | 23678 | -112 | 23566 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Jiaxipera compressor factory | Individual | ASP | CPR | SOL | 22 | INV | 203 | A | I | CFC | 76 | 76 |  |  | 1997-05-01 | 1998-10-01 | 1998-12-01 |  | 1999-05-01 | 2000-04-14 | 308604 | 0 | 308604 | 308604 | 100% | 0 | 0 |  | 40119 | 0 | 40119 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from CFC-113 to trichloroethylene at Hangli Refrigeration Ltd. | Individual | ASP | CPR | SOL | 22 | INV | 212 | A | I | CFC | 28.8 | 28.8 |  |  | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1999-12-01 | 2001-03-01 | 217762 | 0 | 217762 | 217762 | 100% | 0 | 0 |  | 28309 | -8 | 28301 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | SOL | 22 | INV | 213 | A | I | CFC | 37.6 | 37.6 |  |  | 1997-05-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 1999-07-01 | 236242 | 0 | 236242 | 236242 | 100% | 0 | 0 |  | 30711 | 0 | 30711 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Pliva D.D. | Individual | EUR | CRO | ARS | 22 | INV | 05 | A | I | CFC | 10.6 | 10.6 |  |  | 1997-05-01 | 1997-10-01 | 1998-08-01 |  | 2000-10-01 | 2001-12-01 | 89779 | -2344 | 87435 | 87434.5 | 100% | 0.5 | 0 |  | 11671 | -323 | 11348 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | EUR | CRO | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -686 | 29314 | 29314 | 100% | 0 | 0 |  | 3900 | -95 | 3805 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Oriolik Co. flexible polyurethane foam plant | Individual | EUR | CRO | FOA | 22 | INV | 04 | A | I | CFC | 25 | 25 |  |  | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-11-01 | 2000-07-01 | 110780 | -24 | 110756 | 110756 | 100% | 0 | 0 |  | 14401 | -26 | 14375 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase-out of HCFC-141b in polyurethane foam production | Individual | EUR | CRO | FOA | 57 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2010-07-01 | 2010-12-01 | 40000 | -14 | 39986 | 39986.25 | 100% | -0.25 | 0 |  | 3000 | -1 | 2999 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid foam at Pavusin | Multi-Year | EUR | CRO | FOA | 59 | INV | 34 | A | I | HCFC | 2 | 0 |  |  | 2009-11-01 | 2010-06-01 | 2011-11-30 |  |  | 2012-05-01 | 271150 | -268988 | 2162 | 2162.35 | 100% | -0.35 | 0 |  | 20336 | -20174 | 162 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (tobacco, tomatoes) | Individual | EUR | CRO | FUM | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide in tobacco production; namely: solarization plus bio-fumigation, the use of low-dose chemicals, and non-soil cultivation, in combination with an integrated pest management programme | Individual | EUR | CRO | FUM | 25 | DEM | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-09-01 | 2000-08-01 |  | 2001-05-01 | 2003-03-01 | 288200 | -28165 | 260035 | 260034.82 | 100% | 0.18 | 0 |  | 37466 | -3715 | 33751 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the tobacco fumigation sector | Individual | EUR | CRO | FUM | 33 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -16341 | 13659 | 13658.86 | 100% | 0.14 | 0 |  | 3900 | -2127 | 1773 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of methyl bromide in tobacco seedlings | Individual | EUR | CRO | FUM | 35 | INV | 14 | A | I | MBR | 16.2 | 16.2 |  |  | 2001-12-01 | 2002-07-01 | 2007-01-01 |  | 2006-12-01 | 2007-12-01 | 476833 | -5789 | 471044 | 471044.2 | 100% | -0.2 | 0 |  | 61988 | -752 | 61236 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | INV | 20 | A | I | CFC | 0 | 33 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2005-04-01 | 2010-04-01 | 184000 | -446 | 183554 | 183554.19 | 100% | -0.19 | 0 |  | 13800 | -33 | 13767 | 0 | 0 | FIN
FIN | UNIDO | Terminal phase-out management plan: 2004 annual implementation programme | Multi-Year | EUR | CRO | PHA | 42 | TAS | 22 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2011-05-01 | 48300 | 0 | 48300 | 48300 | 100% | 0 | 0 |  | 3623 | 0 | 3623 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 26 | A | I | CFC | 20 | 20 |  |  | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2011-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC phase-out management plan (4th tranche) | Multi-Year | EUR | CRO | PHA | 49 | TAS | 29 | A | I | CFC | 65 | 65 |  |  | 2006-07-01 | 2008-02-01 | 2008-12-01 |  | 2008-12-01 | 2011-12-01 | 20200 | -2100 | 18100 | 18100 | 100% | 0 | 0 |  | 1515 | -157 | 1358 | 0 | -1 | FIN |  |  |  | INV
FIN | UNIDO | Monitoring and verification audit report | Individual | EUR | CRO | PHA | 52 | TAS | 30 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-01-31 |  | 2008-09-01 | 2009-09-01 | 20000 | -3296 | 16704 | 16703.54 | 100% | 0.46 | 0 |  | 1800 | -297 | 1503 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | CRO | PHA | 55 | PRP | 31 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 150000 | -456 | 149544 | 149543.63 | 100% | 0.37 | 0 |  | 11250 | -34 | 11216 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | CRO | PHA | 61 | INV | 36 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2014-12-31 | 2015-07-01 |  |  | 180000 | 0 | 180000 | 171536.32 | 95.3% | 8463.68 | 8463.88 | 8000 | 13500 | 0 | 12865 | 635 | 635 | - The Environmental Protection and Energy Efficiency Fund of the Republic of Croatia ("Fund") provided UNIDO the first and the second progress reports summarizing its activities in 2013-2014. - According to the Agreement concluded with the Environment Fund of Croatia, at least three sites are to be retrofitted to HFCs and at least seven sites are to be converted/replaced to low GWP alternatives in Croatia. - The implementation of the Agreement by the Fund progressed well. - Additional co-financing offered by the Fund. - The modification of AC units for the vocational schools got finalized and inspected by national expert in the beginning of April 2014. In the course of April the units have been distributed to the eight vocational schools of Croatia. - The training of vocational school teachers was organized in December 2014 with the involvement of the University of Zagreb, Faculty of Mechanical Engineering and Naval Architecture. - The training of customs officers and environmental inspectors took place the end of the year at various locations in the country with the active involvement of the national Customs Authorities. - All the project activities are completed. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - All the project activities are completed. - Pending obligations to be closed. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second and third tranches) | Multi-Year | EUR | CRO | PHA | 66 | INV | 38 | A | I | HCFC | 4.3 | 4.3 |  |  | 2012-04-01 | 2013-01-01 | 2013-07-31 | 2015-12-21 |  |  | 360000 | 0 | 360000 | 226240.93 | 62.84% | 133759.07 | 5904.83 | 130000 | 27000 | 0 | 16968 | 10032 | 442.8623 | - The Environmental Protection and Energy Efficiency Fund of the Republic of Croatia ("Fund") provided UNIDO the first and the second progress reports summarizing its activities in 2013-2014. - According to the Agreement concluded with the Environment Fund of Croatia, at least three sites are to be retrofitted to HFCs and at least seven sites are to be converted/replaced to low GWP alternatives in Croatia. - The implementation of the Agreement by the Fund progressing well. - Additional co-financing offered by the Fund. - The modification of AC units for the vocational schools got finalized and inspected by national expert in the beginning of April 2014. In the course of April the units have been distributed to the eight vocational schools of Croatia. - The training of vocational school teachers was organized in December 2014 with the involvement of the University of Zagreb, Faculty of Mechanical Engineering and Naval Architecture. - The training of customs officers and environmental inspectors took place by the end of the year at various locations in the country with the active involvement of the national Customs Authorities. - On the request of the NOU the Croatian publication of two GIZ publications is arranged. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Due to the success of the project the Fund decided to increase its co-financing. The internal procedure from the side of the Fund to approve the increased co-financing level slightly delayed implementation. Any recurring problem? No Any impact on project completion date: Project to be completed by the end of 2015. Any action required by Executive Committee? No | - By 31 March 2015 the Fund successfully completed all the project activities as defined in the Agreement and the Terms of Reference. - With the retrofitting of five and the conversion/replacement of nine refrigeration units at eight beneficiaries in total, the project reached the phase-out of 1,222 kg of HCFC-22. - An auditing firm was contracted to verify the Fund's final report. - Final report audited, final payment transferred to the Fund in June 2015. - National expert finalizing a handbook for vocational school teachers. Material is based on the training provided in Dec 2014. - On the request of the NOU the Croatian publication of two GIZ publications is arranged. Actions towards next goals: Pending obligations to be closed. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (fourth tranche) | Multi-Year | EUR | CRO | PHA | 71 | INV | 40 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2014-12-31 | 2015-12-21 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 30000 | 4500 | 0 | 0 | 4500 | 0 | - The Environmental Protection and Energy Efficiency Fund of the Republic of Croatia ("Fund") provided UNIDO the first and the second progress reports summarizing its activities in 2013-2014. - According to the Agreement concluded with the Environment Fund of Croatia, at least three sites are to be retrofitted to HFCs and at least seven sites are to be converted/replaced to low GWP alternatives in Croatia. - The implementation of the Agreement by the Fund progressing well. - Additional co-financing offered by the Fund. - The modification of AC units for the vocational schools got finalized and inspected by national expert in the beginning of April 2014. In the course of April the units have been distributed among the eight vocational schools of Croatia. - The training of vocational school teachers was organized in December 2014 with the involvement of the University of Zagreb, Faculty of Mechanical Engineering and Naval Architecture. - The training of customs officers and environmental inspectors took place by the end of the year at various locations in the country with the active involvement of the national Customs Authorities. - On the request of the NOU the Croatian publication of two GIZ publications is arranged. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Due to the success of the project the Fund decided to increase its co-financing. The internal procedure to approve the increased co-financing level slightly delayed implementation. Any recurring problem? No Any impact on project completion date: Project to be completed by the end of 2015. Any action required by Executive Committee? No | - Remaining funds are committed for additional retrofitting under a second contract with the Fund on the request of the NOU. - As per the current plans, these retrofits will be completed by the end of 2015. Actions towards next goals: Fund to submit progress reports during 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: NOU's request to conclude a second agreement with the Fund came in the beginning of 2015. Lengthy contractual procedures. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be closed by the end of 2015. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | CRO | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-02-01 | 1999-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | EUR | CRO | REF | 28 | TAS | 10 | A | I | CFC | 15 | 15 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2003-10-01 | 289910 | -3739 | 286171 | 286171.08 | 100% | -0.08 | 0 |  | 37688 | -545 | 37143 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | EUR | CRO | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2003-02-01 | 2003-07-01 | 70000 | -1483 | 68517 | 68517 | 100% | 0 | 0 |  | 9100 | -207 | 8893 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | EUR | CRO | REF | 28 | TRA | 12 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2001-04-01 | 2001-08-01 |  | 2002-06-01 | 2003-07-01 | 38250 | -2227 | 36023 | 36022.65 | 100% | 0.35 | 0 |  | 4973 | -297 | 4676 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the solvents (CTC) sector | Individual | EUR | CRO | SOL | 45 | TAS | 25 | A | I | CTC | 2.3 | 2.3 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a phase out project (tobacco) | Individual | LAC | CUB | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-01-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Phasing out methyl bromide in the tobacco sector | Individual | LAC | CUB | FUM | 26 | INV | 11 | A | I | MBR | 48 | 48 |  |  | 1998-11-01 | 1999-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-12-01 | 1673324 | -294 | 1673030 | 1673030.39 | 100% | -0.39 | 0 |  | 194066 | -324 | 193742 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to eliminate methyl bromide consumption (horticulture) | Individual | LAC | CUB | FUM | 43 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2006-09-01 | 30000 | -1068 | 28932 | 28931.73 | 100% | 0.27 | 0 |  | 2250 | -80 | 2170 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide in soil, substrate, storage and structure fumigation | Individual | LAC | CUB | FUM | 44 | INV | 29 | A | I | MBR | 24.1 | 24.1 |  |  | 2004-12-01 | 2005-07-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 537763 | -3543 | 534220 | 534220.49 | 100% | -0.49 | 0 |  | 40332 | -265 | 40067 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project (hospitals) in the commercial refrigeration sector | Individual | LAC | CUB | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-02-14 | 2001-07-01 | 50000 | -1874 | 48126 | 48126 | 100% | 0 | 0 |  | 6500 | -253 | 6247 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | UNIDO | Preparation of a demonstration project (tobacco, curcubits, flowers, tomatoes) | Individual | LAC | DOM | FUM | 25 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: alternatives to the use of methyl bromide: soil pasteurization (steam), non soil cultivation, solarization with biofumigation and low dose chemicals all in combination with IPM system | Individual | LAC | DOM | FUM | 26 | DEM | 19 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2002-03-01 | 2003-05-01 | 324500 | -699 | 323801 | 323800.91 | 100% | 0.09 | 0 |  | 42185 | -158 | 42027 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the fumigants (methyl bromide) sector for TPO-soil fumigation | Individual | LAC | DOM | FUM | 36 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2004-03-01 | 30000 | -2722 | 27278 | 27278.42 | 100% | -0.42 | 0 |  | 3900 | -359 | 3541 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in melon, flowers and tobacco | Individual | LAC | DOM | FUM | 38 | INV | 33 | A | I | MBR | 141 | 141 |  |  | 2002-11-01 | 2003-01-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 922900 | -886 | 922014 | 922014.19 | 100% | -0.19 | 0 |  | 111519 | -97 | 111422 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a phase-out plan in the solvents (CTC) sector | Individual | AFR | DRC | SOL | 45 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -1605 | 28395 | 28394.89 | 100% | 0.11 | 0 |  | 2250 | -120 | 2130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phasing out CFC-11 at Hamhung Foam Factory, Hamgyong South Province | Individual | ASP | DRK | FOA | 23 | INV | 06 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 102680 | -2145 | 100535 | 100535 | 100% | 0 | 0 |  | 13348 | -299 | 13049 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Pyongyang Foam Plant | Individual | ASP | DRK | FOA | 23 | INV | 07 | A | I | CFC | 83 | 83 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 103570 | -1984 | 101586 | 101585.63 | 100% | 0.37 | 0 |  | 13464 | -279 | 13185 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Chongjin Foam Factory, Hamgyong North Province | Individual | ASP | DRK | FOA | 23 | INV | 08 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 103670 | -72 | 103598 | 103598 | 100% | 0 | 0 |  | 13477 | -31 | 13446 | 0 | 0 | FIN
ONG | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | DRK | FOA | 64 | PRP | 54 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 | 2015-12-31 |  |  | 50000 | 0 | 50000 | 22318.4 | 44.64% | 27681.6 | 18040.23 | 27680 | 3750 | 0 | 1674 | 2076 | 1353 | - Submitted HPMP was deferred pending the requested written confirmation of the UN Security Council that the equipment to be supplied was not included into the list of items prohibited for import under the respective UN Sanctions. Milestones achieved: Milestone 1: Planning of the study tour - Yes Activities planned but not implemented, reasons and strategy: Study tour to visit HCFC production facilities in a A-5 country. Actions towards next goals: Study tour to visit HCFC production facilities in India scheduled for September 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delay in approval of the HPMP Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Study tour was originally planned for China but the FECO refused to accept the tour because of congestion of commitments. Instead, the tour has been agreed with the Government of India (the Ozone Cell). Milestones achieved: Milestone 1: Planning of the study tour - Yes Milestone 2: Organization of the study tour - No Activities planned but not implemented, reasons and strategy: Study tour to visit HCFC production facilities in a A-5 country Actions towards next goals: Study tour to visit HCFC production facilities in India scheduled for September 2015. Was there any delay during the reporting year? Yes. Delay due to non-acceptance of the tour by FECO China If yes, reasons and action plan: Study tour was agreed with the Indian Government as is being organized in September 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | DRK | FUM | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-01-01 | 2001-07-01 | 15000 | 8050 | 23050 | 23050 | 100% | 0 | 0 |  | 1950 | 1042 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Non-investment project: promotion and information transfer of alternatives to the use of methyl bromide in the preparation of seedbeds for the cultivation of rice and maize | Individual | ASP | DRK | FUM | 25 | TAS | 09 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 1999-07-01 |  | 1999-11-01 | 2001-03-01 | 27500 | -153 | 27347 | 27347 | 100% | 0 | 0 |  | 3575 | -25 | 3550 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvents, process agents and fumigants sector (CTC) | Individual | ASP | DRK | MUS | 39 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 40000 | -22 | 39978 | 39977.88 | 100% | 0.12 | 0 |  | 3000 | -6 | 2994 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a process agent terminal umbrella project | Individual | ASP | DRK | PAG | 48 | PRP | 42 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-05-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Supplementary plan for terminal phase-out of CTC as process agent | Individual | ASP | DRK | PAG | 49 | INV | 46 | A | I | CTC | 229.9 | 229.9 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 884399 | -799 | 883600 | 883599.54 | 100% | 0.46 | 0 |  | 66330 | -60 | 66270 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (first tranche) | Multi-Year | ASP | DRK | PHA | 41 | INV | 30 | A | I | CTC | 0 | 613.8 |  |  | 2003-12-01 | 2004-02-01 | 2004-12-01 |  | 2009-12-01 | 2011-05-01 | 3500000 | -2013 | 3497987 | 3497986.94 | 100% | 0.06 | 0 |  | 262500 | -151 | 262349 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (third tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 35 | A | I | CTC | 1441.4 | 597.7 |  |  | 2005-07-01 | 2006-04-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 300000 | 0 | 300000 | 300000.01 | 100% | -0.01 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (second tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 36 | A | I | CTC | 0 | 0 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 1000000 | -157 | 999843 | 999842.55 | 100% | 0.45 | 0 |  | 75000 | -12 | 74988 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-12-01 | 2006-12-01 | 15000 | -11196 | 3804 | 3804.13 | 100% | -0.13 | 0 |  | 1125 | -840 | 285 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the NPP: recovery and recycling | Multi-Year | ASP | DRK | PHA | 47 | TAS | 40 | A | I | CFC | 121.7 | 163.7 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 536000 | -7549 | 528451 | 528451.01 | 100% | -0.01 | 0 |  | 40200 | -566 | 39634 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (fourth tranche) | Multi-Year | ASP | DRK | PHA | 49 | INV | 45 | A | I | CTC | 100 | 100 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (fifth tranche) | Multi-Year | ASP | DRK | PHA | 52 | INV | 48 | A | I | CTC | 15 | 15 |  |  | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-12-01 | 2009-05-01 | 284840 | -142 | 284698 | 284698.36 | 100% | -0.36 | 0 |  | 21363 | -11 | 21352 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (6th tranche) | Multi-Year | ASP | DRK | PHA | 55 | INV | 52 | A | I | CTC | 77.8 | 77.8 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 100000 | -2024 | 97976 | 97975.55 | 100% | 0.45 | 0 |  | 7500 | -152 | 7348 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 55 | PRP | 51 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-12-01 | 2013-10-01 | 50000 | -2026 | 47974 | 47974.03 | 100% | -0.03 | 0 |  | 3750 | -152 | 3598 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | DRK | PHA | 64 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 | 2015-12-31 |  |  | 65000 | 0 | 65000 | 59216.63 | 91.1% | 5783.37 | 28.32 | 5783 | 4875 | 0 | 4441 | 434 | 2 | - Submitted HPMP was deferred pending the requested written confirmation of the UN Security Council that the equipment to be supplied was not included into the list of items prohibited for import under the respective UN Sanctions. - Same as for DRK/FOA/64/PRP/54 | - Same as for DRK/FOA/64/PRP/54 |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | Multi-Year | ASP | DRK | PHA | 73 | INV | 59 | A | I | HCFC | 2.8 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2017-03-01 |  |  | 83517 | 0 | 83517 | 0 | 0% | 83517 | 0 | 30000 | 5846 | 0 | 0 | 5846 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014 in accordance with the Agreement between the Government and the Executive Committee for the period 2014 to 2018 to reduce HCFC consumption by 15 per cent of the baseline on the understanding that approval was without prejudice to the operation of the Montreal Protocol’s mechanism for addressing non compliance. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption the baseline of 78.0 ODP tonnes, calculated using actual consumption of 61.8 ODP tonnes and 94.1 ODP tonnes reported for 2009 and 2010, respectively, under the Article 7 of the Montreal Protocol; and the commitment of the Government of the Democratic People’s Republic of Korea to ban imports of HCFC-141b, both pure and contained in pre-blended polyols, no later than 1 January 2018. UNIDO, UNEP and the Government were requested to deduct 20.03 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption. - UNIDO was further requested to report to the first meeting in 2015 on the results of the consultations with the UN Security Council Committee regarding equipment items considered unlikely to be prohibited by UN resolutions but for which additional information was collected by UNIDO to determine that with certainty. In the event that there are items not cleared by the UN Security Council Committee, UNIDO was requested to present an alternative action plan to address the associated HCFC consumption. UNIDO and UNEP were requested to follow an approach similar to that taken for the first tranche of the HPMP for the Democratic People’s Republic of Korea in terms of compliance with the resolutions of the UN Security Council, the modality of disbursement, organizational structures and monitoring procedures when submitting and implementing future tranches of the HPMP. | - Procurement of spray foam equipment for the Puhung Building Materials Factory has been initiated in January 2015. Offers from two qualified suppliers were received and Purchase Order (Contract) for the selected supplier was issued in February 2015. The equipment was delivered in July 2015. - A letter from UNIDO to the UN Security Council Committee requesting confirmation that the foam equipment to be purchased under the HPMP investment component does not contravene the UNSC sanctions in respect to the DPRK was sent in February 2015. The confirmation from the UNSCC received in May 2015. - International foam expert from China was hired to prepare TOR for the equipment for conversion of the Sonbong PU Foam Factory to pentane. The expert visited the beneficiary company during the mission on 22-26 June 2015 and TOR is published in August 2015. Milestones achieved: Milestone 1: Contract award for spray foam equipment - Yes Milestone 2: Spray foam equipment delivery - Yes Milestone 3: Confirmation from UNSCC received - Yes Milestone 4: International foam expert recruited and visit of the factory performed - Yes Milestone 5: Technical specification for pentane equipment prepared - Yes Activities planned but not implemented, reasons and strategy: The TOR is published in August but the contract can't be awarded until the 2nd tranche of HPMP is approved and transferred to UNIDO. Actions towards next goals: Technical and commercial evaluation of the submitted offers, waiting for the 2nd tranche. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? Yes - Approval of the 2nd tranche. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | DRK | PHA | 73 | TAS | 60 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2017-03-01 |  |  | 40183 | 0 | 40183 | 0 | 0% | 40183 | 0 | 20000 | 2813 | 0 | 0 | 2813 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014 in accordance with the Agreement between the Government and the Executive Committee for the period 2014 to 2018 to reduce HCFC consumption by 15 per cent of the baseline on the understanding that approval was without prejudice to the operation of the Montreal Protocol’s mechanism for addressing non compliance. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption the baseline of 78.0 ODP tonnes, calculated using actual consumption of 61.8 ODP tonnes and 94.1 ODP tonnes reported for 2009 and 2010, respectively, under the Article 7 of the Montreal Protocol; and the commitment of the Government of the Democratic People’s Republic of Korea to ban imports of HCFC-141b, both pure and contained in pre-blended polyols, no later than 1 January 2018. UNIDO, UNEP and the Government were requested to deduct 20.03 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption. - UNIDO was further requested to report to the first meeting in 2015 on the results of the consultations with the UN Security Council Committee regarding equipment items considered unlikely to be prohibited by UN resolutions but for which additional information was collected by UNIDO to determine that with certainty. In the event that there are items not cleared by the UN Security Council Committee, UNIDO was requested to present an alternative action plan to address the associated HCFC consumption. UNIDO and UNEP were requested to follow an approach similar to that taken for the first tranche of the HPMP for the Democratic People’s Republic of Korea in terms of compliance with the resolutions of the UN Security Council, the modality of disbursement, organizational structures and monitoring procedures when submitting and implementing future tranches of the HPMP. | - Procurement of 3 units of advanced ODS identifiers started in January 2015. Offers from 4 qualified suppliers were received and Purchase Order (Contract) was issued in February 2015. The identifiers were delivered in April 2015. - Monitoring mission of the UNIDO Project Manager to discuss with local counterparts support for in-country activities was conducted on 22-26 June 2015. During the mission meetings with UN agencies such as WFP, UNICEF as well as bilateral development cooperation agencies (SDC, FBC, DEVCO) were conducted and alternative solutions to the funding of in-country activities were discussed and presented to UNEP after the mission. Milestones achieved: Milestone 1: Contract for ODS identifiers awarded - Yes Milestone 2: ODS identifiers delivered - Yes Milestone 3: Monitoring mission and discussion with local partners conducted - Yes Milestone 4: Modality of funding of in-country local activities agreed: Pending Actions towards next goals: Submission of the 2nd tranche request will be prepared upon consultations with UNEP and NCCE Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? Approval of 2nd tranche |  |  | INV
FIN | UNIDO | Closure of ODS production plant | Multi-Year | ASP | DRK | PRO | 36 | INV | 17 | A | R | CFC | 0 | 0 | 500 | 500 | 2002-03-01 | 2002-10-01 | 2003-03-01 |  | 2002-10-01 | 2003-05-01 | 1344350 | 0 | 1344350 | 1344350 | 100% | 0 | 0 |  | 67217 | 0 | 67217 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant: verification of complete closure of all CFC-11 and CFC-12 production facilities (second tranche) | Multi-Year | ASP | DRK | PRO | 42 | INV | 33 | A | I | CFC | 0 | 0 | 1250 | 1250 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2004-06-01 | 2004-12-01 | 733700 | 0 | 733700 | 733700 | 100% | 0 | 0 |  | 36685 | 0 | 36685 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant (third tranche) | Multi-Year | ASP | DRK | PRO | 49 | INV | 43 | A | I |  | 0 | 0 | 2530 | 2530 | 2006-07-01 | 2006-11-01 | 2008-12-01 |  | 2006-12-01 | 2008-04-01 | 488750 | 0 | 488750 | 488750 | 100% | 0 | 0 |  | 24438 | 0 | 24438 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the refrigeration sector (CFC) | Individual | ASP | DRK | REF | 39 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 20000 | -267 | 19733 | 19732.67 | 100% | 0.33 | 0 |  | 1500 | -22 | 1478 | 0 | 0 | FIN
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (first tranche) | Multi-Year | ASP | DRK | REF | 40 | INV | 26 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-10-01 | 2004-07-01 |  | 2004-12-01 | 2008-07-01 | 384000 | 0 | 384000 | 384000 | 100% | 0 | 0 |  | 28800 | 0 | 28800 | 0 | 0 | FIN
FIN | UNIDO | Provision of basic tools for the registered service workshops | RMP Update | ASP | DRK | REF | 40 | TAS | 29 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-09-01 | 2006-09-01 | 100000 | -10480 | 89520 | 89519.9 | 100% | 0.1 | 0 |  | 9000 | -943 | 8057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (second tranche) | Multi-Year | ASP | DRK | REF | 42 | INV | 32 | A | I | CFC | 56 | 56 |  |  | 2004-04-01 | 2004-08-01 | 2005-12-01 |  | 2009-12-01 | 2010-12-01 | 981011 | -33 | 980978 | 980978.41 | 100% | -0.41 | 0 |  | 73576 | -3 | 73573 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (commercial refrigeration sector) | Individual | ASP | DRK | REF | 64 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-11-01 | 2012-07-31 | 2015-12-31 |  |  | 30000 | 0 | 30000 | 13800.74 | 46% | 16199.26 | 5576.78 | 7000 | 2250 | 0 | 1035 | 1215 | 418 | - Submitted HPMP was deferred pending the requested written confirmation of the UN Security Council that the equipment to be supplied was not included into the list of items prohibited for import under the respective UN Sanctions. - Same as for DRK/FOA/64/PRP/54 | - Same as for DRK/FOA/64/PRP/54 |  |  | NON-INV
FIN | UNIDO | Project formulation of investment projects in all sectors | Individual | ASP | DRK | SEV | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 2000-10-01 | 2001-07-01 | 70000 | -1720 | 68280 | 68280 | 100% | 0 | 0 |  | 9100 | -238 | 8862 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 23 | INV | 05 | A | I | CTC | 110 | 110 |  |  | 1997-11-01 | 1999-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-07-01 | 311922 | 0 | 311922 | 311922.08 | 100% | -0.08 | 0 |  | 40550 | 0 | 40550 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvent to vapour at Pyongyang September 18 Bearings Factory | Individual | ASP | DRK | SOL | 26 | INV | 10 | A | I | CTC | 121 | 121 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 1081024 | -2425 | 1078599 | 1078598.62 | 100% | 0.38 | 0 |  | 128913 | -455 | 128458 | 0 | 0 | FIN
FIN | UNIDO | Conversion of remaining metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 26 | INV | 11 | A | I | CTC | 168 | 168 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2001-12-01 | 2002-12-01 | 490157 | -2198 | 487959 | 487958.96 | 100% | 0.04 | 0 |  | 63720 | -386 | 63334 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from CTC solvent to TCE vapour degreasing at Ceramic Tools Factory (CTF) | Individual | ASP | DRK | SOL | 28 | INV | 12 | A | I | CTC | 19.8 | 19.8 |  |  | 1999-07-01 | 2000-08-01 | 2000-08-01 |  | 2001-12-01 | 2002-12-01 | 206657 | 0 | 206657 | 206657 | 100% | 0 | 0 |  | 26865 | 0 | 26865 | 0 | 0 | FIN
FIN | UNIDO | Preparation for four projects in the solvent (CTC) sector | Individual | ASP | DRK | SOL | 33 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-10-01 |  | 2002-12-01 | 2003-05-01 | 70000 | -17 | 69983 | 69983.13 | 100% | -0.13 | 0 |  | 9100 | -17 | 9083 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride to aqueous cleaning techniques at the Gumsong Tractor Factory (GST) | Individual | ASP | DRK | SOL | 36 | INV | 18 | A | I | CTC | 198 | 198 |  |  | 2002-03-01 | 2002-06-01 | 2004-09-01 |  | 2004-12-01 | 2006-05-01 | 1932207 | 0 | 1932207 | 1932207.01 | 100% | -0.01 | 0 |  | 222543 | -1 | 222542 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning processes from CTC to aqueous and solvent cleaning techniques at Huichon February 26 Factory (HUI) | Individual | ASP | DRK | SOL | 37 | INV | 19 | A | I | CTC | 209 | 209 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-12-01 | 2006-05-01 | 1945477 | -950 | 1944527 | 1944527.06 | 100% | -0.06 | 0 |  | 224002 | -443 | 223559 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of methyl chloroform and CTC to non-ODS solvent cleaning in the plating workshop of the Taedong-gang Television Factory (PTV), Taedong-gang District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 20 | A | I | CTC | 59.8 | 59.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-06-01 | 2006-07-01 | 597886 | -4408 | 593478 | 593477.81 | 100% | 0.19 | 0 |  | 75767 | -484 | 75283 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of Cleaning Processes from CTC to perchloroethylene cleaning at the galvanising workshop of the Pyongyang Illuminating Fixtures Factory (PIF) | Individual | ASP | DRK | SOL | 38 | INV | 21 | A | I | CTC | 29.7 | 29.7 |  |  | 2002-11-01 | 2004-06-01 | 2004-06-01 |  | 2004-12-01 | 2006-09-01 | 230172 | -59 | 230113 | 230112.94 | 100% | 0.06 | 0 |  | 29922 | -7 | 29915 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning processes from CTC (formerly methyl chloroform) to perchloroethylene cleaning at the Plating Workshop (PLT) of the refrigeration factory of the 5 October Automation Complex, Pyongchon District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 22 | A | I | CTC | 69.3 | 69.3 |  |  | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2006-05-01 | 508068 | -1981 | 506087 | 506086.6 | 100% | 0.4 | 0 |  | 65887 | -306 | 65581 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam manufacturing sector) | Individual | LAC | ECU | FOA | 60 | PRP | 46 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2012-03-01 | 2012-05-01 | 60000 | 0 | 60000 | 59999.53 | 100% | 0.47 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment activities in cut-flowers production | Individual | LAC | ECU | FUM | 63 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-05-01 | 2012-03-31 |  | 2012-03-01 | 2012-05-01 | 45000 | -111 | 44889 | 44889.25 | 100% | -0.25 | 0 |  | 3375 | -8 | 3367 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | INV | 57 | A | I | MBR | 40.8 | 40.8 |  |  | 2011-11-01 | 2012-03-01 | 2014-11-30 |  | 2014-12-01 |  | 317500 | 0 | 317500 | 317233.45 | 99.92% | 266.55 | 0 | 1 | 23813 | 0 | 23793 | 20 | 0 | All the results have been collected and we are planning a final workshop by the end of May. It is expected to complete the project in Nov 2014. | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ECU | PHA | 59 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-03-01 | 2010-11-30 |  | 2012-03-01 | 2013-01-01 | 75000 | 0 | 75000 | 74999.87 | 100% | 0.13 | 0 |  | 5625 | 0 | 5625 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 47 | A | I | CFC | 42 | 42 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 10849 | 0 | 10849 | 10848.65 | 100% | 0.35 | 0 |  | 814 | 0 | 814 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 49 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-04-01 | 134575 | -95 | 134480 | 134480.04 | 100% | -0.04 | 0 |  | 10093 | -7 | 10086 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 51 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-12-01 | 134576 | 0 | 134576 | 134576 | 100% | 0 | 0 |  | 10093 | 0 | 10093 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing by Indurama) | Multi-Year | LAC | ECU | PHA | 65 | INV | 55 | A | I | HCFC | 15 | 15 |  |  | 2011-11-01 | 2012-03-01 | 2013-11-30 | 2015-03-01 |  |  | 1331440 | 0 | 1331440 | 1288227.96 | 96.75% | 43212.04 | 8136.63 | 43212 | 99858 | 0 | 96617 | 3241 | 610 | The commissioning and start up the production with cyclopentane took place in January 2014. Currently INDURAMA is producing 100% with cyclopentane, the HCFC-141b is phased out. The Safety Audit was supposed to take place in April 2014 by TÜV. In addition, the company started the process to phase out HFC-134a by using R-600a from their own funds. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - The production with cyclopentane has not been interrupted since the equipment was commissioned. The TÜV audit was carried out and the pending issues were completed by the producer. - Project activities are completed and the project is operationally closed in March 2015. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | INV | 58 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-08-01 | 2013-11-30 |  | 2014-08-15 |  | 200500 | 0 | 200500 | 189418.8 | 94.47% | 11081.2 | 8432.74 | 11081 | 15038 | 0 | 14206 | 832 | 632 | The project was completed in April 2014. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - The project is operationally completed and will be financially closed in August 2015. Actions towards next goals: Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | ECU | PHA | 70 | INV | 60 | A | I | HCFC | 1.8 | 1.8 |  |  | 2013-07-01 | 2014-01-01 | 2016-07-31 | 2015-09-01 |  |  | 86500 | 0 | 86500 | 32415.79 | 37.47% | 54084.21 | 19192.47 | 43000 | 6488 | 0 | 2431 | 4057 | 1439.4352 | - To continue with the training and certification program including the introduction of HC as alternative. - To develop a local manual for the use of HC as HCFC-22 alternative. - To follow up on the use of the reclaiming unit and maybe purchase two more units. - Three workshops for the introduction of the hydrocarbon as refrigerant took place in June 2014. - The importers are already importing hydrocarbon as refrigerant and the training and certification is included this in the scope. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Due to the delay in the signature of the Agreement between NOU and UNEP, the training program for technicians was delayed. Since the Agreement was finally signed the trainers of SECAP required to be trained again. A new training of trainers program took place in May 2015 at the same time with some workshops for refrigeration technicians. - A pilot program for ODS phase out in Galapagos was launched. For the program, all the refrigeration technicians in the islands were trained and tools were provided for the training centre. - The promotion of HC as refrigerant will be implemented through a new unit designed for R-290 to replace a cool room in the flower sector. - A local expert in refrigeration was contracted to follow up the activities and received training to be able to replace the international expert. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
CLO | UNIDO | Preparation of an investment project in a plant (Elasta) for the production of polyurethane flexible foam for automotive industry | Individual | LAC | ECU | SEV | 17 | PRP | 17 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1995-09-01 |  |  | 1999-12-01 | 15000 | -9243 | 5757 | 5757 | 100% | 0 | 0 |  | 1950 | -1203 | 747 | 0 | 0 | CLO
FIN | UNIDO | Preparation of a MDI phase-out plan (CFC) | Individual | AFR | EGY | ARS | 45 | PRP | 90 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 50000 | -337 | 49663 | 49663.07 | 100% | -0.07 | 0 |  | 3750 | -25 | 3725 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | AFR | EGY | ARS | 50 | INV | 92 | A | I | CFC | 159.5 | 159.5 |  |  | 2006-11-01 | 2007-01-01 | 2009-12-01 | 2016-12-01 |  |  | 5899000 | 0 | 5899000 | 5646506.95 | 95.72% | 252493.05 | 193450.12 | 20000 | 442425 | 0 | 423488 | 18937 | 14509 | - Early 2014, the revised planned completion date for this project was April 2014, since a final mission of the technology provider was scheduled for the first quarter of 2014 for the technology transfer of the last product. However, due to the failure of the stability tests for the last product, the supplier and the beneficiary are discussing to re-run the 3-month and 6-month stability tests incurring a minimum of 6 month-delay. - Furthermore, a fire has occurred in the factory of the second beneficiary resulting in the damage of the equipment supplied within the project’s framework. - The technology transfer mission is hence postponed until the new equipment is delivered, after the insurer’s reimbursement. The complete procedure is expected to take 18 months. - A meeting between the supplier and UNIDO was held in Vienna and the TOR for the 2nd stability tests have consequently been modified. Milestones achieved: TOR for new stability tests completed: Yes Was there any delay during the reporting year: Yes If yes, reasons and action plan: Lengthy discussions between technology supplier and beneficiary regarding the failed stability test. Face to face meeting between the three parties (beneficiary, supplier and UNIDO) to agree on the technical details and the date of the production of the test batch planned. Any recurring problem? No If yes, description of the problem/s: (narrative): Any action required by Executive Committee? No | - A face to face meeting between the three parties (beneficiary, supplier and UNIDO) took place in Cairo in the presence of the NOU to agree on the technical details for the production of the test batch. - After internal consultation, the beneficiary informed UNIDO that they agree to repeat the tests and discussions are ongoing for cost covering as equipment and raw material are required. Milestones achieved: Beneficiary agreed to new test batch production: Yes Was there any delay during the reporting year: Yes If yes, reasons and action plan: Lengthy discussions between technology supplier and beneficiary regarding the failed stability test. A deadline is set for final decision regarding new test. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The procurement of the equipment required for the new tests will delay the conversion. Any action required by Executive Committee? No |  |  | INV |  | Continued Monitoring
FIN | UNIDO | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at (ADVECHEMS) | Individual | AFR | EGY | FOA | 10 | INV | 16 | A | I | CFC | 196 | 183.3 |  |  | 1993-06-01 | 1994-03-01 | 1994-06-01 |  | 1994-12-01 | 2000-12-01 | 904000 | 0 | 904000 | 904000 | 100% | 0 | 0 |  | 117520 | -44 | 117476 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (appliance foam sector) | Individual | AFR | EGY | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-12-01 | 100000 | -374 | 99626 | 99626.09 | 100% | -0.09 | 0 |  | 7500 | -28 | 7472 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Mondial Freezers Company | Multi-Year | AFR | EGY | FOA | 62 | INV | 104 | A | I | HCFC | 6.6 | 6.6 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 436300 | 0 | 436300 | 348434.05 | 79.86% | 87865.95 | 82847.36 | 82847 | 32723 | 0 | 26133 | 6590 | 6214 | - Preparation for the installation underway involving some civil work. Was there any delay during the reporting year?: Yes) If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No | - Commissioning and start up of new equipment completed. Milestones achieved: Commissioning and start up completed: Yes Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No |  |  | INV
CLO | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Delta Electric Applicances | Individual | AFR | EGY | FOA | 62 | INV | 109 | A | I | HCFC | 8.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  |  | 2013-04-01 | 422740 | -406844 | 15896 | 15895.51 | 100% | 0.49 | 0 |  | 31706 | -30514 | 1192 | 0 | 0 | CLO |  |  |  | INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at El-Araby Co. for Engineering Industries | Multi-Year | AFR | EGY | FOA | 62 | INV | 110 | A | I | HCFC | 11 | 11 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 456540 | 0 | 456540 | 367971.48 | 80.6% | 88568.52 | 88315.6 | 50000 | 34241 | 0 | 27598 | 6643 | 6624 | - Commissioning and start up of new equipment completed. Milestones achieved: Commissioning and start up completed: Yes Was there any delay during the reporting year?: Yes If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No | - Commissioning and start up of new equipment completed. Milestones achieved: Commissioning and start up completed: Yes Was there any delay during the reporting year?: Yes If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | EGY | FOA | 73 | PRP | 120 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2015-11-30 | 2016-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 5000 | 4200 | 0 | 0 | 4200 | 0 | - The project was approved at the 73rd Meeting of the ExCom in November 2014. | - Discussions were held with NOU during a UNEP-UNIDO joint mission and it was agreed to have a meeting with stakeholders. The meeting is planned for Sep-Oct 2015. |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | EGY | FUM | 30 | PRP | 77 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-12-01 | 2003-05-01 | 25000 | -858 | 24142 | 24142.35 | 100% | -0.35 | 0 |  | 3250 | -116 | 3134 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | AFR | EGY | FUM | 33 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-12-01 | 2003-05-01 | 30000 | -528 | 29472 | 29471.78 | 100% | 0.22 | 0 |  | 3900 | -75 | 3825 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation | Individual | AFR | EGY | FUM | 38 | INV | 86 | A | I | MBR | 185.6 | 185.6 |  |  | 2002-11-01 | 2003-09-01 | 2009-11-01 |  | 2009-06-01 | 2011-03-01 | 2750592 | -95 | 2750497 | 2750497.35 | 100% | -0.35 | 0 |  | 312565 | -10 | 312555 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation except in date use | Individual | AFR | EGY | FUM | 56 | INV | 98 | A | I | MBR | 184.2 | 184.2 |  |  | 2008-11-01 | 2009-04-01 | 2013-11-30 |  | 2014-12-01 |  | 1934994 | 0 | 1934994 | 1849831.26 | 95.6% | 85162.74 | 47392.07 | 85000 | 145125 | 0 | 138737 | 6388 | 3554 | - Due to political unrest, some of the activities planned for 2013 had to be rephased to 2014. - The field activities were completed in 2014. - However, the final workshop has been postponed, a couple of times to 2015. | - The final report and some brochures in English and Arabic have been prepared. - The final workshop and the finalization of the project is expected in 2015. |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | EGY | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-04-01 | 2003-09-01 |  | 2005-12-01 | 2006-12-01 | 75000 | -33 | 74967 | 74966.89 | 100% | 0.11 | 0 |  | 9750 | -4 | 9746 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | AFR | EGY | PHA | 46 | INV | 91 | A | I | CFC | 190 | 190 |  |  | 2005-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -1043 | 998957 | 998956.56 | 100% | 0.44 | 0 |  | 75000 | -78 | 74922 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | AFR | EGY | PHA | 50 | INV | 93 | A | I | CFC | 182 | 182 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 1200000 | 0 | 1200000 | 1200000.08 | 100% | -0.08 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | AFR | EGY | PHA | 54 | INV | 95 | A | I | CFC | 100 | 100 |  |  | 2008-04-01 | 2008-11-01 | 2009-03-31 |  | 2013-12-01 |  | 600000 | 0 | 600000 | 587702.91 | 97.95% | 12297.09 | 12025.09 | 10000 | 45000 | 0 | 44078 | 922 | 902 |  |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | EGY | PHA | 55 | PRP | 96 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-08-01 | 2012-12-01 | 195000 | -834 | 194166 | 194166.18 | 100% | -0.18 | 0 |  | 14625 | -63 | 14562 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | EGY | PHA | 60 | INV | 101 | A | I |  | 65 | 65 |  |  | 2010-04-01 | 2010-05-01 | 2011-04-30 |  | 2013-12-01 | 2014-08-01 | 300000 | -2060 | 297940 | 297940.41 | 100% | -0.41 | 0 |  | 22500 | -155 | 22346 | -1 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the manufacture of insulation foam for refrigeration equipment) | Multi-Year | AFR | EGY | PHA | 65 | INV | 112 | A | I | HCFC | 23.5 | 23.5 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 | 2016-12-01 |  |  | 905700 | 0 | 905700 | 708377.61 | 78.21% | 197322.39 | 92265.91 | 70000 | 67928 | 0 | 53128 | 14800 | 6920 | - Preparation for the installation underway. - Safety issues addressed by the Egyptian company and the supplier. Was there any delay during the reporting year: Yes If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No | - Commissioning and start up of new equipment completed. Milestones achieved: Commissioning and start up completed: Yes Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in the installation due to security situation in the country Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project to be completed by end 2015 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (coordination and management) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 111 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-11-01 | 2012-11-30 | 2016-04-01 |  |  | 20000 | 0 | 20000 | 1543.54 | 7.718% | 18456.46 | 0 | 1000 | 1500 | 0 | 116 | 1384 | 0 | Funding under this component is reserved until installation activities under the FOAM components have been completed for verification proposes. Activities planned but not implemented, reasons and strategy:: Verification delayed due to foam components not completed. To be conducted after the latter's completion Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Foam components delayed due to security situation Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Verification to be completed by Apr 2016 Any action required by Executive Committee? No | - Funding under this component is reserved until installation activities under the FOAM components have been completed for verification proposes. Activities planned but not implemented, reasons and strategy: Verification delayed due to foam components not completed. To be conducted after the latter's completion Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Foam components delayed due to security situation Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Verification to be completed by Apr 2016 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 114 | A | I | HCFC | 0.3 | 0.3 |  |  | 2011-11-01 | 2013-05-01 | 2012-11-30 | 2016-12-01 |  |  | 24300 | 0 | 24300 | 12987.89 | 53.45% | 11312.11 | 0 | 1000 | 1823 | 0 | 974 | 849 | 0 | - Training and servicing centers are to be selected for upgrade in order to undertake training activities focusing on the use of low GWP refrigerants and RRR of HCFC refrigerants. - The organization of technical education and vocational training in Egypt has been recently changed. Contacts have been made with the General Directorate of Industrial Education in the technical education. Candidate centers have been identified. Technical evaluation visits are planned to finalize the selection. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Security situation and change in the Ministerial organization of the sector. Contacts with the new structures established. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Selected centers should be upgraded by 2016 Any action required by Executive Committee? No | - Contact with the newly established Ministry of Technical Education and Training is maintained. - Visits to training and servicing centers have been conducted for technical evaluation. - A coordination meeting will be held with the NOU once technical evaluation of the visited centers is completed to develop the structure of assistance to be provided. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Security situation and change in the Ministerial organization of the sector. Contacts with the new structures established. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Selected centers should be upgraded by 2016 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 68 | TAS | 116 | A | I | HCFC | 3.1 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2018-12-31 | 2018-12-01 |  |  | 250000 | 0 | 250000 | 109045.21 | 43.62% | 140954.79 | 9872.1 | 30000 | 18750 | 0 | 8178 | 10572 | 740.4075 | - A workshop was held in June 2014 with the Egyptian AC manufacturers to discuss the initiative for testing alternative refrigerant in prototypes built in Egypt. - A second workshop was held in December during which prototypes and refrigerants to be tested were defined. | - Technology providers contacted and agreements for the supply of refrigerants were made. - A national testing lab has been selected and an agreement between the lab and the NOU for work arrangement has been drafted. |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | EGY | PHA | 73 | PRP | 121 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2015-11-30 | 2016-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 5000 | 4900 | 0 | 0 | 4900 | 0 | - The project was approved at the 73rd Meeting of the ExCom in November 2014. | - Discussions were held with NOU during a UNEP-UNIDO joint mission and it was agreed to have a meeting with stakeholders. The meeting is planned for Sep-Oct 2015. |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for elimination of CFCs in manufacturing foams at Advechems and El Fateh | Individual | AFR | EGY | REF | 09 | TAS | 11 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-08-01 | 1998-08-01 | 50000 | -9289 | 40711 | 40711 | 100% | 0 | 0 |  | 6500 | -1216 | 5284 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the production of household refrigerators at Electrostar & Kiriazi | Individual | AFR | EGY | REF | 09 | TAS | 63 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-03-01 | 1998-08-01 | 50000 | 6602 | 56602 | 56602 | 100% | 0 | 0 |  | 6500 | 858 | 7358 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plants of Delta Industrial Co. | Individual | AFR | EGY | REF | 13 | INV | 32 | A | I | CFC | 97 | 117 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1997-05-01 | 2000-07-01 | 2611986 | -133089 | 2478897 | 2478897 | 100% | 0 | 0 |  | 339558 | -17812 | 321746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Electrostar for Refrigeration Co. | Individual | AFR | EGY | REF | 13 | INV | 33 | A | I | CFC | 46 | 51 |  |  | 1994-07-01 | 1995-02-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1450585 | -13996 | 1436589 | 1436589 | 100% | 0 | 0 |  | 188576 | -2115 | 186461 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Kiriazi Refrigerators Manufacturing Co. | Individual | AFR | EGY | REF | 13 | INV | 35 | A | I | CFC | 137 | 137 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1643040 | -52934 | 1590106 | 1590106 | 100% | 0 | 0 |  | 213595 | -7209 | 206386 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in production of household refrigeration at additional four companies | Individual | AFR | EGY | REF | 13 | PRP | 34 | A | I |  | 0 | 0 |  |  | 1994-07-01 | 1994-10-01 | 1994-10-01 |  | 1995-08-01 | 1998-08-01 | 15000 | 3364 | 18364 | 18364 | 100% | 0 | 0 |  | 1950 | 437 | 2387 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Helwan Company for Metallic Appliances domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 38 | A | I | CFC | 7.5 | 7.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 644239 | -29419 | 614820 | 614820 | 100% | 0 | 0 |  | 83751 | -3951 | 79800 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Super Bosh Factory domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 39 | A | I | CFC | 13 | 13 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 760066 | -34709 | 725357 | 725357 | 100% | 0 | 0 |  | 98809 | -4662 | 94147 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Islamic Company for Industrialization (Siltal) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 40 | A | I | CFC | 26 | 26 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 866633 | -39576 | 827057 | 827057 | 100% | 0 | 0 |  | 112662 | -5315 | 107347 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Société Mondiale pour Refroidissement (Alaska) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 41 | A | I | CFC | 55 | 55 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 1518606 | -69349 | 1449257 | 1449257 | 100% | 0 | 0 |  | 197419 | -9314 | 188105 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at International Co. for Refrigeration and Appliances (Iberna) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 42 | A | I | CFC | 19 | 19 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 852738 | -38941 | 813797 | 813797 | 100% | 0 | 0 |  | 110856 | -5230 | 105626 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at El Nasr Company for Electric and Electronic Apparatus (Philips) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 43 | A | I | CFC | 22.5 | 22.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 854690 | -39030 | 815660 | 815660 | 100% | 0 | 0 |  | 111110 | -5242 | 105868 | 0 | 0 | FIN
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | AFR | EGY | REF | 73 | PRP | 119 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2015-11-30 | 2016-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 5000 | 10500 | 0 | 0 | 10500 | 0 | - The project was approved at the 73rd Meeting of the ExCom in November 2014. | - Discussions were held with NOU during a UNEP-UNIDO joint mission and it was agreed to have a meeting with stakeholders. The meeting is planned for Sep-Oct 2015. |  |  | NON-INV
FIN | UNIDO | Institutional strengthening unit for the Montreal Protocol related activities | Individual | AFR | EGY | SEV | 10 | INS | 14 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1996-05-01 |  | 1996-12-01 | 2000-07-01 | 263450 | 0 | 263450 | 263450 | 100% | 0 | 0 |  | 34249 | 0 | 34249 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening project for the Montreal Protocol related activities (Phase II) | Individual | AFR | EGY | SEV | 21 | INS | 61 | N | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1999-02-01 |  | 1998-12-01 | 1999-09-01 | 43900 | 132009 | 175909 | 175909 | 100% | 0 | 0 |  | 5707 | 17125 | 22832 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase III: Institutional Strengthening Project for the Montreal Protocol Related Activities | Individual | AFR | EGY | SEV | 27 | INS | 73 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 2001-04-01 |  | 2001-11-01 | 2002-05-01 | 175000 | 0 | 175000 | 175000.46 | 100% | -0.46 | 0 |  | 22750 | -1 | 22749 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase IV) | Individual | AFR | EGY | SEV | 34 | INS | 83 | N | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-12-01 | 175000 | -8670 | 166330 | 166330.22 | 100% | -0.22 | 0 |  | 22750 | -1161 | 21589 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project | Individual | AFR | EGY | SEV | 40 | INS | 87 | N | I |  | 18.9 | 18.9 |  |  | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-08-01 | 228323 | -1 | 228322 | 228322 | 100% | 0 | 0 |  | 17125 | -1 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase VI) | Individual | AFR | EGY | SEV | 51 | INS | 94 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening projects (phase VII) | Individual | AFR | EGY | SEV | 56 | INS | 97 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2011-03-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | EGY | SEV | 61 | INS | 103 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2011-02-01 | 2012-12-31 |  | 2011-12-01 | 2013-10-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | AFR | EGY | SEV | 67 | INS | 115 | N | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2014-12-31 |  | 2014-12-01 |  | 228323 | 0 | 228323 | 228000 | 99.86% | 323 | 0 | 1 | 15983 | 0 | 15960 | 23 | 0 | - Activities implementation achieved as per Contract with counterpart. - Progress reports and Final report received and cleared. - Project completed as of December 2014. - Preparation of IS extension request submitted for the consideration of the 72nd Meeting of the ExCom. Milestones achieved: Milestone 1: Progress Reports received - Yes Milestone 2: Project completed - Yes Actions towards next goals: Preparation of IS extension achieved Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project completed as of December 2014. - IS extension approved by the 72nd Meeting of the ExCom. |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | AFR | EGY | SEV | 72 | INS | 118 | N | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-12-01 | 2016-12-31 | 2017-03-01 |  |  | 228323 | 0 | 228323 | 18.15 | 0.007949% | 228304.85 | 22800 | 102600 | 15983 | 0 | 1 | 15982 | 1596 | - Project approved at the 72nd Meeting of the ExCom in May 2014. - Contract with counterpart agreed in the second quarter of 2014. - Implementation initiated as per project activities' work plan. Milestones achieved: Milestone 1: PAD release - Yes Milestone 2: Contract agreed with counterpart - Yes Actions towards next goals: Follow-up on activities implementation based on progress report Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Follow up on progress reports and activities implementation as per the contractual arrangements. - Annual progress report due in December 2015. Milestones achieved: Milestone 1: Half year progress report- Yes Milestone 2: Annual implementation progress report (including awareness activities in 2015) - No Actions towards next goals: Initiation of terminal report preparation in view of project completion and new extension submission during the last quarter of 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
CLO | UNIDO | Conversion of cleaning processes from CFC-113 to Aqueous Cleaning at Optica | Individual | AFR | EGY | SOL | 18 | INV | 51 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-06-01 |  |  | 1996-06-01 | 12043 | -12043 | 0 | 0 |  | 0 | 0 |  | 1566 | -1566 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to non-ODS cleaning at 3 electronic companies | Individual | AFR | EGY | SOL | 18 | INV | 52 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-10-01 | 1998-11-01 | 227203 | 0 | 227203 | 227203 | 100% | 0 | 0 |  | 29536 | 0 | 29536 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from CFC-113 and 1,1,1 TCA to semi-aqueous cleaning at Arab International Optronics | Individual | AFR | EGY | SOL | 18 | INV | 53 | A | I | CFC TCA | 2.1 | 2.1 |  |  | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1999-12-01 | 2000-03-01 | 48533 | 0 | 48533 | 48533 | 100% | 0 | 0 |  | 6309 | 0 | 6309 | 0 | 0 | FIN |  |  | 1999-07-01
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Siltal | Individual | AFR | EGY | SOL | 18 | INV | 54 | A | I | TCA | 2 | 2 |  |  | 1995-11-01 | 1997-11-01 | 1996-06-01 |  | 1998-10-01 | 2000-07-01 | 48784 | -419 | 48365 | 48365 | 100% | 0 | 0 |  | 6342 | -65 | 6277 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Technopol | Individual | AFR | EGY | SOL | 19 | INV | 56 | A | I | TCA | 6 | 6 |  |  | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2000-05-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282 | 0 | 16282 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to cleaning in perchloroethylene at Abbasol | Individual | AFR | EGY | SOL | 19 | INV | 57 | A | I | TCA | 8 | 8 |  |  | 1996-05-01 | 1998-10-01 | 1997-05-01 |  | 1998-12-01 | 1999-07-01 | 154544 | 0 | 154544 | 154544 | 100% | 0 | 0 |  | 20091 | 0 | 20091 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector | Individual | AFR | EGY | SOL | 21 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-07-01 | 1997-06-01 |  | 2000-07-01 | 2000-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2001-03-01 | 15000 | 0 | 15000 | 14999.85 | 100% | 0.15 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Conversion of TCA used for the formulation of degreasing and contact cleaners and crack detectors to new formulations with special hydrocarbons and heavy chlorinated ester at Sien | Individual | AFR | EGY | SOL | 28 | INV | 79 | A | I | TCA | 9 | 9 |  |  | 1999-07-01 | 2000-11-01 | 2000-08-01 |  | 2002-06-01 | 2003-10-01 | 231435 | 0 | 231435 | 231435.42 | 100% | -0.42 | 0 |  | 30087 | -34 | 30053 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 30 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-12-01 | 2001-04-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000.05 | 100% | -0.05 | 0 |  | 1950 | -1 | 1949 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at Maasara Co. for engineering industries | Individual | AFR | EGY | SOL | 31 | INV | 80 | A | I | TCA | 10.7 | 10.7 |  |  | 2000-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-12-01 | 2004-03-01 | 294950 | 0 | 294950 | 294950.23 | 100% | -0.23 | 0 |  | 38344 | -4 | 38340 | 0 | 0 | FIN
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | AFR | EGY | SOL | 44 | INV | 89 | A | I | CFC CTC TCA | 41 | 41 |  |  | 2004-12-01 | 2005-02-01 | 2006-06-01 |  | 2007-12-01 | 2009-05-01 | 778464 | -5845 | 772619 | 772619.45 | 100% | -0.45 | 0 |  | 58385 | -439 | 57946 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | ELS | FUM | 45 | TAS | 18 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-09-01 | 2007-12-01 | 40000 | -2757 | 37243 | 37243.08 | 100% | -0.08 | 0 |  | 3600 | -248 | 3352 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | EQG | PHA | 65 | INV | 06 | A | I | HCFC | 0.3 | 0.3 |  |  | 2011-11-01 | 2012-09-01 | 2016-11-30 |  | 2014-12-31 |  | 75000 | 0 | 75000 | 72546.23 | 96.73% | 2453.77 | 2416.06 | 2416 | 6750 | 0 | 6529 | 221 | 217 | - Training was provided on the use of the procured equipment and tools in June 2014, and equipment has been distributed to beneficiaries. Milestones achieved: Milestone 1: Yes - Equipment and tools delivered at beneficiaries Actions towards next goals: (-) Tranche I of UNIDO's component completed Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Next tranche is due in 2016. |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | INV | 05 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2010-05-01 | 2010-03-31 |  | 2012-03-01 | 2012-04-01 | 100000 | -1 | 99999 | 99999.35 | 100% | -0.35 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | INV | 09 | A | I | CFC | 4.2 | 4.2 |  |  | 2011-04-01 | 2011-12-01 | 2012-03-31 |  | 2013-12-01 | 2014-08-01 | 75000 | -527 | 74473 | 74472.99 | 100% | 0.01 | 0 |  | 6750 | -47 | 6703 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ERI | PHA | 67 | INV | 10 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-04-01 | 2016-07-31 | 2016-07-01 |  |  | 40000 | 0 | 40000 | 19290.45 | 48.23% | 20709.55 | 20.19 | 20689 | 3600 | 0 | 1736 | 1864 | 1.8171 | - National expert was hired for coordination and survey. - The survey is being carried out. - Tools will be purchased for certified technicians and fishing industry. - It was agreed to establish the training centers with the new approach, it is expected to have the centers operating during the second semester 2014. - Training for trainer took place in December 2014 in Asmara. A total of 26 trainers were certified by Centro Studi Galileo. Milestones achieved: Milestone 1: Mission to the country to start project activities. Yes Milestone 2: Purchase and delivery of tools. Yes Milestone 3: Training and certification of trainers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - A joint mission with UNEP was planned originally, but it was not possible for UNEP to join. UNIDO's mission was scheduled for mid-August 2015, but due to flight cancellation, it had to be rescheduled to September to plan the activities for the second tranche. Milestones achieved: Milestone 1: Mission to the country to start project activities. Yes Milestone 2: Purchase and delivery of tools. Yes Milestone 3: Training and certification of trainers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Project preparation in the fumigant sector (flowers) | Individual | AFR | ETH | FUM | 54 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2015-12-01 |  |  | 35000 | 0 | 35000 | 2435.44 | 6.958% | 32564.56 | 0 | 2500 | 2625 | 0 | 183 | 2442 | 0 | - The NOU was contacted to follow-upon on the outcomes from the mission. Response is pending. - Lack of communication, but UNIDO will insist on getting a feedback and necessary guidance from the NOU in order to prepare a training to flower producers, with involvement of international experts. Milestones achieved: - Initial stages of project implementation began - Yes Activities planned but not implemented, reasons and strategy: Due to the lack of responsiveness from NOU, activities could not be implemented. Actions towards next goals: UNIDO will try the liaising with the NOU to agree on a plan of action. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of positive feedback from NOU Any recurring problem? Yes If yes, description of the problem/s: Lack of positive feedback from NOU Any impact on project completion date: Yes If yes, implications: Project grant needs to be extended Any action required by Executive Committee? No | - The NOU was contacted to follow-upon on the outcomes from the mission. Response is pending. - Lack of communication, but UNIDO will insist on getting a feedback and necessary guidance from the NOU in order to prepare a training to flower producers, with involvement of international experts. - Project is planned to be completed not later than December 2015. Milestones achieved: - Initial stages of project implementation began - Yes Activities planned but not implemented, reasons and strategy: Due to the lack of responsiveness from NOU, activities could not be implemented. Actions towards next goals: UNIDO will try the liaising with the NOU to agree on a plan of action. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of positive feedback from NOU Any recurring problem? Yes If yes, description of the problem/s: Lack of positive feedback from NOU Any impact on project completion date: Yes If yes, implications: Project grant needs to be extended Any action required by Executive Committee? Yes; to urge the government to liaise with the IA and provide a positive environment for the proper project implementation. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ETH | PHA | 68 | INV | 22 | A | I | HCFC | 0.2 | 0 |  |  | 2012-12-01 |  | 2016-12-31 | 2017-06-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 15000 | 6300 | 0 | 0 | 6300 | 0 | - UNIDO will be ready to purchase relevant equipment and materials as soon as the overall set-up (e.g. identification of training partner, training scheme for technicians, training programme for the custom authorities, scheme of quality certification of imported refrigerants, etc.) is agreed by NOU and UNEP. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Activities planned but not implemented, reasons and strategy: Agreement on scope of supply. Actions towards next goals: Discuss with the NOU on the scope of supply. Was there any delay during the reporting year? Yes If yes, reasons and action plan: NOU did not provide the list of items to be purchased. Any recurring problem? Yes If yes, description of the problem/s: Lack of responsiveness from NOU. Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO is ready to purchase relevant equipment and materials as soon as the overall set-up (e.g. identification of training partner, training scheme for technicians, training programme for the custom authorities, scheme of quality certification of imported refrigerants, etc.) is agreed by NOU and UNEP. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Activities planned but not implemented, reasons and strategy: Agreement on scope of supply. Actions towards next goals: Discuss with the NOU on the scope of supply. Was there any delay during the reporting year? Yes If yes, reasons and action plan: NOU did not provide the list of items to be purchased. Any recurring problem? Yes If yes, description of the problem/s: Lack of responsiveness from NOU. Any impact on project completion date: Yes. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
CLO | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | AFR | ETH | SOL | 45 | TAS | 15 | A | I | CTC TCA | 5.4 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  |  | 2007-12-01 | 40000 | -35474 | 4526 | 4526.08 | 100% | -0.08 | 0 |  | 3600 | -3193 | 407 | 0 | 0 | CLO |  |  |  | INV
COM | UNIDO | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) | Individual | EUR | EUR | DES | 65 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 |  | 2014-05-31 |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | -6.06 |  | 2625 | 0 | 2625 | 0 | 0 | - Final project was designed and approved at the 69th Meeting of the ExCom. - The project was completed in May 2014. |  |  |  | NON-INV
ONG | UNIDO | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | Individual | EUR | EUR | DES | 69 | DEM | 14 | A | I |  | 0 | 0 |  |  | 2013-04-01 | 2014-02-01 | 2015-04-30 | 2015-12-31 |  |  | 274480 | 0 | 274480 | 104165.28 | 37.95% | 170314.72 | 74799.52 | 95515.2 | 19214 | 0 | 7292 | 11922 | 5235.9664 | - Tools to support aggregation activities in RRR centers were delivered. - The contract for the destruction of a second batch of 10.2 MT of ODS waste was signed and was on-going as of 31 December 2014. Milestones achieved: Milestone 1: Yes - Tools to support aggregation activities in RRR centers delivered Milestone 2: Yes - Contract for the destruction of a second batch of 10.2 MT of ODS waste was signed Actions towards next goals: (-) Complete execution of works linked to the destruction of a second batch of 10.2 MT of ODS waste. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Execution of the works for the destruction of the second batch of 10.2 MT of ODS waste were completed. - Preparation of the documents to issue the Call for Bids for the 3rd and final batch is ongoing. Milestones achieved: Milestone 1: Yes - Completion of the works for the destruction of the second batch of 10.2 MT of ODS waste Activities planned but not implemented, reasons and strategy: The Call for Bids for the 3rd batch has not been issued yet due to a delay in the chemical analysis of the waste stored at one of the 3 Croatian recycling centres participating in the implementation of the project. Actions towards next goals: (-) Chemical analysis of the ODS waste finalized (-) Call for bids published and related contract signed (-) Execution of the works for the disposal of the 3rd and final batch of waste Was there any delay during the reporting year? Yes If yes, reasons and action plan: The delay was caused by the time needed to compile the information on the ODS waste available for the 3rd batch; this has already been solved. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date has been moved to Dec-15 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro) | Individual | EUR | EUR | REF | 47 | DEM | 06 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 | 2015-07-15 |  |  | 1069074 | 0 | 1069074 | 898499.66 | 84.04% | 170574.34 | 166396.4 | 69124.76 | 80181 | 0 | 67387 | 12794 | 12480 | - Delay caused by the fact that the Clinical Center Serbia was not ready to continue the project. Two old CFC-12 chillers were found in the Joint Administrative Services of the Government in Belgrade and the JAS agreed to undertake the conversion with assistance of the project. - Technical Specifications for replacement chillers have been prepared in March 2014 and Invitation to Bidding was published at the UNIDO Procurement Portal in April 2014. Contract to the selected supplier was awarded in July 2014. - Equipment was delivered to the country and cleared by the customs in September 2014. - The beneficiary was not ready with the site preparation in time so the chillers were stored in the supplier's warehouse. Milestones achieved: Milestone 1: Technical specification for two chillers published - Yes Milestone 2: Contract awarded to selected supplier - Yes Milestone 3: Equipment delivered and cleared through the customs - Yes Milestone 4: Installation and commissioning completed - No Activities planned but not implemented, reasons and strategy: The installation and commissioning had to wait until the beneficiary completed preparatory work for the site. Actions towards next goals: Wait for the beneficiary to have the site prepared. Was there any delay during the reporting year? Ye. for preparation of the site to host the chillers, the beneficiary had to make a local tender for the works which took much longer than expected. If yes, reasons and action plan: This was out of control of the PM. Any recurring problem? No Any impact on project completion date: Delay in operational completion If yes, implications: 6 month delay Any action required by Executive Committee? No | - The beneficiary finished the preparation of the site in February and at the end of February the installation and commissioning was performed by the supplier in June/July 2015. Milestones achieved: Installation and commissioning completed - Yes Actions towards next goals: Closure of the project Was there any delay during the reporting year? Delay from 2014 If yes, reasons and action plan: Delay in preparation of the project site Any recurring problem? No Any impact on project completion date: 6 month delay Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | INV | 27 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2017-04-01 |  |  | 130000 | 0 | 130000 | 77686.32 | 59.76% | 52313.68 | 0 | 1000 | 11700 | 0 | 6992 | 4708 | 0 | - Agreement is being set up between the Ministries for the handover of equipment to the training center Milestones achieved: Procurement of initial equipment lot: Yes Procurement of additional equipment: No Activities planned but not implemented, reasons and strategy: Procurement of additional equipment pending agreement signature Was there any delay during the reporting year?: Yes If yes, reasons and action plan: delay in signature of agreement. UNIDO encourages NOU to speed up signature process. Any impact on project completion date: Yes If yes, implications: Current tranche to be completed by 2017 Any action required by Executive Committee? No | - Agreement is being set up between the Ministries for the handover of equipment to the training center Milestones achieved: Procurement of initial equipment lot: Yes Procurement of additional equipment: No Activities planned but not implemented, reasons and strategy: Procurement of additional equipment pending agreement signature Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in signature of agreement. UNIDO encourages NOU to speed up signature process. Any impact on project completion date: Yes If yes, implications: Current tranche to be completed by 2017 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2012-07-01 | 2016-11-30 | 2015-12-01 |  |  | 50000 | 0 | 50000 | 45344.14 | 90.69% | 4655.86 | 2902.38 | 4500 | 4500 | 0 | 4081 | 419 | 261 | - Training on the use of equipment were planned for 2014 with the little funds remaining. Milestones achieved: Milestone 1: Yes - Materials prepared for training on use of equipment. Activities planned but not implemented, reasons and strategy: Training session in 2014 did not take place due to difficulties convening all stakeholders. Was there any delay during the reporting year?: Yes Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The project is planned to be completed by the end of 2015. Any action required by Executive Committee? No | - One training session on the use of supplied equipment planned for the last quarter in 2015. Actions towards next goals: Planning will commence to hold the last activity for the investment component; training on use of equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: The project is planned to be completed by the end of 2015. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Refrigeration recovery and recycling scheme | RMP | AFR | GAM | REF | 22 | TAS | 05 | A | I | CFC | 7.7 | 7.7 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 68000 | -243 | 67757 | 67757 | 100% | 0 | 0 |  | 8840 | -45 | 8795 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | INV | 15 | A | I | HCFC | 0.1 | 0 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 39138.2 | 97.85% | 861.8 | 0 | 1 | 3600 | 0 | 3522 | 78 | 0 | - The NOU and UNIDO could not agree on suitable dates for the provision of training on the use of the procured equipment and tools, after which these will be distributed to recipients. Reason for delay: instability in the country. Activities planned but not implemented, reasons and strategy: Provision of training and distribution of equipment among beneficiaries delayed due to instability in the country. Actions towards next goals: Need to agree on training dates. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Instability in the country; UNIDO is ready to provide the training and support the NOU in the distribution of the equipment as soon as there is a suitable date to provide the training. Any recurring problem? Yes If yes, description of the problem/s: Instability in the country Any impact on project completion date: Yes If yes, implications: Completion date adjusted to initial estimate. Any action required by Executive Committee? No | - The NOU and UNIDO could not agree on suitable dates for the provision of training on the use of the procured equipment and tools, after which these will be distributed to recipients. Reason for delay: instability in the country. Activities planned but not implemented, reasons and strategy: Provision of training and distribution of equipment among beneficiaries delayed due to instability in the country Actions towards next goals: Need to agree on training dates. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Instability in the country; UNIDO is ready to provide the training and support the NOU in the distribution of the equipment as soon as there is a suitable date to provide the training. Any recurring problem? Yes If yes, description of the problem/s: Instability in the country Any impact on project completion date: Yes If yes, implications: Completion date adjusted to initial estimate Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | EUR | GEO | FUM | 33 | PRP | 09 | A | I | MBR | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-05-01 | 2003-05-01 | 30000 | -1001 | 28999 | 28998.87 | 100% | 0.13 | 0 |  | 3900 | -136 | 3764 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance for the phase-out of methyl bromide for soil fumigation | Individual | EUR | GEO | FUM | 37 | TAS | 13 | A | I | MBR | 6 | 6 |  |  | 2002-07-01 | 2003-02-01 | 2006-08-01 |  | 2006-12-01 | 2009-12-01 | 220000 | -957 | 219043 | 219043.42 | 100% | -0.42 | 0 |  | 28600 | -124 | 28476 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of structure in fumigation of commodities in mill factories and grain storage | Individual | EUR | GEO | FUM | 44 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 30000 | -62 | 29938 | 29937.84 | 100% | 0.16 | 0 |  | 2250 | -5 | 2245 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance for the elimination of methyl bromide in grain and storage facilities | Individual | EUR | GEO | FUM | 47 | INV | 20 | A | I | MBR | 7.2 | 7.2 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2012-05-01 | 225500 | -2 | 225498 | 225498.11 | 100% | -0.11 | 0 |  | 20295 | 0 | 20295 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a national halon bank | Individual | EUR | GEO | HAL | 44 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-09-01 | 15000 | -1438 | 13562 | 13561.63 | 100% | 0.37 | 0 |  | 1125 | -108 | 1017 | 0 | 0 | FIN
FIN | UNIDO | Halon banking management programme | Individual | EUR | GEO | HAL | 47 | TAS | 21 | A | I | HAL | 42.5 | 42.5 |  |  | 2005-11-01 | 2006-08-01 | 2008-12-01 |  | 2008-01-01 | 2008-09-01 | 64930 | -603 | 64327 | 64327.46 | 100% | -0.46 | 0 |  | 5844 | -55 | 5789 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 288 | A | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2008-07-01 |  |  | 2008-09-01 | 390000 | -390000 | 0 | 0 |  | 0 | 0 |  | 29250 | -29250 | 0 | 0 | 0 | CLO |  |  |  | NON-INV
FIN | UNIDO | Strategy for phasing out of ODS in low ODS-consuming countries | Individual | GLO | GLO | REF | 11 | TAS | 46 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-09-01 | 1994-11-01 |  | 1996-06-01 | 1998-08-01 | 100000 | -159 | 99841 | 99841 | 100% | 0 | 0 |  | 13000 | -41 | 12959 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Development of Refrigeration Management Plans | Individual | GLO | GLO | REF | 22 | PRP | 134 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1997-12-01 |  | 2001-04-01 | 2001-09-01 | 60000 | -23740 | 36260 | 36260.31 | 100% | -0.31 | 0 |  | 7800 | -3094 | 4706 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2005-11-01 |  | 2006-06-01 | 2007-12-01 | 119000 | -640 | 118360 | 118360.18 | 100% | -0.18 | 0 |  | 8925 | -48 | 8877 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Joint UNIDO/UNEP preparation of country programmes | Individual | GLO | GLO | SEV | 12 | TAS | 62 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1996-06-01 | 1998-08-01 | 75000 | -3155 | 71845 | 71845 | 100% | 0 | 0 |  | 9750 | -425 | 9325 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 175 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  | 1999-12-01 | 2001-02-01 | 169000 | -169000 | 0 | 0 |  | 0 | 0 |  | 21970 | -21970 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance for 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 189 | A | I |  | 0 | 0 |  |  | 1999-11-01 |  | 2000-04-01 |  | 2000-12-01 | 2003-05-01 | 170000 | -170000 | 0 | 0 |  | 0 | 0 |  | 22100 | -22100 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 216 | A | I |  | 0 | 0 |  |  | 2000-12-01 |  | 2001-12-01 |  | 2001-03-01 | 2001-03-01 | 139500 | -139500 | 0 | 0 |  | 0 | 0 |  | 18135 | -18135 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 35 | PRP | 234 | A | I |  | 0 | 0 |  |  | 2001-12-01 |  | 2002-03-01 |  | 2002-03-01 | 2002-03-01 | 176250 | -176250 | 0 | 0 |  | 0 | 0 |  | 22913 | -22913 | 0 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 244 | A | I |  | 0 | 0 |  |  | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 250 | A | I |  | 0 | 0 |  |  | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget for 2005 | Individual | GLO | GLO | SEV | 44 | TAS | 258 | A | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 272 | A | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1700000 | 0 | 1700000 | 0 | 0 | FIN
FIN | UNIDO | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 277 | A | I |  | 0 | 0 |  |  | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1751000 | 0 | 1751000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 287 | A | I |  | 0 | 0 |  |  | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2008-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1803530 | 0 | 1803530 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 293 | A | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1857636 | 0 | 1857636 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 300 | A | I |  | 0 | 0 |  |  | 2009-11-01 |  | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1913365 | 0 | 1913365 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 303 | A | I |  | 0 | 0 |  |  | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2011-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1970766 | 0 | 1970766 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Mobilizing co-financing for Multilateral Fund funded projects based on the "Monetization" of their climate benefits | Individual | GLO | GLO | SEV | 63 | TAS | 307 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-12-01 | 2012-09-30 |  | 2014-12-23 |  | 200000 | 0 | 200000 | 182960.64 | 91.48% | 17039.36 | 16393.06 | 16000 | 18000 | 0 | 16466 | 1534 | 1475 | - The project component focusing on dissemination has been organized. - Report was sent to ExCom as per relevant Decision. - The project was successfully completed in March 2014. |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 311 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1984561 | 0 | 1984561 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 317 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2013-12-31 |  | 2013-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1998453 | 0 | 1998453 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Core unit budget (2014) | Individual | GLO | GLO | SEV | 71 | TAS | 319 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2014-12-31 |  | 2014-12-01 | 2014-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 2012442 | 0 | 2012442 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Core unit budget (2015) | Individual | GLO | GLO | SEV | 73 | TAS | 325 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2015-12-31 | 2015-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 2026529 | 0 | 0 | 2026529 | 0 | Core Unit Budget for 2015 was approved in November 2014. | Core Unit Functionalities in 2015 have continued to be undertaken and a report with estimated costs will be submitted to the 75th Meeting of the Executive Committee. |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | GUA | FOA | 60 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-10-01 | 2011-04-30 |  | 2012-03-01 | 2013-04-01 | 60000 | -364 | 59636 | 59635.53 | 100% | 0.47 | 0 |  | 4500 | -27 | 4473 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of demonstraton project in the methyl bromide sector | Individual | LAC | GUA | FUM | 21 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-03-01 | 1997-08-01 |  | 1999-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Demonstration project: four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization, and low-dose chemicals in combination with an IPM system | Individual | LAC | GUA | FUM | 22 | DEM | 15 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-07-01 | 440000 | -57777 | 382223 | 382222.67 | 100% | 0.33 | 0 |  | 57200 | -7590 | 49610 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase out of 800 tonnes in the methyl bromide sector (melon) | Individual | LAC | GUA | FUM | 29 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2002-04-01 | 2000-12-01 |  | 2002-12-01 | 2003-12-01 | 45000 | -1164 | 43836 | 43836.4 | 100% | -0.4 | 0 |  | 5850 | -160 | 5690 | 0 | 0 | FIN
FIN | UNIDO | National phase out of methyl bromide | Individual | LAC | GUA | FUM | 38 | INV | 29 | A | I | MBR | 502.6 | 502.6 |  |  | 2002-11-01 | 2003-03-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 3257377 | 0 | 3257377 | 3257376.85 | 100% | 0.15 | 0 |  | 368311 | 0 | 368311 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | INV | 38 | A | I | MBR | 48 | 48 |  |  | 2009-11-01 | 2010-12-01 | 2013-11-30 | 2015-12-01 |  |  | 1300000 | -210000 | 1090000 | 1024303.48 | 93.97% | 65696.52 | 651.89 | 3657.3 | 97500 | -15750 | 76823 | 4927 | 49 | - The 71st Meeting of the ExCom decided to penalize Guatemala due to deviation in 2012 data, and possible deviations in 2013 and 2014, which have been reported by UNIDO. - Refund was reported to 72nd Meeting of the ExCom, May 2014. - Based on the new budget in March 2014, a new plan of activities was prepared. However, in the meantime, the Government has already put in place the law to forbid the importation of MB in 2015 and thus, guarantee the compliance of the country. - The procurement of grafting facilities has been organized. - Training programme on grafting techniques started to be drafted. | - The supplier of the grafting facilities has been selected through the bidding procedure. - A training programme for the dissemination of grafting techniques to farmers, University and Research Centers has been prepared. However, due to forthcoming elections in the country, the plan has been slowed down. |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | LAC | GUA | FUM | 68 | INV | 46 | A | I | MBR | 217.7 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2014-12-31 | 2015-12-01 |  |  | 943047 | 0 | 943047 | 300751.52 | 31.89% | 642295.48 | 0 | 1000 | 70729 | 0 | 22556 | 48173 | 0 | - The 71st Meeting of the ExCom decided to penalize Guatemala due to deviation in 2012 data, and possible deviations in 2013 and 2014, which have been reported by UNIDO. - Based on the new budget in March 2014, a new plan of activities was prepared. However, in the meantime, the Government has already put in place the law to forbid the importation of MB in 2015 and thus, guarantee the compliance of the country. '- Refund was reported to 72nd Meeting of the ExCom, May 2014. - The procurement of grafting facilities has been organized. - Training programme on grafting techniques started to be drafted. | - The supplier of the grafting facilities has been selected through the bidding procedure. - A training programme for the dissemination of grafting techniques to farmers, University and Research Centers has been prepared. However, due to forthcoming elections in the country, the plan has been slowed down. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | GUA | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-07-01 | 2010-03-31 |  | 2012-03-01 | 2013-04-01 | 75000 | -1370 | 73630 | 73630.11 | 100% | -0.11 | 0 |  | 5625 | -103 | 5522 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 43 | A | I | HCFC | 1.7 | 1.7 |  |  | 2011-07-01 | 2012-10-01 | 2013-07-31 |  | 2013-07-01 | 2014-07-01 | 109637 | -348 | 109289 | 109289.01 | 100% | -0.01 | 0 |  | 8223 | -26 | 8197 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 44 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-06-01 | 2013-07-31 |  | 2013-07-01 | 2014-07-01 | 8450 | -18 | 8432 | 8431.63 | 100% | 0.37 | 0 |  | 634 | -1 | 632 | 1 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GUA | PHA | 68 | INV | 45 | A | I | HCFC | 0.6 | 0.6 |  |  | 2012-12-01 | 2013-07-01 | 2015-07-31 | 2015-09-01 |  |  | 97925 | 0 | 97925 | 84885.57 | 86.68% | 13039.43 | 10506.59 | 11000 | 7344 | 0 | 6366 | 978 | 787.9942 | - To distribute the tools to the training centers and start with the training program. - To continue with the training and certification program including the introduction of HC as alternative. - To commission the reclaiming unit purchased and start with the service for HCFC-22. - UNIDO mission took place in March 2014. Note: The conversion of FOGEL de CENTROAMERICA under UNIDO project was visited and the producer is producing only with cyclopentane, the HCFC-141b was phased-out in factory. The project has been successful. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: TOR prepared and reviewed, bidding. Milestone 3: Purchase and delivery of tools for training centres. Yes Milestone 4: Study tour focused on hydrocarbon and natural refrigerants. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment for training centres including a refrigerant reclaiming unit was delivered and training of technicians through workshops was carried out. - A reclaiming centre will be established in one of the training centres. - The training program to be implemented by UNEP is delayed. - A study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico. - A national expert was hired to help with the implementation of the project activities. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: TOR prepared and reviewed, bidding. Milestone 3: Purchase and delivery of tools for training centres. Yes Milestone 4: Study tour focused on hydrocarbon and natural refrigerants. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | GUA | PHA | 73 | TAS | 47 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2015-11-30 | 2015-11-01 |  |  | 30000 | 0 | 30000 | 4500 | 15% | 25500 | 0 | 20000 | 2700 | 0 | 405 | 2295 | 0 | Approved on the understanding that the verification report should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for its HPMP is being sought, in accordance with paragraph 5(b) of the agreement between Guatemala and the Executive Committee for the reduction of consumption of HCFCs. Planned completion date was changed as per Secretariat’s communication dated 11 February 2015. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | The verification report was carried out and submitted to the MLF together with the Second Tranche however the tranche was withdrawn due to the potential non-compliance and low disbursement of the Cooperating Agency. The verification report will be reviewed using the country data submitted to the Ozone Secretariat and resubmitted with the next tranche to the 75th Meeting of the ExCom. Milestones achieved: Milestone 1: Auditor selected and contracted. Yes Milestone 2: Verification report prepared and submitted. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | AFR | GUI | FOA | 21 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -8983 | 11017 | 11017 | 100% | 0 | 0 |  | 2600 | -1170 | 1430 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | GUI | PHA | 49 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-06-01 | 2009-03-01 | 15000 | -2888 | 12112 | 12111.6 | 100% | 0.4 | 0 |  | 1125 | -217 | 908 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | INV | 20 | A | I | CFC | 1.4 | 1.4 |  |  | 2008-07-01 | 2009-06-01 | 2009-12-31 |  | 2012-02-01 | 2013-04-01 | 140000 | -62 | 139938 | 139937.85 | 100% | 0.15 | 0 |  | 12600 | -6 | 12594 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | INV | 24 | A | I |  | 1.5 | 1.5 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2013-12-01 | 2013-12-01 | 60000 | -3523 | 56477 | 56476.78 | 100% | 0.22 | 0 |  | 5400 | -317 | 5083 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GUI | PHA | 66 | INV | 26 | A | I | HCFC | 1.2 | 0 |  |  | 2012-04-01 | 2013-05-01 | 2016-04-30 | 2015-12-01 |  |  | 160000 | 0 | 160000 | 153819.32 | 96.14% | 6180.68 | 0 | 1000 | 12000 | 0 | 11536 | 464 | 0 | - The NOU and UNIDO discussed the organization of a train-the-trainers sessions for technicians working in one of the three centers located outside Conakry (Kindia Region). Activities planned but not implemented, reasons and strategy: Train-the-trainers sessions could not be organized due to the constraints caused by the Ebola outbreak in the country. Actions towards next goals: As soon as the Ebola outbreak is under control, UNIDO will be in a position to support the NOU in the completion of UNIDO's component of Tranche I HPMP. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Ebola outbreak. Action plan: take action as soon as the outbreak is controlled. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date moved back to the original estimate. Any action required by Executive Committee? No | - The NOU and UNIDO are discussing the organization of a Customs training given the logistic challenges in the organization of the train-the-trainers sessions in Kindia province. Actions towards next goals: (-) Organization of the Customs training Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date moved to December 2015, which would be still ahead of original schedule. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | GUI | REF | 22 | TAS | 05 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-01 | 80780 | 0 | 80780 | 80780 | 100% | 0 | 0 |  | 10501 | 0 | 10501 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at a domestic refrigeration plant (Guyana Refrigeration Ltd.) | Individual | LAC | GUY | REF | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1995-09-01 |  | 1998-01-01 | 1999-08-01 | 15000 | -659 | 14341 | 14341 | 100% | 0 | 0 |  | 1950 | -89 | 1861 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Guyana Refrigerator Ltd., Guyana (GRL) | Individual | LAC | GUY | REF | 23 | INV | 05 | A | I | CFC | 7.2 | 7.2 |  |  | 1997-11-01 | 1998-08-01 | 1999-06-01 |  | 2001-04-01 | 2002-09-01 | 461000 | 0 | 461000 | 461000.01 | 100% | -0.01 | 0 |  | 59930 | -6 | 59924 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | HON | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1998-04-01 | 1997-05-01 |  | 2000-12-01 | 2001-09-01 | 30000 | -11403 | 18597 | 18597.21 | 100% | -0.21 | 0 |  | 3900 | -1486 | 2414 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | LAC | HON | FUM | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-03-01 | 2002-04-01 |  | 2002-11-01 | 2003-05-01 | 30000 | -482 | 29518 | 29517.96 | 100% | 0.04 | 0 |  | 3900 | -69 | 3831 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in melon and banana production sector and tobacco seedling | Individual | LAC | HON | FUM | 37 | INV | 10 | A | I | MBR | 213 | 213 |  |  | 2002-07-01 | 2002-11-01 | 2008-12-01 |  | 2006-12-01 | 2007-09-01 | 1977454 | -6 | 1977448 | 1977448.01 | 100% | -0.01 | 0 |  | 227519 | 0 | 227519 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (first tranche) | Multi-Year | LAC | HON | FUM | 50 | INV | 21 | A | I | MBR | 31.8 | 31.8 |  |  | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-09-01 | 2008-12-01 | 600000 | 0 | 600000 | 600000.02 | 100% | -0.02 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (second tranche) | Multi-Year | LAC | HON | FUM | 53 | INV | 24 | A | I | MBR | 47.5 | 47.5 |  |  | 2007-11-01 | 2007-12-01 | 2008-11-30 |  | 2009-10-01 | 2010-09-01 | 800000 | 0 | 800000 | 799999.95 | 100% | 0.05 | 0 |  | 60000 | 0 | 60000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (third tranche) | Multi-Year | LAC | HON | FUM | 56 | INV | 29 | A | I | MBR | 23.9 | 23.9 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-12-01 | 2012-05-01 | 300000 | -73 | 299927 | 299800.08 | 99.96% | 126.92 | 0 |  | 22500 | -5 | 22485 | 10 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (fourth tranche) | Multi-Year | LAC | HON | FUM | 59 | INV | 31 | A | I | MBR | 20.4 | 20.4 |  |  | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2011-12-01 | 2012-05-01 | 106301 | -45 | 106256 | 106255.65 | 100% | 0.35 | 0 |  | 7973 | -4 | 7969 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-09-01 | 2008-09-01 | 15000 | -95 | 14905 | 14904.8 | 100% | 0.2 | 0 |  | 1125 | -7 | 1118 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | INV | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-12-31 |  | 2010-12-01 | 2011-12-01 | 301000 | -224 | 300776 | 300771.18 | 100% | 4.82 | 0 |  | 22575 | -17 | 22558 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | HON | PHA | 55 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 115000 | -82 | 114918 | 114917.64 | 100% | 0.36 | 0 |  | 8625 | -6 | 8619 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | INV | 33 | A | I | CFC | 39.7 | 39.7 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 37500 | -271 | 37229 | 37228.69 | 100% | 0.31 | 0 |  | 2813 | -21 | 2792 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | INV | 34 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-09-01 | 2014-03-31 |  | 2014-07-01 |  | 100000 | 0 | 100000 | 96261.56 | 96.26% | 3738.44 | 3577.79 | 3578 | 7500 | 0 | 7220 | 280 | 268 | - The project was successfully completed in 2014. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - All project activities were successfully completed in 2014. - No activities were implemented during 2015. - Financial completion in 2015. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | HON | PHA | 70 | INV | 37 | A | I | HCFC | 1.2 | 0.8 |  |  | 2013-07-01 | 2013-09-01 | 2016-07-31 | 2015-12-01 |  |  | 90000 | 0 | 90000 | 63764.72 | 70.85% | 26235.28 | 20362.11 | 26000 | 6750 | 0 | 4782 | 1968 | 1527.1582 | - A new National Ozone Officer was designated, however the activities will continue as planned. - UNIDO mission took place in March 2014. - Purchase of tools for certified technicians and continuation with the programme for training and certification. - A study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico, the activity took place in September 2014. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: Study tour for local experts. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Since only little funding left on the project, a few activities like the purchase of some spare parts and tools were implemented. - A training of custom officers was organized in March 2015. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: Study tour for local experts. Yes Milestone 5: Purchase of additional tools. Yes Milestone 6: Training of custom officers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | HON | PHA | 73 | TAS | 39 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2016-05-30 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 4500 | 15% | 25500 | 0 | 20000 | 2700 | 0 | 405 | 2295 | 0 | Approved on the understanding that the verification report should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for its HPMP is being sought, in accordance with paragraph 5(b) of the agreement between Honduras and the Executive Committee for the reduction of consumption of HCFCs. Planned completion date was changed as per Secretariat’s communication dated 11 February 2015. Was there any delay during the reporting year?: Yes Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | The report was prepared during the first quarter 2015 and will be reviewed and updated to be submitted with the respective tranche to the 76th Meeting of the ExCom. Was there any delay during the reporting year?: Yes Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | HON | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-11-01 | 2000-07-01 | 30000 | -7251 | 22749 | 22749 | 100% | 0 | 0 |  | 3900 | -947 | 2953 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | LAC | HON | REF | 28 | TAS | 07 | A | I | CFC | 14.2 | 14.2 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 245900 | -951 | 244949 | 244949.04 | 100% | -0.04 | 0 |  | 31967 | -174 | 31793 | 0 | 0 | FIN |  |  | 2003-06-01 | INV
FIN | UNIDO | Refrigerant management plan: customs training | RMP | LAC | HON | REF | 28 | TRA | 05 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2002-04-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 38250 | 0 | 38250 | 38250 | 100% | 0 | 0 |  | 4973 | 0 | 4973 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | LAC | HON | REF | 28 | TRA | 06 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out ODS at PT Naviri Kencana Perdana | Individual | ASP | IDS | FOA | 19 | INV | 43 | A | I | CFC | 47.8 | 47.8 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 377382 | -402 | 376980 | 376980 | 100% | 0 | 0 |  | 49060 | -130 | 48930 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Winnerfoam Abadi | Individual | ASP | IDS | FOA | 22 | INV | 56 | A | I | CFC | 40 | 40 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 79472 | -1287 | 78185 | 78185 | 100% | 0 | 0 |  | 10331 | -183 | 10148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Panca Duta foam industry | Individual | ASP | IDS | FOA | 22 | INV | 57 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2001-12-01 | 86955 | -621 | 86334 | 86334.05 | 100% | -0.05 | 0 |  | 11304 | -98 | 11206 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Elastino Satyajaya flexible polyurethane foam plant | Individual | ASP | IDS | FOA | 22 | INV | 58 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 75943 | 0 | 75943 | 75943 | 100% | 0 | 0 |  | 9873 | -5 | 9868 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IDS | FOA | 27 | PRP | 109 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2002-01-01 | 2003-05-01 | 50000 | -177 | 49823 | 49822.81 | 100% | 0.19 | 0 |  | 6500 | -33 | 6467 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Nirwana in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 110 | A | I | CFC | 32.6 | 32.6 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 206911 | 0 | 206911 | 206911.12 | 100% | -0.12 | 0 |  | 26898 | -27 | 26871 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Meta Presindo Utama in the manufacture of polyurethane integral skin and moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 113 | A | I | CFC | 21.8 | 21.8 |  |  | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 213603 | 0 | 213603 | 213603.43 | 100% | -0.43 | 0 |  | 27768 | -15 | 27753 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown technology in the manufacturing of polyurethane integral skin shoe soles at P.T. Trias Rantai Mas | Individual | ASP | IDS | FOA | 31 | INV | 119 | A | I | CFC | 18.4 | 18.4 |  |  | 2000-07-01 | 2000-11-01 | 2003-01-01 |  | 2003-01-01 | 2003-12-01 | 141319 | 0 | 141319 | 141319.29 | 100% | -0.29 | 0 |  | 18371 | 0 | 18371 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 122 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -2204 | 22796 | 22796.41 | 100% | -0.41 | 0 |  | 3250 | -291 | 2959 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of integral skin automotive parts at PT Wulansari Raharja | Individual | ASP | IDS | FOA | 36 | INV | 141 | A | I | CFC | 10.8 | 10.8 |  |  | 2002-03-01 | 2004-02-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 101301 | -632 | 100669 | 100668.52 | 100% | 0.48 | 0 |  | 13169 | -103 | 13066 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid insulation foam parts at two companies: PT Morodadi Prima and PT Tentrem Industri Karosseri | Individual | ASP | IDS | FOA | 36 | INV | 143 | A | I | CFC | 25.5 | 25.5 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-11-01 | 2007-04-01 | 164947 | -567 | 164380 | 164379.96 | 100% | 0.04 | 0 |  | 21443 | -74 | 21369 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT Solindah Kita | Individual | ASP | IDS | FOA | 36 | INV | 144 | A | I | CFC | 48 | 48 |  |  | 2002-03-01 | 2002-08-01 | 2004-09-01 |  | 2005-12-01 | 2006-12-01 | 390760 | -5753 | 385007 | 385007.42 | 100% | -0.42 | 0 |  | 50799 | -748 | 50051 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT. Accurai | Individual | ASP | IDS | FOA | 37 | INV | 147 | A | I | CFC | 50 | 50 |  |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2005-06-01 | 2006-09-01 | 523943 | -656 | 523287 | 523287.38 | 100% | -0.38 | 0 |  | 67634 | -72 | 67562 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project to phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Ganesha Rattesko and Sindari Nusatama | Individual | ASP | IDS | FOA | 38 | INV | 150 | A | I | CFC | 52 | 52 |  |  | 2002-11-01 | 2003-12-01 | 2005-06-01 |  | 2005-12-01 | 2006-12-01 | 283490 | -101 | 283389 | 283389.34 | 100% | -0.34 | 0 |  | 36854 | -13 | 36841 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Delta Atlantik and Samudra Plastics | Individual | ASP | IDS | FOA | 38 | INV | 152 | A | I | CFC | 18.8 | 18.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2004-11-01 | 2006-05-01 | 146388 | 0 | 146388 | 146387.89 | 100% | 0.11 | 0 |  | 19030 | -10 | 19020 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector (tobacco, tomatoes, pepper) | Individual | ASP | IDS | FUM | 23 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 1998-09-01 | 2001-07-01 | 10000 | 17659 | 27659 | 27659 | 100% | 0 | 0 |  | 1300 | 2290 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in store products (rice, coffee and corn) | Individual | ASP | IDS | FUM | 26 | DEM | 94 | A | I |  | 0 | 0 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-12-01 | 2003-10-01 | 332200 | -5985 | 326215 | 326214.65 | 100% | 0.35 | 0 |  | 43186 | -845 | 42341 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the fumigant (methyl bromide) sector in TPO-grain fumigation | Individual | ASP | IDS | FUM | 36 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 44 | INV | 168 | A | I | MBR | 37.8 | 37.8 |  |  | 2004-12-01 | 2005-04-01 | 2007-12-01 |  | 2008-09-01 | 2009-09-01 | 350000 | -372 | 349628 | 349628.38 | 100% | -0.38 | 0 |  | 26250 | -28 | 26222 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a sector phase-out plan in process agents sector | Individual | ASP | IDS | PAG | 36 | PRP | 140 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-12-01 | 2004-12-01 | 60000 | -1890 | 58110 | 58109.61 | 100% | 0.39 | 0 |  | 7800 | -258 | 7542 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (Umbrella project to phase-out HCFC-141b from the manufacturing of rigid polyurethane foam at Isotech Jaya Makmur, Airtekindo, Sinar Lentera Kencana and Mayer Jaya) | Multi-Year | ASP | IDS | PHA | 64 | INV | 194 | A | I | HCFC | 10.4 | 10.4 |  |  | 2011-07-01 | 2012-02-01 | 2012-03-31 | 2015-12-01 |  |  | 777395 | 0 | 777395 | 10559.22 | 1.358% | 766835.78 | 722208.7 | 350000 | 58305 | 0 | 792 | 57513 | 54166 | - Competitive bidding resumed; - Counterparts cost sharing to be quantified after evaluation of the offers. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - No Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: Works towards milestones No 5 through 7; main reason - delayed Government's signature of the project. Project approved in July 2011; Government's clearance, 28 June 2013; UNIDO received, 16 July 2013; strategy: strictly follow procurement procedures to catch-up. Actions towards next goals: execution of repeated bidding Was there any delay during the reporting year? No If yes, reasons and action plan: (narrative): Any recurring problem? No Any impact on project completion date: Yes If yes, implications: impossible to shorten initial delay; completion will be very likely delayed. Any action required by Executive Committee? No | - The reason for low disbursement is that no payment for equipment could have been effected, since the equipment was not yet at the site, despite PO delivery term January 2015. - However equipment for two beneficiaries reached Indonesia; not yet cleared from customs due to lengthy procedures for tax exemption at the Government side. - Shipment for other two beneficiaries underway, to reach Indonesia by September 2015. Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Partially Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: Works towards milestones No 5 through 7; main reason - delayed Government's signature of the project. Project approved in July 2011; Government's clearance, 28 June 2013; UNIDO received the clearance, 16 July 2013; Strategy: strictly follow procurement procedures to catch-up. Actions towards next goals: accomplishment of the contract, fulfillment of supplier's commitments. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delivery of equipment delayed, due to supplier's delay and Government import bureaucracy. Plan: UNIDO's careful coordination among supplier of equipment, counterparts and the NOU. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: impossible to shorten initial delay; completion is expected by the end of 2015. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
FIN | UNIDO | Phasing out of ODS at P.T. Air Tech. Co. Ltd. | Individual | ASP | IDS | REF | 18 | INV | 35 | A | I | CFC | 30.1 | 30.1 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-05-01 | 409850 | 0 | 409850 | 409850 | 100% | 0 | 0 |  | 53281 | 0 | 53281 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at P.T. Jalur Sejuk | Individual | ASP | IDS | REF | 22 | INV | 59 | A | I | CFC | 30.85 | 30.85 |  |  | 1997-05-01 | 1997-09-01 | 1998-11-01 |  | 1999-06-01 | 2001-07-01 | 171470 | 0 | 171470 | 171470 | 100% | 0 | 0 |  | 22291 | -17 | 22274 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Project formulation for phasing out ODS in small and medium scale industries | Individual | ASP | IDS | SEV | 15 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-01-01 | 2002-05-01 | 80000 | -2803 | 77197 | 77197.25 | 100% | -0.25 | 0 |  | 10400 | -380 | 10020 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project formulation of investment projects in the aerosol and foam sectors | Individual | ASP | IDS | SEV | 21 | PRP | 54 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 2000-10-01 | 2001-07-01 | 20000 | -4478 | 15522 | 15522 | 100% | 0 | 0 |  | 2600 | -585 | 2015 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of an investment project for phasing out ODS at three enterprises including the companies Nirwana and P.T. Success | Individual | ASP | IDS | SEV | 23 | PRP | 64 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-10-01 | 2001-07-01 | 10000 | 9025 | 19025 | 19024.96 | 100% | 0.04 | 0 |  | 1300 | 1169 | 2469 | 0 | 0 | FIN
FIN | UNIDO | Plan for terminal phase-out of ODS in the solvent sector | Multi-Year | ASP | IDS | SOL | 44 | INV | 162 | A | I | CFC CTC TCA | 100.1 | 100.1 |  |  | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-10-01 | 2009-09-01 | 1464733 | -670 | 1464063 | 1464062.74 | 100% | 0.26 | 0 |  | 108974 | -50 | 108924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | ASP | IDS | SOL | 61 | PRP | 190 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-05-01 | 10000 | -353 | 9647 | 9647.1 | 100% | -0.1 | 0 |  | 750 | -26 | 724 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Preparation of umbrella project for ODS phase out in the Aerosol sector (small-scale industries) | Individual | ASP | IND | ARS | 18 | PRP | 53 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-05-01 |  |  | 1997-06-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
CLO | UNIDO | Preparation of an investment project in the fumigant sector | Individual | ASP | IND | FUM | 39 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2004-07-01 | 2004-04-01 |  |  | 2005-12-01 | 35000 | -34038 | 962 | 962.37 | 100% | -0.37 | 0 |  | 2625 | -2553 | 72 | 0 | 0 | CLO
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to trichloromethane at M/S Alpha Drugs India Ltd., Patiala | Individual | ASP | IND | PAG | 32 | INV | 283 | A | I | CTC | 69.7 | 69.7 |  |  | 2000-12-01 | 2001-11-01 | 2002-06-01 |  | 2003-03-01 | 2004-04-01 | 145866 | -130 | 145736 | 145735.54 | 100% | 0.46 | 0 |  | 15453 | -38 | 15415 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Svis Labs Ltd., Ranipet | Individual | ASP | IND | PAG | 32 | INV | 284 | A | R | CTC | 54.2 | 54.2 |  |  | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 249547 | 0 | 249547 | 249547.11 | 100% | -0.11 | 0 |  | 25352 | -9 | 25343 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Satya Deeptha Pharmaceuticals Ltd., Humnabad | Individual | ASP | IND | PAG | 32 | INV | 287 | A | I | CTC | 27.9 | 27.9 |  |  | 2000-12-01 | 2001-11-01 | 2002-07-01 |  | 2002-12-01 | 2004-12-01 | 260133 | -659 | 259474 | 259473.58 | 100% | 0.42 | 0 |  | 33817 | -139 | 33678 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Doctors Organic Chemicals Ltd., Tanuku | Individual | ASP | IND | PAG | 32 | INV | 291 | A | I | CTC | 94.6 | 94.6 |  |  | 2000-12-01 | 2002-01-01 | 2002-06-01 |  | 2002-12-01 | 2003-12-01 | 288809 | -171 | 288638 | 288638.31 | 100% | -0.31 | 0 |  | 37545 | -82 | 37463 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the process agent (pharmaceutical) sector | Individual | ASP | IND | PAG | 33 | PRP | 302 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-10-01 |  | 2003-10-01 | 2004-09-01 | 70000 | -5813 | 64187 | 64186.69 | 100% | 0.31 | 0 |  | 9100 | -769 | 8331 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | Individual | ASP | IND | PAG | 34 | INV | 303 | A | I | CTC | 23 | 23 |  |  | 2001-07-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 136786 | -3906 | 132880 | 132880.22 | 100% | -0.22 | 0 |  | 17782 | -508 | 17274 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at Praddep Shetye Ltd., Alibagh | Individual | ASP | IND | PAG | 34 | INV | 311 | A | I | CTC | 133.9 | 133.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 279001 | -10 | 278991 | 278991.21 | 100% | -0.21 | 0 |  | 36270 | -1 | 36269 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to ethylene dichloride at Chiplun Fine Chemicals Ltd., Ratnagiri | Individual | ASP | IND | PAG | 34 | INV | 313 | A | I | CTC | 16.7 | 16.7 |  |  | 2001-07-01 | 2002-02-01 | 2003-02-01 |  | 2003-07-01 | 2004-09-01 | 155830 | 0 | 155830 | 155829.82 | 100% | 0.18 | 0 |  | 20258 | -2 | 20256 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | Individual | ASP | IND | PAG | 34 | INV | 314 | A | I | CTC | 34.1 | 34.1 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2008-05-01 | 238371 | -191 | 238180 | 238179.69 | 100% | 0.31 | 0 |  | 30988 | -25 | 30963 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at GRD Chemicals Ltd., Indore, M.P. | Individual | ASP | IND | PAG | 34 | INV | 316 | A | I | CTC | 17.9 | 17.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-04-01 | 127667 | 0 | 127667 | 127667.03 | 100% | -0.03 | 0 |  | 16597 | -9 | 16588 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to cyclohexane at Amoli Organics Ltd., Mumbai | Individual | ASP | IND | PAG | 35 | INV | 338 | A | I | CTC | 38.5 | 38.5 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-08-01 | 2007-01-01 | 385367 | -1454 | 383913 | 383912.67 | 100% | 0.33 | 0 |  | 50098 | -189 | 49909 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 385 | A | I | CTC | 733 | 733 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2013-12-01 | 2014-08-01 | 3500000 | -79643 | 3420357 | 3420356.44 | 100% | 0.56 | 0 |  | 262500 | -5973 | 256527 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | CTC phase-out for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 402 | A | I | CTC | 347 | 347 | 347 |  | 2006-07-01 | 2007-06-01 | 2007-07-01 |  | 2013-12-01 | 2013-12-01 | 399046 | -150288 | 248758 | 248757.82 | 100% | 0.18 | 0 |  | 29928 | -11272 | 18657 | -1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (transportation refrigeration and air-conditioning sectors) | Individual | ASP | IND | PHA | 56 | PRP | 427 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-05-01 | 2011-05-01 | 70000 | -170 | 69830 | 69829.97 | 100% | 0.03 | 0 |  | 5250 | -13 | 5237 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Feasibility study for recovery/recycling of CFC refrigerants | RMP | ASP | IND | REF | 10 | TAS | 05 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-02-01 | 1993-10-01 |  | 1998-06-01 | 1999-08-01 | 55000 | -42920 | 12080 | 12080 | 100% | 0 | 0 |  | 7150 | -5582 | 1568 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project for phasing out ODS in the refrigeration sector (project under identification | Individual | ASP | IND | REF | 23 | PRP | 159 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2002-05-01 | 25000 | 24369 | 49369 | 49369.43 | 100% | -0.43 | 0 |  | 3250 | 3158 | 6408 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 30 | PRP | 248 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 20000 | -703 | 19297 | 19297.01 | 100% | -0.01 | 0 |  | 2600 | -95 | 2505 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | Individual | ASP | IND | REF | 32 | INV | 290 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-01-01 | 2003-02-01 |  | 2004-08-01 | 2005-09-01 | 328894 | -49284 | 279610 | 279609.93 | 100% | 0.07 | 0 |  | 42756 | -6464 | 36292 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 36 | PRP | 346 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-04-01 |  | 2003-09-01 | 2004-09-01 | 30000 | -4889 | 25111 | 25111.42 | 100% | -0.42 | 0 |  | 3900 | -641 | 3259 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | Multi-Year | ASP | IND | REF | 38 | INV | 359 | A | I | CFC | 40 | 59 |  |  | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2006-11-01 | 2007-12-01 | 500000 | 0 | 500000 | 499999.63 | 100% | 0.37 | 0 |  | 65000 | 0 | 65000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 366 | A | I | CFC | 67 | 77 |  |  | 2003-12-01 | 2006-10-01 | 2005-12-01 |  | 2007-03-01 | 2009-12-01 | 173200 | -35 | 173165 | 173164.63 | 100% | 0.37 | 0 |  | 19052 | -4 | 19048 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation for phasing out ODS in the unorganized sector | Individual | ASP | IND | SEV | 10 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-05-01 | 1993-10-01 |  | 1999-12-01 | 2000-09-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project formulation for the conversion of electronic cleaning processes from CFC-113/alcohol blended and 1,1,1 trichlorethane to non-CFC cleaning | Individual | ASP | IND | SOL | 10 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-10-01 | 1993-10-01 |  | 1998-12-01 | 2000-07-01 | 74000 | -332 | 73668 | 73668 | 100% | 0 | 0 |  | 9620 | -58 | 9562 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents aqueous cleaning at ITI Mankapur | Individual | ASP | IND | SOL | 13 | INV | 25 | A | I | CFC | 34 | 48.8 |  |  | 1994-07-01 | 1996-06-01 | 1996-01-01 |  | 1996-10-01 | 2000-12-01 | 610160 | 0 | 610160 | 610160 | 100% | 0 | 0 |  | 79321 | -2 | 79319 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes for ODS solvents to non-clean and hydrocarbon cleaning technologies at ERL-Bangalore | Individual | ASP | IND | SOL | 18 | INV | 65 | A | I | CFC TCA | 16.4 | 16.4 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2000-12-01 | 192421 | -1899 | 190522 | 190522 | 100% | 0 | 0 |  | 25015 | -286 | 24729 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to no-clean and aqueous photo resist developing and stripping technologies at ITI Palakkad | Individual | ASP | IND | SOL | 18 | INV | 66 | A | I | CFC TCA | 15 | 15 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1998-08-01 | 235744 | 5652 | 241396 | 241396 | 100% | 0 | 0 |  | 30647 | 734 | 31381 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to semi-aqueous cleaning and no-clean soldering technologies at ITI, Bangalore | Individual | ASP | IND | SOL | 19 | INV | 95 | A | I | CFC TCA | 7 | 7 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1996-12-01 | 1999-08-01 | 107954 | -808 | 107146 | 107146 | 100% | 0 | 0 |  | 14034 | -127 | 13907 | 0 | 0 | FIN
FIN | UNIDO | Preparation investment projects in the solvent (CFC 113) sector at Harbans Lal Mahotra & Sons Ltd. Calcutta | Individual | ASP | IND | SOL | 24 | PRP | 162 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 25000 | -177 | 24823 | 24822.7 | 100% | 0.3 | 0 |  | 3250 | -28 | 3222 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS solvents to heat cleaning technologies and ODS free solvent coating at Malhotra Shaving Products Ltd. | Individual | ASP | IND | SOL | 25 | INV | 181 | A | I | CFC | 13.6 | 13.6 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-01-01 | 255112 | 0 | 255112 | 255111.63 | 100% | 0.37 | 0 |  | 33165 | 0 | 33165 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS to heat cleaning technologies and ODS free solvent coating at Lal Malhotra & Sons Ltd. | Individual | ASP | IND | SOL | 26 | INV | 191 | A | I | CFC | 16 | 16 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 308899 | 0 | 308899 | 308899.16 | 100% | -0.16 | 0 |  | 40157 | -8 | 40149 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the solvent sector | Individual | ASP | IND | SOL | 27 | PRP | 195 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-07-20 | 2000-11-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 and CTC to processes based on IPA at Vidyut Metallics Ltd. (VML) | Individual | ASP | IND | SOL | 28 | INV | 223 | A | I | CFC CTC | 19.7 | 19.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2003-09-01 | 2004-06-01 | 225452 | -387 | 225065 | 225064.66 | 100% | 0.34 | 0 |  | 29309 | -97 | 29212 | 0 | 0 | FIN |  |  | 2002-03-01
FIN | UNIDO | Conversion of cleaning processes from TCA and CTC to non-ODS solvent cleaning technologies (trichloroethylene and alkozypropanol) at Videocon Group (VDC) | Individual | ASP | IND | SOL | 28 | INV | 225 | A | I | CTC TCA | 7.2 | 7.2 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2002-01-01 | 2003-03-01 | 234978 | -4 | 234974 | 234973.65 | 100% | 0.35 | 0 |  | 30547 | -49 | 30498 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 to IPA and xylene at Microraj Electronics PVT Ltd. & RCC (Sales) PVT ltd., Hyderabad (MRJ) | Individual | ASP | IND | SOL | 28 | INV | 230 | A | I | CFC | 4.3 | 4.3 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2001-11-01 | 2002-12-01 | 85431 | -431 | 85000 | 85000.01 | 100% | -0.01 | 0 |  | 11106 | -74 | 11032 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Blue Star Ltd., Thane | Individual | ASP | IND | SOL | 31 | INV | 266 | A | I | CTC | 6.6 | 6.6 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-12-01 | 2003-10-01 | 76027 | 0 | 76027 | 76027 | 100% | 0 | 0 |  | 9884 | 0 | 9884 | 0 | 0 | FIN
FIN | UNIDO | Formulation of CTC process cleaning agent project in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 264 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2002-03-01 | 2003-05-01 | 20000 | -261 | 19739 | 19739 | 100% | 0 | 0 |  | 2600 | -38 | 2562 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for SMEs in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2002-04-01 |  | 2003-06-01 | 2003-06-01 | 30000 | -29 | 29971 | 29971.09 | 100% | -0.09 | 0 |  | 3900 | -10 | 3890 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Engineering, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 306 | A | I | CTC | 14.5 | 14.5 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 240435 | 0 | 240435 | 240434.89 | 100% | 0.11 | 0 |  | 31257 | -19 | 31238 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Engineer Industries, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 308 | A | I | CTC | 20.2 | 20.2 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 238776 | 0 | 238776 | 238775.51 | 100% | 0.49 | 0 |  | 31041 | -9 | 31032 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Coils Ltd., Palghar | Individual | ASP | IND | SOL | 34 | INV | 327 | A | I | CTC | 22.8 | 22.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 245024 | 0 | 245024 | 245023.89 | 100% | 0.11 | 0 |  | 31853 | -19 | 31834 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the solvent (CFC-113) sector | Individual | ASP | IND | SOL | 36 | PRP | 347 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-04-01 | 2004-04-01 | 30000 | -479 | 29521 | 29521.01 | 100% | -0.01 | 0 |  | 3900 | -68 | 3832 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Navdeep Engineering, Palghar | Individual | ASP | IND | SOL | 38 | INV | 354 | A | I | CTC | 53.9 | 53.9 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-12-01 | 2007-01-01 | 661842 | -1087 | 660755 | 660754.55 | 100% | 0.45 | 0 |  | 82803 | -120 | 82683 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-113 as cleaning solvent to TCE at Bharat Electronics Limited (BEL), Bangalore | Individual | ASP | IND | SOL | 40 | INV | 362 | A | I | CFC | 16 | 16 |  |  | 2003-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-12-01 | 2006-12-01 | 151291 | -684 | 150607 | 150606.61 | 100% | 0.39 | 0 |  | 13616 | -61 | 13555 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an MDI project | Individual | ASP | IRA | ARS | 47 | PRP | 173 | A | I |  |  | 0 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2008-04-01 | 2008-09-01 | 70000 | 0 | 70000 | 69999.9 | 100% | 0.1 | 0 |  | 5250 | 0 | 5250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | ASP | IRA | ARS | 52 | INV | 183 | A | I | CFC | 96.4 | 96.4 |  |  | 2007-07-01 | 2007-12-01 | 2010-09-30 |  | 2010-12-01 | 2012-12-01 | 3529508 | -233499 | 3296009 | 3296009.14 | 100% | -0.14 | 0 |  | 264713 | -17512 | 247201 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | DBL project Iran. Phasing out CFC-11 through conversion of rigid PU-foam manufactured with the technique of continuous lamination at Fabis, Iran Steel, Mammoth Tehran, F.M., and Urethane Systems | Individual | ASP | IRA | FOA | 17 | INV | 11 | A | I | CFC | 1200 | 1200 |  |  | 1995-07-01 | 1995-12-01 | 1997-07-01 |  | 1998-12-01 | 2003-05-01 | 2571250 | 0 | 2571250 | 2571249.92 | 100% | 0.08 | 0 |  | 334263 | -361 | 333902 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Safoam Co. | Individual | ASP | IRA | FOA | 22 | INV | 20 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 2002-12-01 | 2003-12-01 | 487125 | 0 | 487125 | 487125.1 | 100% | -0.1 | 0 |  | 63326 | -85 | 63241 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Urethane Systems Company (USC) | Individual | ASP | IRA | FOA | 22 | INV | 21 | A | I | CFC | 110 | 110 |  |  | 1997-05-01 | 2001-09-01 | 1998-06-01 |  | 2003-03-01 | 2004-02-01 | 487125 | -4690 | 482435 | 482435.39 | 100% | -0.39 | 0 |  | 63326 | -709 | 62617 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 from flexible slabstock foam manufacturing at Shizar Co. | Individual | ASP | IRA | FOA | 22 | INV | 22 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2003-12-01 | 2004-12-01 | 487125 | 0 | 487125 | 487124.7 | 100% | 0.3 | 0 |  | 63326 | 0 | 63326 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Mashhad Foam | Individual | ASP | IRA | FOA | 23 | INV | 29 | A | I | CFC | 90 | 90 |  |  | 1997-11-01 | 1999-01-01 | 1998-12-01 |  | 2003-12-01 | 2004-12-01 | 503330 | -1856 | 501474 | 501473.82 | 100% | 0.18 | 0 |  | 65433 | -345 | 65088 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Preparation of an investment project in the foam sector for phasing out ODS at three enterprises including Bahaman Plastic | Individual | ASP | IRA | FOA | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-06-01 |  | 2000-09-01 | 2001-07-01 | 10000 | -2561 | 7439 | 7439 | 100% | 0 | 0 |  | 1300 | -334 | 966 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IRA | FOA | 27 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 18000 | -1160 | 16840 | 16839.62 | 100% | 0.38 | 0 |  | 2340 | -154 | 2186 | 0 | 0 | FIN
CLO | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | Individual | ASP | IRA | FOA | 28 | INV | 50 | A | I | CFC | 83 | 83 |  |  | 1999-07-01 | 2000-11-01 | 2001-02-01 |  |  | 2009-05-01 | 485929 | -5381 | 480548 | 480548.04 | 100% | -0.04 | 0 |  | 63171 | -700 | 62471 | 0 | 0 | CLO |  |  | 2002-06-01
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | Individual | ASP | IRA | FOA | 31 | INV | 73 | A | I | CFC | 70 | 70 |  |  | 2000-07-01 | 2001-04-01 | 2003-01-01 |  | 2005-07-01 | 2005-12-01 | 539882 | 0 | 539882 | 539882.07 | 100% | -0.07 | 0 |  | 69387 | -79 | 69308 | 0 | 0 | FIN
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | ASP | IRA | FOA | 34 | PRP | 106 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 20000 | -840 | 19160 | 19160.19 | 100% | -0.19 | 0 |  | 2600 | -113 | 2487 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out ODS in the manufacture of flexible slab stock foam through the use of LCD blowing technology at Abre Shomal Co. | Individual | ASP | IRA | FOA | 35 | INV | 115 | A | I | CFC | 90.4 | 90.4 |  |  | 2001-12-01 | 2002-06-01 | 2003-07-01 |  | 2004-03-01 | 2005-08-01 | 552148 | -50609 | 501539 | 501538.52 | 100% | 0.48 | 0 |  | 70736 | -5654 | 65082 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Formulation of two umbrella investment projects in the rigid and flexible foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 148 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2003-10-01 | 2004-07-01 | 35000 | -557 | 34443 | 34442.85 | 100% | 0.15 | 0 |  | 4550 | -80 | 4470 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | Individual | ASP | IRA | FOA | 37 | INV | 149 | A | I | CFC | 91.1 | 91.1 |  |  | 2002-07-01 | 2002-11-01 | 2004-03-01 |  | 2008-12-01 | 2009-03-01 | 373515 | 0 | 373515 | 373514.99 | 100% | 0.01 | 0 |  | 48557 | 0 | 48557 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Yakhchavan Co. | Individual | ASP | IRA | FOA | 37 | INV | 155 | A | I | CFC | 73.6 | 73.6 |  |  | 2002-07-01 | 2002-11-01 | 2005-03-01 |  | 2005-12-01 | 2008-12-01 | 531838 | -7193 | 524645 | 524645.32 | 100% | -0.32 | 0 |  | 68502 | -791 | 67711 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | IRA | FUM | 23 | PRP | 33 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | Individual | ASP | IRA | FUM | 29 | INV | 57 | A | I | MBR | 12.4 | 12.4 |  |  | 1999-11-01 | 2000-04-01 | 2001-12-01 |  | 2006-12-01 | 2009-03-01 | 260698 | -15748 | 244950 | 244950.15 | 100% | -0.15 | 0 |  | 33891 | -2047 | 31844 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in soil fumigation | Individual | ASP | IRA | FUM | 33 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  |  | 2003-05-01 | 25000 | -19845 | 5155 | 5155 | 100% | 0 | 0 |  | 3250 | -2581 | 669 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries) | Individual | ASP | IRA | FUM | 44 | PRP | 168 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 9830 | -1250 | 8580 | 8579.53 | 99.99% | 0.47 | 0 |  | 737 | -93 | 643 | 1 | 0 | FIN
FIN | UNIDO | Total phase-out of methyl bromide in soil fumigation in olive seedings, fruit trees, nurseries and others | Individual | ASP | IRA | FUM | 47 | INV | 175 | A | I | MBR | 14.4 | 14.4 |  |  | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2008-12-01 | 2009-12-01 | 227950 | -107 | 227843 | 227842.61 | 100% | 0.39 | 0 |  | 20516 | -10 | 20506 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Halon phase-out project (Transfer from France) | Individual | ASP | IRA | HAL | 63 | TAS | 198 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-11-01 | 2012-04-01 | 2015-12-01 |  |  | 397500 | 0 | 397500 | 271276.87 | 68.25% | 126223.13 | 25227.4 | 50000 | 29813 | 0 | 20346 | 9467 | 1892 | By early 2014 the following project activities were implemented: '- Complete custom clearance, '- Equipment has been delivered and installed at beneficiary and the related training has been organized. | The project was extended until December 2015 at the 74th ExCom Meeting and it is being implemented according to the new schedule. The contract for the management of the halons bank has been issued. |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (first tranche of implementation plan 2004) | Multi-Year | ASP | IRA | PHA | 41 | INV | 162 | A | I | CFC | 274.1 | 274.1 |  |  | 2003-12-01 | 2004-03-01 | 2005-04-01 |  | 2005-12-01 | 2007-12-01 | 361840 | 2104066 | 2465906 | 2465905.96 | 100% | 0.04 | 0 |  | 27138 | 157805 | 184943 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 170 | A | I | CFC | 115.5 | 115.5 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 742449 | -52 | 742397 | 742396.93 | 100% | 0.07 | 0 |  | 55684 | -4 | 55680 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 177 | A | I | CFC | 230 | 230 |  |  | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2008-12-01 | 66224 | -549 | 65675 | 65675.33 | 100% | -0.33 | 0 |  | 4967 | -41 | 4926 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | TRA | 182 | A | I |  | 0 | 66.6 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-04-01 | 2009-03-01 | 36179 | -1894 | 34285 | 34284.79 | 100% | 0.21 | 0 |  | 2713 | -142 | 2571 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | IRA | PHA | 63 | INV | 202 | A | I | HCFC | 32.1 | 0 |  |  | 2011-04-01 | 2011-08-01 | 2015-03-31 | 2015-12-01 |  |  | 1300000 | 0 | 1300000 | 916404.59 | 70.49% | 383595.41 | 365286.93 | 300000 | 97500 | 0 | 68730 | 28770 | 27397 | Four out of seven machines delivered to beneficiaries by March 2014. | All equipment is delivered to all beneficiaries. Five machines installed and commissioned, two machines yet to be installed. The installation is expected to be completed by October 2015. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 209 | A | I | HCFC | 11.9 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 | 2015-12-01 |  |  | 830000 | 0 | 830000 | 156334.79 | 18.84% | 673665.21 | 251868.75 | 250000 | 62250 | 0 | 11725 | 50525 | 18890.1562 | A new action plan was submitted to the 72nd Meeting of the ExCom for implementation during the 3rd and 4th Q 2014. Equipment delivery for Paya Telecommunication tis in progress. | - Equipment for Paya Telecommunication delivered, installed and commissioned, '- The procurement of equipment completed for Emersun, but waiting for Security Council Committee clearance since March 2015 to issue the purchase order |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 72 | INV | 215 | A | I | HCFC | 1.2 | 0 |  |  | 2014-05-01 |  | 2016-05-31 | 2016-05-01 |  |  | 101450 | 0 | 101450 | 0 | 0% | 101450 | 0 | 40000 | 7609 | 0 | 0 | 7609 | 0 | Approved at the 72nd Meeting of the ExCom in May 2014 with the understanding that the approved funds will not be transferred to UNDP and UNIDO until the Secretariat has received a verification report confirming that the Government of the Islamic Republic of Iran was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. Noted the change in the foam sector plan proposed by UNIDO and that the amount of US $97,127 associated to one non-eligible foam enterprise (Nobough) will be reallocated to the three new eligible enterprises manufacturing insulation foam for domestic refrigerators added to stage I, but its tonnage reduction (3.8 ODP tonnes) will continue to be deducted from the starting point; that the Government of the Islamic Republic of Iran commits to reduce its HCFC consumption by 30 per cent of the baseline by 1 January 2018; and that the Agreement was updated based on the revised sector plan submitted by UNIDO. Additional 63.1 ODP tonnes from the remaining eligible consumption would be deducted. | Verification report submitted and approved at the 73rd Meeting of the ExCom. '- Procurement of equipment completed. '- Part of the funds to be used for the company Emersun, waiting for Security Council Committee clearance for issuing the purchase order. |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in domestic refrigeration industry | Individual | ASP | IRA | REF | 09 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-06-01 |  | 1996-05-01 | 1998-08-01 | 50000 | 13633 | 63633 | 63633 | 100% | 0 | 0 |  | 6500 | 1772 | 8272 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase-out CFC-11 and CFC-12 | Individual | ASP | IRA | REF | 11 | INV | 08 | A | I | CFC | 757 | 757 |  |  | 1993-11-01 | 1994-12-01 | 1995-11-01 |  | 1997-12-01 | 2002-09-01 | 3228395 | 5674963 | 8903358 | 8903358 | 100% | 0 | 0 |  | 419691 | 735911 | 1155602 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phase-out of CFC-11 and CFC-12 in the commercial and small domestic refrigeration industry | Individual | ASP | IRA | REF | 15 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Movalled Home Appliances Co. | Individual | ASP | IRA | REF | 18 | INV | 12 | A | I | CFC | 70 | 70 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 607732 | -1500 | 606232 | 606231.7394 | 100% | 0.2606 | 0 |  | 79005 | -320 | 78685 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Machine Manufacturing Co. | Individual | ASP | IRA | REF | 18 | INV | 13 | A | I | CFC | 62 | 62 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 608605 | -1737 | 606868 | 606867.5278 | 100% | 0.4722 | 0 |  | 79119 | -351 | 78768 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Lorestan Refrigerator Manufacturing Industries | Individual | ASP | IRA | REF | 18 | INV | 14 | A | I | CFC | 94 | 94 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 615018 | -1793 | 613225 | 613225.4118 | 100% | -0.4118 | 0 |  | 79952 | -359 | 79593 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Gadook Industries, Co. | Individual | ASP | IRA | REF | 18 | INV | 15 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 373838 | -944 | 372894 | 372894.3966 | 100% | -0.3966 | 0 |  | 48599 | -200 | 48399 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Faritz, Iran | Individual | ASP | IRA | REF | 18 | INV | 16 | A | I | CFC | 109 | 109 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 612504 | -1822 | 610682 | 610682.2582 | 100% | -0.2582 | 0 |  | 79626 | -363 | 79263 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Monark Co. | Individual | ASP | IRA | REF | 18 | INV | 17 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 369939 | -859 | 369080 | 369079.6662 | 100% | 0.3338 | 0 |  | 48092 | -188 | 47904 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Electro Steel Co. | Individual | ASP | IRA | REF | 23 | INV | 24 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 898159 | -20754 | 877405 | 877404.93 | 100% | 0.07 | 0 |  | 116761 | -2879 | 113882 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Chavan Manufacturing Company | Individual | ASP | IRA | REF | 23 | INV | 25 | A | I | CFC | 41.8 | 41.8 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-03-01 | 527802 | 0 | 527802 | 527801.81 | 100% | 0.19 | 0 |  | 68614 | 0 | 68614 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Saran Co. | Individual | ASP | IRA | REF | 23 | INV | 26 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 2002-06-01 | 2003-10-01 | 458663 | -2976 | 455687 | 455687.08 | 100% | -0.08 | 0 |  | 59626 | -481 | 59145 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Zagross II Co. | Individual | ASP | IRA | REF | 23 | INV | 28 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 444858 | -3734 | 441124 | 441123.94 | 100% | 0.06 | 0 |  | 57832 | -577 | 57255 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at Sobouhi Refrigeration | Individual | ASP | IRA | REF | 26 | INV | 35 | A | I | CFC | 30.4 | 30.4 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 237847 | -23768 | 214079 | 214078.79 | 100% | 0.21 | 0 |  | 30920 | -3134 | 27786 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b in manufacture of commercial refrigeration equipment at Yazd Arg Metal, Yazd Sardin and Shervin Electric | Individual | ASP | IRA | REF | 26 | INV | 37 | A | I | CFC | 62.2 | 62.2 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2003-02-01 | 743990 | -95365 | 648625 | 648625.39 | 100% | -0.39 | 0 |  | 91839 | -10603 | 81236 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 27 | PRP | 38 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -1807 | 18193 | 18192.87 | 100% | 0.13 | 0 |  | 2600 | -239 | 2361 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and domestic refrigeration at the Sherkate Sanayee Emerson (Emerson Co). | Individual | ASP | IRA | REF | 28 | INV | 42 | A | I | CFC | 45.8 | 45.8 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-05-01 | 343873 | -10039 | 333834 | 333833.93 | 100% | 0.07 | 0 |  | 44703 | -1373 | 43330 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b AND cfc-12 TO hfc-134A in commercial refrigeration at the second group of Iranian Commercial Refrigeration Manufacturers | Individual | ASP | IRA | REF | 28 | INV | 45 | A | I | CFC | 42.5 | 42.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-09-01 | 309966 | -1621 | 308345 | 308345.18 | 100% | -0.18 | 0 |  | 40296 | -275 | 40021 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Broudati Ghandil Iran (Ghandil Co.) | Individual | ASP | IRA | REF | 28 | INV | 47 | A | I | CFC | 27.5 | 27.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 335423 | -3923 | 331500 | 331499.51 | 100% | 0.49 | 0 |  | 43605 | -578 | 43027 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | Individual | ASP | IRA | REF | 28 | INV | 51 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2008-08-01 | 2009-09-01 | 1076148 | 58673 | 1134821 | 1134821.36 | 100% | -0.36 | 0 |  | 128376 | 6454 | 134830 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Saiwan Sannat Co. | Individual | ASP | IRA | REF | 29 | INV | 52 | A | I | CFC | 14.9 | 14.9 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-03-01 | 200709 | 0 | 200709 | 200709 | 100% | 0 | 0 |  | 26092 | 0 | 26092 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co. | Individual | ASP | IRA | REF | 29 | INV | 53 | A | I | CFC | 16.4 | 16.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 205529 | 0 | 205529 | 205528.61 | 100% | 0.39 | 0 |  | 26719 | 0 | 26718 | 1 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Minavand Refrigeration Company | Individual | ASP | IRA | REF | 29 | INV | 54 | A | I | CFC | 13.4 | 13.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 176777 | -3308 | 173469 | 173468.82 | 100% | 0.18 | 0 |  | 22981 | -466 | 22515 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Forouzan Yakhchal Company (Forouzan Ref. Co.) | Individual | ASP | IRA | REF | 29 | INV | 59 | A | I | CFC | 16.7 | 16.7 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 192704 | -5358 | 187346 | 187345.54 | 100% | 0.46 | 0 |  | 25052 | -736 | 24316 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-05-01 | 2003-02-01 | 30000 | -108 | 29892 | 29891.68 | 100% | 0.32 | 0 |  | 3900 | -20 | 3880 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at Sanayee Broudati Partou Sard Tawan (Barez-Himalia) and Sanayee Broudati Himalia (Himalia) | Individual | ASP | IRA | REF | 31 | INV | 69 | A | I | CFC | 36.09 | 36.09 |  |  | 2000-07-01 | 2000-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-06-01 | 377544 | -3754 | 373790 | 373789.7 | 100% | 0.3 | 0 |  | 49081 | -565 | 48516 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | ASP | IRA | REF | 31 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-04-01 | 2002-01-01 |  | 2002-08-01 | 2003-02-01 | 70000 | -1431 | 68569 | 68568.92 | 100% | 0.08 | 0 |  | 9100 | -200 | 8900 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Tehran Shirak | Individual | ASP | IRA | REF | 34 | INV | 101 | A | I | CFC | 20.5 | 20.5 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2005-09-01 | 202836 | -1649 | 201187 | 201186.61 | 100% | 0.39 | 0 |  | 26369 | -256 | 26113 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Donyaye Mojdeh | Individual | ASP | IRA | REF | 34 | INV | 103 | A | I | CFC | 15.4 | 15.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2004-09-01 | 191020 | -2225 | 188795 | 188794.71 | 100% | 0.29 | 0 |  | 24833 | -329 | 24504 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Zarifan Mashad | Individual | ASP | IRA | REF | 34 | INV | 104 | A | I | CFC | 22 | 22 |  |  | 2001-07-01 | 2002-03-01 | 2003-12-01 |  | 2004-06-01 | 2005-12-01 | 200550 | -1183 | 199367 | 199367.16 | 100% | -0.16 | 0 |  | 26072 | -195 | 25877 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Novin Enjemad | Individual | ASP | IRA | REF | 34 | INV | 105 | A | I | CFC | 10.1 | 10.1 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 138702 | -1665 | 137037 | 137037.35 | 100% | -0.35 | 0 |  | 18031 | -244 | 17787 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Roshan Ind. Group | Individual | ASP | IRA | REF | 34 | INV | 107 | A | I | CFC | 18.6 | 18.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 203960 | -5201 | 198759 | 198759.1 | 100% | -0.1 | 0 |  | 26515 | -717 | 25798 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Avaj Sarma Co. | Individual | ASP | IRA | REF | 34 | INV | 108 | A | I | CFC | 15.2 | 15.2 |  |  | 2001-07-01 | 2001-11-01 | 2004-08-01 |  | 2004-06-01 | 2005-08-01 | 176477 | -534 | 175943 | 175943.3 | 100% | -0.3 | 0 |  | 22942 | -106 | 22836 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 111 | A | I | CFC | 27.4 | 27.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2005-06-01 | 2006-09-01 | 209425 | -304 | 209121 | 209121.07 | 100% | -0.07 | 0 |  | 27225 | -39 | 27186 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Gasso Co. | Individual | ASP | IRA | REF | 34 | INV | 113 | A | I | CFC | 11.7 | 11.7 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 158232 | -4811 | 153421 | 153421.46 | 100% | -0.46 | 0 |  | 20570 | -657 | 19913 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the Takran Mobbarad Co. | Individual | ASP | IRA | REF | 34 | INV | 98 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 119864 | -2915 | 116949 | 116948.51 | 100% | 0.49 | 0 |  | 15582 | -403 | 15179 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of 12 investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 15000 | -403 | 14597 | 14597.4 | 100% | -0.4 | 0 |  | 1950 | -55 | 1895 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Abbaspour Co. | Individual | ASP | IRA | REF | 35 | INV | 119 | A | I | CFC | 9.7 | 9.7 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 144206 | -741 | 143465 | 143464.74 | 100% | 0.26 | 0 |  | 18747 | -126 | 18621 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Moradi Company | Individual | ASP | IRA | REF | 35 | INV | 120 | A | I | CFC | 6.4 | 6.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-03-01 | 82400 | -2031 | 80369 | 80368.84 | 100% | 0.16 | 0 |  | 10712 | -281 | 10431 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Bouran Saz Karaj (Kohsar Co.) | Individual | ASP | IRA | REF | 35 | INV | 121 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 120526 | -2024 | 118502 | 118501.73 | 100% | 0.27 | 0 |  | 15668 | -287 | 15381 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Sherkate Taavoni 435 (Khorsandi Co.) | Individual | ASP | IRA | REF | 35 | INV | 122 | A | I | CFC | 5.4 | 5.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 82107 | -1871 | 80236 | 80236.24 | 100% | -0.24 | 0 |  | 10674 | -260 | 10414 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alborz Neishabour | Individual | ASP | IRA | REF | 35 | INV | 123 | A | I | CFC | 16 | 16 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2005-08-01 | 189669 | -4567 | 185102 | 185102.48 | 100% | -0.48 | 0 |  | 24657 | -632 | 24025 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at the Ariz Pooyaye Sanat (Ariz Co.) | Individual | ASP | IRA | REF | 35 | INV | 124 | A | I | CFC | 7.6 | 7.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 86365 | -3752 | 82613 | 82612.98 | 100% | 0.02 | 0 |  | 11227 | -504 | 10723 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Yaghoubali Bazdid Vahdat (Isun Co.) | Individual | ASP | IRA | REF | 35 | INV | 125 | A | I | CFC | 10.5 | 10.5 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 131605 | -2900 | 128705 | 128704.73 | 100% | 0.27 | 0 |  | 17109 | -404 | 16705 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Darvish Mohamad Nazari Company (Jahan Nama) | Individual | ASP | IRA | REF | 35 | INV | 126 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-05-01 | 139970 | -140 | 139830 | 139830.4 | 100% | -0.4 | 0 |  | 18196 | -47 | 18149 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Borna Sanat Arak | Individual | ASP | IRA | REF | 35 | INV | 127 | A | I | CFC | 8 | 8 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2007-05-01 | 108238 | -802 | 107436 | 107435.59 | 100% | 0.41 | 0 |  | 14071 | -104 | 13967 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sard Va Garm | Individual | ASP | IRA | REF | 35 | INV | 128 | A | I | CFC | 8.4 | 8.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 125350 | -4570 | 120780 | 120779.6 | 100% | 0.4 | 0 |  | 16296 | -619 | 15677 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardintous Co. | Individual | ASP | IRA | REF | 35 | INV | 129 | A | I | CFC | 10.3 | 10.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 145879 | -281 | 145598 | 145597.6 | 100% | 0.4 | 0 |  | 18964 | -66 | 18898 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Gostar Co. | Individual | ASP | IRA | REF | 35 | INV | 130 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 100384 | -3803 | 96581 | 96580.99 | 100% | 0.01 | 0 |  | 13050 | -514 | 12536 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of 3 umbrella investment projects in the commercial and domestic refrigeration sector | Individual | ASP | IRA | REF | 36 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 30000 | -2109 | 27891 | 27890.98 | 100% | 0.02 | 0 |  | 3900 | -280 | 3620 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (room air-conditioning and compressors) | Individual | ASP | IRA | REF | 58 | PRP | 196 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-10-01 | 2010-07-31 |  | 2011-04-01 | 2012-12-01 | 45000 | -61 | 44939 | 44938.82 | 100% | 0.18 | 0 |  | 3375 | -5 | 3370 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | IRA | REF | 72 | PRP | 210 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2016-05-31 | 2016-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 18000 | 1400 | 0 | 0 | 1400 | 0 | Approved at the 72nd Meeting of the ExCom in May 2014, funds became available December 2014, no actions in 2014. | Project implementation according to the schedule: - Survey and data collection completed, - Data to be processed during 4Q 2015. |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the foam sector | Individual | ASP | IRA | SEV | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-08-01 | 32065 | 698 | 32763 | 32763 | 100% | 0 | 0 |  | 4168 | 91 | 4259 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the commercial refrigeration sector (remaining enterprises), compressors and the foam sector | Individual | ASP | IRA | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -8 | 6492 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent (CTC) sector | Individual | ASP | IRA | SOL | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2005-12-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000.02 | 100% | -0.02 | 0 |  | 2600 | -2 | 2598 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the solvent sector (CTC/TCA) | Individual | ASP | IRA | SOL | 39 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | 0 | 10000 | 10000.47 | 100% | -0.47 | 0 |  | 750 | 0 | 750 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the solvent sector CTC/TCA | Individual | ASP | IRA | SOL | 42 | PRP | 164 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -110 | 14890 | 14889.61 | 100% | 0.39 | 0 |  | 1125 | -8 | 1117 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the solvent sector | Individual | ASP | IRA | SOL | 48 | PRP | 178 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-07-01 | 2007-04-01 |  | 2006-12-01 | 2007-05-01 | 15000 | -512 | 14488 | 14487.67 | 100% | 0.33 | 0 |  | 1125 | -38 | 1087 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | ASP | IRA | SOL | 50 | INV | 180 | A | I | CTC TCA | 52.7 | 52.7 |  |  | 2006-11-01 | 2007-11-01 | 2008-02-01 |  | 2009-12-01 | 2012-09-01 | 856478 | -1457 | 855021 | 855021.12 | 100% | -0.12 | 0 |  | 64236 | -109 | 64127 | 0 | 0 | FIN |  |  | 2009-12-01 | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al Hadi Co. | Individual | ASP | IRQ | FOA | 57 | INV | 06 | A | I | CFC | 20 | 20 |  |  | 2009-04-01 | 2010-12-01 | 2011-03-31 |  | 2014-09-01 | 2014-09-01 | 126457 | -1352 | 125105 | 125104.58 | 100% | 0.42 | 0 |  | 11381 | -122 | 11259 | 0 | 0 | FIN |  |  | 2011-12-01 | INV
FIN | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in pre and post-harvest sectors | Individual | ASP | IRQ | FUM | 58 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-07-01 | 2010-07-31 |  | 2010-12-01 | 2011-06-01 | 40000 | -239 | 39761 | 39761.16 | 100% | -0.16 | 0 |  | 3000 | -18 | 2982 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for alternatives to methyl bromide | Individual | ASP | IRQ | FUM | 62 | INV | 13 | A | I | MBR | 3.5 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2016-07-01 |  |  | 211970 | 0 | 211970 | 151336.18 | 71.4% | 60633.82 | 38659.93 | 5000 | 19077 | 0 | 13620 | 5457 | 3479 | 2014 was a very critical year for project implementation in Iraq. UNIDO is still exploring modalities to ensure a timely disbursement of money for the training to be implemented. - In 2014 the focus has been on training activities. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes (partially: some training activities still needed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: All contracts have been signed and everything is in place for a full project implementation. However, some training activities could not be implemented because of some logistic impediments in the country. Actions towards next goals: Develop an alternative training scheme to overcome the logistic impediments in a safe manner. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Internal political instability. Develop an alternative training scheme to overcome the logistic impediments in a safe manner. Any recurring problem? Yes If yes, description of the problem/s: Internal political instability. Any impact on project completion date: Yes If yes, implications: Training activates need to be re-organized taking into consideration the safe implementation of project activities according to local instability. Any action required by Executive Committee? Yes; to extend the grant validity | - Not much activities have been implemented in the first months of 2015 in Iraq. - ExCom took decision on possible cancellation of the project. UNIDO is in touch with the NOU to re-design training component to allow a safe achievement of the tasks. - All contractual arrangements are in place to ensure a timely implementation as soon as logistic and safe conditions allow. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes (partially: some training activities still needed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: All contracts have been signed and everything is in place for a full project implementation. However, some training activities could not be implemented because of some logistic impediments in the country. Actions towards next goals: Develop an alternative training scheme to overcome the logistic impediments in a safe manner. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Internal political instability. Develop an alternative training scheme to overcome the logistic impediments in a safe manner. Any recurring problem? Yes If yes, description of the problem/s: Internal political instability. Any impact on project completion date: Yes If yes, implications: Training activates need to be re-organized taking into consideration the safe implementation of project activities according to local instability Any action required by Executive Committee? Yes; To extend the grant validity |  |  | INV |  | No Progress - Possible cancellation
FIN | UNIDO | Preparation of country programme and national phase-out plan. | Individual | ASP | IRQ | PHA | 55 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2009-07-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000.01 | 100% | -0.01 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | IRQ | PHA | 55 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 30000 | -2909 | 27091 | 27090.88 | 100% | 0.12 | 0 |  | 2250 | -218 | 2032 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | INV | 09 | A | I | CFC CTC | 1257.9 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2012-07-31 | 2015-12-01 |  |  | 4353530 | 0 | 4353530 | 3106580.92 | 71.36% | 1246949.08 | 1272805.75 | 200000 | 326515 | 0 | 232994 | 93521 | 95460.4312 | 1. Coordinating the installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel was delivered to the beneficiary in the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (no) Milestone 4: All equipment at beneficiary premises (no) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: Equipment for Light Industries and Nassr State company not released from customs. Equipment for Iraqi Steel not installed/commissioned. UNIDO in cooperation with stakeholders continuously trying to facilitate customs clearance. The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: Find solution to improve customs clearance and installation/commissioning. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Very complicated customs clearance procedure. Action: Explore how to overcome. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No | 1. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel was delivered to the beneficiary in the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (yes) Milestone 4: All equipment at beneficiary premises (yes) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: UNIDO will recruit engineering company to supervise the installation/commissioning. ToR for this has been drafted. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Security situation in Iraq does not allow for regular travel to the project sites; and UNIDO will recruit engineering company to supervise installation/commissioning. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | IRQ | PHA | 59 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 |  | 65000 | 0 | 65000 | 62289.79 | 95.83% | 2710.21 | 0 | 1 | 4875 | 0 | 4672 | 203 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | NON-INV
ONG | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | INV | 15 | A | I |  | 0 | 0 |  |  | 2011-04-01 |  | 2012-03-31 | 2015-12-01 |  |  | 303000 | 0 | 303000 | 0 | 0% | 303000 | 303000 | 50000 | 22725 | 0 | 0 | 22725 | 22725 | 1. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel to be shipped in the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (no) Milestone 4: All equipment at beneficiary premises (no) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: Equipment for Light Industries and Nassr State company not released from customs. Equipment for Iraqi Steel not installed/commissioned. UNIDO in cooperation with stakeholders continuously trying to facilitate customs clearance. The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: Find solution to improve customs clearance and installation/commissioning. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Very complicated customs clearance procedure. Action: Explore how to overcome. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No | 1. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel to be shipped in the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (yes) Milestone 4: All equipment at beneficiary premises (yes) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: UNIDO will recruit engineering company to supervise installation/commissioning. ToR for this has been drafted. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Security situation in Iraq does not allow for regular travel to the project sites; and UNIDO will recruit engineering company to supervise installation/commissioning. Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | INV | 16 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2013-11-30 | 2015-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 80000 | 40000 | 6000 | 0 | 0 | 6000 | 6000 | Equipment for 3 reclaim centers as well as for smaller manufacturer of commercial refrigerating equipment from NPP; in combination with filter kits and cylinders from HPMP 1st tranche has been ordered through one tender. Milestones achieved: Milestone 1: Equipment ordered (Yes) Milestone 2: Equipment shipped (Yes) Milestone 3: Equipment released from customs (No) Milestone 4: Equipment at beneficiary premises (No) Milestone 5: Equipment commissioned and personnel trained (No) Activities planned but not implemented, reasons and strategy: None Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Re-tendering process had negative impact on completion date. Any action required by Executive Committee? No | Equipment for 3 reclaim centers as well as for smaller manufacturer of commercial refrigerating equipment from NPP; in combination with filter kits and cylinders from HPMP 1st tranche has been ordered through one tender. Milestones achieved: Milestone 1: Equipment ordered (Yes) Milestone 2: Equipment shipped (Yes) Milestone 3: Equipment released from customs (Yes) Milestone 4: Equipment at beneficiary premises (Yes) Milestone 5: Equipment commissioned and personnel trained (No) Activities planned but not implemented, reasons and strategy: None Actions towards next goals: Verification of shipment will take place during September and commissioning/training in Erbil is being scheduled. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Customs clearance took several months but equipment is now released, so no further actions needed. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Re-tendering process and customs clearance had negative impact on completion date. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRQ | PHA | 73 | PRP | 19 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 1000 | 1750 | 0 | 0 | 1750 | 0 | No actions taken yet. Focus on completion of NPP and HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: NPP and HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Brief report: No actions taken yet. Focus on completion of NPP and HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: NPP and HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | Individual | ASP | IRQ | REF | 57 | INV | 07 | A | I | CFC | 193.6 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 | 2015-12-01 |  |  | 2161581 | 0 | 2161581 | 1755517.26 | 81.21% | 406063.74 | 418911.39 | 100000 | 162119 | 0 | 131664 | 30455 | 31418.3543 | 1. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel to be shipped in the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (no) Milestone 4: All equipment at beneficiary premises (no) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: Equipment for Light Industries and Nassr State company not released from customs. Equipment for Iraqi Steel not installed/commissioned. UNIDO in cooperation with stakeholders continuously trying to facilitate customs clearance. The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: Find solution to improve customs clearance and installation/commissioning. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Very complicated customs clearance procedure. Action: Explore how to overcome. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No | 1. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel was delivered to beneficiary by the end of 2014. The planned completion date has been extended as per decision 73/8. Milestones achieved: Milestone 1: All purchase orders issued (yes) Milestone 2: All equipment shipped from suppliers (yes) Milestone 3: All equipment released from customs (yes) Milestone 4: All equipment at beneficiary premises (yes) Milestone 5: All equipment installed/commissioned (no) Activities planned but not implemented, reasons and strategy: The supplier of the foam equipment refused to do installation/commissioning for security reasons; and UNIDO is seeking alternative solution on this matter. Actions towards next goals: UNIDO will recruit engineering company to supervise the installation/commissioning. ToR for this has been drafted. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Security situation in Iraq does not allow for regular travel to the project sites; and UNIDO will recruit engineering company to supervise installation/commissioning. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Time consuming customs clearance has direct impact on project completion date. Also, that installation/commissioning should be done by 3rd party will delay completion. Any action required by Executive Committee? No |  |  | INV |  | Continued Monitoring
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | IRQ | REF | 73 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 1000 | 2100 | 0 | 0 | 2100 | 0 | No actions taken yet. Focus on completion of NPP and HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: NPP and HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No | Brief report: No actions taken yet. Focus on completion of NPP and HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: NPP and HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No If yes, reasons and action plan: n/a Any recurring problem? No Any impact on project completion date: No |  |  | NON-INV
FIN | UNIDO | Phasing out CFCs at Parfumerie Gandour D.A.F. | Individual | AFR | IVC | ARS | 20 | INV | 07 | A | I | CFC | 66 | 66 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-10-01 | 106061 | 0 | 106061 | 106060.67 | 100% | 0.33 | 0 |  | 13788 | 0 | 13788 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Sicobel | Individual | AFR | IVC | ARS | 20 | INV | 08 | A | I | CFC | 20.8 | 20.8 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-09-01 | 59171 | -453 | 58718 | 58717.83 | 100% | 0.17 | 0 |  | 7692 | -71 | 7621 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | AFR | IVC | ARS | 44 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -1832 | 13168 | 13167.99 | 100% | 0.01 | 0 |  | 1125 | -137 | 988 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC-12 in the manufacture of cosmetics aerosols (deodorants) by conversion to hydrocarbon aerosol propellant (HAP) at COPACI, Abidjan (terminal aerosol sector project) | Individual | AFR | IVC | ARS | 46 | INV | 23 | A | I | CFC | 43.4 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-09-01 |  |  | 2009-06-01 | 110428 | -109351 | 1077 | 1077 | 100% | 0 | 0 |  | 9939 | -9842 | 97 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at F.I.M.A. flexible polyurethane foam plant | Individual | AFR | IVC | FOA | 19 | INV | 06 | A | I | CFC | 53.1 | 53.1 |  |  | 1996-05-01 | 1997-09-01 | 1997-07-01 |  | 1997-12-01 | 2001-03-01 | 85087 | -246 | 84841 | 84841 | 100% | 0 | 0 |  | 11061 | -49 | 11012 | 0 | 0 | FIN
CLO | UNIDO | Preparation of a project for stored commodities (cocoa beans) | Individual | AFR | IVC | FUM | 27 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector | Individual | AFR | IVC | FUM | 39 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-11-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -198 | 9802 | 9801.98 | 100% | 0.02 | 0 |  | 750 | -16 | 734 | 0 | 0 | FIN
FIN | UNIDO | Phase-out the use of methyl bromide commodities and storage fumigation | Individual | AFR | IVC | FUM | 42 | INV | 19 | A | I | MBR | 8.5 | 8.5 |  |  | 2004-04-01 | 2004-04-01 | 2006-10-01 |  | 2008-12-01 | 2010-12-01 | 222210 | -19676 | 202534 | 202534.15 | 100% | -0.15 | 0 |  | 19999 | -1771 | 18228 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | IVC | PHA | 48 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2008-04-01 | 2008-12-01 | 15000 | -15 | 14985 | 14984.65 | 100% | 0.35 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | INV | 29 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-11-01 | 2010-03-31 |  | 2009-12-01 | 2010-12-01 | 162000 | 0 | 162000 | 162000.02 | 100% | -0.02 | 0 |  | 12150 | 0 | 12150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | INV | 34 | A | I | CFC | 44.1 | 44.1 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2014-03-01 | 2014-09-01 | 121000 | -11401 | 109599 | 109599.34 | 100% | -0.34 | 0 |  | 9075 | -855 | 8220 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | INV | 36 | A | I | HCFC | 3.3 | 0 |  |  | 2012-04-01 | 2013-11-01 | 2016-04-30 | 2017-04-01 |  |  | 460000 | 0 | 460000 | 2145.09 | 0.4663% | 457854.91 | 0 | 20000 | 34500 | 0 | 161 | 34339 | 0 | - The agreement has been signed by one of the parties, namely the Ministry of Environment. - The signature of the Ministry of Vocational Training is pending. Milestones achieved: Agreement signed by one of the two parties: Yes Agreement signed by second party: No Activities planned but not implemented, reasons and strategy: Procurement of equipment delayed awaiting signature of interministerial agreement establishing beneficiary centre Was there any delay during the reporting year?: Yes If yes, reasons and action plan: delay in signature of interministerial agreement establishing beneficiary centre. UNIDO encourages NOU to speed up the signature process Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Implementation of current tranche to be completed by April 2017 Any action required by Executive Committee? No | - The agreement between the Ministry of Environment and the Ministry of Vocational Training establishing a training centre as a beneficiary of the project has been signed. - Subsequently a mission was planned to assess equipment needs of the centre for July, which, due to health reasons has been postponed to September 2015. - Technical specifications for the equipment to be procured will be prepared subsequently. Milestones achieved: Interministerial Agreement signed: Yes Equipment needs assessment completed: No Activities planned but not implemented, reasons and strategy: Procurement of equipment delayed due to lengthy process for signature of interministerial agreement establishing beneficiary centre Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in signature of interministerial agreement establishing beneficiary centre. UNIDO to group equipment procurement. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Implementation of current tranche to be completed by April 2017 Any action required by Executive Committee? No |  |  | INV
CLO | UNIDO | Project formulation for the ODS phase-out in the refrigeration sector | Individual | AFR | IVC | REF | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  |  | 1999-11-01 | 15000 | -84 | 14916 | 14916 | 100% | 0 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | CLO
FIN | UNIDO | Preparation of an investment project in the domestic refrigeration (hydrocarbon) sector for Serti | Individual | AFR | IVC | REF | 24 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-10-01 | 2000-12-01 | 20000 | -10918 | 9082 | 9082 | 100% | 0 | 0 |  | 2600 | -1421 | 1179 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 57 | INV | 32 | A | I | CFC | 18 | 17.5 |  |  | 2009-04-01 | 2009-06-01 | 2011-04-01 |  | 2013-12-01 | 2014-04-01 | 1000000 | -968376 | 31624 | 31573.91 | 99.84% | 50.09 | 0 |  | 75000 | -72628 | 2368 | 4 | 0 | FIN |  |  |  | INV
FIN | UNIDO | ODS phase-out of a foam producing plant (Fabrique Ivoirienne de mousse et amemblement) and 2 aerosol fillers (Sicobel and Gandoor) | Individual | AFR | IVC | SEV | 17 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-02-01 | 1995-09-01 |  | 1996-10-01 | 1998-08-01 | 10000 | -388 | 9612 | 9612 | 100% | 0 | 0 |  | 1300 | -52 | 1248 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase out project (tobacco fumigation) | Individual | LAC | JAM | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-09-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
CLO | UNIDO | Demonstration project - alternatives to the use of methyl bromide in structural and commodity fumigation | Individual | LAC | JAM | FUM | 26 | DEM | 10 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  |  | 2001-07-01 | 102850 | -102850 | 0 | 0 |  | 0 | 0 |  | 13371 | -13371 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the aerosol sector | Individual | ASP | JOR | ARS | 30 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-08-01 | 2001-04-01 |  | 2001-01-01 | 2002-05-01 | 20000 | -7413 | 12587 | 12587.48 | 100% | -0.48 | 0 |  | 2600 | -966 | 1634 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Jordan Tunisian Chemical Company | Individual | ASP | JOR | ARS | 32 | INV | 68 | A | I | CFC | 12 | 12 |  |  | 2000-12-01 | 2001-10-01 | 2003-03-01 |  | 2002-12-01 | 2003-10-01 | 52800 | -23 | 52777 | 52776.74 | 100% | 0.26 | 0 |  | 6864 | -14 | 6850 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | JOR | FUM | 23 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-03-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation and optimal use of soil fumigants in combination with an integrated pest management | Individual | ASP | JOR | FUM | 25 | DEM | 40 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-10-01 | 2000-08-01 |  | 2001-12-01 | 2003-08-01 | 385000 | -64217 | 320783 | 320783.16 | 100% | -0.16 | 0 |  | 50050 | -8414 | 41636 | 0 | 0 | FIN
FIN | UNIDO | National ODS phase out plan: commercial manufacturing and servicing and transport refrigeration | One-off Phase Out | ASP | JOR | PHA | 38 | INV | 78 | A | I | CFC | 41 | 41 |  |  | 2002-11-01 | 2003-06-01 | 2009-12-01 |  | 2006-12-01 | 2007-12-01 | 410000 | -2466 | 407534 | 407534.13 | 100% | -0.13 | 0 |  | 53300 | -321 | 52979 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | JOR | PHA | 55 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 | 2012-05-01 | 150000 | -975 | 149025 | 149025.08 | 100% | -0.08 | 0 |  | 11250 | -73 | 11177 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (policy support, awareness promotion, monitoring) | Multi-Year | ASP | JOR | PHA | 65 | TAS | 90 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2013-11-30 | 2015-12-01 |  |  | 70000 | 0 | 70000 | 13496.23 | 19.28% | 56503.77 | 22603.15 | 28037.02 | 6300 | 0 | 1215 | 5085 | 2034 | - Workshop on Policy and Regulation was held in December 2014. - The second tranche was submitted to the 73th Meeting of the ExCom, but was not approved due to the low implementation rate of the cooperating implementing agency, WB. - Verification report on the achievement of ODS reduction targets was prepared and submitted. | - A new submission has been prepared for the 75th Meeting of the ExCom, assuming that the cooperating agency has solved the problems of implementation. |  |  | INV
FIN | UNIDO | Preparation of investment project for phase out of ODS in selected industries in the refrigeration and air-conditioning sector | Individual | ASP | JOR | REF | 10 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1993-10-01 |  | 1994-12-01 | 1998-08-01 | 90000 | -14930 | 75070 | 75070 | 100% | 0 | 0 |  | 11700 | -1956 | 9744 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at National Refrigeration Co. (NRC) | Individual | ASP | JOR | REF | 13 | INV | 18 | A | I | CFC | 14.3 | 19.3 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-07-01 | 813887 | -29 | 813858 | 813857.62 | 100% | 0.38 | 0 |  | 105805 | -171 | 105634 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Household Appliance Manufacturing Co. (HAMCO) | Individual | ASP | JOR | REF | 13 | INV | 19 | A | I | CFC | 21.2 | 21.2 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 775602 | 0 | 775602 | 775602.11 | 100% | -0.11 | 0 |  | 100828 | -19 | 100809 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Middle East Electrical Industries Co. Ltd. | Individual | ASP | JOR | REF | 13 | INV | 20 | A | I | CFC | 16.6 | 23 |  |  | 1994-07-01 | 1994-12-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 883153 | -51 | 883102 | 883102.34 | 100% | -0.34 | 0 |  | 114810 | -189 | 114621 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Abdin Industrial Est.Co. | Individual | ASP | JOR | REF | 20 | INV | 29 | A | I | CFC | 10.4 | 21.5 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1997-12-01 | 2000-07-01 | 116928 | -636 | 116292 | 116292 | 100% | 0 | 0 |  | 15201 | -107 | 15094 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at the Ihsan & Tahseen Baalbaki Co. | Individual | ASP | JOR | REF | 23 | INV | 35 | A | I | CFC | 66.5 | 66.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-06-01 | 2001-12-01 | 545103 | -5327 | 539776 | 539776.26 | 100% | -0.26 | 0 |  | 70863 | -803 | 70060 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | JOR | REF | 24 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-05-01 | 2000-12-01 | 30000 | -3410 | 26590 | 26590 | 100% | 0 | 0 |  | 3900 | -449 | 3451 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at six Jordanian companies | Individual | ASP | JOR | REF | 26 | INV | 42 | A | I | CFC | 25.1 | 25.1 |  |  | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 1999-12-01 | 2002-09-01 | 305764 | -4822 | 300942 | 300941.61 | 100% | 0.39 | 0 |  | 39749 | -689 | 39060 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in manufacture of commercial refrigeration equipment at Maurice al-Deek Co. | Individual | ASP | JOR | REF | 26 | INV | 43 | A | I | CFC | 25.7 | 25.7 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 336233 | -7042 | 329191 | 329191.08 | 100% | -0.08 | 0 |  | 43710 | -983 | 42727 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 27 | PRP | 45 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 1999-12-01 | 2001-03-01 | 5000 | -693 | 4307 | 4307 | 100% | 0 | 0 |  | 650 | -91 | 559 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Third Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 52 | A | I | CFC | 16.8 | 17.74 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 243764 | -79664 | 164100 | 164100.37 | 100% | -0.37 | 0 |  | 31689 | -10390 | 21299 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Second Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 62 | A | I | CFC | 25.8 | 25.8 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2000-08-01 | 2002-09-01 | 278950 | -2424 | 276526 | 276526.2 | 100% | -0.2 | 0 |  | 36264 | -373 | 35891 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: technical assistance and support to develop regulations for ODS to implement the Environment law of 1999 | RMP | ASP | JOR | REF | 28 | TAS | 49 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-03-01 | 2002-07-01 | 20000 | -2979 | 17021 | 17020.85 | 100% | 0.15 | 0 |  | 2600 | -391 | 2209 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | ASP | JOR | REF | 28 | TAS | 50 | A | I | CFC | 19.1 | 19.1 |  |  | 1999-07-01 | 2001-09-01 | 2001-08-01 |  | 2004-06-01 | 2005-09-01 | 311950 | -2650 | 309300 | 309299.95 | 100% | 0.05 | 0 |  | 40554 | -409 | 40145 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | ASP | JOR | REF | 28 | TRA | 47 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2001-08-01 |  | 2002-10-01 | 2004-03-01 | 70000 | -654 | 69346 | 69345.66 | 100% | 0.34 | 0 |  | 9100 | -99 | 9001 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | ASP | JOR | REF | 28 | TRA | 48 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-07-01 | 2003-06-01 | 38250 | -187 | 38063 | 38062.56 | 100% | 0.44 | 0 |  | 4973 | -33 | 4940 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigertion equipment at Al-Arghawin & Marka commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 29 | INV | 55 | A | I | CFC | 27.4 | 27.4 |  |  | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 255203 | -9070 | 246133 | 246133.04 | 100% | -0.04 | 0 |  | 33176 | -1229 | 31947 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-04-01 | 2001-04-01 |  | 2002-12-01 | 2003-08-01 | 20000 | -1759 | 18241 | 18241.11 | 100% | -0.11 | 0 |  | 2600 | -232 | 2368 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in production commercial refrigeration equipment at the medium size commercial refrigerator manufacturers (Jordan Catering Supplies, El-Shami, and Nedal Raja Al-Dwaik companies) in Jordan | Individual | ASP | JOR | REF | 31 | INV | 65 | A | I | CFC | 34.72 | 34.72 |  |  | 2000-07-01 | 2000-10-01 | 2003-08-01 |  | 2002-12-01 | 2004-09-01 | 469525 | -33258 | 436267 | 436266.87 | 100% | 0.13 | 0 |  | 61038 | -4413 | 56625 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at Fourth Group of small size Jordanian Commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 31 | INV | 66 | A | I | CFC | 23.1 | 23.07 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 270034 | -18831 | 251203 | 251203.16 | 100% | -0.16 | 0 |  | 35104 | -2499 | 32605 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration (umbrella project) sector | Individual | ASP | JOR | REF | 33 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-04-01 |  | 2002-07-01 | 2003-09-01 | 20000 | -477 | 19523 | 19523.09 | 100% | -0.09 | 0 |  | 2600 | -66 | 2534 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in the production of commercial refrigeration equipment at the second medium-size commercial refrigerator manufacturers group (Abu Azmi, Hasouni Refrigeration and Majdi) | Individual | ASP | JOR | REF | 34 | INV | 71 | A | I | CFC | 26.4 | 26.4 |  |  | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-07-01 | 2005-09-01 | 342652 | -5429 | 337223 | 337222.65 | 100% | 0.35 | 0 |  | 44545 | -776 | 43769 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at 6th group of SMEs (Abu-Khalaf, Al-Taghwa, Farough Refrigeration, Dawudiah Workshop, Makka Refrigeration and Teck-Tack workshop) | Individual | ASP | JOR | REF | 34 | INV | 72 | A | I | CFC | 24.4 | 24.4 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 286523 | -5667 | 280856 | 280856.08 | 100% | -0.08 | 0 |  | 37248 | -795 | 36453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacturing commercial refrigeration equipment at 5th group of SMEs (Abdoulah Factory, Emad Addin Al- Sareegy, Ma-nna, Al-Mansour, Al-Ostath, Raed) | Individual | ASP | JOR | REF | 34 | INV | 74 | A | I | CFC | 26 | 26 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 244954 | -5781 | 239173 | 239173.25 | 100% | -0.25 | 0 |  | 31844 | -801 | 31043 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project for the conversion of HCFC to non-HCFC technology in the manufacturing of mini-split units at Petra Engineering | Individual | ASP | JOR | REF | 56 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-04-01 | 2009-11-30 |  | 2010-12-01 | 2011-07-01 | 40000 | -327 | 39673 | 39672.83 | 100% | 0.17 | 0 |  | 3000 | -25 | 2975 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment at Petra Engineering Industries Co. | Multi-Year | ASP | JOR | REF | 60 | INV | 86 | A | I | HCFC | 8.1 | 8.1 |  |  | 2010-04-01 | 2010-12-01 | 2011-10-31 | 2015-12-01 |  |  | 2167033 | 126500 | 2293533 | 1498256.79 | 65.33% | 795276.21 | 670539 | 490279 | 162527 | 9488 | 112369 | 59646 | 50290 | - Some delays occurred during the production of the heat exchangers by the supplier, but the situation was solved. | - Equipment installed in March 2015. - Contract prepared and signed for final IOC payment.
FIN | UNIDO | Preparatory assistance for investment projects in commercial refrigeration, air-conditioning, foam and halon sectors | Individual | ASP | JOR | SEV | 15 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 50000 | -827 | 49173 | 49173 | 100% | 0 | 0 |  | 6500 | -118 | 6382 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the solvent sector (CFC-113) sector | Individual | ASP | JOR | SOL | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2002-12-01 | 2003-06-01 | 25000 | -2455 | 22545 | 22544.58 | 100% | 0.42 | 0 |  | 3250 | -324 | 2926 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the King Hussein Workshop, Zarqa | Individual | ASP | JOR | SOL | 34 | INV | 75 | A | I | TCA | 6.4 | 6.4 |  |  | 2001-07-01 | 2002-12-01 | 2003-02-01 |  | 2003-12-01 | 2004-10-01 | 191316 | 0 | 191316 | 191316.01 | 100% | -0.01 | 0 |  | 24871 | 0 | 24871 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the Royal Jordanian Air Force | Individual | ASP | JOR | SOL | 37 | INV | 76 | A | I | TCA | 10.4 | 10.4 |  |  | 2002-07-01 | 2003-11-01 | 2004-08-01 |  | 2005-12-01 | 2007-01-01 | 342757 | -17 | 342740 | 342740.39 | 100% | -0.39 | 0 |  | 44558 | -2 | 44556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | KAM | FUM | 46 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 30000 | -2430 | 27570 | 27569.64 | 100% | 0.36 | 0 |  | 2700 | -219 | 2481 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | ASP | KAM | SOL | 57 | TAS | 21 | A | I | TCA | 0.3 | 0.3 |  |  | 2009-04-01 | 2010-02-01 | 2010-03-31 |  | 2010-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out CFCs at Aesthetics Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 10 | A | I | CFC | 107 | 107 |  |  | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 55000 | 0 | 55000 | 54999.76 | 100% | 0.24 | 0 |  | 7150 | -1 | 7149 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mirage Industries Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 11 | A | I | CFC | 51 | 51 |  |  | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 47250 | -371 | 46879 | 46879.18 | 100% | -0.18 | 0 |  | 6143 | -58 | 6085 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | AFR | KEN | FUM | 23 | PRP | 15 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in cut-flowers at Kenya Agricultural Research Institute - KARI | Individual | AFR | KEN | FUM | 24 | DEM | 17 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-10-01 | 2000-04-01 |  | 2003-03-01 | 2004-03-01 | 328900 | -2958 | 325942 | 325942.31 | 100% | -0.31 | 0 |  | 42757 | -452 | 42305 | 0 | 0 | FIN
CLO | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | AFR | KEN | FUM | 30 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Technology transfer leading to methyl bromide phase-out in soil fumigation | Multi-Year | AFR | KEN | FUM | 53 | INV | 43 | A | I | MBR | 53 | 53 |  |  | 2007-11-01 | 2008-02-01 | 2010-11-01 |  | 2009-12-01 | 2012-07-01 | 510659 | -1888 | 508771 | 508770.66 | 100% | 0.34 | 0 |  | 38300 | -142 | 38158 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in post-harvest sector | Individual | AFR | KEN | FUM | 60 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 40000 | -184 | 39816 | 39815.8 | 100% | 0.2 | 0 |  | 3000 | -14 | 2986 | 0 | 0 | FIN
COM | UNIDO | Technical assistance for the final elimination of methyl bromide in post harvest sector | Individual | AFR | KEN | FUM | 65 | INV | 52 | A | I | MBR | 6.6 | 6.6 |  |  | 2011-11-01 | 2012-09-01 | 2012-11-30 |  | 2014-12-01 |  | 287700 | 0 | 287700 | 224736.6 | 78.11% | 62963.4 | 55643.46 | 59000 | 21578 | 0 | 16855 | 4723 | 4173 | - Equipment purchased and delivery completed in 2013. - Installation completed. - Monitoring mission planned for April 2014 to monitor on equipment delivery and installation and urge NCPB to complete the agreed civil works to allow installation of equipment delivered. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - NA Actions towards next goals: Official project completion Was there any delay during the reporting year? Yes If yes, reasons and action plan: To decide on a date for official project completion. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Actual closure followed 7 months after planned completion date. Any action required by Executive Committee? No | - Closing ceremony took place in April 2015. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - NA Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  | 2014-01-01 | INV
FIN | UNIDO | CFC-phase out project at Kenya Cold Storages Ltd. and subsidiary companies: Hall Equatorial, Premier Refrigeration and Engineering, Refrigeration Services | Individual | AFR | KEN | REF | 11 | INV | 06 | A | I | CFC | 40.8 | 40.8 |  |  | 1993-11-01 | 1996-12-01 | 1997-03-01 |  | 1998-12-01 | 2001-07-01 | 380875 | 123140 | 504015 | 504015 | 100% | 0 | 0 |  | 49514 | 15904 | 65418 | 0 | 0 | FIN
FIN | UNIDO | Identification and preparation of projects in the solvents and aerosols sectors | Individual | AFR | KEN | SEV | 17 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1995-11-01 |  | 1998-03-02 | 1999-08-01 | 15000 | -938 | 14062 | 14062 | 100% | 0 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from TCA to aqueous cleaning and cleaning in TCE at Kenyan Railways Central Workshop | Individual | AFR | KEN | SOL | 23 | INV | 14 | A | I | TCA | 6 | 6 |  |  | 1997-11-01 | 1998-08-01 | 1998-12-01 |  | 1999-12-01 | 2002-09-01 | 205524 | 0 | 205524 | 205524.21 | 100% | -0.21 | 0 |  | 26718 | 0 | 26718 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | AFR | KEN | SOL | 57 | TAS | 47 | A | I | CTC TCA | 0.2 | 0.2 |  |  | 2009-04-01 | 2010-12-01 | 2010-03-31 |  | 2012-07-01 | 2012-12-01 | 40000 | -988 | 39012 | 39012.44 | 100% | -0.44 | 0 |  | 3600 | -89 | 3511 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | ASP | KUW | FOA | 63 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 | 2013-12-01 | 60000 | -700 | 59300 | 59300.05 | 100% | -0.05 | 0 |  | 4500 | -52 | 4448 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Preparation of a halon phase-out plan | Individual | ASP | KUW | HAL | 45 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2007-01-01 | 2006-04-01 |  |  | 2010-09-01 | 25000 | -3210 | 21790 | 21790 | 100% | 0 | 0 |  | 1875 | -241 | 1634 | 0 | 0 | CLO |  |  |  | NON-INV
FIN | UNIDO | Preparation of a terminal phase-out management project | Individual | ASP | KUW | PHA | 48 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-07-01 | 2008-08-01 | 25000 | -2 | 24998 | 24998.08 | 100% | -0.08 | 0 |  | 1875 | 0 | 1875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | ASP | KUW | PHA | 52 | INV | 11 | A | I | CFC | 15 | 15 |  |  | 2007-07-01 | 2007-12-01 | 2008-11-01 |  | 2010-11-01 | 2013-04-01 | 220000 | -527 | 219473 | 219472.94 | 100% | 0.06 | 0 |  | 19800 | -47 | 19753 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | KUW | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 70000 | -757 | 69243 | 69242.53 | 100% | 0.47 | 0 |  | 5250 | -57 | 5193 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | KUW | PHA | 66 | INV | 18 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2014-10-01 | 2014-04-30 | 2016-06-01 |  |  | 12000 | 0 | 12000 | 9899.57 | 82.5% | 2100.43 | 1928.16 | 1900 | 900 | 0 | 742 | 158 | 144.612 | 1. In line with our report submitted to the 71st Mtg of the ExCom, the Secretariat has made the inventory modifications for this project and the project budget has been reduced to USD 12,000. 2. Expert has been identified and recruitment will proceed. 3. Activity to be completed and reported to the NOU by the 3rd quarter of 2014. Milestones achieved: Milestone 1: Expert recruited (Yes) Milestone 2: Expert report to NOU (Yes) Milestone 3: (Yes/No) Milestone 4: (Yes/No) Milestone 5: (Yes/No) Activities planned but not implemented, reasons and strategy: n/a Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Activity completed. Milestones achieved: Milestone 1: Expert recruited (Yes) Milestone 2: Expert report to NOU (Yes) Milestone 3: (Yes/No) Milestone 4: (Yes/No) Milestone 5: (Yes/No) Activities planned but not implemented, reasons and strategy: n/a Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Multi-Year | ASP | KUW | PHA | 66 | INV | 20 | A | I | HCFC | 10.9 | 0 |  |  | 2012-04-01 | 2013-01-01 | 2014-04-30 | 2015-12-01 |  |  | 15000 | 0 | 15000 | 4056.72 | 27.04% | 10943.28 | 9645.69 | 9000 | 1125 | 0 | 304 | 821 | 723.4267 | In line with our report submitted to the 71st Mtg of the ExCom, the Secretariat has made the inventory modifications for this project and the project budget has been reduced to USD15,000. 1. Expert has been identified and recruitment will proceed.2. Activity to be completed and reported to the NOU by the 3rd quarter of 2014. Milestones achieved: Milestone 1: Expert recruited (No) Milestone 2: Report submitted (No) Milestone 3: (Yes/No) Milestone 4: (Yes/No) Milestone 5: (Yes/No) Activities planned but not implemented, reasons and strategy: Focus has been on progress in the XPS sector and this activity will be postponed to 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Focus on XPS sector and postponement of this activity to 2015 Any recurring problem? No Any impact on project completion date: No | In line with our report submitted to the 71st Mtg of the ExCom, the Secretariat has made the inventory modifications for this project and the project budget has been reduced to USD15,000. 1. Expert has been identified and recruitment will proceed.2. Activity to be completed and reported to the NOU by the 3rd quarter of 2014. Milestones achieved: Milestone 1: Expert recruited (Yes) Milestone 2: Report submitted (No) Milestone 3: (Yes/No) Milestone 4: (Yes/No) Milestone 5: (Yes/No) Activities planned but not implemented, reasons and strategy: Focus has been on progress in the XPS sector and this activity will be postponed to 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Focus on XPS sector and postponement of this activity to 2015 Any recurring problem? No Any impact on project completion date: No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Comapny) | Multi-Year | ASP | KUW | PHA | 66 | INV | 21 | A | I | HCFC | 49.8 | 0 |  |  | 2012-04-01 | 2013-01-01 | 2014-04-30 | 2017-03-01 |  |  | 3510450 | 0 | 3510450 | 220717.33 | 6.287% | 3289732.67 | 47323.88 | 200000 | 263284 | 0 | 16554 | 246730 | 3549.291 | Similarly to KUW/PHA/66/INV/18 and KUW/PHA/66/INV/20, the Secretariat has made the inventory modifications for this project as well and the project budget has been increased to USD 3,510,450. First stage will focus on the Gulf Insulation and Isofoam. 2. Meeting with Gulf Insulation and Isofoam as well as the NOU has taken place. 3. Tendering equipment will start in April and is expected to be concluded end May; with potential delivery end 2014. Milestones achieved: Milestone 1: TOR for equipment agreed (Yes) Milestone 2: Equipment procured (Yes) Milestone 3: Equipment delivered (No) Milestone 4: Equipment installed (No) Milestone 5: Equipment commissioned (No) Activities planned but not implemented, reasons and strategy: Due to complexity of the scope of equipment and the potential substantial co-financing from beneficiaries both finalization of TOR as well as concluding the procurement took longer. Also, lead time from equipment supplier is substantial; hence equipment delivery couldn't take place in 2014. Actions towards next goals: All on track Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No | Similarly to KUW/PHA/66/INV/18 and KUW/PHA/66/INV/20, the Secretariat has made the inventory modifications for this project as well and the project budget has been increased to USD 3,510,450. First stage will focus on the Gulf Insulation and Isofoam. Equipment has been ordered and will be delivered end 2015. Milestones achieved: Milestone 1: TOR for equipment agreed (Yes) Milestone 2: Equipment procured (Yes) Milestone 3: Equipment delivered (No) Milestone 4: Equipment installed (No) Milestone 5: Equipment commissioned (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: All on track Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No |  |  | INV
FIN | UNIDO | Implementation of the RMP: national recovery and recycling | RMP Update | ASP | KUW | REF | 37 | TAS | 05 | A | I | CFC | 64 | 64 |  |  | 2002-07-01 | 2003-07-01 | 2005-08-01 |  | 2006-12-01 | 2008-12-01 | 448816 | -2441 | 446375 | 446375.13 | 100% | -0.13 | 0 |  | 22441 | 35588 | 58029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon phase-out programme | Individual | EUR | KYR | HAL | 48 | TAS | 12 | A | I | HAL | 2.4 | 2.4 |  |  | 2006-04-01 | 2006-12-01 | 2009-04-01 |  | 2008-12-01 | 2012-05-01 | 50000 | -3838 | 46162 | 46161.89 | 100% | 0.11 | 0 |  | 4500 | -345 | 4155 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of a demonstration project for broccoli, cucurbits, tobacco, seed beds, grain fumigation in El Salvador, Honduras and Nicaragua | Individual | LAC | LAC | FUM | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  |  | 2001-12-01 | 40000 | -29186 | 10814 | 10814 | 100% | 0 | 0 |  | 5200 | -3796 | 1404 | 0 | 0 | CLO
FIN | UNIDO | Project formulation for phase out of ODS in aerosol sector (Cosmaline Industries S.A.) | Individual | ASP | LEB | ARS | 16 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -8784 | 6216 | 6216 | 100% | 0 | 0 |  | 1950 | -1143 | 807 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of CFCs at Cosmaline Industries s.a.al. | Individual | ASP | LEB | ARS | 19 | INV | 05 | A | I | CFC | 87.7 | 87.7 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-07-01 | 212500 | 0 | 212500 | 212500 | 100% | 0 | 0 |  | 27625 | 0 | 27625 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Zeeni's Trading Agency | Individual | ASP | LEB | ARS | 19 | INV | 06 | A | I | CFC | 212 | 212 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 361900 | -9467 | 352433 | 352433 | 100% | 0 | 0 |  | 47047 | -1303 | 45744 | 0 | 0 | FIN
COM | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | LEB | DES | 61 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2014-11-01 |  | 85000 | 0 | 85000 | 84602.66 | 99.53% | 397.34 | 21.82 | 1 | 6375 | 0 | 6345 | 30 | 2 | - Project has been submitted to the 72nd ExCom, but got approval only at the 73rd Meeting. | Project completed. |  |  | NON-INV
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | LEB | DES | 73 | DEM | 83 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2017-03-01 |  |  | 123475 | 0 | 123475 | 0 | 0% | 123475 | 0 | 10000 | 11113 | 0 | 0 | 11113 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014, on the understanding that no further funds would be available for Lebanon for any ODS disposal projects in future; and that any marketing of GHG emission reductions that may be generated by or associated with the project would be subject to a decision by the Executive Committee. The Government of Lebanon, through UNIDO, was requested to establish a monitoring system for the operation of, and the activities associated with, the ODS waste management and disposal demonstration project, and UNIDO was requested to report thereon to the Executive Committee at the completion of the project in 2016, ensuring that no marketing of GHG emission reductions had taken place. 12.7 mt of ODS waste is to be exported for destruction. | - 12.7 mt of ODS waste to be exported for destruction. - Work plan discussed and agreed on with NOU. - Aggregation point for interim-storage of CFCs identified. - National consultant recruited to coordinate transport of cylinders (of approx. 70 companies) to aggregation point in Beirut. Milestones achieved: Milestone 1 - Yes - Legal arrangements for grant approval - Government of Lebanon Milestone 2 - No - CFC cylinders aggregated Milestone 3 - No - Bids for destruction facility prepared and requested Milestone 4 - No - Contract awarded Milestone 5 - No - CFC exported to destruction facility abroad and destroyed Actions towards next goals: - Monitor aggregation of cylinders for interim storage. - Initiate call for proposals from destruction facilities once CFC cylinders are stored at aggregation points, with contents verified. Was there any delay during the reporting year? No, but realistically project is expected to be completed by early 2017 only. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project formulation for the phase out of ODS in the foam sector in 2 plants (Ets. Henri Abdallah and Nasri Karam) | Individual | ASP | LEB | FOA | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-07-01 |  | 1997-03-01 | 1998-08-01 | 20000 | -7358 | 12642 | 12642 | 100% | 0 | 0 |  | 2600 | -959 | 1641 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Nasri Karam and Sons | Individual | ASP | LEB | FOA | 20 | INV | 09 | A | I | CFC | 22 | 22 |  |  | 1996-10-01 | 1997-07-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 100109 | -106 | 100003 | 100003 | 100% | 0 | 0 |  | 13014 | -34 | 12980 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Ets. Henri Abdallah P.F.M. | Individual | ASP | LEB | FOA | 21 | INV | 18 | A | I | CFC | 16.6 | 16.6 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 81291 | -583 | 80708 | 80708 | 100% | 0 | 0 |  | 10568 | -93 | 10475 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants (strawberries) sector | Individual | ASP | LEB | FUM | 33 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -904 | 29096 | 29096.46 | 100% | -0.46 | 0 |  | 3900 | -123 | 3777 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 44 | A | I | MBR | 26.1 | 26.1 |  |  | 2001-07-01 | 2002-04-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide (strawberries): release of second tranche | Multi-Year | ASP | LEB | FUM | 38 | INV | 52 | A | I | MBR | 10.1 | 10.1 |  |  | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2007-12-01 | 421946 | 0 | 421946 | 421945.97 | 100% | 0.03 | 0 |  | 54853 | 0 | 54853 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 54 | A | I | MBR | 14.2 | 25.3 |  |  | 2003-12-01 | 2005-07-01 | 2004-12-01 |  | 2008-12-01 | 2011-05-01 | 450000 | -18846 | 431154 | 431153.54 | 100% | 0.46 | 0 |  | 33750 | -1413 | 32337 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 62 | A | I | MBR | 9 | 9 |  |  | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 | 2010-12-01 | 42504 | -692 | 41812 | 41811.71 | 100% | 0.29 | 0 |  | 3188 | -52 | 3136 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation for phase out of ODS in the refrigeration sector (Weather-mate and OPACO Ltd.) | Individual | ASP | LEB | REF | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1997-08-01 | 1995-07-01 |  | 1997-12-01 | 2000-12-01 | 15000 | -1497 | 13503 | 13503 | 100% | 0 | 0 |  | 1950 | -197 | 1753 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Lebanese Modern Industrial and Trading Co. | Individual | ASP | LEB | REF | 22 | INV | 19 | A | I | CFC | 135 | 135 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1999-12-01 | 2002-10-01 | 1313121 | -65527 | 1247594 | 1247593.65 | 100% | 0.35 | 0 |  | 170706 | -8776 | 161930 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141B and CFC-12 to HFC-134a in the manufacture of commercial refrigeration at the first group of Lebanese Commercial Refrigerator Manufacturers | Individual | ASP | LEB | REF | 29 | INV | 33 | A | I | CFC | 18.5 | 18.5 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2000-07-01 | 2002-09-01 | 258006 | -8773 | 249233 | 249233.23 | 100% | -0.23 | 0 |  | 33541 | -1192 | 32349 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the second group of Lebanese commercial refrigeration manufacturers | Individual | ASP | LEB | REF | 31 | INV | 36 | A | I | CFC | 15.66 | 15.66 |  |  | 2000-07-01 | 2000-09-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 203191 | -1043 | 202148 | 202147.72 | 100% | 0.28 | 0 |  | 26415 | -177 | 26238 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the third group of Lebanese commercial refrigerator manufacturers | Individual | ASP | LEB | REF | 31 | INV | 39 | A | I | CFC | 15.8 | 15.8 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 208498 | -8133 | 200365 | 200364.97 | 100% | 0.03 | 0 |  | 27105 | -1099 | 26006 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of two umbrella investment projects in the commercial refrigeration sector, covering six SME factories each | Individual | ASP | LEB | REF | 31 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1076 | 18924 | 18923.55 | 100% | 0.45 | 0 |  | 2600 | -144 | 2456 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two umbrella projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 33 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-01-01 | 2002-04-01 |  | 2002-07-01 | 2003-06-01 | 15000 | -229 | 14771 | 14770.5 | 100% | 0.5 | 0 |  | 1950 | -33 | 1917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 4th group of enterprises | Individual | ASP | LEB | REF | 34 | INV | 45 | A | I | CFC | 18.8 | 18.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2004-06-01 | 2005-12-01 | 279672 | -9510 | 270162 | 270161.81 | 100% | 0.19 | 0 |  | 36357 | -1292 | 35065 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of 2 umbrella investment projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 36 | PRP | 47 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | AFR | LIB | FOA | 63 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-02-01 | 2012-03-31 | 2016-07-31 |  |  | 60000 | 0 | 60000 | 24109.04 | 40.18% | 35890.96 | 5412.66 | 14000 | 4500 | 0 | 1808 | 2692 | 406 | - Project document prepared and submitted for the consideration of the 72nd Meeting of the ExCom in May 2014; - Evidence documents on the ratification of Beijing and Montreal Amendments have been received; - Government confirmation on Licensing system received. - Project document discussed with MLFS; agreement not yet reached. Effective functioning of licensing and quota as well as HCFC 22 consumption data still questioned. - Government letter to correct 2010 consumption sent to Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Activities planned but not implemented, reasons and strategy: Assistance to the Government to establish and operationalize licensing and quota system on HCFCs. Reason: unrest in Libya, un-stable Government. Strategy: work with EGA staff, Ozone Officer and NOU staff to assist with the preparation of necessary legislation, licensing and quota system. To review and update HPMP accordingly. Actions towards next goals: Continue with assistance to EGA Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes If yes, implications: Delayed submission of HPMP Stage I, non compliance with HCFC reduction schedule Any action required by Executive Committee? No | - Project document for HPMP Stage I is being updated. - Formal announcement on non-compliance received. - Action plan to return to compliance prepared and sent to Ozone Secretariat, for further submission to the 54th Meeting of the ImpCom. - Libyan Government licensing system regulations also submitted to the Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Continue with assistance to EGA. Follow recommendation of the 54th Meeting of the ImpCom, to return the Country back to compliance in shortest possible time. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes Uncertainty of ExCom approval. If yes, implications: Potential thread of further non compliance with HCFC reduction schedule Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector (methyl bromide) | Individual | AFR | LIB | FUM | 45 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-11-01 | 15000 | -1137 | 13863 | 13863.13 | 100% | -0.13 | 0 |  | 1125 | -85 | 1040 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others | Multi-Year | AFR | LIB | FUM | 47 | INV | 27 | A | I | MBR | 56 | 56 |  |  | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2012-10-01 | 743000 | 0 | 743000 | 743000.05 | 100% | -0.05 | 0 |  | 55725 | 0 | 55725 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a halon phase-out plan | Individual | AFR | LIB | HAL | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 25000 | -264 | 24736 | 24736 | 100% | 0 | 0 |  | 1875 | -20 | 1855 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | AFR | LIB | HAL | 47 | TAS | 26 | A | I | HAL | 653.9 | 0 |  |  | 2005-11-01 | 2006-09-01 | 2008-12-01 |  |  | 2010-09-01 | 343500 | -335125 | 8375 | 8375.18 | 100% | -0.18 | 0 |  | 25763 | -25135 | 628 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | LIB | PHA | 41 | INV | 22 | A | I | CFC | 150 | 150.4 |  |  | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-08-01 | 2008-12-01 | 1500000 | -21 | 1499979 | 1499978.61 | 100% | 0.39 | 0 |  | 112500 | -2 | 112498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | AFR | LIB | PHA | 45 | INV | 25 | A | I | CFC | 124 | 124 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2013-12-01 | 2014-04-01 | 720000 | -679 | 719321 | 719321.13 | 100% | -0.13 | 0 |  | 54000 | -51 | 53949 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | National ODS phase-out plan: 3rd tranche | Multi-Year | AFR | LIB | PHA | 54 | INV | 28 | A | I | CFC | 176 | 176 |  |  | 2008-04-01 | 2010-03-01 | 2009-03-31 |  | 2013-12-01 |  | 277947 | 0 | 277947 | 254709.84 | 91.64% | 23237.16 | 22354.63 | 22000 | 20846 | 0 | 19103 | 1743 | 1677 |  |  |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | LIB | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2016-07-31 |  |  | 85000 | 0 | 85000 | 64699.08 | 76.12% | 20300.92 | 1789.82 | 17437 | 6375 | 0 | 4852 | 1523 | 134 | - Project document prepared and submitted for the consideration of the 72nd Meeting of the ExCom in May 2014; - Evidence documents on the ratification of Beijing and Montreal Amendments have been received; - Government confirmation on Licensing system received. - Project document discussed with MLFS; agreement not yet reached. Effective functioning of licensing and quota as well as HCFC 22 consumption data still questioned. - Government letter to correct 2010 consumption sent to Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Activities planned but not implemented, reasons and strategy: Assistance to the Government to establish and operationalize licensing and quota system on HCFCs. Reason: unrest in Libya, un-stable Government. Strategy: work with EGA staff, Ozone Officer and NOU staff to assist with the preparation of necessary legislation, licensing and quota system. To review and update HPMP accordingly. Actions towards next goals: Continue with assistance to EGA Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes If yes, implications: Delayed submission of HPMP Stage I, non compliance with HCFC reduction schedule Any action required by Executive Committee? No | - Project document for HPMP Stage I is being updated. - Formal announcement on non-compliance received. - Action plan to return to compliance prepared and sent to Ozone Secretariat, for further submission to the 54th Meeting of the ImpCom. - Libyan Government licensing system regulations also submitted to the Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Continue with assistance to EGA. Follow recommendation of the 54th Meeting of the ImpCom, to return the Country back to compliance in shortest possible time. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes Uncertainty of ExCom approval. If yes, implications: Potential thread of further non compliance with HCFC reduction schedule Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | LIB | PHA | 63 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-08-01 | 2012-03-31 | 2016-07-31 |  |  | 65000 | 0 | 65000 | 41065.19 | 63.18% | 23934.81 | 10566.58 | 10567 | 4875 | 0 | 3080 | 1795 | 792 | - Project document prepared and submitted for the consideration of the 72nd Meeting of the ExCom in May 2014; - Evidence documents on the ratification of Beijing and Montreal Amendments have been received; - Government confirmation on Licensing system received. - Project document discussed with MLFS; agreement not yet reached. Effective functioning of licensing and quota as well as HCFC 22 consumption data still questioned. - Government letter to correct 2010 consumption sent to Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Activities planned but not implemented, reasons and strategy: Assistance to the Government to establish and operationalize licensing and quota system on HCFCs. Reason: unrest in Libya, un-stable Government. Strategy: work with EGA staff, Ozone Officer and NOU staff to assist with the preparation of necessary legislation, licensing and quota system. To review and update HPMP accordingly. Actions towards next goals: Continue with assistance to EGA Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes If yes, implications: Delayed submission of HPMP Stage I, non compliance with HCFC reduction schedule Any action required by Executive Committee? No | - Project document for HPMP Stage I is being updated. - Formal announcement on non-compliance received. - Action plan to return to compliance prepared and sent to Ozone Secretariat, for further submission to the 54th Meeting of the ImpCom. - Libyan Government licensing system regulations also submitted to the Ozone Secretariat. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Continue with assistance to EGA. Follow recommendation of the 54th Meeting of the ImpCom, to return the Country back to compliance in shortest possible time. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislative process in the country very slow. Action: continuous assistance to EGA Any recurring problem? Yes If yes, description of the problem/s: unstable Government Any impact on project completion date: Yes Uncertainty of ExCom approval. If yes, implications: Potential thread of further non compliance with HCFC reduction schedule Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in the Refrigeration sector | Individual | AFR | LIB | REF | 30 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2003-07-01 | 2004-04-01 | 20000 | -550 | 19450 | 19449.96 | 100% | 0.04 | 0 |  | 2600 | -76 | 2524 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS in the production of refrigerators and freezers at Electrical Household Appliance Manufacturing | Individual | AFR | LIB | REF | 32 | INV | 03 | A | I | CFC | 53.4 | 53.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-06-01 |  | 2004-03-01 | 2009-12-01 | 558113 | -1527 | 556586 | 556585.87 | 100% | 0.13 | 0 |  | 71392 | -168 | 71224 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in the commercial refrigeration sector | Individual | AFR | LIB | REF | 33 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-03-01 |  | 2002-04-01 |  |  | 2003-06-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | AFR | LIB | REF | 36 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-06-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 20000 | -722 | 19278 | 19277.77 | 100% | 0.23 | 0 |  | 2600 | -98 | 2502 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of country programme | Individual | AFR | LIB | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 80000 | -3440 | 76560 | 76560.15 | 100% | -0.15 | 0 |  | 10400 | -463 | 9937 | 0 | 0 | FIN
FIN | UNIDO | Creation of the National Ozone Unit | Individual | AFR | LIB | SEV | 32 | INS | 04 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2009-06-01 | 2011-12-01 | 157000 | -48043 | 108957 | 108956.98 | 100% | 0.02 | 0 |  | 20410 | -6246 | 14164 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan | Individual | AFR | LIB | SEV | 38 | PRP | 21 | A | I | CFC | 0 | 0 |  |  | 2002-11-01 | 2003-09-01 | 2003-12-01 |  | 2005-06-01 | 2006-08-01 | 40000 | -468 | 39532 | 39531.5 | 100% | 0.5 | 0 |  | 5200 | -61 | 5139 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Renewal of institutional strengthening project (phase II) | Individual | AFR | LIB | SEV | 59 | INS | 31 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2014-03-01 |  | 73702 | 62363 | 136065 | 135168.21 | 99.34% | 896.79 | 878.7 | 879 | 5528 | 4677 | 10138 | 67 | 66 | - Project was operationally completed in 2014. - Activities executed in 2014 will be financially completed in 2015. |  |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase III: 12/2013-11/2015) | Individual | AFR | LIB | SEV | 71 | INS | 34 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-07-01 | 2015-11-30 | 2016-04-01 |  |  | 136065 | 0 | 136065 | 42940.31 | 31.56% | 93124.69 | 8633.62 | 60000 | 9525 | 0 | 3006 | 6519 | 604.3534 | - Briefing mission at UNIDO HQ organized in January 2014 and Work plan for the year 2014 was agreed. - NCs contract extension initiated in May 2014. - Awareness materials local bidding and purchase organized during the 1st half 2014; - Data collection activities and monitoring activities continued in 2014. Milestones achieved: Milestone 1: Initiation of project implementation - Yes Milestone 2: NOU staff contracts released - Yes Milestone 3: Awareness materials publication and distribution - Yes Actions towards next goals: Preparation of work plan for the year 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: In spite of the security situation that affected disbursement by means of delays, the project achieved relevant progress. Any recurring problem? Yes If yes, description of the problem/s: Disbursement continues to be affected by the security situation and reduced activity of the local UNDP Office. Any action required by Executive Committee? No | - NOU staff and consultants contracts extended by July 2015 and based on progress reports, NOU staff contracts will be extended by end of the year. - Local missions organized in view of data collection and verification of the HCFCs consumption data. - Work plan for follow-up of legislation approval process agreed with counterpart. Milestones achieved: Milestone 1: NOU staff contracts - Yes Milestone 2: Work plan for following up legislative approval process - Yes Milestone 3:New legislation in place - No Activities planned but not implemented, reasons and strategy: Publication of new legislation pending upon approval process. Actions towards next goals: Commitment of remaining balance and terminal report in view of next IS extension submission achieved as of April 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Some delays (3 - 5 months) in disbursements in the period January - May 2015. Situation improved in the country and there are no major delays expected for the second half of 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV |  | To report to the 75th meeting on the licensing system for ODS imports and exports
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | AFR | MAG | FUM | 45 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 40000 | -724 | 39276 | 39275.61 | 100% | 0.39 | 0 |  | 3600 | -65 | 3535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | INV | 16 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-01 |  | 2008-11-01 | 2009-05-01 | 78000 | -13 | 77987 | 77986.83 | 100% | 0.17 | 0 |  | 7020 | -1 | 7019 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | INV | 19 | A | I | CFC CTC | 2.4 | 2.4 |  |  | 2008-11-01 | 2009-02-01 | 2009-11-30 |  | 2009-11-01 | 2010-12-01 | 47000 | -2474 | 44526 | 44526.18 | 100% | -0.18 | 0 |  | 4230 | -223 | 4007 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2016-12-01 |  |  | 140000 | 0 | 140000 | 122003.24 | 87.15% | 17996.76 | 4622.14 | 5000 | 10500 | 0 | 9150 | 1350 | 347 | - Training for the fisheries sector carried out in 2014. - Equipment distribution is only outstanding for Tamatave and Tulear, which should start in June 2014. - Left open to enable to use funds together with the 2nd tranche. Milestones achieved: Milestone 1: Yes - 24 technicians from the fisheries sector trained on alternatives to HCFCs. Milestone 2: Yes - All equipment delivered to Tamatave and Tulear Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - Remaining balance will be used towards training on reclamation and incentives for reclamation. was there any delay during the reporting year? No, but project needs to be extended until the new tranche is approved, so that the Remaining funding can be properly utilized. any recurring problem? No any impact on project completion date: No any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | ASP | MAL | FOA | 18 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-02-01 |  | 1999-02-01 | 2000-07-01 | 40000 | -35 | 39965 | 39965 | 100% | 0 | 0 |  | 5200 | -13 | 5187 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Phasing out ODS at Summer Technologies Sdn. Bhd. | Individual | ASP | MAL | FOA | 23 | INV | 100 | A | I | CFC | 12.1 | 12.1 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 89407 | 0 | 89407 | 89407.11 | 100% | -0.11 | 0 |  | 11623 | 0 | 11623 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Kean Chong Industries Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 101 | A | I | CFC | 16.3 | 16.3 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-11-23 | 107819 | 0 | 107819 | 107819 | 100% | 0 | 0 |  | 14016 | 0 | 14016 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Visdamax Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 102 | A | I | CFC | 18.5 | 18.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 139959 | 0 | 139959 | 139958.67 | 100% | 0.33 | 0 |  | 18195 | 0 | 18195 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (rigid polyurethane) for Chon Son, Ngui Soon, Ming Soon, Yon Tuck | Individual | ASP | MAL | FOA | 24 | PRP | 110 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 20000 | -205 | 19795 | 19795 | 100% | 0 | 0 |  | 2600 | -31 | 2569 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the insulation of GRP fish boxes and flotation buoys at C.C. Chong Co. | Individual | ASP | MAL | FOA | 26 | INV | 112 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-11-01 | 1999-03-01 | 2000-06-01 |  | 2000-05-01 | 2001-09-01 | 34583 | 0 | 34583 | 34583.03 | 100% | -0.03 | 0 |  | 4496 | -1 | 4495 | 0 | 0 | FIN
FIN | UNIDO | The replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Ming Soon Enterprise Sdn. Bhd. | Individual | ASP | MAL | FOA | 26 | INV | 113 | A | I | CFC | 6.2 | 6.23 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-02-01 | 2002-09-01 | 48799 | 0 | 48799 | 48798.94 | 100% | 0.06 | 0 |  | 6344 | -8 | 6336 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Yong Tuck Refrigerators Trading Co. | Individual | ASP | MAL | FOA | 27 | INV | 120 | A | I | CFC | 8 | 8 |  |  | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2000-06-01 | 2001-09-01 | 61735 | -643 | 61092 | 61091.82 | 100% | 0.18 | 0 |  | 8026 | -97 | 7929 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the foam sector (rigid polyrethane) | Individual | ASP | MAL | FOA | 27 | PRP | 118 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 25000 | -47 | 24953 | 24953.14 | 100% | -0.14 | 0 |  | 3250 | -11 | 3239 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption by conversion to HCFC-141b AT Perniagaan Hower in the manufacture of sandwich panels | Individual | ASP | MAL | FOA | 28 | INV | 124 | A | I | CFC | 5.3 | 5.3 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 41499 | -87 | 41412 | 41412.44 | 100% | -0.44 | 0 |  | 5395 | -20 | 5375 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology at Automated Plastic System Sdn. Bhd. in the manufacture of insulated fishing boxes | Individual | ASP | MAL | FOA | 28 | INV | 125 | A | I | CFC | 5.2 | 5.2 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-01-01 | 2001-12-01 | 40716 | 0 | 40716 | 40716.48 | 100% | -0.48 | 0 |  | 5293 | 0 | 5293 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption at Chong Brother Group of Companies | Individual | ASP | MAL | FOA | 28 | INV | 127 | A | I | CFC | 27.6 | 27.6 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 216108 | 0 | 216108 | 216107.83 | 100% | 0.17 | 0 |  | 28094 | -21 | 28073 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the rigid foam sector | Individual | ASP | MAL | FOA | 31 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2001-07-01 |  | 2002-01-01 | 2003-05-01 | 20000 | -740 | 19260 | 19259.64 | 100% | 0.36 | 0 |  | 2600 | -100 | 2500 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Composites Truck Body Sdn., Bhd. | Individual | ASP | MAL | FOA | 34 | INV | 143 | A | I | CFC | 8.1 | 8.1 |  |  | 2001-07-01 | 2002-12-01 | 2004-02-01 |  | 2003-12-01 | 2003-12-01 | 63280 | -129 | 63151 | 63150.56 | 100% | 0.44 | 0 |  | 8226 | -29 | 8197 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigerating equipment at Tung Kiong Factories Sdn. Bhd. | Individual | ASP | MAL | REF | 32 | INV | 143 | A | I | CFC | 18.9 | 18.9 |  |  | 2000-12-01 | 2001-10-01 | 2003-07-01 |  | 2003-03-01 | 2004-05-01 | 202075 | -503 | 201572 | 201571.65 | 100% | 0.35 | 0 |  | 26270 | -107 | 26163 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | EUR | MDN | ARS | 30 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2001-07-01 | 15000 | -2425 | 12575 | 12575.43 | 100% | -0.43 | 0 |  | 1950 | -318 | 1632 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | Individual | EUR | MDN | ARS | 32 | INV | 17 | A | I | CFC | 25 | 25 |  |  | 2000-12-01 | 2001-12-01 | 2003-03-01 |  |  | 2008-12-01 | 110000 | -10533 | 99467 | 99467 | 100% | 0 | 0 |  | 14300 | -1369 | 12931 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 05 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2002-09-01 | 520125 | -4895 | 515230 | 515230.18 | 100% | -0.18 | 0 |  | 67616 | -742 | 66874 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from manufacturing of rigid PU sandwich panels at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 06 | A | I | CFC | 67.6 | 67.6 |  |  | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1997-12-01 | 2002-05-01 | 284236 | -6661 | 277575 | 277574.83 | 100% | 0.17 | 0 |  | 36951 | -923 | 36028 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in methyl bromide (tobacco, pepper, tomatoes) | Individual | EUR | MDN | FUM | 25 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - three alternatives to the use of methyl bromide: non-soil cultivation, biofumigation and low dose chemicals in tobacco and horticultural production | Individual | EUR | MDN | FUM | 26 | DEM | 09 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-04-01 | 2003-05-01 | 259600 | -558 | 259042 | 259042.44 | 100% | -0.44 | 0 |  | 33748 | -126 | 33622 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | MDN | FUM | 30 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -499 | 19501 | 19500.93 | 100% | 0.07 | 0 |  | 2600 | -69 | 2531 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling and horticulture production sector | Individual | EUR | MDN | FUM | 32 | INV | 16 | A | I | MBR | 27.2 | 27.2 |  |  | 2000-12-01 | 2001-10-01 | 2006-01-01 |  | 2004-12-01 | 2006-05-01 | 1075207 | -3327 | 1071880 | 1071880.3 | 100% | -0.3 | 0 |  | 128273 | -553 | 127720 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in preparation of the national halon management plan | Individual | EUR | MDN | HAL | 37 | TAS | 19 | A | I | HAL | 32.1 | 32.1 |  |  | 2002-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-05-01 | 2004-02-01 | 25000 | -8 | 24992 | 24992.06 | 100% | -0.06 | 0 |  | 3250 | -6 | 3244 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | MDN | PHA | 45 | INV | 21 | A | I | CFC | 10 | 10 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-11-01 | 2007-12-01 | 154210 | -134 | 154076 | 154075.51 | 100% | 0.49 | 0 |  | 11566 | -10 | 11556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | EUR | MDN | PHA | 50 | INV | 23 | A | I | CFC | 5 | 5 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-11-01 | 2008-07-01 | 79871 | -123 | 79748 | 79748.05 | 100% | -0.05 | 0 |  | 5990 | -9 | 5981 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (third tranche) | Multi-Year | EUR | MDN | PHA | 53 | INV | 24 | A | I | CFC | 5 | 5 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2008-11-01 | 2010-05-01 | 15000 | -15 | 14985 | 14985.03 | 100% | -0.03 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MDN | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-04-01 | 2010-12-01 | 85000 | -634 | 84366 | 84366.02 | 100% | -0.02 | 0 |  | 6375 | -48 | 6327 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (fourth tranche) | Multi-Year | EUR | MDN | PHA | 56 | INV | 26 | A | I | CFC | 5 | 5 |  |  | 2008-11-01 | 2009-08-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 14999.99 | 100% | 0.01 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (fifth tranche) | Multi-Year | EUR | MDN | PHA | 59 | INV | 28 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2013-12-01 | 2014-04-01 | 15000 | -941 | 14059 | 14040.68 | 99.87% | 18.32 | 0 |  | 1125 | -71 | 1053 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | MDN | PHA | 60 | INV | 29 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2015-12-31 |  | 2011-03-01 | 2012-05-01 | 15000 | 0 | 15000 | 14999.98 | 100% | 0.02 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | FIN
FIN | UNIDO | HCFC phase-out management plan (advance funding for the institutional strengthening) | Multi-Year | EUR | MDN | PHA | 63 | INV | 30 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-06-01 | 2012-03-31 |  | 2011-12-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000.01 | 100% | -0.01 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, remainder of second tranche) | Multi-Year | EUR | MDN | PHA | 64 | INV | 31 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 |  | 2013-12-01 |  | 81000 | 0 | 81000 | 80998.72 | 100% | 1.28 | 0 | 1 | 6075 | 0 | 6075 | 0 | 0 |  |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, third tranche) (conversion from HCFC-141b to HFCs in the manufacture of polyurethane foam for the commercial refrigeration units, sandwich panels and insulated doors) | Multi-Year | EUR | MDN | PHA | 67 | INV | 32 | A | I | HCFC | 1.6 | 1.6 |  |  | 2012-07-01 | 2012-11-01 | 2014-07-31 |  | 2014-12-01 |  | 136955 | 0 | 136955 | 124422.16 | 90.85% | 12532.84 | 8205.84 | 12000 | 10272 | 0 | 9332 | 940 | 615.438 | - Bidding on the supply of a new foaming machine to Koper completed. - Supplier selected and the purchase order placed. - Equipment delivered to the project side. Installation and commissioning completed in 2014. Training activities for technicians organized. Milestones achieved: Milestone 1: Contract for equipment purchase concluded - Yes Milestone 2: Delivery of equipment and commissioning - Yes Milestone 3: New technology in place - Yes Actions towards next goals: Completion of the foam conversion component of the project in 2015 (at the end of 2014, the conversion of 2 companies to non-HCFCs technologies was completed and bidding for the remaining 2 foam companies was planned for 2015) If yes, reasons and action plan: (narrative): NA Any recurring problem? No Any impact on project completion date: Yes If yes, implications: 3 months delay due to administrative verification of expenditures and obligations clearance in the new financial system Any action required by Executive Committee? No | - Tranche 3 implementation completed in 2014. - Financial completion took place in March 2015. |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, third tranche) | Multi-Year | EUR | MDN | PHA | 67 | INV | 33 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2012-11-01 | 2013-07-31 |  | 2014-12-01 |  | 158000 | 0 | 158000 | 150785.64 | 95.43% | 7214.36 | 6000 | 6118 | 11850 | 0 | 11309 | 541 | 450 | - Bids evaluated, PO issued, equipment delivered to the project site. - Operational completion was achieved early 2014, financial completion to be concluded. Milestones achieved: Milestone 1: Contract for equipment purchase - Yes Milestone 2: Equipment delivered - Yes Was there any delay during the reporting year? Yes If yes, reasons and action plan: (narrative): 3 months delay in financial completion cause by verification of expenditure and closure of obligations in the new financial system Any recurring problem? No Any impact on project completion date: yes If yes, implications: Slight delay compared to the planned completion date as per BP 2014. Any action required by Executive Committee? No | - Tranche activities completed in 2014. - Financial completion in early 2015. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, fourth tranche) | Multi-Year | EUR | MDN | PHA | 70 | INV | 34 | A | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-12-01 | 2014-07-31 | 2015-09-01 |  |  | 148000 | 0 | 148000 | 122051.2 | 82.47% | 25948.8 | 10000 | 25069 | 11100 | 0 | 9154 | 1946 | 750 | - Training workshops for customs officers and service technicians implemented. - Additional R&R equipment procured and disseminated. Milestones achieved: Milestone 1: Customs training - Yes Milestone 2: Equipment delivery, commissioning and training - Yes Milestone 3: Legislation publication into OJ for logbooks - Yes Actions towards next goals: Work plan for the year 2015 Was there any delay during the reporting year? Yes If yes, reasons and action plan: There was a slight delay in financial completion due to interrelation with tranche 5 and due to administrative clearance of the pending obligations in the new financial system Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The slight delay in achieving financial completion is due to interrelation with tranche 5 Any action required by Executive Committee? No | - Completion of training activities on logbooks and e-reporting. - Completion of tranche 4 implementation and progress report. Milestones achieved: Milestone 1: Completion of training activities on logbooks and e-reporting - Yes Milestone 2: Completion of tranche IV implementation - Yes Actions towards next goals: Work plan for progressing the 5th tranche implementation agreed in the end of 2014. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: slight delay in financial completion due to interrelation with tranche 5 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, fifth tranche) | Multi-Year | EUR | MDN | PHA | 72 | INV | 35 | A | I | HCFC | 0.2 | 0 |  |  | 2014-05-01 | 2014-12-01 | 2016-05-31 | 2016-05-31 |  |  | 82000 | 0 | 82000 | 8329.62 | 10.16% | 73670.38 | 0 | 35848 | 6150 | 0 | 625 | 5525 | 0 | - Tranche approved at the 72nd Meeting of the ExCom in May 2014. - Training following publication of guidelines for e-reporting continued and will be finalized in 2015. - Logbooks keeping regulation / e-registration is applicable as of 1st January 2015. - Training of service technicians was achieved as per the tranche 5 work plan. Milestones achieved: Milestone 1: National consultants contracted - Yes Milestone 2: Training activities completed - Yes Actions towards next goals: Implement and finalize activities as per work plan. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Conversion of foam Company Zlatna Raka was finalized (equipment purchase and delivery has been achieved). - Training activities as per the tranche 5 work plan are schedule and under implementation. Milestones achieved: Milestone 1: Equipment delivery and commissioning at Zlatna Raka Co. - Yes Milestone 2: Training activities completed - Yes Milestone 3: Consumption verification report contracted - Yes Actions towards next goals: Progress report elaboration initiated in view of submission of the Tranche 6 request. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Phasing out of CFCs at the refrigerator plant of Frinko | Individual | EUR | MDN | REF | 20 | INV | 03 | A | I | CFC | 104 | 104 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1998-12-01 | 2001-12-01 | 1081724 | -556 | 1081168 | 1081168.35 | 100% | -0.35 | 0 |  | 140624 | -295 | 140329 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | MDN | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 30000 | -4462 | 25538 | 25538 | 100% | 0 | 0 |  | 3900 | -585 | 3315 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | MDN | REF | 28 | TAS | 10 | A | I | CFC | 13.5 | 13.5 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2002-02-01 | 2003-12-01 | 220044 | -43661 | 176383 | 176382.7 | 100% | 0.3 | 0 |  | 28606 | -5713 | 22893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | MDN | REF | 28 | TRA | 11 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-06-01 |  | 2002-03-01 | 2003-05-01 | 70000 | -6146 | 63854 | 63853.74 | 100% | 0.26 | 0 |  | 9100 | -812 | 8288 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers | RMP | EUR | MDN | REF | 28 | TRA | 15 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-03-01 |  | 2002-03-01 | 2003-05-01 | 37180 | -6973 | 30207 | 30207.28 | 100% | -0.28 | 0 |  | 4833 | -912 | 3921 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a Country Programme | Individual | EUR | MDN | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-08-01 | 1995-12-01 |  | 1996-12-01 | 1998-08-01 | 80000 | -7780 | 72220 | 72220 | 100% | 0 | 0 |  | 10400 | -1026 | 9374 | 0 | 0 | FIN
FIN | UNIDO | Preparation of projects in the refrigeration, aerosol and foam sector | Individual | EUR | MDN | SEV | 18 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-01-01 | 1996-03-01 |  | 2000-12-01 | 2002-05-01 | 30000 | -3675 | 26325 | 26325.22 | 100% | -0.22 | 0 |  | 3900 | -483 | 3417 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | MDN | SEV | 20 | INS | 04 | N | I |  | 0 | 0 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-08-01 | 2001-07-01 | 152900 | 0 | 152900 | 152900 | 100% | 0 | 0 |  | 19877 | -25 | 19852 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Institutional strengthening for Montreal Protocol related activities, Phase II | Individual | EUR | MDN | SEV | 30 | INS | 12 | N | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 101950 | 0 | 101950 | 101949.6 | 100% | 0.4 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MDN | SEV | 35 | INS | 18 | N | I |  | 0 | 0 |  |  | 2001-12-01 | 2002-08-01 | 2004-01-01 |  | 2004-07-01 | 2005-09-01 | 101950 | 0 | 101950 | 101949.96 | 100% | 0.04 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project: phase IV | Individual | EUR | MDN | SEV | 42 | INS | 20 | N | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-05-01 | 132347 | 0 | 132347 | 132347 | 100% | 0 | 0 |  | 9926 | 0 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase V) | Individual | EUR | MDN | SEV | 48 | INS | 22 | N | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2008-04-01 |  | 2008-12-01 | 2011-05-01 | 132347 | -1127 | 131220 | 131220.16 | 100% | -0.16 | 0 |  | 9926 | -84 | 9842 | 0 | -1 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MDN | SEV | 57 | INS | 27 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2012-02-01 | 132347 | -43 | 132304 | 132304.06 | 100% | -0.06 | 0 |  | 9926 | -3 | 9923 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a MDI project, including the development of a national transitional strategy for the sector | Individual | LAC | MEX | ARS | 52 | PRP | 134 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-04-01 | 2008-07-01 | 50000 | -275 | 49725 | 49724.98 | 100% | 0.02 | 0 |  | 3750 | -21 | 3729 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | MEX | ARS | 53 | INV | 135 | A | I | CFC | 97 | 97 |  |  | 2007-11-01 | 2008-04-01 | 2010-01-31 |  | 2011-09-01 | 2013-10-01 | 2630503 | -6079 | 2624424 | 2624423.87 | 100% | 0.13 | 0 |  | 197288 | -456 | 196832 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Phase-out of HCFC-22 and HCFC-141b in aerosol manufacturing at Silimex | Multi-Year | LAC | MEX | ARS | 63 | INV | 156 | A | I | HCFC | 11.1 | 11.1 |  |  | 2011-04-01 | 2011-07-01 | 2013-09-30 |  | 2014-12-01 |  | 520916 | 0 | 520916 | 520893.65 | 100% | 22.35 | 0 | 1 | 39069 | 0 | 39067 | 2 | 0 | - Installation and commissioning of equipment finished in April. Milestones achieved: Milestone 1: Yes - Installation and commissioning of equipment finished in April. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  |  | INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (aerosol sector) | Individual | LAC | MEX | ARS | 72 | PRP | 169 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-06-01 | 2015-05-31 |  | 2014-12-01 |  | 40000 | 0 | 40000 | 23467.99 | 58.67% | 16532.01 | 16365.83 | 15000 | 2800 | 0 | 1643 | 1157 | 1146 | - The project was approved at the 72nd Meeting of the Executive Committee on an exceptional basis in order to optimize the aerosol sector plan proposal to explore options to further reduce its climate impact. - Immediately after approval consultants were recruited and the project proposal has been reviewed and amended and a revised Stage II HPMP was submitted to and approved by the Executive Committee at its 73rd Meeting in November 2014. | - The project will be financially completed upon clearance of all outstanding obligations. |  |  | NON-INV
FIN | UNIDO | Preparation of ODS disposal pilot project | Individual | LAC | MEX | DES | 57 | PRP | 142 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-10-01 | 2010-12-31 |  | 2011-12-01 | 2012-04-01 | 50000 | -872 | 49128 | 49127.52 | 100% | 0.48 | 0 |  | 3750 | -65 | 3685 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | LAC | MEX | DES | 63 | DEM | 154 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2013-03-31 | 2016-04-01 |  |  | 927915 | 0 | 927915 | 222549.14 | 23.98% | 705365.86 | 354307.25 | 225195 | 69594 | 0 | 16691 | 52903 | 26573 | - The Contractor selected for the disposal of a 1st batch of 74.1 metric tonnes of ODS waste reported on arrangements made with 3rd-parties for execution of the works, without reporting on actual disposal. - Bidding process for the destruction of a second batch was initiated but it was canceled due to delays in implementation of the 1st batch. Activities planned but not implemented, reasons and strategy: Destruction of the first batch of ODS waste was scheduled to take place in 2014 but it did not take place. UNIDO tried to overcome the difficulties presented by the Contractor in executing the works. Actions towards next goals: In the event of the Contractor not being able to deliver, the contract will be cancelled and a new Call for Bids will take place. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The reason for the delay was the difficulties reported by the Contractor to undertake disposal of the 1st batch of 74.1 metric tonnes of ODS waste. In view of the difficulties, UNIDO and the NOU followed up closely to facilitate the Contractor's work, with no success. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date delayed due to the problems to complete works related to disposal of the 1st batch of ODS waste. Any action required by Executive Committee? No | - Due to the incapability of the selected Contractor to execute the works, UNIDO cancelled the contract and issued a new Call for Bids. Milestones achieved: Milestone 1: Yes - contract signed with a new Contractor for the disposal of the 1st batch of 74.1 metric tonnes of ODS waste Milestone 2: Yes - trial disposal operations in a cement kiln facility in order for the company to obtain the permits to destroy ODS waste. Disposal of 1,000 kg. Activities planned but not implemented, reasons and strategy: Disposal of the 1st batch of 74.1 metric tonnes of ODS waste was not undertaken due to the lack of capacity of the selected Contractor to execute the works. Actions towards next goals: (-) Disposal of the 1st batch of 74.1 metric tonnes of ODS waste (-) Call for bids for the disposal of a 2nd batch of ODS waste Was there any delay during the reporting year? Yes If yes, reasons and action plan: The reason for the delay was the difficulties reported by the Contractor to undertake disposal of the 1st batch of 74.1 metric tonnes of ODS waste. In view of the difficulties, UNIDO and the NOU followed up closely to facilitate the Contractor's work, with no success. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date delayed due to the problems to complete works related to disposal of the 1st batch of ODS waste. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of investment projects in the rigid foam sector | Individual | LAC | MEX | FOA | 30 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-04-01 |  | 2001-10-01 | 2003-03-01 | 30000 | -838 | 29162 | 29162.18 | 100% | -0.18 | 0 |  | 3900 | -115 | 3785 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | LAC | MEX | FUM | 22 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-07-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide in the cultivation of tomatoes, strawberries, tobacco, melons and cut flowers | Individual | LAC | MEX | FUM | 25 | DEM | 81 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-08-01 |  | 2004-12-01 | 2006-05-01 | 790350 | -13975 | 776375 | 776375.15 | 100% | -0.15 | 0 |  | 102746 | -1977 | 100769 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector (methyl bromide) | Individual | LAC | MEX | FUM | 39 | PRP | 113 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-01-01 | 2005-05-01 | 50000 | 0 | 50000 | 49999.86 | 100% | 0.14 | 0 |  | 3750 | -3 | 3747 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 121 | A | I | MBR | 36.9 | 132.9 |  |  | 2004-04-01 | 2004-11-01 | 2006-10-01 |  | 2006-12-01 | 2008-06-01 | 207035 | -1912 | 205123 | 205122.67 | 100% | 0.33 | 0 |  | 18633 | -172 | 18461 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigant sector | Individual | LAC | MEX | FUM | 51 | PRP | 131 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-08-01 | 2009-05-01 | 60000 | -509 | 59491 | 59490.51 | 100% | 0.49 | 0 |  | 4500 | -38 | 4462 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 136 | A | I | MBR | 130 | 130 |  |  | 2008-04-01 | 2008-06-01 | 2014-03-31 |  | 2012-07-01 | 2012-12-01 | 2000000 | -39 | 1999961 | 1999961.17 | 100% | -0.17 | 0 |  | 150000 | -3 | 149997 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 150 | A | I | MBR | 250 | 250 |  |  | 2010-04-01 | 2010-05-01 | 2012-04-30 |  | 2012-12-01 | 2014-07-01 | 2000000 | -576 | 1999424 | 1999423.89 | 100% | 0.11 | 0 |  | 150000 | -43 | 149957 | 0 | 0 | FIN
ONG | UNIDO | Methyl bromide phase-out plan (Transfer from Canada) | Multi-Year | LAC | MEX | FUM | 63 | INV | 153 | A | I | MBR | 50 | 50 |  |  | 2011-04-01 | 2011-07-01 | 2012-04-30 | 2015-12-01 |  |  | 500000 | 0 | 500000 | 486832.13 | 97.37% | 13167.87 | 4765.93 | 4079.7 | 37500 | 0 | 36512 | 988 | 357 | - A successful workshop was organized in Monterrey with the new equipment. | - Publications and videos have been prepared. - The project is near to completion. - A final official event will be organized with the Mexican Authorities during the second semester of 2015. |  |  | INV
ONG | UNIDO | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 162 | A | I | MBR | 120 | 120 |  |  | 2012-04-01 | 2012-07-01 | 2013-04-30 | 2015-12-01 |  |  | 1200000 | 0 | 1200000 | 1146646.19 | 95.55% | 53353.81 | 39823.29 | 51039.55 | 90000 | 0 | 85998 | 4002 | 2986.7467 | - Final greenhouse installation and training activities were carried out in 2014. '- A successful workshop was organized in Monterrey with the new equipment. | - Publications and videos have been prepared. - The project is near to completion. - A final official event will be organized with the Mexican Authorities during the second semester of 2015. |  |  | INV
ONG | UNIDO | National methyl bromide phase-out plan (fourth tranche) | Multi-Year | LAC | MEX | FUM | 69 | INV | 166 | A | I | MBR | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-04-30 | 2015-12-01 |  |  | 422379 | 0 | 422379 | 423508.84 | 100.3% | -1129.84 | -1380.11 |  | 31678 | 0 | 31763 | -85 | -103.5083 | - Final greenhouse installation and training activities were carried out in 2014. '- A successful workshop was organized in Monterrey with the new equipment. | - Publications and videos have been prepared. - The project is near to completion. - A final official event will be organized with the Mexican Authorities during the second semester of 2015. |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (aerosol and solvent sectors) | Individual | LAC | MEX | MUS | 58 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2013-12-01 | 2013-12-01 | 100000 | -538 | 99462 | 99462.43 | 100% | -0.43 | 0 |  | 7500 | -40 | 7460 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a process agent project | Individual | LAC | MEX | PAG | 48 | PRP | 129 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -94 | 29906 | 29906.35 | 100% | -0.35 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Umbrella project for terminal phase-out of CTC | Individual | LAC | MEX | PAG | 52 | INV | 133 | A | I | CTC | 87.3 | 87.3 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-31 |  | 2009-12-01 | 2012-08-01 | 1518094 | -9212 | 1508882 | 1508881.83 | 100% | 0.17 | 0 |  | 113857 | -691 | 113166 | 0 | 0 | FIN |  |  | 2010-01-01 | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | MEX | PHA | 42 | INV | 120 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2009-12-01 | 3517000 | 0 | 3517000 | 3517000.03 | 100% | -0.03 | 0 |  | 263775 | 0 | 263775 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | MEX | PHA | 45 | INV | 123 | A | I | CFC | 100 | 100 |  |  | 2005-04-01 | 2006-05-01 | 2007-04-01 |  | 2011-12-01 | 2014-07-01 | 4478000 | -203408 | 4274592 | 4277938.25 | 100.1% | -3346.25 | 0.01 |  | 335850 | -15256 | 320845 | -251 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | MEX | PHA | 50 | INV | 130 | A | I | CFC | 1435 | 1435 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-07-01 | 2010-12-01 | 299500 | -7411 | 292089 | 292088.84 | 100% | 0.16 | 0 |  | 22463 | -556 | 21907 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-10-01 | 104250 | -291 | 103959 | 103959 | 100% | 0 | 0 |  | 7819 | -22 | 7797 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (umbrella project for conversion from HCFC-141b to cyclopentane insulation foam blowing technology at three refrigeration appliances manufacturing enterprises: FERSA, Frigopanel and Metalfrio) | Multi-Year | LAC | MEX | PHA | 64 | INV | 157 | A | I | HCFC | 23 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2014-01-31 | 2016-11-01 |  |  | 2046110 | 0 | 2046110 | 674642.3 | 32.97% | 1371467.7 | 208512.34 | 200000 | 153458 | 0 | 50598 | 102860 | 15638 | - Conversion and destruction of ODS-related equipment at Metalfrio completed in December 2014, however TUV certification was not initiated by the supplier during the reporting period. - With respect to the other two companies, both have been visited in January 2014 to agree on the way forward, namely to source some equipment locally and to co-finance the purchase. - Bidding with a reduced scope was completed for Ojeda and bidding for Fersa was also completed. UNIDO agreed in December 2014 with Ojeda to proceed with the contract with the selected supplier based on a reduced scope. - At both enterprises reallocation of IOC to ICC was agreed upon to cover the additional costs of equipment beyond the approved amount. - The delays at Ojeda/Frigopanel and Fersa were mainly related to the very high share of counterpart inputs required for the project. Milestones achieved: Conversion completed at Metalfrio: Yes, December 2014; TUV certificate issued for Metalfrio: No; Bidding completed for Fersa: Yes, December 2013; Contract signed for Fersa: No Bidding completed for Ojeda: Yes, December 2013; Contract issued for Ojeda: No; Equipment delivered and installed for Fersa: No; Equipment delivered and installed for Ojeda: No; Commissioning and trial runs completed at Fersa: No; Commissioning and trial runs completed at Ojeda: No; TUV certificate issued for Fersa: No; TUV certificate issued for Ojeda: No; Activities planned but not implemented, reasons and strategy: TUV certification at Metalfrio was not done by the supplier, UNIDO, after several reminders has called for a meeting with the supplier to fulfil their contractual obligations. Contract signatures for the conversion at Fersa and Ojeda were delayed due to the not sufficient funding approved by the ExCom and consequently because of the high level of co-financing required. Actions: please see next column. Actions towards next goals: please see next column. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Reasons explained above. Actions please see next column. Any recurring problem? No, its the same problem, funds approved are not sufficient for the conversion. Any impact on project completion date: Yes. Completion date was revised to June 2016, by which time all three companies should be completed. If yes, implications: Companies may face difficulties in getting HCFC-141b quota. Any action required by Executive Committee? Increase ICC for the refrigeration foam sub-sector. | - UNIDO managed to convince the supplier to initiate TUV certification at Metalfrio. The supplier fielded a mission to Metalfrio to provide clear guidance to Metalfrio on the required modifications so to get TUV approval. TUV mission is planned for the first week of September 2015. - Contract with Ojeda/Frigopanel was signed and the supplier has arranged for a mission to start the contract. For Fersa, finally the contract details have been agreed upon with counterpart co-financing and UNIDO submitted the contract for signature by the beneficiary in June. UNIDO received the countersigned contract mid July 2015. Milestones achieved: Conversion completed at Metalfrio: Yes, December 2014; TUV certificate issued for Metalfrio: No; Bidding completed for Fersa: Yes, December 2013; Contract signed for Fersa: Yes, July 2015; Bidding completed for Ojeda: Yes, December 2013; Contract signed for Ojeda: Yes, February 2015; Equipment delivered and installed for Fersa: No; Equipment delivered and installed for Ojeda: No; Commissioning and trial runs completed at Fersa: No; Commissioning and trial runs completed at Ojeda: No; TUV certificate issued for Fersa: No; TUV certificate issued for Ojeda: No; Activities planned but not implemented, reasons and strategy: First visit of TUV to Metalfrio is scheduled for September 2015. This should have happened much earlier, but the supplier delayed the process. Contracts for both Fersa and Ojeda were delayed, but finally contracts were signed. Actions towards next goals: UNIDO will closely monitor the TUV certification process at Metalfrio and will regularly follow-up on the equipment delivery for the other two companies and the necessary preparatory work required at the beneficiaries' site. Was there any delay during the reporting year? Yes If yes, reasons and action plan: For Metalfrio the delay was caused by the supplier. For the other two companies the delay was of financial nature due to the high level of co-financing requirement. Any recurring problem? No Any impact on project completion date: Yes, above mentioned problems have seriously delayed the project and revised completion date is now in 2016. If yes, implications: If further delay occur, companies may face shortage of HCFC-141b supply. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b as a cleaning agent in refrigeration servicing) | Multi-Year | LAC | MEX | PHA | 64 | INV | 160 | A | I | HCFC | 4.3 | 4.3 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 |  | 2013-03-01 | 2014-07-01 | 100000 | -823 | 99177 | 99177.38 | 100% | -0.38 | 0 |  | 7500 | -62 | 7438 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (legislation customs training and monitoring) | Multi-Year | LAC | MEX | PHA | 64 | TAS | 158 | A | I | HCFC | 1.1 | 1.1 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2013-03-01 |  | 125500 | 0 | 125500 | 125232.58 | 99.79% | 267.42 | 0.01 | 1 | 9413 | 0 | 9392 | 21 | 0 |  |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 68 | INV | 164 | A | I | HCFC | 11.4 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2013-12-31 | 2016-12-01 |  |  | 695011 | 0 | 695011 | 423682.86 | 60.96% | 271328.14 | 65696.41 | 65000 | 52126 | 0 | 31776 | 20350 | 4927.2307 | - During a UNIDO mission that was organized in January 2014, the work plan has been updated, since the equipment required for the training arrived only in January 2014 instead of October 2013. - Preparation of training activities has started to be organized in May 2014 in Leon and Mexico City to train 50 to 60 trainers. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Training equipment purchased and delivered: Yes, in January 2014 Training of trainers completed: No Actions towards next goals: Upon completion of the training of trainers activities, large scale training and purchase of equipment and tools will follow. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Main reason for the delay were two-fold. The flushing agent delivered by the supplier was very aggressive and damaged several training flushing units, which had to be replaced and new flushing agent had to be supplied. Furthermore, training centers faced problems with the operation of the flushing units, which got over-heated. Suppliers were contacted, damaged units were replaced and new flushing agents were delivered. The supplier of the flushing units fielded a trouble-shooting mission to Mexico in November 2014. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No major implications, and no impact on compliance. Any action required by Executive Committee? No | - Trainings at 12 training centers (6 trainings each) are ongoing and half of them have been successfully completed. Flushing units with over-heat problems were shipped to the supplier and finally a new supplier of the motors was identified to avoid the over-heat. In parallel, new flushing units were purchased and tested locally. New motors will be shipped end August. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Training equipment purchased and delivered: Yes, in January 2014 Flushing units replaced: No Training of trainers completed: No Activities planned but not implemented, reasons and strategy: Activities were implemented as originally planned, but with delays. Actions towards next goals: Shipment of flushing units ASAP and continue training operation at larger scale. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The main reason for the delay was the fault operation of the flushing units (motors got over-heated) and the supply of the new motors was delayed by at least 1 year. The new motors mounted on the flushing units are expected to reach Mexico no later than in September 2015. In the meantime, alternative equipment were found guaranteeing reliable operation for future. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No major implications, and no impact on compliance. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 71 | INV | 167 | A | I | HCFC | 10.5 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 | 2017-03-01 |  |  | 578341 | 0 | 578341 | 151962.25 | 26.28% | 426378.75 | 36954.16 | 120000 | 43376 | 0 | 11397 | 31979 | 2771.562 | - A UNIDO mission was organized in January 2014, among others, to agree on the work plan for the subject tranche. - Subsequently, preparation of training activities has started to be organized in May 2014. - Extension of Project Management Unit was done in April 2014. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes TOR for equipment purchase agreed: No Equipment and tools delivered: No Large scale training completed: Yes Actions towards next goals: Agree on TOR and initiate bidding process Was there any delay during the reporting year? Yes If yes, reasons and action plan: As explained under MEX/PHA/64/INV/157, there have been technical problems with the flushing units, which delayed further activities. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No major implications, and no impact on compliance. Any action required by Executive Committee: No | - Trainings at 12 training centers (6 trainings each) are ongoing and half of them have been successfully completed. Flushing units with over-heat problems were shipped to the supplier and finally a new supplier of the motors was identified to avoid the over-heat. In parallel, new flushing units were purchased and tested locally. - TOR for equipment and tools to be purchased have been agreed upon in July 2015. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes TOR for equipment purchase agreed: Yes, July 2015 Equipment and tools delivered: No Large scale training completed: Yes Actions towards next goals: Initiate bidding and purchase of tools. Contract to be issued by September 2015. Tranche 2 and 3 are closely inter-linked, under both tranches there both training and equipment purchase activities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: As explained under MEX/PHA/64/INV/157, there have been technical problems with the flushing units, which delayed further activities. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No major implications, and no impact on compliance. Any action required by Executive Committee: No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 73 | INV | 170 | A | I | HCFC | 1.8 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2017-03-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 30000 | 9000 | 0 | 0 | 9000 | 0 | - The tranche was approved at the 73rd ExCom Meeting in November 2015. - Subsequently, the Government was informed on the approval of the tranche and PAD was issued in December 2014. 'Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: No Consultants recruited: No Verification audit of the 2015 consumption undertaken: No Actions towards next goals: Agreement on work plan and recruitment of experts for monitoring of the HPMP activities. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - Work Plan was agreed upon taking also into consideration that Stage II HPMP was approved. - Contracts of consultants for the HPMP monitoring unit have been extended. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes Consultants recruited: Yes Verification audit of the 2015 consumption undertaken: No Actions towards next goals: Continue monitoring all HPMP activities and take actions in each component as required. 2015 verification will only be initiated during 2016. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (phase-out of HCFC-22 and HCFC-141b in solvent) | Multi-Year | LAC | MEX | PHA | 73 | INV | 173 | A | I | HCFC | 39.6 | 0 |  |  | 2014-11-01 |  | 2018-11-30 | 2018-11-01 |  |  | 1731403 | 0 | 1731403 | 0 | 0% | 1731403 | 0 | 60000 | 121198 | 0 | 0 | 121198 | 0 | - Stage II HPMP was approved at the 73rd ExCom Meeting in November 2015. - Subsequently, the Government was informed on the approval of the tranche and PAD was issued in December 2014. Milestones achieved: PAD issued: Yes Work Plan agreed with NOU: No Technical expert recruited: No Conversion activities initiated: No Sub-contracts for IOC payment signed: No Phase-out of HCFCs verified: No Actions towards next goals: Agree on work plan with NOU and recruit technical expert. Was there any delay during the reporting year? No Any action required by Executive Committee? No | - Work plan was agreed with the NOU and a technical expert was recruited to verify the production lines and latest consumption at each beneficiary enterprise and to review their action plan. Milestones achieved: PAD issued: Yes Work Plan agreed with NOU: Yes , in February 2015 Technical expert recruited: Yes, in March 2015 Conversion activities initiated: Yes, in June 2015 Sub-contracts for IOC payment signed: No Phase-out of HCFCs verified: No Actions towards next goals: Lab tests for the alternatives will be undertaken and contracts for IOC payments will be prepared and payments will be released based on performance. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (phase-out in refrigeration servicing sector) | Multi-Year | LAC | MEX | PHA | 73 | INV | 174 | A | I | HCFC | 19.8 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2017-06-01 |  |  | 673009 | 0 | 673009 | 0 | 0% | 673009 | 0 | 20000 | 47111 | 0 | 0 | 47111 | 0 | - Stage II HPMP was approved at the 73rd ExCom Meeting in November 2015. Subsequently, the Government was informed on the approval of the tranche and PAD was issued in December 2014. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: No Milestones defined: No Actions towards next goals: Agreement on work plan and agree on milestones. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - This component of the Stage II HPMP was somewhat delayed during 2015, since service sector activities were running in parallel under Stage I and there was a need for a local stakeholder consultation for the implementation of the Stage II strategy, before activities could kick off. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: No Stakeholder consultation organized: No Milestones defined: No Activities planned but not implemented, reasons and strategy: Agreement on work plan and stakeholder consultation. Reason: Focus on service sector activities under Stage I as well as implementation of the Italian bilateral project on RRR and the aerosol sector conversion. Actions towards next goals: Agreement on work plan and agree on milestones. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Focus on service sector activities under Stage I as well as implementation of the Italian bilateral project on RRR and the aerosol sector conversion. The NOU and UNIDO will meet towards the 4th quarter in 2015 to discuss the action plan for this component. Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Closure of CFC production facilities of the company Quimobasicos | Individual | LAC | MEX | PRO | 38 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-06-01 | 2004-04-01 | 38000 | -286 | 37714 | 37713.62 | 100% | 0.38 | 0 |  | 4940 | -45 | 4895 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | Multi-Year | LAC | MEX | PRO | 40 | INV | 115 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-11-01 | 2004-03-01 |  | 2005-06-01 | 2006-12-01 | 5300000 | 0 | 5300000 | 5300000 | 100% | 0 | 0 |  | 397500 | 0 | 397500 | 0 | 0 | FIN
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (second tranche) | Multi-Year | LAC | MEX | PRO | 42 | INV | 119 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-05-01 | 2005-04-01 |  | 2005-06-01 | 2006-12-01 | 10700000 | 0 | 10700000 | 10700000.01 | 100% | -0.01 | 0 |  | 802500 | 0 | 802500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: third tranche | Multi-Year | LAC | MEX | PRO | 45 | INV | 126 | A | I | CFC | 0 | 0 | 5616 | 5616 | 2005-04-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-05-01 | 4000000 | -563 | 3999437 | 3999437.41 | 100% | -0.41 | 0 |  | 300000 | -42 | 299958 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: fourth tranche | Multi-Year | LAC | MEX | PRO | 47 | INV | 128 | A | I | CFC | 0 | 0 | 6739 | 6739 | 2005-11-01 | 2006-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-12-01 | 11850000 | -139 | 11849861 | 11849861.21 | 100% | -0.21 | 0 |  | 888750 | -10 | 888740 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFCs at Criotec S.A. | Individual | LAC | MEX | REF | 23 | INV | 67 | A | R | CFC | 16 | 16 |  |  | 1997-11-01 | 1998-09-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 240794 | 0 | 240794 | 240794 | 100% | 0 | 0 |  | 31303 | 0 | 31303 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Torrey S.A. | Individual | LAC | MEX | REF | 23 | INV | 68 | A | I | CFC | 15.1 | 15.1 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 228165 | -4430 | 223735 | 223734.8 | 100% | 0.2 | 0 |  | 29661 | -622 | 29039 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Nieto S.A. | Individual | LAC | MEX | REF | 23 | INV | 70 | A | R | CFC | 24.6 | 24.6 |  |  | 1997-11-01 | 1998-06-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 353976 | 0 | 353976 | 353976 | 100% | 0 | 0 |  | 46017 | 0 | 46017 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Vendo S.A. | Individual | LAC | MEX | REF | 23 | INV | 74 | A | R | CFC | 16.5 | 16.5 |  |  | 1997-11-01 | 1999-03-01 | 1998-10-01 |  | 1998-12-01 | 1999-07-01 | 248524 | 0 | 248524 | 248524 | 100% | 0 | 0 |  | 32308 | 0 | 32308 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS at several small enterprises in the commercial refrigeration | Individual | LAC | MEX | REF | 23 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-06-01 |  | 1999-11-01 | 2001-03-01 | 20000 | -49 | 19951 | 19951 | 100% | 0 | 0 |  | 2600 | -11 | 2589 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Plasticos Tecnicos Mexicanos (PTM) in the manufacture of commercial refrigeration equipment | Individual | LAC | MEX | REF | 25 | INV | 85 | A | I | CFC | 50.6 | 50.6 |  |  | 1998-07-01 | 1998-11-01 | 2000-01-01 |  | 1999-12-01 | 2002-09-01 | 398439 | 0 | 398439 | 398438.59 | 100% | 0.41 | 0 |  | 51797 | -1 | 51796 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | MEX | REF | 27 | PRP | 88 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 15000 | -2159 | 12841 | 12840.95 | 100% | 0.05 | 0 |  | 1950 | -283 | 1667 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with cyclopentane and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators of Metaplus S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 90 | A | I | CFC | 20.1 | 20.1 |  |  | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-12-01 | 2004-04-01 | 303094 | -1405 | 301689 | 301689.18 | 100% | -0.18 | 0 |  | 39402 | -245 | 39157 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators at Refrigeracion Duran S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 91 | A | I | CFC | 15.1 | 15.1 |  |  | 2000-03-01 | 2000-09-01 | 2001-10-01 |  | 2002-07-01 | 2003-10-01 | 112985 | 0 | 112985 | 112984.94 | 100% | 0.06 | 0 |  | 14688 | -3 | 14685 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | MEX | REF | 31 | TAS | 99 | A | I | CFC | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2002-05-01 |  | 2004-06-01 | 2004-12-01 | 100000 | -294 | 99706 | 99705.68 | 100% | 0.32 | 0 |  | 13000 | -59 | 12941 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | LAC | MEX | REF | 33 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2004-04-01 | 2004-12-01 | 50000 | 0 | 50000 | 49999.71 | 100% | 0.29 | 0 |  | 6500 | -3 | 6497 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a sectoral phase-out plan in refrigeration | Individual | LAC | MEX | REF | 36 | PRP | 107 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-04-01 | 2005-05-01 | 30000 | 0 | 30000 | 30000.19 | 100% | -0.19 | 0 |  | 3900 | -1 | 3899 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | MEX | REF | 58 | PRP | 145 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-06-01 | 2010-07-31 |  | 2013-12-01 | 2014-04-01 | 150000 | -490 | 149510 | 149509.63 | 100% | 0.37 | 0 |  | 11250 | -37 | 11213 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects | Individual | LAC | MEX | SEV | 18 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-08-01 |  | 1997-09-01 | 2000-07-01 | 50000 | -477 | 49523 | 49523 | 100% | 0 | 0 |  | 6500 | -72 | 6428 | 0 | 0 | FIN
FIN | UNIDO | Renewal of the institutional strengthening project for the phase out of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 37 | INS | 109 | N | I |  | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2002-08-01 |  | 2003-12-01 | 2005-03-01 | 0 | 50040 | 50040 | 50039.54 | 100% | 0.46 | 0 |  | 0 | 6495 | 6495 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | MEX | SEV | 37 | INS | 110 | N | I | CFC | 20.4 | 20.4 |  |  | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2005-03-01 | 2006-05-01 | 247000 | -4309 | 242691 | 242690.6 | 100% | 0.4 | 0 |  | 32110 | -610 | 31500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase VII | Individual | LAC | MEX | SEV | 45 | INS | 125 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-08-01 | 2008-08-01 | 247000 | 0 | 247000 | 247000 | 100% | 0 | 0 |  | 18525 | 0 | 18525 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase VIII) | Individual | LAC | MEX | SEV | 52 | INS | 132 | N | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2009-07-31 |  | 2009-06-01 | 2011-12-01 | 247000 | -1203 | 245797 | 245797.09 | 100% | -0.09 | 0 |  | 18525 | -90 | 18435 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase IX) | Individual | LAC | MEX | SEV | 58 | INS | 147 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2012-12-01 | 185250 | -281 | 184969 | 184969.2 | 100% | -0.2 | 0 |  | 13894 | -21 | 13873 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase X) | Individual | LAC | MEX | SEV | 62 | INS | 152 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2012-06-01 |  | 247000 | 0 | 247000 | 246464.37 | 99.78% | 535.63 | 396.42 | 1 | 18525 | 0 | 18485 | 40 | 30 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | MEX | SEV | 68 | INS | 163 | N | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2014-12-31 | 2015-12-01 |  |  | 247000 | 0 | 247000 | 118017.3 | 47.78% | 128982.7 | 2819.35 | 120000 | 17290 | 0 | 8261 | 9029 | 197.3545 | - Implementation as per work plan (ODS data collection and monitoring; up-date of SISSAO database; monitoring with a view to HPMP implementation; awareness activities). Milestones achieved: Milestone 1: NOU staff contracted - Yes Milestone 2: Short-term National consultants contracted - Yes Milestone 3: Office equipment delivered - Yes Actions towards next goals: Implementation of activities as per the work plan. Was there any delay during the reporting year? Yes If yes, reasons and action plan: (narrative): the re-location of NOU Office to new address caused some delay in the expenditures flow, however, the main project activities were organized as per the planning Any recurring problem? No Any impact on project completion date: yes If yes, implications: Financial completion to be achieved in 2015 due to administrative financial matters (no real impact on the activities implementation of NOU) Any action required by Executive Committee? No | - Implementation as per work plan (ODS data collection and monitoring; up-date of SISSAO database; monitoring with a view to HPMP implementation; awareness activities). Milestones achieved: Milestone 1: NOU staff contracts released - Yes Milestone 2: Update of SSISAO database - No Actions towards next goals: Implementation of activities as per the work plan. Milestone 2 to be achieved during 3rd quarter of 2015 Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: yes, financial completion is slightly delayed due to inter-relation with IS Phase XII Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase XII: 1/2015-12/2016) | Individual | LAC | MEX | SEV | 73 | INS | 175 | N | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2017-07-01 |  |  | 247000 | 0 | 247000 | 0 | 0% | 247000 | 0 | 6775 | 17290 | 0 | 0 | 17290 | 0 | - Project was approved at the 73rd Meeting of the ExCom in November 2014. - Project activities starting in 2015. Milestones achieved: NA Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - NOU staff and NC contract for the year 2015 released. - Work plan for the years 2015 - 2016 concluded and implementation initiated as per the project document. Milestones achieved: Milestone 1: NOU staff contracts released - Yes Milestone 2: Awareness activities planned - Yes Milestone 3: Data collection process for SSISAO database up-date initiated - Yes Actions towards next goals: Follow-up on the progress of the activities' implementation. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
CLO | UNIDO | Preparation of a sectoral phase-out plan in the solvents sector | Individual | LAC | MEX | SOL | 36 | PRP | 108 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-07-01 |  |  | 2003-05-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of investment projects in the solvent sector (TCA) | Individual | LAC | MEX | SOL | 39 | PRP | 114 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  |  | 2004-06-01 | 30000 | -18965 | 11035 | 11035.41 | 100% | -0.41 | 0 |  | 2250 | -1424 | 826 | 0 | 0 | CLO
FIN | UNIDO | Preparation of an awareness workshop in the methyl bromide sector | Individual | AFR | MLI | FUM | 36 | TRA | 12 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-03 |  | 2003-07-01 | 2004-04-01 | 30000 | -596 | 29404 | 29403.72 | 100% | 0.28 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | INV | 32 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2013-05-01 | 2014-07-01 | 60000 | -1277 | 58723 | 58750.33 | 100% | -27.33 | 0 |  | 5400 | -115 | 5288 | -3 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out plan for CFCs (first tranche) | Multi-Year | EUR | MOG | PHA | 53 | INV | 03 | A | I | CFC | 3 | 3 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 | 2013-10-01 | 175000 | -418 | 174582 | 174582.41 | 100% | -0.41 | 0 |  | 13125 | -31 | 13094 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MOG | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2009-12-01 | 2012-02-01 | 85000 | -767 | 84233 | 84233.23 | 100% | -0.23 | 0 |  | 6375 | -58 | 6317 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Terminal phase-out plan for CFCs (second tranche) | Multi-Year | EUR | MOG | PHA | 58 | INV | 06 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2013-12-01 |  | 95295 | 0 | 95295 | 93829.13 | 98.46% | 1465.87 | 1444.9 | 1000 | 7147 | 0 | 7037 | 110 | 108.3675 |  |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOG | PHA | 63 | INV | 08 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-10-01 | 2013-03-31 |  | 2013-12-01 |  | 155000 | 0 | 155000 | 154931.86 | 99.96% | 68.14 | 0 | 1 | 11625 | 0 | 11620 | 5 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | MOG | PHA | 71 | INV | 09 | A | I | HCFC | 0.1 | 0.04 |  |  | 2013-12-01 | 2014-01-01 | 2015-12-31 | 2016-12-01 |  |  | 100000 | 0 | 100000 | 47950.57 | 47.95% | 52049.43 | 5321.9 | 40000 | 7500 | 0 | 3596 | 3904 | 399.1425 | - The work plan must be revised due to reduction of the HPMP funding. The main change is the elimination of investment activities from the HPMP. No additional R+R equipment can be provided due to the funds reduction. - Purchase of identifiers for customs officers initiated. Bids prepared and requested. - New programme under finalization. - Intermediate goals achieved. Milestones achieved: 1. Terms of reference (for equipment) completed - Yes 2.Bidding completed, supplier selected - Yes Activities planned but not implemented, reasons and strategy: Delivery and training for the equipment. Actions towards next goals: Preparation of public awareness activities (Ozone Day). Planning of new activities for 2016. Was there any delay during the reporting year? Yes The reason: The HPMP budget was reduced. Therefore it was necessary to revise the planned activities in order to meet the available budget the HPMP objectives. Additional consultation with stakeholder were required. Any recurring problem? No Any impact on project completion date: Yes. The planned date of completion moved from Dec 2015 to Dec 2016. Any action required by Executive Committee? No | Milestone 1: Equipment delivered - No Milestone 2: Training conducted - No Milestone 3: Tranche request prepared - Yes Activities planned but not implemented, reasons and strategy: The equipment will arrive in September 2015. Training will be organized after the summer season. Actions towards next goals: Preparation of public awareness activities (Ozone Day). Planning of new activities for 2016. Was there any delay during the reporting year? Yes Reason: The HPMP budget was reduced. Therefore it was necessary to revise the planned activities in order to meet the available budget the HPMP objectives. Additional consultation were required. Any recurring problem? No Any impact on project completion date: The planned date of completion moved from Dec 2015 to Dec 2016. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation for a country programme and a terminal phase-out plan | Individual | EUR | MOG | SEV | 51 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-04-01 | 2009-09-01 | 40000 | -826 | 39174 | 39174.1 | 100% | -0.1 | 0 |  | 3600 | -74 | 3526 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Establishment of the ozone unit | Individual | EUR | MOG | SEV | 51 | INS | 02 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-09-01 | 30000 | -8112 | 21888 | 21888.39 | 100% | -0.39 | 0 |  | 2250 | -608 | 1642 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening project (Phase I) | Individual | EUR | MOG | SEV | 55 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-06-30 |  | 2010-12-01 | 2013-12-01 | 60000 | -1324 | 58676 | 58676.08 | 100% | -0.08 | 0 |  | 4500 | -99 | 4401 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Institutional strengthening project (phase II) | Individual | EUR | MOG | SEV | 61 | INS | 07 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-06-30 |  | 2013-12-01 |  | 60000 | 0 | 60000 | 57104.17 | 95.17% | 2895.83 | 2235.01 | 2000 | 4500 | 0 | 4283 | 217 | 168 |  |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | EUR | MOL | FUM | 45 | TAS | 13 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 30000 | -1838 | 28162 | 28161.61 | 100% | 0.39 | 0 |  | 2700 | -165 | 2535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | MOR | ARS | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -7939 | 12061 | 12061.37 | 100% | -0.37 | 0 |  | 2600 | -1035 | 1566 | -1 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | MOR | FOA | 60 | PRP | 64 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2010-12-01 | 2011-04-01 | 60000 | -65 | 59935 | 59934.64 | 100% | 0.36 | 0 |  | 4500 | -5 | 4495 | 0 | 0 | FIN
COM | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Manar | Multi-Year | AFR | MOR | FOA | 62 | INV | 67 | A | I | HCFC | 11 | 11 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2013-12-01 |  | 951740 | 0 | 951740 | 948157.08 | 99.62% | 3582.92 | 884.04 | 1 | 71381 | 0 | 71112 | 269 | 66 | N.a. | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | MOR | FOA | 73 | PRP | 71 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-30 | 2016-12-30 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 1000 | 7000 | 0 | 0 | 7000 | 0 | - Project approved at the 73rd Meeting of the ExCom in November 2014. - UNIDO and NOU agreed on a plan of action for the preparation of the II stage HPMP. However, it was agreed to put the project preparation in stand-by waiting for the results from the DEMO project on low-volume pentane foam technology. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Actions towards next goals: Wait for the outcomes of the DEMO project on low-volume pentane foam technology. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and NOU agreed on a plan of action for the preparation of the II stage HPMP. However, it was agreed to put the project preparation in stand-by waiting for the results from the DEMO project on low-volume pentane foam technology. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Actions towards next goals: Wait for the outcomes of the DEMO project on low-volume pentane foam technology. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Demonstration project - four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization and low-dose chemicals in combination with an integrated pesticide management system | Individual | AFR | MOR | FUM | 22 | DEM | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 2000-12-01 | 2002-08-01 | 487300 | -7238 | 480062 | 480062.23 | 100% | -0.23 | 0 |  | 63349 | -1040 | 62309 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (bananas) | Individual | AFR | MOR | FUM | 27 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -482 | 14518 | 14518.35 | 100% | -0.35 | 0 |  | 1950 | -66 | 1884 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (flowers) | Individual | AFR | MOR | FUM | 27 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -148 | 14852 | 14852.35 | 100% | -0.35 | 0 |  | 1950 | -22 | 1928 | 0 | 0 | FIN
FIN | UNIDO | Preparation of phase-out project in the methyl bromide sector | Individual | AFR | MOR | FUM | 30 | PRP | 39 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -260 | 29740 | 29739.89 | 100% | 0.11 | 0 |  | 3900 | -40 | 3860 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide for soil fumigation in strawberry production | Individual | AFR | MOR | FUM | 32 | INV | 41 | A | I | MBR | 155 | 155 |  |  | 2000-12-01 | 2001-01-01 | 2006-01-01 |  | 2007-12-01 | 2008-12-01 | 2189729 | 0 | 2189729 | 2189728.97 | 100% | 0.03 | 0 |  | 250870 | 0 | 250870 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | Multi-Year | AFR | MOR | FUM | 34 | INV | 44 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-10-01 | 2002-12-01 |  | 2005-09-01 | 2008-09-01 | 400000 | 0 | 400000 | 399999.97 | 100% | 0.03 | 0 |  | 52000 | 0 | 52000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (balance of the first tranche) | Multi-Year | AFR | MOR | FUM | 44 | INV | 52 | A | I | MBR | 34.1 | 34.1 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-12-01 | 607513 | -236 | 607277 | 607277.03 | 100% | -0.03 | 0 |  | 45563 | -17 | 45546 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (third tranche) | Multi-Year | AFR | MOR | FUM | 47 | INV | 54 | A | I | MBR | 39 | 39 |  |  | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 1670995 | 0 | 1670995 | 1670995 | 100% | 0 | 0 |  | 125325 | 0 | 125325 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fourth tranche) | Multi-Year | AFR | MOR | FUM | 50 | INV | 55 | A | I | MBR | 56.4 | 56.4 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 411633 | 0 | 411633 | 411633.01 | 100% | -0.01 | 0 |  | 30872 | 0 | 30872 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a methyl bromide phase-out plan (green beans and cucumber) | Individual | AFR | MOR | FUM | 51 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-03-01 |  | 2008-06-01 | 2009-05-01 | 35000 | -133 | 34867 | 34866.96 | 100% | 0.04 | 0 |  | 2625 | -10 | 2615 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fifth tranche) | Multi-Year | AFR | MOR | FUM | 53 | INV | 58 | A | I | MBR | 78 | 78 |  |  | 2007-11-01 | 2008-02-01 | 2008-11-30 |  | 2010-12-01 | 2010-12-01 | 424381 | 0 | 424381 | 424380.99 | 100% | 0.01 | 0 |  | 31829 | 0 | 31829 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (sixth tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 60 | A | I | MBR | 182.4 | 182.4 |  |  | 2008-11-01 | 2009-03-01 | 2010-11-30 |  | 2011-12-01 | 2013-12-01 | 398427 | -11389 | 387038 | 387037.51 | 100% | 0.49 | 0 |  | 29882 | -854 | 29028 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 61 | A | I | MBR | 35 | 35 |  |  | 2008-11-01 | 2008-12-01 | 2012-11-30 |  | 2012-10-01 | 2014-05-01 | 690000 | 0 | 690000 | 689999.98 | 100% | 0.02 | 0 |  | 51750 | 0 | 51750 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and cucurbits (second tranche) | Multi-Year | AFR | MOR | FUM | 62 | INV | 66 | A | I | MBR | 94.9 | 94.9 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2014-12-08 |  | 437594 | 0 | 437594 | 431953.11 | 98.71% | 5640.89 | 5024.74 | 5000 | 32820 | 0 | 32396 | 424 | 377 | - Project activities officially completed and PCR submitted. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - NA | - Project activities officially completed and PCR submitted in 2014. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | MOR | PHA | 55 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 | 2013-12-01 | 150000 | -677 | 149323 | 149323.05 | 100% | -0.05 | -0.01 |  | 11250 | -51 | 11199 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 65 | INV | 68 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-03-01 | 2012-11-30 | 2016-07-01 |  |  | 80000 | 0 | 80000 | 25167.1 | 31.46% | 54832.9 | 100 | 40000 | 6000 | 0 | 1888 | 4112 | 8 | - UNIDO in contact with the NOU to agree on work plan. - JD for an international expert to conduct training to customs authorities and design the TOR for the equipment for flushing was send. Response from NOU is pending. - The training of customs authorities as well as purchase of equipment for the replacement of HCFC 141b in the flushing of refrigeration circuits sector expected to be implemented in 2014. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Activities planned but not implemented, reasons and strategy: All activities were stopped due to lack of positive feedback from NOU. Actions towards next goals: In December 2014, a mission took place to Morocco to agree on communication and cooperation modalities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of feedback from NOU. Any recurring problem? Yes If yes, description of the problem/s: Lack of feedback from NOU. Any impact on project completion date: Yes If yes, implications: NOU confirmed that the delay will not impact country's compliance. Any action required by Executive Committee? No | - UNIDO agreed with the NOU on JD for international expert. International expert was recruited but contract cancelled because lf lack of response from custom authorities and ONCF (beneficiary). NOU tried to facilitate the communication flow and a new set of training is set for October. UNIDO has launched the bidding for the audit of the HCFC consumption for the year 2013 and 2014. Milestones achieved: Milestone 1: (Yes/No) Yes Milestone 2: (Yes/No) Yes Milestone 3: (Yes/No) Yes Milestone 4: (Yes/No) No Milestone 5: (Yes/No) No Milestone 6: (Yes/No) No Activities planned but not implemented, reasons and strategy: (narrative): Actions towards next goals: (narrative): execute the training to custom authorities; audit the HCFC consumption figures; finalize the technical specifications for the conversion of ONCF (flushing) and purchase the necessary equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: NOU confirmed that the delay will not impact country's compliance. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 68 | INV | 69 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2017-12-31 | 2017-12-01 |  |  | 220000 | 0 | 220000 | 14.3 | 0.0065% | 219985.7 | 9098.26 | 40000 | 16500 | 0 | 1 | 16499 | 682.3695 | - UNIDO in contact with the NOU to agree on work plan. - JD for an international expert to conduct training to customs authorities and design the TOR for the equipment for flushing was send. Response from NOU is pending. - The training of customs authorities as well as purchase of equipment for the replacement of HCFC 141b in the flushing of refrigeration circuits sector expected to be implemented in 2014. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Activities planned but not implemented, reasons and strategy: All activities were stopped due to lack of positive feedback from NOU. Actions towards next goals: In December 2014, a mission took place to Morocco to agree on communication and cooperation modalities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of feedback from NOU. Any recurring problem? Yes If yes, description of the problem/s: Lack of feedback from NOU. Any impact on project completion date: Yes If yes, implications: NOU confirmed that the delay will not impact country's compliance. Any action required by Executive Committee? No | - UNIDO agreed with the NOU on JD for international expert. International expert was recruited but contract cancelled because lf lack of response from custom authorities and ONCF (beneficiary). NOU tried to facilitate the communication flow and a new set of training is set for October. - UNIDO has launched the bidding for the audit of the HCFC consumption for the year 2013 and 2014. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Execute the training to custom authorities; audit the HCFC consumption figures; finalize the technical specifications for the conversion of ONCF (flushing) and purchase the necessary equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: NOU confirmed that the delay will not impact country's compliance. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | MOR | PHA | 73 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-30 | 2017-11-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 28000 | 4900 | 0 | 0 | 4900 | 0 | - Project approved at the 73rd Meeting of the ExCom in November 2014. - UNIDO in contact with the NOU to agree on JD for international and national experts to prepare the draft document for the II stage preparation. Response from NOU is pending. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Activities planned but not implemented, reasons and strategy: All activities were stopped due to lack of positive feedback from NOU. Actions towards next goals: In December 2014, a mission took place to Morocco to agree on communication and cooperation modalities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of feedback from NOU. Any recurring problem? Yes If yes, description of the problem/s: Lack of feedback from NOU. Any impact on project completion date: Yes If yes, implications: NOU confirmed that the delay will not impact country's compliance. Any action required by Executive Committee? No | - UNIDO and NOU agreed on the JD for international and national experts to prepare the draft document for the II stage preparation. - Selection of experts is ongoing. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Actions towards next goals: Recruit national and international experts and execute the country survey and draft strategy. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: NOU confirmed that the date will be according to country's compliance plans. Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector for Allom du Nord and others | Individual | AFR | MOR | REF | 24 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-09-01 | 2001-03-01 | 15000 | -4090 | 10910 | 10910 | 100% | 0 | 0 |  | 1950 | -534 | 1416 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Alom du Nord | Individual | AFR | MOR | REF | 25 | INV | 24 | A | I | CFC | 7.7 | 7.7 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-04-01 | 2002-09-01 | 99402 | -12788 | 86614 | 86614.26 | 100% | -0.26 | 0 |  | 12922 | -1680 | 11242 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox | Individual | AFR | MOR | REF | 25 | INV | 25 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-05-01 | 2002-09-01 | 32920 | -341 | 32579 | 32578.65 | 100% | 0.35 | 0 |  | 4280 | -51 | 4228 | 1 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Smifam | Individual | AFR | MOR | REF | 26 | INV | 27 | A | I | CFC | 4.9 | 4.9 |  |  | 1998-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-04-01 | 2002-09-01 | 62447 | -2267 | 60180 | 60179.88 | 100% | 0.12 | 0 |  | 8118 | -307 | 7811 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | MOR | REF | 27 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-09-01 | 1999-12-01 |  | 2001-04-01 | 2001-10-01 | 7000 | -1517 | 5483 | 5483.21 | 100% | -0.21 | 0 |  | 910 | -198 | 712 | 0 | 0 | FIN
FIN | UNIDO | Conversion of HCFC-141b technology (rigid foam) and HFC-134a (refrigeration) in the manufacture of domestic refrigerators and freezers at Manar | Individual | AFR | MOR | REF | 29 | INV | 33 | A | R | CFC | 38.6 | 38.6 |  |  | 1999-11-01 | 2000-04-01 | 2000-07-01 |  | 1999-12-01 | 2000-11-01 | 434183 | 0 | 434183 | 434183 | 100% | 0 | 0 |  | 26051 | 0 | 26051 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Siafmo | Individual | AFR | MOR | REF | 29 | INV | 34 | A | I | CFC | 8.7 | 8.7 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 126240 | -3250 | 122990 | 122990.02 | 100% | -0.02 | 0 |  | 16411 | -448 | 15963 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Mafidec | Individual | AFR | MOR | REF | 29 | INV | 35 | A | I | CFC | 5.6 | 5.6 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 117360 | -7879 | 109481 | 109480.65 | 100% | 0.35 | 0 |  | 15257 | -1047 | 14210 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Sonyafroid | Individual | AFR | MOR | REF | 29 | INV | 36 | A | I | CFC | 13.1 | 13.1 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 275895 | -2567 | 273328 | 273327.76 | 100% | 0.24 | 0 |  | 35866 | -390 | 35476 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic commercial refrigeration equiment at Comafro | Individual | AFR | MOR | REF | 29 | INV | 38 | A | I | CFC | 6.5 | 6.5 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 134750 | -1142 | 133608 | 133608.19 | 100% | -0.19 | 0 |  | 17518 | -177 | 17342 | -1 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Climatisation et Froid Loudaya (CFL) | Individual | AFR | MOR | REF | 35 | INV | 45 | A | I | CFC | 15 | 15 |  |  | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 177312 | -847 | 176465 | 176464.91 | 100% | 0.09 | 0 |  | 23051 | -147 | 22904 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at First Clim Co. | Individual | AFR | MOR | REF | 35 | INV | 46 | A | I | CFC | 9 | 9 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 135258 | -980 | 134278 | 134277.6 | 100% | 0.4 | 0 |  | 17584 | -156 | 17428 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Etablissement Lahdar | Individual | AFR | MOR | REF | 35 | INV | 47 | A | I | CFC | 7.4 | 7.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 101451 | -1363 | 100088 | 100087.56 | 100% | 0.44 | 0 |  | 13189 | -198 | 12991 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the terminal umbrella group of commercial refrigeration manufactures. | Individual | AFR | MOR | REF | 43 | INV | 50 | A | I | CFC | 18.4 | 18.4 |  |  | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 359864 | 0 | 359864 | 359863.76 | 100% | 0.24 | 0 |  | 26990 | 0 | 26990 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning sectors) | Individual | AFR | MOR | REF | 60 | PRP | 65 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 40000 | -254 | 39746 | 39746.38 | 100% | -0.38 | 0.01 |  | 3000 | -19 | 2981 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in domestic refrigeration and methyl bromide sectors | Individual | AFR | MOR | SEV | 21 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-06-01 |  | 1999-09-01 | 2000-12-01 | 22150 | -1502 | 20648 | 20648 | 100% | 0 | 0 |  | 2880 | -200 | 2680 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Country programme update | Individual | AFR | MOR | SEV | 38 | CPG | 48 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-12-01 | 2005-05-01 | 40000 | -1747 | 38253 | 38253.07 | 100% | -0.07 | 0 |  | 5200 | -235 | 4965 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvent and process agents (CTC & TCA ) sectors | Individual | AFR | MOR | SOL | 45 | TAS | 53 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -591 | 39409 | 39409.32 | 100% | -0.32 | 0 |  | 3600 | -53 | 3547 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Technical assistance for the elimination of controlled uses of methyl bromide in soil fumigation | Individual | AFR | MOZ | FUM | 60 | TAS | 20 | A | I |  | 0.4 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 | 2015-12-01 |  |  | 40000 | 0 | 40000 | 59.51 | 0.1488% | 39940.49 | 8708.28 | 3000 | 3600 | 0 | 5 | 3595 | 784 | - Mission to Mozambique took place in late February 2014 and extensive discussion with NOU and representatives from Ministry of Agriculture took place. - It was agreed to support a survey of the national circumstances related to the use of methyl bromide and its alternatives (e.g. legislation, market, import/export, products and commodities where MB could be potentially used, ongoing programs for agricultural development, etc.) in order to design and implement the most effective training and awareness campaign to national stakeholders. - UNIDO and UNEP agreed to cooperate in supporting the country in revising the policy components, while UNIDO alone will focus on technical aspects related to alternative technologies. - Nothing of the planned activities was implemented in 2014. Activities planned but not implemented, reasons and strategy: No activities were implemented Actions towards next goals: Report on non-implementation Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Lack of positive response from NOU Any recurring problem? Yes If yes, description of the problem/s: Lack of positive response from NOU Any impact on project completion date: Yes If yes, implications: The project could not be implemented Any action required by Executive Committee? Yes; To send a letter of possible cancellation | - NOU was contacted following the letter of possible cancellation. - UNIDO proposed the NOU to agree on another final plan of action, with the help of an international expert. - Dialogue is ongoing to agree on a concrete plan of action to complete the project not later than December 2015. Activities planned but not implemented, reasons and strategy: Agree on a new and final plan of action. Actions towards next goals: Liaise with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date No Any action required by Executive Committee? Yes; To cancel the project if no progresses are achieved and reported by UNIDO |  |  |  |  | No Progress - Possible cancellation
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MOZ | PHA | 66 | INV | 23 | A | I | HCFC | 0.3 | 0 |  |  | 2012-04-01 | 2014-09-01 | 2016-04-30 | 2017-03-01 |  |  | 75000 | 0 | 75000 | 1826.41 | 2.435% | 73173.59 | 6070.78 | 6000 | 6750 | 0 | 164 | 6586 | 546.3702 | 1. UNIDO has requested new dates for a mission, but has been informed by the Government that due to upcoming elections a mission can be accommodated in the 2nd quarter of 2014. Milestones achieved: Milestone 1: Meeting with stakeholders (Yes) Milestone 2: TOR for equipment (Yes) Milestone 3: Procurement of equipment (No) Milestone 4: Equipment delivered (No) Milestone 5: Training in use of equipment (No) Activities planned but not implemented, reasons and strategy: Purchase of equipment. Due to funding available and local needs for support, definition of scope of equipment required additional time. Actions towards next goals: Procurement of equipment Was there any delay during the reporting year? Yes If yes, reasons and action plan: Government change and delays in meeting with stakeholders. Any recurring problem? No Any impact on project completion date: No | Brief report: NOU has requested change of scope of equipment to strengthen border controls. Milestones achieved: Milestone 1: Meeting with stakeholders (Yes) Milestone 2: Revised TOR for equipment (Yes) Milestone 3: Procurement of equipment (No) Milestone 4: Equipment delivered (No) Milestone 5: Training in use of equipment (No) Activities planned but not implemented, reasons and strategy: Purchase of equipment. Due to funding available and local needs for support and revised definition of scope of equipment. Actions towards next goals: Procurement of equipment Was there any delay during the reporting year? Yes If yes, reasons and action plan: Change of scope of equipment. Any recurring problem? No Any impact on project completion date: No |  |  | INV
FIN | UNIDO | Preparation of projects in commercial refrigeration | Individual | AFR | MOZ | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-08-01 | 1998-08-01 | 15000 | -1697 | 13303 | 13303 | 100% | 0 | 0 |  | 1950 | -223 | 1727 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at INDATEC/Industria de aplicacoes technico-domesticas Ltd. | Individual | AFR | MOZ | REF | 18 | INV | 04 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1997-03-01 |  |  | 2002-04-01 | 581515 | -246871 | 334644 | 334644 | 100% | 0 | 0 |  | 75597 | -32162 | 43435 | 0 | 0 | CLO |  |  | 1999-11-01
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | MYA | PHA | 57 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2012-12-01 | 2014-07-01 | 42500 | -889 | 41611 | 41610.75 | 100% | 0.25 | 0 |  | 3188 | -67 | 3121 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: establishing conversion practice of domestic refrigerators | Individual | ASP | MYA | REF | 45 | TAS | 07 | A | I | CFC | 32.1 | 32.1 |  |  | 2005-04-01 | 2005-10-01 | 2006-10-01 |  | 2007-11-01 | 2008-07-01 | 80000 | -15 | 79985 | 79984.53 | 100% | 0.47 | 0 |  | 7200 | -1 | 7199 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 53 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2008-12-01 | 2009-03-01 | 12000 | -6598 | 5402 | 5401.91 | 100% | 0.09 | 0 |  | 900 | -495 | 405 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | INV | 21 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-12-01 | 2012-12-01 | 131000 | -185 | 130815 | 130814.51 | 100% | 0.49 | 0 |  | 11790 | -17 | 11773 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | NER | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-07-01 | 2013-12-01 | 85000 | -7688 | 77312 | 77311.52 | 100% | 0.48 | 0 |  | 6375 | -577 | 5798 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | INV | 23 | A | I | CFC | 4.8 | 4.8 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-02-01 | 2012-12-01 | 53000 | -17 | 52983 | 52983.49 | 100% | -0.49 | 0 |  | 4770 | -1 | 4769 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | INV | 28 | A | I | HCFC | 1.7 | 0 |  |  | 2012-04-01 | 2012-11-01 | 2016-04-30 | 2016-04-01 |  |  | 175000 | 0 | 175000 | 26677.75 | 15.24% | 148322.25 | 60212.75 | 50000 | 13125 | 0 | 2001 | 11124 | 4515.9563 | - Subcontract for training activities with NOU under implementation. - Equipment specification for recovery/recycling network developed and bidding process scheduled for 2015. Milestones achieved: Milestone 1: Contract award for training activities implementation - Yes Milestone 2: Progress report on technicians training activities in 2014 - Yes Actions towards next goals: Follow-up on activities implementation according to the contract. Was there any delay during the reporting year? No Any recurring problem?: No Any impact on project completion date: No Any action required by Executive Committee? No | - ToR for the bidding and bidding for equipment purchase carried out in 2015. - Award of the contract and equipment delivery to take place during the second half of 2015. Milestones achieved: Milestone 1: Contract award for equipment purchase - No Milestone 2: Equipment delivery - No Milestone 3: Completion of training activities - Yes Actions towards next goals: Local consultancy selection for elaboration of data verification report to be initiated second half of 2015. Was there any delay during the reporting year? No Any recurring problem?: No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | NER | PHA | 71 | TAS | 29 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2016-05-31 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 10000 | 2700 | 0 | 0 | 2700 | 0 | - IC and/or NCs contract for development of verification report selection is scheduled for the second half of 2015. - Planned completion date was changed as per Secretariat’s communication dated 11 February 2015. Milestones achieved: Milestone 1: Training activities completed in 2015 - Yes Milestone 2: Verification report contracted second half of 2015 - No Activities planned but not implemented, reasons and strategy: Verification report due date is end of 2015 in view of submission of the next tranche request in 2016, as per the Agreement between country and the ExCom. Actions towards next goals: Initiation of progress report for tranche submission at the last quarter of 2015. Was there any delay during the reporting year? No Verification report due date is end of 2015 in view of submission of the next tranche request in 2016, as per the Agreement between country and the ExCom. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Brief report: Contracting and elaboration of the Verification report is scheduled for the second half of the 2015 year Milestones achieved: Milestone 1: ToR development for verification report - Yes Milestone 2: Selection of the consultant fore verification report - No Activities planned but not implemented, reasons and strategy: Activity planned second half of the 2015 year Actions towards next goals: As per the work plan agreed in 2014 Was there any delay during the reporting year? Yes If yes, reasons and action plan: (narrative): Verification report due date is end of 2015 in view of submission of the next tranche request in 2016, as per the Agreement between country and the ExCom. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Verification report due date is end of 2015 in view of submission of the next tranche request in 2016, as per the Agreement between country and the ExCom. Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a project for the phase-out of methyl bromide soil fumigation | Individual | LAC | NIC | FUM | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-05-01 | 2003-12-01 | 30000 | -27242 | 2758 | 2757.82 | 99.99% | 0.18 | 0 |  | 3900 | -3542 | 358 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | NIC | FUM | 45 | TAS | 12 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | -275 | 29725 | 29725.16 | 100% | -0.16 | 0 |  | 2700 | -25 | 2675 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | NIC | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 85000 | -130 | 84870 | 84869.65 | 100% | 0.35 | 0 |  | 6375 | -10 | 6365 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | NIC | PHA | 66 | INV | 27 | A | I | HCFC | 0.5 | 0.5 |  |  | 2012-04-01 | 2012-09-01 | 2015-04-30 | 2015-10-01 |  |  | 96500 | 0 | 96500 | 88209.83 | 91.41% | 8290.17 | -136.55 | 8200 | 8685 | 0 | 7939 | 746 | -12.2895 | - To distribute the tools and start with the training and certification program for technicians. - Equipment was delivered at the end of March 2014. - UNIDO mission took place in March 2014. - As per UNIDO suggestion, 5 training centers (including refrigeration in the curriculum)were established in different regions during the year 2014. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Milestone 5: Creation of code of conduct and certification system. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Since the funds are almost exhausted few activities have taken place in the project during 2015. - The certification program is established and a study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Milestone 5: Creation of code of conduct and certification system. Yes Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Milestone 5: Creation of code of conduct and certification system. Yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project formulation of investment projects in the refrigeration sector | Individual | LAC | NIC | REF | 21 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-08-01 |  | 1998-05-01 | 2001-12-01 | 50000 | -8349 | 41651 | 41651.46 | 100% | -0.46 | 0 |  | 6500 | -1094 | 5406 | 0 | 0 | FIN
CLO | UNIDO | Preparation of refrigerant management plan | Individual | LAC | NIC | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 |  | 1999-04-01 |  |  | 2001-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Fogel S.A. in the manufacture of commercial refrigeration equipment | Individual | LAC | NIC | REF | 25 | INV | 05 | A | R | CFC | 9.6 | 9.6 |  |  | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 1999-12-01 | 2001-03-01 | 130027 | 0 | 130027 | 130027 | 100% | 0 | 0 |  | 16904 | -22 | 16882 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosols sector | Individual | AFR | NIR | ARS | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2000-10-01 | 2001-09-01 | 25000 | -9266 | 15734 | 15733.87 | 100% | 0.13 | 0 |  | 3250 | -1208 | 2042 | 0 | 0 | FIN
FIN | UNIDO | Preparation for a pilot demonstration project on ODS waste management and disposal | Individual | AFR | NIR | DES | 60 | PRP | 126 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 60000 | -480 | 59520 | 59520.33 | 100% | -0.33 | 0 |  | 4500 | -36 | 4464 | 0 | 0 | FIN
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | AFR | NIR | DES | 67 | DEM | 133 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2014-07-31 | 2017-03-01 |  |  | 911724 | 0 | 911724 | 108625.13 | 11.91% | 803098.87 | 85629.63 | 93359.34 | 63821 | 0 | 7604 | 56217 | 5994.0741 | - Project Management Unit set up with a coordinator. Aggregation and testing activities starting in the 1st quarter of 2014. - ToR for local vendor agreed with the government. - Agreement between UNIDO and project developer ongoing. Milestones achieved: Milestone 1: Yes - Local vendor selected for aggregation Milestone 2: Yes - Aggregation and testing of waste CFCs started Activities planned but not implemented, reasons and strategy: The project developer decided not to continue with the project due to losses during a previous project. Low amounts of wastes found. Was there any delay during the reporting year? Yes If yes, reasons and action plan: A new vendor/project developer will be selected. Any recurring problem? Yes If yes, description of the problem/s: Levels of found wastes still low. Any impact on project completion date: Yes If yes, implications: Planned completion date: December 2016. Any action required by Executive Committee? No | - Stakeholders Workshop on the amendment of ODS legislation to include mandatory disposal will be held in the 2nd half of 2015. - Vendor will be selected for final disposal of aggregated wastes. Milestones achieved: Milestone 1: Yes - CFC wastes aggregated at central facility (ongoing) Actions towards next goals: Discussion ongoing with the National Environmental Standards and Regulations Enforcement Agency (NESREA) on amendment of legislation. Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Low levels of CFC wastes found. Any impact on project completion date: Yes If yes, implications: Planned completion date: March 2017. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | National CFC phase-out plan: refrigeration manufacturing | Multi-Year | AFR | NIR | PHA | 38 | INV | 105 | A | I | CFC | 42.9 | 42.9 |  |  | 2002-11-01 | 2003-03-01 | 2005-06-01 |  | 2006-03-01 | 2008-09-01 | 682386 | 0 | 682386 | 682385.99 | 100% | 0.01 | 0 |  | 82521 | 0 | 82521 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | UNIDO | National CFC phase-out plan (aerosol sector) | Multi-Year | AFR | NIR | PHA | 41 | INV | 109 | A | I | CFC | 57.9 | 57.9 |  |  | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2008-03-01 | 2008-06-01 | 255000 | -2 | 254998 | 254998.02 | 100% | -0.02 | 0 |  | 33150 | 0 | 33150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (3rd tranche) | Multi-Year | AFR | NIR | PHA | 49 | INV | 115 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 425000 | 0 | 425000 | 425000.01 | 100% | -0.01 | 0 |  | 31875 | 0 | 31875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 120 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 20000 | -4 | 19996 | 19996.09 | 100% | -0.09 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 129 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 |  | 2013-12-01 |  | 550000 | 0 | 550000 | 74435.41 | 13.53% | 475564.59 | 462894.53 | 450000 | 41250 | 0 | 5583 | 35667 | 34717 |  |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration air-conditioning manufacturing and coordination) | Multi-Year | AFR | NIR | PHA | 66 | INV | 131 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2013-02-01 | 2013-04-30 | 2016-07-01 |  |  | 550000 | 0 | 550000 | 24444.57 | 4.444% | 525555.43 | 511615.12 | 300000 | 41250 | 0 | 1833 | 39417 | 38371.134 | - New foaming machines have been procured and delivered to the country. - Installation and commissioning completed. Milestones achieved: Milestone 1: Yes - 30 Foaming machines were distributed to beneficiaries in October 2014 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Installation and training on use of equipment to be carried out in 2015. Milestones achieved: Milestone 1: Yes 1st batch of 16 foaming machines installed at various companies in Ibadan. Activities planned but not implemented, reasons and strategy: Installation and training had to be cut short due to elections. Actions towards next goals: Next batch of 14 foaming machines is getting installed at Abuja starting July 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Installation and training had to be cut short due to elections. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Extend to 2016 to enable complete installation of all equipment. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | Multi-Year | AFR | NIR | PHA | 71 | INV | 136 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2016-06-01 | 2017-03-01 |  |  | 645172 | 0 | 645172 | 0 | 0% | 645172 | 611759 | 20000 | 48388 | 0 | 0 | 48388 | 45881.925 | -The requested implementation plan submitted. - The number and technical specifications of the new foaming machines for 45 eligible end-users coordinated. - - International bidding arranged. - A contract was awarded for supply of 45 foaming machines in Nov 2014. Milestones achieved: Milestone 1: Yes - A contract was awarded for supply of 45 foaming machines in Nov 2014. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment was shipped in July 2015. Milestones achieved: Milestone 1: Yes - Equipment shipped in July 2015 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date should be changed to March 2017 to allow for delivery of equipment, installation and training. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of CFC phase out strategy for refrigeration and A/C industries and services | Individual | AFR | NIR | REF | 11 | TAS | 07 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1999-12-01 | 2000-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  | 1999-12-01 | NON-INV
FIN | UNIDO | Phasing out of CFCs at Debo Industries Ltd. Nigeria | Individual | AFR | NIR | REF | 18 | INV | 10 | A | I | CFC | 52 | 52 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1048053 | 0 | 1048053 | 1048052.6 | 100% | 0.4 | 0 |  | 136247 | -44 | 136203 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Thermocool Eng. Co. Ltd. | Individual | AFR | NIR | REF | 18 | INV | 11 | A | I | CFC | 82 | 82 |  |  | 1995-11-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1465750 | 0 | 1465750 | 1465750.06 | 100% | -0.06 | 0 |  | 190548 | -10 | 190538 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at A.G. Leventis | Individual | AFR | NIR | REF | 26 | INV | 30 | A | I | CFC | 19.1 | 19.1 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2003-03-01 | 2004-04-01 | 190420 | 0 | 190420 | 190420.01 | 100% | -0.01 | 0 |  | 24755 | 0 | 24755 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at New Ltd. | Individual | AFR | NIR | REF | 26 | INV | 40 | A | I | CFC | 20.9 | 20.9 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2003-05-01 | 361770 | 0 | 361770 | 361769.86 | 100% | 0.14 | 0 |  | 47030 | 0 | 47030 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at Kolinton Technical Industries | Individual | AFR | NIR | REF | 26 | INV | 44 | A | I | CFC | 39.5 | 39.5 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2003-12-01 | 2004-06-01 | 674348 | -902 | 673446 | 673445.54 | 100% | 0.46 | 0 |  | 84178 | -216 | 83962 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Soesons Ltd. | Individual | AFR | NIR | REF | 28 | INV | 48 | A | I | CFC | 16.1 | 16.1 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-08-01 | 221353 | 0 | 221353 | 221353 | 100% | 0 | 0 |  | 28776 | 0 | 28776 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Onward Electrical Industry Ltd. | Individual | AFR | NIR | REF | 28 | INV | 51 | A | I | CFC | 10.7 | 10.7 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2003-12-01 | 2004-04-01 | 146927 | 0 | 146927 | 146927 | 100% | 0 | 0 |  | 19101 | 0 | 19101 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at United Technologies Ltd. | Individual | AFR | NIR | REF | 28 | INV | 52 | A | I | CFC | 9.6 | 9.6 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-12-01 | 130579 | 0 | 130579 | 130578.84 | 100% | 0.16 | 0 |  | 16975 | -6 | 16969 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration equipment at De Johnson Ltd. | Individual | AFR | NIR | REF | 29 | INV | 53 | A | I | CFC | 9 | 9 |  |  | 1999-11-01 | 2000-09-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 123816 | 0 | 123816 | 123816 | 100% | 0 | 0 |  | 16096 | 0 | 16096 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration at Austin-Laz & Co. Ltd | Individual | AFR | NIR | REF | 29 | INV | 54 | A | I | CFC | 11.6 | 11.6 |  |  | 1999-11-01 | 2000-10-01 | 2001-06-01 |  | 2002-08-01 | 2003-07-01 | 147181 | 0 | 147181 | 147181 | 100% | 0 | 0 |  | 19134 | 0 | 19134 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | NIR | REF | 30 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-02-01 | 2002-09-01 | 25000 | -2212 | 22788 | 22787.85 | 100% | 0.15 | 0 |  | 3250 | -292 | 2958 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC=12 withHFC-134a, and foam flowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration equipment at Bosmak Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 71 | A | I | CFC | 10.8 | 10.8 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2003-10-01 | 2004-06-01 | 154245 | -420 | 153825 | 153825.48 | 100% | -0.48 | 0 |  | 20052 | -86 | 19966 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Coldcare Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 76 | A | I | CFC | 11.4 | 11.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-12-01 | 2003-12-01 | 173200 | 0 | 173200 | 173200 | 100% | 0 | 0 |  | 22516 | 0 | 22516 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Akocen Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 77 | A | I | CFC | 12.1 | 12.1 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2003-10-01 | 157894 | 0 | 157894 | 157894.01 | 100% | -0.01 | 0 |  | 20526 | 0 | 20526 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for three projects in the commercial refrigeration sector | Individual | AFR | NIR | REF | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1718 | 18282 | 18282.2 | 100% | -0.2 | 0 |  | 2600 | -227 | 2373 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Polade | Individual | AFR | NIR | REF | 35 | INV | 97 | A | I | CFC | 8.3 | 8.3 |  |  | 2001-12-01 | 2002-03-01 | 2004-05-01 |  | 2004-06-01 | 2005-03-01 | 70382 | 0 | 70382 | 70381.99 | 100% | 0.01 | 0 |  | 9150 | -4 | 9146 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Ristian | Individual | AFR | NIR | REF | 35 | INV | 98 | A | I | CFC | 11 | 11 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2004-06-01 | 2005-12-01 | 143729 | -706 | 143023 | 143023.47 | 100% | -0.47 | 0 |  | 18685 | -122 | 18564 | -1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | AFR | NIR | REF | 58 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2012-10-01 | 50000 | -2342 | 47658 | 47658.44 | 100% | -0.44 | 0 |  | 3750 | -176 | 3574 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning manufacturing sector) | Individual | AFR | NIR | REF | 72 | PRP | 137 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-08-01 | 2015-05-31 | 2016-06-30 |  |  | 150000 | 0 | 150000 | 4936.62 | 3.291% | 145063.38 | 918.75 | 19110.99 | 10500 | 0 | 346 | 10154 | 64 | - Approved at the 72nd Meeting of the ExCom in May 2014. | - Surveys are ongoing in the ice-machine and AC manufacturing sectors for the preparation of Stage II of the HPMP and are expected be completed in July 2015. - Stakeholder workshop planned for the 3rd quarter of 2015. Milestones achieved: Milestone 1: Yes - National consultant hired to carry out surveys Was there any delay during the reporting year? Yes If yes, reasons and action plan: Surveys had to be delayed during the election periods. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date should be changed to June 2016. Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a sectoral phase-out plan in solvents | Individual | AFR | NIR | SOL | 36 | PRP | 101 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-06-01 | 2004-11-01 | 70000 | 0 | 70000 | 69999.95 | 100% | 0.05 | 0 |  | 9100 | -8 | 9092 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase out umbrella project in the solvent sector (first tranche) | Multi-Year | AFR | NIR | SOL | 43 | INV | 110 | A | I | CTC | 152.1 | 152.1 |  |  | 2004-07-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-05-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 39750 | 0 | 39750 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (2nd tranche) | Multi-Year | AFR | NIR | SOL | 46 | INV | 113 | A | I | CTC TCA | 0 | 0 |  |  | 2005-07-01 | 2005-11-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 23775 | 0 | 23775 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (fourth tranche) | Multi-Year | AFR | NIR | SOL | 52 | INV | 116 | A | I | CTC | 45.9 | 45.9 |  |  | 2007-07-01 | 2007-12-01 | 2010-01-01 |  | 2012-11-01 |  | 303200 | 0 | 303200 | 288812.68 | 95.25% | 14387.32 | 8910 | 13000 | 22740 | 0 | 21661 | 1079 | 668 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
FIN | UNIDO | Awareness workshop and training on methyl bromide alternatives | Individual | ASP | OMA | FUM | 44 | TRA | 10 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-09-01 | 2007-10-01 | 35000 | -2078 | 32922 | 32921.71 | 100% | 0.29 | 0 |  | 3150 | -187 | 2963 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Halon consumption phase-out through a technical assistance programme and a halon recycling | Individual | ASP | OMA | HAL | 46 | TAS | 12 | A | I | HAL | 6.85 | 6.85 |  |  | 2005-07-01 | 2007-02-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -4821 | 59779 | 59779.2 | 100% | -0.2 | 0 |  | 5814 | -434 | 5380 | 0 | 0 | FIN |  |  | 2008-02-01 | INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | OMA | PHA | 46 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2007-03-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | OMA | PHA | 52 | INV | 15 | A | I | CFC | 10 | 10 |  |  | 2007-07-01 | 2007-12-01 | 2009-12-31 |  | 2009-07-01 | 2012-12-01 | 305800 | 0 | 305800 | 305800.47 | 100% | -0.47 | 0 |  | 22935 | 0 | 22935 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | OMA | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 100000 | -292 | 99708 | 99708.42 | 100% | -0.42 | 0 |  | 7500 | -22 | 7478 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | OMA | PHA | 57 | INV | 19 | A | I | CFC | 25 | 25 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2011-12-01 | 2013-12-01 | 164200 | -37297 | 126903 | 126903.03 | 100% | -0.03 | 0 |  | 12315 | -2797 | 9518 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Audit for the terminal phase-out management plan | Individual | ASP | OMA | PHA | 57 | TAS | 20 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2010-09-01 | 2010-03-31 |  | 2010-12-01 | 2011-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1800 | 0 | 1800 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 23 | A | I | HCFC | 2.3 | 0 |  |  | 2011-11-01 | 2013-01-01 | 2015-11-30 | 2015-11-01 |  |  | 210000 | 0 | 210000 | 50847 | 24.21% | 159153 | 144726.3 | 157564 | 15750 | 0 | 3814 | 11936 | 10854 | - Installation and training on the use of the reclamation equipment and visit to international reclamation centre during the 2nd quarter of 2014. - Technical assistance to fisheries sector on alternatives to HCFC-22 during the 2nd quarter of 2014. Milestones achieved: Milestone 1: Yes 1st workshop for fisheries sector held in June 2014 Milestone 2: Yes - 2nd workshop for decision makers in fisheries sector held in November 2014 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Due to low funds in 1st tranche, visit to international reclamation centre to be done with 2nd tranche funds in 2015. - Residual funds to be used together with 2nd tranche. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No, project is planned to be completed by the end of 2015 Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the foam sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 24 | A | I | HCFC | 2.3 | 2.3 |  |  | 2011-11-01 | 2012-05-01 | 2012-12-31 |  | 2014-06-01 |  | 104120 | 0 | 104120 | 102455.51 | 98.4% | 1664.49 | 1585.49 | 1580 | 7809 | 0 | 7684 | 125 | 119 | - The water blown foam machine was delivered to Oman in January 2014. - Installation and training on the use of the equipment took place in the 1st quarter of 2014. Equipment has been installed and staff of NHI have been trained on the use of the equipment. - The project is successfully closed. Milestones achieved: Milestone 1: Yes - Equipment installed and in operation. | - The project is successfully closed. |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | OMA | PHA | 73 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-06-30 | 2016-06-30 |  |  | 33000 | 0 | 33000 | 0 | 0% | 33000 | 0 | 30000 | 2310 | 0 | 0 | 2310 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014. | - Surveys for the preparation of Stage II are ongoing and are planned to be completed in July 2015. - An international expert has been hired to prepare the project document. - A stakeholder workshop is planned for end of July 2015. Milestones achieved: Milestone 1: Yes Survey carried out May to July 2015 Milestone 2: Yes International expert hired Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | OMA | REF | 34 | TAS | 05 | A | I | CFC | 9 | 9 |  |  | 2001-07-01 | 2007-03-01 | 2004-08-01 |  | 2007-12-01 | 2008-09-01 | 20000 | -196 | 19804 | 19804 | 100% | 0 | 0 |  | 2600 | -25 | 2575 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Recovery and recycling project | RMP Update | ASP | OMA | REF | 34 | TAS | 06 | A | I | CFC | 103.3 | 103.3 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2005-12-01 | 2007-12-01 | 230000 | -502 | 229498 | 229498.29 | 100% | -0.29 | 0 |  | 29900 | -65 | 29835 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Training of trainers in good refrigerant management practices | RMP Update | ASP | OMA | REF | 34 | TRA | 02 | A | I | CFC | 80 | 80 |  |  | 2001-07-01 | 2002-06-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 178000 | -1359 | 176641 | 176641.2 | 100% | -0.2 | 0 |  | 23140 | -213 | 22927 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Customs training programme | RMP Update | ASP | OMA | REF | 34 | TRA | 04 | A | I | CFC | 18.9 | 18.9 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-09-01 | 42000 | -4469 | 37531 | 37530.63 | 100% | 0.37 | 0 |  | 5460 | -589 | 4871 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country programme preparation | Individual | ASP | OMA | SEV | 29 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-12-01 | 2002-05-01 | 80000 | -1455 | 78545 | 78544.87 | 100% | 0.13 | 0 |  | 10400 | -205 | 10195 | 0 | 0 | FIN
FIN | UNIDO | Institutional Strengthening/Support to the National Ozone Unit in Oman | Individual | ASP | OMA | SEV | 32 | INS | 02 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2005-12-01 | 2006-02-01 | 79000 | 0 | 79000 | 78999.73 | 100% | 0.27 | 0 |  | 10270 | -1 | 10269 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase II) | Individual | ASP | OMA | SEV | 46 | INS | 14 | N | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-03-01 | 2007-07-01 |  | 2007-12-01 | 2009-09-01 | 68467 | -73 | 68394 | 68394.4 | 100% | -0.4 | 0 |  | 5135 | -5 | 5130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase III) | Individual | ASP | OMA | SEV | 56 | INS | 18 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2011-02-01 | 2010-11-30 |  | 2011-11-01 | 2012-11-01 | 68467 | 0 | 68467 | 68467 | 100% | 0 | 0 |  | 5135 | 0 | 5135 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Renewal of institutional strengthening support (phase IV: 12/2011-11/2013) | Individual | ASP | OMA | SEV | 65 | INS | 21 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2013-11-30 |  | 2013-12-01 |  | 68467 | 0 | 68467 | 68274.86 | 99.72% | 192.14 | 0 | 1 | 5135 | 0 | 5121 | 14 | 0 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening support (phase V: 12/2013-11/2015) | Individual | ASP | OMA | SEV | 71 | INS | 25 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-06-01 | 2015-11-30 | 2015-11-01 |  |  | 68467 | 0 | 68467 | 30054.3 | 43.9% | 38412.7 | 38229.52 | 38279 | 4793 | 0 | 2104 | 2689 | 2676.0664 | - TOR and new contract with counterpart to commit the funding for 2 years (disbursement of 50 % of funding in 2014 and 50 % in 2015) agreed with counterpart and it is under signature process. Milestones achieved: Milestone 1: NOU staffed - Yes Milestone 2: Contract awarded - Yes Milestone 3: Awareness activities reported with the half-year and annual progress report - Yes Actions towards next goals: Follow-up on implementation and preparation of the terminal report Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Follow-up on the activities foreseen under contractual obligations with counterpart. - Progress reports clearance and initiation of IS extension. - Terminal Report and extension of the IS project approved by the 74th Meeting of the ExCom. Milestones achieved: Milestone 1: Project completion - No Milestone 2: Submission of extension request - Yes Actions towards next goals: Initiation of the newly approved extension implementation. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee?: No |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvent sector (CTC) | Individual | ASP | OMA | SOL | 45 | TAS | 11 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 35000 | 0 | 35000 | 34999.74 | 100% | 0.26 | 0 |  | 3150 | 0 | 3150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | PAK | FOA | 59 | PRP | 75 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 80000 | -106 | 79894 | 79894.17 | 100% | -0.17 | 0 |  | 6000 | -8 | 5992 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at United Refrigeration, HNR (Haier), Varioline Intercool and Shadman Electronics companies | Multi-Year | ASP | PAK | FOA | 60 | INV | 77 | A | I | HCFC | 49.2 | 49.2 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 | 2015-12-01 |  |  | 3559359 | 0 | 3559359 | 3367636.43 | 94.61% | 191722.57 | 156434.86 | 150000 | 266952 | 0 | 252573 | 14379 | 11733 | - Final ductworks, ventilation and other safety measures are being finalized. - Third party safety certification; post certification rectification of non-standard findings are in progress. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Partially (Shadman delayed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - Partially (Shadman delayed) Activities planned but not implemented, reasons and strategy: Site preparatory works delayed. Commissioning and start up trials and certification delayed. Actions towards next goals: Local technical assistance to be mobilized. Counterparts sources to be mobilized. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delays in the project site preparations: renovation and reconstruction of old manufacturing premises; limited space especially at United Refrigeration, Hyderabad and Shadman, Karachi. Counterparts' careful financial planning and its limited activities carried out, postponed the installations. Delays in the installations activities of the supplier: quite complicated and therefore lengthy coordination and harmonization of installation plans among counterparts and vis-a-vis contractors. Delays in replacements of malfunctioned components damaged during transport. Action plan: Accelerated schedule for necessary site preparatory works: Amended installation schedule, to be consented with supplier of equipment and harmonized with other components of this umbrella project. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Delays in different activities will cause delay in project completion Any action required by Executive Committee? No | - Local site reconstruction and safety related activities (ductworks, ventilation and other safety measures) have been finalized at three factories. (Delays accrued at Shadman and United Refrigeration). - Third party safety certification; post certification rectification of non standard findings to be finalized. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Partially (Shadman and United Refrigeration delayed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: Site preparatory works delayed. Commissioning and start up trials and certification at Shadman delayed. Actions towards next goals: Local technical assistance to be mobilized. Counterparts sources to be mobilized. UNIDO will scrutinize the shortcomings and agree on possible technical and managerial assistance to be covered mostly by counterparts. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delays in the project site preparations: renovation and reconstruction of old manufacturing premises; limited space especially at United Refrigeration, Hyderabad and Shadman, Karachi. Counterparts' careful financial planning and its limited activities carried out postponed the installations. Delays in the installations activities of the supplier: quite complicated and therefore lengthy coordination and harmonization of installation plans among counterparts and vis-a-vis contractors. Delays in replacements of malfunctioned components damaged during transport. Action plan: Accelerated schedule for necessary site preparatory works: Amended installation schedule, to be consented with supplier of equipment and harmonized with other components of this umbrella project. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Delays in different activities caused delay in project completion Any action required by Executive Committee? No
ONG | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at Dawlance | Multi-Year | ASP | PAK | FOA | 60 | INV | 78 | A | I | HCFC | 22.4 | 22.4 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 | 2015-12-01 |  |  | 1281490 | 0 | 1281490 | 1260499.69 | 98.36% | 20990.31 | 17468.1 | 20000 | 96112 | 0 | 94537 | 1575 | 1310 | - Final ductworks, ventilation and other safety measures are being finalized. - Commissioning, start-up and operators training is being finalized. - Third party safety certification; post certification rectification of non standard findings are in progress. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Partially (Planed in Hyderabad, DPL-2 delayed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - Partially (Planed in Hyderabad, DPL-2 delayed) Actions towards next goals: Counterparts sources to be mobilized. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Site preparatory works at DPL-2 delayed; congested space, lengthy reconstructions and renovations. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: (narrative): Any action required by Executive Committee? No | - Certifications are being finalized at DPL2 plant. - Non-standard findings after certification to be amended. - Project is completed. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - Yes Activities planned but not implemented, reasons and strategy: Project activities were implemented and completed.
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | PAK | FOA | 72 | PRP | 87 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 3500 | 0 | 0 | 3500 | 0 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in the foam sector and identification of HCFC -141b users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - No Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC 141b users. Study tour for selected entrepreneurs, experts and government officials to learn about non-ODS and low-GWP alternative technologies in the PS and PUR subsectors was initiated. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Study tour had been delayed in a year time. Chinese counterparts could not book mutually acceptable time. Study tour to take place in July 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in the foam sector accomplished users of HCFC -141b and potential project beneficiaries of conversion investment projects identified. - Drafting of the investment component, HPMP Stage II for the foam sector in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission, Commitment letters from eligible counterparts and Government Letter of transmittal are being obtained. Independent technical review is being arranged. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Study tour to China could not take place as planned. New planning is set up for end August 2015. Any recurring problem? No Any impact on project completion date: No Uncertainty of ExCom approval for Stage II. Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | ASP | PAK | FUM | 24 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-12-01 | 1999-04-01 |  | 2000-01-01 | 2000-07-01 | 30000 | -21118 | 8882 | 8882 | 100% | 0 | 0 |  | 3900 | -2747 | 1153 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector | Individual | ASP | PAK | FUM | 39 | PRP | 49 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2004-04-01 | 2004-06-01 | 30000 | -9323 | 20677 | 20676.75 | 100% | 0.25 | 0 |  | 2250 | -702 | 1548 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | PAK | FUM | 45 | TAS | 63 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 30000 | -7149 | 22851 | 22850.78 | 100% | 0.22 | 0 |  | 2700 | -643 | 2057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a halon sector phase-out plan | Individual | ASP | PAK | HAL | 40 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2003-12-01 | 2004-12-01 | 22000 | -780 | 21220 | 21219.63 | 100% | 0.37 | 0 |  | 1650 | -61 | 1589 | 0 | 0 | FIN
FIN | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | ASP | PAK | HAL | 41 | TAS | 55 | A | I | HAL | 24.2 | 24.2 |  |  | 2003-12-01 | 2004-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 209400 | -786 | 208614 | 208614.4 | 100% | -0.4 | 0 |  | 18846 | -71 | 18775 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | Individual | ASP | PAK | PAG | 35 | INV | 42 | A | I | CTC | 80 | 80 |  |  | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2008-10-01 | 2011-03-01 | 485701 | -3651 | 482050 | 482050.16 | 100% | -0.16 | 0 |  | 63141 | -474 | 62667 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector phase-out plan of CTC | Multi-Year | ASP | PAK | PHA | 41 | INV | 57 | A | I | CTC | 100 | 109.7 |  |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-07-01 | 2010-12-01 | 1200000 | -542 | 1199458 | 1199458.28 | 100% | -0.28 | 0 |  | 90000 | -41 | 89959 | 0 | 0 | FIN |  |  | 2006-07-01 | INV
FIN | UNIDO | Sector phase-out plan of CTC (second tranche) | Multi-Year | ASP | PAK | PHA | 44 | INV | 62 | A | I | CTC | 326.5 | 326.5 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-07-01 | 2012-05-01 | 1300000 | -2137 | 1297863 | 1297862.63 | 100% | 0.37 | 0 |  | 97500 | -160 | 97340 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector phase-out plan of CTC (third tranche) | Multi-Year | ASP | PAK | PHA | 54 | INV | 67 | A | I | CTC | 62.5 | 62.5 |  |  | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2009-12-01 | 2012-05-01 | 245665 | -912 | 244753 | 244752.62 | 100% | 0.38 | 0 |  | 25924 | -96 | 25828 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | PAK | PHA | 55 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 90000 | -5024 | 84976 | 84976.18 | 100% | -0.18 | 0 |  | 6750 | -377 | 6373 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | PAK | PHA | 59 | PRP | 76 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2010-12-01 | 2012-06-01 | 45000 | -831 | 44169 | 44169.11 | 100% | -0.11 | 0 |  | 3375 | -62 | 3313 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | INV | 79 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2013-03-01 |  | 68000 | 0 | 68000 | 64162.16 | 94.36% | 3837.84 | 1948.53 | 1000 | 5100 | 0 | 4812 | 288 | 146 |  |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | PAK | PHA | 70 | INV | 83 | A | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-09-01 | 2014-07-31 | 2015-12-01 |  |  | 80000 | 0 | 80000 | 25844.02 | 32.31% | 54155.98 | 45993.1 | 46051 | 6000 | 0 | 1938 | 4062 | 3449.4825 | - Workshop and refrigeration technology fair had been planned jointly with Lahore RAC association for March 2014; postponed for later date. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: See above. Actions towards next goals: Provide assistance to NOU on monitoring, licensing and quota set-up based on information from foam and refrigeration/AC manufacturing sectors. Country is in compliance with HCFC reduction schedule. | - UNIDO works jointly with UNEP as co-implementing agency, to support non-investment activities developed by UNEP. Contribution to public awareness campaign and conference on Environment organized by Lahore University of Management Science supported by NOU. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Actions towards next goals: Assistance to customs authorities and national board of revenues through feedback from foam and refrigeration manufacturing sectors. Was there any delay during the reporting year? Yes Change in the post of Ozone Officer; Officer in charge served by March 2015; new appointed served for two months before resignation in May 2015. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: The project is supposed to be completed by the end of 2015. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | PAK | PHA | 72 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 42000 | 0 | 42000 | 0 | 0% | 42000 | 805.08 | 20000 | 2940 | 0 | 0 | 2940 | 56 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in respective HCFCs consuming sectors and identification of HCFC users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC users. Study tour for selected entrepreneurs, experts and government officials to learn about non-ODS and low-GWP alternative technologies and new developments in safety and industrial standardization in the air-conditioning manufacturing and servicing sector with special focus on hydrocarbons was initiated. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in respective HCFC consuming sectors accomplished. - Users of HCFCs and potential project beneficiaries including government, non-governmental organizations, RAC associations and other stakeholders identified. - Drafting of the project document, HPMP Stage II in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission are being obtained. Independent technical review is being organized. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Study tour to China could not take place as planned. New planning was set up for end August 2015. Any recurring problem? No Any impact on project completion date: No Uncertainty of ExCom approval for Stage II. Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | PAK | PHA | 73 | INV | 89 | A | I | HCFC | 2 | 0 |  |  | 2014-11-01 |  | 2015-11-30 | 2015-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 10000 | 1500 | 0 | 0 | 1500 | 0 | - Project was approved at the 73rd Meeting of the ExCom in November 2014. - UNIDO and UNEP were requested to submit to the Executive Committee the project completion report (PCR) for Stage I of the HPMP of Pakistan no later than the 75th Meeting of the ExCom; and to submit a verification report confirming that the country had met the Montreal Protocol targets for 2015 no later than the first meeting of 2016; and to satisfactorily address the issues on the licensing and quota system identified in the verification report for Pakistan during the preparation of stage II of the HPMP. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Actions towards next goals: Contribute to the organization of the training for 100 customs officers and 400 refrigeration officers (by NOU and UNEP). Jointly specify the needs for equipment. Purchase necessary equipment and didactic tools. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: (narrative): Any action required by Executive Committee? No | - Project stagnant as the National Ozone Officer resigned and new one has not yet been selected. - UNEP Small Scale Funding Agreement has also been signed only in 2015. Pakistan however successfully controlled import of ODS through strong monitoring system. - Project activities are expected to be completed by end 2015. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Actions towards next goals: Training for 100 customs officers and 400 refrigeration officers jointly organized by NOU - UNEP and UNIDO is scheduled for July-August 2015. UNIDO will purchase training equipment. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Strategy for ODS phase out in refrigeration industry | Individual | ASP | PAK | REF | 12 | TAS | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1995-08-01 | 1994-06-01 |  | 1998-03-01 | 2000-07-01 | 50000 | -232 | 49768 | 49768 | 100% | 0 | 0 |  | 6500 | -40 | 6460 | 0 | 0 | FIN |  |  | 1999-02-01 | NON-INV
FIN | UNIDO | Phasing out ODS at the Chest Freezer Factory of Riaz Electric Co. Ltd. | Individual | ASP | PAK | REF | 19 | INV | 09 | A | I | CFC | 48.2 | 48.2 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-12-01 | 2005-12-01 | 822987 | -4083 | 818904 | 818903.75 | 100% | 0.25 | 0 |  | 106988 | -699 | 106289 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the refrigerator and chest freezer plants of Pak Elektron Ltd. (PEL) | Individual | ASP | PAK | REF | 19 | INV | 10 | A | I | CFC | 68 | 68 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-10-01 | 2006-05-01 | 1210295 | -67215 | 1143080 | 1143080.24 | 100% | -0.24 | 0 |  | 157338 | -8973 | 148365 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the freezer factory of Hirra Farooq's (Pvt) Ltd. | Individual | ASP | PAK | REF | 23 | INV | 17 | A | I | CFC | 31.2 | 31.2 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 2003-08-01 | 2003-12-01 | 521580 | -3110 | 518470 | 518469.84 | 100% | 0.16 | 0 |  | 67805 | -511 | 67294 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | PAK | REF | 27 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-03-01 | 1999-12-01 |  | 2003-07-01 | 2003-10-01 | 30000 | -2206 | 27794 | 27794 | 100% | 0 | 0 |  | 3900 | -292 | 3608 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the production of domestic refrigeration equipment at Ideal Appliances, Ltd. | Individual | ASP | PAK | REF | 35 | INV | 43 | A | I | CFC | 12.9 | 12.9 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2004-07-01 | 2005-09-01 | 173101 | -1342 | 171759 | 171759.09 | 100% | -0.09 | 0 |  | 22503 | -210 | 22293 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a phase-out plan in the refrigeration sector (CFC manufacturing) | Individual | ASP | PAK | REF | 39 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2005-05-01 | 20000 | -168 | 19832 | 19831.68 | 100% | 0.32 | 0 |  | 1500 | -15 | 1485 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (first tranche) | Multi-Year | ASP | PAK | REF | 41 | TAS | 56 | A | I | CFC | 55 | 55 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2004-12-01 | 2009-12-01 | 191000 | 0 | 191000 | 191000.21 | 100% | -0.21 | 0 |  | 14325 | 0 | 14325 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (second tranche) | Multi-Year | ASP | PAK | REF | 44 | TAS | 61 | A | I | CFC | 80 | 80 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-05-01 | 2010-09-01 | 534200 | -3137 | 531063 | 531062.64 | 100% | 0.36 | 0 |  | 40065 | -235 | 39830 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (third tranche) | Multi-Year | ASP | PAK | REF | 47 | INV | 64 | A | I | CFC | 80 | 80 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2008-09-01 | 2010-09-01 | 414300 | -1421 | 412879 | 412879.45 | 100% | -0.45 | 0 |  | 31073 | -107 | 30966 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | ASP | PAK | REF | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2011-07-01 | 2014-05-01 | 120000 | -5074 | 114926 | 114926.12 | 100% | -0.12 | 0 |  | 9000 | -381 | 8619 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | PAK | REF | 72 | PRP | 86 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 749.74 | 30000 | 4200 | 0 | 0 | 4200 | 52 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in respective HCFCs consuming sectors and identification of HCFC users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC users. Study tour for selected entrepreneurs, experts and government officials to learn about non-ODS and low-GWP alternative technologies and new developments in safety and industrial standardization in the air-conditioning manufacturing and servicing sector with special focus on hydrocarbons was initiated. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in respective HCFC consuming sectors accomplished. - Users of HCFCs and potential project beneficiaries including government, non-governmental organizations, RAC associations and other stakeholders identified. - Drafting of the project document, HPMP Stage II in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission are being obtained. Independent technical review is being organized. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Study tour to China could not take place as planned. New planning was set up for end August 2015. Any recurring problem? No Any impact on project completion date: No Uncertainty of ExCom approval for Stage II. If yes, implications: (narrative): Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Conversion of ODS coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Hyderabad | Individual | ASP | PAK | SOL | 22 | INV | 13 | A | I | CFC | 18.9 | 18.9 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 1999-12-01 | 2002-09-01 | 321172 | -3201 | 317971 | 317970.94 | 100% | 0.06 | 0 |  | 41752 | -481 | 41271 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning and coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Lahore | Individual | ASP | PAK | SOL | 22 | INV | 14 | A | I | CFC | 40.7 | 40.7 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2002-06-01 | 2003-06-01 | 510162 | 0 | 510162 | 510162.15 | 100% | -0.15 | 0 |  | 66321 | -37 | 66284 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for four projects in the solvent (CTC) sector | Individual | ASP | PAK | SOL | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | -7022 | 22978 | 22977.9 | 100% | 0.1 | 0 |  | 3900 | -918 | 2982 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two projects in the solvents sector | Individual | ASP | PAK | SOL | 36 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 20000 | -639 | 19361 | 19360.91 | 100% | 0.09 | 0 |  | 2600 | -87 | 2513 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | Individual | ASP | PAK | SOL | 37 | INV | 47 | A | I | CTC | 10 | 10 |  |  | 2002-07-01 | 2004-10-01 | 2004-08-01 |  | 2005-12-01 | 2006-12-01 | 122078 | -665 | 121413 | 121412.8 | 100% | 0.2 | 0 |  | 15870 | -86 | 15784 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the solvents sector (CTC/TCA) | Individual | ASP | PAK | SOL | 39 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 25000 | -807 | 24193 | 24192.9 | 100% | 0.1 | 0 |  | 1875 | -63 | 1812 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) and methyl chloroform (MCF) to tetrachloroethylene (PER) and water in combination with partial process modification at Hirra Farooq Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 51 | A | I | CTC MCF | 37.5 | 37.5 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 246493 | -536 | 245957 | 245956.64 | 100% | 0.36 | 0 |  | 22184 | -48 | 22136 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC), methyl chloroform (MCF) and CFC-113 to tetrachloroethylene (PER) and water in combination with process modification at Breeze Frost Industries Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 52 | A | I | CTC MCF CFC | 33.2 | 33.2 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 282056 | -204 | 281852 | 281852.22 | 100% | -0.22 | 0 |  | 21254 | -15 | 21239 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an awareness workshop on methyl bromide | Individual | LAC | PAN | FUM | 36 | TRA | 16 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-10-01 | 2003-12-01 | 30000 | -5344 | 24656 | 24656.21 | 100% | -0.21 | 0 |  | 3900 | -700 | 3200 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 65 | INV | 44 | A | I | CFC | 15 | 15 |  |  | 2011-11-01 | 2012-01-01 | 2012-12-31 |  | 2014-04-15 |  | 183500 | 0 | 183500 | 171084.33 | 93.23% | 12415.67 | 11490.01 | 12378.75 | 13763 | 0 | 12831 | 932 | 862 | - Since 2013 the Customs Authorities have claimed that the equipment was abandoned and disappeared. - An International Expert in customs visited the country to find out where the equipment could be and try to solve the impasse. As a result, the delivered tools lost in the customs' premises were found and the last option was to request 'donation' to a Instituto Tecnico de la Producción (ITP). - The ITP belongs to the Ministry of Industry and will deliver the tools to the Training Centers as planned in the ProDoc. - The project activities were completed in spring 2014. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: Any action required by Executive Committee? No | - UNIDO continued trying to recover the equipment. The institutions SENATI and GAMOR were visited and the impasse explained, unfortunately the institutions are not allowed to request the adjudication of the tools. The ITP seems to be the only option and UNIDO contacted it again. - The tools will be delivered to the training centers through ITP after the customs clearance is complete. - The project was financially completed in April 2015. Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation assistance in solvent sector | Individual | LAC | PER | SOL | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -8097 | 21903 | 21903 | 100% | 0 | 0 |  | 3900 | -1057 | 2843 | 0 | 0 | FIN |  |  | 1999-01-01
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Faber Castell | Individual | LAC | PER | SOL | 20 | INV | 18 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-11-01 | 1997-10-01 |  | 1998-09-01 | 2000-12-01 | 16409 | -4827 | 11582 | 11582 | 100% | 0 | 0 |  | 2133 | -630 | 1503 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Carbolan | Individual | LAC | PER | SOL | 20 | INV | 19 | A | I | TCA | 0.4 | 0.4 |  |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 31457 | -7307 | 24150 | 24150 | 100% | 0 | 0 |  | 4089 | -954 | 3135 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Papeles Industriales | Individual | LAC | PER | SOL | 20 | INV | 20 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-12-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 47953 | -957 | 46996 | 46996 | 100% | 0 | 0 |  | 6234 | -134 | 6100 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the aerosol sector | Individual | ASP | PHI | ARS | 27 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | PHI | FOA | 59 | PRP | 86 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 70000 | -5751 | 64249 | 64249.09 | 100% | -0.09 | 0 |  | 5250 | -431 | 4819 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Sector plan to phase out HCFC-141b in the foam sector | Multi-Year | ASP | PHI | FOA | 62 | INV | 90 | A | I | HCFC | 40 | 40 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-09-01 |  |  | 1770650 | 0 | 1770650 | 1484474.15 | 83.84% | 286175.85 | 286067.98 | 30000 | 132799 | 0 | 111336 | 21463 | 21455 | 10 companies with fixed foaming equipment received assistance to convert their technologies. Installation was finalized at 8 beneficiaries. - On spray foam sector, last tests on spray foam applications took place. - UNIDO discussed with beneficiaries and the NOU to finalize the scope of supply for those 8 eligible beneficiaries. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes (partially) Milestone 5: Equipment delivered - Yes (partially) Milestone 6: Commissioning and trial runs - Yes (partially) Activities planned but not implemented, reasons and strategy: Completion of installation at all beneficiaries with fixed-foam equipment. Main reason was lack of cooperation by one beneficiary (Blutherm) and technical issues at one beneficiary (DYD). Procure the agreed items to support the 8 spray foam companies. Actions towards next goals: Solve the technical issue at DYD and pursue cooperation from Blutherm. Purchase items to spray foam companies. Make sure about the destruction of baseline equipment. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Technical issues and lack of cooperation from a beneficiary. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: No impact on overall country's compliance. Any action required by Executive Committee? No | - 10 companies with fixed foaming equipment received assistance to convert their technologies. - Installation was finalized at 9 beneficiaries. - On spray foam sector, UNIDO started procuring agreed items to finalize the assistance to eligible 8 eligible beneficiaries. - The equipment to Blutherm was confiscated and sold back to technology provider. The money recovered will be transferred back to the MLF at project closure. - UNIDO certified the destruction of baseline equipment in July 2015. - The technical brochure resulted from the tests in the spray foam activities was published and launched (copy is available for the MLF, if required so). Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes (partially) Milestone 5: Equipment delivered - Yes (partially) Milestone 6: Commissioning and trial runs - Yes (partially) Activities planned but not implemented, reasons and strategy: Finalization of procurement contracts for spray foam companies. Actions towards next goals: Monitor the disbursement of agreed items for spray-foam companies. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a recovery and recycling project in the refrigeration sector | Individual | ASP | PHI | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-01-01 |  | 1997-11-01 | 1998-08-01 | 15000 | 543 | 15543 | 15543 | 100% | 0 | 0 |  | 1950 | 71 | 2021 | 0 | 0 | FIN
FIN | UNIDO | National CFC recovery and recycling scheme | RMP | ASP | PHI | REF | 22 | TAS | 49 | A | I | CFC | 60 | 60 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2002-05-01 | 557500 | -49 | 557451 | 557450.97 | 100% | 0.03 | 0 |  | 72475 | -121 | 72354 | 0 | 0 | FIN
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | INV | 17 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-07-01 | 2010-03-31 |  | 2010-12-01 | 2011-05-01 | 50000 | -73 | 49927 | 49927.32 | 100% | -0.32 | 0 |  | 4500 | -7 | 4493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | INV | 21 | A | I |  | 1.8 | 1.8 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 |  | 2013-12-01 | 2014-04-01 | 45000 | -300 | 44700 | 44700.37 | 100% | -0.37 | 0 |  | 4050 | -27 | 4023 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | INV | 23 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-03-01 | 2013-03-31 | 2015-12-01 |  |  | 100000 | 0 | 100000 | 98570.94 | 98.57% | 1429.06 | 0 | 1429 | 9000 | 0 | 8871 | 129 | 0 | - The NOU and UNIDO are discussing activities to complete the first tranche of UNIDO's component and move into the second tranche. Activities planned but not implemented, reasons and strategy: Limited funds remaining under Tranche I and the fact that Tranche II is scheduled for 2016 makes it difficult to complete the former. Actions towards next goals: Reach an agreement on completion of Tranche I Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack agreement on how to use remaining funds under Tranche I; discussions in progress Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project completion date moved back to initial estimate Any action required by Executive Committee? No | - The NOU and UNIDO are discussing activities to complete the first tranche of UNIDO's component and move into the second tranche. Activities planned but not implemented, reasons and strategy: Limited funds remaining under Tranche I and the fact that Tranche II is scheduled for 2016 makes it difficult to complete the former. Actions towards next goals: Reach an agreement on completion of Tranche I Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack agreement on how to use remaining funds under Tranche I; discussions in progress Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project completion date moved back to initial estimate Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | QAT | FOA | 60 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 80000 | -891 | 79109 | 79108.51 | 100% | 0.49 | 0 |  | 6000 | -67 | 5933 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | QAT | PHA | 46 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-10-01 | 2006-07-01 |  | 2007-12-01 | 2007-12-01 | 30000 | -97 | 29903 | 29903.3 | 100% | -0.3 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | INV | 09 | A | I | CFC | 3 | 3 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2013-12-01 |  | 242500 | 0 | 242500 | 239799.63 | 98.89% | 2700.37 | 2534.52 | 2000 | 18188 | 0 | 17985 | 203 | 190 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | QAT | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 55000 | -1045 | 53955 | 53955.29 | 100% | -0.29 | 0 |  | 4125 | -78 | 4047 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | INV | 13 | A | I | CFC | 12 | 12 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2013-12-01 | 2013-12-01 | 70000 | -896 | 69104 | 69104.43 | 100% | -0.43 | 0 |  | 5250 | -67 | 5183 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | INV | 18 | A | I | HCFC | 1.6 | 0 |  |  | 2011-11-01 | 2013-02-01 | 2013-11-30 | 2015-12-01 |  |  | 131157 | 0 | 131157 | 130583.76 | 99.56% | 573.24 | 573.04 | 500 | 9837 | 0 | 9794 | 43 | 43 | 1. Expert has been identified and recruitment will proceed. 2. Activity to be completed and reported to the NOU by the 4th quarter in 2014. | Verification report was prepared and UNIDO and UNEP have prepared the second tranche submission to the 73rd ExCom Meeting. Unfortunately, obtaining Governmental endorsement has since then not happened. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | Multi-Year | ASP | QAT | PHA | 65 | INV | 19 | A | I | HCFC | 19.1 | 0 |  |  | 2011-11-01 | 2012-09-01 | 2013-11-30 | 2015-12-01 |  |  | 914750 | 0 | 914750 | -0.24 | -2.624e-05% | 914750.24 | 851847.04 | 650000 | 68606 | 0 | 0 | 68606 | 63889 | 1. Equipment is due to be delivered in the 3rd quarter of 2014. 2. Installation and commission will follow. Milestones achieved: Milestone 1: TOR for equipment prepared (Yes) Milestone 2: Equipment ordered (Yes) Milestone 3: Equipment delivered (Yes) Milestone 4: Equipment installed (No) Milestone 5: Equipment commissioned (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: Installation and commissioning Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No | 1. Equipment was delivered end 2014. 2. Installation and commissioning is planned to be completed by end 2015. Milestones achieved: Milestone 1: TOR for equipment prepared (Yes) Milestone 2: Equipment ordered (Yes) Milestone 3: Equipment delivered (Yes) Milestone 4: Equipment installed (No) Milestone 5: Equipment commissioned (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: Installation and commissioning Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | QAT | PHA | 73 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2016-11-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 1000 | 2800 | 0 | 0 | 2800 | 0 | No actions taken yet. Focus on completion of HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | No actions taken yet. Focus on completion of HPMP stage I. Milestones achieved: Milestone 1: Consultant recruited (No) Milestone 2: Data on sector available (No) Milestone 3: Draft strategy formulated (No) Milestone 4: Strategy agreed with stakeholders (No) Milestone 5: HPMP stage II submitted (No) Activities planned but not implemented, reasons and strategy: n/a Actions towards next goals: HPMP tranche 1 in final stage of implementation. Actions planned end 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | QAT | REF | 34 | TAS | 02 | A | I | CFC | 3.7 | 3.7 |  |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2007-12-01 | 2009-05-01 | 20000 | -3392 | 16608 | 16608.46 | 100% | -0.46 | 0 |  | 2600 | -441 | 2159 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of RMP: National recovery and recycling project | RMP Update | ASP | QAT | REF | 34 | TAS | 03 | A | I | CFC | 54.1 | 54.1 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2006-12-01 | 2007-12-01 | 295000 | -35 | 294965 | 294964.71 | 100% | 0.29 | 0 |  | 38350 | -5 | 38345 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Training of customs and Ozone Unit in monitoring and control of ODS | RMP Update | ASP | QAT | REF | 34 | TRA | 04 | A | I | CFC | 9.2 | 9.2 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 50000 | -2501 | 47499 | 47499.48 | 100% | -0.48 | 0 |  | 6500 | -335 | 6165 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of RMP: Training of trainers and technicians training in good refrigerant management practices | RMP Update | ASP | QAT | REF | 34 | TRA | 05 | A | I | CFC | 19.3 | 19.3 |  |  | 2001-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-12-01 | 2006-03-01 | 105000 | -5978 | 99022 | 99022.03 | 100% | -0.03 | 0 |  | 13650 | -798 | 12852 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of the Country Programme | Individual | ASP | QAT | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Institutional Strengthening Project: Creation of the National Ozone Unit | Individual | ASP | QAT | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-11-01 | 2002-04-01 |  | 2004-10-01 | 2005-12-01 | 68450 | -4279 | 64171 | 64170.89 | 100% | 0.11 | 0 |  | 8899 | -570 | 8329 | 0 | 0 | FIN |  |  | 2002-04-01 | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase 2 | Individual | ASP | QAT | SEV | 41 | INS | 06 | N | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2006-09-01 | 2008-05-01 | 44500 | -1215 | 43285 | 43284.99 | 100% | 0.01 | 0 |  | 3338 | -92 | 3246 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase II, second year funding) | Individual | ASP | QAT | SEV | 49 | INS | 08 | N | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-01-01 | 2007-07-01 |  | 2009-06-01 | 2012-12-01 | 44500 | -1719 | 42781 | 42780.98 | 100% | 0.02 | 0 |  | 3338 | -129 | 3209 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase III) | Individual | ASP | QAT | SEV | 59 | INS | 15 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2011-11-01 | 2017-12-01 |  |  | 48208 | 40792 | 89000 | 52.58 | 0.05908% | 88947.42 | 0 | 45000 | 3616 | 3059 | 4 | 6671 | 0 | - UNIDO continued liaising with Ministry of Environment to progress on the nomination of NOU staff to carry out IS implementation and to develop the work plan for the year 2014. Milestones achieved: Milestone 1: Agreement signed with Government for project implementation - Yes Milestone 2: NOU Officer nomination - No Milestone 3: NCs contracts - No Activities planned but not implemented, reasons and strategy: Project activities are planned, however, the implementation could not be progressed as nomination of the responsible team of experts (National Ozone Officer and experts) has not been received from counterpart. Actions towards next goals: UNIDO will continue liaising with Ministry of Environment to progress on the nomination of NOU staff to carry out IS implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Nomination of the National Ozone Officer and responsible team of experts pending. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date of project was re-scheduled in 2016. Any action required by Executive Committee? No | - There is no progress in implementation as no Ozone Officer and team of experts have been nominated by the relevant Government institution to carry the IS project implementation. Milestones achieved: Milestone 1: Nomination of Ozone Officer - No Milestone 2: Contracts for National Consultants - No Milestone 3: Work plan for re-scheduling the project activities - No Activities planned but not implemented, reasons and strategy: Nomination of NOU Ozone Officer and responsible team of experts pending Actions towards next goals: UNIDO will continue liaising with Ministry of Environment to progress on the nomination of NOU staff to carry out IS implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: as above Any recurring problem? Yes If yes, description of the problem/s: As quoted above Any impact on project completion date: Yes If yes, implications: Forecasted completion date was re-scheduled for 2017. Any action required by Executive Committee? No |  |  | NON-INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
FIN | UNIDO | Phasing out of CFCs at FARMEC SA | Individual | EUR | ROM | ARS | 18 | INV | 05 | A | I | CFC | 730 | 730 |  |  | 1995-11-01 | 1996-09-01 | 1997-11-01 |  | 1998-12-01 | 2001-07-01 | 895880 | -29399 | 866481 | 866481 | 100% | 0 | 0 |  | 116464 | -4000 | 112464 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | Individual | EUR | ROM | ARS | 44 | INV | 26 | A | I | CFC | 46.5 | 46.5 |  |  | 2004-12-01 | 2005-07-01 | 2007-02-01 |  | 2006-06-01 | 2007-09-01 | 204776 | -640 | 204136 | 204136 | 100% | 0 | 0 |  | 18430 | -58 | 18372 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS at Spumotim flexible foam plant | Individual | EUR | ROM | FOA | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1996-05-01 | 15000 | 132 | 15132 | 15132 | 100% | 0 | 0 |  | 1950 | 17 | 1967 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at S.C. Spumotim S.A. | Individual | EUR | ROM | FOA | 20 | INV | 09 | A | I | CFC | 30 | 30 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1997-12-01 | 2000-07-01 | 142293 | -83 | 142210 | 142210 | 100% | 0 | 0 |  | 18498 | -40 | 18458 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | EUR | ROM | FOA | 23 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-05-01 | 2001-07-01 | 10000 | 1667 | 11667 | 11667 | 100% | 0 | 0 |  | 1300 | 214 | 1514 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC 11 and CFC-12 in the manufacture of extruded polyethylene and polystyrene foams through the use of butane as a blowing agent at Romcarbon, S.A. | Individual | EUR | ROM | FOA | 27 | INV | 15 | A | I | CFC | 132.4 | 132.4 |  |  | 1999-03-01 | 2000-04-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 516512 | 0 | 516512 | 516511.83 | 100% | 0.17 | 0 |  | 66816 | -11 | 66805 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | EUR | ROM | FUM | 23 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-03-01 | 2001-07-01 | 10000 | -780 | 9220 | 9220 | 100% | 0 | 0 |  | 1300 | -103 | 1197 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | ROM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 10000 | -322 | 9678 | 9678.05 | 100% | -0.05 | 0 |  | 1300 | -44 | 1256 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | ROM | HAL | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-04-01 | 15000 | -571 | 14429 | 14429.08 | 100% | -0.08 | 0 |  | 1125 | -43 | 1082 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Halon management programme | Individual | EUR | ROM | HAL | 50 | TAS | 37 | A | I | HAL | 3.5 | 3.5 |  |  | 2006-11-01 | 2007-11-01 | 2008-11-01 |  | 2008-06-01 | 2009-06-01 | 32500 | -447 | 32053 | 32053.47 | 100% | -0.47 | 0 |  | 2925 | -40 | 2885 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Terminal phase-out management plan of CTC production/consumption for process agent uses | Individual | EUR | ROM | PAG | 50 | INV | 36 | A | I | CTC | 120.5 | 120.5 |  |  | 2006-11-01 | 2007-06-01 | 2007-11-01 |  |  | 2010-09-01 | 1389800 | -370032 | 1019768 | 1019768.14 | 100% | -0.14 | 0 |  | 104235 | -27752 | 76483 | 0 | 0 | CLO |  |  | 2009-12-01 | INV
FIN | UNIDO | Project preparation: CFC phase-out plan (aerosol and refrigeration) | Individual | EUR | ROM | PHA | 42 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-10-01 |  | 2005-08-01 | 2005-08-01 | 10000 | -1012 | 8988 | 8988.31 | 100% | -0.31 | 0 |  | 750 | -77 | 673 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | INV | 30 | A | I | CFC | 14.6 | 40 |  |  | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-03-01 | 2010-12-01 | 159050 | 0 | 159050 | 159050.03 | 100% | -0.03 | 0 |  | 11929 | 0 | 11929 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | ROM | PHA | 48 | INV | 34 | A | I | CFC | 35.8 | 35.8 |  |  | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2010-12-01 | 2011-05-01 | 236750 | 0 | 236750 | 236750.01 | 100% | -0.01 | 0 |  | 17756 | 0 | 17756 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | ROM | PHA | 51 | INV | 38 | A | I | CFC | 48.9 | 48.9 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | ROM | PHA | 60 | TAS | 41 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2012-02-01 | 83219 | -898 | 82321 | 82320.82 | 100% | 0.18 | 0 |  | 6241 | -67 | 6174 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a closure project in the production of CFC/CTC/MBR | Individual | EUR | ROM | PRO | 45 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-12-01 | 25000 | -3848 | 21152 | 21151.72 | 100% | 0.28 | 0 |  | 1875 | -289 | 1586 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Sector plan for production sector | Multi-Year | EUR | ROM | PRO | 47 | INV | 32 | A | I | MBR | 0 | 0 | 5 | 5 | 2005-11-01 | 2006-04-01 | 2006-07-01 |  | 2006-12-01 | 2011-12-01 | 3200000 | -150 | 3199850 | 3199850.03 | 100% | -0.03 | 0 |  | 240000 | -11 | 239989 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (second tranche) | Multi-Year | EUR | ROM | PRO | 50 | INV | 35 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2007-06-01 | 2012-10-01 | 900000 | -41472 | 858528 | 858528.16 | 100% | -0.16 | 0 |  | 67500 | -3110 | 64390 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (third tranche) | Multi-Year | EUR | ROM | PRO | 52 | INV | 39 | A | I | CTC | 0 | 0 | 170 | 170 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2007-12-01 | 2008-07-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (fourth tranche) | Multi-Year | EUR | ROM | PRO | 53 | INV | 40 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2010-12-01 | 2012-11-01 | 1200000 | 0 | 1200000 | 1199999.88 | 100% | 0.12 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 at refrigerator plant at mechanical enterprises SADU and ARCTIC | Individual | EUR | ROM | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-04-01 | 1995-06-01 |  | 1996-07-01 | 1998-08-01 | 50000 | -4907 | 45093 | 45093 | 100% | 0 | 0 |  | 6500 | -647 | 5853 | 0 | 0 | FIN
FIN | UNIDO | Phase out ODS at the domestic refrigeration factory Arctic S.A. | Individual | EUR | ROM | REF | 18 | INV | 06 | A | R | CFC | 206 | 206.7 |  |  | 1995-11-01 | 1996-10-01 | 1997-05-01 |  | 1997-05-01 | 2000-07-01 | 1095300 | -48009 | 1047291 | 1047291 | 100% | 0 | 0 |  | 142389 | -6457 | 135932 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic and commercial refrigeration sector | Individual | EUR | ROM | REF | 18 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-05-01 |  | 1999-03-01 | 2000-07-01 | 20000 | -808 | 19192 | 19192 | 100% | 0 | 0 |  | 2600 | -109 | 2491 | 0 | 0 | FIN |  |  | 1999-03-01
CLO | UNIDO | Conversion of commercial refrigeration equipment to phase out CFC-12, HCFC-502 and CFC-11 at Technofrig S.A. | Individual | EUR | ROM | REF | 19 | INV | 08 | A | I | CFC | 6.92 | 6.92 |  |  | 1996-05-01 | 1997-03-01 | 1999-06-01 |  |  | 2000-07-01 | 297768 | -255677 | 42091 | 42091 | 100% | 0 | 0 |  | 38710 | -33247 | 5463 | 0 | 0 | CLO |  |  | 1999-07-01
FIN | UNIDO | Phasing out CFC-11 and CFC-12 in the production of domestic refrigerators and replacing them by cyclopentane and HFC-134a at Ratmil, Uzine Mecanica Sadu | Individual | EUR | ROM | REF | 20 | INV | 10 | A | I | CFC | 73.3 | 73.3 |  |  | 1996-10-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2002-05-01 | 937859 | 0 | 937859 | 937859.21 | 100% | -0.21 | 0 |  | 121922 | 0 | 121922 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | ROM | REF | 24 | PRP | 14 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 30000 | -1043 | 28957 | 28957 | 100% | 0 | 0 |  | 3900 | -142 | 3758 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | ROM | REF | 28 | TAS | 16 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 373840 | 0 | 373840 | 373840.46 | 100% | -0.46 | 0 |  | 48599 | -69 | 48530 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | EUR | ROM | REF | 28 | TRA | 17 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-10-01 |  | 2002-08-01 | 2003-10-01 | 23100 | -1349 | 21751 | 21750.58 | 100% | 0.42 | 0 |  | 3003 | -180 | 2823 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | ROM | REF | 28 | TRA | 19 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2001-01-01 | 2001-06-01 | 70000 | 0 | 70000 | 70000.07 | 100% | -0.07 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Preparation of Country Programme | Individual | EUR | ROM | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1995-07-01 | 1998-08-01 | 80000 | -23457 | 56543 | 56543 | 100% | 0 | 0 |  | 10400 | -3061 | 7339 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | ROM | SEV | 17 | INS | 04 | N | I |  | 0 | 0 |  |  | 1995-07-01 | 1997-12-01 | 1998-07-01 |  | 2003-12-01 | 2005-01-01 | 168443 | -80350 | 88093 | 88092.81 | 100% | 0.19 | 0 |  | 21898 | -10464 | 11434 | 0 | 0 | FIN |  |  | 2000-01-01 | NON-INV
FIN | UNIDO | Country programme update | Individual | EUR | ROM | SEV | 36 | CPG | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-01-01 | 2004-04-01 | 60000 | -356 | 59644 | 59644 | 100% | 0 | 0 |  | 7800 | -59 | 7741 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase II | Individual | EUR | ROM | SEV | 45 | INS | 29 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-05-01 | 145984 | -981 | 145003 | 145003.27 | 100% | -0.27 | 0 |  | 10949 | -74 | 10875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvent sector | Individual | EUR | ROM | SOL | 39 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-10-01 | 2005-05-01 | 15000 | -785 | 14215 | 14215.32 | 100% | -0.32 | 0 |  | 1125 | -61 | 1064 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project for the phase-out of ODS solvents | Individual | EUR | ROM | SOL | 41 | INV | 22 | A | I | CTC | 11.1 | 11.1 |  |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-12-01 | 2007-05-01 | 220615 | -6247 | 214368 | 214367.81 | 100% | 0.19 | 0 |  | 19855 | -562 | 19293 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal umbrella project to phase out CTC | Individual | EUR | ROM | SOL | 44 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 20000 | -900 | 19100 | 19099.72 | 100% | 0.28 | 0 |  | 1500 | -67 | 1432 | 1 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | INV | 18 | A | I | HCFC | 0.2 | 0 |  |  | 2011-07-01 | 2012-11-01 | 2016-07-31 | 2015-12-01 |  |  | 55000 | 0 | 55000 | 51620.53 | 93.86% | 3379.47 | 0 | 3000 | 4950 | 0 | 4646 | 304 | 0 | - 'The NOU requested residual funds to be used for purchase of HC demonstration units. Milestones achieved: Milestone 1: Yes - Equipment were delivered in early 2014. Was there any delay during the reporting year? Yes If yes, reasons and action plan: There were problems encountered with clearing the equipment at the ports. Any recurring problem? Yes If yes, description of the problem/s: There were problems encountered with clearing the equipment at the ports. They were moved to customs warehouses and a lengthy procedure ensued to release them. Any impact on project completion date: No Any action required by Executive Committee? No | - There were problems encountered with clearing the equipment at the ports. They were moved to customs warehouses and a lengthy procedure ensued to release them. - The clearing agent has now retrieved the equipment with the customs, and equipment have been delivered to beneficiaries. Milestones achieved: Milestone 1: Yes - Equipment retrieved from Customs warehouse Milestone 2: Yes - Equipment delivered to beneficiaries. Was there any delay during the reporting year? No. Any recurring problem? No. Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SAU | FOA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2010-12-01 | 2013-12-01 | 80000 | -681 | 79319 | 79319.34 | 100% | -0.34 | 0 |  | 6000 | -51 | 5949 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Multi-Year | ASP | SAU | FOA | 62 | INV | 11 | A | I | HCFC | 28.9 | 28.9 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2016-10-01 |  |  | 615323 | 0 | 615323 | 101664.88 | 16.52% | 513658.12 | 212930.87 | 260000 | 46149 | 0 | 7625 | 38524 | 15970 | - The Purchase Order for the equipment has been issued in January 2014 and first tranche of funds (50%) disbursed in February 2014. - The equipment has been delivered to the project site in January 2014. - The company had to conduct an engineering study for the erection of the new production facilities which was completed in October. The erection of the new facility was completed in December 2014. Milestones achieved: Milestone 1: Equipment delivery to the beneficiary - Yes Milestone 2: Installation, start-up and commissioning - No Activities planned but not implemented, reasons and strategy: Installation, start-up and commissioning delayed, but this is out of control of the PM Was there any delay during the reporting year? Yes If yes, reasons and action plan: The site was not ready for installation Any recurring problem? No Any impact on project completion date: 6 month delay If yes, implications: The completion of the project was shifted into 2016 Any action required by Executive Committee? No | - Installation, start-up and commissioning was completed in March 2015 and confirmed by the Certificate of Acceptance. - The final payment for the equipment was disbursed. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Verification visit of the Project Manager on the full operation of the new line - No Activities planned but not implemented, reasons and strategy: Visit planned in the 4th Q 2015. As reported earlier, funds reallocated from the NPP to HPMP were partially used to cover the costs of this project in order to fulfil ExCom requirements to financially close the NPP, since the certification and code of practice conducted by UNEP was delayed. Remaining funds under this tranche will be used for the purpose approved for it by the ExCom when reallocation of funds was decided. |  |  | INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Multi-Year | ASP | SAU | FOA | 62 | INV | 13 | A | I | HCFC | 19 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2016-06-16 |  |  | 1103578 | 0 | 1103578 | 10702.98 | 0.9698% | 1092875.02 | 879682.63 | 250000 | 82768 | 0 | 803 | 81965 | 65976 | - After breakdown in communication with the company, finally the company agreed to go ahead with the procurement of the equipment. - The Invitation to Bidding was published in April 2014. Offers from two qualified suppliers were received in June 2014. - The technical and financial evaluation was conducted in July/August 2014 and the best technically acceptable offer was selected in September 2014. - Negotiations about the contract with UNIDO Procurement Service and the supplier about details in the contract (acceptance of payment schedule, TUV certification of the equipment, change of the supplier company) extended into 2015. Milestones achieved: Milestone 1: Invitation to bidding published - Yes Milestone 2: Bids from qualified suppliers received - Yes Milestone 3: Technical and financial evaluation completed - Yes Milestone 4: Contract to the selected supplier awarded - No Activities planned but not implemented, reasons and strategy: The award of the contract was delayed due to the fact that the supplier requested several changes to UNIDO standard contract and negotiations with UNIDO Procurement service prolonged until end of 2014. Was there any delay during the reporting year? Yes see above If yes, reasons and action plan: Out of control of the PM. See above. Any recurring problem? No Any impact on project completion date: Estimated delay of 12 months If yes, implications: No implications on compliance since 142b is banned in KSA Any action required by Executive Committee? No | - The contract to the selected supplier was issued in February 2015. - Technical meeting at Al-Watania was organized in June 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Contract issued - Yes Milestone 2: Technical meeting organized - Yes Milestone 3: Customs clearance of the equipment arranged - No Milestone 4: Equipment delivered at the project site - No Milestone 5: Equipment installed and commissioned - No Activities planned but not implemented, reasons and strategy: Customs clearance to be organized on provision that either the beneficiary pays the import tax or applies for the industrial exemption from the customs tax Actions towards next goals: Beneficiary notified of the requirements on the customs tax Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | INV | 03 | A | I | CFC | 269.7 | 269.7 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2013-12-01 |  | 1287000 | 0 | 1287000 | 1256042.41 | 97.59% | 30957.59 | 30792.62 | 30000 | 96525 | 0 | 94203 | 2322 | 2309 |  |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SAU | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-03-01 | 2009-07-31 |  | 2012-12-01 | 2013-12-01 | 130000 | -24 | 129976 | 129975.6 | 100% | 0.4 | 0 |  | 9750 | -2 | 9748 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | INV | 10 | A | I | CFC | 532 | 532 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2013-12-01 | 2013-12-01 | 143000 | -4506 | 138494 | 138493.69 | 100% | 0.31 | 0 |  | 10725 | -377 | 10387 | -39 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2015-12-31 | 2015-12-01 |  |  | 341733 | 0 | 341733 | 341732.63 | 100% | 0.37 | -0.23 |  | 23921 | 0 | 23921 | 0 | -0.0161 | - Progress of work depending on progress of UNEP implemented component, namely on the Update of Code of Practice on RAC, Finalization of the certification scheme for RAC service workshops that were planned for the 2nd half of 2014. Milestones achieved: Milestone 1: Training programme for service technicians developed - Yes Milestone 2: Pilot training workshop of trainers implemented - No Activities planned but not implemented, reasons and strategy: Pilot training of trainers will be organized once the Code of Practice in RAC is fully updated and the scheme for certification of service technicians is introduced Actions towards next goals: Organize the pilot training and follow-up trainings Was there any delay during the reporting year? Yes due to protracted negotiations of UNEP with the KSA Government on approval and introduction of the certification scheme for service technicians. The delay was caused by the request for harmonization of the scheme with similar efforts in other states in the GCC. If yes, reasons and action plan: The training programme will start in mid 2015. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Progress of work depending on progress of UNEP implemented component, namely on the Update of Code of Practice on RAC, Finalization of the certification scheme for RAC service workshops that were finalized only in 1st half of 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Pilot training workshop organized on 24-27 August 2015 - Yes Milestone 2: Follow-up workshops organized - No Activities planned but not implemented, reasons and strategy: Follow-up workshops will be organized in the 4th Q 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | INV | 19 | A | I | HCFC | 52.1 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2015-12-31 | 2016-06-16 |  |  | 1827867 | 0 | 1827867 | 1355850.63 | 74.18% | 472016.37 | 236693.77 | 235694 | 127951 | 0 | 94910 | 33041 | 16568.5639 | - The down payment of 30% value of the Purchase Order was disbursed in January 2014 which brought the level of disbursement as of 7 March 2014 to a level satisfactory for submission of the request for the 2nd tranche that was approved by the 72nd ExCom in May 2014. - The equipment was delivered in July 2014 but was detained by the Saudi customs since they refused to clear it. - Initial workshop for the systems houses conducted in February 2014. - A consultant appointed to prepare technical specification and concept of assistance to the SHs. - Follow-up workshop was organized in December 2014 but only one SH indicated readiness to undergo the conversion. Milestones achieved: Milestone 1: Delivery of equipment to KSA - Yes Milestone 2: Customs clearance - No Milestone 3: Delivery to beneficiary companies - No Milestone 4: Installation, commissioning, start-up - No Milestone 5: Follow up workshop for SHs - Yes Activities planned but not implemented, reasons and strategy: Customs clearance was rejected by the Saudi customs on entry to the KSA, UNDP was requested to help. Actions towards next goals: A letter from the Ministry of Foreign Affairs KSA was obtained in December 2014 requesting the customs to clear the equipment. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Refusal of the Saudi Customs to clear the equipment Any recurring problem? No Any impact on project completion date: Yes. Delay in delivery of the equipment to the beneficiaries. Any action required by Executive Committee? The problem was reported to the MLF Evaluation mission in March 2015. | - Despite the Letter from the MFA requesting the customs to clear the equipment the latter refused to do so. - Protracted negotiations with the customs and the beneficiary companies led to an agreement that the beneficiaries will pay the due customs tax. - The NOU sent a request for a waiver of the port detention fees but after protracted proceedings this was rejected by the Saudi Customs. - Finally decision was taken to pay all due charges to get the equipment released from the customs. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Customs clearance of PU foam equipment - Yes Milestone 2: Delivery to the beneficiaries - Yes Milestone 3: Installation and commissioning of PU foam equipment - No Activities planned but not implemented, reasons and strategy: Customs clearance for the SH equipment has to be ensured prior the shipment starts. Actions towards next goals: Beneficiary should apply for industrial exemption or pay the customs import tax. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 72 | INV | 20 | A | I | HCFC | 2.6 | 0 |  |  | 2014-05-01 |  | 2016-12-31 | 2017-03-01 |  |  | 270000 | 0 | 270000 | 0 | 0% | 270000 | 0 | 1000 | 18900 | 0 | 0 | 18900 | 0 | - Approved at the 72nd Meeting of the ExCom in May 2014 on the understanding that the approved funds will not be transferred to UNIDO until the Secretariat has received a verification report confirming that the Government of Saudi Arabia was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. - Due to the delay in approval of the Verification Report for 2013 consumption the 2nd tranche was received only in November 2014. Further progress was delayed by the slow progress in implementation of the UNEP component on Code of Practice and certification scheme (see more details under the 1st tranche, SAU/PHA/68/INV/17). Activities planned but not implemented, reasons and strategy: Wait for the completion of the UNEP preparatory activities on certification and code of good practice. Was there any delay during the reporting year? Yes as above. | - As mentioned above under the 1st tranche, SAU/PHA/68/INV/17, the progress in the service sector delayed by slow progress of UNEP work on code of good practice and certification of service technicians. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Training programme planned - Yes Milestone 2: Training workshops implemented - No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 72 | INV | 21 | A | I | HCFC | 75.8 | 0 |  |  | 2014-05-01 |  | 2016-12-31 | 2017-06-01 |  |  | 2701487 | -7813 | 2693674 | 0 | 0% | 2693674 | 0 | 500000 | 189104 | -547 | 0 | 188557 | 0 | - Approved at the 72nd Meeting of the ExCom in May 2014 on the understanding that the approved funds will not be transferred to UNIDO until the Secretariat has received a verification report confirming that the Government of Saudi Arabia was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. - The Verification Report had to be amended according to the requirements of the MLF Secretariat, hence the 2nd tranche was received only in November 2014. - Mission of international foam expert was fielded in July 2014 to finalize Technical Specification for the next 3-4 PU foam manufacturers. - The Invitation to Bidding was published in August 2014 and supplier for of equipment for 3 companies was selected in November 2014. Milestones achieved: Milestone 1: Verification Report approved and 2nd tranche received - Yes Milestone 2: Foam Expert mission and Tech. Specification for PU foam companies finalized - Yes Milestone 3: Invitation to bidding published - Yes Milestone 4: Contract issued for selected supplier - No Activities planned but not implemented, reasons and strategy: Contract issuance was delayed due to protracted negotiations about the contract terms with the supplier. Actions towards next goals: UNIDO Procurement to negotiate the contract terms with the selected supplier. Was there any delay during the reporting year? Yes. Delay due to the late arrival of the 2nd tranche. If yes, reasons and action plan: The delay was partially overcome by advance publishing of the Invitation to Bidding. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - International foam expert visited the System House ready for conversion in April 2015 and finalized the Technical Specification for the equipment. - Invitation to bidding for one System House was published in May 2015 and a contract to the selected supplier was awarded in August 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Milestones achieved: Milestone 1: Expert mission to finalize the Technical Specification for SH - Yes Milestone 2: Invitation to bidding for equipment for SH - Yes Milestone 3: Contract issued for selected supplier for SH equipment - Yes Milestone 4: Shipment to the first beneficiary (Alamut/ALBA) - Yes Milestone 5: Shipment to the other 2 beneficiaries - No Activities planned but not implemented, reasons and strategy: Shipment to the other 2 beneficiaries planned in October/November 2015. Actions towards next goals: The 2 beneficiaries must obtain industrial exemption from the customs tax or pay the tax themselves. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | SAU | REF | 60 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2012-12-01 | 2013-12-01 | 80000 | -1008 | 78992 | 78992.43 | 100% | -0.43 | 0 |  | 6000 | -76 | 5924 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a country programme/national phase-out plan | Individual | ASP | SAU | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-09-01 | 2008-01-01 |  | 2007-12-01 | 2008-12-01 | 65000 | -3270 | 61730 | 61729.79 | 100% | 0.21 | 0 |  | 4875 | -245 | 4630 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | AFR | SEN | FOA | 18 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 | 0 |  | 1300 | -73 | 1227 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, peanuts) | Individual | AFR | SEN | FUM | 25 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-01-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide used in peanut seed fumigation in Novasen Ltd. | Individual | AFR | SEN | FUM | 26 | INV | 12 | A | I | MBR | 0.7 | 0.7 |  |  | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-02-01 | 62945 | -3226 | 59719 | 59718.78 | 100% | 0.22 | 0 |  | 8183 | -432 | 7751 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | SEN | PHA | 48 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 15000 | -3043 | 11957 | 11957.21 | 100% | -0.21 | 0 |  | 1125 | -228 | 897 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SEN | PHA | 55 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-05-01 | 85000 | -1026 | 83974 | 83973.9 | 100% | 0.1 | 0 |  | 6375 | -77 | 6298 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | INV | 31 | A | I | HCFC | 2.4 | 2.4 |  |  | 2011-11-01 | 2012-02-01 | 2014-11-30 | 2016-12-01 |  |  | 200000 | 0 | 200000 | 103022.08 | 51.51% | 96977.92 | 3150.56 | 2437 | 15000 | 0 | 7727 | 7273 | 236 | - Technicians training programme and certification was achieved as scheduled in the tranche 1 work plan. - Technical specification for equipment delivery has been developed, however, purchase of equipment is subject to second tranche approval. Milestones achieved: Milestone 1: Train the trainer component for servicing sector - Yes Milestone 2: Training of technicians - Yes Milestone 3: Equipment specification in view of equipment purchase - Yes Actions towards next goals: Contracting Verification report in view of tranche 2 submission Was there any delay during the reporting year? No If yes, reasons and action plan: (narrative): NA Any recurring problem? Yes If yes, description of the problem/s: Discrepancies in HCFCs consumption data that needs to be addressed within verification report. Any impact on project completion date: No If yes, implications: (narrative): NA Any action required by Executive Committee? No | - Tranche 1 activities are implemented. - Initiation of the implementation of the activities under tranche 2 are pending on the approval of the second tranche of the HPMP. Milestones achieved: Milestone 1: Verification report elaboration - Yes Milestone 2: Submission of tranche 2 to the 74th Meeting of the ExCom - No Activities planned but not implemented, reasons and strategy: Tranche 2 approval was withdrawn from 74th ExCom's agenda due to discrepancies in the HCFCs consumption data in the 2013 year. Actions towards next goals: NOU committed additional data verifications and review of the Consumption Verification Report for the years 2013 and 2014. Was there any delay during the reporting year? Yes If yes, reasons and action plan: There is 1.5 years delay in implementation due to resubmission of tranche 2 for the consideration of the 75th ExCom and due to the fact that equipment purchase depends on the next tranche approval (the remaining tranche balance is insufficient for achieving the purchase) Any recurring problem? No Any impact on project completion date: 6 months delays for the completion of current tranche implementation. If yes, implications: (narrative): There are no expected further delays in completion of the current tranche implementation; activities were implemented except equipment delivery for which available project balance is insufficient. The equipment purchase is pending on the approval of tranche 2, that's why the planned completion date has been moved to the end of 2016. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | SEN | REF | 22 | TAS | 08 | A | I | CFC | 36.12 | 36.12 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-03-01 | 136250 | 0 | 136250 | 136250 | 100% | 0 | 0 |  | 17713 | 0 | 17713 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP: Refrigerant recovery and recycling scheme | RMP Update | AFR | SEN | REF | 33 | TAS | 16 | A | I | CFC | 56.1 | 56.1 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2003-03-01 | 2004-04-01 | 85000 | -1970 | 83030 | 83030.13 | 100% | -0.13 | 0 |  | 11050 | -273 | 10777 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a project proposal for setting up a national refrigerant recovery and recycling centre, National Halon Bank | Individual | AFR | SEY | REF | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1998-01-01 | 2000-07-01 | 15000 | -10846 | 4154 | 4154 | 100% | 0 | 0 |  | 1950 | -1411 | 539 | 0 | 0 | FIN |  |  | 1999-02-01
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 | 2015-12-01 |  |  | 50000 | 0 | 50000 | 47620 | 95.24% | 2380 | 0 | 2000 | 4500 | 0 | 4286 | 214 | 0 | - Training use of equipment continued in 2014. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Activities were suspended due to the Ebola outbreak. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Planned completion date: May 2016. Any action required by Executive Committee? No | - Activities were suspended due to the Ebola outbreak. - Training on use of equipment will continue in 2015 with residual funds. - Planned completion date: December 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SOA | FOA | 59 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2012-12-01 | 2014-07-01 | 150000 | -2119 | 147881 | 147881.22 | 100% | -0.22 | 0 |  | 11250 | -159 | 11091 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | FOA | 67 | INV | 03 | A | I | HCFC | 24.9 | 0 |  |  | 2012-07-01 | 2013-02-01 | 2013-07-31 | 2016-12-01 |  |  | 1850224 | 0 | 1850224 | 1645050.63 | 88.91% | 205173.37 | 121015.95 | 140000 | 129516 | 0 | 115154 | 14362 | 8471.1165 | - The ToR prepared, bidding was completed. - The delivery and training are still pending. - Contracts awarded for foam SME. Equipment delivered. - Commissioning and trial runs are planned for the 2nd half of 2014. Milestones achieved: Milestone 1: Equipment for the completed biddings delivered - Yes Milestone 2: Contractions and civil works completed - No Milestone 3: New contract for remaining enterprises/ ToR prepared- No Milestone 4: New biddings conducted - No Activities planned but not implemented, reasons and strategy: The contract between a System House and UNIDO could not be signed. The system house did not agree on the terms and conditions for UNIDO tenders proposed by UNIDO procurement. Due to the large co-fin. (larger then the approved fund) the enterprise prefers to conduct the tender themselves without financial support from HPMP. Actions towards next goals: Preparation of ToR/agreements with remaining eligible SMEs in the foam sector. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The approved costs for System Houses are lower than the actual cost. Co-financing from the SH is required. Development of procurement conditions acceptable for the end-users. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Procurement of equipment -Yes Milestone 2: Extension of contract of national expert - Yes Milestone 3: Preparation of the ToR /agreements for other SMEs in foams - No Activities planned but not implemented, reasons and strategy: Conversion of System Houses to MF technology. The MF technology needs adoption at the end-user level. This is connected to additional cost and time. Without qualified support the new technology is not competitive on the market. Actions towards next goals: Continue the programme with the SMEs in foam sector. Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Clarifications on the bidding process needed. Any impact on project completion date: Yes If yes, implications: Implementation delays due to the complicated approving process, bid number of SME, co-investment. Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOA | PHA | 55 | PRP | 01 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-06-01 | 2009-07-31 |  | 2012-12-01 |  | 195000 | 0 | 195000 | 194998.11 | 100% | 1.89 | -123.47 | 1 | 14625 | 0 | 14625 | 0 | -9 |  | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 67 | TAS | 04 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 | 2016-06-16 |  |  | 110005 | 0 | 110005 | -0.37 | -0.0003363% | 110005.37 | -0.05 | 40000 | 7700 | 0 | 0 | 7700 | -0.0035 | - Stakeholders workshop held. - Local institutions identified. Experts recruited. - Training of customs officers (CO) conducted 2nd half of 2014. Milestones achieved: Milestone 1: Training of Customs officers conducted Yes Milestone 2: Training materials for CO distributed Yes Milestone 3: Stakeholders workshop conducted Yes Milestone 4: Awareness material No Milestone 5: Improvement of the legislation by the Government No Activities planned but not implemented, reasons and strategy: Awareness material not finalized. The NOU is working on the recommendations (from Customs Officers workshops and Stakeholders meetings) Actions towards next goals: Continue the consultation process with the Stakeholders. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The consultation workshops identified some needs to improve the planned legislation changes. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | - Experts recruited. - Additional training of customs officers is planned for 2nd half of 2015. Milestones achieved: Milestone 1: Stakeholders workshop conducted Yes Milestone 2: Awareness material No Milestone 3: Revision of the BL data by the Government No Activities planned but not implemented, reasons and strategy: Baseline data under revision by the NOU. Actions towards next goals: National expert recruited to assist the NOU in collection of the relevant data. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The Ministry is not able to share the internal data, therefore no assistance can be provided with the revision of the data. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Additional assistance for IA could speed up the revision of data. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, secondtranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | PHA | 71 | INV | 05 | A | I | HCFC | 35.7 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-06-01 | 2017-03-01 |  |  | 2042620 | 0 | 2042620 | 121531.85 | 5.95% | 1921088.15 | 819133.06 | 500000 | 142983 | 0 | 8507 | 134476 | 57339.3142 | - The ToR prepared, bidding was completed. - The delivery and training are still pending. - Contracts awarded for foam SME. Equipment delivered. - Commissioning and trial runs are planned for the 2nd half of 2014. Milestones achieved: Milestone 1: Equipment for the completed biddings delivered - Yes Milestone 2: Contractions and civil works completed - No Milestone 3: New contract for remaining enterprises/ ToR prepared- No Milestone 4: New biddings conducted - No Activities planned but not implemented, reasons and strategy: The contract between a System House and UNIDO could not be signed. The system house did not agree on the terms and conditions for UNIDO tenders proposed by UNIDO procurement. Due to the large co-fin. (larger then the approved fund) the enterprise prefers to conduct the tender themselves without financial support from HPMP. Actions towards next goals: Preparation of ToR/agreements with remaining eligible SMEs in the foam sector. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The approved costs for System Houses are lower than the actual cost. Co-financing from the SH is required. Development of procurement conditions acceptable for the end-users. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Procurement of equipment -Yes Milestone 2: Extension of contract of national expert - Yes Milestone 3: Preparation of the ToR /agreements for other SMEs in foams - No Activities planned but not implemented, reasons and strategy: Conversion of System Houses to MF technology. The MF technology needs adoption at the end-user level. This is connected to additional cost and time. Without qualified support the new technology is not competitive on the market. Actions towards next goals: Continue the programme with the SMEs in foam sector. Was there any delay during the reporting year? No Any recurring problem? No If yes, description of the problem/s: Clarifications on the bidding process needed. Any impact on project completion date: No If yes, implications: Implementation delays due to the complicated approving process, bid number of SME, co-investment. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 71 | INV | 06 | A | I | HCFC | 6.2 | 0 |  |  | 2013-12-01 | 2014-03-01 | 2016-06-01 | 2017-03-01 |  |  | 550000 | 0 | 550000 | 10072.57 | 1.831% | 539927.43 | 0 | 50000 | 38500 | 0 | 705 | 37795 | 0 | - Stakeholders workshop held. - Local institutions identified. Experts recruited. - Training of customs officers (CO) conducted 2nd half of 2014. Milestones achieved: Milestone 1: Training of Customs officers conducted Yes Milestone 2: Training materials for CO distributed Yes Milestone 3: Stakeholders workshop conducted Yes Milestone 4: Awareness material No Milestone 5: Improvement of the legislation by the Government No Activities planned but not implemented, reasons and strategy: Awareness material not finalized. The NOU is working on the recommendations (from Customs Officers workshops and Stakeholders meetings) Actions towards next goals: Continue the consultation process with the Stakeholders. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The consultation workshops identified some needs to improve the planned legislation changes. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Experts recruited. - Additional training of customs officers is planned for 2nd half of 2015. Milestones achieved: Milestone 1: Stakeholders workshop conducted Yes Milestone 2: Awareness material No Milestone 3: Revision of the BL data by the Government No Activities planned but not implemented, reasons and strategy: Baseline data under revision by the NOU. Actions towards next goals: National expert recruited to assist the NOU in collection of the relevant data. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The Ministry is not able to share the internal data, therefore no assistance can be provided with the revision of the data. Any recurring problem? No Any impact on project completion date: No If yes, implications: Additional assistance for IA could speed up the revision of data. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 75th meeting to monitor the low disbursement rates of approved funds
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOM | PHA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2012-12-01 | 2014-05-01 | 85000 | -4040 | 80960 | 80959.62 | 100% | 0.38 | 0 |  | 6375 | -303 | 6072 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SOM | PHA | 67 | INV | 08 | A | I | HCFC | 0.5 | 0 |  |  | 2012-07-01 | 2013-02-01 | 2016-07-31 | 2017-03-01 |  |  | 133500 | 0 | 133500 | 82415.8 | 61.73% | 51084.2 | 22064.3 | 20000 | 9345 | 0 | 5769 | 3576 | 1544.501 | - Shipment of equipment. - Identification of potential counterparts for training. Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2: Advance training conducted - Yes Activities planned but not implemented, reasons and strategy: Training for R+R technicians Actions towards next goals: No offers received for the training in Somalia or outside. Was there any delay during the reporting year? No If yes, reasons and action plan: Due to the visa difficulties it was not possible to organize the training at the training facilities of the equipment supplier. Supply of the training equipment to neighboring countries is difficult and expensive. Moreover air tickets costs and visa problems would still remain problems. Any recurring problem? Yes If yes, description of the problem/s: Security situation in the country. Any impact on project completion date: Yes If yes, implications: Delays in the implementation Any action required by Executive Committee? No | Milestones achieved: Milestone 1: ToR for the training prepared - Yes Milestone 2: Bidding conducted - Yes Milestone 3: Contract awarded - No Activities planned but not implemented, reasons and strategy: Training for R+R technicians Actions towards next goals: Training outside Somalia. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Due to the visa difficulties it was not possible to organize the training at the training facilities of the equipment supplier. Supply of the training equipment to neighboring countries is difficult and expensive. Moreover air tickets costs and visa problems would still remain problems. UNIDO is investigating the possibilities to conduct the training in the Seychelles or in Djibouti like the trainings organized by other UN organizations (like FAO). Any recurring problem? Yes If yes, description of the problem/s: Security situation in the country. Any impact on project completion date: Yes If yes, implications: Delays in the implementation Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (additional security) | Multi-Year | AFR | SOM | PHA | 67 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-02-01 | 2016-07-31 | 2017-03-01 |  |  | 40374 | 0 | 40374 | -0.2 | -0.0004954% | 40374.2 | 0.3 | 20000 | 2826 | 0 | 0 | 2826 | 0.021 | - Shipment of equipment. - Identification of potential counterparts for training. Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2:Advance training conducted - Yes Activities planned but not implemented, reasons and strategy: Training for R+R technicians Actions towards next goals: No offers received for the training in Somalia or outside. Was there any delay during the reporting year? No If yes, reasons and action plan: Due to the visa difficulties it was not possible to organize the training at the training facilities of the equipment supplier. Supply of the training equipment to neighboring countries is difficult and expensive. Moreover air tickets costs and visa problems would still remain problems. Any recurring problem? Yes If yes, description of the problem/s: Security situation in the country. Any impact on project completion date: Yes If yes, implications: Delays in the implementation Any action required by Executive Committee? No | Milestones achieved: Milestone 1: ToR for the training prepared - Yes Milestone 2:Bidding conducted - Yes Milestone 3:Contract awarded - No Activities planned but not implemented, reasons and strategy: Training for R+R technicians Actions towards next goals: Training outside Somalia. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Due to the visa difficulties it was not possible to organize the training at the training facilities of the equipment supplier. Supply of the training equipment to neighboring countries is difficult and expensive. Moreover air tickets costs and visa problems would still remain problems. UNIDO is investigating the possibilities to conduct the training in the Seychelles or in Djibouti like the trainings organized by other UN organizations (like FAO). Any recurring problem? Yes If yes, description of the problem/s: Security situation in the country. Any impact on project completion date: Yes If yes, implications: (narrative): Delays in the implementation Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | INV | 17 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-04-01 | 2012-07-31 |  | 2014-07-01 | 2014-07-01 | 88850 | -2 | 88848 | 88847.7 | 100% | 0.3 | 0 |  | 7997 | 0 | 7996 | 1 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | INV | 21 | A | I | HCFC | 0.1 | 0.05 |  |  | 2012-12-01 | 2013-06-01 | 2015-12-31 | 2015-12-01 |  |  | 11000 | 0 | 11000 | 1387.99 | 12.62% | 9612.01 | 0 | 9612 | 990 | 0 | 125 | 865 | 0 | - Training of the trainers and technicians is planned. It is also planned to purchase some refrigeration simulators. Milestones achieved: Milestone 1: Plan for training and certification. No Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO was prepared for the submission of the next tranche to the 74th Meeting of the ExCom, but was informed by UNEP, that UNEP as lead agency and the Government of St. Lucia agreed to delay the submission to the 75th Meeting of the ExCom. - The training of trainers and technicians is targeted. A first attempt was made with Centro Galileo but the funds available were not enough to cover the activity. - A second option proposed by UNIDO is being evaluated. - It is expected to carry out the training before the end of 2015. Milestone 1: Plan for training and certification. No Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | INV | 14 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-08-01 | 2010-03-31 |  | 2009-12-01 | 2011-05-01 | 66000 | -242 | 65758 | 65758.46 | 100% | -0.46 | 0 |  | 5940 | -22 | 5918 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | INV | 17 | A | I | CFC | 0.7 | 0.7 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2011-12-01 | 2011-12-01 | 49000 | -479 | 48521 | 48520.81 | 100% | 0.19 | 0 |  | 4410 | -43 | 4367 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | INV | 20 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-07-01 | 2013-04-01 | 2014-12-31 | 2015-12-01 |  |  | 124115 | 0 | 124115 | 105572.32 | 85.06% | 18542.68 | 16436.25 | 16436 | 11170 | 0 | 9502 | 1668 | 1479 | - Residual funds will be used for distribution, local procurement of training materials and training on use of equipment. Milestones achieved: Milestone 1: Yes - TOR was agreed with NOO. Milestone 2: Yes - Residual funds were used to procure additional service tools and equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Residual funds were used to procure additional service tools and equipment. - The final activity was concluded in the 1st quarter of the year. - Project will be closed after distribution of equipment ends, expectedly by the end of 2015. Milestones achieved: Milestone 1: Yes - Equipment were delivered in March 2015 Actions towards next goals: Equipment distribution is ongoing Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Phasing out of CFCs at Sudanese Cosmetics and Household Products | Individual | AFR | SUD | ARS | 18 | INV | 04 | A | I | CFC | 281.5 | 281.5 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 497613 | -297 | 497316 | 497316 | 100% | 0 | 0 |  | 64690 | -141 | 64549 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | SUD | ARS | 27 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 25000 | -7393 | 17607 | 17606.64 | 100% | 0.36 | 0 |  | 3250 | -965 | 2285 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Tag Cosmetics Ltd. | Individual | AFR | SUD | ARS | 28 | INV | 13 | A | I | CFC | 45.1 | 45.1 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2002-07-01 | 2002-12-01 | 131718 | 0 | 131718 | 131718 | 100% | 0 | 0 |  | 17123 | -8 | 17115 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Patra Foam Co. flexible polyurethane foam plant | Individual | AFR | SUD | FOA | 19 | INV | 05 | A | I | CFC | 16 | 16 |  |  | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1997-12-01 | 2000-04-01 | 72227 | 0 | 72227 | 72227 | 100% | 0 | 0 |  | 9390 | -1 | 9389 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SUD | FOA | 59 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 40000 | -607 | 39393 | 39393.45 | 100% | -0.45 | 0 |  | 3000 | -45 | 2955 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of domestic refrigerators, commercial refrigerators and PU insulated composite panels (Modern, Amin, Coldair, Akadabi) | Multi-Year | AFR | SUD | FOA | 62 | INV | 28 | A | I | HCFC | 11.9 | 11.9 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2015-12-01 |  |  | 1056341 | 0 | 1056341 | 1055371.31 | 99.91% | 969.69 | 11.91 | 900 | 79226 | 0 | 79153 | 73 | 1 | - Foaming equipment, to convert technology at four beneficiaries to cyclopentane, has been delivered in 2013; waiting for installation. Project sites are being prepared (by Counterparts) for installation and commissioning. As installation, commissioning start-up and training activities to be financed by counterparts (as a cost sharing), separate offers have been prepared for these activities by the supplier of equipment. Technical content and costs of the offers agreed earlier under UNIDO auspice (as in the course of the evaluation of the offers) and further formalized in Working Agreements countersigned by Counterparts, National Ozone Unit, and UNIDO. - Separate offers have been received and accepted by each counterpart. Down payment for installation, commissioning start-up and training has yet been effected by two counterparts. Installation, commissioning start-up and training originally planned for October 2013 have been re-scheduled for April 2014. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: Activities: Installation, commissioning, training and trial runs. Reasons: 1. lack of agreement/understanding of counterparts with the supplier of equipment on the payment of their cost sharing for commissioning, training, start-up, 2. supplier's lack of planning for Sudan and also over estimation of security situation in the Country. Strategy: UNIDO to closely coordinate among the counterparts, supplier of equipment and the NOU to help with planning and to mobilize counterpart technical and financial sources to install and utilize the equipment. Actions towards next goals: UNIDO mission to revisit the counterparts; review work plans and set up new milestones. (UNIDO - NOU joint visits to counterparts took place in November 2014; milestones for installation activities in first quarter of 2015 (before high season) were set up ) Was there any delay during the reporting year? Yes If yes, reasons and action plan: See above Any impact on project completion date: Yes If yes, implications: Delayed installation, commissioning, training, start up trials will cause delay in project completion. Any action required by Executive Committee? No | - The project was stagnant since; a) counterparts have been still utilizing allowed import quota and eventually also their (quite large) stocks, b) Installation and commissioning of equipment missed two seasonal terms (relatively lower activity autumn and winter time), due to; 1. lack of agreement/understanding of counterparts with the supplier of equipment on the payment of their cost sharing for commissioning, training, start-up, 2. supplier's lack of planning for Sudan and also due to over estimated security concerns. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: Activities: Installation, commissioning, training and trial runs. Reasons: 1. lack of agreement/understanding of counterparts with the supplier of equipment on the payment of their cost sharing for commissioning, training, start-up, 2. supplier's lack of planning for Sudan and also over estimation of security situation in the Country. Strategy: In the course of coordination between counterparts, NOU and supplier of equipment, UNIDO set up final term for installation latest in October - November 2015. The NOU committed to monitor locally and coordinate with counterparts as the non availability of blowing agent should not cause sudden production hardship in the Country . Supplier of equipment has not confirmed fixed term, at the time of completion of this report. Actions towards next goals: Close coordination towards soonest possible installation and utilization of equipment. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Reasons as mentioned above. Project activities are supposed to be completed by December 2015. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | SUD | FOA | 72 | PRP | 34 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 20000 | 2800 | 0 | 0 | 2800 | 0 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in the foam sector and identification of HCFC -141b users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC 141b users Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in the foam sector accomplished, users of HCFC -141b and potential project beneficiaries of conversion investment projects identified. - Drafting of the investment component, HPMP Stage II for the foam sector in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission, commitment letters from eligible counterparts and Government Letter of transmittal are being obtained. Independent technical review is being arranged. Was there any delay during the reporting year? No Uncertainty of ExCom approval for Stage II. Any recurring problem? No Any impact on project completion date: No Uncertainty of ExCom approval for Stage II. Any action required by Executive Committee? No |  |  | NON-INV
COM | UNIDO | Project preparation in the fumigants sector (post-harvest) | Individual | AFR | SUD | FUM | 71 | PRP | 31 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 |  | 2014-12-31 |  | 30000 | 0 | 30000 | 23782.27 | 79.27% | 6217.73 | 4586.47 | 4000 | 2100 | 0 | 1665 | 435 | 321.0529 | - UNIDO and the NOU met and agreed on a work plan for the project preparation. - Project submitted and approved at the 73rd Meeting of the ExCom in November 2014. |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for the final phase-out of methyl bromide in the post harvest sector | Individual | AFR | SUD | FUM | 73 | TAS | 36 | A | I | MBR | 1.2 | 0 |  |  | 2014-11-01 |  | 2016-12-30 | 2017-03-01 |  |  | 181610 | 0 | 181610 | 0 | 0% | 181610 | 0 | 40000 | 16345 | 0 | 0 | 16345 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014 on the understanding that no additional funding will be provided for Sudan for the phase-out of controlled uses of MB in the country; and that the Government of the Sudan is committed to meeting the complete phase-out of MB by 1 January 2015 by banning imports for controlled MB uses. | - UNIDO and NOU discussed and agreed on implementation modalities. - UNIDO finalized the technical specifications and initiated the bidding procedures. Milestones achieved: Milestone 1: Legal agreements - Yes Milestone 2: Initial stages of project implementation began - Yes Milestone 3: Intermediate goals achieved - Yes Milestone 4: Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: All on track Actions towards next goals: Finalize the bidding, proceed with installation and commissioning. Ensure proper training. Implement awareness and policy activities, as per project document. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | SUD | PHA | 41 | PRP | 15 | A | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 70000 | -294 | 69706 | 69706.47 | 100% | -0.47 | 0 |  | 5250 | -30 | 5220 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (first tranche) | Multi-Year | AFR | SUD | PHA | 44 | INV | 18 | A | I | CFC CTC | 17.4 | 17.4 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2010-12-01 | 499480 | -105 | 499375 | 499375.19 | 100% | -0.19 | 0 |  | 37461 | -8 | 37453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (second tranche) | Multi-Year | AFR | SUD | PHA | 50 | INV | 19 | A | I | CFC | 70 | 70 |  |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2007-12-01 | 2009-05-01 | 220000 | -88 | 219912 | 219912.27 | 100% | -0.27 | 0 |  | 16500 | -7 | 16493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (third tranche) | Multi-Year | AFR | SUD | PHA | 53 | INV | 20 | A | I | CFC | 65 | 65 |  |  | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-12-01 | 2012-12-01 | 220000 | -298 | 219702 | 219701.7 | 100% | 0.3 | 0 |  | 16500 | -22 | 16478 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SUD | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 30000 | -2950 | 27050 | 27050.21 | 100% | -0.21 | 0 |  | 2250 | -221 | 2029 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC/CTC phase-out plan (fourth tranche) | Multi-Year | AFR | SUD | PHA | 58 | INV | 23 | A | I | CFC | 65.3 | 65.3 |  |  | 2009-07-01 | 2009-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-10-01 | 200000 | -1130 | 198870 | 198869.69 | 100% | 0.31 | 0 |  | 15000 | -85 | 14915 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | SUD | PHA | 59 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 | 2014-04-01 | 120000 | -402 | 119598 | 119597.9 | 100% | 0.1 | 0 |  | 9000 | -30 | 8970 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SUD | PHA | 66 | INV | 29 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2013-05-01 | 2013-04-30 | 2015-12-01 |  |  | 250000 | 0 | 250000 | 206748.49 | 82.7% | 43251.51 | 25526.49 | 40935 | 18750 | 0 | 15506 | 3244 | 1914.4868 | - HCFC consumption verification audit initiated. Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Actions towards next goals: Training of trainers to be organized for the organizations which received training/didactic equipment in the course of the implementing of NPP Was there any delay during the reporting year No Any recurring problem? No | - Assistance with monitoring and public awareness has been provided to the NOU. - Technical assistance to customs office has been also provided to launch electronic system for licensing and quota. - Training of trainers for participants from Technical University in Khartoum, Association of Refrigeration & Air-conditioning Engineers, Ministry of Industry an Institute for Refrigeration and Air- conditioning Research, took place in Germany. The training was organized in collaboration with GIZ and focused on new systems using natural refrigerants. - Project activities are planned to be completed by the end of 2015. Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | SUD | PHA | 72 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 22000 | 1750 | 0 | 0 | 1750 | 0 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in respective HCFCs consuming sectors and identification of HCFC users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC users Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in respective HCFC consuming sectors accomplished; users of HCFCs and potential project beneficiaries, including government, non-governmental organizations, RAC associations and other stakeholders identified. - Drafting of the project document, HPMP Stage II in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission are being obtained. Independent technical review is being organized. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Uncertainty of ExCom approval for Stage II. If yes, implications: (narrative): Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | SUD | PHA | 73 | INV | 35 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2017-12-31 | 2017-12-31 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 20000 | 7700 | 0 | 0 | 7700 | 0 | - Approved at the 73rd Meeting of the ExCom in November 2014 on the understanding that approval of further funding will be subject to satisfactorily addressing the issues on the licensing and quota system identified in the verification report. Noted that the Agreement was updated to reflect the change in support costs owing to the new administrative cost regime. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - No Milestone 4:- Project completion and follow-up - No | - Technical specification for purchase of equipment to identify refrigerants and monitor their imports is drafted in collaboration with customs office and NOU. - TOR for verification audit is being prepared. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Actions towards next goals: Purchase of refrigerants identifiers for customs authorities and for recovery and recycling centers. Organize certification of service shops for proper recovery and recycling in multi refrigerant market. Training on proper use of identification, service and recovery recycling equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Phasing out of ODS at three small domestic refrigerator factories in Sudan (Coldair Refrigerator Factory, Modern Refrigerator + Metal furniture Co., Sheet Metal Industries Co. Refrigerator Factory) | Individual | AFR | SUD | REF | 19 | INV | 06 | A | I | CFC | 7.28 | 7.3 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 2002-03-01 | 2003-05-01 | 100000 | -13637 | 86363 | 86363.36 | 100% | -0.36 | 0 |  | 13000 | -1791 | 11209 | 0 | 0 | FIN |  |  | 1997-08-01
FIN | UNIDO | Preparation of Refrigerant Management Plan | Individual | AFR | SUD | REF | 23 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 1998-12-01 | 2000-04-01 | 10000 | 16173 | 26173 | 26173 | 100% | 0 | 0 |  | 1300 | 2097 | 3397 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | AFR | SUD | REF | 28 | TAS | 10 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2004-08-01 | 2006-09-01 | 350000 | -1732 | 348268 | 348268.38 | 100% | -0.38 | 0 |  | 45500 | -225 | 45275 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | AFR | SUD | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2002-06-01 |  | 2003-12-01 | 2003-12-01 | 70000 | -510 | 69490 | 69490.04 | 100% | -0.04 | 0 |  | 9100 | -81 | 9019 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | AFR | SUD | REF | 28 | TRA | 11 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2001-08-01 | 2001-02-01 |  | 2002-10-01 | 2004-09-01 | 38250 | -1916 | 36334 | 36333.7 | 100% | 0.3 | 0 |  | 4973 | -257 | 4716 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic/commercial refrigeration sector | Individual | AFR | SUD | REF | 39 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-09-01 | 2004-04-01 |  | 2005-04-01 | 2005-08-01 | 20000 | -345 | 19655 | 19655.29 | 100% | -0.29 | 0 |  | 1500 | -28 | 1472 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | AFR | SUD | REF | 59 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2012-12-01 | 2014-04-01 | 60000 | -290 | 59710 | 59710.36 | 100% | -0.36 | 0 |  | 4500 | -22 | 4478 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | AFR | SUD | REF | 72 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 | 2016-07-31 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 19000 | 2450 | 0 | 0 | 2450 | 0 | - Project was approved at the 72nd Meeting of the ExCom in May 2014. - Survey in the refrigeration and air-conditioning sector and identification of HCFC -22 importers and users have been initiated. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - No Milestone 7: Draft document completed - No Actions towards next goals: Verification of the consumption data at identified HCFC 22 users Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Survey in the refrigeration and air conditioning sector accomplished users of HCFC -22 and potential receivers of technical and financial assistance identified. - Drafting of the non-investment component, HPMP Stage II for the refrigeration and air-conditioning sectors in progress. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission are being obtained. Independent technical review is being organized. Was there any delay during the reporting year? No Uncertainty of ExCom approval for Stage II. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the refrigeration, aerosol and foam sectors | Individual | AFR | SUD | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-03-01 | 1995-01-01 |  | 1998-04-01 | 1999-08-01 | 50000 | -5442 | 44558 | 44558 | 100% | 0 | 0 |  | 6500 | -717 | 5783 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | INV | 18 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 | 2016-12-01 |  |  | 68000 | 0 | 68000 | 57178.4 | 84.09% | 10821.6 | 0 | 1000 | 6120 | 0 | 5146 | 974 | 0 | - Training on use of equipment will continue. - Residual funds will be used together with 2nd tranche. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: A new Ozone Officer was supposed to be appointed as the previous one was promoted. However, after a long wait, this did not happen and Ozone officer remains the same. Activities will continue under the current Ozone Officer and funds will be combined with 2nd tranche. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | - The needs of the service sector will be reassessed together with the National Ozone Officer Actions towards next goals: Re-assess needs of service sector and combine funds with 2nd tranche to make interventions more effective. Was there any delay during the reporting year? Yes If yes, reasons and action plan: A new Ozone Officer was supposed to be appointed as the previous one was promoted. However, after a long wait, this did not happen and Ozone officer remains the same. Activities will continue under the current Ozone Officer and funds will be combined with 2nd tranche. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration production at FridgeMaster | Individual | AFR | SWA | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 25000 | -13308 | 11692 | 11692 | 100% | 0 | 0 |  | 3250 | -1733 | 1517 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | ASP | SYR | ARS | 18 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-05-01 |  | 1998-05-01 | 1999-08-01 | 25000 | -746 | 24254 | 24254 | 100% | 0 | 0 |  | 3250 | -102 | 3148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Gaston Banna & Sons Co. | Individual | ASP | SYR | ARS | 19 | INV | 13 | A | I | CFC | 104 | 104 |  |  | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 1998-12-01 | 2000-04-01 | 299500 | 0 | 299500 | 299500 | 100% | 0 | 0 |  | 38935 | 0 | 38935 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Careesse Cosmetics | Individual | ASP | SYR | ARS | 21 | INV | 16 | A | I | CFC | 185 | 185 |  |  | 1997-02-01 | 1997-06-01 | 1998-04-01 |  | 1998-12-01 | 2000-12-01 | 272621 | -1208 | 271413 | 271413 | 100% | 0 | 0 |  | 35441 | -213 | 35228 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al Yaman | Individual | ASP | SYR | ARS | 22 | INV | 20 | A | I | CFC | 95 | 95 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2002-08-01 | 216128 | -2737 | 213391 | 213391.36 | 100% | -0.36 | 0 |  | 28097 | -400 | 27697 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ahmed Ali Harsho Sons Co. | Individual | ASP | SYR | ARS | 22 | INV | 21 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-12-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 175328 | -3796 | 171532 | 171532.15 | 100% | -0.15 | 0 |  | 22793 | -529 | 22264 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Taki Eddin & Co. | Individual | ASP | SYR | ARS | 22 | INV | 22 | A | I | CFC | 118.8 | 118.8 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 244203 | 0 | 244203 | 244203.21 | 100% | -0.21 | 0 |  | 31746 | -44 | 31702 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Laboratories Kosmeto | Individual | ASP | SYR | ARS | 23 | INV | 23 | A | I | CFC | 59.9 | 59.9 |  |  | 1997-11-01 | 1998-10-01 | 1999-02-01 |  | 1999-10-01 | 2001-11-01 | 175062 | -1772 | 173290 | 173289.67 | 100% | 0.33 | 0 |  | 22758 | -266 | 22492 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Dina Cosmetics | Individual | ASP | SYR | ARS | 23 | INV | 24 | A | I | CFC | 70 | 70 |  |  | 1997-11-01 | 1998-10-01 | 1999-08-01 |  | 2000-07-01 | 2001-12-01 | 228477 | -456 | 228021 | 228021.2 | 100% | -0.2 | 0 |  | 29702 | -106 | 29596 | 0 | 0 | FIN
FIN | UNIDO | Preparation of at least three investment projects in the aerosol sector for phasing out ODS at three enterprises including Nweylati | Individual | ASP | SYR | ARS | 23 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2001-05-01 | 10000 | 4480 | 14480 | 14480.39 | 100% | -0.39 | 0 |  | 1300 | 579 | 1879 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mariza Co. | Individual | ASP | SYR | ARS | 25 | INV | 31 | A | I | CFC | 90 | 90 |  |  | 1998-07-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 207652 | -3210 | 204442 | 204442.48 | 100% | -0.48 | 0 |  | 26995 | -460 | 26535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al-Fajer Co. | Individual | ASP | SYR | ARS | 26 | INV | 36 | A | I | CFC | 44 | 44 |  |  | 1998-11-01 | 1999-10-01 | 2000-04-01 |  | 2000-06-01 | 2001-07-01 | 169985 | -1059 | 168926 | 168926 | 100% | 0 | 0 |  | 22098 | -172 | 21926 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 27 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-07-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 8000 | -1359 | 6641 | 6640.69 | 100% | 0.31 | 0 |  | 1040 | -178 | 862 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | Individual | ASP | SYR | ARS | 32 | INV | 71 | A | I | CFC | 15.6 | 15.6 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 68640 | 0 | 68640 | 68639.82 | 100% | 0.18 | 0 |  | 8923 | -3 | 8920 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | Individual | ASP | SYR | ARS | 32 | INV | 72 | A | I | CFC | 10.5 | 10.5 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 46200 | 0 | 46200 | 46200.14 | 100% | -0.14 | 0 |  | 6006 | -3 | 6003 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | Individual | ASP | SYR | ARS | 32 | INV | 73 | A | I | CFC | 11 | 11 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 48400 | -31 | 48369 | 48369.2 | 100% | -0.2 | 0 |  | 6292 | -14 | 6278 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | Individual | ASP | SYR | ARS | 32 | INV | 74 | A | I | CFC | 36 | 36 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 87298 | -770 | 86528 | 86527.74 | 100% | 0.26 | 0 |  | 11349 | -118 | 11231 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 from the manufacturing of pre-fabricated sandwich panels at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -1404 | 13596 | 13596 | 100% | 0 | 0 |  | 1950 | -185 | 1765 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for phasing out of CFC-11 from the sub sector of flexible foams manufacturing | Individual | ASP | SYR | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Phasing out CFC-11 at Dakkak Co. flexible polyurethane foam plant | Individual | ASP | SYR | FOA | 19 | INV | 14 | A | I | CFC | 17 | 17 |  |  | 1996-05-01 | 1996-10-01 | 1997-05-01 |  | 1998-12-01 | 2001-11-01 | 96553 | 0 | 96553 | 96552.94 | 100% | 0.06 | 0 |  | 12552 | -17 | 12535 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 19 | INV | 15 | A | I | CFC | 65 | 65 |  |  | 1996-05-01 | 1996-11-01 | 1997-09-01 |  | 1998-12-01 | 2001-07-01 | 644600 | -9228 | 635372 | 635371.9 | 100% | 0.1 | 0 |  | 83798 | -1331 | 82467 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Abdul Karim Sbei | Individual | ASP | SYR | FOA | 21 | INV | 17 | A | I | CFC | 61.7 | 61.7 |  |  | 1997-02-01 | 1997-06-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 92256 | -1984 | 90272 | 90272 | 100% | 0 | 0 |  | 11993 | -276 | 11717 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Walid and Nabil Rankousi Ltd. | Individual | ASP | SYR | FOA | 21 | INV | 18 | A | I | CFC | 38.7 | 38.7 |  |  | 1997-02-01 | 1998-11-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 86782 | -2175 | 84607 | 84607 | 100% | 0 | 0 |  | 11282 | -301 | 10981 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | ASP | SYR | FOA | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-06-01 |  | 2000-12-01 | 2002-09-01 | 10000 | -362 | 9638 | 9638.11 | 100% | -0.11 | 0 |  | 1300 | -49 | 1251 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Akal Factory | Individual | ASP | SYR | FOA | 23 | INV | 25 | A | I | CFC | 101 | 101 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 2002-10-01 | 2004-04-01 | 510130 | 0 | 510130 | 510130.14 | 100% | -0.14 | 0 |  | 66317 | -26 | 66291 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of investment projects for NPD in Damascus and others in rigid foam sector | Individual | ASP | SYR | FOA | 24 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-04-01 | 2002-09-01 | 15000 | -238 | 14762 | 14762.04 | 100% | -0.04 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU slabstock foam through the use of CO2 blowing technology at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 26 | INV | 32 | A | I | CFC | 96 | 96 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2001-12-01 | 2003-12-01 | 543918 | 0 | 543918 | 543917.73 | 100% | 0.27 | 0 |  | 69831 | -3 | 69828 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Phasing out CFC-11 in the manufacture of flexible PU slabstock foam through the use of methylene chloride as blowing agent at Chaar Bros Co. | Individual | ASP | SYR | FOA | 26 | INV | 34 | A | I | CFC | 50 | 50 |  |  | 1998-11-01 | 1999-02-01 | 2000-04-01 |  | 2000-05-01 | 2001-07-01 | 98248 | -79 | 98169 | 98169 | 100% | 0 | 0 |  | 12772 | -30 | 12742 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to cyclopenthane in the production of rigid foam panels at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 31 | INV | 61 | A | I | CFC | 61.1 | 61.1 |  |  | 2000-07-01 | 2001-04-01 | 2002-08-01 |  | 2004-10-01 | 2005-04-01 | 426104 | 0 | 426104 | 426103.9 | 100% | 0.1 | 0 |  | 55394 | -46 | 55348 | 0 | 0 | FIN |  |  | 2003-11-01
FIN | UNIDO | Preparation of a project in the flexible foam sector | Individual | ASP | SYR | FOA | 31 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-12-01 | 2003-05-01 | 20000 | -27 | 19973 | 19973.47 | 100% | -0.47 | 0 |  | 2600 | -8 | 2592 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | Individual | ASP | SYR | FOA | 32 | INV | 68 | A | I | CFC | 16.4 | 16.4 |  |  | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2005-12-01 | 2006-12-01 | 126862 | -2164 | 124698 | 124697.51 | 100% | 0.49 | 0 |  | 16492 | -281 | 16211 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al-Muzayek | Individual | ASP | SYR | FOA | 34 | INV | 76 | A | I | CFC | 33.7 | 33.7 |  |  | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-12-01 | 2004-12-01 | 106789 | 0 | 106789 | 106789.12 | 100% | -0.12 | 0 |  | 13883 | -9 | 13874 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the extruded polystyrene foam sector | Individual | ASP | SYR | FOA | 36 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 15000 | -80 | 14920 | 14919.91 | 100% | 0.09 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polystyrene (EPS) foam for packing purposes at Shanko and Partners Co. | Individual | ASP | SYR | FOA | 38 | INV | 88 | A | I | CFC | 16 | 16 |  |  | 2002-11-01 | 2003-11-01 | 2005-06-01 |  | 2004-08-01 | 2004-12-01 | 132200 | 0 | 132200 | 132200.18 | 100% | -0.18 | 0 |  | 17186 | -23 | 17163 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SYR | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 | 2016-12-01 |  |  | 40000 | 0 | 40000 | 23387.53 | 58.47% | 16612.47 | 16540 | 16540 | 3000 | 0 | 1754 | 1246 | 1241 | No progress due to the situation in the country. | No progress due to the situation in the country. |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | SYR | FUM | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in horticulture and commodities fumigation | Individual | ASP | SYR | FUM | 24 | DEM | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 2001-05-01 | 2003-05-01 | 509850 | -33283 | 476567 | 476566.89 | 100% | 0.11 | 0 |  | 66281 | -4425 | 61856 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a project in the fumigant (methyl bromide) sector for grain fumigation | Individual | ASP | SYR | FUM | 31 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2001-07-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -5357 | 14643 | 14642.91 | 100% | 0.09 | 0 |  | 2600 | -699 | 1901 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage (first tranche) | Multi-Year | ASP | SYR | FUM | 34 | INV | 80 | A | I | MBR | 5 | 5 |  |  | 2001-07-01 | 2002-08-01 | 2002-12-01 |  | 2006-12-01 | 2008-12-01 | 300000 | 0 | 300000 | 299999.97 | 100% | 0.03 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | FIN |  |  | 2005-12-01 | INV
FIN | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | Multi-Year | ASP | SYR | FUM | 41 | INV | 89 | A | I | MBR | 29.8 | 29.8 |  |  | 2003-12-01 | 2005-02-01 | 2004-12-01 |  | 2010-12-01 | 2010-12-01 | 351725 | -1572 | 350153 | 350152.88 | 100% | 0.12 | 0 |  | 26379 | -118 | 26261 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Phase-out methyl bromide in grain fumigation (third tranche) | Multi-Year | ASP | SYR | FUM | 47 | INV | 94 | A | I | MBR | 70.2 | 70.2 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2011-12-01 | 2013-10-01 | 432414 | -6506 | 425908 | 425907.91 | 100% | 0.09 | 0 |  | 32431 | -488 | 31943 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Methyl bromide national phase-out plan (soil fumigation) | Individual | ASP | SYR | FUM | 49 | TAS | 95 | A | I | MBR | 48 | 75 |  |  | 2006-07-01 | 2007-12-01 | 2010-07-01 |  | 2013-12-01 |  | 240000 | 0 | 240000 | 239805.64 | 99.92% | 194.36 | 193.8 | 1 | 21600 | 0 | 21583 | 17 | 17 | N.a. | Refund will be returned to the 74th ExCom and the project will have a FIN status. |  |  | INV
CLO | UNIDO | Preparation of a national ODS phase-out plan | Individual | ASP | SYR | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-10-01 |  |  | 2003-05-01 | 60000 | -56845 | 3155 | 3155.02 | 100% | -0.02 | 0 |  | 7800 | -7390 | 410 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of CFC-phase-out plan including methyl bromide | Individual | ASP | SYR | PHA | 45 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-12-01 | 2008-12-01 | 70000 | -1900 | 68100 | 68100.06 | 100% | -0.06 | 0 |  | 5250 | -142 | 5108 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan for Syria (first tranche) | Multi-Year | ASP | SYR | PHA | 49 | INV | 96 | A | I | CFC | 100 | 100 |  |  | 2006-07-01 | 2006-10-01 | 2008-07-01 |  | 2010-12-01 | 2013-10-01 | 430000 | -550 | 429450 | 429450.08 | 100% | -0.08 | 0 |  | 32250 | -41 | 32209 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SYR | PHA | 55 | PRP | 97 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2016-12-01 |  |  | 136250 | 0 | 136250 | 108362.56 | 79.53% | 27887.44 | 0 | 1000 | 10219 | 0 | 8127 | 2092 | 0 | No progress due to the situation in the country. | No progress due to the situation in the country. |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | ASP | SYR | PHA | 56 | INV | 98 | A | I | CFC | 328.7 | 328.7 |  |  | 2008-11-01 | 2009-12-01 | 2009-11-30 |  | 2010-12-01 | 2012-10-01 | 170000 | 0 | 170000 | 169999.98 | 100% | 0.02 | 0 |  | 12750 | 0 | 12750 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | ASP | SYR | PHA | 58 | INV | 99 | A | I | CFC | 70 | 70 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2013-12-01 | 2013-12-01 | 154050 | -130197 | 23853 | 23852.73 | 100% | 0.27 | 0 |  | 11554 | -9765 | 1789 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFCs at Al Hafez Refrigeration Co. | Individual | ASP | SYR | REF | 13 | INV | 04 | A | I | CFC | 106.7 | 100.7 |  |  | 1994-07-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 2001-05-01 | 2883277 | 0 | 2883277 | 2883277 | 100% | 0 | 0 |  | 374826 | 0 | 374826 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFC at Penguin (Syrian Batric Co.) | Individual | ASP | SYR | REF | 15 | INV | 05 | A | I | CFC | 82.3 | 77.3 |  |  | 1994-12-01 | 1996-01-01 | 1996-06-01 |  | 1996-12-01 | 2000-12-01 | 1719900 | -1241 | 1718659 | 1718659 | 100% | 0 | 0 |  | 223587 | -515 | 223072 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Barada General Co. for Metallic Industry | Individual | ASP | SYR | REF | 15 | INV | 09 | A | I | CFC | 109 | 97 |  |  | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-12-01 | 2001-07-01 | 989650 | -95593 | 894057 | 894057.23 | 100% | -0.23 | 0 |  | 128655 | -12612 | 116043 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC in manufacturing of refrigerators at Krayem Int. Co. | Individual | ASP | SYR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -711 | 14289 | 14289 | 100% | 0 | 0 |  | 1950 | -95 | 1855 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs from Manufacturing of domestic and commercial refrigerators at Krayem Brothers Co. | Individual | ASP | SYR | REF | 18 | INV | 11 | A | I | CFC | 89 | 89 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1998-12-01 | 2002-09-01 | 1071575 | -13558 | 1058017 | 1058016.79 | 100% | 0.21 | 0 |  | 139305 | -1981 | 137324 | 0 | 0 | FIN
CLO | UNIDO | Preparation of an investment project in recovery and recycling sector | Individual | ASP | SYR | REF | 18 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-01-01 |  |  | 2001-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  | 1999-12-01
FIN | UNIDO | Project preparation of investment projects in the domestic refrigeration sector | Individual | ASP | SYR | REF | 27 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2002-09-01 | 20000 | -2856 | 17144 | 17143.74 | 100% | 0.26 | 0 |  | 2600 | -375 | 2225 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Golden Penguin Co. | Individual | ASP | SYR | REF | 28 | INV | 45 | A | I | CFC | 18.4 | 18.4 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 247481 | -52260 | 195221 | 195221.44 | 100% | -0.44 | 0 |  | 32173 | -6834 | 25339 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Alaman Co. | Individual | ASP | SYR | REF | 28 | INV | 60 | A | I | CFC | 15.9 | 15.9 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 215910 | -36884 | 179026 | 179026.39 | 100% | -0.39 | 0 |  | 28068 | -4832 | 23237 | -1 | 0 | FIN
CLO | UNIDO | Preparation of an investment project in the domestic refrigeration sector | Individual | ASP | SYR | REF | 36 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 87 | A | I | CFC | 51 | 51 |  |  | 2002-11-01 | 2003-06-01 | 2004-11-01 |  | 2006-12-01 | 2007-12-01 | 353100 | -527 | 352573 | 352573.39 | 100% | -0.39 | 0 |  | 40590 | -61 | 40529 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers | Individual | ASP | SYR | REF | 47 | DEM | 93 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 |  | 2013-12-01 | 2013-12-01 | 585961 | -210532 | 375429 | 375428.74 | 100% | 0.26 | 0 |  | 43947 | -15790 | 28157 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | ASP | SYR | REF | 58 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2011-12-01 | 60000 | -1229 | 58771 | 58770.71 | 100% | 0.29 | 0 |  | 4500 | -92 | 4408 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Individual | ASP | SYR | REF | 62 | INV | 103 | A | I | HCFC | 12.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2017-06-01 |  |  | 1465361 | 0 | 1465361 | 211294.27 | 14.42% | 1254066.73 | 192118.5 | 80000 | 109902 | 0 | 15847 | 94055 | 14409 | - In the context of the subcontract for the redesign and prototyping of the company's main products, the subcontractor Second Progress Report was received and cleared by UNIDO. - For the time being, any activity involving the procurement and delivery of equipment in the company's facilities is not possible due to the situation in the country. Milestones achieved: Milestone 1: Yes - Prototype units working on R410A selected Activities planned but not implemented, reasons and strategy: For the time being, any activity involving the procurement and delivery of equipment in the company's facilities is not possible due to the situation in the country. Actions towards next goals: Completion of the redesign and prototyping and re-assessment of the situation in the country Was there any delay during the reporting year? Yes If yes, reasons and action plan: Situation in the country. Action plan: periodic re-assessment of the situation in the country Any recurring problem? Yes If yes, description of the problem/s: Situation in the country prevents any on-site operation involving purchase of equipment overseas. Any impact on project completion date: Yes If yes, implications: Given the situation in the country, determining completion dates is fairly difficult Any action required by Executive Committee? No | - In the context of the subcontract for the redesign and prototyping of the company's main products, the subcontractor Second Progress Report was received and cleared by UNIDO. - For the time being, any activity involving the procurement and delivery of equipment in the company's facilities is not possible due to the situation in the country. Milestones achieved: Milestone 1: Yes - Prototype units working on R410A selected Activities planned but not implemented, reasons and strategy: For the time being, any activity involving the procurement and delivery of equipment in the company's facilities is not possible due to the situation in the country. Actions towards next goals: Meeting with company representatives to explore possible activities to be undertaken in 2015 Was there any delay during the reporting year? Yes If yes, reasons and action plan: Situation in the country. Action plan: periodic re-assessment of the situation in the country Any recurring problem? Yes If yes, description of the problem/s: Situation in the country prevents any on-site operation involving purchase of equipment overseas. Any impact on project completion date: Yes If yes, implications: Given the situation in the country, determining completion dates is fairly difficult Any action required by Executive Committee? No |  |  | INV |  | Continued Monitoring
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration industry | Individual | ASP | SYR | SEV | 09 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-11-01 | 1993-09-01 |  | 1994-12-01 | 1996-05-01 | 35000 | -5 | 34995 | 34995 | 100% | 0 | 0 |  | 4550 | -8 | 4542 | 0 | 0 | FIN
FIN | UNIDO | Support to strengthening the General Commission for Environmental Affairs to implement Montreal Protocol related activities | Individual | ASP | SYR | SEV | 10 | INS | 03 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 2002-11-01 | 2003-06-01 | 235180 | -15273 | 219907 | 219907.1 | 100% | -0.1 | 0 |  | 30573 | -2030 | 28543 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Renewal of institutional strengthening (Phase II) | Individual | ASP | SYR | SEV | 33 | INS | 75 | N | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-12-01 | 2003-04-01 |  | 2006-12-01 | 2009-09-01 | 195000 | -3117 | 191883 | 191882.56 | 100% | 0.44 | 0 |  | 25350 | -405 | 24945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening: phase III | Individual | ASP | SYR | SEV | 45 | INS | 91 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2007-04-01 |  | 2009-12-01 | 2013-12-01 | 203823 | -1926 | 201897 | 201896.98 | 100% | 0.02 | 0 |  | 15287 | -145 | 15142 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening (phase IV) | Individual | ASP | SYR | SEV | 58 | INS | 101 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-12-01 | 2016-06-01 |  |  | 152867.25 | 0 | 152867.25 | 77227.21 | 50.52% | 75640.04 | 4772.2 | 10000 | 11465 | 0 | 5792 | 5673 | 357.915 | - Work plan for the year 2014 was agreed. - Awareness activities. - Follow-up and release of NCs contracts assisting NOU was jeopardized by the security situation. Milestones achieved: Milestone 1: NCs contracts - No Milestone 2: Office equipment delivery - Yes Milestone 3: Awareness activities - No (limited progress) Activities planned but not implemented, reasons and strategy: Implementation of specific activities could not be achieved due to special security situation in the country. Actions towards next goals: UNIDO is liaising with NOU to implement activities of the project taking into consideration the security situation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Due to security situation fields visits are limited, NCs contract release process is limited. Any recurring problem? Yes If yes, description of the problem/s: Security situation Any impact on project completion date: Yes If yes, implications: Completion date to be rescheduled pending on the improvement of the security situation. Any action required by Executive Committee? No | - Work plan for the year 2015 was agreed. - Publications for awareness and data collection related activities are scheduled to be achieved through local bidding process. - Implementation is limited due to the security situation in the country. Milestones achieved: Milestone 1: NOU staff continuity maintained - Yes Milestone 2: Work plan for 2015 agreed - Yes Milestone 3: Office equipment and awareness activities delivered - No Milestone 4: NC contracts release - No Activities planned but not implemented, reasons and strategy: NCs contracts release were not cleared due to security situation. Actions towards next goals: UNIDO will continue to liaise with NOU to progress the implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Security situation in the country Any recurring problem? Yes If yes, description of the problem/s: Security situation in the country. Any impact on project completion date: Yes If yes, implications: Project completion date to be rescheduled pending on the improvement of the security situation. Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening (phase V: 1/2015- 12/2016) | Individual | ASP | SYR | SEV | 73 | INS | 104 | N | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2017-12-31 |  |  | 203823 | 0 | 203823 | 0 | 0% | 203823 | 0 | 1000 | 14268 | 0 | 0 | 14268 | 0 | - Project approved at the 73rd Meeting of the ExCom in November 2014. | - Work plan for the implementation of the project activities is agreed with counterpart. - NOU team is maintained ensuring continuity of the process. - Disbursement will progress pending on the development of the security situation of the country. Milestones achieved: Milestone 1: NOU team nominated - Yes Milestone 2: NCs contracts - No Milestone 3: Awareness activities - No Activities planned but not implemented, reasons and strategy: NCs contracts releases and organization of awareness activities are jeopardized by the security situation in the country. Actions towards next goals: UNIDO will liaise with NOU Syria to progress the implementation, pending on the development of the security situation in the country. Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Security situation Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | THA | FUM | 22 | PRP | 65 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-12-01 |  | 1998-05-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide ingrain storage (rice, maize, tapioca, feed grains and pulses) | Individual | ASP | THA | FUM | 25 | DEM | 97 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-04-01 | 2000-08-01 |  | 2003-07-01 | 2004-12-01 | 280500 | -21687 | 258813 | 258813.44 | 100% | -0.44 | 0 |  | 36465 | -2873 | 33592 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Preparation of a project for the elimination of methyl bromide in the post harvest sector | Individual | EUR | TKM | FUM | 53 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 |  | 2009-12-01 | 2011-12-01 | 20000 | -609 | 19391 | 19391.34 | 100% | -0.34 | 0 |  | 1500 | -46 | 1454 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Technical assistance for the elimination of methyl bromide in post harvest sector | Individual | EUR | TKM | FUM | 59 | INV | 06 | A | I | MBR | 2.8 | 2.8 |  |  | 2009-11-01 | 2010-07-01 | 2013-12-01 |  | 2013-12-01 |  | 179586 | 0 | 179586 | 174546.98 | 97.19% | 5039.02 | 4882.36 | 4000 | 16163 | 0 | 15709 | 454 | 439 | N.a. |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TKM | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-02-01 | 85000 | -909 | 84091 | 84090.6 | 100% | 0.4 | 0 |  | 6375 | -68 | 6307 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | TKM | PHA | 62 | INV | 08 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 309050 | 0 | 309050 | 256260.93 | 82.92% | 52789.07 | 27244.74 | 50000 | 23179 | 0 | 19220 | 3959 | 2043 | - The work plan must be revised due to reduction of the HPMP funding. The main change is the elimination of investment activities from the HPMP. No additional R+R equipment can be provided due to the funds reduction. - Purchase of identifiers for customs officers initiated. Bids prepared and requested. - New programme under finalization. - Intermediate goals achieved. Milestones achieved: 1. Terms of reference (for equipment) completed - Yes 2.Bidding completed, supplier selected - Yes Activities planned but not implemented, reasons and strategy: Delivery and training for the equipment. Actions towards next goals: Preparation of public awareness activities (Ozone Day). Planning of new activities for 2016. Was there any delay during the reporting year? Yes; Delays due to reduction of funds by ExCom. Any recurring problem? No Any impact on project completion date: Yes, tranche is expected to be completed in December 2015. Any action required by Executive Committee? No | - Activities under first tranche are being finalized and progress will continue under second tranche. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | TKM | PHA | 71 | INV | 09 | A | I | HCFC | 0.7 | 0 |  |  | 2013-12-01 | 2014-07-01 | 2016-12-31 | 2017-03-01 |  |  | 94500 | 0 | 94500 | 8024.09 | 8.491% | 86475.91 | 0 | 20000 | 7088 | 0 | 602 | 6486 | 0 | - The work plan must be revised due to reduction of the HPMP funding. The main change is the elimination of investment activities from the HPMP. No additional R+R equipment can be provided due to the funds reduction. - Purchase of identifiers for customs officers initiated. Bids prepared and requested. - New programme under finalization. - Intermediate goals achieved. Milestones achieved: 1. Terms of reference (for equipment) completed - Yes 2.Bidding completed, supplier selected - Yes Activities planned but not implemented, reasons and strategy: Delivery and training for the equipment. Actions towards next goals: Preparation of public awareness activities (Ozone Day). Planning of new activities for 2016. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Equipment delivered - No Milestone 2: Training conducted - No Milestone 3: Tranche request prepared - Yes Activities planned but not implemented, reasons and strategy: The equipment will arrive September. Training will be organized after the summer season. Actions towards next goals: n/a Was there any delay during the reporting year? No Any recurring problem? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | TKM | PHA | 71 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-05-31 | 2015-12-01 |  |  | 30000 | 0 | 30000 | 22186.52 | 73.96% | 7813.48 | 0 | 7813 | 2700 | 0 | 1997 | 703 | 0 | - Preparation of ToR for Verification. - International tender or recruitment. - Planned completion date was changed as per Secretariat’s communication dated 11 February 2015. Milestones achieved: Milestone 1: ToR prepared - Yes Milestone 2: Consultant recruited - Yes Activities planned but not implemented, reasons and strategy: n/a Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Verification completed. Milestones achieved: Milestone 1: Draft report submitted to IA/NOU - Yes Milestone 2: Verification report ready for submission to MLFS - Yes |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-11-01 | 2009-03-31 |  | 2010-12-01 | 2012-02-01 | 15000 | -62 | 14938 | 14938.25 | 100% | -0.25 | 0 |  | 1125 | -5 | 1120 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2016-12-01 |  |  | 200000 | 0 | 200000 | 138624.54 | 69.31% | 61375.46 | 5039.44 | 14000 | 15000 | 0 | 10397 | 4603 | 378 | A 4-day training session on the safe installation, operation and maintenance of hydrocarbon ACs, using the demo units was organized. Milestones achieved: Milestone 1: Yes - Training on installation and maintenance of Hydrocarbon ACs was held in Oct 2014 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - The last activity involves identifying beneficiaries for an incentive programme to convert to low GWP alternatives. - Funds from the 2nd tranche would have to be combined with residual funds from 1st tranche for actual conversion, depending on results of the survey and assessment. Milestones achieved: Milestone 1: Yes - Survey of industrial and large commercial facilities held June-July 2015 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project should be left open to enable funds to be combined with 2nd tranche Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Phasing out CFCs at Jasminal Laboratories | Individual | AFR | TUN | ARS | 19 | INV | 14 | A | I | CFC | 86 | 86 |  |  | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1998-12-01 | 2001-03-01 | 210000 | -77 | 209923 | 209923 | 100% | 0 | 0 |  | 27300 | -53 | 27247 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Satem Parfums et Produits Cosmetiques | Individual | AFR | TUN | ARS | 19 | INV | 15 | A | I | CFC | 29 | 29 |  |  | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 119500 | 0 | 119500 | 119500 | 100% | 0 | 0 |  | 15535 | 0 | 15535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at CODIFA | Individual | AFR | TUN | ARS | 22 | INV | 19 | A | I | CFC | 60.25 | 60.25 |  |  | 1997-05-01 | 1997-09-01 | 1998-09-01 |  | 1999-12-01 | 2000-11-01 | 179986 | 0 | 179986 | 179986 | 100% | 0 | 0 |  | 23398 | 0 | 23398 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Alki S.A. | Individual | AFR | TUN | ARS | 22 | INV | 20 | A | I |  | 0 | 0 |  |  | 1997-05-01 |  | 1998-09-01 |  |  | 1999-12-01 | 74565 | -74565 | 0 | 0 |  | 0 | 0 |  | 9693 | -9693 | 0 | 0 | 0 | CLO |  |  | 1999-03-01
FIN | UNIDO | Phasing out CFCs at Sogepar | Individual | AFR | TUN | ARS | 22 | INV | 21 | A | I | CFC | 18.15 | 18.15 |  |  | 1997-05-01 | 1998-11-01 | 1998-09-01 |  | 2000-01-01 | 2001-07-01 | 68833 | 0 | 68833 | 68832.64 | 100% | 0.36 | 0 |  | 8948 | -4 | 8944 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parhycos, Sfax, Tunisia | Individual | AFR | TUN | ARS | 23 | INV | 25 | A | I | CFC | 10 | 10 |  |  | 1997-11-01 | 1999-04-01 | 1999-02-01 |  | 1999-12-01 | 2001-03-01 | 41195 | 0 | 41195 | 41195 | 100% | 0 | 0 |  | 5355 | -2 | 5353 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Laboratoires Parcos | Individual | AFR | TUN | ARS | 28 | INV | 35 | A | I | CFC | 29.8 | 29.8 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2004-03-01 | 2004-09-01 | 76127 | -469 | 75658 | 75658.39 | 100% | -0.39 | 0 |  | 9897 | -77 | 9820 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Meublatex | Individual | AFR | TUN | FOA | 19 | INV | 16 | A | I | CFC | 28 | 28 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-10-01 | 2000-07-01 | 105000 | -681 | 104319 | 104319 | 100% | 0 | 0 |  | 13650 | -110 | 13540 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sud Inter Mousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 23 | A | I | CFC | 102 | 102 |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 2001-12-01 | 2003-08-01 | 546920 | -271 | 546649 | 546649.3 | 100% | -0.3 | 0 |  | 71100 | -148 | 70952 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sotrapoc flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 24 | A | I | CFC | 20 | 20 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 90037 | -1704 | 88333 | 88332.94 | 100% | 0.06 | 0 |  | 11705 | -240 | 11465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Polymousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 26 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 104343 | -88 | 104255 | 104255.05 | 100% | -0.05 | 0 |  | 13565 | -33 | 13532 | 0 | 0 | FIN
COM | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | TUN | FOA | 58 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-10-01 | 2010-07-31 |  | 2014-05-01 |  | 65000 | 0 | 65000 | 61289.19 | 94.29% | 3710.81 | 2240.98 | 1260 | 4875 | 0 | 4597 | 278 | 168.0735 | - HPMP approved at the 72nd Meeting of the ExCom. Milestones achieved: Milestone 1: Yes - HPMP approved at the 72nd Meeting of the ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  |  | NON-INV
FIN | UNIDO | Alternatives to the use of methyl bromide in horticulture at Société Méditeranéene Fruitière | Individual | AFR | TUN | FUM | 24 | DEM | 29 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 2001-02-01 | 2003-05-01 | 301730 | -11452 | 290278 | 290277.8 | 100% | 0.2 | 0 |  | 39225 | -1549 | 37676 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants (dates) sector | Individual | AFR | TUN | FUM | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -12728 | 12272 | 12271.57 | 100% | 0.43 | 0 |  | 3250 | -1655 | 1595 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Project preparation in the fumigants sector (high moisture dates) | Individual | AFR | TUN | FUM | 71 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 |  | 2014-12-31 |  | 35000 | 0 | 35000 | 19057.48 | 54.45% | 15942.52 | 15942.93 | 15942 | 2450 | 0 | 1334 | 1116 | 1116.0051 | - UNIDO, NOU and representatives from date packing industry met and agreed on a work plan for the project preparation. - Project submitted and approved at the 73rd Meeting of the ExCom in November 2014. |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for the final phase-out of methyl bromide in the palm dates sector | Individual | AFR | TUN | FUM | 73 | TAS | 63 | A | I | MBR | 4.4 | 0 |  |  | 2014-11-01 |  | 2015-11-30 | 2016-11-01 |  |  | 267657 | 0 | 267657 | 0 | 0% | 267657 | 0 | 100000 | 18736 | 0 | 0 | 18736 | 0 | Approved at the 73rd Meeting of the ExCom in November 2014 on the understanding that no additional funding will be provided for Tunisia for the phase-out of controlled uses of methyl bromide (MB) in the country; and the Government of Tunisia is committed to meeting the complete phase-out of MB by 1 January 2015 and banning imports for controlled MB uses as of that date. | - NOU and UNIDO agreed on implementation modalities. - UNIDO and NOU finalized technical specifications for the purchase of necessary equipment and biddings are ongoing. Milestones achieved: Milestone 1: Legal agreements - Yes Milestone 2: Initial stages of project implementation began - Yes Milestone 3: Intermediate goals achieved - Yes Milestone 4: Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: All on track Actions towards next goals: Finalize bidding and deliver the equipment in the fall. Make sure all fumigation chambers are set-up to receive the new technology. Ensure proper training to technicians. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | TUN | PHA | 55 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2014-05-01 |  | 150000 | 0 | 150000 | 144535.05 | 96.36% | 5464.95 | 4072.29 | 2200 | 11250 | 0 | 10840 | 410 | 305 | - HPMP approved at the 72nd Meeting of the ExCom. Milestones achieved: Milestone 1: Yes - HPMP approved at the 72nd Meeting of the ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  |  | NON-INV
COM | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | AFR | TUN | PHA | 68 | INV | 54 | A | I | CFC | 172.5 | 172.5 |  |  | 2012-12-01 | 2014-01-01 | 2013-12-31 |  | 2014-03-01 |  | 705518 | -250000 | 455518 | 76137.6 | 16.71% | 379380.4 | 328047.28 | 30000 | 52914 | -18750 | 5710 | 28454 | 24603.546 | Project was completed in Mar 2014 as per ExCom decision. 'Refund was reported to 73rd ExCom, Nov 2014. COM. | Project was operationally completed on 31 March 2014 as per ExCom decision 71/11, and UNIDO did not incur any new commitments for the project after this date. The obligated amounts correspond to a contract for the procurement of equipment which was signed between UNIDO and the supplier before the completion date. However, installation and commissioning of the equipment has been postponed a number of times upon request from the country; dates for the related mission have been already confirmed and agreed upon between the NOU, the supplier and UNIDO (27 April – 9 May). Upon successful installation and commissioning of the equipment, the last payment of the related contract will be released, after which UNIDO will be in a position to financially closed the project; therefore, financial completion will take place before ExCom 75. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 58 | A | I | HCFC | 1.3 | 0 |  |  | 2014-05-01 |  | 2017-05-31 | 2017-05-31 |  |  | 231920 | 0 | 231920 | 0 | 0% | 231920 | 0 | 20000 | 16234 | 0 | 0 | 16234 | 0 | - Approved at the at the 72nd Meeting of the ExCom in May 2014. - This HPMP component supports conversion at two companies: (-) SOFAP: manufacturer of disposable medical devices using HCFC-141b as silicone oil thinner; demonstration project to test low-GWP alternatives; research stage has led to two substances ready for testing, one is HFO-based and the second one is HFE-based; other alternatives explored have proved not to be ready for testing. (-) SNCFT: railway company using HCFC-141b for flushing; alternative identified, but need to identify adequate equipment for its implementation. Milestones achieved: Milestone 1: Yes - two alternatives identified for conversion at SOFAP. Activities planned but not implemented, reasons and strategy: Testing of alternatives at SOFAP did not start in 2014 due to the complexity of the market research and the need for time for contacts with various agent suppliers Actions towards next goals: (-) SOFAP: laboratory testing, selection of alternative, modification of the process based on the physic-chemical properties of the selected alternative (-) SNCFT: definition of technical specifications of flushing units, purchase of units. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | (-) SOFAP: laboratory testing stage started, and results are available for one of the two tested alternatives; a manufacturer informed UNIDO that a third substance (HFO-based solution) is available for testing. (-) SNCFT: site visit with experts to define technical specifications of flushing units required to use the selected alternative. Milestones achieved: Milestone 1: Yes - SOFAP, laboratory testing yielded results on one alternative Milestone 2: Yes - SNCFT, technical specifications of flushing units completed Actions towards next goals: (-) SOFAP: completion of laboratory testing, selection of alternative, modification of the process based on the physic-chemical properties of the selected alternative (-) SNCFT: purchase of flushing units. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | INV | 59 | A | I | HCFC | 1.4 | 0 |  |  | 2014-05-01 |  | 2017-05-31 | 2017-05-31 |  |  | 175000 | 0 | 175000 | 0 | 0% | 175000 | 0 | 80000 | 12250 | 0 | 0 | 12250 | 0 | - Approved at the at the 72nd Meeting of the ExCom in May 2014. - Discussion on technical activities under this HPMP component took place among NOU, UNIDO and relevant stakeholders. Actions towards next goals: Implementation of activities planned for 2015 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Under this project component, a review of the curricula of training in vocational schools has been made, as well as a needs assessment related to equipment and tools for these schools to support HPMP implementation. Milestones achieved: Milestone 1: Yes - updated curricula of training in vocational schools Milestone 2: Yes - needs assessment related to equipment and tools for these schools to support HPMP implementation undertaken Milestone 3: Yes - initial stage of implementation of a certification programmed for servicing technicians and workshops Actions towards next goals: Continue implementation of activities initiated in the first half of the year. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning manufacturing sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 61 | A | I | HCFC | 0.5 | 0 |  |  | 2014-05-01 | 2014-09-01 | 2017-05-31 | 2017-05-31 |  |  | 105965 | 0 | 105965 | 1996.5 | 1.884% | 103968.5 | 1395.97 | 36000 | 7418 | 0 | 140 | 7278 | 98 | - Approved at the at the 72nd Meeting of the ExCom in May 2014. - Discussion on technical activities under this HPMP component took place among NOU, UNIDO and relevant stakeholders. Actions towards next goals: Implementation of technical assistance activities planned for 2015 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Technical assistance activities ongoing for the participating companies Milestones achieved: Participation of representatives of participating companies in training sessions on low-GWP alternatives. Actions towards next goals: Implementation of technical assistance activities planned for the second half of 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Umbrella project to phase out ODS at the six small refrigerator manufacturers | Individual | AFR | TUN | REF | 19 | INV | 17 | A | I | CFC | 78.5 | 78.5 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 1997-05-01 | 2001-10-01 | 764557 | -124194 | 640363 | 640362.85 | 100% | 0.15 | 0 |  | 99392 | -16277 | 83115 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project to phase out ODS at 7 manufacturers of commercial and domestic refrigerators (Chahed Refrigeration, Sogima, Sotiem, Rei, Frigo BAF, Societe Moderne Refrigeration, Frigo Technique) | Individual | AFR | TUN | REF | 23 | INV | 27 | A | I | CFC | 29 | 29 |  |  | 1997-11-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2001-03-01 | 374111 | -1034 | 373077 | 373077 | 100% | 0 | 0 |  | 48634 | -211 | 48423 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | AFR | TUN | REF | 24 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 1998-12-01 | 2000-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the aerosol, foam, domestic refrigeration and solvent sectors | Individual | AFR | TUN | SEV | 17 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1998-03-01 | 1999-08-01 | 30000 | -1697 | 28303 | 28303 | 100% | 0 | 0 |  | 3900 | -226 | 3674 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the aerosol, foam, solvents and methyl bromide sectors | Individual | AFR | TUN | SEV | 21 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 1999-05-01 | 2000-12-01 | 27150 | -1020 | 26130 | 26130 | 100% | 0 | 0 |  | 3530 | -138 | 3392 | 0 | 0 | FIN |  |  | 1999-12-01
ONG | UNIDO | Extension of institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | AFR | TUN | SEV | 66 | INS | 53 | N | I |  | 0 | 0 |  |  | 2012-04-01 | 2014-07-01 | 2014-06-30 | 2015-09-01 |  |  | 247270 | 0 | 247270 | 171554.11 | 69.38% | 75715.89 | 75162.19 | 40000 | 18545 | 0 | 12867 | 5678 | 5637.1642 | - Contract with counterpart was agreed and signed upon UNIDO field mission in March 2014. - NOU staff was re-assigned further to administrative restructuring. - Project activities were implemented according to the agreed work plan. Milestones achieved: Milestone 1: NOU staff nomination - Yes Milestone 2: Awareness activities - Yes Milestone 3: Office equipment delivery - Yes Actions towards next goals: Follow-up on progress reports and project completion. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Operational completion will be achieved in September 2015 and financial completion during the first quarter 2016. Milestones achieved: Milestone 1: Awareness activities committed - Yes Milestone 2: Terminal report and Action Plan for IS extension - Yes Actions towards next goals: Submission of IS extension Was there any delay during the reporting year? yes Any recurring problem? No Any impact on project completion date: yes Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | TUN | SOL | 45 | TAS | 45 | A | I | CTC | 0.9 | 0.9 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 50000 | -18930 | 31070 | 31070.38 | 100% | -0.38 | 0 |  | 4500 | -1704 | 2796 | 0 | 0 | FIN |  |  | 2007-06-01 | INV
FIN | UNIDO | Preparation of ODS disposal pilot project | Individual | EUR | TUR | DES | 57 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2012-05-01 | 2013-04-01 | 60000 | -1752 | 58248 | 58248.21 | 100% | -0.21 | 0 |  | 4500 | -131 | 4369 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | EUR | TUR | DES | 66 | DEM | 99 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2012-06-01 | 2014-04-30 | 2016-07-01 |  |  | 1076250 | 0 | 1076250 | 535620.1 | 49.77% | 540629.9 | 464113.81 | 1 | 80719 | 0 | 40172 | 40547 | 34808.5358 | - Difficulties in collecting planned amount of ODS waste has led to a re-design of the disposal strategy. Activities planned but not implemented, reasons and strategy: Waste disposal was not possible due to the availability of a significant lower amount of ODS waste. Actions towards next goals: Definition of a new disposal strategy. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Availability of a significant lower amount of ODS waste requires re-design of the implementation plan. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Problems explained above requires more time for implementation of the new strategy. Any action required by Executive Committee? No | - UNIDO terminated the contract with the previous Contractor in order to be able to implement the new disposal strategy. Actions towards next goals: Disposal of the available waste and completion of the project. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Problems explained above requires more time for implementation of the new strategy. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of investment projects in ODS phase out in the foam sector | Individual | EUR | TUR | FOA | 15 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-04-01 | 2001-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -6 | 6494 | 0 | 0 | FIN |  |  | 1999-02-01
CLO | UNIDO | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Barlan Metal | Individual | EUR | TUR | FOA | 18 | INV | 18 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  |  | 1997-09-01 | 804050 | -802115 | 1935 | 1935 | 100% | 0 | 0 |  | 104527 | -104276 | 251 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 at Urosan Kimiya Sanayii A.S. | Individual | EUR | TUR | FOA | 20 | INV | 22 | A | I | CFC | 135 | 135 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1999-12-01 | 2002-04-01 | 643500 | -10955 | 632545 | 632544.84 | 100% | 0.16 | 0 |  | 83655 | -1555 | 82100 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | UNIDO | Phasing out CFC-11 at Isbir Termoset Plastic San. A.S., Ankara, Turkey | Individual | EUR | TUR | FOA | 23 | INV | 30 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1999-03-01 | 1998-12-01 |  | 2001-04-01 | 2002-09-01 | 501350 | 0 | 501350 | 501350.19 | 100% | -0.19 | 0 |  | 65176 | -45 | 65131 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Go-Ya Sungar Ltd. Sti. | Individual | EUR | TUR | FOA | 23 | INV | 31 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-11-01 | 1998-12-01 |  |  | 2002-04-01 | 533400 | -313280 | 220120 | 220120.42 | 100% | -0.42 | 0 |  | 69342 | -40772 | 28570 | 0 | 0 | CLO
FIN | UNIDO | Preparation of investment project in the rigid foam sub sector | Individual | EUR | TUR | FOA | 24 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-11-01 | 2001-05-01 | 15000 | -9583 | 5417 | 5417.06 | 100% | -0.06 | 0 |  | 1950 | -1247 | 703 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of investment projects in the foam sector (polyurethane) at Sungersan AS and Serra Sunger | Individual | EUR | TUR | FOA | 24 | PRP | 37 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1999-12-01 | 2000-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of CO2 blowing technology at Serra Sunger | Individual | EUR | TUR | FOA | 25 | INV | 47 | A | I | CFC | 86 | 86 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-08-01 | 454358 | 0 | 454358 | 454358.36 | 100% | -0.36 | 0 |  | 59067 | -16 | 59051 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in the manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Sungersan | Individual | EUR | TUR | FOA | 27 | INV | 52 | A | I | CFC | 78 | 78 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 467397 | 0 | 467397 | 467397 | 100% | 0 | 0 |  | 60762 | 0 | 60762 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU molded foam through the use of CO2 blosing technology at Sungersan, Bursa | Individual | EUR | TUR | FOA | 27 | INV | 53 | A | I | CFC | 30 | 30 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2002-05-01 | 327374 | 0 | 327374 | 327374.39 | 100% | -0.39 | 0 |  | 42559 | -9 | 42550 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane panels for thermal insulation for cold rooms and cold storages at Izotek | Individual | EUR | TUR | FOA | 28 | INV | 65 | A | I | CFC | 74.8 | 74.8 |  |  | 1999-07-01 | 2000-08-01 | 2001-08-01 |  | 2001-08-01 | 2002-09-01 | 430721 | -4807 | 425914 | 425914.32 | 100% | -0.32 | 0 |  | 55994 | -713 | 55281 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the flexible foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 15000 | -10124 | 4876 | 4876.38 | 100% | -0.38 | 0 |  | 1950 | -1317 | 633 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-09-01 | 2001-04-01 |  | 2002-03-01 | 2002-05-01 | 15000 | -941 | 14059 | 14058.97 | 100% | 0.03 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Espol Sunger Company | Individual | EUR | TUR | FOA | 31 | INV | 68 | A | I | CFC | 95 | 95 |  |  | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2004-02-01 | 2004-12-01 | 552297 | 0 | 552297 | 552297.4 | 100% | -0.4 | 0 |  | 70753 | -31 | 70722 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 31 | PRP | 67 | A | I |  | 0 | 0 |  |  | 2000-07-01 |  | 2001-07-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology at Purtiz Co. in the manufacture of rigid polyurethane foam for insulating purposes | Individual | EUR | TUR | FOA | 32 | INV | 72 | A | I | CFC | 52.8 | 52.8 |  |  | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-07-01 | 2004-09-01 | 301094 | -139 | 300955 | 300954.69 | 100% | 0.31 | 0 |  | 39142 | -80 | 39062 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | EUR | TUR | FOA | 58 | PRP | 94 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-04-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 150000 | -23470 | 126530 | 126530.07 | 100% | -0.07 | 0 |  | 11250 | -1760 | 9490 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of PU insulated sandwich panels and phaseout HCFC-142b and HCFC-22 in the manufacture of extruded polystyrene boardstock | Multi-Year | EUR | TUR | FOA | 62 | INV | 97 | A | I | HCFC | 213.2 | 213.2 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2015-12-01 |  |  | 7713490 | 0 | 7713490 | 7021474.75 | 91.03% | 692015.25 | 240429.6 | 200000 | 578512 | 0 | 526611 | 51901 | 18032 | - Conversion of all foam enterprises was completed in 2014. Milestones achieved: Milestone 1: IOC calculation completed - Yes Milestone 2: IOC disbursement completed - No Activities planned but not implemented, reasons and strategy: IOC contract release for Aluform is pending on the commissioning completion. The delay in commissioning was caused by technical difficulties with raw materials supply system, that required contract amendment and delivery of specific additional spare-parts. The activity will be completed in 2015. Actions towards next goals: Contract amendment to be released in 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: As above Any recurring problem? No Any impact on project completion date: Yes If yes, implications: IOC disbursement will be completed in 2015, thus financial completion of the project will be achieved in 2015. Any action required by Executive Committee? No | - Technical specification development for contract amendment for Aluform conversion has been agreed with factory management and the equipment supplier. - IOC disbursement to be disbursed second half of 2015. - Project to be completed by the end of 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Due to delays of previous years, the completion date had been modified to December 2015. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (flowers, tobacco) | Individual | EUR | TUR | FUM | 24 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticulture (tomatoes and cucumbers) and ornamental (carnations) crops | Individual | EUR | TUR | FUM | 25 | DEM | 46 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-02-01 | 2000-08-01 |  | 2001-05-01 | 2002-12-01 | 314600 | -9324 | 305276 | 305276.17 | 100% | -0.17 | 0 |  | 40898 | -1275 | 39623 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector (horticulture) | Individual | EUR | TUR | FUM | 30 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -787 | 29213 | 29213.03 | 100% | -0.03 | 0 |  | 3900 | -108 | 3792 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide in protected tomato, cucumber and carnation crops (first tranche) | Multi-Year | EUR | TUR | FUM | 35 | INV | 74 | A | I | MBR | 29.2 | 29.2 |  |  | 2001-12-01 | 2002-08-01 | 2002-12-01 |  | 2003-12-01 | 2006-11-01 | 1000000 | 0 | 1000000 | 999999.99 | 100% | 0.01 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (second tranche) | Multi-Year | EUR | TUR | FUM | 41 | INV | 82 | A | I | MBR | 58 | 58 |  |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 | 2011-04-01 | 1000000 | -2624 | 997376 | 997375.92 | 100% | 0.08 | 0 |  | 75000 | -197 | 74803 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (third and fourth tranches) | Multi-Year | EUR | TUR | FUM | 47 | INV | 88 | A | I | MBR | 205 | 205 |  |  | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2009-11-01 | 2012-09-01 | 1408844 | -76709 | 1332135 | 1332135.31 | 100% | -0.31 | 0 |  | 105663 | -5753 | 99910 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TUR | PHA | 55 | PRP | 91 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2012-12-01 | 2014-04-01 | 195000 | -6430 | 188570 | 188570.43 | 100% | -0.43 | 0 |  | 14625 | -482 | 14143 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) | Multi-Year | EUR | TUR | PHA | 68 | INV | 102 | A | I |  | 16.3 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 | 2015-12-01 |  |  | 658470 | 0 | 658470 | 169154.56 | 25.69% | 489315.44 | 10285.62 | 100000 | 46093 | 0 | 11841 | 34252 | 719.9934 | - Work plan for SH Companies conversion agreed in January 2014. - Technical specification for SH conversion (with private co-financing component) developed in 2014. - Training on alternatives for SMEs (downstream users of the SH companies) has been implemented. Milestones achieved: Milestone 1: SH implementation concept - Yes Milestone 2: Conference on alternatives for downstream users of SH companies - Yes Milestone 3: Technical specification for safety equipment at SH companies - Yes Actions towards next goals: Initiation of bidding for equipment purchase in 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Technical specifications for equipment delivery at system house companies completed for all enterprises. - Bidding has been initiated. - Delivery and commissioning of equipment at SHs companies is expected to be finalized by the end of 2015. Milestones achieved: Milestone 1: Bidding for equipment purchase initiated - Yes Milestone 2: Suppliers selection - No Milestone 3: Equipment delivery - No Milestone 4: Conversion of SH to methyl formate and hydrocarbons achieved with private investment component - Yes Milestone 5: Safety measures for manufacturing of flammable alternatives achieved at all manufacturing sites - No Actions towards next goals: Follow-up the bidding process for suppliers selection and completion of equipment delivery process expected during the second half of 2015. Was there any delay during the reporting year? No Any recurring problem? Yes If yes, description of the problem/s: Tranche 1 of HPMP allocated 50% of the funding required for the full conversion at the SH manufacturers. Completion of the conversion is pending on the approval of the tranche 2. Any impact on project completion date: No If yes, implications: (narrative): NA Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 100 | A | I | HCFC | 0 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 | 2015-12-01 |  |  | 149280 | 0 | 149280 | 117138.03 | 78.47% | 32141.97 | 31047.89 | 32142 | 10450 | 0 | 8200 | 2250 | 2173.3523 | - Update of the regulations for the certification system was progressed. - The new certification scheme, addressing technicians and refrigeration workshops providing service/maintenance in refrigeration and AC sectors, is being under approval process at relevant authorities. - The new system aligns Turkey's legislation with F-Gas Regulation of the EU. - Train the trainer component for servicing sector was organized in 2014, jointly with study tour in UK Training and certification center for technicians, to prepare the implementation of the new certification scheme (mandatory as of 1st January 2015). Milestones achieved: Milestone 1: Policy and regulation up-date on HCFCs - Yes Milestone 2: Train the trainer component - Yes Milestone 3: Training on alternatives in refrigeration sector - Yes Actions towards next goals: Preparation of the training and certification programme for technicians subject to tranche 2 approval. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Follow-up on the approval of the new legislation for the certification scheme. - Continuing awareness component on recovery/recycling scheme. - Initiation of inventory on recovered/recycled quantities. - Elaboration of Progress Report and Consumption Verification Report in view of tranche 2 submission to the 75th Meeting of the ExCom. Milestones achieved: Milestone 1: Workshops on alternatives for RAC in refrigeration sector - Yes Milestone 2: Contracting consultancy for elaboration of verification report - Yes Milestone 3: Submission of tranche II request for ExCom approval - No Activities planned but not implemented, reasons and strategy: Submission of tranche 2 request was re-scheduled for the 75th Meeting of the ExCom since data for the year 2014 were not available first quarter of 2015. Actions towards next goals: Verification Report to be finalized by the end of August 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Verification Report will be finalized in August 2015, thus tranche 2 submission is rescheduled for the 75th ExCom Meeting. Any recurring problem? No Any impact on project completion date: Yes Planned completion date is December 2015 since BP2014. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | EUR | TUR | REF | 58 | PRP | 95 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2012-12-01 | 2014-04-01 | 150000 | -1380 | 148620 | 148619.75 | 100% | 0.25 | 0 |  | 11250 | -104 | 11146 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase IV) | Individual | EUR | TUR | SEV | 58 | INS | 93 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 | 2014-08-01 | 195000 | -7955 | 187045 | 187044.59 | 100% | 0.41 | 0 |  | 14625 | -597 | 14028 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase V) | Individual | EUR | TUR | SEV | 64 | INS | 98 | N | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2013-06-30 |  | 2014-03-01 |  | 260000 | 0 | 260000 | 232126.59 | 89.28% | 27873.41 | 18370.73 | 25263 | 19500 | 0 | 17409 | 2091 | 1378 | - Project activities were operationally completed in March 2014. - Financial completion to be achieved in 2015 due to verification of the expenditures and obligations in the new UNIDO financial system (transition to new financial system occurring 2013 - 2014). Milestones achieved: Milestone 1: Project operationally completed - Yes Milestone 2: Terminal report and new IS extension submission - Yes Actions towards next goals: Preparation of new IS extension request proposal. Was there any delay during the reporting year? yes Any recurring problem?: No Any impact on project completion date: No impact on the operations, due to administrative expenditures verification financial completion will be achieve during 2015 year Any action required by Executive Committee? No | - Project was operationally completed in 2014. - Financial completion to be achieved in 2015. Milestones achieved: Milestone 1: Project operationally completed - Yes Milestone 2: IS extension submitted and approved by ExCom - Yes Was there any delay during the reporting year? Yes No delay in activities implementation, financial completion will be achieve during 2015 year due to administrative expenditures verification Any recurring problem? No Any impact on project completion date: Yes No impact on the operations, due to administrative expenditures verification financial completion will be achieve during 2015 year Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | EUR | TUR | SEV | 70 | INS | 103 | N | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-09-01 | 2015-06-30 | 2015-12-01 |  |  | 260000 | 0 | 260000 | 102038.87 | 39.25% | 157961.13 | 43529 | 132619 | 18200 | 0 | 7143 | 11057 | 3047.03 | - Extension of NCs contracts achieved during the first quarter 2014. - Monitoring of ODS consumption with a specific view to HPMP has been achieved. - Follow-up on legislation review process. - Public awareness activities. Milestones achieved: Milestone 1: NC contracts release - Yes Milestone 2: Awareness activities organized - Yes Milestone 3: Site visits to the manufacturing companies to follow up conversion status - Yes Milestone 4: Office equipment delivered upon local bidding - Yes Actions towards next goals: Follow-up the work programme implementation and project completion in 2015. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project activities were implemented according to the work plan for 2015, and as per the project document. - NOU consultants contracts extended over 2015. - Public awareness activities for Ozone Day celebrations were committed. - Terminal Report and preparation of IS extension request were achieved. Milestones achieved: Milestone 1: NOU consultants contracts for 2015 released - Yes Milestone 2: Awareness activities committed - Yes Milestone 3: Terminal Report and submission of IS project extension to the 74th Meeting of the ExCom - Yes Actions towards next goals: Preparation of activities for the implementation of the new IS extension submitted to the 74th ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a sectoral phase-out project in the solvents sector | Individual | EUR | TUR | SOL | 36 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-07-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000.37 | 100% | -0.37 | 0 |  | 6500 | -2 | 6498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal umbrella project for phase-out of remaining ozone depleting solvents | Individual | EUR | TUR | SOL | 41 | INV | 83 | A | I | CTC | 24 | 24 |  |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2005-12-01 | 2007-03-01 | 531644 | -52625 | 479019 | 479018.64 | 100% | 0.36 | 0 |  | 39873 | -3947 | 35926 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | UGA | FUM | 30 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -560 | 29440 | 29440.08 | 100% | -0.08 | 0 |  | 3900 | -79 | 3821 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | UGA | FUM | 34 | INV | 08 | A | I | MBR | 30 | 30 |  |  | 2001-07-01 | 2002-10-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 228800 | -797 | 228003 | 228003.23 | 100% | -0.23 | 0 |  | 29744 | -104 | 29640 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2014-12-01 | 2016-12-31 | 2015-11-01 |  |  | 40000 | 0 | 40000 | 38113.9 | 95.28% | 1886.1 | 0 | 1886 | 3600 | 0 | 3430 | 170 | 0 | - UNIDO mission took place in June 2014. - Equipment was purchased to upgrade the main training centre in Kampala which is quite complete and to establish centres in six cities around the country. - TOR for the purchase of equipment to upgrade the main training centre in Kampala, which is quite complete, and to establish centres in six cities around the country were defined and cleared by the NOU. - Tools were purchased in autumn 2014. Milestones achieved: Milestone 1: Mission to define the project implementation. Yes Milestone 2: TOR prepare and review, equipment bidding, purchase. Yes Milestone 3: Equipment delivery and distributed. Yes Was there any delay during the reporting year?: No If yes, reasons and action plan: N/A Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment was purchased in autumn 2014 and due to some delays and problems with the transport, the equipment only reached Uganda in April 2015. - The distribution of the tools is being done locally. - Project activities are completed. Milestones achieved: Milestone 1: Mission to define the project implementation. Yes Milestone 2: TOR prepare and review, equipment bidding, purchase. Yes Milestone 3: Equipment delivery and distributed. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of investment project in aerosol sector at Mansoor Daya | Individual | AFR | URT | ARS | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 10000 | -1456 | 8544 | 8544 | 100% | 0 | 0 |  | 1300 | -191 | 1109 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Mansoor Daya Chemicals Ltd. | Individual | AFR | URT | ARS | 18 | INV | 05 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1997-12-01 | 1999-08-01 | 417163 | -2138 | 415025 | 415025 | 100% | 0 | 0 |  | 54231 | -363 | 53868 | 0 | 0 | FIN
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | INV | 30 | A | I | HCFC | 0.1 | 0.1 |  |  | 2012-07-01 | 2013-12-01 | 2015-07-31 |  | 2014-12-14 |  | 50000 | 0 | 50000 | 49935.69 | 99.87% | 64.31 | 0 | 1 | 4500 | 0 | 4494 | 6 | 0 | - Training on the proper use of delivered tools was held in March 2014. - UNIDO sent an expert to commission the reclaim unit available in the country. - Training of technicians took place as planned and the reclaiming unit were commissioned. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: TOR prepared and reviewed, bidding. Milestone 3: Purchase and delivery of tools for training centres. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | -Project is operationally completed. Milestones achieved: Milestone 1: Mission to define the project implementation. Yes Milestone 2: TOR prepare and review, equipment bidding, purchase. Yes Milestone 3: Equipment delivery and distributed. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production | Individual | AFR | URT | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-05-01 | 1996-05-01 | 10000 | -51 | 9949 | 9949 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at Tanzania Domestic Appliance Manufacturers Ltd. | Individual | AFR | URT | REF | 18 | INV | 06 | A | I | CFC | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1997-03-01 |  |  | 2002-12-01 | 592790 | -101002 | 491788 | 491788.45 | 100% | -0.45 | 0 |  | 77063 | -13232 | 63831 | 0 | 0 | CLO |  |  | 1999-12-01
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flowers) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1381 | 297819 | 297819.43 | 100% | -0.43 | 0 |  | 38896 | -241 | 38655 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the fumigants (methyl bromide) sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -935 | 24065 | 24065.16 | 100% | -0.16 | 0 |  | 3250 | -126 | 3124 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | I | MBR | 24 | 24 |  |  | 2001-07-01 | 2002-02-01 | 2012-12-01 |  | 2009-12-01 | 2010-12-01 | 469370 | -204 | 469166 | 469166.21 | 100% | -0.21 | 0 |  | 61018 | -26 | 60992 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | URU | REF | 60 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 | 2015-08-01 |  |  | 50000 | 0 | 50000 | 46628.54 | 93.26% | 3371.46 | 827.64 | 2911.78 | 3750 | 0 | 3497 | 253 | 62 | - Status was changed to "ONGOING". 'As reported to the 72nd and 73rd Meetings of the Executive Committee, and as per ExCom Dec. 65/47 (d), during the implementation of stage I of the HPMP, Uruguay could submit an investment project to phase out the use of HCFC-22 in the refrigeration manufacturing assembly of cold rooms, should appropriate alternatives be available. In line with this decision, funds were not returned until this project had been prepared. - UNIDO was not able to convince local beneficiaries on a suitable alternative. | - After seeking for alternatives, UNIDO was still not able to convince local beneficiaries on a suitable alternative.
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -927 | 29073 | 29073 | 100% | 0 | 0 |  | 3900 | -126 | 3774 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Decocar | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | I | CFC | 16.2 | 16.2 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | 0 | 126614 | 126614.49 | 100% | -0.49 | 0 |  | 16460 | -3 | 16457 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | I | CFC | 21.6 | 21.6 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -62 | 164530 | 164529.74 | 100% | 0.26 | 0 |  | 21397 | -42 | 21355 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | 0 | 104030 | 104030 | 100% | 0 | 0 |  | 13524 | -16 | 13508 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | I | CFC | 17.8 | 17.8 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17878 | 0 | 17878 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -56 | 9944 | 9944 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC -11 with HCFC-141b at TECNOFRIGO in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | I | CFC | 9 | 9 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | 0 | 71946 | 71946.49 | 100% | -0.49 | 0 |  | 9353 | -13 | 9340 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid PU panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | I | CFC | 13.9 | 13.9 |  |  | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | 0 | 107850 | 107849.94 | 100% | 0.06 | 0 |  | 14021 | -7 | 14014 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | I | CFC | 15.3 | 15.3 |  |  | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | 0 | 115382 | 115382.29 | 100% | -0.29 | 0 |  | 15000 | -10 | 14990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of moulded integral skin flexible PU foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | I | CFC | 11.4 | 11.4 |  |  | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882.27 | 100% | -0.27 | 0 |  | 20525 | 0 | 20525 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -2 | 1298 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 19999.63 | 100% | 0.37 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/ polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -37 | 19963 | 19963.34 | 100% | -0.34 | 0 |  | 2600 | -9 | 2591 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | I | CFC | 45 | 45 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | 0 | 290481 | 290480.82 | 100% | 0.18 | 0 |  | 37763 | -15 | 37748 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Novemeca in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | I | CFC | 16.2 | 16.2 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -632 | 69254 | 69254.09 | 100% | -0.09 | 0 |  | 9085 | -96 | 8989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | I | CFC | 11.8 | 11.8 |  |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -173 | 87866 | 87865.84 | 100% | 0.16 | 0 |  | 11445 | -40 | 11404 | 1 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | 0 | 25000 | 24999.54 | 100% | 0.46 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | I | CFC | 16.5 | 1.1 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119558 | 8829 | 8829 | 100% | 0 | 0 |  | 16690 | -15544 | 1146 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | I | CFC | 36.4 | 36.4 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | 0 | 198374 | 198374.15 | 100% | -0.15 | 0 |  | 25789 | -13 | 25776 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -227 | 19773 | 19772.54 | 100% | 0.46 | 0 |  | 2600 | -34 | 2566 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1: Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | I | CFC | 62.8 | 53.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71323 | 366694 | 366694.41 | 100% | -0.41 | 0 |  | 56942 | -9347 | 47595 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | I | CFC | 32 | 32 |  |  | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | 0 | 198882 | 198881.59 | 100% | 0.41 | 0 |  | 25855 | -15 | 25840 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project. | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | I | CFC | 135.5 | 135.5 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 | 2006-05-01 | 851432 | -86779 | 764653 | 764652.66 | 100% | 0.34 | 0 |  | 103658 | -9679 | 93978 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | VEN | FOA | 60 | PRP | 115 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-12-01 | 2013-10-01 | 100000 | -56 | 99944 | 99943.84 | 100% | 0.16 | 0 |  | 7500 | -4 | 7496 | 0 | 0 | FIN
FIN | UNIDO | Workshop on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -2 | 5198 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2008-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | 0 | 95000 | 94999.88 | 100% | 0.12 | 0 |  | 12350 | -12 | 12338 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-09-01 | 2008-05-01 | 1895062 | 0 | 1895062 | 1895062 | 100% | 0 | 0 |  | 142130 | 0 | 142130 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | I | CFC | 50 | 50 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2007-07-01 | 2010-05-01 | 1631831 | 0 | 1631831 | 1631831 | 100% | 0 | 0 |  | 122387 | 0 | 122387 | 0 | 0 | FIN |  |  | 2007-12-01 | INV
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | VEN | PHA | 51 | INV | 109 | A | I | CFC | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2011-12-01 | 2012-12-01 | 2071831 | -286 | 2071545 | 2071545.2 | 100% | -0.2 | 0 |  | 155387 | -21 | 155366 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | VEN | PHA | 55 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 173750 | -718 | 173032 | 173031.53 | 100% | 0.47 | 0 |  | 13031 | -54 | 12977 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan: 2009 work programme | Multi-Year | LAC | VEN | PHA | 57 | INV | 114 | A | I | CFC | 985 | 985 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2012-06-01 | 2013-12-01 | 513465 | -769 | 512696 | 513003.49 | 100.1% | -307.49 | 0 |  | 38510 | -58 | 38475 | -23 | 0 | FIN |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | INV | 118 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 | 2015-09-01 |  |  | 654854 | 0 | 654854 | 618341.88 | 94.42% | 36512.12 | 34916.34 | 36512 | 49114 | 0 | 46376 | 2738 | 2619 | - To continue with the training programme including the use of HC. - To implement a pilot project to replace HCFC-22 for HC in air-conditioners in two small hotels. - Activities are linked to the second tranche. - Some refrigerant identifiers were purchased in April 2014. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Few additional activities were carried out in this project since little funds are available. - The project will be completed latest in September 2015. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Milestone 5: New manuals for good refrigeration practices and custom officers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | INV | 120 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 | 2015-12-01 |  |  | 603339 | 0 | 603339 | 389017.04 | 64.48% | 214321.96 | 34916.71 | 107300 | 45250 | 0 | 29176 | 16074 | 2618.7533 | - To purchase tools for the trained and certified technicians. - To purchase refrigerant identifiers required to upgrade the customs. - To prepare a manual for the use of HC as alternative. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Special public awareness and project activities to reduce refrigerant leaks was launched. Public awareness programs are continuous and very effective in the country. - The program for training of technicians with the national vocational institution (INCES) is delayed due to different circumstances, alternatives have been found and the program is expected to start during the third quarter of 2015. - Tools for certified technicians are planned to be purchased in the second semester 2015. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Milestone 5: New manuals for good refrigeration practices and custom officers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | INV | 124 | A | I | HCFC | 4 | 0 |  |  | 2013-07-01 | 2014-04-01 | 2015-07-31 | 2015-12-01 |  |  | 324875 | 0 | 324875 | 141700.16 | 43.62% | 183174.84 | 0 | 50000 | 24366 | 0 | 10628 | 13738 | 0 | - All the activities are linked to the previous tranches. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Brief report: All the activities are linked to the previous tranches. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Milestone 5: New manuals for good refrigeration practices and custom officers. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | VEN | PHA | 72 | PRP | 127 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-08-01 | 2015-05-31 | 2016-03-01 |  |  | 90000 | 0 | 90000 | 24592.24 | 27.32% | 65407.76 | 2501.3 | 35000 | 6300 | 0 | 1721 | 4579 | 175 | - The project preparation was approved at the 72nd Meeting of the ExCom in May 2014. Milestones achieved: Milestone 1: International experts for the project preparation and strategy contracted. Yes Milestone 2: Surveys on HCFC consumption and alternatives carried out. Yes Milestone 3: Strategy for the HPMP Second phase defined. Yes Milestone 4: National coordinator for the activities contracted. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - The project is being prepared by the NOU team with the support of some international experts and the guide of UNIDO PM. - The general strategy has been defined. - It is expected to submit the Second Phase to the 76th Meeting of the ExCom. Milestones achieved: Milestone 1: International experts for the project preparation and strategy contracted. Yes Milestone 2: Surveys on HCFC consumption and alternatives carried out. Yes Milestone 3: Strategy for the HPMP Second phase defined. Yes Milestone 4: National coordinator for the activities contracted. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Phasing out CFC-11 and CFC-12 withHCFC-141b and HFC-134a at INVITREL in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | I | CFC | 46.4 | 46.4 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -1714 | 417380 | 417379.62 | 100% | 0.38 | 0 |  | 54482 | -309 | 54173 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -325 | 24675 | 24675.21 | 100% | -0.21 | 0 |  | 3250 | -47 | 3203 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressor sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -113 | 19887 | 19887.32 | 100% | -0.32 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at five commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 76 | A | I | CFC | 30.9 | 30.9 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64008 | 405132 | 405131.58 | 100% | 0.42 | 0 |  | 60988 | -8404 | 52584 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at three domestic refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 79 | A | I | CFC | 27 | 27 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -75965 | 295740 | 295740.37 | 100% | -0.37 | 0 |  | 48322 | -9937 | 38385 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -124 | 19876 | 19875.84 | 100% | 0.16 | 0 |  | 2600 | -20 | 2580 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -238 | 29762 | 29761.76 | 100% | 0.24 | 0 |  | 3900 | -37 | 3863 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -2912 | 67088 | 67087.78 | 100% | 0.22 | 0 |  | 9100 | -392 | 8708 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | I | CFC | 32.3 | 32.3 |  |  | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | -84678 | 318912 | 318912.44 | 100% | -0.44 | 0 |  | 52467 | -11074 | 41393 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning manufacturing sector) | Individual | LAC | VEN | REF | 60 | PRP | 116 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2011-12-01 | 2013-10-01 | 100000 | -783 | 99217 | 99216.82 | 100% | 0.18 | 0 |  | 7500 | -59 | 7441 | 0 | 0 | FIN
ONG | UNIDO | Update the preparation for HCFC phase-out investment activities (stage II) (refrigeration manufacturing sector) | Individual | LAC | VEN | REF | 72 | PRP | 125 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-12-01 | 2015-05-31 | 2016-03-01 |  |  | 50000 | 0 | 50000 | 4.51 | 0.00902% | 49995.49 | 4794.14 | 15000 | 3500 | 0 | 0 | 3500 | 336 | - The project preparation was approved at the 72nd Meeting of the ExCom in May 2014. Milestones achieved: Milestone 1: International experts for the project preparation and strategy contracted. Yes Milestone 2: Surveys on HCFC consumption and alternatives carried out. Yes Milestone 3: Strategy for the HPMP Second phase defined. Yes Milestone 4: National coordinator for the activities contracted. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - The activities under the project preparation and under this project are the same. '- The project is being prepared by the NOU team with the support of some international experts and the guide of UNIDO PM. - The general strategy has been defined. - It is expected to submit the Second Phase to the 76th Meeting of the ExCom. Milestones achieved: Milestone 1: International experts for the project preparation and strategy contracted. Yes Milestone 2: Surveys on HCFC consumption and alternatives carried out. Yes Milestone 3: Strategy for the HPMP Second phase defined. Yes Milestone 4: National coordinator for the activities contracted. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | I | TCA | 1.9 | 1.9 |  |  | 2005-04-01 | 2006-04-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -1005 | 38995 | 38994.65 | 100% | 0.35 | 0 |  | 3600 | -90 | 3510 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -9744 | 401436 | 401435.78 | 100% | 0.22 | 0 |  | 53453 | -1349 | 52104 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | I | HAL | 37.1 | 37.1 |  |  | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7148 | 17852 | 17851.65 | 100% | 0.35 | 0 |  | 3250 | -933 | 2317 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 04 | A | I | CFC | 40 | 40 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -2690 | 494380 | 494380 | 100% | 0 | 0 |  | 64619 | -452 | 64167 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1921 | 29 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11168 | 8832 | 8832 | 100% | 0 | 0 |  | 2600 | -1454 | 1146 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2885 | 17115 | 17114.86 | 100% | 0.14 | 0 |  | 2600 | -379 | 2221 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 08 | A | R | CFC | 96.6 | 96.6 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | -5910 | 360894 | 360893.99 | 100% | 0.01 | 0 |  | 34676 | -613 | 34063 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | I | CFC | 82.7 | 82.7 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | 0 | 179508 | 179507.91 | 100% | 0.09 | 0 |  | 23336 | -33 | 23303 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam component) | Individual | ASP | YEM | FOA | 63 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-01-01 | 2012-03-31 |  | 2012-12-01 | 2014-04-01 | 60000 | -48664.5 | 11335.5 | 11335.71 | 100% | -0.21 | 0 |  | 4500 | -3650 | 850 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | YEM | FOA | 73 | PRP | 46 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2016-12-16 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 40000 | 5600 | 0 | 0 | 5600 | 0 | - Project approved at the 73rd Meeting of the ExCom in November 2014. - Due to the political and security situation in the country, coordination meeting with the NOU planned for the regional network meeting in early 2015. | - The coordination meeting with NOU Yemen took place on the margins of the Regional Network Meeting in Bahrain in March 2015. Milestones achieved: Milestone 1: Coordination meeting to agree working arrangements - Yes Milestone 2: TOR for HCFC Survey - No Milestone 3: Experts recruited - No Milestone 4: Local institutions identified - No Milestone 5: Stakeholders workshop held - No Activities planned but not implemented, reasons and strategy: Since the last day of the regional meeting, the political and security situation in the country has deteriorated and the NOU is currently out of the country therefore any planning has been put on hold. Actions towards next goals: See above Was there any delay during the reporting year? Yes. See above Out of control of the PM Any recurring problem? Yes. See above See above Any impact on project completion date: Delay if the political and security situation does not improve. See above Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | INV | 28 | A | I | CFC | 339.4 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-12-31 | 2016-06-15 |  |  | 1137500 | 0 | 1137500 | 1093705.72 | 96.15% | 43794.28 | 32331.37 | 32331 | 85313 | 0 | 82028 | 3285 | 2425 | - The remaining balances will be used for the outstanding payments for the equipment already delivered by OMS, Italy. The OMS currently unable to conduct commissioning and start up because of the security situation in the country. - It was agreed with the supplier that instead technicians from the beneficiary companies will receive training at the suppliers facilities in order to complete the commissioning. Milestones achieved: Milestone 1: Commissioning of equipment - No Milestone 2: Training of national personnel at the supplier's facility for commissioning Activities planned but not implemented, reasons and strategy: Commissioning, start up and training due the security situation in the country. Actions towards next goals: Organize training at the suppliers' facilities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: as above. Any recurring problem? Yes If yes, description of the problem/s: as above. Any impact on project completion date: Yes If yes, implications: as above. Any action required by Executive Committee? No | - As per Dec 74/2, project completion date extended until June 2016. - Uncertain political situation in the country. - No NOU in charge. |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | YEM | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2012-12-01 | 2014-04-01 | 70000 | -1156 | 68844 | 68843.64 | 100% | 0.36 | 0 |  | 5250 | -87 | 5163 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | INV | 36 | A | I |  | 268.7 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 | 2016-06-01 |  |  | 233000 | 0 | 233000 | 132976.04 | 57.07% | 100023.96 | 97260.85 | 40000 | 17475 | 0 | 9973 | 7502 | 7295 | - The remaining balances will be used for the outstanding payments for the equipment already delivered by OMS, Italy. The OMS currently unable to conduct commissioning and start up because of the security situation in the country. - It was agreed with the supplier that instead technicians from the beneficiary companies will receive training at the suppliers facilities in order to complete the commissioning. Milestones achieved: Milestone 1: Commissioning of equipment - No Milestone 2: Training of national personnel at the supplier's facility for commissioning Activities planned but not implemented, reasons and strategy: Commissioning, start up and training due the security situation in the country. Actions towards next goals: Organize training at the suppliers' facilities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: as above. Any recurring problem? Yes If yes, description of the problem/s: as above. Any impact on project completion date: Yes If yes, implications: as above. Any action required by Executive Committee? No | - As per Dec 74/2, project completion date extended until June 2016. - Uncertain political situation in the country. - No NOU in charge.
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 39 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2014-10-01 | 2014-12-31 | 2017-06-01 |  |  | 410000 | 0 | 410000 | 154373.86 | 37.65% | 255626.14 | 3243.8 | 22480.93 | 28700 | 0 | 10806 | 17894 | 227.066 | - The delay was caused by the inability to arrange consultation meeting with the NOU, which took place only in November 2013. - After the scope of the procurement was agreed with the NOU, the request for quotations for equipment to the refrigeration service sector (refrigerant identifiers, vacuum pumps, recycling filter kits, upgrade kits, flushing units, acid test kits) published in December 2013. - The suppliers were selected in February 2014 and Purchase Orders issued in March 2014. The delivery completed in September 2014. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Security situation in the country. Any recurring problem? Yes If yes, description of the problem/s: as above. Any impact on project completion date: Yes If yes, implications: as above. Any action required by Executive Committee? No | - Meeting with NOU Yemen took place on the margins of the Regional Network Meeting in Bahrain in March 2015. - No NOU in charge. |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | YEM | PHA | 73 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2016-12-16 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 1000 | 1400 | 0 | 0 | 1400 | 0 | - Same as YEM/FOA/73/PRP/46. | - Same as YEM/FOA/73/PRP/46. |  |  | NON-INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3268 | 16732 | 16732.05 | 100% | -0.05 | 0 |  | 2600 | -428 | 2172 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | I | CFC | 7.3 | 7.3 |  |  | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1328 | 104313 | 104313.09 | 100% | -0.09 | 0 |  | 13733 | -194 | 13539 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | I | CFC | 6.1 | 6.1 |  |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1456 | 88775 | 88774.93 | 100% | 0.07 | 0 |  | 11730 | -208 | 11522 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2349 | 7651 | 7651 | 100% | 0 | 0 |  | 1300 | -307 | 993 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2008-04-01 | 2008-09-01 | 30000 | -453 | 29547 | 29547.47 | 100% | -0.47 | 0 |  | 2250 | -34 | 2216 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | I | TCA | 0.2 | 0.2 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 35000 | -164 | 34836 | 34836.35 | 100% | -0.35 | 0 |  | 3150 | -15 | 3135 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -15 | 14985 | 14984.86 | 100% | 0.14 | 0 |  | 1950 | -5 | 1945 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -201 | 14799 | 14799.45 | 100% | -0.45 | 0 |  | 1950 | -29 | 1921 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | I | CFC | 75 | 75 |  |  | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2006-12-01 | 2011-05-01 | 475728 | -4430 | 471298 | 471297.59 | 100% | 0.41 | 0 |  | 61845 | -576 | 61269 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | I | CFC | 34.4 | 34.4 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -169 | 100071 | 100071.22 | 100% | -0.22 | 0 |  | 13031 | -42 | 12989 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2009-09-01 | 2009-09-01 | 25000 | -9189 | 15811 | 15811.39 | 100% | -0.39 | 0 |  | 1875 | -689 | 1186 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -82 | 19918 | 19918.09 | 100% | -0.09 | 0 |  | 2600 | -15 | 2585 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | I | HAL | 370 | 370 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | -4216 | 245484 | 245483.51 | 100% | 0.49 | 0 |  | 32461 | -599 | 31862 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7481 | 32519 | 32518.95 | 100% | 0.05 | 0 |  | 3000 | -565 | 2435 | 0 | 0 | FIN
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | I | CFC | 2 | 2 |  |  | 2004-07-01 | 2004-08-01 | 2005-03-01 |  | 2009-12-01 | 2013-10-01 | 474700 | -34974 | 439726 | 439725.51 | 100% | 0.49 | 0 |  | 35603 | -2624 | 32979 | 0 | 0 | FIN |  |  | 2006-07-01 | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | I | cFC | 18 | 18 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2013-12-01 | 2014-08-01 | 759000 | -623749 | 135251 | 135250.61 | 100% | 0.39 | 0 |  | 56925 | -46781 | 10144 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | YUG | PHA | 50 | INV | 30 | A | I | CFC | 124 | 124 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2013-12-01 | 2014-04-01 | 1033344 | -12 | 1033332 | 1033331.99 | 100% | 0.01 | 0 |  | 77501 | -1 | 77500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 51 | INV | 31 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2009-12-01 | 2008-03-01 |  | 2013-12-01 | 2014-04-01 | 222000 | -23917 | 198083 | 198083.19 | 100% | -0.19 | 0 |  | 16650 | -1794 | 14856 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | YUG | PHA | 55 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-12-01 | 150000 | -955 | 149045 | 149044.87 | 100% | 0.13 | 0 |  | 11250 | -72 | 11178 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | EUR | YUG | PHA | 60 | INV | 36 | A | I |  | 268 | 268 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2014-06-01 | 2014-09-01 | 193500 | -145499 | 48001 | 48001.21 | 100% | -0.21 | 0 |  | 14513 | -10912 | 3600 | 1 | 0 | FIN
FIN | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 40678 | -121 | 40557 | 40556.58 | 100% | 0.42 | 0 |  | 3051 | -9 | 3042 | 0 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | INV | 38 | A | I | HCFC | 2.3 | 2.3 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2015-12-01 |  |  | 360130 | 0 | 360130 | 158291.54 | 43.95% | 201838.46 | 183032.5 | 182821 | 27010 | 0 | 11872 | 15138 | 13727 | - Conversion of 2 enterprises has been completed and technology fully committed. - Train the trainer component was achieved in parallel with the up-date of the policies and regulations on the certification system. Milestones achieved: Milestone 1: Conversion of 2 companies (commercial refrigeration sector) - Yes Milestone 2: Train the trainer component completed - Yes Milestone 3: Development of agreements with vocational schools for implementation of the certification scheme - Yes Actions towards next goals: Preparation of the implementation of the technicians certification programme. Was there any delay during the reporting year? Yes If yes, reasons and action plan: the implementation of specific training activities at Vocational Schools are inter-related with the second tranche, thus financial completion will be achieved by end of 2015 Any recurring problem? No Any impact on project completion date: Project is to be completed by December 2015. If yes, implications: (narrative):NA Any action required by Executive Committee? No | - Agreements with vocational schools were signed in the first quarter 2015 and certification programme implementation has been initiated. Milestones achieved: Milestone 1: Signature of Agreements with vocational schools for technicians training and certification - Yes Milestone 2: Completion of the activities under tranche 1 - No Activities planned but not implemented, reasons and strategy: Financial completion of tranche 1 will be achieved by the end of 2015, remaining balance is to be used for the implementation of the training programmes that are continuing under tranche 2. Actions towards next goals: Continuation of Implementation of the training programmes under tranche 2. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: the implementation of specific training activities at Vocational Schools are inter-related with the second tranche, thus financial completion will be achieved by end of 2015 Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | INV | 41 | A | I | HCFC | 2.7 | 0.12 |  |  | 2013-12-01 |  | 2016-12-31 | 2017-03-01 |  |  | 444130 | 0 | 444130 | 0 | 0% | 444130 | 0 | 80000 | 33310 | 0 | 0 | 33310 | 0 | - Tranche 2 approved in the end of 2013. - Technical specifications for equipment delivery for conversion of the remaining 2 enterprises in commercial refrigeration was achieved. - Development of technical specification for the recovery network was initiated. - Training in connection with the legislation up-date has been achieved with the involvement of the Refrigeration Association and relevant stakeholders. Milestones achieved: Milestone 1: Technical specifications developed for conversion of 2 remaining enterprises - Yes Milestone 2: Work plan for the certification training programme - Yes Actions towards next goals: Implementation of the certification programme Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Administrative changes took place at the level of Ministry of Environment in Serbia. - New Ozone Officer was appointed in May 2015. - Arrangements for the implementation of the technicians training programme (occurring under NOU supervision)is delayed with 5 months, however, new work plan and related preparatory work are to be agreed upon with the new Ozone Officer in July 2015, upon scheduling a UNIDO mission to the field. - It is expected that the training programme to be implemented during 2015 without further major delays. - Delivery of equipment for the remaining 2 enterprises in commercial sector is scheduled for the second half of 2015. Milestones achieved: Milestone 1: Initiation of training and certification programme for technicians - Yes Milestone 2: Equipment delivery for commercial enterprises - No Actions towards next goals: Preparation of tranche 3 submission in 2016. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Administrative changes and NOU Officer change caused minor delays in implementation. It is expected that completion date and tranche 3 submission will not be affected. Any recurring problem? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | YUG | PHA | 71 | TAS | 42 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2016-11-30 | 2016-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 1000 | 2700 | 0 | 0 | 2700 | 0 | - Verification report on implementation by NCs / IC. - Planned completion date was changed as per Secretariat’s communication dated 11 February 2015. Milestones achieved: Not applicable Actions towards next goals: Verification report to be contracted in the beginning of 2016. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - ToR for verification report and consultancy service selection scheduled for the second half of 2015. Milestones achieved: Milestone 1: Selection of consultancy services - No Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -1 | 1299 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2325 | 7675 | 7674.59 | 99.99% | 0.41 | 0 |  | 1300 | -304 | 996 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at seven enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | I | CFC | 59.6 | 59.6 |  |  | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -19150 | 736012 | 736012.22 | 100% | -0.22 | 0 |  | 93068 | -2235 | 90833 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -119 | 19881 | 19881.28 | 100% | -0.28 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | I | CFC | 10.9 | 10.9 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | -1869 | 148240 | 148239.7 | 100% | 0.3 | 0 |  | 19514 | -273 | 19241 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | I | CFC | 2 | 2 |  |  | 2002-11-01 | 2003-06-01 | 2005-06-01 |  | 2006-06-01 | 2007-09-01 | 223412 | -44 | 223368 | 223367.9 | 100% | 0.1 | 0 |  | 29044 | -6 | 29038 | 0 | 0 | FIN |  |  |  | INV