FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning manufacturing sector) | Individual | EUR | YUG | REF | 61 | PRP | 37 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-11-01 | 2011-07-31 |  | 2011-07-01 | 2011-12-01 | 60000 | -388 | 59612 | 59611.83 | 100% | 0.17 | 0 |  | 4500 | -29 | 4471 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country Programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Creation of Ozone Secretariat | Individual | EUR | YUG | SEV | 25 | INS | 07 | N | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | 0 | 151500 | 151500.04 | 100% | -0.04 | 0 |  | 19695 | -5 | 19690 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-07-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 131300 | -7175 | 124125 | 124124.73 | 100% | 0.27 | 0 |  | 9848 | -539 | 9309 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase III) | Individual | EUR | YUG | SEV | 59 | INS | 34 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2011-11-01 |  | 71121 | 60179 | 131300 | 116247.09 | 88.54% | 15052.91 | 3814.28 | 13000 | 5334 | 4513 | 8719 | 1128 | 286 |  |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | EUR | YUG | SEV | 65 | INS | 40 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-01-01 | 2013-11-30 | 2015-12-01 |  |  | 131300 | 0 | 131300 | 73799.62 | 56.21% | 57500.38 | 24463.66 | 39390 | 9848 | 0 | 5535 | 4313 | 1835 | - Restructuring of the Government continued and decision to nominate new staff in NOU office has been taken. - Awareness activities were organized involving NGOs selection process. - NOU office equipment and office supplies were delivered locally. - Data collection related activities performed by NOU were implemented as scheduled. Milestones achieved: Milestone 1: Office equipment delivery - Yes Milestone 2: Awareness activities involving NGOs - Yes Actions towards next goals: Work plan for the year 2015. Was there any delay during the reporting year? No Yes. If yes, reasons and action plan: Administrative restructuring and change of personnel in NOU; New Ozone Officer appointment in May 2015. Any recurring problem? No Any impact on project completion date: Yes. The project is to be completed by the end of 2015. Any action required by Executive Committee? No | - New NOU Officer has been appointed in May 2015, and activities implementation were slightly delayed. - Awareness activities to celebrate International Ozone Day were agreed in June 2015 with the new NOU team, and work plan to cover second half of 2015 will be expedite end of July 2015 (upon UNIDO field mission in Serbia). Milestones achieved: Milestone 1: NOU staff nomination - Yes Milestone 2: Awareness activities planned - Yes Milestone 3: Awareness activities organization - No Milestone 4: Work plan for second half of 2015 - No Activities planned but not implemented, reasons and strategy: Activities to be concluded between July and September 2015. Actions towards next goals: UNIDO Mission to Belgrade scheduled for the end of July 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Administrative restructuring and change of personnel in NOU; New Ozone Officer appointment in May 2015. Any recurring problem? No Any impact on project completion date: yes ; The project is to be completed by the end of 2015. Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | EUR | YUG | SEV | 71 | INS | 44 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-06-01 | 2015-11-30 | 2017-02-01 |  |  | 131300 | 0 | 131300 | 125.25 | 0.09539% | 131174.75 | 1830.29 | 30000 | 9191 | 0 | 9 | 9182 | 128.1203 | - Implementation initiated in the second half of 2014 since there were still on-going activities from previous phase. Milestones achieved: Milestone 1: Work plan agreement - Yes Milestone 2: NOU consultants selection - Yes Activities planned but not implemented, reasons and strategy: (narrative): NA Actions towards next goals: Work plan for the year 2015 Was there any delay during the reporting year? Yes If yes, reasons and action plan: Initiation of the activities was delayed as there were still on-going activities to be completed from the previous IS phase Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion of the project is expected to be delayed 6 months Any action required by Executive Committee? No | Brief report: (narrative): Work plan agreed with Government Initiation of implementation of planned activities in 2015 was delayed by restructuring and new appointment for the position of Ozone Officer in the Government. NOU Officer was appointed in May 2015. Milestones achieved: Milestone 1: Work plan for the year 2015 revised - Yes Milestone 2: Awareness activities planned for the International Ozone Day - Yes Milestone 3: consultants contracts - No Actions towards next goals: (narrative): UNIDO mission to Belgrade will take place end of July to review the project implementation and actions forward. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Government restructuring and New Ozone Officer appointment in May 2015 caused a delay in activities implementation of approx. 6 months Any recurring problem? No Any impact on project completion date: Yes If yes, implications: It expected that completion date will be delayed 8 months Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2587 | 7413 | 7413.15 | 100% | -0.15 | 0 |  | 1300 | -338 | 962 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-113 as solvent for dyaliser cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 08 | A | R | CFC | 54.6 | 54.6 |  |  | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960 | 0 | 76960 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2008-12-01 | 2009-06-01 | 15000 | -1991 | 13009 | 13009.15 | 100% | -0.15 | 0 |  | 1125 | -149 | 976 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the fumigants sector (soil fumigation) | Individual | AFR | ZAM | FUM | 54 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-09-01 | 2009-03-31 |  | 2008-12-01 | 2011-09-01 | 35000 | -9714 | 25286 | 25285.83 | 100% | 0.17 | 0 |  | 2625 | -729 | 1896 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses | Individual | AFR | ZAM | FUM | 56 | INV | 21 | A | I | MBR | 7.4 | 7.4 |  |  | 2008-11-01 | 2009-12-01 | 2011-11-30 | 2015-12-01 |  |  | 289548 | 0 | 289548 | 243246.62 | 84.01% | 46301.38 | 23117.36 | 20000 | 21716 | 0 | 18243 | 3473 | 1734 | - The delivery of last set of equipment and materials took place. - Last training activities are still under preparation. Milestones achieved: Milestone 1: Legal agreements - Yes Milestone 2: Initial stages of project implementation began - Yes Milestone 3: Intermediate goals achieved - Yes Milestone 4: Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: Last training activities are missing, in particular training to tobacco growers on the floating tray system. Actions towards next goals: Promote the finalization of the last training activities. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of prompt responses from the field. Promote a more frequent dialogue with the responsible persons in the field. Any recurring problem? Yes If yes, description of the problem/s: Lack of prompt responses from the field. Promote a more frequent dialogue with the responsible persons in the field. Any impact on project completion date: Yes If yes, implications: Project will be finalized by the end of 2015. However, the country is fully in compliance with ExCom and MP targets. Any action required by Executive Committee? No | - UNIDO mission to Zambia took place in April 2015, to discuss on last activities. - NOU and field team showed commitment and agreed on the need to put additional resources to have the project successfully finalized before the year end. Milestones achieved: Milestone 1: Legal agreements - Yes Milestone 2: Initial stages of project implementation began - Yes Milestone 3: Intermediate goals achieved - Yes Milestone 4: Project completion and follow-up - No Actions towards next goals: Last training activities was agreed. NOU will call for a meeting of the steering committee to arrange the training activities to the tobacco farmers. Last resources will be allocated to finalize the awareness and training activities as well as involve the custom authorities to ensure sustainable ban to the import of MB. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: Project will be finalized by the end of 2015. However, the country is fully in compliance with ExCom and MP targets. Any action required by Executive Committee? No |  |  | INV |  | Continued Monitoring
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | INV | 26 | A | I | HCFC | 0.4 | 0.4 |  |  | 2011-07-01 | 2013-02-01 | 2016-07-31 | 2015-07-01 |  |  | 70000 | 0 | 70000 | 67827.55 | 96.9% | 2172.45 | 0 | 2000 | 6300 | 0 | 6104 | 196 | 0 | - Equipment delivered and commissioning took place. - All milestones achieved as expected without any delay or recurring problems. - Project to be completed earlier than originally planned. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes Milestone 5: Equipment shipped/delivered/installed at site - Yes Milestone 6: Commissioning and trial runs completed - Yes Activities planned but not implemented, reasons and strategy: Closing ceremony was missing. All substantial activities were completed. Actions towards next goals: Organize final ceremony and close the project. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No If yes, implications: Project closed earlier than originally planned. Any action required by Executive Committee? No. | - Final ceremony took place in April 2015. - Project is closed. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes Milestone 5: Equipment shipped/delivered/installed at site - Yes Milestone 6: Commissioning and trial runs completed - Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No If yes, implications: Project closed earlier than originally planned. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 03 | A | I |  | 0 | 17.7 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5625 | 76475 | 76475 | 100% | 0 | 0 |  | 10673 | -747 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 40000 | -1745 | 38255 | 38254.73 | 100% | 0.27 | 0 |  | 3600 | -157 | 3443 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Demonstration project - Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17402 | 353298 | 353297.55 | 100% | 0.45 | 0 |  | 48191 | -2335 | 45856 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -570 | 29430 | 29430.39 | 100% | -0.39 | 0 |  | 3900 | -80 | 3820 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | I | MBR | 132 | 132 |  |  | 2000-07-01 | 2001-03-01 | 2004-08-01 |  | 2006-12-01 | 2010-03-01 | 904200 | -10989 | 893211 | 893211.37 | 100% | -0.37 | 0 |  | 109462 | -1209 | 108253 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -600 | 29400 | 29399.78 | 100% | 0.22 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | -599 | 14401 | 14401.14 | 100% | -0.14 | 0 |  | 1125 | -47 | 1078 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | I | MBR | 50 | 50 |  |  | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-09-01 | 1862486 | 0 | 1862486 | 1862486.01 | 100% | -0.01 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigant sector (grain storage) | Individual | AFR | ZIM | FUM | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-08-01 | 2007-03-01 |  | 2006-12-01 | 2007-03-01 | 20000 | -806.5 | 19193.5 | 19193.5 | 100% | 0 | 0 |  | 1500 | -60 | 1440 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide used in grain fumigation | Individual | AFR | ZIM | FUM | 50 | INV | 36 | A | I | MBR | 10.2 | 10.2 |  |  | 2006-11-01 | 2007-01-01 | 2010-11-01 |  | 2008-12-01 | 2011-05-01 | 192073 | -246 | 191827 | 191826.75 | 100% | 0.25 | 0 |  | 17287 | -23 | 17264 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (second tranche) | Multi-Year | AFR | ZIM | FUM | 51 | INV | 37 | A | I | MBR | 120 | 120 |  |  | 2007-03-01 | 2007-11-01 | 2009-12-01 |  | 2008-12-01 | 2010-09-01 | 1862486 | -2 | 1862484 | 1862483.73 | 100% | 0.27 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 04 | A | I | CFC | 47 | 47 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -143 | 312157 | 312157 | 100% | 0 | 0 |  | 40599 | -83 | 40516 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the refrigeration, air conditioning and recovery/recycling | Individual | AFR | ZIM | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -463 | 39537 | 39537 | 100% | 0 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | MAC servicing demonstration |  | LAC | ARG | REF | 16 | DEM | 22 | A | I | CFC | 20.4 | 20 | 0 |  | 1995-03-01 | 1995-09-01 | 1995-12-01 |  | 1997-06-01 | 1998-06-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-06-01
FIN | USA | Project preparation/technical assistance |  | LAC | ARG | SEV | 13 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | South-east Asia halon-1211 training workshop in Japan |  | ASP | ASP | HAL | 08 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1992-10-01 |  | 1992-10-01 | 1992-10-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Demonstration mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | CHI | REF | 19 | DEM | 15 | A | I | CFC | 10 | 10 | 0 |  | 1996-05-01 | 1996-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-10-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-12-01
FIN | USA | MAC emissions reduction demonstration programme |  | LAC | COL | REF | 15 | DEM | 13 | A | I | CFC | 11.5 | 12 | 0 |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1999-06-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. Project will be classified as financially complete at that time. |  | 1994
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | COS | REF | 19 | DEM | 09 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 2000-05-01 | 2000-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery are planned for May 2000. |  | 1995 | 1997-12-01
FIN | USA | Halon management resource manual |  | ASP | CPR | HAL | 11 | TAS | 53 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Halon-1211 recovery/recharge training workshops |  | ASP | CPR | HAL | 11 | TRA | 57 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 271000 | 0 | 271000 | 271000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Deployment of halon-1211 recovery/recharge machines |  | ASP | CPR | HAL | 12 | INV | 59 | A | I | HAL | 200 | 231 | 0 |  | 1994-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1996-06-01 | 735000 | 72000 | 807000 | 807000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation |  | ASP | CPR | HAL | 13 | PRP | 80 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1996-01-01 |  | 1997-12-01 | 1998-04-01 | 200000 | -68517 | 131483 | 131483 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. No further activities foreseen on this project with the approval of China's Halon Sector Strategy (23rd meeting). |  | 1994 | 1997-12-01
FIN | USA | Halon leak reduction demonstration |  | ASP | CPR | HAL | 16 | DEM | 121 | A | I | HAL | 221.7 | 74 | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-12-01 | 1998-06-01 | 90437 | 0 | 90437 | 90437 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
COM | USA | CFCs, CTC and halon accelerated phase-out plan (first tranche) | Multi-Year | ASP | CPR | PRO | 44 | INV | 425 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2006-10-01 | 2005-12-01 |  | 2006-10-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Completed. Funds disbursed in Oct. 2006.
COM | USA | CFCs, CTC and halon accelerated phase-out-plan (second tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 439 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2009-01-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 |  |  | 375000 | 0 | 375000 | 0 |  | Ongoing.
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1a: model prototype development and testing) |  | ASP | CPR | REF | 10 | TAS | 33 | A | I |  | 0 |  | 0 |  | 1993-06-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 396110 | 0 | 396110 | 396110 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | MAC servicing demonstration |  | ASP | CPR | REF | 16 | DEM | 117 | A | I | CFC | 7 | 11.4 | 0 |  | 1995-03-01 | 1995-04-01 | 1995-03-01 |  | 1996-03-01 | 1996-03-01 | 172500 | -6667 | 165833 | 165833 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) |  | ASP | CPR | REF | 16 | INV | 116 | N | I | CFC | 29 |  | 0 |  | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 2000-05-01 | 2000-05-01 | 1643865 | 0 | 1643865 | 1643865 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Conversion of line to produce cyclopentane-152a/22 refrigerators completed, certified Aug96; CFCs eliminated. Final funding to follow verification of old equipment destruction, review of receipts, final safety certification, and initial production. |  | 1995 | 1999-12-01
FIN | USA | Refrigeration management demonstration project preparation |  | ASP | CPR | REF | 16 | PRP | 118 | A | I |  | 0 |  | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Demonstration project (refrigeration - large food stores) |  | ASP | CPR | REF | 17 | DEM | 135 | A | I |  | 0 |  | 0 |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1998-01-01 | 1998-12-01 | 132000 | 26400 | 158400 | 158400 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-06-01
FIN | USA | Refrigeration mobile air conditioning (MAC) servicing |  | ASP | CPR | REF | 19 | DEM | 163 | A | I | CFC | 11.4 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1999-05-01 |  | 1998-11-01 | 1998-12-01 | 385000 | 77600 | 462600 | 462600 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1995 | 1997-12-01
FIN | USA | Support for the FESCAST international conference |  | ASP | CPR | SEV | 08 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1994-04-01 | 87000 | 96000 | 183000 | 183000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $96,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Demonstration project in MACs |  | LAC | DOM | REF | 17 | DEM | 03 | A | I |  | 0 | 10 | 0 |  | 1995-07-01 | 1995-09-01 | 1996-12-01 |  | 1997-12-01 | 1999-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Project preparation in commercial refrigeration |  | LAC | DOM | REF | 17 | PRP | 02 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1995-09-01 | 1995-09-01 | 19000 | 0 | 19000 | 19000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Demonstration project in commercial refrigeration (food storage, distribution and retailing) |  | LAC | DOM | REF | 18 | DEM | 05 | A | I |  | 0 | 7 | 0 |  | 1995-11-01 | 1995-11-01 | 1996-12-01 |  | 1998-02-01 | 1999-10-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Technical assistance in aerosol project preparation |  | LAC | ECU | ARS | 08 | PRP | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-04-01 |  | 1993-04-01 | 1993-04-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Feasibility study for reduction of CFC-11 in rigid polyurethane foam insulation for refrigerators using water/CO2 formulation |  | LAC | ECU | FOA | 08 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 41000 | 50000 | 91000 | 91000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $50,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Halon-1211 management plan |  | LAC | ECU | HAL | 13 | TAS | 16 | A | I |  | 5.5 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Support for country programme preparation |  | LAC | ECU | SEV | 07 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-09-01 |  | 1993-09-01 | 1993-09-01 | 50000 | 6000 | 56000 | 56000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $6,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Assistance in implementation of country programme |  | LAC | ECU | SEV | 11 | CPG | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Regional workshops in halon-1211 training |  | GLO | GLO | HAL | 08 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 429000 | 0 | 429000 | 429000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Refrigeration: mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | GUA | REF | 19 | DEM | 10 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 1998-08-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. |  | 1995 | 1997-12-01
FIN | USA | MAC demonstration project |  | LAC | JAM | REF | 23 | DEM | 07 | A | I | CFC | 9.6 |  | 0 |  | 1997-11-01 | 1998-02-01 | 1998-12-01 |  | 1999-06-01 | 2000-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Equipment delivered and training conducted in March 99, with follow-up mission in June 1999. Final report will be submitted June 2000. |  | 1997
FIN | USA | Follow-up to regional halon-1211 workshop |  | LAC | LAC | HAL | 08 | TRA | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Project preparation for low consuming countries |  | LAC | LAC | REF | 13 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation in MAC and refrigerated transport in Central American and the Caribbean |  | LAC | LAC | REF | 19 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1998-02-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Final report submitted in June 1998. |  | 1995 | 1997-05-01
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) in Central America: El Salvador, Honduras, Nicaragua and Panama |  | LAC | LAC | REF | 24 | DEM | 27 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-06-01 | 2000-07-01 | 569000 | 0 | 569000 | 569000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training and equipment were provided in El Salvador, Honduras, Nicaragua and Panama in April - May 1999. Final report will be submitted in June 2000.
FIN | USA | Project preparation in the halon sector |  | ASP | MAL | HAL | 15 | PRP | 54 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-06-01 |  | 1995-06-01 | 1996-06-01 | 45000 | -28116 | 16884 | 16884 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Conference on the elimination of ozone depleting solvents |  | ASP | MAL | SOL | 11 | TRA | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Chiller hands-on training |  | LAC | MEX | REF | 08 | TRA | 19 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 81000 | 259000 | 340000 | 340000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $259,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Demonstration project in MAC |  | LAC | MEX | REF | 13 | DEM | 27 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Pilot sectoral study and action plan in commercial refrigeration |  | LAC | MEX | REF | 13 | TAS | 26 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 410000 | -139742 | 270258 | 270258 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Cancun chiller workshop |  | LAC | MEX | REF | 13 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Institutional strengthening |  | LAC | MEX | SEV | 07 | INS | 16 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 285000 | 65000 | 350000 | 350000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. US $65,000 against 1994 contributions (15th meeting)
FIN | USA | Support for country programme preparation and development of project proposals |  | LAC | MEX | SEV | 07 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-06-01 | 145000 | 136000 | 281000 | 281000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $136,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Assistance to country programme and investment projects preparation |  | LAC | MEX | SEV | 08 | CPG | 18 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Mexican solvents programme to reduce CFC-113 and methyl chloroform |  | LAC | MEX | SOL | 08 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 360000 | 138000 | 498000 | 498000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $138,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Project preparation |  | LAC | MEX | SOL | 13 | PRP | 28 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 450000 | -119143 | 330857 | 330857 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Technical assistance in halon-1211 |  | LAC | PAN | HAL | 13 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 120000 | -42445 | 77555 | 77555 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | MACs servicing demonstration project |  | ASP | PHI | REF | 18 | DEM | 41 | A | I | CFC | 11 |  | 0 |  | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1999-09-01 | 1999-09-01 | 285500 | 0 | 285500 | 285500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | UNDP is working with the Government of the Philippines to complete the project. |  | 1995 | 1997-05-01
FIN | USA | Follow-up activities of the USA/Thailand/Japan conference on conservation, containment and alternatives |  | ASP | THA | SOL | 08 | TAS | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 203000 | -67000 | 136000 | 136000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | MAC demonstration project |  | LAC | TRI | REF | 23 | DEM | 08 | A | I | CFC | 10 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1999-05-01 | 2000-05-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1997
FIN | USA | MACs servicing demonstration project |  | EUR | TUR | REF | 23 | DEM | 32 | A | I | CFC | 12 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 2000-07-01 | 205000 | 0 | 205000 | 205000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery planned for May 99. |  | 1997
FIN | USA | Technical assistance in halon-1211 management |  | LAC | URU | HAL | 13 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | I |  | 76.1 |  | 0 |  | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Technical assistance in halon-1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | I | HAL | 2 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector |  | LAC | VEN | REF | 15 | DEM | 30 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Assistance in country programme preparation |  | LAC | VEN | SEV | 08 | CPG | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Training in all ODS sectors in Venezuelan Military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | MAC servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Terminated. |  | 1996 | 1998-12-01
Note on A4098: Patrick Salifu Yes Status is correct
Note on A4117: Patrick Salifu Yes Status is correct
Note on A4120: E: FIN?
Note on A4121: Patrick Salifu yes
Note on A4172: Ayman Eltalouny: Masa to confirm if this can be considered financilally closed
Note on A4174: Ayman Eltalouny: Masa to confirm if this can be considered financilally closed
Note on A4200: Yamar Guisse: Yes it is finilised
Note on A4219: Yamar Guisse: Correct!
Note on A4278: Yamar Guisse: Correct!
Note on A4343: Yamar Guisse: YES
Note on A4350: Yamar Guisse: FIN
Note on A4371: Yamar Guisse: Correct!
Note on A4420: Yamar Guisse: Correct!
Note on A4471: Yamar Guisse: Correct!
Note on A4529: Yamar Guisse: Correct!
Note on A4579: Patrick Salifu Status correct, funds returned to ExCom 74
Note on A4594: Florence Asher: Status correct, final payment made March 2011
Note on A4629: Yamar Guisse: Correct!
Note on A4947: Yamar Guisse: Correct!
Note on A5077: Patrick Salifu Status is correct. Project is completed.New IS phase approved at Ex-com 74
Note on A5165: Florence Asher: Status is correct, final payment made in October 2013
Note on A5200: Yamar Guisse: Correct!
Note on A5309: Patrick Salifu: Project finished and all fund disbursed
Note on A5340: Patrick Salifu: Project completed and new IS phase approved at Ex-com 74
Note on A5390: Yamar Guisse: Correct!
Note on A5515: Patrick Salifu: Project finished and all funds disbursed
Note on A5526: Patrick Salifu: Project finished and all funds disbursed
Note on A5554: Yamar Guisse: Project not completed yet
Note on A5575: Patrick Salifu: Project finished and all funds disbursed
Note on A5581: Patrick Salifu: Project finished, all funds disbursed
Note on A5582: Patrick Salifu: Project completed, second tranche approved
Note on A5705: Patrick Salifu: Yes, all funds disbursed
Note on A5706: Patrick Salifu: Yes, all funds disbursed
Note on A5783: Patrick Salifu: Very old project, finished and balance of funds returned to Ex-com 74
Note on A5788: Patrick Salifu: Project finished and all funds disbursed
Note on A5855: Patrick Salifu: Project finished, all funds disbursed
Note on E5187: E: we changed the region as this is in ROA
Note on I5138: Pipat Poopeerasupong: This is correct according to the inventory.
Note on V4172: Asiya.Amin: Note FMO comments in column 'AL'. ROWA adjusted funds in Dec-14 & some balances were returned to ExCom 72 (30,000) & ExCom 73 (20,000) +$105000 moved to HPMP-1
Note on AA4122: Florence Asher: 3rd payment of $32225 was made in 2015
Note on AA4308: Florence Asher: All funds has been disbursed.
Note on AA4309: Florence Asher: 1st payment was disbursed.
Note on AA4595: Florence Asher: 1st and 2nd payments were made. Balance is $27,000
Note on AA5086: Patcharin Udompornwirat: Should be "15,000"
Note on AA5166: Florence Asher: 1st and 2nd payments were disbursed
Note on AA5257: Florence Asher: 1st payment was disbursed.
Note on AA5594: Florence Asher: 1st and 2nd payments were disbursed.
Note on AA5689: Florence Asher: 1st and 2nd payments were disbursed.
Note on AA5777: Patcharin Udompornwirat: Should be 60,000

## Multi-Year
Agency | Country | Sector Plan/National ODS Phase-Out Plan | Date Approved | Date Completed | Planned Date of Completion | Funds Committed by ExCom (US$) | Funds Released including Present Year by ExCom (US$) | Funds Disbursed to the Country (US$) | Total ODP Consumption to be Phase-out for the Plan | ODP Counsumption Allowed for the Reporting Year | Actual ODP Consumption for Reporting Year | Total ODP Production to be Phase-out for the Plan | ODP Production Allowed for the Reporting Year | Actual ODP Production for Reporting Year | Remarks (Achievement of Conditions of Approval, Milestones, Relevant Issues concerning next Targets) | Remarks (Latest information) | Disbursements made to final beneficiaries from FECO/ MEP
Australia | Indonesia | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2016-12-01 | 300000 | 300000 | 0 | 3.03 | [5 empty] | There were delays in signing (due to govt. internal processes) the project document between UNDP and Government of Indonesia and also the agreement between Australia and UNDP. Eventually this documentation was signed in March 2012 and December 2012 respectively. The activities in the UNDP component were prioritized for 2012. The 2012 work plan for the Australian bilateral component was moved to 2013. | During the year 2015, the translation of service training manuals were completed. Regular meetings were held with AMRI on implementation of national regulations prohibiting use of HCFCs in RAC sector. A revised plan of action covering information outreach on R-32 as well as safe use of flammable refrigerants, service technician database development including training materials compilation and dissemination and regulations needed for service sector to ensure proper and safe use of flammable refrigerants was developed. These activities would be implemented during the period 2015-2016.
Canada | Bolivia | ODS Phase Out Plan | 2007-03-01 | 2013-07-01 |  | 162000 | 162000 | 162000 | 0 | 0 | 0 | 0 |  |  | First tranche fully completed. Second tranche nearly completed. Targets met.
Canada | Burkina Faso | CFC Phase Out Plan | 2006-11-01 | 2010-12-01 |  | 165000 | 185000 | 182000 | 7.41 | 0 | 0 | 0 |  |  | Both tranches of project completed and targets met.
Canada | Chile | CFC Phase Out Plan | 2008-07-01 | 2013-03-01 |  | 437500 | 437500 | 437500 | 32.9 | 0 | 0 | 0 |  |  | First tranche completed by March 2012. Second tranche completed in March 2013. Targets met.
Canada | Cuba | ODS Phase Out Plan | 2004-07-01 | 2011-06-01 |  | 462000 | 462000 | 462000 | 30 | 0 | 0 | 0 |  |  | Project completed and relevant targets (for Canada, 2004 and 2005) were met.
Canada | Mexico | Methyl Bromide - Commodities | 2008-04-01 | 2012-03-01 |  | 500000 | 500000 | 500000 | 20 | 795 | 745.4 | 0 |  |  | First tranche target consumption of 795 ODP T for 2009 was met. Targets for later years are not relevant for Canada as they are associated with subsequent tranches of the project to be implemented by other agencies.
Canada | Saint Lucia | CFC Phase Out Plan | 2007-07-01 | 2012-03-01 |  | 205000 | 205000 | 203457 | 1.2 | 0 | 0 | 0 |  |  | Project completed by March 2012 and targets met.
Canada | Uruguay | CFC Phase Out Plan | 2006-11-01 | 2011-12-01 |  | 232000 | 232000 | 232000 | 0 | 0 | 0 | 0 |  |  | Project completed by December 2011 and targets met.
France | Central African Republic | CFC Phase Out Plan | 2008-07-01 | 2011-12-01 |  | 100000 | 100000 | 100000 | 1.3 | 0 | 0 |  |  |  | In 2010, an international consultant was hired, and the equipment was tendered after the approval of the 2nd tranche of the TPMP and a re-scheduling of both tranches together. Equipment was prepared and shipped, and is foreseen to arrive in Bangui during the first quarter of 2011.
France | Cuba | ODS Phase Out Plan | 2004-07-01 |  |  | 80319 | 80319 | 80319 |  | 94.2 |  |  |  |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
France | India | CTC Phase Out Plan | 2004-04-01 | 2009-12-01 |  | 3000000 | 3000000 | 3000000 | 1385 | 708 |  |  |  |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of the activities has been training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
France | Iran | CFC Phase Out Plan - MAC R&R | 2003-12-01 | 2010-06-01 |  | 1506620 | 1358639 | 1358639 | 424.5 | 29.3 | 29.3 |  |  |  | The French contribution is implemented by GIZ-Proklima. Monitoring report was compiled in 2010. The project is completed.
France | Kenya | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2015-10-01 | 900000 | 457500 | 433850 | 11 | 52.2 | 24.7 |  |  |  | The French contribution is implemented by GIZ. The most important task has been to take on suggestions of the verification report from the last tranche and update the enforcement accordingly. This has been managed with some degree of success. As there was also a more aggressive campaign in the media on ODS phase out and enforcement successes, more importers were encouraged to come forward and register with NEMA. However, the country has also seen a dramatic decline in R22 imports largely resulting from reduced economic activity in the country, more old equipment no longer working and the fact that new imported equipment appears to be non R22 based, i.e. car ACs with HFOs are in the market creating a completely new set of problems due to lack of knowhow. A refrigeration association has been set up to assist the project to promote better service practices and to encourage industry to participate in the trainings organised through the project. | A verification report was completed allowing for the submission of the next tranche request to the 75th ExCom. Efforts are been made to see how to involve the Association more actively in the project, and especially in relation to the certification and registration of technicians. Meanwhile technican trainings are ongoing and 4 of them have already been completed in 2015.
France | Kenya | CFC Phase Out Plan | 2004-12-01 | 2012-03-01 |  | 725000 | 692000 | 553967 | 138.8 | 0 | 0 |  |  |  | The French contribution is implemented by GTZ-Proklima. The project is completed.
France | Lao, DPR | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2013-03-01 |  | 33750 | 0 |  | 0.1 | [5 empty] | See condition of disbursement.
France | Lao, DPR | CFC Phase Out Plan | 2008-04-01 | 2013-04-01 |  | 320000 | 320000 | 320000 | 6.5 | 6.5 |  |  |  |  | In addition to previous training session, a ftraining on Good Practices in refrigerant Management and Pilot Retrofit Incentive Programme to HFC-134a System in Domestic Refrigeration, Commercial Refrigeration and MAC was also organized in Khammouane Province for the central and southern provinces in June 2011. Furthermore, with respect to the Regulations enforcement and update, a national workshop was organized in Febuary 2011 for 95 participants of Lao PDR authorities of central and provincial levels to work on the review of the Ministerial Decision on the Control of the Import-Export licensing system of the ODS in Lao PDR. A training on transit control and an annual refreshment training of custom's officers on ODS licensing system was also carried out in October 2011.
France | Seychelles | CFC Phase Out Plan | 2007-03-01 | 2010-12-01 |  | 193000 | 193000 | 139879 | 1.4 | 0 | 0 |  |  |  | The French contribution was implemented by GTZ-Proklima. The project is completed.
France | Tunisia | HCFC Phase Out Plan (Stage I) | 2014-05-01 |  | 2017-05-01 | 600000 | 135690 | 0 | 3.53 | [5 empty] | The French contribution is implemented in cooperation with UNIDO. HPMP is implemented as planned, no issues. 2014 consumption target achieved. Detailed information is provided for each component in the Database.
France | Uganda | ODS Phase Out Plan | 2008-07-01 | 2011-04-01 |  | 215000 | 215000 | 209429 | 1.9 | 0 | 0 |  |  |  | The French contribution was implemented by GTZ-Proklima. The project is completed.
Germany | Afghanistan | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 280276 | 169000 | 27517 | 3.44 | 3.4 | 3.4 |  |  |  | In 2014 the beneficiary for conversion Qasr Yakh was reassessed. Due to the fact that there was no consumption and the company was not operating HPMP activities were changed. In agreement with MLFS the budget was shifted to the reclamation and recycling component. In October a mission of UNEP and GIZ to Kabul was organised. Various potential beneficiaries such as supermarkets, workshops and vocational training centers were visited. Due to safety conditions in the country the mission was undertaken by GIZ national staff from Iran. The conitinous safety concerns repetedly led to the consideration of transferring the project to an IA. | Discussions about project transfer were held with the NOU latest at the 35 OEWG in Paris.
Germany | Afghanistan | ODS Phase Out Plan | 2005-11-01 | 2009-12-01 |  | 760806 | 760806 | 760806 | 179.82 | 179.82 | 179.8 |  |  |  | M-Y-A plan completed
Germany | Bolivia | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 315000 | 189000 | 94500 | 2.13 | 1.7 | 1.7 |  |  |  | implementation of train the trainer and RAC training as well as dissemination activities. | Project has been tranferred to UNIDO at 74th ExCom
Germany | Botswana | CFC Phase Out Plan | 2009-04-01 | 2011-11-01 |  | 205000 | 205000 | 205000 | 1 | 0 | 0 |  |  |  | The NOU requested 10 additional identifiers for the customs dept. These identifiers were then provided to the various border posts and the bureau of standards. 3 customs trainings were conducted at remote border posts. Project was successfully completed with all CFCs being phased out.
Germany | Brazil | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2015-12-01 | 4090909 | 3681818 | 1903860 | 45.99 | 46 | 46 |  |  |  | Project Delay, 5 train-the-trainer courses carried out and 56 instructors trained, 776 technicians in commercial refrigeration trained, demonstration tools purchased, case studies for demo projects selected, identification, measurement and performance analysis equipment for refrigeration systems puchased, technical analysis of first case study conducted, adaptation of online documentation system & planning of the introductory workshop, technical publications and best practice guidelines prepared | 1616 technicians trainined in better containment of HCFCs in supermarket installations, 76 technicians trained in best practices and better containment of HCFCs in split air conditioners, additional training institution hired, technical analysis of second supermarket conducted, test phase of online doc system
Germany | Brazil | CFC Phase Out Plan | 2002-07-01 | 2011-12-01 |  | 3883600 | 3883600 | 3883600 |  | 0 | 0 |  |  |  | M-Y-A plan completed
Germany | China | HCFC Phase Out Plan (Stage I) - XPS Foam | 2011-07-01 |  | 2015-12-01 | 1350000 | 850000 | 850000 | 12.14 | 16.9 | 16.9 |  |  |  | Interagency meetings were held in July 2014 and September 2014 -, alll companies to be converted have been visited -discussions with UNEP on servicing sector were held - decisions were made | TORS auditing and whitebook in China in preparation -TORs were verified and XPS standards prepared
Germany | Cuba | ODS Phase Out Plan | 2004-07-01 |  |  | 43453 | 43453 | 43453 |  | 0 | 0 |  |  |  | Cuba requested the change of implementation agencies. The transfer to UNDP is completed.
Germany | India | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2015-12-01 | 1994400 | 1794960 | 1020978 | 32.01 | [5 empty] | 1. RAC Technicians Training in Installation & Servicing Room Air conditioners up to 2 ton in progress. 2. Training of Trainers (ToT) condcuted. 3. Contact established / initiated and meetings done with Instituional users - Defence and Railways for conducting training for their RAC technical staff. 4. One training for Defence - Technical staff conducted in Secunderabad. 5. Discussions with Reclamation Centre entreprenuers and preparing of action plan . 6. Discussions and proposal to DGET for Training RAC Trainers and syllabus revision. 7. IA and Core Group Meetings. 8. Planning and Co-ordination with the consultants and training partners in the field on a ongoing process. 9. Capacity building for Training Partners. 10. PMU - Servicing Sector - management ongoing, coordination with UNEP ongoing. 11. Participation and Presentation at Awareness Workshops | Activites to be completed - 1. Capacity building for Training Partners, 2. Insitutional training Railways and Defence RAC Techncial Staff 3. Training of RAC Teaching staff from ITI - that will require close follow up with DGET 4. Impact Monitoring - this activity will be completed early 2016 5. PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing. 6. Participation and Presentation at Awareness Workshops
Germany | India | CFC Phase Out Plan - Refrigeration Servicing | 2004-04-01 | 2009-12-01 |  | 2415260 | 1156738 | 1156738 | 316 | 59.1 | 59.1 |  |  |  | All project activities have been completed.
Germany | India | CTC Phase Out Plan | 2004-04-01 | 2010-12-01 |  | 2000000 | 2000000 | 2000000 | 970 | 268 |  |  |  |  | The environment, health and safety material has been completed and capacity building with institutional stakeholders from the power sector has taken place. All project activities have been completed now.
Germany | Iran | CFC Phase Out Plan - Foam, MAC Training, Management | 2003-12-01 | 2011-12-01 |  | 5289619 | 5289619 | 5289619 | 608.4 | 608.4 | 608.4 |  |  |  | M-Y-A plan completed
Germany | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-12-01 | 2885815 | 2885815 | 2104620 | 46.42 | 28.6 | 28.6 |  |  |  | Continuous Project Delay - follow up installation Karamadan - beneficiary USC opted out of conversion scheme and was replaced by the beneficiary Pakran, in agreement with MLFS - preparation of techical specification for tendering Arya Baron - technical assistance to the installation procedures | Final acceptance of equipment installation partially completed - all tendering finished, supply of equipment for Pakran and Elektrosteel Arya Baron planned for October 2015 - preparation of technical specifications for Behdor Rangin - Editing of Iranian Cold Chain Study - follow up of converted supermarket (monitoring, leakage controll etc.)
Germany | Kenya | Methyl Bromide - Horticulture | 2003-04-01 | 2010-01-01 |  | 574492 | 574492 | 574492 | 34 | 29 | 17.4 |  |  |  | The Project has been completed. PCR submitted in September 2010
Germany | Lesotho | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 280000 | 168000 | 100000 | 1.4 | 3.9 | 1.14 |  |  |  | Lesotho has already been phasing out HCFC use faster than what was included in the HPMP. R&AC centres have included best practices and safe handling of HCs in their curriculum. | NOU spent the early part of the ensuring enforcement of the licensing and the quota system for the imports of ODS for the year 2015. Currently the NOU is planning a stakeholder worksop to discuss the future activities under the HPMP, the results of the verification report and ensure that stakeholders are involved especially in the planned registration of technicians.
Germany | Lesotho | CFC Phase Out Plan | 2003-12-01 | 2009-11-01 |  | 127300 | 127300 | 127300 | 2.6 | 0.4 | 0 |  |  |  | Project has been completed final report being prepared. Lesotho achieved complete CFC phase out as per the Agreement with the Excom.
Germany | Liberia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 315000 | 283500 | 140504 | 1.93 | 5.5 | 3.74 |  |  |  | Liberia experienced a slowing down of activities due to the outbreak of Ebola for most of 2014. However, the country conducted 2 technician trainings and did distribute 7 recovery units among the local Association for use among the industry. The ebola did make it very difficult for imports and controls but customs did capture the relevant HCFC imports which have been reported and do show a continued decline in use of HCFCs. | Liberia was just becoming normal after Ebola when the NOU passed away suddenly. This has once again delayed implementation of activities however currently planned demonstration of 15 AC from R22 to R290 are being done where the Refrigeration Associatio is using these demonstration to develop a code of practice for the industry to undertake safe conversions.
Germany | Mauritius | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2025-12-01 | 950000 | 288450 | 266532 | 8 | 10.2 | 7.93 |  |  |  | Mauritius is the only known country that has a specially constructed training unit which is a cascade system for supermarkets running on ammonia and Co2. The local curriculum has been adapted to include natural refrigerants as component of the training offered to students attending the local universities. | Training of trainers conducted for 15 participants on the new cascade system.
Germany | Mauritius | ODS Phase Out Plan | 2003-12-01 | 2010-12-01 |  | 212030 | 212030 | 212030 | 4 | 1 | 0.2 |  |  |  | Project has been completed.
Germany | Mexico | HCFC Phase Out Plan (Stage II) | 2014-11-01 |  | Dec-16 | 650000 | 325000 | 0 | 31.28 | [5 empty] | In 2014 no activities have been implemented yet.
Germany | Namibia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 900000 | 540000 | 270791 | 8.4 | 4.85 | 3.64 |  |  |  | Namibia has expericened several changes in personnel at the ozone office but despite that the trainers of the country have managed to continue conducting trainings and keeping the activities moving forward based on the needs of the industry. Trainings are being conducted mostly at own costs of the participants with project covering only costs of consummables and advertising of the course which has been a positive development. The Industry acknowledges the usefullness of the course on best pratices and safe handling. | Technician trainings are ongoing in the country with industry contribution for the subsidised courses. Additionally 30 conversions of R22 Ac to R290 are being done on demonstration basis through out the country to highlight safe handling and energy efficiency of alternative natural refrigerants.
Germany | Namibia | CFC Phase Out Plan | 2003-12-01 | 2010-12-01 |  | 252500 | 252500 | 252500 | 12 | 5 | 0 |  |  |  | Project has been completed.
Germany | Papua New Guinea | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2025-12-01 | 1250000 | 690000 | 315133 | 3.4 | 3.08 | 2.7 |  |  |  | The licensing and quota system has been working effectively with imports being well restricted to below max allowable limits established in the HPMP agreement. Efforts are also underway to include import license permits also for HFCs which so far have been without a fee payment. Additionally PNG has conducted technician trainings where 39 technicians have participated. Industry trainers are being encouraged to also assist as part time trainers for the courses to bring about more hands on trainings. | New ozone officer was hired to start in Jan 2015. Cooperation with the climate division has been initiated with several joint meetings already taken place for more concerted efforts to assist PNG meet its carbon neutrality goals which are also part of the HPMP. Painting competition for school kids has just been completed as part of awareness activities
Germany | Papua New Guinea | CFC Phase Out Plan | 2003-04-01 | 2010-12-01 |  | 700000 | 700000 | 700000 | 35 | 8 | 2.2 |  |  |  | Project completed
Germany | Seychelles | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 600000 | 360000 | 237915 | 1.4 | 0.7 | 0.43 |  |  |  | Seychelles hired an energy expert to determine the precise requirements of Solar PVs for the University to run R290 ACs independent off the grid. Best practice trainings were done where the HFC phase out was an essential component. Seychelles reduction on HCFC use continues well ahead of the planned schedule of the HPMP. | A monitoring officer has been hired since Jan to assist the NOU to implement the HPMP activities which have stalled over sometime. Customs trainings have been conducted and tender for supply of Solar PVs published and order to purchase will take place in few days.
Germany | Yemen | Methyl Bromide | 2008-11-01 |  | 2015-02-01 | 601450 | 601450 | 599450 | 35.9 | 0 | 0 |  |  |  | The most important achievements within the reporting year 2014 can be briefed as follows: In according to agreement with Yemen Nabat for Agriculture & Development (Y.Nabat) two agricultural engineers were trained on grafting in Jordan, a modern grafting machine was imported and Y. Nabat nurseries started grown grafted nurses. On-farm training workshop on solarization, biofumigation, grafting, soilless as MBr alternatives for 32 participants was convened at the farm of Y.Nabat in Dhamar. In addition to fifteen-onsite trainings on biofumigation by radish seeds were implemented in Sadah, Dhamar, Al-Mahweet, Amran and Sana'a. Two training sessions covered by Alsaedah TV. 265 plastic sheets were distributed for eligible farmers to encourage using solarization and biofumigation technologies at 265 farms. Morover, 30 farmers received radish seeds in order to use it in combination with solarization in cold areas in Yemen. 102 farmers and 15 extentionists in several governorates trained on biofumigation, 6 farmers in Amran Governorate trained on soilless and five women trained at Sana'a & 2 agricultural engineers trained in Jordan on grafting technology. Methyl bromide consumption phase-out that achieved in 2014 was approximately 11 ODP tones. However, for meeting the 2015 control measures of the Montreal Protocol, necessary measures and procedures for amending "Cabinet Decree # (275) on controlling of ODSs" were followed in order to accommodate banning on MBr Importation. Consequently, Decree of Environment Protection Authority # (63) was issued on December 23, 2014. The Decree amendment prohibited the importation of methyl bromide for soil fumigation by January 1st, 2015. Furthermore, the Decree immediately circulated officially to the related institutions such as the Cabinet, Custom Authority, Yemen Standardization, Metrology, & Quality Control Organization, Ministry of Agriculture, Ministry of Finance, Ministry of Water and Environment, Ministry of Industry & Trade and Plant Protection. | Since the project started until 28th of February 2015, one thousand four hundred and fifteen farmers and 70 Extentionists & Engineers were trained and 602 farms received materials of Solarization and Biofumigation technologies. A total reduction of 35.9 ODP tonnes of MB was achieved by the end of 2014 (Consumption of 2007 was 35.85ODP and of 2014 was 00.0 ODP). Commercial production of grafted nurses is expected to take place in second half of 2015.
Germany | Zimbabwe | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 1038818 | 702818 | 682521 | 12.34 | 15.44 | 13.32 |  |  |  | The project is a combination of a conversion project for the foam sector and a servicing sector component. Under the foam project, the installation and comissionig of the equipment was completed and necessary training and skills provided to engineers from all the companies locally using R141b. Under the R&AC sector recovery units have been distributed against a fee paid by the beneficiary. This fee was then used by the NOU to conducting monitoring and follow ups of the companies. | The foam project is expected to be completed by end of 2015. The R&AC sector will aim to assiting industry through the recovery untis and tools to reduce dependence on HCFCs.
Germany | Zimbabwe | CFC Phase Out Plan | 2007-03-01 | 2009-03-01 |  | 565000 | 565000 | 565000 | 65 | 65 | 53.3 |  |  |  | project completed
IBRD | Antigua Barbuda | CFC phase-out management plan | 2004-12-02 | 2011-12-01 |  | 97300 | 97300 | 62987 | 1.8 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Argentina | HCFC phase-out management plan (stage I, first tranche) | 2012-04-01 |  | 2017-04-01 | 914612 | 914612 | 385000 | 18.46 | 0 | 0 | 0 | 0 | 0 | During 2014, actual project execution remained pending as the GoA countersigned the HCFC Project's Grant Agreement (GA) for Ministry of Industry only on Dec. 19, 2014. Mabe has proceeded with implementation despite the lack of effectiveness of the overall Grant Agreement (GA) as of the end of 2014. Conversion completed and phase-out achieved. Enterprise will be compensated retroactively. During 2014, UEPRO continued carrying out office-based monitoring and reporting of national HCFC-22 production, based on production and input information provided by the only producer, FIASA S.A. UEPRO has shared the complete 2014 monitoring reports with the NOU and WBG, stating the FIASA S.A. being in compliance with its production limits set out in the HPMP. | The HCFC Project with the Ministry of Industry became effective on Jan. 30, 2015. However, no further advance has been reached as the Minister of Industry has not signed the decree that reestablishes the PCU after the CFC project closed execution on Dec. 30, 2014, and the grace period on Apr. 30, 2015. WB conducted a supervision mission in May 2015 in order to prompt project operalization and carry out a technical verification visit to the Mabe plant in San Luis to verify completion. Phaseout achieved. The Ministry of Industry was given until Jun. 30, 2015 to reestablish the PCU. PCU was reconstituted when the Ministry of Industry signed the required resolution on June 19, 2015. Since then, the PCU has been proceeding promptly with the necessary next steps to get the Project fully operational. The subgrant agreement was signed on July 7, 2015 with Mabe which has now completed conversion.
IBRD | Argentina | CFC production closure plan | 2002-11-02 | 2009-12-01 |  | 10600000 | 10600000 | 10600000 | 0 | 0 | 0 | 3020 | 0 | 0 | Project completed.
IBRD | Argentina | National CFC phase-out plan | 2005-11-02 | 2013-12-01 |  | 500000 | 500000 | 236630.4 | 1.5 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Bahamas | Terminal CFC Phaseout Plan for The Bahamas | 2001-12-01 | 2009-01-01 |  | 560000 | 560000 | 530946 | 66 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Chile | Phase-out of all the remaining uses of methyl bromide in soil application pest control | 2005-04-01 |  |  | 2547156 | 691703 | 0 | 136.3 | 0 | 0 | 0 | 0 | 0 | Project cancelled Jul 06.
IBRD | China | HCFC phase-out management plan (polyurethane rigid foam sector plan) (stage I) | 2011-07-02 |  | 2016-12-01 | 73000000 | 62050000 | 42299200 | 1615 | 5392.2 | n/a | 0 | 0 | 0 | 23 additional subgrants were signed in 2014 making total commitment $61.263 million with 12,762.95 MT of HCFC-141b to be phased out. In addition to 9 subprojects completed in 2013, 2 additional subprojects from tranche 2 were completed in 2014. Cumulative disbursement reached $16,857,839 at end of 2014. In addition, 5 system house conversion agreements were signed with committed funding of $1.75 million. | 2 system house conversion agreements were signed during the first half of 2015. It is expected that 7 additional subprojects will be completed in 2015 with a total HCFC consumption reduction of 100 ODP tons. No additional subgrants will be signed as the total resources have been committed to conversion. Unallocated funds are for TA and the PMU. | 16857839.45
IBRD | China | HCFC production phase-out management plan (stage I) | 2013-04-02 |  | 2017-07-02 | 95000000 | 71000000 | 30900000 | 0 | 0 | 0 | 3970 | 29122 | 27198.4 | From the 2013 tranche, FECO disbursed all payments for the 12 quota reduction contracts with a total value of $10.427 million. Remaining balance of 2013 tranche was used to pay against production line closure contracts for the 10% reduction target of 2015 and TA activities under the annual program. 2014 annual program and tranche approved in May 2014. Production quotas for 2014 were issued. To meet 10% reduction target for 2015, FECO signed production line closure contracts with 5 producers to phase-out 58,864 MT production quota of HCFCs (33,237 MT of HCFC-22 and 25,627 MT of HCFC-141b) with a total contract amount of $75,072,962 in Nov 2014. A total of 88,000 MT (43,000 MT of HCFC-22 and 45,000 MT of HCFC-141b) HCFC production capacity to be closed and dismantled. 2014 unaudited production figure indicates that China has met its target (2014 production verification report will be submitted to the 75th ExCom). | 2014 production data reported by producers showing that production contract targets were met. Production quotas for 2015 were issued. All environment mgmt. plans (EMPs) for dismantling closure production lines prepared by enterprises and reviewed and approved by WB. Four of 5 closed production lines have been dismantled; the other will be dismantled in Jun 15. | 30893828.28
IBRD | China | Foam Sector | 2001-12-01 | 2010-12-01 |  | 53846000 | 53846000 | 53846000 | 14143 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | China | Halon Sector | 1997-11-01 | 2011-12-01 |  | 62000000 | 62000000 | 62000000 | 24480 | 0 | 0 | 30060 | 0 | 0 | Project completed. Sector plan financially closed as June 30, 2013.
IBRD | China | CTC/PA Sector Phase I | 2002-11-02 | 2011-12-01 |  | 65000000 | 65000000 | 65000000 | 11160.2 | 0 | 0 | 52162 | 0 | 0 | CTC/PA Sector Phase I completed..
IBRD | China | CTC/PA Sector Phase II | 2005-11-02 | 2010-07-31 |  | 46500000 | 46500000 | 46500000 | 6945 | 0 | 0 | 0 | 0 | 0 | CTC/PA Sector Phase II completed..
IBRD | China | CFC Production Sector | 1999-03-01 | 2010-12-01 |  | 150000000 | 150000000 | 150000000 | 0 | 0 | 0 | 44931 | 0 | 0 | Project completed. Verification report (CPR/PRO/69/TAS/531) submitted to the 71st ExCom Meeting as planned and was considered by the Subgroup on the Production Sector.
IBRD | China | TCA Sector | 2004-07-01 | 2010-11-01 |  | 2100000 | 2100000 | 2100000 | 0 | 0 | 0 | 113 | 0 | 0 | TCA sector plan completed.
IBRD | Ecuador | National CFC phase-out plan | 2003-12-02 | 2009-09-01 |  | 1194471 | 1194471 | 1194471 | 246 | 0 | 0 | 0 | 0 | 0 | Project completed. Original ExCom approval and funds released amount to US$1,689,800. Upon closing, balance of $495,329 was returned to the MLF at the 62nd ExCom Meeting.
IBRD | India | Accelerated CFC Production Phase-out | 2008-01-04 | 2014-03-31 |  | 3169900 | 3169900 | 3169900 | 0 | 0 | 0 | 690 | 0 | 0 | Funds fully disbursed to the financial intermediary in the country but could not be released to the beneficiaries before project closing date. | Financial completion pending return of unreleased funds to the WB from the financial intermediary in India.
IBRD | India | CFC production sector gradual phase-out project | 1999-11-01 | 2011-11-01 |  | 82000000 | 82000000 | 82000000 | 0 | 0 | 0 | 22588 | 0 | 0 | CFC production sector plan is now completed physically and financially.
IBRD | India | CTC phase-out plan for the consumption and production sectors | 2003-07-01 | 2014-03-31 |  | 38100954 | 38100954 | 37629080 | 7537 | 0 | 0 | 11206 | 0 | 0 | Funds disbursed to the financial intermediary but could not be fully released to the PMU before project closing date. | Financial completion pending return of unreleased funds to the WB from the financial intermediary in India.
IBRD | Indonesia | HCFC Phase Out Plan (Stage I): Foam Sector Plan | 2011-07-02 |  | 2017-12-01 | 2714187 | 2442767 | 1640400 | 34.1 | n/a | n/a | 0 | 0 | 0 | By end 2014, 8 companies signed subgrant agreements (SGAs). Disbursements to two large foam producers that completed subprojects in 2014 (PT. Maspion, PT. Top Jaya) was made for a total phase-out of 15.3 ODP tons. Other companies were considering their options as contract preparation continued. Import quota system is being applied and a ban on HCFC use in the foam sector is in place. NOU held 2 workshops in 2014. NOU had some administrative difficulties with hiring of project/PMU consultants, mainly due to a new government procurement system and centralization of procurement. | Three companies have now completed conversion for a total phase-out of their average 2009/10 HCFC-141b use of 5.7 ODP tons and 3 other companies are finalizing their conversion. Other foam producers are still undecided. The NOU is planning to redirect freed-up funds to support the work of any domestic foam system houses on the formulation of HCFC substitutes. Import quota system continues to be applied and a ban on HCFC use in the foam sector is in place. The NOU continues with TA but its work, including staffing-up of the PMU, has been further hampered by national elections and the government transition process, including a merger between the Ministries of Environment and Forestry.
IBRD | Indonesia | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | 2004-12-31 | 2010-06-01 |  | 371910 | 371910 | 371910 | 70 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Indonesia | Phase-out of residual CFCs in the foam sector | 2004-04-01 | 2010-06-01 |  | 2957564 | 2957564 | 2957564 | 352 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Indonesia | Refrigeration sector phase-out plan: MAC servicing sector | 2002-11-02 | 2010-03-01 |  | 4317000 | 4317000 | 4317000 | 915 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Jordan | HCFC Phase Out Plan (Stage I): Air-conditioning Sector Plan | 2011-11-02 |  | 2017-11-01 | 2341150 | 1070100 | 132444.84 | 16.78 | n/a | n/a | 0 | 0 | 0 | GA signed by GoJ and WB May 13. Disbursement under the AC Sector Plan started in Jan 14 to retroactively finance project management expenditures incurred the previous year. Two subgrant agreements (SGAs) for 2 of 3 enterprises signed Feb and Sep 2014. Equipment procurement underway. Third SGA delayed because enterprise is experiencing financial difficulties. NOU/WB agreed with MEC on milestones for submitting a business plan and other documents to prove viability. Project completion date is not expected to be adversely affected. | 2013-2014 consumption verification completed under UNIDO as lead IA. Abu Haltam's equipment package is being shipped; NRC opened bids in May 15 and has selected the equipment supplier. Conditions for MEC's participation in the project set in May but not met by end of Jun 15. Subproject will be cancelled.
IBRD | Malaysia | National CFC phaseout plan | 2001-12-01 | 2010-12-01 |  | 11517005 | 11517005 | 11441013 | 1910.51 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Mexico | National CFC phase-out plan: Chiller Subsector | 2005-04-01 | 2006-02-01 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed.
IBRD | Philippines | National CFC phase out plan | 2002-11-01 | 2011-06-01 |  | 8381671 | 8381671 | 8381671 | 2017.6 | 0 | 0 | 0 | 0 | 0 | Original ExCom approval and funds released amount to US$10,216,876. Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP continued as IA for remaining NCPP servicing sector component.
IBRD | Thailand | HCFC phase-out management plan (stage I, first tranche) | 2012-12-01 |  | 2018-12-01 | 22749072 | 4817166 | 0 | 219.54 | 927.6 | 864.3 | 0 | 0 | 0 | Appraisal completed in Jan. 2014. Grant agreement (GA) negotiation completed in Feb. 14 and GA sent for counter-signing in Apr. 14. However, due to the political situation, GA signing was delayed until Nov. 14. Two PMUs established in DIW and GSB in Jan and Aug. 14 respectively. Project implementation manual prepared. 12 environment management plans completed for AC enterprises, and 1 environmental framework done for foam beneficiaries. Three subgrant agreements (SGAs) signed Nov. 14 w/AC manufacturers and 1 SGA signed in Dec. 14 w/a foam enterprise. Thru TA component and with counterpart funding, a risk assessment was done on R-32 leading to revision of a standard for use of R-32 AC in tall buildings and quota allocation meetings conducted. A tech use agreement was negotiated between Thai AC enterprises and Daikin, facilitated by GoT and WB. A study tour for Thai AC industry to Japan done Nov 14 to learn about risk assessment from Daikin. Due to GA signing delay, all expenditures incurred in 2014 will be retroactively reimbursed in 2015. | Since Jan. 2015, 3 more SGAs signed w/AC manufacturers and 3 w/foam enterprises worth a total US$4.2 million. Executing agency GSB disbursed $1,104,883 to these 10 enterprises as of 23 Mar. 15. Four out of 5 remaining a/c manufacturers will sign SGAs by end 2015. One foam enterprise will sign an SGA Jul 15. There are 6 additional foam proposals in the pipeline; 10 additional enterprises expressed interest to participate. By end 2015 at least 6 more foam SGAs will be signed. For smaller firms, DIW will invite expression of interest by Sep 15. Modalities to channel technical and financial assistance to these SMEs will be agreed prior to Jan 16. By end of 2015, all 5 foam enterprises with SGAs signed before Aug 15 will have completed conversion. GSB PMU fully staffed. One technical consultant appointed in DIW PMU. Additional staff under recruitment. 2nd tranche request submitted to 74th ExCom and approved, however funds have not been released as of July 2015 due to the pending consumption verification report.
IBRD | Thailand | National methyl bromide phase-out plan | 2004-12-01 | 2013-12-01 |  | 2901600 | 2901600 | 1668733.15 | 241.8 | 0 | 0 | 0 | 0 | 0 | Project completed. US$1,232,867 in NMBPP savings returned to the MLF ExCom in 2014.
IBRD | Thailand | National CFC phaseout plan | 2001-12-01 | 2013-12-01 |  | 14728626 | 14728626 | 12638243 | 3107.52 | 0 | 0 | 0 | 0 | 0 | Project completed. US$2,090,383 in NCPP savings returned to the MLF ExCom in 2014.
IBRD | Tunisia | National ODS phase-out plan | 2006-07-01 | 2012-06-01 |  | 429877 | 429877 | 429877 | 342 | 0 | 0 | 0 | 0 | 0 | Umbrella project closed in June 2012. Original ExCom approval and funds released amount to US$1,135,395. Balance of NOPP funds transferred to UNIDO at the 68th Meeting of the ExCom.
IBRD | Turkey | CFC Phase-out plan for Turkey | 2001-12-01 | 2008-04-01 |  | 9000000 | 9000000 | 8565903.15 | 977 | 0 | 0 | 0 | 0 | 0 | Refrigeration Sector Project (RSP) and overall ODS umbrella project with the World Bank physically and financially completed.
IBRD | Venezuela | Phased reduction and closure of the entire CFC production | 2004-12-02 | 2009-11-01 |  | 16500000 | 16500000 | 16500000 | 0 | 0 | 0 | 4400 | 0 | 0 | Project completed.
IBRD | Vietnam | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | 2011-04-02 |  | 2016-12-02 | 9763820 | 8717439 | 3485869 | 140.1 | 221.2 | 210.823 | 0 | 0 | 0 | HCFC import quota issued for 2014. First subproject out of 12 completed May 13; another 3 completed in Aug, Sep, and Dec 14. Four enterprises are in various stages of conversion. 3 additional enterprises signed subgrant agreements by end of Dec. 14; 1 of which already started equipment procurement. 5 subprojects delayed in reporting year due to insufficient capital (3), relocation (1), or decision not to participate (1). PMU/WB modified payment method to facilitate equipment purchase. Another eligible enterprise will participate. None of these delays are expected to affect planned HPMP completion. 3 customs training workshops and 4 technical training workshops for industry held in 2014. Ban on HCFC-141b imports as of Jan. 1, 2015 put into place Dec 14. All tranche funds disbursed by Dec. 14. | HCFC import quota issued for 2015. One subproject completed in Jan 2015. Three foam companies entered into equipment contracts in Jan and Feb 2015 and are expected to complete subprojects by Sep 15. A total of 6 subprojects are ongoing, 5 completed and 1 to be appraised. No bulk HCFC-141b has or will be imported in 2015.
IBRD | Vietnam | National phase-out plan for methyl bromide | 2006-11-01 | 2014-12-01 |  | 1098284 | 1098284 | 1098284 | 85.2 | 35 | 25.863 | 0 | 0 | 0 | Project completed.
IBRD | Vietnam | National CFC and halon phase-out plan | 2005-04-01 | 2010-12-01 |  | 1260000 | 1260000 | 1259448 | 258.69 | 0 | 0 | 0 | 0 | 0 | Project completed.
Italy | Argentina | HCFC Phase Out Plan (Stage I) | 2010-07-01 |  | 2014-07-01 | 300000 | 300000 | 122008 |  | 0 | 0 |  |  |  | IOC payment completed. - The consumption of HCFC-22 was completely phased out. - Technical problems with some items supplied by Agramkow were solved. - The last company pending to install the equipment started the civil work at its premises. | UNIDO followed up with the supplier and the beneficiary company for the installation. - It is expected that the installation will be completed by end of August 2015.
Italy | China | Domestic Refrigeration | 2002-11-01 | 2005-10-01 |  | 1788991 | 1788991 | 1788991 | 181 | 0 | 0 |  |  |  | FIN
Italy | China | Methyl Bromide | 2005-07-01 | 2009-12-01 |  | 4000000 | 4000000 | 4000000 | 534 | 390 | 390 |  |  |  | FIN
Italy | Croatia | HCFC Phase Out Plan (Stage I) | 2010-07-01 | 2013-12-01 |  | 210000 | 210000 | 202545 | 1.7 | 1.7 | 1.7 |  |  |  | FIN
Italy | Ghana | HCFC Phase Out Plan (Stage I) | 2010-07-01 |  | 2020-12-01 | 325000 | 200000 | 128673 | 6.29 | 57.3 | 23.34 |  | 0 | 0 | On track with MP requirements. | Legislative consultant is under contract (ongoing); customs identifiers procurement under way; procurement of reclaim equipement in preparation, as well as refrigeration training programme in relation to this equipement. Support and monitoring by international consultant is ongoing.
Italy | Mexico | HCFC Phase Out Plan (Stage II) | 2014-11-01 |  |  | 458191 | 458191 |  | 22.05 | [5 empty] | PAD initiated and project is progressing as scheduled.
Italy | Mexico | Methyl Bromide - Soil Fumigation | 2008-04-01 | 2012-11-01 |  | 1000000 | 1000000 | 993996 | 70 | 0 | 0 |  |  |  | FIN
Italy | Morocco | Methyl Bromide - Green Beans and Melon | 2008-11-01 | 2014-12-01 |  | 310000 | 310000 | 306267 |  | 260.9 | 260.9 |  |  |  | Project completed in Dec 2014.
Italy | Senegal | CFC Phase Out Plan | 2007-07-01 | 2012-12-01 |  | 355000 | 355000 | 350406 | 23.4 | 26.1 |  |  |  |  | FIN
Japan | China | HCFC Phase Out Plan (Stage I) - Servicing Sector, including enabling | 2011-07-01 |  | 2015-12-01 | 400000 | 240000 | 160000 | 3.6 | [6 empty] | The implementation in this sector is being done by the sector lead agency, UNEP. Refer to UNEP's progress report for details including disbursement status.
Japan | China | Refrigeration Servicing | 2004-12-01 | 2012-12-01 |  | 4000000 | 4000000 | 3998420 | 511 | 3790 |  |  |  |  | Financial completion in Dec 2014. Refund was reported to 74th ExCom, May 2015. FIN.
Japan | India | CTC Phase Out Plan | 2004-04-01 |  | 2014-12-01 | 5000000 | 5000000 | 3381149 | 533 | 1726 |  |  | 1726
Japan | Mongolia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 130000 | 130000 | 100000 | 0.36 | [6 empty] | MOU signed with XPS compaines in 2012 and HCFC-22 is no longer used by XPS compaines as of July 2013, but XPS companies are still looking for a suitable alternative technology.
Japan | Mongolia (2) | CFC Phase Out Plan | 2005-11-01 | 2010-12-01 |  | 205000 | 205000 | 205000 | 3.3 | 0 | 0 |  |  |  | Completed. PCR already submitted.
Japan | Philipinnes | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2015-12-01 | 317350 | 317350 | 123601 | [6 empty] | - 10 companies with fixed foaming equipment received assistance to convert their technologies. Installation was finalized at 8 beneficiaries (MLF component). - On spray foam sector, last tests on spray foam applications took place (Japanese component) and material for the dissemination of project results was drafted. UNIDO discussed with beneficiaries and the NOU to finalize the scope of supply for those 8 eligible beneficiaries. | - 9 companies with fixed foaming equipment successfully completed the conversion of their manufacturing technologies. UNIDO completed the certification of destruction of baseline equipment in July 2015. The equipment delivered to Blutherm was confiscated and sold back to technology provider. The money recovered will be transferred back to the MLF at project closure (MLF component). - On spray foam sector (Japanese component), UNIDO started procuring agreed items to finalize the assistance to eligible 8 eligible beneficiaries. A technical brochure resulted from the tests in the spray foam activities was launched.
Japan | Saudi Arabia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-06-01 | 220000 | 220000 |  | 7.1 | [5 empty] | Arabian Chemical company: The Purchase Order for the equipment has been issued in January 2014 and equipment has been delivered to the project site in January 2015. The company had to conduct an engineering study for the erection of the new production facilities which was completed in October. The erection of the new facility was completed in December 2014. Al Watania: The Invitation to Bidding was published in April 2014. Offers from two qualified suppliers were received in June 2014. The technical and financial evaluation was conducted in July/August 2014 and the best technically acceptable offer was selected in September 2014. Negotiations about the contract with UNIDO Procurement Service and the supplier about details in the contract (acceptance of payment schedule,TUV certification of the equipment, change of the supplier company) extended into 2015. | Arabian Chemical Company: Installation, start-up and commissioning was completed in March 2015 and confirmed by the Certificate of Acceptance. Al Watania: The contract to the selected supplier was issued in February 2015. Technical meeting at Al-Watania was organized in June 2015.
Japan | Thailand | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2018-12-01 | 302965 | 302965 |  | 15.19 | [6 empty] | The main reason for the delay was politic situation in the country. Grant Agreement has been ready for counter signing by Government of Thai. Kickoff will be held in September 2014. Total funding including support costs have been transferred to the World Bank. Disbursement of this fund will be channeled through the same legal agreement between the Bank and Thailand.
Spain | Libya | Methyl Bromide | 2008-11-01 |  | 2014-12-01 | 500000 | 500000 | 220112 | 40 | 30 | 30 |  |  |  | Project about to be completed, however, the installation of the last equipment could not be done until now. It will be done as soon as the security situation allow such installation | Political situation contributed to the delay
Spain | Mexico | Methyl Bromide - Soil Fumigation | 2010-04-01 |  | 2015-03-01 | 1600000 | 1600000 | 799997 | 90 | [5 empty] | Project activities almost completed in March 2015, it remains US$ 7,000 for the organization of a final official event with the Mexican Authorities to conclude the project
Sweden | Croatia | CFC Phase Out Plan | 2003-04-01 | 2006-06-30 |  | 92200 | 92200 | 92200 | 13 |  |  | 0 |  |  | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. The project was completed in June 2006. PCR was submitted in April 2010.
Sweden | Philippines | CFC Phase Out Plan | 2002-11-01 | 2011-12-31 |  | 358534 | 358534 | 345799 | 0 |  |  | 0 |  |  | The original plan to establish a functioning Reclamation Facility in partnership with PARII was deemed not financially-viable and economically-feasible by PARII due to low amounts of reclaimable refrigerants from the servicing sector. Hence, an alternative model to establish an ODS management plan, including the collection, transport, and storage of recovered refrigerants and unwanted ODS was proposed by the PMU and included in the 2010-2011 Biennual Plan of the NCPP approved at the 60th ExCom Meeting. Procurement and selection process for equipment which complements that already procured under the reclamation scheme, as well as for contractors for ODS collection, transport and storage was not completed until 2010. Delsa Chemicals and Multi-Products Inc (DCMI), a member of PARII, the refrigerant importer association, is the contractor selected for the collection, transport and storage of recovered refrigerants for the NCPP. The contract between DENR and Delsa Chemicals was signed 13 Sep 2010 after a long negotiation on the scheme and financial requirements. Delsa Chemicals started collection of recovered refrigerants Oct 2010 and has so far 3.0 MT of various recovered refrigerants stored in their warehouse. Task expected to be completed by mid-2011.
Sweden | Romania | CFC Phase Out Plan | 2005-04-01 | 2010-12-31 |  | 36281 | 36281 | 36281 | 0 |  |  | 0 |  |  | With ExCom decision 60/3 in April 2010, the remaining components of this project was formally handed over from Sweden to UNIDO and the contract with the international consultant was terminated. This progress report therefore only includes activities up to April 2010: The project has been suffering from a long delay even though a lot of progress was made during the last two years. The training of trainers for the vocation schools have been held and they have received the equipment needed for their training. Training of the existing workforce has also been conducted although in April 2010 a number of training sessions still remained to be undertaken. Up to April 2010, the Association of Refrigeration had given interim certificates to 19 Companies and 148 technicians (from which 89 are still under evaluation). A Governmental Decision had been sent for approval at all the signatory ministries and it was said that it would be published in the Official Journal no later than September 2010. The Governmental Decision was expected to be followed by a Ministerial Order which would establish the Association of Refrigeration as the interim certification body until 2011. With regards to the reuse scheme this activity is still not finalised. A number of seminars have been held to discuss the reuse scheme which raised a lot of interest. A survey was made of all the destruction facilities in the country to see which ones are incinerating based on the criteria of the Annex VI of the Regulation 1005/2009 regarding the ozone depleting substances. GreenWEEE was found to be the biggest integrated treatment plant for electric and electronic equipment waste (WEEE) in Romania and one of the most modern in Europe. They have 3 collection centers in the country (Lasi, Timisoara, Bucuresti). GreenWEEE can collect all the WEEE categories mentioned in the legislation (including large household appliances- refrigerators, freezers). The NOU has drafted a report for recycling systems in accordance with the EU existing legislation and based on the key aspects underlined by the consultation with the companies with interests in this field. Due to the existing economical situation the market is rather small. Also, meetings have been held with the customs and an draft instructions handbook was prepared based on the EU regulations. The additional delay is due to the initial long delay and the difficulties to speed up the process as much as needed to stick to the revised time plan. Also, the Governmental Decision was delayed and until September 2010 which further delayed the implementation of some of the measures proposed therein. Sweden also estimate that it will take time to get the reclamation system fully operational, something which will cause additional delay. Even if Romania had come quite far in April 2010 by holding stakeholder workshops and discussions and survey among the destruction facilities, this is much delayed already and it will take additional time to get it fully operational. The Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010.
Sweden | Serbia | CFC Phase Out Plan | 2004-07-01 | 2010-12-31 |  | 19322 | 19322 | 19322 | 0 |  |  | 0 |  |  | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010.
Switzerland | India | CFC Phase Out Plan - Refrigeration Servicing | 2004-04-01 | 2009-03-31 |  | 1600600 | 1314601 | 1304053 | 211.4075 |  |  | 0 |  |  | Consumption reporting by Lead Agency (GTZ)
UNDP | Angola | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2016-05-01 | 176000 | 125333 | 50453 | 1.59 | 15.95 |  |  |  |  | A total of 2 tranches have been approved for Angola under UNDP. In 2014, 4 national training sessons took place in Luanda and in 3 cities in the countryside. Consultations with training centers were undertaken in order to identify specific needs of equipment to be procured. | An internal assessment of the project has been conducted and remaining funds allocated to cover national needs on equipment for technicians and training centers. Specs and TOR were agreed with GOV and bid is expected to start in mid-July 2015.
UNDP | Argentina | Methyl Bromide | 2002-03-01 | 2009-06-01 |  | 3588000 | 3588000 | 3587926.51 | 156 | 184.4 |  |  |  |  | Completed in 2009. | From Jan. to Jun. (2015), ProDoc is still under GOV review to be signed. UNDP is monitoring the issue. In the meanwhile, procurement plan has been prepared.
UNDP | Armenia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-12-15 | 562838 | 562838 | 519015 | 2.09 | [5 empty] | Two tranches have been approved for Armenia with the first tranche's approval in December 2010. The situation at SAGA has not changed from 2013, and no additional progress was achieved with local constructions except for previous finishing of blender housing outside of the main facility. Multiple meetings held between NOU/UNDP and SAGA on clarifying plans, and then on attempting to convince SAGA to continue with the project. Additional consultations with Ministry of Environment (Deputy Minister)/NOU and UNDP/UNEP held in November 2014 at MOP in Paris resulted in the decision to begin prepararations to cancel the SAGA project. An action plan was developed to contact SAGA to start project cancellation. | SAGA submitted a project cancellation letter to NOU-Armenia, and NOU informed that no last tranche for UNDP's remaining work with SAGA would be requested. Any unfunded eligible activities in the servicing sector as a part of the last third tranche would be taken from the existing balance of two first tranches of HPMP Stage I. MLF Secretariat was informed accordingly, and with the agreement, only UNEP's second and last tranche was requested at the 75th ExCom in May 2015, and approved. UNDP started cancellation process of the SAGA component by negotiating with the equipment supplier a possible return of two lines (refrigerant filling and foam) and compensation which was rejected by Transfair. UNDP is currently negotiating a transfer of this equipment to one of UNIDO's programmes with special thanks to UNIDO. Once such projects and transfer procedures are identified, and transfer is complete, UNDP will start return of obtained funds from the transfer to the MLF Secretariat.
UNDP | Bahrain | CFC Phase Out Plan | 2006-11-01 | 2012-12-01 |  | 312500 | 312500 | 305653.87 | 58.71 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Bangladesh | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 1201074 | 1201074 | 1141311 | 20.78 | [5 empty] | The first tranche was approved in November 2011 and an investment project was approved earlier in December 2010. During the year 2014, NOU closely monitored completion of the project at Walton. The project completion procedures (technical aspects) were completed. The NOU also had extensive interactions with industry associations and Government department on project implementation modalities and mechanisms to be adopted for promoting low-GWP technologies. Verification report for 2013 was completed during the year through an independent consultant. Other components relating to HPMP project for Stage-I are under implementation - particularly relating to the service sector and policy training support. The Government is also actively considering updating standards for adoption of low GWP flammable technologies and has had a consultative report prepared on the same. | HPMP Stage-I second tranche was submitted to the 74th Excom and approved. Verification report for 2013 and 2014 also completed by Q1 - 2015.
UNDP | Bangladesh | ODS Phase Out Plan | 2004-04-04 | 2012-12-01 |  | 879750 | 879750 | 874862 | 267.6 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Barbados | HCFC Phase Out Plan (Stage I) | 2013-04-01 |  | 2016-04-01 | 88000 | 50000 | 0 | 0.41 | 3.69 |  |  |  |  | Only 1 tranche was approved for Barbados under UNDP. By December 2014, the government had reviewed and approved the contents of the ProDoc upon final adjustments required by UNDP. The ProDoc was sent for signature in December 2014. | The ProDoc is still under GOV review to be signed. UNDP is monitoring the issue. In the meanwhile, the procurement plan has been prepared.
UNDP | Belize | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-01 | 66500 | 60000 | 60000 | 0.24 | 2.94 |  |  |  |  | Only 1 tranche was approved for Belize under UNDP. By December 2014, some equipment (approx. 30%) has been delivered to final users. Capacitation and delivery of equipment are to be continued through 2015. | Up to mid-2015, additional equipment (approx- 45% cumulative) has been delivered to end-users.
UNDP | Belize | CFC Phase Out Plan | 2007-11-07 | 2010-08-01 |  | 194000 | 194000 | 193980 | 3.7 | 0 | 0 |  |  |  | Completed in 2010. | N/A
UNDP | Bhutan | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2025-12-01 | 188000 | 112000 | 111259 | 0.12 | [5 empty] | The first tranche was approved in April 2011 and the second tranche was approved in July 2013. In 2014, the project activities under investment component were progressing in a satisfactory manner. The country is reviewing technology situation relating to HCFC alternatives and planning to implement suitable retrofit promotion schemes through their trained technicians. | The activities in the country are progressing satisfactorily.
UNDP | Bolivia | ODS Phase Out Plan | 2007-03-07 | 2012-10-01 |  | 378000 | 378000 | 372848.2 | 26.9 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Brazil | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2017-07-01 | 15506257 | 13856257 | 3020544 | 174.31 | 1327.3 | 1164.74 |  |  |  | Three tranches have been approved for Brazil under UNDP. By December 2014, activities related to the first and second tranches had advanced substantially. For the Continuous Panels component, four companies have designed the reconversion plans and 2 are in the final stages of conversion. Five integral skins companies are at an advanced stage of reconversion. All 11 system houses have been assisted with trials and tests. Purcom and Ariston have completed the conversion at the system house level, other system houses that operate in the Integral Skin sector are at an advanced stage of reconversion. 50 clients supported by Purcom and Arinos had started to do initial trials on formulations. Details can be found in the Tranche Report submitted to the 74th ExCom The third tranche was approved by the 73rd ExCom and activities related to system houses and downstream users operating in the rigid foam applications had been initiated by December 2014. | 4 tranches have been approved so far. Activities under tranches 1, 2 and 3 are being implemented sactisfactorily. Activities under tranche 4 have succesfully started with initial trials under rigid PU end-users initiated by one System House.
UNDP | Brazil | CFC Phase Out Plan | 2002-07-01 | 2013-12-01 |  | 22816400 | 22816400 | 22802709 | 5801 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Brunei Darusssalam | HCFC Phase Out Plan (Stage I) | 2012-04-16 |  | 2022-04-16 | 132000 | 92400 | 30000 | 0.89676 | [5 empty] | One tranche has been approved in April 2012. In Jan and Dec 2014, the invitation bid was announced and one reclamation machine and 16 recovery machines had been procured. The delivery of equipment is planned in Jan 2015. | In late Februray 2015, a joint mission with UNEP, to participate the R&R training and to prepare the 2nd tranche request was conducted. The 2nd tranche request was submitted to and approved at the 74th ExCom.
UNDP | Cambodia | HCFC Phase Out Plan (Stage I) | 2010-07-01 |  | 2020-12-20 | 650000 | 400000 | 250000 | 6.0938 | [5 empty] | Two tranches have been approved for Cambodia, with the first tranche having been approved in July 2010. During the year 2014, the implementation plan was discussed and finalized in mid-2014. The focus is on R&R activities and promotion of HCFC-free alternatives. | Under the 2nd tranche, several awareness outreach activities for the users, relevance stakeholders and constitutions have been conducted to promote the alternative with non ODS and climate friendly based equipment.
UNDP | Cambodia | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 280000 | 280000 | 278225.94 | 13.5 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Chad | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 174000 | 174000 | 163018.11 | 5.2 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Chile | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2017-01-01 | 1497966 | 1298667 | 306035 | 18.45 | 87.5 | 74.2 |  |  |  | Three tranches have been approved for Chile under UNDP with the first tranche having been approved in April 2011. Project activities were underway according to the workplan. During 2014, training courses for customs officers and refrigeration technicians were conducted. 5 refrigerant identifiers were bought and delivered to the National Customs Office. GRP manual was prepared by international expert, followed by a train-the-trainers seminar. Workshop on HCFC-141b alternatives for flushing was carried out with participation of international experts and suppliers. A workshop on HC-based refrigerants was conducted by an international expert. Although most of the work plan has been carried out according to plan, there have been some delays in the proposal of alternatives for supermarket pilot. UNDP and NOU organized meeting a and follow up with participant stakeholders. A consultant was hired to design the selection scheme of proposal. | Selection scheme for participating supermarkets was prepared by local consultant and is in final revision by NOU. A mission was conducted to review workplan and discuss implementation of the project. 2 local experts participated in especialized training on natural alternatives to HCFC in Germany.
UNDP | China | HCFC Phase Out Plan (Stage I) - Industrial, Commercial and Air Conditioning (ICR) | 2011-07-01 |  | 2017-07-01 | 61000000 | 51850000 | 40691373 | 548.33 | [5 empty] | Four tranches under the ICR sector have been approved with the first being approved in July 2011. During the year 2014, the project implementation progressed satisfactorily. 11 beneficiaries aggregating to more than 80% of the total phase-out under the plan have signed the agreement. More beneficiaries are being identified and are expected to sign the agreement for project implementation in 2015. The fourth tranche for the sector plan was approved in November 2014. The activities progressed satisfactorily in the year 2014. Conversion projects are progressing satisfactorily towards completion. In 2014, Government also pursued issues related to standards for safe adoption of low GWP. | Activities are progressing satisfactorily with most of the companies covered under ICR sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 14531022
UNDP | China | HCFC Phase Out Plan (Stage I) - National Co-ordination | 2011-07-01 |  | 2016-04-01 | 360000 | 360000 | 300000 | 3.24 | [5 empty] | During the year 2014, the project activities relating to HPMP implementation are progressing in a satisfactory manner. Fourth tranche request for HPMP was submitted and approved in 73 Excom held in November 2014. 2013 targets were satisfactorily achieved. All planned activities are progressing satisfactorily. | Activities are progressing satisfactorily on project management, coordination and implementation.
UNDP | China | HCFC Phase Out Plan (Stage I) - Solvent | 2011-11-01 |  | 2017-11-01 | 5000000 | 4500000 | 4100000 | 44.94 | [5 empty] | Two tranches for the solvents sector have been approved with the first having been approved in July 2011. During the year 2014, projects under solvent sector plans made significant progress towards completion of conversion activities. Demonstration project report for KDL was also submitted to the 73rd meeting. | Activities are progressing satisfactorily with most of the companies covered under solvent sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2480000
UNDP | China | Solvent | 2000-03-01 | 2012-12-01 |  | 52000000 | 52000000 | 51999999.6 | 4031 | 0 |  |  |  |  | Completed in 2012. Work plan for other pending activities provided to MFS in Nov 2014. | N/A
UNDP | Colombia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2015-12-01 | 6721483 | 6721483 | 6523050 | 77 | 225.6 | 156.11 |  |  |  | Three tranches have been approved for Colombia under UNDP with the first tranche having been approved in December 2010. Most of the planned activities were carried out during 2014. The NOU continued with its activities related to training of refrigeration technicians on GRP (15 workshops and 433 trained technicians). 3 train-the-trainers workshops on GRP, HC and other natural refrigerants conducted. The NOU has kept its work with end-users by organizing 12 seminars on HCFC alternatives. An awareness campaign accompanied all activities. | 4 workshops on good refrigeration practices conducted. 2 consultancies to standarize operation of reclaiming centers were initiated. 8 collection centers obtained their environmental license and operating in the R&R&R network. 2 follow up missions were conducted.
UNDP | Colombia | ODS Phase Out Plan | 2003-12-03 | 2011-12-01 |  | 4500000 | 4500000 | 4499881.24 | 805.85 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Comoros | CFC Phase Out Plan | 2007-07-01 | 2010-12-01 |  | 75000 | 75000 | 74280 | 0.4 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Congo, DR | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2017-12-01 | 240000 | 216000 | 118525 | 2.9305 | [5 empty] | Two tranches have been aproved for DRC and the second tranche was approved by the ExCom in July 2013. Up to the beginning of 2014, the first tranche of the project was being completed, and activities for the second tranche were initiated in the second half of 2014. A key part of the activities consists in the second set of procurement of equipment for the refrigeration servicing sector. A first procurement notice was launched in June 2014 but turned out to be unsuccessful. After review and improvement of the notice, in consultation with international consultant, the notice was issued again in September, this time successfully with several applications by international suppliers (under review/assessment by end 2014). | In first half of 2015, the equipment procurement process has been completed. Implementation is ongoing, with preparation of the next tranche submission and of the PRP request for Stage II, with the new NOU team in place in DRC.
UNDP | Congo, DR | CFC Phase Out Plan | 2006-07-01 | 2011-12-01 |  | 337500 | 337500 | 329184 | 51.5 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Costa Rica | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2022-07-01 | 1153523 | 991523 | 794354 | 18.93 | 14.1 |  |  |  |  | Two tranches have been approved for Costa Rica under UNDP with the first tranche having been approved in July 2011. A visit from an expert of SENA took place in Costa Rica to develop a Curriculum for training schools. Train the trainers with SENA specialist in October with the participation of 17 trainers from INA in Costa Rica. Agreement with institute to develop speciality course of Commercial and Industrial refrigeration and AC. Agreement with SENAI from Brazil on south-south collaboration. Visit of INA to SENAI in Brazil. Training of technicians in INA. | 2015 action plan is under implementation. Third tranche request prepared and submitted. Training of custom users on online system continues. Implementation of agreement between INA and SENAI for training refrigeration and AA technicans is underway. 1 follow up mission was conducted.
UNDP | Costa Rica | CFC Phase Out Plan | 2007-07-01 | 2011-12-01 |  | 565000 | 565000 | 564999.93 | 37.5 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Costa Rica | Methyl Bromide | 2001-12-01 | 2014-06-01 |  | 4845283 | 4845283 | 4843696 | 342 | 140 |  |  |  |  | Technical assistance was provided to Melon growers to assure zero use of MB. This was the first harvest with no use of MB. Trouble shooting was needed in several cases. The project is considered successfully completed as it is expected to be sustained. The government has introduced a ban on the use of MB in agriculture in Costa Rica.
UNDP | Cuba | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-11-01 | 1747527 | 1450000 | 296412 | 19.26 | 16.88 |  |  |  |  | Two tranches have been approved for Cuba under UNDP with the first tranche having been approved in November 2011. In the foam sector, the planned milestone of selecting the technology suppliers was achieved, awarding contracts was achieved for one company, implementation of plant conversion started as suppliers paid a visit to the company, action plan and technical specifications of equipment agreed. For the other company, the NOU and supplier could not reached an agreement on commercial conditions, another supplier was contacted and discussions are underway. Import of HCFC-141b in preblended polyols have been banned since 31/12/14. For the refrigeration sector, the project advanced according to work plan, 16 training centers were strengthened with equipment and training tools. Activities to promote the reconversion of refrigeration systems continue, in 2014 80 systems were converted to HCFC-alternatives. | Conversion of commercial equipment continues, training centers around the country recieved equipment to strengthten technical capabilities. Pending contract was signed and construction of equipment started, so equipment for both plants are currently under construction. Preparation of plants for conversion was conducted. 1 follow up mission was carried out.
UNDP | Cuba | ODS Phase Out Plan | 2005-04-05 | 2013-12-01 |  | 1559228 | 1559228 | 1558051.91 | 331.3 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Djibouti | CFC Phase Out Plan | 2007-11-01 | 2009-12-01 |  | 147000 | 147000 | 144849.12 | 0 | 0 |  |  |  |  | Completed in 2009. | N/A
UNDP | Dominica | CFC Phase Out Plan | 2006-04-01 | 2013-12-31 |  | 103000 | 103000 | 96208 | 0.74 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Dominican Republic | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-11-01 | 1646225 | 1646225 | 1082655 | 26.28 | 51.2 | 36.89 |  |  |  | Two tranches have been approved for the Dominican Republic under UNDP with the first tranche having been approved in November 2011. In 2014, in the refrigeration sector, the planned milestone of implementing the MOA with INFOTEP was achieved, 600 technicians trained and 25 courses carried out. 3 training centers were strengthened. It is worth noting that the Legal framework for certification of refrigeration technicians was agreed between stakeholders and launched during Ozone Day celebration. In the foam sector, the conversion activities in the foam producers continued. The milestone of converting four enterprises was achieved. Installation process of 2 injection machines in two of the main producers was conducted. One mission from the intenational expert was conducted to support the conversion process. | Third tranche requested and approved. Implementation of MOA with Infotep continues. 3 workshops to End-users and refrigeration technicians were conducted. Installation of injection machines completed in Paredomi. Finals trials conducted in 2 doors manufacturers facilities. Workshop with PU suppliers and end-users to disseminate new regulation on HCFC-141b based systems.
UNDP | Dominican Republic | CFC Phase Out Plan | 2005-04-05 | 2012-05-01 |  | 1711600 | 1711600 | 1703442.03 | 311.2 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Egypt | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2018-12-01 | 6195400 | 5479000 | 2123794 | 128.6756 | [5 empty] | Three tranches have been approved for Egypt with the first tranche's approval in 2010. In 2014, the Reftruck and Al Fateh projects were completed, with hand-over protocols signed and no residual pending payments remaining. Dow system house signed the MOA agreement and completed a first milestone on technology development. Technocom and Baalbaki system houses will be signing the MOAs in 2015. Unstable situation in the country put limitations on some activities, and each mission required a special consideration and clearance by UNDSS. | Two missions completed in April and May 2015 by senior foam expert. All standalone conversion projects are now complete with the last safety audit done in May 2015. Currently, the focus is on system house level with two system houses (Dow-MidEast and Technocom) moving ahead under a signed MoA on HCFC-free formula development. Additional discussions being held with the remaining two system houses with facilitation of NOU-Egypt on signing agreed MoAs to start work in parallel to Dow-MidEast and Technocom.
UNDP | El Salvador | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2022-11-01 | 699277 | 589277 | 445058 | 5.88 | 11.68 | 8.54 |  |  |  | One tranche has been approved for El Salvador under UNDP, which was approved in November 2011.During 2014, in the refrigeration sector, the milestone of training on good refrigeration practices was achieved, The NOU continued with training activities where courses on alternatives to HCFC were conducted. HCFC import quota for 2014 was established. In the foam sector, the milestone of installing the equipment at Unimetal was achieved, the company converted to HC. Hecasa converted its production line to HCFC-free alternatives. A mission by the international expert was conducted to follow up on project implementation and to verify Unimetal's conversion. | 2015 work plan is under implementation. Training of technicians on good refrigeration practices continues. Second tranche requested and approved. Material for trials was purchased and delivered to country, building where trials will be conducted was prepared; beneficiary company is ready for using MF system.
UNDP | El Salvador | CFC Phase Out Plan | 2007-11-07 | 2011-06-01 |  | 515000 | 515000 | 514995 | 46 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Fiji | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2022-11-01 | 189500 | 109700 | 71028 | 1.22 | [5 empty] | Two tranches have been approved for Fiji. During the year 2014, R&R equipment were procured and distributed to beneficiaries. The second tranche request along with verification report was submitted for Fiji. The tranche request was approved in the 73rd Excom after certain adjustments keeping in mind consumption levels of Fiji for the year 2013. Fiji also initiated process of revising baseline data. | Activities progressing satisfactorily. Government is working with Ozone Secretariat on baseline data change in line with decision of 73rd Excom meeting.
UNDP | Gabon | CFC Phase Out Plan | 2007-07-01 | 2009-12-01 |  | 90000 | 90000 | 83283.3 | 1.5 | [5 empty] | Completed in 2009. | N/A
UNDP | Gambia | CFC Phase Out Plan | 2007-11-07 | 2010-12-10 |  | 130000 | 130000 | 126999 | 3.6 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Georgia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 500900 | 350000 | 199139 | 2.33 | [5 empty] | Two tranches have been approved for Georgia with the first tranche's approval in 2010. In 2014, the ODS related regulations were revised and recommendations, alongside with the relevant legislation packages, were developed in order to improve the certification system; to control service methods; to control and execute all types of legal issues related to ozone depleting substances (import/export permit, certification, service standard implementation, etc.). Survey for the correct management of the transferred equipment was conducted for National Refrigeration Association and R/R centers. Two (2) workshops were conducted with the stakeholders to get acquainted with the new ODS regulations and create awareness amongst attended staff on their role in enforcing Montreal Protocol at the national level. Training of Custom officers was conducted and a modern-type refrigerant analyzer (Pur-chek) purchased and handed over. | Tranche 1 is complete. As for Tranche 2, NOU-Georgia and UNDP currently conduct best practice trainings. One (1) training is complete in June 2015 in a vocational school SPEKTR. 15 people trained. In Eastern Georgia, 4 training sessions planned for 2015 for 80 technicians with certification. This is being done in support of a new legislation on technician certification that will be adopted in October 2015. Demonstration and diagnostic training stand (computer controlled: via a local or internet network from other colleges) is being designed by the Refrigeration Association for use in vocational colleges. A special article is prepared for two editions (August and September) of the National Geographic magazine along with 5 internet-based blogs devoted to the HCFC phaseout in Georgia. Welding machine for aluminum purchased and delivered to the R/R center in Kutaisi, and out 3 planned sets of R/R main and ancillary equipment 1 set purchased for Kutaisi R/R center to back the planned trainings on technician certification.
UNDP | Georgia | CFC Phase Out Plan | 2006-11-01 | 2009-12-01 |  | 325000 | 325000 | 324918.06 | 8.18 | 0 |  |  |  |  | Completed in 2009. | N/A
UNDP | Ghana | HCFC Phase Out Plan (Stage I) | 2010-07-01 |  | 2020-12-01 | 1031311 | 590000 | 296121 | 19.9752 |  | 23.34 |  |  |  | Three tranches have been approved for Ghana. The second tranche was approved in July 2012 and in 2014, the funding for the third tranche was requested and approved. In 2014, it was planned that all activities would be completed under the second tranche, however, some activities are still being finalised, for example, the process of procurement of customs identifiers was initiated but not completed. The agreement for the Centre of Excellence at the Accra Technical Training Centre is now in place and the centre is available for trainings. Most of the activities in this tranche required institutional agreements to be negotiated and agreed with partner institutions, leading to processes which have taken longer than planned initially. This background work is now completed and will allow for completion of the tranche activities in 2015. | Mission held by the International consultant in May-June 2015, supporting the planning of the activities and procurement processes, in addition to first UNDP mission in February 2015. Work continued for the procurement of equipment, continued strengthening of the centre of excellence, and strengthening of the technicians' capacity. Customs training is being actively prepared.
UNDP | Ghana | CFC Phase Out Plan | 2006-11-01 | 2009-11-01 |  | 344894 | 344894 | 344894 | 17.5 | 0 |  |  |  |  | Completed in 2009. | N/A
UNDP | Grenada | CFC Phase Out Plan | 2006-07-01 | 2011-11-01 |  | 120000 | 120000 | 119337 | 2.986 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Guatemala | CFC Phase Out Plan | 2008-11-01 | 2013-12-01 |  | 249000 | 249000 | 205231.95 | 5.9 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Guyana | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-12-01 |  | 48000 | 48000 | 47998 | 0.072727 | 0.97 | 0.8 |  |  |  | Only 1 tranche was approved for Guyana under UNDP. In 2014, the equipment was procured and delivered to the country. Detailed information is in the Tranche Report submitted to the 74th ExCom.
UNDP | Guyana | CFC Phase Out Plan | 2007-11-07 | 2011-11-01 |  | 215000 | 215000 | 214524 | 8 | 0 |  |  |  |  | Completed in 2011
UNDP | Haiti | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2022-12-01 | 97119 | 0 | 0 | 0.44 | 3.6 |  |  |  |  | N/A | N/A
UNDP | Haiti | CFC Phase Out Plan | 2009-07-01 | 2014-12-01 |  | 150000 | 150000 | 61975 | 2.3 | 0 |  |  |  |  | In 2014, the milestone of conducting three workshops was achieved, 60 technicians were trainned. TOR for purchasing equipment for training centeres were prepared and equipment purchased.
UNDP | India | HCFC Phase Out Plan (Stage I) | 2012-04-16 |  | 2017-04-16 | 18438490 | 17000000 | 9130216 | 295.93 | [5 empty] | Two tranches have been approved for India, with the first tranche having been approved in April 2012. During the year 2014, conversion projects in foam sector and systems houses progressed satisfactorily. New formulations have been developed by systems houses. These are being optimised for cost effective solution to SMEs. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche would be submitted to the 75th Excom.
UNDP | India | CFC Phase Out Plan - Foam | 2002-07-01 | 2006-12-01 |  | 5424577 | 5424577 | 5424577 | 639 | 0 |  |  |  |  | Completed in 2006. | N/A
UNDP | India | CFC Phase Out Plan - Refrigeration Manufacturing | 2002-11-01 | 2006-12-01 |  | 2935986 | 2935986 | 2801419 | 428 | 0 |  |  |  |  | Completed in 2006. | N/A
UNDP | India | CFC Phase Out Plan - Refrigeration Servicing | 2004-04-01 | 2010-08-01 |  | 1522260 | 1218341 | 1102561.47 | 219.08 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Indonesia | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-07-01 | 8953902 | 8052800 | 2981845 | 90.01 | [5 empty] | Two tranches have been approved for Indonesia with the first being approved in July 2011. During the yeaar 2014, conversion projects for large enterprises were completed for most of the enterprises. Government has also imposed a regulation prohibiting use of HCFCs in manufacturing RAC equipment from 1 Jan 2015. | Government has successfully implemented regulations for prohibiting use of HCFCs in RAC manufacturing from 1 Jan 2015. Monitoring of HCFC consumption is ongoing satisfactorily. Third tranche would be submitted to the 75th Excom
UNDP | Indonesia | ODS Phase Out Plan - Aerosol | 2004-12-01 | 2006-06-01 |  | 224000 | 224000 | 181887 | 80 | 0 | 0 |  |  |  | Completed in 2006. | N/A
UNDP | Indonesia | ODS Phase Out Plan - Refrigeration Manufacturing | 2002-07-01 | 2011-12-01 |  | 6398000 | 6398000 | 6391359.93 | 1141 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Indonesia | ODS Phase Out Plan - Refrigeration Servicing | 2002-11-01 | 2010-12-01 |  | 4912300 | 4912300 | 4903252 | 1072 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Iran | CFC Phase Out Plan - Refrigeration Manufacturing | 2004-04-01 | 2007-12-01 |  | 770000 | 770000 | 756547 | 56 | 0 |  |  |  |  | Completed in 2007. | N/A
UNDP | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2017-12-01 | 4340246 | 4340246 | 3311922 | 71.39 | [5 empty] | Three tranches were approved for Iran with the first tranche having been approved in April 2011. During the year 2014, the project in residential AC manufacturing company progressed well and the enterprise is expected to complete conversion project in 2015. Systems house project faced issues relating to technololgy access and choices partcularly in the context of cost-effective usage in SMEs. Consultations were held with beneficiary on technological choices for the foam system house component. The enterprise expressed its inability to make technology choices due to technical issues and commercial considerations. The NOU and UNDP discussed this and agreed to return the related funds back to Excom at its 74th meeting. Government is closely monitoring project implementation to ensure successful completion of all projects by 2015. | Activities progressing satisfactorily. Last tranche request for HPMP submitted to and approved in 74th Excom.
UNDP | Jamaica | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2021-12-01 | 578450 | 337450 | 207644 | 7.1484 |  | 2.36 |  |  |  | Two tranches have been approved for Jamaica under UNDP with the first tranche having been approved in July 2011. By December 2014, the following activities were implemented/milestones achieved. In foam, the company SEAL reconverted to MLF. In the RAC sector, two "train the trainers" courses took place in Kingston and in Montego Bay. The iplementation plan for the delivery of training to technicians has been approved by GOV. HC based pilot equipment was procured and delivered to training centers to create capatities in installation and maintenance of such type of equipment. | 2 tranches have been approved for Jamaica thus far and activities have progressed well. Since 2014, a third "train the trainers" course took place in Ocho Rios and ancilliary equipment was delivered to training center.
UNDP | Kenya | Methyl Bromide | 2002-11-01 | 2009-12-01 |  | 510660 | 510660 | 504124 | 10 | [5 empty] | Completed in 2009. | N/A
UNDP | Kyrgyzstan | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2016-05-01 | 52800 | 52800 | 46862 | 0.19 | [5 empty] | Two tranches have been approved for Kyrgyzstan with the first tranche's approval in April 2011. In 2014, 25 units of equipment were purchased. An additional 15 units are planned to be purchased in 2015. There were problems on the agreement of the funds disbursement modality. A harmonized system of fund advance (HACT) was proposed as a solution, which is now being tested. By this system, funding advances are made with follow-up financial reporting from NOU. | Mission held in February 2015. Additional R/R equipment (10 sets) purchased and delivered to recipients as planned. Project is set for closure, and NOU-Kyrgyzstan will focus on the start-up of the newly approved HPMP Stage II.
UNDP | Kyrgyzstan | HCFC Phase Out Plan (Stage II) | 2015-05-15 |  | 2018-05-15 | 400000 | 170000 | 0 | 1.73 | [5 empty] | N/A | Newly approved.
UNDP | Kyrgyzstan | CFC Phase Out Plan | 2006-11-01 | 2010-12-10 |  | 317000 | 317000 | 317000 | 7 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Lebanon | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2019-07-01 | 2495109 | 2370349 | 2089466 | 24.51 | [5 empty] | During the year 2014, investment projects relating to foam and refrigeration. sector were completed and all milestones achievement were verified. Monitoring of activites will be continued during the next 2 years. Technical assistance activities for foam and ref sector would also be continued and implementation of all activities under this component is expected to be completed in 2016. Other activities relating to technical capacity building, policy enforcement and information outreach are also under implementation. | Activities progressing satisfactorily. Third tranche request for Lebanon approved in 74th Excom. Enterprise level conversion in RAC and foam sector completed. Other technical support and information outreach activities are in progress.
UNDP | Lebanon | CFC Phase Out Plan | 2004-12-01 | 2010-12-01 |  | 2091420 | 2091420 | 2091020 | 417 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Lebanon | Methyl Bromide | 2001-07-01 | 2009-12-01 |  | 2567300 | 2567300 | 2566716.59 | 186.1 | 0 |  |  |  |  | Completed in 2009. | N/A
UNDP | Liberia | CFC Phase Out Plan | 2007-11-01 | 2009-12-01 |  | 132000 | 132000 | 130563.05 | 8.4 | 0 |  |  |  |  | Completed in 2009. | N/A
UNDP | Malawi | CFC Phase Out Plan | 2007-11-01 | 2011-12-01 |  | 173000 | 173000 | 171755 | 8.7 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Malawi | Methyl Bromide | 2000-12-01 | 2006-12-01 |  | 2999824 | 2999824 | 2988303 | 129 | 0 |  |  |  |  | Completed in 2006. | N/A
UNDP | Malaysia | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-11-01 | 9587471 | 8628723 | 7056382 | 103.02 | [5 empty] | Two tranches have been approved for Malaysia, with the first tranche having been approved in 2011. In the year 2014, enterprises actively pursued their conversion project. Most of the enterprises have procured equipment and were almost at the final stages of commercial production of HCFC free products. Systems houses also tested formulations which are HCFC free. MFS evaluation was also undertaken in August 2014. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom.
UNDP | Maldives | HCFC Phase Out Plan (Stage I) | 2010-04-01 |  | 2020-12-01 | 420000 | 420000 | 240670 | 1.41 | 3.7 |  |  |  |  | Two tranches have been approved for the Maldives, with the first tranche having been approved in April 2010. During the year 2014, the project activities were progressing in a satisfactory manner. Policy inputs were provided with the Government undertaking necessary steps to control and monitor HCFC used. The government is working on tackling challenges associated with adoption of low GWP alternatives. The focus was on implementation of R&R program and retrofit incentive scheme focusing on fisheries sector. The latter program was implemented with available and cost-effectively feasible technologies and these are primarily HFC based. The fisheries sector is actively engaged in identification of low-GWP, safe and cost effective options and technical information was shared on available retrofit technologies. | HPMP Stage-I targets are being satisfactory met. Country still facing challenges in retrofit options (mainly low GWP refrigerants) for existing fishing vessels and working closely with UNDP and tech experts on this. Project for demonstration of low GWP has been approved in the 74th Excom and this is expcted to provide solutions for Maldives.
UNDP | Maldives | CFC Phase Out Plan | 2007-11-01 |  | 2015-12-01 | 85000 | 85000 | 70000 | 0.69 | 0 |  |  |  |  | In the year 2014, these activities were under implementation. In 2014, the equipment procurement was completed and sufficient technical inputs were provided to service technicians on R&R. The equipment would be distributed to beneficiaries in early 2015. Training will also be provided to the servicing enterprises. The project activities are expected to be completed by early 2015. The start-up was delayed due to administrative approval process. But activities progressing satisfactorily. | Reclamation centre operationalisation is underway. Technical support has been requested from India where reclamation centers are in operations - study tour is expected to be undertaken for this in Q3-2015.
UNDP | Mali | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2021-12-01 | 280000 | 160000 | 150571.19 | 2.6 | [5 empty] | One tranche was approved for Mali under UNDP in April 2011 and the first tranche activities were completed and equipment were distributed in Mali as planned and with support from the international consultant. Both international and national consultants were in place and the Project Document was signed. However, the second tracnhe focused primarily on capacity building and insitutional activities coordinated by UNEP, and UNDP is preparing for the following tranche to be submitted for approval in 2016 - the situation and progress will be assessed and support from international expert provided. No delay to report. | No specific milestone to report in first half of 2015.
UNDP | Mali | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 322000 | 322000 | 319198 | 16.2 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Mauritania | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 140000 | 140000 | 135034 | 3 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Mexico | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-07-01 | 13654016 | 12531513 | 6942206 | 315.97 | 1148.8 |  |  |  |  | Three tranches have been approved for Mexico under UNDP with the first tranche having been approved in July 2011. The implementation of the projects at the national system houses has been completed and the focus in 2014 was on final clients. A substantial number of clients are in the process of being reconverted. There have been some challenges with the new systems and the System Houses are continously improving their new non-ODS low GWP systems. UNDP has provided continous Technical Assistance to all local System Houses. The international System houses have also progressed with the implementation although at a lower speed. In the last trimester of 2014, a special effort was put in place to advance the implementation of international system houses and 3 missions took place with international experts in November and December. The list of final clients of international system houses is being evaluated and implementation willl start at end-user level in 2015. | In the first half of 2015, the reconversion work at downstream user (DSU) level progressed with the National SHs. For the international SHs, Polioles/BASF had signed MOA with the project and had started trials with end-users; DOW has also agreed with the terms of MOA and document is in process of signature (in the meanwhile, their clients alread started to receive technical assistance preparation for trials) and Bayer is reviewing the terms of the MOA to engage in the reconversaion process.
UNDP | Moldova | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-12-14 | 88000 | 88000 | 78252 | 0.1 | [5 empty] | One tranche was approved for Moldova under UNDP in 2011. HCFCs controls introduced with annual quota effective starting 01.01.2013. Technicians training and certification system harmonized with F-Gas EU framework. Three (3) advanced portable refrigerant identifiers purchased and delivered to the Customs Department, and a specialized training on the use of this equipment organized by NOU-Moldova. Twenty six (26) Customs officers received training. Handbook for Customs Officers has been updated with new information on ODSs in general, and HCFC and HCFC equipment. Twenty one (21) in 2014 according to the new mentioned F-Gas. Twenty (20) equipment sets purchased and delivered to service centers to qualified technicians. Tranche 2 being prepared for. Baseline changes were expected, but not approved by ImpCom in 2014. Lower import limits triggered HCFC stockpiling in 2012 before freeze, and reductions in HPMP funding expected in Stage II due to lower HCFC consumption category. | Funds under Tranche 1 of HPMP Stage 1 almost fully disbursed and 2014 report outlines the activities which were implemented. This first tranche is set for closure. During Q1 of 2015, NOU-Moldova and UNDP prepared a request for the last tranche under HPMP-Stage I. The last tranche was submitted to and approved at the 74th ExCom. Mission planned for the third quarter in 2015 to enable the start of last tranche of HPMP Stage I which was approved in May 2015.
UNDP | Moldova | CFC Phase Out Plan | 2007-07-01 | 2010-12-10 |  | 305000 | 305000 | 304841 | 10 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Mozambique | CFC Phase Out Plan | 2008-11-01 | 2011-12-01 |  | 117500 | 117500 | 116371 | 2.3 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Nepal | HCFC Phase Out Plan (Stage I) | 2012-04-16 |  | 2022-04-16 | 84000 | 42000 | 0 | 0.256 | [5 empty] | One tranche has been approved for Nepal in 2012. The implementation plan was discussed and finalized in July 2014. The changes in the procurement plan were discussed and being finalized. There were delays in the procurement process. The NOU has requested UNDP to undertake the procurement and make the payment for the training consultant. Also there was a change in the procurement plan. Follow-up actions have been taken to resolve the matters. | The first disbursement (20%) for R&R training has been made in May 2015. This was delayed due to the earthquake happened in April 2015. Also due to the earthquake, the procurement process for R&R equipment has been delayed. A planned mission is also postponed to late 2015 at the time of R&R training upon the arrival of R&R equipment in the country.
UNDP | Nepal | CFC Phase Out Plan | 2007-07-01 | 2013-12-01 |  | 100000 | 100000 | 99914 | 12 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Nicaragua | CFC Phase Out Plan | 2008-11-01 | 2010-11-10 |  | 320000 | 320000 | 319958 | 3.7 | 0 |  |  |  |  | Completed in 2010. | N/A
UNDP | Nigeria | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-12-01 | 2999750 | 2699776 | 1738972 | 54.725 | [5 empty] | Three tranches have been approved for Nigeria with the first tranche having been approved in 2010. Activities for the third tranche are ongoing, although expenditures are still at a limited level, reflecting some delays in implementation. In the Refrigeration component, official launch of the Pamaque facility is under preparation and logistical improvements to the operation of the plant have been completed. For the foam component, the laboratory has been completed at the Vitapur site and after initial trials, full launch of production is expected. The fine tuning of the launch of the use of methyl formate at the foam plant has taken more time than expected. Additional visit by international technical expert will help complete this component. Please note that the baseline allowed under the ExCom agreement is 398.2 ODP T, which includes HCFCs contained in pre-blended polyols. The A7 data baseline is 344.9 ODP T (without pre-blended polyols). | Mission by International consultant was held in April 2015, facilitating the progress of activities at the two foam companies and monitoring of the status of the refrigeration component.
UNDP | Nigeria | CFC Phase Out Plan | 2002-11-01 | 2012-12-01 |  | 12193400 | 12193400 | 12175141.01 | 2388.8 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Panama | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-11-01 | 265545 | 265545 | 203006 | 3.78 | 24.77 | 19.22 |  |  |  | Two tranches have been approved for Panama under UNDP with the first tranche having been approved in November 2011. Planned activities related to training on good refrigeration practices were achieved. Quota system is working properly and quota for 2014 set. Verification report was conducted, showing that the country is complying with its reduction commitments. Purchasing of Nitrogen tools and filters for phasing out HCFC-141b in flushing was carried out. Inventory of refrigeration equipment in local hospital was completed. All planned milesones in 2014 were achieved. | Second tranche implementation report and third tranche request were prepared and submitted. Implementation of 2015 workplan is underway, 2 workshops on good refrigeration practices were conducted; meetings with customs authorities, HCFC importerts and users have been carried out.
UNDP | Panama | CFC Phase Out Plan | 2004-12-01 | 2010-12-01 |  | 943152 | 943152 | 942712.99 | 168.42 | 0 | 0 |  |  |  | Completed in 2010. | N/A
UNDP | Paraguay | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2021-12-01 | 300000 | 300000 | 113056 | 2.99 | 18 | 17.83 |  |  |  | One tranche has been approved for Paraguay under UNDP with the first tranche having been approved in April 2011.The NOU was reconfigured in 2013 with good results, which led to improving the implementation of the project. The milestones related to training on good refrigeration practices were achieved and the certification framework was strengthened. Four training centers strengthened with training equipment and 184 technicians trained in good refrigeration practices. | 1st tranche implementation report and 2nd tranche request prepared, submitted and approved. 1 workshop on good refrigeration practices and alternatives to HCFC was prepared and conducted by international expert.
UNDP | Paraguay | CFC Phase Out Plan | 2007-03-07 | 2012-12-01 |  | 371000 | 371000 | 370995.39 | 31.6 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Peru | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2017-12-01 | 232671 | 108000 | 0 | 3.08 | 26.88 | 22.01 |  |  |  | One tranche was approved for Peru under UNDP in December 2012. By December 2014, the ProDoc was approved by all stakeholders and submitted to the Government for signature. An international expert on RAC was hired and has assessed the needs of country, who is finalizing the procurement plan and TORs. A mission took place and constant conference calls were held to clarify missing points on the ProDoc to facilitate its signature. | The ProDoc of the HPMP has been signed and the local implementation team is at the final stage of recruitment. Equipment needs are being assessed by GOV in order to install a training center for the HCFC-141b flushing alternatives.
UNDP | Rwanda | CFC Phase Out Plan | 2007-11-01 | 2012-12-01 |  | 168000 | 168000 | 156586 | 4.6 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Saint Kitts and Nevis | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2022-07-01 | 40000 | 40000 | 0 | 0.04 | 0.5 |  |  |  |  | One tranche was approved for St Kitts & Nevis under UNDP in July 2011. By December 2014, the ProDoc draft has been prepared and discussed with the Government. The final document was submitted for Government signature (hasn´t been signed by Dec 2014). On the other hand, an International Expert on RAC was hired and had prepared a list of equipment and technical specifications for the HPMP. TOR has been completed and it is expected that the bid should start in March 2015, as soon as the ProDoc is signed, so that equipment can be purchased and delivered to the country. | Up to July 2015, ProDoc is still under GOV review to be signed. UNDP is monitoring the issue. In the meanwhile, procurement plan has been prepared.
UNDP | Saint Kitts and Nevis | CFC Phase Out Plan | 2006-04-01 | 2014-01-01 |  | 108000 | 105000 | 50000 | 1.847 | 0 |  |  |  |  | Completed in 2014. All activities cancelled as per ExCom decision. Funds returned to MLF. | From Jan. to Jun. (2015), ProDoc is still under GOV review to be signed. UNDP is monitoring the issue. In the meanwhile, procurement plan has been prepared.
UNDP | Saint Vincent and the Grenadines | ODS Phase Out Plan | 2005-11-01 | 2012-05-01 |  | 128000 | 128000 | 127826.54 | 2.08 | 0 |  |  |  |  | Completed in 2012. | N/A
UNDP | Samoa | CFC Phase Out Plan | 2007-11-01 | 2013-12-01 |  | 75000 | 75000 | 43950 | 0 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Sierra Leone | ODS Phase Out Plan | 2009-04-01 | 2011-12-01 |  | 60000 | 60000 | 54715 | 12.2 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Sri Lanka | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-01 | 398866 | 240000 | 156372 | 2.9305 | [5 empty] | Two tranches have been approved for Sri Lanka, with the first tranche having been approved in December 2010. During the year 2014, the project activities were progressing in a satisfactory manner. Regnis completed its HCFC-141b phase-out project in foam manufacturing. Support activities to service sector are also progressing satisfactorily. | Monitoring of the Recovery and Reclamation equipment which were distributed in late 2014 has been continued. The operation mechanism of Recovery and Reclamation is being discussed and finalized with the stakeholders. The reclamation centre is expected to be operational in late 2015.
UNDP | Suriname | CFC Phase Out Plan | 2008-11-01 | 2011-12-01 |  | 125000 | 125000 | 124997.63 | 6.2 | 0 |  |  |  |  | Completed in 2011. | N/A
UNDP | Swaziland | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2013-11-01 |  | 667948 | 667948 | 667920 | 4.7094 | [5 empty] | Completed in 2013. | N/A
UNDP | Swaziland | CFC Phase Out Plan | 2008-11-01 | 2011-11-01 |  | 121500 | 121500 | 113799 | 0 | 3.69 |  |  |  |  | Completed in 2011. | N/A
UNDP | Tanzania | ODS Phase Out Plan | 2008-04-01 | 2013-12-01 |  | 276000 | 276000 | 252198 | 54 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Timor-Leste | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2017-12-01 | 106800 | 96120 | 61120 | 0.02 | [5 empty] | One tranche was approved for Timor Leste, with approval in April 2011. In 2014, there were difficulties with the procurement process of the Recovery and Reclamation equipment. The potential supplier for Recovery and Reclamation equiment had been closed for the business, thus the procurement process had to be re-started. The procurement plan was reviewed and discussed for changes so that another local vendor could supply the equipment. | The procurement plan for R&R activity is being reviewed and will be finalized by the NOU soon.
UNDP | Togo | CFC Phase Out Plan | 2008-04-01 | 2010-12-01 |  | 157000 | 157000 | 156133.96 | 5.9 | 5.9 |  |  |  |  | Completed in 2010. | N/A
UNDP | Trinidad and Tobago | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2022-07-01 | 1462733 | 757900 | 194304 | 17.9 | 46.2 | 26.58 |  |  |  | Two tranches have been approved for Trinidad & Tobago under UNDP. By December 2014, in the foam sector, 4 out of 5 companies had signed MOA to facilitate reconversion activities. The Company Vetter Boxes was reconverted. Three companies took PU blowing agent samples to undertake trials. The fifth company had reviewed and agreed on the MOA and the document was sent for signature. In the RAC sector, training activities had advanced and 20 people had been trained. The project also procured pilot HC equipment (splits and domestic refrigerators) to be used by training centers in capacitation activities. | In 2015, the implementation of PU foam subprojects has progressed well. One company reconversion has been completed and 4 are designing their reconversion plans. On the RAC side, additional training courses took place and procurement of tools had been initiated.
UNDP | Trinidad and Tobago | CFC Phase Out Plan | 2003-07-01 | 2008-12-01 |  | 460000 | 460000 | 451622 | 77 | 0 |  |  |  |  | Completed in 2008. | N/A
UNDP | Uruguay | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-11-01 | 380004 | 335000 | 266918 | 4.18 | 23.33 | 17.8 |  |  |  | Four tranches have been approved for Uruguay under UNDP with the first tranche having been approved in November 2011.The project achieved its planned activities related to training on good refrigeration practices. Two one-week workshops were conducted in Montevideo and other cities. Verification report for 2013 was completed, showing that the country is in compliance of its reduction obligations. | Implementation of 20155 workplan is underway, meetings with customs authorities and technical counterpart (LATU) were conducted. 1 follow up mission was conducted.
UNDP | Uruguay | CFC Phase Out Plan | 2006-11-01 | 2013-12-01 |  | 333000 | 333000 | 333000 | 29.86 | 0 |  |  |  |  | Completed in 2013. | N/A
UNDP | Zambia | CFC Phase Out Plan | 2007-11-01 | 2011-12-01 |  | 109000 | 109000 | 78510 | 0 | 0 |  |  |  |  | Completed in 2011. | N/A
UNEP | Afghanistan | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 398825 | 238000 | 89353 | 4.82 |  |  | 0 |  |  | Brief progress report (actual/planned): 147 Customs officers trainned in 2014. NOU developed the 2014 annual plan for strengthening the measures for controlling HCFCs import and consumption. Stakeholders consultations including one with registered importers and goods transporting companies were organized. Legal arrangement (actual/ planned): Implementation delay has required a rephasing of UNEP agreement with the government in the last Q of 2014. First mission (actual/ planned): Jan. 2012. TOR completed (actual/ planned): N/A. First disbursement date: 08/12/2011. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: No funds transfer to the beneficiary due to UNEP internal review of funds transfer modality. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. 4 units of refrigerants identifiers delivered in 2nd quarter of 2015. Implementation halted 2nd quarter of 2015 due to lack of funds in the country and new fund transfer modality by UNEP HQs not finalised. Legal arrangement (actual/ planned): Draft SSFA prepared, but processing pending. | 0
UNEP | Afghanistan | ODS Phase Out Plan | 2005-11-01 | 2010-12-09 |  | 305000 | 305000 | 305000 | 0 | 57 | 0 | 0 |  |  |  |  | 0
UNEP | Albania | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-31 | 85000 | 45000 | 44946 | 0.56667 |  |  | 0 |  |  | Brief progress report (actual/planned): Three training workshops are organized in the country: 1. Training of Technicians on Good Practice in Refrigeration, 27 – 28 February 2014, ABA Business Center, Tirana 2. Training of Technicians on Good Practice in Refrigeration, 28 – 30 April 2014, Hotel “Majestic”, DURRES 3. Training of Technicians on Good Practice in Refrigeration, 28 – 30 October 2014, University “PAVARESIA”, VLORE The trainings workshops were attended by 87 technicians from service sector of refrigeration and 69 of them received certificates (planned about 60 technicians to be trained). The Customs training workshop on monitoring and control of Ozone Depleting Substances was organized on 2 – 3 October 2014, in Hotel Victoria, Tirana. This workshop was organized with the assistance of the international resource person, Dr. Janusz Kozakiewicz. UNEP was requested to attend the meeting and assist the NOU in running the workshop. Participants were 20 officers (as planned) from the General Directorate of Customs (customs officers from various points of entry and customs sections - computer and data processing unit, document processing unit, administration unit, enforcement officer etc.). The representatives of the Refrigeration Association were also present (one was also acting as National Consultant). The meetings between the NOPIU, UNEP and other stakeholders on implementation of the IS and HPMP projects on 4 of October of 2014 (back to back). The activities under the project are completed. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the Ministry and UNEP in December of 2013 (as planned) First mission (actual/planned): n/a – NOPIU implements all activities at national level. Involvement of international experts upon request from the NOU TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in January of 2014 (as planned) All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The NOPIU in cooperation with UNEP and UNIDO has drafted the final report and request for the third tranche. The request will be sent for ExCom-75 as the country should finalize the verification report in cooperation with UNIDO as a lead agency. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the Ministry and UNEP in December of 2013 (as planned) First mission (actual/planned): n/a – NOPIU implements all activities at national level. Involvement of international experts upon request from the NOU TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in January of 2014 (as planned) All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | 0
UNEP | Albania | ODS Phase Out Plan | 2003-04-01 | 2006-07-01 |  | 118125 | 118125 | 107684 | 0 | 6.6 |  | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Antigua and Barbuda | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2015-12-30 | 51700 | 45850 | 27235 | 0.03 |  |  | 0 |  |  | Brief progress report (actual/planned): ___Four workshops have been held and 35 customs officers have been trained. Other 50 more customs officers are already planned to be trained under current stage of the HPMP; An R&AC Train the Trainers Workshop has been held and 10 Technicians have been trained in installation, servicing and retrofitting (if applicable) to current HCFC-based and R-410A systems; forty R&AC technicians have been trained by trainers in four workshops; specialized radio and TV messages targeted to refrigeration technicians, demonstration activity on alternatives to HCFC during ozone day celebration, and distribution of public awareness material . Legal arrangements (actual/planned): SSFA signed in Nov-13___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): First disbursement in Nov-13___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Outsanding progress and financial reports, next disbursement to be processed once UMOJA is operative. NOO focused on the preparation of the HPMP second stage. Workplan agreed, information collection ongoing and stakeholders meeting convened for the preparatory mission in Jun-2015 | 0
UNEP | Armenia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-05-01 | 39000 | 39000 | 31581 | 0.14 | 0.14 |  | 0 |  |  | All project activities of tranche 1 are completed. The final report and last tranche request was prepared. The NOU and UNDP (lead agency) should submit the verification report. | Tranche 2 approved by ExCom 74. | 0
UNEP | Bahamas | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 156900 | 67750 | 19490 | 0.85493 |  |  | 0 |  |  | Brief progress report (actual/planned): SSFA was not signed by the Government. The SSFA was drafted and was signed by UNEP. The country informed that the procedure requires the approval of Cabinet Ministers. It needs extra time. Legal arrangements (actual/planned): SSFA drafted in Jan-2014 and sent to country for considerations___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve:. ___ If Yes, will delay have impact on project completion date (yes/no): yes ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Follow up on IS SSFA signature in Feb-2015, Mar-2015 and Apr-2015. Country sent an amended version of SSFA approved by Cabinet in May-2015; this will require a new UNEP's signature of the amended version. Country also requested to modify some clauses; these proposed modifications required consultation with the legal department. Legal department answered requested modification to the agreement in Jun-2015. Agreement as cleared by legal department sent to country for their consideration in Jun-2015. | 0
UNEP | Bahrain | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2020-12-01 | 470000 | 120000 | 51015 | 3.8835 |  |  | 0 |  |  | `• Brief progress report (actual/planned): - Enact the new ODS Regulation 54/2014 for the control of ODS and start preparing the respective bylaws under the enforcement component of the HPMP - Concluding the executing arrangements at the national level where Bahrain Society of Engineers (BSE) will be the main executing agency under the supervision of the Supreme Council of Environment (SCE) - Finalize and sign the country contracts - Form Project Steering Committee composed of SCE and BSE with advisory role to UNEP • Legal arrangements(actual/planned): Two legal instruments signed; one with the Bahrain Society of Engineers and one with the Supreme Council for Environment • First mission (actual/planned): No mission needed since UNEP-ROWA is based in Bahrain • TOR completed(actual/planned): TORs for the technical components were drafted and reviewed by the Project Steering Committee • First disbursement date (actual/planned): First disbursement under both legal instruments will be in 2015 since contracts signed end of 2014 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in concluding national executing arrangements, signing the contracts and start of work. After signature of contracts end of 2014, expedited work-plan is agreed to compensate delays • If Yes, will delay have impact on project completion date (yes/no): Yes, impact on submission the 2nd tranche by one year • Any ongoing problems (yes/no): No • If Yes, is any action required by ExCom: No | # Finalize the preparatory arrangements for the technical components of reviewing/updating the national standards and the establishment of national certification scheme # Processing the first payments of the country contracts (expected to be received by the country by end of June 2015) # Develop special publication on the enforcement of the new ODS Regulation as part of the enforcement campaign under the HPMP and design special enforcement sessions for different stakeholders # Start forming the working group of updating the national certification scheme in cooperation with the Ministry of Labor | 0
UNEP | Bahrain | CFC Phase Out Plan | 2006-11-01 | 2014-12-01 |  | 330000 | 305000 | 80000 | 0 | 20.3 |  | 0 |  |  | Project Completed, remaining funds transferred to HPMP as per Decision 68/33, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 68/33, respective progress is under the HPMP project | 0
UNEP | Bangladesh | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2018-12-01 | 355000 | 320000 | 54170 | 3.7491 |  |  | 0 |  |  | Brief progress report (actual/planned): Amendment done to the “Ozone Depleting Substances (Control) Rules, 2004”. So far 614 technicians trained by 4 master trainers through 12 Training workshops. 1,000 copies of 5 booklets on good servicing practice printed in Bengali. Factsheet on energy efficiency and servicing sector printed and distributed. Legal arrangement (actual/ planned): SSFA signed in November 2013. First mission (actual/ planned): 8-11/08/2010. TOR completed (actual/ planned): N/A. First disbursement date: 16/12/2013. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delayed in signing the agreement. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Enforcement Training organized in Feb. 2015. DoE and NBR agreed to prepare a MoU for inter-agency collaboration on Montreal Protocol enforcement. Customs Quick Tool and the “Training Manual: Green Trade for the Protection of the Ozone Layer” were prepared and distributed. 5 units of refrigerants identifiers delivered in 2nd quarter of 2015. Legal arrangement (actual/ planned): In May 2015, additional US$60,000 transferred to the government. | 0
UNEP | Bangladesh | ODS Phase Out Plan | 2004-04-01 | 2008-12-01 |  | 294175 | 294175 | 294175 | 0 | 87.2 |  | 0 |  |  |  |  | 0
UNEP | Barbados | HCFC Phase Out Plan (Stage I) | 2013-04-01 |  | 2020-12-01 | 192000 | 74000 | 0 | 0.88 |  |  | 0 |  |  | Brief progress report (actual/planned): the Draft Terms of Reference (TOR) for the Policy and Legislative Component of the HPMP and the TOR for the Capacity Building Component of the HPMP have been finalized, and are pending approval by the Permanent Secretary before requests for proposals are disseminated.___ Legal arrangements (actual/planned): SSFA signed in Dec-13___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): First disbursement in Dec-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in government administrative processes have delayed expeditures ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | A meeting was held with the Environmental Protection Department, Ministry of Environment and Drainage; the Refrigeration and Air Conditioning Association of Barbados; and the Samuel Jackman Prescod Polytechnic on Feb-2015 to discuss how elements of the Capacity building component of the HPMP would be implemented. PS approved TORs in Jun-2015, requests for proposals will be disseminated. | 0
UNEP | Belize | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-01 | 213500 | 80000 | 80000 | 0.79 |  |  | 0 |  |  | Brief progress report (actual/planned): the quota system is being implemented administratively. One 5-day train the trainers workshop on alternative refrigerants to HCFC Jan-2014; 13 trainers trained. Development of the RAC asociation website. Printing of brochures targeting the hotel sector. Quotas for 2015 assigned in Dec 2014. The NOU works hand in hand with refrigeration technicians association (ARACT) to ensure that from the month of October through December, a one day Training session is held for each district of the country. After the training session, the technicians take the admission exam and if they pass the exam, the technicians are granted their licenses to be able to practice refrigeration and air conditioning servicing. In early 2014 the vocational institute (ITVETS) has undertaken trials with AC’s and refrigerators using HCs. Last disbursement processed in May-2014. ___ Legal arrangements (actual/planned): Agreement signed in May 2011, amended in July 2013.___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): June 2011, second and third payment made in March and December 2013 respectively. Last disbursement made in May 2014.___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no):no ___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): n/a. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | The quota system is being implemented administratively since January 2013. In May-2015, the Cayo Center for Employment Training held a demonstration on the conversion of mobile air conditioning units, and refrigeration equipment to hydrocarbon refrigerant; some refrigeration and air conditioning technicians were able to attend. Unveiling of a billboard that promotes traning, membership and licensing of technicians in refrigeration and air conditioning servicing. Brochures and other awareness material s to encourage the phase out of HCFCs in the hotel sector are still being disseminated. Over forty eight (48) Customs Officers were trained in March and April 2015. Training was conducted in all the border points and included the enforcement unit in Orange Walk Town, Belize. Since Mar-2015, the NOU is conducting a monitoring exercise which aims to identify whether there were any stockpiles of CFC refrigerants in the market. All funds disbursed. | 0
UNEP | Belize | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 101000 | 101000 | 101000 | 0 | 3.7 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Benin | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-03-01 |  | 370000 | 170000 | 81314 | 4.8922 |  |  | 0 |  |  | Completed since december 2013 and final payment already done. |  | 0
UNEP | Benin | CFC Phase Out Plan | 2008-07-01 | 2010-11-01 |  | 150000 | 150000 | 150000 | 0 | 9 |  | 0 |  |  | Completed as Final payment ($15,000) sent in Dec 2011. | Completed | 0
UNEP | Bhutan | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 282000 | 170000 | 130245 | 0.18 |  |  | 0 |  |  | Brief progress report (actual/planned): The first-ever Certificate Course Curriculum for Refrigeration and Air Conditioning developed. The National Stakeholder Workshop on HPMP and climate and energy linkages held in June 2014. Officials from MOLHR took part in the workshop o Good Practices of RAC Servicing in Manila, Philippines, in May 2014. A two week Training of Trainers at TTI Thimphu held in August 2014. In 2014 alone, over 80 Customs officers, Customs brokers and officers from Department of Trade received training on ODS control with special focus on HCFCs. Legal arrangement (actual/ planned): The agreement was signed in May 2014. First mission (actual/ planned): March 2012. TOR completed (actual/ planned): N/A. First disbursement date: 12/06/2014 All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delayed reporting by the government. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. Awareness event with the Hotels Associations organized in January 2015. National Customs Manual was launched on the World Customs Day on 26 January 2015. 3 units of refrigerants identifiers procured in 2nd quarter of 2015. Legal arrangement (actual/ planned): As of 22 May 2015, additional US$33,000 is pending transfer to the government. | 0
UNEP | Brunei Darusssalam | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2020-12-01 | 183000 | 150500 | 79322 | 1.2432 |  |  | 0 |  |  | Brief progress report (actual/planned): In 2014, only the first tranche has been approved to Brunei Darussalam at the 66th ExCom meeting in April 2012. The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented since 2013 and continued in 2014. The NOU continues to conduct regular checks with retailers and servicing workshops to inspect whether HCFC containers are properly labelled as required. In 2014, additional 9 training workshops were organized to train 121 RAC technicians at the training center established under HPMP, Jefri Bolkiah Vocational School. The certification system has been implemented in conjunction with the training workshops of RAC technicians on code of good practice. Only RAC technician passed the theoretical and practical examination will be certified by Department of Environment, Park and Recreation, which houses the NOU. In total, 191 RAC technicians were trained and certified from 15 workshops under HPMP since 2013. As the Department of Mechanical and Electrical (DME) has already had the certification system for technical companies that would like to obtain the government projects, DEPR initiated the discussion with DME to standardize or harmonize the certification program so that a single certification system would be in place so that it would accommodate works in the private as well as government sectors. Moreover, to support HCFC phase-out effort in the country, requirement of ODS-free equipment installation in tender issued by the government has been applied to all types of RAC equipment. DEPR also initiated the dialogue with DME as well as the Energy Department on the ban of HCFC based equipment. In 2014, posters on non-HCFC based air-conditioner were developed and produced to emphasize the use of non-HCFC based air conditioners Legal arrangements (actual/planned): The SSFA has been signed in August 2012. First Mission: September 2012. TOR completed: N/A First disbursement date: December 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Training workshops of RAC technicians is planned in 2015, but will be organized when the second tranche of HPMP is released to the country. As a follow-up to the discussion in 2014, the meeting between DEPR, DME and Energy Department concluded that the ban on equipment would fall under the purview of the Energy Department under their Energy, Efficiency and Conservation Act (EEC). If the regulation is established, the grace period would be one year after announcement. This includes the amendment to the existing Custom’s Act-Prohibition and Restriction on Imports and Exports 2006 to ban the import of HCFC-based RAC equipment. Moreover, DEPR is reviewing the existing regulations to determine whether there are any restrictions on the use of flammable refrigerant in RAC sector the country. DEPR is consulting with relevant authorities to examine when (i) the restriction to sale refrigerant to only certified technicians and (ii) the mandatory requirement that only certified technicians will be allowed to handle or service RAC equipment can be put in place. The second tranche was approved at the 74th ExCom meeting in May 2015. 2014 CP data was submitted online. | 0
UNEP | Burkina Faso | HCFC Phase Out Plan (Stage I) | 2010-12-01 | 2014-12-01 |  | 546168 | 240000 | 120000 | 6.9363 |  |  | 0 |  |  | Completed as final payment ($25,000) in Dec 2013. | Completed | 0
UNEP | Burkina Faso | CFC Phase Out Plan | 2006-11-11 | 2009-03-01 |  | 180000 | 203000 | 202369 | 0 | 5.4 |  | 0 |  |  | Completed as TPMP 2nd Tranche Final payment ($1,000) sent 16 Aug. 2011 | Completed | 0
UNEP | Burundi | HCFC Phase Out Plan (Stage I) | 2011-11-01 | 2014-11-01 |  | 172000 | 75000 | 45000 | 1.2952 |  |  | 0 |  |  | Completed in November 2013. Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in March 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2012 __ All funds disbursed (yes): _ Final payment processed in April 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | SSFA of HPMP tranche 2 signed by the country on 21/04/2015 | 0
UNEP | Burundi | CFC Phase Out Plan | 2008-07-01 | 2013-12-01 |  | 115000 | 115000 | 114730 | 0 | 8.9 | 0 | 0 |  |  | Completed as Final payment ($10,730) sent in June 2013. | Completed | 0
UNEP | Cambodia | HCFC Phase Out Plan (Stage I) | 2010-07-01 |  | 2031-12-01 | 950000 | 250000 | 189411 | 8.9062 |  |  | 0 |  |  | Brief progress report (actual/planned): In 2014, Cambodia have alreay received the first and the second tranches at the 61st and 70th ExCom Meeting. The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented since 2013 and continued in 2014. NOU conducted monthly spot check of the retailers, import companies and service workshops located in Phnom Penh and quarterly for those located in the provinces. The Customs Handbook has been translated into local (Khmer) language and is under reviewing. NOU initiated the discussion with the General Department of Customs and Excise on how to put training courses on the Montreal Protocol in place, but there was no conclusion reached. In 2014, workshops for enforcement officers were held on 26-27 Feb. 2014 at Battambang Province with 32 participants and on 24-25 June 2014 at Kampong Cham province with 35 participants. In total, about 170 enforcement officers were trained from 5 workshops organized since the implementation of Cambodia HPMP. For RAC technicians training, NOU organized 2 training workshops, i.e. on 19-20 March 2014 at Kampong Cham province with 32 participants and on 25-26 November 2014 in Phnom Penh with 36 participants. In total, about 193 RAC Technicians were trained from 6 workshops organized since the implementation of Cambodia HPMP. UNEP training manual has been translated and distributed to the vocational training schools and RAC technicians attended the training. Round table discussion with National TV Channel on the implementation HPMP was conducted on 12 September 2014 and rebroadcasted on 15, 16 and 17 September 2014. Legal arrangements (actual/planned): The SSFA for the first and the second tranche was signed in Nov 2010 and March 2014 respectively. The SSFA for the fitst payment has been closed due to the tranche completion in December 2013. First Mission: September 2011. TOR completed: N/A First disbursement date: December 2010 (of first tranche). All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Training workshops of enforcement officers and RAC technicians are planned in 2015. It is planned that 500 Customs handbooks in local language will be publicized in 2015. NOU is discussing with the Department of Customs and Excise to include training on the Montreal Protocol in place. NOU have discussed with some of vocational training school on how to enforce the certification requirement of RAC technician and to recruit more centers in specific provinces and the standard testing procedure have in place. 2014 CP data was submitted online. | 0
UNEP | Cambodia | CFC Phase Out Plan | 2007-11-01 | 2010-03-01 |  | 170000 | 170000 | 170000 | 0 | 14.1 | 0 | 0 |  |  | Project financially completed |  | 0
UNEP | Cape Verde | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2016-07-01 | 160000 | 79000 | 24000 | 0.1 |  |  | 0 |  |  | Brief progress report (actual/planned): Under the second tranche UNEP amended the SSFA for extention till Dec 2014. Amended SSFA signed by country a. Country submited interim HPMP reports in September 2014 and UNEP processed the 2nd payment ($10,000) in October 2014. Legal arrangements (actual/planned): Agreement signed in February 2012. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2012 __ All funds disbursed (yes/no): _ Final payment being processed in June of 2014.__ Any delay? (yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: Delay in implementing activities, SSFA amended for extension. ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Country organized training of trainers for customs officers (3 experts) and police officers (2 officers) as trainers on identification and control of HCFCs and HCFCs based equipment in March 2015 in Praia; a training of 47 refrigeration technicians in Praia in March 2015 was held . | 0
UNEP | Cape Verde | CFC Phase Out Plan | 2008-04-01 | 2009-12-01 |  | 100000 | 100000 | 100000 | 0.3 | 0.3 | 0 | 0 |  |  | Completed as Final payment ($10,000) sent in March 2011. | Completed | 0
UNEP | Central African Republic | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2017-07-01 | 310000 | 75000 | 45000 | 2.325 |  |  | 0 |  |  | Country still in political unrest. No activities undertaken in 2014. | Country still in political unrest. UNEP met with the Minister and the Director of Environment in March 2015 in Cairo | 0
UNEP | Central African Republic | CFC Phase Out Plan | 2008-07-01 | 2012-12-01 |  | 105000 | 105000 | 105000 | 0 | 1.7 |  | 0 |  |  | Completed as Final payment ($11,200) sent. Dec 2012 | Completed | 0
UNEP | Chad | HCFC Phase Out Plan (Stage I) | 2010-12-01 | 2014-06-01 |  | 325000 | 170000 | 95000 | 3.2674 |  |  | 0 |  |  | Completed as Final payment ($5,000) sent. Oct 2012 | Completed | 0
UNEP | Chad | CFC Phase Out Plan | 2007-11-01 | 2010-03-01 |  | 171000 | 171000 | 171000 | 0 | 5.2 |  | 0 |  |  | Completed as Final payment ($1,000) sent in July 2010. | Completed | 0
UNEP | Chile | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 288489 | 220366 | 83848 | 3.55 |  |  | 0 |  |  | Brief progress report: Activities will be merged with those outstanding of first tranche. Legal arrangements: A new agreement will be signed once outstanding activities of first tranche are near completion. First disbursement date (actual/planned): Planned for 2015. All funds disbursed? No. Any delay? Yes. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | 2015 annual implementation and procurement plan being drafted. Mission planned for July 2015 to finalize workplan and implementation modalities under UMOJA. | 0
UNEP | Chile | Methyl Bromide | 2010-04-01 |  | 2016-03-31 | 73000 | 73000 | 27812 | 0 |  |  | 0 |  |  | Brief progress report: An informative booklet with applicable alternatives to MB was designed and distributed among producers of strawberries in May-14. Discussions on the agreement related to the web-based MB tracking system with Servicio Agricola y Ganadero (SAG) has been resumed by the NOU. Mission in Jun-14 to discuss and agree on funding and activities to be carried out. Additional discussions took place between the NOU and SAG on the agreement. A revised version of the SSFA was sent to UNEP in Sep-2014 that required consultation with legal departement. A counterproposal of SSFA with legal department observations was sent to NOU fro their consideration on Oct-2014. An additional modification to the SSFA was requested by NOU in Nov-2014. UNEP's legal department agreed with this modification and SSFA is ready for signature, Dec-14 . Legal arrangements: SSFA signed in July 2013.___ First mission: n/a___TOR completed (actual/planned): N/A. First disbursement date: August 2010. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: terms of the agreement were modified by SAG and NOU several times. Those changes required the clearance of legal department of UNEP. Consultations with legal department of UNEP on modifications proposed by counterparts were requested and followed-up ina prompt manner. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | Rephasal of corresponding budget line in 2015 was requested in Jan-2015: this is necessary to create the obligation in the system and for signature of the RD. RD signed in Jan-2015. SSFA sent to country for signatures in Feb-2015. Follow up on signatures in Apr-2015. Both SAG and Minsitry of Environment (NOU) have signed the agreement. Agreement was sent to Ministry of Foreign Affairs for cleareance before Comptroller's final approval to start implementation. | 0
UNEP | China | HCFC Phase Out Plan (Stage I) - Servicing Sector, including enabling | 2011-07-01 |  | 2016-12-01 | 5240000 | 4454000 | 2487100 | 47.1 |  |  | 0 |  |  | Brief progress report (actual/planned): Code/standards development plan in the servicing sector for both the industrial/commercial refrigeration and air conditioing, and room air conditioniner sectors were finalized in 2014 following consultations, revisions; The training material on good practices was developed, revised and completed by the end of 2014; Organized a public bidding process for the selection of the national/regional training centers following government rules/procudures, and contracted 6 training institutions, i.e. 2 as national training centers, 4 as regional training centers; Organized kick-off training workshop in Shanghai on 1 July 2014 with 40 participants; Organized a two-day Train-the-Trainers workshop on 17-18 September 2014 at Guangzhou Light Industrial Mechanic School with 50 participants; The training centers were prepared to organize the their training, and completed their equipment procuremen following FECO's advice; Shanghai Jigao Vocational Training School, Guangzhou Light Industrial Mechanic School, Shougang Institute Technology (SGIT) organized their training to technicians. The Vocational Training and Qualification Certification Association of China finalized their feasibility study to incorporate requirements on environmental practices into the existing qualification certification syllabus of refrigeration servicing technicians; FECO/MEP and CRAA commenced a joint work in July 2014 to revise the existing voluntary system and to encourage more participation in the existing scheme. The CRAA engaged the stakeholders for their input; Organized Ozone2Climate Industry Roadshow and Roundtable in Beining in April 2014; Coordinated the implementation of Shenzhen Pilot project as planned; Organized a Launch Meeting and Training Workshop in March 2014 in Beijing with around 100 participants from 35 provinces, autonomous regions and municipalities and selected cities; organized a workshop to train government officers on ozone issue in Chongqing, December 2014, with 40 participants from 12 west and south-west provinces; Organized a training workshop targeting the ODS importer and exporters in Guangzhou on 20-22 April 2014 with 70 participants; Organized a training workshop targeting the officers from Local License Bureaus under the Ministry of Commerce (MoC) in Xining City on 24-27 June 2014with 100 participants; The capacity building of four Custom’s Branches at Huangpu, Shanghai, Ningbo, and Urumqi was completed by the end of 2014. Each Custom’s Branch held a series of training courses. Memo of Understanding was signed with the Anti-smuggling Bureau of General Administration of China Customs (GACC) in November 2014 to extend to 10 more Custom Branches such as Shenzhen, Nanjing, Qingdao, Nanning, Harbin, Xiamen, etc. Delegations from Bangladesh, Democratic People’s Republic of Korea, Pakistan, and the Philippines visited China in 2014 to discuss ODS import/export management and control. In these visits, each delegation visited China covered their own expenses. However, a small amount of funds from the HPMP China (Stage I) was used to cover local expenses for FECO/MEP to participate in the local visit to allow investigation into ODS illegal trade cases. From 3- 10 December 2014, six members from FECO, MOC and GACC visited Singapore and Indonesia to discuss and exchange ODS import and export management experience and how to enhance the capacity building of enforcement officers. The China-Lao’s Roundtable Dialogue was jointly organized by UNEP and FECO/MEP from December 23-25 2014 in Mengla city, Yunan Province. About 50 participants, of whom 90% were from the local Customs of both China and Lao, took part in the roundtable discussion. A Public Service Announcement (PSA) on ozone layer protection was initiated for development; On the occasion of the commissioning of the demonstration project in Yantai Moon Group in March 2014, Midea R290 production line in July 2014 and the signing ceremony of Qingdao Haier Group in March 2014, members of major national press, including Xinhua News Agency, were invited to cover these events. FECO/MEP organized a range of activities for the 2014 celebration of the International Day for the Preservation of the Ozone Layer (“Ozone Day”), including organisation of a coordination meeting with international agencies on 11-12 September 2014, an important meeting with the participant of Mr. Zhai Qing, the Vice Minister of MEP, Ms. Tina Birmpili, the Executive Secretary of the Ozone Secretariat, international and domestic partners and media journalists on 15 September, and a table tennis match with the name of ozone layer protection. During the Ozone Day celebration meeting, FECO/MEP announced the bidding results for the closure of 5 HCFC production lines for the 2015 10% reduction of HCFCs. Legal arrangements(actual/planned): PCA amended in Oct 2014. First mission (actual/planned): Sep 2014; First disbursement date (actual/planned):Oct 2014; All funds disbursed (yes/no): no Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: There was delay in signing Amendmnet, but project activities were being implemented. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): N0 | FECO/MEP is planning to select 5-8 more training centres nationwide in other provinces; The training centres organized training workshops like Shandong Institute of Commerce and Technology in March 2015. organized a workshop to train government officers on ozone issue in Fuzhou, Fujian province, January 2015, with 40 participants from the south and south-east provinces. The procured 30 sets of the latest model of portable refrigerants identifiers are expected to be delivered by June 2015. | UNEP condiers FECO as final beneficiary
UNEP | China | Refrigeration Servicing | 2005-04-01 | 2010-12-01 |  | 450000 | 450000 | 450000 | 0 | 8672.8 | Not available | 0 |  |  | Project was already completed. |  | 0
UNEP | Colombia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2015-12-01 | 100000 | 100000 | 89128 | 1.91 |  |  | 0 |  |  | Brief progress report: The implementation of the HPMP (second tranche) is progressing without significant delays. Disbursements released through the UNDP country office according to the advance of activities. Intermediate goals achieved in 2014 are as planned: (a) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port; (b) The NOU and Customs collected data on ODSs trade across the country through monitoring the facilities of ODS suppliers in order to prevent ODS illegal trade; (c) A specific study on HCFCs used in Colombian-flagged ships was completed. The study is aimed to gain a better understanding of HCFC uses in this sub-sector and also facilitate the assessment of new measures to prevent the ODSs illegal trade. Legal arrangements (actual/planned): The signature of SSFA to implement the first tranche activities was completed in July 2012, while it initially was planned in May 2011. In December 2012, the SSFA was amended to include activities approved in the second tranche. A second amendment was signed in May 2014. First mission: July 2014 while no specific date was established in the project document. TOR completed: N/A. First disbursement date: December 2012/ Planned for October 2012. All funds disbursed? No. Any delay? Late start of the project has been partially recovered. The HPMP was initially planned to be completed in April 2014. Completion date has now been rescheduled for December 2015. If Yes, reasons for delay & action plan to resolve: Administrative reasons. Late start of the project is due to the signature of agreement. If Yes, will delay have impact on project completion date: Yes, an 8 months delay expected. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | Brief progress report: The implementation of the HPMP (second tranche) is progressing without significant delays. Disbursements released through the UNDP country office according to the advance of activities in April 2015. Intermediate goals achieved in 2015 are as planned: (a) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port; (b) The NOU and Customs collected data on ODSs trade across the country through monitoring the facilities of ODS suppliers in order to prevent ODS illegal trade; (c) National manual to Customs trained has been published. Legal arrangements (actual/planned): The signature of SSFA to implement the first tranche activities was completed in July 2012, while it initially was planned in May 2011. In December 2012, the SSFA was amended to include activities proved in the second tranche. A second amendment was signed in May 2014. First mission: July 2014 while no specific date was established in the project document. TOR completed: N/A. First disbursement date: December 2012/ Planned for October 2012. All funds disbursed? No. Any delay? Late start of the project has been partially recovered. The HPMP was initially planned to be completed in April 2014. Completion date has now been rescheduled for December 2015. If Yes, reasons for delay & action plan to resolve: Administrative reasons. Late start of the project is due to the signature of agreement. If Yes, will delay have impact on project completion date: Yes, an 8 months delay expected. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A | 0
UNEP | Comoros | HCFC Phase Out Plan (Stage I) | 2011-07-01 | 2014-07-01 |  | 160000 | 79000 | 44000 | 0.05 |  |  | 0 |  |  | Completed as Final payment ($15,000) sent. Sept 2013 | Completed | 0
UNEP | Comoros | CFC Phase Out Plan | 2007-07-01 | 2011-12-01 |  | 130000 | 130000 | 124022 | 0 | 0.4 |  | 0 |  |  | Completed as Final payment ($18,000) sent. Feb. 2012 | Completed | 0
UNEP | Congo | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-12-01 |  | 175000 | 75000 | 45000 | 1.775 |  |  | 0 |  |  | Completed. Country submitted final activity report and expenditure report in April 2014. UNEP proceeded with the Final payment in June 2014. | Completed | 0
UNEP | Congo | ODS Phase Out Plan | 2008-04-01 | 2012-01-01 |  | 110000 | 110000 | 110000 | 0 | 1.8 |  | 0 |  |  | Completed in May 2012 | Completed | 0
UNEP | Congo, DR | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-07-01 | 235000 | 211500 | 180000 | 2.87 |  |  | 0 |  |  | Completed as final payment sent in december 2013. | Completed | 0
UNEP | Congo, DR | CFC Phase Out Plan | 2006-07-01 | 2011-12-01 |  | 287500 | 287500 | 287500 | 0 | 99.8 |  | 0 |  |  | Completed as TPMP 3rd Tranche Final payment sent ($3,000). Feb. 2012 | Completed | 0
UNEP | Cook Islands | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 99000 | 89100 | 46125 | 0.0231 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted. The license requirement for technician in handling HCFCs and for workshop/dealer in storing and sales of HCFCs has been implemented in 2014. Cook Islands was in the process of amending the regulation to ban the import of HCFC-based equipment. Refrigerant identifier was handed over to Customs for inspection. National training workshop for RAC technicians was organized in January 2014 with 30 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in December 2011. First Mission: August 2013 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. | 0
UNEP | Cote D'Ivoire | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2014-04-01 | 905740 | 250000 | 142966 | 11.0778 |  |  | 0 |  |  | Brief progress report (actual/planned): Three (3) workshops for customs officers and environment inspectors have been organized between March and May 2014: in Abidjan (37 officers), in Daloa (38 officers) and in San-Pedro (25 officers). A total of one hundred (l00) officers have been trained in 2014. Three refrigerant identifiers were purchased and are being used as training tool kit. Three more workshops for one hundred and seven (107) refrigeration technicians and thirteen (13) marine officers have been organised between March and May 2014 in Abidjan, Divo and San-Pedro. 2.__ Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _ ExCom approval was US$250,000; it was split into 2 SSFAs, for US$145,000 and US$105,000 respectively, each to run for one year. 1st disbursement done in September 2012 __ All funds disbursed (yes/no): yes. .__ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: The main reason was the war in Cote d`Ivoire. Situation returned to normal and First SSFA completed. Second SSFA signed by country on 19/02/2015___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | SSFA for 145,000$ completed. SSFA for 100,000$ signed by the country on 19/02/2015 | 0
UNEP | Cote D'Ivoire | CFC Phase Out Plan | 2008-04-01 | 2012-02-01 |  | 282000 | 282000 | 282000 | 0 | 44.1 |  | 0 |  |  | Completed as Final payment ($29,000) sent. Feb. 2012 | Completed | 0
UNEP | Djibouti | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2016-04-01 | 164500 | 81000 | 50000 | 0.24 |  |  | 0 |  |  | Brief progress report (actual/planned): Country submitted interim progress report on HPMP showing that two training workshop for refrigeration technicians were organized in 2014: 35 technicians trained. Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in August 2012 __ All funds disbursed (yes/no): _ SSFA up to Apr-16.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): two training workshop for refrigeration technicians were organized in March and June 2015: 55 technicians trained. Two training workshops for customs officers in March and May 2015: 50 customs trained. Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in August 2012 __ All funds disbursed (yes/no): _ SSFA up to Apr-16.__ Any delay? | 0
UNEP | Djibouti | CFC Phase Out Plan | 2007-11-01 | 2014-12-01 |  | 138000 | 138000 | 138000 | 3.15 | 3.2 |  | 0 |  |  | Completed. SSFA renewed and signed by country and UNEP in April 2013. $18,000 balance returned in 2014 and project closed. | Completed | 0
UNEP | Dominica | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2015-12-01 | 164500 | 82250 | 10061 | 0.08 |  |  | 0 |  |  | Brief progress report (actual/planned): NOU requested UNEP to contract consultant services for training and coordination of HPMP. The request for contracting consultant services coincided with financial closure of 2014. UNEP followed up with NOU in the beginning of 2015 but no further communication received on this matter. ___ Legal arrangements (actual/planned): SSFA signed in Sept 2013.___ First mission (actual/planned): ___ TOR completed (actual/planned): TORs for regional and national consultants have been drafted. ___ First disbursement date (actual/planned): First disbursement in Apr 2013.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes.___ If Yes, reasons for delay & action plan to resolve: Outstanding progress and financial reports to process further disbursements of SSFA. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: n/a.___ | Agreement expired in January 2015. Financial and progress reports sent on February 2015. Next disbursement coud not be processsed because progress report required additional information. NOU has been contacted several times to provide additional information but has not responded. Mission approved for 2Q of 2015. UMOJA travel restrictions. Mission re-scheduled for July 2015 once UMOJA is operative. | 0
UNEP | Dominica | CFC Phase Out Plan | 2006-04-01 | 2013-12-01 |  | 114000 | 114000 | 114000 | 0 | 0.2 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Dominican Republic | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2015-12-01 | 50000 | 50000 | 25000 | 0.85812 |  |  | 0 |  |  | Brief progress report: The HPMP second tranche implementation was approved in July 2013. Its implementation has been deferred to 2015 because there was no tranche for UNEP and the country decided to continue implementation of the second tranche (non-investment components) in the year of 2015. Legal arrangements: N/A. First disbursement date (actual/planned): No disbursements/Planned for October of 2015 (some delays because of UMOJA). All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: A managerial decisions is the reason for the late start of the project. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The Government continued to enforce the ODS rules and regulations that have been established since 2012, with regard to HCFCs. A policy to ban the import of HCFC-141b contained in imported pre-blended polyols will be in effect from 1 January 2016, and a draft resolution to ban the use of HCFC-141b for flushing in the refrigeration servicing sector has been prepared, and is expected to be completed by end of 2015. In cooperation with Implementing Agencies the progress report and annual implementation plan were submitted to request the third tranche. The NOU and UNEP agreed on specifications to purchase ODSs identifiers. Bidding process expected to be completed by the second half of 2015. Legal arrangements: N/A. First disbursement date (actual/planned): No disbursements/Planned for 2015. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: A managerial decisions is the reason for the late start of the project. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | 0
UNEP | Ecuador | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 115000 | 50000 | 45186 | 1.3591 |  |  | 0 |  |  | Brief progress report: Project progressed satisfactorily. National Consultant hired to assist in the liason between NOO and Customs. Intermediate goals achieved in 2014 are as planned: (a) HCFC quota system implemented; (b) HCFC baseline kept; (c) Customs training delivered to 32 customs officers. (d) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port. Legal arrangements: N/A. Funds directly administered by UNEP ROLAC as requested by the NOU. First disbursement date (actual/planned): January 2014/Planned for December 2013. All funds disbursed? No. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: Project progressed satisfactorily. National Consultant hired to assist in the liason between NOO and Customs. Intermediate goals achieved in 2015 are as planned: (a) HCFC quota system implemented; (b) HCFC baseline kept; (c) Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port. Legal arrangements: N/A. Funds directly administered by UNEP ROLAC as requested by the NOU. First disbursement date (actual/planned): January 2014/Planned for December 2013. All funds disbursed? No. Any delay? No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | 0
UNEP | Ecuador | CFC Phase Out Plan | 2010-07-01 | 2013-12-01 |  | 193155 | 193155 | 78558 | 0 |  |  | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | El Salvador | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 375000 | 185000 | 31372 | 3.1521 |  |  | 0 |  |  | Brief progress report: Meetings with ODS importers for 2014 quota allocation; preparation and signing of Executive Agreement No. 52, setting up quota system and reduction targets; diffusion through media of the actions performed with support of the MLF of the Montreal Protocol to protect the ozone layer in the framework of the International Day for the Preservation of the Ozone Layer in 2014; training of customs officers on prevention of ODS illegal trade and use of refrigerant identifiers. Legal arrangements (actual/planned): Tri-partite agreement signed by the Government, UNEP, and UNDP Country Office in November 2013. First mission (actual/planned): It was carried out in July 2013, while no specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): Financial authorization issued in November 2013. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: UNEP’s HPMP components and ISP were incorporated into a UNDP ProDoc for implementation of activities, but investment activities were prioritized. However, all planned activities will be completed during last half of 2014 and 2015. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | Progress and financial report sent on Feb-2015. Second financial authorization processed in Apr-2015. Agreement expired. Drafting of new agreement ongoing and to be implemented after UMOJA goes live. | 0
UNEP | El Salvador | CFC Phase Out Plan | 2007-11-01 | 2012-06-01 |  | 50000 | 50000 | 50000 | 0 | 46 | Not available | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Equatorial Guinea | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2013-11-01 | 165000 | 70000 | 21985 | 1.1524 |  |  | 0 |  |  | Brief progress report (actual/planned): One refrigeration workshop for 25 participants on recovery and recycling was organized in August 2014. Also an awarness workshop for importer of refrigerant has been organized in October 2014._ Legal arrangements (actual/planned): Agreement signed in February 2012. . __ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2012__ All funds disbursed (yes/no): _ No. SSFA has a balance of US$13,000.__ Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: The delay was due to the problems encountered by the Implementing Agencies to travel to Malabo but UNEP decided to use an Expert from a neighboring country (Gabon) to start activities ___ If Yes, will delay have impact on project completion date (yes/no): _NO __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | UNEP CAP organized a mission to Malabo in March 2015. A workshop for 20 Customs officers on identification of ODS and application of the quota system organized in Malabo in March 2015. | 0
UNEP | Equatorial Guinea | ODS Phase Out Plan | 2009-04-01 | 2014-06-01 |  | 180000 | 105000 | 80000 | 4.6 | 4.7 |  | 0 |  |  | Project closed in 2014 due to slow implementation and disbursment and balance returned. | Project closed | 0
UNEP | Eritrea | HCFC Phase Out Plan (Stage I) | 2012-07-01 |  | 2016-07-01 | 84500 | 40000 | 2818 | 0.01541 |  |  | 0 |  |  | Brief progress report (actual/planned): Country recruited Ozone Officer in June 2014. CAP undertook a mission in Dec 2014 to train Ozone Officer on speedy implementation of the Montreal Protocol activities and prepared all pending reports. Legal arrangements(actual/planned): SSFA was prepared and signed by the country. Initial stages of project implementation(actual/planned): Not achieved due to the delay in appointing ozone officer__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): Disbursement has delayed due to the launch of UMOJA_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | SSFA was signed by country, awaiting first disbursement and disbursement delayed due to the launch of UMOJA. Country has registered all the importesr of HCFC for 2015 | 0
UNEP | Eritrea | ODS Phase Out Plan | 2008-04-01 | 2014-12-01 |  | 170000 | 170000 | 80000 | 0 | 6.2 |  | 0 |  |  | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The country has been without an Ozone Officer for a long time, resulting in delay in implementation of activities in the country. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in April 2010. Initial stages of project implementation(actual/planned): Not achieved due to the delay in appointing ozone officer__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Implementation of activities has resumed__ First disbursement date (actual/planned): The first disbursement was made in May 2010, not as planned._ All funds disbursed (yes/no): NO, Country submitted all the reports awaiting disbursement of final payment_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _Country did not have Ozone Officer for a long time__ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | NOU registered all importers of HCFC for 2015, supported the planning meeting of the Refrigeration Association and undertook inspection visits to shops to check what type of refrigerant is sold on the market | 0
UNEP | Ethiopia | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2016-12-01 | 175000 | 85000 | 80000 | 1.0667 |  |  | 0 |  |  | Brief progress report (actual/planned): _Country conducted National Customs training where asbout 90 customs officers from various boarders were trained. Country trained 30 Refrigeration technicians in standards and certification during the Regional Workshop which was hosted by the country.__ Legal arrangements(actual/planned): SSFA signed and first payment sent in June 2013___ First mission (actual/planned): __UNEP conducted a Joint mission with UNIDO in December 2013 and met all stakeholders involved in the implementation of the project to plan for the speedy implementation of activities.Another mission by CAP to conduct customs officer training was done inAugust 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): first payment sent in June 2013___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): __Yes_ If Yes, reasons for delay & action plan to resolve: _The project experienced some delays due to the change of the Montreal Protocol Focal Point from Meteorological Department to Minsitry of Environment. CAP trained the new NOU and implementation of activities is on track.__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | NOU registered all importers of HCFC for 2015, advertised for quota allocation for 2015 HCFC importation and conducted inspection visists to various boarders to check how customs officers are enforcing the control measures of HCFC imporation | 0
UNEP | Fiji | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 125000 | 72300 | 47900 | 1.176 |  |  | 0 |  |  | Brief progress report (actual/planned): The first and the second tranche of HPMP was approved at the 65th ExCom and the 73rd ExCom Meeting in November 2014 respectively. In 2014, a total of 119 RAC technicians were trained at National Training & Productivity Centre from the workshops in April, May, October and November. All trained technicians granted licenses are recorded within NOU database. In May 2014, the training of enforcement officers was organized in the Central Division and 17 officers were trained. Moreover, enforcement officers were trained on the job and through WCO- UNEP e- learning. Refrigerant identifiers procured under HPMP have been kept at the NOU. When the ODS shipment arrives, the Customs contacted the NOU to bring refrigerant identifier for inspection during the Customs clearance. Four sets of refrigerant identifiers would be distributed once the contract between NOU and the Customs is vetted by the Solicitor- General’s Office. Ongoing awareness raising and monitoring activities of HPMP were held in 2014. Awareness materials were developed time to time upon need basis especially for Customs/ Shipping agents and Enforcement Officers. Materials included pamphlets, posters and Customs booklet for identification of ODS. First tranche was completed in December 2014. After the ExCom approval of the 2nd tranche, UNEP worked with the NOU to draft the SSFA. Legal arrangement: The SSFA for the first tranche has been signed in September 2012. TOR completed: N/A First disbursement date: September 2012 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | First tranche completed and he last payment has been made to Fiji in December 2014. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. For second tranche, UNEP and the country prepared and agreed on a detailed work plan of the second tranche of HPMP (2015-2016), which was finalized in February 2015. The draft SSFA has been prepared based on agreed work plan and is being reviewed by the Solicitor- General’s Office. 2014 CP data timely submitted online. | 0
UNEP | Gabon | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-07-01 | 290100 | 136000 | 53251 | 5.5871 |  |  | 0 |  |  | Brief progress report (actual/planned): 35 Refrigeration technicians have been trained on 16 September 2014. Two awareness workshop of around 200 participants have been organized in June 2014 in Libreville and Port Gentil .___ 2.__ Legal arrangements (actual/planned): Agreement signed in November 2011. All activities under the SSFA are completed (as planned) ___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in Jan. 2012. __ All funds disbursed (yes/no): _ Yes. Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: Change of NOO ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Completed | 0
UNEP | Gabon | CFC Phase Out Plan | 2007-07-01 | 2011-12-01 |  | 115000 | 115000 | 97555 | 0 | 1.5 |  | 0 |  |  | Completed in December 2013 | Completed | 0
UNEP | Gambia | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2016-07-01 | 110000 | 48000 | 15740 | 0.27238 |  |  | 0 |  |  | Brief progress report (actual/planned): _The NOU conducted training for 60 refrigeration technicians and 40 Custom Officers on ODS control. The country procurred and distributed toolkits to the Refrigeration Association. NOU conducted inspection visists to the fish factories to check what refrigerants are being used and discuss with companies on the switch to ODS alternatives . Implementation of first tranche activities completed and country is processing to start implementation of second tranche activities. Legal arrangements(actual/planned):SSFA was signed in March 2012___ First mission (actual/planned): __UNEP conducted first mission in May 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement ($10,000) was made in April 2012.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Project completed and second tranche was approved. | 0
UNEP | Gambia | CFC Phase Out Plan | 2007-11-01 | 2011-03-01 |  | 165000 | 165000 | 165000 | 0 | 3.6 |  | 0 |  |  | Project completed |  | 0
UNEP | Grenada | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-01 | 210000 | 105000 | 52032 | 0.3 |  |  | 0 |  |  | Brief progress report (actual/planned): HCFC electronic licensing system and quota system in place. Quotas for 2014 assigned in Nov-13. Mandatory reporting of HCFC and HCFC-based equipment importers in compliance during 2014. Fiscal policy already in place to included tax exemptions for EE appliances. Certification systems for technicians completed: level I and level II competency skils approved by the National Training Agency. Development of standards for refrigerants and equipment is ongoing. 30 technicians trained in good refrigeration practices. 20 customs officers trained .___ Legal arrangements (actual/planned): Agreement signed in Aug-13___ First mission (actual/planned): Mission in Nov-13___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Aug-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes ___ If Yes, reasons for delay & action plan to resolve: agreement expired in Jul-2014. Country undertaking activities with funds available.___ If Yes, will delay have impact on project completion date (yes/no): no ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | As of May 2015 activities are taking place with funds available. Discussions to include AC equipment in EE fiscal policy ongoing. Progress and financial reports to be submited by country once funds are exhausted. New agreement/implementation modalities to be discussed with country once UMOJA goes live. | 0
UNEP | Grenada | CFC Phase Out Plan | 2006-07-01 | 2013-12-01 |  | 130000 | 117500 | 108972 | 0 | 0.9 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Guatemala | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 96500 | 28250 | 0 | 0.93851 |  |  | 0 |  |  | Brief progress report: No progress. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Since January 2012, the implementation of UNEP projects was stopped because the new Minister of Enironment informed UNEP on a substantive and financial review process of the previous administration work plan and activities. UNEP specifically received a letter asking to cancel all agreements signed by the former administration and indicating that in due course new arrangements would be communicated. After 18 months of no progress in project implementation, a bilateral meeting between RNC of Latin America and the NOO was held at the margin of the Network Meeting carried out in June 2013. However, the meeting did not allow reaching a firm conclusion about how to reassume the HPMP and ISP implementation. In December 2013, an official mission to Guatemala was carried out by UNEP to oversee the situation directly on HCFC quota system approval. In January 2014, a new Minister of Environment was designated in Guatemala. For that reason a second official mission was carried out in July 2014. The RNC met new authorities in the Ministry and did follow up on the conclusions and recommendations of previous country mission carried out in December 2013. The Minister of the Environment suggested to ask to the UNDP Country office to manage the payments of services. A draft Agreement was prepared and submitted to the Division of International Cooperation of the Ministry as instructed by the Minister. However, no answer received from the Government. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Brief progress report: Slow progress. Legal arrangements: Not signed/Planned for Dec 2011. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: In June 2014, a country mission was carried out to held a meeting with the Minister of Environment and the International Cooperation Officer. After that, the Government was focused on the HCFC non-compliance situation. HCFC quotas system has been approved. However, no progress in the funds disbursement level . The Minister of Environment informed that the administration of funds should be carried out through UNEP ROLAC or UNDP Country Office. Due to no definition about who is the responsible person for HPPM implementation, UNEP has not had a valid counterpart to plan and execute activities. Another official mission is planned to second half of 2015. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | 0
UNEP | Guatemala | CFC Phase Out Plan | 2008-11-01 | 2012-12-01 |  | 65000 | 33000 | 33000 | 0 | 33.7 |  | 0 |  |  | Brief progress report: No progress. The identification of the partner to implement the technical assistance was not completed. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. A bilateral meeting with the NOO was carried-out at the margin of the LA Network Meeting in June 2013. In December 2013, an official mission to Guatemala was conducted in order to define the disbursement mechanisms to be adopted. However, the government decision was not made. A follow up mission carried out in 2014 but no immediate results achieved. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. Legal arrangements: Not signed/Planned for April 2010. First disbursement date (actual/planned): No disbursement/Planned for May 2010. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: The Government of Guatemala did not opened a special bank account for implementing the Montreal Protocol projects. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Project balance to be returned to Multilateral Funds. | 0
UNEP | Guatemala | Methyl Bromide | 2009-11-01 | 2014-12-01 |  | 70000 | 70000 | 0 | 0 | 320.6 |  | 0 |  |  | Brief progress report: No progress. The identification of the partner to implement the technical assistance was not completed. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. A bilateral meeting with the NOO was carried-out at the margin of the LA Network Meeting in June 2013. In December 2013, an official mission to Guatemala was conducted in order to define the disbursement mechanisms to be adopted. However, the government decision was not made. A follow up mission carried out in 2014 but no immediate results achieved. The 71th ExCom requested UNEP to partially return the project budget because Guatemala could not reach the MB total phase-out in January 2013. Legal arrangements: Not signed/Planned for April 2010. First disbursement date (actual/planned): No disbursement/Planned for May 2010. All funds disbursed? No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: The Government of Guatemala did not opened a special bank account for implementing the Montreal Protocol projects. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? Yes, NOU is working in a silo approach, without enough communication with authorities in the Ministry of Environment and limited impact amongst main country stakeholders. Those actions drove to a lack of information on Montreal Protocol country commitments at the high level authorities of the Ministry of Environment. If Yes, is any action required by ExCom? ExCom may advice the country about high level authorities should be more involved in Montreal Protocol implementation. | Project balance to be returned to Multilateral Funds. | 0
UNEP | Guinea | HCFC Phase Out Plan (Stage I) | 2012-04-01 | 2014-12-01 |  | 327000 | 145000 | 75000 | 3.9978 |  |  | 0 |  |  | Completed as final payment sent to the country in December 2013. | Completed | 0
UNEP | Guinea | CFC Phase Out Plan | 2008-07-01 | 2011-12-01 |  | 132000 | 132000 | 131000 | 0 | 6.4 |  | 0 |  |  | Completed as2nd and final payments ($12,500) sent in March 2011. | Completed | 0
UNEP | Guinea-Bissau | HCFC Phase Out Plan (Stage I) | 2011-11-01 | 2014-12-01 |  | 165000 | 87000 | 29757 | 0.58339 |  |  | 0 |  |  | Project completed in December 2013. |  | 0
UNEP | Guinea-Bissau | CFC Phase Out Plan | 2008-11-01 | 2011-12-01 |  | 100000 | 100000 | 99982 | 3.9 | 3.9 |  | 0 |  |  | Completed as 2nd and final payments ($12,500) sent in March 2011. | Completed | 0
UNEP | Guyana | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-12-01 | 18000 | 18000 | 10932 | 0.027273 |  |  | 0 |  |  | Brief progress report (actual/planned): Two (2) customs workshops were conducted. Thirty (30) customs officers and customs officials participated in these workshops. Licensing system is in place; a component on the Montreal Protocol and ODS monitoring have been included in the regular upgrade for customs training; a total of ninety nine (99) technicians participated in the eight workshops facilitated by a national trainer who was trained under the Terminal Phase out Management Plan (TPMP); a one-day workshop on alternative technologies was held on September 2014. Thirty Four (34) technicians from various regions in Guyana participated; a full-time refrigeration and air conditioning programme was introduced at the Kuru Kuru Training Center in September 2014. Currently 19 (17 males and 2 females) students are enrolled in this programme; three training modules were developed to support the introduction of the Caribbean Vocational Qualification Level 1 Standard for Refrigeration and Air Conditioning; television, radio programmes and published articles to educate stakeholders on the Montreal Protocol’s phase out activities as well as to educate importers on national legislation with regard to importation of ozone depleting substances and equipment which contain them. ___ Legal arrangements (actual/planned): n/a___ First mission (actual/planned): ___ TOR completed (actual/planned): Nov-2012. Revised Oct-2014___ First disbursement date (actual/planned): Mar-2013/Dec-13 ___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): no. ___ If Yes, reasons for delay & action plan to resolve: n/a. ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: n/a.___ | Training consultant submitted last report and payment processed in March-2015. Project completed. | 0
UNEP | Guyana | CFC Phase Out Plan | 2007-11-01 | 2011-12-01 |  | 130000 | 130000 | 111434 | 0 | 8 | 1.74 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Haiti | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2020-12-01 | 182881 | 40000 | 15271 | 0.82296 |  |  | 0 |  |  | Brief progress report (actual/planned): three workshops on Good Refrigeration Management Practices, Recovery, Recycling, Retrofitting and Alternative Technologies of Ozone Depleting Substances, were held during July and October 2014, with participation of 27 and 38 informal refrigeration servicing technicians, respectively. Organization of workshops count with the support of the Apex Technical Institute (main vocational institute of Haiti). Specialized training delivered to 127 Customs and Border Control enforcement personnel were provided in two workshops held in May and July, 2014.___ Legal arrangements (actual/planned): UNEP is providing direct administrative services to Haiti with the support of UNEP's and UNDP's national offices.___ First mission (actual/planned): ___TOR completed (actual/planned): ___ All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country towards the end of the year, second tranche request was not submitted to the 73 ExCom. UNEP followed up with NOU on outstanding report, endorsement letter with wording required by the ExCom. Examples of second tranche requests already approved were facilitated to NOU. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___ | Follow-up communications with NOU in Jan-2015. Political instability remains, NOO is not able to reach office because of street protests and blockages. New Minister appointed in Feb-2015. Government have planned and will focus on parliamentarian, municipal and presidential elections to take place between July and November 2015. The second Minister of 2015 was appointed in early June. | 0
UNEP | Haiti | CFC Phase Out Plan | 2009-07-01 | 2013-06-01 |  | 190000 | 125000 | 110351 | 0 | 25.4 |  | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Honduras | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 250000 | 125000 | 7047 | 2.77 |  |  | 0 |  |  | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. No new disbursements requested from the Government in the year. However, intermediate goals achieved as planned for the year 2014: ODSs license system implemented; NOO collected ODSs data and cross-checked information with Customs before submission of 2013 Country Programme and Article 7 Reports. Article 7 data and CP progress report data submitted; NOU is responsible for the HPMP implementation. On 16 October, the NOU organized an awareness raising activity to celebrate the International Ozone Day. With the presence of mass media, the Minister of Environment awarded main partners and relevant stakeholders for their contribution to the Ozone layer protection. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal will be postponed until the level of expenditures reaches the 80% of project budget. Any ongoing problems? No. If Yes, is any action required by ExCom? Difficulties sorted out by middle of 2014 year. | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. Government has not requested any dibursment in the year. However, intermediate goals achieved as planned for the year 2015: NOO has been collecting ODS data and cross-checking information to prepare the 2014 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Legal arrangements (actual/planned): August 2013/Planned for May 2013. First mission: N/A. TOR completed (actual/planned): N/A. First disbursement date: September 2013/Planned for June 2013. All funds disbursed? No. Any delay? Yes, 12 months. If Yes, reasons for delay & action plan to resolve: Despite Government changes, it is worth to note that the country met its HCFCs and MB phase-out goals. However, changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed by new authorities, the implementation of Multilateral Fund projects should be introduced/re-launched when management lines are changed. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment. A summary of the Montreal Protocol and purpose of projects/funds approved were introduced in such meeting, carried out in March 2014. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Project renewal to be submitted to the 75 ExCom. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | 0
UNEP | Honduras | CFC Phase Out Plan | 2008-07-01 | 2014-12-31 |  | 198000 | 198000 | 189268 | 0 | 49.7 |  | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | India | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2015-12-01 | 861600 | 775440 | 285000 | 13.8284 |  |  | 0 |  |  | Brief progress report (actual/planned): meetings between NACEN, DRI, Ozone Cell and UNEP to agree on terms of cooperation. Legal arrangement (actual/ planned): The SSFA drafted and revised on multiple occasions in 2014, but not signed. First mission (actual/ planned): Feb. 2013. TOR completed (actual/ planned): N/A. First disbursement date: 3rd quarter of 2015. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Delay in signing of the agreement with UNEP due to inter-Ministry negotiation of terms. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): 30 units of refrigerants identifiers delivered in 2nd quarter of 2015. Legal arrangement (actual/ planned): The SSFA still not signed. | 0
UNEP | India | CFC Phase Out Plan - Refrigeration Servicing | 2004-04-04 | 2011-01-01 |  | 800000 | 702500 | 702500 | 101.5157 | 1002.2 | Not available | 0 |  |  |  |  | 0
UNEP | Iran (Islamic Republic of) | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-12-01 | 262000 | 262000 | 107965 | 4.31 |  |  | 0 |  |  | Brief progress report (actual/planned): Interagency meeting in March 2014. Awareness and training workshop for custom officers in DoE in March 2014. The National Ozone Committee (NOC) meeting held in 1st quarter 2014 for HCFCs quota allocation. The Customs Officers Training Workshop held in March 2014 with resource people from national enforcement authorities, UNDP, UNIDO, GIZ and UNEP. The NOU with help of national resource people commenced provincial-level Customs training in Aug. 2014. Legal arrangement (actual/ planned): The SSFA signed in March 2013. As result of return of US$60,000 agreed with ExCom, the country and UNEP revised the implementation plan for the remaining activities in the last Q of 2014. First mission (actual/ planned): 5-7/09/2011. TOR completed (actual/ planned): N/A. First disbursement date: 29/08/2013. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Lengthy inter-agency negotiation of terms within the country. UNEP solicited assistance from UN Resident Coordinator's Office. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Two servicing technicians workshops in Mazandaran Province in Feb. 2015, in cooperation with Provincial DoE of Mazandaran Province and the Mazandaran Technical and Vocational Training Organization (TVTO). Implementation delayed since Jan. 2015 due to negotiations on activity re-programming, post- return of funds to MLF. Legal arrangement (actual/ planned): A new SSFA yet to be signed. | 0
UNEP | Iran (Islamic Republic of) | CFC Phase Out Plan - Regulations | 2003-12-01 | 2010-12-01 |  | 140253 | 140253 | 140253 | 0 | 685.8 | Not available | 0 |  |  |  |  | 0
UNEP | Iraq | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2017-12-01 | 770000 | 440000 | 0 | 8.38 |  |  | 0 |  |  | `• Brief progress report (actual/planned): Project start delayed due to delay in NPP since all HPMP activities are continuation of the NPP. Revised work-plan concluded with NOU taking into consideration progress in NPP related activities. • Legal arrangements(actual/planned): - Country contract drafted and sent for signature by end of 2014 • First mission (actual/planned): No dedicated mission • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): N/A • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract, country contract is ready for signature by end of 2014. • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Yes, local institutional and political challenges • If Yes, is any action required by ExCom: No | # Country contract signed and first payment is under processing (expected by end of June 2015) # UNEP/UNIDO organized coordination meeting for PMU/NOU (Amman, May 2015) and agreed on detailed work-plan for expediting the implementation of the HPMP # 2nd tranche of the HPMP is drafted, reviewed and submitted to ExCom-74 which approved it. # UNEP/UNIDO and country agreed to amend the duration of Stage-I till 2017 and the request for 2nd tranche was drafted/approved accordingly | 0
UNEP | Iraq | ODS Phase Out Plan | 2009-07-01 |  | 2016-12-01 | 1641000 | 1641000 | 1220360 | 0 | 227.6 |  | 0 |  |  | Brief progress report (actual/planned): - Training of Customs and respective authorities is completed resulting in 195 officers trained - National technical and vocational curricula are updated and entered into service from the academic year of 2014-2015. Final printed versions of the curricula are also developed and copies handed to UNEP for record - The training programme on refrigeration good practices is completed in 2014 concluding in 81 sessions were conducted (in 3 years) on which 1931 Participants representing domestic, light commercial and MAC servicing workshops were trained in 8 training centers in different governorates in Iraq. - Specialized workshop on updating the national certification scheme for technicians organized in Amman, Jordan during Sept 2014 and attended by 18 local experts and 3 international speakers - Coordination meeting for the PMU team to review/adjust the work-plan and technical/financial reports organized twice in margins with technical events i.e. Erbil-May 2014 and Amman- Sept 2014 • Legal arrangements(actual/planned): - Country contract already established in 2010 and amended later to incorporate 2nd tranche with 1st tranche in once contract • First mission (actual/planned): Two missions conducted in 2014, one to evaluate the training programs (customs and good practices) in Erbil, Iraq May 2014 and another one in Amman, Jordan Sept 2014 for organizing the Certification Scheme workshop. Both missions included coordination meetings with PMU representatives • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): Third payment against NPP contract was made in 2014 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes, • If Yes, reasons for delay & action plan to resolve: several delays due to political and institutional difficulties in Iraq resulted in delay in disbursing transferred funds during 2014. Financial disbursement started to get back to normal by beginning of 2015 • If Yes, will delay have impact on project completion date (yes/no): Yes • Any ongoing problems (yes/no): Yes, financial closure of the project is expected to be by 2016 due to financial and auditing requirements under the country contract • If Yes, is any action required by ExCom: Yes, Request to amend the date of the completion of the project to be end of 2016 instead of end of 2015 is sought from ExCom | # Remaining refrigeration good practices training is continuing aiming at completing the project by 3rd quarter of 2015 # Pending financial reports are submitted by the government and disbursement of due payments to different stakeholders under NPP are made by PMU/MoE # The certification scheme committee completed the draft certification modules and its under review # UNEP organized the final coordination meeting for NPP project attended by PMU, NOU and UNIDO (May 2015 in Amman) and revised the work-plan of remaining activities and cash-flow of remaining balances | 0
UNEP | Jamaica | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 77000 | 38000 | 17645 | 0.95156 |  |  | 0 |  |  | Brief progress report (actual/planned): Gazetting of The Trade (Montreal Protocol) (Trade in Ozone Depleting Controlled Substances) Order, 2014 (24 November 2014); existing labeling standards amended to include HCFCs;the Bureau of Standards convened a labelling sub-committee which started the review and amendment of the 'Jamaican Standard Specification for The labelling of commodities Part 29: Labelling of products and equipment containing or manufactured using ozone depleting substances and/or their substitutes' to include HCFCs. The draft amended standard will then be submitted to the Standards and Technical Committee of the Standards Council for a recommendation on approval of the draft standard; three days of training for the Jamaica Customs Officers: the first two days training were theoretical while the other was a practical session and included the use of the refrigerant identifier. A one day workshop was organized with Officers from the Ministry of Health, Trade Board , Ministry of Industry, Investment and Commerce on the HCFC quota system and Montreal Protocol in general. ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: completion of outstanding activities with balance from 2013 ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | No new obligation could be raised because of UMOJA ramp-down and black-out periods. New agreement with balance from first tranche to be discussed in Jun-2015. | 0
UNEP | Kiribati | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 109000 | 98100 | 51829 | 0.0275 |  |  | 0 |  |  | Brief progress report (actual/planned):The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. The Customs Office has upgraded its HS code to 2012 HS code since April 2014. Requirement for storage and handling of HCFCs has been put in place. However, the standard/requirement for handling HCFCs was being developed by Sub-committee established under the National Ozone Committee, which would be submitted to the Parliament for approval to fully enforce this permit system. NOU and the Office of Attorney General worked to amend specific sections of regulation related to restricted goods to include the HCFC based products. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The Sub-committee for Establishment of RAC Association was established and the NOU has worked closely with the Office of Attorney General to finalize the TOR for RAC Association. A refresher training workshop for RAC technicians was organized in April 2014 with 28 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in August 2011. First Mission: August 2014 TOR completed: N/A First disbursement date: October 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Reasons for delay is due to national institutional procedures for obtaining required approvals. UNEP CAP conducted mission in August of 2014, to meet with high level officials on the status of project impletation and seeking to find mechanisms for expediting implementation. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Training New NOU in the HPMP management including reporting requirements (progress and financial report). Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. | 0
UNEP | Korea, DPR | HCFC Phase Out Plan (Stage I) | 2014-11-01 |  |  | 202000 | 43500 | 8592 | 4.48 | 4.48
UNEP | Korea, DPR | CFC Phase Out Plan | 2005-11-01 | 2011-04-01 |  | 528000 | 528000 | 501468 | 72 | 66.3 | Not available | 0 |  |  |  |  | 0
UNEP | Kuwait | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2018-12-01 | 1043000 | 614000 | 161860 | 25.1802 |  |  | 0 |  |  | `• Brief progress report (actual/planned): - Country contract concluded and signed end of 2014 along with revised work-plan to accommodate delay in start - Standards and Certification Committees started work in 2014 and draft work-plan is made by both committees - National Ozone Committee started to draft the bylaws and procedures to enforce the new ODS legislation which is part of Kuwait new Environment Law 42/2014 - Customs Authority and NOU prepared training plan for train customs and trade authorities during 2015 - UNEP/UNIDO and country started to prepare the 2nd tranche of the HPMP for submission to the 74th ExCom • Legal arrangements(actual/planned): - Signed end of 2014 • First mission (actual/planned): UNEP conducted one mission in 2014 • TOR completed(actual/planned): N/A • First disbursement date (actual/planned): To be made in 2015 • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract, country contract signed end of 2014 • If Yes, will delay have impact on project completion date (yes/no): Yes, 2nd tranche delayed by one year • Any ongoing problems (yes/no): No • If Yes, is any action required by ExCom: No | # First payment of the country country contract is disbursed # National workshop on the enforcement of the new ODS legislation is organized (March 2015), and attended b y UNEP/UNIDO, for all governmental authorities # National committees and working teams started functioning expedite # UNEP/UNIDO and NOU prepared and submitted, to ExCom-74, the 2nd tranche of the HPMP of Kuwait which is approved. # Complete the verification report for the submission of the 2nd tranche # UNEP/UNIDO conducted one mission to country and met with different stakeholders i.e. Customs, standards, Certification Authority, foam industry and National Ozone Committee to agree on the revised work-plan for the HPMP implementation including activities under 2nd tranche which will overlap with 1st tranche activities. | 0
UNEP | Kuwait | ODS Phase Out Plan | 2007-07-01 | 2014-12-01 |  | 335000 | 240000 | 1757 | 0 | 72.1 |  | 0 |  |  | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project | 0
UNEP | Kyrgyzstan | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-12-01 |  | 35200 | 35200 | 35200 | 0.18 |  |  | 0 |  |  | Brief progress report (actual/planned): The NOU continued the training programme on the good practices in refrigeration including the recovery and recycling and development of capacity of refrigeration technicians for handling and right management of the recycled refrigerants and those for final disposal. Two training workshops were held for refrigeration specialists: Cholpon-Ata city, 24-25.10. 2014 (34 participants) Osh city, 18-19.11.2014 (38 participants). During the two-day workshops, participants learned about the country's legal framework for the protection of the ozone layer and measures for its restoration, implementation of the Kyrgyz Republic’s obligations to reduce ODS (ozone depleting substances) under the Montreal Protocol. The best methods of cooling equipment and servicing of HVAC equipment, the main alternatives to HCFCs were considered. The NOU supported the organization of the annual meeting of the Refrigeration Association in 2014. The Eighth National Congress "Ecoholod" Republican Public Association was held in Bosteri. The Congress was attended by 42 experts on 15-16 October 2014. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the country and UNEP in July of 2014 (as planned). First mission (actual/planned): N/A – NOU implements all activities at the national level without involvement of international experts. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in August of 2014 (as planned) All funds disbursed (yes/no): Yes, all funds were disbursed Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The last payment was released in January 2015 as all activities were finalized in 2014. All activities are completed. Legal arrangements (actual/planned): The SSFA (Small Scale Funding Agreement) was signed between the country and UNEP in July of 2014 (as planned). First mission (actual/planned): N/A – NOU implements all activities at the national level without involvement of international experts. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): 1st disbursement done in July of 2014 (as planned) All funds disbursed (yes/no): Yes, all funds were disbursed Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | 0
UNEP | Kyrgyzstan | CFC Phase Out Plan | 2006-11-01 | 2011-04-01 |  | 233000 | 233000 | 233000 | 0 | 10.9 |  | 0 |  |  | Financially completed. | Financially completed. | 0
UNEP | Lao, DPR | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 235000 | 211500 | 83199 | 0.52 |  |  | 0 |  |  | Brief progress report (actual/planned): In 2014, only the first tranche has been approved to Lao PDR at the 63rd ExCom meeting in April 2011. The licensing and quota system was strictly implemented in 2014. The mandatory labeling requirement for all HCFC containers has been implemented in 2014 for the first year. PCD and the customs officers have jointly inspected type of refrigerant for all shipments to ensure that refrigerant being imported is the same as those allowed by the government. RAC technicians training workshop was organized during 17-19 December 2014 in Champasack Province with 37 RAC technicians from servicing workshops trained. RAC Association was established in 2014. PCD and the training centers initiated the discussion with the RAC Association on its roles in the design and implementation of RAC technician certification system. PCD conducted one industry awareness workshops and develop dissemination tools for customs officers, importers and distributors of HCFCs and RAC equipment to raise awareness of licensing system and mandatory labelling requirement for HCFC cylinders. Legal arrangements (actual/planned): The SSFA has been signed in May 2012. First Mission: June 2012. TOR completed: N/A First disbursement date: Oct 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The licensing and quota system and mandatory labeling requirement are being implemented in 2015. Refresher train-the-trainer workshops of enforcement officers and RAC technicians are planned in 2015/2016. PCD will also collaborate with concerned ministries and the RAC Association to examine when the restriction to sale refrigerant to only certified technicians can be put in place. This includes the possible timeline for the mandatory requirement that only certified technicians will be allowed to handle or service RAC equipment. PCD will be working closely with RAC Association and the Ministry of Labour and Social Welfare regarding this activity. The NOU plans to conduct regular checks with retailers and servicing workshops to inspect whether HCFC containers are properly labelled as required. The second tranche was approved at the 74th ExCom meeting in May 2015. 2014 CP data was submitted online. | 0
UNEP | Liberia | CFC Phase Out Plan | 2007-11-01 | 2011-12-01 |  | 213000 | 213000 | 208000 | 0 | 8.4 |  | 0 |  |  | Project completed | Project completed | 0
UNEP | Madagascar | HCFC Phase Out Plan (Stage I) | 2010-12-01 | 2014-12-01 |  | 300000 | 140000 | 70000 | 3.2143 |  |  | 0 |  |  | Completed in March 2013. | Completed | 0
UNEP | Madagascar | ODS Phase Out Plan | 2007-07-01 | 2009-07-01 |  | 220000 | 220000 | 220000 | 0 | 7.2 |  | 0 |  |  | Completed in November 2011 | Completed | 0
UNEP | Malawi | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2016-07-01 | 230000 | 115000 | 76815 | 2.484 |  |  | 0 |  |  | Brief progress report (actual/planned): _Country implementing second tranche activities. NOU conducted training for both customs officer and refrigeration technicians. 40 customs officers and 30 refrigeration technicians were trained.The NOU conducted inspection visist to Songwe Boarder (Malawi/Tanzania boarder) to check on how customs officers and beaural of standards officers are enforcing the HCFC control measures and conducted briefing session with enforcement officers at the boarder. Legal arrangements (actual/planned): SSFA was signed and first disbursement was made in February, 2014. Any delay (Yes/No): There is delay in processing for second disbursement due to the launch of UMOJA, country submitted all the required reports for processing of second disbursement._ First mission (actual/planned): __CAP planning for a mission to the country_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in February 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | The NOU registered all the importers and allocated the 2015 quotas to the importers. | 0
UNEP | Malawi | CFC Phase Out Plan | 2007-11-01 | 2011-12-01 |  | 172000 | 172000 | 172000 | 0 | 8.7 |  | 0 |  |  | Project completed | Project completed | 0
UNEP | Maldives | HCFC Phase Out Plan (Stage I) | 2010-04-01 |  | 2020-12-01 | 680000 | 529340 | 443140 | 2.29 |  |  | 0 |  |  | Brief progress report (actual/planned): Two enforcement trainings in February and October 2014; Inauguration of the first-ever national Refrigeration and Air-conditioning Association on the Ozone Day 2014 Celebration; Two In-house Training Workshops on Good Service Practices in Refrigeration and Airconditioning for Resorts in Sep. and in Nov. 2014; Signing of a MOU between the Faculty of Engineering Technology of Maldives National University and the Ministry of Environment and Energy for sustaining the technician training efforts; Side event during 26th MOP to highlight the challenges Maldives and other SIDS are facing in the fishery sector. Legal arrangement (actual/ planned): The SSFA signed in August 2014. First mission (actual/ planned): 01-03/06/2014. TOR completed (actual/ planned): N/A. First disbursement date: 14/11/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued. Inter-agency negotiations on establishing technician certification scheme and equipment/ product labelling. Legal arrangement (actual/ planned): As of 22 May 2015, additional US$72,200 is pending transfer to the government. | 0
UNEP | Maldives | CFC Phase Out Plan | 2007-11-01 | 2010-07-01 |  | 95000 | 95000 | 95000 | 0 | 0.7 | 0 | 0 |  |  |  |  | 0
UNEP | Mali | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-03-01 |  | 280000 | 120000 | 91830 | 2.6 |  |  | 0 |  |  | Completed in March 2013 | Completed | 0
UNEP | Mali | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 198000 | 198000 | 192412 | 0 | 16.2 |  | 0 |  |  | Completed in September 2011 | Completed | 0
UNEP | Marshall Islands | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 113000 | 101700 | 45603 | 0.077 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. However, Marshall Islands has not yet adopted the 2012 HS code. The Customs Act has been reviewed for amendments and 2012 HS code has been considered as priority the country. It is expected that the RMI Customs would adopt the 2012 HS code by the last quarter of 2015. A permit system for importers or businesses entity that sale ODS in the regulation has been put in place. A permit system for handling ODS has not been established and would be enforced after the establishment of RAC Association. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The establishment of RAC Association was on-going. RAC servicing tools equipment/tools have not yet distributed to RAC technicians due to the need to finalize the legal agreement for distributing equipment and it would link with RAC Association. The recovery machines have been disseminated to technicians who made the application to NOU from time to time to follow the good practice. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in April 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Change in senior level management and no immediate replacement. UNEP maintained constant communication with interim senior management encouraging the early appointment of required staff. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: No | The refresher training of RAC technicians was organized during 17-20 February 2015 with 15 participants attending the training. Refresher training for enforcement officers was originally planned during the week of 23-27 February 2015. However, the refresher training was postponed. NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. | 0
UNEP | Mauritania | CFC Phase Out Plan | 2007-11-01 | 2013-12-01 |  | 155000 | 155000 | 96000 | 0 | 2.4 |  | 0 |  |  | All activities supended due to ongoing UN audit. | UN audit being finalised. CAP team in consultation with NOU started negotiating new contract in order to resume activites | 0
UNEP | Micronesia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 112000 | 100800 | 50174 | 0.04455 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. Federal States of Micronesia (FSM) has not yet adopted the 2012 HS code because the FSM National Government along with the four state governments were undergoing major tax reform process including the upgrading of 2012 HS code. Custom officers have been trained on the migrating of the 2012 HS code. The permit system for storage and sales of HCFCs and requirement for HCFC handlers to be certified for enrolling in RAC sector has been in place. The government also conducted the RAC Certification Program under piloting stage. The banning process on selected HCFC-based equipment was still under discussion as there was a need to provide some reliable data to assess the impact of such ban. An Assessment Survey was conducted to get data to analyse the impact. Refrigerant identifier was handed over to Customs for inspection. Additional 3 RAC Associations were established in 2014 making FSM to have RAC Associations in all stages. Two refresher training workshops for RAC technicians were organized in May and November 2014. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in April 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: September 2012 All funds disbursed (yes/no): No Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Migrating of 2012 HS code awaits results from FSM Congress and FSM President on the future prospects of the proposed tax reform scheme. The full scheme of certification program will be launched after evaluation and improvement by the OEEM and COM-FSM. The Assessment Survey was completed. NOU has requested legal advice from Department of Justice on amending the current ODS regulation to include the banning of HCFC-based equipment. NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. | 0
UNEP | Moldova | CFC Phase Out Plan | 2007-07-01 | 2010-06-01 |  | 215000 | 215000 | 215000 | 0 | 11 |  | 0 |  |  | Financially completed. | Financially completed. | 0
UNEP | Mongolia | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 236000 | 130000 | 88000 | 0.64481 |  |  | 0 |  |  | Brief progress report (actual/planned): Government Resolution issued on the list of (non-ODS and HCFCs) environmentally friendly techniques and equipments. Government memo on use of non-HCFCs and non-HFC alternatives in new international airport in Ulaanbaatar. Legal arrangement (actual/ planned): The SSFA signed in June 2014. First mission (actual/ planned): September 2015. TOR completed (actual/ planned): N/A. First disbursement date: June 2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Servicing training equipment procurement arranged. HCFCs quota 2015 issued and the information shared through iPIC. 2 units of refrigerants identifiers procured in 2nd quarter of 2015. Legal arrangement (actual/ planned): Additional US$18,000 is to be transferred to the government in the 3rd quarter of 2015. | 0
UNEP | Mozambique | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2014-04-01 | 165000 | 75000 | 22975 | 1.189 |  |  | 0 |  |  | Brief progress report (actual/planned): _The country conducted 3 regional (Maputo, Biera, Nacala)training workshops for refrigeration technicians and a total of 85 technicians were trained. The NOU conducted regional training workshops (Manica, Nampula, Sofala provinces) and a total of 120 enforcement officers (customs officers, boarder patrol Police and clearing agents ) were trained. Legal arrangements (actual/planned): SSFA was signed in May 2013. Any delay (Yes/No): Country experienced some delays at the UNDP country office in transferring of funds to the country_ First mission (actual/planned): __CAP first mission to the country to launch the implementation of HPMP activities was conducted in May, 2014._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in June 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | first trache implementation completed and the country is processing to start implementation of second trache which was approved at Ex-com 73 | 0
UNEP | Mozambique | CFC Phase Out Plan | 2008-11-01 | 2013-12-01 |  | 134000 | 134000 | 107464 | 0 | 2.7 |  | 0 |  |  | project completed | Project completed | 0
UNEP | Myanmar | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2020-12-01 | 220000 | 159000 | 0 | 1.1786 |  |  | 0 |  |  | Brief progress report (actual/planned): This is a long delayed project following its approval by Excom at its 68th meeting, mainly due to the condition attached to the project when it was approved, i.e. the Ozone Order needs to be in place as per Excom decision 68/31. Following the Ozone Order in place in later April 2014, the draft SSFA was submitted to Myanmar for review and comments. Due to the long internal procedures, the government completed its reviewing process of the draft SSFA by December 2014. Legal arrangements (actual/planned): The SSFA is waiting for the government co-signature to become effective. First Mission: Feb 2014. First disbursement date: N/A All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: the delay in signing SSFA due to the long review process of the country. UNEP maintained regular communications with the government to expedite the signing of SSFA. UNEP conducted missions in Feb, Sep 2014, and April 2015 to build the capacity of the NOU/stakeholders, and get the country prepared for the implementation after effectiveness of the SSFA. If Yes, will delay have impact on project completion date (yes/no): Although there is delay at the tranche level, it is expected that there is no impact on the project completion date of HPMP Stage I. Any ongoing problems (yes/no): Yes. The country is in the process of obtaining the Cabinet approval to sign SSFA. If Yes, is any action required by ExCom: No. | The SSFA was signed by UNEP in February 2015 and is in the process of the Cabinet approval which is prerequisite for signatory. UNEP is following up with the government to expedite the signatory of SSFA to allow the transfer of funds for the implementation of HPMP activities. In the meantime, UNEP conducted a mission in April 2015 for the preparation of HPMP implementation. A national stakeholder workshop as well as meetings with key stakeholders (Myanmar Engineering Society, Customs Department) were organized to discuss the action plan for HPMP implementation. It was agreed that a train-the-trainer workshop for customs and enforcement officers will be organized in August 2015, while a train-the-trainer workshop on good practices for servicing will be organized in September 2015. | 0
UNEP | Nauru | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 74000 | 66600 | 43748 | 0.0055 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted by the Customs. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. National training workshop for RAC technicians was organized in May 2014 with 10 participants. RAC servicing tools equipment/tools have not yet distributed to RAC technicians, but planned to be implemented in 2015. Due to very small number of technicians (7) and limited scope of the industry in the countries, national RAC Association may not be practical. Instead, the technicians will use the website for PIC RAC Association to allow for information exchange. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. The SSFA has been signed in August 2012. First Mission: August 2014 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: L ost of NOU in May of 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP conducted country mission in September of 2014, to meet with high level officials on reaching an agreement for resumption of Montreal Protocol work. The Environment Division gave its committment. UNEP continued with emails and phone calls communications. UNEP maintained constant communication with interim senior management encouraging the recruitment of required staff . If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: yes, to encourage to address implementation and implications to compliance. | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. UNEP met with Minister of Foreign Affairs and Senior international office in May of 2015 (in Bangkok), to give a detailed presentation on project, delays being encountered and requesting the support from this office on implementation. | 0
UNEP | Nepal | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2020-12-01 | 126000 | 63000 | 30318 | 0.384 |  |  | 0 |  |  | Brief progress report (actual/planned): 147 Customs officers trainned in 2014. NOU developed the 2014 annual plan for strengthening the measures for controlling HCFCs import and consumption. Stakeholders consultations including one with registered importers and goods transporting companies were organized. Legal arrangement (actual/ planned): The SSFA signed in November 2012. Implementation delay has required a rephasing of UNEP agreement with the government in the last Q of 2014. First mission (actual/ planned): 25-27/06/2012. TOR completed (actual/ planned): N/A. First disbursement date: 28/11/2012. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: national inter-agency coordination requiring extra time. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: Take note of major earthquakes on 25 April and 12 May 2015 and its implication to project implementation capacity. | Brief progress report (actual/planned): 2 units of refrigerants identifiers procured in 2nd quarter of 2015 and are with UNEP pending delivery. Two major earthquakes on 25 April and 12 May 2015 and aftershocks continuing have destroyed/ damaged the NOU premises. Further delay in implemantion is expected. Legal arrangement (actual/ planned): Revised SSFA signed in March 2015, and the first disbursement under the new agreement done in early May 2015. | 0
UNEP | Nepal | CFC Phase Out Plan | 2007-07-01 | 2010-03-01 |  | 70000 | 70000 | 70000 | 0 | 4.1 | 3 | 0 |  |  |  |  | 0
UNEP | Nicaragua | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2020-12-01 | 108000 | 68000 | 33000 | 0.88036 |  |  | 0 |  |  | Brief progress report: The SSFA (agreement) implementation carried out without significant delays. Second and third disbursements released. Intermediate goals achieved as planned for the year 2014: a) in coordination with Customs General Direction, random road controls were implemented in three different sites, in Yalaguina, Las Manos and El Espino, to monitor the public transportation units to avoid the illegal trade of ODSs. In the roads of Nueva Segovia and Madriz: 57 vehicles and trucks in Yalaguina (October 5), in El Espino (October 30) and in Las Manos (Sep. 28), in coordination with the police and army, it was found one cylinder of HCFC-22 in possession of one person not authorized to import and with no quota issued. b) A training workshop and update on the upgraded controls to avoid the illegal trade of ODS carried out in July 2014 in the city of Managua. The trainees were 20 new officers of the Custom General Direction. This training workshop was aimed at public servants on new import and export requirements of ODS in order to guarantee the controls of HCFCs and related technology. Legal arrangements: signed in June 2013/planned September 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): July 2013/October 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report: HPMP progress report and 2nd tranche Annual Implementation plan submitted to the 74 ExCom meeting. Legal arrangements: signed in June 2013/planned September 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): July 2013/October 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | 0
UNEP | Nicaragua | CFC Phase Out Plan | 2008-11-01 | 2012-06-01 |  | 200000 | 200000 | 193567 | 0 | 12.4 | Not available | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Niger | HCFC Phase Out Plan (Stage I) | 2012-04-01 |  | 2016-04-01 | 275000 | 100000 | 64062 | 2.75 |  |  | 0 |  |  | Brief progress report (actual/planned): Country trained 110 refrigeration technicians and 80 customs officers in 2014.Legal arrangements (actual/planned): Agreement signed in July 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - project completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): _ Final payment being processed in July 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Organistion of an awareness day on Ozone in June 2015. Elaboration of a manuel on Ozone for kids in May 2015.Capacity-building of teachers from four schools of vocational and technical training by providing the UNEP document on "Good practices in individual air conditioning". | 0
UNEP | Niger | CFC Phase Out Plan | 2008-04-01 | 2010-12-01 |  | 149000 | 149000 | 148000 | 0 | 4.8 |  | 0 |  |  | Completed in March 2012 | Completed | 0
UNEP | Niue | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 73000 | 65700 | 27388 | 0.00275 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014, but no request for the import of HCFC. Based on 2014 Country Programme, Niue maintained zero HCFC consumption. Report to be submitted on time and on the required quality. The Niue Customs has adopted the 2012 HS code for the ODS import and export control. Refrigerant identifier was handed over to Customs for inspection. National training workshop for RAC technicians was organized in May 2014 with 12 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. Due to very small number of technicians (3) and limited scope of the industry in the countries, national RAC Association may not be practical. Instead, the technicians will use the website for PIC RAC Association and align with Tonga RAC Association to allow for information exchange. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. The SSFA has been signed in September 2011. First Mission: August 2013 TOR completed: N/A First disbursement date: October 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Lost of NOU since May of 2013. No new NOU since appointed. NEP maintained constant communication with interim senior management encouraging the early appointment of required staff and to address delays. New NOU planned to be recrutied in the second half of 2015. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: No | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted. Training New NOU in the HPMP management including reporting requirements (progress and financial report). Assisted the NOU in the preparation of legal draft required for the private sector use and date management of the RAC equipment provided under the HPMP | 0
UNEP | Oman | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2015-11-01 | 85000 | 85000 | 42899 | 1.3295 |  |  | 0 |  |  | Brief progress report (actual/planned): The NOC established by ministerial decision No. 121/2012 holds regular meetings which highly contributed to the enhancement of the ODS decision making on a more participatory fashion. Oman enacted an updated ODS regulations by ministerial decision no. 107/2013 as required by the unified GCC regulations. Oman currently operates a strict licensing and quota system that includes HCFCs. All preparatory works including the design and components of the database for a web based licensing system have been completed during 2013. Due to the ministry's plan to integrate this system into a more comprehensive national licensing system for all chemicals which is being currently finalized, it is expected to have this activity completed during early 2015. The RAC curricula reviewed and updated as required to include the latest developments related to HCFCs phase out. Several technical and policy meetings took place to discuss and agree on the CoP and to finalize the institutional requirements for setting up a sound certification system for RAC technicians including the review of the existing vocational standards to meet with the current requirements under the HPMP. The CoP was drafted and is being finalized in close consultation with relevant bodies. General outlines of a certification system have been drafted and an international consultant worked closely with UNEP and respective national authorities in developing the required standards, working procedures and tools including tools for assessment. A study tour was organized to the Philippines to exchange experiences on operating such certification systems. A train the trainers training workshop on certification and good practices was held during 7-11 Sept. 2014 in Muscat with participation of 20 trainers from all governorates along with a regional experts meeting on certification. Legal arrangements (actual/planned): The SSFA agreement for the implementation of the first stage under HPMP was finalized and signed in Feb. 2013 and still valid till Nov 2015. mission (actual/planned): several missions to the country took place during 2014 to finalize CoP and certification systems expedite implementation of other planned activities - TOR completed (actual/planned): completed - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): 1st disbursement done in Q2 2013 All funds disbursed (yes/no): No, second payment is pending due to late submission of financial progress report. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the LS. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | The development of e-Licensing is being finalized as part of a global licensing process within the ministry and it's expected to be completed during 2015. however, the ministry is currently granting electronic permissions via a specialized portal of the Customs dept. ; the updated ODS regulations are being enforced effectively through full engagement of NOC and stakeholders. A meeting organized in Feb 2015 with the NOC, NOU and UNIDO to discuss and follow up the progress in implementing the remaining activities under 1st stage and agree on steps required to complete the project as planned by 2015; a steady progress is being made towards finalizing all technical and set up arrangements for adopting the national certification scheme for RAC technicians. A follow up meeting organized in Feb 2015 with the Oman Occupational Standards and Certification Center to review the progress made and to provide technical support for finalizing the certification system for adoption by the respective bodies in Oman. a full package of technical and procedural requirement for certification have been prepared and submitted to respective authorities for adoption. it is hoped that the system to be adopted during 2015. | 0
UNEP | Pakistan | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2015-12-01 | 440000 | 440000 | 200000 | 5.3553 |  |  | 0 |  |  | Brief progress report (actual/planned): Consultative Meeting of HCFC Importers/Industries in Karachi and site visits to 3 companies in July 2014. In Aug. 2014, a study tour to Beijing and cities in Guangdong Province to learn about HCFCs alternatives and phase-out approaches. 1 face-to-face meeting (May 2014) and 1 virtual meeting (Aug. 2014) held between Pakistan and Afghanistan authorities to discuss ODS trade issues. Press coverage on HCFCs quota, etc. Legal arrangement (actual/ planned): The SSFA signed in Oct. 2013. First mission (actual/ planned): The 3rd quarter of 2015. TOR completed (actual/ planned): N/A. First disbursement date: 20/03/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: Severe delay, mainly due to prolonged absense of a NOO. UNEP is coordinating with UNDP to expedite the appointment of a new NOO. High-level bilateral meeting organized in May 2015 to reiterate to the government urgency of resolving the problem. If Yes, will delay have impact on project completion date (yes/no): yes. Any ongoing problems (yes/no): yes. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): In Jan. 2015, a half-day servicing sector awareness workshop held (32 participants). HCFCs quota 2015 issued and the information shared through iPIC. Agreement between NOU and Sindh Technical Education and Vocational Training Authority (STEVTA) drafted. | 0
UNEP | Palau | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 120000 | 108000 | 60552 | 0.0572 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. The Palau Customs has adopted the 2012 HS code in January 2014. Provisions of service license for RAC technicians and storage license of ODSs including HCFCs both in bulk and containing in equipment have been in place. NOU has worked on additional amendments to include ban on importation of used HCFC based-equipment. Refrigerant identifier was handed over to Customs for inspection. RAC Industries and Technicians has been established since September 2013. RAC servicing tools equipment/tools were distributed to RAC technicians through RAC Association. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in February 2012. First Mission: September 2012 TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. 2014 CP data timely submitted online. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards. | 0
UNEP | Panama | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2015-12-31 | 70000 | 70000 | 45976 | 0.99718 |  |  | 0 |  |  | Brief progress report: The implementation of the HPMP is progressing well. Intermediate goals achieved in the first tranche are as planned for 2014: (a) Capacity building and awareness rising of public and private stakeholders in several regions of Panama. (b) The Government of Panama granted annual HCFC import licenses to 33 importers. (c) In addition, the ban on imports of pure HCFC-141b for use in the refrigeration servicing sector entered into force on 1 January 2014. Legal arrangements: CAP staff is implementing the project directly based on an official request from the Director of Environmental Health, who is the Montreal Protocol Focal Point in Panama. First mission: N/A. Regional CAP staff is based in Panama. 2 meetings carried out during the year for providing support to NOU with planning and mid-term review, while no specific actions established in the project document. TOR completed (actual/planned): N/A. Direct payments were issued to suppliers and contractors. First disbursement date: June 2012/Planned for May 2012. All funds disbursed: No. Any delay? Yes. If Yes, reasons for delay & action plan to resolve: Administrative reassons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | Brief progress report: The implementation of the HPMP is progressing well. The NOU participates in the committee on standards for HC and will support the preparation of regulations for HC-based refrigerants. In cooperation with Implementing Agencies the progress report and annual implementation plan were submitted to request the third tranche. Legal arrangements: CAP staff is implementing the project directly based on an official request from the Director of Environmental Health, who is the Montreal Protocol Focal Point in Panama. First mission: N/A. Regional CAP staff is based in Panama. A meeting carried out for providing support to NOU with planning of 2015 activities. TOR completed (actual/planned): N/A. Direct payments were issued to suppliers and contractors. First disbursement date: June 2012/Planned for May 2012. All funds disbursed: No. Any delay? Some delays. If Yes, reasons for delay & action plan to resolve: Administrative reasons already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom: N/A. | 0
UNEP | Panama | CFC Phase Out Plan | 2004-12-01 | 2011-06-01 |  | 50000 | 50000 | 50000 | 0 | 57.6 | 11.53 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Paraguay | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 330000 | 267000 | 102027 | 3.29 |  |  | 0 |  |  | Brief progress report: The SSFA (agreement) implementation carried out without significant delays. Intermediate goals achieved as planned for the year 2014: a) Banned the imports of HCFCs-based equipment for lower BTU ranges is in force. A Customs Code was established for the correct classification of the HCFC based equipment. Currently, the online control system has been updated to implement the HCFCs import quotas system as well as for the prohibition of equipment based on HCFCs. b) A meeting with environmental enforcement officers to inform about the banning of R-22 based RAC equipment carried out on November 27, 2014, attended by 29 participants. ODSs illegal trade control and prevention measures seminar carried out on October 15, 2014, attended by 28 environmental enforcement officers. Training on HCFC quota system operations carried out on July 31, 2014, attended by 20 environmental enforcement officers. On 22/04/2014 a seminar aimed to Customs Agents was carried out in Asunción del Paraguay. 15 enterprises who handle ODSs shipments attended the seminar carried out to inform on Customs Codes for registering respective imports. c) Training courses for front line officers carried out to explain the new HCFCs law and the HCFC illegal trade modalities. The courses were held in different cities of the country. A total of 78 front line officers aware on different aspects of HCFCs and HCFCs-based equipment verification methodology. These courses also facilitated coordination links and communication between Customs and the NOU. Legal arrangements: signed in April 2012/planned April 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report: HPMP progress report and 2nd tranche Annual Implementation plan submitted to the 74 ExCom meeting. Legal arrangements: signed in April 2012/planned April 2012. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | 0
UNEP | Paraguay | CFC Phase Out Plan | 2007-03-01 | 2011-12-01 |  | 194000 | 194000 | 194000 | 0 | 31.6 | 27.334 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Peru | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2015-12-01 | 50000 | 25000 | 0 | 0.66155 |  |  | 0 |  |  | Brief Progress No progress. Legal arrangements: SSFA is not signed. UNEP submitted the document which was signed in the year of 2013. The Government did not sign the agreement even in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Oct 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of HCFCs license system. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. UNEP and UNDP joint country mission conducted in July 2013 to streamline HPMP implementation. Clarifications provided to the NOU Head about the pre-requisite of HCFC license/quota system is established before launching the HPMP implementation. ODSs revised liecense/quota system issued in September 2013 in order to meet the HCFCs baseline. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. | Brief Progress: No disbursements. Legal arrangements: The Government signed the agreement in May 2015. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): Oct 2013/no disbursements. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The initial delay was due to lack of HCFCs license system. Head of NOU was appointed in 2013. A revision of project status was conducted by new authorities to check administrative procedures and policy measures' consistency. UNEP and UNDP joint country mission conducted in July 2013 to streamline HPMP implementation. Clarifications provided to the NOU Head about the pre-requisite of HCFC license/quota system is established before launching the HPMP implementation. ODSs revised liecense/quota system issued in September 2013 in order to meet the HCFCs baseline. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. Administrative and national legal procedures requires time. If Yes, is any action required by ExCom: No. | 0
UNEP | Peru | CFC Phase Out Plan | 2008-07-01 | 2013-12-01 |  | 155000 | 77500 | 36266 | 0 | 43.4 | Not available | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Philipinnes | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2016-12-01 | 230000 | 207000 | 207000 | 5 |  |  | 0 |  |  | Brief progress report (actual/planned): The licensing and quota system was implemented in 2014. Despite a delay in transferring the first payment, which was made in June 2014, activities were implemented (i) preparation of Term of Reference (TOR) for hiring consultant/expert or (ii) coordination/meeting with other stakeholders to get their inputs to finalize the customs training manuals or intervention with policy. Procurement of equipment for servicing shops has not yet undertaken in 2014, but selection criteria of beneficiaries who will receive financial support is finalized in late 2014. The key achievements during the reporting period were organization of the training workshops for key stakeholders e.g. one train-the-trainer workshop and four workshops for Customs and enforcement officers, one train-the-trainer workshop and four workshops for RAC technicians and orientation/training on environmental laws and policy updates etc. The Code of Practices (COP) has been revised to include handling and servicing of flammable refrigerants such as HFC-32 and hydrocarbon R290) and was integrated to the training curriculum for service technicians. Collection, Transport and Storage (CTS) schemes was finalized in December 2014 to identified depository sites. Legal arrangement: The PCA has been signed in December 2013. First Mission: 2012. TOR completed: N/A First disbursement date: June 2014 All funds disbursed (yes/no): No Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The delay in transferring the first payment. If Yes, will delay have impact on project completion date (yes/no): Yes, the revised project completion date of HPMP Stage I is expected to be in December 2016. Any ongoing problems (yes/no): No, the implementation is progressing If Yes, is any action required by ExCom: N/A | The second payment as of PCA has been transferred to the government to implement the activities planned in March of 2015. Procurement of equipment for the CTS has been conducted and the award has been issued to the bidding winner. The procurement of equipment for servicing workshops will be implemented in 2015. Country mission to review status and support implementation was conducted in March of 2015. | 0
UNEP | Philippines | CFC Phase Out Plan | 2012-04-01 |  | 2015-12-01 | 1835205 | 1835205 | 750000 | 0 |  |  | 0 |  |  | Brief progress report (actual/planned): Assisted the conduction of the audit report, and prepared all the internal and extenal reports as required by the MLF and the government for the close of NCPP project. Prepared and submitted the final payment request. The PCA was signed in October 2012 and amended in October 2013. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The last disbursement from UNEP to the country was delayed due to the discrepancy of Excom decisions on the approved amount to NCPP. If Yes, will delay have impact on project completion date (yes/no): No, as all substiantial activities have already been completed. Any ongoing problems (yes/no): Yes. If Yes, is any action required by ExCom: Yes, Excom needs to make decision on the approved amount for NCPP. This was addressed at the 74th Ex. Com. | The new decision of Excom was made at the 74th meeting. The last payment then could be released, and the project could be financially completed soon. | 0
UNEP | Qatar | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2015-12-01 | 310000 | 105000 | 0 | 8.8071 |  |  | 0 |  |  | `• Brief progress report (actual/planned): - Country contract for UNEP's non-investment activities remains pending waiting country comments and input on the work-plan. Investment components for the foam conversion are almost completed by UNIDO as it deals directly with the private sector. - Several follow-ups and side-meetings with NOU and officials in margins of regional. International events - Preparation for the 2nd tranche request was made by UNIDO and UNEP along with verification for 2013 data aiming to submit the 2nd tranche to the 73rd ExCom but no support letter was provided by country. Same for the ExCom-74 - UNIDO and UNEP submitted the request for the preparation of Stage-II of the HPMP which is approved by ExCom-73 • Legal arrangements(actual/planned): No signed yet • First mission (actual/planned): Three attempts for joint missions with UNIDO to the country were postponed • TOR completed(actual/planned): TORs for technical components were drafted and handed to NOU for comments/inputs and action • First disbursement date (actual/planned): No • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract and responses from the country • If Yes, will delay have impact on project completion date (yes/no): Yes, 2nd tranche delayed by 2 years • Any ongoing problems (yes/no): Yes, message from ExCom would be helpful to alert the country about delays consequences • If Yes, is any action required by ExCom: No | # Meeting with MoE officials in margins of network meeting to push for country action and feedback. New ODS Officer is likely to be appointed shortly. # Plans are made to visit the country during the 3rd quarter of 2015 and bring the project back on track. | 0
UNEP | Qatar | CFC Phase Out Plan | 2007-11-01 | 2014-12-01 |  | 120000 | 120000 | 15000 | 0 | 15.2 |  | 0 |  |  | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project | 0
UNEP | Region: PIC | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 285000 | 240000 | 125000 | 0 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. UNEP continued to provide support to assist the countries to strengthen their existing legislation and regulations to effectively control imports and exports of HCFCs and HCFC-based equipment (licensing and quota system, iPIC, provision of policy advice, high level political support, development of legislation/regulations, training and capacity building, and synergy with others). UNEP OzonAction partnered with other parts of UNEP, namely the Division of Environment Law Enforcement (DLEC) and UNEP Chemicals organized the Second Joint Meeting of Ozone Officers and Customs Officer of Pacific Islands Countries in March 2014 in Tonga back-to-back with the Meeting of the PIC Network and the Workshop for Customs Officers on Controlling of Environmentally Sensitive Commodities in PIC. In collaboration with the Australia-Pacific Technical College-Samoa office (APTC), the second regional RAC technician training was organized in August 2014 in Fiji back-to-back with the PIC Thematic Meeting on HPMPs Implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in May 2011 with OCO; August 2011 with SPREP; and December 2011 with SCT. First Mission: May 2011 TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No,project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | The second tranche of Regional PIC HPMP including 12 national HPMP was submitted and approved by the ExCom 74 in May 2015. UNEP keeps regular communication with the countries to complete the remaining tasks under the first tranche. Upon request by PIC countries, UNEP is developing a simple (field use) manual on good practices for servicing RAC equipment using flammable refrigerant. A thematic meeting on the implementation of the HPMP stage 1 second tranche is planned in August 2015. | 0
UNEP | Rwanda | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  |  | 170000 | 82000 | 41317 | 0.87429 |  |  | 0 |  |  | Brief progress report (actual/planned): __Country implementing second tranche activities. NOU conducted training for both customs officer and refrigeration technicians. 40 customs officers and 30 refrigeration technicians were trained. NOU conducted inspection visists to major boarders and conducted briefings with all the enforcement officers at the boarders on the enforcement of national ODS legislation. Legal arrangements (actual/planned): SSFA was signed in July 2012. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visited the Country in June, 2014_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in August, 2012.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: ___ | Country processed allocation of 2015 HCFC quotas, conducted the planning meeting of the refrigeration association and conducted inspection visits to major reatail shops of refrigerants | 0
UNEP | Rwanda | CFC Phase Out Plan | 2007-11-01 | 2013-04-01 |  | 177000 | 177000 | 170013 | 0 | 4.6 |  | 0 |  |  | project completed in Jul 13 |  | 0
UNEP | Saint Kitts and Nevis | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 124500 | 107600 | 41524 | 0.13623 |  |  | 0 |  |  | Brief progress report (actual/planned): HCFCs license system in place, HCFC quota assigned January 2014. Licensing regulations updated to include the HCFC blends in 2014. Draft standards manual developed in 2014; World Environment Day celebrations included ozone layer protection issues and highlighting the activities of the HPMP. Awareness on the need to switch to energy efficient, low global warming potential (GWP) alternatives was also raised among the general public and the RAC sector.___ Legal arrangements (actual/planned): Agreement signed in Jul-12___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Jul-12 ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Project completed. Second tranche request prepared in Mar-2015. Comments from the MLFS addressed in Apr-2015. Second tranche approved in May-2015 by ExCom 74. Legal agreement under preparation. | 0
UNEP | Saint Kitts and Nevis | CFC Phase Out Plan | 2006-04-01 | 2013-07-01 |  | 144000 | 130000 | 130000 | 0 | 0.6 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Saint Lucia | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2020-12-01 | 51892 | 26150 | 23500 | 0.022082 |  |  | 0 |  |  | Brief progress report (actual/planned): 44 technicians trained in good refrigeration practices. 40 technicians certified and issued 'Certified Technician' ID cards. 50 Customs and Marine Police Officers trained in the application of the HCFC licensing and Quota Systems. Customs quick tool and Customs desk book distributed to all Customs officers. Training for 20 shipping agencies on harmonized systems codes. Meetings with importers to discuss progress in HPMP implementation and quota controls. Posters on sale restrictions to only certified technicians distributed to retailers.___ Legal arrangements (actual/planned): SSFA signed in Jun-2014 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): June-2014___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Progress and financial reports sent on Apr-2015. Reports cleared in Apr-2015. Second payment processed and issued in Apr-2015 | 0
UNEP | Saint Vincent and the Grenadines | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2025-12-01 | 345800 | 55809 | 54992 | 0.20605 |  |  | 0 |  |  | Brief progress report (actual/planned): All importers of refrigerants were invited to register with the NOU. A total of 24 registered importers were formally informed by the NOU, Ministry of Health, Wellness and the Environment of their 2014 quota for the importation of HCFCs and are in compliance; a total of 25 technicians were successfully trained in retrofitting, safe handling and storage of refrigerants in May 2014; 10 Customs Brokers and Importers participated in procedures for imports license and quota systems on Feb-2014; 14 Senior frontline Customs Officers were trained in Phase I Safe Storage and Handling of ODS, Import license and Quota Systems as well as Protecting St. Vincent and the Grenadines Borders from Illegal Trade of ODSs in Apr-2014; Refrigerant posters designed, printed and distributed to stakeholders to guide them in acknowledging ODS imported in the country; article placed in the newspapers on Jun-2014 directed at importers of refrigerants highlighting the regulations for importing refrigerants; the Technical College, division of Technical and Vocational Education was supported to be the first fully equipped and comprehensive refrigeration and Air-conditioning Technicians Training Centre in St.Vincent and the Grenadines .___ Legal arrangements (actual/planned): n/a___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: n/a.___ | Registrations of twenty (20) Importers were done and six (6) out of the twenty (20) importers who are historical importers of HCFC were assignment quotas. Importers consultations on Safe Handling Storage Labelling and Transportation of Refrigerant, held on the 10th & 11th, February. March 6th, an additional MOU was signed to establish a 5th recovery centre. As part of the customs curriculum the NOU facilitated training of 16 junior customs officers on the green customs initiative and the import license and quota system on June 2. | 0
UNEP | Saint Vincent and the Grenadines | ODS Phase Out Plan | 2005-11-01 | 2011-12-01 |  | 109000 | 109000 | 109000 | 0 | 0.3 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Samoa | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 148500 | 133650 | 71252 | 0.0748 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. 2012 HS code has been adopted. The provisions for licensing for storage, sale, distribution, purchasing and handling of ODSs including HCFCs have been put in place. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. RAC Association was re-established under the support of NOU through HPMP. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. The recovery machines have been kept at the NOU tool bank and released to technician upon request from time to time. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in August 2012. TOR completed: N/A First disbursement date: April 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards. | 0
UNEP | Samoa | CFC Phase Out Plan | 2007-11-01 | 2010-12-01 |  | 75000 | 75000 | 75000 | 0 | 0.7 | Not available | 0 |  |  | Project Financially completed |  | 0
UNEP | Sao Tome & Principe | HCFC Phase Out Plan (Stage I) | 2011-04-01 | 2014-03-01 |  | 160000 | 79000 | 39012 | 0.05 |  |  | 0 |  |  | Completed | Completed | 0
UNEP | Sao Tome & Principe | CFC Phase Out Plan | 2008-04-01 | 2010-12-01 |  | 75000 | 75000 | 75000 | 0 | 0.7 |  | 0 |  |  | Completed | Completed | 0
UNEP | Saudi Arabia | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2020-12-01 | 720800 | 290400 | 26999 | 32.8125 |  |  | 0 |  |  | Brief progress report (actual/planned): A follow up consultation meeting took place in Riyadh during May 2014 to continue discussions with stakeholders on the draft updated ODS bylaws and to advance the preparation of the certification scheme; slow progress towards the update of the code of practice while the RAC curricula updated, and adoption of the certification scheme for RAC technicians. A study visit to the Philippines has been organized during Feb. 2014 where 2 national experts participated to exchange experience about the operation of such scheme and related accreditation systems for servicing sector. International expert recruited to assist in developing and adopting an operational certification scheme including guidance for updating the national occupational standards, entry and final tests and required procedures. A refresher TT training workshop organized during July 2014 along with consultation workshop for all stakeholders. Technicians training will follow in 2015 when agreement reached with the vocational training authority; Engagement of stakeholders has been strengthened through supporting regular meeting of the NOC. Activities for Customs are pending the finalization and adoption of the updated bylaws. Activities for Customs are pending the finalization and adoption of the updated bylaws. Two policy and technical workshops for the foam sector to assist in raising awareness of the PU end users and provide them along with the system house companies with the required TA and advice in concert with the phase out investment activities planned for the sector. the workshops organized during April and December 2014 jointly with UNIDO. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities at national level is not signed yet due to difficulties faced by the NOU to open a special account to receive projects funds. However, UNEP continued to implement directly as feasible and explore other options for funds transfer mission (actual/planned): several missions to KSA during 2014 to expedite implementation of planned activities. - TOR completed (actual/planned): completed - with CAP staff implementing directly key activities First disbursement date (actual/planned): 1st disbursement done in Oct. 2013 All funds disbursed (yes/no): No, Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: delayed countersignature of the required SSFA for implementing project activities at national level. If Yes, will delay have impact on project completion date (yes/no): UNEP is still trying to agree with the country on the best options for expediting implementation to absorb the delays faced so far. Any ongoing problems (yes/no): the NOU has been unable to open a special account for receiving project's funds If Yes, is any action required by ExCom: n/a- different alternative modalities are being explored to resolve the problem | UNEP continue working with the Government to adopt the updated ODS regulations. It was agreed to have all control measures and provisions included in one package for easy reference and better enforcement; The NOU, in cooperation with the NOC and concerned authorities, strictly enforced the agreed control measures including the new quota system to control the imports of HCFCs that was put in operation since January 2013. Extensive discussions and analysis took place to conclude on the possible ban on imports of HCFCs containing products, taking into account the availability of alternative technologies suitable to the circumstances in the country. A ban of disposable cylinders is currently being discussed and will be taken into account when adopting the updated regulations by 2015 as required by HPMP. Coordination with UNIDO continued as to ensure timely and sound HCFCs phase out in the foam sector. and support provided during early 2015 for the preparing and conducting the site visit under the Global evaluation study on the foam sector. Initiated support for development of a national strategy to encourage end-users of RAC equipment to carry out leak detection, repair and maintenance to minimize ODS emissions will be follow-up during the HPMP implementation; Preparation for customs training to take place during 2015 the trainings in 2015 as per the new requirements under the updated ODS regulations. Moreover, additional advanced identifiers (5 units) are being purchased for subsequent distribution after training. | 0
UNEP | Saudi Arabia | ODS Phase Out Plan | 2007-11-01 | 2014-07-01 |  | 405000 | 405000 | 270493 | 0 | 269.8 |  | 0 |  |  | Brief progress report (actual/planned): The remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting; Draft bylaws for the enforcement of the updated GCC regulations on ODS has been prepared and circulated in Nov. 2013 for inputs from all concerned authorities. a follow up consultation meeting took place in Riyadh during May 2014 to continue discussions with stakeholders on the draft update of the ODS bylaws and to advance the preparation of the certification scheme; Steady progress has been made towards the update of the RAC curricula and code of practice, and adoption of national certification scheme for RAC technicians; recruitment of an international expert has been initiated to assist in the update of the RAC curricula and code of practice, and adoption of national certification scheme for RAC technicians; the engagement of stakeholders have been strengthened through supporting regular meeting of the NOC. The NOC met in Nov. 2013 with UNEP participation. Activities for Customs are pending the finalization and adoption of the updated bylaws. | Project completed and the remaining activities under the NPP have been integrated within the HPMP approved at 68th EC meeting | 0
UNEP | Senegal | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2014-11-01 | 530000 | 100000 | 95000 | 6.4764 |  |  | 0 |  |  | Brief progress report (actual/planned): Country trained 30 customs officers in May 2014 in Dakar; also trained 91 refrigeration technicians between January and March 2014 in Saint-Louis, Kaolack and Kolda. Legal arrangements (actual/planned): Agreement signed in March 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2012 __ All funds disbursed (yes/no): _ Final payment being processed in march 2013.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | NOU organized two meeting of the Ozone steering committee. Verification report is being finalised and consultant has already submitted the draft. | 0
UNEP | Senegal | CFC Phase Out Plan | 2007-07-01 | 2010-12-01 |  | 210000 | 210000 | 209000 | 0 | 23.4 |  | 0 |  |  | Completed and Final payment ($1,500) sent in Oct. 2011 | Completed | 0
UNEP | Serbia | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-31 | 75500 | 53500 | 18713 | 0.22807 |  |  | 0 |  |  | Brief progress report (actual/planned): UNEP and the NOU have planned the activities: the first sub-component on preparation, printing and dissemination of the check-lists, templates for reporting, log-books and other enforcement related materials. The NOU has requested to obtain the best practices from EU countries regarding the check list for environment inspectorate. The NOU will print and disseminate the check list among environment inspectors. Under the second sub-component was agreed to organize 4 national meetings with the Environmental Inspection, as a follow up activity on the initial training. The third sub-component on training for operators of the ODS installations and ODS waste centers to enforce requirements of national legislation will be implemented by the end of the tranche. The last sub-component which is awareness raising is implemented through organizing the annual exhibition booth and 1 day forum on environmentally friendly modern refrigeration technologies jointly with the Ministry of Environment, the Serbian HVAC&R association KGH and UNEP. Legal arrangements (actual/planned): The project is directly implemented by UNEP First mission (actual/planned): No. NOU implements all activities at national level. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): NO, planning stage All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): There are delays in the implementation as the Ozone officer left the Ministry. The new Ozone Officer has been recently appointed by the Government and UNEP plans to re-start implementing activities in the second half of the year of 2015. Legal arrangements (actual/planned): The project is directly implemented by UNEP First mission (actual/planned): No. NOU implements all activities at national level. TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): No All funds disbursed (yes/no): NO Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: The appointment of the new Ozone Officer If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | 0
UNEP | Sierra Leone | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2016-12-01 | 110000 | 48000 | 36138 | 0.30381 |  |  | 0 |  |  | Brief progress report (actual/planned): __The NOU trained 50 technician in the use of hydrocarbon refrigerant as alternative to HCFC. A total of 20 custom officers were trained on monitoring and control of ODS. The NOU procurred and distributed toolkits to the major repair workshops and to a few technicians. Implementation of activities has delayed dur to the Ebola outbreak. Legal arrangements (actual/planned): SSFA was signed in March 2014. Any delay (Yes/No): No_ First mission (actual/planned): __CAP can not visist the country due to Ebola outbreak_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in May 2014.___ All funds disbursed (yes/no): _YES__ Any delay? (yes/no): _Yes_ If Yes, reasons for delay & action plan to resolve: Ebola outbreak has delayed implementation of activities_ If Yes, will delay have impact on project completion date (yes/no): _YESS__ Any ongoing problems (yes/no): __YES_ If Yes, is any action required by ExCom: __NO_ | Most activities are delayed due to Ebola situation in the country | 0
UNEP | Sierra Leone | ODS Phase Out Plan | 2009-04-01 | 2013-12-01 |  | 150000 | 150000 | 150000 | 0 | 11.8 |  | 0 |  |  | project completed in Dec 2013 | project completed | 0
UNEP | Solomon Islands | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 195000 | 175000 | 106690 | 0.6666 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. The Customs and Excise has adopted the 2012 HS code for the import and export control. Permit requirement for selling of ODS, non-ODS and RAC equipment has been put in place . The permit requirement is also applied to handle and store the HCFCs. The license requirement for handling of HCFCs by technicians had been informed to technicians during the technician trainings. However, license for handling of ODS including HCFCs will enter into effect when the RAC Association is established. Refrigerant identifiers were kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. The NOU has been working with concerned stakeholders to establish a formal RAC association in the country. A meeting with stakeholders was organized in Feb 2014 to form the association. A meeting with RAC technicians was organized in Dec 2014 to discuss the operation of association. RAC technician receiving a tools kit signed Agreement with the Energy Division as a pre-requisite receipt of tools. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in August 2011. First Mission: March 2014 TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Refresher training for enforcement officers in the Solomon Islands was organized on 4 March 2015 in Honiara (16 trainees). Refresher training for RAC technicians in the Solomon Islands will be organized on 26 March 2015 in Honiara (20 trainees). NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. This was approved at the 74th Ex. Com. 2014 CP dta timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. | 0
UNEP | Sri Lanka | HCFC Phase Out Plan (Stage I) | 2010-12-01 |  | 2020-12-01 | 249000 | 149000 | 141000 | 1.8295 |  |  | 0 |  |  | Brief progress report (actual/planned): In 2014, Technician Training workshop on Good Practices in Refrigeration with 79 technicians; 45 Customs Officers trained; Production and dissemination of awareness and training materials such as ‘Ozone 20+’ magazine, 2012 HS Code poster, work ethics for technicians; NOU participation in 2 national industry exhibitions; HCFC phaseout message/ information dissemination. Legal arrangement (actual/ planned): The SSFA signed in Dec. 2013. First mission (actual/ planned): 20-24/09/2012. TOR completed (actual/ planned): N/A. First disbursement date: 20/03/2014. All funds disbursed (yes/no): no. Any delay? (yes/no): no. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): HCFCs quota 2015 issued and the information shared through iPIC. Servicing training in February 2015. Montreal Protocol module has become part of Sri Lankan Customs mandatory training. In 2015, the primary focuses are: to conclude the work with Industry Associations and to produce/ disseminate non-print awareness materials. Legal arrangement (actual/ planned): In April 2015, additional US$8,000 transferred to the government. | 0
UNEP | Suriname | HCFC Phase Out Plan (Stage I) | 2011-11-01 |  | 2020-12-01 | 104000 | 55500 | 27000 | 0.34171 |  |  | 0 |  |  | Brief progress report (actual/planned): Capacity building programme including training of 60 customs officers on illegal trade and identification of ODS and ODS-based equipment, and training of 140 technicians in handling, installation and servicing of equipment operating with R-410A, R-290 and other alternative refrigerants; capacity building of both customs and technicians is an on-going process. Frequent exchange of information with Customs who are making use of refrigerant identifiers during inspections. Refrigeration association (ARVAS) has trained and certified more than 100 technicians out of a total of 200 nationwide. Awareness programme for phasing-out the use of HCFCs and high-GWP refrigerants as commercially viable technologies become available; strengthening of the recovery and recycling programme in operation through the distribution of recovery units, multifunction recovery, recycling, evacuation and charging units, multi-refrigerant analyzer, recovery cylinders, vacuum pumps, tools and spares; monitoring and evaluating the implementation of the HPMP to ensure effectiveness of all the activities proposed within the HPMP.___ Legal arrangements (actual/planned): SSFA signed in Apr-2012 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Apr-2012___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: change of NOO delayed submission of progress and financial reports. UNEP assisted NOU with reporting and processing of disbursements ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Project completed. Last disbursement made in Jul-2014. Second tranche request prepared in Feb-Mar 2015. Submitted and comments from MLFS addressed in Apr-2015. Second tranche approved in May-2015 by 74 ExCom. | 0
UNEP | Suriname | CFC Phase Out Plan | 2008-11-01 | 2013-12-01 |  | 153000 | 100000 | 99473 | 0 | 6.2 | 0 | 0 |  |  | Project financially completed. | Project financially completed. | 0
UNEP | Swaziland | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2016-07-01 | 210000 | 130000 | 69180 | 1.4806 |  |  | 0 |  |  | Brief progress report (actual/planned): __ The country conducted awareness meeting on ODS Phase-out. The NOU supported the registration of the Association and conducted two meetings for the Association. 25 customs officers were trained on the control of ODS importation and 45 technicains were trained on the use of ODS alternatives. NOU visited the Palfridge Fridge Factory to follow up on the completion of Conversion project of the factory, a project funded by Multilateral Fund Secretariat. Legal arrangements (actual/planned):SSFA was signed in January 2014. Any delay (Yes/No): No_ First mission (actual/planned): CAP visited the country in October 2014 to monotor implementation of second tranche and had meetings with the Refrigeration Association, customs officers and management of SEA__N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in April 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU processed the allocation of 2015 HCFC quotas , conducted stakeholders' consultative meetings on 2015 HCFC 10% reduction target. NOU registered all importers of HCFC for 2015 | 0
UNEP | Swaziland | CFC Phase Out Plan | 2008-11-01 | 2013-03-01 |  | 132000 | 132000 | 127018 | 0 | 3.7 |  | 0 |  |  | Project completed |  | 0
UNEP | Tanzania | HCFC Phase Out Plan (Stage I) | 2012-07-01 |  | 2015-07-01 | 110000 | 55000 | 35000 | 0.30905 |  |  | 0 |  |  | Brief progress report (actual/planned): __ The country conducted regional training workshops and trained a total of 65 refrigeration and air-conditioning experts from Mbeya and Mwanza regions. A total of 80 customs officers from Arusha and Dodoma regions were trained in the enforcement of ODS control measures. The country has completed implementation of first tranche activities and second tranche request is being prepared. Legal arrangements (actual/planned):SSFA was signed in January 2013. Any delay (Yes/No): No_ First mission (actual/planned): __First mission by CAP to launch the HPMP and conduct training for technicians was made jointly done with UNIDO in June, 2013._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in February 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU registered all importers for 2015 and processed the allocation of 2015 HCFC quotas. | 0
UNEP | Tanzania | ODS Phase Out Plan | 2008-04-01 | 2013-06-01 |  | 209000 | 209000 | 209000 | 0 | 38.1 |  | 0 |  |  | project completed | Project completed | 0
UNEP | Timor-Leste | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2016-12-01 | 164900 | 148500 | 93236 | 0.03 |  |  | 0 |  |  | Brief progress report (actual/planned): Two tranches have been approved for Timor Leste HPMP. The first tranche was approved at the 63rd ExCom meeting and the second tranche was approved at the 69th ExCom meeting. The Customs training workshop was organized during 21 - 23 of January 2014 with 17 customs officer and one person from Industry department. The stakeholders’ consultation meeting was conducted on 24 of January 2014 to discuss the HPMP implementation. National training workshop in good practices conducted in Jun 2014 and with south/south support from senior trainer of Indonesia- 12 technicains compelted the training and from this 5 were selected to be national trainers. Following the consultation meeting conducted in November 2014 among the National Ozone Unit (NOU), State Secretary of Environment (SEMA), United Nation Environmental Programme (UNEP) , United Nation Development Programme (UNDP) and the Centro Nacional Formacão Professional (CNFP). It was agreed that CNFP and NOU will sign an agreement to list the roles/responsibility for the cooperation on the delivery of the training programme, while UNEP and UNDP will provide their technical assistance for the cooperation. The certificate system for the technician who handle ODS refrigerant was also discussed, and it was agreed to further explore the possibility to jointly establish such system by the NOU and CNFP.The Customs and enforcement training has been conducted in December 2014 and with the support of the Indonesia NOU. Legal arrangements (actual/planned): The SSFA for first tranche and the second tranche was signed in March 2012 and June 2014 respectively. However, the SSFA for the first tranche was closed in December 2013 and the remaining balance from the first tranche was transferred to the SSFA of the second tranche to facilitate project implementation and monitoring. TOR completed: N/A First disbursement date: June 2012 (first tranche) All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow implementation in follow up activities after the initial activities conducted by UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes, the revised project completion date of HPMP Stage I is expected to be in December 2016. Any ongoing problems (yes/no): No, the implementation is progressing If Yes, is any action required by ExCom: N/A | The MOU between the NOU and the Centro Nacional Formacão Professional (CNFP) On training of technician on good service practices and retrofitting was drafted in 2015. In May 2015, two senior RAC trainers received refresher training in good refrigeration servicing skills in Malaysia. UNEP held high level meetings with the Vice Minister of Envionment, NOU and his technical team in May of 2015, to present on the status of Montreal Protocol implementation and seeking the support of his good office to expedite approved projects. At this meeting held in Bangkok, the Vice Minister gave his support for the Montreal Protocol implementation. 2014 CP data timely submitted online. | 0
UNEP | Togo | HCFC Phase Out Plan (Stage I) | 2010-12-01 | 2012-09-01 |  | 280000 | 115000 | 70000 | 3.1111 |  |  | 0 |  |  | Completed in September 2011 | Completed | 0
UNEP | Togo | CFC Phase Out Plan | 2008-04-01 | 2010-12-01 |  | 159000 | 159400 | 158708 | 0 | 6 |  | 0 |  |  | Completed since 2010 | Completed | 0
UNEP | Tonga | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 127000 | 114300 | 57976 | 0.02585 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. The Tonga Customs has adopted the 2012 HS code in February 2014. Provisions of permit system for technicians to handle controlled substances and for workshops/dealers to store and sell controlled substances have been put in place. The regulation also includes the labelling requirement of controlled substances. Refrigerant identifier was handed over to Customs for inspection. RAC Association has been established since November 2013. A refresher training workshop for RAC technicians was organized in December 2014 with 25 participants. RAC servicing tools equipment/tools were distributed to RAC technicians through contractual agreement under monitoring of NOU. The recovery machines have been kept at the NOU tool bank and released to technician upon request from time to time. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in August 2011. TOR completed: N/A First disbursement date: September 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | NOU as lead HPMP national agency prepared and submitted required reports allow for submission as part of the PIC regional HPMP Phase1, tranche 2. The NOU provided the input in preparing and finalizing the second tranche report. This was approved at the 74th Ex. Com. 2014 CP data timely submitted online. Activities proposed in the second tranche report are to be implemented under the second tranche of HPMP. The ban on HCFC-based equipment will be entered into force from January 1, 2016 onwards. | 0
UNEP | Turkey | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2017-12-01 | 103450 | 103450 | 64403 | 3.4033 |  |  | 0 |  |  | Brief progress report (actual/planned): UNEP in cooperation with the NOU of Turkey decided to organize two consecutive workshops was (1) to train at the Training-of -Trainers workshop in Istanbul the group of 30 officers representing different customs points and provincial environmental directorates in the country who would be later supposed to train their colleagues and (2) to check the training skills of few trainers selected from that group by letting them conduct the workshop in Izmir under supervision of International Consultant. The advantage of such system is that the sustainability of the results of customs training can be better secured provided that the customs authorities will decide to organize a series of next training workshops on a provincial level utilizing the skills and knowledge of officers trained at the Training-of-Trainers workshop. The Agenda and Concept Note for both workshops were prepared and the international consultant was recruited. All logistics were agreed and UNDP country office informed about the travel and DSA for both meetings. Legal arrangements (actual/planned): The project is directly managed and implemented by UNEP First mission (actual/planned): Not planned TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): The first disbursement is planned for February 2015. All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The National Training of Trainers workshop for Customs officers (ToT) was organized on 25-27 February of 2015 in Istanbul, Turkey and the Training workshop for other customs officers was organized on 2-3 March of 2015 in Izmir, Turkey. The main objective of the training programme was to provide the customs and enforcement officers of Turkey with the necessary practical skills and knowledge to identify HCFCs and HCFCs containing equipment. It was important to enable customs officers to get acquainted with the ODSs regulations and other legislation regarding ozone issues and create awareness amongst customs officers on their role in enforcing Montreal Protocol at the national level. An additional special objective of TOT workshop was to make the participants acquainted with the methodology of dealing with the issues at the training workshops they will be supposed to conduct in the future in their capacity as trainers. The idea of holding two consecutive customs training workshops on monitoring and control of ODS trade – one designed as special ToT workshop and the other as the “standard” customs training workshop – was proved to be perfect. It is therefore recommended that similar approach is taken to customs trainings foreseen in the HPMPs in other developing countries. Legal arrangements (actual/planned): The project is directly managed and implemented by UNEP First mission (actual/planned): Not planned TOR completed (actual/planned): n/a - CAP staff implementing directly First disbursement date (actual/planned): The first disbursement was done in February 2015. All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | 0
UNEP | Tuvalu | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 92000 | 82800 | 44398 | 0.0308 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014.The Department of Customs has adopted the 2012 HS code for the import and export control. Tuvalu was in the process of amending the Ozone Depleting Substance Regulation to control the import/export of HCFC-based equipment and to include provision regarding requirement of handling license and renewal of license. The amendment was on its last stage of getting signed after approved by cabinet. Refrigerant identifier was kept at the NOU and the Customs requested NOU to have refrigerant identifier for inspection when needed. A refresher training workshop for customs and enforcement officers was organized in November 2014 with 20 participants. TOR for RAC Association was being finalized in close collaboration with the Attorney General Office. RAC servicing tools equipment/tools have not yet distributed to RAC technicians due to the need to link with the established RAC Association. However, equipment was released to technicians who made the application to NOU from time to time. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in November 2011. First Mission: August 2014 TOR completed: N/A First disbursement date: December 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): No, project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted on line. Training New NOU in the HPMP management including reporting requirements (progress and financial report). | 0
UNEP | Uganda | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2016-12-01 | 84500 | 40500 | 2771 | 0.035957 |  |  | 0 |  |  | Brief progress report (actual/planned): __ NOU organized National Workshop for main stakeholders to discuss the implementation of HPMP activities. NOU conducted a survey of equipment available in the vocational training centres in-order to determine the need for new equipment to be procured under the HPMP. A total of 50 Customs Officers were trained in the implementation and enforcement of ODS control measures and 30 RAC technicians were trained in the use of ODS alternatives. Legal arrangements (actual/planned):SSFA was signed in July 2013. Any delay (Yes/No): No_ First mission (actual/planned): __N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in October 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Country conducted steering committee meeting to process HCFC quota allocations for 2015 and registered all importers of HCFC for 2015 | 0
UNEP | Vanuatu | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2020-12-01 | 148500 | 133650 | 71919 | 0.13035 |  |  | 0 |  |  | Brief progress report (actual/planned): The first tranche was approved at the 63rd ExCom Meeting in April 2011. The licensing and quota system has been enforced in 2014. The Vanuatu Customs & Inland Revenue (VCIR) has adopted the 2012 HS code, which will be effective from 1 January 2015 onwards. The provisions for licensing for storage, sale and handling of HCFCs have been put in place. NOU has worked with concerned agencies to ban all HCFC-based equipment (both new and used). Refrigerant identifiers were handed over to Customs for inspection. A refresher training workshop for customs and enforcement officers was organized in September 2014. The RAC Association of Technicians has been established since March 2011. About 40% of servicing tools were handed-over to technicians and the remaining would be distributed to technicians upon finalization of eligibility criteria. Ongoing awareness raising and monitoring of HPMP implementation. In 2014, the second tranche of HPMP was prepared, which would be submitted to 74th ExCom Meeting in May 2015. Legal arrangement: The SSFA has been signed in August 2011. First Mission: May 2012 TOR completed: N/A First disbursement date: August 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): No, , project being timely implemented. If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Negiotated successfully with country and including addressing all MLF Secretarait commments for the preparation of the Second Tranche HPMP request. This was submitted in advance of the MLF 74th mandatory deadlines. Tranche was approved. CP data timely submitted on line. Held meeting with the NOU and UNEP CAP staff in the margins of the OEWG April 2015 to discuss possible revision need of the HPMP and taking into consideration the devastation on the built infrastructure following Cyclon Pam in early 2015. Refresher RAC sector training to be delivered in July 2015 in three of the islands in Vanuatu. | 0
UNEP | Venezuela | HCFC Phase Out Plan (Stage I) | 2011-04-01 |  | 2015-12-01 | 136000 | 122432 | 10678 | 1.66 |  |  | 0 |  |  | Brief progress report: No disbursements in 2014. UNEP submitted a signed agreement with remaining budget but the Government did not sign it in 2014. First mission (actual/planned):N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): April 2011/Nov 2011. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: NOO changes in 2014. A request of changing the signatory of the agreement (by Chief of NOU instead of Minister) was not acceptable to UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): Yes. The NOU requested the funds are transferred to UNIDO in April 2015. If Yes, is any action required by ExCom: Transfer project balances from UNEP to UNIDO | Government asked project balances are transferred from UNEP to UNIDO | 0
UNEP | Yemen | HCFC Phase Out Plan (Stage I) | 2012-12-01 |  | 2015-12-01 | 380000 | 215000 | 0 | 30.4385 |  |  | 0 |  |  | `• Brief progress report (actual/planned): - Country contract was signed at end of 2014 incorporating relocated balances from NPP as per ExCom decision 68/53. First payment planned in 2015 - Country made detailed work-plan for the implementation of the HPMP which is was pending the funds disbursement • Legal arrangements(actual/planned): Signed end of 2014 • First mission (actual/planned): No mission possible to Yemen for the last 3 years due to security considerations • TOR completed(actual/planned): TORs for technical components were drafted and handed to NOU for comments/inputs and action • First disbursement date (actual/planned): No • All funds disbursed (yes/no): No • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in signing the country contract • If Yes, will delay have impact on project completion date (yes/no): Yes, stage-I is likely to be extended beyond 2015 • Any ongoing problems (yes/no): Yes, special consideration for the implementation in Yemen given the current conflict situation • If Yes, is any action required by ExCom: No | # UNEP/UNIDO organized coordination meeting with NOU of Yemen (March 2015) in Bahrain where a detailed work-plan for expediting HPMP activities was concluded # Conflict started in Yemen end of March 2015 resulting in putting all activities on pause status due to high risks and deteriorated security situation in most areas of the country # Country contract payment was ready to be transferred but recent conflict resulted in postponing the payment after consultation with NOU till verifying the condition of the project special bank account. | 0
UNEP | Yemen | ODS Phase Out Plan | 2008-07-01 |  | 2016-12-01 | 455000 | 455000 | 232213 | 0 | 269.4 |  | 0 |  |  | Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project | 0
UNEP | Zambia | HCFC Phase Out Plan (Stage I) | 2011-07-01 |  | 2013-07-01 | 175000 | 80000 | 35000 | 0.94444 |  |  | 0 |  |  | Brief progress report (actual/planned): __ The NOU implementing certification scheme for RAC technicians and certified 25 refrigeration experts on the refrigeration and air-conditioning services. The NOU conducted 4 training workshops for customs officers and a total 80 officers were trained. The NOU conducted 3 meetings of the Refrigeration Association and conducted joint annual inspection visits to major retail shops of refrigerants to check on the quality of refrigerants that are available on the market. Legal arrangements (actual/planned):SSFA was signed in February 2012. Any delay (Yes/No): No_ First mission (actual/planned): __CAP visisted the country in October 2014._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made inApril 2012.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | NOU processed the allocation of 2015 HCFC quotas , conducted stakeholders' consultative meetings on 2015 HCFC 10% reduction target. Implementation of project activities completed and country processing implementation of second tranche activities. | 0
UNEP | Zambia | CFC Phase Out Plan | 2007-11-01 | 2012-03-01 |  | 136000 | 136000 | 131000 | 4.11 | 4.1 |  | 0 |  |  | Project completed |  | 0
UNIDO | Albania | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2020-12-01 | 230000 | 137000 | 43209.39 | 1.5333 | 6 |  |  |  |  | - Ongoing HPMP since 2011, first and second tranches approved at the 64th and the 70th Meetings. Milestones: Milestone 1: Equipment specification development - Yes Milestone 2: Specific legislation on certification scheme - No Milestone 3: Equipment delivery - Partly Actions towards next goals: Work plan development for the year 2015 and new tranche release submission in 2015. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Legislation up-date for certification scheme was initiated but not finalized due to required time for the approval process in the Government. The activity will continue in 2015 and approval process will be finalized in 2016. Any impact on project completion date: Yes. Administrative restructuring and change of NOU Officer in Albania caused few months of delay, however, the delay was compensated through revised work plan agreed in December 2014 and active involvement of NOU newly appointed officer first half of 2015. | - Tranche I implementation was completed in March 2015. - Tranche II implementation was initiated and disbursement reached 35% by June 2015. - Technical specification for additional equipment purchase was developed and delivery will take place second half of 2015. - Verification report in view of tranche II submission will be finalized by September 2015. - New legislation for certification scheme is under development and it is expected to be completed by the end of 2015. - Equipment delivery is scheduled for second half of 2015 - Progress report for Tranche II submission is under development in view of its consideration by the 75th Meeting of the ExCom.
UNIDO | Albania | National ozone depleting substances phase-out plan | 2003-04-01 | 2012-09-01 |  | 535000 | 535000 | 533166.76 | 68 | 0 | 0
UNIDO | Algeria | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2017-12-01 | 1993331 | 1809240 | 47137.02 | 14.48 | 62.1 | 53.66 |  |  |  | - Ongoing HPMP since 2012, first tranches in the refrigeration servicing and the conversion of the RAC manufacturing sectors, approved at the 66th Meeting. Additional investment component for the manufacturing of polyurethane rigid insulation foam approved in 2010. Milestones achieved: REF manufacturing First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: No (Draft ToR prepared, but not yet agreed by the beneficiary); Bids prepared & request: No Contract awarded: No Equipment delivered & installed: No Commissioning & trial runs: No UNIDO planned to agree on the TOR during the reporting period, however, no agreement reached yet due to the long lead time required before a decision is taken by the company management on the actual conversion activities. Together with the component supplier a joint field visit is planned to be organized on the 3rd or 4th quarter 2015. The introduction of a new technology requires extensive preparatory work by the beneficiary, preparation of prototype, negotiation with component suppliers and training of company staff. The company will require HCFC-22 quota for a longer period. In addition, if the disbursement rate does not achieve 20%, the country will face difficulties in getting the next tranche for the servicing sector approved. PU Foam Investment component Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes (had to be re-initiated) Milestone 4: Contracts awarded - No | Conversion in the refrigeration manufacturing '- As reported to the 74th Meeting of the ExCom, disbursement level was not expected to increase significantly during 2015. Disbursement level is still less than 10%. Revised TOR was sent to the beneficiary's review and comments. UNIDO was informed by Condor in May 2015 that they received a prototype from the component supplier without refrigerant charge. However, it is to be noted that Condor is currently investigating the possibility of R290 as alternative instead of R32. However, since R290 is not available in the country, Condor submitted a request to local authorities in order to import R290, which is a lengthy procedure and the refrigerant might not be available before August 2015. Thus, testing can only be undertaken after August. In the meantime, UNIDO is in contact with Condor to get an agreement on the TOR and to start bidding at the earliest possibility. Since both R32 and R290 are flammable and as designed in the project document, whichever technology is selected, Condor and UNIDO would have to comply with ATEX safety standards. Reasons for low disbursements: Slow progress due to new technology, long lead time required before a decision is taken by the company management on the actual conversion activities. REF Servicing - NOU was contacted to provide feedback on various pending issues from previous years. Activities planned but not implemented, reasons and strategy: Agreement with NOU on project scope and planning could not be finalized. Actions towards next goals: Liaise with the NOU on a concrete plan of action. Foam investment component - ExCom endorsed the revised scope of supply (one full line instead of partial conversion of three lines). UNIDO has contacted the beneficiary and NOU on this regard to allow the action on the conversion. Actions towards next goals: Pursue the beneficiary to finalize the technical specification for the intervention and initiate the bidding exercise.
UNIDO | Algeria | National phase-out plan | 2007-11-01 | 2013-12-01 |  | 921500 | 921500 | 917890.19 | 284.6 | 0 | 0
UNIDO | Algeria | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector | 2002-07-01 | 2007-11-01 |  | 1424647 | 1424647 | 1412104 | 245 | 0 | 0
UNIDO | Argentina | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2017-12-01 | 9560542 | 9435542 | 7537102.94 | 65.1 | 400.7 | not yet available |  |  |  | - Ongoing HPMP since 2012 with first tranche in the refrigeration servicing sector and investment component in the AC manufacturing since 2010. Refrigeration servicing sector First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: Yes Bids prepared & request: Yes Contract awarded: Yes Equipment delivered & installed: Yes Commissioning & trial runs: No - Training equipment was delivered and training workshops were organized. - Training activities continued in 2014. - Distribution of kits. AC manufacturing Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes - IOC payment completed. - The consumption of HCFC-22 was completely phased out. - Technical problems with some items supplied by Agramkow were solved. - The last company pending to install the equipment started the civil work at its premises. | Refrigeration servicing sector - In the beginning of 2015 training activities have continued. - The 74th Meeting of the ExCom in May 2015 approved the second tranche. - Budget allocation was prepared for the second tranche. - The first activity was a training in the city of Rosario. AC manufacturing - UNIDO followed up with the supplier and the beneficiary company for the installation. - It is expected that the installation will be completed by end of August 2015.
UNIDO | Argentina | National CFC phase-out plan | 2004-04-01 |  | 2015-10-01 | 6860850 | 6860850 | 5931039.86 | 1808 | 0 | 0 |  |  |  | - National CFC phase-out plan ongoing since 2004 with 2007 and 2008 work programmes currently ongoing. Activities done in relation to the HPMP, as Dec 66/42 (h). The HPMP continues as reported to the 74th Meeting of the ExCom, (second tranche approved). We are reviewing the obligations and expenditures of this project before final completion. | - As per Dec 73/8, project could be extended due to reallocation of funds to HPMP. - Project will be completed after the obligation review.
UNIDO | Bahamas | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 151420 | 115592 | 93103 | 0.82507 | 4.81 | not yet available |  |  |  | - Ongoing HPMP with first and second tranches approved at the 65th and the 71st Meetings. Milestones achieved: Milestone: Training and certification for RAC technicians took place June-July 2015 | - After re-assessment of the needs of the service sector in the country, a training programme was planned for technicians. - Funds from both the 1st tranche and 2nd tranche were earmarked for this programme.
UNIDO | Bahrain | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2020-12-01 | 2338985 | 549455 | 5464.72 | 19.3265 | 51.9 | not yet available |  |  |  | - HPMP ongoing since 2012 with first tranche in the AC manufacturing and a technical assistance component for a reclamation facility. Milestones achieved: AC manufacturing First mission held: Yes Agreement signed: Yes TOR for equipment completed: Yes TAS Mission undertaken: Yes TOR for the reclamation center completed: Yes Call for bids for the selection the company issued: Yes Procurement of equipment for the reclamation center: No Was there any delay during the reporting year? Yes If yes, reasons and action plan: A change of the Ozone officer occurred in 2014. Local call for bids not issued by NOU. | AC manufacturing - TOR have been prepared for the procurement of equipment but the procurement process has been suspended as UNIDO was contacted by UNDP to explore the possibility of transferring equipment purchased for the SAGA project (being cancelled). - UNIDO see that the Bahraini company could be interested. They have been informed and a review of the equipment is ongoing. Activities planned but not implemented, reasons and strategy: procurement process suspended to explore to explore the opportunity of equipment transfer from the SAGA project Any impact on project completion date: Yes If yes, implications: The conversion can be delayed due to the delay in the test and trials for the selection of the alternative technology TAS - A mission has been conducted to support the NOU in the local call for bids process. - Criteria for the selection of the company to host the center have been developed and the call has been published. Activities planned but not implemented, reasons and strategy: Procurement of equipment for the reclamation center was not initiated as the beneficiary was not yet selected through local bidding. To avoid further delay, the procurement of equipment will be initiated in parallel with the selection of the company to host the center instead of doing it after the beneficiary is known as first planned. Actions towards next goals: Initiate procurement of equipment in parallel with the selection of the beneficiary Was there any delay during the reporting year? Yes If yes, reasons and action plan: A change of the Ozone officer occurred in 2014. Local call for bids not issued by NOU before July 2015, hence beneficiary not yet selected. The action plan is to initiate the procurement of equipment in parallel with the selection of the beneficiary.
UNIDO | Benin | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2020-12-01 | 260000 | 140000 | 91704.51 | 3.4 | 23.8 | not yet available |  |  |  | - HPMP ongoing since 2011 with first and second tranches approved at the 63rd and 70th Meeting. Milestones achieved: ToR for equipment purchase agreed upon: Yes, June 2014; Bids prepared & requested: Yes, September 2014; Contract awarded: Yes, December 2014; Equipment delivered: No Training of trainers organized: No Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Clearance of goods upon arrival and organization of training, distribution of equipment. | - Equipment has reached Benin early April, but despite the supplier's and UNIDO's advance information to UNDP Cotonou, customs clearance was delayed until after 15 May 2015. Currently, training of trainers is being organized in one of the excellence centers for servicing in Cotonou, after which equipment will be distributed to service technicians. The training will have a special session on the proper installation and servicing of R290 air conditioners. For this purpose, 3 AC units designed for R290 were delivered end June 2015, which will be distributed to the 3 excellence centers in Benin for further training in future. Actions towards next goals: Organization of training activities and distribution of equipment afterwards.
UNIDO | Benin | Terminal phase-out management plan | 2008-07-01 | 2011-12-01 |  | 175000 | 175000 | 174599.38 | 7.9 | 0 | 0
UNIDO | Bolivia | HCFC phase-out management plan (stage I) | 2015-05-01 |  | 2017-05-01 | 124500 | 124500 | 0 | 1.89 | 6.1 | not yet available |  |  |  |  | The project was transferred from Germany to UNIDO at the 74th ExCom in May 2015.
UNIDO | Bosnia and Herzegovina | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 953284 | 760261 | 553343.19 | 6.59 | 4.7 | 3.37 |  |  |  | - Ongoing HPMP with first (REF servicing, and conversion in the foam sector) and second tranches approved at the 66th and the 72nd Meetings. Milestones REF servicing, first tranche Milestone 1: Review of Ozone legislation and the quota system - Yes Milestone 2: Preparation of quota permits for HCFC import - Yes Milestone 3: Preparation of Code of Good Practice in Refrigeration - No Milestone 4: Training programme for custom & maritime officers - Yes Milestone 5: Programme for certification of refrigeration service technicians - Yes Activities planned but not implemented, reasons and strategy: The preparation of the Code of Good Practice had to be delayed due to health problems of the national expert. The work is scheduled for the 2nd half of 2015. REF servicing, second tranche - Project approved at the 72nd Meeting of the ExCom in May 2014. - Noted that the Agreement was updated to reflect the change in support costs owing to the new administrative cost regime; that there were indications in the verification report that the country might have had a consumption of 580 ODP kg of HCFCs in 2013 above the maximum allowable consumption limit established in the Agreement; that further work was required to establish the actual consumption of Bosnia and Herzegovina in 2013; and that Bosnia and Herzegovina had undertaken the necessary steps to return to compliance with the Agreement in 2014 and future years. - Approved on the understanding that 10 per cent of the agreed funding for the second tranche was withheld in line with decision 54/34 until the exact consumption in the year 2013 had been established; and that on the basis of the actual 2013 consumption, whether and at what level a penalty would have to be applied, up to the limit of the funds withheld from the second tranche would be considered. Milestone 1: Preparation of Technical Specification for refrigeration equipment for 6 SMEs - Yes Milestone 2: Publication of Request for Proposals - No Milestone 3: Contract Award for selected supplier - No Milestone 4: Delivery of equipment to 6 SMEs - No Milestone 5: Training workshops for custom officers and maritime agents - No Activities planned but not implemented, reasons and strategy: Due to delays in preparation of technical specification, the procurement was initiated only early 2015. Was there any delay during the reporting year? Yes: One of the SMEs (Ordagic D.O.O. from Srebrenik) refused to cooperate with the NOU despite effort by the NOU and national expert. Conversion in the foam sector, first tranche Milestone 1: Equipment for Alternatives delivered and commissioned - Yes Milestone 2: Foaming equipment for 6 SMEs delivered and commissioned - Yes Milestone 3: Training on foaming with for 6 SMEs by UNIDO foam expert conducted - Yes Milestone 4: Final commissioning and safety certification of „ALTERNATIVA“ HCFC-conversion project - No Milestone 5: Technical specification for refrigeration equipment for 6 SMEs prepared - Yes Was there any delay during the reporting year? Yes If yes, reasons and action plan: 1. Commissioning of the pentane foaming line at Alternativa was delayed since the supplier and the beneficiary could not agree on the scope of work to be done by each of them. Commissioning of one foaming machine was delayed since the machine was damaged by a flooding in BiH in August 2014. Quotation from the supplier for the repair of the damaged part was received and the repair scheduled for 2015. | REF servicing, first tranche Project implementation is ongoing in 2015, targeting completion in December. REF servicing, second tranche '- Procurement of refrigeration equipment for 5 SMEs initiated in February 2015, offers received from 3 qualified suppliers, contracts awarded for supply of equipment to two suppliers (split of the required list for better price) in April 2015. - Customs clearance process initiated in June 2015, delivery expected in July 2015. Actions towards next goals: Delivery of equipment. Training activities for customs officers and maritime agents. Conversion in the foam sector, first tranche Safety review and certification by international consultant planned for September 2015. Operational completion planned by December 2015.
UNIDO | Bosnia and Herzegovina | National ODS phase-out plan | 2003-12-01 | 2013-12-01 |  | 864160 | 864160 | 838992.82 | 121.1 | 0 | 0
UNIDO | Burkina Faso | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 249900 | 150000 | 138968.4 | 3.2 | 28.9 | 12.38 |  |  |  | - Since there were no funds for investment component in the 2nd tranche, the NOU requested the remaining funds to be used to upgrade the capacity of the training center to carry out demonstrations on the safe installation, operation and maintenance of hydrocarbon ACs. Was there any delay during the reporting year? Yes. There were internal problems in the Ministry of Environment. The person known to UNIDO as the Ozone Officer was removed therefore no new activities could be initiated. A new Ozone Officer has since been appointed. | - A new Ozone Officer has since been appointed. - Activities will continue in the 2nd half of 2015 after the Ozone Officer has reviewed the needs of the service sector.
UNIDO | Burundi | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 160000 | 80000 | 65611.49 | 1.2048 | 7.15 | 6.82 |  |  |  | - HPMP ongoing since 2011 with first tranche approved at the 65th Meeting. Milestones achieved: Mission undertaken: Yes TOR for the reclamation center completed: Yes Call for bids for the selection the company issued: Yes Equipment procured, delivered and distributed: Yes | - HPMP ongoing since 2011 with first tranche approved at the 65th Meeting. Milestones achieved: Mission undertaken: Yes TOR for the reclamation center completed: Yes Call for bids for the selection the company issued: Yes Equipment procured, delivered and distributed: Yes Actions towards next goals: Discuss the next tranche with NOU
UNIDO | Burundi | Terminal phase-out management plan | 2008-07-01 | 2013-12-01 |  | 129000 | 129000 | 128799.48 | 3.1 | 0 | 0
UNIDO | Cameroon | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2017-12-01 | 1182725 | 1064453 | 776116.7 | 20.5 | 88.8 | not yet available |  |  |  | - Ongoing HPMP since 20122 with first (REF servicing and foam) and second (REF servicing) tranches approved at the 64th and the 71st Meetings. First tranche in REF servicing - Technicians training workshops as a follow up of train the trainer component were initiated in the last quarter of 2013 and continued during 2014. - Quota system implementation in 2014 took into account the revised ExCom agreement upon approval of the second tranche of HPMP. - Customs officers training programme (concept development and workshop in 2014) under planning process. Milestones achieved: Milestone 1: Contract with counterpart for training activities achieved - Yes Milestone 2: Customs training achieved - Yes First tranche in the foam sector - Conversion of foam enterprises was achieved (equipment was delivered and training performed by the supplier on the use of methyl format technology). - Additional training for SMEs in the foam sector was performed, including field demonstration activity. Milestones achieved: Milestone 1: Equipment delivered - Yes Milestone 2: Training for SMEs - Yes Milestone 3: Conversion to methyl format technology in place - Yes Actions towards next goals: Additional training for SMEs has been scheduled for the remaining project balance to address the SMEs sector in 2015. Second tranche in the REF servicing - Work plan for the second tranche covering 2014 - 2015 was agreed with counterpart in July 2014. - Technical specification development for recovery/recycling network and equipment delivery was developed. Milestones achieved: Milestone 1: Work plan for the implementation of Tranche II - additional training activities - Yes Milestone 2: ToR for equipment purchase - Yes Actions towards next goals: Early data collection activities in view of elaboration of Consumption Verification Report for the year 2014 initiated. | First tranche in REF servicing '- ToR for equipment purchase for servicing sector agreed with counterpart upon training activities outcome. - Bidding for contract with supplier for equipment purchase ongoing. - Equipment delivery scheduled second half of 2015. First tranche in the foam sector - Additional training on the use of Methyl Formate is scheduled to take place in August 2015. - For additional equipment (spare-parts) local bidding was organized and the contract will be finalized in August 2015. - Additional equipment (spare-parts) will be delivered to ensure proper use of the delivered portable foaming machines. - Foam component implementation to be finalized during current year. Actions towards next goals: Operational completion by end of 2015. Any impact on project completion date: Yes If yes, implications: Completion date is delayed against original forecast due to training activities for SMES that required longer time period for organization than initially planned and due to additional training required. Training has been scheduled to take place 1st week of August 2015, and additional spare parts delivery will be achieved last quarter of 2015 Second tranche in the REF servicing '- Development of ToR for continuing the training activities in servicing sector has been agreed with counterpart. - Contract to be released during the 3rd quarter of 2015 and additional training workshops to take place in the second half of 2015. - Verification report in view of the 3rd tranche submission was contracted as of July 2015. Actions towards next goals: Preparation of the progress report for the tranche 3 submission for the consideration of the 75th Meeting of the ExCom. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Submission of the tranche 3 request to the 74th Meeting of the ExCom was rescheduled for the 75th Meeting, as ODS consumption data for the year 2014, subject to Verification Report, were not yet available in the first quarter of 2015.
UNIDO | Cameroon | Terminal CFC/TCA phase-out management plan | 2006-11-01 | 2011-12-01 |  | 800000 | 800000 | 797941.22 | 50.6 | 0 | 0
UNIDO | Central African Republic | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2020-12-01 | 250000 | 125000 | 19000.74 | 1.875 | 12 | not yet available |  |  |  | - HPMP is ongoing with first tranche approved in 2011. - The situation in the country was not improved to allow for resuming project implementation. - UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Activities planned but not implemented, reasons and strategy: Delivery of equipment is planned as soon as the situation in the country improves, but the situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. Actions towards next goals: Delivery of equipment is planned as soon as the situation in the country improves. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. | - The situation in the country was not improved to allow for resuming project implementation. - UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Activities planned but not implemented, reasons and strategy: Delivery of equipment is planned as soon as the situation in the country improves, but the situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. Actions towards next goals: Delivery of equipment is planned as soon as the situation in the country improves. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The situation remains highly unstable thus making it impossible to deliver the equipment with a minimum assurance that the equipment will reach end beneficiaries. UNIDO has taken the necessary measures to ensure expedite implementation as soon as the situation in the country allows for it. Any recurring problem? Yes If yes, description of the problem/s: High social and political instability in the country. Any impact on project completion date: Yes If yes, implications: Project implementation and completion delayed indefinitely. Any action required by Executive Committee? No
UNIDO | Chad | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 235000 | 135000 | 124162.44 | 2.4 | 16.1 | not yet available |  |  |  | - HPMP is ongoing with first tranche approved in 2010. - A joint UNIDO-UNEP training that was envisaged did not materialize. - Further needs for equipment were discussed with NOU and subsequently purchased from a local supplier. Milestones achieved: Equipment procured: Yes Actions towards next goals: Discuss the next tranche (due in 2016) with NOU | - The additional equipment purchased locally was delivered to the N'Djamena reference center and is in use for training purposes. Milestones achieved: Equipment delivered: Yes Actions towards next goals: Discuss the next tranche (due in 2016) with NOU
UNIDO | Chile | National phase-out of methyl bromide - terminal project | 2010-04-01 |  | 2015-12-01 | 1657917 | 1657917 | 1479163.82 | 164.4 | 164.4 | not yet available |  |  |  | - National methyl bromide phase-out project is ongoing since 2010 with first and second tranches approved at the 60th and the 69th Meetings. - A study tour for the strawberry farmers was organized in February 2014. - Some workshops for the strawberry sector were organized in March and April 2014. - Information and data were compiled for dissemination and promotion of alternatives in the country. | - In January 2015 a workshop was organized to celebrate the achievement: no more MB in the country - The strawberry component is being finalized. - A manual has been prepared on alternatives of MB used in the production of strawberries. - Two last workshops with the participation of international experts took place in June 2015. - The final activities will be the dissemination of the results at universities, in publications, and through general awareness raising campaign on the success of the project and the production without methyl bromide.
UNIDO | China | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2017-12-01 | 75000000 | 63750000 | 39917116.75 | 520 | 4108.5 | not yet available |  |  |  | - Ongoing HPMP in the room AC manufacturing sector with four ongoing tranches since 2011, the last approved at the 73rd Meeting in 2014. First tranche '- Under this tranche 8 lines are planned to be converted to R290, 7 lines to R410A and 1 compressor line to R290. - Conversion to R410A of six production lines was completed in 2014. - Bidding was completed for all R290 conversions under the tranche and main equipment have been delivered for 4 lines by the end of 2014. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes,partially (for six R290 lines) Conversion completed: Yes partially (3 R290 lines and 6 R410A lines) TUV certification and national acceptance completed: Yes partially Second tranche '- Under this tranche 1 R290 line, 1 R410A line and 2 R290 compressor conversions are planned. - Contracts with all companies have been signed and equipment have been delivered for all companies. - With the exception of 1 compressor line, all conversions have been completed by end 2014. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes (3 companies), No (1 company) TUV certification and national acceptance completed: Yes, partially. Third tranche '- Under this tranche 4 lines will be converted to R290. - Work plan has been agreed upon for R290 RAC production lines conversion for all beneficiaries. - A UNIDO mission was undertaken in April 2014 to verify the production lines. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes for 3 lines Equipment delivered and converted: Yes, main equipment delivered for 3 lines TUV certification issued: No Fourth tranche - The Treasurer was requested to offset future transfers to UNIDO by US$67,293 representing additional interest accrued by the Government of China in 2012 and interest accrued up to 31 December 2013 from funds previously transferred for the implementation of the RAC sector plan for China in line with decision 69/24. UNIDO took relevant actions to recover the interest. | First tranche '- Conversion to R290 at 3 enterprises' production lines was completed so far in 2015. - Conversion at 3 companies partially completed. Second tranche '- Technical verification of the converted lines was done in June 2015. - Conversion of the remaining compressor line is expected to be completed by end 2015. Third tranche '- Progress was made, main equipment was delivered for the conversion of 3 lines and bidding has been completed for the remaining 1 line for which contract signature is expected by September. - During inspection it was found that two companies do not meet safety requirements of the local Administration of Work Safety and thus, the buildings with the R290 tanks have to be adjusted. - Additional inspections will be carried out by the local government in September 2015. Fourth tranche '- Working arrangements were agreed upon early 2015 and first mission was undertaken in February 2015. The current tranche will support China for the conversion of 4 lines to R290. | 16116127
UNIDO | China | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2017-12-01 | 48650000 | 41917000 | 29629416.79 | 592 | 2540 | not yet available |  |  |  | Ongoing HPMP in the extruded polystyrene foam sector with four ongoing tranches since 2011, the last approved at the 73rd Meeting in 2014. First tranche (-) By November 2013, the 12 beneficiaries linked to Tranche 1 had all signed the performance-based sub-contracts with FECO. The total value of the 12 sub-contracts is 19,724,880 US dollars, which will result in 3,929.96 metric tonnes of HCFCs to be eliminated. In accordance with the sub-contracts, the beneficiaries initiated works upon signature of the contracts, and the duration of the conversion was initially set at 24 months. In the course of the sub-contract implementation, beneficiaries are obliged to strictly follow the detailed implementation plans approved by FECO/MEP. (-) By mid-August 2014, 9 beneficiaries, out of 12 charged by Tranche 1, had already finished their equipment procurement and signed the contracts with suppliers. Among the 9 companies, there are 5 companies having received all the equipment purchased. (-) In March 2014, FECO/MEP, with the joint participation of UNIDO, GIZ, the international expert and the selected accounting firm, conducted the verifications of equipment delivery to 2 companies. (-) In May 2014, FECO/MEP, with ISA and the accounting firm conducted the same verification on a third company. (-) In October 2014, one of the companies initially included in this tranche decided to withdraw from the phase-out project; the company committed to stop the production of XPS foam and to phase out HCFCs by themselves. Therefore, the number of the beneficiaries in Tranche 1 reduced to 11, with the total contract value of 18,955,620 US dollars, and all the 11 beneficiaries will result in 3,801.75 metric tonnes of HCFCs to be eliminated. The withdrawal of Zhejiang Yuegong does not have an impact in the achievement of the phase-out targets as initially set for 2013 and 2015, due to the phase-out contribution of both the completed and on-going conversions. Second tranche (-) A total of 6 beneficiaries included in the scope of supply of tranche 2 have signed their contracts for a total value of 9,990,080 US dollars, which will result in a phase-out of 1,890.02 metric tonnes of HCFCs. Third tranche (-) In May 2014, Beijing Bokeman finished its equipment procurement and signed all the contracts with suppliers. Fourth tranche (-) The Treasurer was requested to offset future transfers to UNIDO by US$43,782 representing additional interest accrued by the Government of China in 2012 and interest accrued up to 31 December 2013 from funds previously transferred for the implementation of the XPS foam sector plan for China in line with decision 69/24. (-) Project approved at the 73rd Meeting of the Excom in November 2014. | First tranche (-) By August 2015, all the 11 beneficiaries charged by Tranche 1, have already finished their equipment procurement and signed the contracts with suppliers. Among the 11 beneficiaries, 9 companies have received all the equipment purchased. From September 2014 to August 2015, FECO/MEP, with the joint participation of ISA, technical experts and the selected accounting firm, conducted the performance verifications to the beneficiaries. Beijing Wuzhou and Tangshan Wanxing have passed the national acceptance in January and July 2015, respectively. Second tranche (-) By August 2015, all the 6 beneficiaries in Tranche 2 have finished their equipment procurement and signed the contracts with suppliers. Two out of the six beneficiaries have completed their trial running, and three other companies have received all the equipment purchased and completed the installation of equipment. In the course of project implementation, FECO, in collaboration with ISA, the accounting firm and technical experts, conducted the performance verifications upon the achievement of milestones by beneficiaries, with the purpose of ensuring duly implementing sub-contracts by beneficiaries and monitoring their financial management as per the requirements stipulated in the sub-contracts. Third tranche (-) The beneficiary under this tranche has received all the equipment purchased, finished equipment installation, and one of the lines has completed the trial runs. Fourth tranche (-) 7 companies have been identified as beneficiaries under Tranches 4 and 5. (-) By the end of July, 5 out of the 7 beneficiaries have already finished their equipment procurement and signed the contracts with suppliers. | 12361891
UNIDO | China | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | 2002-11-01 | 2009-12-01 |  | 5571539 | 5571539 | 5543998 | 918 | 0 | 0
UNIDO | China | Refrigeration servicing sector CFC phase-out plan | 2004-12-01 | 2013-04-01 |  | 3435000 | 3435000 | 3431991.59 | 3391 | 0 | 0
UNIDO | China | Tobacco Sector Plan | 2000-12-01 | 2007-12-01 |  | 11000000 | 11000000 | 11000000 | 1090 | 0 | 0
UNIDO | China | National phase-out of methyl bromide | 2003-12-01 |  | 2015-12-01 | 10789342 | 10789342 | 10311596.51 | 553.8 | 50 | 50 |  |  |  | - The National methyl bromide phase-out plan is ongoing since 2003. Out of nine tranches eight have been completed so far, currently the nineth tranche is under implementation. - The Government of China, the Government of Italy and UNIDO were requested to submit the project completion report to the Executive Committee to the first meeting in 2016. | Project implementation according to the time schedule. 8 model farms are set up in the ginger and yam sector for large scale commercial application of MB alternatives, including the use of new application equipment (for Dazomet and for chloropicrin). Continuous monitoring of MB alternatives applications in all sectors and the compilation of final report for all sectors are ongoing.
UNIDO | China | Sector plan for methyl bromide production sector | 2005-11-01 |  | 2015-12-01 | 9790000 | 9790000 | 7332736.62 |  |  |  | 621 | 50 | 50 | - The Sector plan for the methyl brpmode production sector is ongoing since 2005. The second and the third tranches have been completed so far, the first and the fourth tranches are currently under implementation. First tranche The project was reinstated by the ExCom to ONGOING in 2013 since there has been an going contract on technical assistance for which the final payment is scheduled in December 2015. Fourth tranche Approved on the understanding that the Government of China would continue to use existing balances to undertake activities for the phase-out of MB production, and that all project activities will be completed no later than 31 December 2018. The Government of China and UNIDO was requested to submit annual reports on the status of implementation the sector plan for the phase-out of MB production and the project completion report to the Executive Committee no later than the first meeting in 2019. | First tranche - Pending payment to be completed. - Project to be closed by the end of 2015. Fourth tranche Contract issued to FECO for the implementation of the tranche IV, contracts for three MB producers signed, subcontract for provision of technical assistance services under preparation.
UNIDO | Congo | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2020-12-01 | 175000 | 100000 | 98570.94 | 1.8 | 10.14 | 8.72 |  |  |  | - Ongoing HPMP with one tranche since 2011. - Activities completed. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Lack of agreement on how to use remaining funds under Tranche I; discussions in progress | The NOU and UNIDO are discussing activities to complete the first tranche of UNIDO's component and move into the second tranche.
UNIDO | Congo | Terminal phase-out management plan | 2008-04-01 | 2013-12-01 |  | 95000 | 95000 | 94627.37 | 3.4 | 0 | 0
UNIDO | Cote D'Ivoire | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 920000 | 460000 | 2145.09 | 11.2522 | 63.8 | not yet available |  |  |  | - Ongoing HPMP with one tranche since 2012. Milestones achieved: Interministerial Agreement signed: Yes Equipment needs assessment completed: Yes | The agreement between the Ministry of Environment and the Ministry of Vocational Training establishing a training centre as a beneficiary of the project has been signed. Activities planned but not implemented, reasons and strategy: Procurement of equipment delayed due to lengthy process for signature of interministerial agreement establishing beneficiary centre Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in signature of interministerial agreement establishing beneficiary centre. UNIDO to group equipment procurement.
UNIDO | Cote D'Ivoire | Terminal phase-out management plan | 2008-04-01 | 2014-03-01 |  | 283000 | 283000 | 271599.34 | 44.1 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Croatia | HCFC phase-out management plan (phase I) | 2010-07-01 |  | 2016-12-01 | 871150 | 871150 | 399939.6 | 6.4 | 4 | not yet available |  |  |  | - Ongoing HPMP since 2010 with four ongoing tranches, last approved at the 71st Meeting. First - fourth tranches - The Environmental Protection and Energy Efficiency Fund of the Republic of Croatia ("Fund") provided UNIDO the first and the second progress reports summarizing its activities in 2013-2014. - According to the Agreement concluded with the Environment Fund of Croatia, at least three sites are to be retrofitted to HFCs and at least seven sites are to be converted/replaced to low GWP alternatives in Croatia. - The implementation of the Agreement by the Fund progressed well. - Additional co-financing offered by the Fund. - The modification of AC units for the vocational schools got finalized and inspected by national expert in the beginning of April 2014. In the course of April the units have been distributed to the eight vocational schools of Croatia. - The training of vocational school teachers was organized in December 2014 with the involvement of the University of Zagreb, Faculty of Mechanical Engineering and Naval Architecture. - The training of customs officers and environmental inspectors took place the end of the year at various locations in the country with the active involvement of the national Customs Authorities. - On the request of the NOU the Croatian publication of two GIZ publications is arranged. | First, second and third tranches - Most of the project activities are completed. Pending obligations to be closed. - By 31 March 2015 the Fund successfully completed all the project activities as defined in the Agreement and the Terms of Reference. - With the retrofitting of five and the conversion/replacement of nine refrigeration units at eight beneficiaries in total, the project reached the phase-out of 1,222 kg of HCFC-22. - An auditing firm was contracted to verify the Fund's final report. - Final report audited, final payment transferred to the Fund in June 2015. - National expert finalizing a handbook for vocational school teachers. Material is based on the training provided in Dec 2014. - On the request of the NOU the Croatian publication of two GIZ publications is arranged. Fourth tranche - Remaining funds are committed for additional retrofiting under a second contract with the Fund on the request of the NOU. - As per the current plans, these retrofits will be completed by the end of 2015. Actions towards next goals: Fund to submit progress reports during 2015.
UNIDO | Croatia | Terminal phase-out management plan for CFCs | 2003-04-01 | 2008-12-01 |  | 287500 | 287500 | 284954 | 85 | 0 | 0
UNIDO | Ecuador | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 1846440 | 1618440 | 1510062.55 | 21.8 | 23.5 | 21.48 |  |  |  | - Ongoing HPMP since 2011 with additional investment compoenent in the foam manufacturing sector. Currently the second tranche of the HPMP and the investment component are under implementation. Second tranche Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Investment The commissioning and start up the production with cyclopentane took place in January 2014. Currently INDURAMA is producing 100% with cyclopentane, the HCFC-141b is phased out. The Safety Audit was supposed to take place in April 2014 by TÜV. In addition, the company started the process to phase out HFC-134a by using R-600a from their own funds. | Second tranche Due to the delay in the signature of the Agreement between NOU and UNEP, the training program for technicians was delayed. Since the Agreement was finally signed the trainers of SECAP required to be trained again. A new training of trainers program took place in May 2015 at the same time with some workshops for refrigeration technicians. - A pilot program for ODS phase out in Galapagos was launched. For the program, all the refrigeration technicians in the islands were trained and tools were provided for the training centre. - The promotion of HC as refrigerant will be implemented through a new unit designed for R-290 to replace a cool room in the flower sector. - A local expert in refrigeration was contracted to follow up the activities and received training to be able to replace the international expert. Investment The production with cyclopentane has not been interrupted since the equipment was commissioned. The TÜV audit was carried out and the pending issues were completed by the producer. - Project activities are completed and the project is operationally closed in March 2015.
UNIDO | Ecuador (3) | National CFC phase-out plan | 2010-07-01 | 2012-03-01 |  | 280000 | 280000 | 279904.69 | 42 | 0 | 0
UNIDO | Egypt | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 2325415 | 2092840 | 1548359.78 | 45.3 | 386.27 | 320.29 |  |  |  | - Ongoing HPMP with two tranches (enabling activities) in the refrigeration and air-conditining sector, one tranche in the manufacture of insulation foam and one further tranche for the coordination and management of the project implementation. In addition two investment projects in the manufacturing of polyurethane foam , approved earlier, also got integrated into the HPMP. Investment Milestones - Grant agreement submitted to beneficiary Y - Grant agreement signature Y - Bids prepared and requested Y - Contracts awarded Y - Equipment delivered Y - Commissioning and trial runs Y Manufacturing of insulation foam Milestones - Grant agreement submitted to beneficiary Y - Grant agreement signature Y - Bids prepared and requested Y - Contracts awarded Y - Equipment delivered Y - Commissioning and trial runs Y Refrigeration and air-conditioning sector - enabling activities - Contact with the newly established Ministry of Technical Education and Training is maintained. - Visits to training and servicing centers have been conducted for technical evaluation. - A coordination meeting will be held with the NOU once technical evaluation of the visited centers is completed to develop the structure of assistance to be provided. | Investment and Manufacturing of insulation foam Project to be completed by end 2015 Refrigeration and air-conditioning sector - enabling activities Technology providers contacted and agreements for the supply of refrigerants were made. - A national testing lab has been selected and an agreement between the lab and the NOU for work arrangement has been drafted. Coordination and management Funding under this component is reserved until installation activities under the FOAM components have been completed for verification proposes. Activities planned but not implemented, reasons and strategy: Verification delayed due to foam components not completed. To be conducted after the latter's completion
UNIDO | Egypt | National CFC phase-out plan | 2005-07-01 | 2013-12-01 |  | 3100000 | 3100000 | 3084600.32 | 537 | 0 | 0
UNIDO | Equatorial Guinea | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 150000 | 75000 | 72546.23 | 1.0476 | 6.29 | 4.95 |  |  |  | - First tranche of the HPMP was approved in 2011 and since then UNIDO completed its components. Training was provided on the use of the procured equipment and tools in June 2014, and equipment has been distributed to beneficiaries. Milestones achieved: Milestone 1: Yes - Equipment and tools delivered at beneficiaries | Next tranche is due in 2016.
UNIDO | Eritrea | HCFC phase-out management plan (phase I) | 2012-07-01 |  | 2020-12-01 | 80000 | 40000 | 19290.45 | 0.01459 | 1.1 | not yet available |  |  |  | - Ongoing HPMP with one tranche approved in 2012. Milestones achieved: Milestone 1: Mission to the country to start project activities. Yes Milestone 2: Purchase and delivery of tools. Yes Milestone 3: Training and certification of trainers. Yes | A joint mission with UNEP was planned originally, but it was not possibel for UNEP to join. UNIDO's mission was scheduled for mid-August 2015, but due to glight cancellation, it had to be rescheduled to September to plan the activities for the second tranche.
UNIDO | Eritrea | Terminal phase-out management plan for CFCs | 2008-04-01 | 2013-03-01 |  | 175000 | 175000 | 174472.34 | 4.2 | 0 | 0
UNIDO | Ethiopia | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2020-12-01 | 140000 | 70000 | 0 | 0.85333 | 5.5 | not yet available |  |  |  | - Ongoing HPMP with one tranche approved in 2012. Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes | UNIDO is ready to purchase relevant equipment and materials as soon as the overall set-up (e.g. identification of training partner, training scheme for technicians, training programme for the custom authorities, scheme of quality certification of imported refrigerants, etc.) is agreed by NOU and UNEP.
UNIDO | Gabon | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 249900 | 130000 | 77686.32 | 4.8 | 30.2 | not yet available |  |  |  | - Ongoing HPMP with one tranche approved in 2010. Milestones achieved: Procurement of initial equipment lot: Yes Procurement of additional equipment: No | - Agreement is being set up between the Ministries for the handover of equipment to the training center
UNIDO | Gambia | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 100000 | 50000 | 45344.14 | 0.3 | 1.5 | 0.77 |  |  |  | - Ongoing HPMP with one tranche approved in 2011. Milestones achieved: Milestone 1: Yes - Materials prepared for training on use of equipment. Activities planned but not implemented, reasons and strategy: Training session in 2014 did not take place due to difficulties convening all stakeholders. | One training session on the use of supplied equipment planned for the last quarter in 2015. Actions towards next goals: Planning will commence to hold the last activity for the investment component; training on use of equipment.
UNIDO | Guatemala | HCFC phase-out management plan (stage I, first tranche) | 2011-07-01 |  | 2020-12-01 | 345637 | 216012 | 202606.21 | 3.3615 | 8.3 | 4.26 |  |  |  | - Ongoing HPMP with two tranches since 2011 in the foam and refrigeration servicing sectors. Currently ongoing second tranche in the REF sector. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: TOR prepared and reviewed, bidding. Milestone 3: Purchase and delivery of tools for training centres. Yes Milestone 4: Study tour focused on hydrocarbon and natural refrigerants. Yes | Equipment for training centres including a refrigerant reclaiming unit was delivered and training of technicians through workshops was carried out. - A reclaiming centre will be established in one of the training centres. - The training program to be implemented by UNEP is delayed. - A study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico. - A national expert was hired to help with the implementation of the project activities.
UNIDO | Guatemala | National phase-out of methyl bromide (phase II) | 2009-11-01 |  | 2016-03-01 | 2243047 | 2243047 | 1325055 | 265.7 | 0 | 240 |  |  |  | - Phase II of the national methyl-bromide phase-out plan is ongoing since 2009. - The 71st Meeting of the ExCom decided to penalize Guatemala due to deviation in 2012 data, and possible deviations in 2013 and 2014, which have been reported by UNIDO. - Refund was reported to 72nd Meeting of the ExCom, May 2014. - Based on the new budget in March 2014, a new plan of activities was prepared. However, in the meantime, the Government has already put in place the law to forbid the importation of MB in 2015 and thus, guarantee the compliance of the country. | - The supplier of the grafting facilities has been selected through the bidding procedure. - A training programme for the dissemination of grafting techniques to farmers, University and Research Centers has been prepared. However, due to forthcoming elections in the country, the plan has been slowed down.
UNIDO | Guinea | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 320000 | 160000 | 153819.32 | 3.9122 | 22.6 | not yet available |  |  |  | - Ongoing HPMP with one tranche approved in 2012. Actions towards next goals: As soon as the Ebola outbreak is under control, UNIDO will be in a position to support the NOU in the completion of UNIDO's component of Tranche I HPMP. | The NOU and UNIDO are discussing the organization of a Customs training given the logistic challenges in the organization of the train-the-trainers sessions in Kindia province.
UNIDO | Guinea | Terminal phase-out management plan | 2008-07-01 | 2013-12-01 |  | 200000 | 200000 | 196414.63 | 2.9 | 0 | 0
UNIDO | Guinea-Bissau | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 115000 | 40000 | 39138.2 | 0.4 | 2.8 | not yet available |  |  |  | - Ongoing HPMP with one tranche approved in 2011. Activities planned but not implemented, reasons and strategy: Provision of training and distribution of equipment among beneficiaries delayed due to instability in the country. | The NOU and UNIDO could not agree on suitable dates for the provision of training on the use of the procured equipment and tools, after which these will be distributed to recipients. Reason for delay: instability in the country. Activities planned but not implemented, reasons and strategy: Provision of training and distribution of equipment among beneficiaries delayed due to instability in the country
UNIDO | Honduras | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2020-12-01 | 380000 | 190000 | 160026.28 | 4.2 | 19.91 | not yet available |  |  |  | - Ongoing HPMP with two tranches since 2011. Currently the second tranche is ongoing. - A study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico, the activity took place in September 2014. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: Study tour for local experts. Yes Milestone 5: Purchase of additional tools. Yes Milestone 6: Training of custom officers. Yes | Since only little funding left on the project, a few activities like the purchase of some spare parts and tools were implemented. - A training of custom officers was organized in March 2015.
UNIDO | Honduras | Terminal phase-out management plan (first tranche) | 2008-07-01 | 2010-12-01 |  | 338500 | 338500 | 337999.87 | 39.7 | 0 | 0
UNIDO | Honduras | National methyl bromide phase-out plan, phase II | 2006-11-01 | 2011-12-01 |  | 1806301 | 1806301 | 1806055.73 | 295.8 | 0 | not yet available
UNIDO | India | Plan for phase-out of CFCs in the refrigeration manufacturing sector | 2002-11-01 | 2007-03-01 |  | 673200 | 673200 | 673165 | 107 | 0 | 0
UNIDO | India | CTC phase-out for the consumption and production sectors | 2005-04-01 | 2013-12-01 |  | 3899046 | 3899046 | 3669114.26 | 1080 | 0 | 0 | 347
UNIDO | Indonesia | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2015-12-01 | 777395 | 777395 | 10559.22 | 8.3 | 403.9 | 257.98 |  |  |  | - Ongoing HPMP with one tranche, an umbrella project targeting the phase-out of HCFC-141b from the manufacturing of rigid polyurethane foam at companies. Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Partially Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No | The reason for low disbursement is that no payment for equipment could have been effected, since the equipment was not yet at the site, despite PO delivery term January 2015. - However equipment for two beneficiaries reached Indonesia; not yet cleared from customs due to lengthy procedures for tax exemption at the Government side. - Shipment for other two beneficiaries underway, to reach Indonesia by September 2015
UNIDO | Indonesia | Plan for terminal phase-out of ODS in the solvent sector | 2004-12-01 | 2008-10-01 |  | 1464733 | 1464733 | 1464063 | 100.1 | 0 | 0
UNIDO | Iran | National CFC phase-out plan | 2003-12-01 | 2008-04-01 |  | 3310758 | 3310758 | 3308263 | 619.6 | 0 | 0
UNIDO | Iran (Islamic Republic of) | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2015-12-01 | 2506277 | 2506277 | 1072739.38 | 41.2 | 380.5 | not yet available |  |  |  | - Ongoing HPMP since 2011 with currently three ongoing tranches in the foam sector. Last approval at the 72nd Meeting. Third tranche Approved at the 72nd Meeting of the ExCom in May 2014 with the understanding that the approved funds will not be transferred to UNDP and UNIDO until the Secretariat has received a verification report confirming that the Government of the Islamic Republic of Iran was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. Noted the change in the foam sector plan proposed by UNIDO and that the amount of US $97,127 associated to one non-eligible foam enterprise (Nobough) will be reallocated to the three new eligible enterprises manufacturing insulation foam for domestic refrigerators added to stage I, but its tonnage reduction (3.8 ODP tonnes) will continue to be deducted from the starting point; that the Government of the Islamic Republic of Iran commits to reduce its HCFC consumption by 30 per cent of the baseline by 1 January 2018; and that the Agreement was updated based on the revised sector plan submitted by UNIDO. Additional 63.1 ODP tonnes from the remaining eligible consumption would be deducted. | First tranche All equipment is delivered to all beneficiaries. Five machines installed and commissioned, two machines yet to be installed. The installation is expected to be completed by October 2015. Second tranche Equipment for Paya Telecommunication delivered, installed and commissioned, '- The procurement of equipment completed for Emersun, but waiting for Security Council Committee clearance since March 2015 to issue the purchase order Third tranche Verification report submitted and approved at the 73rd Meeting of the ExCom. '- Procurement of equipment completed. '- Part of the funds to be used for the company Emersun, waiting for Security Council Committee clearance for issuing the purchase order.
UNIDO | Iraq | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2015-12-01 | 410000 | 310000 | 0 | 6.6 | 108.4 | not yet available |  |  |  | - Ongoing HPMP with one tranche in the REF servicing sector since 2011. Awaiting Equipment to be shipped by Supplier. The planned completion date has been extended as per decision 73/8.
UNIDO | Iraq | National phase-out plan | 2009-07-01 |  | 2015-12-01 | 4656530 | 4656530 | 3106580.92 | 1640.8 | 0 | 0 |  |  |  | Ongoing national phase-out plan since 2009 with two tranches. Coordinating the Installation and commissioning for Light Industry, Nassr state Company and Al Hadi Company. 2. Equipment for Iraqi Steel to be shipped during the 2 quarter. The planned completion date has been extended as per decision 73/8.
UNIDO | Jordan | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2017-12-01 | 2259217 | 2237033 | 1511753.02 | 8.73 | 83 | not yet available |  |  |  | - Ongoing HPMP with one tranche since 2011 targeting policy support, awareness promotion and monitoring. In addition, an investment project approved in 2010 in the manufacturing of unitary air-conditioning equipment was also integrated in the HPMP. - The second tranche was submitted to the 73th Meeting of the ExCom, but was not approved due to the low implementation rate of the cooperating implementing agency, WB. - Verification report on the achievement of ODS reduction targets was prepared and submitted. | Second tranche A new submission has been prepared for the 75th Meeting of the ExCom, assuming that the cooperating agency has solved the problems of implementation. Investment - Equipment installed in March 2015. - Contract prepared and signed for final IOC payment.
UNIDO | Kenya | Technology transfer leading to methyl bromide phase-out in soil fumigation | 2007-11-01 | 2009-12-01 |  | 510659 | 510659 | 508770.66 | 53 | 0 | 0 |  |  |  |  | #NAME?
UNIDO | Korea, DPR | HCFC phase-out management plan (phase I) | 2014-11-01 |  | 2018-12-01 | 701880 | 123700 | 0 | 15.5537 | 80 | 79.37 |  |  |  | - Approved at the 73rd Meeting of the ExCom in November 2014 in accordance with the Agreement between the Government and the Executive Committee for the period 2014 to 2018 to reduce HCFC consumption by 15 per cent of the baseline. The commitment of the Government of the Democratic People’s Republic of Korea was secured to ban imports of HCFC-141b, both pure and contained in pre-blended polyols, no later than 1 January 2018. - UNIDO was further requested to report to the first meeting in 2015 on the results of the consultations with the UN Security Council Committee regarding equipment items considered unlikely to be prohibited by UN resolutions but for which additional information was collected by UNIDO to determine that with certainty. In the event that there are items not cleared by the UN Security Council Committee, UNIDO was requested to present an alternative action plan to address the associated HCFC consumption. UNIDO and UNEP were requested to follow an approach similar to that taken for the first tranche of the HPMP for the Democratic People’s Republic of Korea in terms of compliance with the resolutions of the UN Security Council, the modality of disbursement, organizational structures and monitoring procedures when submitting and implementing future tranches of the HPMP. - Currently two ongoing tranches in the REF servicing and monitoring and in the polyurethane foam sectors. | REF servicing and monitoring sector - Procurement of 3 units of advanced ODS identifiers started in January 2015. Offers from 4 qualified suppliers were received and Purchase Order (Contract) was issued in February 2015. The identifiers were delivered in April 2015. - Monitoring mission of the UNIDO Project Manager to discuss with local counterparts support for in-country activities was conducted on 22-26 June 2015. During the mission meetings with UN agencies such as WFP, UNICEF as well as bilateral development cooperation agencies (SDC, FBC, DEVCO) were conducted and alternative solutions to the funding of in-country activities were discussed and presented to UNEP after the mission. Milestones achieved: Milestone 1: Contract for ODS identifiers awarded - Yes Milestone 2: ODS identifiers delivered - Yes Milestone 3: Monitoring mission and discussion with local partners conducted - Yes Milestone 4: Modality of funding of in-country local activities agreed: Pending Polyurethane foam sector '- Procurement of spray foam equipment for the Puhung Building Materials Factory has been initiated in January 2015. Offers from two qualified suppliers were received and Purchase Order (Contract) for the selected supplier was issued in February 2015. The equipment was delivered in July 2015. - A letter from UNIDO to the UN Security Council Committee requesting confirmation that the foam equipment to be purchased under the HPMP investment component does not contravene the UNSC sanctions in respect to the DPRK was sent in February 2015. The confirmation from the UNSCC received in May 2015. - International foam expert from China was hired to prepare TOR for the equipment for conversion of the Sonbong PU Foam Factory to pentane. The expert visited the beneficiary company during the mission on 22-26 June 2015 and TOR is published in August 2015. Milestones achieved: Milestone 1: Contract award for spray foam equipment - Yes Milestone 2: Spray foam equipment delivery - Yes Milestone 3: Confirmation from UNSCC received - Yes Milestone 4: International foam expert recruited and visit of the factory performed - Yes Milestone 5: Technical specification for pentane equipment prepared - Yes
UNIDO | Korea, DPR | Implementation of the NPP: recovery and recycling | 2005-11-01 | 2010-12-01 |  | 536000 | 536000 | 528451.01 | 121.7 | 0 | 0
UNIDO | Korea, DPR | Plan for terminal phase-out of CTC | 2003-12-01 | 2010-12-01 |  | 5684844 | 5684840 | 5680503.55 | 1634.2 | 0 | 0
UNIDO | Korea, DPR | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company | 2003-07-01 | 2009-12-01 |  | 1365011 | 1365011 | 1364978 | 56 | 0 | 0
UNIDO | Korea, DPR | Closure of ODS production plant | 2002-03-01 | 2006-12-01 |  | 2566800 | 2566800 | 2566800 |  |  |  | 4280 | 0 | 0
UNIDO | Kuwait | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2018-12-01 | 8861677 | 6886832 | 234673.62 | 213.9398 | 418.6 | not yet available |  |  |  | - Ongoing HPMP with tranches in the REF servicing and in the polyurethane and the extruded polystyrene foam sectors since 2012. Refrigeration servicing and technical assistance in the foam sector - In line with our report submitted to the 71st Mtg of the ExCom, the Secretariat has made the inventory modifications and the project budget has been reduced to USD 12,000 and USD 15,000 respectively. 2. Expert has been identified and recruitment will proceed. Extruded polystyrene foam Similarly to KUW/PHA/66/INV/18 and KUW/PHA/66/INV/20 , the Secretariat has made the inventory modifications for this project as well and the project budget has been increased to USD 3,510,450. First stage will focus on the Gulf Insulation and Isofoam. 2. Meeting with Gulf Insulation and Isofoam as well as the NOU has taken place. 3. Tendering equipment will start in April and is expected to be concluded end May | Refrigeration servicing and technical assistance in the foam sector Coordination meeting was organized in Kuwait during the third week of February to discuss reports outcome, and to develop follow up actions. Extruded polystyrene foam Contract has been awarded for the investment project covering Gulf and Isofoam. Equipment is expected to be shipped and installation work is scheduled within 2015. 2. Contract awarded and financed by both UNIDO projects as well as co-financed by the owners of Gulf and Isofoam. Final disbursement will be made once the goods have been cleared from customs, in accordance with the contract between UNIDO and the supplier. Over 90% of the tranche are committed.
UNIDO | Kuwait | Terminal phase-out management plan for Annex A Group I substances | 2007-07-01 | 2010-11-01 |  | 230000 | 220000 | 219472.94 | 70 | 0 | 0
UNIDO | Lebanon | Phase-out of methyl bromide for soil fumigation in strawberry production | 2001-07-01 | 2009-12-01 |  | 1264450 | 1264450 | 1244911.54 | 50.4 | 0 | 0
UNIDO | Libya | National phase-out plan | 2003-12-01 | 2013-12-01 |  | 2497947 | 2497947 | 2474009.97 | 450.5 | 0 | 0
UNIDO | Libya | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others. | 2005-11-01 | 2010-12-01 |  | 743000 | 743000 | 743000.05 | 56 | 0 | 0
UNIDO | Macedonia, FYR | HCFC phase-out management plan (phase I) | 2010-04-01 |  | 2020-12-01 | 1166955 | 646955 | 527587.33 | 2.2 | 1.8 | 0.57 |  |  |  | - Ongoing HPMP with five tranches and additional investment component in the polyurethane foam sector since 2010. Out of the five tranches currently two are ongoing: the fourth and the fifth. Fourth tranche Milestones achieved: Milestone 1: Completion of training activities on logbooks and e-reporting - Yes Milestone 2: Completion of tranche IV implementation - Yes Fifth tranche Milestones achieved: Milestone 1: Equipment delivery and commissioning at Zlatna Raka Co. - Yes Milestone 2: Training activities completed - Yes Milestone 3: Consumption verification report contracted - Yes | Fourth tranche Completion of training activities on logbooks and e-reporting. - Completion of tranche 4 implementation and progress report. Fifth tranche Conversion of foam Company Zlatna Raka was finalized (equipment purchase and delivery has been achieved). - Training activities as per the tranche 5 work plan are schedule and under implementation.
UNIDO | Macedonia, FYR | Terminal phase-out management plan for CFCs | 2005-04-01 | 2013-01-01 |  | 279081 | 279081 | 277849.67 | 49.34 | 0 | 0
UNIDO | Madagascar | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 260000 | 140000 | 122003.24 | 2.8 | 24.9 | not yet available |  |  |  | - Ongoing HPMP with one tranche since 2010. - Training for the fisheries sector carried out in 2014. - Outstanding equipment delivery to Tamawate and Tulear completed in the 3rd quarter 2014. Milestones achieved: Milestone 1: Yes - 24 technicians from the fisheries sector trained on alternatives to HCFCs. Milestone 2: Yes - All equipment delivered to Tamatave and Tulear | - Remaining balance will be used towards training on reclamation and incentives for reclamation. - Project needs to be extended until the new tranche is approved, so that the remaining funding can be properly utilized.
UNIDO | Madagascar | Terminal phase-out management plan (first tranche) | 2007-07-01 | 2009-12-01 |  | 125000 | 125000 | 122513.18 | 2.3 | 0 | 0
UNIDO | Malawi | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 120000 | 60000 | 58750.33 | 1.3 | 10.8 | 9.35 |  |  |  | Tranche completed in May 2013.
UNIDO | Mexico | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2018-12-01 | 4412195 | 4185878 | 1995591.02 | 101.3 | 1148.8 | 720.28 |  |  |  | - Ongoing HPMP with four tranches since 2011 covering an umbrella project for conversion from HCFC-141b to cyclopentane insulation foam blowing technology at three refrigeration appliances manufacturing enterprises, the phase-out of HCFC-141b as a cleaning agent in refrigeration servicing sector, and legislation customs training and monitoring. The second and third tranches target the REF servicing sector and provide TAS. - Among the above tranches the umbrella project and the second, third and fourth tranches are ongoing. Umbrella project Milestones achieved: Conversion completed at Metalfrio: Yes, December 2014; TUV certificate issued for Metalfrio: No; Bidding completed for Fersa: Yes, December 2013; Contract signed for Fersa: Yes, July 2015; Bidding completed for Ojeda: Yes, December 2013; Contract signed for Ojeda: Yes, February 2015; Equipment delivered and installed for Fersa: No; Equipment delivered and installed for Ojeda: No; Commissioning and trial runs completed at Fersa: No; Commissioning and trial runs completed at Ojeda: No; TUV certificate issued for Fersa: No; TUV certificate issued for Ojeda: No; Second tranche Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Training equipment purchased and delivered: Yes, in January 2014 Flushing units replaced: No Training of trainers completed: No Third tranche Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes TOR for equipment purchase agreed: Yes, July 2015 Equipment and tools delivered: No Large scale training completed: Yes | Umbrella project UNIDO managed to convince the supplier to initiate TUV certification at Metalfrio. The supplier fielded a mission to Metalfrio to provide clear guidance to Metalfrio on the required modifications so to get TUV approval. TUV mission is planned for the first week of September 2015. - Contract with Ojeda/Frigopanel was signed and the supplier has arranged for a mission to start the contract. For Fersa, finally the contract details have been agreed upon with counterpart co-financing and UNIDO submitted the contract for signature by the beneficiary in June. UNIDO received the countersigned contract mid July 2015. Refrigeration servicing Trainings at 12 training centers (6 trainings each) are ongoing and half of them have been successfully completed. Flushing units with over-heat problems were shipped to the supplier and finally a new supplier of the motors was identified to avoid the over-heat. In parallel, new flushing units were purchased and tested locally. New motors will be shipped end August. - TOR for equipment and tools to be purchased have been agreed upon in July 2015.
UNIDO | Mexico | HCFC phase-out management plan (phase II) | 2014-11-01 |  | 2022-12-01 | 9899581 | 2404412 | 0 | 476.4182 | 0 | 0 |  |  |  | - As first Stage II HPMPs, the first tranche was approved with two components, in the REF servicing and in the solvent sectors, at the 73rd Meeting in November 2014. REF servicing Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: No Stakeholder consultation organized: No Milestones defined: No Solvents Milestones achieved: PAD issued: Yes Work Plan agreed with NOU: No. | REF servicing This component of the Stage II HPMP was somewhat delayed during 2015, since service sector activities were running in parallel under Stage I and there was a need for a local stakeholder consultation for the implementation of the Stage II strategy, before activities could kick off. Actions towards next goals: Agreement on work plan and agree on milestones. Solvents Work plan was agreed with the NOU and a technical expert was recruited to verify the production lines and latest consumption at each beneficiary enterprise and to review their action plan. Actions towards next goals: Lab tests for the alternatives will be undertaken and contracts for IOC payments will be prepared and payments will be released based on performance.
UNIDO | Mexico | National CFC phase-out plan | 2004-04-01 | 2011-12-01 |  | 8294500 | 8294500 | 8087027.09 | 1535 | 0 | 0
UNIDO | Mexico | Sector plan for phasing out CFC-11 and CFC-12 production sector | 2003-07-01 | 2009-12-01 |  | 31850000 | 31850000 | 31849298.21 |  |  |  | 12355 | 0 | 0
UNIDO | Mexico | National methyl bromide phase-out plan | 2008-04-01 |  | 2015-12-01 | 6122379 | 6122379 | 6056372.22 | 715 | 0 | not yet available |  |  |  | - The National methyl bromide phase-out is ongoing since 2008 and it covers four tranches, out of which the third and the fourth are still ongoing. Furthermore, an additional tranche was transferred to UNIDO from Canada in 2011. - Final greenhouse installation and training activities were carried out in 2014. '- A successful workshop was organized in Monterrey with the new equipment. | - Publications and videos have been prepared. - The project is near to completion. - A final official event will be organized with the Mexican Authorities during the second semester of 2015.
UNIDO | Montenegro | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2020-12-01 | 404500 | 255000 | 202882.43 | 0.3 | 0.8 | 0.72 |  |  |  | - Ongoing HPMP with two tranches since 2011. - The activities of the first tranche have been completed, currently the second tranche is under implementation. Second tranche Milestone 1: Equipment delivered - No Milestone 2: Training conducted - No Milestone 3: Tranche request prepared - Yes | The equipment will arrive in September 2015. Training will be organized after the summer season. Was there any delay during the reporting year? Yes Reason: The HPMP budget was reduced. Therefore it was necessary to revise the planned activities in order to meet the available budget the HPMP objectives. Additional consultation were required.
UNIDO | Montenegro | Terminal phase-out management plan | 2007-11-01 | 2013-12-01 |  | 270295 | 270295 | 268411.54 | 5.15 | 0 | 0
UNIDO | Morocco | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2017-12-01 | 1286740 | 1251740 | 973338.48 | 16.77 | 59.67 | 49.1 |  |  |  | - Ongoing HPMP since 2011 currently with two ongoing tranches in the REF servicing sector. Furthermore, an investment project, approved earlier, Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators, also got integrated in the HPMP. - The investment project has been completed. First and second tranches Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No | First and second tranches UNIDO agreed with the NOU on JD for international expert. International expert was recruited but contract cancelled because of lack of response from custom authorities and ONCF (beneficiary). NOU tried to facilitate the communication flow and a new set of training is set for October. - UNIDO has launched the bidding for the audit of the HCFC consumption for the year 2013 and 2014. Actions towards next goals: Execute the training to custom authorities; audit the HCFC consumption figures; finalize the technical specifications for the conversion of ONCF (flushing) and purchase the necessary equipment.
UNIDO | Morocco | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits | 2008-11-01 | 2014-12-01 |  | 1127594 | 1127594 | 1121953.09 | 106.2 | 0 | not yet available |  |  |  | The project was successfully completed.
UNIDO | Morocco | Phase-out of methyl bromide for soil fumigation in tomato production | 2001-07-01 | 2011-12-01 |  | 3912949 | 3912949 | 3901323.51 | 389.9 | 0 | 0
UNIDO | Mozambique | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 150000 | 75000 | 1826.41 | 1.081 | 6.5 | not yet available |  |  |  | -Ongoing HPMP since 2012 with one tranche. A mission took place in August 2014.
UNIDO | Myanmar | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2020-12-01 | 60000 | 0 | 0 | 0.32143 | 4.3 | not yet available |  |  |  | The funds will be released.
UNIDO | Nicaragua | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 222000 | 146500 | 88209.83 | 1.7962 | 6.8 | 5.4 |  |  |  | -Ongoing HPMP since 2012 with one tranche. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres. Yes Milestone 3: Training of trainers and workshops for technicians. Yes Milestone 4: National experts to help during the implementation of the project and capacity build. Yes Milestone 5: Creation of code of conduct and certification system. Yes | Since the funds are almost exhausted few activities have taken place in the project during 2015. - The certification program is established and a study tour was organized for two trainers, for this purpose 3 factories and a recycling centre were visited in Mexico.
UNIDO | Niger | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2020-12-01 | 285000 | 175000 | 26677.75 | 2.8449 | 16 | 14.32 |  |  |  | -Ongoing HPMP since 2012 with one tranche. Milestones achieved: Milestone 1: Contract award for equipment purchase - No Milestone 2: Equipment delivery - No Milestone 3: Completion of training activities - Yes | ToR for the bidding and bidding for equipment purchase carried out in 2015. - Award of the contract and equipment delivery to take place during the second half of 2015. Actions towards next goals: Local consultancy selection for elaboration of data verification report to be initiated second half of 2015.
UNIDO | Niger | Terminal phase-out management plan | 2008-04-01 | 2012-02-01 |  | 184000 | 184000 | 183798 | 4.8 | 0 | 0
UNIDO | Nigeria | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2015-12-01 | 1939080 | 1745172 | 98879.98 | 35.4 | 398.2 | not yet available |  |  |  | -Ongoing HPMP since 2010 with three tranches in the refrigeration air-conditioning manufacturing sector. - The activities of the first tranche have been completed, the second and the third tranches are currently under implementation. Milestones achieved: Second tranche 30 Foaming machines were distributed to beneficiaries in October 2014 - Y 1st batch of 16 foaming machines installed at various companies in Ibadan. Third tranche A contract was awarded for supply of 45 foaming machines in Nov 2014 -Y Equipment shipped - no | Equipment shipped in July 2015 - Yes Installation and training on use of equipment to be carried out in 2015.
UNIDO | Nigeria | National CFC phase-out plan | 2002-11-01 | 2008-03-01 |  | 937386 | 937386 | 937384 | 100.9 | 0 | 0
UNIDO | Nigeria | Terminal ODS phase out umbrella project in the solvent sector | 2004-07-01 | 2012-11-01 |  | 1575200 | 1575200 | 1560812.69 | 198 | 0 | 0
UNIDO | Oman | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2015-12-01 | 349120 | 349120 | 153302.51 | 5.5 | 31.47 | 20.37 |  |  |  | -Ongoing HPMP since 2011 with two tranches, one in the refrigeration servicing sector and one TAS in the foam sector. The latter one has been completed, thus currently there is one tranche under implementation. - Installation and training on the use of the reclamation equipment and visit to international reclamation centre during the 2nd quarter of 2014. Milestones achieved: Milestone 1: Yes 1st workshop for fisheries sector held in June 2014 Milestone 2: Yes - 2nd workshop for decision makers in fisheries sector held in November 2014 | - Due to low funds in 1st tranche, visit to international reclamation centre to be done with 2nd tranche funds in 2015.
UNIDO | Oman | Terminal phase-out management plan | 2007-07-01 | 2011-12-01 |  | 470000 | 470000 | 432703.5 | 35 | 0 | 0
UNIDO | Pakistan | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2015-12-01 | 5008849 | 5008849 | 4718142.3 | 73.7 | 247.4 | 239.79 |  |  |  | - Ongoing HPMP since 2010 with three tranches, the latest one approved in 2014 at the 73rd Meeting. First tranche has been completed. - An investment project in the manufacturing of insulation PU rigid foam, approved earlier, has been integrated in the HPMP. Refrigeration sector Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Foam investment Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - Yes | Refrigeration sector - UNIDO works jointly with UNEP as co-implementing agency, to support non-investment activities developed by UNEP. - Contribution to public awareness campaign and conference on Environment organized by Lahore University of Management Science supported by NOU. - Project stagnant as the National Ozone Officer resigned and new one has not yet been selected. - UNEP Small Scale Funding Agreement has also been signed only in 2015. Pakistan however successfully controlled import of ODS through strong monitoring system. - Project activities are expected to be completed by end 2015. Foam Investment - Certifications are being finalized at DPL2 plant. - Non-standard findings after certification to be amended. - Project is completed.
UNIDO | Pakistan | Sector phase-out plan of CTC | 2003-12-01 | 2009-12-01 |  | 2745665 | 2745665 | 2742073.25 | 489 | 0 | 0
UNIDO | Pakistan | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) | 2003-12-01 | 2008-09-01 |  | 1139500 | 1139500 | 1134941.64 | 215 | 0 | 0 |  |  |  |  | - Residual funds to be used together with 2nd tranche.
UNIDO | Peru | Terminal phase-out management plan for Annex A Group I substances (first tranche) | 2008-07-01 | 2014-04-01 |  | 183500 | 183500 | 171084.33 | 15 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Philipinnes | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2015-12-01 | 1770650 | 1770650 | 1484474.15 | 40 | 208.4 | 149.42 |  |  |  | - Since 2010 UNIDO is responsible for the Sector plan to phase out HCFC-141b in the foam sector in the context of the HPMP of the country. 10 companies with fixed foaming equipment received assistance to convert their technologies. - Installation was finalized at 8 beneficiaries. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes (partially) Milestone 5: Equipment delivered - Yes (partially) Milestone 6: Commissioning and trial runs - Yes (partially) | 1 additional company with fixed foaming equipment finalized installation, while equipment to the last beneficiary (Blutherm) was confiscated and sold back to technology provider. The money recovered will be transferred back to the MLF at project closure. - On spray foam sector, UNIDO started procuring agreed items to finalize the assistance to eligible 8 eligible beneficiaries. - UNIDO certified the destruction of baseline equipment in July 2015. - The technical brochure resulted from the tests in the spray foam activities was published and launched (copy is available for the MLF, if required so).
UNIDO | Qatar | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2017-12-01 | 1726600 | 1045907 | 130583.52 | 49.0529 | 86.9 | not yet available |  |  |  | - HPMP ongoing in the REF servicing sector and in the production of extruded polystyrene insulation boards since 2011. REF servicing Expert has been identified and recruitment will proceed. 2. Activity to be completed and reported to the NOU by the 4th quarter in 2014. Production of extruded polystyrene - Equipment is due to be delivered in the 3rd quarter of 2014. - Installation and commission will follow. | UNIDO and UNEP have prepared the second tranche submission since the 73rd ExCom Meeting. Unfortunately, obtaining governmental endorsement has not happened. For this reason, completion of Stage I before Dec 2017 is unlikely.
UNIDO | Qatar | Terminal phase-out management plan | 2007-11-01 | 2013-12-01 |  | 312500 | 312500 | 308904.06 | 15 | 0 | 0
UNIDO | Romania | National CFC phase-out plan | 2005-04-01 | 2010-12-01 |  | 509019 | 509019 | 508120.85 | 99.3 | 0 | 0
UNIDO | Romania | Sector plan for production sector | 2005-11-01 | 2010-12-01 |  | 6300000 | 6300000 | 6258378.07 |  |  |  | 175 | 0 | 0
UNIDO | Rwanda | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2020-12-01 | 110000 | 55000 | 51620.53 | 0.55 | 4.1 | not yet available |  |  |  | - Ongoing HPMP since 2011 with one tranche. Milestones achieved: Milestone 1: Yes - Equipment retrieved from Customs warehouse Milestone 2: Yes - Equipment delivered to beneficiaries. | There were problems encountered with clearing the equipment at the ports. They were moved to customs warehouses and a lengthy procedure ensued to release them. - The clearing agent has now retrieved the equipment with the customs, and equipment have been delivered to beneficiaries.
UNIDO | Saint Lucia | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2020-12-01 | 112608 | 99850 | 90235.69 | 0.1 | 1.1 | 0.83 |  |  |  | - Ongoing HPMP since 2011. The first tranche has been completed, the second tranche is under implementation. UNIDO was prepared for the submission of the next tranche to the 74th Meeting of the ExCom, but was informed by UNEP, that UNEP as lead agency and the Government of St. Lucia agreed to delay the submission to the 75th Meeting of the ExCom. | The training of trainers and technicians is targeted. A first attempt was made with Centro Galileo but the funds available were not enough to cover the activity. - A second option proposed by UNIDO is being evaluated. - It is expected to carry out the training before the end of 2015.
UNIDO | Saint Vincent and the Grenadines | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2025-12-01 | 124115 | 124115 | 105572.32 | 0.073954 | 0.25 | 0.09 |  |  |  | - Ongoing HPMP since 2011. with one tranche under implementation. Milestones achieved: Milestone: Yes - TOR was agreed with NOO. Milestone: Yes - Residual funds were used to procure additional service tools and equipment. Milestone: Yes - Equipment were delivered in March 2015 | - The final activity was concluded in the 1st quarter of 2015. - The tranche will be closed after distribution of equipment ends, expectedly by the end of 2015.
UNIDO | Sao Tome and Principe | Terminal phase-out management plan for CFCs | 2008-04-01 | 2011-12-01 |  | 115000 | 115000 | 114279.27 | 0.7 | 0 | 0
UNIDO | Saudi Arabia | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2020-12-01 | 12480171 | 6852175 | 1809951.12 | 663.4 | 1468.69 | 1441.53 |  |  |  | - Ongoing HPMP with two-two tranches in the REF servicing and in the PU foam sectors. Furthermore, two investment projects targeting the manufacturing of extruded polystyrene, approved earlier, have also been integrated to the HPMP. Milestones achieved: Investment #1 Milestone: Equipment delivery to the beneficiary - Yes Milestone: Installation, start-up and commissioning - No Milestone: Verification visit of the Project Manager on the full operation of the new line - No As reported earlier, funds reallocated from the NPP to HPMP were partially used to cover the costs of this project in order to fulfil ExCom requirements to financially close the NPP, since the certification and code of practice conducted by UNEP was delayed. Remaining funds under this tranche will be used for the purpose approved for it by the ExCom when reallocation of funds was decided. Investment #2 Milestone: Invitation to bidding published - Yes Milestone: Bids from qualified suppliers received - Yes Milestone: Technical and financial evaluation completed - Yes Milestone: Contract issued - Yes Milestone: Technical meeting organized - Yes Milestone: Customs clearance of the equipment arranged - No Milestone: Equipment delivered at the project site - No Milestone: Equipment installed and commissioned - No REF servicing - First and second tranches Milestone: Training programme for service technicians developed - Yes Milestone: Pilot training workshop of trainers implemented - No Milestone: Pilot training workshop organized on 24-27 August 2015 - Yes Milestone: Follow-up workshops organized - No PU foam - First and second tranches Milestone: Delivery of equipment to KSA - Yes Milestone: Customs clearance of PU foam equipment - Yes Milestone: Delivery to the beneficiaries - Yes Milestone: Installation, commissioning, start-up - No Milestone: Follow up workshop for SHs - Yes Milestone: Expert mission to finalize the Technical Specification for SH - Yes Milestone: Invitation to bidding for equipment for SH - Yes Milestone: Contract issued for selected supplier for SH equipment - Yes Milestone: Shipment to the first beneficiary (Alamut/ALBA) - Yes Milestone: Shipment to the other 2 beneficiaries - NoNo | Investment #1 Installation, start-up and commissioning was completed in March 2015 and confirmed by the Certificate of Acceptance. - The final payment for the equipment was disbursed. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. Investment #2 The contract to the selected supplier was issued in February 2015. - Technical meeting at Al-Watania was organized in June 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. REF servicing - First and second tranches Progress of work depending on progress of UNEP implemented component, namely on the Update of Code of Practice on RAC, Finalization of the certification scheme for RAC service workshops that were finalized only in 1st half of 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. PU foam - First and second tranches - Despite the Letter from the MFA requesting the customs to clear the equipment the latter refused to do so. - Protracted negotiations with the customs and the beneficiary companies led to an agreement that the beneficiaries will pay the due customs tax. - The NOU sent a request for a waiver of the port detention fees but after protracted proceedings this was rejected by the Saudi Customs. - Finally decision was taken to pay all due charges to get the equipment released from the customs. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP. - International foam expert visited the System House ready for conversion in April 2015 and finalized the Technical Specification for the equipment. - Invitation to bidding for one System House was published in May 2015 and a contract to the selected supplier was awarded in August 2015. - Mission to the country in the beginning of August to coordinate with the NOU and UNEP.
UNIDO | Saudi Arabia | National phase-out plan | 2007-11-01 | 2013-12-01 |  | 1430000 | 1430000 | 1394536.1 | 782 | 0 | 0
UNIDO | Senegal | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 505216 | 200000 | 103022.08 | 6.1736 | 36.15 | not yet available |  |  |  | - Ongoing HPMP since 2011 with one tranche. Milestones achieved: Milestone: Train the trainer component for servicing sector - Yes Milestone: Training of technicians - Yes Milestone: Equipment specification in view of equipment purchase - Yes Milestone: Verification report elaboration - Yes Milestone: Submission of tranche 2 to the 74th Meeting of the ExCom - N Activities planned but not implemented, reasons and strategy: Tranche 2 approval was withdrawn from 74th ExCom's agenda due to discrepancies in the HCFCs consumption data in the 2013 year. Actions towards next goals: NOU committed additional data verifications and review of the Consumption Verification Report for the years 2013 and 2014. | - Tranche 1 activities are implemented. - Initiation of the implementation of the activities under tranche 2 are pending on the approval of the second tranche of the HPMP.
UNIDO | Serbia | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 897760 | 804260 | 158291.54 | 2.65 | 8.4 | 8.03 |  |  |  | HPMP approved at the 62nd Meeting in 2010. Currently the first and the second tranches are under implementation. First tranche Milestones achieved: Milestone: Conversion of 2 companies (commercial refrigeration sector) - Yes Milestone: Train the trainer component completed - Yes Milestone: Development of agreements with vocational schools for implementation of the certification scheme - Yes Milestone: Signature of Agreements with vocational schools for technicians training and certification - Yes Milestone: Completion of the activities under tranche 1 - No Second tranche Milestones achieved: Milestone: Technical specifications developed for conversion of 2 remaining enterprises - Yes Milestone: Work plan for the certification training programme - Yes Milestone: Initiation of training and certification programme for technicians - Yes Milestone: Equipment delivery for commercial enterprises - No | First tranche Remaining balance is to be used for the implementation of the training programmes that are continuing under tranche 2. Second tranche - Administrative changes took place at the level of Ministry of Environment in Serbia. - New Ozone Officer was appointed in May 2015. - Arrangements for the implementation of the technicians training programme (occuring under NOU supervision)is delayed with 5 months, however, new workplan and related preparatory work are to be agreed upon with the new Ozone Officer in July 2015, upon scheduling a UNIDO mission to the field. - It is expected that the training programme to be implemented during 2015 without further major delays. - Delivery of equipment for the remaining 2 enterprises in commercial sector is scheduled for the second half of 2015.
UNIDO | Serbia | National CFC phase-out plan | 2004-07-01 | 2014-06-01 |  | 2723222 | 2723222 | 1894949.09 | 327 | 0 | 0 |  |  |  | The project was successfully completed.
UNIDO | Sierra Leone | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 100000 | 50000 | 47620 | 0.27619 | 1.67 | not yet available |  |  |  | - Ongoing HPMP with one tranche since 2011. - In 2014 activities were suspended due to the Ebola outbreak. | - Training on use of equipment will continue in 2015 with residual funds. - Planned completion date o fthe tranche is December 2015.
UNIDO | Somalia | HCFC phase-out management plan (phase I) | 2012-07-01 |  | 2020-12-01 | 315000 | 173874 | 82415.6 | 1.85 | 45.1 | not yet available |  |  |  | - Ongoing HPMP with one tranche in the REF servicing and with an additional security allowance since 2012. Milestones achieved: Milestone 1: ToR for the training prepared - Yes Milestone 2: Bidding conducted - Yes Milestone 3: Contract awarded - No | Due to the visa difficulties it was not possible to organize the training at the training facilities of the equipment supplier. Supply of the training equipment to neighboring countries is difficult and expensive. Moreover air tickets costs and visa problems would still remain problems. UNIDO is investigating the possibilities to conduct the training in the Seychelles or in Djibouti like the trainings organized by other UN organizations (like FAO).
UNIDO | South Africa | HCFC phase-out management plan (phase I) | 2012-07-01 |  | 2020-12-01 | 6533556 | 4552849 | 1776654.68 | 176.72 | 369.7 | not yet available |  |  |  | - Ongoing HPMP with two-two tranches in the REF servicing and in the PU foam sectors since 2012. REF servicing - First and second tranche Milestones achieved: Milestone 1: Stakeholders workshop conducted Yes Milestone 2: Awareness material No Milestone 3: Revision of the BL data by the Government No PU foam - First tranche Milestones achieved: Milestone 1: Equipment for the completed biddings delivered - Yes Milestone 2: Contractions and civil works completed - No Milestone 3: New contract for remaining enterprises/ ToR prepared- No Milestone 4: New biddings conducted - No PU foam - Second tranche Milestone 1: Procurement of equipment -Yes Milestone 2: Extension of contract of national expert - Yes Milestone 3: Preparation of the ToR /agreements for other SMEs in foams - No | REF servicing - Experts recruited. - Additional training of customs officers is planned for 2nd half of 2015. PU foam - First and second tranche Activities planned but not implemented, reasons and strategy: Conversion of System Houses to MF technology. The MF technology needs adoption at the end-user level. This is connected to additional cost and time. Without qualified support the new technology is not competitive on the market.
UNIDO | Sudan | HCFC phase-out management plan (stage I) | 2012-04-01 |  | 2017-12-01 | 1456341 | 1416341 | 1262119.8 | 16.15 | 52.7 | not yet available |  |  |  | - Ongoing HPMP since 2012 with two open tranches in the REF servicing sector. Furthermore an investment project approved earlier, umbrella project for the phase-out of HCFC-141b from the polyurethane rigid foam production, also got integrated in the HPMP. REF servicing Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - No Umbrella project Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - No Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No | REF servicing - Assistance with monitoring and public awareness has been provided to the NOU. - Technical assistance to customs office has been also provided to launch electronic system for licensing and quota. - Training of trainers for participants from Technical University in Khartoum, Association of Refrigeration & Air-conditioning Engineers, Ministry of Industry an Institute for Refrigeration and Air- conditioning Research, took place in Germany. The training was organized in collaboration with GIZ and focused on new systems using natural refrigerants. - Project activities are planned to be completed by the end of 2015. Umbrella project The project was stagnant since; a) counterparts have been still utilizing allowed import quota and eventually also their (quite large) stocks, b) Installation and commissioning of equipment missed two seasonal terms (relatively lower activity autumn and winter time), due to; 1. lack of agreement/understanding of counterparts with the supplier of equipment on the payment of their cost sharing for commissioning, training, start-up, 2. supplier's lack of planning for Sudan and also due to over estimated security concerns. Actions towards next goals: Close coordination towards soonest possible installation and utilization of equipment.
UNIDO | Sudan | National CFC/CTC phase-out plan | 2004-12-01 | 2012-03-01 |  | 1139480 | 1139480 | 1137858.39 | 217.4 | 0 | 0
UNIDO | Suriname | HCFC phase-out management plan (stage I) | 2011-11-01 |  | 2020-12-01 | 106000 | 68000 | 57178.4 | 0.34829 | 1.98 | not yet available |  |  |  | - Ongoing HPMP with one tranche since 2011. - Training on use of equipment will continue. | The needs of the service sector will be reassessed together with the National Ozone Officer Actions towards next goals: Re-assess needs of service sector and combine funds with 2nd tranche to make interventions more effective.
UNIDO | Syria | National CFC phase-out plan for Syria | 2006-07-01 | 2013-12-01 |  | 754050 | 754050 | 623302.79 | 498.65 | 0 | 0
UNIDO | Syria | Phase-out of the use of methyl bromide in grain storage | 2001-07-01 | 2011-12-01 |  | 1084139 | 1084139 | 1076060.91 | 105 | 0 | 0
UNIDO | Tanzania | HCFC phase-out management plan (phase I) | 2012-07-01 |  | 2020-12-01 | 100000 | 50000 | 49935.69 | 0.28095 | 1.7 | not yet available |  |  |  | - HPMP approved in 2012. - First tranche has been completed. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: TOR prepared and reviewed, bidding. Milestone 3: Purchase and delivery of tools for training centres. Yes | - Tranche got completed.
UNIDO | Togo | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 350000 | 200000 | 138624.54 | 3.85 | 20 | 17.88 |  |  |  | - Ongoing HPMP with one tranche since 2010. Milestones achieved: Milestone: Yes - Training on installation and maintenance of Hydrocarbon ACs was held in Oct 2014 Milestone: Yes - Survey of industrial and large commercial facilities held June-July 2015 | The last activity involves identifying beneficiaries for an incentive programme to convert to low GWP alternatives. - Funds from the 2nd tranche would have to be combined with residual funds from 1st tranche for actual conversion, depending on results of the survey and assessment.
UNIDO | Tunisia | HCFC phase-out management plan (stage I) | 2014-05-01 |  | 2018-12-01 | 1100195 | 512885 | 1996.5 | 6.4782 | 40.7 | not yet available |  |  |  | - HPMP approved at the 72nd Meeting in 2014 with tranches in the REF servicing, solvent and in the residential air-conditioning manufacturing sectors. REF servicing Milestone 1: Yes - updated curricula of training in vocational schools Milestone 2: Yes - needs assessment related to equipment and tools for these schools to support HPMP implementation undertaken Milestone 3: Yes - initial stage of implementation of a certification programmed for servicing technicians and workshops Solvent Milestone 1: Yes - SOFAP, laboratory testing yielded results on one alternative Milestone 2: Yes - SNCFT, technical specifications of flushing units completed Residential air-conditioning manufacturing Milestone: Participation of representatives of participating companies in training sessions on low-GWP alternatives. | REF servicing Under this project component, a review of the curricula of training in vocational schools has been made, as well as a needs assessment related to equipment and tools for these schools to support HPMP implementation. Solvent - SOFAP: laboratory testing stage started, and results are available for one of the two tested alternatives; a manufacturer informed UNIDO that a third substance (HFO-based solution) is available for testing. - SNCFT: site visit with experts to define technical specifications of flushing units required to use the selected alternative. Residential air-conditioning manufacturing Technical assistance activities ongoing for the participating companies
UNIDO | Tunisia | National ODS phase-out plan | 2012-12-01 | 2014-03-01 |  | 705518 | 705518 | 76137.6 | 172.45 | N/A | not yet available |  |  |  | The project was successfully completed.
UNIDO | Turkey | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2017-12-01 | 14120090 | 8521240 | 7307767.34 | 504.5 | 360.8 | not yet available |  |  |  | HPMP approved at the 68th Meeting in 2012 with a tranche in the REF servicing and one for technical assistance for small and medium enterprises in the foam sector. Furthermore, an earlier approved investment project, Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production, also got included in the HPMP. REF servicing Milestones achieved: Milestone 1: Workshops on alternatives for RAC in refrigeration sector - Yes Milestone 2: Contracting consultancy for elaboration of verification report - Yes Milestone 3: Submission of tranche II request for ExCom approval - No TAS Milestones achieved: Milestone 1: Bidding for equipment purchase initiated - Yes Milestone 2: Suppliers selection - No Milestone 3: Equipment delivery - No Milestone 4: Conversion of SH to methyl formate and hydrocarbons achieved with private investment component - Yes Milestone 5: Safety measures for manufacturing of flammable alternatives achieved at all manufacturing sites - No Umbrella project Milestones achieved: Milestone 1: IOC calculation completed - Yes Milestone 2: IOC disbursement completed - No | REF servicing - Follow-up on the approval of the new legislation for the certification scheme. - Continuing awareness component on recovery/recycling scheme. - Initiation of inventory on recovered/recycled quantities. - Elaboration of Progress Report and Consumption Verification Report in view of tranche 2 submission to the 75th Meeting of the ExCom. TAS Actions towards next goals: Follow-up the bidding process for suppliers selection and completion of equipment delivery process expected during the second half of 2015. Umbrella project - Technical specification development for contract amendment for Aluform conversion has been agreed with factory management and the equipment supplier. - Project to be completed by the end of 2015.
UNIDO | Turkey | Phase out of methyl bromide in protected tomato, cucumber and carnation crops | 2001-12-01 | 2009-11-01 |  | 3408844 | 3408844 | 3329511.23 | 292.2 | 0 | 0
UNIDO | Turkmenistan | HCFC phase-out management plan (phase I) | 2010-12-01 |  | 2020-12-01 | 652050 | 403550 | 264285.02 | 2.35 | 6.8 | 2.7 |  |  |  | - Ongoing HPMP since 2010. First and second tranches are under implementation. Milestones achieved: Milestone: Terms of reference (for equipment) completed - Yes Milestone: Bidding completed, supplier selected - Yes Milestone: Equipment delivered - No Milestone: Training conducted - No Milestone: Tranche request prepared - Yes The work plan must be revised due to reduction of the HPMP funding. The main change is the elimination of investment activities from the HPMP. No additional R+R equipment can be provided due to the funds reduction. | Activities planned but not implemented, reasons and strategy: The equipment will arrive September. Training will be organized after the summer season.
UNIDO | Uganda | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2020-12-01 | 80000 | 40000 | 38113.9 | 0.034043 | 0.2 | not yet available |  |  |  | - HPMP ongoing since 2012. Currently there is one tranche under implementation. Milestones achieved: Milestone 1: Mission to define the project implementation. Yes Milestone 2: TOR prepare and review, equipment bidding, purchase. Yes Milestone 3: Equipment delivery and distributed. Yes | - Equipment was purchased in autumn 2014 and due to some delays and problems with the transport, the equipment only reached Uganda in April 2015. - The distribution of the tools is being done locally. - Project activities are completed. Milestones achieved: Milestone 1: Mission to define the project implementation. Yes Milestone 2: TOR prepare and review, equipment bidding, purchase. Yes Milestone 3: Equipment delivery and distributed. Yes Was there any delay during the reporting year?: No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
UNIDO | Venezuela | HCFC phase-out management plan (phase I) | 2011-04-01 |  | 2015-12-01 | 1758500 | 1583068 | 1149059.08 | 21.5 | 207 | not yet available |  |  |  | - HPMP approved in 2011. Currently it is under implementation with three tranches. Milestones achieved: Milestone 1: Missions for project implementation. Yes Milestone 2: Purchase and delivery of tools for training centres and certified technicians. Yes Milestone 3: Training of trainers and workshops for technicians and training program for technicians, continuation with certification program. Yes Milestone 4: Study tour for local experts to Mexico. Yes Milestone 5: New manuals for good refrigeration practices and custom officers. Yes | First tranche - Few additional activities were carried out in this project since little funds are available. Second and third tranches - Special public awareness and project activities to reduce refrigerant leaks was launched. Public awareness programs are continuous and very effective in the country. - The program for training of technicians with the national vocational institution (INCES) is delayed due to different circumstances, alternatives have been found and the program is expected to start during the third quarter of 2015. - Tools for certified technicians are planned to be purchased in the second semester 2015.
UNIDO | Venezuela | National CFC phase-out plan | 2004-04-01 | 2012-12-01 |  | 6240555 | 6112189 | 6111441.69 | 1035 | 0 | 0
UNIDO | Yemen | HCFC phase-out management plan (stage I) | 2012-12-01 |  | 2015-12-01 | 410000 | 410000 | 154373.86 | 32.8415 | 158.2 | not yet available |  |  |  | - The HPMP got approved at the 68th Meeting in 2012. - Delay caused by the inability to arrange consultation meeting with the NOU, which took place only in November 2013. - After the scope of the procurement was agreed with the NOU, the request for quotations for equipment to the refrigeration service sector (refrigerant identifiers, vacuum pumps, recycling filter kits, upgrade kits, flushing units, acid test kits) published in December 2013. - The suppliers were selected in February 2014 and Purchase Orders issued in March 2014. - The delivery completed in September 2014. | - No NOU in charge.
UNIDO | Yemen | National ODS phase-out plan | 2008-07-01 |  | 2016-12-01 | 1370500 | 1370500 | 1226681.76 | 269.1 | 0 | 0 |  |  |  | - The National ODS phase-out plan is ongoing since 2008 with two ongoing tranches at the moment. Milestones achieved: Milestone 1: Commissioning of equipment - No Milestone 2: Training of national personnel at the supplier's facility for commissioning - The remaining balances will be used for the outstanding payments for the equipment already delivered by OMS, Italy. The OMS currently unable to conduct commissioning and start up because of the security situation in the country. - It was agreed with the supplier that instead technicians from the beneficiary companies will receive training at the suppliers facilities in order to complete the commissioning. | - As per Dec 74/2, project completion date extended until June 2016. - Uncertain political situation in the country. - No NOU in charge.
UNIDO | Zambia | HCFC phase-out management plan (stage I) | 2011-07-01 |  | 2020-12-01 | 140000 | 70000 | 67827.55 | 0.75556 | 5 | 4.4 |  |  |  | - HPMP approved at the 64th Meeting in 2011. Currently the first tranche is under implementation. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2: Terms of reference (for equipment and/or services) completed - Yes Milestone 3: First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes Milestone 5: Equipment shipped/delivered/installed at site - Yes Milestone 6: Commissioning and trial runs completed - Yes | - Final ceremony took place in April 2015. - Tranche is closed.
UNIDO | Zimbabwe | Total phase-out of methyl bromide used in tobacco seedlings | 2005-11-01 | 2008-12-01 |  | 3724972 | 3724972 | 3724970 | 170 | 0 | 0
USA | China | CFCs/CTC/Halon Accelerated Phase-Out Plan | 2004-12-01 | 2009-01-01 |  | 10000000 | 10000000 | 10000000 | NA | 1000 | 1000 | NA | 1550 | 1537 | CFC production stopped by June 30, 2007 as per agreement. Five CFC plants have been closed and dismantled. 1 CFC plant, Juhua, remains open for production of CFCs for MDIs (with 550 MT allocated for 2009 and 547 MT produced). Verification report indicates that CFC and halon production were within the agreed limits for 2008; data for 2009 shows that compliance with production phase-out target continues.